## 220KV TL(Fdn)
220KV Transmission Line_Mandvi Project (7.03 KM)
Sr.No. | Loc.No. | Deviation angle | Type of Tower | Span | Elevation (MSL) | Village | ROW | Classification | Check Survey |  | ROW clearance |  | Soil testing Status |  | Excavation |  |  |  | PCC |  |  |  | Stub Setting |  |  |  | Steel Binding |  |  |  | Raft Casting |  |  |  | Chimney Casting |  |  |  | Backfilling Completion date
[5 empty] | Z |  |  |  | Status | Completion date | Approach Road | Tower Location | Start Date | Finish Date | Plan Start Date | Plan Finish date | Actual Start Date | Actual Finish Date | Plan Start Date | Plan Finsih date | Actual Start Date | Actual Finish Date | Plan Start Date | Plan Finsih date | Actual Start Date | Actual Finish Date | Plan Start Date | Plan Finsih date | Actual Start Date | Actual Finish Date | Plan Start Date | Plan Finsih date | Actual Start Date | Actual Finish Date | Plan Start Date | Plan Finsih date | Actual Start Date | Actual Finish Date | Plan Start Date | Plan Finsih date | Actual Start Date | Actual Finish Date
| 28 | [5 empty] | 13 | 6 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 |  | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | GANTRY | 59°13'35"RT | YTD+0 |  | 62.217 | Ramaniya
2 | 1/0 |  | YTD+0 |  | 56.759 | Ramaniya | Clear | NDS | Clear | 2026-08-20 | [6 empty] | 2026-08-20 | 2026-08-21
3 | 2/0 | 8°15'43"LT | YTD+0 |  | 60.767 | Ramaniya
4 | 2/1 |  | SYTA+0 |  | 56.575 | Ramaniya
5 | 2/2 | 24°42'52"LT | SYTA+3 |  | 58.836 | Ramaniya
6 | 3/0 | 28°18'39"LT | YTD+0 |  | 68.775 | Ramaniya
7 | 3/1 | 2°15'10"RT | SYTA+0 |  | 70.775 | Beraja
8 | 4/0 | 17°20'36"LT | YTD+0 |  | 65.946 | Ramaniya
9 | 4/1 | 47°36'07"RT | SYTA+0 |  | 65.223 | Ramaniya
10 | 4/2 | 35°38'47"RT | SYTA+6 |  | 58.531 | Ramaniya | Clear | NDS | Clear | 2026-08-26 | [6 empty] | 2026-08-28 | 2026-08-29 | [6 empty] | 2026-09-19 | 2026-09-20
11 | 5/0 |  | YTD+3 |  |  |  | Clear | NDS | Clear | 2026-08-26 | [6 empty] | 2026-08-29 | 2026-08-30 | [6 empty] | 2026-09-20 | 2026-09-20
12 | 5/1 |  | SYTA+3 |  | 53.354 | Depa |  |  | Clear | 2026-08-26
13 | 6/0 |  | YTD+0 |  | 59.045 | Depa | Clear | NDS | Clear | 2026-08-26 | [6 empty] | 2026-08-31 | 2026-09-02
14 | 7/0 | 23°09'13"LT | YTD+0 |  | 58.537 | Depa | Clear | NDS | Clear | 2026-08-26 | [6 empty] | 2026-09-04 | 2026-09-05
15 | 8/0 |  | YTD+0 |  | 57.831 | Depa |  |  | Clear | 2026-08-26
16 | 9/0 | 36°27'07"RT | YTD+6 |  | 58.004 | Depa | Clear | NDS | Clear | 2026-08-26 | [6 empty] | 2026-09-06 | 2026-09-08
17 | 10/0 | 24°04'26"RT | YTD+6 |  | 56.368 | Depa | Clear |  | Clear | 2026-08-26
18 | 10/1 |  | SYTA+6 |  | 55.706 | Depa | Clear |  | Clear | 2026-08-26 | [6 empty] | 2026-09-12 | 2026-09-13
19 | 11/0 | 41°37'03"LT | YTD+3 |  | 51.476 | Depa | Clear |  | Clear | 2026-08-26 | [6 empty] | 2026-09-10 | 2026-09-12
20 | 12/0 | 27°38'14"LT | YTD+0 |  | 51.158 | Depa |  |  | Clear | 2026-08-26
21 | 13/0 |  | YTD+0 |  | 60.432 | Ramaniya |  |  | Clear | 2026-08-26
22 | 14/0 |  | YTD+0 |  | 62.81 | Ramaniya | Clear |  | Clear | 2026-08-26 | [6 empty] | 2026-09-13 | 2026-09-14
23 | 14/1 |  | SYTA+0 |  |  |  | Clear |  | Clear | 2026-08-26
24 | 15/0 |  | YTD+3 |  |  |  | Clear |  | Clear | 2026-08-26
25 | 16/0 |  | YTD+0 |  |  |  | Clear |  | Clear | 2026-08-26 | [6 empty] | 2026-09-18 | 2026-09-20
26 | 17/0 |  | YTD+0 | [5 empty] | Clear | 2026-08-26
27 | 18/0 |  | YTD+0
28 | EXI.LOC.TAP POINT |  | YTD+0
Note on V15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: De-Watering WIP