## SPV wise Summary (hidden)
ADANI GREEN ENERGY KHAVADA PH-II 200WTGs (1040 MWac)
S.No | Description | PSS Number | Total Scope | Achieved | Balance | PSS Number | SPV Name | Total Scope | Achieved | Balance | PSS Number | SPV Name | Total Scope | Achieved | Balance | PSS Number | SPV Name | Total Scope | Achieved | Balance | PSS Number | SPV Name | Total Scope | Achieved | Balance | PSS Number | SPV Name | Total Scope | Achieved | Balance
I | WTG CIVIL & MECH
1 | Soil Test |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
2 | Stone Column Drawing's Status |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
3 | Stone Column |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
4 | Plateload test |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
5 | Excavation |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
6 | PCC |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
7 | Anchor Cage & Assembly |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
8 | Steel Binding works |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
9 | Raft Casting |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
10 | Backfilling |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
11 | Grouting |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
12 | USS & Transformer Foundation |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
13 | WTG Connecting Road |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
14 | Crane Pad |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
15 | WTG Erection |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
16 | MCC |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
17 | Pre-Comm |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
18 | WTG Commissioining |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
II | WTG ELECTRICAL (USS, Trafo & 33kV)
1 | USS Erection & Readiness | PSS-4 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
2 | USS Testing | PSS-4 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
I | WTG CIVIL & MECH
23 | Soil Test | PSS-8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0
24 | Stone Column Drawing's Status | PSS-8 | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [14 empty] | 0
25 | Stone Column | PSS-8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0
26 | Plateload test | PSS-8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0
27 | Excavation | PSS-8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0
28 | PCC | PSS-8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0
29 | Anchor Cage & Assembly | PSS-8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0
30 | Steel Binding works | PSS-8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0
31 | Raft Casting | PSS-8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0
32 | Backfilling | PSS-8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0
33 | Grouting | PSS-8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0
34 | USS & Transformer Foundation | PSS-8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0
35 | WTG Connecting Road | PSS-8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0
36 | Crane Pad | PSS-8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0
37 | WTG Erection | PSS-8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0
38 | MCC | PSS-8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0
39 | Pre-Comm | PSS-8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0
40 | WTG Commissioining | PSS-8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0
II | WTG ELECTRICAL (USS, Trafo & 33kV)
1 | USS Erection & Readiness | PSS-8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0
2 | USS Testing | PSS-8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0
I | WTG CIVIL & MECH
42 | Soil Test | PSS-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0
43 | Stone Column Drawing's Status | PSS-10 | 0 |  |  |  |  | 0
44 | Stone Column | PSS-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0
45 | Plateload test | PSS-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0
49 | Excavation | PSS-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0
50 | PCC | PSS-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0
51 | Anchor Cage & Assembly | PSS-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0
52 | Steel Binding works | PSS-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0
53 | Raft Casting | PSS-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0
54 | Backfilling | PSS-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0
55 | Grouting | PSS-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0
56 | USS & Transformer Foundation | PSS-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0
57 | WTG Connecting Road | PSS-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0
58 | Crane Pad | PSS-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0
59 | WTG Erection | PSS-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0
60 | MCC | PSS-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0
61 | Pre-Comm | PSS-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0
62 | WTG Commissioining | PSS-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0
II | WTG ELECTRICAL (USS, Trafo & 33kV) | PSS-10
1 | USS Erection & Readiness | PSS-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0
2 | USS Testing | PSS-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0
1080
1260
1950
1320
4880
10490
1180
2770

## Sheet2 (hidden)
WTG 243 | WTG 230
WTG 133 | WTG 208
WTG 405 | WTG 186
WTG 244 | WTG 164
WTG 327 | WTG 141
WTG 329 | WTG 121
WTG 233A | WTG 123
WTG 353 | WTG 143
WTG 354 | WTG 144
WTG 373 | WTG 145
WTG 377 | WTG 400
WTG 378 | WTG 376
WTG 379 | WTG 351
WTG 328 | WTG 326
WTG 380 | WTG 302
WTG 381 | WTG 327
WTG 382 | WTG 352
WTG 399 | WTG 002
WTG 401 | WTG 551
WTG 403 | WTG 552
WTG 404 | WTG 132
WTG 406 | WTG 553
WTG 407 | WTG 152
WTG 424 | WTG 153
WTG 425 | WTG 133
WTG 426 | WTG 154
WTG 429 | WTG 131
WTG 430 | WTG 175
WTG 431 | WTG 176
WTG 432 | WTG 197
WTG 433 | WTG 198
WTG 448 | WTG 178
WTG 449 | WTG 177
WTG 454 | WTG 199
WTG 455 | WTG 221
WTG 456 | WTG 200
WTG 473 | WTG 155
WTG 474 | WTG 554
WTG 480 | WTG 555
WTG 481 | WTG 156
WTG 482 | WTG 179
WTG 503 | WTG 243
WTG 504 | WTG 222
WTG 505 | WTG 244
WTG 520 | WTG 266
WTG 524 | WTG 267
WTG 457 | WTG 314
WTG 423 | WTG 290
WTG 398 | WTG 315
KH 53 | WTG 291
KH 54 | WTG 316
KH 55 | WTG 201
KH 56 | WTG 223
KH 57 | WTG 245
KH 58 | WTG 268
KH 59 | WTG 292
KH 60 | WTG 328
KH 61 | WTG 353
KH 556 | WTG 354
KH 523 | WTG 378
KH 522 | WTG 379
KH 521 | WTG 380
KH 508 | WTG 381
KH 555 | WTG 382
KH 557 | WTG 403
KH 581 | WTG 404
KH 582 | WTG 405
KH 583 | WTG 406
KH 52 | WTG 407
KH 51 | WTG 429
KH 552 | WTG 430
KH 588 | WTG 431
KH 589 | WTG 432
KH 590 | WTG 433
KH 591 | WTG 454
KH 592 | WTG 455
KH 550 | WTG 456
KH 551 | WTG 480
KH 579 | WTG 481
KH 596 | WTG 482
KH 597 | WTG 503
KH 598 | WTG 504
KH 599 | WTG 505
KH 600 | WTG 524
KH 553 | WTG 457
KH 580 | WTG 233A
KH 478 | WTG 329
KH 604 | WTG 377
KH 605 | WTG 520
KH 606 | KH 47
KH 607 | KH 51
KH 608 | KH 52
KH 509 | KH 53
KH 554 | KH 54
KH 611 | KH 55
KH 612 | KH 56
KH 613 | KH 57
KH 614 | KH 58
KH 615 | KH 59
KH 47 | KH 60
KH 617 | KH 61
KH 618 | KH 478
KH 619 | KH 508
KH 620 | KH 509
KH 621 | KH 521
KH 622 | KH 522
KH 34 | KH 523
KH 35 | KH 550
KH 68 | KH 551
WTG 177 | KH 552
WTG 199 | KH 553
WTG 154 | KH 554
WTG 002 | KH 555
WTG 290 | KH 556
WTG 315 | KH 557
WTG 266 | KH 579
WTG 221 | KH 580
WTG 131 | KH 581
WTG 132 | KH 582
WTG 152 | KH 583
WTG 153 | KH 588
WTG 155 | KH 589
WTG 156 | KH 590
WTG 175 | KH 591
WTG 176 | KH 592
WTG 178 | KH 596
WTG 179 | KH 597
WTG 197 | KH 598
WTG 198 | KH 599
WTG 200 | KH 600
WTG 201 | KH 604
WTG 222 | KH 605
WTG 223 | KH 606
WTG 245 | KH 607
WTG 267 | KH 608
WTG 268 | KH 611
WTG 291 | KH 612
WTG 292 | KH 613
WTG 314 | KH 614
WTG 316 | KH 615
WTG 555 | KH 617
WTG 554 | KH 618
WTG 552 | KH 619
WTG 551 | KH 620
WTG 553 | KH 621
WTG 121 | KH 622
WTG 123 | KH 34
WTG 143 | KH 35
WTG 144 | KH 68
WTG 145 | WTG 373
WTG 230 | WTG 399
WTG 302 | WTG 424
WTG 326 | WTG 425
WTG 351 | WTG 448
WTG 376 | WTG 449
WTG 400 | WTG 473
WTG 208 | WTG 474
WTG 141 | WTG 398
WTG 164
WTG 352
WTG 186

## SUMMARY
ADANI GREEN ENERGY KHAVDA PH-III 194 WTGs (1008.8 MWac) | [10 empty] | Reporting Date |  | 2026-02-28 |  | 2026-02-23 | 2026-03-01
[11 empty] | Progress Date |  | 2026-02-27
S.No | Description | Total Scope | Achieved | Balance | Weekly Plan (23-Feb'26 -01 -Mar'26) |  |  | Monthly Plan |  |  | Cumulative |  |  | SPV
[5 empty] | Plan | Achieved | Balance | Plan | Achieved | Balance | Plan | Achieved | Balance | ARE3L | ASEJ6PL | AHEJ5L | AGE25BL | AGE25CL | AGE26AL | AGE25CL | AGE26AL
I | WTG CIVIL & MECH | [12 empty] | PSS-08 | PSS-08 | PSS-05 | PSS-09 | PSS-11 | PSS-12 | PSS-14 | PSS-14
1 | Soil Test | 194 | 194 | 0 | 0 | 0 | 0 |  |  |  | 194 | 194 | 0 | 5 | 12 | 39 | 2 | 36 | 27 | 13 | 60 | 194 | TRUE
2 | Stone Column Drawing's Status | 194 | 194 | 0 | 0 | 0 | 0 |  |  |  | 194 | 194 | 0 | 5 | 12 | 39 | 2 | 36 | 27 | 13 | 60
3 | Stone Column | 194 | 192 | 2 | 0 | 0 | 0 | 5 | 2 | 3 | 194 | 192 | 2 | 5 | 12 | 39 | 2 | 36 | 27 | 13 | 58 | 192 | TRUE
4 | Plateload test | 63 | 61 | 2 | 0 | 1 | -1 | 7 |  | 7 | 63 | 57 | 6 | 1 | 5 | 10 | 0 | 12 | 10 | 5 | 17 | 60 | FALSE
5 | Excavation | 194 | 187 | 7 | 0 | 2 | -2 | 0 |  | 0 | 194 | 187 | 7 | 5 | 11 | 39 | 2 | 36 | 27 | 12 | 55 | 187 | TRUE
6 | PCC | 194 | 180 | 14 | 0 | 2 | -2 | 0 |  | 0 | 194 | 180 | 14 | 5 | 11 | 39 | 2 | 36 | 27 | 12 | 48 | 180 | TRUE
7 | Anchor Cage & Assembly | 194 | 177 | 17 | 0 | 3 | -3 | 0 |  | 0 | 194 | 177 | 17 | 5 | 11 | 39 | 2 | 36 | 27 | 12 | 45 | 177 | TRUE
8 | Steel Binding works | 194 | 173 | 21 | 0 | 3 | -3 | 0 |  | 0 | 194 | 173 | 21 | 5 | 10 | 39 | 2 | 36 | 27 | 12 | 42 | 173 | TRUE
9 | Raft Casting | 194 | 172 | 22 | 0 | 6 | -6 | 0 |  | 0 | 194 | 172 | 22 | 5 | 10 | 39 | 2 | 36 | 27 | 12 | 41 | 172 | TRUE
10 | Backfilling | 194 | 76 | 118 | 0 | 1 | -1 | 0 |  | 0 | 194 | 76 | 118 | 5 | 6 | 26 | 0 | 29 | 8 | 2 | 0 | #VALUE! | #VALUE!
11 | Grouting | 194 | 163 | 31 | 0 | 7 | -7 | 0 |  | 0 | 194 | 163 | 31 | 5 | 10 | 39 | 2 | 36 | 27 | 11 | 33 | 163 | TRUE
12 | USS & Transformer Foundation | 194 | 148 | 46 | 0 | 7 | -7 | 0 |  | 0 | 194 | 148 | 46 | 5 | 10 | 39 | 2 | 36 | 27 | 12 | 17 | 148 | TRUE
13 | WTG Connecting Road | 194 | 193 | 1 | 0 | 0 | 0 |  |  |  | 194 | 193 | 1 | 5 | 10 | 39 | 1 | 32 | 17 | 5 | 20 | 129 | FALSE
14 | Crane Pad | 194 | 153 | 41 | 0 | 8 | -8 |  |  |  | 194 | 153 | 41 | 5 | 11 | 39 | 2 | 36 | 27 | 11 | 22 | 153 | TRUE
15 | WTG Erection | 194 | 119 | 75 | 10 | 4 | 6 |  |  | 0 | 194 | 119 | 75 | 5 | 9 | 39 | 2 | 36 | 23 | 5 | 0 | 119 | TRUE
16 | MCC | 194 | 113 | 81 | 9 | 7 | 2 |  |  | 0 | 184 | 113 | 71 | 5 | 8 | 39 | 2 | 36 | 20 | 3 | 0 | 113 | TRUE
17 | Pre-Comm | 194 | 108 | 86 | 7 | 5 | 2 |  |  | 0 | 181 | 108 | 73 | 5 | 7 | 39 | 2 | 36 | 17 | 2 | 0 | 108 | TRUE
18 | WTG Commissioining | 194 | 82 | 112 | 1 | 4 | -3 |  |  |  | 172 | 82 | 90 | 5 | 0 | 39 | 2 | 36 | 0 | 0 | 0 | 82 | TRUE
II | WTG ELECTRICAL (USS, Trafo & 33kV)
1 | USS Erection | 194 | 117 | 77 | 0 | 2 | -2 |  |  | 0 | 194 | 117 | 77 | 5 | 7 | 39 | 2 | 36 | 25 | 3 | 0 | 117 | TRUE
2 | USS Testing | 194 | 114 | 80 | 13 | 0 | 13 |  |  |  | 192 | 114 | 78 | 5 | 6 | 39 | 2 | 36 | 26 | 0 | 0 | 114 | TRUE
2 | 33kV Cable Laying
2.01 | PSS-05
2.01.01 | HT Cable Laying | 103107 | 103107 | 0 | [6 empty] | 103107 | 103107 | 0
2.01.02 | FO Cable Laying | 74955 | 74955 | 0 | [6 empty] | 74955 | 74955 | 0
2.01.03 | Cable Joint | 122 | 122 | 0 | [6 empty] | 122 | 122 | 0
2.01.04 | Termination | 78 | 78 | 0 | 1 | 1 | 0 |  |  |  | 78 | 78 | 0
2.02 | PSS-08
2.02.01 | HT Cable Laying | 61930 | 54730 | 7200 | 5000 | 3100 | 1900 |  |  |  | 61475 | 54730 | 6745
2.02.02 | FO Cable Laying | 42395 | 31795 | 10600 | 1000 | [5 empty] | 42020 | 31795 | 10225
2.02.03 | Cable Joint | 74 | 54 | 20 | [6 empty] | 73 | 54 | 19
2.02.04 | Termination | 34 | 26 | 8 | [6 empty] | 34 | 26 | 8
2.03 | PSS-11
2.03.01 | HT Cable Laying | 110000 | 110000 | 0 | [6 empty] | 110000 | 110000 | 0
2.03.02 | FO Cable Laying | 71895 | 71895 | 0 | [6 empty] | 71895 | 71895 | 0
2.03.03 | Cable Joint | 138 | 138 | 0 | [6 empty] | 138 | 138 | 0
2.03.04 | Termination | 72 | 72 | 0 | [6 empty] | 72 | 72 | 0
2.04 | PSS-12
2.04.01 | HT Cable Laying | 77487 | 77487 | 0 | [6 empty] | 77487 | 77487 | 0
2.04.02 | FO Cable Laying | 49200 | 49200 | 0 | [6 empty] | 49200 | 49200 | 0
2.04.03 | Cable Joint | 88 | 88 | 0 | [6 empty] | 88 | 88 | 0
2.04.04 | Termination | 54 | 54 | 0 | [6 empty] | 54 | 54 | 0
2.05 | PSS-14
2.05.01 | HT Cable Laying | 200810 | 76977 | 123833 | 10000 | 8850 | 1150 |  |  |  | 200810 | 76977 | 123833
2.05.02 | FO Cable Laying | 142770 | 0 | 142770 | 3000 |  | 3000 |  |  |  | 142770 | 0 | 142770
2.05.03 | Cable Joint | 230 | 0 | 230 | 10 |  | 10 |  |  |  | 230 | 0 | 230
2.05.04 | Termination | 146 | 0 | 146 | 5 |  | 5 |  |  |  | 146 | 0 | 146
2.06 | PSS-09
2.06.01 | HT Cable Laying | 4350 | 4350 | 0 | [6 empty] | 4350 | 4350 | 0
2.06.02 | FO Cable Laying | 2225 | 2225 | 0 | [6 empty] | 2225 | 2225 | 0
2.06.03 | Cable Joint | 5 | 5 | 0 | [6 empty] | 5 | 5 | 0
2.06.04 | Termination | 4 | 4 | 0 | [6 empty] | 4 | 4 | 0

## WTG PH-III
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184
Sr. No. | SUB Station | SPV | 1: Locations; 2: Feeder; 3: WTG FDN VENDOR; 4: FDN Allotment Date; 5: Stone Column Contractor; 6: Soil Test Status; 7: WTG Coordinates; 9: Soil Test; 15: Stone Column; 24: Plate Load Test; 32: Excavation; 39: Gravel Bed (Stone Blanket); 46: PCC; 53: Anchor Cage Assembly; 60: Steel Binding; 67: Raft Casting; 75: Backfilling & Compaction; 82: Grouting; 91: USS Precast Installation; 98: Road Construction (For WTG Erection); 105: TURNING Development; 113: Crane Pad Construction; 120: WTG Erection; 127: USS Erection; 134: MCC; 141: Pre-commissioning; 148: USS Testing; 155: HT Cable Laying & Termination; 162: CEA Approval; 169: USS CFT; 176: WTG Commissioining; 183: Trial Run; 184: Remarks
[9 empty] | E | N | Soil Test Plan Start Date | Soil Test Plan Finish Date | Fore Cast Finish Date | Soil Test Actual Start Date | Soil Test Actual FInish Date | Impact days due to hindrance | Stone Column Scope (Nos) | Stone Column Completed (Nos) | Stone Column Plan Start Date | Stone Column Plan Finish Date | Stone Column Forecast Completion | Stone Column Actual Start Date | Stone Column Actual Finish Date | No of Days | Impact days due to hindrance | Scope | Vendor | PLT Plan Start Date | PLT Plan Finish Date | PLT Forecast Completion Date | PLT Actual Start Date | PLT Actual Finish Date | Impact days due to hindrance | Excavation Plan Start Date | Excavation Plan Finish Date | Excavation Forecast Completion | Excavation Actual Start Date | Excavation Actual FInish Date | No of Days | Impact days due to hindrance | Gravel Bed Plan Start Date | Gravel Bed Plan Finish Date | Gravel Bed Forecast Completion | Gravel Bed Actual Start Date | Gravel Bed Actual Finish Date | No of Days | Impact days due to hindrance | PCC Plan Start Date | PCC Plan Finish Date | Forecast Completion | PCC Actual Start Date | PCC Actual Finish Date | No of Days | Impact days due to hindrance | Anchor Cage Plan Start Date | Anchor Cage Plan Finish Date | Forecast Completion | Anchor Cage Actual Start Date | Anchor Cage Actual Finish Date | No of Days | Impact day due to hindrance | Steel Binding Plan Start Date | Steel Binding Plan Finish Date | Forecast Completion | Steel Binding Actual Start Date | Steel Binding Actual FInish Date | No of Days | Impact day due to hindrance | Raft Casting Plan Start Date | Raft Casting Plan Finish Date | Forecast Completion | Raft Casting Actual Start Date | Raft Casting Actual Finish Date | No of Days | No of Days Excavation & Raft Casting | Impact day due to hindrance | Backfilling Plan Start Date | Backfilling Plan Finish Date | Forecast Completion | Backfilling Actual Start Date | Backfilling Actual Finish Date | No of Days | Impact day due to hindrance | Grouting Plan Start Date | Grouting Plan Finish Date | Forecast Completion | Grouting Actual Start Date | Grouting Actual Finish Date | No of Days |  | Excavation to Casting (excl. curing) | Impact day due to hindrance | USS Civil Plan Start Date | USS Civil Plan Finish Date | Forecast Completion | USS Civil Actual Start Date | USS Civil Actual Finish Date | No of Days | Impact day due to hindrance | Road Plan Start Date | Road Plan Finish Date | Forecast Completion | Road Actual Start Date | Road Actual Finish Date | No of Days | Impact day due to hindrance | Turning Devlopment Plan Start Date | Turning Devlopment Finish Start Date | Forecast Completion | Turning Devlopment Actual Start Date | Turning Devlopment Actual Finish Date | No of Days | Impact day due to hindrance | Vendor | Crane Pad Plan Start Date | Crane Pad Plan Finish Date | Forecast Completion | Crane Pad Actual Start Date | Crane Pad Actual Finish Date | No of Days | Impact day due to hindrance | WTG Ere Plan Start Date | WTG Ere Plan Finish Date | Forecast Completion | WTG Ere Actual Start Date | WTG Ere Actual End Date | No of Days | Impact day due to hindrance | USS Ere Plan Start Date | USS Ere Plan Finish Date | Forecast Completion | USS Ere Actual Start Date | USS Ere Actual Finish Date | No of Days | Impact day due to hindrance | MCC Plan Start Date | MCC Plan Finish Date | Forecast Completion | MCC Actual Start Date | MCC Actual Finish Date | No of Days | Impact day due to hindrance | Pre-Comm Plan Start Date | Pre-Comm Plan Finish Date | Forecast Completion | Pre-Comm Actual Start Date | Pre-Comm Actual Finish Date | No of Days | Impact day due to hindrance | USS Testing Plan Start Date | USS Testing Plan Finish Date | Forecast Completion | USS Testing Actual Start Date | USS Testing Actual Finish Date | No of Days | Impact day due to hindrance | HT Cable Plan Start Date | HT Cable Plan Finish Date | Forecast Completion | HT Cable Actual Start Date | HT Cable Actual Finish Date | No of Days | Impact day due to hindrance | CEA Approval Plan Start Date | CEA Approval Plan Finish Date | Forecast Completion | CEA Approval Actual Start Date | CEA Approval Actual Finish Date | No of Days | Impact day due to hindrance | Grid-Conne Plan Start Date | Grid-Conne Plan Finish Date | Forecast Completion | Grid-Conne Actual Start Date | Grid-Conne Actual Finish Date | No of Days | Impact day due to hindrance | WTG Comm Plan Start Date | WTG Comm Plan Finish Date | Forecast Completion | WTG Comm Actual Start Date | WTG Comm Actual Finish Date | No of Days | Impact day due to hindrance | Trial Run Date
|  |  | 194 | 194 | 191 | 191 | 193 | 194 | 194 | 194 | 0 | 0 | 0 | 194 | 194 | 0 | 49577 | 49190 | 194 | 194 |  | 192 | 192 |  | 18 | 63 | 61 | 20 | 20 | 0 | 61 | 61 | 1 | 194 | 194 | 0 | 189 | 187 |  |  | 194 | 194 | 0 | 185 | 182 |  | 6 | 194 | 194 | 0 | 180 | 180 |  | 3 | 194 | 194 | 0 | 178 | 177 |  | 1 | 194 | 194 | 0 | 177 | 173 |  | 4 | 194 | 194 | 0 | 172 | 172 |  |  | 5 | 194 | 194 | 0 | 161 | 76 |  | 0 | 194 | 194 | 0 | 163 | 163 |  |  |  | 0 | 194 | 194 | 0 | 177 | 148 |  | 0 | 194 | 194 | 0 | 193 | 193 |  | 0 | 194 | 194 | 0 | 148 | 140 |  | 0 | 194 | 194 | 194 | 0 | 163 | 153 |  | 0 | 194 | 194 | 0 | 131 | 119 |  | 0 | 194 | 194 | 0 | 135 | 117 |  | 0 | 194 | 194 | 0 | 118 | 113 |  | 1 | 194 | 194 | 0 | 111 | 108 |  | 2 | 194 | 194 | 0 | 114 | 114 |  | 0 | 194 | 194 | 0 | 162 | 127 |  | 0 | 194 | 194 |  | 154 | 154 |  |  | 194 | 194 | 0 | 111 | 96 |  | 0 | 194 | 194 | 0 | 87 | 82 |  | 0 | 1
1 | PSS-08 | ASEJ6PL | 1: WTG 121; 2: F11; 3: BIPL; 4: 24-Aug-25; 5: Saritha; 6: Yes; 7: 533604; 8: 2674223; 12: Done; 13: Done; 15: 199; 16: 199; 17: 2025-02-08; 18: 2025-02-18; 20: 2025-01-15; 21: 2025-01-25; 24: YES; 25: Keller; 29: 2025-05-26; 30: 2025-06-26; 32: 2025-02-20; 33: 2025-02-21; 35: 2025-08-17; 36: 2025-08-21; 39: 2025-02-22; 40: 2025-02-22; 42: 2025-08-25; 43: 2025-08-25; 46: 2025-02-23; 47: 2025-02-24; 49: 2025-08-28; 50: 2025-08-28; 53: 2025-02-25; 54: 2025-02-26; 56: 2025-08-29; 57: 2025-08-30; 60: 2025-02-27; 61: 2025-03-09; 63: 2025-09-04; 64: 2026-01-18; 66: Delay dur to Water logging; 67: 2025-03-10; 68: 2025-03-11; 70: 2026-01-18; 71: 2026-01-21; 75: 2025-03-16; 76: 2025-03-19; 78: 2026-02-01; 82: 2025-03-18; 83: 2025-03-18; 85: 2026-01-27; 86: 2026-01-27; 91: 2025-03-28; 92: 2025-04-07; 94: 2026-01-20; 95: 2026-02-13; 98: 2025-03-13; 99: 2025-03-20; 101: 2025-02-13; 102: 2025-02-21; 105: 2025-03-13; 106: 2025-03-20; 108: 2026-02-02; 109: 2026-02-06; 112: GP Project; 113: 2025-03-22; 114: 2025-03-29; 116: 2025-02-21; 117: 2025-03-08; 120: 2025-05-04; 121: 2025-05-14; 123: 2026-02-05; 124: 2026-02-25; 127: 2025-05-07; 128: 2025-05-15; 130: 2026-02-25; 134: 2025-05-15; 135: 2025-05-22; 137: 2026-02-27; 141: 2025-05-23; 142: 2025-05-25; 148: 2025-05-30; 149: 2025-05-31; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-05-21; 159: 2025-07-10; 162: 2025-04-20; 163: 2025-05-15; 165: 2025-08-31; 166: 2025-09-19; 169: 2025-06-01; 170: 2025-06-04; 176: 2025-06-05; 177: 2025-06-07; 184: HBG- Excavation done loc alloted on30-May-25 / BIPL- Balance Work continue from 24-Aug-25
2 | PSS-08 | ASEJ6PL | 1: WTG 123; 2: F11; 3: MECC; 4: 2025-02-20; 5: Bauer; 6: Yes; 7: 533983; 8: 2672250; 12: Done; 13: Done; 15: 199; 16: 199; 17: 2025-02-08; 18: 2025-02-18; 20: 2025-02-04; 21: 2025-02-13; 32: 2025-02-20; 33: 2025-02-21; 35: 2025-02-25; 36: 2025-02-27; 39: 2025-02-22; 40: 2025-02-22; 42: 2025-02-27; 43: 2025-02-28; 46: 2025-02-23; 47: 2025-02-24; 49: 2025-03-01; 50: 2025-03-01; 53: 2025-02-25; 54: 2025-02-26; 56: 2025-03-02; 57: 2025-03-03; 60: 2025-02-27; 61: 2025-03-09; 63: 2025-03-04; 64: 2025-03-10; 67: 2025-03-10; 68: 2025-03-11; 70: 2025-03-11; 71: 2025-03-12; 75: 2025-03-16; 76: 2025-03-19; 78: 2025-05-10; 79: 2025-06-20; 82: 2025-03-18; 83: 2025-03-18; 85: 2025-03-25; 86: 2025-03-25; 91: 2025-03-28; 92: 2025-04-07; 94: 2025-03-03; 95: 2025-06-15; 98: 2025-03-13; 99: 2025-03-20; 101: 2025-02-10; 102: 2025-02-23; 105: 2025-03-13; 106: 2025-03-20; 108: 2025-12-05; 109: 2025-12-09; 112: GP Project(Reuse); 113: 2025-03-22; 114: 2025-03-29; 116: 2025-03-20; 117: 2025-04-02; 120: 2025-05-10; 121: 2025-05-20; 123: 2025-12-09; 124: 2025-12-29; 127: 2025-04-27; 128: 2025-05-05; 130: 2025-12-01; 131: 2025-12-02; 134: 2025-05-21; 135: 2025-05-28; 137: 2026-01-06; 138: 2026-01-10; 141: 2025-05-29; 142: 2025-05-31; 144: 2026-01-10; 145: 2026-01-14; 148: 2025-05-25; 149: 2025-05-26; 151: 2025-12-15; 152: 2025-12-15; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-05-22; 159: 2025-07-10; 162: 2025-04-20; 163: 2025-05-15; 165: 2025-08-31; 166: 2025-09-19; 169: 2025-05-27; 170: 2025-05-30; 172: 2026-01-03; 173: 2026-01-19; 176: 2025-06-01; 177: 2025-06-03; 179: 2026-02-27
3 | PSS-08 | ASEJ6PL | 1: WTG 143; 2: F11; 3: AB INFRA; 4: 2025-02-22; 5: Saritha; 6: Yes; 7: 534437; 8: 2673958; 12: Done; 13: Done; 15: 199; 16: 199; 17: 2025-02-19; 18: 2025-02-28; 20: 2025-02-10; 21: 2025-02-18; 32: 2025-03-15; 33: 2025-03-16; 35: 2025-02-26; 36: 2025-02-27; 39: 2025-03-17; 40: 2025-03-17; 42: 2025-02-27; 43: 2025-02-28; 46: 2025-03-18; 47: 2025-03-19; 49: 2025-02-28; 50: 2025-02-28; 53: 2025-03-20; 54: 2025-03-21; 56: 2025-03-02; 57: 2025-03-02; 60: 2025-03-22; 61: 2025-04-01; 63: 2025-03-05; 64: 2025-03-23; 67: 2025-04-02; 68: 2025-04-03; 70: 2025-03-27; 71: 2025-03-28; 75: 2025-04-08; 76: 2025-04-11; 78: 2025-04-03; 79: 2025-07-14; 82: 2025-04-10; 83: 2025-04-10; 85: 2025-04-01; 86: 2025-04-01; 91: 2025-04-20; 92: 2025-04-30; 94: 2025-02-28; 95: 2025-09-05; 98: 2025-04-05; 99: 2025-04-12; 101: 2025-05-01; 102: 2025-05-18; 105: 2025-04-05; 106: 2025-04-12; 108: 2025-11-29; 109: 2025-12-02; 112: GP Project; 113: 2025-04-14; 114: 2025-04-21; 116: 2025-05-19; 117: 2025-05-27; 120: 2025-05-15; 121: 2025-05-25; 123: 2025-12-05; 124: 2025-12-18; 127: 2025-05-20; 128: 2025-05-28; 130: 2025-06-19; 131: 2025-12-03; 134: 2025-05-26; 135: 2025-06-02; 137: 2025-12-20; 138: 2025-12-23; 141: 2025-06-03; 142: 2025-06-05; 144: 2025-12-23; 145: 2025-12-25; 148: 2025-06-07; 149: 2025-06-08; 151: 2025-12-19; 152: 2025-12-19; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-05-24; 159: 2025-05-30; 162: 2025-04-20; 163: 2025-05-15; 165: 2025-08-31; 166: 2025-09-19; 169: 2025-06-09; 170: 2025-06-12; 172: 2025-12-20; 173: 2025-12-25; 176: 2025-06-13; 177: 2025-06-15; 179: 2026-01-07; 184: 09-Sep-25 RC 2 Reached at Loc.143, Cabin unloading hold due to water logging & wet soil, Main crane breakdown from 5-Dec-25.AC 7 Reached at loc. 143 date 5-DEC-25
4 | PSS-08 | ASEJ6PL | 1: WTG 144; 2: F11; 3: HBG; 4: 2025-05-24; 5: Bauer; 6: Yes; 7: 534627; 8: 2672972; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-02-19; 18: 2025-02-28; 20: 2025-02-24; 21: 2025-03-01; 24: YES; 25: Keller; 26: 2025-03-05; 27: 2025-03-12; 29: 2025-04-27; 30: 2025-05-22; 32: 2025-03-20; 33: 2025-03-21; 35: 2025-05-27; 36: 2025-05-31; 39: 2025-03-22; 40: 2025-03-22; 42: 2025-06-01; 43: 2025-06-01; 46: 2025-03-23; 47: 2025-03-24; 49: 2025-06-01; 50: 2025-06-01; 53: 2025-03-25; 54: 2025-03-26; 56: 2025-06-02; 57: 2025-06-02; 60: 2025-03-27; 61: 2025-04-06; 63: 2025-06-07; 64: 2025-06-14; 66: Hold due to water logged from 16-Jun-25; 67: 2025-04-07; 68: 2025-04-08; 70: 2025-06-25; 71: 2025-06-25; 75: 2025-04-13; 76: 2025-04-16; 78: 2025-08-13; 82: 2025-04-15; 83: 2025-04-15; 85: 2025-07-25; 86: 2025-07-25; 91: 2025-03-23; 92: 2025-04-02; 94: 2025-08-30; 95: 2025-12-06; 98: 2025-04-10; 99: 2025-04-17; 101: Done; 102: Done; 105: 2025-04-10; 106: 2025-04-17; 108: 2026-01-19; 109: 2026-01-21; 112: GP Project; 113: 2025-04-19; 114: 2025-04-26; 116: 2025-11-01; 117: 2026-01-16; 120: 2025-05-12; 121: 2025-05-23; 123: 2026-01-21; 124: 2026-01-31; 127: 2025-04-27; 128: 2025-05-05; 130: 2025-12-08; 131: 2025-12-15; 134: 2025-05-24; 135: 2025-05-31; 137: 2026-02-06; 138: 2026-02-10; 141: 2025-06-01; 142: 2025-06-03; 144: 2026-02-12; 145: 2026-02-15; 148: 2025-05-20; 149: 2025-05-21; 151: 2025-12-16; 152: 2025-12-16; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-08-20; 159: 2025-12-25; 162: 2025-04-20; 163: 2025-05-15; 165: 2025-08-31; 166: 2025-09-19; 169: 2025-05-22; 170: 2025-05-25; 172: 2025-12-20; 176: 2025-06-04; 177: 2025-06-06; 184: AC 7 Reached at loc. 143 date 5-DEC-25
5 | PSS-08 | ASEJ6PL | 1: WTG 145; 2: F11; 3: TEJAS; 4: 2025-02-25; 5: Bauer; 6: Yes; 7: 534816; 8: 2671985; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-02-12; 18: 2025-02-22; 20: 2025-02-14; 21: 2025-02-22; 32: 2025-02-24; 33: 2025-02-25; 35: 2025-03-04; 36: 2025-03-06; 39: 2025-02-26; 40: 2025-02-26; 42: 2025-03-07; 43: 2025-03-09; 46: 2025-02-27; 47: 2025-02-28; 49: 2025-03-10; 50: 2025-03-10; 53: 2025-03-01; 54: 2025-03-02; 56: 2025-03-12; 57: 2025-03-12; 60: 2025-03-03; 61: 2025-03-13; 63: 2025-03-13; 64: 2025-04-03; 67: 2025-03-14; 68: 2025-03-15; 70: 2025-04-04; 71: 2025-04-05; 75: 2025-03-20; 76: 2025-03-23; 78: 2025-05-05; 79: 2025-12-25; 82: 2025-03-22; 83: 2025-03-22; 85: 2025-04-17; 86: 2025-04-17; 91: 2025-04-01; 92: 2025-04-11; 94: 2025-04-04; 95: 2025-12-01; 98: 2025-03-17; 99: 2025-03-24; 101: 2025-05-14; 102: 2025-05-17; 105: 2025-03-17; 106: 2025-03-24; 108: 2025-08-12; 109: 2025-08-28; 112: GP Project; 113: 2025-03-26; 114: 2025-04-02; 116: 2025-03-20; 117: 2025-05-17; 120: 2025-05-21; 121: 2025-06-01; 123: 2025-08-31; 124: 2025-11-20; 127: 2025-05-01; 128: 2025-05-09; 130: 2025-12-01; 131: 2025-12-12; 134: 2025-06-02; 135: 2025-06-09; 137: 2025-11-24; 138: 2025-11-29; 141: 2025-06-10; 142: 2025-06-12; 144: 2025-11-30; 145: 2025-12-02; 148: 2025-05-29; 149: 2025-05-30; 151: 2025-12-17; 152: 2025-12-17; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-06-01; 159: 2025-12-25; 162: 2025-04-20; 163: 2025-05-15; 165: 2025-08-31; 166: 2025-09-19; 169: 2025-05-21; 170: 2025-05-24; 172: 2025-12-20; 173: 2025-12-25; 176: 2025-06-13; 177: 2025-06-15; 179: 2026-01-07
6 | PSS-08 | ASEJ6PL | 1: WTG 230; 2: F10; 3: HBG; 4: 2025-05-30; 5: Bauer; 6: Yes; 7: 537216; 8: 2675831; 12: Done; 13: Done; 15: 303; 16: 303; 17: 2025-02-13; 18: 2025-02-23; 20: 2025-03-06; 21: 2025-03-15; 23: drawing release on 28th Feb; 24: YES; 25: Bauer; 26: 2025-02-28; 27: 2025-03-07; 29: 2026-01-10; 30: 2026-01-23; 32: 2025-03-10; 33: 2025-03-11; 35: 2026-02-19; 36: 2026-02-22; 38: Extra stone solumn; 39: 2025-03-12; 40: 2025-03-12; 42: 2026-02-23; 43: 2026-02-24; 46: 2025-03-13; 47: 2025-03-14; 49: 2026-02-24; 50: 2026-02-24; 53: 2025-03-15; 54: 2025-03-16; 56: 2026-02-26; 57: 2026-02-26; 60: 2025-03-17; 61: 2025-03-27; 63: 2026-02-27; 67: 2025-03-28; 68: 2025-03-29; 75: 2025-04-03; 76: 2025-04-06; 82: 2025-04-05; 83: 2025-04-05; 91: 2025-04-02; 92: 2025-04-12; 94: 0; 98: 2025-03-31; 99: 2025-04-07; 101: 2025-03-21; 102: 2025-04-12; 105: 2025-03-31; 106: 2025-04-07; 112: GP Project; 113: 2025-04-09; 114: 2025-04-16; 116: 2025-04-30; 117: 2025-05-21; 120: 2025-05-18; 121: 2025-05-29; 127: 2025-05-15; 128: 2025-05-23; 130: 0; 134: 2025-05-30; 135: 2025-06-06; 141: 2025-06-07; 142: 2025-06-09; 148: 2025-06-04; 149: 2025-06-05; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-11-16; 162: 2025-04-20; 163: 2025-05-15; 165: 2025-08-31; 166: 2025-09-19; 169: 2025-06-06; 170: 2025-06-09; 176: 2025-06-10; 177: 2025-06-12; 184: 50 nos Additional column finish by bauer Date 11-Feb-26 to 13-Feb-26
7 | PSS-08 | ARE3L | 1: WTG 302; 2: F13; 3: SHREEJI; 4: 2025-04-15; 5: Keller; 6: Yes; 7: 540111; 8: 2672933; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-02-23; 18: 2025-03-04; 20: 2025-03-18; 21: 2025-03-27; 23: RIG not availbale; 32: 2025-03-19; 33: 2025-03-20; 35: 2025-04-16; 36: 2025-04-18; 39: 2025-03-21; 40: 2025-03-21; 42: 2025-04-19; 43: 2025-04-19; 46: 2025-03-22; 47: 2025-03-23; 49: 2025-04-19; 50: 2025-04-19; 53: 2025-03-24; 54: 2025-03-25; 56: 2025-04-20; 57: 2025-04-20; 60: 2025-03-26; 61: 2025-04-05; 63: 2025-04-20; 64: 2025-04-26; 67: 2025-04-06; 68: 2025-04-07; 70: 2025-04-26; 71: 2025-04-27; 75: 2025-04-12; 76: 2025-04-15; 78: 2025-05-01; 79: 2025-08-26; 82: 2025-04-14; 83: 2025-04-14; 85: 2025-05-03; 86: 2025-05-03; 91: 2025-03-22; 92: 2025-04-01; 94: 2025-04-19; 95: 2025-04-24; 98: 2025-04-09; 99: 2025-04-16; 101: 2025-05-18; 102: 2025-05-30; 105: 2025-04-09; 106: 2025-04-16; 108: 2025-05-20; 109: 2025-06-03; 112: Odhav; 113: 2025-04-18; 114: 2025-04-25; 116: 2025-05-20; 117: 2025-06-03; 120: 2025-05-26; 121: 2025-06-05; 123: 2025-06-14; 124: 2025-07-01; 127: 2025-05-01; 128: 2025-05-09; 130: 2025-06-14; 131: 2025-07-26; 134: 2025-06-06; 135: 2025-06-13; 137: 2025-07-12; 138: 2025-07-21; 141: 2025-06-14; 142: 2025-06-16; 144: 2025-07-25; 145: 2025-07-26; 148: 2025-05-29; 149: 2025-05-30; 151: 2025-08-22; 152: 2025-08-22; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-06-10; 159: 2025-08-17; 162: 2025-04-20; 163: 2025-05-15; 165: 2025-05-31; 166: 2025-06-19; 169: 2025-05-21; 170: 2025-05-24; 172: 2025-08-21; 173: 2025-08-24; 176: 2025-06-17; 177: 2025-06-19; 179: 2025-08-28; 180: 2025-08-29
8 | PSS-08 | ARE3L | 1: WTG 326; 2: F13; 3: SHREEJI; 4: 2025-04-15; 5: Keller; 6: Yes; 7: 540754; 8: 2673654; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-02-16; 18: 2025-02-26; 20: 2025-02-28; 21: 2025-03-09; 23: Delay due to RIG assy; 32: 2025-02-28; 33: 2025-03-01; 35: 2025-04-16; 36: 2025-04-21; 39: 2025-03-02; 40: 2025-03-02; 42: 2025-04-21; 43: 2025-04-22; 46: 2025-03-03; 47: 2025-03-04; 49: 2025-04-22; 50: 2025-04-22; 53: 2025-03-05; 54: 2025-03-06; 56: 2025-04-22; 57: 2025-04-22; 60: 2025-03-07; 61: 2025-03-17; 63: 2025-04-23; 64: 2025-04-30; 67: 2025-03-18; 68: 2025-03-19; 70: 2025-04-30; 71: 2025-05-01; 75: 2025-03-24; 76: 2025-03-27; 78: 2025-05-11; 79: 2025-08-27; 82: 2025-03-26; 83: 2025-03-26; 85: 2025-05-08; 86: 2025-05-08; 91: 2025-04-05; 92: 2025-04-15; 94: 2025-04-22; 95: 2025-05-30; 98: 2025-03-21; 99: 2025-03-28; 101: 2025-04-01; 102: 2025-04-18; 105: 2025-03-21; 106: 2025-03-28; 108: 2025-04-20; 109: 2025-05-20; 112: Harsh; 113: 2025-03-30; 114: 2025-04-06; 116: 2025-04-20; 117: 2025-05-20; 120: 2025-06-06; 121: 2025-06-17; 123: 2025-06-07; 124: 2025-06-16; 127: 2025-05-05; 128: 2025-05-13; 130: 2025-06-20; 131: 2025-07-20; 134: 2025-06-18; 135: 2025-06-25; 137: 2025-07-01; 138: 2025-07-12; 141: 2025-06-26; 142: 2025-06-28; 144: 2025-07-13; 145: 2025-07-15; 148: 2025-06-22; 149: 2025-06-23; 151: 2025-08-15; 152: 2025-08-15; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-06-05; 159: 2025-06-20; 162: 2025-04-20; 163: 2025-05-15; 165: 2025-05-31; 166: 2025-06-19; 169: 2025-06-24; 170: 2025-06-27; 172: 2025-08-17; 173: 2025-08-24; 176: 2025-06-29; 177: 2025-06-30; 179: 2025-08-28; 180: 2025-08-28
9 | PSS-08 | ARE3L | 1: WTG 327; 2: F13; 3: SHREEJI; 4: 2025-04-15; 5: Keller; 6: Yes; 7: 540944; 8: 2672668; 12: Done; 13: Done; 15: 199; 16: 199; 17: 2025-02-14; 18: 2025-02-24; 20: 2025-03-10; 21: 2025-03-17; 23: Platform preparation delay; 24: YES; 25: Bauer; 26: 2025-02-27; 27: 2025-02-05; 29: 2025-04-29; 30: 2025-05-26; 32: 2025-03-08; 33: 2025-03-09; 35: 2025-05-30; 36: 2025-06-01; 39: 2025-03-09; 40: 2025-03-10; 42: 2025-06-01; 43: 2025-06-01; 46: 2025-03-11; 47: 2025-03-12; 49: 2025-06-02; 50: 2025-06-02; 53: 2025-03-13; 54: 2025-03-14; 56: 2025-06-02; 57: 2025-06-02; 60: 2025-03-15; 61: 2025-03-25; 63: 2025-06-03; 64: 2025-06-07; 67: 2025-03-26; 68: 2025-03-27; 70: 2025-06-08; 71: 2025-06-08; 75: 2025-04-02; 76: 2025-04-05; 78: 2025-06-15; 79: 2025-08-26; 82: 2025-04-04; 83: 2025-04-04; 85: 2025-06-12; 86: 2025-06-13; 91: 2025-04-15; 92: 2025-04-25; 94: 2025-06-16; 95: 2025-06-26; 98: 2025-03-19; 99: 2025-03-26; 101: 2025-04-20; 102: 2025-05-01; 105: 2025-03-19; 106: 2025-03-26; 108: 2025-05-02; 109: 2025-05-26; 112: Harsh; 113: 2025-03-28; 114: 2025-04-04; 116: 2025-05-02; 117: 2025-05-26; 120: 2025-05-24; 121: 2025-06-05; 123: 2025-06-15; 124: 2025-06-26; 127: 2025-05-03; 128: 2025-05-11; 130: 2025-07-10; 131: 2025-07-30; 134: 2025-06-06; 135: 2025-06-13; 137: 2025-07-08; 138: 2025-07-18; 141: 2025-06-14; 142: 2025-06-16; 144: 2025-07-24; 145: 2025-07-25; 148: 2025-06-10; 149: 2025-06-11; 151: 2025-08-14; 152: 2025-08-14; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-06-04; 159: 2025-08-09; 162: 2025-04-20; 163: 2025-05-15; 165: 2025-05-31; 166: 2025-06-19; 169: 2025-06-12; 170: 2025-06-15; 172: 2025-08-17; 173: 2025-08-24; 176: 2025-06-17; 177: 2025-06-18; 179: 2025-08-28; 180: 2025-08-29
10 | PSS-08 | ARE3L | 1: WTG 351; 2: F13; 3: SHREEJI; 4: 2025-04-15; 5: Keller; 6: Yes; 7: 541595; 8: 2673350; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-02-27; 18: 2025-03-08; 20: 2025-03-20; 21: 2025-03-30; 23: Drawing available on 17Mar; 32: 2025-03-28; 33: 2025-03-29; 35: 2025-04-20; 36: 2025-04-23; 39: 2025-03-30; 40: 2025-03-30; 42: 2025-04-23; 43: 2025-04-24; 46: 2025-03-31; 47: 2025-04-01; 49: 2025-04-25; 50: 2025-04-25; 53: 2025-04-02; 54: 2025-04-03; 56: 2025-04-27; 57: 2025-04-27; 60: 2025-04-04; 61: 2025-04-14; 63: 2025-04-28; 64: 2025-05-03; 67: 2025-04-15; 68: 2025-04-16; 70: 2025-05-04; 71: 2025-05-05; 75: 2025-04-21; 76: 2025-04-24; 78: 2025-05-10; 79: 2025-08-25; 82: 2025-04-23; 83: 2025-04-23; 85: 2025-05-13; 86: 2025-05-13; 91: 2025-03-31; 92: 2025-04-10; 94: 2025-05-16; 95: 2025-06-02; 98: 2025-04-18; 99: 2025-04-25; 101: 2025-05-22; 102: 2025-05-31; 105: 2025-04-18; 106: 2025-04-25; 108: 2025-06-08; 109: 2025-06-11; 112: Harsh; 113: 2025-04-27; 114: 2025-05-04; 116: 2025-06-04; 117: 2025-06-09; 120: 2025-06-02; 121: 2025-06-14; 123: 2025-06-12; 124: 2025-06-26; 127: 2025-04-30; 128: 2025-05-08; 130: 2025-07-12; 131: 2025-07-31; 134: 2025-06-15; 135: 2025-06-22; 137: 2025-07-07; 138: 2025-07-17; 141: 2025-06-23; 142: 2025-06-25; 144: 2025-07-19; 145: 2025-07-23; 148: 2025-06-07; 149: 2025-06-08; 151: 2025-08-18; 152: 2025-08-18; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-05-30; 159: 2025-06-15; 162: 2025-04-20; 163: 2025-05-15; 165: 2025-05-31; 166: 2025-06-19; 169: 2025-06-09; 170: 2025-06-12; 172: 2025-08-21; 173: 2025-08-24; 176: 2025-06-26; 177: 2025-06-27; 179: 2025-08-28; 180: 2025-08-28
11 | PSS-05 | AHEJ5L | 1: WTG 316; 2: F07; 3: MSC; 4: 2025-05-07; 5: Bauer; 6: Yes; 7: 542960; 8: 2658138; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-31; 18: 2025-04-09; 20: 2025-04-09; 21: 2025-04-16; 24: YES; 25: Pinnacle; 29: 2025-05-26; 30: 2025-06-09; 32: 2025-04-11; 33: 2025-04-12; 35: 2025-06-05; 36: 2025-08-10; 39: 2025-04-13; 40: 2025-04-13; 42: 2025-08-10; 43: 2025-08-11; 46: 2025-04-14; 47: 2025-04-15; 49: 2025-08-11; 50: 2025-08-11; 53: 2025-04-16; 54: 2025-04-17; 56: 2025-08-12; 57: 2025-08-25; 60: 2025-04-18; 61: 2025-04-28; 63: 2025-08-30; 64: 2025-09-28; 67: 2025-04-29; 68: 2025-04-30; 70: 2025-09-29; 71: 2025-09-30; 75: 2025-05-05; 76: 2025-05-08; 78: 2025-10-08; 79: 2025-11-15; 82: 2025-05-07; 83: 2025-05-07; 85: 2025-10-14; 86: 2025-10-14; 91: 2025-05-12; 92: 2025-05-22; 94: 2025-08-10; 95: 2025-08-29; 98: 2025-05-02; 99: 2025-05-09; 101: 2025-05-02; 102: 2025-05-10; 105: 2025-05-02; 106: 2025-05-09; 108: 2025-10-05; 109: 2025-10-08; 112: GP Project; 113: 2025-05-11; 114: 2025-05-18; 116: 2025-04-29; 117: 2025-05-26; 120: 2025-06-19; 121: 2025-06-30; 123: 2025-10-10; 124: 2025-10-22; 127: 2025-06-11; 128: 2025-06-19; 130: 2025-09-21; 131: 2025-10-30; 134: 2025-07-01; 135: 2025-07-08; 137: 2025-10-29; 138: 2025-11-10; 141: 2025-07-09; 142: 2025-07-11; 144: 2025-11-10; 145: 2025-11-11; 148: 2025-10-17; 149: 2025-10-18; 151: 2025-10-10; 152: 2025-10-10; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-06-13; 159: 2025-10-10; 162: 2025-06-25; 163: 2025-07-20; 165: 2025-08-31; 166: 2025-09-21; 169: 2025-10-19; 170: 2025-10-22; 172: 2025-11-01; 173: 2025-11-11; 176: 2025-10-23; 177: 2025-10-25; 179: 2025-11-11; 180: 2025-11-18
12 | PSS-05 | AHEJ5L | 1: WTG 177; 2: F04; 3: MSC; 4: 2025-03-31; 5: Bauer; 6: Yes; 7: 537727; 8: 2660813; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-09; 18: 2025-03-19; 20: 2025-04-22; 21: 2025-04-26; 32: 2025-04-08; 33: 2025-04-09; 35: 2025-04-28; 36: 2025-04-29; 39: 2025-04-10; 40: 2025-04-10; 42: 2025-04-29; 43: 2025-04-29; 46: 2025-04-11; 47: 2025-04-12; 49: 2025-04-30; 50: 2025-04-30; 53: 2025-04-13; 54: 2025-04-14; 56: 2025-05-12; 57: 2025-05-13; 60: 2025-04-15; 61: 2025-04-25; 63: 2025-05-14; 64: 2025-05-20; 67: 2025-04-26; 68: 2025-04-27; 70: 2025-05-21; 71: 2025-05-22; 75: 2025-05-02; 76: 2025-05-05; 78: 2025-06-09; 79: 2025-11-15; 82: 2025-05-04; 83: 2025-05-04; 85: 2025-06-10; 86: 2025-06-10; 91: 2025-04-11; 92: 2025-04-21; 94: 2025-10-09; 95: 2025-10-15; 98: 2025-04-29; 99: 2025-05-06; 101: 2025-10-11; 102: 2025-10-15; 105: 2025-04-29; 106: 2025-05-06; 108: 2025-10-15; 109: 2025-10-16; 112: Varudi; 113: 2025-05-08; 114: 2025-05-15; 116: 2025-09-26; 117: 2025-10-14; 120: 2025-06-16; 121: 2025-06-27; 123: 2025-10-17; 124: 2025-10-29; 127: 2025-05-26; 128: 2025-06-03; 130: 2025-10-18; 131: 2025-10-29; 134: 2025-06-28; 135: 2025-07-05; 137: 2025-11-04; 138: 2025-11-11; 141: 2025-07-06; 142: 2025-07-08; 144: 2025-11-11; 145: 2025-11-12; 148: 2025-07-03; 149: 2025-07-04; 151: 2025-10-31; 152: 2025-10-31; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-06-14; 159: 2025-11-01; 162: 2025-05-15; 163: 2025-06-09; 165: 2025-08-31; 166: 2025-09-21; 169: 2025-07-05; 170: 2025-07-08; 172: 2025-10-31; 173: 2025-11-11; 176: 2025-07-09; 177: 2025-07-10; 179: 2025-11-11; 180: 2025-11-18
13 | PSS-08 | ASEJ6PL | 1: WTG 208; 2: F10; 3: DNC; 4: 2025-04-15; 5: Bauer; 6: Yes; 7: 536418; 8: 2675782; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-02-24; 18: 2025-03-04; 20: 2025-03-16; 21: 2025-03-28; 23: Drawing release on 15Mar; 24: YES; 25: Saritha; 26: 2025-03-06; 27: 2025-03-13; 29: 2025-06-04; 30: 2025-06-16; 32: 2025-03-16; 33: 2025-03-17; 35: 2025-07-16; 36: 2025-07-25; 39: 2025-03-18; 40: 2025-03-19; 42: 2025-07-26; 43: 2025-07-27; 46: 2025-03-20; 47: 2025-03-20; 49: 2025-07-27; 50: 2025-07-27; 53: 2025-03-21; 54: 2025-03-22; 56: 2025-08-03; 57: 2025-08-03; 60: 2025-03-22; 61: 2025-03-29; 63: 2025-08-07; 64: 2025-08-24; 67: 2025-03-30; 68: 2025-03-31; 70: 2025-08-25; 71: 2025-08-26; 75: 2025-04-01; 76: 2025-04-04; 78: 2025-09-03; 82: 2025-04-03; 83: 2025-04-03; 85: 2025-09-05; 86: 2025-09-05; 91: 2025-04-12; 92: 2025-04-22; 94: 2025-09-06; 95: 2026-02-27; 98: 2025-03-28; 99: 2025-04-04; 101: 2025-03-21; 102: 2025-04-16; 105: 2025-03-28; 106: 2025-04-04; 112: GP Project; 113: 2025-04-06; 114: 2025-04-13; 116: 2025-05-20; 117: 2025-06-03; 120: 2025-05-30; 121: 2025-06-09; 123: 2026-02-22; 127: 2025-05-12; 128: 2025-05-20; 130: 0; 134: 2025-06-10; 135: 2025-06-17; 141: 2025-06-18; 142: 2025-06-20; 148: 2025-06-19; 149: 2025-06-20; 155: 2025-04-01; 156: 2025-05-07; 162: 2025-04-20; 163: 2025-05-15; 165: 2025-08-31; 166: 2025-09-19; 169: 2025-06-21; 170: 2025-06-24; 176: 2025-06-25; 177: 2025-06-27
14 | PSS-08 | ASEJ6PL | 1: WTG 141; 2: F10; 3: DNC; 4: 2025-04-15; 5: Bauer; 6: Yes; 7: 533982; 8: 2676416; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-02-17; 18: 2025-02-27; 20: 2025-04-16; 21: 2025-04-26; 32: 2025-03-01; 33: 2025-03-02; 35: 2025-06-04; 36: 2025-06-06; 39: 2025-03-03; 40: 2025-03-03; 42: 2025-07-02; 43: 2025-07-04; 45: Delay due to water logging; 46: 2025-03-04; 47: 2025-03-05; 49: 2025-07-08; 50: 2025-07-08; 53: 2025-03-06; 54: 2025-03-07; 56: 2025-07-09; 57: 2025-07-09; 60: 2025-03-08; 61: 2025-03-18; 63: 2025-07-13; 64: 2025-07-28; 67: 2025-03-19; 68: 2025-03-20; 70: 2025-07-29; 71: 2025-07-30; 75: 2025-03-25; 76: 2025-03-28; 78: 2025-08-13; 82: 2025-03-27; 83: 2025-03-27; 85: 2025-08-14; 86: 2025-08-15; 91: 2025-04-06; 92: 2025-04-16; 94: 2025-07-26; 95: 2025-08-07; 98: 2025-03-22; 99: 2025-03-29; 101: 2025-03-17; 102: 2025-04-15; 105: 2025-03-22; 106: 2025-03-29; 108: 2026-01-17; 109: 2026-01-20; 112: GP Project; 113: 2025-03-31; 114: 2025-04-07; 116: 2025-05-18; 117: 2025-06-02; 120: 2025-05-14; 121: 2025-05-25; 123: 2026-01-24; 124: 2026-02-20; 127: 2025-05-06; 128: 2025-05-14; 130: 2026-02-17; 134: 2025-05-26; 135: 2025-06-02; 137: 2026-02-24; 138: 2026-02-28; 141: 2025-06-03; 142: 2025-06-05; 148: 2025-06-03; 149: 2025-06-04; 155: 2025-04-01; 156: 2025-05-07; 158: 2026-02-22; 162: 2025-04-20; 163: 2025-05-15; 165: 2025-08-31; 166: 2025-09-19; 169: 2025-06-05; 170: 2025-06-08; 176: 2025-06-09; 177: 2025-06-11
15 | PSS-08 | ASEJ6PL | 1: WTG 164; 2: F10; 5: Bauer; 6: Yes; 7: 534805; 8: 2676185; 12: Done; 13: Done; 15: 378; 16: 378; 17: 2025-02-28; 18: 2025-03-09; 20: 2025-04-07; 21: 2025-04-16; 24: YES; 25: 1.Saritha 2.Bauer; 26: 2025-03-10; 27: 2025-03-17; 29: 05-05-2025 12-2-2026; 30: 02-06-2025 26-02-2026; 32: 2025-03-18; 33: 2025-03-19; 39: 2025-03-20; 40: 2025-03-20; 46: 2025-03-21; 47: 2025-03-21; 53: 2025-03-22; 54: 2025-03-23; 60: 2025-03-23; 61: 2025-03-30; 67: 2025-03-30; 68: 2025-03-31; 75: 2025-04-05; 76: 2025-04-08; 82: 2025-04-07; 83: 2025-04-07; 91: 2025-04-16; 92: 2025-04-26; 94: 0; 98: 2025-04-01; 99: 2025-04-08; 101: 2025-03-17; 102: 2025-04-13; 105: 2025-04-01; 106: 2025-04-08; 112: GP Project; 113: 2025-04-10; 114: 2025-04-17; 116: 2025-11-03; 120: 2025-05-26; 121: 2025-06-05; 127: 2025-05-16; 128: 2025-05-24; 130: 0; 134: 2025-06-06; 135: 2025-06-13; 141: 2025-06-14; 142: 2025-06-16; 148: 2025-06-18; 149: 2025-06-19; 155: 2025-04-01; 156: 2025-05-07; 158: 2026-02-22; 162: 2025-04-20; 163: 2025-05-15; 165: 2025-08-31; 166: 2025-09-19; 169: 2025-06-20; 170: 2025-06-23; 176: 2025-06-24; 177: 2025-06-26
16 | PSS-08 | ARE3L | 1: WTG 352; 2: F13; 3: SHREEJI; 4: 2025-04-15; 5: Keller; 6: Yes; 7: 541786; 8: 2672364; 12: Done; 13: Done; 15: 211; 16: 211; 17: 2025-02-25; 18: 2025-03-06; 20: 2025-03-28; 21: 2025-04-03; 32: 2025-03-07; 33: 2025-03-08; 35: 2025-04-24; 36: 2025-04-26; 39: 2025-03-09; 40: 2025-03-09; 42: 2025-04-26; 43: 2025-04-27; 46: 2025-03-10; 47: 2025-03-11; 49: 2025-04-28; 50: 2025-04-28; 53: 2025-03-12; 54: 2025-03-13; 56: 2025-05-15; 57: 2025-05-16; 60: 2025-03-14; 61: 2025-03-24; 63: 2025-05-16; 64: 2025-05-24; 67: 2025-03-25; 68: 2025-03-26; 70: 2025-05-24; 71: 2025-05-24; 75: 2025-03-31; 76: 2025-04-03; 78: 2025-06-02; 79: 2025-08-26; 82: 2025-04-02; 83: 2025-04-02; 85: 2025-06-02; 86: 2025-06-02; 91: 2025-04-12; 92: 2025-04-22; 94: 2025-04-28; 95: 2025-06-04; 98: 2025-03-28; 99: 2025-04-04; 101: 2025-05-28; 102: 2025-06-06; 105: 2025-03-28; 106: 2025-04-04; 108: 2025-05-31; 109: 2025-06-06; 112: Odhav; 113: 2025-04-06; 114: 2025-04-13; 116: 2025-05-31; 117: 2025-06-06; 120: 2025-06-06; 121: 2025-06-17; 123: 2025-06-14; 124: 2025-07-03; 127: 2025-05-12; 128: 2025-05-20; 130: 2025-06-15; 131: 2025-07-20; 134: 2025-06-18; 135: 2025-06-25; 137: 2025-07-07; 138: 2025-07-15; 141: 2025-06-26; 142: 2025-06-28; 144: 2025-07-17; 145: 2025-07-18; 148: 2025-06-14; 149: 2025-06-15; 151: 2025-08-18; 152: 2025-08-18; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-06-02; 159: 2025-06-15; 162: 2025-04-20; 163: 2025-05-15; 165: 2025-05-31; 166: 2025-06-19; 169: 2025-06-16; 170: 2025-06-19; 172: 2025-08-21; 173: 2025-08-24; 176: 2025-06-29; 177: 2025-06-30; 179: 2025-08-28; 180: 2025-08-28
17 | PSS-08 | ASEJ6PL | 1: WTG 186; 2: F10; 3: DNC; 4: 2025-04-15; 5: Bauer; 6: Yes; 7: 535604; 8: 2675999; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-10; 18: 2025-03-19; 20: 2025-03-28; 21: 2025-04-07; 32: 2025-03-20; 33: 2025-03-21; 35: 2025-04-18; 36: 2025-04-21; 39: 2025-03-22; 40: 2025-03-22; 42: 2025-04-22; 43: 2025-04-23; 46: 2025-03-23; 47: 2025-03-24; 49: 2025-04-25; 50: 2025-04-25; 53: 2025-03-25; 54: 2025-03-26; 56: 2025-05-31; 57: 2025-05-31; 60: 2025-03-27; 61: 2025-04-06; 63: 2025-06-05; 64: 2025-06-20; 67: 2025-04-07; 68: 2025-04-08; 70: 2025-06-23; 71: 2025-06-24; 75: 2025-04-13; 76: 2025-04-16; 78: 2025-08-26; 79: 2026-02-04; 82: 2025-04-15; 83: 2025-04-15; 85: 2025-08-27; 86: 2025-08-27; 91: 2025-03-23; 92: 2025-04-02; 94: 2025-08-29; 95: 2025-09-02; 98: 2025-04-10; 99: 2025-04-17; 101: Done; 102: Done; 105: 2025-04-10; 106: 2025-04-17; 108: 2026-01-02; 109: 2026-01-04; 112: GP Project; 113: 2025-04-19; 114: 2025-04-26; 116: 2025-08-28; 117: 2025-09-03; 120: 2025-06-06; 121: 2025-06-16; 123: 2026-01-03; 124: 2026-01-15; 127: 2025-05-02; 128: 2025-05-10; 130: 2026-01-04; 131: 2026-02-20; 134: 2025-06-17; 135: 2025-06-24; 137: 2026-01-20; 138: 2026-01-25; 141: 2025-06-25; 142: 2025-06-27; 144: 2026-01-26; 145: 2026-01-26; 148: 2025-06-08; 149: 2025-06-09; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-11-16; 162: 2025-04-20; 163: 2025-05-15; 165: 2025-08-31; 166: 2025-09-19; 169: 2025-06-06; 170: 2025-06-09; 176: 2025-06-28; 177: 2025-06-29
18 | PSS-05 | AHEJ5L | 1: WTG 199; 2: F04; 3: MSC; 4: 2025-03-31; 5: Bauer; 6: Yes; 7: 538550; 8: 2660542; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-02-22; 18: 2025-03-03; 20: 2025-02-19; 21: 2025-02-28; 32: 2025-03-23; 33: 2025-03-24; 35: 2025-03-31; 36: 2025-04-01; 39: 2025-03-25; 40: 2025-03-25; 42: 2025-04-01; 43: 2025-04-01; 46: 2025-03-26; 47: 2025-03-27; 49: 2025-04-02; 50: 2025-04-02; 53: 2025-03-28; 54: 2025-03-29; 56: 2025-04-04; 57: 2025-04-06; 60: 2025-03-30; 61: 2025-04-09; 63: 2025-04-06; 64: 2025-04-17; 67: 2025-04-10; 68: 2025-04-11; 70: 2025-04-19; 71: 2025-04-20; 75: 2025-04-16; 76: 2025-04-19; 78: 2025-10-09; 79: 2025-11-14; 82: 2025-04-18; 83: 2025-04-18; 85: 2025-10-16; 86: 2025-10-16; 91: 2025-03-26; 92: 2025-04-05; 94: 2025-10-08; 95: 2025-10-16; 98: 2025-04-13; 99: 2025-04-20; 101: 2025-10-16; 102: 2025-10-22; 105: 2025-04-13; 106: 2025-04-20; 108: 2025-10-09; 109: 2025-10-13; 112: SS Jadeja; 113: 2025-04-22; 114: 2025-04-29; 116: 2025-10-10; 117: 2025-10-15; 120: 2025-07-04; 121: 2025-09-02; 123: 2025-10-18; 124: 2025-10-30; 127: 2025-04-25; 128: 2025-05-03; 130: 2025-10-24; 131: 2025-10-29; 134: 2025-09-03; 135: 2025-09-10; 137: 2025-11-05; 138: 2025-11-11; 141: 2025-09-11; 142: 2025-09-13; 144: 2025-11-11; 145: 2025-11-12; 148: 2025-08-28; 149: 2025-08-29; 151: 2025-10-31; 152: 2025-10-31; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-06-14; 159: 2025-11-02; 162: 2025-06-25; 163: 2025-07-20; 165: 2025-08-31; 166: 2025-09-21; 169: 2025-08-03; 170: 2025-08-06; 172: 2025-11-01; 173: 2025-11-11; 176: 2025-09-14; 177: 2025-09-15; 179: 2025-11-11; 180: 2025-11-18
19 | PSS-05 | AHEJ5L | 1: WTG 176; 2: F03; 3: MSC; 4: 2025-04-15; 5: Bauer; 6: Yes; 7: 537553; 8: 2661818; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-23; 18: 2025-04-02; 20: 2025-04-16; 21: 2025-04-21; 32: 2025-04-11; 33: 2025-04-12; 35: 2025-04-26; 36: 2025-04-27; 39: 2025-04-13; 40: 2025-04-13; 42: 2025-04-27; 43: 2025-04-28; 46: 2025-04-14; 47: 2025-04-15; 49: 2025-04-28; 50: 2025-04-28; 53: 2025-04-16; 54: 2025-04-17; 56: 2025-04-29; 57: 2025-04-30; 60: 2025-04-18; 61: 2025-04-28; 63: 2025-04-30; 64: 2025-05-10; 67: 2025-04-29; 68: 2025-04-30; 70: 2025-05-12; 71: 2025-05-13; 75: 2025-05-05; 76: 2025-05-08; 78: 2025-05-29; 82: 2025-05-07; 83: 2025-05-07; 85: 2025-06-01; 86: 2025-06-01; 91: 2025-05-09; 92: 2025-05-19; 94: 2025-05-01; 95: 2025-06-05; 98: 2025-05-02; 99: 2025-05-09; 101: Done; 102: Done; 105: 2025-05-02; 106: 2025-05-09; 108: 2025-10-10; 109: 2025-10-12; 112: GP Project; 113: 2025-05-11; 114: 2025-05-18; 116: 2025-10-07; 117: 2025-10-12; 120: 2025-05-23; 121: 2025-06-03; 123: 2025-10-13; 124: 2025-10-26; 127: 2025-05-29; 128: 2025-06-06; 130: 2025-10-09; 131: 2025-10-26; 134: 2025-06-04; 135: 2025-06-11; 137: 2025-10-30; 138: 2025-11-15; 141: 2025-06-12; 142: 2025-06-14; 144: 2025-11-16; 145: 2025-11-18; 148: 2025-06-11; 149: 2025-06-12; 151: 2025-10-27; 152: 2025-10-27; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-10-15; 159: 2025-11-19; 162: 2025-05-15; 163: 2025-06-09; 165: 2025-10-15; 166: 2025-11-08; 169: 2025-06-13; 170: 2025-06-16; 172: 2025-11-04; 173: 2025-11-21; 176: 2025-06-17; 177: 2025-06-19; 179: 2025-11-22; 180: 2025-11-26
20 | PSS-11 | AGE25CL | 1: WTG 378; 2: F01; 3: BHAVANI; 4: 2025-05-24; 5: Kamar/Menard; 6: Yes; 7: 542809; 8: 2671113; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-02; 18: 2025-04-11; 20: 2025-02-01; 21: 2025-04-08; 23: Shifted to PSS & Start this loc by menard on 1-Apr-25; 32: 2025-04-25; 33: 2025-04-26; 35: 2025-05-26; 36: 2025-05-28; 39: 2025-04-27; 40: 2025-04-27; 42: 2025-05-29; 43: 2025-05-30; 46: 2025-04-28; 47: 2025-04-29; 49: 2025-05-31; 50: 2025-05-31; 53: 2025-04-30; 54: 2025-05-01; 56: 2025-06-08; 57: 2025-06-09; 60: 2025-05-02; 61: 2025-05-12; 63: 2025-06-10; 64: 2025-06-15; 67: 2025-05-13; 68: 2025-05-14; 70: 2025-06-21; 71: 2025-06-22; 75: 2025-05-19; 76: 2025-05-22; 78: 2025-07-17; 79: 2025-12-12; 82: 2025-05-21; 83: 2025-05-21; 85: 2025-08-24; 86: 2025-08-24; 91: 2025-05-08; 92: 2025-05-18; 94: 2025-08-10; 95: 2025-11-11; 98: 2025-05-16; 99: 2025-05-23; 101: 2025-11-13; 102: 2025-11-16; 105: 2025-05-16; 106: 2025-05-23; 108: 2025-11-12; 109: 2025-11-16; 112: Odhav; 113: 2025-05-18; 114: 2025-05-25; 116: 2025-11-06; 117: 2025-11-16; 120: 2025-10-06; 121: 2025-10-21; 123: 2025-11-20; 124: 2025-11-29; 127: 2025-10-23; 128: 2025-10-31; 130: 2025-11-13; 131: 2025-11-23; 134: 2025-10-22; 135: 2025-10-29; 137: 2025-12-03; 138: 2025-12-08; 141: 2025-10-30; 142: 2025-11-01; 144: 2025-12-08; 145: 2025-12-10; 148: 2025-11-07; 149: 2025-11-08; 151: 2025-11-24; 152: 2025-11-24; 155: 2025-10-05; 156: 2025-10-25; 158: 2025-11-10; 159: 2025-12-27; 162: 2025-09-25; 163: 2025-10-20; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-11-09; 170: 2025-11-12; 172: 2026-01-08; 173: 2026-01-31; 176: 2025-11-15; 177: 2025-11-16; 179: 2026-02-06; 180: 2026-02-09
21 | PSS-05 | AHEJ5L | 1: WTG 002; 2: F01; 3: MSC; 4: 2025-02-18; 5: Bauer; 6: Yes; 7: 535036; 8: 2662691; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-15; 18: 2025-03-24; 20: 2025-02-05; 21: 2025-02-12; 32: 2025-03-26; 33: 2025-03-27; 35: 2025-02-19; 36: 2025-02-20; 39: 2025-03-28; 40: 2025-03-28; 42: 2025-02-20; 43: 2025-02-21; 46: 2025-03-29; 47: 2025-03-30; 49: 2025-02-21; 50: 2025-02-21; 53: 2025-03-31; 54: 2025-04-01; 56: 2025-02-24; 57: 2025-02-24; 60: 2025-04-02; 61: 2025-04-12; 63: 2025-02-25; 64: 2025-03-01; 67: 2025-04-13; 68: 2025-04-14; 70: 2025-03-02; 71: 2025-03-02; 75: 2025-04-19; 76: 2025-04-22; 78: 2025-07-20; 79: 2025-07-31; 82: 2025-04-21; 83: 2025-04-21; 85: 2025-03-26; 86: 2025-03-26; 91: 2025-04-06; 92: 2025-04-16; 94: 2025-04-14; 95: 2025-06-05; 98: 2025-04-16; 99: 2025-04-23; 101: 2025-03-07; 102: 2025-03-20; 105: 2025-04-16; 106: 2025-04-23; 108: 2025-10-05; 109: 2025-10-09; 112: SS Jadeja; 113: 2025-04-25; 114: 2025-05-02; 116: 2025-03-20; 117: 2025-03-31; 120: 2025-05-21; 121: 2025-06-01; 123: 2025-10-11; 124: 2025-10-18; 127: 2025-05-26; 128: 2025-06-03; 130: 2025-09-20; 131: 2025-09-23; 134: 2025-06-02; 135: 2025-06-09; 137: 2025-10-27; 138: 2025-11-06; 141: 2025-06-10; 142: 2025-06-12; 144: 2025-11-06; 145: 2025-11-07; 148: 2025-06-13; 149: 2025-06-14; 151: 2025-10-23; 152: 2025-10-23; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-05-30; 159: 2025-08-10; 162: 2025-05-15; 163: 2025-06-09; 165: 2025-10-15; 166: 2025-11-08; 169: 2025-06-15; 170: 2025-06-18; 172: 2025-10-29; 173: 2025-11-13; 176: 2025-06-19; 177: 2025-06-20; 179: 2025-11-14; 180: 2025-11-21
22 | PSS-05 | AHEJ5L | 1: WTG 133; 2: F02; 3: MSC; 4: 2025-04-15; 5: Bauer; 6: Yes; 7: 536049; 8: 2661379; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-10; 18: 2025-03-20; 20: 2025-03-08; 21: 2025-03-17; 32: 2025-04-09; 33: 2025-04-10; 35: 2025-04-16; 36: 2025-04-17; 39: 2025-04-11; 40: 2025-04-11; 42: 2025-04-17; 43: 2025-04-17; 46: 2025-04-12; 47: 2025-04-13; 49: 2025-04-18; 50: 2025-04-18; 53: 2025-04-14; 54: 2025-04-15; 56: 2025-04-19; 57: 2025-04-20; 60: 2025-04-16; 61: 2025-04-26; 63: 2025-04-20; 64: 2025-05-01; 67: 2025-04-27; 68: 2025-04-28; 70: 2025-05-05; 71: 2025-05-06; 75: 2025-05-03; 76: 2025-05-06; 78: 2025-05-15; 79: 2025-08-02; 82: 2025-05-05; 83: 2025-05-05; 85: 2025-05-18; 86: 2025-05-18; 91: 2025-04-12; 92: 2025-04-22; 94: 2025-10-09; 95: 2025-10-14; 98: 2025-04-30; 99: 2025-05-07; 101: 2025-10-26; 102: 2025-10-30; 105: 2025-04-30; 106: 2025-05-07; 108: 2025-10-24; 109: 2025-10-27; 112: GP Project; 113: 2025-05-09; 114: 2025-05-16; 116: 2025-10-17; 117: 2025-10-27; 120: 2025-06-07; 121: 2025-06-17; 123: 2025-10-28; 124: 2025-11-13; 127: 2025-05-27; 128: 2025-06-04; 130: 2025-10-22; 131: 2025-11-03; 134: 2025-06-18; 135: 2025-06-25; 137: 2025-11-13; 138: 2025-11-20; 141: 2025-06-26; 142: 2025-06-28; 144: 2025-11-20; 145: 2025-11-21; 148: 2025-06-14; 149: 2025-06-15; 151: 2025-11-15; 152: 2025-11-15; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-10-17; 159: 2025-11-20; 162: 2025-05-15; 163: 2025-06-09; 165: 2025-10-15; 166: 2025-11-08; 169: 2025-06-16; 170: 2025-06-19; 172: 2025-11-18; 173: 2025-11-21; 176: 2025-06-29; 177: 2025-06-30; 179: 2025-11-22; 180: 2025-11-26
23 | PSS-05 | AHEJ5L | 1: WTG 290; 2: F07; 3: AB INFRA; 4: 2025-02-28; 5: Bauer; 6: Yes; 7: 541903; 8: 2659403; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-01; 18: 2025-03-10; 20: 2025-02-17; 21: 2025-02-27; 32: 2025-03-15; 33: 2025-03-16; 35: 2025-03-11; 36: 2025-03-13; 39: 2025-03-17; 40: 2025-03-17; 42: 2025-03-16; 43: 2025-03-16; 46: 2025-03-18; 47: 2025-03-19; 49: 2025-03-16; 50: 2025-03-17; 53: 2025-03-20; 54: 2025-03-21; 56: 2025-03-18; 57: 2025-03-18; 60: 2025-03-22; 61: 2025-04-01; 63: 2025-03-21; 64: 2025-03-28; 67: 2025-04-02; 68: 2025-04-03; 70: 2025-03-30; 71: 2025-03-31; 75: 2025-04-08; 76: 2025-04-11; 78: 2025-04-11; 79: 2025-06-28; 82: 2025-04-10; 83: 2025-04-10; 85: 2025-04-16; 86: 2025-04-16; 91: 2025-03-26; 92: 2025-04-05; 94: 2025-03-14; 95: 2025-05-03; 98: 2025-04-05; 99: 2025-04-12; 101: Done; 102: Done; 105: 2025-04-05; 106: 2025-04-12; 108: 2025-08-11; 109: 2025-08-18; 112: GP Project; 113: 2025-04-14; 114: 2025-04-21; 116: 2025-05-29; 117: 2025-07-07; 120: 2025-06-24; 121: 2025-07-15; 123: 2025-08-23; 124: 2025-09-30; 127: 2025-05-15; 128: 2025-05-23; 130: 2025-08-13; 131: 2025-09-15; 134: 2025-07-16; 135: 2025-07-23; 137: 2025-10-01; 138: 2025-10-09; 141: 2025-07-24; 142: 2025-07-26; 144: 2025-10-10; 145: 2025-10-11; 148: 2025-08-06; 149: 2025-08-07; 151: 2025-09-21; 152: 2025-09-21; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-05-26; 159: 2025-10-16; 162: 2025-06-25; 163: 2025-07-20; 165: 2025-08-31; 166: 2025-09-21; 169: 2025-08-08; 170: 2025-08-11; 172: 2025-09-28; 173: 2025-09-30; 176: 2025-08-12; 177: 2025-08-13; 179: 2025-10-17; 180: 2025-10-27
24 | PSS-05 | AHEJ5L | 1: WTG 315; 2: F07; 3: SHREERAM; 4: 2025-02-20; 5: Bauer; 6: Yes; 7: 542753; 8: 2659107; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-11; 18: 2025-03-20; 20: 2025-02-05; 21: 2025-02-15; 32: 2025-03-22; 33: 2025-03-23; 35: 2025-02-23; 36: 2025-02-24; 39: 2025-03-24; 40: 2025-03-24; 42: 2025-02-25; 43: 2025-02-25; 46: 2025-03-25; 47: 2025-03-26; 49: 2025-02-25; 50: 2025-02-25; 53: 2025-03-27; 54: 2025-03-28; 56: 2025-02-27; 57: 2025-02-27; 60: 2025-03-29; 61: 2025-04-08; 63: 2025-02-28; 64: 2025-03-11; 67: 2025-04-09; 68: 2025-04-10; 70: 2025-03-13; 71: 2025-03-13; 75: 2025-04-15; 76: 2025-04-18; 78: 2025-03-19; 79: 2025-10-28; 82: 2025-04-17; 83: 2025-04-17; 85: 2025-03-18; 86: 2025-03-18; 91: 2025-03-25; 92: 2025-04-04; 94: 2025-04-19; 95: 2025-07-30; 98: 2025-04-12; 99: 2025-04-19; 101: 2025-03-18; 102: 2025-03-30; 105: 2025-04-12; 106: 2025-04-19; 108: 2025-03-30; 109: 2025-04-20; 112: GP Project; 113: 2025-04-21; 114: 2025-04-28; 116: 2025-03-30; 117: 2025-04-20; 120: 2025-05-28; 121: 2025-06-07; 123: 2025-08-30; 124: 2025-09-12; 127: 2025-05-04; 128: 2025-05-12; 130: 2025-08-12; 131: 2025-09-18; 134: 2025-06-08; 135: 2025-06-15; 137: 2025-09-14; 138: 2025-09-23; 141: 2025-06-16; 142: 2025-06-18; 144: 2025-09-23; 145: 2025-09-24; 148: 2025-05-30; 149: 2025-05-31; 151: 2025-09-20; 152: 2025-09-20; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-05-23; 159: 2025-09-03; 162: 2025-05-15; 163: 2025-06-09; 165: 2025-08-31; 166: 2025-09-21; 169: 2025-05-29; 170: 2025-06-01; 172: 2025-09-19; 173: 2025-09-25; 176: 2025-06-19; 177: 2025-06-21; 179: 2025-10-15; 180: 2025-10-21
25 | PSS-05 | AHEJ5L | 1: WTG 266; 2: F06; 3: C&B; 4: 2025-02-20; 5: Bauer; 6: Yes; 7: 541076; 8: 2659675; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-24; 18: 2025-04-02; 20: 2025-02-07; 21: 2025-02-17; 32: 2025-04-10; 33: 2025-04-11; 35: 2025-02-25; 36: 2025-02-27; 39: 2025-04-12; 40: 2025-04-12; 42: 2025-02-27; 43: 2025-02-28; 46: 2025-04-13; 47: 2025-04-14; 49: 2025-02-28; 50: 2025-02-28; 53: 2025-04-15; 54: 2025-04-16; 56: 2025-03-06; 57: 2025-03-07; 60: 2025-04-17; 61: 2025-04-27; 63: 2025-03-07; 64: 2025-03-21; 67: 2025-04-28; 68: 2025-04-29; 70: 2025-03-22; 71: 2025-03-24; 75: 2025-05-04; 76: 2025-05-07; 78: 2025-03-31; 79: 2025-06-03; 82: 2025-05-06; 83: 2025-05-06; 85: 2025-03-27; 86: 2025-03-27; 91: 2025-04-13; 92: 2025-04-23; 94: 2025-03-24; 95: 2025-06-09; 98: 2025-05-01; 99: 2025-05-08; 101: 2025-03-13; 102: 2025-03-29; 105: 2025-05-01; 106: 2025-05-08; 108: 2025-08-18; 109: 2025-08-24; 112: GP Project; 113: 2025-05-10; 114: 2025-05-17; 116: 2025-03-31; 117: 2025-04-11; 120: 2025-07-19; 121: 2025-08-11; 123: 2025-08-28; 124: 2025-09-26; 127: 2025-06-12; 128: 2025-06-20; 130: 2025-08-11; 131: 2025-09-19; 134: 2025-08-12; 135: 2025-08-19; 137: 2025-09-27; 138: 2025-10-02; 141: 2025-08-20; 142: 2025-08-22; 144: 2025-10-02; 145: 2025-10-04; 148: 2025-10-28; 149: 2025-10-29; 151: 2025-09-19; 152: 2025-09-19; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-06-01; 159: 2025-06-02; 162: 2025-06-25; 163: 2025-07-20; 165: 2025-08-31; 166: 2025-09-21; 169: 2025-10-30; 170: 2025-11-02; 172: 2025-09-28; 173: 2025-09-29; 176: 2025-11-03; 177: 2025-11-05; 179: 2025-10-17; 180: 2025-10-27
26 | PSS-05 | AHEJ5L | 1: WTG 221; 2: F04; 3: MSC; 4: 2025-03-31; 5: Bauer; 6: Yes; 7: 539395; 8: 2660244; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-04; 18: 2025-03-13; 20: 2025-02-18; 21: 2025-03-01; 24: YES; 25: Pinnacle; 26: 2025-03-16; 27: 2025-03-22; 29: 2025-10-09; 30: 2025-10-17; 32: 2025-03-25; 33: 2025-03-27; 35: 2025-11-04; 36: 2025-11-06; 39: 2025-03-28; 40: 2025-03-28; 42: 2025-11-07; 43: 2025-11-07; 46: 2025-03-29; 47: 2025-03-29; 49: 2025-11-07; 50: 2025-11-07; 53: 2025-03-30; 54: 2025-03-31; 56: 2025-11-11; 57: 2025-11-11; 60: 2025-04-01; 61: 2025-04-09; 63: 2025-11-11; 64: 2025-11-15; 67: 2025-04-10; 68: 2025-04-11; 70: 2025-11-16; 71: 2025-11-16; 75: 2025-04-14; 76: 2025-04-17; 78: 2025-11-18; 79: 2025-12-13; 82: 2025-04-16; 83: 2025-04-16; 85: 2025-11-18; 86: 2025-11-18; 91: 2025-04-18; 92: 2025-04-28; 94: 2025-11-21; 95: 2025-11-28; 98: 2025-04-05; 99: 2025-04-12; 101: 2025-03-09; 102: 2025-03-24; 105: 2025-04-05; 106: 2025-04-12; 108: 2025-11-18; 109: 2025-11-24; 112: GP Project; 113: 2025-04-14; 114: 2025-04-21; 116: 2025-03-25; 117: 2025-03-31; 120: 2025-05-28; 121: 2025-06-07; 123: 2025-11-25; 124: 2025-11-30; 127: 2025-05-27; 128: 2025-06-04; 130: 2025-02-01; 131: 2025-12-02; 134: 2025-06-08; 135: 2025-06-15; 137: 2025-12-03; 138: 2025-12-07; 141: 2025-06-16; 142: 2025-06-18; 144: 2025-12-07; 145: 2025-12-09; 148: 2025-06-09; 149: 2025-06-10; 151: 2025-12-03; 152: 2025-12-03; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-05-30; 159: 2025-11-25; 162: 2025-05-15; 163: 2025-06-09; 165: 2025-08-31; 166: 2025-09-21; 169: 2025-06-11; 170: 2025-06-14; 172: 2025-12-07; 173: 2025-12-15; 176: 2025-06-19; 177: 2025-06-21; 179: 2025-12-15; 180: 2025-12-24
27 | PSS-05 | AHEJ5L | 1: WTG 243; 2: F06; 3: MSC; 4: 2025-04-11; 5: Bauer; 6: Yes; 7: 540229; 8: 2659973; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-14; 18: 2025-03-23; 20: 2025-03-01; 21: 2025-03-10; 32: 2025-03-31; 33: 2025-04-01; 35: 2025-04-11; 36: 2025-04-12; 39: 2025-04-02; 40: 2025-04-02; 42: 2025-04-12; 43: 2025-04-13; 46: 2025-04-03; 47: 2025-04-04; 49: 2025-04-13; 50: 2025-04-13; 53: 2025-04-05; 54: 2025-04-06; 56: 2025-04-15; 57: 2025-04-15; 60: 2025-04-07; 61: 2025-04-17; 63: 2025-04-16; 64: 2025-04-21; 67: 2025-04-18; 68: 2025-04-19; 70: 2025-04-22; 71: 2025-04-22; 75: 2025-04-24; 76: 2025-04-27; 78: 2025-04-26; 79: 2025-09-04; 82: 2025-04-26; 83: 2025-04-26; 85: 2025-05-01; 86: 2025-05-01; 91: 2025-04-03; 92: 2025-04-13; 94: 2025-04-12; 95: 2025-05-23; 98: 2025-04-21; 99: 2025-04-28; 101: 2025-03-17; 102: 2025-03-30; 105: 2025-04-21; 106: 2025-04-28; 108: 2025-07-25; 109: 2025-08-11; 112: GP Project; 113: 2025-04-30; 114: 2025-05-07; 116: 2025-03-29; 117: 2025-04-04; 120: 2025-06-16; 121: 2025-07-06; 123: 2025-08-11; 124: 2025-08-22; 127: 2025-05-28; 128: 2025-06-05; 130: 2025-08-13; 131: 2025-09-18; 134: 2025-07-07; 135: 2025-07-14; 137: 2025-08-26; 138: 2025-09-04; 141: 2025-07-15; 142: 2025-07-17; 144: 2025-09-04; 145: 2025-09-05; 148: 2025-07-20; 149: 2025-07-21; 151: 2025-09-18; 152: 2025-09-18; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-06-13; 159: 2025-09-23; 162: 2025-05-15; 163: 2025-06-09; 165: 2025-08-31; 166: 2025-09-21; 169: 2025-07-22; 170: 2025-07-25; 172: 2025-09-19; 173: 2025-09-23; 176: 2025-07-26; 177: 2025-07-28; 179: 2025-10-14; 180: 2025-10-21
28 | PSS-05 | AHEJ5L | 1: WTG 175; 2: F03; 3: MSC; 4: 2025-04-15; 5: Saritha; 6: Yes; 7: 537363; 8: 2662804; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-12; 18: 2025-03-22; 20: 2025-04-01; 21: 2025-05-17; 32: 2025-03-24; 33: 2025-03-25; 35: 2025-05-22; 36: 2025-05-23; 39: 2025-03-26; 40: 2025-03-26; 42: 2025-05-24; 43: 2025-05-24; 46: 2025-03-27; 47: 2025-03-28; 49: 2025-05-24; 50: 2025-05-24; 53: 2025-03-29; 54: 2025-03-30; 56: 2025-05-26; 57: 2025-05-26; 60: 2025-03-31; 61: 2025-04-10; 63: 2025-05-27; 64: 2025-06-04; 67: 2025-04-11; 68: 2025-04-12; 70: 2025-06-05; 71: 2025-06-06; 75: 2025-04-17; 76: 2025-04-20; 78: 2025-06-07; 82: 2025-04-19; 83: 2025-04-19; 85: 2025-06-08; 86: 2025-06-08; 91: 2025-03-27; 92: 2025-04-06; 94: 2025-05-24; 95: 2025-05-28; 98: 2025-04-14; 99: 2025-04-21; 101: 2025-10-26; 102: 2025-10-29; 105: 2025-04-14; 106: 2025-04-21; 108: 2025-10-26; 109: 2025-10-29; 112: GP Project; 113: 2025-04-23; 114: 2025-04-30; 116: 2025-10-11; 117: 2025-10-20; 120: 2025-06-08; 121: 2025-06-18; 123: 2025-11-01; 124: 2025-11-16; 127: 2025-05-01; 128: 2025-05-09; 130: 2025-11-01; 131: 2025-11-03; 134: 2025-06-19; 135: 2025-06-25; 137: 2025-11-17; 138: 2025-11-21; 141: 2025-06-26; 142: 2025-06-28; 144: 2025-11-21; 145: 2025-11-22; 148: 2025-06-15; 149: 2025-06-16; 151: 2025-11-05; 152: 2025-11-05; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-10-19; 159: 2025-11-15; 162: 2025-05-15; 163: 2025-06-09; 165: 2025-10-15; 166: 2025-11-08; 169: 2025-05-21; 170: 2025-05-24; 172: 2025-11-17; 173: 2025-11-21; 176: 2025-06-29; 177: 2025-06-30; 179: 2025-11-22; 180: 2025-11-26
29 | PSS-05 | AHEJ5L | 1: WTG 132; 2: F01; 3: MSC; 4: 2025-04-15; 5: Bauer; 6: Yes; 7: 535878; 8: 2662387; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-21; 18: 2025-03-30; 20: 2025-02-27; 21: 2025-03-07; 32: 2025-04-01; 33: 2025-04-02; 35: 2025-04-16; 36: 2025-04-17; 39: 2025-04-03; 40: 2025-04-03; 42: 2025-04-17; 43: 2025-04-17; 46: 2025-04-04; 47: 2025-04-05; 49: 2025-04-19; 50: 2025-04-19; 53: 2025-04-06; 54: 2025-04-07; 56: 2025-04-23; 57: 2025-04-23; 60: 2025-04-08; 61: 2025-04-18; 63: 2025-04-24; 64: 2025-04-30; 67: 2025-04-19; 68: 2025-04-20; 70: 2025-05-02; 71: 2025-05-03; 75: 2025-04-25; 76: 2025-04-28; 78: 2025-05-12; 82: 2025-04-27; 83: 2025-04-27; 85: 2025-05-17; 86: 2025-05-17; 91: 2025-04-04; 92: 2025-04-14; 94: 2025-05-01; 95: 2025-10-07; 98: 2025-04-22; 99: 2025-04-29; 101: Done; 102: Done; 105: 2025-04-22; 106: 2025-04-29; 108: 2025-10-10; 109: 2025-10-11; 112: GP Project; 113: 2025-05-01; 114: 2025-05-08; 116: 2025-04-30; 117: 2025-05-26; 120: 2025-06-02; 121: 2025-06-12; 123: 2025-10-11; 124: 2025-10-19; 127: 2025-05-24; 128: 2025-06-01; 130: 2025-10-01; 131: 2025-10-15; 134: 2025-06-13; 135: 2025-06-19; 137: 2025-10-25; 138: 2025-11-02; 141: 2025-06-20; 142: 2025-06-22; 144: 2025-11-02; 145: 2025-11-03; 148: 2025-06-16; 149: 2025-06-17; 151: 2025-10-23; 152: 2025-10-23; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-05-27; 159: 2025-11-01; 162: 2025-05-15; 163: 2025-06-09; 165: 2025-10-15; 166: 2025-11-08; 169: 2025-06-18; 170: 2025-06-21; 172: 2025-10-29; 173: 2025-11-13; 176: 2025-06-23; 177: 2025-06-24; 179: 2025-11-14; 180: 2025-11-21
30 | PSS-05 | AHEJ5L | 1: WTG 153; 2: F02; 3: MSC; 4: 2025-04-15; 5: Bauer; 6: Yes; 7: 536712; 8: 2662122; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-23; 18: 2025-04-01; 20: 2025-05-19; 21: 2025-05-26; 32: 2025-04-03; 33: 2025-04-04; 35: 2025-05-27; 36: 2025-05-28; 39: 2025-04-05; 40: 2025-04-05; 42: 2025-05-29; 43: 2025-05-30; 46: 2025-04-06; 47: 2025-04-07; 49: 2025-06-02; 50: 2025-06-02; 53: 2025-04-08; 54: 2025-04-09; 56: 2025-06-21; 57: 2025-06-22; 60: 2025-04-10; 61: 2025-04-20; 63: 2025-06-23; 64: 2025-06-28; 67: 2025-04-21; 68: 2025-04-22; 70: 2025-07-01; 71: 2025-07-02; 75: 2025-04-27; 76: 2025-04-30; 78: 2025-07-06; 82: 2025-04-29; 83: 2025-04-29; 85: 2025-07-09; 86: 2025-07-09; 91: 2025-04-14; 92: 2025-04-24; 94: 2025-06-02; 95: 2025-09-29; 98: 2025-04-24; 99: 2025-05-01; 101: Done; 102: Done; 105: 2025-04-24; 106: 2025-05-01; 108: 2025-10-17; 109: 2025-10-31; 112: GP Project; 113: 2025-05-03; 114: 2025-05-10; 116: 2025-10-04; 117: 2025-10-13; 120: 2025-06-13; 121: 2025-06-23; 123: 2025-10-28; 124: 2025-11-15; 127: 2025-06-13; 128: 2025-06-21; 130: 2025-10-08; 131: 2025-10-16; 134: 2025-06-24; 135: 2025-06-30; 137: 2025-11-17; 138: 2025-11-22; 141: 2025-07-01; 142: 2025-07-03; 144: 2025-11-22; 145: 2025-11-23; 148: 2025-08-05; 149: 2025-08-06; 151: 2025-10-24; 152: 2025-10-24; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-08-12; 159: 2025-10-25; 162: 2025-06-25; 163: 2025-07-20; 165: 2025-10-15; 166: 2025-11-08; 169: 2025-08-07; 170: 2025-08-10; 172: 2025-11-17; 173: 2025-11-21; 176: 2025-08-11; 177: 2025-08-13; 179: 2025-11-21; 180: 2025-11-26
31 | PSS-05 | AHEJ5L | 1: WTG 197; 2: F03; 3: MSC; 4: 2025-04-15; 5: Bauer; 6: Yes; 7: 538197; 8: 2662539; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-11; 18: 2025-03-20; 20: 2025-04-27; 21: 2025-05-03; 32: 2025-03-29; 33: 2025-03-30; 35: 2025-05-06; 36: 2025-05-07; 39: 2025-03-31; 40: 2025-03-31; 42: 2025-05-08; 43: 2025-05-08; 46: 2025-04-01; 47: 2025-04-02; 49: 2025-05-13; 50: 2025-05-13; 53: 2025-04-03; 54: 2025-04-04; 56: 2025-05-17; 57: 2025-05-17; 60: 2025-04-05; 61: 2025-04-15; 63: 2025-05-18; 64: 2025-06-13; 67: 2025-04-16; 68: 2025-04-17; 70: 2025-06-16; 71: 2025-06-17; 75: 2025-04-22; 76: 2025-04-25; 78: 2025-10-26; 82: 2025-04-24; 83: 2025-04-24; 85: 2025-10-27; 86: 2025-10-27; 91: 2025-05-19; 92: 2025-05-29; 94: 2025-05-07; 95: 2025-07-31; 98: 2025-04-19; 99: 2025-04-26; 101: Done; 102: Done; 105: 2025-04-19; 106: 2025-04-26; 108: 2025-11-05; 109: 2025-11-08; 112: GP Project; 113: 2025-04-28; 114: 2025-05-05; 116: 2025-10-12; 117: 2025-11-01; 120: 2025-07-01; 121: 2025-08-10; 123: 2025-11-08; 124: 2025-11-17; 127: 2025-06-18; 128: 2025-06-26; 130: 2025-11-12; 131: 2025-11-16; 134: 2025-08-11; 135: 2025-08-18; 137: 2025-11-19; 138: 2025-11-22; 141: 2025-08-19; 142: 2025-08-21; 144: 2025-11-22; 145: 2025-11-23; 148: 2025-10-04; 149: 2025-10-05; 151: 2025-11-17; 152: 2025-11-17; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-10-24; 159: 2025-11-20; 162: 2025-06-25; 163: 2025-07-20; 165: 2025-10-15; 166: 2025-11-08; 169: 2025-10-06; 170: 2025-10-09; 172: 2025-11-18; 173: 2025-11-21; 176: 2025-10-10; 177: 2025-10-12; 179: 2025-11-22; 180: 2025-11-26
32 | PSS-05 | AHEJ5L | 1: WTG 155; 2: F05; 3: MSC; 4: 2025-05-24; 5: Bauer; 6: Yes; 7: 537091; 8: 2660149; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-11; 18: 2025-03-21; 20: 2025-04-10; 21: 2025-05-23; 32: 2025-03-23; 33: 2025-03-24; 35: 2025-05-25; 36: 2025-05-26; 39: 2025-03-25; 40: 2025-03-25; 42: 2025-05-27; 43: 2025-05-27; 46: 2025-03-26; 47: 2025-03-27; 49: 2025-05-27; 50: 2025-05-27; 53: 2025-03-28; 54: 2025-03-29; 56: 2025-06-05; 57: 2025-06-06; 60: 2025-03-30; 61: 2025-04-09; 63: 2025-06-06; 64: 2025-06-12; 67: 2025-04-10; 68: 2025-04-11; 70: 2025-06-13; 71: 2025-06-14; 75: 2025-04-16; 76: 2025-04-19; 78: 2025-07-04; 82: 2025-04-18; 83: 2025-04-18; 85: 2025-07-05; 86: 2025-07-05; 91: 2025-03-26; 92: 2025-04-05; 94: 2025-09-25; 95: 2025-10-11; 98: 2025-04-13; 99: 2025-04-20; 101: Done; 102: Done; 105: 2025-04-13; 106: 2025-04-20; 108: 2025-09-30; 109: 2025-10-02; 112: GP Project; 113: 2025-04-22; 114: 2025-04-29; 116: 2025-09-23; 117: 2025-10-04; 120: 2025-06-18; 121: 2025-07-05; 123: 2025-10-05; 124: 2025-10-14; 127: 2025-04-25; 128: 2025-05-03; 130: 2025-10-16; 131: 2025-10-26; 134: 2025-07-06; 135: 2025-07-13; 137: 2025-10-25; 138: 2025-10-31; 141: 2025-07-14; 142: 2025-07-16; 144: 2025-10-31; 145: 2025-11-01; 148: 2025-06-27; 149: 2025-06-28; 151: 2025-11-04; 152: 2025-11-04; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-05-29; 159: 2025-10-17; 162: 2025-05-15; 163: 2025-06-09; 165: 2025-10-15; 166: 2025-11-08; 169: 2025-06-19; 170: 2025-06-22; 172: 2025-11-05; 173: 2025-11-13; 176: 2025-07-17; 177: 2025-07-19; 179: 2025-11-14; 180: 2025-11-21
33 | PSS-05 | AHEJ5L | 1: WTG 156; 2: F05; 3: MSC; 4: 2025-05-24; 5: Bauer; 6: Yes; 7: 537281; 8: 2659163; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-22; 18: 2025-03-31; 20: 2025-05-16; 21: 2025-05-20; 32: 2025-04-02; 33: 2025-04-03; 35: 2025-05-24; 36: 2025-05-25; 39: 2025-04-04; 40: 2025-04-04; 42: 2025-05-25; 43: 2025-05-26; 46: 2025-04-05; 47: 2025-04-06; 49: 2025-05-26; 50: 2025-05-26; 53: 2025-04-07; 54: 2025-04-08; 56: 2025-05-31; 57: 2025-06-01; 60: 2025-04-09; 61: 2025-04-19; 63: 2025-06-02; 64: 2025-06-08; 67: 2025-04-20; 68: 2025-04-21; 70: 2025-06-11; 71: 2025-06-12; 75: 2025-04-26; 76: 2025-04-29; 78: 2025-06-23; 82: 2025-04-28; 83: 2025-04-28; 85: 2025-07-03; 86: 2025-07-03; 91: 2025-04-05; 92: 2025-04-15; 94: 2025-05-26; 95: 2025-05-31; 98: 2025-04-23; 99: 2025-04-30; 101: Done; 102: Done; 105: 2025-04-23; 106: 2025-04-30; 108: 2025-09-25; 109: 2025-09-28; 112: GP Project; 113: 2025-05-02; 114: 2025-05-09; 116: 2025-09-20; 117: 2025-09-30; 120: 2025-06-20; 121: 2025-07-13; 123: 2025-10-01; 124: 2025-10-10; 127: 2025-05-05; 128: 2025-05-13; 130: 2025-10-03; 131: 2025-10-26; 134: 2025-07-14; 135: 2025-07-21; 137: 2025-10-14; 138: 2025-10-28; 141: 2025-07-22; 142: 2025-07-24; 144: 2025-10-28; 145: 2025-10-29; 148: 2025-07-05; 149: 2025-07-06; 151: 2025-10-17; 152: 2025-10-17; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-09-20; 159: 2025-10-18; 162: 2025-05-15; 163: 2025-06-09; 165: 2025-10-15; 166: 2025-11-08; 169: 2025-06-29; 170: 2025-07-02; 172: 2025-11-06; 173: 2025-11-13; 176: 2025-07-25; 177: 2025-07-27; 179: 2025-11-14; 180: 2025-11-21
34 | PSS-05 | AHEJ5L | 1: WTG 131; 2: F03; 3: MSC; 4: 2025-04-15; 5: Bauer; 6: Yes; 7: 535688; 8: 2663373; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-02-19; 18: 2025-02-28; 20: 2025-01-15; 21: 2025-01-24; 24: YES; 25: Keller; 26: 2025-03-07; 27: 2025-03-14; 29: 2025-05-26; 30: 2025-06-03; 32: 2025-03-20; 33: 2025-03-21; 35: 2025-06-25; 36: 2025-07-26; 39: 2025-03-22; 40: 2025-03-22; 42: 2025-07-27; 43: 2025-07-27; 46: 2025-03-23; 47: 2025-03-24; 49: 2025-07-30; 50: 2025-07-30; 53: 2025-03-25; 54: 2025-03-26; 56: 2025-08-01; 57: 2025-08-01; 60: 2025-03-27; 61: 2025-04-06; 63: 2025-08-05; 64: 2025-08-12; 67: 2025-04-07; 68: 2025-04-08; 70: 2025-08-31; 71: 2025-09-01; 75: 2025-04-13; 76: 2025-04-16; 78: 2025-10-14; 82: 2025-04-15; 83: 2025-04-15; 85: 2025-10-16; 86: 2025-10-16; 91: 2025-04-15; 92: 2025-04-25; 94: 2025-10-19; 95: 2025-10-29; 98: 2025-04-10; 99: 2025-04-17; 101: 2025-04-07; 102: 2025-04-20; 105: 2025-04-10; 106: 2025-04-17; 108: 2025-10-25; 109: 2025-10-29; 112: GP Project; 113: 2025-04-19; 114: 2025-04-26; 116: 2025-04-21; 117: 2025-05-10; 120: 2025-05-28; 121: 2025-06-07; 123: 2025-10-26; 124: 2025-11-16; 127: 2025-06-04; 128: 2025-06-12; 130: 2025-11-01; 131: 2025-11-03; 134: 2025-06-08; 135: 2025-06-15; 137: 2025-11-19; 138: 2025-11-22; 141: 2025-06-16; 142: 2025-06-18; 144: 2025-11-22; 145: 2025-11-24; 148: 2025-06-17; 149: 2025-06-18; 151: 2025-11-06; 152: 2025-11-06; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-06-03; 159: 2025-11-18; 162: 2025-05-15; 163: 2025-06-09; 165: 2025-10-15; 166: 2025-11-08; 169: 2025-06-19; 170: 2025-06-22; 172: 2025-11-17; 173: 2025-11-21; 176: 2025-06-23; 177: 2025-06-25; 179: 2025-11-22; 180: 2025-11-26
35 | PSS-05 | AHEJ5L | 1: WTG 152; 2: F02; 3: MSC; 4: 2025-04-15; 5: Bauer; 6: Yes; 7: 536522; 8: 2663108; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-01; 18: 2025-03-10; 20: 2025-05-05; 21: 2025-05-19; 32: 2025-03-30; 33: 2025-03-31; 35: 2025-05-29; 36: 2025-05-30; 39: 2025-04-01; 40: 2025-04-01; 42: 2025-05-31; 43: 2025-05-31; 46: 2025-04-02; 47: 2025-04-03; 49: 2025-06-06; 50: 2025-06-06; 53: 2025-04-04; 54: 2025-04-05; 56: 2025-08-05; 57: 2025-08-05; 60: 2025-04-06; 61: 2025-04-16; 63: 2025-08-07; 64: 2025-09-26; 67: 2025-04-17; 68: 2025-04-18; 70: 2025-09-27; 71: 2025-09-28; 75: 2025-04-23; 76: 2025-04-26; 78: 2025-10-11; 82: 2025-04-25; 83: 2025-04-25; 85: 2025-10-24; 86: 2025-10-24; 91: 2025-04-02; 92: 2025-04-12; 94: 2025-06-01; 95: 2025-06-14; 98: 2025-04-20; 99: 2025-04-27; 101: Done; 102: Done; 105: 2025-04-20; 106: 2025-04-27; 108: 2025-10-17; 109: 2025-10-23; 112: GP Project; 113: 2025-04-29; 114: 2025-05-06; 116: 2025-10-05; 117: 2025-10-14; 120: 2025-06-21; 121: 2025-07-09; 123: 2025-10-21; 124: 2025-11-13; 127: 2025-05-02; 128: 2025-05-10; 130: 2025-10-28; 131: 2025-11-15; 134: 2025-07-10; 135: 2025-07-17; 137: 2025-11-14; 138: 2025-11-21; 141: 2025-07-18; 142: 2025-07-20; 144: 2025-11-21; 145: 2025-11-24; 148: 2025-08-18; 149: 2025-08-19; 151: 2025-11-05; 152: 2025-11-05; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-08-16; 159: 2025-10-24; 162: 2025-06-25; 163: 2025-07-20; 165: 2025-10-15; 166: 2025-11-08; 169: 2025-08-20; 170: 2025-08-23; 172: 2025-11-17; 173: 2025-11-21; 176: 2025-08-24; 177: 2025-08-26; 179: 2025-11-21; 180: 2025-11-26
36 | PSS-05 | AHEJ5L | 1: WTG 178; 2: F04; 3: MSC; 4: 2025-03-31; 5: Bauer; 6: Yes; 7: 537933; 8: 2659845; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-08; 18: 2025-03-19; 20: 2025-05-03; 21: 2025-05-21; 24: YES; 25: Keller; 29: 2025-06-01; 30: 2025-06-13; 32: 2025-03-21; 33: 2025-03-22; 35: 2025-06-19; 36: 2025-06-20; 39: 2025-03-23; 40: 2025-03-23; 42: 2025-06-20; 43: 2025-06-21; 46: 2025-03-24; 47: 2025-03-25; 49: 2025-06-21; 50: 2025-06-21; 53: 2025-03-26; 54: 2025-03-27; 56: 2025-06-26; 57: 2025-06-26; 60: 2025-03-28; 61: 2025-04-07; 63: 2025-07-02; 64: 2025-07-22; 67: 2025-04-08; 68: 2025-04-09; 70: 2025-07-22; 71: 2025-07-23; 75: 2025-04-14; 76: 2025-04-17; 78: 2025-07-30; 79: 2025-08-16; 82: 2025-04-16; 83: 2025-04-16; 85: 2025-08-10; 86: 2025-08-10; 91: 2025-05-11; 92: 2025-05-21; 94: 2025-06-20; 95: 2025-08-05; 98: 2025-04-11; 99: 2025-04-18; 101: Done; 102: Done; 105: 2025-04-11; 106: 2025-04-18; 108: 2025-10-06; 109: 2025-10-08; 112: GP Project; 113: 2025-04-20; 114: 2025-04-27; 116: 2025-08-25; 117: 2025-09-19; 120: 2025-06-04; 121: 2025-06-15; 123: 2025-10-08; 124: 2025-10-15; 127: 2025-05-31; 128: 2025-06-08; 130: 2025-09-22; 131: 2025-10-06; 134: 2025-06-16; 135: 2025-06-23; 137: 2025-10-15; 138: 2025-10-20; 141: 2025-06-24; 142: 2025-06-26; 144: 2025-10-20; 145: 2025-10-21; 148: 2025-06-18; 149: 2025-06-19; 151: 2025-10-11; 152: 2025-10-11; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-06-01; 159: 2025-10-19; 162: 2025-05-15; 163: 2025-06-09; 165: 2025-08-31; 166: 2025-09-21; 169: 2025-06-20; 170: 2025-06-23; 172: 2025-10-19; 173: 2025-10-22; 176: 2025-06-27; 177: 2025-06-29; 179: 2025-10-23; 180: 2025-10-27
37 | PSS-05 | AHEJ5L | 1: WTG 179; 2: F05; 3: MSC; 4: 2025-05-24; 5: Bauer; 6: Yes; 7: 538123; 8: 2658859; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-20; 18: 2025-03-30; 20: 2025-04-29; 21: 2025-05-15; 32: 2025-04-01; 33: 2025-04-02; 35: 2025-05-26; 36: 2025-05-27; 39: 2025-04-03; 40: 2025-04-03; 42: 2025-05-27; 43: 2025-05-27; 46: 2025-04-04; 47: 2025-04-05; 49: 2025-05-28; 50: 2025-05-28; 53: 2025-04-06; 54: 2025-04-07; 56: 2025-06-09; 57: 2025-06-10; 60: 2025-04-08; 61: 2025-04-18; 63: 2025-06-11; 64: 2025-06-18; 67: 2025-04-19; 68: 2025-04-20; 70: 2025-06-20; 71: 2025-06-20; 75: 2025-04-25; 76: 2025-04-28; 78: 2025-06-25; 79: 2025-11-16; 82: 2025-04-27; 83: 2025-04-27; 85: 2025-07-04; 86: 2025-07-04; 91: 2025-05-07; 92: 2025-05-17; 94: 2025-05-30; 95: 2025-06-13; 98: 2025-04-22; 99: 2025-04-29; 101: Done; 102: Done; 105: 2025-04-22; 106: 2025-04-29; 108: 2025-08-21; 109: 2025-09-28; 112: GP Project; 113: 2025-05-01; 114: 2025-05-08; 116: 2025-06-09; 117: 2025-06-27; 120: 2025-06-16; 121: 2025-07-10; 123: 2025-09-24; 124: 2025-10-08; 127: 2025-06-01; 128: 2025-06-09; 130: 2025-09-27; 131: 2025-10-09; 134: 2025-07-11; 135: 2025-07-18; 137: 2025-10-10; 138: 2025-10-17; 141: 2025-07-19; 142: 2025-07-21; 144: 2025-10-27; 145: 2025-10-29; 148: 2025-09-12; 149: 2025-09-13; 151: 2025-10-09; 152: 2025-10-09; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-06-08; 159: 2025-11-02; 162: 2025-06-25; 163: 2025-07-20; 165: 2025-10-15; 166: 2025-11-08; 169: 2025-09-14; 170: 2025-09-17; 172: 2025-10-30; 173: 2025-11-13; 176: 2025-09-18; 177: 2025-09-19; 179: 2025-11-14; 180: 2025-11-21
38 | PSS-08 | ASEJ6PL | 1: WTG 400; 2: F12; 3: SHREEJI; 4: 2025-04-15; 5: Keller; 6: Yes; 7: 543080; 8: 2673767; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-02-26; 18: 2025-03-07; 20: 2025-04-12; 21: 2025-06-04; 32: 2025-03-08; 33: 2025-03-09; 35: 2025-06-11; 36: 2025-06-19; 39: 2025-03-10; 40: 2025-03-10; 42: 2025-06-20; 43: 2025-06-21; 46: 2025-03-11; 47: 2025-03-12; 49: 2025-06-22; 50: 2025-06-22; 53: 2025-03-13; 54: 2025-03-14; 56: 2025-06-23; 57: 2025-06-23; 60: 2025-03-15; 61: 2025-03-25; 63: 2025-06-25; 64: 2025-07-09; 67: 2025-03-26; 68: 2025-03-27; 70: 2025-07-10; 71: 2025-07-11; 75: 2025-04-01; 76: 2025-04-04; 78: 2025-07-23; 79: 2025-12-01; 82: 2025-04-03; 83: 2025-04-03; 85: 2025-07-17; 86: 2025-07-17; 91: 2025-04-08; 92: 2025-04-18; 94: 2025-11-01; 95: 2025-11-05; 98: 2025-03-29; 99: 2025-04-05; 101: 2025-10-29; 102: 2025-10-30; 105: 2025-03-29; 106: 2025-04-05; 108: 2025-10-27; 109: 2025-10-29; 112: Odhav; 113: 2025-04-07; 114: 2025-04-14; 116: 2025-09-03; 117: 2025-10-28; 120: 2025-06-02; 121: 2025-06-12; 123: 2025-10-30; 124: 2025-11-13; 127: 2025-04-28; 128: 2025-05-06; 130: 2025-11-07; 131: 2025-11-13; 134: 2025-06-13; 135: 2025-06-20; 137: 2025-11-13; 138: 2025-11-19; 141: 2025-06-21; 142: 2025-06-23; 144: 2025-11-25; 145: 2025-11-27; 148: 2025-06-05; 149: 2025-06-06; 151: 2025-11-14; 152: 2025-11-14; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-06-03; 159: 2025-06-15; 162: 2025-04-20; 163: 2025-05-15; 165: 2025-08-31; 166: 2025-09-19; 169: 2025-06-07; 170: 2025-06-10; 172: 2025-11-25; 173: 2025-11-29; 176: 2025-06-24; 177: 2025-06-26; 179: 2025-12-03
39 | PSS-05 | AHEJ5L | 1: WTG 198; 2: F03; 3: MSC; 4: 2025-04-15; 5: Bauer; 6: Yes; 7: 538387; 8: 2661553; 12: Done; 13: Done; 15: 451; 16: 451; 17: 2025-03-21; 18: 2025-03-30; 20: 2025-03-01; 21: 2025-04-15; 23: Rig shifted to PSS; 24: YES; 25: ITDC/Bauer; 26: 2025-04-03; 27: 2025-04-10; 29: 29-May-25 2-Nov-25; 30: 09-Jun-25 14-Nov-25; 32: 2025-04-13; 33: 2025-04-14; 35: 2025-11-16; 36: 2025-11-17; 39: 2025-04-15; 40: 2025-04-15; 42: 2025-11-17; 43: 2025-11-18; 46: 2025-04-16; 47: 2025-04-17; 49: 2025-11-18; 50: 2025-11-18; 53: 2025-04-18; 54: 2025-04-18; 56: 2025-11-18; 57: 2025-11-20; 60: 2025-04-19; 61: 2025-04-29; 63: 2025-11-20; 64: 2025-11-23; 67: 2025-04-30; 68: 2025-04-30; 70: 2025-11-24; 71: 2025-11-25; 75: 2025-05-03; 76: 2025-05-08; 78: 2025-12-03; 79: 2025-12-15; 82: 2025-05-07; 83: 2025-05-07; 85: 2025-12-04; 86: 2025-12-04; 91: 2025-05-12; 92: 2025-05-22; 94: 2025-11-18; 95: 2025-11-29; 98: 2025-04-22; 99: 2025-04-29; 101: Done; 102: Done; 105: 2025-04-22; 106: 2025-04-29; 108: 2025-11-30; 109: 2025-12-02; 112: Varudi; 113: 2025-05-01; 114: 2025-05-08; 116: 2025-05-22; 117: 2025-06-02; 120: 2025-06-04; 121: 2025-06-15; 123: 2025-12-01; 124: 2025-12-13; 127: 2025-06-01; 128: 2025-06-09; 130: 2025-11-30; 131: 2025-12-05; 134: 2025-06-16; 135: 2025-06-23; 137: 2025-12-15; 138: 2025-12-17; 141: 2025-06-24; 142: 2025-06-26; 144: 2025-12-17; 145: 2025-12-18; 148: 2025-06-19; 149: 2025-06-20; 151: 2025-12-06; 152: 2025-12-06; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-10-26; 159: 2025-11-19; 162: 2025-05-15; 163: 2025-06-09; 165: 2025-10-15; 166: 2025-11-08; 169: 2025-06-21; 170: 2025-06-24; 172: 2025-12-15; 173: 2025-12-19; 176: 2025-06-27; 177: 2025-06-29; 179: 2025-12-19; 180: 2025-12-24; 184: Location falling under transmission line, due to that loc. co-ordinates change
40 | PSS-05 | AHEJ5L | 1: WTG 200; 2: F04; 3: MSC; 4: 2025-03-31; 5: Bauer; 6: Yes; 7: 538767; 8: 2659580; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-02-20; 18: 2025-03-01; 20: 2025-03-11; 21: 2025-03-21; 23: RIG shifting from Loc.243; 32: 2025-03-21; 33: 2025-03-22; 35: 2025-04-02; 36: 2025-04-03; 39: 2025-03-23; 40: 2025-03-23; 42: 2025-04-03; 43: 2025-04-03; 46: 2025-03-24; 47: 2025-03-25; 49: 2025-04-04; 50: 2025-04-04; 53: 2025-03-26; 54: 2025-03-27; 56: 2025-04-05; 57: 2025-04-06; 60: 2025-03-28; 61: 2025-04-07; 63: 2025-04-06; 64: 2025-04-12; 67: 2025-04-08; 68: 2025-04-09; 70: 2025-04-13; 71: 2025-04-14; 75: 2025-04-14; 76: 2025-04-17; 78: 2025-04-17; 79: 2025-08-17; 82: 2025-04-16; 83: 2025-04-16; 85: 2025-05-01; 86: 2025-05-01; 91: 2025-04-21; 92: 2025-05-01; 94: 2025-04-14; 95: 2025-06-13; 98: 2025-04-11; 99: 2025-04-18; 101: Done; 102: Done; 105: 2025-04-11; 106: 2025-04-18; 108: 2025-10-10; 109: 2025-10-12; 112: Varudi; 113: 2025-04-20; 114: 2025-04-27; 116: 2025-03-30; 117: 2025-04-11; 120: 2025-06-08; 121: 2025-06-18; 123: 2025-10-01; 124: 2025-10-13; 127: 2025-05-26; 128: 2025-06-03; 130: 2025-09-18; 131: 2025-10-13; 134: 2025-06-19; 135: 2025-06-25; 137: 2025-10-15; 138: 2025-10-20; 141: 2025-06-26; 142: 2025-06-28; 144: 2025-10-20; 145: 2025-10-21; 148: 2025-06-23; 149: 2025-06-24; 151: 2025-10-18; 152: 2025-10-18; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-05-26; 159: 2025-10-19; 162: 2025-05-15; 163: 2025-06-09; 165: 2025-08-31; 166: 2025-09-21; 169: 2025-06-25; 170: 2025-06-28; 172: 2025-10-19; 173: 2025-10-22; 176: 2025-06-29; 177: 2025-06-30; 179: 2025-10-23; 180: 2025-10-27
41 | PSS-05 | AHEJ5L | 1: WTG 201; 2: F08; 3: ODHAV; 4: 2025-05-02; 5: Bauer; 6: Yes; 7: 538957; 8: 2658594; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-31; 18: 2025-04-10; 20: 2025-04-15; 21: 2025-04-21; 32: 2025-04-11; 33: 2025-04-12; 35: 2025-05-03; 36: 2025-05-04; 39: 2025-04-13; 40: 2025-04-13; 42: 2025-05-04; 43: 2025-05-05; 46: 2025-04-14; 47: 2025-04-15; 49: 2025-05-06; 50: 2025-05-06; 53: 2025-04-16; 54: 2025-04-17; 56: 2025-05-29; 57: 2025-05-29; 60: 2025-04-18; 61: 2025-04-28; 63: 2025-05-29; 64: 2025-06-13; 67: 2025-04-29; 68: 2025-04-30; 70: 2025-06-15; 71: 2025-06-16; 75: 2025-05-05; 76: 2025-05-08; 78: 2025-06-26; 79: 2025-10-28; 82: 2025-05-07; 83: 2025-05-07; 85: 2025-07-27; 86: 2025-07-27; 91: 2025-05-17; 92: 2025-05-27; 94: 2025-05-06; 95: 2025-09-16; 98: 2025-05-02; 99: 2025-05-09; 101: 2025-02-01; 102: 2025-02-20; 105: 2025-05-02; 106: 2025-05-09; 108: 2025-08-21; 109: 2025-08-27; 112: Varudi; 113: 2025-05-11; 114: 2025-05-18; 116: 2025-09-02; 117: 2025-09-20; 120: 2025-08-20; 121: 2025-10-12; 123: 2025-09-21; 124: 2025-10-02; 127: 2025-06-16; 128: 2025-06-24; 130: 2025-09-16; 131: 2025-09-22; 134: 2025-10-13; 135: 2025-10-20; 137: 2025-10-03; 138: 2025-10-15; 141: 2025-10-21; 142: 2025-10-23; 144: 2025-10-15; 145: 2025-10-17; 148: 2025-11-01; 149: 2025-11-02; 151: 2025-10-18; 152: 2025-10-18; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-10-12; 159: 2025-10-20; 162: 2025-06-25; 163: 2025-07-20; 165: 2025-08-31; 166: 2025-09-21; 169: 2025-11-03; 170: 2025-11-06; 172: 2025-10-19; 173: 2025-10-22; 176: 2025-11-07; 177: 2025-11-09; 179: 2025-10-23; 180: 2025-10-27
42 | PSS-05 | AHEJ5L | 1: WTG 222; 2: F06; 3: MSC; 4: 2025-04-15; 5: Bauer; 6: Yes; 7: 539608; 8: 2659276; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-02; 18: 2025-03-11; 20: 2025-03-21; 21: 2025-04-03; 23: Drawing release on 17Mar; 32: 2025-03-31; 33: 2025-04-01; 35: 2025-04-15; 36: 2025-04-16; 39: 2025-04-02; 40: 2025-04-02; 42: 2025-04-16; 43: 2025-04-16; 46: 2025-04-03; 47: 2025-04-04; 49: 2025-04-16; 50: 2025-04-16; 53: 2025-04-05; 54: 2025-04-06; 56: 2025-04-19; 57: 2025-04-20; 60: 2025-04-07; 61: 2025-04-17; 63: 2025-04-21; 64: 2025-05-06; 67: 2025-04-18; 68: 2025-04-19; 70: 2025-05-07; 71: 2025-05-08; 75: 2025-04-24; 76: 2025-04-27; 78: 2025-05-16; 79: 2025-09-03; 82: 2025-04-26; 83: 2025-04-26; 85: 2025-05-20; 86: 2025-05-20; 91: 2025-05-11; 92: 2025-05-21; 94: 2025-04-15; 95: 2025-05-23; 98: 2025-04-21; 99: 2025-04-28; 101: 2025-02-01; 102: 2025-02-20; 105: 2025-04-21; 106: 2025-04-28; 108: 2025-07-21; 109: 2025-08-09; 112: Varudi; 113: 2025-04-30; 114: 2025-05-07; 116: 2025-04-12; 117: 2025-04-29; 120: 2025-06-21; 121: 2025-08-01; 123: 2025-08-09; 124: 2025-08-17; 127: 2025-06-10; 128: 2025-06-18; 130: 2025-08-11; 131: 2025-09-19; 134: 2025-08-02; 135: 2025-08-09; 137: 2025-08-18; 138: 2025-08-24; 141: 2025-08-10; 142: 2025-08-12; 144: 2025-08-31; 145: 2025-09-02; 148: 2025-09-06; 149: 2025-09-07; 151: 2025-09-18; 152: 2025-09-18; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-07-20; 159: 2025-09-23; 162: 2025-06-25; 163: 2025-07-20; 165: 2025-08-31; 166: 2025-09-21; 169: 2025-09-08; 170: 2025-09-11; 172: 2025-09-19; 173: 2025-09-23; 176: 2025-09-12; 177: 2025-09-14; 179: 2025-10-14; 180: 2025-10-21
43 | PSS-05 | AHEJ5L | 1: WTG 223; 2: F08; 3: MSC; 4: 2025-05-07; 5: Bauer; 6: Yes; 7: 539798; 8: 2658290; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-02-20; 18: 2025-03-01; 20: 2025-04-03; 21: 2025-04-14; 32: 2025-03-21; 33: 2025-03-22; 35: 2025-05-17; 36: 2025-05-18; 39: 2025-03-23; 40: 2025-03-23; 42: 2025-05-19; 43: 2025-05-19; 46: 2025-03-24; 47: 2025-03-25; 49: 2025-05-19; 50: 2025-05-19; 53: 2025-03-26; 54: 2025-03-27; 56: 2025-05-21; 57: 2025-05-21; 60: 2025-03-28; 61: 2025-04-07; 63: 2025-05-23; 64: 2025-05-30; 67: 2025-04-08; 68: 2025-04-09; 70: 2025-06-01; 71: 2025-06-02; 75: 2025-04-14; 76: 2025-04-17; 78: 2025-06-08; 79: 2025-08-13; 82: 2025-04-16; 83: 2025-04-16; 85: 2025-06-07; 86: 2025-06-07; 91: 2025-04-21; 92: 2025-05-01; 94: 2025-05-19; 95: 2025-05-22; 98: 2025-04-11; 99: 2025-04-18; 101: 2025-04-12; 102: 2025-04-23; 105: 2025-04-11; 106: 2025-04-18; 108: 2025-04-25; 109: 2025-05-03; 112: Varudi; 113: 2025-04-20; 114: 2025-04-27; 116: 2025-04-25; 117: 2025-05-05; 120: 2025-05-28; 121: 2025-06-07; 123: 2025-10-10; 124: 2025-10-18; 127: 2025-05-26; 128: 2025-06-03; 130: 2025-10-11; 131: 2025-10-11; 134: 2025-06-08; 135: 2025-06-14; 137: 2025-10-16; 138: 2025-10-22; 141: 2025-06-15; 142: 2025-06-17; 144: 2025-10-22; 145: 2025-10-23; 148: 2025-06-18; 149: 2025-06-19; 151: 2025-10-19; 152: 2025-10-19; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-06-12; 159: 2025-10-19; 162: 2025-05-15; 163: 2025-06-09; 165: 2025-08-31; 166: 2025-09-21; 169: 2025-06-20; 170: 2025-06-23; 172: 2025-10-19; 173: 2025-10-22; 176: 2025-06-24; 177: 2025-06-25; 179: 2025-10-23; 180: 2025-10-27
44 | PSS-05 | AHEJ5L | 1: WTG 244; 2: F06; 3: MSC; 4: 2025-04-15; 5: Bauer; 6: Yes; 7: 540442; 8: 2659011; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-12; 18: 2025-03-21; 20: 2025-03-01; 21: 2025-03-13; 24: YES; 25: ITDC; 26: 2025-03-24; 27: 2025-04-10; 29: 2025-04-29; 30: 2025-05-24; 32: 2025-04-13; 33: 2025-04-14; 35: 2025-06-03; 36: 2025-06-04; 39: 2025-04-15; 40: 2025-04-15; 42: 2025-06-05; 43: 2025-06-05; 46: 2025-04-16; 47: 2025-04-16; 49: 2025-06-06; 50: 2025-06-06; 53: 2025-04-17; 54: 2025-04-17; 56: 2025-06-13; 57: 2025-06-13; 60: 2025-04-18; 61: 2025-04-26; 63: 2025-06-14; 64: 2025-06-21; 67: 2025-04-27; 68: 2025-04-28; 70: 2025-06-23; 71: 2025-06-23; 75: 2025-05-02; 76: 2025-05-07; 78: 2025-07-02; 79: 2025-08-12; 82: 2025-05-06; 83: 2025-05-06; 85: 2025-07-08; 86: 2025-07-08; 91: 2025-05-08; 92: 2025-05-18; 94: 2025-06-04; 95: 2025-08-07; 98: 2025-04-13; 99: 2025-04-20; 101: 2025-02-01; 102: 2025-02-15; 105: 2025-04-13; 106: 2025-04-20; 108: 2025-07-12; 109: 2025-07-26; 112: GP Project; 113: 2025-04-22; 114: 2025-04-29; 116: 2025-03-30; 117: 2025-04-11; 120: 2025-06-08; 121: 2025-06-18; 123: 2025-07-28; 124: 2025-08-07; 127: 2025-05-28; 128: 2025-06-05; 130: 2025-08-13; 131: 2025-09-19; 134: 2025-06-19; 135: 2025-06-25; 137: 2025-08-18; 138: 2025-08-29; 140: Delay due to material non available; 141: 2025-06-26; 142: 2025-06-28; 144: 2025-08-30; 145: 2025-09-02; 148: 2025-06-20; 149: 2025-06-21; 151: 2025-09-20; 152: 2025-09-20; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-06-17; 159: 2025-08-29; 162: 2025-05-15; 163: 2025-06-09; 165: 2025-08-31; 166: 2025-09-21; 169: 2025-06-22; 170: 2025-06-25; 172: 2025-09-19; 173: 2025-09-25; 176: 2025-06-29; 177: 2025-06-30; 179: 2025-10-14; 180: 2025-10-21
45 | PSS-05 | AHEJ5L | 1: WTG 245; 2: F08; 3: AB INFRA; 4: 2025-05-02; 5: Bauer; 6: Yes; 7: 540632; 8: 2658025; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-02; 18: 2025-03-11; 20: 2025-04-22; 21: 2025-04-28; 32: 2025-03-31; 33: 2025-04-01; 35: 2025-05-03; 36: 2025-05-05; 39: 2025-04-02; 40: 2025-04-02; 42: 2025-05-06; 43: 2025-05-07; 46: 2025-04-03; 47: 2025-04-04; 49: 2025-05-07; 50: 2025-05-07; 53: 2025-04-05; 54: 2025-04-06; 56: 2025-05-14; 57: 2025-05-14; 60: 2025-04-07; 61: 2025-04-17; 63: 2025-05-15; 64: 2025-05-28; 67: 2025-04-18; 68: 2025-04-19; 70: 2025-05-29; 71: 2025-05-29; 75: 2025-04-24; 76: 2025-04-27; 78: 2025-06-02; 79: 2025-08-12; 82: 2025-04-26; 83: 2025-04-26; 85: 2025-06-02; 86: 2025-06-02; 91: 2025-05-06; 92: 2025-05-16; 94: 2025-05-07; 95: 2025-06-10; 98: 2025-04-21; 99: 2025-04-28; 101: 2025-03-24; 102: 2025-05-12; 105: 2025-04-21; 106: 2025-04-28; 108: 2025-09-21; 109: 2025-09-26; 112: GP Project; 113: 2025-04-30; 114: 2025-05-07; 116: 2025-06-05; 117: 2025-06-25; 120: 2025-06-20; 121: 2025-07-10; 123: 2025-09-28; 124: 2025-10-08; 127: 2025-06-15; 128: 2025-06-23; 130: 2025-08-11; 131: 2025-10-09; 134: 2025-07-11; 135: 2025-07-18; 137: 2025-10-10; 138: 2025-10-18; 141: 2025-07-19; 142: 2025-07-21; 144: 2025-10-18; 145: 2025-10-19; 148: 2025-11-20; 149: 2025-11-21; 151: 2025-10-09; 152: 2025-10-09; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-06-13; 159: 2025-10-20; 162: 2025-06-25; 163: 2025-07-20; 165: 2025-08-31; 166: 2025-09-21; 169: 2025-11-22; 170: 2025-11-25; 172: 2025-10-13; 173: 2025-10-22; 176: 2025-11-26; 177: 2025-11-28; 179: 2025-10-23; 180: 2025-10-27
46 | PSS-05 | AHEJ5L | 1: WTG 267; 2: F06; 3: MSC; 4: 2025-04-15; 5: Bauer; 6: Yes; 7: 541284; 8: 2658707; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-22; 18: 2025-03-31; 20: 2025-03-16; 21: 2025-03-28; 24: YES; 25: Pinnacle; 26: 2025-04-03; 27: 2025-04-11; 29: 2025-04-24; 30: 2025-05-23; 32: 2025-04-14; 33: 2025-04-15; 35: 2025-06-08; 36: 2025-06-09; 39: 2025-04-16; 40: 2025-04-16; 42: 2025-06-09; 43: 2025-06-09; 46: 2025-04-17; 47: 2025-04-17; 49: 2025-06-09; 50: 2025-06-09; 53: 2025-04-18; 54: 2025-04-18; 56: 2025-06-14; 57: 2025-06-15; 60: 2025-04-19; 61: 2025-04-28; 63: 2025-06-16; 64: 2025-07-16; 67: 2025-04-29; 68: 2025-04-30; 70: 2025-07-16; 71: 2025-07-17; 75: 2025-05-05; 76: 2025-05-11; 78: 2025-07-31; 79: 2025-08-15; 82: 2025-05-10; 83: 2025-05-10; 85: 2025-08-01; 86: 2025-08-01; 91: 2025-05-12; 92: 2025-05-22; 94: 2025-06-09; 95: 2025-06-12; 98: 2025-04-24; 99: 2025-05-01; 101: 2025-02-01; 102: 2025-02-12; 105: 2025-04-24; 106: 2025-05-01; 108: 2025-07-21; 109: 2025-08-09; 112: Varudi; 113: 2025-05-03; 114: 2025-05-10; 116: 2025-04-11; 117: 2025-04-28; 120: 2025-07-16; 121: 2025-09-01; 123: 2025-08-09; 124: 2025-08-17; 127: 2025-06-01; 128: 2025-06-09; 130: 2025-08-15; 131: 2025-09-19; 134: 2025-09-02; 135: 2025-09-09; 137: 2025-08-24; 138: 2025-09-04; 141: 2025-09-10; 142: 2025-09-12; 144: 2025-09-04; 145: 2025-09-09; 148: 2025-09-07; 149: 2025-09-08; 151: 2025-09-18; 152: 2025-09-18; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-06-04; 159: 2025-09-02; 162: 2025-06-25; 163: 2025-07-20; 165: 2025-08-31; 166: 2025-09-21; 169: 2025-09-09; 170: 2025-09-12; 172: 2025-09-19; 173: 2025-09-25; 176: 2025-09-13; 177: 2025-09-15; 179: 2025-10-14; 180: 2025-10-21
47 | PSS-05 | AHEJ5L | 1: WTG 268; 2: F08; 3: MSC; 4: 2025-05-24; 5: Bauer; 6: Yes; 7: 541474; 8: 2657721; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-12; 18: 2025-03-21; 20: 2025-04-25; 21: 2025-05-02; 32: 2025-03-23; 33: 2025-03-24; 35: 2025-06-02; 36: 2025-06-03; 39: 2025-03-25; 40: 2025-03-25; 42: 2025-06-04; 43: 2025-06-04; 46: 2025-03-26; 47: 2025-03-27; 49: 2025-06-07; 50: 2025-06-07; 53: 2025-03-28; 54: 2025-03-29; 56: 2025-06-20; 57: 2025-06-22; 60: 2025-03-30; 61: 2025-04-09; 63: 2025-06-22; 64: 2025-06-25; 67: 2025-04-10; 68: 2025-04-11; 70: 2025-06-26; 71: 2025-06-26; 75: 2025-04-16; 76: 2025-04-19; 78: 2025-08-07; 79: 2026-02-22; 82: 2025-04-18; 83: 2025-04-18; 85: 2025-08-10; 86: 2025-08-10; 91: 2025-04-20; 92: 2025-04-30; 94: 2025-06-04; 95: 2025-08-29; 98: 2025-04-13; 99: 2025-04-20; 101: 2025-04-05; 102: 2025-05-16; 105: 2025-04-13; 106: 2025-04-20; 108: 2025-08-20; 109: 2025-09-12; 112: GP Project; 113: 2025-04-22; 114: 2025-04-29; 116: 2025-05-11; 117: 2025-05-26; 120: 2025-06-08; 121: 2025-06-18; 123: 2025-09-15; 124: 2025-10-01; 127: 2025-05-25; 128: 2025-06-02; 130: 2025-09-13; 131: 2025-09-30; 134: 2025-06-19; 135: 2025-06-26; 137: 2025-10-02; 138: 2025-10-12; 141: 2025-06-27; 142: 2025-06-29; 144: 2025-10-13; 145: 2025-10-14; 148: 2025-06-22; 149: 2025-06-23; 151: 2025-10-12; 152: 2025-10-12; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-06-12; 159: 2025-10-19; 162: 2025-05-15; 163: 2025-06-09; 165: 2025-08-31; 166: 2025-09-21; 169: 2025-06-24; 170: 2025-06-27; 172: 2025-10-13; 173: 2025-10-22; 176: 2025-06-30; 177: 2025-07-01; 179: 2025-10-22; 180: 2025-10-27
48 | PSS-05 | AHEJ5L | 1: WTG 291; 2: F07; 3: MSC; 4: 2025-05-07; 5: Bauer; 6: Yes; 7: 542118; 8: 2658443; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-21; 18: 2025-03-30; 20: 2025-03-28; 21: 2025-04-09; 32: 2025-04-05; 33: 2025-04-06; 35: 2025-05-09; 36: 2025-05-10; 39: 2025-04-07; 40: 2025-04-07; 42: 2025-05-11; 43: 2025-05-11; 46: 2025-04-08; 47: 2025-04-09; 49: 2025-05-11; 50: 2025-05-11; 53: 2025-04-10; 54: 2025-04-11; 56: 2025-05-14; 57: 2025-05-14; 60: 2025-04-12; 61: 2025-04-22; 63: 2025-05-16; 64: 2025-05-23; 67: 2025-04-23; 68: 2025-04-24; 70: 2025-05-25; 71: 2025-05-26; 75: 2025-04-29; 76: 2025-05-02; 78: 2025-06-02; 79: 2025-08-17; 82: 2025-05-01; 83: 2025-05-01; 85: 2025-06-04; 86: 2025-06-04; 91: 2025-05-11; 92: 2025-05-21; 94: 2025-05-12; 95: 2025-05-23; 98: 2025-04-26; 99: 2025-05-03; 101: 2025-02-01; 102: 2025-02-14; 105: 2025-04-26; 106: 2025-05-03; 108: 2025-07-10; 109: 2025-07-25; 112: GP Project; 113: 2025-05-05; 114: 2025-05-12; 116: 2025-04-23; 117: 2025-05-12; 120: 2025-06-21; 121: 2025-07-10; 123: 2025-07-28; 124: 2025-08-07; 127: 2025-06-10; 128: 2025-06-18; 130: 2025-08-13; 131: 2025-08-31; 134: 2025-07-11; 135: 2025-07-18; 137: 2025-08-17; 138: 2025-08-24; 141: 2025-07-19; 142: 2025-07-21; 144: 2025-08-30; 145: 2025-09-05; 148: 2025-09-06; 149: 2025-09-07; 151: 2025-09-18; 152: 2025-09-18; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-05-18; 159: 2025-09-04; 162: 2025-06-25; 163: 2025-07-20; 165: 2025-08-31; 166: 2025-09-21; 169: 2025-09-08; 170: 2025-09-11; 172: 2025-09-19; 173: 2025-09-23; 176: 2025-09-12; 177: 2025-09-14; 179: 2025-10-14; 180: 2025-10-21
49 | PSS-05 | AHEJ5L | 1: WTG 292; 2: F08; 3: HBG; 4: 2025-05-02; 5: Bauer; 6: Yes; 7: 542308; 8: 2657456; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-22; 18: 2025-03-31; 20: 2025-04-17; 21: 2025-04-25; 32: 2025-04-02; 33: 2025-04-03; 35: 2025-05-06; 36: 2025-05-09; 39: 2025-04-04; 40: 2025-04-04; 42: 2025-05-10; 43: 2025-05-12; 46: 2025-04-05; 47: 2025-04-06; 49: 2025-05-13; 50: 2025-05-13; 53: 2025-04-07; 54: 2025-04-08; 56: 2025-05-17; 57: 2025-05-18; 60: 2025-04-09; 61: 2025-04-19; 63: 2025-05-18; 64: 2025-05-29; 67: 2025-04-20; 68: 2025-04-21; 70: 2025-05-30; 71: 2025-05-31; 75: 2025-04-26; 76: 2025-04-29; 78: 2025-06-26; 82: 2025-04-28; 83: 2025-04-28; 85: 2025-06-06; 86: 2025-06-06; 91: 2025-05-01; 92: 2025-05-11; 94: 2025-05-12; 95: 2025-06-06; 98: 2025-04-23; 99: 2025-04-30; 101: 2025-03-25; 102: 2025-05-15; 105: 2025-04-23; 106: 2025-04-30; 108: 2025-08-21; 109: 2025-08-27; 112: GP Project; 113: 2025-05-02; 114: 2025-05-09; 116: 2025-05-08; 117: 2025-05-25; 120: 2025-07-10; 121: 2025-09-04; 123: 2025-09-17; 124: 2025-09-25; 127: 2025-06-10; 128: 2025-06-18; 130: 2025-09-15; 131: 2025-10-01; 134: 2025-09-05; 135: 2025-09-12; 137: 2025-09-26; 138: 2025-10-06; 141: 2025-09-13; 142: 2025-09-15; 144: 2025-10-07; 145: 2025-10-08; 148: 2025-09-26; 149: 2025-09-27; 151: 2025-10-13; 152: 2025-10-13; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-06-11; 159: 2025-10-19; 162: 2025-06-25; 163: 2025-07-20; 165: 2025-08-31; 166: 2025-09-21; 169: 2025-09-28; 170: 2025-10-01; 172: 2025-10-13; 173: 2025-10-14; 176: 2025-10-02; 177: 2025-10-04; 179: 2025-10-23; 180: 2025-10-27
50 | PSS-05 | AHEJ5L | 1: WTG 314; 2: F07; 3: MSC; 4: 2025-05-24; 5: Bauer; 6: Yes; 7: 542579; 8: 2660111; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-02-19; 18: 2025-02-28; 20: 2025-01-16; 21: 2025-02-03; 24: YES; 25: Pinnacle; 26: 2025-03-06; 27: 2025-03-15; 29: 2025-04-22; 30: 2025-05-09; 32: 2025-03-20; 33: 2025-03-21; 35: 2025-06-06; 36: 2025-06-07; 39: 2025-03-22; 40: 2025-03-22; 42: 2025-06-08; 43: 2025-06-08; 46: 2025-03-23; 47: 2025-03-24; 49: 2025-06-08; 50: 2025-06-08; 53: 2025-03-25; 54: 2025-03-26; 56: 2025-09-19; 57: 2025-09-21; 60: 2025-03-27; 61: 2025-04-06; 63: 2025-09-22; 64: 2025-09-30; 67: 2025-04-07; 68: 2025-04-08; 70: 2025-09-30; 71: 2025-10-01; 75: 2025-04-13; 76: 2025-04-16; 78: 2025-10-08; 79: 2025-11-18; 82: 2025-04-15; 83: 2025-04-15; 85: 2025-10-15; 86: 2025-10-15; 91: 2025-04-25; 92: 2025-05-05; 94: 2025-06-06; 95: 2025-10-13; 98: 2025-04-10; 99: 2025-04-17; 101: 2025-02-01; 102: 2025-02-18; 105: 2025-04-10; 106: 2025-04-17; 108: 2025-10-11; 109: 2025-10-15; 112: GP Project; 113: 2025-04-19; 114: 2025-04-26; 116: 2025-03-29; 117: 2025-04-08; 120: 2025-06-11; 121: 2025-06-23; 123: 2025-10-16; 124: 2025-10-24; 127: 2025-05-30; 128: 2025-06-07; 130: 2025-10-05; 131: 2025-10-17; 134: 2025-06-24; 135: 2025-07-01; 137: 2025-10-28; 138: 2025-11-07; 141: 2025-07-02; 142: 2025-07-04; 144: 2025-11-07; 145: 2025-11-09; 148: 2025-07-05; 149: 2025-07-06; 151: 2025-10-30; 152: 2025-10-30; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-05-18; 159: 2025-05-21; 162: 2025-05-15; 163: 2025-06-09; 165: 2025-08-31; 166: 2025-09-21; 169: 2025-07-07; 170: 2025-07-10; 172: 2025-10-31; 173: 2025-11-11; 176: 2025-07-11; 177: 2025-07-13; 179: 2025-11-11; 180: 2025-11-18
51 | PSS-08 | ASEJ6PL | 1: WTG 376; 2: F12; 3: SHREEJI; 4: 2025-04-15; 5: Keller; 6: Yes; 7: 542429; 8: 2673085; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-02-15; 18: 2025-02-25; 20: 2025-04-01; 21: 2025-04-11; 24: YES; 25: Bauer; 26: 2025-03-01; 27: 2025-03-08; 29: 2025-04-24; 30: 2025-05-02; 32: 2025-03-11; 33: 2025-03-12; 35: 2025-05-06; 36: 2025-05-08; 39: 2025-03-13; 40: 2025-03-14; 42: 2025-05-13; 43: 2025-05-15; 46: 2025-03-15; 47: 2025-03-16; 49: 2025-05-16; 50: 2025-05-16; 53: 2025-03-17; 54: 2025-03-18; 56: 2025-05-17; 57: 2025-05-19; 60: 2025-03-19; 61: 2025-03-29; 63: 2025-05-20; 64: 2025-05-29; 67: 2025-03-30; 68: 2025-03-31; 70: 2025-05-29; 71: 2025-05-30; 75: 2025-04-02; 76: 2025-04-06; 78: 2025-06-08; 79: 2025-08-03; 82: 2025-04-05; 83: 2025-04-05; 85: 2025-06-10; 86: 2025-06-10; 91: 2025-03-29; 92: 2025-04-08; 94: 2025-05-16; 95: 2025-07-23; 98: 2025-03-19; 99: 2025-03-26; 101: 2025-11-06; 102: 2025-11-12; 105: 2025-03-19; 106: 2025-03-26; 108: 2025-11-06; 109: 2025-11-12; 112: Odhav; 113: 2025-03-28; 114: 2025-04-04; 116: 2025-10-15; 117: 2025-11-12; 120: 2025-05-21; 121: 2025-06-01; 123: 2025-11-13; 124: 2025-11-20; 127: 2025-04-28; 128: 2025-05-06; 130: 2025-06-20; 131: 2025-11-12; 134: 2025-06-02; 135: 2025-06-09; 137: 2025-11-24; 138: 2025-11-27; 141: 2025-06-10; 142: 2025-06-12; 144: 2025-11-27; 145: 2025-11-28; 148: 2025-05-30; 149: 2025-05-31; 151: 2025-11-23; 152: 2025-11-23; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-06-05; 159: 2025-11-25; 162: 2025-04-20; 163: 2025-05-15; 165: 2025-08-31; 166: 2025-09-19; 169: 2025-05-18; 170: 2025-05-21; 172: 2025-11-25; 173: 2025-11-29; 176: 2025-06-13; 177: 2025-06-14; 179: 2025-12-03
52 | PSS-05 | AHEJ5L | 1: WTG 555; 2: F05; 3: MSC; 4: 2026-01-03; 5: Bauer; 6: Yes; 7: 536453; 8: 2659434; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-27; 18: 2025-04-06; 20: 2025-12-27; 21: 2026-01-09; 32: 2025-04-10; 33: 2025-04-11; 35: 2026-01-11; 36: 2026-01-13; 39: 2025-04-12; 40: 2025-04-12; 42: 2026-01-13; 43: 2026-01-13; 46: 2025-04-13; 47: 2025-04-14; 49: 2026-01-14; 50: 2026-01-14; 53: 2025-04-15; 54: 2025-04-16; 56: 2026-01-15; 57: 2026-01-15; 60: 2025-04-17; 61: 2025-04-27; 63: 2026-01-16; 64: 2026-01-18; 67: 2025-04-28; 68: 2025-04-29; 70: 2026-01-18; 71: 2026-01-19; 75: 2025-05-04; 76: 2025-05-07; 78: 2026-01-30; 82: 2025-05-06; 83: 2025-05-06; 85: 2026-01-30; 86: 2026-01-30; 91: 2025-05-16; 92: 2025-05-26; 94: 2026-01-13; 95: 2026-01-20; 98: 2025-05-01; 99: 2025-05-08; 101: 2025-02-26; 102: Done; 105: 2025-05-01; 106: 2025-05-08; 108: 2026-01-26; 109: 2026-01-30; 112: GP Project(Reuse); 113: 2025-05-10; 114: 2025-05-17; 116: 2026-01-15; 117: 2026-01-30; 120: 2025-07-07; 121: 2025-08-29; 123: 2026-01-31; 124: 2026-02-13; 127: 2025-06-15; 128: 2025-06-23; 130: 2026-02-08; 131: 2026-02-17; 134: 2025-08-30; 135: 2025-09-06; 137: 2026-02-14; 138: 2026-02-18; 141: 2025-09-07; 142: 2025-09-09; 144: 2026-02-18; 145: 2026-02-20; 148: 2025-10-01; 149: 2025-10-02; 151: 2026-02-17; 152: 2026-02-17; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-05-30; 159: 2025-11-25; 162: 2025-06-25; 163: 2025-07-20; 165: 2025-10-15; 166: 2025-11-08; 169: 2025-10-03; 170: 2025-10-06; 172: 2026-02-19; 173: 2026-02-21; 176: 2025-10-07; 177: 2025-10-09; 179: 2026-02-22; 180: 2026-02-26
53 | PSS-11 | AGE25CL | 1: WTG 430; 2: F03; 3: SHREERAM; 4: 2025-09-22; 5: Keller; 6: Yes; 7: 544675; 8: 2669557; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-16; 18: 2025-04-25; 20: 2025-08-23; 21: 2025-09-02; 32: 2025-05-12; 33: 2025-05-13; 35: 2025-10-05; 36: 2025-10-09; 39: 2025-05-14; 40: 2025-05-14; 42: 2025-10-11; 43: 2025-10-14; 46: 2025-05-15; 47: 2025-05-16; 49: 2025-10-15; 50: 2025-10-15; 53: 2025-05-17; 54: 2025-05-18; 56: 2025-10-17; 57: 2025-10-18; 60: 2025-05-19; 61: 2025-05-29; 63: 2025-10-24; 64: 2025-11-03; 67: 2025-05-30; 68: 2025-05-31; 70: 2025-11-05; 71: 2025-11-05; 75: 2025-06-05; 76: 2025-06-08; 78: 2025-11-13; 79: 2026-01-05; 82: 2025-06-07; 83: 2025-06-07; 85: 2025-11-14; 86: 2025-11-14; 91: 2025-06-02; 92: 2025-06-12; 94: 2025-10-09; 95: 2025-12-25; 98: 2025-06-02; 99: 2025-06-09; 101: 2025-11-23; 102: Done; 105: 2025-06-02; 106: 2025-06-09; 108: 2025-11-22; 109: 2026-01-09; 112: GP Project; 113: 2025-06-04; 114: 2025-06-11; 116: 2025-11-03; 117: 2026-01-05; 120: 2025-11-08; 121: 2025-11-18; 123: 2026-01-08; 124: 2026-01-20; 127: 2025-11-03; 128: 2025-11-11; 130: 2025-12-26; 131: 2026-01-05; 134: 2025-11-19; 135: 2025-11-26; 137: 2026-01-22; 138: 2026-01-26; 141: 2025-11-27; 142: 2025-11-29; 144: 2026-01-27; 145: 2026-01-28; 148: 2025-12-11; 149: 2025-12-12; 151: 2026-12-31; 152: 2025-12-31; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-11-10; 159: 2026-01-30; 162: 2025-10-25; 163: 2025-11-19; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-12-13; 170: 2025-12-16; 172: 2026-01-24; 173: 2026-01-31; 176: 2025-12-17; 177: 2025-12-19; 179: 2026-02-08; 180: 2026-02-09
54 | PSS-05 | AHEJ5L | 1: WTG 552; 2: F01; 3: DNC; 4: 2025-02-28; 5: Bauer; 6: Yes; 7: 535251; 8: 2661705; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-25; 18: 2025-04-03; 20: 2025-02-15; 21: 2025-02-26; 32: 2025-04-08; 33: 2025-04-09; 35: 2025-02-28; 36: 2025-03-02; 39: 2025-04-10; 40: 2025-04-10; 42: 2025-03-02; 43: 2025-03-03; 46: 2025-04-11; 47: 2025-04-12; 49: 2025-03-04; 50: 2025-03-04; 53: 2025-04-13; 54: 2025-04-14; 56: 2025-03-05; 57: 2025-03-05; 60: 2025-04-15; 61: 2025-04-25; 63: 2025-03-06; 64: 2025-03-19; 67: 2025-04-26; 68: 2025-04-27; 70: 2025-03-19; 71: 2025-03-20; 75: 2025-05-02; 76: 2025-05-05; 78: 2025-03-29; 79: 2026-01-30; 82: 2025-05-04; 83: 2025-05-04; 85: 2025-03-30; 86: 2025-03-30; 91: 2025-05-19; 92: 2025-05-29; 94: 2025-12-29; 95: 2025-12-31; 98: 2025-04-29; 99: 2025-05-06; 101: 2025-02-25; 102: Done; 105: 2025-04-29; 106: 2025-05-06; 108: 2026-01-02; 109: 2026-01-05; 112: GP Project; 113: 2025-05-08; 114: 2025-05-15; 116: 2025-12-28; 117: 2026-01-05; 120: 2025-06-28; 121: 2025-08-01; 123: 2026-01-10; 124: 2026-01-17; 127: 2025-06-18; 128: 2025-06-26; 130: 2026-01-07; 131: 2026-01-12; 134: 2025-08-02; 135: 2025-08-09; 137: 2026-01-20; 138: 2026-01-22; 141: 2025-08-10; 142: 2025-08-12; 144: 2026-01-23; 145: 2026-01-24; 148: 2025-10-04; 149: 2025-10-05; 151: 2026-01-17; 152: 2026-01-17; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-06-14; 159: 2026-02-11; 162: 2025-06-25; 163: 2025-07-20; 165: 2025-10-15; 166: 2025-11-08; 169: 2025-10-06; 170: 2025-10-09; 172: 2026-02-18; 173: 2026-02-21; 176: 2025-10-10; 177: 2025-10-12; 179: 2026-02-22; 180: 2026-02-26
55 | PSS-05 | AHEJ5L | 1: WTG 551; 2: F01; 3: MSC; 4: 2025-12-28; 5: Bauer; 6: Yes; 7: 534218; 8: 2662969; 12: Done; 13: Done; 15: 199; 16: 199; 17: 2025-03-04; 18: 2025-03-14; 20: 2025-01-27; 21: 2025-02-01; 32: 2025-04-03; 33: 2025-04-04; 35: 2025-02-14; 36: 2025-03-01; 38: Excavator breakdwon; 39: 2025-04-05; 40: 2025-04-05; 42: 2025-03-01; 43: 2025-03-03; 46: 2025-04-06; 47: 2025-04-07; 49: 2025-03-16; 50: 2025-03-16; 52: Approch road not available due to that delayed in PCC; 53: 2025-04-08; 54: 2025-04-09; 56: 2025-03-19; 57: 2025-03-20; 60: 2025-04-10; 61: 2025-04-20; 63: 2025-03-21; 64: 2026-01-14; 67: 2025-04-21; 68: 2025-04-22; 70: 2026-01-14; 71: 2026-01-15; 75: 2025-04-27; 76: 2025-04-30; 78: 2026-01-17; 82: 2025-04-29; 83: 2025-04-29; 85: 2026-01-18; 86: 2026-01-18; 91: 2025-05-09; 92: 2025-05-19; 94: 2026-02-01; 95: 2026-02-03; 98: 2025-04-24; 99: 2025-05-01; 101: Done; 102: Done; 105: 2025-04-24; 106: 2025-05-01; 108: 2026-01-26; 109: 2026-01-30; 112: GP Project; 113: 2025-05-03; 114: 2025-05-10; 116: 2026-01-22; 117: 2026-01-27; 120: 2025-06-10; 121: 2025-06-20; 123: 2026-01-31; 124: 2026-02-12; 127: 2025-06-18; 128: 2025-06-26; 130: 2026-02-15; 131: 2026-02-17; 134: 2025-06-21; 135: 2025-06-28; 137: 2026-02-13; 138: 2026-02-18; 141: 2025-06-29; 142: 2025-07-01; 144: 2026-02-18; 145: 2026-02-20; 148: 2025-07-26; 149: 2025-07-27; 151: 2026-02-17; 152: 2026-02-17; 155: 2025-05-15; 156: 2025-06-07; 158: 2026-02-05; 159: 2026-02-18; 162: 2025-06-25; 163: 2025-07-20; 165: 2025-10-15; 166: 2025-11-08; 169: 2025-07-28; 170: 2025-07-31; 172: 2026-02-18; 173: 2026-02-21; 176: 2025-08-01; 177: 2025-08-03; 179: 2026-02-22; 180: 2026-02-26; 184: PSB INFRA Work to be done Anchore cage
56 | PSS-05 | AHEJ5L | 1: WTG 553; 2: F01; 3: MSC; 4: 2025-10-13; 5: Bauer; 6: Yes; 7: 535427; 8: 2660700; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-04; 18: 2025-03-13; 20: 2025-03-19; 21: 2025-03-28; 24: YES; 25: Bauer; 26: 2025-03-15; 27: 2025-03-20; 29: 2026-12-22; 30: 2026-01-04; 32: 2025-03-22; 33: 2025-03-23; 35: 2026-01-08; 36: 2026-01-09; 39: 2025-03-24; 40: 2025-03-24; 42: 2026-01-09; 43: 2026-01-10; 46: 2025-03-25; 47: 2025-03-25; 49: 2026-01-11; 50: 2026-01-11; 53: 2025-03-26; 54: 2025-03-26; 56: 2026-01-12; 57: 2026-01-13; 60: 2025-03-27; 61: 2025-04-03; 63: 2026-01-15; 64: 2026-01-18; 67: 2025-04-04; 68: 2025-04-05; 70: 2026-01-25; 71: 2026-01-26; 75: 2025-04-10; 76: 2025-04-13; 78: 2026-01-30; 82: 2025-04-12; 83: 2025-04-12; 85: 2026-01-30; 86: 2026-01-30; 91: 2025-04-22; 92: 2025-05-02; 94: 2026-01-10; 95: 2026-02-03; 98: 2025-04-07; 99: 2025-04-14; 101: 2025-03-05; 102: Done; 105: 2025-04-07; 106: 2025-04-14; 108: 2026-01-27; 109: 2026-02-02; 112: GP Project(Reuse); 113: 2025-04-09; 114: 2025-04-16; 116: 2026-01-15; 117: 2026-01-30; 120: 2025-06-18; 121: 2025-06-29; 123: 2026-02-09; 124: 2026-02-14; 127: 2025-06-01; 128: 2025-06-09; 130: 2026-02-07; 131: 2026-02-17; 134: 2025-06-30; 135: 2025-07-07; 137: 2026-02-16; 138: 2026-02-19; 141: 2025-07-08; 142: 2025-07-10; 144: 2026-02-19; 145: 2026-02-21; 148: 2025-08-08; 149: 2025-08-09; 151: 2026-02-18; 152: 2026-02-18; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-08-28; 159: 2026-02-12; 162: 2025-06-25; 163: 2025-07-20; 165: 2025-10-15; 166: 2025-11-08; 169: 2025-08-10; 170: 2025-08-13; 172: 2026-02-19; 173: 2026-02-21; 176: 2025-08-14; 177: 2025-08-15; 179: 2026-02-22; 180: 2026-02-26
57 | PSS-11 | AGE25CL | 1: WTG 329; 2: F01; 3: DNC; 4: 2025-11-25; 5: Menard; 6: Yes; 7: 541325; 8: 2670695; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-11; 18: 2025-03-22; 20: 2025-02-24; 21: 2025-06-04; 23: Slow Progress and after achieved 120 no. of stone coumn ITDC move to the WTG 473 because of rig not penetrate inside the soil; 24: YES; 25: Bauer; 29: 2025-11-17; 30: 2025-11-22; 32: 2025-04-10; 33: 2025-04-11; 35: 2025-11-26; 36: 2025-11-29; 39: 2025-04-12; 40: 2025-04-12; 42: 2025-11-29; 43: 2025-11-30; 46: 2025-04-13; 47: 2025-04-14; 49: 2025-12-02; 50: 2025-12-02; 53: 2025-04-15; 54: 2025-04-16; 56: 2025-12-02; 57: 2025-12-03; 60: 2025-04-17; 61: 2025-04-27; 63: 2025-12-05; 64: 2025-12-11; 67: 2025-04-28; 68: 2025-04-29; 70: 2025-12-11; 71: 2025-12-12; 75: 2025-05-04; 76: 2025-05-07; 78: 2025-12-15; 79: 2026-02-05; 82: 2025-05-06; 83: 2025-05-06; 85: 2025-12-16; 86: 2025-12-16; 91: 2025-04-21; 92: 2025-05-01; 94: 2025-11-29; 95: 2025-12-04; 98: 2025-05-01; 99: 2025-05-08; 101: Done; 102: Done; 105: 2025-05-01; 106: 2025-05-08; 108: 2026-01-01; 109: 2026-01-04; 112: Odhav; 113: 2025-05-03; 114: 2025-05-10; 116: 2026-01-01; 117: 2026-01-04; 120: 2025-06-25; 121: 2025-09-01; 123: 2026-01-08; 124: 2026-01-16; 127: 2025-05-31; 128: 2025-06-08; 130: 2025-12-06; 131: 2025-12-26; 134: 2025-09-02; 135: 2025-09-09; 137: 2026-01-20; 138: 2026-01-24; 141: 2025-09-10; 142: 2025-09-12; 144: 2026-01-25; 145: 2026-01-27; 148: 2025-10-30; 149: 2025-10-31; 151: 2025-12-26; 152: 2025-12-26; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-11-19; 159: 2026-01-29; 162: 2025-09-25; 163: 2025-10-20; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-11-01; 170: 2025-11-04; 172: 2026-01-20; 173: 2026-01-31; 176: 2025-11-04; 177: 2025-11-05; 179: 2026-02-07; 180: 2026-02-09; 184: 1) ITDC - 120 nos, Menard continue after that
58 | PSS-11 | AGE25CL | 1: WTG 353; 2: F01; 3: SHREEJI; 4: 2025-05-24; 5: Menard; 6: Yes; 7: 541976; 8: 2671377; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-23; 18: 2025-04-01; 20: 2025-04-08; 21: 2025-05-03; 32: 2025-05-01; 33: 2025-05-02; 35: 2025-05-25; 36: 2025-05-28; 39: 2025-05-03; 40: 2025-05-03; 42: 2025-05-29; 43: 2025-05-30; 46: 2025-05-04; 47: 2025-05-05; 49: 2025-05-31; 50: 2025-05-31; 53: 2025-05-06; 54: 2025-05-07; 56: 2025-06-03; 57: 2025-06-03; 60: 2025-05-08; 61: 2025-05-18; 63: 2025-06-04; 64: 2025-06-13; 67: 2025-05-19; 68: 2025-05-20; 70: 2025-06-14; 71: 2025-06-14; 75: 2025-05-25; 76: 2025-05-28; 78: 2025-11-10; 79: 2026-01-01; 82: 2025-05-27; 83: 2025-05-27; 85: 2025-11-11; 86: 2025-11-11; 91: 2025-05-12; 92: 2025-05-22; 94: 2025-11-11; 95: 2025-11-18; 98: 2025-05-22; 99: 2025-05-29; 101: 2025-11-08; 102: 2025-11-09; 105: 2025-05-22; 106: 2025-05-29; 108: 2025-11-06; 109: 2025-11-08; 112: Odhav; 113: 2025-05-24; 114: 2025-05-31; 116: 2025-10-29; 117: 2025-11-08; 120: 2025-09-10; 121: 2025-10-01; 123: 2025-11-09; 124: 2025-11-20; 127: 2025-10-05; 128: 2025-10-13; 130: 2025-11-23; 131: 2025-12-02; 134: 2025-10-02; 135: 2025-10-09; 137: 2025-11-24; 138: 2025-11-28; 141: 2025-10-10; 142: 2025-10-12; 144: 2025-11-29; 145: 2025-11-30; 148: 2025-10-30; 149: 2025-10-31; 151: 2025-12-02; 152: 2025-12-02; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-11-19; 159: 2025-12-27; 162: 2025-09-25; 163: 2025-10-20; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-11-01; 170: 2025-11-04; 172: 2026-01-08; 173: 2026-01-31; 176: 2025-11-06; 177: 2025-11-07; 179: 2026-02-06; 180: 2026-02-09
59 | PSS-11 | AGE25CL | 1: WTG 354; 2: F01; 3: SHREERAM; 4: 2025-11-21; 5: Bauer; 6: Yes; 7: 542166; 8: 2670391; 12: Done; 13: Done; 15: 199; 16: 199; 17: 2025-03-23; 18: 2025-04-01; 20: 2024-04-26; 21: 2024-05-08; 24: YES; 25: Bauer; 26: 2025-04-15; 27: 2025-04-23; 29: 2025-11-06; 30: 2025-11-14; 32: 2025-05-03; 33: 2025-05-04; 35: 2025-11-22; 36: 2025-11-26; 39: 2025-05-05; 40: 2025-05-05; 42: 2025-11-26; 43: 2025-11-28; 46: 2025-05-06; 47: 2025-05-07; 49: 2025-11-29; 50: 2025-11-29; 53: 2025-05-08; 54: 2025-05-09; 56: 2025-12-01; 57: 2025-12-03; 60: 2025-05-10; 61: 2025-05-20; 63: 2025-12-08; 64: 2025-12-16; 67: 2025-05-21; 68: 2025-05-22; 70: 2025-12-17; 71: 2025-12-18; 75: 2025-05-27; 76: 2025-05-30; 78: 2025-12-23; 79: 2026-02-06; 82: 2025-05-29; 83: 2025-05-29; 85: 2025-12-24; 86: 2025-12-24; 91: 2025-05-14; 92: 2025-05-24; 94: 2025-11-25; 95: 2025-12-02; 98: 2025-05-24; 99: 2025-05-31; 101: 2025-02-05; 102: 2025-02-14; 105: 2025-05-24; 106: 2025-05-31; 108: 2025-12-26; 109: 2025-12-29; 112: Odhav(Reuse); 113: 2025-05-26; 114: 2025-06-02; 116: 2025-02-16; 117: 2025-03-06; 120: 2025-09-11; 121: 2025-10-06; 123: 2025-12-29; 124: 2026-01-06; 127: 2025-10-10; 128: 2025-10-18; 130: 2025-12-05; 131: 2026-01-09; 134: 2025-10-07; 135: 2025-10-14; 137: 2026-01-09; 138: 2026-01-13; 141: 2025-10-15; 142: 2025-10-17; 144: 2026-01-13; 145: 2026-01-16; 148: 2025-11-03; 149: 2025-11-04; 151: 2025-12-27; 152: 2025-12-27; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-11-10; 159: 2026-01-16; 162: 2025-09-25; 163: 2025-10-20; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-11-05; 170: 2025-11-08; 172: 2026-01-08; 173: 2026-01-31; 176: 2025-11-08; 177: 2025-11-09; 179: 2026-02-06; 180: 2026-02-09
60 | PSS-14 | AGE25CL | 1: WTG 373; 2: F13; 3: SHREEJI; 4: 2025-10-13; 5: Bauer; 6: Yes; 7: 541858; 8: 2676044; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-13; 18: 2025-03-24; 20: 2025-06-17; 21: 2025-06-30; 32: 2025-04-14; 33: 2025-04-15; 35: 2025-10-29; 36: 2025-10-31; 39: 2025-04-16; 40: 2025-04-16; 42: 2025-11-01; 43: 2025-11-01; 46: 2025-04-17; 47: 2025-04-18; 49: 2025-11-02; 50: 2025-11-02; 53: 2025-04-19; 54: 2025-04-20; 56: 2025-11-04; 57: 2025-11-06; 60: 2025-04-21; 61: 2025-05-01; 63: 2025-11-08; 64: 2025-11-17; 67: 2025-05-02; 68: 2025-05-03; 70: 2025-11-19; 71: 2025-11-20; 75: 2025-05-08; 76: 2025-05-11; 78: 2025-11-24; 82: 2025-05-10; 83: 2025-05-10; 85: 2025-11-24; 86: 2025-11-24; 91: 2025-04-25; 92: 2025-05-05; 94: 2025-10-31; 95: 2026-01-16; 98: 2025-05-05; 99: 2025-05-12; 101: Done; 102: Done; 105: 2025-05-05; 106: 2025-05-12; 108: 2026-01-20; 109: 2026-01-25; 112: Vaibhav; 113: 2025-05-07; 114: 2025-05-14; 116: 2026-01-15; 117: 2026-01-24; 120: 2025-07-15; 121: 2025-09-08; 123: 2026-01-26; 124: 2026-02-23; 127: 2025-10-03; 128: 2025-10-11; 130: 2026-01-21; 134: 2025-09-09; 135: 2025-09-16; 137: 2026-02-26; 141: 2025-09-17; 142: 2025-09-19; 148: 2025-10-30; 149: 2025-10-31; 155: 2025-05-15; 156: 2025-06-07; 158: 2026-02-01; 162: 2025-09-25; 163: 2025-10-20; 165: 2026-01-31; 166: 2026-02-15; 169: 2025-11-01; 170: 2025-11-04; 176: 2025-11-04; 177: 2025-11-05
61 | PSS-12 | AGE26AL | 1: WTG 377; 2: F01; 3: SHREEJI; 4: 2025-12-29; 5: Bauer; 6: Yes; 7: 542619; 8: 2672099; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-22; 18: 2025-04-01; 20: 2025-08-14; 21: 2025-11-24; 24: YES; 25: Bauer; 29: 2025-12-12; 30: 2025-12-28; 32: 2025-04-30; 33: 2025-05-01; 35: 2025-12-31; 36: 2026-01-04; 39: 2025-05-02; 40: 2025-05-02; 42: 2026-01-09; 43: 2026-01-10; 46: 2025-05-03; 47: 2025-05-04; 49: 2026-01-11; 50: 2026-01-11; 53: 2025-05-05; 54: 2025-05-06; 56: 2026-01-12; 57: 2026-01-13; 60: 2025-05-07; 61: 2025-05-17; 63: 2026-01-13; 64: 2026-01-16; 67: 2025-05-18; 68: 2025-05-19; 70: 2026-01-22; 71: 2026-01-23; 74: Delay due to concrete not availabel; 75: 2025-05-24; 76: 2025-05-27; 78: 2026-01-30; 82: 2025-05-26; 83: 2025-05-26; 85: 2026-01-30; 86: 2026-01-30; 91: 2025-04-30; 92: 2025-05-10; 94: 2026-01-10; 95: 2026-01-16; 98: 2025-05-21; 99: 2025-05-28; 101: Done; 102: Done; 105: 2025-05-21; 106: 2025-05-28; 108: 2026-02-01; 109: 2026-02-03; 112: GP Project; 113: 2025-05-23; 114: 2025-05-30; 116: 2025-12-11; 117: 2025-12-22; 120: 2025-07-25; 121: 2025-10-03; 123: 2026-02-15; 124: 2026-02-22; 127: 2025-10-08; 128: 2025-10-16; 130: 2026-01-24; 131: 2026-02-12; 134: 2025-10-04; 135: 2025-10-11; 137: 2026-02-25; 141: 2025-10-12; 142: 2025-10-14; 148: 2025-11-01; 149: 2025-11-02; 151: 2026-02-04; 152: 2026-02-04; 155: 2025-09-20; 156: 2025-10-10; 158: 2025-12-22; 159: 2026-01-31; 162: 2025-09-25; 163: 2025-10-20; 165: 2025-11-30; 166: 2025-12-19; 169: 2025-11-03; 170: 2025-11-06; 172: 2026-02-23; 176: 2025-11-08; 177: 2025-11-09; 184: 133 stone columns completed by ITDC Thane Tack Bauer(120 nos) continues the work. Date:-20/11/25
62 | PSS-11 | AGE25CL | 1: WTG 481; 2: F04; 3: SHREEJI; 4: 2025-10-13; 5: Saritha; 6: Yes; 7: 546541; 8: 2668002; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-16; 18: 2025-04-25; 20: 2025-06-21; 21: 2025-08-25; 24: YES; 25: Keller; 29: 2025-10-22; 30: 2025-10-30; 32: 2025-05-08; 33: 2025-05-09; 35: 2025-11-25; 36: 2025-11-28; 39: 2025-05-10; 40: 2025-05-10; 42: 2025-11-30; 43: 2025-12-03; 46: 2025-05-11; 47: 2025-05-12; 49: 2025-12-03; 50: 2025-12-03; 53: 2025-05-13; 54: 2025-05-14; 56: 2025-12-04; 57: 2025-12-05; 60: 2025-05-15; 61: 2025-05-25; 63: 2025-12-05; 64: 2025-12-11; 67: 2025-05-26; 68: 2025-05-27; 70: 2025-12-12; 71: 2025-12-12; 75: 2025-06-01; 76: 2025-06-04; 78: 2025-12-16; 82: 2025-06-03; 83: 2025-06-03; 85: 2025-12-16; 86: 2025-12-16; 91: 2025-05-19; 92: 2025-05-29; 94: 2025-11-26; 95: 2025-12-23; 98: 2025-05-29; 99: 2025-06-05; 101: 2025-03-22; 102: 2025-04-28; 105: 2025-05-29; 106: 2025-06-05; 108: 2025-12-18; 109: 2025-12-24; 112: SS Jadeja; 113: 2025-05-31; 114: 2025-06-07; 116: 2025-11-04; 117: 2025-11-18; 120: 2025-11-14; 121: 2025-11-24; 123: 2025-12-22; 124: 2025-12-31; 127: 2025-11-11; 128: 2025-11-19; 130: 2025-12-19; 131: 2026-01-04; 134: 2025-11-25; 135: 2025-12-02; 137: 2026-01-06; 138: 2026-01-12; 141: 2025-12-03; 142: 2025-12-05; 144: 2026-01-12; 145: 2026-01-14; 148: 2025-12-19; 149: 2025-12-20; 151: 2026-01-10; 152: 2026-01-10; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-11-19; 159: 2026-02-01; 162: 2025-11-15; 163: 2025-12-10; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-12-21; 170: 2025-12-24; 172: 2026-01-24; 173: 2026-02-03; 176: 2025-12-25; 177: 2025-12-27; 179: 2026-02-08; 180: 2026-02-10
63 | PSS-05 | AHEJ5L | 1: WTG 154; 2: F02; 3: MSC; 4: 2025-04-15; 5: Bauer; 6: Yes; 7: 536879; 8: 2661112; 12: Done; 13: Done; 15: 369; 16: 253; 17: 2025-03-20; 18: 2025-03-29; 20: 2025-03-29; 21: 2025-04-09; 24: YES; 25: ITDC; 26: 2025-03-31; 27: 2025-04-08; 29: 2025-05-26; 30: 2025-06-01; 32: 2025-04-12; 33: 2025-04-13; 35: 2025-10-30; 36: 2025-11-01; 39: 2025-04-13; 40: 2025-04-13; 42: 2025-11-02; 43: 2025-11-02; 46: 2025-04-14; 47: 2025-04-14; 49: 2025-11-02; 50: 2025-11-02; 53: 2025-04-15; 54: 2025-04-16; 56: 2025-11-07; 57: 2025-11-08; 60: 2025-04-17; 61: 2025-04-27; 63: 2025-11-09; 64: 2025-11-13; 67: 2025-04-28; 68: 2025-04-29; 70: 2025-11-13; 71: 2025-11-13; 75: 2025-05-04; 76: 2025-05-07; 78: 2025-11-17; 79: 2025-12-14; 82: 2025-05-06; 83: 2025-05-06; 85: 2025-11-17; 86: 2025-11-17; 91: 2025-04-13; 92: 2025-04-23; 94: 2025-11-08; 95: 2025-11-24; 98: 2025-05-01; 99: 2025-05-08; 101: 2025-11-17; 102: 2025-11-19; 105: 2025-05-01; 106: 2025-05-08; 108: 2025-11-17; 109: 2025-11-19; 112: Varudi; 113: 2025-05-10; 114: 2025-05-17; 116: 2025-11-06; 117: 2025-11-19; 120: 2025-05-27; 121: 2025-06-06; 123: 2025-11-19; 124: 2025-11-26; 127: 2025-06-02; 128: 2025-06-10; 130: 2025-11-25; 131: 2025-11-28; 134: 2025-06-07; 135: 2025-06-14; 137: 2025-11-29; 138: 2025-12-03; 141: 2025-06-15; 142: 2025-06-17; 144: 2025-12-03; 145: 2025-12-05; 148: 2025-06-20; 149: 2025-06-21; 151: 2025-11-30; 152: 2025-11-30; 155: 2025-04-01; 156: 2025-05-07; 158: 2025-06-17; 159: 2025-11-26; 162: 2025-05-15; 163: 2025-06-09; 165: 2025-10-15; 166: 2025-11-08; 169: 2025-06-22; 170: 2025-06-25; 172: 2025-12-07; 173: 2025-12-15; 176: 2025-06-26; 177: 2025-06-28; 179: 2025-12-15; 180: 2025-12-24; 184: Three time PLT 1.ITDC 2.Pinnacle 3.Bauer
64 | PSS-11 | AGE25CL | 1: WTG 328; 2: F01; 3: SHREEJI; 4: 2025-07-12; 5: Menard; 6: Yes; 7: 541135; 8: 2671682; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-11; 18: 2025-03-22; 20: 2025-06-06; 21: 2025-06-27; 32: 2025-05-02; 33: 2025-05-03; 35: 2025-07-30; 36: 2025-08-03; 39: 2025-05-04; 40: 2025-05-04; 42: 2025-08-04; 43: 2025-08-04; 46: 2025-05-05; 47: 2025-05-06; 49: 2025-08-05; 50: 2025-08-05; 53: 2025-05-07; 54: 2025-05-08; 56: 2025-08-06; 57: 2025-08-06; 60: 2025-05-09; 61: 2025-05-19; 63: 2025-08-07; 64: 2025-08-13; 67: 2025-05-20; 68: 2025-05-21; 70: 2025-08-14; 71: 2025-08-15; 75: 2025-05-26; 76: 2025-05-29; 78: 2025-11-01; 82: 2025-05-28; 83: 2025-05-28; 85: 2025-08-26; 86: 2025-08-26; 91: 2025-05-14; 92: 2025-05-24; 94: 2025-11-26; 95: 2025-12-01; 98: 2025-05-23; 99: 2025-05-30; 101: 2025-11-12; 102: 2025-11-14; 105: 2025-05-23; 106: 2025-05-30; 108: 2025-11-09; 109: 2025-11-14; 112: Odhav; 113: 2025-05-25; 114: 2025-06-01; 116: 2025-10-26; 117: 2025-11-09; 120: 2025-07-23; 121: 2025-10-05; 123: 2025-11-15; 124: 2025-11-24; 127: 2025-10-14; 128: 2025-10-22; 130: 2025-12-03; 131: 2025-12-08; 134: 2025-10-06; 135: 2025-10-13; 137: 2025-11-27; 138: 2025-12-01; 141: 2025-10-14; 142: 2025-10-16; 144: 2025-12-01; 145: 2025-12-02; 148: 2025-11-05; 149: 2025-11-06; 151: 2025-12-18; 152: 2025-12-18; 155: 2025-09-20; 156: 2025-10-10; 158: 2025-11-23; 159: 2025-12-28; 162: 2025-09-25; 163: 2025-10-20; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-11-07; 170: 2025-11-10; 172: 2026-01-08; 173: 2026-01-31; 176: 2025-11-10; 177: 2025-11-11; 179: 2026-02-06; 180: 2026-02-09
65 | PSS-14 | AGE25CL | 1: WTG 399; 2: F14; 3: BHAVANI; 4: 2025-10-19; 5: Bauer; 6: Yes; 7: 542890; 8: 2674753; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-15; 18: 2025-03-25; 20: 2025-05-28; 21: 2025-06-05; 32: 2025-04-21; 33: 2025-04-22; 35: 2025-10-28; 36: 2025-11-11; 39: 2025-04-23; 40: 2025-04-23; 42: 2025-11-14; 43: 2025-11-17; 46: 2025-04-24; 47: 2025-04-25; 49: 2025-11-17; 50: 2025-11-18; 53: 2025-04-26; 54: 2025-04-27; 56: 2025-11-18; 57: 2025-11-18; 60: 2025-04-28; 61: 2025-05-08; 63: 2025-11-19; 64: 2025-11-24; 67: 2025-05-09; 68: 2025-05-10; 70: 2025-11-26; 71: 2025-11-26; 75: 2025-05-15; 76: 2025-05-18; 78: 2025-12-01; 79: 2025-12-02; 82: 2025-05-17; 83: 2025-05-17; 85: 2025-12-04; 86: 2025-12-04; 91: 2025-05-12; 92: 2025-05-22; 94: 2025-11-17; 95: 2026-01-06; 98: 2025-05-12; 99: 2025-05-19; 101: 2025-12-07; 102: 2025-12-14; 105: 2025-05-12; 106: 2025-05-19; 108: 2025-12-08; 109: 2025-12-20; 112: Odhav; 113: 2025-05-14; 114: 2025-05-21; 116: 2025-12-06; 117: 2025-12-13; 120: 2025-08-20; 121: 2025-10-09; 123: 2026-01-06; 124: 2026-01-17; 127: 2025-10-15; 128: 2025-10-23; 130: 2026-02-02; 131: 2026-02-19; 134: 2025-10-10; 135: 2025-10-17; 137: 2026-01-22; 138: 2026-01-28; 141: 2025-10-18; 142: 2025-10-20; 144: 2026-01-29; 145: 2026-01-31; 148: 2025-11-03; 149: 2025-11-04; 155: 2025-09-20; 156: 2025-10-10; 158: 2026-01-02; 162: 2025-09-25; 163: 2025-10-20; 165: 2026-01-31; 166: 2026-02-15; 169: 2025-11-05; 170: 2025-11-08; 176: 2025-11-10; 177: 2025-11-11
66 | PSS-12 | AGE26AL | 1: WTG 401; 2: F01; 3: MSC; 4: 2025-09-23; 5: Keller; 6: Yes; 7: 543270; 8: 2672781; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-02; 18: 2025-04-11; 20: 2025-07-05; 21: 2025-07-15; 32: 2025-04-22; 33: 2025-04-23; 35: 2025-09-25; 36: 2025-09-30; 39: 2025-04-24; 40: 2025-04-24; 42: 2025-10-01; 43: 2025-10-02; 46: 2025-04-25; 47: 2025-04-26; 49: 2025-10-03; 50: 2025-10-03; 53: 2025-04-27; 54: 2025-04-28; 56: 2025-10-13; 57: 2025-10-14; 60: 2025-04-29; 61: 2025-05-09; 63: 2025-10-18; 64: 2025-10-24; 67: 2025-05-10; 68: 2025-05-11; 70: 2025-10-26; 71: 2025-10-26; 75: 2025-05-16; 76: 2025-05-19; 78: 2025-12-16; 82: 2025-05-18; 83: 2025-05-18; 85: 2025-12-17; 86: 2025-12-17; 91: 2025-05-13; 92: 2025-05-23; 94: 2025-10-01; 95: 2026-01-10; 98: 2025-05-13; 99: 2025-05-20; 101: Done; 102: Done; 105: 2025-05-13; 106: 2025-05-20; 108: 2025-12-17; 109: 2025-12-25; 112: Vaibhav; 113: 2025-05-15; 114: 2025-05-22; 116: 2025-12-04; 117: 2025-12-24; 120: 2025-09-08; 121: 2025-10-13; 123: 2025-12-26; 124: 2026-01-05; 127: 2025-10-19; 128: 2025-10-27; 130: 2026-01-11; 131: 2026-01-12; 134: 2025-10-14; 135: 2025-10-21; 137: 2026-01-07; 138: 2026-01-12; 141: 2025-10-22; 142: 2025-10-24; 144: 2026-01-13; 145: 2026-01-15; 148: 2025-11-03; 149: 2025-11-04; 151: 2026-01-17; 152: 2026-01-17; 155: 2025-09-20; 156: 2025-10-10; 158: 2025-12-07; 159: 2026-01-20; 162: 2025-09-25; 163: 2025-10-20; 165: 2025-11-30; 166: 2025-12-19; 169: 2025-11-05; 170: 2025-11-08; 172: 2026-02-13; 176: 2025-11-11; 177: 2025-11-12
67 | PSS-14 | AGE25CL | 1: WTG 424; 2: F14; 3: MSC; 4: 2025-12-29; 5: Bauer; 6: Yes; 7: 543533; 8: 2675475; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-06; 18: 2025-04-15; 20: 2025-06-13; 21: 2025-06-24; 24: YES; 25: Bauer; 29: 2025-12-18; 30: 2025-12-27; 32: 2025-05-04; 33: 2025-05-05; 35: 2025-12-29; 36: 2025-12-30; 39: 2025-05-06; 40: 2025-05-06; 42: 2025-12-30; 43: 2025-12-31; 46: 2025-05-07; 47: 2025-05-08; 49: 2025-12-31; 50: 2025-12-31; 53: 2025-05-09; 54: 2025-05-10; 56: 2026-01-02; 57: 2026-01-03; 60: 2025-05-11; 61: 2025-05-21; 63: 2026-01-22; 64: 2026-01-29; 67: 2025-05-22; 68: 2025-05-23; 70: 2026-02-14; 71: 2026-02-14; 75: 2025-05-28; 76: 2025-05-31; 78: 2026-02-24; 82: 2025-05-30; 83: 2025-05-30; 85: 2026-02-25; 86: 2026-02-25; 91: 2025-05-30; 92: 2025-06-09; 94: 2026-02-02; 95: 2026-02-02; 98: 2025-05-25; 99: 2025-06-01; 101: Done; 102: Done; 105: 2025-05-25; 106: 2025-06-01; 108: 2026-02-14; 109: 2026-02-15; 112: Odhav; 113: 2025-05-27; 114: 2025-06-03; 116: 2026-02-05; 117: 2026-02-13; 120: 2025-09-10; 121: 2025-10-05; 123: 2026-02-23; 127: 2025-11-02; 128: 2025-11-10; 130: 2026-02-21; 134: 2025-10-06; 135: 2025-10-13; 141: 2025-10-14; 142: 2025-10-16; 148: 2025-11-05; 149: 2025-11-06; 155: 2025-09-20; 156: 2025-10-10; 158: 2026-01-01; 159: 2026-02-22; 162: 2025-09-25; 163: 2025-10-20; 165: 2026-01-31; 166: 2026-02-15; 169: 2025-11-07; 170: 2025-11-10; 176: 2025-11-12; 177: 2025-11-13
68 | PSS-14 | AGE25CL | 1: WTG 425; 2: F14; 3: SHREEJI; 4: 2025-10-13; 5: Bauer; 6: Yes; 7: 543723; 8: 2674488; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-26; 18: 2025-04-04; 20: 2025-06-25; 21: 2025-07-08; 32: 2025-05-12; 33: 2025-05-13; 35: 2025-12-01; 36: 2025-12-05; 39: 2025-05-14; 40: 2025-05-14; 42: 2025-12-06; 43: 2025-12-07; 46: 2025-05-15; 47: 2025-05-16; 49: 2025-12-07; 50: 2025-12-07; 53: 2025-05-17; 54: 2025-05-18; 56: 2025-12-11; 57: 2025-12-11; 60: 2025-05-19; 61: 2025-05-29; 63: 2025-12-15; 64: 2025-12-18; 67: 2025-05-30; 68: 2025-05-31; 70: 2025-12-19; 71: 2025-12-19; 75: 2025-06-05; 76: 2025-06-08; 78: 2025-12-23; 82: 2025-06-07; 83: 2025-06-07; 85: 2025-12-23; 86: 2025-12-23; 91: 2025-05-18; 92: 2025-05-28; 94: 2025-12-06; 95: 2026-01-19; 98: 2025-06-02; 99: 2025-06-09; 101: 2025-03-16; 102: 2025-05-18; 105: 2025-06-02; 106: 2025-06-09; 108: 2026-02-02; 109: 2026-02-04; 112: Odhav; 113: 2025-06-04; 114: 2025-06-11; 116: 2026-01-12; 117: 2026-02-04; 120: 2025-10-08; 121: 2025-10-23; 123: 2026-02-20; 127: 2025-09-28; 128: 2025-10-06; 130: 2026-02-23; 131: 2026-02-25; 134: 2025-10-24; 135: 2025-10-31; 141: 2025-11-01; 142: 2025-11-03; 148: 2025-11-13; 149: 2025-11-14; 155: 2025-10-05; 156: 2025-10-25; 158: 2026-01-04; 162: 2025-09-25; 163: 2025-10-20; 165: 2026-01-31; 166: 2026-02-15; 169: 2025-11-15; 170: 2025-11-18; 176: 2025-11-18; 177: 2025-11-19
69 | PSS-12 | AGE26AL | 1: WTG 426; 2: F01; 3: MSC; 4: 2026-01-12; 5: Bauer; 6: Yes; 7: 543914; 8: 2673502; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-12; 18: 2025-04-21; 20: 2025-09-03; 21: 2025-09-23; 24: YES; 25: keller; 29: 2025-12-24; 30: 2026-01-08; 32: 2025-05-24; 33: 2025-05-25; 35: 2026-01-19; 36: 2026-01-20; 39: 2025-05-26; 40: 2025-05-26; 42: 2026-01-20; 43: 2026-01-20; 46: 2025-05-27; 47: 2025-05-28; 49: 2026-01-20; 50: 2026-01-20; 53: 2025-05-29; 54: 2025-05-30; 56: 2026-01-21; 57: 2026-01-21; 60: 2025-05-31; 61: 2025-06-10; 63: 2026-01-24; 64: 2026-02-01; 67: 2025-06-11; 68: 2025-06-12; 70: 2026-02-07; 71: 2026-02-08; 75: 2025-06-17; 76: 2025-06-20; 78: 2026-02-10; 82: 2025-06-19; 83: 2025-06-19; 85: 2026-02-10; 86: 2026-02-10; 91: 2025-05-30; 92: 2025-06-09; 94: 2026-01-19; 95: 2026-01-23; 98: 2025-06-14; 99: 2025-06-21; 101: 2025-03-22; 102: 2025-04-25; 105: 2025-06-14; 106: 2025-06-21; 108: 2026-02-01; 109: 2026-02-16; 112: GP Project; 113: 2025-06-16; 114: 2025-06-23; 116: 2026-01-06; 117: 2026-02-02; 120: 2025-10-17; 121: 2025-11-01; 123: 2026-02-15; 124: 2026-02-21; 127: 2025-11-10; 128: 2025-11-18; 130: 2026-01-27; 131: 2026-02-11; 134: 2025-11-02; 135: 2025-11-09; 137: 2026-02-24; 138: 2026-02-28; 141: 2025-11-10; 142: 2025-11-12; 148: 2025-11-11; 149: 2025-11-12; 151: 2026-02-03; 152: 2026-02-03; 155: 2025-10-05; 156: 2025-10-25; 158: 2025-12-06; 159: 2026-01-20; 162: 2025-10-02; 163: 2025-10-27; 165: 2025-11-30; 166: 2025-12-19; 169: 2025-11-13; 170: 2025-11-16; 172: 2026-02-26; 176: 2025-11-18; 177: 2025-11-19
70 | PSS-12 | AGE26AL | 1: WTG 427; 2: F02; 3: SHREERAM; 4: 2025-11-14; 5: Keller; 6: Yes; 7: 544104; 8: 2672516; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-22; 18: 2025-05-02; 20: 2025-11-01; 21: 2025-11-11; 32: 2025-05-10; 33: 2025-05-11; 35: 2025-11-16; 36: 2025-11-18; 39: 2025-05-12; 40: 2025-05-12; 42: 2025-11-18; 43: 2025-11-21; 46: 2025-05-13; 47: 2025-05-14; 49: 2025-11-22; 50: 2025-11-22; 53: 2025-05-15; 54: 2025-05-16; 56: 2025-11-26; 57: 2025-11-27; 60: 2025-05-17; 61: 2025-05-27; 63: 2025-11-27; 64: 2025-12-04; 67: 2025-05-28; 68: 2025-05-29; 70: 2025-12-05; 71: 2025-12-05; 75: 2025-06-03; 76: 2025-06-06; 78: 2025-12-12; 82: 2025-06-05; 83: 2025-06-05; 85: 2025-12-13; 86: 2025-12-13; 91: 2025-05-10; 92: 2025-05-20; 94: 2025-11-17; 95: 2026-01-13; 98: 2025-05-31; 99: 2025-06-07; 101: Done; 102: Done; 105: 2025-05-31; 106: 2025-06-07; 108: 2026-01-31; 109: 2026-02-02; 112: GP Project; 113: 2025-06-02; 114: 2025-06-09; 116: 2026-01-15; 117: 2026-01-23; 120: 2025-10-07; 121: 2025-10-22; 123: 2026-02-16; 124: 2026-02-24; 127: 2025-09-26; 128: 2025-10-04; 130: 2026-01-18; 131: 2026-01-28; 134: 2025-10-23; 135: 2025-10-30; 137: 2026-02-27; 141: 2025-10-31; 142: 2025-11-02; 148: 2025-11-09; 149: 2025-11-10; 151: 2026-01-26; 152: 2026-01-26; 155: 2025-10-05; 156: 2025-10-25; 158: 2025-12-18; 159: 2026-01-20; 162: 2025-10-02; 163: 2025-10-27; 165: 2025-11-30; 166: 2025-12-19; 169: 2025-11-11; 170: 2025-11-14; 172: 2026-02-26; 176: 2025-11-17; 177: 2025-11-18
71 | PSS-14 | AGE25CL | 1: WTG 448; 2: F14; 3: SHREEJI; 4: 2025-10-13; 5: Bauer; 6: Yes; 7: 544184; 8: 2676157; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-16; 18: 2025-03-26; 20: 2025-06-02; 21: 2025-06-13; 32: 2025-05-17; 33: 2025-05-18; 35: 2025-11-18; 36: 2025-11-20; 39: 2025-05-19; 40: 2025-05-19; 42: 2025-11-21; 43: 2025-11-25; 46: 2025-05-20; 47: 2025-05-21; 49: 2025-11-26; 50: 2025-11-26; 53: 2025-05-22; 54: 2025-05-23; 56: 2025-12-04; 57: 2025-12-05; 60: 2025-05-24; 61: 2025-06-03; 63: 2025-12-05; 64: 2025-12-09; 67: 2025-06-04; 68: 2025-06-05; 70: 2025-12-09; 71: 2025-12-09; 75: 2025-06-10; 76: 2025-06-13; 78: 2025-12-13; 82: 2025-06-12; 83: 2025-06-12; 85: 2025-12-17; 86: 2025-12-17; 91: 2025-05-23; 92: 2025-06-02; 94: 2025-11-25; 95: 2026-01-31; 98: 2025-06-07; 99: 2025-06-14; 101: 2025-03-16; 102: 2025-05-16; 105: 2025-06-07; 106: 2025-06-14; 108: 2025-12-21; 109: 2026-01-09; 112: GP Project; 113: 2025-06-09; 114: 2025-06-16; 116: 2026-01-01; 117: 2026-01-08; 120: 2025-10-19; 121: 2025-11-03; 123: 2026-01-14; 124: 2026-01-28; 127: 2025-10-09; 128: 2025-10-17; 130: 2026-02-22; 134: 2025-11-04; 135: 2025-11-11; 137: 2026-01-29; 138: 2026-02-05; 141: 2025-11-12; 142: 2025-11-14; 144: 2026-02-12; 147: Delay due to Material; 148: 2025-11-15; 149: 2025-11-16; 155: 2025-10-20; 156: 2025-11-10; 158: 2026-01-06; 159: 2026-01-16; 162: 2025-10-02; 163: 2025-10-27; 165: 2026-01-31; 166: 2026-02-15; 169: 2025-11-17; 170: 2025-11-20; 176: 2025-11-20; 177: 2025-11-21
72 | PSS-14 | AGE25CL | 1: WTG 449; 2: F14; 3: SHREEJI; 4: 2025-10-13; 5: ITDC; 6: Yes; 7: 544374; 8: 2675170; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-27; 18: 2025-04-05; 20: 2025-06-21; 21: 2025-08-08; 32: 2025-04-25; 33: 2025-04-26; 35: 2025-11-14; 36: 2025-11-15; 39: 2025-04-27; 40: 2025-04-27; 42: 2025-11-16; 43: 2025-11-17; 46: 2025-04-28; 47: 2025-04-29; 49: 2025-11-18; 50: 2025-11-18; 53: 2025-04-30; 54: 2025-05-01; 56: 2025-11-20; 57: 2025-11-21; 60: 2025-05-02; 61: 2025-05-12; 63: 2025-11-21; 64: 2025-11-27; 67: 2025-05-13; 68: 2025-05-14; 70: 2025-11-30; 71: 2025-12-01; 75: 2025-05-19; 76: 2025-05-22; 78: 2025-12-05; 82: 2025-05-21; 83: 2025-05-21; 85: 2025-12-06; 86: 2025-12-06; 91: 2025-05-16; 92: 2025-05-26; 94: 2025-11-18; 95: 2026-01-24; 98: 2025-05-16; 99: 2025-05-23; 101: Done; 102: Done; 105: 2025-05-16; 106: 2025-05-23; 108: 2026-01-17; 109: 2026-01-20; 112: GP Project; 113: 2025-05-18; 114: 2025-05-25; 116: 2026-01-15; 117: 2026-01-20; 120: 2025-10-14; 121: 2025-11-01; 123: 2026-02-04; 124: 2026-02-21; 127: 2025-10-02; 128: 2025-10-10; 130: 2026-02-22; 134: 2025-11-02; 135: 2025-11-09; 137: 2026-02-26; 141: 2025-11-10; 142: 2025-11-12; 148: 2025-11-14; 149: 2025-11-15; 155: 2025-10-05; 156: 2025-10-25; 158: 2026-01-07; 162: 2025-10-02; 163: 2025-10-27; 165: 2026-01-31; 166: 2026-02-15; 169: 2025-11-16; 170: 2025-11-19; 176: 2025-11-21; 177: 2025-11-22
73 | PSS-14 | AGE25CL | 1: WTG 450; 2: F15; 3: MSC; 4: 2026-01-22; 5: Bauer; 6: Yes; 7: 544565; 8: 2674184; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-05; 18: 2025-04-15; 20: 2025-09-23; 21: 2025-10-08; 24: YES; 25: Bauer; 29: 2026-01-13; 30: 2026-01-21; 32: 2025-04-13; 33: 2025-04-14; 35: 2026-01-21; 36: 2026-01-22; 39: 2025-04-15; 40: 2025-04-15; 42: 2026-01-22; 43: 2026-01-23; 46: 2025-04-16; 47: 2025-04-17; 49: 2026-01-24; 50: 2026-01-24; 53: 2025-04-18; 54: 2025-04-19; 56: 2026-01-25; 57: 2026-01-25; 60: 2025-04-20; 61: 2025-04-30; 63: 2026-01-27; 64: 2026-02-07; 67: 2025-05-01; 68: 2025-05-02; 70: 2026-02-17; 71: 2026-02-17; 75: 2025-05-07; 76: 2025-05-10; 82: 2025-05-09; 83: 2025-05-09; 85: 2026-02-27; 86: 2026-02-27; 91: 2025-05-09; 92: 2025-05-19; 94: 2026-01-23; 95: 2026-02-05; 98: 2025-05-04; 99: 2025-05-11; 101: 2025-03-19; 102: 2025-05-19; 105: 2025-05-04; 106: 2025-05-11; 108: 2026-02-13; 109: 2026-02-18; 112: GP Project(Reuse); 113: 2025-05-06; 114: 2025-05-13; 116: 2026-02-02; 117: 2026-02-15; 120: 2025-10-03; 121: 2025-10-18; 127: 2025-10-28; 128: 2025-11-05; 130: 2026-02-25; 134: 2025-10-19; 135: 2025-10-26; 141: 2025-10-27; 142: 2025-10-29; 148: 2025-11-04; 149: 2025-11-05; 155: 2025-09-20; 156: 2025-10-10; 158: 2026-01-31; 159: 2026-02-12; 162: 2025-10-02; 163: 2025-10-27; 165: 2026-01-31; 166: 2026-02-15; 169: 2025-11-06; 170: 2025-11-09; 176: 2025-11-12; 177: 2025-11-13
74 | PSS-14 | AGE26AL | 1: KH 598; 2: F01; 3: SHREEJI; 4: 2025-10-13; 5: Bauer; 6: Yes; 7: 546492; 8: 2679182; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-30; 18: 2025-06-08; 20: 2025-09-23; 21: 2025-10-04; 32: 2025-10-20; 33: 2025-10-21; 35: 2025-10-14; 36: 2025-10-18; 39: 2025-10-22; 40: 2025-10-22; 42: 2025-10-19; 43: 2025-10-21; 46: 2025-10-23; 47: 2025-10-24; 49: 2025-10-24; 50: 2025-10-24; 53: 2025-10-25; 54: 2025-10-26; 56: 2025-10-25; 57: 2025-10-26; 60: 2025-10-27; 61: 2025-11-06; 63: 2025-10-27; 64: 2025-11-04; 67: 2025-11-07; 68: 2025-11-08; 70: 2025-11-04; 71: 2025-11-05; 75: 2025-11-13; 76: 2025-11-16; 78: 2025-12-07; 82: 2025-11-15; 83: 2025-11-15; 85: 2025-12-08; 86: 2025-12-08; 91: 2025-10-29; 92: 2025-11-08; 94: 2025-10-17; 95: 2026-02-11; 98: 2025-11-10; 99: 2025-11-17; 101: Done; 102: Done; 105: 2025-11-10; 106: 2025-11-17; 108: 2025-12-28; 112: Keshav; 113: 2025-11-12; 114: 2025-11-19; 116: 2025-12-22; 117: 2025-12-29; 120: 2026-02-19; 121: 2026-02-28; 127: 2026-01-04; 128: 2026-01-12; 130: 0; 134: 2026-03-01; 135: 2026-03-08; 141: 2026-03-09; 142: 2026-03-11; 148: 2026-02-20; 149: 2026-02-21; 155: 2025-01-22; 156: 2025-02-14; 162: 2026-01-22; 163: 2026-02-16; 169: 2026-01-15; 170: 2026-01-18; 176: 2026-03-12; 177: 2026-03-14
75 | PSS-14 | AGE25CL | 1: WTG 398; 2: F13; 3: BHAVANI; 4: 2025-06-22; 5: Bauer; 6: Yes; 7: 542699; 8: 2675739; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-04; 18: 2025-04-13; 20: 2025-06-06; 21: 2025-06-16; 32: 2025-05-20; 33: 2025-05-21; 35: 2025-06-23; 36: 2025-06-26; 39: 2025-05-22; 40: 2025-05-22; 42: 2025-07-09; 43: 2025-07-09; 46: 2025-05-23; 47: 2025-05-24; 49: 2025-07-09; 50: 2025-07-09; 53: 2025-05-25; 54: 2025-05-26; 56: 2025-07-18; 57: 2025-07-21; 59: Delay due to dewatering wip; 60: 2025-05-27; 61: 2025-06-06; 63: 2025-07-30; 64: 2025-08-16; 67: 2025-06-07; 68: 2025-06-08; 70: 2025-08-17; 71: 2025-08-17; 75: 2025-06-13; 76: 2025-06-16; 78: 2025-08-27; 79: 2025-12-02; 82: 2025-06-15; 83: 2025-06-15; 85: 2025-09-01; 86: 2025-09-01; 91: 2025-05-26; 92: 2025-06-05; 94: 2025-07-08; 95: 2026-01-23; 98: 2025-06-10; 99: 2025-06-17; 101: Done; 102: Done; 105: 2025-06-10; 106: 2025-06-17; 108: 2026-01-04; 109: 2026-01-06; 112: Vaibhav; 113: 2025-06-12; 114: 2025-06-19; 116: 2025-12-24; 117: 2026-01-06; 120: 2025-09-16; 121: 2025-10-14; 123: 2026-01-07; 124: 2026-01-21; 127: 2025-10-16; 128: 2025-10-24; 130: 2026-02-02; 131: 2026-02-18; 134: 2025-10-15; 135: 2025-10-22; 137: 2026-01-22; 138: 2026-01-29; 141: 2025-10-23; 142: 2025-10-25; 144: 2026-01-29; 145: 2026-01-30; 148: 2025-11-07; 149: 2025-11-08; 155: 2025-09-20; 156: 2025-10-10; 158: 2026-01-01; 162: 2025-10-02; 163: 2025-10-27; 165: 2026-01-31; 166: 2026-02-15; 169: 2025-11-09; 170: 2025-11-12; 176: 2025-11-14; 177: 2025-11-15
76 | PSS-11 | AGE25CL | 1: WTG 233A; 2: F08; 3: MSC; 4: 2025-12-03; 5: Bauer; 6: Yes; 7: 548174; 8: 2667382; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-08; 18: 2025-04-19; 20: 2025-08-02; 21: 2025-08-12; 24: YES; 25: Pinnacle; 29: 2025-11-15; 30: 2025-11-26; 32: 2025-04-23; 33: 2025-04-24; 35: 2025-12-09; 36: 2025-12-11; 38: wip; 39: 2025-04-25; 40: 2025-04-25; 42: 2025-12-12; 43: 2025-12-13; 46: 2025-04-26; 47: 2025-04-27; 49: 2025-12-15; 50: 2025-12-15; 53: 2025-04-28; 54: 2025-04-29; 56: 2025-12-16; 57: 2025-12-16; 60: 2025-04-30; 61: 2025-05-10; 63: 2025-12-20; 64: 2025-12-26; 66: steel set not available; 67: 2025-05-11; 68: 2025-05-12; 70: 2025-12-28; 71: 2025-12-28; 75: 2025-05-17; 76: 2025-05-20; 78: 2026-01-06; 82: 2025-05-19; 83: 2025-05-19; 85: 2026-01-07; 86: 2026-01-07; 91: 2025-05-14; 92: 2025-05-24; 94: 2025-12-29; 95: 2026-01-09; 98: 2025-05-14; 99: 2025-05-21; 101: Done; 102: Done; 105: 2025-05-14; 106: 2025-05-21; 108: 2025-12-29; 109: 2026-01-04; 112: Bipin; 113: 2025-05-16; 114: 2025-05-23; 116: 2025-12-29; 117: 2026-01-04; 120: 2025-11-04; 121: 2025-11-14; 123: 2026-01-21; 124: 2026-01-30; 127: 2025-10-25; 128: 2025-11-02; 130: 2026-01-11; 131: 2026-01-18; 134: 2025-11-15; 135: 2025-11-22; 137: 2026-01-31; 138: 2026-02-04; 141: 2025-11-23; 142: 2025-11-25; 144: 2026-02-04; 145: 2026-02-09; 148: 2025-11-12; 149: 2025-11-13; 151: 2026-01-16; 152: 2026-01-16; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-10-26; 159: 2025-12-17; 162: 2025-10-02; 163: 2025-10-27; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-11-14; 170: 2025-11-17; 172: 2026-01-24; 173: 2026-02-05; 176: 2025-11-26; 177: 2025-11-28; 179: 2026-02-11; 180: 2026-02-14
77 | PSS-11 | AGE25CL | 1: WTG 380; 2: F02; 3: BHAVANI; 4: 2025-05-30; 5: Saritha; 6: Yes; 7: 543190; 8: 2669140; 12: Done; 13: Done; 15: 199; 16: 199; 17: 2025-04-05; 18: 2025-04-15; 20: 2025-03-29; 21: 2025-05-28; 23: Delay Due to wet area; 32: 2025-04-24; 33: 2025-04-25; 35: 2025-06-12; 36: 2025-11-21; 38: Delay due to dewatering required; 39: 2025-04-26; 40: 2025-04-26; 42: 2025-11-21; 43: 2025-11-22; 46: 2025-04-27; 47: 2025-04-28; 49: 2025-11-24; 50: 2025-11-24; 53: 2025-04-29; 54: 2025-04-30; 56: 2025-11-25; 57: 2025-11-26; 60: 2025-05-01; 61: 2025-05-11; 63: 2025-11-27; 64: 2025-11-29; 67: 2025-05-12; 68: 2025-05-13; 70: 2025-11-30; 71: 2025-11-30; 75: 2025-05-18; 76: 2025-05-21; 78: 2025-12-03; 79: 2026-01-01; 82: 2025-05-20; 83: 2025-05-20; 85: 2025-12-04; 86: 2025-12-04; 91: 2025-05-15; 92: 2025-05-25; 94: 2025-11-21; 95: 2025-12-17; 98: 2025-05-15; 99: 2025-05-22; 101: 2025-12-05; 102: 2025-12-10; 105: 2025-05-15; 106: 2025-05-22; 108: 2025-12-07; 109: 2025-12-10; 112: Odhav; 113: 2025-05-17; 114: 2025-05-24; 116: 2025-12-06; 117: 2025-12-10; 120: 2025-10-27; 121: 2025-11-06; 123: 2025-12-10; 124: 2025-12-25; 127: 2025-11-01; 128: 2025-11-09; 130: 2025-12-18; 131: 2026-01-01; 134: 2025-11-07; 135: 2025-11-14; 137: 2025-12-29; 138: 2026-01-03; 141: 2025-11-15; 142: 2025-11-17; 144: 2026-01-03; 145: 2026-01-05; 148: 2025-11-19; 149: 2025-11-20; 151: 2025-12-29; 152: 2025-12-29; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-12-05; 159: 2025-12-26; 162: 2025-10-02; 163: 2025-10-27; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-11-21; 170: 2025-11-24; 172: 2026-01-12; 173: 2026-01-31; 176: 2025-11-25; 177: 2025-11-26; 179: 2026-02-06; 180: 2026-02-09
78 | PSS-11 | AGE25CL | 1: WTG 406; 2: F07; 3: BHAVANI; 4: 2025-03-31; 5: Keller; 6: Yes; 7: 544221; 8: 2667850; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-15; 18: 2025-04-24; 20: 2025-02-21; 21: 2025-02-28; 32: 2025-05-18; 33: 2025-05-19; 35: 2025-04-19; 36: 2025-04-27; 39: 2025-05-20; 40: 2025-05-20; 42: 2025-04-28; 43: 2025-04-30; 46: 2025-05-21; 47: 2025-05-22; 49: 2025-05-01; 50: 2025-05-01; 53: 2025-05-23; 54: 2025-05-24; 56: 2025-05-21; 57: 2025-05-21; 60: 2025-05-25; 61: 2025-06-04; 63: 2025-05-21; 64: 2025-05-29; 67: 2025-06-05; 68: 2025-06-06; 70: 2025-06-01; 71: 2025-06-01; 75: 2025-06-11; 76: 2025-06-14; 78: 2025-06-04; 79: 2026-01-03; 82: 2025-06-13; 83: 2025-06-13; 85: 2025-06-06; 86: 2025-06-06; 91: 2025-06-13; 92: 2025-06-23; 94: 2025-04-30; 95: 2025-11-27; 98: 2025-06-08; 99: 2025-06-15; 101: 2025-03-30; 102: 2025-05-18; 105: 2025-06-08; 106: 2025-06-15; 108: 2025-10-26; 109: 2025-11-20; 112: GP Project; 113: 2025-06-10; 114: 2025-06-17; 116: 2025-10-27; 117: 2025-11-20; 120: 2025-11-02; 121: 2025-11-12; 123: 2025-11-21; 124: 2025-11-29; 127: 2025-10-30; 128: 2025-11-07; 130: 2025-11-30; 131: 2025-12-06; 134: 2025-11-13; 135: 2025-11-20; 137: 2025-12-01; 138: 2025-12-06; 141: 2025-11-21; 142: 2025-11-23; 144: 2025-12-06; 145: 2025-12-08; 148: 2025-12-07; 149: 2025-12-08; 151: 2025-12-10; 152: 2025-12-10; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-10-25; 159: 2025-12-17; 162: 2025-10-25; 163: 2025-11-19; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-12-09; 170: 2025-12-12; 172: 2025-12-31; 173: 2026-02-03; 176: 2025-12-13; 177: 2025-12-15; 179: 2026-02-07; 180: 2026-02-09
79 | PSS-11 | AGE25CL | 1: WTG 382; 2: F07; 3: SVRE; 4: 2025-02-14; 5: Keller; 6: Yes; 7: 543570; 8: 2667168; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-03; 18: 2025-04-13; 20: 2025-02-06; 21: 2025-02-12; 32: 2025-04-20; 33: 2025-04-21; 35: 2025-02-15; 36: 2025-02-18; 39: 2025-04-22; 40: 2025-04-22; 42: 2025-02-18; 43: 2025-02-20; 46: 2025-04-23; 47: 2025-04-24; 49: 2025-02-20; 50: 2025-02-20; 53: 2025-04-25; 54: 2025-04-26; 56: 2025-02-23; 57: 2025-02-24; 60: 2025-04-27; 61: 2025-05-07; 63: 2025-02-24; 64: 2025-03-11; 67: 2025-05-08; 68: 2025-05-09; 70: 2025-03-13; 71: 2025-03-14; 75: 2025-05-14; 76: 2025-05-17; 78: 2025-04-04; 79: 2025-11-25; 82: 2025-05-16; 83: 2025-05-16; 85: 2025-03-22; 86: 2025-03-22; 91: 2025-05-01; 92: 2025-05-11; 94: 2025-05-07; 95: 2025-10-31; 98: 2025-05-11; 99: 2025-05-18; 101: 2025-03-11; 102: 2025-03-21; 105: 2025-05-11; 106: 2025-05-18; 108: 2025-10-29; 109: 2025-10-31; 112: GP Project; 113: 2025-05-13; 114: 2025-05-20; 116: 2025-03-20; 117: 2025-03-31; 120: 2025-09-16; 121: 2025-10-11; 123: 2025-11-08; 124: 2025-11-18; 127: 2025-10-27; 128: 2025-11-04; 130: 2025-10-10; 131: 2025-11-08; 134: 2025-10-12; 135: 2025-10-19; 137: 2025-11-24; 138: 2025-11-28; 141: 2025-10-20; 142: 2025-10-22; 144: 2025-11-29; 145: 2025-11-30; 148: 2025-11-14; 149: 2025-11-15; 151: 2025-11-24; 152: 2025-11-24; 155: 2025-09-20; 156: 2025-10-10; 158: 2025-11-15; 159: 2025-12-16; 162: 2025-10-02; 163: 2025-10-27; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-11-16; 170: 2025-11-19; 172: 2025-12-31; 173: 2026-02-03; 176: 2025-11-20; 177: 2025-11-22; 179: 2026-02-07; 180: 2026-02-09
80 | PSS-11 | AGE25CL | 1: WTG 403; 2: F02; 3: ODHAV; 4: 2025-11-25; 5: Saritha; 6: Yes; 7: 543651; 8: 2670808; 12: Done; 13: Done; 15: 313; 16: 313; 17: 2025-04-03; 18: 2025-04-12; 20: 2025-05-27; 21: 2025-11-12; 24: YES; 25: Saritha; 29: 2025-11-18; 30: 2025-11-24; 32: 2025-05-02; 33: 2025-05-03; 35: 2025-12-01; 36: 2025-12-05; 39: 2025-05-04; 40: 2025-05-04; 42: 2025-12-07; 43: 2025-12-08; 46: 2025-05-05; 47: 2025-05-06; 49: 2025-12-10; 50: 2025-12-10; 53: 2025-05-07; 54: 2025-05-08; 56: 2025-12-13; 57: 2025-12-13; 60: 2025-05-09; 61: 2025-05-19; 63: 2025-12-22; 64: 2025-12-25; 67: 2025-05-20; 68: 2025-05-21; 70: 2025-12-26; 71: 2025-12-27; 75: 2025-05-26; 76: 2025-05-29; 78: 2026-12-31; 79: 2026-01-10; 82: 2025-05-28; 83: 2025-05-28; 85: 2025-12-31; 86: 2025-12-31; 91: 2025-05-13; 92: 2025-05-23; 94: 2025-12-09; 95: 2025-12-19; 98: 2025-05-23; 99: 2025-05-30; 101: 2025-03-20; 102: 2025-04-15; 105: 2025-05-23; 106: 2025-05-30; 108: 2025-12-29; 109: 2026-01-04; 112: Odhav; 113: 2025-05-25; 114: 2025-06-01; 116: 2025-11-14; 117: 2026-01-04; 120: 2025-11-02; 121: 2025-11-11; 123: 2026-01-04; 124: 2026-01-13; 127: 2025-10-29; 128: 2025-11-06; 130: 2025-12-22; 131: 2026-01-10; 134: 2025-11-12; 135: 2025-11-19; 137: 2026-01-20; 138: 2026-01-23; 141: 2025-11-20; 142: 2025-11-22; 144: 2026-01-24; 145: 2026-01-26; 148: 2025-11-16; 149: 2025-11-17; 151: 2026-01-07; 152: 2026-01-07; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-11-19; 159: 2025-12-27; 162: 2025-10-02; 163: 2025-10-27; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-11-18; 170: 2025-11-21; 172: 2026-01-20; 173: 2026-01-31; 176: 2025-11-23; 177: 2025-11-25; 179: 2026-02-06; 180: 2026-02-09
81 | PSS-11 | AGE25CL | 1: WTG 404; 2: F02; 3: SVRE; 4: 2025-06-01; 5: Saritha; 6: Yes; 7: 543841; 8: 2669822; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-05; 18: 2025-04-15; 20: 2025-04-30; 21: 2025-05-29; 23: Delay Due to wet area; 32: 2025-05-08; 33: 2025-05-09; 35: 2025-06-02; 36: 2025-06-04; 39: 2025-05-10; 40: 2025-05-10; 42: 2025-06-06; 43: 2025-06-08; 46: 2025-05-11; 47: 2025-05-12; 49: 2025-06-08; 50: 2025-06-08; 53: 2025-05-13; 54: 2025-05-14; 56: 2025-06-10; 57: 2025-06-11; 60: 2025-05-15; 61: 2025-05-25; 63: 2025-06-12; 64: 2025-07-06; 67: 2025-05-26; 68: 2025-05-27; 70: 2025-07-08; 71: 2025-07-09; 75: 2025-06-01; 76: 2025-06-04; 78: 2025-08-25; 79: 2026-01-02; 82: 2025-06-03; 83: 2025-06-03; 85: 2025-07-19; 86: 2025-07-19; 91: 2025-05-19; 92: 2025-05-29; 94: 2025-06-05; 95: 2025-11-22; 98: 2025-05-29; 99: 2025-06-05; 101: 2025-05-24; 102: 2025-06-02; 105: 2025-05-29; 106: 2025-06-05; 108: 2025-11-22; 109: 2025-12-23; 112: Odhav; 113: 2025-05-31; 114: 2025-06-07; 116: 2025-11-06; 117: 2025-12-21; 120: 2025-10-28; 121: 2025-11-07; 123: 2025-12-25; 124: 2025-12-31; 127: 2025-10-30; 128: 2025-11-07; 130: 2025-11-24; 131: 2025-12-02; 134: 2025-11-08; 135: 2025-11-15; 137: 2026-01-05; 138: 2026-01-09; 141: 2025-11-16; 142: 2025-11-18; 144: 2026-01-09; 145: 2026-01-11; 148: 2025-12-07; 149: 2025-12-08; 151: 2025-12-03; 152: 2025-12-03; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-11-07; 159: 2026-01-09; 162: 2025-10-25; 163: 2025-11-19; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-12-09; 170: 2025-12-12; 172: 2026-01-12; 173: 2026-01-31; 176: 2025-12-13; 177: 2025-12-15; 179: 2026-02-06; 180: 2026-02-09
82 | PSS-11 | AGE25CL | 1: WTG 379; 2: F02; 3: SHREEJI; 4: 2025-05-24; 5: Kamar/Menard; 6: Yes; 7: 543000; 8: 2670126; 12: Done; 13: Done; 15: 199; 16: 199; 17: 2025-04-02; 18: 2025-04-11; 20: 2025-01-29; 21: 2025-03-29; 23: Shifted to PSS- Start by menard from 24-Mar-24; 32: 2025-05-02; 33: 2025-05-03; 35: 2025-06-22; 36: 2025-06-24; 39: 2025-05-04; 40: 2025-05-04; 42: 2025-06-25; 43: 2025-07-03; 45: Delay due to water logging; 46: 2025-05-05; 47: 2025-05-06; 49: 2025-07-04; 50: 2025-07-06; 52: PCC hold (49cum), Boom choked; 53: 2025-05-07; 54: 2025-05-08; 56: 2025-07-06; 57: 2025-07-07; 60: 2025-05-09; 61: 2025-05-19; 63: 2025-07-13; 64: 2025-07-24; 67: 2025-05-20; 68: 2025-05-21; 70: 2025-07-25; 71: 2025-07-26; 75: 2025-05-26; 76: 2025-05-29; 78: 2025-08-05; 79: 2026-01-04; 82: 2025-05-28; 83: 2025-05-28; 85: 2025-08-06; 86: 2025-08-06; 91: 2025-05-18; 92: 2025-05-28; 94: 2025-11-03; 95: 2025-11-08; 98: 2025-05-23; 99: 2025-05-30; 101: 2025-11-17; 102: 2025-11-21; 105: 2025-05-23; 106: 2025-05-30; 108: 2025-11-16; 109: 2025-11-21; 112: Odhav; 113: 2025-05-25; 114: 2025-06-01; 116: 2025-10-31; 117: 2025-11-21; 120: 2025-10-09; 121: 2025-10-24; 123: 2025-11-21; 124: 2025-12-05; 127: 2025-09-28; 128: 2025-10-06; 130: 2025-11-13; 131: 2025-12-10; 134: 2025-10-25; 135: 2025-11-01; 137: 2025-12-08; 138: 2025-12-12; 141: 2025-11-02; 142: 2025-11-04; 144: 2025-12-12; 145: 2025-12-14; 148: 2025-11-11; 149: 2025-11-12; 151: 2025-12-10; 152: 2025-12-10; 155: 2025-10-05; 156: 2025-10-25; 158: 2025-11-07; 159: 2026-01-15; 162: 2025-09-25; 163: 2025-10-20; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-11-13; 170: 2025-11-16; 172: 2026-01-12; 173: 2026-01-31; 176: 2025-11-16; 177: 2025-11-17; 179: 2026-02-06; 180: 2026-02-09
83 | PSS-11 | AGE25CL | 1: WTG 381; 2: F07; 3: BHAVANI; 4: 2025-03-31; 5: Keller; 6: Yes; 7: 543380; 8: 2668154; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-04; 18: 2025-04-14; 20: 2025-02-17; 21: 2025-02-24; 32: 2025-05-02; 33: 2025-05-03; 35: 2025-04-07; 36: 2025-04-09; 39: 2025-05-04; 40: 2025-05-04; 42: 2025-04-10; 43: 2025-04-12; 46: 2025-05-05; 47: 2025-05-06; 49: 2025-04-13; 50: 2025-04-13; 53: 2025-05-07; 54: 2025-05-08; 56: 2025-04-17; 57: 2025-04-18; 60: 2025-05-09; 61: 2025-05-19; 63: 2025-04-20; 64: 2025-05-01; 67: 2025-05-20; 68: 2025-05-21; 70: 2025-05-02; 71: 2025-05-03; 75: 2025-05-26; 76: 2025-05-29; 78: 2025-05-14; 79: 2025-11-25; 82: 2025-05-28; 83: 2025-05-28; 85: 2025-06-07; 86: 2025-06-07; 91: 2025-05-13; 92: 2025-05-23; 94: 2025-04-15; 95: 2025-11-19; 98: 2025-05-23; 99: 2025-05-30; 101: 2025-03-30; 102: 2025-04-06; 105: 2025-05-23; 106: 2025-05-30; 108: 2025-11-15; 109: 2025-11-21; 112: GP Project; 113: 2025-05-25; 114: 2025-06-01; 116: 2025-10-23; 117: 2025-11-21; 120: 2025-10-22; 121: 2025-11-01; 123: 2025-11-26; 124: 2025-12-06; 127: 2025-10-27; 128: 2025-11-04; 130: 2025-11-20; 131: 2025-11-24; 134: 2025-11-02; 135: 2025-11-09; 137: 2025-12-10; 138: 2025-12-14; 141: 2025-11-10; 142: 2025-11-12; 144: 2025-12-14; 145: 2025-12-17; 148: 2025-11-14; 149: 2025-11-15; 151: 2025-12-07; 152: 2025-12-07; 155: 2025-10-05; 156: 2025-10-25; 158: 2025-11-10; 159: 2025-12-10; 162: 2025-10-02; 163: 2025-10-27; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-11-16; 170: 2025-11-19; 172: 2026-01-07; 173: 2026-02-03; 176: 2025-11-20; 177: 2025-11-22; 179: 2026-02-07; 180: 2026-02-09
84 | PSS-11 | AGE25CL | 1: WTG 407; 2: F07; 3: BHAVANI; 4: 2025-11-25; 5: Keller; 6: Yes; 7: 544412; 8: 2666863; 12: Done; 13: Done; 15: 369; 16: 369; 17: 2025-04-14; 18: 2025-04-23; 20: 2025-02-08; 21: 2025-02-15; 24: YES; 25: ITDC; 26: 2025-04-29; 27: 2025-05-05; 29: 2025-11-07; 30: 2025-11-13; 32: 2025-05-10; 33: 2025-05-11; 35: 2025-11-26; 36: 2025-11-27; 39: 2025-05-12; 40: 2025-05-12; 42: 2025-11-28; 43: 2025-11-29; 46: 2025-05-13; 47: 2025-05-14; 49: 2025-12-02; 50: 2025-12-02; 53: 2025-05-15; 54: 2025-05-16; 56: 2025-12-02; 57: 2025-12-02; 60: 2025-05-17; 61: 2025-05-27; 63: 2025-12-03; 64: 2025-12-06; 67: 2025-05-28; 68: 2025-05-29; 70: 2025-12-07; 71: 2025-12-08; 75: 2025-06-03; 76: 2025-06-06; 78: 2025-12-16; 79: 2026-02-02; 82: 2025-06-05; 83: 2025-06-05; 85: 2025-12-16; 86: 2025-12-16; 91: 2025-06-05; 92: 2025-06-15; 94: 2025-11-28; 95: 2025-12-08; 98: 2025-05-31; 99: 2025-06-07; 101: 2025-03-21; 102: 2025-04-04; 105: 2025-05-31; 106: 2025-06-07; 108: 2025-12-16; 109: 2025-12-19; 112: Odhav; 113: 2025-06-02; 114: 2025-06-09; 116: 2025-04-04; 117: 2025-04-15; 120: 2025-10-15; 121: 2025-11-01; 123: 2025-12-19; 124: 2025-12-28; 127: 2025-11-02; 128: 2025-11-10; 130: 2025-12-10; 131: 2025-12-26; 134: 2025-11-02; 135: 2025-11-09; 137: 2025-12-30; 138: 2026-01-05; 141: 2025-11-10; 142: 2025-11-12; 144: 2026-01-05; 145: 2026-01-07; 148: 2025-12-10; 149: 2025-12-11; 151: 2025-12-29; 152: 2025-12-29; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-11-19; 159: 2025-12-17; 162: 2025-10-25; 163: 2025-11-19; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-12-12; 170: 2025-12-15; 172: 2026-01-12; 173: 2026-02-03; 176: 2025-12-16; 177: 2025-12-18; 179: 2026-02-07; 180: 2026-02-09
85 | PSS-11 | AGE25CL | 1: WTG 429; 2: F03; 3: ODHAV; 4: 2025-06-25; 5: Saritha; 6: Yes; 7: 544485; 8: 2670544; 12: Done; 13: Done; 15: 199; 16: 199; 17: 2025-04-13; 18: 2025-04-22; 20: 2025-05-31; 21: 2025-06-12; 32: 2025-05-11; 33: 2025-05-12; 35: 2025-08-10; 36: 2025-08-11; 39: 2025-05-13; 40: 2025-05-13; 42: 2025-08-14; 43: 2025-09-03; 45: Dewatering Reuiqred; 46: 2025-05-14; 47: 2025-05-15; 49: 2025-09-04; 50: 2025-09-04; 53: 2025-05-16; 54: 2025-05-17; 56: 2025-09-05; 57: 2025-09-05; 60: 2025-05-18; 61: 2025-05-28; 63: 2025-11-07; 64: 2025-11-16; 67: 2025-05-29; 68: 2025-05-30; 70: 2025-11-16; 71: 2025-11-23; 74: Delay due to road Damage; 75: 2025-06-04; 76: 2025-06-07; 78: 2025-12-08; 79: 2026-01-08; 82: 2025-06-06; 83: 2025-06-06; 85: 2025-12-09; 86: 2025-12-09; 91: 2025-06-01; 92: 2025-06-11; 94: 2025-12-07; 95: 2025-12-22; 98: 2025-06-01; 99: 2025-06-08; 101: 2025-03-20; 102: 2025-04-19; 105: 2025-06-01; 106: 2025-06-08; 108: 2025-12-13; 109: 2025-12-15; 112: SS Jadeja; 113: 2025-06-03; 114: 2025-06-10; 116: 2025-11-06; 117: 2025-12-15; 120: 2025-11-12; 121: 2025-11-21; 123: 2025-12-18; 124: 2026-01-07; 127: 2025-11-02; 128: 2025-11-10; 130: 2025-12-23; 131: 2026-01-09; 134: 2025-11-22; 135: 2025-11-29; 137: 2026-01-10; 138: 2026-01-15; 141: 2025-11-30; 142: 2025-12-02; 144: 2026-01-16; 145: 2026-01-18; 148: 2025-11-20; 149: 2025-11-21; 151: 2026-01-08; 152: 2026-01-08; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-12-15; 159: 2025-12-26; 162: 2025-10-25; 163: 2025-11-19; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-11-22; 170: 2025-11-25; 172: 2026-01-20; 173: 2026-01-31; 176: 2025-12-03; 177: 2025-12-05; 179: 2026-02-09; 180: 2026-02-10; 183: 2026-02-10
86 | PSS-12 | AGE26AL | 1: WTG 498; 2: F06; 3: BIPL; 4: 2025-09-22; 5: Bauer; 6: Yes; 7: 546239; 8: 2673615; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-27; 18: 2025-05-06; 20: 2025-08-19; 21: 2025-09-01; 32: 2025-06-08; 33: 2025-06-09; 35: 2025-09-25; 36: 2025-09-29; 39: 2025-06-10; 40: 2025-06-10; 42: 2025-10-07; 43: 2025-10-07; 46: 2025-06-11; 47: 2025-06-12; 49: 2025-10-08; 50: 2025-10-08; 53: 2025-06-13; 54: 2025-06-14; 56: 2025-10-11; 57: 2025-10-13; 60: 2025-06-15; 61: 2025-06-25; 63: 2025-10-19; 64: 2025-11-01; 67: 2025-06-26; 68: 2025-06-27; 70: 2025-11-07; 71: 2025-11-08; 75: 2025-07-02; 76: 2025-07-05; 78: 2025-11-07; 79: 2026-02-03; 82: 2025-07-04; 83: 2025-07-04; 85: 2025-12-16; 86: 2025-12-16; 91: 2025-06-19; 92: 2025-06-29; 94: 2025-10-05; 95: 2026-01-09; 98: 2025-06-29; 99: 2025-07-06; 101: 2025-03-21; 102: 2025-05-07; 105: 2025-06-29; 106: 2025-07-06; 108: 2025-12-14; 109: 2025-12-18; 112: SS Jadeja; 113: 2025-07-01; 114: 2025-07-08; 116: 2025-12-03; 117: 2025-12-18; 120: 2025-12-10; 121: 2025-12-20; 123: 2026-01-01; 124: 2026-01-12; 127: 2025-12-02; 128: 2025-12-10; 130: 2026-01-15; 131: 2026-01-23; 134: 2025-12-21; 135: 2025-12-28; 137: 2026-01-20; 138: 2026-01-22; 141: 2025-12-29; 142: 2025-12-31; 144: 2026-01-23; 145: 2026-01-24; 148: 2026-01-04; 149: 2026-01-05; 151: 2026-01-23; 152: 2026-01-23; 155: 2025-11-20; 156: 2025-12-10; 158: 2025-11-22; 159: 2026-01-20; 162: 2025-11-26; 163: 2025-12-21; 165: 2025-11-30; 166: 2025-12-19; 169: 2026-01-06; 170: 2026-01-09; 172: 2026-02-05; 173: 2026-02-18; 176: 2026-01-10; 177: 2026-01-12
87 | PSS-11 | AGE25CL | 1: WTG 431; 2: F03; 3: SHREEJI; 4: 2025-06-12; 5: Saritha; 6: Yes; 7: 544865; 8: 2668571; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-26; 18: 2025-05-05; 20: 2025-05-29; 21: 2025-06-08; 32: 2025-05-10; 33: 2025-05-11; 35: 2025-07-11; 36: 2025-07-18; 39: 2025-05-12; 40: 2025-05-12; 42: 2025-07-20; 43: 2025-07-22; 46: 2025-05-13; 47: 2025-05-14; 49: 2025-07-24; 50: 2025-07-24; 53: 2025-05-15; 54: 2025-05-16; 56: 2025-07-26; 57: 2025-07-26; 60: 2025-05-17; 61: 2025-05-27; 63: 2025-07-30; 64: 2025-08-03; 67: 2025-05-28; 68: 2025-05-29; 70: 2025-08-08; 71: 2025-08-09; 75: 2025-06-03; 76: 2025-06-06; 78: 2025-11-04; 79: 2026-01-02; 82: 2025-06-05; 83: 2025-06-05; 85: 2025-08-20; 86: 2025-08-20; 91: 2025-06-05; 92: 2025-06-15; 94: 2025-12-03; 95: 2025-12-09; 98: 2025-05-31; 99: 2025-06-07; 101: 2025-03-22; 102: 2025-05-02; 105: 2025-05-31; 106: 2025-06-07; 108: 2025-12-06; 109: 2025-12-08; 112: GP Project; 113: 2025-06-02; 114: 2025-06-09; 116: 2025-10-21; 117: 2025-12-06; 120: 2025-11-18; 121: 2025-11-28; 123: 2025-12-08; 124: 2025-12-22; 127: 2025-11-03; 128: 2025-11-11; 130: 2025-12-11; 131: 2025-12-21; 134: 2025-11-29; 135: 2025-12-06; 137: 2025-12-25; 138: 2025-12-29; 141: 2025-12-07; 142: 2025-12-09; 144: 2025-12-29; 145: 2025-12-31; 148: 2025-12-11; 149: 2025-12-12; 151: 2025-12-22; 152: 2025-12-22; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-11-02; 159: 2026-01-12; 162: 2025-10-25; 163: 2025-11-19; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-12-13; 170: 2025-12-16; 172: 2026-01-20; 173: 2026-01-31; 176: 2025-12-17; 177: 2025-12-19; 179: 2026-02-07; 180: 2026-02-09
88 | PSS-11 | AGE25CL | 1: WTG 432; 2: F07; 3: MSC; 4: 2025-11-25; 5: Saritha; 6: Yes; 7: 545055; 8: 2667585; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-24; 18: 2025-05-02; 20: 2025-04-25; 21: 2025-05-17; 24: YES; 25: Keller; 26: 2025-05-04; 27: 2025-05-09; 29: 2025-11-16; 30: 2025-11-19; 32: 2025-05-12; 33: 2025-05-13; 35: 2025-11-28; 36: 2025-11-29; 39: 2025-05-13; 40: 2025-05-14; 42: 2025-11-29; 43: 2025-11-29; 46: 2025-05-14; 47: 2025-05-15; 49: 2025-11-30; 50: 2025-11-30; 53: 2025-05-16; 54: 2025-05-17; 56: 2025-12-03; 57: 2025-12-03; 60: 2025-05-18; 61: 2025-05-28; 63: 2025-12-06; 64: 2025-12-15; 67: 2025-05-29; 68: 2025-05-30; 70: 2025-12-15; 71: 2025-12-16; 75: 2025-06-04; 76: 2025-06-07; 78: 2025-12-22; 82: 2025-06-06; 83: 2025-06-06; 85: 2025-12-23; 86: 2025-12-23; 91: 2025-06-06; 92: 2025-06-16; 94: 2025-11-29; 95: 2025-12-11; 98: 2025-06-01; 99: 2025-06-08; 101: 2025-03-31; 102: 2025-05-19; 105: 2025-06-01; 106: 2025-06-08; 108: 2025-12-22; 109: 2025-12-25; 112: Odhav; 113: 2025-06-03; 114: 2025-06-10; 116: 2025-12-01; 117: 2025-12-23; 120: 2025-11-13; 121: 2025-11-23; 123: 2025-12-25; 124: 2025-12-31; 127: 2025-11-04; 128: 2025-11-12; 130: 2025-12-12; 131: 2026-01-04; 134: 2025-11-24; 135: 2025-12-01; 137: 2026-01-06; 138: 2026-01-11; 141: 2025-12-02; 142: 2025-12-04; 144: 2026-01-11; 145: 2026-01-13; 148: 2025-12-12; 149: 2025-12-13; 151: 2025-12-28; 152: 2025-12-28; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-10-27; 159: 2025-12-17; 162: 2025-10-25; 163: 2025-11-19; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-12-14; 170: 2025-12-17; 172: 2026-01-12; 173: 2026-02-03; 176: 2025-12-18; 177: 2025-12-20; 179: 2026-02-07; 180: 2026-02-09
89 | PSS-11 | AGE25CL | 1: WTG 433; 2: F08; 3: SHREEJI; 4: 2025-10-13; 5: Keller; 6: Yes; 7: 545246; 8: 2666599; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-24; 18: 2025-05-02; 20: 2025-02-13; 21: 2025-02-20; 24: YES; 25: Bauer; 26: 2025-05-04; 27: 2025-05-09; 29: 2025-10-10; 30: 2025-10-15; 32: 2025-05-12; 33: 2025-05-13; 35: 2025-11-07; 36: 2025-11-10; 39: 2025-05-13; 40: 2025-05-14; 42: 2025-11-11; 43: 2025-11-11; 46: 2025-05-14; 47: 2025-05-15; 49: 2025-11-12; 50: 2025-11-12; 53: 2025-05-16; 54: 2025-05-17; 56: 2025-11-14; 57: 2025-11-16; 60: 2025-05-18; 61: 2025-05-28; 63: 2025-11-17; 64: 2025-11-23; 67: 2025-05-29; 68: 2025-05-30; 70: 2025-11-24; 71: 2025-11-24; 75: 2025-06-04; 76: 2025-06-07; 78: 2025-12-01; 82: 2025-06-06; 83: 2025-06-06; 85: 2025-12-04; 86: 2025-12-04; 91: 2025-06-06; 92: 2025-06-16; 94: 2025-11-23; 95: 2025-12-22; 98: 2025-06-01; 99: 2025-06-08; 101: 2025-12-06; 102: 2025-12-08; 105: 2025-06-01; 106: 2025-06-08; 108: 2025-12-06; 109: 2025-12-08; 112: Odhav; 113: 2025-06-03; 114: 2025-06-10; 116: 2025-04-04; 117: 2025-04-18; 120: 2025-11-02; 121: 2025-11-12; 123: 2025-12-08; 124: 2025-12-20; 127: 2025-11-05; 128: 2025-11-13; 130: 2025-12-25; 131: 2026-01-01; 134: 2025-11-13; 135: 2025-11-20; 137: 2025-12-22; 138: 2025-12-29; 141: 2025-11-21; 142: 2025-11-23; 144: 2025-12-29; 145: 2025-12-31; 148: 2025-12-13; 149: 2025-12-14; 151: 2026-01-01; 152: 2026-01-01; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-11-11; 159: 2025-12-18; 162: 2025-10-25; 163: 2025-11-19; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-12-15; 170: 2025-12-18; 172: 2026-01-20; 173: 2026-02-05; 176: 2025-12-19; 177: 2025-12-21; 179: 2026-02-08; 180: 2026-02-10
90 | PSS-11 | AGE25CL | 1: WTG 454; 2: F03; 3: SHREEJI; 4: 2025-08-31; 5: Keller; 6: Yes; 7: 545326; 8: 2670239; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-23; 18: 2025-05-02; 20: 2025-08-08; 21: 2025-08-26; 32: 2025-05-20; 33: 2025-05-21; 35: 2025-10-16; 36: 2025-10-18; 39: 2025-05-22; 40: 2025-05-22; 42: 2025-10-26; 43: 2025-10-27; 46: 2025-05-23; 47: 2025-05-24; 49: 2025-10-27; 50: 2025-10-27; 53: 2025-05-25; 54: 2025-05-26; 56: 2025-10-28; 57: 2025-10-28; 60: 2025-05-27; 61: 2025-06-06; 63: 2025-10-29; 64: 2025-11-08; 67: 2025-06-07; 68: 2025-06-08; 70: 2025-11-09; 71: 2025-11-10; 75: 2025-06-13; 76: 2025-06-16; 78: 2025-11-22; 82: 2025-06-15; 83: 2025-06-15; 85: 2025-11-23; 86: 2025-11-23; 91: 2025-06-15; 92: 2025-06-25; 94: 2025-10-25; 95: 2025-12-29; 98: 2025-06-10; 99: 2025-06-17; 101: 2025-03-20; 102: 2025-04-15; 105: 2025-06-10; 106: 2025-06-17; 108: 2025-12-24; 109: 2025-12-28; 112: SS Jadeja; 113: 2025-06-12; 114: 2025-06-19; 116: 2025-11-06; 117: 2025-12-27; 120: 2025-11-22; 121: 2025-12-01; 123: 2025-12-27; 124: 2026-01-05; 127: 2025-11-06; 128: 2025-11-14; 130: 2026-01-01; 131: 2026-01-18; 134: 2025-12-02; 135: 2025-12-09; 137: 2026-01-09; 138: 2026-01-12; 141: 2025-12-10; 142: 2025-12-12; 144: 2026-01-13; 145: 2026-01-15; 148: 2025-11-24; 149: 2025-11-25; 151: 2026-01-16; 152: 2026-01-16; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-10-28; 159: 2026-02-01; 162: 2025-10-25; 163: 2025-11-19; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-11-26; 170: 2025-11-29; 172: 2026-01-24; 173: 2026-01-31; 176: 2025-12-13; 177: 2025-12-15; 179: 2026-02-08; 180: 2026-02-09
91 | PSS-11 | AGE25CL | 1: WTG 505; 2: F08; 3: ODHAV; 4: 2025-09-22; 5: Bauer; 6: Yes; 7: 547573; 8: 2666712; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-04; 18: 2025-04-14; 20: 2025-07-11; 21: 2025-07-19; 32: 2025-04-21; 33: 2025-04-22; 35: 2025-09-25; 36: 2025-09-27; 39: 2025-04-23; 40: 2025-04-23; 42: 2025-09-28; 43: 2025-09-28; 46: 2025-04-24; 47: 2025-04-25; 49: 2025-09-29; 50: 2025-09-29; 53: 2025-04-26; 54: 2025-04-27; 56: 2025-10-02; 57: 2025-10-03; 60: 2025-04-28; 61: 2025-05-08; 63: 2025-10-13; 64: 2025-10-31; 67: 2025-05-09; 68: 2025-05-10; 70: 2025-11-02; 71: 2025-11-03; 75: 2025-05-15; 76: 2025-05-18; 78: 2025-11-09; 79: 2026-02-04; 82: 2025-05-17; 83: 2025-05-17; 85: 2025-11-11; 86: 2025-11-11; 91: 2025-05-07; 92: 2025-05-17; 94: 2025-09-29; 95: 2025-11-25; 98: 2025-05-12; 99: 2025-05-19; 101: 2025-03-29; 102: 2025-05-07; 105: 2025-05-12; 106: 2025-05-19; 108: 2025-11-27; 109: 2025-11-28; 112: Bipin; 113: 2025-05-14; 114: 2025-05-21; 116: 2025-11-21; 117: 2025-11-28; 120: 2025-10-26; 121: 2025-11-05; 123: 2025-11-28; 124: 2025-12-10; 127: 2025-11-13; 128: 2025-11-21; 130: 2025-11-27; 131: 2025-12-12; 134: 2025-11-06; 135: 2025-11-13; 137: 2025-12-10; 138: 2025-12-16; 141: 2025-11-14; 142: 2025-11-16; 144: 2025-12-16; 145: 2025-12-18; 148: 2025-12-21; 149: 2025-12-22; 151: 2026-01-04; 152: 2026-01-04; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-11-12; 159: 2025-12-17; 162: 2025-11-15; 163: 2025-12-10; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-12-23; 170: 2025-12-26; 172: 2026-01-22; 173: 2026-02-05; 176: 2025-12-27; 177: 2025-12-29; 179: 2026-02-08; 180: 2026-02-10 | 280
92 | PSS-11 | AGE25CL | 1: WTG 405; 2: F02; 3: ODHAV; 4: 2025-05-24; 5: Keller; 6: Yes; 7: 544031; 8: 2668836; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-16; 18: 2025-04-25; 20: 2025-03-05; 21: 2025-03-17; 32: 2025-05-16; 33: 2025-05-17; 35: 2025-05-26; 36: 2025-05-29; 39: 2025-05-18; 40: 2025-05-18; 42: 2025-05-30; 43: 2025-05-31; 46: 2025-05-19; 47: 2025-05-20; 49: 2025-06-02; 50: 2025-06-02; 53: 2025-05-21; 54: 2025-05-22; 56: 2025-07-16; 57: 2025-07-16; 60: 2025-05-23; 61: 2025-06-02; 63: 2025-07-27; 64: 2025-08-10; 67: 2025-06-03; 68: 2025-06-04; 70: 2025-08-12; 71: 2025-08-13; 75: 2025-06-09; 76: 2025-06-12; 78: 2025-08-21; 79: 2026-02-05; 82: 2025-06-11; 83: 2025-06-11; 85: 2025-11-24; 86: 2025-11-24; 91: 2025-06-11; 92: 2025-06-21; 94: 2025-06-01; 95: 2025-11-22; 98: 2025-06-06; 99: 2025-06-13; 101: 2025-03-24; 102: 2025-04-05; 105: 2025-06-06; 106: 2025-06-13; 108: 2025-11-26; 109: 2025-11-28; 112: GP Project; 113: 2025-06-08; 114: 2025-06-15; 116: 2025-11-01; 117: 2025-11-28; 120: 2025-11-07; 121: 2025-11-17; 123: 2025-11-28; 124: 2025-12-10; 127: 2025-11-01; 128: 2025-11-09; 130: 2025-11-26; 131: 2025-12-19; 134: 2025-11-18; 135: 2025-11-25; 137: 2025-12-13; 138: 2025-12-17; 141: 2025-11-26; 142: 2025-11-28; 144: 2025-12-17; 145: 2025-12-20; 148: 2025-12-09; 149: 2025-12-10; 151: 2025-12-20; 152: 2025-12-20; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-11-25; 159: 2026-01-28; 162: 2025-10-25; 163: 2025-11-19; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-12-11; 170: 2025-12-14; 172: 2026-01-20; 173: 2026-01-31; 176: 2025-12-15; 177: 2025-12-17; 179: 2026-02-06; 180: 2026-02-09
93 | PSS-05 | AHEJ5L | 1: WTG 554; 2: F05; 3: MSC; 4: 2025-10-27; 5: Bauer; 6: Yes; 7: 536274; 8: 2660409; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-16; 18: 2025-03-26; 20: 2025-03-29; 21: 2025-10-27; 32: 2025-03-28; 33: 2025-03-29; 35: 2025-10-28; 36: 2025-10-29; 39: 2025-03-30; 40: 2025-03-30; 42: 2025-10-30; 43: 2025-10-31; 46: 2025-03-31; 47: 2025-04-01; 49: 2025-10-31; 50: 2025-10-31; 53: 2025-04-02; 54: 2025-04-03; 56: 2025-11-01; 57: 2025-11-05; 60: 2025-04-04; 61: 2025-04-14; 63: 2025-11-07; 64: 2025-11-11; 67: 2025-04-15; 68: 2025-04-16; 70: 2025-11-11; 71: 2025-11-11; 75: 2025-04-21; 76: 2025-04-24; 78: 2025-11-13; 79: 2025-12-15; 82: 2025-04-23; 83: 2025-04-23; 85: 2025-11-14; 86: 2025-11-14; 91: 2025-04-25; 92: 2025-05-05; 94: 2025-10-28; 95: 2025-11-24; 98: 2025-04-18; 99: 2025-04-25; 101: 2025-02-25; 102: 2025-03-04; 105: 2025-04-18; 106: 2025-04-25; 108: 2025-11-14; 109: 2025-11-20; 112: GP Project(Reuse); 113: 2025-04-27; 114: 2025-05-04; 116: 2025-11-13; 117: 2025-11-26; 120: 2025-05-30; 121: 2025-06-09; 123: 2025-11-26; 124: 2025-12-09; 127: 2025-06-04; 128: 2025-06-12; 130: 2025-11-27; 131: 2025-12-06; 134: 2025-06-10; 135: 2025-06-17; 137: 2025-12-11; 138: 2025-12-14; 141: 2025-06-18; 142: 2025-06-20; 144: 2025-12-14; 145: 2025-12-16; 148: 2025-06-22; 149: 2025-06-23; 151: 2025-12-12; 152: 2025-12-12; 155: 2025-05-15; 156: 2025-06-07; 158: 2025-05-20; 159: 2025-05-29; 162: 2025-05-15; 163: 2025-06-09; 165: 2025-10-15; 166: 2025-11-08; 169: 2025-06-24; 170: 2025-06-27; 172: 2025-12-15; 173: 2025-12-19; 176: 2025-06-28; 177: 2025-06-30; 179: 2025-12-19; 180: 2025-12-24
94 | PSS-11 | AGE25CL | 1: WTG 480; 2: F04; 3: MSC; 4: 2025-12-22; 5: Keller; 6: Yes; 7: 546350; 8: 2668988; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-27; 18: 2025-05-06; 20: 2025-08-11; 21: 2025-08-22; 24: YES; 25: Keller; 29: 2025-12-09; 30: 2025-12-17; 32: 2025-05-18; 33: 2025-05-19; 35: 2025-12-25; 36: 2025-12-26; 39: 2025-05-20; 40: 2025-05-20; 42: 2025-12-27; 43: 2025-12-27; 46: 2025-05-21; 47: 2025-05-22; 49: 2025-12-27; 50: 2025-12-27; 53: 2025-05-23; 54: 2025-05-24; 56: 2025-12-28; 57: 2025-12-29; 60: 2025-05-25; 61: 2025-06-04; 63: 2025-12-29; 64: 2026-01-07; 67: 2025-06-05; 68: 2025-06-06; 70: 2026-01-08; 71: 2026-01-09; 75: 2025-06-11; 76: 2025-06-14; 78: 2026-01-16; 82: 2025-06-13; 83: 2025-06-13; 85: 2026-01-17; 86: 2026-01-17; 91: 2025-06-13; 92: 2025-06-23; 94: 2025-12-26; 95: 2026-01-09; 98: 2025-06-08; 99: 2025-06-15; 101: Done; 102: Done; 105: 2025-06-08; 106: 2025-06-15; 108: 2026-01-20; 109: 2026-01-22; 112: Vaibhav; 113: 2025-06-10; 114: 2025-06-17; 116: 2026-01-14; 117: 2026-01-23; 120: 2025-11-13; 121: 2025-11-23; 123: 2026-01-24; 124: 2026-01-31; 127: 2025-11-09; 128: 2025-11-17; 130: 2026-01-01; 131: 2026-01-22; 134: 2025-11-24; 135: 2025-12-01; 137: 2026-02-03; 138: 2026-02-08; 141: 2025-12-02; 142: 2025-12-04; 144: 2026-02-09; 145: 2026-02-11; 148: 2025-12-17; 149: 2025-12-18; 151: 2026-01-29; 152: 2026-01-29; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-11-19; 159: 2026-02-02; 162: 2025-11-15; 163: 2025-12-10; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-12-19; 170: 2025-12-22; 172: 2026-01-30; 173: 2026-02-08; 176: 2025-12-23; 177: 2025-12-25; 179: 2026-02-13; 180: 2026-02-19
95 | PSS-11 | AGE25CL | 1: WTG 479; 2: F04; 3: SHREEJI; 4: 2025-08-31; 5: Keller; 6: Yes; 7: 546160; 8: 2669975; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-28; 18: 2025-05-07; 20: 2025-07-29; 21: 2025-08-07; 32: 2025-05-10; 33: 2025-05-11; 35: 2025-10-10; 36: 2025-10-11; 39: 2025-05-12; 40: 2025-05-12; 42: 2025-10-12; 43: 2025-10-13; 46: 2025-05-13; 47: 2025-05-14; 49: 2025-10-14; 50: 2025-10-14; 53: 2025-05-15; 54: 2025-05-16; 56: 2025-10-17; 57: 2025-10-18; 60: 2025-05-17; 61: 2025-05-27; 63: 2025-10-19; 64: 2025-10-29; 67: 2025-05-28; 68: 2025-05-29; 70: 2025-10-30; 71: 2025-10-31; 75: 2025-06-03; 76: 2025-06-06; 78: 2025-11-18; 79: 2026-01-07; 82: 2025-06-05; 83: 2025-06-05; 85: 2025-11-18; 86: 2025-11-18; 91: 2025-06-05; 92: 2025-06-15; 94: 2025-10-29; 95: 2025-11-06; 98: 2025-05-31; 99: 2025-06-07; 101: 2025-03-20; 102: 2025-04-25; 105: 2025-05-31; 106: 2025-06-07; 108: 2025-11-23; 109: 2025-11-28; 112: SS Jadeja; 113: 2025-06-02; 114: 2025-06-09; 116: 2025-11-06; 117: 2025-11-28; 120: 2025-11-28; 121: 2025-12-08; 123: 2025-11-29; 124: 2025-12-09; 127: 2025-11-09; 128: 2025-11-17; 130: 2025-11-13; 131: 2025-12-27; 134: 2025-12-09; 135: 2025-12-16; 137: 2025-12-14; 138: 2025-12-19; 141: 2025-12-17; 142: 2025-12-19; 144: 2025-12-19; 145: 2025-12-21; 148: 2025-12-01; 149: 2025-12-02; 151: 2025-12-29; 152: 2025-12-29; 155: 2025-11-20; 156: 2025-12-10; 158: 2025-11-02; 159: 2026-01-10; 162: 2025-10-25; 163: 2025-11-19; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-11-29; 170: 2025-12-02; 172: 2026-01-22; 173: 2026-02-03; 176: 2025-12-20; 177: 2025-12-22; 179: 2026-02-08; 180: 2026-02-10
96 | PSS-11 | AGE25CL | 1: WTG 482; 2: F08; 3: ODHAV; 4: 2025-12-15; 5: Bauer; 6: Yes; 7: 546731; 8: 2667016; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-15; 18: 2025-04-24; 20: 2025-08-16; 21: 2025-08-27; 24: YES; 25: Bauer; 29: 2025-11-11; 30: 2025-12-11; 32: 2025-04-30; 33: 2025-05-01; 35: 2025-12-19; 36: 2025-12-20; 39: 2025-05-02; 40: 2025-05-02; 42: 2025-12-21; 43: 2025-12-22; 46: 2025-05-03; 47: 2025-05-04; 49: 2025-12-23; 50: 2025-12-23; 53: 2025-05-05; 54: 2025-05-06; 56: 2025-12-25; 57: 2025-12-27; 60: 2025-05-07; 61: 2025-05-17; 63: 2025-12-28; 64: 2026-01-03; 67: 2025-05-18; 68: 2025-05-19; 70: 2026-01-05; 71: 2026-01-06; 75: 2025-05-24; 76: 2025-05-27; 78: 2026-01-10; 79: 2026-02-03; 82: 2025-05-26; 83: 2025-05-26; 85: 2026-01-11; 86: 2026-01-11; 91: 2025-05-11; 92: 2025-05-21; 94: 2025-12-22; 95: 2026-01-03; 98: 2025-05-21; 99: 2025-05-28; 101: 2025-03-29; 102: 2025-05-20; 105: 2025-05-21; 106: 2025-05-28; 108: 2026-01-19; 109: 2026-01-22; 112: Bipin; 113: 2025-05-23; 114: 2025-05-30; 116: 2025-11-30; 117: 2026-01-20; 120: 2025-11-06; 121: 2025-11-16; 123: 2026-01-23; 124: 2026-01-30; 127: 2025-11-11; 128: 2025-11-19; 130: 2026-01-02; 131: 2026-01-22; 134: 2025-11-17; 135: 2025-11-24; 137: 2026-01-31; 138: 2026-02-04; 141: 2025-11-25; 142: 2025-11-27; 144: 2026-02-04; 145: 2026-02-10; 148: 2025-12-19; 149: 2025-12-20; 151: 2026-01-31; 152: 2026-01-31; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-10-29; 159: 2025-12-06; 162: 2025-11-15; 163: 2025-12-10; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-12-21; 170: 2025-12-24; 172: 2026-01-30; 173: 2026-02-05; 176: 2025-12-25; 177: 2025-12-27; 179: 2026-02-10; 180: 2026-02-13
97 | PSS-11 | AGE25CL | 1: WTG 501; 2: F06; 3: BHAVANI; 4: 2025-12-03; 5: Keller; 6: Yes; 7: 546811; 8: 2670657; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-01; 18: 2025-05-11; 20: 2025-09-03; 21: 2025-09-24; 24: YES; 25: Keller; 29: 2025-11-19; 30: 2025-11-30; 32: 2025-05-18; 33: 2025-05-19; 35: 2025-12-04; 36: 2025-12-06; 39: 2025-05-20; 40: 2025-05-20; 42: 2025-12-07; 43: 2025-12-08; 46: 2025-05-21; 47: 2025-05-22; 49: 2025-12-08; 50: 2025-12-09; 53: 2025-05-23; 54: 2025-05-24; 56: 2025-12-10; 57: 2025-12-10; 60: 2025-05-25; 61: 2025-06-04; 63: 2025-12-11; 64: 2025-12-13; 67: 2025-06-05; 68: 2025-06-06; 70: 2025-12-13; 71: 2025-12-14; 75: 2025-06-11; 76: 2025-06-14; 78: 2025-12-18; 79: 2026-02-03; 82: 2025-06-13; 83: 2025-06-13; 85: 2025-12-19; 86: 2025-12-19; 91: 2025-06-08; 92: 2025-06-18; 94: 2025-12-04; 95: 2025-12-29; 98: 2025-06-08; 99: 2025-06-15; 101: 2025-03-22; 102: 2025-05-02; 105: 2025-06-08; 106: 2025-06-15; 108: 2025-12-27; 109: 2025-12-29; 112: Vaibhav; 113: 2025-06-10; 114: 2025-06-17; 116: 2025-12-26; 117: 2025-12-29; 120: 2025-11-15; 121: 2025-11-25; 123: 2026-01-02; 124: 2026-01-11; 127: 2025-11-11; 128: 2025-11-19; 130: 2025-12-30; 131: 2026-01-04; 134: 2025-11-26; 135: 2025-12-03; 137: 2026-01-15; 138: 2026-01-20; 141: 2025-12-04; 142: 2025-12-06; 144: 2026-01-20; 145: 2026-01-21; 148: 2025-12-19; 149: 2025-12-20; 151: 2026-01-13; 152: 2026-01-13; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-11-26; 159: 2026-01-09; 162: 2025-11-15; 163: 2025-12-10; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-12-21; 170: 2025-12-24; 172: 2026-01-22; 173: 2026-02-03; 176: 2025-12-25; 177: 2025-12-27; 179: 2026-02-08; 180: 2026-02-10
98 | PSS-11 | AGE25CL | 1: WTG 502; 2: F04; 3: DNC; 4: 2025-09-22; 5: Keller; 6: Yes; 7: 547001; 8: 2669670; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-18; 18: 2025-04-27; 20: 2025-08-28; 21: 2025-09-11; 32: 2025-05-16; 33: 2025-05-17; 35: 2025-10-15; 36: 2025-10-18; 39: 2025-05-18; 40: 2025-05-18; 42: 2025-10-28; 43: 2025-10-31; 46: 2025-05-19; 47: 2025-05-20; 49: 2025-11-11; 50: 2025-11-12; 53: 2025-05-21; 54: 2025-05-22; 56: 2025-11-12; 57: 2025-11-13; 60: 2025-05-23; 61: 2025-06-02; 63: 2025-11-13; 64: 2025-11-19; 67: 2025-06-03; 68: 2025-06-04; 70: 2025-11-25; 71: 2025-11-26; 75: 2025-06-09; 76: 2025-06-12; 78: 2025-12-09; 79: 2026-01-01; 82: 2025-06-11; 83: 2025-06-11; 85: 2025-12-10; 86: 2025-12-10; 91: 2025-06-06; 92: 2025-06-16; 94: 2025-10-30; 95: 2025-12-26; 98: 2025-06-06; 99: 2025-06-13; 101: 2025-03-22; 102: 2025-04-18; 105: 2025-06-06; 106: 2025-06-13; 108: 2025-12-09; 109: 2025-12-11; 112: GP Project; 113: 2025-06-08; 114: 2025-06-15; 116: 2025-11-05; 117: 2025-12-10; 120: 2025-11-17; 121: 2025-11-27; 123: 2025-12-11; 124: 2025-12-22; 127: 2025-11-10; 128: 2025-11-18; 130: 2025-12-29; 131: 2026-01-01; 134: 2025-11-28; 135: 2025-12-05; 137: 2025-12-24; 138: 2025-12-29; 141: 2025-12-06; 142: 2025-12-08; 144: 2025-12-29; 145: 2025-12-31; 148: 2025-12-18; 149: 2025-12-19; 151: 2026-01-06; 152: 2026-01-06; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-10-27; 159: 2026-01-10; 162: 2025-11-15; 163: 2025-12-10; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-12-20; 170: 2025-12-23; 172: 2026-01-20; 173: 2026-02-03; 176: 2025-12-24; 177: 2025-12-26; 179: 2026-02-08; 180: 2026-02-10
99 | PSS-11 | AGE25CL | 1: WTG 503; 2: F05; 3: HBG; 4: 2025-08-31; 5: Bauer; 6: Yes; 7: 547192; 8: 2668684; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-17; 18: 2025-04-26; 20: 2025-08-13; 21: 2025-08-23; 32: 2025-05-20; 33: 2025-05-21; 35: 2025-09-02; 36: 2025-09-23; 39: 2025-05-22; 40: 2025-05-22; 42: 2025-09-26; 43: 2025-09-28; 46: 2025-05-23; 47: 2025-05-24; 49: 2025-09-29; 50: 2025-09-29; 53: 2025-05-25; 54: 2025-05-26; 56: 2025-10-02; 57: 2025-10-03; 60: 2025-05-27; 61: 2025-06-06; 63: 2025-10-10; 64: 2025-10-22; 67: 2025-06-07; 68: 2025-06-08; 70: 2025-10-23; 71: 2025-10-24; 75: 2025-06-13; 76: 2025-06-16; 78: 2025-11-11; 79: 2026-01-02; 82: 2025-06-15; 83: 2025-06-15; 85: 2025-12-04; 86: 2025-12-04; 91: 2025-06-10; 92: 2025-06-20; 94: 2025-09-28; 95: 2025-11-02; 98: 2025-06-10; 99: 2025-06-17; 101: 2025-12-13; 102: 2025-12-15; 105: 2025-06-10; 106: 2025-06-17; 108: 2025-12-13; 109: 2025-12-15; 112: GP Project; 113: 2025-06-12; 114: 2025-06-19; 116: 2025-11-02; 117: 2025-12-14; 120: 2025-11-09; 121: 2025-11-19; 123: 2025-12-18; 124: 2025-12-27; 127: 2025-11-10; 128: 2025-11-18; 130: 2025-11-25; 131: 2025-12-14; 134: 2025-11-20; 135: 2025-11-27; 137: 2025-12-30; 138: 2026-01-05; 141: 2025-11-28; 142: 2025-11-30; 144: 2026-01-05; 145: 2026-01-07; 148: 2025-12-18; 149: 2025-12-19; 151: 2025-12-15; 152: 2025-12-15; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-11-19; 159: 2026-01-16; 162: 2025-11-15; 163: 2025-12-10; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-12-20; 170: 2025-12-23; 172: 2026-01-08; 173: 2026-02-03; 176: 2025-12-24; 177: 2025-12-26; 179: 2026-02-07; 180: 2026-02-10
100 | PSS-11 | AGE25CL | 1: WTG 504; 2: F05; 3: ODHAV; 4: 2025-09-22; 5: Bauer; 6: Yes; 7: 547382; 8: 2667698; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-26; 18: 2025-05-05; 20: 2025-07-21; 21: 2025-08-01; 32: 2025-05-10; 33: 2025-05-11; 35: 2025-10-06; 36: 2025-10-08; 39: 2025-05-12; 40: 2025-05-12; 42: 2025-10-15; 43: 2025-10-16; 46: 2025-05-13; 47: 2025-05-14; 49: 2025-10-16; 50: 2025-10-16; 53: 2025-05-15; 54: 2025-05-16; 56: 2025-10-31; 57: 2025-11-10; 60: 2025-05-17; 61: 2025-05-27; 63: 2025-11-14; 64: 2025-11-26; 67: 2025-05-28; 68: 2025-05-29; 70: 2025-11-29; 71: 2025-11-30; 75: 2025-06-03; 76: 2025-06-06; 78: 2025-12-05; 79: 2026-02-05; 82: 2025-06-05; 83: 2025-06-05; 85: 2025-12-06; 86: 2025-12-06; 91: 2025-06-05; 92: 2025-06-15; 94: 2025-10-01; 95: 2025-11-02; 98: 2025-05-31; 99: 2025-06-07; 101: 2025-03-22; 102: 2025-04-29; 105: 2025-05-31; 106: 2025-06-07; 108: 2025-12-10; 109: 2025-12-13; 112: GP Project; 113: 2025-06-02; 114: 2025-06-09; 116: 2025-11-05; 117: 2025-12-09; 120: 2025-11-03; 121: 2025-11-13; 123: 2025-12-11; 124: 2025-12-24; 127: 2025-11-12; 128: 2025-11-20; 130: 2025-11-25; 131: 2025-12-08; 134: 2025-11-14; 135: 2025-11-21; 137: 2025-12-26; 138: 2025-12-30; 141: 2025-11-22; 142: 2025-11-24; 144: 2026-12-31; 145: 2026-01-02; 148: 2025-12-20; 149: 2025-12-21; 151: 2025-12-09; 152: 2025-12-09; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-10-27; 159: 2026-01-11; 162: 2025-11-15; 163: 2025-12-10; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-12-22; 170: 2025-12-25; 172: 2026-01-08; 173: 2026-02-03; 176: 2025-12-26; 177: 2025-12-28; 179: 2026-02-07; 180: 2026-02-10
101 | PSS-11 | AGE25CL | 1: WTG 456; 2: F04; 3: SHREEJI; 4: 2025-07-12; 5: Saritha; 6: Yes; 7: 545707; 8: 2668267; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-05; 18: 2025-04-15; 20: 2025-06-09; 21: 2025-06-20; 32: 2025-05-08; 33: 2025-05-09; 35: 2025-07-27; 36: 2025-07-29; 39: 2025-05-10; 40: 2025-05-10; 42: 2025-07-30; 43: 2025-07-30; 46: 2025-05-11; 47: 2025-05-12; 49: 2025-07-31; 50: 2025-07-31; 53: 2025-05-13; 54: 2025-05-14; 56: 2025-08-01; 57: 2025-08-01; 60: 2025-05-15; 61: 2025-05-25; 63: 2025-08-02; 64: 2025-08-10; 67: 2025-05-26; 68: 2025-05-27; 70: 2025-08-11; 71: 2025-08-12; 75: 2025-06-01; 76: 2025-06-04; 78: 2025-11-05; 79: 2026-01-04; 82: 2025-06-03; 83: 2025-06-03; 85: 2025-11-07; 86: 2025-11-07; 91: 2025-05-19; 92: 2025-05-29; 94: 2025-11-06; 95: 2025-12-06; 98: 2025-05-29; 99: 2025-06-05; 101: 2025-03-21; 102: 2025-04-27; 105: 2025-05-29; 106: 2025-06-05; 108: 2025-11-27; 109: 2025-11-30; 112: GP Project; 113: 2025-05-31; 114: 2025-06-07; 116: 2025-10-22; 117: 2025-11-30; 120: 2025-11-25; 121: 2025-12-05; 123: 2025-12-01; 124: 2025-12-11; 127: 2025-11-08; 128: 2025-11-16; 130: 2025-12-09; 131: 2025-12-13; 134: 2025-12-06; 135: 2025-12-13; 137: 2025-12-18; 138: 2025-12-23; 141: 2025-12-14; 142: 2025-12-16; 144: 2025-12-23; 145: 2025-12-25; 148: 2025-12-16; 149: 2025-12-17; 151: 2026-01-07; 152: 2026-01-07; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-10-28; 159: 2026-01-11; 162: 2025-10-25; 163: 2025-11-19; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-12-18; 170: 2025-12-21; 172: 2026-01-23; 173: 2026-02-03; 176: 2025-12-22; 177: 2025-12-24; 179: 2026-02-08; 180: 2026-02-10
102 | PSS-11 | AGE25CL | 1: WTG 522; 2: F06; 3: BHAVANI; 4: 2025-10-07; 5: Keller; 6: Yes; 7: 547645; 8: 2670392; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-20; 18: 2025-04-30; 20: 2025-09-15; 21: 2025-09-26; 32: 2025-05-07; 33: 2025-05-08; 35: 2025-10-11; 36: 2025-10-13; 39: 2025-05-09; 40: 2025-05-09; 42: 2025-10-22; 43: 2025-10-23; 46: 2025-05-10; 47: 2025-05-11; 49: 2025-10-25; 50: 2025-10-26; 53: 2025-05-12; 54: 2025-05-13; 56: 2025-10-27; 57: 2025-10-27; 60: 2025-05-14; 61: 2025-05-24; 63: 2025-10-28; 64: 2025-11-08; 67: 2025-05-25; 68: 2025-05-26; 70: 2025-11-11; 71: 2025-11-11; 75: 2025-05-31; 76: 2025-06-03; 78: 2025-11-17; 79: 2026-01-31; 82: 2025-06-02; 83: 2025-06-02; 85: 2025-11-20; 86: 2025-11-20; 91: 2025-06-02; 92: 2025-06-12; 94: 2025-10-24; 95: 2025-12-30; 98: 2025-05-28; 99: 2025-06-04; 101: 2025-03-23; 102: 2025-05-02; 105: 2025-05-28; 106: 2025-06-04; 108: 2025-12-10; 109: 2025-12-24; 112: Vaibhav; 113: 2025-05-30; 114: 2025-06-06; 116: 2025-12-10; 117: 2025-12-21; 120: 2025-11-26; 121: 2025-12-06; 123: 2025-12-23; 124: 2025-12-31; 127: 2025-11-14; 128: 2025-11-22; 130: 2025-12-31; 131: 2026-01-07; 134: 2025-12-07; 135: 2025-12-14; 137: 2026-01-04; 138: 2026-01-10; 141: 2025-12-15; 142: 2025-12-17; 144: 2026-01-10; 145: 2026-01-12; 148: 2025-12-22; 149: 2025-12-23; 151: 2026-01-17; 152: 2026-01-17; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-11-25; 159: 2026-01-09; 162: 2025-11-15; 163: 2025-12-10; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-12-24; 170: 2025-12-27; 172: 2026-01-24; 173: 2026-02-03; 176: 2025-12-28; 177: 2025-12-30; 179: 2026-02-08; 180: 2026-02-10
103 | PSS-11 | AGE25CL | 1: WTG 523; 2: F05; 3: DNC; 4: 2025-09-22; 5: Bauer; 6: Yes; 7: 547835; 8: 2669406; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-07; 18: 2025-04-17; 20: 2025-08-27; 21: 2025-09-03; 32: 2025-04-25; 33: 2025-04-26; 35: 2025-09-28; 36: 2025-10-02; 39: 2025-04-27; 40: 2025-04-27; 42: 2025-10-06; 43: 2025-10-09; 46: 2025-04-28; 47: 2025-04-29; 49: 2025-10-11; 50: 2025-10-12; 53: 2025-04-30; 54: 2025-05-01; 56: 2025-10-16; 57: 2025-10-16; 60: 2025-05-02; 61: 2025-05-12; 63: 2025-10-19; 64: 2025-10-24; 67: 2025-05-13; 68: 2025-05-14; 70: 2025-10-29; 71: 2025-10-29; 75: 2025-05-19; 76: 2025-05-22; 78: 2025-11-18; 79: 2026-01-04; 82: 2025-05-21; 83: 2025-05-21; 85: 2025-11-15; 86: 2025-11-15; 91: 2025-05-21; 92: 2025-05-31; 94: 2025-10-02; 95: 2025-11-28; 98: 2025-05-16; 99: 2025-05-23; 101: 2025-03-22; 102: 2025-04-27; 105: 2025-05-16; 106: 2025-05-23; 108: 2025-12-07; 109: 2025-12-09; 112: GP Project; 113: 2025-05-18; 114: 2025-05-25; 116: 2025-11-26; 117: 2025-12-05; 120: 2025-11-06; 121: 2025-11-16; 123: 2025-12-09; 124: 2025-12-21; 127: 2025-11-14; 128: 2025-11-22; 130: 2025-11-30; 131: 2025-12-27; 134: 2025-11-17; 135: 2025-11-24; 137: 2025-12-23; 138: 2025-12-27; 141: 2025-11-25; 142: 2025-11-27; 144: 2025-12-27; 145: 2025-12-29; 148: 2025-12-22; 149: 2025-12-23; 151: 2025-12-28; 152: 2025-12-28; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-10-26; 159: 2026-01-29; 162: 2025-11-15; 163: 2025-12-10; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-12-24; 170: 2025-12-27; 172: 2026-01-20; 173: 2026-02-03; 176: 2025-12-28; 177: 2025-12-30; 179: 2026-02-07; 180: 2026-02-10
104 | PSS-11 | AGE25CL | 1: WTG 457; 2: F08; 3: SHREERAM; 4: 2025-10-29; 5: Keller; 6: Yes; 7: 545897; 8: 2667281; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-25; 18: 2025-05-04; 20: 2025-10-16; 21: 2025-10-25; 32: 2025-05-08; 33: 2025-05-09; 35: 2025-11-04; 36: 2025-11-05; 39: 2025-05-10; 40: 2025-05-10; 42: 2025-11-11; 43: 2025-11-12; 46: 2025-05-11; 47: 2025-05-12; 49: 2025-11-12; 50: 2025-11-12; 53: 2025-05-13; 54: 2025-05-14; 56: 2025-11-13; 57: 2025-11-15; 60: 2025-05-15; 61: 2025-05-25; 63: 2025-11-15; 64: 2025-11-21; 67: 2025-05-26; 68: 2025-05-27; 70: 2025-11-23; 71: 2025-11-24; 75: 2025-06-01; 76: 2025-06-04; 78: 2025-11-30; 79: 2026-02-07; 82: 2025-06-03; 83: 2025-06-03; 85: 2025-11-30; 86: 2025-11-30; 91: 2025-06-03; 92: 2025-06-13; 94: 2025-11-23; 95: 2025-12-11; 98: 2025-05-29; 99: 2025-06-05; 101: 2025-03-31; 102: 2025-05-20; 105: 2025-05-29; 106: 2025-06-05; 108: 2025-12-02; 109: 2025-12-06; 112: Bipin; 113: 2025-05-31; 114: 2025-06-07; 116: 2025-11-27; 117: 2025-12-04; 120: 2025-11-17; 121: 2025-11-27; 123: 2025-12-06; 124: 2025-12-13; 127: 2025-11-15; 128: 2025-11-23; 130: 2025-12-13; 131: 2025-12-22; 134: 2025-11-28; 135: 2025-12-05; 137: 2025-12-18; 138: 2025-12-23; 141: 2025-12-06; 142: 2025-12-08; 144: 2025-12-23; 145: 2025-12-25; 148: 2025-12-23; 149: 2025-12-24; 151: 1965-09-27; 152: 2025-12-24; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-10-28; 159: 2025-12-05; 162: 2025-11-15; 163: 2025-12-10; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-12-25; 170: 2025-12-28; 172: 2026-01-12; 173: 2026-02-05; 176: 2025-12-29; 177: 2025-12-31; 179: 2026-02-08; 180: 2026-02-10
105 | PSS-11 | AGE25CL | 1: WTG 455; 2: F03; 3: SHREEJI; 4: 2025-10-13; 5: Saritha; 6: Yes; 7: 545516; 8: 2669253; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-26; 18: 2025-05-05; 20: 2025-06-23; 21: 2025-08-08; 24: YES; 25: Keller; 26: 2025-05-08; 27: 2025-05-16; 29: 2025-10-13; 30: 2025-10-18; 32: 2025-05-20; 33: 2025-05-21; 35: 2025-11-14; 36: 2025-11-15; 39: 2025-05-22; 40: 2025-05-22; 42: 2025-11-16; 43: 2025-11-17; 46: 2025-05-23; 47: 2025-05-24; 49: 2025-11-17; 50: 2025-11-17; 53: 2025-05-25; 54: 2025-05-26; 56: 2025-11-18; 57: 2025-11-19; 60: 2025-05-27; 61: 2025-06-06; 63: 2025-11-20; 64: 2025-11-25; 67: 2025-06-07; 68: 2025-06-08; 70: 2025-11-26; 71: 2025-11-27; 75: 2025-06-13; 76: 2025-06-16; 78: 2025-12-01; 79: 2026-01-05; 82: 2025-06-15; 83: 2025-06-15; 85: 2025-12-04; 86: 2025-12-04; 91: 2025-06-15; 92: 2025-06-25; 94: 2025-11-23; 95: 2025-12-20; 98: 2025-06-10; 99: 2025-06-17; 101: 2025-12-03; 102: 2025-12-07; 105: 2025-06-10; 106: 2025-06-17; 108: 2025-12-05; 109: 2025-12-07; 112: SS Jadeja; 113: 2025-06-12; 114: 2025-06-19; 116: 2025-11-03; 117: 2025-12-05; 120: 2025-11-19; 121: 2025-11-29; 123: 2025-12-07; 124: 2025-12-15; 127: 2025-11-08; 128: 2025-11-16; 130: 2025-12-23; 131: 2025-12-30; 134: 2025-11-30; 135: 2025-12-07; 137: 2025-12-19; 138: 2025-12-24; 141: 2025-12-08; 142: 2025-12-10; 144: 2025-12-24; 145: 2025-12-26; 148: 2025-12-16; 149: 2025-12-17; 151: 2026-01-08; 152: 2026-01-08; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-11-07; 159: 2026-01-28; 162: 2025-10-25; 163: 2025-11-19; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-12-18; 170: 2025-12-21; 172: 2026-01-23; 173: 2026-01-31; 176: 2025-12-22; 177: 2025-12-24; 179: 2026-02-08; 180: 2026-02-09
106 | PSS-12 | AGE26AL | 1: WTG 402; 2: F01; 3: BHAVANI; 4: 2025-12-08; 5: Keller; 6: Yes; 7: 543460; 8: 2671795; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-11; 18: 2025-04-21; 20: 2025-11-26; 21: 2025-12-05; 32: 2025-05-06; 33: 2025-05-07; 35: 2025-12-10; 36: 2025-12-12; 39: 2025-05-08; 40: 2025-05-08; 42: 2025-12-13; 43: 2025-12-14; 46: 2025-05-09; 47: 2025-05-10; 49: 2025-12-17; 50: 2025-12-17; 53: 2025-05-11; 54: 2025-05-12; 56: 2025-12-23; 57: 2025-12-23; 60: 2025-05-13; 61: 2025-05-23; 63: 2025-12-24; 64: 2025-12-29; 67: 2025-05-24; 68: 2025-05-25; 70: 2025-12-29; 71: 2025-12-30; 75: 2025-05-30; 76: 2025-06-02; 78: 2026-01-04; 79: 2026-02-03; 82: 2025-06-01; 83: 2025-06-01; 85: 2026-01-05; 86: 2026-01-05; 91: 2025-05-17; 92: 2025-05-27; 94: 2025-12-16; 95: 2026-01-05; 98: 2025-05-27; 99: 2025-06-03; 101: 2025-03-25; 102: 2025-04-16; 105: 2025-05-27; 106: 2025-06-03; 108: 2026-01-08; 109: 2026-01-11; 112: GP Project; 113: 2025-05-29; 114: 2025-06-05; 116: 2026-01-07; 117: 2026-01-12; 120: 2025-11-20; 121: 2025-11-30; 123: 2026-01-10; 124: 2026-01-21; 127: 2025-10-29; 128: 2025-11-06; 130: 2026-01-06; 131: 2026-01-16; 134: 2025-12-01; 135: 2025-12-08; 137: 2026-01-22; 138: 2026-01-29; 141: 2025-12-09; 142: 2025-12-11; 144: 2026-01-29; 145: 2026-01-31; 148: 2025-12-01; 149: 2025-12-02; 151: 2026-02-01; 152: 2026-02-01; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-12-07; 159: 2026-01-20; 162: 2025-10-25; 163: 2025-11-19; 165: 2025-11-30; 166: 2025-12-19; 169: 2025-12-03; 170: 2025-12-06; 172: 2026-02-05; 176: 2025-12-12; 177: 2025-12-14
107 | PSS-12 | AGE26AL | 1: WTG 428; 2: F02; 3: SHREEJI; 4: 2025-12-03; 5: Saritha; 6: Yes; 7: 544294; 8: 2671530; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-22; 18: 2025-05-01; 20: 2025-11-12; 21: 2025-11-29; 32: 2025-05-08; 33: 2025-05-09; 35: 2025-12-09; 36: 2025-12-10; 39: 2025-05-10; 40: 2025-05-10; 42: 2025-12-11; 43: 2025-12-15; 46: 2025-05-11; 47: 2025-05-12; 49: 2025-12-16; 50: 2025-12-16; 53: 2025-05-13; 54: 2025-05-14; 56: 2025-12-22; 57: 2025-12-23; 60: 2025-05-15; 61: 2025-05-25; 63: 2025-12-24; 64: 2026-01-03; 67: 2025-05-26; 68: 2025-05-27; 70: 2026-01-05; 71: 2026-01-06; 75: 2025-06-01; 76: 2025-06-04; 78: 2026-01-11; 82: 2025-06-03; 83: 2025-06-03; 85: 2026-01-12; 86: 2026-01-12; 91: 2025-05-16; 92: 2025-05-26; 94: 2025-12-10; 95: 2026-01-08; 98: 2025-05-29; 99: 2025-06-05; 101: 2025-03-26; 102: 2025-04-17; 105: 2025-05-29; 106: 2025-06-05; 108: 2026-01-20; 109: 2026-01-26; 112: Odhav; 113: 2025-05-31; 114: 2025-06-07; 116: 2026-01-05; 117: 2026-01-27; 120: 2025-12-01; 121: 2025-12-11; 123: 2026-01-27; 124: 2026-02-17; 127: 2025-11-24; 128: 2025-12-02; 130: 2026-01-15; 131: 2026-01-27; 134: 2025-12-12; 135: 2025-12-19; 137: 2026-02-21; 138: 2026-02-25; 141: 2025-12-20; 142: 2025-12-22; 144: 2026-02-26; 148: 2025-12-27; 149: 2025-12-28; 151: 2026-02-02; 152: 2026-02-02; 155: 2025-11-20; 156: 2025-12-10; 158: 2025-12-08; 159: 2026-01-20; 162: 2025-11-26; 163: 2025-12-21; 165: 2025-11-30; 166: 2025-12-19; 169: 2025-12-29; 170: 2026-01-01; 172: 2026-02-21; 176: 2026-01-02; 177: 2026-01-04
108 | PSS-12 | AGE26AL | 1: WTG 451; 2: F02; 3: SHREEJI; 4: 2026-01-19; 5: Bauer; 6: Yes; 7: 544755; 8: 2673198; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-14; 18: 2025-04-24; 20: 2025-09-26; 21: 2025-10-10; 24: YES; 25: Bauer; 29: 2026-01-01; 30: 2026-01-10; 32: 2025-05-05; 33: 2025-05-06; 35: 2026-01-21; 36: 2026-01-23; 39: 2025-05-07; 40: 2025-05-07; 42: 2026-01-25; 43: 2026-01-26; 46: 2025-05-08; 47: 2025-05-09; 49: 2026-01-28; 50: 2026-01-28; 53: 2025-05-10; 54: 2025-05-11; 56: 2026-01-29; 57: 2026-01-30; 60: 2025-05-12; 61: 2025-05-22; 63: 2026-01-31; 64: 2026-02-05; 67: 2025-05-23; 68: 2025-05-24; 70: 2026-02-05; 71: 2026-02-06; 75: 2025-05-29; 76: 2025-06-01; 78: 2026-02-11; 82: 2025-05-31; 83: 2025-05-31; 85: 2026-02-13; 86: 2026-02-13; 91: 2025-05-16; 92: 2025-05-26; 94: 2026-01-27; 95: 2026-02-07; 98: 2025-05-26; 99: 2025-06-02; 101: 2025-03-26; 102: Done; 105: 2025-05-26; 106: 2025-06-02; 108: 2026-02-18; 112: GP Project; 113: 2025-05-28; 114: 2025-06-04; 116: 2026-02-08; 117: 2026-02-20; 120: 2025-11-24; 121: 2025-12-04; 123: 2026-02-20; 127: 2025-10-29; 128: 2025-11-06; 130: 2026-02-09; 131: 2026-02-24; 134: 2025-12-05; 135: 2025-12-12; 141: 2025-12-13; 142: 2025-12-15; 148: 2025-12-01; 149: 2025-12-02; 151: 2026-02-20; 152: 2026-02-20; 155: 2025-11-20; 156: 2025-12-10; 158: 2025-12-09; 159: 2026-01-20; 162: 2025-10-25; 163: 2025-11-19; 165: 2025-11-30; 166: 2025-12-19; 169: 2025-12-03; 170: 2025-12-06; 176: 2025-12-16; 177: 2025-12-18
109 | PSS-12 | AGE26AL | 1: WTG 452; 2: F02; 3: SHREERAM; 4: 2026-01-03; 5: Bauer; 6: Yes; 7: 544945; 8: 2672212; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-15; 18: 2025-04-24; 20: 2025-11-07; 21: 2025-11-16; 24: YES; 25: Bauer; 29: 2025-12-12; 30: 2026-01-03; 32: 2025-04-30; 33: 2025-05-01; 35: 2026-01-08; 36: 2026-01-09; 39: 2025-05-02; 40: 2025-05-02; 42: 2026-01-09; 43: 2026-01-10; 46: 2025-05-03; 47: 2025-05-04; 49: 2026-01-10; 50: 2026-01-10; 53: 2025-05-05; 54: 2025-05-06; 56: 2026-01-12; 57: 2026-01-14; 60: 2025-05-07; 61: 2025-05-17; 63: 2026-01-19; 64: 2026-01-24; 67: 2025-05-18; 68: 2025-05-19; 70: 2026-01-26; 71: 2026-01-27; 75: 2025-05-24; 76: 2025-05-27; 78: 2026-02-05; 82: 2025-05-26; 83: 2025-05-26; 85: 2026-02-06; 86: 2026-02-06; 91: 2025-05-11; 92: 2025-05-21; 94: 2026-01-26; 95: 2026-01-28; 98: 2025-05-21; 99: 2025-05-28; 101: Done; 102: Done; 105: 2025-05-21; 106: 2025-05-28; 108: 2026-02-17; 112: Odhav; 113: 2025-05-23; 114: 2025-05-30; 116: 2026-01-20; 117: 2026-02-18; 120: 2025-11-24; 121: 2025-12-04; 123: 2026-02-19; 124: 2026-02-28; 127: 2025-10-28; 128: 2025-11-05; 130: 2026-02-01; 131: 2026-02-13; 134: 2025-12-05; 135: 2025-12-12; 141: 2025-12-13; 142: 2025-12-15; 148: 2025-11-30; 149: 2025-12-01; 151: 2026-02-22; 152: 2026-02-22; 155: 2025-11-20; 156: 2025-12-10; 158: 2025-12-26; 159: 2026-01-20; 162: 2025-10-25; 163: 2025-11-19; 165: 2025-11-30; 166: 2025-12-19; 169: 2025-12-02; 170: 2025-12-05; 176: 2025-12-16; 177: 2025-12-18
110 | PSS-12 | AGE26AL | 1: WTG 453; 2: F02; 3: SHREERAM; 4: 2025-12-08; 5: Bauer; 6: Yes; 7: 545136; 8: 2671226; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-02; 18: 2025-04-11; 20: 2025-11-08; 21: 2025-11-16; 32: 2025-04-12; 33: 2025-04-13; 35: 2025-12-20; 36: 2025-12-23; 39: 2025-04-14; 40: 2025-04-14; 42: 2025-12-26; 43: 2025-12-27; 46: 2025-04-15; 47: 2025-04-16; 49: 2025-12-27; 50: 2025-12-27; 53: 2025-04-17; 54: 2025-04-18; 56: 2025-12-28; 57: 2025-12-29; 60: 2025-04-19; 61: 2025-04-29; 63: 2025-12-29; 64: 2026-01-04; 67: 2025-04-30; 68: 2025-05-01; 70: 2026-01-06; 71: 2026-01-07; 75: 2025-05-06; 76: 2025-05-09; 78: 2026-01-25; 82: 2025-05-08; 83: 2025-05-08; 85: 2026-01-25; 86: 2026-01-25; 91: 2025-04-23; 92: 2025-05-03; 94: 2026-01-17; 95: 2026-01-23; 98: 2025-05-03; 99: 2025-05-10; 101: 2025-03-22; 102: 2025-04-16; 105: 2025-05-03; 106: 2025-05-10; 108: 2026-01-20; 109: 2026-01-25; 112: Odhav; 113: 2025-05-05; 114: 2025-05-12; 116: 2026-01-13; 117: 2026-01-26; 120: 2025-12-12; 121: 2025-12-22; 123: 2026-01-26; 124: 2026-02-15; 127: 2025-11-25; 128: 2025-12-03; 130: 2026-01-24; 131: 2026-02-13; 134: 2025-12-23; 135: 2025-12-30; 137: 2026-02-17; 138: 2026-02-21; 141: 2025-12-31; 142: 2026-01-02; 144: 2026-02-21; 145: 2026-02-23; 148: 2025-12-28; 149: 2025-12-29; 151: 2026-02-22; 152: 2026-02-22; 155: 2025-11-20; 156: 2025-12-10; 158: 2025-12-15; 159: 2026-01-20; 162: 2025-11-26; 163: 2025-12-21; 165: 2025-11-30; 166: 2025-12-19; 169: 2025-12-30; 170: 2026-01-02; 172: 2026-02-23; 176: 2026-01-03; 177: 2026-01-05
111 | PSS-14 | AGE25CL | 1: WTG 473; 2: F15; 3: ODHAV; 4: 2026-01-22; 5: ITDC; 6: Yes; 7: 545017; 8: 2675892; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-14; 18: 2025-04-24; 20: 2025-04-09; 21: 2025-05-22; 23: Drwaing received on 8-Apr-25; 24: YES; 25: Keller; 29: 2026-01-10; 30: 2026-01-20; 32: 2025-04-30; 33: 2025-05-01; 35: 2026-02-03; 36: 2026-02-06; 39: 2025-05-02; 40: 2025-05-02; 42: 2026-02-06; 43: 2026-02-07; 46: 2025-05-03; 47: 2025-05-04; 49: 2026-02-08; 50: 2026-02-08; 53: 2025-05-05; 54: 2025-05-06; 56: 2026-02-09; 57: 2026-02-11; 60: 2025-05-07; 61: 2025-05-17; 63: 2026-02-12; 64: 2026-02-18; 67: 2025-05-18; 68: 2025-05-19; 70: 2026-02-23; 71: 2026-02-23; 75: 2025-05-24; 76: 2025-05-27; 82: 2025-05-26; 83: 2025-05-26; 91: 2025-05-08; 92: 2025-05-18; 94: 2026-02-07; 95: 2026-02-10; 98: 2025-05-21; 99: 2025-05-28; 101: 2025-03-20; 102: 2025-05-26; 105: 2025-05-21; 106: 2025-05-28; 112: Odhav(Reuse); 113: 2025-05-23; 114: 2025-05-30; 116: 2026-02-22; 120: 2025-12-09; 121: 2025-12-19; 127: 2025-10-30; 128: 2025-11-07; 130: 2026-02-24; 134: 2025-12-20; 135: 2025-12-27; 141: 2025-12-28; 142: 2025-12-30; 148: 2025-12-11; 149: 2025-12-12; 155: 2025-11-20; 156: 2025-12-10; 158: 2026-01-01; 159: 2026-01-17; 162: 2025-11-15; 163: 2025-12-10; 165: 2026-01-31; 166: 2026-02-15; 169: 2025-12-04; 170: 2025-12-07; 176: 2025-12-31; 177: 2026-01-02
112 | PSS-14 | AGE25CL | 1: WTG 474; 2: F15; 3: ODHAV; 4: 2026-01-18; 5: ITDC; 6: Yes; 7: 545208; 8: 2674906; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-20; 18: 2025-04-30; 20: 2025-05-23; 21: 2025-06-19; 24: YES; 25: Keller; 29: 2026-01-03; 30: 2026-01-14; 32: 2025-05-05; 33: 2025-05-06; 35: 2026-01-21; 36: 2026-01-22; 39: 2025-05-07; 40: 2025-05-07; 42: 2026-01-23; 43: 2026-01-24; 46: 2025-05-08; 47: 2025-05-09; 49: 2026-01-25; 50: 2026-01-25; 53: 2025-05-10; 54: 2025-05-11; 56: 2026-01-31; 57: 2026-01-31; 60: 2025-05-12; 61: 2025-05-22; 63: 2026-02-03; 64: 2026-02-07; 67: 2025-05-23; 68: 2025-05-24; 70: 2026-02-14; 71: 2026-02-15; 75: 2025-05-29; 76: 2025-06-01; 78: 2026-02-25; 82: 2025-05-31; 83: 2025-05-31; 85: 2026-02-26; 86: 2026-02-26; 91: 2025-05-16; 92: 2025-05-26; 94: 2026-01-24; 95: 2026-02-19; 98: 2025-05-26; 99: 2025-06-02; 101: Done; 102: Done; 105: 2025-05-26; 106: 2025-06-02; 108: 2026-02-19; 109: 2026-02-22; 112: Odhav(Reuse); 113: 2025-05-28; 114: 2025-06-04; 116: 2026-02-03; 117: 2026-02-22; 120: 2025-11-28; 121: 2025-12-08; 127: 2025-11-25; 128: 2025-12-03; 130: 0; 134: 2025-12-09; 135: 2025-12-16; 141: 2025-12-17; 142: 2025-12-19; 148: 2025-12-28; 149: 2025-12-29; 155: 2025-11-20; 156: 2025-12-10; 158: 2026-01-03; 162: 2025-11-26; 163: 2025-12-21; 165: 2026-01-31; 166: 2026-02-15; 169: 2025-12-30; 170: 2026-01-02; 176: 2026-01-03; 177: 2026-01-05
113 | PSS-12 | AGE26AL | 1: WTG 475; 2: F06; 3: MSC; 4: 2025-09-23; 5: Bauer; 6: Yes; 7: 545398; 8: 2673919; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-16; 18: 2025-04-26; 20: 2025-08-05; 21: 2025-08-17; 32: 2025-05-30; 33: 2025-05-31; 35: 2025-10-03; 36: 2025-10-05; 39: 2025-06-01; 40: 2025-06-01; 42: 2025-10-07; 43: 2025-10-08; 46: 2025-06-02; 47: 2025-06-03; 49: 2025-10-21; 50: 2025-10-21; 53: 2025-06-04; 54: 2025-06-05; 56: 2025-11-03; 57: 2025-11-04; 60: 2025-06-06; 61: 2025-06-16; 63: 2025-11-05; 64: 2025-11-18; 67: 2025-06-17; 68: 2025-06-18; 70: 2025-11-21; 71: 2025-11-22; 75: 2025-06-23; 76: 2025-06-26; 78: 2025-12-17; 82: 2025-06-25; 83: 2025-06-25; 85: 2025-12-18; 86: 2025-12-18; 91: 2025-06-02; 92: 2025-06-12; 94: 2025-10-05; 95: 2026-01-07; 98: 2025-06-20; 99: 2025-06-27; 101: 2025-03-22; 102: 2025-03-27; 105: 2025-06-20; 106: 2025-06-27; 108: 2026-01-19; 109: 2026-01-22; 112: Odhav; 113: 2025-06-22; 114: 2025-06-29; 116: 2026-01-11; 117: 2026-01-12; 120: 2025-11-29; 121: 2025-12-09; 123: 2026-01-21; 124: 2026-01-29; 127: 2025-11-28; 128: 2025-12-06; 130: 2026-01-09; 131: 2026-01-15; 134: 2025-12-10; 135: 2025-12-17; 137: 2026-01-30; 138: 2026-02-06; 141: 2025-12-18; 142: 2025-12-20; 144: 2026-02-11; 145: 2026-02-13; 148: 2025-12-16; 149: 2025-12-17; 151: 2026-01-31; 152: 2026-01-31; 155: 2025-11-20; 156: 2025-12-10; 158: 2025-11-20; 159: 2026-01-20; 162: 2025-11-15; 163: 2025-12-10; 165: 2025-11-30; 166: 2025-12-19; 169: 2025-12-18; 170: 2025-12-21; 172: 2026-02-05; 173: 2026-02-18; 176: 2025-12-22; 177: 2025-12-24
114 | PSS-12 | AGE26AL | 1: WTG 476; 2: F03; 3: SHREERAM; 4: 2025-11-10; 5: Keller; 6: Yes; 7: 545589; 8: 2672933; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-25; 18: 2025-05-04; 20: 2025-10-07; 21: 2025-10-17; 32: 2025-05-10; 33: 2025-05-11; 35: 2025-12-01; 36: 2025-12-03; 39: 2025-05-12; 40: 2025-05-12; 42: 2025-12-10; 43: 2025-12-12; 46: 2025-05-13; 47: 2025-05-14; 49: 2025-12-13; 50: 2025-12-13; 53: 2025-05-15; 54: 2025-05-16; 56: 2025-12-18; 57: 2025-12-18; 60: 2025-05-17; 61: 2025-05-27; 63: 2025-12-20; 64: 2025-12-24; 67: 2025-05-28; 68: 2025-05-29; 70: 2025-12-25; 71: 2025-12-26; 75: 2025-06-03; 76: 2025-06-06; 78: 2026-01-15; 82: 2025-06-05; 83: 2025-06-05; 85: 2026-01-20; 86: 2026-01-20; 91: 2025-05-21; 92: 2025-05-31; 94: 2025-12-01; 95: 2026-01-16; 98: 2025-05-31; 99: 2025-06-07; 101: 2025-03-22; 102: 2025-04-14; 105: 2025-05-31; 106: 2025-06-07; 108: 2026-01-26; 109: 2026-01-30; 112: SS Jadeja; 113: 2025-06-02; 114: 2025-06-09; 116: 2026-01-03; 117: 2026-01-23; 120: 2025-12-05; 121: 2025-12-15; 123: 2026-01-31; 124: 2026-02-17; 127: 2025-11-27; 128: 2025-12-05; 130: 2026-01-17; 131: 2026-01-28; 134: 2025-12-16; 135: 2025-12-23; 137: 2026-02-21; 138: 2026-02-26; 141: 2025-12-24; 142: 2025-12-26; 144: 2026-02-27; 148: 2025-12-30; 149: 2025-12-31; 155: 2025-11-20; 156: 2025-12-10; 158: 2025-12-17; 159: 2025-12-22; 162: 2025-11-26; 163: 2025-12-21; 165: 2025-11-30; 166: 2025-12-19; 169: 2026-01-01; 170: 2026-01-04; 176: 2026-01-05; 177: 2026-01-07
115 | PSS-12 | AGE26AL | 1: WTG 477; 2: F03; 3: MSC; 4: 2025-12-22; 5: Bauer; 6: Yes; 7: 545779; 8: 2671947; 12: Done; 13: Done; 15: 434; 16: 434; 17: 2025-04-25; 18: 2025-05-04; 20: 2025-10-13; 21: 2025-10-24; 24: YES; 25: Bauer; 29: 21-11-2025 10-Jan-26; 30: 13-12-2025 15-Jan-26; 32: 2025-06-04; 33: 2025-06-05; 35: 2026-01-17; 36: 2026-01-18; 39: 2025-06-06; 40: 2025-06-06; 42: 2026-01-18; 43: 2026-01-19; 46: 2025-06-07; 47: 2025-06-08; 49: 2026-01-20; 50: 2026-01-20; 53: 2025-06-09; 54: 2025-06-10; 56: 2026-01-22; 57: 2026-01-22; 60: 2025-06-11; 61: 2025-06-21; 63: 2026-01-26; 64: 2026-02-11; 67: 2025-06-22; 68: 2025-06-23; 70: 2026-02-12; 71: 2026-02-13; 75: 2025-06-28; 76: 2025-07-01; 78: 2026-02-16; 82: 2025-06-30; 83: 2025-06-30; 85: 2026-02-17; 86: 2026-02-17; 91: 2025-06-15; 92: 2025-06-25; 94: 2026-01-19; 95: 2026-01-24; 98: 2025-06-25; 99: 2025-07-02; 101: Done; 102: Done; 105: 2025-06-25; 106: 2025-07-02; 108: 2026-02-21; 109: 2026-02-23; 112: Bipin; 113: 2025-06-27; 114: 2025-07-04; 116: 2026-01-14; 117: 2026-02-23; 120: 2025-12-05; 121: 2025-12-15; 123: 2026-02-23; 127: 2025-11-29; 128: 2025-12-07; 130: 2026-01-24; 131: 2026-02-12; 134: 2025-12-16; 135: 2025-12-23; 141: 2025-12-24; 142: 2025-12-26; 148: 2026-01-01; 149: 2026-01-02; 151: 2026-02-04; 152: 2026-02-04; 155: 2025-11-20; 156: 2025-12-10; 158: 2025-12-18; 159: 2026-01-22; 162: 2025-11-26; 163: 2025-12-21; 165: 2025-11-30; 166: 2025-12-19; 169: 2026-01-03; 170: 2026-01-06; 172: 2026-02-23; 176: 2026-01-07; 177: 2026-01-09; 184: Extra stone column number 181, with a length of 12 meters.Finish by keller (Date:22-Dec-25 to 30-Dec-25) Start by bauer(181) Date-22-12-25
116 | PSS-12 | AGE26AL | 1: WTG 478; 2: F03; 3: ODHAV; 4: 2025-11-11; 5: Bauer; 6: Yes; 7: 545969; 8: 2670961; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-12; 18: 2025-05-21; 20: 2025-10-25; 21: 2025-11-07; 32: 2025-06-04; 33: 2025-06-05; 35: 2025-11-23; 36: 2025-11-26; 39: 2025-06-06; 40: 2025-06-06; 42: 2025-11-27; 43: 2025-11-29; 46: 2025-06-07; 47: 2025-06-08; 49: 2025-12-02; 50: 2025-12-02; 53: 2025-06-09; 54: 2025-06-10; 56: 2025-12-05; 57: 2025-12-05; 60: 2025-06-11; 61: 2025-06-21; 63: 2025-12-11; 64: 2025-12-16; 67: 2025-06-22; 68: 2025-06-23; 70: 2025-12-16; 71: 2025-12-17; 75: 2025-06-28; 76: 2025-07-01; 78: 2025-12-23; 79: 2026-02-06; 82: 2025-06-30; 83: 2025-06-30; 85: 2025-12-24; 86: 2025-12-24; 91: 2025-06-15; 92: 2025-06-25; 94: 2025-12-28; 95: 2026-01-10; 98: 2025-06-25; 99: 2025-07-02; 101: 2025-03-26; 102: 2025-04-28; 105: 2025-06-25; 106: 2025-07-02; 108: 2026-01-10; 109: 2026-01-14; 112: SS Jadeja; 113: 2025-06-27; 114: 2025-07-04; 116: 2026-01-11; 117: 2026-01-14; 120: 2025-12-08; 121: 2025-12-18; 123: 2026-01-13; 124: 2026-01-23; 127: 2025-11-30; 128: 2025-12-08; 130: 2026-01-14; 131: 2026-01-22; 134: 2025-12-19; 135: 2025-12-26; 137: 2026-01-24; 138: 2026-01-31; 141: 2025-12-27; 142: 2025-12-29; 144: 2026-01-31; 145: 2026-02-02; 147: Material requeid; 148: 2026-01-02; 149: 2026-01-03; 151: 2026-02-01; 152: 2026-02-01; 155: 2025-11-20; 156: 2025-12-10; 158: 2025-12-18; 159: 2026-01-22; 162: 2025-11-26; 163: 2025-12-21; 165: 2025-11-30; 166: 2025-12-19; 169: 2026-01-04; 170: 2026-01-07; 172: 2026-02-05; 176: 2026-01-08; 177: 2026-01-10
117 | PSS-12 | AGE26AL | 1: WTG 496; 2: F06; 3: BHAVANI; 4: 2025-09-22; 5: Bauer; 6: Yes; 7: 545858; 8: 2675587; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-25; 18: 2025-05-05; 20: 2025-07-17; 21: 2025-08-02; 32: 2025-06-06; 33: 2025-06-07; 35: 2025-09-24; 36: 2025-09-28; 39: 2025-06-08; 40: 2025-06-08; 42: 2025-09-29; 43: 2025-10-02; 46: 2025-06-09; 47: 2025-06-10; 49: 2025-10-05; 50: 2025-10-05; 53: 2025-06-11; 54: 2025-06-12; 56: 2025-10-06; 57: 2025-10-06; 60: 2025-06-13; 61: 2025-06-23; 63: 2025-10-08; 64: 2025-10-15; 67: 2025-06-24; 68: 2025-06-25; 70: 2025-10-16; 71: 2025-10-17; 75: 2025-06-30; 76: 2025-07-03; 78: 2025-11-07; 79: 2026-02-23; 82: 2025-07-02; 83: 2025-07-02; 85: 2025-11-14; 86: 2025-11-14; 91: 2025-06-17; 92: 2025-06-27; 94: 2025-09-30; 95: 2025-12-24; 98: 2025-06-27; 99: 2025-07-04; 101: 2025-03-19; 102: 2025-05-06; 105: 2025-06-27; 106: 2025-07-04; 108: 2026-01-12; 109: 2026-01-15; 112: Bipin; 113: 2025-06-29; 114: 2025-07-06; 116: 2025-12-28; 117: 2026-01-15; 120: 2025-12-20; 121: 2025-12-30; 123: 2026-01-24; 124: 2026-02-05; 127: 2025-12-01; 128: 2025-12-09; 130: 2025-12-31; 131: 2026-01-18; 134: 2025-12-31; 135: 2026-01-07; 137: 2026-02-07; 138: 2026-02-13; 141: 2026-01-08; 142: 2026-01-10; 144: 2026-02-14; 145: 2026-02-17; 148: 2026-01-03; 149: 2026-01-04; 151: 2026-02-03; 152: 2026-02-03; 155: 2025-11-20; 156: 2025-12-10; 158: 2025-11-20; 159: 2026-01-22; 162: 2025-11-26; 163: 2025-12-21; 165: 2025-11-30; 166: 2025-12-19; 169: 2026-01-05; 170: 2026-01-08; 172: 2026-02-13; 173: 2026-02-18; 176: 2026-01-11; 177: 2026-01-13
118 | PSS-12 | AGE26AL | 1: WTG 497; 2: F06; 3: ODHAV; 4: 2026-01-09; 5: Bauer; 6: Yes; 7: 546049; 8: 2674601; 12: Done; 13: Done; 15: 253; 16: 434; 17: 2025-05-01; 18: 2025-05-10; 20: 2025-07-05; 21: 2025-07-17; 24: YES; 25: PINNACLE/Bauer; 29: 07-11-2025 2-Jan-26; 30: 14-11-2025 7-Jan-26; 32: 2025-06-08; 33: 2025-06-09; 35: 2026-01-13; 36: 2026-01-15; 39: 2025-06-10; 40: 2025-06-10; 42: 2026-01-16; 43: 2026-01-22; 45: delay due to material shortage; 46: 2025-06-11; 47: 2025-06-12; 49: 2026-01-22; 50: 2026-01-22; 53: 2025-06-13; 54: 2025-06-14; 56: 2026-01-24; 57: 2026-01-24; 60: 2025-06-15; 61: 2025-06-25; 63: 2026-01-31; 64: 2026-02-07; 67: 2025-06-26; 68: 2025-06-27; 70: 2026-02-11; 71: 2026-02-12; 75: 2025-07-02; 76: 2025-07-05; 78: 2026-02-18; 82: 2025-07-04; 83: 2025-07-04; 85: 2026-02-20; 86: 2026-02-20; 91: 2025-06-19; 92: 2025-06-29; 94: 2026-01-21; 95: 2026-02-06; 98: 2025-06-29; 99: 2025-07-06; 101: Done; 102: Done; 105: 2025-06-29; 106: 2025-07-06; 108: 2026-02-18; 112: Bipin; 113: 2025-07-01; 114: 2025-07-08; 116: 2026-01-20; 117: 2026-02-18; 120: 2025-12-09; 121: 2025-12-19; 123: 2026-02-20; 127: 2025-12-01; 128: 2025-12-09; 130: 2026-02-10; 134: 2025-12-20; 135: 2025-12-27; 141: 2025-12-28; 142: 2025-12-30; 148: 2026-01-03; 149: 2026-01-04; 151: 2026-02-21; 152: 2026-02-21; 155: 2025-11-20; 156: 2025-12-10; 158: 2025-11-22; 159: 2026-01-22; 162: 2025-11-26; 163: 2025-12-21; 165: 2025-11-30; 166: 2025-12-19; 169: 2026-01-05; 170: 2026-01-08; 172: 2026-02-21; 176: 2026-01-09; 177: 2026-01-11; 184: Extra stone column start 11-Dec-25 by keller(Scope-181) Finish by 18-Dec-25 2.PLT executed by Bauer 2-Jan-26 to 7-Jan-26
119 | PSS-11 | AGE25CL | 1: WTG 524; 2: F06; 3: HBG; 4: 2025-08-31; 5: Bauer; 6: Yes; 7: 548026; 8: 2668420; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-06; 18: 2025-04-16; 20: 2025-08-03; 21: 2025-08-12; 32: 2025-04-25; 33: 2025-04-26; 35: 2025-09-23; 36: 2025-10-07; 38: Delay due to dewatering required; 39: 2025-04-27; 40: 2025-04-27; 42: 2025-10-08; 43: 2025-10-09; 46: 2025-04-28; 47: 2025-04-29; 49: 2025-10-11; 50: 2025-10-12; 53: 2025-04-30; 54: 2025-05-01; 56: 2025-10-29; 57: 2025-10-30; 60: 2025-05-02; 61: 2025-05-12; 63: 2025-11-01; 64: 2025-11-11; 67: 2025-05-13; 68: 2025-05-14; 70: 2025-11-12; 71: 2025-11-13; 75: 2025-05-19; 76: 2025-05-22; 78: 2025-11-18; 79: 2026-01-02; 82: 2025-05-21; 83: 2025-05-21; 85: 2025-12-04; 86: 2025-12-04; 91: 2025-05-21; 92: 2025-05-31; 94: 2025-10-09; 95: 2025-12-26; 98: 2025-05-16; 99: 2025-05-23; 101: 2025-12-06; 102: 2025-12-10; 105: 2025-05-16; 106: 2025-05-23; 108: 2025-12-06; 109: 2025-12-10; 112: Vaibhav; 113: 2025-05-18; 114: 2025-05-25; 116: 2025-11-26; 117: 2025-12-07; 120: 2025-10-29; 121: 2025-11-08; 123: 2025-12-14; 124: 2025-12-25; 127: 2025-11-13; 128: 2025-11-21; 130: 2025-12-28; 131: 2026-01-02; 134: 2025-11-09; 135: 2025-11-16; 137: 2025-12-30; 138: 2026-01-06; 141: 2025-11-17; 142: 2025-11-19; 144: 2026-01-06; 145: 2026-01-09; 148: 2025-12-21; 149: 2025-12-22; 151: 2026-01-05; 152: 2026-01-05; 155: 2025-10-20; 156: 2025-11-10; 158: 2025-11-24; 159: 2025-12-26; 162: 2025-11-15; 163: 2025-12-10; 165: 2025-10-30; 166: 2025-11-30; 169: 2025-12-23; 170: 2025-12-26; 172: 2026-01-21; 173: 2026-02-03; 176: 2025-12-27; 177: 2025-12-29; 179: 2026-02-08; 180: 2026-02-10
120 | PSS-12 | AGE26AL | 1: WTG 499; 2: F03; 3: SHREERAM; 4: 2025-12-03; 5: Bauer; 6: Yes; 7: 546430; 8: 2672629; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-05; 18: 2025-05-14; 20: 2025-11-10; 21: 2025-11-17; 32: 2025-06-09; 33: 2025-06-10; 35: 2025-12-28; 36: 2025-12-29; 39: 2025-06-11; 40: 2025-06-11; 42: 2025-12-30; 43: 2025-12-31; 46: 2025-06-12; 47: 2025-06-13; 49: 2026-01-03; 50: 2026-01-03; 53: 2025-06-14; 54: 2025-06-15; 56: 2026-01-05; 57: 2026-01-06; 60: 2025-06-16; 61: 2025-06-26; 63: 2026-01-07; 64: 2026-01-13; 67: 2025-06-27; 68: 2025-06-28; 70: 2026-01-15; 71: 2026-01-17; 75: 2025-07-03; 76: 2025-07-06; 78: 2026-01-26; 82: 2025-07-05; 83: 2025-07-05; 85: 2026-01-26; 86: 2026-01-26; 91: 2025-06-20; 92: 2025-06-30; 94: 2026-01-02; 95: 2026-02-02; 98: 2025-06-30; 99: 2025-07-07; 101: 2025-03-24; 102: 2025-04-27; 105: 2025-06-30; 106: 2025-07-07; 108: 2026-01-31; 109: 2026-02-03; 112: SS Jadeja; 113: 2025-07-02; 114: 2025-07-09; 116: 2026-01-04; 117: 2026-01-23; 120: 2025-12-16; 121: 2025-12-26; 123: 2026-02-10; 124: 2026-02-17; 127: 2025-10-28; 128: 2025-11-05; 130: 2026-02-07; 131: 2026-02-11; 134: 2025-12-27; 135: 2026-01-03; 137: 2026-02-20; 138: 2026-02-25; 141: 2026-01-04; 142: 2026-01-06; 144: 2026-02-25; 145: 2026-02-27; 148: 2025-12-23; 149: 2025-12-24; 151: 2026-02-21; 152: 2026-02-21; 155: 2025-11-20; 156: 2025-12-10; 158: 2025-12-09; 159: 2026-01-01; 162: 2025-11-26; 163: 2025-12-21; 165: 2025-11-30; 166: 2025-12-19; 169: 2025-12-02; 170: 2025-12-05; 172: 2026-02-23; 176: 2026-01-07; 177: 2026-01-09
121 | PSS-12 | AGE26AL | 1: WTG 500; 2: F03; 3: MSC; 4: 2025-12-08; 5: Keller; 6: Yes; 7: 546620; 8: 2671643; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-05; 18: 2025-05-14; 20: 2025-11-12; 21: 2025-11-23; 24: YES; 25: Keller; 29: 2025-12-01; 30: 2025-12-08; 32: 2025-06-10; 33: 2025-06-11; 35: 2025-12-09; 36: 2025-12-15; 38: wip; 39: 2025-06-12; 40: 2025-06-12; 42: 2025-12-16; 43: 2025-12-16; 46: 2025-06-13; 47: 2025-06-14; 49: 2025-12-20; 50: 2025-12-21; 53: 2025-06-15; 54: 2025-06-16; 56: 2025-12-23; 57: 2025-12-24; 60: 2025-06-17; 61: 2025-06-27; 63: 2025-12-26; 64: 2025-12-30; 67: 2025-06-28; 68: 2025-06-29; 70: 2026-01-02; 71: 2026-01-03; 75: 2025-07-04; 76: 2025-07-07; 78: 2026-01-15; 82: 2025-07-06; 83: 2025-07-06; 85: 2026-01-16; 86: 2026-01-16; 91: 2025-06-18; 92: 2025-06-28; 94: 2025-12-24; 95: 2026-01-31; 98: 2025-07-01; 99: 2025-07-08; 101: Done; 102: Done; 105: 2025-07-01; 106: 2025-07-08; 108: 2026-01-22; 109: 2026-01-31; 112: SS Jadeja; 113: 2025-07-03; 114: 2025-07-10; 116: 2026-01-14; 117: 2026-01-23; 120: 2025-12-16; 121: 2025-12-26; 123: 2026-01-31; 124: 2026-02-17; 127: 2025-12-02; 128: 2025-12-10; 130: 2026-02-01; 131: 2026-02-22; 134: 2025-12-27; 135: 2026-01-03; 137: 2026-02-20; 138: 2026-02-24; 141: 2026-01-04; 142: 2026-01-06; 144: 2026-02-24; 145: 2026-02-26; 148: 2026-01-04; 149: 2026-01-05; 151: 2026-02-20; 152: 2026-02-20; 155: 2025-11-20; 156: 2025-12-10; 158: 2025-12-21; 159: 2026-01-22; 162: 2025-11-26; 163: 2025-12-21; 165: 2025-11-30; 166: 2025-12-19; 169: 2026-01-06; 170: 2026-01-09; 172: 2026-02-23; 176: 2026-01-10; 177: 2026-01-12
122 | PSS-12 | AGE26AL | 1: WTG 517; 2: F06; 3: BHAVANI; 4: 2026-01-09; 5: Bauer; 6: Yes; 7: 546692; 8: 2675323; 12: Done; 13: Done; 15: 303; 16: 303; 17: 2025-05-06; 18: 2025-05-16; 20: 2025-07-25; 21: 2025-08-06; 24: YES; 25: PINNACLE; 29: 2025-11-12; 30: 2025-12-07; 32: 2025-06-10; 33: 2025-06-11; 35: 2026-01-20; 36: 2026-01-21; 39: 2025-06-12; 40: 2025-06-12; 42: 2026-01-22; 43: 2026-01-24; 46: 2025-06-13; 47: 2025-06-14; 49: 2026-01-24; 50: 2026-01-24; 53: 2025-06-15; 54: 2025-06-16; 56: 2026-01-29; 57: 2026-01-30; 60: 2025-06-17; 61: 2025-06-27; 63: 2026-01-30; 64: 2026-02-05; 67: 2025-06-28; 68: 2025-06-29; 70: 2026-02-08; 71: 2026-02-09; 74: Delay due to not available acc concarate; 75: 2025-07-04; 76: 2025-07-07; 78: 2026-02-13; 82: 2025-07-06; 83: 2025-07-06; 85: 2026-02-14; 86: 2026-02-14; 91: 2025-06-20; 92: 2025-06-30; 94: 2026-01-23; 95: 2026-01-29; 98: 2025-07-01; 99: 2025-07-08; 101: 2025-03-18; 102: 2025-05-06; 105: 2025-07-01; 106: 2025-07-08; 108: 2026-01-17; 109: 2026-02-01; 112: Vaibhav; 113: 2025-07-03; 114: 2025-07-10; 116: 2026-01-03; 117: 2026-01-19; 120: 2025-12-19; 121: 2025-12-29; 123: 2026-02-19; 127: 2025-12-03; 128: 2025-12-11; 130: 2026-02-01; 134: 2025-12-30; 135: 2026-01-06; 141: 2026-01-07; 142: 2026-01-09; 148: 2026-01-05; 149: 2026-01-06; 151: 2026-02-20; 152: 2026-02-20; 155: 2025-11-20; 156: 2025-12-10; 158: 2025-11-23; 159: 2026-01-22; 162: 2025-11-26; 163: 2025-12-21; 165: 2025-11-30; 166: 2025-12-19; 169: 2026-01-07; 170: 2026-01-10; 176: 2026-01-11; 177: 2026-01-13
123 | PSS-12 | AGE26AL | 1: WTG 518; 2: F05; 3: SHREEJI; 4: 2025-09-22; 5: Bauer; 6: Yes; 7: 546883; 8: 2674337; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-11; 18: 2025-05-20; 20: 2025-07-13; 21: 2025-07-23; 32: 2025-05-25; 33: 2025-05-26; 35: 2025-10-01; 36: 2025-10-06; 39: 2025-05-27; 40: 2025-05-27; 42: 2025-10-08; 43: 2025-10-09; 46: 2025-05-28; 47: 2025-05-29; 49: 2025-10-10; 50: 2025-10-10; 53: 2025-05-30; 54: 2025-05-31; 56: 2025-10-12; 57: 2025-10-12; 60: 2025-06-01; 61: 2025-06-11; 63: 2025-10-13; 64: 2025-10-18; 67: 2025-06-12; 68: 2025-06-13; 70: 2025-10-18; 71: 2025-10-19; 75: 2025-06-18; 76: 2025-06-21; 78: 2025-11-18; 79: 2026-02-05; 82: 2025-06-20; 83: 2025-06-20; 85: 2025-11-27; 86: 2025-11-27; 91: 2025-06-05; 92: 2025-06-15; 94: 2025-10-05; 95: 2025-12-27; 98: 2025-06-15; 99: 2025-06-22; 101: 2025-12-07; 102: 2025-12-10; 105: 2025-06-15; 106: 2025-06-22; 108: 2025-12-06; 109: 2025-12-10; 112: Vaibhav; 113: 2025-06-17; 114: 2025-06-24; 116: 2025-12-03; 117: 2025-12-10; 120: 2025-12-20; 121: 2025-12-30; 123: 2025-12-17; 124: 2025-12-29; 127: 2025-12-03; 128: 2025-12-11; 130: 2025-12-27; 131: 2026-01-06; 134: 2025-12-31; 135: 2026-01-07; 137: 2026-01-03; 138: 2026-01-09; 141: 2026-01-08; 142: 2026-01-10; 144: 2026-01-09; 145: 2026-01-11; 148: 2026-01-05; 149: 2026-01-06; 151: 2026-01-15; 152: 2026-01-15; 155: 2025-11-20; 156: 2025-12-10; 158: 2025-11-11; 159: 2026-01-22; 162: 2025-11-26; 163: 2025-12-21; 165: 2025-11-30; 166: 2025-12-19; 169: 2026-01-07; 170: 2026-01-10; 172: 2026-02-05; 173: 2026-02-14; 176: 2026-01-11; 177: 2026-01-13
124 | PSS-12 | AGE26AL | 1: WTG 519; 2: F05; 3: SHREEJI; 4: 2025-10-13; 5: Bauer; 6: Yes; 7: 547073; 8: 2673350; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-07; 18: 2025-05-16; 20: 2025-09-23; 21: 2025-10-06; 32: 2025-05-24; 33: 2025-05-25; 35: 2025-11-22; 36: 2025-11-24; 39: 2025-05-26; 40: 2025-05-26; 42: 2025-11-25; 43: 2025-11-28; 46: 2025-05-27; 47: 2025-05-28; 49: 2025-11-29; 50: 2025-11-29; 53: 2025-05-29; 54: 2025-05-30; 56: 2025-12-06; 57: 2025-12-06; 60: 2025-05-31; 61: 2025-06-10; 63: 2025-12-08; 64: 2025-12-13; 67: 2025-06-11; 68: 2025-06-12; 70: 2025-12-14; 71: 2025-12-14; 75: 2025-06-17; 76: 2025-06-20; 78: 2025-12-17; 82: 2025-06-19; 83: 2025-06-19; 85: 2025-12-18; 86: 2025-12-18; 91: 2025-06-04; 92: 2025-06-14; 94: 2025-11-25; 95: 2026-01-12; 98: 2025-06-14; 99: 2025-06-21; 101: 2025-03-18; 102: 2025-05-04; 105: 2025-06-14; 106: 2025-06-21; 108: 2026-01-10; 109: 2026-01-13; 112: Vaibhav; 113: 2025-06-16; 114: 2025-06-23; 116: 2025-12-29; 117: 2026-01-11; 120: 2025-12-21; 121: 2025-12-31; 123: 2026-01-12; 124: 2026-01-22; 127: 2025-10-29; 128: 2025-11-06; 130: 2026-01-15; 131: 2026-01-23; 134: 2026-01-01; 135: 2026-01-08; 137: 2026-01-23; 138: 2026-01-31; 141: 2026-01-09; 142: 2026-01-11; 144: 2026-01-31; 145: 2026-02-02; 148: 2025-12-24; 149: 2025-12-25; 151: 2026-01-24; 152: 2026-01-24; 155: 2025-11-20; 156: 2025-12-10; 158: 2025-11-09; 159: 2026-01-22; 162: 2025-11-26; 163: 2025-12-21; 165: 2025-11-30; 166: 2025-12-19; 169: 2025-12-03; 170: 2025-12-06; 172: 2026-02-05; 173: 2026-02-14; 176: 2026-01-12; 177: 2026-01-14
125 | PSS-12 | AGE26AL | 1: WTG 520; 2: F04; 3: DNC; 4: 2025-11-15; 5: Keller; 6: Yes; 7: 547264; 8: 2672364; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-15; 18: 2025-05-24; 20: 2025-10-29; 21: 2025-11-11; 32: 2025-06-04; 33: 2025-06-05; 35: 2025-11-22; 36: 2025-11-24; 39: 2025-06-06; 40: 2025-06-06; 42: 2025-12-09; 43: 2025-12-11; 46: 2025-06-07; 47: 2025-06-08; 49: 2025-12-14; 50: 2025-12-14; 53: 2025-06-09; 54: 2025-06-10; 56: 2025-12-16; 57: 2025-12-16; 60: 2025-06-11; 61: 2025-06-21; 63: 2025-12-17; 64: 2025-12-19; 67: 2025-06-22; 68: 2025-06-23; 70: 2025-12-20; 71: 2025-12-21; 75: 2025-06-28; 76: 2025-07-01; 78: 2025-12-23; 79: 2026-02-05; 82: 2025-06-30; 83: 2025-06-30; 85: 2025-12-24; 86: 2025-12-24; 91: 2025-06-15; 92: 2025-06-25; 94: 2025-12-08; 95: 2026-01-15; 98: 2025-06-25; 99: 2025-07-02; 101: 2025-03-26; 102: 2025-04-25; 105: 2025-06-25; 106: 2025-07-02; 108: 2025-12-18; 109: 2025-12-29; 112: Harsh; 113: 2025-06-27; 114: 2025-07-04; 116: 2025-12-04; 117: 2025-12-28; 120: 2025-12-22; 121: 2025-12-31; 123: 2025-12-30; 124: 2026-01-08; 127: 2025-11-30; 128: 2025-12-08; 130: 2026-01-16; 131: 2026-01-23; 134: 2026-01-01; 135: 2026-01-08; 137: 2026-01-12; 138: 2026-01-18; 141: 2026-01-09; 142: 2026-01-11; 144: 2026-01-18; 145: 2026-01-20; 148: 2026-01-02; 149: 2026-01-03; 151: 2026-01-27; 152: 2026-01-27; 155: 2025-11-20; 156: 2025-12-10; 158: 2025-12-08; 159: 2026-01-01; 162: 2025-11-26; 163: 2025-12-21; 165: 2025-11-30; 166: 2025-12-19; 169: 2026-01-04; 170: 2026-01-07; 172: 2026-02-05; 173: 2026-02-14; 176: 2026-01-12; 177: 2026-01-14
126 | PSS-12 | AGE26AL | 1: WTG 521; 2: F04; 3: BHAVANI; 4: 2025-11-04; 5: Keller; 6: Yes; 7: 547454; 8: 2671378; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-15; 18: 2025-05-24; 20: 2025-10-18; 21: 2025-10-27; 32: 2025-06-04; 33: 2025-06-05; 35: 2025-11-06; 36: 2025-11-08; 39: 2025-06-06; 40: 2025-06-06; 42: 2025-11-09; 43: 2025-11-10; 46: 2025-06-07; 47: 2025-06-08; 49: 2025-11-10; 50: 2025-11-11; 53: 2025-06-09; 54: 2025-06-10; 56: 2025-11-12; 57: 2025-11-12; 60: 2025-06-11; 61: 2025-06-21; 63: 2025-11-13; 64: 2025-11-18; 67: 2025-06-22; 68: 2025-06-23; 70: 2025-11-20; 71: 2025-11-21; 75: 2025-06-28; 76: 2025-07-01; 78: 2025-11-24; 79: 2026-02-02; 82: 2025-06-30; 83: 2025-06-30; 85: 2025-11-24; 86: 2025-11-24; 91: 2025-06-15; 92: 2025-06-25; 94: 2025-11-20; 95: 2026-01-08; 98: 2025-06-25; 99: 2025-07-02; 101: 2025-12-12; 102: 2025-12-15; 105: 2025-06-25; 106: 2025-07-02; 108: 2025-12-09; 109: 2025-12-14; 112: Harsh; 113: 2025-06-27; 114: 2025-07-04; 116: 2025-12-05; 117: 2025-12-14; 120: 2025-12-02; 121: 2025-12-11; 123: 2025-12-31; 124: 2026-01-10; 127: 2025-12-04; 128: 2025-12-12; 130: 2026-01-10; 131: 2026-01-14; 134: 2025-12-12; 135: 2025-12-19; 137: 2026-01-13; 138: 2026-01-19; 141: 2025-12-20; 142: 2025-12-22; 144: 2026-01-19; 145: 2026-01-21; 148: 2026-01-06; 149: 2026-01-07; 151: 2026-01-20; 152: 2026-01-20; 155: 2025-11-20; 156: 2025-12-10; 158: 2025-12-22; 159: 2026-01-22; 162: 2025-11-26; 163: 2025-12-21; 165: 2025-11-30; 166: 2025-12-19; 169: 2026-01-08; 170: 2026-01-11; 172: 2026-02-05; 173: 2026-02-14; 176: 2026-01-12; 177: 2026-01-14
127 | PSS-12 | AGE26AL | 1: WTG 533; 2: F05; 3: SHREEJI; 4: 2025-12-08; 5: Bauer; 6: Yes; 7: 547534; 8: 2675018; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-18; 18: 2025-04-28; 20: 2025-08-28; 21: 2025-09-10; 24: YES; 25: Bauer; 29: 2025-11-27; 30: 2025-12-05; 32: 2025-05-20; 33: 2025-05-21; 35: 2025-12-09; 36: 2025-12-14; 38: wip; 39: 2025-05-22; 40: 2025-05-22; 42: 2025-12-16; 43: 2025-12-18; 46: 2025-05-23; 47: 2025-05-24; 49: 2025-12-22; 50: 2025-12-22; 53: 2025-05-25; 54: 2025-05-26; 56: 2025-12-24; 57: 2025-12-25; 60: 2025-05-27; 61: 2025-06-06; 63: 2025-12-26; 64: 2026-01-02; 67: 2025-06-07; 68: 2025-06-08; 70: 2026-01-03; 71: 2026-01-04; 75: 2025-06-13; 76: 2025-06-16; 78: 2026-01-07; 82: 2025-06-15; 83: 2025-06-15; 85: 2026-01-08; 86: 2026-01-08; 91: 2025-05-31; 92: 2025-06-10; 94: 2025-12-21; 95: 2026-01-08; 98: 2025-06-10; 99: 2025-06-17; 101: 2025-03-20; 102: 2025-05-21; 105: 2025-06-10; 106: 2025-06-17; 108: 2026-01-04; 109: 2026-01-09; 112: Harsh; 113: 2025-06-12; 114: 2025-06-19; 116: 2026-01-02; 117: 2026-01-09; 120: 2025-12-21; 121: 2025-12-31; 123: 2026-01-26; 124: 2026-02-17; 127: 2025-12-04; 128: 2025-12-12; 130: 2026-01-10; 131: 2026-01-26; 134: 2026-01-01; 135: 2026-01-08; 137: 2026-02-19; 138: 2026-02-24; 141: 2026-01-09; 142: 2026-01-11; 144: 2026-02-24; 145: 2026-02-26; 148: 2026-01-06; 149: 2026-01-07; 151: 2026-01-22; 152: 2026-01-22; 155: 2025-11-20; 156: 2025-12-10; 158: 2025-11-19; 159: 2026-01-22; 162: 2025-11-26; 163: 2025-12-21; 165: 2025-11-30; 166: 2025-12-19; 169: 2026-01-08; 170: 2026-01-11; 172: 2026-02-18; 176: 2026-01-12; 177: 2026-01-14
128 | PSS-12 | AGE26AL | 1: WTG 534; 2: F05; 3: SHREEJI; 4: 2025-09-22; 5: Bauer; 6: Yes; 7: 547724; 8: 2674032; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-29; 18: 2025-05-08; 20: 2025-08-08; 21: 2025-08-25; 32: 2025-05-20; 33: 2025-05-21; 35: 2025-10-01; 36: 2025-10-02; 39: 2025-05-22; 40: 2025-05-22; 42: 2025-10-05; 43: 2025-10-06; 46: 2025-05-23; 47: 2025-05-24; 49: 2025-10-07; 50: 2025-10-07; 53: 2025-05-25; 54: 2025-05-26; 56: 2025-10-08; 57: 2025-10-09; 60: 2025-05-27; 61: 2025-06-06; 63: 2025-10-10; 64: 2025-10-14; 67: 2025-06-07; 68: 2025-06-08; 70: 2025-10-15; 71: 2025-10-16; 75: 2025-06-13; 76: 2025-06-16; 78: 2025-11-28; 79: 2026-02-06; 82: 2025-06-15; 83: 2025-06-15; 85: 2025-11-28; 86: 2025-11-28; 91: 2025-05-31; 92: 2025-06-10; 94: 2025-10-02; 95: 2025-12-27; 98: 2025-06-10; 99: 2025-06-17; 101: Done; 102: Done; 105: 2025-06-10; 106: 2025-06-17; 108: 2025-12-21; 109: 2025-12-30; 112: Varudi; 113: 2025-06-12; 114: 2025-06-19; 116: 2025-12-05; 117: 2025-12-29; 120: 2025-12-10; 121: 2025-12-20; 123: 2026-01-05; 124: 2026-01-16; 127: 2025-12-05; 128: 2025-12-13; 130: 2025-12-28; 131: 2026-01-18; 134: 2025-12-21; 135: 2025-12-28; 137: 2026-01-20; 138: 2026-01-26; 141: 2025-12-29; 142: 2025-12-31; 144: 2026-01-27; 145: 2026-01-28; 148: 2026-01-07; 149: 2026-01-08; 151: 2026-01-23; 152: 2026-01-23; 155: 2025-11-20; 156: 2025-12-10; 158: 2025-11-20; 159: 2026-01-22; 162: 2025-11-26; 163: 2025-12-21; 165: 2025-11-30; 166: 2025-12-19; 169: 2026-01-09; 170: 2026-01-12; 172: 2026-02-05; 173: 2026-02-14; 176: 2026-01-13; 177: 2026-01-15
129 | PSS-12 | AGE26AL | 1: WTG 535; 2: F05; 3: MSC; 4: 2025-12-03; 5: Bauer; 6: Yes; 7: 547915; 8: 2673046; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-09; 18: 2025-05-18; 20: 2025-09-12; 21: 2025-09-21; 24: YES; 25: Bauer; 29: 2025-11-22; 30: 2025-11-29; 32: 2025-05-23; 33: 2025-05-24; 35: 2025-12-05; 36: 2025-12-08; 39: 2025-05-25; 40: 2025-05-25; 42: 2025-12-08; 43: 2025-12-09; 46: 2025-05-26; 47: 2025-05-27; 49: 2025-12-09; 50: 2025-12-09; 53: 2025-05-28; 54: 2025-05-29; 56: 2025-12-16; 57: 2025-12-17; 60: 2025-05-30; 61: 2025-06-09; 63: 2025-12-17; 64: 2025-12-23; 67: 2025-06-10; 68: 2025-06-11; 70: 2025-12-24; 71: 2025-12-24; 75: 2025-06-16; 76: 2025-06-19; 78: 2026-01-05; 82: 2025-06-18; 83: 2025-06-18; 85: 2026-01-06; 86: 2026-01-06; 91: 2025-06-03; 92: 2025-06-13; 94: 2025-12-08; 95: 2026-01-05; 98: 2025-06-13; 99: 2025-06-20; 101: 2025-03-16; 102: 2025-05-20; 105: 2025-06-13; 106: 2025-06-20; 108: 2026-01-06; 109: 2026-01-10; 112: Varudi; 113: 2025-06-15; 114: 2025-06-22; 116: 2025-12-28; 117: 2026-01-11; 120: 2025-11-30; 121: 2025-12-09; 123: 2026-01-24; 124: 2026-02-17; 127: 2025-12-05; 128: 2025-12-13; 130: 2026-01-07; 131: 2026-01-17; 134: 2025-12-10; 135: 2025-12-17; 137: 2026-02-19; 138: 2026-02-22; 141: 2025-12-18; 142: 2025-12-20; 144: 2026-02-23; 145: 2026-02-27; 148: 2026-01-07; 149: 2026-01-08; 151: 2026-01-20; 152: 2026-01-20; 155: 2025-11-20; 156: 2025-12-10; 158: 2025-11-15; 159: 2026-01-22; 162: 2025-11-26; 163: 2025-12-21; 165: 2025-11-30; 166: 2025-12-19; 169: 2026-01-09; 170: 2026-01-12; 172: 2026-02-18; 176: 2026-01-13; 177: 2026-01-15
130 | PSS-12 | AGE26AL | 1: WTG 536; 2: F04; 3: MSC; 4: 2025-11-25; 5: Keller; 6: Yes; 7: 548105; 8: 2672060; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-04-20; 18: 2025-04-30; 20: 2025-10-03; 21: 2025-10-14; 32: 2025-05-18; 33: 2025-05-19; 35: 2025-11-30; 36: 2025-12-01; 39: 2025-05-20; 40: 2025-05-20; 42: 2025-12-06; 43: 2025-12-08; 46: 2025-05-21; 47: 2025-05-22; 49: 2025-12-08; 50: 2025-12-08; 53: 2025-05-23; 54: 2025-05-24; 56: 2025-12-11; 57: 2025-12-11; 60: 2025-05-25; 61: 2025-06-04; 63: 2025-12-12; 64: 2025-12-21; 67: 2025-06-05; 68: 2025-06-06; 70: 2025-12-21; 71: 2025-12-22; 75: 2025-06-11; 76: 2025-06-14; 78: 2026-01-25; 82: 2025-06-13; 83: 2025-06-13; 85: 2025-12-26; 86: 2025-12-26; 91: 2025-05-29; 92: 2025-06-08; 94: 2025-12-07; 95: 2026-01-01; 98: 2025-06-08; 99: 2025-06-15; 101: Done; 102: Done; 105: 2025-06-08; 106: 2025-06-15; 108: 2025-12-21; 109: 2026-01-13; 112: Varudi; 113: 2025-06-10; 114: 2025-06-17; 116: 2025-12-04; 117: 2026-01-13; 120: 2025-12-12; 121: 2025-12-21; 123: 2026-01-13; 124: 2026-01-25; 127: 2025-12-04; 128: 2025-12-12; 130: 2025-12-30; 131: 2026-01-08; 134: 2025-12-22; 135: 2025-12-29; 137: 2026-01-26; 138: 2026-02-03; 141: 2025-12-30; 142: 2026-01-01; 144: 2026-02-03; 145: 2026-02-05; 148: 2026-01-06; 149: 2026-01-07; 151: 2026-01-12; 152: 2026-01-12; 155: 2025-11-20; 156: 2025-12-10; 158: 2025-12-26; 159: 2026-01-22; 162: 2025-11-26; 163: 2025-12-21; 165: 2025-11-30; 166: 2025-12-19; 169: 2026-01-08; 170: 2026-01-11; 172: 2026-02-05; 173: 2026-02-14; 176: 2026-01-12; 177: 2026-01-14
131 | PSS-14 | AGE25CL | 1: WTG 532; 2: F13; 3: DNC; 4: 2025-12-17; 5: Bauer; 6: Yes; 7: 547361; 8: 2675905; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-01; 18: 2025-05-10; 20: 2025-11-19; 21: 2025-11-29; 32: 2025-05-16; 33: 2025-05-17; 35: 2025-12-17; 36: 2025-12-18; 39: 2025-05-18; 40: 2025-05-18; 42: 2025-12-24; 43: 2025-12-25; 46: 2025-05-19; 47: 2025-05-20; 49: 2025-12-26; 50: 2025-12-26; 53: 2025-05-21; 54: 2025-05-22; 56: 2025-12-29; 57: 2025-12-29; 60: 2025-05-23; 61: 2025-06-02; 63: 2025-12-31; 64: 2026-01-06; 67: 2025-06-03; 68: 2025-06-04; 70: 2026-01-07; 71: 2026-01-08; 75: 2025-06-09; 76: 2025-06-12; 78: 2026-01-20; 82: 2025-06-11; 83: 2025-06-11; 85: 2026-01-21; 86: 2026-01-21; 91: 2025-05-27; 92: 2025-06-06; 94: 2025-12-25; 95: 2026-02-23; 98: 2025-06-06; 99: 2025-06-13; 101: Done; 102: Done; 105: 2025-06-06; 106: 2025-06-13; 108: 2026-02-17; 109: 2026-02-20; 112: GP Project(Reuse); 113: 2025-06-08; 114: 2025-06-15; 116: 2026-02-06; 117: 2026-02-18; 120: 2025-12-07; 121: 2025-12-16; 127: 2025-10-31; 128: 2025-11-08; 130: 0; 134: 2025-12-17; 135: 2025-12-24; 141: 2025-12-25; 142: 2025-12-27; 148: 2025-12-08; 149: 2025-12-09; 155: 2025-11-20; 156: 2025-12-10; 162: 2025-11-15; 163: 2025-12-10; 165: 2026-01-31; 166: 2026-02-15; 169: 2025-12-05; 170: 2025-12-08; 176: 2025-12-28; 177: 2025-12-30
132 | PSS-14 | AGE25CL | 1: WTG 516; 2: F13; 3: SHREERAM; 4: 2026-01-30; 5: Bauer/Keller; 6: Yes; 7: 546537; 8: 2676123; 12: Done; 13: Done; 15: 434; 16: 434; 17: 2025-05-11; 18: 2025-05-20; 20: 2025-11-30; 21: 2025-12-10; 24: YES; 25: Keller; 29: 2026-01-11; 30: 2026-01-24; 31: PLT fail; 32: 2025-05-25; 33: 2025-05-26; 39: 2025-05-27; 40: 2025-05-27; 46: 2025-05-28; 47: 2025-05-29; 53: 2025-05-30; 54: 2025-05-31; 60: 2025-06-01; 61: 2025-06-11; 67: 2025-06-12; 68: 2025-06-13; 75: 2025-06-18; 76: 2025-06-21; 82: 2025-06-20; 83: 2025-06-20; 91: 2025-06-05; 92: 2025-06-15; 94: 0; 98: 2025-09-23; 99: 2025-09-30; 101: Done; 102: Done; 105: 2025-09-23; 106: 2025-09-30; 112: GP Project(Reuse); 113: 2025-09-25; 114: 2025-10-02; 116: 2026-02-22; 120: 2025-12-17; 121: 2025-12-26; 127: 2025-12-07; 128: 2025-12-15; 130: 0; 134: 2025-12-27; 135: 2026-01-03; 141: 2026-01-04; 142: 2026-01-06; 148: 2026-01-09; 149: 2026-01-10; 155: 2025-11-20; 156: 2025-12-10; 158: 2026-02-04; 162: 2025-12-08; 163: 2026-01-02; 165: 2026-01-31; 166: 2026-02-15; 169: 2026-01-11; 170: 2026-01-14; 176: 2026-01-15; 177: 2026-01-17; 184: Keller start SC date 9-Feb 26 Additional 181 and finish Date-19-02-26
133 | PSS-14 | AGE26AL | 1: KH 53; 2: F07; 3: HBG; 4: 2025-06-12; 5: Keller; 6: Yes; 7: 543761; 8: 2677522; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-29; 18: 2025-06-08; 20: 2025-03-24; 21: 2025-04-01; 32: 2025-09-17; 33: 2025-09-18; 35: 2025-06-16; 36: 2025-11-22; 38: Delay due to dewatering required; 39: 2025-09-19; 40: 2025-09-19; 42: 2025-11-23; 43: 2025-11-24; 46: 2025-09-20; 47: 2025-09-21; 49: 2025-11-24; 50: 2025-11-24; 53: 2025-09-22; 54: 2025-09-23; 56: 2025-11-28; 57: 2025-11-29; 60: 2025-09-24; 61: 2025-10-04; 63: 2025-11-30; 64: 2025-12-14; 67: 2025-10-05; 68: 2025-10-06; 70: 2025-12-15; 71: 2025-12-15; 75: 2025-10-11; 76: 2025-10-14; 78: 2025-12-18; 82: 2025-10-13; 83: 2025-10-13; 85: 2025-12-19; 86: 2025-12-19; 91: 2025-10-08; 92: 2025-10-18; 94: 2025-11-22; 98: 2026-01-16; 99: 2026-01-23; 101: 2025-03-16; 102: 2025-04-18; 105: 2026-01-16; 106: 2026-01-23; 112: GP Project; 113: 2026-01-18; 114: 2026-01-25; 120: 2025-12-27; 121: 2026-01-06; 127: 2025-12-25; 128: 2026-01-02; 130: 0; 134: 2026-01-07; 135: 2026-01-14; 141: 2026-01-15; 142: 2026-01-17; 148: 2026-01-27; 149: 2026-01-28; 155: 2025-11-20; 156: 2025-12-10; 158: 2026-02-07; 162: 2025-12-08; 163: 2026-01-02; 169: 2026-01-29; 170: 2026-02-01; 176: 2026-02-02; 177: 2026-02-04
134 | PSS-14 | AGE26AL | 1: KH 54; 2: F08; 3: CEIPL; 4: 2025-04-18; 5: Keller; 6: Yes; 7: 544578; 8: 2677237; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-09; 18: 2025-06-19; 20: 2025-04-02; 21: 2025-04-11; 32: 2025-09-28; 33: 2025-09-29; 35: 2025-04-21; 36: 2025-04-24; 39: 2025-09-30; 40: 2025-09-30; 42: 2025-04-25; 43: 2025-04-27; 46: 2025-10-01; 47: 2025-10-02; 49: 2025-04-27; 50: 2025-04-27; 53: 2025-10-03; 54: 2025-10-04; 56: 2025-04-28; 57: 2025-04-28; 60: 2025-10-05; 61: 2025-10-15; 63: 2025-04-29; 64: 2025-05-11; 67: 2025-10-16; 68: 2025-10-17; 70: 2025-05-12; 71: 2025-05-13; 75: 2025-10-22; 76: 2025-10-25; 78: 2025-05-17; 82: 2025-10-24; 83: 2025-10-24; 85: 2025-06-03; 86: 2025-06-03; 91: 2025-10-01; 92: 2025-10-11; 94: 2025-04-26; 98: 2025-12-18; 99: 2025-12-25; 101: 2025-03-19; 102: 2025-04-16; 105: 2025-12-18; 106: 2025-12-25; 108: 2025-12-20; 109: 2026-01-05; 112: GP Project; 113: 2025-12-20; 114: 2025-12-27; 116: 2025-12-22; 117: 2025-12-30; 120: 2026-01-07; 121: 2026-01-17; 127: 2025-12-29; 128: 2026-01-06; 130: 0; 134: 2026-01-18; 135: 2026-01-25; 141: 2026-01-26; 142: 2026-01-28; 148: 2026-02-05; 149: 2026-02-06; 155: 2025-12-23; 156: 2025-01-13; 158: 2026-02-19; 162: 2025-12-30; 163: 2026-01-24; 165: 2026-01-31; 166: 2026-02-15; 169: 2026-02-07; 170: 2026-02-10; 176: 2026-02-11; 177: 2026-02-13
135 | PSS-14 | AGE26AL | 1: KH 55; 2: F09; 3: BHAVANI; 4: 2026-01-13; 5: Keller; 6: Yes; 7: 545396; 8: 2676952; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-20; 18: 2025-06-30; 20: 2025-04-11; 21: 2025-04-18; 32: 2025-10-02; 33: 2025-10-03; 35: 2026-01-30; 36: 2026-01-31; 39: 2025-10-04; 40: 2025-10-04; 42: 2026-02-17; 43: 2026-02-21; 46: 2025-10-05; 47: 2025-10-06; 49: 2026-02-21; 50: 2026-02-22; 53: 2025-10-07; 54: 2025-10-08; 56: 2026-02-23; 57: 2026-02-24; 60: 2025-10-09; 61: 2025-10-19; 63: 2026-01-25; 67: 2025-10-20; 68: 2025-10-21; 75: 2025-10-26; 76: 2025-10-29; 82: 2025-10-28; 83: 2025-10-28; 91: 2025-10-05; 92: 2025-10-15; 94: 0; 98: 2025-12-22; 99: 2025-12-29; 101: 2025-03-19; 102: Done; 105: 2025-12-22; 106: 2025-12-29; 112: SS Jadeja; 113: 2025-12-24; 114: 2025-12-31; 116: 2026-02-06; 120: 2026-01-18; 121: 2026-01-27; 127: 2025-11-25; 128: 2025-12-03; 130: 0; 134: 2026-01-28; 135: 2026-02-04; 141: 2026-02-05; 142: 2026-02-07; 148: 2026-01-19; 149: 2026-01-20; 155: 2025-12-23; 156: 2025-01-13; 158: 2026-02-05; 162: 2025-12-30; 163: 2026-01-24; 165: 2026-01-31; 166: 2026-02-15; 169: 2026-01-19; 170: 2026-01-22; 176: 2026-02-08; 177: 2026-02-10
136 | PSS-14 | AGE26AL | 1: KH 56; 2: F09; 3: BHAVANI; 4: 2026-01-30; 5: Keller; 6: Yes; 7: 546214; 8: 2676667; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-23; 18: 2025-06-02; 20: 2025-04-19; 21: 2025-04-30; 32: 2025-06-03; 33: 2025-06-04; 35: 2026-02-06; 36: 2026-02-09; 39: 2025-06-05; 40: 2025-06-05; 42: 2026-02-10; 43: 2026-02-11; 46: 2025-06-06; 47: 2025-06-07; 49: 2026-02-13; 50: 2026-02-13; 53: 2025-06-08; 54: 2025-06-09; 56: 2026-02-18; 57: 2026-02-19; 60: 2025-06-10; 61: 2025-06-20; 63: 2026-02-20; 64: 2026-02-24; 67: 2025-06-21; 68: 2025-06-22; 70: 2026-02-24; 71: 2026-02-25; 75: 2025-06-27; 76: 2025-06-30; 82: 2025-06-29; 83: 2025-06-29; 91: 2025-06-06; 92: 2025-06-16; 94: 2026-02-12; 98: 2025-10-02; 99: 2025-10-09; 101: 2025-03-18; 102: 2025-04-16; 105: 2025-10-02; 106: 2025-10-09; 112: Keshav; 113: 2025-10-04; 114: 2025-10-11; 120: 2026-01-28; 121: 2026-02-07; 127: 2025-11-26; 128: 2025-12-04; 130: 0; 134: 2026-02-08; 135: 2026-02-15; 141: 2026-02-16; 142: 2026-02-18; 148: 2026-02-02; 149: 2026-02-03; 155: 2025-12-23; 156: 2025-01-13; 158: 2026-02-15; 159: 2026-02-20; 162: 2025-12-30; 163: 2026-01-24; 165: 2026-01-31; 166: 2026-02-15; 169: 2026-02-04; 170: 2026-02-07; 176: 2026-02-19; 177: 2026-02-21
137 | PSS-14 | AGE26AL | 1: KH 57; 2: F10; 3: SHREERAM; 4: 2025-05-30; 5: Bauer; 6: Yes; 7: 547669; 8: 2677030; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-03; 18: 2025-06-13; 20: 2025-04-25; 21: 2025-05-02; 32: 2025-09-22; 33: 2025-09-23; 35: 2025-05-31; 36: 2025-06-02; 39: 2025-09-24; 40: 2025-09-24; 42: 2025-06-03; 43: 2025-06-04; 46: 2025-09-25; 47: 2025-09-26; 49: 2025-06-05; 50: 2025-06-05; 53: 2025-09-27; 54: 2025-09-28; 56: 2025-06-06; 57: 2025-06-07; 60: 2025-09-29; 61: 2025-10-09; 63: 2025-06-10; 64: 2025-06-23; 67: 2025-10-10; 68: 2025-10-11; 70: 2025-06-26; 71: 2025-06-26; 75: 2025-10-16; 76: 2025-10-19; 78: 2025-07-01; 82: 2025-10-18; 83: 2025-10-18; 85: 2025-08-02; 86: 2025-08-02; 91: 2025-09-25; 92: 2025-10-05; 94: 2025-06-04; 98: 2025-10-13; 99: 2025-10-20; 101: Done; 102: Done; 105: 2025-10-13; 106: 2025-10-20; 112: GP Project(Reuse); 113: 2025-10-15; 114: 2025-10-22; 120: 2026-02-08; 121: 2026-02-18; 127: 2025-12-25; 128: 2026-01-02; 130: 0; 134: 2026-02-19; 135: 2026-02-26; 141: 2026-02-27; 142: 2026-03-01; 148: 2026-02-13; 149: 2026-02-14; 155: 2025-01-22; 156: 2025-02-14; 162: 2026-01-22; 163: 2026-02-16; 165: 2026-01-31; 166: 2026-02-15; 169: 2026-01-05; 170: 2026-01-08; 176: 2026-03-02; 177: 2026-03-04
138 | PSS-14 | AGE26AL | 1: KH 58; 2: F11; 3: HBG; 4: 2025-12-17; 5: Bauer; 6: Yes; 7: 548487; 8: 2676745; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-14; 18: 2025-06-24; 20: 2025-04-17; 21: 2025-04-24; 32: 2025-10-03; 33: 2025-10-04; 35: 2025-12-26; 36: 2025-12-29; 39: 2025-10-05; 40: 2025-10-05; 42: 2026-01-01; 43: 2026-01-02; 46: 2025-10-06; 47: 2025-10-07; 49: 2026-01-02; 50: 2026-01-02; 53: 2025-10-08; 54: 2025-10-09; 56: 2026-01-07; 57: 2026-01-07; 60: 2025-10-10; 61: 2025-10-20; 63: 2026-01-08; 64: 2026-01-11; 67: 2025-10-21; 68: 2025-10-22; 70: 2026-01-12; 71: 2026-01-14; 75: 2025-10-27; 76: 2025-10-30; 78: 2026-01-20; 82: 2025-10-29; 83: 2025-10-29; 85: 2026-01-21; 86: 2026-01-21; 91: 2025-10-06; 92: 2025-10-16; 94: 2026-01-01; 95: 2026-01-20; 98: 2025-10-24; 99: 2025-10-31; 101: Done; 102: Done; 105: 2025-10-24; 106: 2025-10-31; 112: Varudi; 113: 2025-10-26; 114: 2025-11-02; 116: 2026-02-04; 120: 2026-01-02; 121: 2026-01-12; 127: 2026-01-03; 128: 2026-01-11; 130: 2026-02-27; 134: 2026-01-13; 135: 2026-01-20; 141: 2026-01-21; 142: 2026-01-23; 148: 2026-01-31; 149: 2026-02-01; 155: 2025-12-23; 156: 2025-01-13; 162: 2025-12-08; 163: 2026-01-02; 169: 2026-02-02; 170: 2026-02-05; 176: 2026-02-06; 177: 2026-02-08
139 | PSS-14 | AGE26AL | 1: KH 59; 2: F11; 3: MSC; 4: 2026-01-30; 5: Bauer; 6: Yes; 7: 549283; 8: 2676438; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-05; 18: 2025-06-15; 20: 2025-04-03; 21: 2025-04-16; 23: Road work is in progress; 24: YES; 25: Pinnacles; 26: 2025-06-20; 27: 2025-06-25; 29: 2026-01-13; 30: 2026-01-26; 32: 2025-09-24; 33: 2025-09-25; 35: 2026-01-30; 36: 2026-01-31; 39: 2025-09-26; 40: 2025-09-26; 42: 2026-01-31; 43: 2026-02-01; 46: 2025-09-27; 47: 2025-09-28; 49: 2026-02-01; 50: 2026-02-01; 53: 2025-09-29; 54: 2025-09-30; 56: 2026-02-02; 57: 2026-02-02; 60: 2025-10-01; 61: 2025-10-11; 63: 2026-02-14; 64: 2026-02-20; 67: 2025-10-12; 68: 2025-10-13; 70: 2026-02-22; 71: 2026-02-23; 75: 2025-10-18; 76: 2025-10-21; 82: 2025-10-20; 83: 2025-10-20; 91: 2025-09-27; 92: 2025-10-07; 94: 2026-01-31; 95: 2026-02-16; 98: 2025-12-19; 99: 2025-12-26; 101: Done; 102: Done; 105: 2025-12-19; 106: 2025-12-26; 112: Varudi(Reuse); 113: 2025-12-21; 114: 2025-12-28; 120: 2026-01-13; 121: 2026-01-23; 127: 2025-12-25; 128: 2026-01-02; 130: 2026-02-27; 134: 2026-01-24; 135: 2026-01-31; 141: 2026-02-01; 142: 2026-02-03; 148: 2026-01-23; 149: 2026-01-24; 155: 2025-12-23; 156: 2025-01-13; 158: 2026-01-07; 162: 2025-12-08; 163: 2026-01-02; 169: 2026-01-05; 170: 2026-01-08; 176: 2026-02-04; 177: 2026-02-06
140 | PSS-14 | AGE26AL | 1: KH 60; 2: F11; 3: ODHAV; 4: 2025-12-18; 5: Bauer; 6: Yes; 7: 551057; 8: 2676644; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-26; 18: 2025-06-05; 20: 2025-10-17; 21: 2025-10-26; 32: 2025-09-14; 33: 2025-09-15; 35: 2025-12-24; 36: 2025-12-25; 39: 2025-09-16; 40: 2025-09-16; 42: 2025-12-29; 43: 2026-01-03; 46: 2025-09-17; 47: 2025-09-18; 49: 2026-01-07; 50: 2026-01-07; 53: 2025-09-19; 54: 2025-09-20; 56: 2026-01-09; 57: 2026-01-10; 60: 2025-09-21; 61: 2025-10-01; 63: 2026-01-11; 64: 2026-01-17; 67: 2025-10-02; 68: 2025-10-03; 70: 2026-01-17; 71: 2026-01-18; 75: 2025-10-08; 76: 2025-10-11; 78: 2026-01-28; 82: 2025-10-10; 83: 2025-10-10; 85: 2026-01-29; 86: 2026-01-29; 91: 2025-10-05; 92: 2025-10-15; 94: 2026-01-07; 95: 2026-02-06; 98: 2026-01-13; 99: 2026-01-20; 101: 2025-03-18; 102: 2025-04-22; 105: 2026-01-13; 106: 2026-01-20; 108: 2026-02-22; 109: 2026-02-27; 112: Varudi; 113: 2026-01-15; 114: 2026-01-22; 116: 2026-02-06; 117: 2026-02-27; 120: 2026-02-04; 121: 2026-02-14; 123: 2026-02-28; 127: 2026-01-02; 128: 2026-01-10; 130: 2026-02-27; 134: 2026-02-15; 135: 2026-02-22; 141: 2026-02-23; 142: 2026-02-25; 148: 2026-02-24; 149: 2026-02-25; 155: 2025-01-22; 156: 2025-02-14; 158: 2026-01-02; 159: 2026-01-15; 162: 2026-01-22; 163: 2026-02-16; 169: 2026-02-26; 170: 2026-03-01; 176: 2026-03-02; 177: 2026-03-04
141 | PSS-14 | AGE26AL | 1: KH 61; 2: F11; 3: ODHAV; 4: 2026-01-04; 5: Bauer; 6: Yes; 7: 550128; 8: 2676105; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-16; 18: 2025-06-26; 20: 2025-10-07; 21: 2025-10-17; 32: 2025-10-10; 33: 2025-10-11; 35: 2026-01-08; 36: 2026-01-10; 39: 2025-10-12; 40: 2025-10-12; 42: 2026-01-11; 43: 2026-01-12; 46: 2025-10-13; 47: 2025-10-14; 49: 2026-01-13; 50: 2026-01-13; 53: 2025-10-15; 54: 2025-10-16; 56: 2026-01-18; 57: 2026-01-20; 60: 2025-10-17; 61: 2025-10-27; 63: 2026-01-21; 64: 2026-01-28; 67: 2025-10-28; 68: 2025-10-29; 70: 2026-01-29; 71: 2026-01-30; 75: 2025-11-03; 76: 2025-11-06; 78: 2026-02-07; 82: 2025-11-05; 83: 2025-11-05; 85: 2026-02-07; 86: 2026-02-07; 91: 2025-10-13; 92: 2025-10-23; 94: 2026-01-12; 98: 2025-12-30; 99: 2026-01-06; 101: Done; 102: Done; 105: 2025-12-30; 106: 2026-01-06; 108: 2026-02-25; 109: 2026-02-27; 112: Varudi; 113: 2026-01-01; 114: 2026-01-08; 116: 2026-02-05; 117: 2026-02-27; 120: 2026-01-24; 121: 2026-02-03; 127: 2025-11-28; 128: 2025-12-06; 130: 2026-02-27; 134: 2026-02-04; 135: 2026-02-11; 141: 2026-02-12; 142: 2026-02-14; 148: 2026-01-26; 149: 2026-01-27; 155: 2025-12-23; 156: 2025-01-13; 158: 2026-01-05; 159: 2026-01-12; 162: 2025-12-30; 163: 2026-01-24; 169: 2025-12-09; 170: 2025-12-12; 176: 2026-02-15; 177: 2026-02-17
142 | PSS-14 | AGE26AL | 1: KH 556; 2: F06; 3: MSC; 4: 2025-08-06; 5: Keller; 6: Yes; 7: 543680; 8: 2681903; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-07; 18: 2025-05-17; 20: 2025-06-24; 21: 2025-07-11; 32: 2025-05-25; 33: 2025-05-26; 35: 2026-01-02; 36: 2026-01-03; 39: 2025-05-27; 40: 2025-05-27; 42: 2026-01-03; 43: 2026-01-03; 46: 2025-05-28; 47: 2025-05-29; 49: 2026-01-03; 50: 2026-01-03; 53: 2025-05-30; 54: 2025-05-31; 56: 2026-01-06; 57: 2026-01-06; 60: 2025-06-01; 61: 2025-06-11; 63: 2026-01-10; 64: 2026-01-13; 67: 2025-06-12; 68: 2025-06-13; 70: 2026-01-28; 71: 2026-01-29; 75: 2025-06-18; 76: 2025-06-21; 78: 2026-02-08; 82: 2025-06-20; 83: 2025-06-20; 85: 2026-02-08; 86: 2026-02-08; 91: 2025-06-15; 92: 2025-06-25; 94: 2026-01-02; 98: 2025-09-23; 99: 2025-09-30; 101: Done; 102: Done; 105: 2025-09-23; 106: 2025-09-30; 112: GP Project(Reuse); 113: 2025-09-25; 114: 2025-10-02; 116: 2026-02-09; 120: 2025-12-30; 121: 2026-01-08; 127: 2025-11-28; 128: 2025-12-06; 130: 0; 134: 2026-01-09; 135: 2026-01-16; 141: 2026-01-17; 142: 2026-01-19; 148: 2026-01-01; 149: 2026-01-02; 155: 2025-12-23; 156: 2025-01-13; 162: 2025-12-08; 163: 2026-01-02; 169: 2025-12-09; 170: 2025-12-12; 176: 2026-01-20; 177: 2026-01-22
143 | PSS-14 | AGE26AL | 1: KH 523; 2: F06; 3: HBG; 4: 2026-01-30; 5: Keller; 6: Yes; 7: 544040; 8: 2680037; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-28; 18: 2025-06-06; 20: 2026-01-03; 21: 2026-01-10; 32: 2025-06-10; 33: 2025-06-11; 35: 2026-02-01; 36: 2026-02-03; 39: 2025-06-12; 40: 2025-06-12; 42: 2026-02-05; 43: 2026-02-07; 46: 2025-06-13; 47: 2025-06-14; 49: 2026-02-09; 50: 2026-02-09; 53: 2025-06-15; 54: 2025-06-16; 56: 2026-02-10; 57: 2026-02-10; 60: 2025-06-17; 61: 2025-06-27; 63: 2026-02-11; 64: 2026-02-17; 67: 2025-06-28; 68: 2025-06-29; 70: 2026-02-21; 71: 2026-02-22; 75: 2025-07-04; 76: 2025-07-07; 78: 2026-02-25; 82: 2025-07-06; 83: 2025-07-06; 85: 2026-02-27; 86: 2026-02-27; 91: 2025-06-13; 92: 2025-06-23; 94: 0; 98: 2025-10-09; 99: 2025-10-16; 101: 2025-03-16; 102: Done; 105: 2025-10-09; 106: 2025-10-16; 112: Bipin(Reuse); 113: 2025-10-11; 114: 2025-10-18; 120: 2026-01-18; 121: 2026-01-28; 127: 2025-12-06; 128: 2025-12-14; 130: 0; 134: 2026-01-29; 135: 2026-02-05; 141: 2026-02-06; 142: 2026-02-08; 148: 2026-01-20; 149: 2026-01-21; 155: 2025-12-23; 156: 2025-01-13; 162: 2025-12-30; 163: 2026-01-24; 169: 2025-12-17; 170: 2025-12-20; 176: 2026-02-09; 177: 2026-02-11
144 | PSS-14 | AGE26AL | 1: KH 522; 2: F05; 3: MSC; 4: 2026-01-30; 5: Keller; 6: Yes; 7: 543860; 8: 2680970; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-18; 18: 2025-05-27; 20: 2025-11-23; 21: 2025-12-03; 32: 2025-06-02; 33: 2025-06-03; 35: 2026-01-31; 36: 2026-02-01; 39: 2025-06-04; 40: 2025-06-04; 42: 2026-02-02; 43: 2026-01-02; 46: 2025-06-05; 47: 2025-06-06; 49: 2026-02-06; 50: 2026-02-06; 53: 2025-06-07; 54: 2025-06-08; 56: 2026-02-12; 57: 2026-02-13; 60: 2025-06-09; 61: 2025-06-19; 63: 2026-02-13; 64: 2026-02-20; 67: 2025-06-20; 68: 2025-06-21; 70: 2026-02-20; 71: 2026-02-21; 75: 2025-06-26; 76: 2025-06-29; 82: 2025-06-28; 83: 2025-06-28; 91: 2025-06-05; 92: 2025-06-15; 94: 2026-02-05; 98: 2025-10-01; 99: 2025-10-08; 101: Done; 102: Done; 105: 2025-10-01; 106: 2025-10-08; 112: SS Jadeja(Reuse); 113: 2025-10-03; 114: 2025-10-10; 120: 2026-02-18; 121: 2026-02-28; 127: 2025-12-05; 128: 2025-12-13; 130: 0; 134: 2026-03-01; 135: 2026-03-08; 141: 2026-03-09; 142: 2026-03-11; 148: 2026-02-22; 149: 2026-02-23; 155: 2025-01-22; 156: 2025-02-14; 162: 2026-01-22; 163: 2026-02-16; 169: 2025-12-16; 170: 2025-12-19; 176: 2026-03-12; 177: 2026-03-14
145 | PSS-14 | AGE26AL | 1: KH 521; 2: F05; 5: Bauer; 6: Yes; 7: 544677; 8: 2680685; 12: Done; 13: Done; 15: 199; 16: 0; 17: 2025-05-18; 18: 2025-05-27; 24: YES; 32: 2025-06-02; 33: 2025-06-03; 39: 2025-06-04; 40: 2025-06-04; 46: 2025-06-05; 47: 2025-06-06; 53: 2025-06-07; 54: 2025-06-08; 60: 2025-06-09; 61: 2025-06-19; 67: 2025-06-20; 68: 2025-06-21; 75: 2025-06-26; 76: 2025-06-29; 82: 2025-06-28; 83: 2025-06-28; 91: 2025-06-05; 92: 2025-06-15; 94: 0; 98: 2025-10-01; 99: 2025-10-08; 105: 2025-10-01; 106: 2025-10-08; 112: GP Project(Reuse); 113: 2025-10-03; 114: 2025-10-10; 120: 2026-02-08; 121: 2026-02-17; 127: 2025-12-15; 128: 2025-12-23; 130: 0; 134: 2026-02-18; 135: 2026-02-25; 141: 2026-02-26; 142: 2026-02-28; 148: 2026-02-22; 149: 2026-02-23; 155: 2025-01-22; 156: 2025-02-14; 162: 2026-01-22; 163: 2026-02-16; 169: 2025-12-26; 170: 2025-12-29; 176: 2026-03-01; 177: 2026-03-03
146 | PSS-14 | AGE26AL | 1: KH 508; 2: F05; 3: HBG; 4: 2026-01-03; 5: Keller; 6: Yes; 7: 544498; 8: 2681618; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-07; 18: 2025-05-17; 20: 2025-12-20; 21: 2025-12-30; 32: 2025-05-28; 33: 2025-05-29; 35: 2026-01-09; 36: 2026-01-12; 39: 2025-05-30; 40: 2025-05-30; 42: 2026-01-13; 43: 2026-01-15; 46: 2025-05-31; 47: 2025-06-01; 49: 2026-01-18; 50: 2026-01-18; 53: 2025-06-02; 54: 2025-06-03; 56: 2026-01-20; 57: 2026-01-21; 60: 2025-06-04; 61: 2025-06-14; 63: 2026-01-24; 64: 2026-02-03; 67: 2025-06-15; 68: 2025-06-16; 70: 2026-02-04; 71: 2026-02-05; 75: 2025-06-21; 76: 2025-06-24; 78: 2026-02-17; 82: 2025-06-23; 83: 2025-06-23; 85: 2026-02-18; 86: 2026-02-18; 91: 2025-06-18; 92: 2025-06-28; 94: 2026-01-17; 98: 2025-09-26; 99: 2025-10-03; 101: 2025-03-16; 102: Done; 105: 2025-09-26; 106: 2025-10-03; 112: GP Project(Reuse); 113: 2025-09-28; 114: 2025-10-05; 120: 2026-01-09; 121: 2026-01-18; 127: 2025-12-14; 128: 2025-12-22; 130: 0; 134: 2026-01-19; 135: 2026-01-26; 141: 2026-01-27; 142: 2026-01-29; 148: 2026-01-15; 149: 2026-01-16; 155: 2025-12-23; 156: 2025-01-13; 162: 2025-12-08; 163: 2026-01-02; 169: 2025-12-25; 170: 2025-12-28; 176: 2026-01-30; 177: 2026-02-01
147 | PSS-14 | AGE26AL | 1: KH 555; 2: F07; 3: MSC; 4: 2025-08-06; 5: Keller; 6: Yes; 7: 545315; 8: 2681333; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-08; 18: 2025-05-18; 20: 2025-06-11; 21: 2025-06-27; 32: 2025-05-24; 33: 2025-05-25; 35: 2026-01-04; 36: 2026-01-05; 39: 2025-05-26; 40: 2025-05-26; 42: 2026-01-06; 43: 2026-01-06; 46: 2025-05-27; 47: 2025-05-28; 49: 2026-01-07; 50: 2026-01-07; 53: 2025-05-29; 54: 2025-05-30; 56: 2026-01-08; 57: 2026-01-09; 60: 2025-05-31; 61: 2025-06-10; 63: 2026-01-20; 64: 2026-01-23; 67: 2025-06-11; 68: 2025-06-12; 70: 2026-02-03; 71: 2026-02-03; 75: 2025-06-17; 76: 2025-06-20; 78: 2026-02-07; 82: 2025-06-19; 83: 2025-06-19; 85: 2026-02-08; 86: 2026-02-08; 91: 2025-05-27; 92: 2025-06-06; 94: 2026-01-06; 98: 2025-09-22; 99: 2025-09-29; 101: 2025-03-16; 102: Done; 105: 2025-09-22; 106: 2025-09-29; 108: 2026-02-09; 109: 2026-02-11; 112: GP Project; 113: 2025-09-24; 114: 2025-10-01; 116: 2026-02-10; 117: 2026-02-11; 120: 2026-01-19; 121: 2026-01-28; 127: 2025-12-01; 128: 2025-12-09; 130: 0; 134: 2026-01-29; 135: 2026-02-05; 141: 2026-02-06; 142: 2026-02-08; 148: 2026-01-22; 149: 2026-01-23; 155: 2025-12-23; 156: 2025-01-13; 158: 2026-02-06; 162: 2025-12-30; 163: 2026-01-24; 169: 2025-12-12; 170: 2025-12-15; 176: 2026-02-09; 177: 2026-02-11
148 | PSS-14 | AGE26AL | 1: KH 557; 2: F07; 3: MSC; 4: 2025-08-06; 5: Keller; 6: Yes; 7: 546591; 8: 2682629; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-09; 18: 2025-05-19; 20: 2025-06-06; 21: 2025-06-23; 32: 2025-05-28; 33: 2025-05-29; 35: 2025-12-31; 36: 2026-01-02; 39: 2025-05-30; 40: 2025-05-30; 42: 2026-01-02; 43: 2026-01-03; 46: 2025-05-31; 47: 2025-06-01; 49: 2026-01-04; 50: 2026-01-04; 53: 2025-06-02; 54: 2025-06-03; 56: 2026-01-05; 57: 2026-01-05; 60: 2025-06-04; 61: 2025-06-14; 63: 2026-01-21; 64: 2026-01-24; 67: 2025-06-15; 68: 2025-06-16; 70: 2026-02-09; 71: 2026-02-10; 75: 2025-06-21; 76: 2025-06-24; 82: 2025-06-23; 83: 2025-06-23; 91: 2025-06-18; 92: 2025-06-28; 94: 2026-01-03; 95: 2026-02-11; 98: 2025-09-26; 99: 2025-10-03; 101: Done; 102: Done; 105: 2025-09-26; 106: 2025-10-03; 108: 2026-02-21; 109: 2026-02-26; 112: Odhav; 113: 2025-09-28; 114: 2025-10-05; 116: 2026-02-22; 117: 2026-02-26; 120: 2026-01-21; 121: 2026-01-30; 127: 2025-12-16; 128: 2025-12-24; 130: 0; 134: 2026-01-31; 135: 2026-02-07; 141: 2026-02-08; 142: 2026-02-10; 148: 2026-01-26; 149: 2026-01-27; 155: 2025-12-23; 156: 2025-01-13; 158: 2026-02-08; 162: 2025-12-30; 163: 2026-01-24; 169: 2025-12-27; 170: 2025-12-30; 176: 2026-02-11; 177: 2026-02-13
149 | PSS-14 | AGE26AL | 1: KH 581; 2: F08; 3: BHAVANI; 4: 2025-12-27; 5: Keller; 6: Yes; 7: 544219; 8: 2679104; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-07; 18: 2025-06-16; 20: 2025-04-18; 21: 2025-04-30; 24: YES; 25: Bauer; 29: 2025-05-26; 30: 2025-06-15; 32: 2025-10-04; 33: 2025-10-05; 35: 2025-12-29; 36: 2025-12-30; 39: 2025-10-06; 40: 2025-10-06; 42: 2025-12-31; 43: 2026-01-01; 46: 2025-10-07; 47: 2025-10-08; 49: 2026-01-02; 50: 2026-01-02; 53: 2025-10-09; 54: 2025-10-10; 56: 2026-01-03; 57: 2026-01-04; 60: 2025-10-11; 61: 2025-10-21; 63: 2026-01-05; 64: 2026-01-08; 67: 2025-10-22; 68: 2025-10-23; 70: 2026-01-09; 71: 2026-01-10; 75: 2025-10-28; 76: 2025-10-31; 78: 2026-02-05; 82: 2025-10-30; 83: 2025-10-30; 85: 2026-02-06; 86: 2026-02-06; 91: 2025-10-18; 92: 2025-10-28; 94: 2025-12-31; 95: 2026-02-25; 98: 2025-12-14; 99: 2025-12-21; 101: 2025-03-20; 102: 2025-04-16; 105: 2025-12-14; 106: 2025-12-21; 108: 2026-02-23; 112: GP Project; 113: 2025-12-16; 114: 2025-12-23; 116: 2026-02-02; 117: 2026-02-05; 120: 2026-01-07; 121: 2026-01-17; 127: 2026-01-15; 128: 2026-01-23; 130: 0; 134: 2026-01-18; 135: 2026-01-25; 141: 2026-01-26; 142: 2026-01-28; 148: 2026-01-24; 149: 2026-01-25; 155: 2025-12-23; 156: 2025-01-13; 158: 2026-02-20; 162: 2025-12-08; 163: 2026-01-02; 165: 2026-01-31; 166: 2026-02-15; 169: 2026-01-26; 170: 2026-01-29; 176: 2026-01-30; 177: 2026-02-01
150 | PSS-14 | AGE26AL | 1: KH 582; 2: F01; 3: BHAVANI; 4: 2026-02-23; 5: Pinnacle; 6: Yes; 7: 544857; 8: 2679752; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-28; 18: 2025-06-06; 20: 2025-08-09; 21: 2025-11-07; 24: YES; 25: keller; 29: 2026-02-10; 30: 2026-02-23; 32: 2025-06-07; 33: 2025-06-08; 39: 2025-06-09; 40: 2025-06-09; 46: 2025-06-10; 47: 2025-06-11; 53: 2025-06-12; 54: 2025-06-13; 60: 2025-06-14; 61: 2025-06-24; 67: 2025-06-25; 68: 2025-06-26; 75: 2025-07-01; 76: 2025-07-04; 82: 2025-07-03; 83: 2025-07-03; 91: 2025-06-10; 92: 2025-06-20; 94: 0; 98: 2025-10-06; 99: 2025-10-13; 101: 2025-03-15; 102: 2025-04-17; 105: 2025-10-06; 106: 2025-10-13; 112: Keshav(Reuse); 113: 2025-10-08; 114: 2025-10-15; 120: 2026-01-29; 121: 2026-02-08; 127: 2025-12-16; 128: 2025-12-24; 130: 0; 134: 2026-02-09; 135: 2026-02-16; 141: 2026-02-17; 142: 2026-02-19; 148: 2026-02-01; 149: 2026-02-02; 155: 2025-01-22; 156: 2025-02-14; 158: 2026-02-26; 162: 2025-12-30; 163: 2026-01-24; 169: 2025-12-27; 170: 2025-12-30; 176: 2026-02-20; 177: 2026-02-22
151 | PSS-14 | AGE26AL | 1: KH 583; 2: F01; 3: MSC; 4: 2026-02-08; 5: Bauer; 6: Yes; 7: 545495; 8: 2680400; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-19; 18: 2025-05-29; 20: 2025-06-10; 21: 2025-06-19; 24: Yes; 25: keller; 29: 2026-01-27; 30: 2026-02-06; 32: 2025-06-05; 33: 2025-06-06; 35: 2026-02-12; 36: 2026-02-13; 39: 2025-06-07; 40: 2025-06-07; 42: 2026-02-13; 43: 2026-02-13; 46: 2025-06-08; 47: 2025-06-09; 49: 2026-02-19; 50: 2026-02-19; 53: 2025-06-10; 54: 2025-06-11; 60: 2025-06-12; 61: 2025-06-22; 67: 2025-06-23; 68: 2025-06-24; 75: 2025-06-29; 76: 2025-07-02; 82: 2025-07-01; 83: 2025-07-01; 91: 2025-06-08; 92: 2025-06-18; 94: 2026-02-18; 98: 2025-06-26; 99: 2025-07-03; 101: Done; 102: Done; 105: 2025-06-26; 106: 2025-07-03; 112: Bipin(Reuse); 113: 2025-06-28; 114: 2025-07-05; 120: 2026-01-29; 121: 2026-02-07; 127: 2025-12-02; 128: 2025-12-10; 130: 0; 134: 2026-02-08; 135: 2026-02-15; 141: 2026-02-16; 142: 2026-02-18; 148: 2026-02-01; 149: 2026-02-02; 155: 2025-12-23; 156: 2025-01-13; 158: 2026-02-26; 162: 2025-12-30; 163: 2026-01-24; 169: 2025-12-13; 170: 2025-12-16; 176: 2026-02-19; 177: 2026-02-21
152 | PSS-14 | AGE26AL | 1: KH 52; 2: F12; 3: MSC; 4: 2026-01-18; 5: Bauer; 6: Yes; 7: 546133; 8: 2681048; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-09; 18: 2025-05-19; 20: 2025-07-17; 21: 2025-07-30; 24: YES; 25: Saritha; 29: 2025-12-26; 30: 2026-01-16; 32: 2025-10-14; 33: 2025-10-15; 35: 2026-01-21; 36: 2026-01-22; 39: 2025-10-16; 40: 2025-10-16; 42: 2026-01-22; 43: 2026-01-23; 46: 2025-10-17; 47: 2025-10-18; 49: 2026-01-24; 50: 2026-01-24; 53: 2025-10-19; 54: 2025-10-20; 56: 2026-01-30; 57: 2026-01-30; 60: 2025-10-21; 61: 2025-10-31; 63: 2026-02-06; 64: 2026-02-13; 67: 2025-11-01; 68: 2025-11-02; 70: 2026-02-18; 71: 2026-02-19; 75: 2025-11-07; 76: 2025-11-10; 82: 2025-11-09; 83: 2025-11-09; 91: 2025-10-04; 92: 2025-10-14; 94: 2026-01-23; 98: 2025-11-04; 99: 2025-11-11; 101: 2025-03-15; 102: Done; 105: 2025-11-04; 106: 2025-11-11; 112: Bipin(Reuse); 113: 2025-11-06; 114: 2025-11-13; 120: 2026-02-19; 121: 2026-02-28; 127: 2026-01-01; 128: 2026-01-09; 130: 0; 134: 2026-03-01; 135: 2026-03-08; 141: 2026-03-09; 142: 2026-03-11; 148: 2026-02-20; 149: 2026-02-21; 155: 2025-01-22; 156: 2025-02-14; 158: 2026-02-06; 162: 2026-01-22; 163: 2026-02-16; 169: 2026-01-12; 170: 2026-01-15; 176: 2026-03-12; 177: 2026-03-14
153 | PSS-14 | AGE26AL | 1: KH 51; 2: F12; 3: ODHAV; 4: 2025-12-25; 5: Bauer; 6: Yes; 7: 546771; 8: 2681696; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-20; 18: 2025-05-29; 20: 2025-11-22; 21: 2025-12-02; 32: 2025-06-10; 33: 2025-06-11; 35: 2025-12-28; 36: 2026-01-02; 39: 2025-06-12; 40: 2025-06-12; 42: 2026-01-03; 43: 2026-01-08; 46: 2025-06-13; 47: 2025-06-14; 49: 2026-01-09; 50: 2026-01-09; 53: 2025-06-15; 54: 2025-06-16; 56: 2026-01-12; 57: 2026-01-13; 60: 2025-06-17; 61: 2025-06-27; 63: 2026-01-15; 64: 2026-01-22; 67: 2025-06-28; 68: 2025-06-29; 70: 2026-01-25; 71: 2026-01-26; 75: 2025-07-04; 76: 2025-07-07; 78: 2026-02-02; 82: 2025-07-06; 83: 2025-07-06; 85: 2026-02-03; 86: 2026-02-03; 91: 2025-06-13; 92: 2025-06-23; 94: 2026-01-08; 98: 2025-07-01; 99: 2025-07-08; 101: Done; 102: Done; 105: 2025-07-01; 106: 2025-07-08; 108: 2026-02-01; 109: 2026-02-03; 112: Harsh; 113: 2025-07-03; 114: 2025-07-10; 116: 2026-02-02; 117: 2026-02-03; 120: 2026-01-11; 121: 2026-01-20; 127: 2025-12-03; 128: 2025-12-11; 130: 0; 134: 2026-01-21; 135: 2026-01-28; 141: 2026-01-29; 142: 2026-01-31; 148: 2026-01-12; 149: 2026-01-13; 155: 2025-12-23; 156: 2025-01-13; 162: 2025-12-08; 163: 2026-01-02; 169: 2025-12-14; 170: 2025-12-17; 176: 2026-02-01; 177: 2026-02-03
154 | PSS-14 | AGE26AL | 1: KH 552; 2: F12; 3: MSC; 4: 2026-02-05; 5: Saritha; 6: Yes; 7: 547409; 8: 2682344; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-10; 18: 2025-05-19; 20: 2025-12-04; 21: 2025-12-25; 24: YES; 25: Saritha; 29: 2026-01-14; 30: 2026-01-26; 32: 2025-05-20; 33: 2025-05-21; 35: 2026-02-06; 36: 2026-02-07; 39: 2025-05-22; 40: 2025-05-22; 42: 2026-02-07; 43: 2026-02-07; 46: 2025-05-23; 47: 2025-05-24; 49: 2026-02-18; 50: 2026-02-18; 53: 2025-05-25; 54: 2025-05-26; 56: 2026-02-21; 57: 2026-02-22; 60: 2025-05-27; 61: 2025-06-06; 63: 2026-02-23; 67: 2025-06-07; 68: 2025-06-08; 75: 2025-06-13; 76: 2025-06-16; 82: 2025-06-15; 83: 2025-06-15; 91: 2025-06-10; 92: 2025-06-20; 94: 2026-02-16; 98: 2025-09-18; 99: 2025-09-25; 101: Done; 102: Done; 105: 2025-09-18; 106: 2025-09-25; 112: GP Project(Reuse); 113: 2025-09-20; 114: 2025-09-27; 120: 2026-01-31; 121: 2026-02-09; 127: 2025-12-17; 128: 2025-12-25; 130: 0; 134: 2026-02-10; 135: 2026-02-17; 141: 2026-02-18; 142: 2026-02-20; 148: 2026-02-02; 149: 2026-02-03; 155: 2025-01-22; 156: 2025-02-14; 162: 2025-12-30; 163: 2026-01-24; 169: 2025-12-28; 170: 2025-12-31; 176: 2026-02-21; 177: 2026-02-23
155 | PSS-14 | AGE26AL | 1: KH 588; 2: F08; 3: CEIPL; 4: 2025-04-18; 5: Keller; 6: Yes; 7: 544399; 8: 2678171; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-17; 18: 2025-06-26; 20: 2025-04-17; 21: 2025-04-25; 32: 2025-10-08; 33: 2025-10-09; 35: 2025-05-02; 36: 2025-05-03; 39: 2025-10-10; 40: 2025-10-10; 42: 2025-05-05; 43: 2025-05-07; 46: 2025-10-11; 47: 2025-10-12; 49: 2025-05-18; 50: 2025-05-19; 53: 2025-10-13; 54: 2025-10-14; 56: 2025-05-21; 57: 2025-05-21; 60: 2025-10-15; 61: 2025-10-25; 63: 2025-05-22; 64: 2025-06-08; 67: 2025-10-26; 68: 2025-10-27; 70: 2025-06-11; 71: 2025-06-12; 75: 2025-11-01; 76: 2025-11-04; 78: 2025-06-20; 82: 2026-02-11; 83: 2026-02-11; 85: 2025-06-22; 86: 2025-06-22; 91: 2025-10-11; 92: 2025-10-21; 94: 2025-05-16; 98: 2025-12-08; 99: 2025-12-15; 101: Done; 102: Done; 105: 2025-12-08; 106: 2025-12-15; 112: GP Project(Reuse); 113: 2025-12-10; 114: 2025-12-17; 116: 2026-02-18; 117: 2026-02-22; 120: 2025-12-27; 121: 2026-01-06; 127: 2026-01-08; 128: 2026-01-16; 130: 0; 134: 2026-01-07; 135: 2026-01-14; 141: 2026-01-15; 142: 2026-01-17; 148: 2026-01-17; 149: 2026-01-18; 155: 2025-11-20; 156: 2025-12-10; 158: 2026-02-19; 162: 2025-12-08; 163: 2026-01-02; 165: 2026-01-31; 166: 2026-02-15; 169: 2026-01-19; 170: 2026-01-22; 176: 2026-01-23; 177: 2026-01-25
156 | PSS-14 | AGE26AL | 1: KH 589; 2: F08; 3: BPS; 4: 2025-07-04; 5: Keller; 6: Yes; 7: 545037; 8: 2678819; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-07; 18: 2025-06-17; 20: 2025-04-09; 21: 2025-04-17; 32: 2025-10-12; 33: 2025-10-13; 35: 2025-05-27; 36: 2025-06-01; 39: 2025-10-14; 40: 2025-10-14; 42: 2025-06-02; 43: 2025-06-05; 46: 2025-10-15; 47: 2025-10-16; 49: 2025-06-09; 50: 2025-06-09; 53: 2025-10-17; 54: 2025-10-18; 56: 2025-06-20; 57: 2025-06-22; 60: 2025-10-19; 61: 2025-10-29; 63: 2025-06-23; 64: 2025-08-09; 67: 2025-10-30; 68: 2025-10-31; 70: 2025-08-10; 71: 2025-08-11; 75: 2025-11-05; 76: 2025-11-08; 78: 2025-08-28; 82: 2025-11-07; 83: 2025-11-07; 85: 2025-12-20; 86: 2025-12-20; 91: 2025-10-18; 92: 2025-10-28; 94: 2025-06-04; 98: 2025-11-02; 99: 2025-11-09; 101: 2025-03-18; 102: 2025-04-22; 105: 2025-11-02; 106: 2025-11-09; 108: 2026-01-03; 112: Keshav; 113: 2025-11-04; 114: 2025-11-11; 116: 2025-11-01; 117: 2026-01-08; 120: 2026-02-09; 121: 2026-02-18; 127: 2026-01-15; 128: 2026-01-23; 130: 0; 134: 2026-02-19; 135: 2026-02-26; 141: 2026-02-27; 142: 2026-03-01; 148: 2026-02-22; 149: 2026-02-23; 155: 2025-01-22; 156: 2025-02-14; 158: 2026-02-17; 162: 2026-01-22; 163: 2026-02-16; 165: 2026-01-31; 166: 2026-02-15; 169: 2026-01-26; 170: 2026-01-29; 176: 2026-03-02; 177: 2026-03-04; 184: CEIPL - upto PCC done loc allotted on 18-Apr-25, BPS - from Anchor Cage from 04-Jul-25
157 | PSS-14 | AGE26AL | 1: KH 590; 2: F01; 3: MSC; 4: 2025-08-06; 5: Bauer; 6: Yes; 7: 545675; 8: 2679467; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-30; 18: 2025-06-08; 20: 2025-06-21; 21: 2025-07-02; 32: 2025-10-04; 33: 2025-10-05; 35: 2025-12-02; 36: 2025-12-03; 39: 2025-10-06; 40: 2025-10-06; 42: 2025-12-04; 43: 2025-12-04; 46: 2025-10-07; 47: 2025-10-08; 49: 2025-12-05; 50: 2025-12-05; 53: 2025-10-09; 54: 2025-10-10; 56: 2026-01-05; 57: 2026-01-05; 60: 2025-10-11; 61: 2025-10-21; 63: 2026-01-05; 64: 2026-01-10; 67: 2025-10-22; 68: 2025-10-23; 70: 2026-01-12; 71: 2026-01-13; 75: 2025-10-28; 76: 2025-10-31; 78: 2026-01-30; 82: 2025-10-30; 83: 2025-10-30; 85: 2026-01-31; 86: 2026-01-31; 91: 2025-10-07; 92: 2025-10-17; 94: 2025-12-04; 95: 2026-02-11; 98: 2025-10-25; 99: 2025-11-01; 101: 2025-03-21; 102: 2025-04-23; 105: 2025-10-25; 106: 2025-11-01; 112: SS Jadeja; 113: 2025-10-27; 114: 2025-11-03; 116: 2026-02-08; 117: 2026-02-09; 120: 2026-02-19; 121: 2026-02-28; 127: 2026-01-04; 128: 2026-01-12; 130: 0; 134: 2026-03-01; 135: 2026-03-08; 141: 2026-03-09; 142: 2026-03-11; 148: 2026-02-22; 149: 2026-02-23; 155: 2025-01-22; 156: 2025-02-14; 158: 2026-02-22; 162: 2026-01-22; 163: 2026-02-16; 169: 2026-01-15; 170: 2026-01-18; 176: 2026-03-12; 177: 2026-03-14
158 | PSS-14 | AGE26AL | 1: KH 591; 2: F01; 3: HBG; 4: 2026-02-08; 5: Bauer; 6: Yes; 7: 546313; 8: 2680115; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-20; 18: 2025-05-29; 20: 2025-05-27; 21: 2025-06-07; 24: YES; 25: Bauer; 29: 2026-01-20; 30: 2026-01-31; 32: 2025-10-15; 33: 2025-10-16; 35: 2026-02-09; 36: 2026-02-11; 39: 2025-10-17; 40: 2025-10-17; 42: 2026-02-26; 43: 2026-02-26; 46: 2025-10-18; 47: 2025-10-19; 53: 2025-10-20; 54: 2025-10-21; 60: 2025-10-22; 61: 2025-11-01; 67: 2025-11-02; 68: 2025-11-03; 75: 2025-11-08; 76: 2025-11-11; 82: 2025-11-10; 83: 2025-11-10; 91: 2025-10-18; 92: 2025-10-28; 94: 0; 98: 2025-11-05; 99: 2025-11-12; 101: Done; 102: Done; 105: 2025-11-05; 106: 2025-11-12; 112: Bipin(Reuse); 113: 2025-11-07; 114: 2025-11-14; 120: 2026-01-30; 121: 2026-02-08; 127: 2025-12-28; 128: 2026-01-05; 130: 0; 134: 2026-02-09; 135: 2026-02-16; 141: 2026-02-17; 142: 2026-02-19; 148: 2026-02-03; 149: 2026-02-04; 155: 2025-01-22; 156: 2025-02-14; 158: 2026-02-22; 162: 2025-12-30; 163: 2026-01-24; 169: 2026-01-08; 170: 2026-01-11; 176: 2026-02-20; 177: 2026-02-22
159 | PSS-14 | AGE26AL | 1: KH 592; 2: F02; 3: DNC; 4: 2025-06-12; 5: Bauer; 6: Yes; 7: 546951; 8: 2680763; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-30; 18: 2025-06-08; 20: 2025-05-04; 21: 2025-05-19; 32: 2025-10-16; 33: 2025-10-17; 35: 2025-08-20; 36: 2025-09-21; 38: Delay due to dewatering required; 39: 2025-10-18; 40: 2025-10-18; 42: 2025-09-23; 43: 2025-09-24; 46: 2025-10-19; 47: 2025-10-20; 49: 2025-09-25; 50: 2025-09-25; 53: 2025-10-21; 54: 2025-10-22; 56: 2025-09-25; 57: 2025-09-29; 60: 2025-10-23; 61: 2025-11-02; 63: 2025-09-30; 64: 2025-10-20; 67: 2025-11-03; 68: 2025-11-04; 70: 2025-10-20; 71: 2025-10-21; 75: 2025-11-09; 76: 2025-11-12; 78: 2025-11-18; 82: 2025-11-11; 83: 2025-11-11; 85: 2025-11-18; 86: 2025-11-18; 91: 2025-10-24; 92: 2025-11-03; 94: 2025-09-24; 98: 2025-11-06; 99: 2025-11-13; 101: 2025-03-27; 102: 2025-05-25; 105: 2025-11-06; 106: 2025-11-13; 108: 2026-02-16; 109: 2026-02-20; 112: Harsh; 113: 2025-11-08; 114: 2025-11-15; 116: 2026-02-02; 117: 2026-02-05; 120: 2026-02-09; 121: 2026-02-18; 123: 2026-02-26; 127: 2025-12-28; 128: 2026-01-05; 130: 0; 134: 2026-02-19; 135: 2026-02-26; 141: 2026-02-27; 142: 2026-03-01; 148: 2026-02-27; 149: 2026-02-28; 155: 2025-01-22; 156: 2025-02-14; 158: 2026-02-23; 162: 2026-01-22; 163: 2026-02-16; 165: 2026-01-31; 166: 2026-02-15; 169: 2026-01-08; 170: 2026-01-11; 176: 2026-03-02; 177: 2026-03-04
160 | PSS-14 | AGE26AL | 1: KH 550; 2: F12; 3: HBG; 4: 2026-01-08; 5: Bauer; 6: Yes; 7: 547588; 8: 2681411; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-20; 18: 2025-05-29; 20: 2025-12-24; 21: 2026-01-06; 32: 2025-10-04; 33: 2025-10-05; 35: 2026-01-19; 36: 2026-01-22; 39: 2025-10-06; 40: 2025-10-06; 42: 2026-01-23; 43: 2026-01-23; 46: 2025-10-07; 47: 2025-10-08; 49: 2026-01-23; 50: 2026-01-23; 53: 2025-10-09; 54: 2025-10-10; 56: 2026-01-24; 57: 2026-01-24; 60: 2025-10-11; 61: 2025-10-21; 63: 2026-01-25; 64: 2026-01-31; 67: 2025-10-22; 68: 2025-10-23; 70: 2026-02-01; 71: 2026-02-02; 75: 2025-10-28; 76: 2025-10-31; 78: 2026-02-18; 82: 2025-10-30; 83: 2025-10-30; 85: 2026-02-22; 86: 2026-02-22; 91: 2025-10-07; 92: 2025-10-17; 94: 2026-01-23; 98: 2025-10-25; 99: 2025-11-01; 101: Done; 102: Done; 105: 2025-10-25; 106: 2025-11-01; 112: SS Jadeja(Reuse); 113: 2025-10-27; 114: 2025-11-03; 120: 2026-01-01; 121: 2026-01-10; 127: 2025-12-31; 128: 2026-01-08; 130: 0; 134: 2026-01-11; 135: 2026-01-18; 141: 2026-01-19; 142: 2026-01-21; 148: 2026-01-09; 149: 2026-01-10; 155: 2025-12-23; 156: 2025-01-13; 162: 2025-12-08; 163: 2026-01-02; 169: 2026-01-11; 170: 2026-01-14; 176: 2026-01-22; 177: 2026-01-24
161 | PSS-14 | AGE26AL | 1: KH 551; 2: F06; 3: BIPL; 4: 2026-01-30; 5: Keller; 6: Yes; 7: 548226; 8: 2682059; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-10; 18: 2025-05-19; 20: 2026-01-13; 21: 2026-01-22; 32: 2025-10-06; 33: 2025-10-07; 35: 2026-02-02; 36: 2026-02-06; 39: 2025-10-08; 40: 2025-10-08; 42: 2026-02-06; 43: 2026-02-06; 46: 2025-10-09; 47: 2025-10-10; 49: 2026-02-08; 50: 2026-02-08; 53: 2025-10-11; 54: 2025-10-12; 56: 2026-02-09; 57: 2026-02-09; 60: 2025-10-13; 61: 2025-10-23; 63: 2026-02-10; 64: 2026-02-16; 67: 2025-10-24; 68: 2025-10-25; 70: 2026-02-17; 71: 2026-02-18; 75: 2025-10-30; 76: 2025-11-02; 82: 2025-11-01; 83: 2025-11-01; 85: 2026-02-25; 86: 2026-02-25; 91: 2025-10-09; 92: 2025-10-19; 94: 2026-02-10; 98: 2025-10-27; 99: 2025-11-03; 101: Done; 102: Done; 105: 2025-10-27; 106: 2025-11-03; 112: SS Jadeja(Reuse); 113: 2025-10-29; 114: 2025-11-05; 116: 2026-02-20; 120: 2026-02-10; 121: 2026-02-19; 127: 2025-12-07; 128: 2025-12-15; 130: 0; 134: 2026-02-20; 135: 2026-02-27; 141: 2026-02-28; 142: 2026-03-02; 148: 2026-02-21; 149: 2026-02-22; 155: 2025-01-22; 156: 2025-02-14; 162: 2026-01-22; 163: 2026-02-16; 169: 2025-12-18; 170: 2025-12-21; 176: 2026-03-03; 177: 2026-03-05
162 | PSS-14 | AGE26AL | 1: KH 579; 2: F07; 3: MSC; 4: 2026-02-11; 5: Keller; 6: Yes; 7: 548864; 8: 2682706; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-25; 18: 2025-06-04; 20: 2025-05-31; 21: 2025-06-08; 24: YES; 25: Saritha; 29: 2026-01-31; 30: 2026-02-08; 32: 2025-10-11; 33: 2025-10-12; 35: 2026-02-12; 36: 2026-02-13; 39: 2025-10-13; 40: 2025-10-13; 42: 2026-02-13; 43: 2026-02-14; 46: 2025-10-14; 47: 2025-10-15; 49: 2026-02-18; 50: 2026-02-18; 53: 2025-10-16; 54: 2025-10-17; 56: 2026-02-20; 57: 2026-02-22; 60: 2025-10-18; 61: 2025-10-28; 63: 2026-02-22; 64: 2026-02-25; 67: 2025-10-29; 68: 2025-10-30; 70: 2026-02-26; 71: 2026-02-27; 75: 2025-11-04; 76: 2025-11-07; 82: 2025-11-06; 83: 2025-11-06; 91: 2025-10-27; 92: 2025-11-06; 94: 2026-02-16; 98: 2025-11-01; 99: 2025-11-08; 101: Done; 102: Done; 105: 2025-11-01; 106: 2025-11-08; 112: Odhav(Reuse); 113: 2025-11-03; 114: 2025-11-10; 116: 2026-02-21; 120: 2026-02-20; 121: 2026-02-28; 127: 2025-12-31; 128: 2026-01-08; 130: 0; 134: 2026-03-01; 135: 2026-03-08; 141: 2026-03-09; 142: 2026-03-11; 148: 2026-03-01; 149: 2026-03-02; 155: 2025-01-22; 156: 2025-02-14; 158: 2026-02-18; 162: 2026-01-22; 163: 2026-02-16; 169: 2026-01-11; 170: 2026-01-14; 176: 2026-03-12; 177: 2026-03-14
163 | PSS-14 | AGE26AL | 1: KH 596; 2: F08; 3: SHREERAM; 4: 2026-01-08; 5: Keller; 6: Yes; 7: 545217; 8: 2677886; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-18; 18: 2025-06-28; 20: 2025-05-03; 21: 2025-05-28; 24: YES; 25: Bauer; 29: 2025-12-22; 30: 2026-01-04; 32: 2025-10-18; 33: 2025-10-19; 35: 2026-01-12; 36: 2026-01-13; 39: 2025-10-20; 40: 2025-10-20; 42: 2026-01-15; 43: 2026-01-18; 46: 2025-10-21; 47: 2025-10-22; 49: 2026-01-22; 50: 2026-01-22; 53: 2025-10-23; 54: 2025-10-24; 56: 2026-01-23; 57: 2026-01-25; 60: 2025-10-25; 61: 2025-11-04; 63: 2026-01-30; 64: 2026-02-07; 67: 2025-11-05; 68: 2025-11-06; 70: 2026-02-10; 71: 2026-02-11; 75: 2025-11-11; 76: 2025-11-14; 78: 2026-02-22; 82: 2025-11-13; 83: 2025-11-13; 85: 2026-03-23; 86: 2026-02-23; 91: 2025-10-26; 92: 2025-11-05; 94: 2026-01-21; 95: 2026-02-05; 98: 2025-11-08; 99: 2025-11-15; 101: Done; 102: Done; 105: 2025-11-08; 106: 2025-11-15; 112: SS Jadeja(Reuse); 113: 2025-11-10; 114: 2025-11-17; 120: 2025-12-27; 121: 2026-01-06; 127: 2026-01-09; 128: 2026-01-17; 130: 2026-02-22; 134: 2026-01-07; 135: 2026-01-14; 141: 2026-01-15; 142: 2026-01-17; 148: 2026-01-18; 149: 2026-01-19; 155: 2025-12-23; 156: 2025-01-13; 158: 2026-02-20; 159: 2026-02-25; 162: 2025-12-08; 163: 2026-01-02; 165: 2026-01-31; 166: 2026-02-15; 169: 2026-01-20; 170: 2026-01-23; 176: 2026-01-24; 177: 2026-01-26
164 | PSS-14 | AGE26AL | 1: KH 597; 2: F09; 3: HBG; 4: 2026-01-22; 5: Keller; 6: Yes; 7: 545855; 8: 2678534; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-09; 18: 2025-06-18; 20: 2025-05-07; 21: 2025-05-29; 24: YES; 25: Bauer; 29: 2026-01-05; 30: 2026-01-18; 32: 2025-10-18; 33: 2025-10-19; 35: 2026-01-24; 36: 2026-01-26; 39: 2025-10-20; 40: 2025-10-20; 42: 2026-01-28; 43: 2026-01-30; 46: 2025-10-21; 47: 2025-10-22; 49: 2026-02-01; 50: 2026-02-01; 53: 2025-10-23; 54: 2025-10-24; 56: 2026-02-04; 57: 2026-02-04; 60: 2025-10-25; 61: 2025-11-04; 63: 2026-02-04; 64: 2026-02-07; 67: 2025-11-05; 68: 2025-11-06; 70: 2026-02-15; 71: 2026-02-16; 75: 2025-11-11; 76: 2025-11-14; 78: 2026-02-22; 82: 2025-11-13; 83: 2025-11-13; 85: 2026-02-26; 86: 2026-02-26; 91: 2025-10-24; 92: 2025-11-03; 94: 2026-01-31; 95: 2026-02-12; 98: 2025-11-08; 99: 2025-11-15; 101: 2025-03-16; 102: 2025-04-21; 105: 2025-11-08; 106: 2025-11-15; 112: Keshav(Reuse); 113: 2025-11-10; 114: 2025-11-17; 116: 2026-02-25; 120: 2026-02-09; 121: 2026-02-18; 127: 2026-01-05; 128: 2026-01-13; 130: 2026-02-25; 134: 2026-02-19; 135: 2026-02-26; 141: 2026-02-27; 142: 2026-03-01; 148: 2026-02-14; 149: 2026-02-15; 155: 2025-01-22; 156: 2025-02-14; 158: 2026-02-05; 159: 2026-02-22; 162: 2026-01-22; 163: 2026-02-16; 165: 2026-01-31; 166: 2026-02-15; 169: 2026-01-16; 170: 2026-01-19; 176: 2026-03-02; 177: 2026-03-04
165 | PSS-14 | AGE25CL | 1: WTG 423; 2: F13; 3: SHREEJI; 4: 2025-10-13; 5: Bauer; 6: Yes; 7: 543367; 8: 2676332; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-03-25; 18: 2025-04-03; 20: 2025-07-03; 21: 2025-07-17; 32: 2025-05-10; 33: 2025-05-11; 35: 2025-10-27; 36: 2025-10-29; 39: 2025-05-12; 40: 2025-05-12; 42: 2025-10-29; 43: 2025-10-30; 46: 2025-05-13; 47: 2025-05-14; 49: 2025-10-31; 50: 2025-10-31; 53: 2025-05-15; 54: 2025-05-16; 56: 2025-11-03; 57: 2025-11-04; 60: 2025-05-17; 61: 2025-05-27; 63: 2025-11-05; 64: 2025-11-13; 67: 2025-05-28; 68: 2025-05-29; 70: 2025-11-13; 71: 2025-11-14; 75: 2025-06-03; 76: 2025-06-06; 78: 2025-11-19; 82: 2025-06-05; 83: 2025-06-05; 85: 2025-11-20; 86: 2025-11-20; 91: 2025-05-21; 92: 2025-05-31; 94: 2025-12-03; 95: 2026-01-16; 98: 2025-05-31; 99: 2025-06-07; 101: Done; 102: Done; 105: 2025-05-31; 106: 2025-06-07; 108: 2026-02-13; 109: 2026-02-14; 112: GP Project; 113: 2025-06-02; 114: 2025-06-09; 116: 2026-01-12; 117: 2026-02-06; 120: 2025-10-17; 121: 2025-11-01; 123: 2026-02-19; 127: 2025-10-09; 128: 2025-10-17; 130: 2026-01-21; 134: 2025-11-02; 135: 2025-11-09; 141: 2025-11-10; 142: 2025-11-12; 148: 2025-11-15; 149: 2025-11-16; 155: 2025-10-20; 156: 2025-11-10; 158: 2026-02-02; 162: 2025-10-02; 163: 2025-10-27; 165: 2026-01-31; 166: 2026-02-15; 169: 2025-11-17; 170: 2025-11-20; 176: 2025-11-22; 177: 2025-11-23
166 | PSS-14 | AGE26AL | 1: KH 599; 2: F02; 3: HBG; 4: 2026-02-05; 5: Bauer; 6: Yes; 7: 547130; 8: 2679830; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-09; 18: 2025-06-18; 20: 2025-04-21; 21: 2025-05-03; 24: YES; 25: Bauer; 29: 2026-01-20; 30: 2026-01-29; 32: 2025-10-23; 33: 2025-10-24; 35: 2026-02-07; 36: 2026-02-09; 39: 2025-10-25; 40: 2025-10-25; 42: 2026-02-10; 43: 2026-02-11; 46: 2025-10-26; 47: 2025-10-27; 49: 2026-02-12; 50: 2026-02-12; 53: 2025-10-28; 54: 2025-10-29; 56: 2026-02-16; 57: 2026-02-16; 60: 2025-10-30; 61: 2025-11-09; 63: 2026-02-17; 64: 2026-02-19; 67: 2025-11-10; 68: 2025-11-11; 70: 2026-02-23; 71: 2026-02-24; 75: 2025-11-16; 76: 2025-11-19; 82: 2025-11-18; 83: 2025-11-18; 91: 2025-11-05; 92: 2025-11-15; 94: 2026-02-11; 95: 2026-02-26; 98: 2025-11-13; 99: 2025-11-20; 101: Done; 102: Done; 105: 2025-11-13; 106: 2025-11-20; 108: 2026-02-17; 112: Harsh(Reuse); 113: 2025-11-15; 114: 2025-11-22; 116: 2026-02-18; 120: 2026-01-20; 121: 2026-01-29; 127: 2026-01-20; 128: 2026-01-28; 130: 0; 134: 2026-01-30; 135: 2026-02-06; 141: 2026-02-07; 142: 2026-02-09; 148: 2026-01-29; 149: 2026-01-30; 155: 2025-12-23; 156: 2025-01-13; 158: 2026-02-23; 162: 2025-12-30; 163: 2026-01-24; 165: 2026-01-31; 166: 2026-02-15; 169: 2026-01-31; 170: 2026-02-03; 176: 2026-02-10; 177: 2026-02-12
167 | PSS-14 | AGE26AL | 1: KH 600; 2: F02; 3: DNC; 4: 2025-06-12; 5: Bauer; 6: Yes; 7: 547768; 8: 2680478; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-30; 18: 2025-06-08; 20: 2025-05-30; 21: 2025-06-10; 32: 2025-10-25; 33: 2025-10-26; 35: 2025-11-12; 36: 2025-11-16; 39: 2025-10-27; 40: 2025-10-27; 42: 2025-11-16; 43: 2025-11-23; 45: Delay due to induction issues; 46: 2025-10-28; 47: 2025-10-29; 49: 2025-11-28; 50: 2025-11-29; 53: 2025-10-30; 54: 2025-10-31; 56: 2025-11-30; 57: 2025-11-30; 60: 2025-11-01; 61: 2025-11-11; 63: 2025-12-01; 64: 2025-12-05; 67: 2025-11-12; 68: 2025-11-13; 70: 2025-12-06; 71: 2025-12-07; 75: 2025-11-18; 76: 2025-11-21; 78: 2026-01-26; 82: 2025-11-20; 83: 2025-11-20; 85: 2025-12-27; 86: 2025-12-27; 91: 2025-11-09; 92: 2025-11-19; 94: 2025-11-16; 98: 2025-11-15; 99: 2025-11-22; 101: 2025-03-28; 102: 2025-04-28; 105: 2025-11-15; 106: 2025-11-22; 108: 2026-02-10; 109: 2026-02-20; 112: Harsh; 113: 2025-11-17; 114: 2025-11-24; 116: 2026-02-10; 117: 2026-02-13; 120: 2026-01-01; 121: 2026-01-10; 127: 2026-01-07; 128: 2026-01-15; 130: 0; 134: 2026-01-11; 135: 2026-01-18; 141: 2026-01-19; 142: 2026-01-21; 148: 2026-01-16; 149: 2026-01-17; 155: 2025-12-23; 156: 2025-01-13; 158: 2026-02-24; 162: 2025-12-08; 163: 2026-01-02; 165: 2026-01-31; 166: 2026-02-15; 169: 2026-01-18; 170: 2026-01-21; 176: 2026-01-22; 177: 2026-01-24
168 | PSS-14 | AGE26AL | 1: KH 553; 2: F06; 3: SHREERAM; 4: 2026-01-23; 5: Bauer; 6: Yes; 7: 548406; 8: 2681126; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-20; 18: 2025-05-29; 20: 2026-01-08; 21: 2026-01-18; 32: 2025-10-17; 33: 2025-10-18; 35: 2026-01-24; 36: 2026-01-28; 39: 2025-10-19; 40: 2025-10-19; 42: 2026-01-31; 43: 2026-02-05; 46: 2025-10-20; 47: 2025-10-21; 49: 2026-02-07; 50: 2026-02-07; 53: 2025-10-22; 54: 2025-10-23; 56: 2026-02-09; 57: 2026-02-10; 60: 2025-10-24; 61: 2025-11-03; 63: 2026-02-11; 64: 2026-02-20; 67: 2025-11-04; 68: 2025-11-05; 75: 2025-11-10; 76: 2025-11-13; 82: 2025-10-20; 83: 2025-10-20; 91: 2025-10-20; 92: 2025-10-30; 94: 2026-02-06; 98: 2025-11-07; 99: 2025-11-14; 101: Done; 102: Done; 105: 2025-11-07; 106: 2025-11-14; 112: SS Jadeja(Reuse); 113: 2025-11-09; 114: 2025-11-16; 116: 2026-02-03; 117: 2026-02-07; 120: 2026-01-01; 121: 2026-01-10; 127: 2025-12-26; 128: 2026-01-03; 130: 0; 134: 2026-01-11; 135: 2026-01-18; 141: 2026-01-19; 142: 2026-01-21; 148: 2026-01-04; 149: 2026-01-05; 155: 2025-12-23; 156: 2025-01-13; 162: 2025-12-08; 163: 2026-01-02; 169: 2026-01-06; 170: 2026-01-09; 176: 2026-01-22; 177: 2026-01-24
169 | PSS-14 | AGE26AL | 1: KH 580; 2: F07; 3: HBG; 4: 2025-06-12; 5: Keller; 6: Yes; 7: 549044; 8: 2681774; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-10; 18: 2025-05-19; 20: 2025-05-29; 21: 2025-06-10; 32: 2025-10-18; 33: 2025-10-19; 35: 2025-11-02; 36: 2025-11-05; 39: 2025-10-20; 40: 2025-10-20; 42: 2025-11-06; 43: 2025-11-07; 46: 2025-10-21; 47: 2025-10-22; 49: 2025-11-08; 50: 2025-11-09; 53: 2025-10-23; 54: 2025-10-24; 56: 2025-11-18; 57: 2025-11-19; 60: 2025-10-25; 61: 2025-11-04; 63: 2025-11-23; 64: 2026-01-02; 66: Delay due to Steel Shortage; 67: 2025-11-05; 68: 2025-11-06; 70: 2026-01-04; 71: 2026-01-05; 75: 2025-11-11; 76: 2025-11-14; 78: 2026-01-18; 82: 2025-11-13; 83: 2025-11-13; 85: 2026-01-19; 86: 2026-01-19; 91: 2025-10-21; 92: 2025-10-31; 94: 2025-11-07; 95: 2026-02-10; 98: 2025-11-08; 99: 2025-11-15; 101: Done; 102: Done; 105: 2025-11-08; 106: 2025-11-15; 108: 2026-02-23; 109: 2026-02-27; 112: Harsh; 113: 2025-11-10; 114: 2025-11-17; 116: 2026-02-23; 117: 2026-02-27; 120: 2026-02-20; 121: 2026-02-28; 127: 2026-01-06; 128: 2026-01-14; 130: 0; 134: 2026-03-01; 135: 2026-03-08; 141: 2026-03-09; 142: 2026-03-11; 148: 2026-02-22; 149: 2026-02-23; 155: 2025-01-22; 156: 2025-02-14; 158: 2026-02-20; 162: 2026-01-22; 163: 2026-02-16; 169: 2026-01-17; 170: 2026-01-20; 176: 2026-03-12; 177: 2026-03-14
170 | PSS-14 | AGE26AL | 1: KH 478; 2: F05; 3: BIPL; 4: 2026-02-18; 5: Bauer; 6: Yes; 7: 549682; 8: 2682421; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-11; 18: 2025-05-20; 20: 2026-01-19; 21: 2026-01-27; 24: YES; 25: Bauer; 29: 2026-02-05; 30: 2026-02-15; 32: 2025-11-01; 33: 2025-11-02; 35: 2026-02-21; 36: 2026-02-26; 39: 2025-11-03; 40: 2025-11-03; 42: 2026-02-26; 46: 2025-11-04; 47: 2025-11-05; 53: 2025-11-06; 54: 2025-11-07; 60: 2025-11-08; 61: 2025-11-18; 67: 2025-11-19; 68: 2025-11-20; 75: 2025-11-25; 76: 2025-11-28; 82: 2025-11-27; 83: 2025-11-27; 91: 2025-11-04; 92: 2025-11-14; 94: 0; 98: 2025-11-22; 99: 2025-11-29; 101: Done; 102: Done; 105: 2025-11-22; 106: 2025-11-29; 112: Odhav(Reuse); 113: 2025-11-24; 114: 2025-12-01; 120: 2026-02-10; 121: 2026-02-19; 127: 2026-01-14; 128: 2026-01-22; 130: 0; 134: 2026-02-20; 135: 2026-02-27; 141: 2026-02-28; 142: 2026-03-02; 148: 2026-02-17; 149: 2026-02-18; 155: 2025-01-22; 156: 2025-02-14; 162: 2026-01-22; 163: 2026-02-16; 169: 2026-01-25; 170: 2026-01-28; 176: 2026-03-03; 177: 2026-03-05
171 | PSS-14 | AGE26AL | 1: KH 604; 2: F09; 3: SHREERAM; 4: 2025-06-12; 5: Keller; 6: Yes; 7: 546034; 8: 2677601; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-19; 18: 2025-06-29; 20: 2025-04-26; 21: 2025-05-06; 32: 2025-11-01; 33: 2025-11-02; 35: 2025-07-28; 36: 2025-08-03; 39: 2025-11-03; 40: 2025-11-03; 42: 2025-08-12; 43: 2025-08-14; 46: 2025-11-04; 47: 2025-11-05; 49: 2025-08-16; 50: 2025-08-16; 53: 2025-11-06; 54: 2025-11-07; 56: 2025-08-20; 57: 2025-08-20; 60: 2025-11-08; 61: 2025-11-18; 63: 2025-09-02; 64: 2025-09-21; 67: 2025-11-19; 68: 2025-11-20; 70: 2025-09-22; 71: 2025-09-23; 75: 2025-11-25; 76: 2025-11-28; 78: 2025-10-22; 82: 2025-11-27; 83: 2025-11-27; 85: 2025-11-07; 86: 2025-11-08; 91: 2025-11-17; 92: 2025-11-27; 94: 2025-08-14; 98: 2025-11-22; 99: 2025-11-29; 101: Done; 102: Done; 105: 2025-11-22; 106: 2025-11-29; 112: Keshav; 113: 2025-11-24; 114: 2025-12-01; 116: 2025-11-05; 117: 2026-02-11; 120: 2026-01-07; 121: 2026-01-17; 127: 2026-01-20; 128: 2026-01-28; 130: 0; 134: 2026-01-18; 135: 2026-01-25; 141: 2026-01-26; 142: 2026-01-28; 148: 2026-01-29; 149: 2026-01-30; 155: 2025-12-23; 156: 2025-01-13; 158: 2026-02-17; 159: 2026-02-21; 162: 2025-12-08; 163: 2026-01-02; 165: 2026-01-31; 166: 2026-02-15; 169: 2026-01-31; 170: 2026-02-03; 176: 2026-02-04; 177: 2026-02-06
172 | PSS-14 | AGE26AL | 1: KH 605; 2: F09; 3: SHREERAM; 4: 2025-06-12; 5: Keller; 6: Yes; 7: 546672; 8: 2678249; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-09; 18: 2025-06-18; 20: 2025-05-05; 21: 2025-06-04; 32: 2025-11-03; 33: 2025-11-04; 35: 2025-09-04; 36: 2025-09-05; 39: 2025-11-05; 40: 2025-11-05; 42: 2025-09-26; 43: 2025-09-26; 46: 2025-11-06; 47: 2025-11-07; 49: 2025-09-27; 50: 2025-09-27; 53: 2025-11-08; 54: 2025-11-09; 56: 2025-09-28; 57: 2025-09-28; 60: 2025-11-10; 61: 2025-11-20; 63: 2025-10-04; 64: 2025-10-12; 67: 2025-11-21; 68: 2025-11-22; 70: 2025-10-13; 71: 2025-10-13; 75: 2025-11-27; 76: 2025-11-30; 78: 2025-11-08; 82: 2025-11-29; 83: 2025-11-29; 85: 2025-11-09; 86: 2025-11-10; 91: 2025-11-06; 92: 2025-11-16; 94: 2025-09-25; 95: 2026-02-26; 98: 2025-11-24; 99: 2025-12-01; 101: 2025-03-10; 102: 2025-04-18; 105: 2025-11-24; 106: 2025-12-01; 108: 2026-02-09; 109: 2026-02-11; 112: Bipin; 113: 2025-11-26; 114: 2025-12-03; 116: 2026-02-07; 117: 2026-02-27; 120: 2026-01-29; 121: 2026-02-08; 127: 2026-01-21; 128: 2026-01-29; 130: 0; 134: 2026-02-09; 135: 2026-02-16; 141: 2026-02-17; 142: 2026-02-19; 148: 2026-01-31; 149: 2026-02-01; 155: 2025-01-22; 156: 2025-02-14; 158: 2026-02-18; 162: 2025-12-30; 163: 2026-01-24; 165: 2026-01-31; 166: 2026-02-15; 169: 2026-02-01; 170: 2026-02-04; 176: 2026-02-20; 177: 2026-02-22
173 | PSS-14 | AGE26AL | 1: KH 606; 2: F02; 3: BHAVANI; 4: 2025-08-06; 5: Bauer; 6: Yes; 7: 547310; 8: 2678897; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-19; 18: 2025-06-29; 20: 2025-05-02; 21: 2025-05-27; 32: 2025-11-04; 33: 2025-11-05; 35: 2025-08-20; 36: 2025-08-30; 39: 2025-11-06; 40: 2025-11-06; 42: 2025-08-31; 43: 2025-09-02; 46: 2025-11-07; 47: 2025-11-08; 49: 2025-09-03; 50: 2025-09-03; 53: 2025-11-09; 54: 2025-11-10; 56: 2025-09-17; 57: 2025-09-17; 60: 2025-11-11; 61: 2025-11-21; 63: 2025-09-25; 64: 2025-10-06; 67: 2025-11-22; 68: 2025-11-23; 70: 2025-10-07; 71: 2025-10-08; 75: 2025-11-28; 76: 2025-12-01; 78: 2025-11-16; 82: 2025-11-30; 83: 2025-11-30; 85: 2025-11-16; 86: 2025-11-16; 91: 2025-11-07; 92: 2025-11-17; 94: 2025-09-03; 95: 2026-02-24; 98: 2025-11-25; 99: 2025-12-02; 101: 2025-03-25; 102: 2025-05-19; 105: 2025-11-25; 106: 2025-12-02; 108: 2026-02-12; 109: 2026-02-14; 112: SS Jadeja; 113: 2025-11-27; 114: 2025-12-04; 116: 2026-01-02; 117: 2026-01-13; 120: 2025-12-31; 121: 2026-01-09; 123: 2026-02-27; 127: 2025-12-27; 128: 2026-01-04; 130: 0; 134: 2026-01-10; 135: 2026-01-17; 141: 2026-01-18; 142: 2026-01-20; 148: 2026-01-05; 149: 2026-01-06; 155: 2025-12-23; 156: 2025-01-13; 158: 2026-02-24; 162: 2025-12-08; 163: 2026-01-02; 165: 2026-01-31; 166: 2026-02-15; 169: 2026-01-07; 170: 2026-01-10; 176: 2026-01-21; 177: 2026-01-23
174 | PSS-14 | AGE26AL | 1: KH 607; 2: F03; 3: HBG; 4: 2026-02-11; 5: Bauer; 6: Yes; 7: 547948; 8: 2679545; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-09; 18: 2025-06-18; 20: 2025-05-28; 21: 2025-06-09; 24: YES; 25: Bauer; 29: 2026-01-25; 30: 2026-02-06; 32: 2025-11-07; 33: 2025-11-08; 35: 2026-02-15; 36: 2026-02-17; 39: 2025-11-09; 40: 2025-11-09; 46: 2025-11-10; 47: 2025-11-11; 53: 2025-11-12; 54: 2025-11-13; 60: 2025-11-14; 61: 2025-11-24; 67: 2025-11-25; 68: 2025-11-26; 75: 2025-12-01; 76: 2025-12-04; 82: 2025-12-03; 83: 2025-12-03; 91: 2025-11-10; 92: 2025-11-20; 94: 0; 98: 2025-11-28; 99: 2025-12-05; 101: Done; 102: Done; 105: 2025-11-28; 106: 2025-12-05; 108: 2026-02-19; 109: 2026-02-23; 112: Harsh(Reuse); 113: 2025-11-30; 114: 2025-12-07; 116: 2026-02-16; 117: 2026-02-23; 120: 2026-01-10; 121: 2026-01-19; 127: 2026-01-23; 128: 2026-01-31; 130: 0; 134: 2026-01-20; 135: 2026-01-27; 141: 2026-01-28; 142: 2026-01-30; 148: 2026-02-01; 149: 2026-02-02; 155: 2025-12-23; 156: 2025-01-13; 162: 2025-12-08; 163: 2026-01-02; 169: 2026-02-03; 170: 2026-02-06; 176: 2026-02-07; 177: 2026-02-09
175 | PSS-14 | AGE26AL | 1: KH 608; 2: F03; 3: BHAVANI; 4: 2025-08-06; 5: Bauer; 6: Yes; 7: 548586; 8: 2680193; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-30; 18: 2025-06-08; 20: 2025-06-11; 21: 2025-06-21; 32: 2025-11-10; 33: 2025-11-11; 35: 2026-01-06; 36: 2026-01-07; 39: 2025-11-12; 40: 2025-11-12; 42: 2026-01-09; 43: 2026-01-11; 46: 2025-11-13; 47: 2025-11-14; 49: 2026-01-11; 50: 2026-01-15; 52: Hold due to road damage; 53: 2025-11-15; 54: 2025-11-16; 56: 2026-01-20; 57: 2026-01-22; 60: 2025-11-17; 61: 2025-11-27; 63: 2026-01-23; 64: 2026-01-28; 67: 2025-11-28; 68: 2025-11-29; 70: 2026-01-29; 71: 2026-01-30; 75: 2025-12-04; 76: 2025-12-07; 78: 2026-02-05; 82: 2025-12-06; 83: 2025-12-06; 85: 2026-02-19; 86: 2026-02-19; 91: 2025-11-13; 92: 2025-11-23; 94: 2026-01-14; 98: 2025-12-01; 99: 2025-12-08; 101: 2025-03-27; 102: 2025-05-18; 105: 2025-12-01; 106: 2025-12-08; 112: Harsh; 113: 2025-12-03; 114: 2025-12-10; 120: 2026-01-11; 121: 2026-01-20; 127: 2026-01-20; 128: 2026-01-28; 130: 0; 134: 2026-01-21; 135: 2026-01-28; 141: 2026-01-29; 142: 2026-01-31; 148: 2026-01-29; 149: 2026-01-30; 155: 2025-12-23; 156: 2025-01-13; 162: 2025-12-08; 163: 2026-01-02; 169: 2026-01-31; 170: 2026-02-03; 176: 2026-02-04; 177: 2026-02-06
176 | PSS-14 | AGE26AL | 1: KH 509; 2: F05; 3: SHREEJI; 4: 2025-10-13; 5: Keller; 6: Yes; 7: 549224; 8: 2680841; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-20; 18: 2025-05-29; 20: 2025-06-19; 21: 2025-06-27; 32: 2025-11-11; 33: 2025-11-12; 35: 2026-01-28; 38: Delay due to water logging; 39: 2025-11-13; 40: 2025-11-13; 46: 2025-11-14; 47: 2025-11-15; 53: 2025-11-16; 54: 2025-11-17; 60: 2025-11-18; 61: 2025-11-28; 67: 2025-11-29; 68: 2025-11-30; 75: 2025-12-05; 76: 2025-12-08; 82: 2025-12-07; 83: 2025-12-07; 91: 2025-11-14; 92: 2025-11-24; 94: 0; 98: 2025-12-02; 99: 2025-12-09; 101: Done; 102: Done; 105: 2025-12-02; 106: 2025-12-09; 112: GP Project(Reuse); 113: 2025-12-04; 114: 2025-12-11; 120: 2026-01-11; 121: 2026-01-20; 127: 2026-01-21; 128: 2026-01-29; 130: 0; 134: 2026-01-21; 135: 2026-01-28; 141: 2026-01-29; 142: 2026-01-31; 148: 2026-01-30; 149: 2026-01-31; 155: 2025-12-23; 156: 2025-01-13; 162: 2025-12-08; 163: 2026-01-02; 169: 2026-02-01; 170: 2026-02-04; 176: 2026-02-05; 177: 2026-02-07
177 | PSS-14 | AGE26AL | 1: KH 554; 2: F06; 3: MSC; 4: 2026-02-18; 5: Keller; 6: Yes; 7: 549861; 8: 2681489; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-21; 18: 2025-05-30; 20: 2025-06-09; 21: 2025-06-18; 24: Yes; 25: Keller; 29: 2026-02-04; 30: 2026-02-15; 32: 2025-05-31; 33: 2025-06-01; 35: 2026-02-25; 36: 2026-02-26; 39: 2025-06-02; 40: 2025-06-02; 42: 2026-02-26; 43: 2026-02-27; 46: 2025-06-03; 47: 2025-06-04; 53: 2025-06-05; 54: 2025-06-06; 60: 2025-06-07; 61: 2025-06-17; 67: 2025-06-18; 68: 2025-06-19; 75: 2025-06-24; 76: 2025-06-27; 82: 2025-06-26; 83: 2025-06-26; 91: 2025-06-03; 92: 2025-06-13; 94: 0; 98: 2025-06-21; 99: 2025-06-28; 101: Done; 102: Done; 105: 2025-06-21; 106: 2025-06-28; 112: Odhav(Reuse); 113: 2025-06-23; 114: 2025-06-30; 120: 2026-01-31; 121: 2026-02-09; 127: 2025-12-17; 128: 2025-12-25; 130: 0; 134: 2026-02-10; 135: 2026-02-17; 141: 2026-02-18; 142: 2026-02-20; 148: 2026-02-23; 149: 2026-02-24; 155: 2025-01-22; 156: 2025-02-14; 162: 2026-01-22; 163: 2026-02-16; 169: 2026-02-25; 170: 2026-02-28; 176: 2026-03-01; 177: 2026-03-03
178 | PSS-14 | AGE26AL | 1: KH 611; 2: F10; 3: BHAVANI; 4: 2026-02-11; 5: Bauer; 6: Yes; 7: 546877; 8: 2677379; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-19; 18: 2025-06-29; 20: 2025-04-23; 21: 2025-05-02; 24: YES; 25: Pinnacles; 29: 2026-01-28; 30: 2026-02-09; 32: 2025-11-10; 33: 2025-11-11; 35: 2026-02-18; 36: 2026-02-18; 39: 2025-11-12; 40: 2025-11-12; 42: 2026-02-19; 43: 2026-02-19; 46: 2025-11-13; 47: 2025-11-14; 49: 2026-02-20; 50: 2026-02-20; 53: 2025-11-15; 54: 2025-11-16; 60: 2025-11-17; 61: 2025-11-27; 67: 2025-11-28; 68: 2025-11-29; 75: 2025-12-04; 76: 2025-12-07; 82: 2025-12-06; 83: 2025-12-06; 91: 2025-11-13; 92: 2025-11-23; 94: 2026-02-18; 98: 2025-12-01; 99: 2025-12-08; 101: Done; 102: Done; 105: 2025-12-01; 106: 2025-12-08; 112: Varudi; 113: 2025-12-03; 114: 2025-12-10; 120: 2026-02-19; 121: 2026-02-28; 127: 2026-01-19; 128: 2026-01-27; 130: 0; 134: 2026-03-01; 135: 2026-03-08; 141: 2026-03-09; 142: 2026-03-11; 148: 2026-02-28; 149: 2026-03-01; 155: 2025-01-22; 156: 2025-02-14; 162: 2026-01-22; 163: 2026-02-16; 165: 2026-01-31; 166: 2026-02-15; 169: 2026-01-30; 170: 2026-02-02; 176: 2026-03-12; 177: 2026-03-14
179 | PSS-14 | AGE26AL | 1: KH 612; 2: F10; 3: SHREERAM; 4: 2025-05-30; 5: Bauer; 6: Yes; 7: 547490; 8: 2677964; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-21; 18: 2025-06-01; 20: 2025-05-04; 21: 2025-05-24; 32: 2025-11-08; 33: 2025-11-09; 35: 2025-06-23; 36: 2025-07-14; 38: Delay due to Soil wet condition; 39: 2025-11-10; 40: 2025-11-10; 42: 2025-07-15; 43: 2025-07-15; 46: 2025-11-11; 47: 2025-11-12; 49: 2025-07-18; 50: 2025-07-18; 53: 2025-11-13; 54: 2025-11-14; 56: 2025-08-05; 57: 2025-08-05; 60: 2025-11-15; 61: 2025-11-25; 63: 2025-08-10; 64: 2025-08-27; 67: 2025-11-26; 68: 2025-11-27; 70: 2025-08-29; 71: 2025-08-29; 75: 2025-12-02; 76: 2025-12-05; 78: 2025-11-07; 82: 2025-12-04; 83: 2025-12-04; 85: 2025-11-08; 86: 2025-11-09; 91: 2025-11-11; 92: 2025-11-21; 94: 2025-07-17; 98: 2025-11-29; 99: 2025-12-06; 101: 2025-03-17; 102: 2025-04-18; 105: 2025-11-29; 106: 2025-12-06; 108: 2026-02-08; 109: 2026-02-11; 112: Bipin; 113: 2025-12-01; 114: 2025-12-08; 116: 2025-11-01; 117: 2026-02-07; 120: 2026-01-18; 121: 2026-01-28; 127: 2025-12-13; 128: 2025-12-21; 130: 0; 134: 2026-01-29; 135: 2026-02-05; 141: 2026-02-06; 142: 2026-02-08; 148: 2026-01-27; 149: 2026-01-28; 155: 2025-12-23; 156: 2025-01-13; 162: 2025-12-30; 163: 2026-01-24; 165: 2026-01-31; 166: 2026-02-15; 169: 2025-12-24; 170: 2025-12-27; 176: 2026-02-09; 177: 2026-02-11
180 | PSS-14 | AGE26AL | 1: KH 613; 2: F02; 3: SHREEJI; 4: 2025-08-06; 5: Bauer; 6: Yes; 7: 548128; 8: 2678612; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-19; 18: 2025-06-29; 20: 2025-05-26; 21: 2025-06-04; 32: 2025-11-09; 33: 2025-11-10; 35: 2025-08-07; 36: 2025-08-09; 39: 2025-11-11; 40: 2025-11-11; 42: 2025-08-09; 43: 2025-08-10; 46: 2025-11-12; 47: 2025-11-13; 49: 2025-06-11; 50: 2025-06-11; 53: 2025-11-14; 54: 2025-11-15; 56: 2025-08-13; 57: 2025-08-13; 60: 2025-11-16; 61: 2025-11-26; 63: 2025-08-14; 64: 2025-08-30; 67: 2025-11-27; 68: 2025-11-28; 70: 2025-09-01; 71: 2025-09-02; 75: 2025-12-03; 76: 2025-12-06; 78: 2026-01-16; 82: 2025-12-05; 83: 2025-12-05; 85: 2026-01-17; 86: 2026-01-17; 91: 2025-11-12; 92: 2025-11-22; 94: 2025-12-10; 95: 2026-02-25; 98: 2025-11-30; 99: 2025-12-07; 101: 2025-03-25; 102: 2025-05-04; 105: 2025-11-30; 106: 2025-12-07; 108: 2026-02-21; 112: SS Jadeja; 113: 2025-12-02; 114: 2025-12-09; 116: 2026-01-01; 117: 2026-01-09; 120: 2026-02-09; 121: 2026-02-18; 127: 2026-01-16; 128: 2026-01-24; 130: 0; 134: 2026-02-19; 135: 2026-02-26; 141: 2026-02-27; 142: 2026-03-01; 148: 2026-02-24; 149: 2026-02-25; 155: 2025-01-22; 156: 2025-02-14; 158: 2026-02-25; 162: 2026-01-22; 163: 2026-02-16; 165: 2026-01-31; 166: 2026-02-15; 169: 2026-01-27; 170: 2026-01-30; 176: 2026-03-02; 177: 2026-03-04
181 | PSS-14 | AGE26AL | 1: KH 614; 2: F03; 3: SHREERAM; 4: 2026-02-16; 5: Bauer; 6: Yes; 7: 548765; 8: 2679260; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-09; 18: 2025-06-18; 20: 2025-06-02; 21: 2025-06-13; 24: Yes; 25: Bauer; 29: 2026-02-01; 30: 2026-02-10; 32: 2025-11-11; 33: 2025-11-12; 35: 2026-02-16; 36: 2026-02-18; 39: 2025-11-13; 40: 2025-11-13; 42: 2026-02-20; 43: 2026-02-23; 46: 2025-11-14; 47: 2025-11-15; 49: 2026-02-24; 50: 2026-02-24; 53: 2025-11-16; 54: 2025-11-17; 56: 2026-02-27; 60: 2025-11-18; 61: 2025-11-28; 67: 2025-11-29; 68: 2025-11-30; 75: 2025-12-05; 76: 2025-12-08; 82: 2025-12-07; 83: 2025-12-07; 91: 2025-11-14; 92: 2025-11-24; 94: 2026-02-22; 98: 2025-12-02; 99: 2025-12-09; 101: Done; 102: Done; 105: 2025-12-02; 106: 2025-12-09; 112: Harsh(Reuse); 113: 2025-12-04; 114: 2025-12-11; 120: 2026-01-21; 121: 2026-01-30; 127: 2025-12-18; 128: 2025-12-26; 130: 0; 134: 2026-01-31; 135: 2026-02-07; 141: 2026-02-08; 142: 2026-02-10; 148: 2026-02-01; 149: 2026-02-02; 155: 2025-12-23; 156: 2025-01-13; 162: 2025-12-30; 163: 2026-01-24; 169: 2025-12-29; 170: 2026-01-01; 176: 2026-02-11; 177: 2026-02-13
182 | PSS-14 | AGE26AL | 1: KH 615; 2: F03; 3: SHREEJI; 4: 2025-08-06; 5: Bauer; 6: Yes; 7: 549403; 8: 2679908; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-30; 18: 2025-06-08; 20: 2025-06-11; 21: 2025-06-28; 32: 2025-06-10; 33: 2025-06-11; 35: 2025-08-12; 36: 2025-08-15; 39: 2025-06-12; 40: 2025-06-12; 42: 2025-08-16; 43: 2025-08-18; 46: 2025-06-13; 47: 2025-06-14; 49: 2025-08-18; 50: 2025-08-18; 53: 2025-06-15; 54: 2025-06-16; 56: 2025-08-23; 57: 2025-08-23; 60: 2025-06-17; 61: 2025-06-27; 63: 2025-08-27; 64: 2025-09-01; 67: 2025-06-28; 68: 2025-06-29; 70: 2025-09-05; 71: 2025-11-23; 75: 2025-07-04; 76: 2025-07-07; 78: 2026-02-10; 82: 2025-07-06; 83: 2025-07-06; 85: 2026-02-11; 86: 2026-02-11; 91: 2025-06-13; 92: 2025-06-23; 94: 2025-09-04; 98: 2025-07-01; 99: 2025-07-08; 101: 2025-03-27; 102: 2025-05-27; 105: 2025-07-01; 106: 2025-07-08; 112: Harsh; 113: 2025-07-03; 114: 2025-07-10; 120: 2026-01-31; 121: 2026-02-09; 127: 2025-12-18; 128: 2025-12-26; 130: 0; 134: 2026-02-10; 135: 2026-02-17; 141: 2026-02-18; 142: 2026-02-20; 148: 2026-02-24; 149: 2026-02-25; 155: 2025-01-22; 156: 2025-02-14; 162: 2026-01-22; 163: 2026-02-16; 169: 2026-02-26; 170: 2026-03-01; 176: 2026-03-02; 177: 2026-03-04
183 | PSS-14 | AGE26AL | 1: KH 47; 2: F12; 3: ODHAV; 4: 2026-02-08; 5: Pinnacle/Bauer; 6: Yes; 7: 550041; 8: 2680556; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-31; 18: 2025-06-09; 20: 2025-12-24; 21: 2026-02-06; 32: 2025-06-11; 33: 2025-06-12; 35: 2026-02-12; 36: 2026-02-17; 39: 2025-06-13; 40: 2025-06-13; 46: 2025-06-14; 47: 2025-06-15; 53: 2025-06-16; 54: 2025-06-17; 60: 2025-06-18; 61: 2025-06-28; 67: 2025-06-29; 68: 2025-06-30; 75: 2025-07-05; 76: 2025-07-08; 82: 2025-07-07; 83: 2025-07-07; 91: 2025-06-14; 92: 2025-06-24; 94: 0; 98: 2025-07-02; 99: 2025-07-09; 101: Done; 102: Done; 105: 2025-07-02; 106: 2025-07-09; 112: GP Project(Reuse); 113: 2025-07-04; 114: 2025-07-11; 120: 2026-01-21; 121: 2026-01-30; 127: 2026-01-12; 128: 2026-01-20; 130: 0; 134: 2026-01-31; 135: 2026-02-07; 141: 2026-02-08; 142: 2026-02-10; 148: 2026-01-22; 149: 2026-01-23; 155: 2025-12-23; 156: 2025-01-13; 158: 2026-02-18; 162: 2025-12-30; 163: 2026-01-24; 169: 2026-01-23; 170: 2026-01-26; 176: 2026-02-11; 177: 2026-02-13
184 | PSS-14 | AGE26AL | 1: KH 617; 2: F10; 3: SHREEJI; 4: 2025-08-08; 5: Bauer; 6: Yes; 7: 548307; 8: 2677679; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-02; 18: 2025-06-12; 20: 2025-05-03; 21: 2025-06-01; 32: 2025-11-09; 33: 2025-11-10; 35: 2026-02-02; 36: 2026-02-03; 38: Road rectification requeid; 39: 2025-11-11; 40: 2025-11-11; 42: 2026-02-04; 43: 2026-02-17; 45: Road rectification requeid; 46: 2025-11-12; 47: 2025-11-13; 49: 2026-02-18; 50: 2026-02-18; 53: 2025-11-14; 54: 2025-11-15; 56: 2026-02-19; 57: 2026-02-19; 60: 2025-11-16; 61: 2025-11-26; 63: 2026-02-20; 64: 2026-02-26; 67: 2025-11-27; 68: 2025-11-28; 70: 2026-02-27; 71: 2026-02-28; 75: 2025-12-03; 76: 2025-12-06; 82: 2025-12-05; 83: 2025-12-05; 91: 2025-11-12; 92: 2025-11-22; 94: 2026-02-16; 98: 2025-11-30; 99: 2025-12-07; 101: 2025-03-20; 102: 2025-04-18; 105: 2025-11-30; 106: 2025-12-07; 112: Bipin; 113: 2025-12-02; 114: 2025-12-09; 120: 2026-01-10; 121: 2026-01-19; 127: 2025-12-28; 128: 2026-01-05; 130: 0; 134: 2026-01-20; 135: 2026-01-27; 141: 2026-01-28; 142: 2026-01-30; 148: 2026-01-11; 149: 2026-01-12; 155: 2025-12-23; 156: 2025-01-13; 162: 2025-12-08; 163: 2026-01-02; 165: 2026-01-31; 166: 2026-02-15; 169: 2026-01-08; 170: 2026-01-11; 176: 2026-01-31; 177: 2026-02-02
185 | PSS-14 | AGE26AL | 1: KH 618; 2: F03; 3: SHREEJI; 4: 2025-08-08; 5: Bauer; 6: Yes; 7: 548945; 8: 2678327; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-19; 18: 2025-06-28; 20: 2025-06-23; 21: 2025-07-06; 32: 2025-11-07; 33: 2025-11-08; 35: 2025-09-03; 38: Delay due to water logging; 39: 2025-11-09; 40: 2025-11-09; 46: 2025-11-10; 47: 2025-11-11; 53: 2025-11-12; 54: 2025-11-13; 60: 2025-11-14; 61: 2025-11-24; 67: 2025-11-25; 68: 2025-11-26; 75: 2025-12-01; 76: 2025-12-04; 82: 2025-12-03; 83: 2025-12-03; 91: 2025-11-10; 92: 2025-11-20; 94: 0; 98: 2025-11-28; 99: 2025-12-05; 101: 2025-03-27; 102: 2025-05-06; 105: 2025-11-28; 106: 2025-12-05; 112: Vaibhav; 113: 2025-11-30; 114: 2025-12-07; 120: 2026-01-30; 121: 2026-02-08; 127: 2025-12-19; 128: 2025-12-27; 130: 0; 134: 2026-02-09; 135: 2026-02-16; 141: 2026-02-17; 142: 2026-02-19; 148: 2026-02-05; 149: 2026-02-06; 155: 2025-01-22; 156: 2025-02-14; 162: 2025-12-30; 163: 2026-01-24; 169: 2025-12-30; 170: 2026-01-02; 176: 2026-02-20; 177: 2026-02-22
186 | PSS-14 | AGE26AL | 1: KH 619; 2: F04; 3: SHREEJI; 4: 2025-08-08; 5: Bauer; 6: Yes; 7: 549583; 8: 2678975; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-09; 18: 2025-06-18; 20: 2025-06-05; 21: 2025-06-15; 32: 2025-11-08; 33: 2025-11-09; 35: 2025-08-24; 36: 2025-08-26; 39: 2025-11-10; 40: 2025-11-10; 42: 2025-08-27; 43: 2025-08-28; 46: 2025-11-11; 47: 2025-11-12; 49: 2025-08-29; 50: 2025-08-29; 53: 2025-11-13; 54: 2025-11-14; 56: 2025-11-07; 57: 2025-11-08; 60: 2025-11-15; 61: 2025-11-25; 63: 2025-11-09; 64: 2025-11-15; 67: 2025-11-26; 68: 2025-11-27; 70: 2025-11-16; 71: 2025-11-16; 75: 2025-12-02; 76: 2025-12-05; 78: 2026-01-04; 82: 2025-12-04; 83: 2025-12-04; 85: 2026-01-05; 86: 2026-01-05; 91: 2025-11-11; 92: 2025-11-21; 94: 2025-12-26; 95: 2026-02-14; 98: 2025-11-29; 99: 2025-12-06; 101: Done; 102: Done; 105: 2025-11-29; 106: 2025-12-06; 112: Vaibhav(Reuse); 113: 2025-12-01; 114: 2025-12-08; 120: 2026-02-19; 121: 2026-02-28; 127: 2025-12-27; 128: 2026-01-04; 130: 0; 134: 2026-03-01; 135: 2026-03-08; 141: 2026-03-09; 142: 2026-03-11; 148: 2026-03-01; 149: 2026-03-02; 155: 2025-01-22; 156: 2025-02-14; 162: 2026-01-22; 163: 2026-02-16; 169: 2026-01-07; 170: 2026-01-10; 176: 2026-03-12; 177: 2026-03-14
187 | PSS-14 | AGE26AL | 1: KH 620; 2: F04; 3: SHREEJI; 4: 2025-10-13; 5: Bauer; 6: Yes; 7: 550221; 8: 2679623; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-10; 18: 2025-06-19; 20: 2025-06-16; 21: 2025-07-02; 32: 2025-11-08; 33: 2025-11-09; 35: 2026-02-11; 36: 2026-02-14; 39: 2025-11-10; 40: 2025-11-10; 42: 2026-02-24; 46: 2025-11-11; 47: 2025-11-12; 53: 2025-11-13; 54: 2025-11-14; 60: 2025-11-15; 61: 2025-11-25; 67: 2025-11-26; 68: 2025-11-27; 75: 2025-12-02; 76: 2025-12-05; 82: 2025-12-04; 83: 2025-12-04; 91: 2025-10-20; 92: 2025-10-30; 94: 0; 98: 2025-11-29; 99: 2025-12-06; 101: Done; 102: Done; 105: 2025-11-29; 106: 2025-12-06; 112: Varudi(Reuse); 113: 2025-12-01; 114: 2025-12-08; 120: 2026-02-10; 121: 2026-02-19; 127: 2026-01-15; 128: 2026-01-23; 130: 0; 134: 2026-02-20; 135: 2026-02-27; 141: 2026-02-28; 142: 2026-03-02; 148: 2026-02-26; 149: 2026-02-27; 155: 2025-01-22; 156: 2025-02-14; 162: 2026-01-22; 163: 2026-02-16; 169: 2026-01-26; 170: 2026-01-29; 176: 2026-03-03; 177: 2026-03-05
188 | PSS-14 | AGE26AL | 1: KH 621; 2: F11; 3: SHREEJI; 4: 2025-10-13; 5: Bauer; 6: Yes; 7: 549125; 8: 2677394; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-13; 18: 2025-06-23; 20: 2025-06-20; 21: 2025-06-28; 32: 2025-10-24; 33: 2025-10-25; 35: 2025-12-03; 36: 2025-12-05; 39: 2025-10-26; 40: 2025-10-26; 42: 2025-12-21; 43: 2025-12-21; 46: 2025-10-27; 47: 2025-10-28; 49: 2025-12-28; 50: 2025-12-28; 53: 2025-10-29; 54: 2025-10-30; 56: 2026-01-08; 57: 2026-01-08; 60: 2025-10-31; 61: 2025-11-10; 63: 2026-01-10; 64: 2026-01-21; 67: 2025-11-11; 68: 2025-11-12; 70: 2026-01-25; 71: 2026-01-26; 74: Delay due to concrete not availabel; 75: 2025-11-17; 76: 2025-11-20; 78: 2026-02-11; 82: 2025-11-19; 83: 2025-11-19; 85: 2026-02-12; 86: 2026-02-12; 91: 2025-10-20; 92: 2025-10-30; 94: 2025-12-06; 95: 2026-02-18; 98: 2025-11-14; 99: 2025-11-21; 101: 2025-03-22; 102: 2025-04-19; 105: 2025-11-14; 106: 2025-11-21; 108: 2026-02-20; 109: 2026-02-23; 112: SS Jadeja; 113: 2025-11-16; 114: 2025-11-23; 116: 2026-02-12; 117: 2026-02-23; 120: 2025-12-31; 121: 2026-01-09; 123: 2026-02-26; 127: 2026-01-16; 128: 2026-01-24; 130: 2026-02-27; 134: 2026-01-10; 135: 2026-01-17; 141: 2026-01-18; 142: 2026-01-20; 148: 2026-01-25; 149: 2026-01-26; 155: 2025-12-23; 156: 2025-01-13; 158: 2026-01-01; 159: 2026-01-17; 162: 2025-12-08; 163: 2026-01-02; 169: 2026-01-27; 170: 2026-01-30; 176: 2026-01-31; 177: 2026-02-02
189 | PSS-14 | AGE26AL | 1: KH 622; 2: F04; 5: 0; 6: Yes; 7: 550401; 8: 2678690; 12: Done; 13: Done; 15: 253; 16: 0; 17: 2025-06-16; 18: 2025-06-26; 24: YES; 32: 2025-10-26; 33: 2025-10-27; 39: 2025-10-28; 40: 2025-10-28; 46: 2025-10-29; 47: 2025-10-30; 53: 2025-10-31; 54: 2025-11-01; 60: 2025-11-02; 61: 2025-11-12; 67: 2025-11-13; 68: 2025-11-14; 75: 2025-11-19; 76: 2025-11-22; 82: 2025-11-21; 83: 2025-11-21; 91: 2025-11-18; 92: 2025-11-28; 94: 0; 98: 2025-11-16; 99: 2025-11-23; 101: Done; 102: Done; 105: 2025-11-16; 106: 2025-11-23; 112: SS Jadeja(Reuse); 113: 2025-11-18; 114: 2025-11-25; 120: 2026-02-20; 121: 2026-02-28; 127: 2025-12-28; 128: 2026-01-05; 130: 0; 134: 2026-03-01; 135: 2026-03-08; 141: 2026-03-09; 142: 2026-03-11; 148: 2026-02-26; 149: 2026-02-27; 155: 2025-01-22; 156: 2025-02-14; 162: 2026-01-22; 163: 2026-02-16; 169: 2026-01-08; 170: 2026-01-11; 176: 2026-03-12; 177: 2026-03-14
190 | PSS-14 | AGE26AL | 1: KH 34; 2: F04; 3: BHAVANI; 4: 2025-12-29; 5: Bauer; 6: Yes; 7: 549773; 8: 2678044; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-19; 18: 2025-06-28; 20: 2025-06-15; 21: 2025-11-04; 32: 2025-10-29; 33: 2025-10-30; 35: 2026-01-11; 36: 2026-01-12; 39: 2025-10-31; 40: 2025-10-31; 42: 2026-01-15; 43: 2026-01-15; 46: 2025-11-01; 47: 2025-11-02; 49: 2026-01-17; 50: 2026-01-17; 53: 2025-11-03; 54: 2025-11-04; 56: 2026-01-18; 57: 2026-01-19; 60: 2025-11-05; 61: 2025-11-15; 63: 2026-01-19; 64: 2026-01-21; 67: 2025-11-16; 68: 2025-11-17; 70: 2026-01-23; 71: 2026-01-24; 74: Delay due to concrete not availabel; 75: 2025-11-22; 76: 2025-11-25; 78: 2026-02-01; 82: 2025-11-24; 83: 2025-11-24; 85: 2026-02-02; 86: 2026-02-02; 91: 2025-11-18; 92: 2025-11-28; 94: 2026-01-16; 95: 2026-02-17; 98: 2025-11-19; 99: 2025-11-26; 101: Done; 102: Done; 105: 2025-11-19; 106: 2025-11-26; 112: SS Jadeja; 113: 2025-11-21; 114: 2025-11-28; 120: 2026-01-20; 121: 2026-01-29; 127: 2025-12-29; 128: 2026-01-06; 130: 0; 134: 2026-01-30; 135: 2026-02-06; 141: 2026-02-07; 142: 2026-02-09; 148: 2026-01-21; 149: 2026-01-22; 155: 2025-12-23; 156: 2025-01-13; 162: 2025-12-30; 163: 2026-01-24; 169: 2026-01-09; 170: 2026-01-12; 176: 2026-02-10; 177: 2026-02-12
191 | PSS-14 | AGE26AL | 1: KH 35; 2: F04; 3: ODHAV; 4: 2026-02-11; 5: Bauer; 6: Yes; 7: 550856; 8: 2677632; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-06-06; 18: 2025-06-15; 20: 2025-12-09; 21: 2025-12-21; 24: YES; 25: Bauer; 29: 2026-01-28; 30: 2026-02-07; 32: 2025-10-31; 33: 2025-11-01; 35: 2026-02-20; 36: 2026-02-22; 39: 2025-11-02; 40: 2025-11-02; 42: 2026-02-23; 46: 2025-11-03; 47: 2025-11-04; 53: 2025-11-05; 54: 2025-11-06; 60: 2025-11-07; 61: 2025-11-17; 67: 2025-11-18; 68: 2025-11-19; 75: 2025-11-24; 76: 2025-11-27; 82: 2025-11-26; 83: 2025-11-26; 91: 2025-11-20; 92: 2025-11-30; 94: 0; 98: 2025-11-21; 99: 2025-11-28; 101: Done; 102: Done; 105: 2025-11-21; 106: 2025-11-28; 112: Vaibhav(Reuse); 113: 2025-11-23; 114: 2025-11-30; 120: 2026-02-15; 121: 2026-02-25; 127: 2025-12-30; 128: 2026-01-07; 130: 0; 134: 2026-02-26; 135: 2026-03-05; 141: 2026-03-06; 142: 2026-03-08; 148: 2026-02-18; 149: 2026-02-19; 155: 2025-01-22; 156: 2025-02-14; 162: 2026-01-22; 163: 2026-02-16; 169: 2026-01-10; 170: 2026-01-13; 176: 2026-03-09; 177: 2026-03-11
192 | PSS-14 | AGE26AL | 1: KH 68; 2: F10; 3: ODHAV; 4: 2025-12-18; 5: Bauer; 6: Yes; 7: 548667; 8: 2675773; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-05-25; 18: 2025-06-04; 20: 2025-10-18; 21: 2025-11-07; 32: 2025-11-02; 33: 2025-11-03; 35: 2025-12-24; 36: 2026-01-30; 38: Hold due to TL Line & Road work; 39: 2025-11-04; 40: 2025-11-04; 42: 2026-02-10; 43: 2026-02-12; 46: 2025-11-05; 47: 2025-11-06; 49: 2026-02-18; 50: 2026-02-18; 53: 2025-11-07; 54: 2025-11-08; 56: 2026-02-24; 57: 2026-02-25; 60: 2025-11-09; 61: 2025-11-19; 63: 2026-02-25; 67: 2025-11-20; 68: 2025-11-21; 75: 2025-11-26; 76: 2025-11-29; 82: 2025-11-28; 83: 2025-11-28; 91: 2025-11-13; 92: 2025-11-23; 94: 2026-02-16; 98: 2025-11-23; 99: 2025-11-30; 101: Done; 102: Done; 105: 2025-11-23; 106: 2025-11-30; 112: Bipin; 113: 2025-11-25; 114: 2025-12-02; 120: 2025-12-23; 121: 2026-01-01; 127: 2025-12-24; 128: 2026-01-01; 130: 0; 134: 2026-01-02; 135: 2026-01-09; 141: 2026-01-10; 142: 2026-01-12; 148: 2026-01-02; 149: 2026-01-03; 155: 2025-11-20; 156: 2025-12-10; 162: 2025-11-26; 163: 2025-12-21; 165: 2026-01-31; 166: 2026-02-15; 169: 2026-01-04; 170: 2026-01-07; 176: 2026-01-13; 177: 2026-01-15
193 | PSS-09 | AGE25BL | 1: WTG 556; 2: F1; 3: MSC; 4: 2025-11-21; 5: Bauer; 6: Yes; 7: 541831; 8: 2656948; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-11-11; 18: 2025-11-20; 20: 2025-11-10; 21: 2025-11-21; 32: 2025-11-26; 33: 2025-11-28; 35: 2025-11-22; 36: 2025-11-23; 39: 2025-11-29; 40: 2025-11-30; 42: 2025-11-24; 43: 2025-11-27; 46: 2025-12-01; 47: 2025-12-02; 49: 2025-11-27; 50: 2025-11-27; 53: 2025-12-03; 54: 2025-12-04; 56: 2025-11-30; 57: 2025-12-01; 60: 2025-12-05; 61: 2025-12-15; 63: 2025-12-01; 64: 2025-12-05; 67: 2026-01-16; 68: 2026-01-17; 70: 2025-12-07; 71: 2025-12-08; 75: 2026-01-22; 76: 2026-01-25; 78: 2025-12-10; 82: 2026-01-26; 83: 2026-01-26; 85: 2025-12-11; 86: 2025-12-11; 91: 2025-11-29; 92: 2025-12-09; 94: 2025-11-26; 95: 2025-12-16; 98: 2025-12-22; 99: 2025-12-31; 101: Done; 102: Done; 105: 2026-01-27; 106: 2026-02-01; 108: 2025-12-26; 109: 2025-12-28; 112: GP Project(Reuse); 113: 2026-01-27; 114: 2026-02-03; 116: 2025-12-24; 117: 2025-12-28; 120: 2025-02-20; 121: 2025-03-02; 123: 2025-12-29; 124: 2026-01-07; 127: 2025-02-20; 128: 2025-02-28; 130: 2025-12-14; 131: 2025-12-24; 134: 2025-03-03; 135: 2025-03-09; 137: 2026-01-12; 138: 2026-01-17; 141: 2025-03-10; 142: 2025-03-12; 144: 2026-01-17; 145: 2026-01-19; 148: 2025-03-03; 149: 2025-03-04; 151: 2025-12-26; 152: 2025-12-26; 155: 2025-02-20; 156: 2025-03-07; 158: 2026-01-05; 159: 2026-01-08; 162: 2026-01-20; 163: 2026-02-14; 165: 2025-12-31; 166: 2026-01-20; 169: 2025-03-05; 170: 2025-03-08; 172: 2026-01-13; 173: 2026-01-20; 176: 2025-03-15; 177: 2025-03-17; 179: 2026-01-31; 180: 2026-02-07
194 | PSS-09 | AGE25BL | 1: WTG 557; 2: F1; 3: MSC; 4: 2025-11-13; 5: Bauer; 6: Yes; 7: 542627; 8: 2656602; 12: Done; 13: Done; 15: 253; 16: 253; 17: 2025-10-29; 18: 2025-11-07; 20: 2025-10-29; 21: 2025-11-09; 32: 2025-11-13; 33: 2025-11-15; 35: 2025-11-14; 36: 2025-11-14; 39: 2025-11-16; 40: 2025-11-17; 42: 2025-11-15; 43: 2025-11-15; 46: 2025-11-18; 47: 2025-11-19; 49: 2025-11-15; 50: 2025-11-15; 53: 2025-11-20; 54: 2025-11-21; 56: 2025-11-17; 57: 2025-11-17; 60: 2025-11-22; 61: 2025-12-02; 63: 2025-11-24; 64: 2025-11-29; 67: 2026-01-21; 68: 2026-01-22; 70: 2025-12-01; 71: 2025-12-02; 75: 2026-01-27; 76: 2026-01-30; 78: 2025-12-05; 82: 2026-02-03; 83: 2026-02-03; 85: 2025-12-06; 86: 2025-12-06; 91: 2025-11-16; 92: 2025-11-26; 94: 2025-11-14; 95: 2025-12-16; 98: 2025-12-20; 99: 2025-12-30; 101: 2025-12-08; 102: 2025-12-12; 105: 2026-02-01; 106: 2026-02-06; 108: 2025-12-11; 109: 2025-12-12; 112: GP Project(Reuse); 113: 2026-02-01; 114: 2026-02-08; 116: 2025-12-06; 117: 2025-12-12; 120: 2025-03-04; 121: 2025-03-14; 123: 2025-12-14; 124: 2025-12-24; 127: 2025-02-26; 128: 2025-03-06; 130: 2025-12-17; 131: 2025-12-22; 134: 2025-03-15; 135: 2025-03-21; 137: 2025-12-29; 138: 2026-01-02; 141: 2025-03-22; 142: 2025-03-24; 144: 2026-01-02; 145: 2026-01-04; 148: 2025-03-09; 149: 2025-03-10; 151: 2025-12-26; 152: 2025-12-26; 155: 2025-02-20; 156: 2025-03-07; 158: 2025-12-28; 159: 2026-01-05; 162: 2026-01-20; 163: 2026-02-14; 165: 2025-12-31; 166: 2026-01-20; 169: 2025-03-11; 170: 2025-03-14; 172: 2026-01-13; 173: 2026-01-20; 176: 2025-03-15; 177: 2025-03-17; 179: 2026-01-31; 180: 2026-02-07
0
Note on BN5: Darshik Dholakiya: 15-1-26
Note on FS83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 CFT Date-31-12-25 2 CFT Date-7-01-26
Note on D160: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CEIPL - upto PCC, BPS - from Anchor Cage

## Stone Column Progress
[9 empty] | P | A
GROUND IMPROVEMENT WORK -Installation of stone column ( Khavda Wind Project) | [283 empty] | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun |  | Mon
Sr No | SPV | Location no | Vendor | PSS | Drawing Status | RIG | Length | Number of column in scope | Commulative stone Column |  |  |  |  | 2024-04-26 |  | 2024-04-27 |  | 2024-04-28 |  | 2024-04-29 |  | 2024-04-30 |  | 2024-05-01 |  | 2024-05-02 |  | 2024-05-03 |  | 2024-05-04 |  | 2024-05-05 |  | 2024-05-06 |  | 2024-05-07 |  | 2024-05-08 |  | 2024-05-09 |  | 2025-01-01 |  | 2025-01-02 |  | 2025-01-03 |  | 2025-01-04 |  | 2025-01-05 |  | 2025-01-06 |  | 2025-01-07 |  | 2025-01-08 |  | 2025-01-09 |  | 2025-01-10 |  | 2025-01-11 |  | 2025-01-12 |  | 2025-01-13 |  | 2025-01-14 |  | 2025-01-15 |  | 2025-01-16 |  | 2025-01-17 |  | 2025-01-18 |  | 2025-01-19 |  | 2025-01-20 |  | 2025-01-21 |  | 2025-01-22 |  | 2025-01-23 |  | 2025-01-24 |  | 2025-01-25 |  | 2025-01-26 |  | 2025-01-27 |  | 2025-01-28 |  | 2025-01-29 |  | 2025-01-30 |  | 2025-01-31 |  | 2025-02-01 |  | 2025-02-02 |  | 2025-02-03 |  | 2025-02-04 |  | 2025-02-05 |  | 2025-02-06 |  | 2025-02-07 |  | 2025-02-08 |  | 2025-02-09 |  | 2025-02-10 |  | 2025-02-11 |  | 2025-02-12 |  | 2025-02-13 |  | 2025-02-14 |  | 2025-02-15 |  | 2025-02-16 |  | 2025-02-17 |  | 2025-02-18 |  | 2025-02-19 |  | 2025-02-20 |  | 2025-02-21 |  | 2025-02-22 |  | 2025-02-23 |  | 2025-02-24 |  | 2025-02-25 |  | 2025-02-26 |  | 2025-02-27 |  | 2025-02-28 |  | 2025-03-01 |  | 2025-03-02 |  | 2025-03-03 |  | 2025-03-04 |  | 2025-03-05 |  | 2025-03-06 |  | 2025-03-07 |  | 2025-03-08 |  | 2025-03-09 |  | 2025-03-10 |  | 2025-03-11 |  | 2025-03-12 |  | 2025-03-13 |  | 2025-03-14 |  | 2025-03-15 |  | 2025-03-16 |  | 2025-03-17 |  | 2025-03-18 |  | 2025-03-19 |  | 2025-03-20 |  | 2025-03-21 |  | 2025-03-22 |  | 2025-03-23 |  | 2025-03-24 |  | 2025-03-25 |  | 2025-03-26 |  | 2025-03-27 |  | 2025-03-28 |  | 2025-03-29 |  | 2025-03-30 |  | 2025-03-31 |  | 2025-04-01 |  | 2025-04-02 |  | 2025-04-03 |  | 2025-04-04 |  | 2025-04-05 |  | 2025-04-06 |  | 2025-04-07 |  | 2025-04-08 |  | 2025-04-09 |  | 2025-04-10 |  | 2025-04-11 |  | 2025-04-12 |  | 2025-04-13 |  | 2025-04-14 |  | 2025-04-15 |  | 2025-04-16 |  | 2025-04-17 |  | 2025-04-18 |  | 2025-04-19 |  | 2025-04-20 |  | 2025-04-21 |  | 2025-04-22 |  | 2025-04-23 |  | 2025-04-24 |  | 2025-04-25 |  | 2025-04-26 |  | 2025-04-27 |  | 2025-04-28 |  | 2025-04-29 |  | 2025-04-30 |  | 2025-05-01 |  | 2025-05-02 |  | 2025-05-03 |  | 2025-05-04 |  | 2025-05-05 |  | 2025-05-06 |  | 2025-05-07 |  | 2025-05-08 |  | 2025-05-09 |  | 2025-05-10 |  | 2025-05-11 |  | 2025-05-12 |  | 2025-05-13 |  | 2025-05-14 |  | 2025-05-15 |  | 2025-05-16 |  | 2025-05-17 |  | 2025-05-18 |  | 2025-05-19 |  | 2025-05-20 |  | 2025-05-21 |  | 2025-05-22 |  | 2025-05-23 |  | 2025-05-24 |  | 2025-05-25 |  | 2025-05-26 |  | 2025-05-27 |  | 2025-05-28 |  | 2025-05-29 |  | 2025-05-30 |  | 2025-05-31 |  | 2025-06-01 |  | 2025-06-02 |  | 2025-06-03 |  | 2025-06-04 |  | 2025-06-05 |  | 2025-06-06 |  | 2025-06-07 |  | 2025-06-08 |  | 2025-06-09 |  | 2025-06-10 |  | 2025-06-11 |  | 2025-06-12 |  | 2025-06-13 |  | 2025-06-14 |  | 2025-06-15 |  | 2025-06-16 |  | 2025-06-17 |  | 2025-06-18 |  | 2025-06-19 |  | 2025-06-20 |  | 2025-06-21 |  | 2025-06-22 |  | 2025-06-23 |  | 2025-06-24 |  | 2025-06-25 |  | 2025-06-26 |  | 2025-06-27 |  | 2025-06-28 |  | 2025-06-29 |  | 2025-06-30 |  | 2025-07-01 |  | 2025-07-02 |  | 2025-07-03 |  | 2025-07-04 |  | 2025-07-05 |  | 2025-07-06 |  | 2025-07-07 |  | 2025-07-08 |  | 2025-07-09 |  | 2025-07-10 |  | 2025-07-11 |  | 2025-07-12 |  | 2025-07-13 |  | 2025-07-14 |  | 2025-07-15 |  | 2025-07-16 |  | 2025-07-17 |  | 2025-07-18 |  | 2025-07-19 |  | 2025-07-20 |  | 2025-07-21 |  | 2025-07-22 |  | 2025-07-23 |  | 2025-07-24 |  | 2025-07-25 |  | 2025-07-26 |  | 2025-07-27 |  | 2025-07-28 |  | 2025-07-29 |  | 2025-07-30 |  | 2025-07-31 |  | 2025-08-01 |  | 2025-08-02 |  | 2025-08-03 |  | 2025-08-04 |  | 2025-08-05 |  | 2025-08-06 |  | 2025-08-07 |  | 2025-08-08 |  | 2025-08-09 |  | 2025-08-10 |  | 2025-08-11 |  | 2025-08-12 |  | 2025-08-13 |  | 2025-08-14 |  | 2025-08-15 |  | 2025-08-16 |  | 2025-08-17 |  | 2025-08-18 |  | 2025-08-19 |  | 2025-08-20 |  | 2025-08-21 |  | 2025-08-22 |  | 2025-08-23 |  | 2025-08-24 |  | 2025-08-25 |  | 2025-08-26 |  | 2025-08-27 |  | 2025-08-28 |  | 2025-08-29 |  | 2025-08-30 |  | 2025-08-31 |  | 2025-09-01 |  | 2025-09-02 |  | 2025-09-03 |  | 2025-09-04 |  | 2025-09-05 |  | 2025-09-06 |  | 2025-09-07 |  | 2025-09-08 |  | 2025-09-09 |  | 2025-09-10 |  | 2025-09-11 |  | 2025-09-12 |  | 2025-09-13 |  | 2025-09-14 |  | 2025-09-15 |  | 2025-09-16 |  | 2025-09-17 |  | 2025-09-18 |  | 2025-09-19 |  | 2025-09-20 |  | 2025-09-21 |  | 2025-09-22 |  | 2025-09-23 |  | 2025-09-24 |  | 2025-09-25 |  | 2025-09-26 |  | 2025-09-27 |  | 2025-09-28 |  | 2025-09-29 |  | 2025-09-30 |  | 2025-10-01 |  | 2025-10-02 |  | 2025-10-03 |  | 2025-10-04 |  | 2025-10-05 |  | 2025-10-06 |  | 2025-10-07 |  | 2025-10-08 |  | 2025-10-09 |  | 2025-10-10 |  | 2025-10-11 |  | 2025-10-12 |  | 2025-10-13 |  | 2025-10-14 |  | 2025-10-15 |  | 2025-10-16 |  | 2025-10-17 |  | 2025-10-18 |  | 2025-10-19 |  | 2025-10-20 |  | 2025-10-21 |  | 2025-10-22 |  | 2025-10-23 |  | 2025-10-24 |  | 2025-10-25 |  | 2025-10-26 |  | 2025-10-27 |  | 2025-10-28 |  | 2025-10-29 |  | 2025-10-30 |  | 2025-10-31 |  | 2025-11-01 |  | 2025-11-02 |  | 2025-11-03 |  | 2025-11-04 |  | 2025-11-05 |  | 2025-11-06 |  | 2025-11-07 |  | 2025-11-08 |  | 2025-11-09 |  | 2025-11-10 |  | 2025-11-11 |  | 2025-11-12 |  | 2025-11-13 |  | 2025-11-14 |  | 2025-11-15 |  | 2025-11-16 |  | 2025-11-17 |  | 2025-11-18 |  | 2025-11-19 |  | 2025-11-20 |  | 2025-11-21 |  | 2025-11-22 |  | 2025-11-23 |  | 2025-11-24 |  | 2025-11-25 |  | 2025-11-26 |  | 2025-11-27 |  | 2025-11-28 |  | 2025-11-29 |  | 2025-11-30 |  | 2025-12-01 |  | 2025-12-02 |  | 2025-12-03 |  | 2025-12-04 |  | 2025-12-05 |  | 2025-12-06 |  | 2025-12-07 |  | 2025-12-08 |  | 2025-12-09 |  | 2025-12-10 |  | 2025-12-11 |  | 2025-12-12 |  | 2025-12-13 |  | 2025-12-14 |  | 2025-12-15 |  | 2025-12-16 |  | 2025-12-17 |  | 2025-12-18 |  | 2025-12-19 |  | 2025-12-20 |  | 2025-12-21 |  | 2025-12-22 |  | 2025-12-23 |  | 2025-12-24 |  | 2025-12-25 |  | 2025-12-26 |  | 2025-12-27 |  | 2025-12-28 |  | 2025-12-29 |  | 2025-12-30 |  | 2025-12-31 |  | 2026-01-01 |  | 2026-01-02 |  | 2026-01-03 |  | 2026-01-04 |  | 2026-01-05 |  | 2026-01-06 |  | 2026-01-07 |  | 2026-01-08 |  | 2026-01-09 |  | 2026-01-10 |  | 2026-01-11 |  | 2026-01-12 |  | 2026-01-13 |  | 2026-01-14 |  | 2026-01-15 |  | 2026-01-16 |  | 2026-01-17 |  | 2026-01-18 |  | 2026-01-19 |  | 2026-01-20 |  | 2026-01-21 |  | 2026-01-22 |  | 2026-01-23 |  | 2026-01-24 |  | 2026-01-25 |  | 2026-01-26 |  | 2026-01-27 |  | 2026-01-28 |  | 2026-01-29 |  | 2026-01-30 |  | 2026-01-31 |  | 2026-02-01 |  | 2026-02-02 |  | 2026-02-03 |  | 2026-02-04 |  | 2026-02-05 |  | 2026-02-06 |  | 2026-02-07 |  | 2026-02-08 |  | 2026-02-09 |  | 2026-02-10 |  | 2026-02-11 |  | 2026-02-12 |  | 2026-02-13 |  | 2026-02-14 |  | 2026-02-15 |  | 2026-02-16 |  | 2026-02-17 |  | 2026-02-18 |  | 2026-02-19 |  | 2026-02-20 |  | 2026-02-21 |  | 2026-02-22 |  | 2026-02-23 |  | 2026-02-24 |  | 2026-02-25 |  | 2026-02-26 |  | 2026-02-27 |  | 2026-02-28 |  | 2026-03-01 |  | 2026-03-02 |  | 2026-03-03 |  | 2026-03-04 |  | 2026-03-05 |  | 2026-03-06 |  | 2026-03-07 |  | 2026-03-08 |  | 2026-03-09 |  | 2026-03-10 |  | 2026-03-11 |  | 2026-03-12 |  | 2026-03-13 |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-23
[8 empty] | 49577 | Plan | Achieved | Balance | Start Date | Finish Date | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A
[9 empty] | 49642 | 49190 | 452 |  |  | 0 | 9 | 0 | 6 | 0 | 10 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 18 | 0 | 20 | 0 | 39 | 0 | 0 | 0 | 40 | 0 | 9 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 50 | 0 | 50 | 0 | 78 | 0 | 4 | 0 | 61 | 0 | 62 | 0 | 58 | 0 | 61 | 0 | 53 | 0 | 43 | 0 | 0 | 0 | 42 | 0 | 65 | 0 | 74 | 0 | 81 | 0 | 78 | 0 | 110 | 0 | 0 | 0 | 82 | 0 | 22 | 0 | 58 | 0 | 54 | 0 | 154 | 36.1818 | 184 | 36.1818 | 69 | 36.1818 | 226 | 36.1818 | 230 | 59.1818 | 148 | 86.7273 | 187 | 104.8182 | 165 | 127.8182 | 213 | 150.8182 | 0 | 173.8182 | 167 | 173.8182 | 169 | 233.4364 | 176 | 284.0364 | 165 | 284.0364 | 163 | 309.3364 | 198 | 311.6364 | 70 | 312.202 | 248 | 315.2111 | 251 | 317.5111 | 192 | 319.8111 | 203 | 334.6111 | 197 | 289.4111 | 155 | 289.4111 | 0 | 289.4111 | 169 | 332.802 | 157 | 279.3909 | 165 | 279.3909 | 203 | 258.2909 | 186 | 254.0742 | 181 | 251.7742 | 48 | 262.2742 | 161 | 327.4409 | 153 | 350.4409 | 199 | 371.5242 | 196 | 346.2242 | 0 | 376.4333 | 157 | 422.4333 | 72 | 422.4333 | 178 | 422.4333 | 91 | 422.4333 | 105 | 412.95 | 144 | 435.05 | 165 | 460.35 | 143 | 488.6833 | 61 | 488.6833 | 106 | 492.9 | 228 | 495.2 | 219 | 497.5 | 215 | 497.5 | 220 | 497.5 | 279 | 460.6 | 208 | 390.2 | 1 | 314.3 | 247 | 316.6 | 268 | 322.6 | 234 | 343.3 | 261 | 405.0909 | 249 | 428.0909 | 0 | 428.0909 | 222 | 449.1742 | 219 | 449.1742 | 224 | 423.8742 | 246 | 423.8742 | 206 | 353.3742 | 251 | 341.9742 | 204 | 376.5742 | 235 | 406.4742 | 267 | 392.9833 | 289 | 395.2833 | 258 | 420.5833 | 311 | 420.5833 | 321 | 468.5 | 0 | 468.5 | 248 | 468.5 | 284 | 473.9 | 322 | 493.2222 | 313 | 488.3222 | 324 | 488.3222 | 333 | 490.6222 | 258 | 490.6222 | 404 | 492.9222 | 334 | 492.9222 | 450 | 497.5222 | 56 | 472.2222 | 353 | 367.7 | 271 | 367.7 | 110 | 324.3 | 331 | 252.9455 | 351 | 273.6455 | 281 | 271.3455 | 92 | 317.3455 | 9 | 393.2455 | 4 | 436.6455 | 0 | 438.9455 | 29 | 438.9455 | 39 | 438.9455 | 36 | 438.9455 | 75 | 438.9455 | 227 | 386.1 | 275 | 385.3 | 244 | 360 | 214 | 364.6 | 193 | 316.9833 | 208 | 291.6833 | 217 | 314.6833 | 230 | 314.6833 | 149 | 310.0833 | 17 | 333.0833 | 169 | 333.0833 | 157 | 338.4833 | 222 | 361.4833 | 214 | 363.7833 | 211 | 363.7833 | 315 | 363.7833 | 191 | 365.7 | 350 | 365.7 | 407 | 365.7 | 316 | 342.7 | 285 | 345 | 275 | 342.7 | 327 | 342.7 | 71 | 342.7 | 240 | 342.7 | 275 | 342.7 | 243 | 342.7 | 317 | 342.7 | 296 | 342.7 | 320 | 342.7 | 229 | 340.4 | 250 | 340.4 | 179 | 340.4 | 210 | 331.2 | 228 | 305.9 | 228 | 305.9 | 270 | 305.9 | 148 | 305.9 | 348 | 282.9 | 320 | 259.9 | 282 | 259.9 | 177 | 188.6 | 146 | 188.6 | 92 | 115 | 0 | 23 | 108 | 0 | 150 | 0 | 112 | 0 | 84 | 0 | 112 | 0 | 133 | 0 | 102 | 0 | 81 | 0 | 71 | 0 | 78 | 0 | 78 | 0 | 105 | 0 | 129 | 0 | 142 | 0 | 130 | 0 | 89 | 0 | 103 | 0 | 88 | 0 | 130 | 0 | 76 | 0 | 1 | 0 | 89 | 0 | 115 | 0 | 85 | 0 | 64 | 0 | 84 | 0 | 94 | 0 | 0 | 0 | 65 | 0 | 93 | 0 | 107 | 0 | 131 | 0 | 104 | 0 | 100 | 0 | 92 | 0 | 121 | 0 | 152 | 0 | 169 | 0 | 108 | 0 | 137 | 0 | 160 | 0 | 0 | 0 | 153 | 0 | 153 | 0 | 151 | 0 | 166 | 0 | 30 | 0 | 165 | 0 | 81 | 0 | 148 | 0 | 134 | 0 | 93 | 0 | 51 | 0 | 86 | 0 | 87 | 0 | 62 | 0 | 137 | 0 | 115 | 0 | 111 | 0 | 145 | 0 | 154 | 0 | 174 | 0 | 51 | 0 | 168 | 0 | 92 | 0 | 120 | 0 | 91 | 0 | 98 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 35 | 0 | 12 | 0 | 50 | 0 | 62 | 0 | 0 | 0 | 93 | 0 | 93 | 0 | 0 | 0 | 91 | 0 | 87 | 0 | 89 | 0 | 100 | 0 | 83 | 0 | 112 | 0 | 108 | 0 | 92 | 0 | 73 | 0 | 108 | 0 | 0 | 0 | 129 | 0 | 77 | 0 | 121 | 0 | 0 | 0 | 119 | 0 | 94 | 0 | 91 | 0 | 48 | 0 | 86 | 0 | 111 | 0 | 104 | 0 | 88 | 0 | 86 | 0 | 51 | 0 | 100 | 0 | 85 | 0 | 67 | 0 | 143 | 0 | 104 | 0 | 162 | 0 | 99 | 0 | 23 | 0 | 163 | 0 | 149 | 0 | 156 | 0 | 131 | 0 | 151 | 0 | 173 | 0 | 100 | 0 | 117 | 25.3 | 123 | 25.3 | 184 | 25.3 | 131 | 25.3 | 199 | 25.3 | 0 | 25.3 | 80 | 25.3 | 67 | 25.3 | 96 | 25.3 | 127 | 25.3 | 175 | 0 | 161 | 0 | 123 | 0 | 135 | 25.3 | 172 | 25.3 | 149 | 25.3 | 156 | 25.3 | 153 | 25.3 | 0 | 25.3 | 160 | 25.3 | 104 | 25.3 | 84 | 25.3 | 70 | 25.3 | 119 | 0 | 99 | 0 | 133 | 0 | 119 | 0 | 117 | 0 | 94 | 0 | 93 | 0 | 113 | 0 | 143 | 0 | 88 | 0 | 91 | 0 | 92 | 0 | 101 | 0 | 80 | 0 | 58 | 0 | 38 | 0 | 22 | 0 | 47 | 0 | 33 | 0 | 55 | 0 | 55 | 0 | 45 | 0 | 77 | 0 | 63 | 0 | 26 | 0 | 46 | 0 | 67 | 0 | 60 | 0 | 40 | 0 | 31 | 0 | 51 | 0 | 6 | 0 | 45 | 0 | 81 | 0 | 78 | 0 | 92 | 0 | 79 | 0 | 101 | 0 | 71 | 0 | 80 | 0 | 80 | 0 | 40 | 0 | 0 | 0 | 53 | 0 | 76 | 0 | 72 | 0 | 61 | 0 | 81 | 0 | 77 | 0 | 121 | 0 | 49 | 0 | 51 | 0 | 40 | 0 | 27 | 0 | 53 | 0 | 0 | 0 | 87 | 0 | 70 | 0 | 79 | 0 | 49 | 0 | 37 | 0 | 67 | 0 | 71 | 0 | 60 | 0 | 30 | 0 | 30 | 0 | 24 | 0 | 29 | 0 | 44 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 18 | 0 | 4 | 0 | 39 | 0 | 30 | 0 | 27 | 0 | 40 | 0 | 12 | 0 | 19 | 0 | 18 | 0 | 30 | 0 | 21 | 0 | 37 | 0 | 47 | 0 | 29 | 0 | 21 | 0 | 0 | 0 | 22 | 0 | 27 | 0 | 23 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | AHEJ5L | WTG 243 | Bauer | PSS-05 | Released | R6 | 13 | 253 | 253 | 253 | 0 | 2025-03-14 | 2025-03-23 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | 0 |  | 0 | 28 | 0 | 34 | 0 | 39 | 0 | 29 | 0 | 44 | 0 | 43 | 0 |  | 0 | 34 | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | AHEJ5L | WTG 133 | Bauer | PSS-05 | Released | R3 | 13 | 253 | 253 | 253 | 0 | 2025-03-10 | 2025-03-20 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | 0 |  | 23 | 30 | 23 | 44 | 23 | 39 | 23 | 41 | 23 |  | 23 | 38 | 23 |  | 23 | 44 | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | AGE25CL | WTG 405 | Keller | PSS-11 | Released | R3 | 10 | 253 | 253 | 253 | 0 | 2025-04-16 | 2025-04-25 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | 0 | 22 | 0 | 22 | 0 | 21 | 0 | 27 | 0 | 24 | 0 | 29 | 0 | 22 | 0 | 21 | 0 |  | 0 | 20 | 0 |  | 0 | 35 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4 | AHEJ5L | WTG 244 | Bauer | PSS-05 | Released | R8 | 10 | 253 | 253 | 253 | 0 | 2025-03-12 | 2025-03-21 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | 0 |  | 0 | 24 | 0 | 30 | 0 | 19 | 0 | 29 | 0 | 17 | 0 | 11 | 0 |  | 0 | 23 | 0 | 24 | 25.3 | 25 | 25.3 | 24 | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | ARE3L | WTG 327 | Keller | PSS-08 | Released | R1 | 11 | 199 | 199 | 199 | 0 | 2025-02-14 | 2025-02-24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | 0 | 28 | 0 | 34 | 0 | 40 | 0 |  | 0 | 31 | 0 | 14 | 0 | 38 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
6 | AGE25CL | WTG 329 | Menard | PSS-11 | Released | R1 / R1 | 12 | 253 | 253 | 253 | 0 | 2025-03-11 | 2025-03-22 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | 0 | 5 | 0 | 5 | 0 | 8 | 0 | 5 | 0 | 5 | 0 |  | 0 | 7 | 0 | 5 | 0 | 7 | 0 | 3 | 0 | 7 | 0 | 7 | 0 |  | 0 | 2 | 21.0833 |  | 21.0833 | 6 | 21.0833 | 6 | 21.0833 |  | 21.0833 | 1 | 21.0833 |  | 21.0833 | 3 | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 | 9 | 0 |  | 0 | 3 | 0 |  | 0 |  | 0 | 3 | 0 | 13 | 0 | 7 | 0 |  | 0 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | 0 | 18 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | 0 |  | 0 | 14 | 0 | 13 | 0 |  | 0 | 26 | 0 | 24 | 0 | 10 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
7 | AGE25CL | WTG 233A | Bauer | PSS-11 | Released | R4 | 12 | 253 | 253 | 253 | 0 | 2025-04-08 | 2025-04-19 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | 0 | 28 | 0 | 22 | 0 | 27 | 0 | 23 | 0 | 25 | 0 | 29 | 0 | 38 | 0 |  | 0 | 35 | 0 | 24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
8 | AGE25CL | WTG 353 | Menard | PSS-11 | Released | R1 | 13 | 253 | 253 | 253 | 0 | 2025-03-23 | 2025-04-01 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | 0 | 27 | 0 | 33 | 0 | 28 | 0 |  | 0 |  | 0 | 16 | 0 | 15 | 0 |  | 0 |  | 0 |  | 0 | 13 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | 0 | 22 | 0 | 24 | 0 | 11 | 0 | 18 | 0 | 24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
9 | AGE25CL | WTG 354 | Bauer | PSS-11 | Released | R1 | 10 | 199 | 199 | 199 | 0 | 2025-03-23 | 2025-04-01 | 0 | 9 | 0 | 6 | 0 | 10 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 18 | 0 | 20 | 0 | 39 | 0 | 0 | 0 | 40 | 0 | 9 | 0 | 24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
10 | AGE25CL | WTG 373 | Bauer | PSS-14 | Released | R6 | 11 | 253 | 253 | 253 | 0 | 2025-03-13 | 2025-03-24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | 0 | 28 | 0 | 13 | 0 | 27 | 0 | 28 | 0 | 9 | 0 | 32 | 0 | 34 | 0 | 21 | 0 | 6 | 0 | 3 | 0 | 18 | 0 |  | 0 | 19 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
11 | AGE26AL | WTG 377 | Bauer | PSS-12 | Released | R1/R3 | 12 | 253 | 253 | 253 | 0 | 2025-03-22 | 2025-04-01 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | 0 |  | 0 | 9 | 0 | 8 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | 0 | 8 | 0 | 6 | 0 |  | 0 | 7 | 0 |  | 0 | 14 | 0 |  | 0 | 14 | 0 | 2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | 0 | 6 | 0 |  | 0 | 14 | 0 | 14 | 0 | 2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 26 | 0 | 18 | 0 | 29 | 0 | 22 | 0 | 25 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
12 | AGE25CL | WTG 378 | Kamar/Menard | PSS-11 | Released | R1/M-R1 | 10 | 253 | 253 | 253 | 0 | 2025-04-02 | 2025-04-11 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | 0 |  | 0 | 13 | 0 | 9 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 32 | 25.3 | 28 | 25.3 | 30 | 25.3 | 45 | 25.3 | 40 | 25.3 |  | 25.3 | 45 | 25.3 | 5 | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
13 | AGE25CL | WTG 379 | Kamar/Menard | PSS-11 | Released | R2/M-R1 | 9.5 | 199 | 199 | 199 | 0 | 2025-04-02 | 2025-04-11 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | 0 | 10 | 0 | 19 | 0 | 18 | 0 |  | 0 | 20 | 0 | 10 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 25 | 0 | 36 | 0 | 5 | 0 | 27 | 0 | 17 | 0 | 9 | 0 |  | 0 |  | 0 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
14 | AGE25CL | WTG 328 | Menard | PSS-11 | Released | R1 | 12 | 253 | 253 | 253 | 0 | 2025-03-11 | 2025-03-22 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 18 | 0 |  | 0 | 21 | 0 | 19 | 0 | 7 | 0 |  | 0 |  | 0 | 23 | 0 |  | 0 | 11 | 0 | 29 | 0 | 11 | 0 | 15 | 0 | 15 | 0 | 14 | 0 |  | 0 | 8 | 0 | 13 | 0 | 15 | 0 | 17 | 0 | 16 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
15 | AGE25CL | WTG 380 | Saritha | PSS-11 | Released | R5 | 10 | 199 | 199 | 199 | 0 | 2025-04-05 | 2025-04-15 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | 0 | 30 | 0 | 24 | 0 | 34 | 0 | 31 | 0 | 21 | 0 |  | 0 | 28 | 0 | 2 | 0 | 4 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
16 | AGE25CL | WTG 381 | Keller | PSS-11 | Released | R2 | 12 | 253 | 253 | 253 | 0 | 2025-04-04 | 2025-04-14 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | 0 | 26 | 0 | 25 | 0 | 28 | 0 | 32 | 0 | 34 | 0 | 40 | 0 | 41 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
17 | AGE25CL | WTG 382 | Keller | PSS-11 | Released | R1 | 10 | 253 | 253 | 253 | 0 | 2025-04-03 | 2025-04-13 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 18 | 0 | 43 | 0 | 45 | 0 | 38 | 0 | 40 | 0 | 44 | 0 | 25 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
18 | AGE25CL | WTG 399 | Bauer | PSS-14 | Released | R6 | 9 | 253 | 253 | 253 | 0 | 2025-03-15 | 2025-03-25 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 25 | 0 | 26 | 0 | 15 | 0 | 39 | 0 | 39 | 0 | 24 | 0 | 36 | 0 | 26 | 0 | 23 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
19 | AGE26AL | WTG 401 | Keller | PSS-12 | Released | R1 | 9 | 253 | 253 | 253 | 0 | 2025-04-02 | 2025-04-11 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | 0 | 16 | 0 | 16 | 0 | 17 | 0 | 18 | 0 | 30 | 0 | 40 | 0 | 38 | 0 | 33 | 0 | 29 | 0 | 8 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
20 | AGE26AL | WTG 402 | Keller | PSS-12 | Released | R1 | 13 | 253 | 253 | 253 | 0 | 2025-04-11 | 2025-04-21 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | 0 | 25 | 0 | 29 | 0 | 30 | 0 | 34 | 0 | 30 | 0 | 33 | 0 | 31 | 0 | 31 | 0 | 7 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
21 | AGE25CL | WTG 403 | Saritha | PSS-11 | Released | R2/R4 | 9 | 313 | 313 | 313 | 0 | 2025-04-03 | 2025-04-12 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 31.3 |  | 31.3 |  | 31.3 |  | 31.3 |  | 31.3 |  | 31.3 |  | 31.3 |  | 31.3 |  | 31.3 |  | 31.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | 0 | 15 | 0 | 6 | 0 | 25 | 0 | 24 | 0 |  | 0 | 23 | 0 | 11 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | 0 | 14 | 0 |  | 0 | 7 | 0 |  | 0 | 4 | 0 | 13 | 0 | 11 | 0 | 16 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | 0 | 8 | 0 |  | 0 | 11 | 0 |  | 0 |  | 0 | 13 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | 0 | 8 | 0 | 3 | 0 | 8 | 0 | 13 | 0 | 14 | 0 | 8 | 0 |  | 0 | 5 | 0 | 11 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
22 | AGE25CL | WTG 404 | Saritha | PSS-11 | Released | R4 | 11 | 253 | 253 | 253 | 0 | 2025-04-05 | 2025-04-15 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | 0 | 25 | 0 | 18 | 0 | 30 | 0 |  | 0 | 16 | 0 | 22 | 0 | 11 | 0 | 2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | 0 |  | 0 | 23 | 0 | 19 | 0 | 27 | 0 | 24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
23 | AGE25CL | WTG 406 | Keller | PSS-11 | Released | R1 | 10 | 253 | 253 | 253 | 0 | 2025-04-15 | 2025-04-24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | 0 | 36 | 0 | 30 | 0 | 36 | 0 | 38 | 0 | 27 | 0 | 30 | 0 | 34 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
24 | AGE25CL | WTG 407 | Keller | PSS-11 | Released | R2 | 11 | 369 | 369 | 369 | 0 | 2025-04-14 | 2025-04-23 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | 0 |  | 0 | 33 | 0 | 40 | 0 | 40 | 0 | 42 | 0 | 36 | 0 | 40 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 36.9 |  | 36.9 |  | 36.9 |  | 36.9 |  | 36.9 |  | 36.9 |  | 36.9 |  | 36.9 |  | 36.9 |  | 36.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | 0 | 31 | 0 | 34 | 0 | 17 | 0 | 17 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
25 | AGE25CL | WTG 424 | Bauer | PSS-14 | Released | R2 | 13 | 253 | 253 | 253 | 0 | 2025-04-06 | 2025-04-15 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | 0 | 25 | 0 | 18 | 0 | 28 | 0 | 14 | 0 | 25 | 0 | 30 | 0 | 21 | 0 | 18 | 0 | 24 | 0 | 16 | 0 | 18 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
26 | AGE25CL | WTG 425 | Bauer | PSS-14 | Released | R2 | 12 | 253 | 253 | 253 | 0 | 2025-03-26 | 2025-04-04 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | 0 | 15 | 0 |  | 0 | 14 | 0 |  | 0 | 16 | 0 | 30 | 0 | 27 | 0 | 27 | 0 | 25 | 0 | 21 | 0 | 16 | 0 | 25 | 0 | 15 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
27 | AGE26AL | WTG 426 | Bauer | PSS-12 | Released | R4 | 9 | 253 | 253 | 253 | 0 | 2025-04-12 | 2025-04-21 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | 0 | 9 | 0 | 21 | 0 | 6 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | 0 | 27 | 0 |  | 0 | 41 | 0 | 23 | 0 |  | 0 | 22 | 0 | 14 | 0 | 12 | 0 | 24 | 0 | 25 | 0 | 15 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
28 | AGE26AL | WTG 427 | Keller | PSS-12 | Released | R1 | 11 | 253 | 253 | 253 | 0 | 2025-04-22 | 2025-05-02 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | 0 |  | 0 | 28 | 0 | 10 | 0 | 27 | 0 | 32 | 0 | 34 | 0 | 34 | 0 | 34 | 0 | 35 | 0 | 15 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
29 | AGE26AL | WTG 428 | Saritha | PSS-12 | Released | R5/R1 | 10 | 253 | 253 | 253 | 0 | 2025-04-22 | 2025-05-01 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | 0 |  | 0 | 5 | 0 |  | 0 | 8 | 0 | 11 | 0 | 26 | 0 | 19 | 0 | 20 | 0 | 17 | 0 | 25 | 0 |  | 0 | 22 | 0 | 25 | 0 | 23 | 0 | 10 | 0 | 34 | 0 | 5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
30 | AGE25CL | WTG 429 | Saritha | PSS-11 | Released | R4 | 11 | 199 | 199 | 199 | 0 | 2025-04-13 | 2025-04-22 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 29 | 0 |  | 0 | 20 | 0 | 33 | 0 | 19 | 0 | 11 | 0 | 24 | 0 | 1 | 0 |  | 0 | 11 | 0 | 22 | 0 | 10 | 0 | 19 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
31 | AGE25CL | WTG 430 | Keller | PSS-11 | Released | R2 | 10.5 | 253 | 253 | 253 | 0 | 2025-04-16 | 2025-04-25 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | 0 | 19 | 0 | 21 | 0 | 27 | 0 | 31 | 0 | 29 | 0 | 30 | 0 | 31 | 0 | 27 | 0 | 30 | 0 | 6 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
32 | AGE25CL | WTG 431 | Saritha | PSS-11 | Released | R5 | 8 | 253 | 253 | 253 | 0 | 2025-04-26 | 2025-05-05 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | 0 | 34 | 0 | 36 | 0 |  | 0 | 30 | 0 | 39 | 0 | 18 | 0 | 17 | 0 | 33 | 0 | 25 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
33 | AGE25CL | WTG 432 | Saritha | PSS-11 | Released | R1 | 9 | 253 | 253 | 253 | 0 | 2025-04-24 | 2025-05-02 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 28.1111 |  | 28.1111 | 19 | 28.1111 | 34 | 28.1111 | 10 | 28.1111 | 29 | 28.1111 | 21 | 28.1111 | 22 | 28.1111 | 9 | 28.1111 | 5 | 0 | 30 | 0 |  | 0 | 19 | 0 | 5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | 0 | 11 | 0 | 14 | 0 | 8 | 0 | 11 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
34 | AGE25CL | WTG 433 | Keller | PSS-11 | Released | R1 | 9 | 253 | 253 | 253 | 0 | 2025-04-24 | 2025-05-02 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | 0 | 42 | 0 | 47 | 0 |  | 0 | 40 | 0 | 43 | 0 | 33 | 0 | 21 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 28.1111 |  | 28.1111 |  | 28.1111 |  | 28.1111 |  | 28.1111 |  | 28.1111 |  | 28.1111 |  | 28.1111 |  | 28.1111 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
35 | AGE25CL | WTG 448 | Bauer | PSS-14 | Released | R2 | 12 | 253 | 253 | 253 | 0 | 2025-03-16 | 2025-03-26 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | 0 | 30 | 0 | 27 | 0 | 28 | 0 | 15 | 0 | 21 | 0 |  | 0 | 32 | 0 | 28 | 0 | 28 | 0 | 27 | 0 | 6 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
36 | AGE25CL | WTG 449 | ITDC | PSS-14 | Released | R1 | 12 | 253 | 253 | 253 | 0 | 2025-03-27 | 2025-04-05 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | 0 |  | 0 | 10 | 0 |  | 0 | 3 | 0 | 9 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | 0 | 16 | 0 | 6 | 0 | 1 | 0 | 14 | 0 | 13 | 0 | 9 | 0 | 8 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 1 | 0 | 9 | 0 | 12 | 0 | 4 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | 0 | 7 | 0 | 13 | 0 | 16 | 0 | 21 | 0 |  | 0 | 10 | 0 | 13 | 0 | 16 | 0 | 8 | 0 | 10 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
37 | AGE25CL | WTG 450 | Bauer | PSS-14 | Released | R1 | 9 | 253 | 253 | 253 | 0 | 2025-04-05 | 2025-04-15 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | 0 | 27 | 0 | 20 | 0 | 13 | 0 | 17 | 0 |  | 0 | 31 | 0 |  | 0 | 11 | 0 |  | 0 | 27 | 0 | 22 | 0 | 25 | 0 | 18 | 0 | 23 | 0 | 3 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
38 | AGE26AL | WTG 451 | Bauer | PSS-12 | Released | R7/R4 | 16 | 253 | 253 | 253 | 0 | 2025-04-14 | 2025-04-24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | 0 | 14 | 0 |  | 0 | 29 | 0 | 24 | 0 | 25 | 0 |  | 0 | 25 | 0 | 21 | 0 | 23 | 0 | 10 | 0 | 20 | 0 | 28 | 0 | 21 | 0 | 10 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
39 | AGE26AL | WTG 452 | Bauer | PSS-12 | Released | R2 | 9.25 | 253 | 253 | 253 | 0 | 2025-04-15 | 2025-04-24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | 0 | 42 | 0 | 26 | 0 | 29 | 0 | 33 | 0 | 23 | 0 | 22 | 0 | 32 | 0 |  | 0 | 19 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
40 | AGE26AL | WTG 453 | Bauer | PSS-12 | Released | R4 | 12 | 253 | 253 | 253 | 0 | 2025-04-02 | 2025-04-11 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 30 | 0 | 11 | 0 | 39 | 0 | 20 | 0 | 44 | 0 | 39 | 0 | 40 | 0 |  | 0 | 30 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
41 | AGE25CL | WTG 454 | Keller | PSS-11 | Released | R1 | 13 | 253 | 253 | 253 | 0 | 2025-04-23 | 2025-05-02 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | 0 | 27 | 0 |  | 0 | 22 | 0 | 16 | 0 | 20 | 0 | 23 | 0 |  | 0 | 21 | 0 |  | 0 | 24 | 0 | 24 | 0 | 4 | 0 |  | 0 |  | 0 | 16 | 0 |  | 0 | 27 | 0 | 13 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
42 | AGE25CL | WTG 455 | Saritha | PSS-11 | Released | R3 | 7.5 | 253 | 253 | 253 | 0 | 2025-04-26 | 2025-05-05 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 28 | 0 | 41 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | 0 | 22 | 0 |  | 0 | 22 | 0 | 28 | 0 | 23 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | 0 | 22 | 0 | 25 | 0 | 16 | 0 | 13 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
43 | AGE25CL | WTG 456 | Saritha | PSS-11 | Released | R5 | 10 | 253 | 253 | 253 | 0 | 2025-04-05 | 2025-04-15 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | 0 | 37 | 0 | 34 | 0 | 20 | 0 | 30 | 0 | 35 | 0 |  | 0 | 14 | 0 |  | 0 | 17 | 0 | 40 | 0 | 18 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
44 | AGE25CL | WTG 473 | ITDC | PSS-14 | Released | R1 | 9.5 | 253 | 253 | 253 | 0 | 2025-04-14 | 2025-04-24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | 0 |  | 0 |  | 0 | 12 | 0 |  | 23 | 4 | 23 | 4 | 23 | 14 | 23 | 12 | 23 | 14 | 23 | 13 | 23 |  | 23 | 4 | 23 | 4 | 23 | 16 | 23 | 9 | 0 | 1 | 0 | 8 | 0 |  | 0 | 11 | 0 | 17 | 0 | 6 | 0 |  | 0 | 19 | 0 | 2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | 0 |  | 0 | 17 | 0 | 16 | 0 | 8 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | 0 | 9 | 0 | 18 | 0 | 4 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
45 | AGE25CL | WTG 474 | ITDC | PSS-14 | Released | R1 | 12 | 253 | 253 | 253 | 0 | 2025-04-20 | 2025-04-30 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | 0 | 11 | 0 |  | 0 |  | 0 |  | 0 | 12 | 0 | 15 | 0 | 15 | 0 | 8 | 0 | 5 | 0 | 4 | 0 | 7 | 0 | 12 | 0 | 12 | 0 | 7 | 0 | 4 | 0 |  | 0 | 15 | 0 | 19 | 0 | 20 | 0 | 19 | 0 | 11 | 0 | 17 | 0 |  | 0 | 1 | 0 |  | 0 | 17 | 0 | 16 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
46 | AGE26AL | WTG 475 | Bauer | PSS-12 | Released | R1 | 13 | 253 | 253 | 253 | 0 | 2025-04-16 | 2025-04-26 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | 0 | 25 | 0 | 24 | 0 | 11 | 0 | 26 | 0 |  | 0 | 33 | 0 | 28 | 0 | 30 | 0 | 20 | 0 | 10 | 0 | 18 | 0 | 8 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
47 | AGE26AL | WTG 476 | Keller | PSS-12 | Released | R2 | 9.5 | 253 | 253 | 253 | 0 | 2025-04-25 | 2025-05-04 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | 0 | 27 | 0 | 23 | 0 | 30 | 0 | 25 | 0 | 26 | 0 | 31 | 0 | 24 | 0 | 21 | 0 | 27 | 0 | 6 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
48 | AGE26AL | WTG 477 | Bauer | PSS-12 | Released | R4/R7 | 9.5 | 434 | 434 | 434 | 0 | 2025-04-25 | 2025-05-04 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 43.4 |  | 43.4 |  | 43.4 |  | 43.4 |  | 43.4 |  | 43.4 |  | 43.4 |  | 43.4 |  | 43.4 |  | 43.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | 0 | 18 | 0 | 9 | 0 | 37 | 0 | 35 | 0 | 42 | 0 |  | 0 |  | 0 | 37 | 0 | 28 | 0 | 30 | 0 | 7 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | 0 | 25 | 0 | 20 | 0 | 27 | 0 | 23 | 0 | 32 | 0 | 12 | 0 | 28 | 0 | 7 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
49 | AGE26AL | WTG 478 | Bauer | PSS-12 | Released | R6/R3 | 11.5 | 253 | 253 | 253 | 0 | 2025-05-12 | 2025-05-21 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | 0 | 35 | 0 |  | 0 | 28 | 0 | 25 | 0 | 40 | 0 | 29 | 0 | 34 | 0 |  | 0 |  | 0 |  | 0 | 16 | 0 | 26 | 0 | 9 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
50 | AGE25CL | WTG 479 | Keller | PSS-11 | Released | R1 | 11 | 253 | 253 | 253 | 0 | 2025-04-28 | 2025-05-07 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | 0 | 21 | 0 | 31 | 0 | 31 | 0 | 33 | 0 | 31 | 0 | 32 | 0 | 30 | 0 | 31 | 0 | 6 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
51 | AGE25CL | WTG 480 | Keller | PSS-11 | Released | R2 | 9.5 | 253 | 253 | 253 | 0 | 2025-04-27 | 2025-05-06 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | 0 | 37 | 0 | 30 | 0 | 29 | 0 |  | 0 | 36 | 0 |  | 0 | 33 | 0 | 31 | 0 | 31 | 0 | 8 | 0 | 15 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
52 | AGE25CL | WTG 481 | Saritha | PSS-11 | Released | R5 | 10 | 253 | 253 | 253 | 0 | 2025-04-16 | 2025-04-25 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | 0 |  | 0 | 34 | 0 | 14 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | 0 | 6 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | 0 | 2 | 0 |  | 0 | 9 | 0 | 6 | 0 | 9 | 0 | 17 | 0 | 20 | 0 |  | 0 | 17 | 0 | 16 | 0 | 15 | 0 | 6 | 0 | 8 | 0 | 5 | 0 | 12 | 0 | 8 | 0 | 15 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
53 | AGE25CL | WTG 482 | Bauer | PSS-11 | Released | R4 | 12 | 253 | 253 | 253 | 0 | 2025-04-15 | 2025-04-24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 19 | 0 | 17 | 0 | 17 | 0 | 23 | 0 | 31 | 0 | 5 | 0 | 27 | 0 | 30 | 0 | 15 | 0 | 30 | 0 | 21 | 0 | 18 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
54 | AGE26AL | WTG 496 | Bauer | PSS-12 | Released | R1 | 14 | 253 | 253 | 253 | 0 | 2025-04-25 | 2025-05-05 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 29 | 0 | 25 | 0 |  | 0 | 21 | 0 | 18 | 0 | 19 | 0 | 19 | 0 | 16 | 0 | 12 | 0 |  | 0 | 13 | 0 | 10 | 0 | 12 | 0 | 25 | 0 | 21 | 0 | 12 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
55 | AGE26AL | WTG 497 | Bauer | PSS-12 | Released | R1 | 14 | 253 | 434 | 434 | 0 | 2025-05-01 | 2025-05-10 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | 0 | 12 | 0 | 7 | 0 | 16 | 0 | 27 | 0 | 23 | 0 | 24 | 0 | 30 | 0 | 23 | 0 | 29 | 0 | 20 | 0 | 27 | 0 | 7 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | 0 | 29 | 0 | 28 | 0 | 26 | 0 | 27 | 0 | 30 | 0 | 30 | 0 | 7 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
56 | AGE26AL | WTG 498 | Bauer | PSS-12 | Released | R1 | 9.5 | 253 | 253 | 253 | 0 | 2025-04-27 | 2025-05-06 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | 0 |  | 0 | 14 | 0 | 8 | 0 | 8 | 0 | 9 | 0 | 18 | 0 | 34 | 0 | 27 | 0 | 31 | 0 | 33 | 0 | 45 | 0 |  | 0 | 22 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
57 | AGE26AL | WTG 499 | Bauer | PSS-12 | Released | R3 | 9 | 253 | 253 | 253 | 0 | 2025-05-05 | 2025-05-14 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | 0 | 46 | 0 | 46 | 0 | 43 | 0 | 31 | 0 |  | 0 | 44 | 0 | 33 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
58 | AGE26AL | WTG 500 | Keller | PSS-12 | Released | R1 | 14.5 | 253 | 253 | 253 | 0 | 2025-05-05 | 2025-05-14 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 24 | 0 | 25 | 0 |  | 0 | 26 | 0 | 25 | 0 | 30 | 0 | 26 | 0 | 21 | 0 | 21 | 0 | 27 | 0 | 27 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
59 | AGE25CL | WTG 501 | Keller | PSS-11 | Released | R2 | 13 | 253 | 253 | 253 | 0 | 2025-05-01 | 2025-05-11 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | 0 | 24 | 0 | 25 | 0 | 16 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | 0 | 15 | 0 |  | 0 | 22 | 0 | 19 | 0 | 23 | 0 | 25 | 0 | 27 | 0 | 24 | 0 | 3 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
60 | AGE25CL | WTG 502 | Keller | PSS-11 | Released | R1 | 14 | 253 | 253 | 253 | 0 | 2025-04-18 | 2025-04-27 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | 0 | 26 | 0 | 16 | 0 | 24 | 0 | 26 | 0 | 25 | 0 | 24 | 0 | 25 | 0 | 27 | 0 | 20 | 0 |  | 0 |  | 0 |  | 0 | 14 | 0 | 12 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
61 | AGE25CL | WTG 503 | Bauer | PSS-11 | Released | R6 | 8 | 253 | 253 | 253 | 0 | 2025-04-17 | 2025-04-26 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 30 | 0 | 38 | 0 |  | 0 | 31 | 0 | 31 | 0 | 31 | 0 | 23 | 0 | 19 | 0 | 16 | 0 | 16 | 0 | 18 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
62 | AGE25CL | WTG 504 | Bauer | PSS-11 | Released | R7 | 12 | 253 | 253 | 253 | 0 | 2025-04-26 | 2025-05-05 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | 0 | 31 | 0 | 15 | 0 | 30 | 0 | 36 | 0 | 31 | 0 |  | 0 | 15 | 0 | 27 | 0 | 13 | 0 | 30 | 0 | 19 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
63 | AGE25CL | WTG 505 | Bauer | PSS-11 | Released | R7/R4 | 11.5 | 253 | 253 | 253 | 0 | 2025-04-04 | 2025-04-14 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | 0 | 33 | 0 | 38 | 0 | 34 | 0 | 20 | 0 | 27 | 0 | 32 | 0 | 36 | 0 | 12 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
64 | AGE26AL | WTG 517 | Bauer | PSS-12 | Released | R2 | 12 | 303 | 303 | 303 | 0 | 2025-05-06 | 2025-05-16 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 27.5455 |  | 27.5455 |  | 27.5455 |  | 27.5455 |  | 27.5455 |  | 27.5455 |  | 27.5455 |  | 27.5455 |  | 27.5455 |  | 27.5455 |  | 27.5455 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | 0 | 31 | 0 |  | 0 | 11 | 0 | 18 | 0 | 30 | 0 | 32 | 0 | 17 | 0 | 32 | 0 | 30 | 0 | 18 | 0 | 2 | 0 | 19 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | 0 | 9 | 0 |  | 0 |  | 0 |  | 0 | 11 | 0 |  | 0 | 17 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
65 | AGE26AL | WTG 518 | Bauer | PSS-12 | Released | R2 | 10 | 253 | 253 | 253 | 0 | 2025-05-11 | 2025-05-20 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | 0 | 15 | 0 | 15 | 0 | 22 | 0 | 34 | 0 | 37 | 0 | 16 | 0 |  | 0 | 33 | 0 | 30 | 0 | 27 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
66 | AGE26AL | WTG 519 | Bauer | PSS-12 | Released | R2 | 11 | 253 | 253 | 253 | 0 | 2025-05-07 | 2025-05-16 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | 0 | 21 | 0 | 27 | 0 | 28 | 0 | 26 | 0 |  | 0 | 29 | 0 | 17 | 0 | 30 | 0 |  | 0 | 28 | 0 | 18 | 0 | 22 | 0 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
67 | AGE26AL | WTG 520 | Keller | PSS-12 | Released | R2 | 11 | 253 | 253 | 253 | 0 | 2025-05-15 | 2025-05-24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | 0 | 25 | 0 | 23 | 0 | 34 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | 0 | 34 | 0 | 39 | 0 | 30 | 0 | 20 | 0 | 20 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
68 | AGE26AL | WTG 521 | Keller | PSS-12 | Released | R2 | 11.5 | 253 | 253 | 253 | 0 | 2025-05-15 | 2025-05-24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | 0 | 39 | 0 |  | 0 | 31 | 0 | 20 | 0 | 30 | 0 | 33 | 0 | 36 | 0 | 34 | 0 | 15 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
69 | AGE25CL | WTG 522 | Keller | PSS-11 | Released | R1 | 12 | 253 | 253 | 253 | 0 | 2025-04-20 | 2025-04-30 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | 0 | 16 | 0 |  | 0 | 17 | 0 | 23 | 0 | 24 | 0 | 27 | 0 | 31 | 0 | 33 | 0 | 29 | 0 | 25 | 0 | 15 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
70 | AGE25CL | WTG 523 | Bauer | PSS-11 | Released | R3 | 10 | 253 | 253 | 253 | 0 | 2025-04-07 | 2025-04-17 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | 0 | 43 | 0 | 30 | 0 | 41 | 0 |  | 0 | 33 | 0 | 43 | 0 | 36 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
71 | AGE25CL | WTG 524 | Bauer | PSS-11 | Released | R3 | 10 | 253 | 253 | 253 | 0 | 2025-04-06 | 2025-04-16 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | 0 | 33 | 0 | 38 | 0 | 30 | 0 | 29 | 0 | 36 | 0 | 39 | 0 |  | 0 | 36 | 0 | 9 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
72 | AGE26AL | WTG 533 | Bauer | PSS-12 | Released | R2 | 14 | 253 | 253 | 253 | 0 | 2025-04-18 | 2025-04-28 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | 0 | 32 | 0 | 26 | 0 |  | 0 | 25 | 0 | 18 | 0 | 27 | 0 | 18 | 0 | 25 | 0 | 21 | 0 |  | 0 |  | 0 | 18 | 0 | 21 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
73 | AGE26AL | WTG 534 | Bauer | PSS-12 | Released | R2 | 13 | 253 | 253 | 253 | 0 | 2025-04-29 | 2025-05-08 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | 0 | 21 | 0 |  | 0 | 15 | 0 | 33 | 0 | 32 | 0 | 36 | 0 |  | 0 | 31 | 0 |  | 0 | 20 | 0 | 2 | 0 |  | 0 |  | 0 | 15 | 0 | 1 | 0 | 11 | 0 | 26 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
74 | AGE26AL | WTG 535 | Bauer | PSS-12 | Released | R3 | 10 | 253 | 253 | 253 | 0 | 2025-05-09 | 2025-05-18 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 45 | 0 | 35 | 0 |  | 0 | 19 | 0 | 39 | 0 |  | 0 | 30 | 0 | 31 | 0 | 30 | 0 | 24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
75 | AGE26AL | WTG 536 | Keller | PSS-12 | Released | Rig-01 | 13 | 253 | 253 | 253 | 0 | 2025-04-20 | 2025-04-30 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | 0 | 16 | 0 | 21 | 0 | 16 | 0 | 25 | 0 | 25 | 0 | 27 | 0 | 28 | 0 | 28 | 0 | 25 | 0 | 27 | 0 | 11 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
76 | AGE25CL | WTG 457 | Keller | PSS-11 | Released | R2 | 12 | 253 | 253 | 253 | 0 | 2025-04-25 | 2025-05-04 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | 0 | 27 | 0 | 36 | 0 | 34 | 0 |  | 0 | 36 | 0 | 31 | 0 | 35 | 0 | 30 | 0 | 10 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
77 | AGE25CL | WTG 532 | Bauer | PSS-14 | Released | R2 | 14 | 253 | 253 | 253 | 0 | 2025-05-01 | 2025-05-10 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 28 | 0 | 37 | 0 | 33 | 0 | 30 | 0 | 10 | 0 | 28 | 0 | 30 | 0 | 27 | 0 | 29 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
78 | AGE25CL | WTG 516 | Bauer/Keller | PSS-14 | Released | R | 14 | 434 | 434 | 434 | 0 | 2025-05-11 | 2025-05-20 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 43.4 |  | 43.4 |  | 43.4 |  | 43.4 |  | 43.4 |  | 43.4 |  | 43.4 |  | 43.4 |  | 43.4 |  | 43.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | 0 | 19 | 0 | 33 | 0 | 27 | 0 | 25 | 0 | 21 | 0 | 22 | 0 | 29 | 0 | 29 | 0 | 30 | 0 | 15 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | 0 | 10 | 0 | 23 | 0 | 22 | 0 | 18 | 0 | 21 | 0 |  | 0 | 22 | 0 | 27 | 0 | 23 | 0 | 8 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
79 | AGE25CL | WTG 423 | Bauer | PSS-14 | Released | R6/R3 | 15 | 253 | 253 | 253 | 0 | 2025-03-25 | 2025-04-03 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | 0 | 9 | 0 | 14 | 0 | 16 | 0 | 12 | 0 | 14 | 0 | 24 | 0 | 15 | 0 | 10 | 0 | 28 | 0 | 24 | 0 | 23 | 0 | 26 | 0 | 27 | 0 | 5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
80 | AGE25CL | WTG 398 | Bauer | PSS-14 | Released | R6 | 11 | 253 | 253 | 253 | 0 | 2025-04-04 | 2025-04-13 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 18 | 0 | 31 | 0 |  | 0 | 28 | 0 | 33 | 0 | 5 | 0 | 30 | 0 | 38 | 0 | 32 | 0 | 30 | 0 | 8 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
81 | AGE26AL | KH 53 | Keller | PSS-14 | Released | R2 | 10.5 | 253 | 253 | 253 | 0 | 2025-05-29 | 2025-06-08 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | 0 | 29 | 0 | 33 | 0 | 34 | 0 | 43 | 0 | 38 | 0 | 27 | 0 |  | 0 | 34 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
82 | AGE26AL | KH 54 | Keller | PSS-14 | Released | R2 | 10.5 | 253 | 253 | 253 | 0 | 2025-06-09 | 2025-06-19 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 35 | 0 | 27 | 0 | 35 | 0 | 29 | 0 |  | 0 | 35 | 0 | 27 | 0 | 28 | 0 | 23 | 0 | 14 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
83 | AGE26AL | KH 55 | Keller | PSS-14 | Released | R2 | 11 | 253 | 253 | 253 | 0 | 2025-06-20 | 2025-06-30 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | 0 | 39 | 0 | 35 | 0 | 18 | 0 | 38 | 0 | 43 | 0 | 33 | 0 | 36 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
84 | AGE26AL | KH 56 | Keller | PSS-14 | Released | R2 | 11 | 253 | 253 | 253 | 0 | 2025-05-23 | 2025-06-02 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | 0 |  | 0 | 26 | 0 | 18 | 0 | 17 | 0 | 16 | 0 | 13 | 0 | 29 | 0 | 15 | 0 | 36 | 0 | 31 | 0 | 42 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
85 | AGE26AL | KH 57 | Bauer | PSS-14 | Released | R1 | 7 | 253 | 253 | 253 | 0 | 2025-06-03 | 2025-06-13 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 26 | 0 | 46 | 0 | 34 | 0 | 34 | 0 | 44 | 0 | 43 | 0 |  | 0 | 26 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
86 | AGE26AL | KH 58 | Bauer | PSS-14 | Released | R1 | 10 | 253 | 253 | 253 | 0 | 2025-06-14 | 2025-06-24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | 0 | 38 | 0 | 49 | 0 |  | 0 | 26 | 0 | 47 | 0 | 37 | 0 | 34 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
87 | AGE26AL | KH 59 | Bauer | PSS-14 | Released | R1 | 12 | 253 | 253 | 253 | 0 | 2025-06-05 | 2025-06-15 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | 0 | 18 | 0 | 20 | 0 |  | 0 | 20 | 0 | 21 | 0 | 19 | 0 |  | 0 |  | 0 | 10 | 0 | 31 | 0 | 36 | 0 | 37 | 0 | 35 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
88 | AGE26AL | KH 60 | Bauer | PSS-14 | Released | R2 | 12 | 253 | 253 | 253 | 0 | 2025-05-26 | 2025-06-05 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | 0 | 35 | 0 |  | 0 |  | 0 | 37 | 0 | 36 | 0 | 40 | 0 | 28 | 0 | 39 | 0 | 29 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
89 | AGE26AL | KH 61 | Bauer | PSS-14 | Released | R2 | 13 | 253 | 253 | 253 | 0 | 2025-06-16 | 2025-06-26 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | 0 | 28 | 0 | 33 | 0 | 20 | 0 | 33 | 0 |  | 0 | 32 | 0 | 32 | 0 | 26 | 0 | 37 | 0 | 7 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
90 | AGE26AL | KH 556 | Keller | PSS-14 | Released | R2 | 11 | 253 | 253 | 253 | 0 | 2025-05-07 | 2025-05-17 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 32 | 0 |  | 0 | 37 | 0 | 19 | 0 | 22 | 0 | 19 | 0 |  | 0 | 6 | 0 |  | 0 |  | 0 | 10 | 0 | 21 | 0 | 18 | 0 | 27 | 0 | 12 | 0 | 1 | 0 | 9 | 0 | 10 | 0 | 10 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
91 | AGE26AL | KH 523 | Keller | PSS-14 | Released | R1 | 9 | 253 | 253 | 253 | 0 | 2025-05-28 | 2025-06-06 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | 0 | 23 | 0 | 21 | 0 | 38 | 0 | 49 | 0 | 57 | 0 | 27 | 0 | 17 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
92 | AGE26AL | KH 522 | Keller | PSS-14 | Released | R2 | 14 | 253 | 253 | 253 | 0 | 2025-05-18 | 2025-05-27 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | 0 | 33 | 0 | 20 | 0 | 20 | 0 | 24 | 0 | 23 | 0 | 25 | 0 | 28 | 0 | 25 | 0 | 18 | 0 | 22 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
93 | AGE26AL | KH 521 | Bauer | PSS-14 | Released |  | 10 | 199 | 199 | 0 | 199 | 2025-05-18 | 2025-05-27 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
94 | AGE26AL | KH 508 | Keller | PSS-14 | Released | R1 | 12 | 253 | 253 | 253 | 0 | 2025-05-07 | 2025-05-17 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | 0 |  | 0 | 19 | 0 | 32 | 0 | 29 | 0 | 30 | 0 | 36 | 0 | 36 | 0 | 32 | 0 | 17 | 0 | 11 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
95 | AGE26AL | KH 555 | Keller | PSS-14 | Released | R4 | 11 | 253 | 253 | 253 | 0 | 2025-05-08 | 2025-05-18 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | 0 | 24 | 0 | 13 | 0 | 17 | 0 | 16 | 0 | 14 | 0 | 5 | 0 |  | 0 | 15 | 0 | 22 | 0 | 22 | 0 | 19 | 0 | 21 | 0 | 23 | 0 | 8 | 0 | 5 | 0 | 14 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
96 | AGE26AL | KH 557 | Keller | PSS-14 | Released | R2 | 12 | 253 | 253 | 253 | 0 | 2025-05-09 | 2025-05-19 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 24 | 0 | 17 | 0 | 8 | 0 | 19 | 0 | 22 | 0 | 22 | 0 | 16 | 0 | 12 | 0 | 9 | 0 | 22 | 0 | 22 | 0 | 21 | 0 | 18 | 0 | 1 | 0 | 12 | 0 | 2 | 0 | 5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
97 | AGE26AL | KH 581 | Keller | PSS-14 | Released | R4 | 8 | 253 | 253 | 253 | 0 | 2025-06-07 | 2025-06-16 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | 0 | 37 | 0 |  | 0 | 7 | 0 | 21 | 0 | 3 | 0 | 37 | 0 | 25 | 0 | 19 | 0 | 25 | 0 | 28 | 0 | 15 | 0 | 27 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
98 | AGE26AL | KH 582 | Pinnacle | PSS-14 | Released | R1 | 12 | 253 | 253 | 253 | 0 | 2025-05-28 | 2025-06-06 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | 0 | 12 | 0 | 2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | 0 |  | 0 | 7 | 0 |  | 0 | 25 | 0 |  | 0 | 5 | 0 |  | 0 |  | 0 | 3 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | 0 | 9 | 0 | 6 | 0 |  | 0 |  | 0 |  | 0 | 14 | 0 | 15 | 0 | 10 | 0 | 12 | 0 | 8 | 0 | 19 | 0 |  | 0 | 14 | 0 | 4 | 0 | 12 | 0 | 6 | 0 | 17 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
99 | AGE26AL | KH 583 | Bauer | PSS-14 | Released | R5 | 9 | 253 | 253 | 253 | 0 | 2025-05-19 | 2025-05-29 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | 0 | 25 | 0 | 36 | 0 | 22 | 0 | 37 | 0 | 22 | 0 | 29 | 0 | 25 | 0 | 23 | 0 | 10 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
100 | AGE26AL | KH 52 | Bauer | PSS-14 | Released | R6 | 13 | 253 | 253 | 253 | 0 | 2025-05-09 | 2025-05-19 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | 0 | 28 | 0 | 22 | 0 |  | 0 | 20 | 0 | 24 | 0 | 20 | 0 | 15 | 0 | 19 | 0 | 20 | 0 |  | 0 | 26 | 0 | 26 | 0 | 24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
101 | AGE26AL | KH 51 | Bauer | PSS-14 | Released | R4 | 11.5 | 253 | 253 | 253 | 0 | 2025-05-20 | 2025-05-29 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 19 | 0 | 25 | 0 | 27 | 0 | 21 | 0 | 17 | 0 | 27 | 0 | 28 | 0 | 28 | 0 | 26 | 0 | 18 | 0 | 17 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
102 | AGE26AL | KH 552 | Saritha | PSS-14 | Released | R | 13 | 253 | 253 | 253 | 0 | 2025-05-10 | 2025-05-19 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | 0 | 10 | 0 |  | 0 | 18 | 0 | 4 | 0 | 15 | 0 | 18 | 0 | 13 | 0 | 19 | 0 | 10 | 0 |  | 0 | 11 | 0 | 12 | 0 | 3 | 0 | 11 | 0 | 4 | 0 | 16 | 0 |  | 0 | 19 | 0 | 24 | 0 | 23 | 0 | 21 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
103 | AGE26AL | KH 588 | Keller | PSS-14 | Released | R1 | 9 | 253 | 253 | 253 | 0 | 2025-06-17 | 2025-06-26 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 18 | 0 | 44 | 0 | 38 | 0 |  | 0 | 35 | 0 | 34 | 0 | 39 | 0 | 20 | 0 | 25 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
104 | AGE26AL | KH 589 | Keller | PSS-14 | Released | R1 | 9 | 253 | 253 | 253 | 0 | 2025-06-07 | 2025-06-17 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | 0 | 38 | 0 | 34 | 0 | 43 | 0 | 16 | 0 | 29 | 0 | 40 | 0 | 39 | 0 | 6 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
105 | AGE26AL | KH 590 | Bauer | PSS-14 | Released | R5 | 12 | 253 | 253 | 253 | 0 | 2025-05-30 | 2025-06-08 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | 0 | 21 | 0 | 30 | 0 | 27 | 0 | 36 | 0 | 23 | 0 | 12 | 0 | 5 | 0 |  | 0 | 23 | 0 | 32 | 0 | 30 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
106 | AGE26AL | KH 591 | Bauer | PSS-14 | Released | R5 | 12 | 253 | 253 | 253 | 0 | 2025-05-20 | 2025-05-29 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 | 14 | 25.3 | 26 | 25.3 | 11 | 0 | 20 | 0 | 29 | 0 | 31 | 0 | 25 | 0 | 22 | 0 | 14 | 0 | 21 | 0 | 17 | 0 | 23 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
107 | AGE26AL | KH 592 | Bauer | PSS-14 | Released | R5 | 9 | 253 | 253 | 253 | 0 | 2025-05-30 | 2025-06-08 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | 0 | 31 | 0 | 42 | 0 | 33 | 0 | 12 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | 0 | 20 | 0 | 33 | 0 | 39 | 0 | 30 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
108 | AGE26AL | KH 550 | Bauer | PSS-14 | Released | R1 | 13 | 253 | 253 | 253 | 0 | 2025-05-20 | 2025-05-29 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | 0 | 14 | 0 | 20 | 0 | 25 | 0 | 12 | 0 | 17 | 0 | 28 | 0 | 16 | 0 |  | 0 | 25 | 0 | 25 | 0 | 23 | 0 | 29 | 0 | 16 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
109 | AGE26AL | KH 551 | Keller | PSS-14 | Released | R1 | 13 | 253 | 253 | 253 | 0 | 2025-05-10 | 2025-05-19 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | 0 |  | 0 | 30 | 0 | 30 | 0 | 39 | 0 | 36 | 0 | 12 | 0 | 32 | 0 | 27 | 0 | 30 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
110 | AGE26AL | KH 579 | Keller | PSS-14 | Released | R1 | 10 | 253 | 253 | 253 | 0 | 2025-05-25 | 2025-06-04 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 | 11 | 23 |  | 23 | 34 | 23 | 33 | 23 | 35 | 0 | 38 | 0 | 35 | 0 | 36 | 0 | 31 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
111 | AGE26AL | KH 596 | Keller | PSS-14 | Released | R4 | 10 | 253 | 253 | 253 | 0 | 2025-06-18 | 2025-06-28 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | 0 |  | 0 | 17 | 0 | 20 | 0 | 19 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | 0 | 20 | 0 | 21 | 0 | 16 | 0 | 18 | 0 | 9 | 0 | 12 | 0 | 12 | 0 | 7 | 0 | 5 | 0 | 10 | 0 | 15 | 0 | 22 | 0 | 11 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
112 | AGE26AL | KH 597 | Keller | PSS-14 | Released | R1 | 13 | 253 | 253 | 253 | 0 | 2025-06-09 | 2025-06-18 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | 0 | 4 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | 0 | 12 | 0 | 27 | 0 | 20 | 0 | 18 | 0 | 24 | 0 | 19 | 0 | 25 | 0 | 27 | 0 | 5 | 0 |  | 0 | 12 | 0 | 4 | 0 | 26 | 0 | 19 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
113 | AGE26AL | KH 598 | Bauer | PSS-14 | Released | R3/R6 | 10 | 253 | 253 | 253 | 0 | 2025-05-30 | 2025-06-08 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 18 | 0 | 28 | 0 | 20 | 0 | 14 | 0 | 27 | 0 |  | 0 | 33 | 0 | 36 | 0 | 30 | 0 |  | 0 | 30 | 0 | 17 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
114 | AGE26AL | KH 599 | Bauer | PSS-14 | Released | R5 | 12 | 253 | 253 | 253 | 0 | 2025-06-09 | 2025-06-18 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | 0 | 23 | 0 | 25 | 0 | 19 | 0 | 23 | 0 | 10 | 0 | 19 | 0 | 17 | 0 | 29 | 0 | 31 | 0 |  | 0 | 33 | 0 | 12 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
115 | AGE26AL | KH 600 | Bauer | PSS-14 | Released | R8 | 12 | 253 | 253 | 253 | 0 | 2025-05-30 | 2025-06-08 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 | 4 | 25.3 | 24 | 25.3 | 30 | 25.3 | 22 | 25.3 | 28 | 25.3 | 28 | 25.3 | 31 | 25.3 | 27 | 25.3 | 23 | 25.3 |  | 0 | 24 | 0 | 12 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
116 | AGE26AL | KH 553 | Bauer | PSS-14 | Released | R1 | 10 | 253 | 253 | 253 | 0 | 2025-05-20 | 2025-05-29 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | 0 | 4 | 0 | 23 | 0 | 40 | 0 | 27 | 0 | 25 | 0 |  | 0 | 40 | 0 | 40 | 0 | 40 | 0 | 5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
117 | AGE26AL | KH 580 | Keller | PSS-14 | Released | R4 | 9 | 253 | 253 | 253 | 0 | 2025-05-10 | 2025-05-19 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | 0 | 22 | 0 | 23 | 0 |  | 0 | 24 | 0 | 21 | 0 | 21 | 0 | 21 | 0 | 25 | 0 | 28 | 0 | 23 | 0 | 25 | 0 | 6 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
118 | AGE26AL | KH 478 | Bauer | PSS-14 | Released | R1 | 10 | 253 | 253 | 253 | 0 | 2025-05-11 | 2025-05-20 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | 0 | 30 | 0 | 38 | 0 | 30 | 0 | 30 | 0 | 30 | 0 | 24 | 0 | 20 | 0 | 34 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
119 | AGE26AL | KH 604 | Keller | PSS-14 | Released | R1 | 12 | 253 | 253 | 253 | 0 | 2025-06-19 | 2025-06-29 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 23 | 0 | 32 | 0 | 30 | 0 | 33 | 0 | 30 | 0 |  | 0 | 29 | 0 | 31 | 0 |  | 0 | 25 | 0 | 20 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
120 | AGE26AL | KH 605 | Keller | PSS-14 | Released | R2 | 13 | 253 | 253 | 253 | 0 | 2025-06-09 | 2025-06-18 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | 0 | 8 | 0 | 9 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | 0 | 9 | 0 | 12 | 0 | 5 | 0 | 4 | 0 | 22 | 0 | 11 | 0 | 20 | 0 | 7 | 0 |  | 0 | 6 | 0 | 5 | 0 | 14 | 0 | 17 | 0 | 25 | 0 | 23 | 0 |  | 0 | 18 | 0 | 16 | 0 | 12 | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
121 | AGE26AL | KH 606 | Bauer | PSS-14 | Released | R4 | 10 | 253 | 253 | 253 | 0 | 2025-06-19 | 2025-06-29 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | 0 | 3 | 0 | 35 | 0 | 29 | 0 | 11 | 0 | 31 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 9 | 0 | 18 | 0 | 24 | 0 | 20 | 0 |  | 0 | 29 | 0 | 19 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
122 | AGE26AL | KH 607 | Bauer | PSS-14 | Released | R4 | 10 | 253 | 253 | 253 | 0 | 2025-06-09 | 2025-06-18 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | 0 | 20 | 0 |  | 0 | 11 | 0 | 35 | 0 | 36 | 0 | 27 | 0 | 26 | 0 | 34 | 0 | 24 | 0 | 21 | 0 |  | 25.3 | 9 | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
123 | AGE26AL | KH 608 | Bauer | PSS-14 | Released | R8 | 11 | 253 | 253 | 253 | 0 | 2025-05-30 | 2025-06-08 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 | 9 | 0 | 33 | 0 | 35 | 0 | 33 | 0 | 29 | 0 | 25 | 0 | 20 | 0 | 14 | 0 | 20 | 0 | 30 | 0 | 5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
124 | AGE26AL | KH 509 | Keller | PSS-14 | Released | R1 | 11 | 253 | 253 | 253 | 0 | 2025-05-20 | 2025-05-29 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 34 | 0 | 35 | 0 | 38 | 0 | 16 | 0 | 35 | 0 | 38 | 0 | 31 | 0 | 22 | 0 | 4 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
125 | AGE26AL | KH 554 | Keller | PSS-14 | Released | R1 | 12 | 253 | 253 | 253 | 0 | 2025-05-21 | 2025-05-30 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | 0 | 18 | 0 | 36 | 0 | 35 | 0 | 16 | 0 | 21 | 0 | 33 | 0 | 32 | 0 | 32 | 0 | 15 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
126 | AGE26AL | KH 611 | Bauer | PSS-14 | Released | R7 | 10 | 253 | 253 | 253 | 0 | 2025-06-19 | 2025-06-29 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 23 | 0 | 35 | 0 | 29 | 0 |  | 0 | 25 | 0 | 37 | 0 | 27 | 0 | 42 | 0 |  | 0 | 35 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
127 | AGE26AL | KH 612 | Bauer | PSS-14 | Released | R7 | 13 | 253 | 253 | 253 | 0 | 2025-05-21 | 2025-06-01 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 19 | 0 | 15 | 0 | 28 | 0 | 36 | 0 | 17 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 23 | 0 | 30 | 21.0833 | 26 | 21.0833 | 10 | 21.0833 | 26 | 21.0833 | 23 | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
128 | AGE26AL | KH 613 | Bauer | PSS-14 | Released | R7 | 10 | 253 | 253 | 253 | 0 | 2025-06-19 | 2025-06-29 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | 0 | 17 | 0 | 28 | 0 | 32 | 0 | 25 | 0 | 21 | 0 | 36 | 0 | 32 | 0 | 32 | 0 | 21 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
129 | AGE26AL | KH 614 | Bauer | PSS-14 | Released | R1 | 11 | 253 | 253 | 253 | 0 | 2025-06-09 | 2025-06-18 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | 0 | 39 | 0 | 36 | 0 | 30 | 0 | 23 | 0 | 35 | 0 |  | 25.3 | 25 | 25.3 | 12 | 25.3 | 13 | 25.3 | 18 | 25.3 | 10 | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
130 | AGE26AL | KH 615 | Bauer | PSS-14 | Released | R4 | 10.5 | 253 | 253 | 253 | 0 | 2025-05-30 | 2025-06-08 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 | 4 | 0 | 14 | 0 | 27 | 0 | 26 | 0 | 15 | 0 | 25 | 0 | 9 | 0 |  | 0 | 4 | 0 | 20 | 0 |  | 0 |  | 0 | 23 | 0 | 28 | 0 | 23 | 0 | 14 | 0 | 18 | 0 | 3 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
131 | AGE26AL | KH 47 | Pinnacle/Bauer | PSS-14 | Released | R1 | 12.5 | 253 | 253 | 253 | 0 | 2025-05-31 | 2025-06-09 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | 0 | 9 | 0 |  | 0 | 9 | 0 | 4 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | 0 | 5 | 0 | 11 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | 0 | 8 | 0 | 5 | 0 | 6 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 18 | 0 | 4 | 0 | 26 | 0 | 24 | 0 | 17 | 0 | 23 | 0 | 4 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
132 | AGE26AL | KH 617 | Bauer | PSS-14 | Released | R1 | 11 | 253 | 253 | 253 | 0 | 2025-06-02 | 2025-06-12 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | 0 | 23 | 0 | 27 | 0 | 17 | 0 | 24 | 0 | 13 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | 0 | 9 | 0 | 25 | 0 | 8 | 0 |  | 0 | 12 | 0 | 31 | 0 | 5 | 0 |  | 0 | 4 | 0 | 20 | 0 | 15 | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
133 | AGE26AL | KH 618 | Bauer | PSS-14 | Released | R8 | 11.5 | 253 | 253 | 253 | 0 | 2025-06-19 | 2025-06-28 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 | 15 | 25.3 | 32 | 25.3 | 27 | 25.3 | 6 | 25.3 | 17 | 25.3 | 16 | 0 |  | 0 | 23 | 0 | 30 | 0 | 29 | 0 | 7 | 0 | 22 | 0 | 27 | 0 | 2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
134 | AGE26AL | KH 619 | Bauer | PSS-14 | Released | R7 | 11 | 253 | 253 | 253 | 0 | 2025-06-09 | 2025-06-18 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 19 | 0 | 25 | 0 | 37 | 0 |  | 25.3 | 19 | 25.3 | 26 | 25.3 | 15 | 25.3 | 20 | 25.3 | 34 | 25.3 | 28 | 25.3 | 30 | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
135 | AGE26AL | KH 620 | Bauer | PSS-14 | Released | R7 | 10.5 | 253 | 253 | 253 | 0 | 2025-06-10 | 2025-06-19 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 | 1 | 25.3 | 3 | 25.3 | 20 | 25.3 |  | 0 |  | 0 | 30 | 0 | 30 | 0 | 26 | 0 | 8 | 0 | 20 | 0 | 23 | 0 | 21 | 0 | 17 | 0 |  | 0 | 14 | 0 | 30 | 0 | 10 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
136 | AGE26AL | KH 621 | Bauer | PSS-14 | Released | R1 | 8 | 253 | 253 | 253 | 0 | 2025-06-13 | 2025-06-23 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 | 28 | 23 | 45 | 23 | 27 | 23 | 33 | 0 | 44 | 0 | 39 | 0 | 18 | 0 | 19 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
137 | AGE26AL | KH 622 |  | PSS-14 | Released |  | 10 | 253 | 253 | 0 | 253 | 2025-06-16 | 2025-06-26 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
138 | AGE26AL | KH 34 | Bauer | PSS-14 | Released | R1 | 11 | 253 | 253 | 253 | 0 | 2025-06-19 | 2025-06-28 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | 0 | 33 | 0 | 5 | 0 | 15 | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | 0 | 34 | 0 | 36 | 0 | 23 | 0 | 36 | 0 |  | 0 | 19 | 0 | 13 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
139 | AGE26AL | KH 35 | Bauer | PSS-14 | Released | R2 | 14 | 253 | 253 | 253 | 0 | 2025-06-06 | 2025-06-15 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | 0 | 22 | 0 | 28 | 0 | 29 | 0 | 25 | 0 |  | 0 | 8 | 0 | 25 | 0 | 27 | 0 | 22 | 0 | 27 | 0 | 24 | 0 | 6 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
140 | AGE26AL | KH 68 | Bauer | PSS-14 | Released | R3 | 12 | 253 | 253 | 253 | 0 | 2025-05-25 | 2025-06-04 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | 0 |  | 0 |  | 0 |  | 0 | 11 | 0 | 13 | 0 | 12 | 0 | 12 | 0 | 10 | 0 | 32 | 0 | 28 | 0 | 23 | 0 | 20 | 0 | 24 | 0 | 32 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | 0 | 17 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
141 | AHEJ5L | WTG 177 | Bauer | PSS-05 | Released | R2 | 9.5 | 253 | 253 | 253 | 0 | 2025-03-09 | 2025-03-19 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 37 | 0 | 60 | 0 | 57 | 0 | 57 | 0 | 42 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
142 | AHEJ5L | WTG 199 | Bauer | PSS-05 | Released | R7 | 12 | 253 | 253 | 253 | 0 | 2025-02-22 | 2025-03-03 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | 0 | 21 | 0 | 25 | 25.3 | 36 | 25.3 |  | 25.3 | 38 | 25.3 | 35 | 25.3 | 25 | 25.3 | 33 | 25.3 | 32 | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
143 | AHEJ5L | WTG 154 | Bauer | PSS-05 | Released | R2 | 11.5 | 369 | 253 | 253 | 0 | 2025-03-20 | 2025-03-29 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 36.9 |  | 36.9 |  | 36.9 |  | 36.9 |  | 36.9 |  | 36.9 |  | 36.9 |  | 36.9 |  | 36.9 |  | 36.9 | 15 | 0 | 18 | 0 |  | 0 | 20 | 0 | 27 | 0 | 22 | 0 | 34 | 0 | 40 | 0 |  | 0 | 6 | 0 | 49 | 0 | 22 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
144 | AHEJ5L | WTG 002 | Bauer | PSS-05 | Released | R3 | 9 | 253 | 253 | 253 | 0 | 2025-03-15 | 2025-03-24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 26 | 0 | 23 | 0 | 48 | 0 | 47 | 0 |  | 0 | 48 | 0 | 39 | 0 | 22 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
145 | AHEJ5L | WTG 290 | Bauer | PSS-05 | Released | R8 | 9 | 253 | 253 | 253 | 0 | 2025-03-01 | 2025-03-10 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | 0 | 15 | 0 | 28 | 0 | 26 | 0 | 24 | 0 | 24 | 0 |  | 0 | 27 | 0 | 41 | 0 | 31 | 0 | 31 | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
146 | AHEJ5L | WTG 315 | Bauer | PSS-05 | Released | R8 | 9.5 | 253 | 253 | 253 | 0 | 2025-03-11 | 2025-03-20 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | 0 | 12 | 0 | 38 | 0 | 26 | 0 |  | 0 | 29 | 0 | 28 | 0 | 23 | 0 | 34 | 0 | 24 | 0 | 27 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
147 | AHEJ5L | WTG 266 | Bauer | PSS-05 | Released | R6 | 11 | 253 | 253 | 253 | 0 | 2025-03-24 | 2025-04-02 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | 0 | 22 | 0 |  | 0 | 27 | 0 | 29 | 0 | 35 | 0 | 39 | 0 | 41 | 0 | 36 | 0 |  | 0 | 17 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
148 | AHEJ5L | WTG 221 | Bauer | PSS-05 | Released | R6 | 12 | 253 | 253 | 253 | 0 | 2025-03-04 | 2025-03-13 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | 0 | 18 | 0 | 13 | 0 | 6 | 0 | 21 | 0 |  | 0 | 31 | 0 | 37 | 0 | 31 | 0 | 38 | 0 | 43 | 0 | 8 | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
149 | AHEJ5L | WTG 131 | Bauer | PSS-05 | Released | R3 | 12 | 253 | 253 | 253 | 0 | 2025-02-19 | 2025-02-28 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | 0 | 19 | 0 | 21 | 0 | 30 | 0 |  | 0 | 27 | 0 | 29 | 0 | 37 | 0 | 35 | 0 | 35 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
150 | AHEJ5L | WTG 132 | Bauer | PSS-05 | Released | R3 | 13 | 253 | 253 | 253 | 0 | 2025-03-21 | 2025-03-30 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | 0 | 34 | 0 | 46 | 0 |  | 0 | 41 | 0 | 25 | 0 | 26 | 0 | 36 | 0 | 29 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
151 | AHEJ5L | WTG 152 | Bauer | PSS-05 | Released | R2 | 10.5 | 253 | 253 | 253 | 0 | 2025-03-01 | 2025-03-10 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 46 | 0 | 49 | 0 | 24 | 0 | 13 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 47 | 0 | 24 | 0 | 48 | 0 | 2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
152 | AHEJ5L | WTG 153 | Bauer | PSS-05 | Released | R2 | 10.5 | 253 | 253 | 253 | 0 | 2025-03-23 | 2025-04-01 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | 0 | 40 | 0 | 49 | 0 | 49 | 0 | 49 | 0 | 20 | 0 |  | 0 | 24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
153 | AHEJ5L | WTG 155 | Bauer | PSS-05 | Released | R3 | 8 | 253 | 253 | 253 | 0 | 2025-03-11 | 2025-03-21 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 25 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | 0 | 34 | 0 | 14 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | 0 | 43 | 0 | 44 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 43 | 0 | 8 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
154 | AHEJ5L | WTG 156 | Bauer | PSS-05 | Released | R6 | 9 | 253 | 253 | 253 | 0 | 2025-03-22 | 2025-03-31 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 32 | 0 | 60 | 0 | 61 | 0 | 57 | 0 | 43 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
155 | AHEJ5L | WTG 175 | Saritha | PSS-05 | Released | R2 | 7 | 253 | 253 | 253 | 0 | 2025-03-12 | 2025-03-22 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 3 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | 0 | 8 | 0 | 3 | 0 | 16 | 0 | 14 | 0 | 14 | 0 | 11 | 0 | 18 | 0 | 25 | 0 |  | 0 | 8 | 0 | 13 | 0 | 13 | 0 | 12 | 0 | 9 | 0 |  | 0 |  | 0 | 12 | 0 | 17 | 0 | 17 | 0 | 13 | 0 | 12 | 0 | 9 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
156 | AHEJ5L | WTG 176 | Bauer | PSS-05 | Released | R2 | 9.5 | 253 | 253 | 253 | 0 | 2025-03-23 | 2025-04-02 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 51 | 0 | 43 | 0 | 55 | 0 | 57 | 0 |  | 0 | 47 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
157 | AHEJ5L | WTG 178 | Bauer | PSS-05 | Released | R8 | 12 | 253 | 253 | 253 | 0 | 2025-03-08 | 2025-03-19 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 21.0833 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | 0 | 9 | 0 | 30 | 0 | 34 | 0 | 39 | 0 | 2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | 0 | 26 | 0 | 33 | 0 | 38 | 0 | 14 | 0 |  | 0 | 11 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
158 | AHEJ5L | WTG 179 | Bauer | PSS-05 | Released | R6 | 13 | 253 | 253 | 253 | 0 | 2025-03-20 | 2025-03-30 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | 0 | 38 | 0 |  | 0 | 45 | 0 | 46 | 0 | 13 | 0 | 42 | 0 | 42 | 0 |  | 0 | 3 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
159 | AHEJ5L | WTG 197 | Bauer | PSS-05 | Released | R2 | 10 | 253 | 253 | 253 | 0 | 2025-03-11 | 2025-03-20 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | 0 | 49 | 0 | 19 | 0 | 59 | 0 |  | 0 | 62 | 0 | 44 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
160 | AHEJ5L | WTG 198 | Bauer | PSS-05 | Released | R2 | 13 | 451 | 451 | 451 | 0 | 2025-03-21 | 2025-03-30 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | 0 |  | 0 | 29 | 0 | 35 | 0 | 39 | 0 | 31 | 0 | 2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 45.1 |  | 45.1 |  | 45.1 |  | 45.1 |  | 45.1 |  | 45.1 |  | 45.1 |  | 45.1 |  | 45.1 |  | 45.1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 25 | 0 | 33 | 0 | 48 | 0 | 30 | 0 | 39 | 0 | 15 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | 0 | 28 | 0 | 20 | 0 | 20 | 0 | 20 | 0 | 23 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
161 | AHEJ5L | WTG 200 | Bauer | PSS-05 | Released | R6 | 12 | 253 | 253 | 253 | 0 | 2025-02-20 | 2025-03-01 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | 0 | 36 | 0 | 33 | 0 |  | 0 | 41 | 0 | 18 | 0 | 17 | 0 | 27 | 0 | 28 | 0 | 31 | 0 | 16 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
162 | AHEJ5L | WTG 201 | Bauer | PSS-05 | Released | R6 | 9 | 253 | 253 | 253 | 0 | 2025-03-31 | 2025-04-10 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 40 | 0 | 48 | 0 | 48 | 0 | 45 | 0 | 45 | 0 |  | 0 | 27 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
163 | AHEJ5L | WTG 222 | Bauer | PSS-05 | Released | R6 | 12.5 | 253 | 253 | 253 | 0 | 2025-03-02 | 2025-03-11 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | 0 | 6 | 0 | 13 | 0 |  | 0 | 8 | 0 | 39 | 0 | 35 | 0 | 35 | 0 | 32 | 0 |  | 0 |  | 0 | 33 | 0 | 34 | 0 | 12 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
164 | AHEJ5L | WTG 223 | Bauer | PSS-05 | Released | R6 | 13 | 253 | 253 | 253 | 0 | 2025-02-20 | 2025-03-01 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | 0 | 24 | 0 | 17 | 0 |  | 0 | 36 | 0 | 32 | 0 | 34 | 0 | 10 | 0 | 17 | 0 | 25 | 0 | 24 | 0 | 26 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
165 | AHEJ5L | WTG 245 | Bauer | PSS-05 | Released | R6 | 12 | 253 | 253 | 253 | 0 | 2025-03-02 | 2025-03-11 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 34 | 0 | 34 | 0 | 36 | 0 | 37 | 0 | 39 | 0 | 22 | 0 | 51 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
166 | AHEJ5L | WTG 267 | Bauer | PSS-05 | Released | R8 | 13 | 253 | 253 | 253 | 0 | 2025-03-22 | 2025-03-31 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | 0 | 24 | 0 | 17 | 0 | 31 | 0 | 25 | 0 | 21 | 0 | 18 | 25.3 | 23 | 25.3 | 12 | 25.3 |  | 25.3 | 25 | 25.3 | 32 | 25.3 | 10 | 25.3 | 10 | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
167 | AHEJ5L | WTG 268 | Bauer | PSS-05 | Released | R8 | 11 | 253 | 253 | 253 | 0 | 2025-03-12 | 2025-03-21 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | 0 | 47 | 0 | 44 | 0 | 45 | 0 | 39 | 0 | 36 | 0 |  | 0 | 18 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
168 | AHEJ5L | WTG 291 | Bauer | PSS-05 | Released | R8 | 8.5 | 253 | 253 | 253 | 0 | 2025-03-21 | 2025-03-30 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 | 4 | 25.3 | 36 | 25.3 | 26 | 0 |  | 0 |  | 0 |  | 0 | 36 | 0 | 43 | 0 | 38 | 0 |  | 0 | 30 | 0 | 29 | 0 | 11 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
169 | AHEJ5L | WTG 292 | Bauer | PSS-05 | Released | R8 | 10 | 253 | 253 | 253 | 0 | 2025-03-22 | 2025-03-31 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 33 | 0 | 37 | 0 | 31 | 0 |  | 0 | 35 | 0 | 38 | 0 | 34 | 0 | 35 | 0 | 10 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
170 | AHEJ5L | WTG 314 | Bauer | PSS-05 | Released | R8 | 11 | 253 | 253 | 253 | 0 | 2025-02-19 | 2025-02-28 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | 0 | 6 | 0 | 16 | 0 | 4 | 0 | 11 | 0 | 14 | 0 | 2 | 0 | 9 | 0 | 18 | 0 | 21 | 0 |  | 0 | 17 | 0 | 22 | 0 | 25 | 0 | 16 | 0 | 19 | 0 | 19 | 0 |  | 0 | 26 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
171 | AHEJ5L | WTG 316 | Bauer | PSS-05 | Released | R8 | 10 | 253 | 253 | 253 | 0 | 2025-03-31 | 2025-04-09 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 | 11 | 0 | 29 | 0 | 38 | 0 | 40 | 0 | 38 | 0 | 35 | 0 | 42 | 0 | 20 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
172 | AHEJ5L | WTG 555 | Bauer | PSS-05 | Released | R2 | 12 | 253 | 253 | 253 | 0 | 2025-03-27 | 2025-04-06 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | 0 | 15 | 0 | 18 | 0 | 24 | 0 | 15 | 0 |  | 0 | 19 | 0 | 26 | 0 | 26 | 0 | 11 | 0 | 27 | 0 | 28 | 0 | 32 | 0 | 4 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
173 | AHEJ5L | WTG 554 | Bauer | PSS-05 | Released | R3 | 10 | 253 | 253 | 253 | 0 | 2025-03-16 | 2025-03-26 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 | 23 | 0 | 37 | 0 |  | 0 | 48 | 0 | 25 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | 0 | 43 | 0 | 48 | 0 | 8 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
174 | AHEJ5L | WTG 552 | Bauer | PSS-05 | Released | R3 | 12 | 253 | 253 | 253 | 0 | 2025-03-25 | 2025-04-03 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 |  | 0 | 26 | 0 | 25 | 0 | 29 | 0 | 25 | 0 | 25 | 0 | 21 | 0 |  | 0 | 36 | 0 | 37 | 0 | 28 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
175 | AHEJ5L | WTG 551 | Bauer | PSS-05 | Released | R3 | 9 | 199 | 199 | 199 | 0 | 2025-03-04 | 2025-03-14 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | 0 | 32 | 0 | 31 | 0 | 43 | 0 | 32 | 0 | 40 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
176 | AHEJ5L | WTG 553 | Bauer | PSS-05 | Released | R3 | 13 | 253 | 253 | 253 | 0 | 2025-03-04 | 2025-03-13 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | 0 | 22 | 0 | 34 | 0 | 31 | 0 | 23 | 0 |  | 0 | 34 | 0 | 37 | 0 | 32 | 0 | 38 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
177 | ASEJ6PL | WTG 121 | Saritha | PSS-08 | Released | R2 | 10 | 199 | 199 | 199 | 0 | 2025-02-08 | 2025-02-18 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | 0 | 23 | 0 | 23 | 0 | 32 | 0 |  | 0 | 23 | 0 | 19 | 0 | 19 | 0 | 17 | 0 |  | 0 | 22 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
178 | ASEJ6PL | WTG 123 | Bauer | PSS-08 | Released | R2 | 11 | 199 | 199 | 199 | 0 | 2025-02-08 | 2025-02-18 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | 0 | 14 | 0 |  | 0 | 18 | 18.0909 | 22 | 18.0909 | 31 | 18.0909 | 38 | 18.0909 | 38 | 18.0909 | 2 | 18.0909 | 33 | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 18.0909 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
179 | ASEJ6PL | WTG 143 | Saritha | PSS-08 | Released | R1 | 11 | 199 | 199 | 199 | 0 | 2025-02-19 | 2025-02-28 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | 0 | 11 | 0 | 15 | 0 | 12 | 0 | 8 | 0 | 27 | 0 |  | 0 | 23 | 0 |  | 0 | 6 | 0 | 1 | 0 |  | 0 |  | 0 |  | 0 | 11 | 0 | 12 | 0 | 1 | 0 | 12 | 0 | 4 | 0 | 18 | 0 |  | 0 | 12 | 0 | 22 | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 19.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
180 | ASEJ6PL | WTG 144 | Bauer | PSS-08 | Released | R2 | 10 | 253 | 253 | 253 | 0 | 2025-02-19 | 2025-02-28 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 | 37 | 25.3 | 58 | 25.3 | 45 | 25.3 | 47 | 25.3 | 39 | 0 | 27 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
181 | ASEJ6PL | WTG 145 | Bauer | PSS-08 | Released | R2 | 10 | 253 | 253 | 253 | 0 | 2025-02-12 | 2025-02-22 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 | 18 | 23 | 44 | 23 |  | 23 | 39 | 23 | 31 | 23 | 35 | 23 | 31 | 23 | 29 | 23 | 26 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
182 | ASEJ6PL | WTG 230 | Bauer | PSS-08 | Released | R4 | 13 | 303 | 303 | 303 | 0 | 2025-02-13 | 2025-02-23 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 27.5455 |  | 27.5455 |  | 27.5455 |  | 27.5455 |  | 27.5455 |  | 27.5455 |  | 27.5455 |  | 27.5455 |  | 27.5455 |  | 27.5455 |  | 27.5455 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 26 | 0 | 44 | 0 | 38 | 0 |  | 0 | 34 | 0 | 22 | 0 | 37 | 0 | 31 | 0 |  | 0 | 21 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | 0 | 25 | 0 | 11 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
183 | ARE3L | WTG 302 | Keller | PSS-08 | Released | R1 | 12 | 253 | 253 | 253 | 0 | 2025-02-23 | 2025-03-04 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | 0 | 25 | 0 | 26 | 0 | 34 | 0 | 34 | 0 |  | 0 | 31 | 0 | 31 | 0 | 33 | 0 | 27 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
184 | ARE3L | WTG 326 | Keller | PSS-08 | Released | R1 | 8 | 253 | 253 | 253 | 0 | 2025-02-16 | 2025-02-26 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 | 10 | 0 | 37 | 0 |  | 0 | 40 | 0 | 28 | 0 | 25 | 0 | 27 | 0 | 21 | 0 | 44 | 0 | 21 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
185 | ARE3L | WTG 351 | Keller | PSS-08 | Released | R3 | 7.5 | 253 | 253 | 253 | 0 | 2025-02-27 | 2025-03-08 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | 0 | 24 | 0 | 20 | 0 |  | 0 | 32 | 0 | 35 | 0 | 25 | 0 | 29 | 0 | 26 | 0 | 28 | 0 | 19 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
186 | ASEJ6PL | WTG 376 | Keller | PSS-08 | Released | R3 | 7.5 | 253 | 253 | 253 | 0 | 2025-02-15 | 2025-02-25 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | 0 | 36 | 0 | 28 | 0 | 27 | 0 | 33 | 0 |  | 0 | 34 | 0 | 15 | 0 | 30 | 0 | 31 | 0 | 2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
187 | ASEJ6PL | WTG 400 | Keller | PSS-08 | Released | R3 | 12 | 253 | 253 | 253 | 0 | 2025-02-26 | 2025-03-07 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | 0 | 3 | 0 | 7 | 0 | 10 | 0 | 16 | 0 | 13 | 0 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | 0 |  | 0 |  | 0 | 7 | 0 | 9 | 0 | 11 | 0 | 11 | 0 | 6 | 0 |  | 0 | 3 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | 0 | 4 | 0 | 10 | 0 | 8 | 0 | 3 | 0 | 10 | 0 | 2 | 0 | 7 | 0 | 7 | 0 | 7 | 0 | 11 | 0 | 12 | 0 | 11 | 0 | 9 | 0 | 8 | 0 | 4 | 0 |  | 0 | 9 | 0 | 9 | 0 | 11 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
188 | ASEJ6PL | WTG 208 | Bauer | PSS-08 | Released | R4 | 15 | 253 | 253 | 253 | 0 | 2025-02-24 | 2025-03-04 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 28.1111 |  | 28.1111 |  | 28.1111 |  | 28.1111 |  | 28.1111 |  | 28.1111 |  | 28.1111 |  | 28.1111 |  | 28.1111 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | 0 | 24 | 0 | 21 | 0 | 25 | 0 | 29 | 0 | 33 | 0 | 20 | 0 | 13 | 0 |  | 0 | 30 | 0 | 15 | 0 | 18 | 0 | 9 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
189 | ASEJ6PL | WTG 141 | Bauer | PSS-08 | Released | R4 | 13 | 253 | 253 | 253 | 0 | 2025-02-17 | 2025-02-27 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | 0 | 30 | 0 | 32 | 0 | 28 | 0 |  | 0 | 29 | 0 | 28 | 0 | 28 | 0 | 15 | 0 | 30 | 0 | 21 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
190 | ASEJ6PL | WTG 164 | Bauer | PSS-08 | Released | R4 | 12 | 378 | 378 | 378 | 0 | 2025-02-28 | 2025-03-09 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 37.8 |  | 37.8 |  | 37.8 |  | 37.8 |  | 37.8 |  | 37.8 |  | 37.8 |  | 37.8 |  | 37.8 |  | 37.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | 0 | 29 | 0 | 30 | 0 | 32 | 0 | 29 | 0 | 32 | 0 | 27 | 0 | 25 | 0 | 26 | 0 | 11 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | 0 | 6 | 0 | 10 | 0 | 17 | 0 | 8 | 0 | 19 | 0 | 18 | 0 | 23 | 0 | 11 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
191 | ARE3L | WTG 352 | Keller | PSS-08 | Released | R1 | 10 | 211 | 211 | 211 | 0 | 2025-02-25 | 2025-03-06 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 21.1 |  | 21.1 |  | 21.1 |  | 21.1 |  | 21.1 |  | 21.1 |  | 21.1 |  | 21.1 |  | 21.1 |  | 21.1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | 0 | 42 | 0 | 42 | 0 |  | 0 | 36 | 0 | 48 | 0 | 29 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
192 | ASEJ6PL | WTG 186 | Bauer | PSS-08 | Released | R4 | 10 | 253 | 253 | 253 | 0 | 2025-03-10 | 2025-03-19 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 25.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | 0 | 38 | 0 | 39 | 0 |  | 0 | 26 | 0 | 32 | 0 | 36 | 0 | 35 | 0 | 32 | 0 |  | 0 | 4 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
193 | AGE25BL | WTG 556 | Bauer | PSS-09 | Released | R1 | 11.5 | 253 | 253 | 253 | 0 | 2025-11-11 | 2025-11-20 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | 25.3 | 33 | 25.3 | 20 | 25.3 | 28 | 25.3 | 20 | 25.3 |  | 25.3 | 33 | 25.3 | 35 | 25.3 | 28 | 25.3 | 24 | 25.3 | 24 | 0 | 6 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
194 | AGE25BL | WTG 557 | Bauer | PSS-09 | Released | R1 | 11.5 | 253 | 253 | 253 | 0 | 2025-10-29 | 2025-11-07 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25.3 | 6 | 25.3 | 34 | 25.3 | 24 | 25.3 | 40 | 25.3 |  | 25.3 | 14 | 25.3 | 32 | 25.3 | 38 | 25.3 | 25 | 25.3 | 24 | 0 | 2 | 0 | 14 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Note on D69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Extra SC-50 Start 8-Jan-26 By Bauer Total Scope=252+50=353
Note on E83: Darshik Dholakiya: Keller start SC date 9-Feb 26 Additional 181

## USS SUMMARY
[5 empty] | 170 | 170 | 160 | 160 | 169 | 169 | 149 | 149 | 153 | 153 |  | 177 | 176 | 177 | 176 |  | 153 | 153 | 84 |  | 151 | 91 |  | 194 | 112 | 135 | 134 | 119 | 117 | 115 | 0 | 118 | 114
S# | PSS | SPV | Location | Feeder | Vendor | Precast readiness | [8 empty] | Vendor | USS Foundation |  |  |  | Vendor | HT Panel civil FDN |  |  | Vendor | DT Erection | BOT Erection | Location | Vendor | Electrical readiness | [6 empty] | USS Commisoning |  | Remarks
[6 empty] | 9No's Column/Loc | Vendor | Slab casting | Vendor | DT Slab Casting | Vendor | BOT Precast | Vendor | Stair Case |  | HT Excavation | HT PCC | DT Excavation | DT PCC |  | HT Panel Column Erection | HT Slab Erection | Backfilling | [5 empty] | Earthing | HT Panel erection | DT Erection | Cable Tray Foundation | Cable Tray Erection | HT/LT Cable Laying |  | Oil Filteration | Testing
1 | PSS-08 | ASEJ6PL | WTG 121 | F11 | Shreeji | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | BIPL | 2026-01-20 | 2026-01-21 | 2026-01-20 | 2026-01-21 | ShreeJi | 2026-02-01 | 2026-02-01 |  | Sachi | 2026-02-13 |  | WTG 121 | ICECUBE |  | 2026-02-25 | 2026-02-25
2 | PSS-08 | ASEJ6PL | WTG 123 | F11 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | MECC | 2025-03-03 | 2025-03-04 | 2025-03-03 | 2025-03-04 | ShreeJi | 2025-06-15 | 2025-06-15 |  | ShreeJi | 2025-05-30 |  | WTG 123 | AKSHAR | Done | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-02 | 2025-12-14 |  | 2025-12-08 | 2025-12-15
3 | PSS-08 | ASEJ6PL | WTG 143 | F11 | Shreeji | 9 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | AB INFRA | 2025-02-28 | 2025-02-28 | 2025-04-08 | 2025-04-09 | Sachi | 2025-09-05 | 2025-09-05 |  | ShreeJi | 2025-04-25 | 2025-12-22 | WTG 143 | Varsha/Akshar | Done | 2025-12-03 | 2025-06-19 | 2025-12-02 | 2025-12-03 | 2025-12-05 |  | 2025-12-07 | 2025-12-19
4 | PSS-08 | ASEJ6PL | WTG 144 | F11 | Sachi | 9 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | HBG | 2025-08-30 | 2025-11-30 | 2025-08-30 | 2025-11-30 | ShreeJi | 2025-12-06 | 2025-12-06 |  | ShreeJi | 2025-12-06 |  | WTG 144 | ICECUBE | Done | 2025-12-08 | 2025-12-08 | 2025-12-15 | 2025-12-15 | 2025-12-16 |  | 2025-12-13 | 2025-12-16
5 | PSS-08 | ASEJ6PL | WTG 145 | F11 | Shreeji | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | TEJAS | 2025-04-04 | 2025-04-05 | 2025-04-09 | 2025-04-09 | Shreeji | 2025-12-01 | 2025-12-01 |  | Shreeji | 2025-11-30 | 2025-12-22 | WTG 145 | ICECUBE | Done | 2025-12-02 | 2025-12-01 | 2025-12-11 | 2025-12-12 | 2025-12-13 |  | 2025-12-13 | 2025-12-17
6 | PSS-08 | ASEJ6PL | WTG 230 | F10 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | HBG | [11 empty] | WTG 230 | ICECUBE
7 | PSS-08 | ARE3L | WTG 302 | F13 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | SHREEJI | 2025-04-19 | 2025-04-19 | 2025-04-19 | 2025-04-19 | ShreeJi | 2025-04-21 | 2025-04-21 | Done | ShreeJi | 2025-04-24 |  | WTG 302 | ICECUBE | Done | 2025-06-14 | 2025-06-14 | 2025-07-18 | 2025-07-22 | 2025-07-25 |  | 2025-07-20 | 2025-08-22
8 | PSS-08 | ARE3L | WTG 326 | F13 | Shreeji | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | SHREEJI | 2025-04-22 | 2025-04-22 | 2025-04-22 | 2025-04-22 | ShreeJi | 2025-05-30 | 2025-05-30 | Done | ShreeJi | 2025-05-04 |  | WTG 326 | ICECUBE | Done | 2025-07-18 | 2025-06-20 | 2025-07-18 | 2025-07-20 | 2025-07-20 |  | 2025-06-22 | 2025-08-15
9 | PSS-08 | ARE3L | WTG 327 | F13 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | SHREEJI | 2025-06-24 | 2025-06-25 | 2025-06-24 | 2025-06-25 | ShreeJi | 2025-06-26 | 2025-06-26 | Done | ShreeJi | 2025-06-16 | 2025-12-24 | WTG 327 | AKSHAR | Done | 2025-07-10 | 2025-07-10 | 2025-07-22 | 2025-07-23 | 2025-07-30 |  | 2025-07-12 | 2025-08-14
10 | PSS-08 | ARE3L | WTG 351 | F13 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | SHREEJI | 2025-05-16 | 2025-05-18 | 2025-05-16 | 2025-05-18 | ShreeJi | 2025-05-26 | 2025-06-02 | Done | ShreeJi | 2025-05-26 | 2026-02-16 | WTG 351 | AKSHAR | Done | 2025-07-12 | 2025-07-12 | 2025-07-25 | 2025-07-27 | 2025-07-31 |  | 2025-07-14 | 2025-08-18
11 | PSS-08 | ASEJ6PL | WTG 376 | F12 | Sachi | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | SHREEJI | 2025-05-16 | 2025-05-17 | 2025-05-16 | 2025-05-17 | ShreeJi | 2025-05-19 | 2025-07-23 | Done | ShreeJi | 2025-05-19 |  | WTG 376 | Varsha/Akshar | Done | 2025-08-01 | 2025-06-20 | 2025-11-11 | 2025-11-11 | 2025-11-12 |  | 2025-11-12 | 2025-11-23
12 | PSS-08 | ASEJ6PL | WTG 400 | F12 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | SHREEJI | 2025-11-01 | 2025-11-02 | 2025-11-01 | 2025-11-02 | ShreeJi | 2025-11-03 | 2025-11-04 | Done |  | 2025-11-05 | 2025-12-23 | WTG 400 | ICECUBE | Done | 2025-11-07 | 2025-11-07 | 2025-11-12 | 2025-11-13 | 2025-11-14 |  | 2025-11-13 | 2025-11-14
13 | PSS-08 | ASEJ6PL | WTG 208 | F10 | Shreeji | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | DNC | 2025-09-06 | 2025-09-06 | 2025-09-06 | 2025-09-06 | Sachi | 2026-02-27 | 2026-02-27 |  | Shreeji | 2026-02-25 |  | WTG 208 | ICECUBE
14 | PSS-08 | ASEJ6PL | WTG 141 | F10 | Shreeji | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | DNC | 2025-07-26 | 2025-07-27 | 2025-07-26 | 2025-07-27 | Shreeji | 2025-08-07 | 2025-08-07 |  | ShreeJi | 2025-07-29 |  | WTG 141 | ICECUBE |  | 2026-02-17 | 2026-02-17
15 | PSS-08 | ASEJ6PL | WTG 164 | F10 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | [12 empty] | WTG 164 | ICECUBE
16 | PSS-08 | ARE3L | WTG 352 | F13 | Shreeji | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | SHREEJI | 2025-04-28 | 2025-04-28 | 2025-04-28 | 2025-04-28 | Shreeji | 2025-05-01 | 2025-06-04 | Done | ShreeJi | 2025-05-01 | 2025-12-24 | WTG 352 | Varsha | Done | 2025-06-15 | 2025-06-15 | 2025-07-16 | 2025-07-18 | 2025-07-20 |  | 2025-07-11 | 2025-08-18
17 | PSS-08 | ASEJ6PL | WTG 186 | F10 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | DNC | 2025-08-29 | 2025-08-31 | 2025-09-29 | 2025-08-31 | sachi | 2025-09-01 | 2025-09-02 |  |  | 2025-09-01 |  | WTG 186 | AKSHAR |  | 2026-01-04 | 2026-01-04 | 2026-02-19 | 2026-02-20 | 2026-02-21 |  | 2026-01-22
18 | PSS-05 | AHEJ5L | WTG 177 | F04 | Shreeji | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | MSC | 2025-10-09 | 2025-10-11 | 2025-10-09 | 2025-10-11 | sachi | 2025-10-14 | 2025-10-15 | Done | SHREEJI | 2025-10-15 | 2025-12-09 | WTG 177 | AKSHAR | Done | 2025-10-30 | 2025-10-18 | 2025-10-25 | 2025-10-26 | 2025-10-29 |  | 2025-10-26 | 2025-10-31
19 | PSS-05 | AHEJ5L | WTG 199 | F04 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | MSC | 2025-10-08 | 2025-10-10 | 2025-10-08 | 2025-10-10 | Sachi | 2025-10-17 | 2025-10-17 | Done | ShreeJi | 2025-10-16 | 2025-12-19 | WTG 199 | ICECUBE | Done | 2025-10-24 | 2025-10-25 | 2025-10-28 | 2025-10-29 | 2025-10-29 |  | 2025-10-30 | 2025-10-31
20 | PSS-05 | AHEJ5L | WTG 154 | F02 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | MSC | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | Shreeji | 2025-11-19 | 2025-11-19 | Done | SHREEJI | 2025-11-24 | 2026-02-03 | WTG 154 | Pratibha | Done | 2025-11-26 | 2025-11-25 | 2025-11-27 | 2025-11-28 | 2025-11-29 |  | 2025-11-27 | 2025-11-30
21 | PSS-05 | AHEJ5L | WTG 002 | F01 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | MSC | 2025-04-14 | 2025-04-15 | 2025-04-14 | 2025-04-15 | Sachi | 2025-05-24 | 2025-06-05 | Done | ShreeJi | 2025-05-22 | 2025-10-27 | WTG 002 | ICECUBE | Done | 2025-09-22 | 2025-09-20 | 2025-09-22 | 2025-09-23 | 2025-09-30 |  | 2025-10-15 | 2025-10-23
22 | PSS-05 | AHEJ5L | WTG 133 | F02 | Shreeji | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | MSC | 2025-10-09 | 2025-10-11 | 2025-10-09 | 2025-10-11 | Shreeji | 2025-10-14 | 2025-10-14 | Done | ShreeJi | 2025-10-12 | 2025-10-22 | WTG 133 | Pratibha | Done | 2025-10-30 | 2025-10-22 | 2025-11-01 | 2025-11-02 | 2025-11-03 |  | 2025-10-31 | 2025-11-15
23 | PSS-05 | AHEJ5L | WTG 290 | F07 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | AB INFRA | 2025-03-14 | 2025-03-16 | 2025-03-14 | 2025-03-16 | ShreeJi | 2025-05-03 | 2025-05-03 | Done | ShreeJi | 2025-04-19 | 2025-10-18 | WTG 290 | AKSHAR | Done | 2025-08-13 | 2025-08-13 | 2025-09-08 | 2025-09-10 | 2025-09-15 |  | 2025-09-15 | 2025-09-21
24 | PSS-05 | AHEJ5L | WTG 315 | F07 | Sachi | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | SHREERAM | 2025-07-24 | 2025-07-25 | 2025-07-22 | 2025-07-24 | sachi | 2025-07-29 | 2025-07-30 | Done | sachi | 2025-04-19 | 2025-10-22 | WTG 315 | AKSHAR | Done | 2025-09-14 | 2025-08-12 | 2025-09-15 | 2025-09-17 | 2025-09-18 |  | 2025-09-14 | 2025-09-20
25 | PSS-05 | AHEJ5L | WTG 266 | F06 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | C&B | 2025-03-24 | 2025-03-25 | 2025-03-24 | 2025-03-25 | ShreeJi | 2025-05-02 | 2025-06-09 | Done | ShreeJi | 2025-04-19 | 2025-10-18 | WTG 266 | AKSHAR | Done | 2025-08-11 | 2025-08-11 | 2025-09-09 | 2025-09-10 | 2025-09-18 |  | 2025-08-19 | 2025-09-19
26 | PSS-05 | AHEJ5L | WTG 221 | F04 | Shreeji | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | MSC | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | sachi | 2025-11-25 | 2025-11-28 | Done | ShreeJi | 2025-11-26 | 2025-12-20 | WTG 221 | ICECUBE | Done | 2025-12-02 | 2025-11-27 | 2025-02-01 | 2025-12-02 | 2025-12-02 |  | 2025-11-29 | 2025-12-03
27 | PSS-05 | AHEJ5L | WTG 243 | F06 | Shreeji | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | MSC | 2025-04-12 | 2025-04-13 | 2025-04-12 | 2025-04-13 | Sachi | 2025-05-03 | 2025-05-23 | Done | ShreeJi | 2025-04-19 | 2025-10-08 | WTG 243 | AKSHAR | Done | 2025-08-13 | 2025-08-13 | 2025-09-15 | 2025-09-17 | 2025-09-18 |  | 2025-09-14 | 2025-09-18
28 | PSS-05 | AHEJ5L | WTG 131 | F03 | Sachi | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | MSC | 2025-10-19 | 2025-10-27 | 2025-10-26 | 2025-10-27 | sachi | 2025-10-28 | 2025-10-28 | Done | ShreeJi | 2025-10-29 | 2025-11-26 | WTG 131 | ICECUBE | Done | 2025-11-01 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 |  | 2025-11-04 | 2025-11-06
29 | PSS-05 | AHEJ5L | WTG 132 | F01 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | MSC | 2025-05-01 | 2025-05-02 | 2025-05-01 | 2025-05-02 | Sachi | 2025-10-06 | 2025-10-07 | Done | ShreeJi | 2025-09-02 | 2025-10-07 | WTG 132 | ICECUBE | Done | 2025-10-12 | 2025-10-13 | 2025-10-01 | 2025-10-03 | 2025-10-15 |  | 2025-10-14 | 2025-10-23
30 | PSS-05 | AHEJ5L | WTG 152 | F02 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | MSC | 2025-06-01 | 2025-06-06 | 2025-06-01 | 2025-06-06 | Sachi | 2025-06-14 | 2025-06-14 | Done | ShreeJi | 2025-06-11 | 2025-11-28 | WTG 152 | AKSHAR | Done | 2025-10-28 | 2025-10-28 | 2025-11-14 | 2025-11-15 | 2025-11-15 |  | 2025-10-29 | 2025-11-05
31 | PSS-05 | AHEJ5L | WTG 153 | F02 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | MSC | 2025-06-02 | 2025-06-04 | 2025-06-02 | 2025-06-04 | Sachi | 2025-06-06 | 2025-09-29 | Done | ShreeJi | 2025-07-31 | 2025-10-07 | WTG 153 | AKSHAR | Done | 2025-10-13 | 2025-10-08 | 2025-10-15 | 2025-10-16 | 2025-10-17 |  | 2025-10-14 | 2025-10-24
32 | PSS-05 | AHEJ5L | WTG 155 | F05 | Sachi | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | MSC | 2025-09-25 | 2025-10-08 | 2025-09-25 | 2025-10-08 | Sachi | 2025-10-11 | 2025-10-11 | Done | ShreeJi | 2025-10-11 | 2025-10-28 | WTG 155 | ICECUBE | Done | 2025-10-16 | 2025-10-16 | 2025-10-29 | 2025-10-30 | 2025-11-01 |  | 2025-10-24 | 2025-11-04
33 | PSS-05 | AHEJ5L | WTG 156 | F05 | Sachi | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | MSC | 2025-05-26 | 2025-05-26 | 2025-05-26 | 2025-05-26 | Sachi | 2025-05-30 | 2025-05-31 | Done | ShreeJi | 2025-05-28 | 2025-10-23 | WTG 156 | Pratibha | Done | 2025-10-03 | 2025-10-03 | 2025-10-23 | 2025-10-24 | 2025-10-26 |  | 2025-10-13 | 2025-10-17
34 | PSS-05 | AHEJ5L | WTG 175 | F03 | Shreeji | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | MSC | 2025-05-24 | 2025-05-24 | 2025-05-24 | 2025-05-24 | Sachi | 2025-05-27 | 2025-05-27 | Done | ShreeJi | 2025-05-28 | 2025-11-26 | WTG 175 | AKSHAR | Done | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-02 | 2025-11-03 |  | 2025-11-03 | 2025-11-05
35 | PSS-05 | AHEJ5L | WTG 176 | F03 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | MSC | 2025-05-01 | 2025-05-02 | 2025-05-01 | 2025-05-02 | Sachi | 2025-05-28 | 2025-06-05 | Done | ShreeJi | 2025-05-23 | 2025-11-14 | WTG 176 | AKSHAR | Done | 2025-10-09 | 2025-10-11 | 2025-10-13 | 2025-10-14 | 2025-10-26 |  | 2025-10-14 | 2025-10-27
36 | PSS-05 | AHEJ5L | WTG 178 | F04 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | MSC | 2025-06-20 | 2025-06-21 | 2025-06-20 | 2025-06-21 | Sachi | 2025-08-05 | 2025-08-05 | Done | sachi | 2025-07-29 | 2025-11-22 | WTG 178 | ICECUBE | Done | 2025-10-06 | 2025-09-22 | 2025-09-29 | 2025-09-30 | 2025-10-01 |  | 2025-10-13 | 2025-10-18
37 | PSS-05 | AHEJ5L | WTG 179 | F05 | Sachi | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | MSC | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-05-30 | ShreeJi | 2025-06-13 | 2025-06-13 | Done | ShreeJi | 2025-06-13 | 2025-10-23 | WTG 179 | AKSHAR | Done | 2025-10-08 | 2025-09-27 | 2025-10-05 | 2025-10-06 | 2025-10-09 |  | 2025-10-09 | 2025-10-13
38 | PSS-05 | AHEJ5L | WTG 197 | F03 | Sachi | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | MSC | 2025-05-07 | 2025-05-18 | 2025-05-07 | 2025-05-18 | Sachi | 2025-05-21 | 2025-06-06 | Done | ShreeJi | 2025-07-31 | 2025-11-25 | WTG 197 | AKSHAR | Done | 2025-11-12 | 2025-11-12 | 2025-11-15 | 2025-11-16 | 2025-11-17 |  | 2025-11-15 | 2025-11-17
39 | PSS-05 | AHEJ5L | WTG 198 | F03 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | MSC | 2025-11-18 | 2025-11-18 | 2025-11-18 | 2025-11-18 | SHREEJI | 2025-11-25 | 2025-11-25 | Done | ShreeJi | 2025-11-29 | 2025-12-19 | WTG 198 | Pratibha | Done | 2025-11-30 | 2025-11-30 | 2025-12-04 | 2025-12-05 | 2025-12-06 |  | 2025-12-03 | 2025-12-06
40 | PSS-05 | AHEJ5L | WTG 200 | F04 | Sachi | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | MSC | 2025-04-14 | 2025-04-15 | 2025-04-14 | 2025-04-15 | ShreeJi | 2025-06-11 | 2025-06-13 | Done | ShreeJi | 2025-04-20 | 2025-10-28 | WTG 200 | ICECUBE | Done | 2025-10-13 | 2025-09-22 | 2025-09-18 | 2025-09-20 | 2025-09-22 |  | 2025-10-12 | 2025-10-18
41 | PSS-05 | AHEJ5L | WTG 201 | F08 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | ODHAV | 2025-05-06 | 2025-05-23 | 2025-05-06 | 2025-05-23 | Sachi | 2025-05-26 | 2025-06-06 | Done | ShreeJi | 2025-09-16 | 2025-11-07 | WTG 201 | ICECUBE | Done | 2025-09-16 | 2025-09-16 | 2025-09-17 | 2025-09-19 | 2025-09-22 |  | 2025-10-11 | 2025-10-18
42 | PSS-05 | AHEJ5L | WTG 222 | F06 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | MSC | 2025-04-15 | 2025-04-16 | 2025-04-15 | 2025-04-16 | Sachi | 2025-05-03 | 2025-05-23 | Done | ShreeJi | 2025-04-19 | 2025-10-08 | WTG 222 | AKSHAR | Done | 2025-08-11 | 2025-08-11 | 2025-09-16 | 2025-09-18 | 2025-09-19 |  | 2025-08-19 | 2025-09-18
43 | PSS-05 | AHEJ5L | WTG 223 | F08 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | MSC | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | ShreeJi | 2025-05-22 | 2025-05-22 | Done | ShreeJi | 2025-05-20 | 2025-10-30 | WTG 223 | ICECUBE | Done | 2025-10-11 | 2025-10-11 | 2025-10-18 | 2025-10-19 | 2025-10-19 |  | 2025-10-13 | 2025-10-19
44 | PSS-05 | AHEJ5L | WTG 244 | F06 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | MSC | 2025-06-04 | 2025-06-07 | 2025-06-04 | 2025-06-07 | Sachi | 2025-08-07 | 2025-08-07 | Done | ShreeJi | 2025-06-09 | 2025-10-08 | WTG 244 | AKSHAR | Done | 2025-08-13 | 2025-08-15 | 2025-09-16 | 2025-09-18 | 2025-09-19 |  | 2025-08-24 | 2025-09-20
45 | PSS-05 | AHEJ5L | WTG 245 | F08 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | AB INFRA | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | ShreeJi | 2025-05-08 | 2025-06-10 | Done | ShreeJi | 2025-06-04 | 2025-10-31 | WTG 245 | AKSHAR | Done | 2025-09-29 | 2025-08-11 | 2025-10-08 | 2025-10-09 | 2025-10-09 |  | 2025-10-05 | 2025-10-09
46 | PSS-05 | AHEJ5L | WTG 267 | F06 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | MSC | 2025-06-09 | 2025-06-10 | 2025-06-09 | 2025-06-10 | ShreeJi | 2025-06-12 | 2025-06-12 | Done | ShreeJi | 2025-06-11 | 2025-10-11 | WTG 267 | AKSHAR | Done | 2025-08-15 | 2025-08-15 | 2025-09-15 | 2025-09-18 | 2025-09-19 |  | 2025-09-14 | 2025-09-18
47 | PSS-05 | AHEJ5L | WTG 268 | F08 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | MSC | 2025-06-04 | 2025-06-07 | 2025-06-04 | 2025-06-07 | ShreeJi | 2025-06-11 | 2025-08-29 | Done | ShreeJi | 2025-06-09 | 2025-10-18 | WTG 268 | ICECUBE | Done | 2025-09-13 | 2025-09-13 | 2025-09-19 | 2025-09-21 | 2025-09-30 |  | 2025-10-08 | 2025-10-12
48 | PSS-05 | AHEJ5L | WTG 291 | F07 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | MSC | 2025-05-12 | 2025-05-13 | 2025-05-12 | 2025-05-13 | ShreeJi | 2025-05-19 | 2025-05-23 | Done | ShreeJi | 2025-05-14 | 2025-10-12 | WTG 291 | AKSHAR | Done | 2025-08-13 | 2025-08-13 | 2025-08-30 | 2025-08-30 | 2025-08-31 |  | 2025-09-02 | 2025-09-18
49 | PSS-05 | AHEJ5L | WTG 292 | F08 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | HBG | 2025-05-12 | 2025-05-13 | 2025-05-12 | 2025-05-13 | Sachi | 2025-05-26 | 2025-06-06 | Done | Sachi | 2025-05-27 | 2025-10-31 | WTG 292 | AKSHAR | Done | 2025-09-15 | 2025-09-15 | 2025-09-30 | 2025-10-01 | 2025-10-01 |  | 2025-10-05 | 2025-10-13
50 | PSS-05 | AHEJ5L | WTG 314 | F07 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | MSC | 2025-06-06 | 2025-06-08 | 2025-06-06 | 2025-06-08 | Sachi | 2025-06-13 | 2025-06-13 | Done | ShreeJi | 2025-10-13 | 2025-10-19 | WTG 314 | AKSHAR | Done | 2025-10-05 | 2025-10-17 | 2025-10-25 | 2025-10-26 | 2025-10-27 |  | 2025-10-24 | 2025-10-30
51 | PSS-05 | AHEJ5L | WTG 316 | F07 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | MSC | 2025-08-10 | 2025-08-11 | 2025-08-10 | 2025-08-11 | Sachi | 2025-08-16 | 2025-08-16 | Done | sachi | 2025-08-29 | 2025-10-07 | WTG 316 | ICECUBE | Done | 2025-09-21 | 2025-09-21 | 2025-10-29 | 2025-10-30 | 2025-10-30 |  | 2025-10-08 | 2025-10-10
52 | PSS-05 | AHEJ5L | WTG 555 | F05 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | MSC | 2026-01-13 | 2026-01-14 | 2026-01-13 | 2026-01-14 | Sachi | 2026-01-20 | 2026-01-20 | Done | SACHI | 2026-01-20 | 2026-02-16 | WTG 555 | ICECUBE |  | 2026-02-08 | 2026-02-08 | 2026-02-16 | 2026-02-17 | 2026-02-17 |  | 2026-02-17 | 2026-02-17
53 | PSS-05 | AHEJ5L | WTG 554 | F05 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | MSC | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-31 | Sachi | 2025-11-14 | 2025-11-15 | Done | SHREEJI | 2025-11-24 | 2025-11-28 | WTG 554 | ICECUBE | Done | 2025-11-27 | 2025-11-27 | 2025-12-05 | 2025-12-06 | 2025-12-07 |  | 2025-12-10 | 2025-12-12
54 | PSS-05 | AHEJ5L | WTG 552 | F01 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | DNC | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | Sachi | 2025-12-31 | 2025-12-31 | Done | Sachi | 2025-12-31 | 2026-02-02 | WTG 552 | Pratibha | Done | 2026-01-10 | 2026-01-07 | 2026-01-10 | 2026-01-12 | 2026-01-13 |  | 2026-01-15 | 2026-01-17
55 | PSS-05 | AHEJ5L | WTG 551 | F01 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | MSC | 2026-02-01 | 2026-02-02 | 2026-02-01 | 2026-02-02 | Sachi | 2026-02-03 | 2026-02-03 | Done | Sachi | 2026-02-03 | 2026-02-16 | WTG 551 | ICECUBE |  | 2026-02-15 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-17 |  | 2026-02-17 | 2026-02-17
56 | PSS-05 | AHEJ5L | WTG 553 | F01 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | MSC | 2026-01-10 | 2026-01-11 | 2026-01-10 | 2026-01-11 | Shreeji | 2026-02-03 | 2026-02-03 | Done | Sachi | 2026-02-03 | 2026-02-03 | WTG 553 | ICECUBE |  | 2026-02-07 | 2026-02-07 | 2026-02-16 | 2026-02-17 | 2026-02-17 |  | 2026-02-17 | 2026-02-18
57 | PSS-11 | AGE25CL | WTG 329 | F01 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | DNC | 2025-11-29 | 2025-12-02 | 2025-11-29 | 2025-12-02 | Shreeji | 2025-12-04 | 2025-12-04 | Done | Shreeji | 2025-12-04 | 2025-12-05 | WTG 329 | AKSHAR | Done | 2025-12-06 | 2025-12-06 | 2025-12-25 | 2025-12-26 | 2026-12-29 |  | 2025-12-15 | 2025-12-26
58 | PSS-11 | AGE25CL | WTG 353 | F01 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | SHREEJI | 2025-11-11 | 2025-11-11 | 2025-11-11 | 2025-11-11 | Shreeji | 2025-11-12 | 2025-11-12 | Done | Shreeji | 2025-11-18 | 2025-11-29 | WTG 353 | AKSHAR | Done | 2025-11-23 | 2025-11-23 | 2025-12-01 | 2025-12-01 | 2025-12-02 |  | 2025-11-30 | 2025-12-02
59 | PSS-11 | AGE25CL | WTG 354 | F01 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | SHREERAM | 2025-11-25 | 2025-11-29 | 2025-11-25 | 2025-11-29 | Shreeji | 2025-12-02 | 2025-12-02 | Done | Shreeji | 2025-12-02 | 2025-12-29 | WTG 354 | AKSHAR | Done | 2025-12-05 | 2025-12-05 | 2026-01-07 | 2026-01-09 | 2026-01-11 |  | 2025-12-16 | 2025-12-27
60 | PSS-14 | AGE25CL | WTG 373 | F13 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Shreeji | 1 | SHREEJI | 2025-10-31 | 2025-11-02 | 2025-10-31 | 2025-11-02 | Shreeji | 2026-01-16 | 2026-01-16 |  | Shreeji | 2026-01-15 |  | WTG 373 | AKSHAR |  | 2026-01-21 | 2026-01-21
61 | PSS-12 | AGE26AL | WTG 377 | F01 | Shreeji | 9 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | SHREEJI | 2026-01-10 | 2026-01-11 | 2026-01-10 | 2026-01-11 | SACHI | 2026-01-14 | 2026-01-14 |  | Sachi | 2026-01-16 |  | WTG 377 | ICECUBE | Done | 2026-01-24 | 2026-01-24 | 2026-02-11 | 2026-02-12 | 2026-02-24 |  | 2026-02-02 | 2026-02-04
62 | PSS-11 | AGE25CL | WTG 378 | F01 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | BHAVANI | 2025-08-10 | 2025-08-10 | 2025-08-10 | 2025-08-10 | SHREEJI | 2025-11-11 | 2025-11-11 | Done | Shreeji | 2025-11-08 | 2025-12-04 | WTG 378 | AKSHAR | Done | 2025-11-13 | 2025-11-13 | 2025-11-22 | 2025-11-23 | 2025-11-23 |  | 2025-11-23 | 2025-11-24
63 | PSS-11 | AGE25CL | WTG 379 | F02 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | SHREEJI | 2025-11-03 | 2025-11-04 | 2025-11-03 | 2025-11-04 | SACHI | 2025-11-07 | 2025-11-08 | Done | Shreeji | 2025-11-08 | 2025-12-27 | WTG 379 | AKSHAR | Done | 2025-11-13 | 2025-11-13 | 2025-12-09 | 2025-12-10 | 2025-12-10 |  | 2025-11-18 | 2025-12-10
64 | PSS-11 | AGE25CL | WTG 328 | F01 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | SHREEJI | 2025-11-26 | 2025-11-27 | 2025-11-26 | 2025-11-27 | Shreeji | 2025-12-01 | 2025-12-01 | Done | Shreeji | 2025-11-29 | 2025-12-29 | WTG 328 | AKSHAR | Done | 2025-12-03 | 2025-12-03 | 2025-12-07 | 2025-12-08 | 2025-12-17 |  | 2025-12-13 | 2025-12-18
65 | PSS-14 | AGE25CL | WTG 399 | F14 | Shreeji | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | BHAVANI | 2025-11-17 | 2025-11-18 | 2025-11-17 | 2025-11-18 | SACHI | 2025-12-10 | 2026-01-06 |  | Sachi | 2026-01-06 |  | WTG 399 | ICECUBE |  | 2026-02-02 | 2026-02-02 | 2026-02-18 | 2026-02-19 |  |  | 2026-02-07
66 | PSS-12 | AGE26AL | WTG 401 | F01 | Shreeji | 9 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | MSC | 2025-10-01 | 2025-10-03 | 2025-10-01 | 2025-10-03 | SACHI | 2026-01-07 | 2026-01-10 |  | Shreeji | 2026-12-31 |  | WTG 401 | AKSHAR | Done | 2026-01-15 | 2026-12-31 | 2026-01-11 | 2026-01-12 | 2026-01-13 |  | 2026-01-09 | 2026-01-17
67 | PSS-14 | AGE25CL | WTG 424 | F14 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Shreeji | 1 | MSC | 2026-12-30 | 2026-12-31 | 2026-12-30 | 2026-12-31 | SACHI | 2026-02-02 | 2026-02-02 |  | Sachi | 2026-02-02 |  | WTG 424 | ICECUBE |  | 2026-02-21 | 2026-02-21 | 2026-02-25
68 | PSS-14 | AGE25CL | WTG 425 | F14 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Shreeji | 1 | SHREEJI | 2025-12-06 | 2025-12-07 | 2025-12-06 | 2025-12-07 | Sachi | 2026-01-17 | 2026-01-17 |  | Sachi | 2026-01-19 |  | WTG 425 | ICECUBE |  | 2026-02-23 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26
69 | PSS-12 | AGE26AL | WTG 426 | F01 | Shreeji | 9 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | MSC | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-20 | Sachi | 2026-01-22 | 2026-01-22 |  | Shreeji | 2026-01-23 |  | WTG 426 | ICECUBE | Done | 2026-01-27 | 2026-01-27 | 2026-02-09 | 2026-02-10 | 2026-02-20 |  | 2026-02-01 | 2026-02-03
70 | PSS-12 | AGE26AL | WTG 427 | F02 | Shreeji | 9 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | SHREERAM | 2025-11-17 | 2025-12-13 | 2025-11-17 | 2025-12-13 | Shreeji | 2026-01-13 | 2026-01-13 |  | Shreeji | 2026-01-13 |  | WTG 427 | ICECUBE | Done | 2026-01-19 | 2026-01-18 | 2026-01-27 | 2026-01-28 | 2026-02-04 |  | 2026-01-20 | 2026-01-26
71 | PSS-14 | AGE25CL | WTG 448 | F14 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Shreeji | 1 | SHREEJI | 2025-11-25 | 2025-11-26 | 2025-11-25 | 2025-11-26 | Sachi | 2026-01-31 | 2026-01-31 |  | Shreeji | 2026-01-27 |  | WTG 448 | AKSHAR |  | 2026-02-22 | 2026-02-22
72 | PSS-14 | AGE25CL | WTG 449 | F14 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Shreeji | 1 | SHREEJI | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-19 | SACHI | 2026-01-23 | 2026-01-23 |  | Shreeji | 2026-01-24 |  | WTG 449 | AKSHAR |  | 2026-02-22 | 2026-02-22
73 | PSS-14 | AGE25CL | WTG 450 | F15 | Shreeji | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | MSC | 2026-01-23 | 2026-01-24 | 2026-01-23 | 2026-01-24 | SACHI | 2026-02-04 | 2026-02-04 |  | Sachi | 2026-02-05 |  | WTG 450 | ICECUBE |  | 2026-02-25 | 2026-02-25 | 2026-02-25
74 | PSS-14 | AGE25CL | WTG 423 | F13 | Shreeji | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | SHREEJI | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-04 | Shreeji | 2025-12-12 | 2025-12-12 |  | Shreeji | 2026-01-16 |  | WTG 423 | AKSHAR |  | 2026-01-21 | 2026-01-21 |  |  |  |  | 2026-02-24
75 | PSS-14 | AGE25CL | WTG 398 | F13 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Shreeji | 1 | BHAVANI | 2025-07-08 | 2025-07-09 | 2025-07-08 | 2025-07-09 | SACHI | 2026-01-23 | 2026-01-23 |  | SACHI | 2026-01-23 |  | WTG 398 | ICECUBE |  | 2026-02-02 | 2026-02-02 | 2026-02-17 | 2026-02-18
76 | PSS-11 | AGE25CL | WTG 233A | F08 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | MSC | 2025-12-29 | 2025-12-30 | 2025-12-29 | 2025-12-30 | Sachi | 2026-01-03 | 2026-01-09 | Done | Shreeji | 2026-01-09 | 2026-01-24 | WTG 233A | ICECUBE | Done | 2026-01-11 | 2026-01-11 | 2026-01-17 | 2026-01-18 | 2026-01-17 |  | 2026-01-13 | 2026-01-16
77 | PSS-11 | AGE25CL | WTG 380 | F02 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | BHAVANI | 2025-11-21 | 2025-11-24 | 2025-11-21 | 2025-11-24 | Sachi | 2025-12-04 | 2025-12-06 | Done | Shreeji | 2025-12-17 | 2025-12-31 | WTG 380 | AKSHAR | Done | 2025-12-18 | 2025-12-18 | 2025-12-29 | 2026-01-01 | 2026-12-02 |  | 2025-12-23 | 2025-12-29
78 | PSS-11 | AGE25CL | WTG 381 | F07 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | BHAVANI | 2025-04-15 | 2025-05-18 | 2025-04-15 | 2025-05-18 | Shreeji | 2025-05-24 | 2025-11-19 | Done | Shreeji | 2025-05-22 | 2025-12-18 | WTG 381 | ICECUBE | Done | 2025-11-20 | 2025-11-20 | 2025-11-23 | 2025-11-24 | 2025-11-25 |  | 2025-11-24 | 2025-12-07
79 | PSS-11 | AGE25CL | WTG 382 | F07 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | SVRE | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | Sachi | 2025-05-08 | 2025-08-11 | Done | Shreeji | 2025-10-31 | 2025-12-18 | WTG 382 | ICECUBE | Done | 2025-10-10 | 2025-11-07 | 2025-11-07 | 2025-11-08 | 2025-11-23 |  | 2025-11-10 | 2025-11-24
80 | PSS-11 | AGE25CL | WTG 403 | F02 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Shreeji | 1 | ODHAV | 2025-12-09 | 2025-12-10 | 2025-12-09 | 2025-12-10 | Shreeji | 2025-12-19 | 2025-12-19 | Done | Shreeji | 2025-12-19 | 2026-01-26 | WTG 403 | AKSHAR | Done | 2025-12-22 | 2025-12-22 | 2026-01-09 | 2026-01-10 | 2026-01-13 |  | 2025-12-25 | 2026-01-07
81 | PSS-11 | AGE25CL | WTG 404 | F02 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | SVRE | 2025-06-05 | 2025-06-09 | 2025-06-05 | 2025-06-09 | Sachi | 2025-11-19 | 2025-11-19 | Done | Shreeji | 2025-11-22 | 2026-01-10 | WTG 404 | AKSHAR | Done | 2025-11-24 | 2025-11-24 | 2025-12-01 | 2025-12-02 | 2025-12-02 |  | 2025-12-02 | 2025-12-03
82 | PSS-11 | AGE25CL | WTG 405 | F02 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | ODHAV | 2025-06-01 | 2025-06-02 | 2025-06-01 | 2025-06-02 | ShreeJi | 2025-11-17 | 2025-11-21 | Done | ShreeJi | 2025-11-22 | 2026-01-26 | WTG 405 | AKSHAR | Done | 2025-11-26 | 2025-11-26 | 2025-12-18 | 2025-12-19 | 2025-12-29 |  | 2025-12-16 | 2025-12-20
83 | PSS-11 | AGE25CL | WTG 406 | F07 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | BHAVANI | 2025-04-30 | 2025-05-01 | 2025-04-30 | 2025-05-01 | Shreeji | 2025-05-05 | 2025-11-23 | Done | ShreeJi | 2025-11-27 | 2025-12-18 | WTG 406 | ICECUBE | Done | 2025-11-30 | 2025-11-30 | 2025-12-05 | 2025-12-06 | 2025-12-07 |  | 2025-12-10 | 2025-12-11
84 | PSS-11 | AGE25CL | WTG 407 | F07 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Shreeji | 1 | BHAVANI | 2025-11-28 | 2025-12-02 | 2025-11-28 | 2025-12-02 | Sachi | 2025-12-02 | 2025-12-03 | Done | Shreeji | 2025-12-08 | 2025-12-18 | WTG 407 | ICECUBE | Done | 2025-12-10 | 2025-12-10 | 2025-12-25 | 2025-12-26 | 2025-12-27 |  | 2025-12-19 | 2025-12-29
85 | PSS-11 | AGE25CL | WTG 429 | F03 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | ODHAV | 2025-12-07 | 2025-12-09 | 2025-12-07 | 2025-12-09 | Shreeji | 2025-12-22 | 2025-12-22 | Done | Shreeji | 2025-12-22 | 2026-01-28 | WTG 429 | ICECUBE | Done | 2025-12-23 | 2025-12-23 | 2026-01-08 | 2026-01-09 | 2026-01-12 |  | 2025-12-26 | 2026-01-08
86 | PSS-11 | AGE25CL | WTG 430 | F03 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Shreeji | 1 | SHREERAM | 2025-10-09 | 2025-10-15 | 2025-10-09 | 2025-10-15 | Sachi | 2025-12-13 | 2025-12-13 | Done | Sachi | 2025-12-25 | 2026-01-28 | WTG 430 | AKSHAR | Done | 2025-12-26 | 2025-12-26 | 2026-01-02 | 2026-01-05 | 2026-01-10 |  | 2025-12-30 | 2025-12-31
87 | PSS-11 | AGE25CL | WTG 431 | F03 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Shreeji | 1 | SHREEJI | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-04 | Shreeji | 2025-12-09 | 2025-12-09 | Done | Shreeji | 2025-12-09 |  | WTG 431 | AKSHAR | Done | 2025-12-12 | 2025-12-11 | 2025-12-20 | 2025-12-21 | 2025-12-24 |  | 2025-12-17 | 2025-12-22
88 | PSS-11 | AGE25CL | WTG 432 | F07 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | MSC | 2025-11-29 | 2025-11-30 | 2025-11-29 | 2025-11-30 | Sachi | 2025-12-03 | 2025-12-03 | Done | Shreeji | 2025-12-11 | 2026-01-31 | WTG 432 | ICECUBE | Done | 2025-12-12 | 2025-12-12 | 2026-01-03 | 2026-01-04 | 2026-01-05 |  | 2025-12-19 | 2025-12-28
89 | PSS-11 | AGE25CL | WTG 433 | F08 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | SHREEJI | 2025-11-23 | 2025-11-24 | 2025-11-23 | 2025-11-24 | Sachi | 2025-12-22 | 2025-12-22 | Done | Sachi | 2025-12-22 | 2026-01-24 | WTG 433 | AKSHAR | Done | 2025-12-25 | 2025-12-25 | 2025-12-27 | 2026-01-01 | 2026-12-02 |  | 2025-12-26 | 2026-01-01
90 | PSS-11 | AGE25CL | WTG 454 | F03 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | SHREEJI | 2025-10-25 | 2025-10-27 | 2025-10-25 | 2025-11-23 | Sachi | 2025-12-09 | 2025-12-28 | Done | Sachi | 2025-12-29 | 2026-01-29 | WTG 454 | AERIS | Done | 2026-01-01 | 2026-01-03 | 2026-01-17 | 2026-01-18 | 2026-01-20 |  | 2026-01-05 | 2026-01-16
91 | PSS-11 | AGE25CL | WTG 455 | F03 | Sachi | 9 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | Shreeji | 1 | SHREEJI | 2025-11-23 | 2025-11-24 | 2025-11-23 | 2025-11-24 | Sachi | 2025-12-12 | 2025-12-20 | Done | Shreeji | 2025-12-20 | 2026-01-12 | WTG 455 | AERIS | Done | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-30 | 2025-12-30 |  | 2025-12-25 | 2026-01-08
92 | PSS-11 | AGE25CL | WTG 456 | F04 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | SHREEJI | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | Sachi | 2025-11-17 | 2025-12-06 | Done | Shreeji | 2025-11-10 | 2026-01-10 | WTG 456 | AERIS | Done | 2025-12-09 | 2025-12-09 | 2025-12-12 | 2025-12-13 | 2025-12-24 |  | 2025-12-20 | 2026-01-07
93 | PSS-11 | AGE25CL | WTG 479 | F04 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Shreeji | 1 | SHREEJI | 2025-10-29 | 2025-10-31 | 2025-10-29 | 2025-10-31 | SHREEJI | 2025-11-06 | 2025-11-06 | Done | Shreeji | 2025-11-04 | 2026-01-29 | WTG 479 | Pratibha | Done | 2025-11-30 | 2025-11-13 | 2025-12-22 | 2025-12-27 | 2025-12-31 |  | 2025-11-20 | 2025-12-29
94 | PSS-11 | AGE25CL | WTG 480 | F04 | Sachi | 9 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | MSC | 2025-12-26 | 2025-12-27 | 2025-12-26 | 2025-12-27 | Sachi | 2026-01-09 | 2026-01-09 | Done | Sachi | 2026-01-06 | 2026-01-13 | WTG 480 | ICECUBE | Done | 2026-01-11 | 2026-01-11 | 2026-01-28 | 2026-01-29 | 2026-01-01 |  | 2026-01-12 | 2026-01-29
95 | PSS-11 | AGE25CL | WTG 481 | F04 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | SHREEJI | 2025-11-26 | 2025-12-03 | 2025-11-26 | 2025-12-03 | Sachi | 2025-12-09 | 2025-12-13 | Done | Sachi | 2025-12-23 | 2026-01-12 | WTG 481 | AERIS | Done | 2025-12-19 | 2025-12-19 | 2026-01-04 | 2026-01-04 | 2026-01-13 |  | 2025-12-23 | 2026-01-10
96 | PSS-11 | AGE25CL | WTG 482 | F08 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | ODHAV | 2025-12-22 | 2025-12-23 | 2025-12-22 | 2025-12-23 | Sachi | 2026-01-03 | 2026-01-03 | Done | Sachi | 2026-01-03 | 2026-01-31 | WTG 482 | Pratibha | Done | 2026-01-06 | 2026-01-06 | 2026-01-30 | 2026-01-31 | 2026-01-02 |  | 2026-01-22 | 2026-01-31
97 | PSS-11 | AGE25CL | WTG 501 | F06 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | BHAVANI | 2025-12-04 | 2025-12-11 | 2025-12-04 | 2025-12-11 | Sachi | 2025-12-23 | 2025-12-29 | Done | Shreeji | 2025-12-26 | 2026-01-30 | WTG 501 | ICECUBE | Done | 2026-01-01 | 2025-12-30 | 2026-01-03 | 2026-01-04 | 2026-01-10 |  | 2026-01-01 | 2026-01-13
98 | PSS-11 | AGE25CL | WTG 502 | F04 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | DNC | 2025-10-30 | 2025-11-11 | 2025-10-30 | 2025-11-11 | Sachi | 2025-12-11 | 2025-12-26 | Done | Sachi | 2025-12-25 | 2026-01-29 | WTG 502 | AKSHAR | Done | 2025-12-29 | 2025-12-29 | 2026-12-31 | 2026-01-01 | 2026-01-10 |  | 2025-12-30 | 2026-01-06
99 | PSS-11 | AGE25CL | WTG 503 | F05 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | HBG | 2025-09-28 | 2025-09-29 | 2025-09-28 | 2025-09-29 | Sachi | 2025-11-02 | 2025-11-02 | Done | Shreeji | 2025-11-02 | 2026-01-29 | WTG 503 | ICECUBE | Done | 2025-11-26 | 2025-11-25 | 2025-12-13 | 2025-12-14 | 2025-12-15 |  | 2025-12-03 | 2025-12-15
100 | PSS-11 | AGE25CL | WTG 504 | F05 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | ODHAV | 2025-10-05 | 2025-10-16 | 2025-10-05 | 2025-10-16 | Sachi | 2025-10-01 | 2025-10-01 | Done | Shreeji | 2025-11-02 | 2026-01-26 | WTG 504 | ICECUBE | Done | 2025-11-26 | 2025-11-25 | 2025-12-07 | 2025-12-08 | 2025-12-08 |  | 2025-12-04 | 2025-12-09
101 | PSS-11 | AGE25CL | WTG 505 | F08 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | ODHAV | 2025-09-29 | 2025-09-30 | 2025-09-29 | 2025-09-30 | Sachi | 2025-10-25 | 2025-10-25 | Done | Sachi | 2025-11-25 | 2025-11-05 | WTG 505 | Pratibha | Done | 2025-11-30 | 2025-11-27 | 2025-12-11 | 2025-12-12 | 2025-12-25 |  | 2025-12-21 | 2026-01-04
102 | PSS-11 | AGE25CL | WTG 522 | F06 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | BHAVANI | 2025-10-24 | 2025-10-26 | 2025-10-24 | 2025-10-26 | Sachi | 2025-12-30 | 2025-12-30 | Done | Sachi | 2025-12-29 | 2026-01-30 | WTG 522 | AERIS | Done | 2025-12-31 | 2025-12-31 | 2026-01-06 | 2026-01-07 | 2026-01-20 |  | 2026-01-06 | 2026-01-17
103 | PSS-11 | AGE25CL | WTG 523 | F05 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | DNC | 2025-10-02 | 2025-10-12 | 2025-10-02 | 2025-10-12 | Shreeji | 2025-11-28 | 2025-11-28 | Done | Shreeji | 2025-11-28 | 2026-01-29 | WTG 523 | ICECUBE | Done | 2025-11-30 | 2025-11-30 | 2025-12-27 | 2025-12-28 | 2025-12-28 |  | 2025-12-04 | 2025-12-28
104 | PSS-11 | AGE25CL | WTG 524 | F06 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | HBG | 2025-10-09 | 2025-10-12 | 2025-10-09 | 2025-10-12 | Sachi | 2025-11-29 | 2025-12-22 | Done | Sachi | 2025-12-26 | 2026-01-15 | WTG 524 | AKSHAR | Done | 2025-12-28 | 2025-12-29 | 2026-01-01 | 2026-01-02 | 2026-01-04 |  | 2026-01-01 | 2026-01-05
105 | PSS-11 | AGE25CL | WTG 457 | F08 | Shreeji | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | SHREERAM | 2025-11-23 | 2025-11-24 | 2025-11-23 | 2025-11-24 | Shreeji | 2025-12-11 | 2025-12-11 | Done | Shreeji | 2025-12-11 | 2026-01-31 | WTG 457 | ICECUBE | Done | 2025-12-13 | 2025-12-13 | 2025-12-21 | 2025-12-22 | 2025-12-24 |  | 2025-12-18 | 2025-12-24
106 | PSS-12 | AGE26AL | WTG 402 | F01 | Shreeji | 9 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | BHAVANI | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-17 | Sachi | 2026-01-05 | 2026-01-05 |  | Sachi | 2026-01-05 | 2026-02-02 | WTG 402 | ICECUBE | Done | 2026-01-06 | 2026-01-06 | 2026-01-15 | 2026-01-16 | 2026-02-05 |  | 2026-01-12 | 2026-02-01
107 | PSS-12 | AGE26AL | WTG 428 | F02 | Shreeji | 9 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | SHREEJI | 2025-12-10 | 2025-12-16 | 2025-12-10 | 2025-12-16 | Sachi | 2026-01-08 | 2026-01-08 |  | Shreeji | 2025-12-30 |  | WTG 428 | ICECUBE | Done | 2026-01-15 | 2026-12-30 | 2026-01-26 | 2026-01-27 | 2026-02-05 |  | 2026-01-04 | 2026-02-02
108 | PSS-12 | AGE26AL | WTG 451 | F02 | Shreeji | 9 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | SHREEJI | 2026-01-27 | 2026-01-28 | 2026-01-27 | 2026-01-27 | Sachi | 2026-02-07 | 2026-02-07 |  | Sachi | 2026-02-07 |  | WTG 451 | ICECUBE | Done | 2026-02-09 | 2026-02-10 | 2026-02-23 | 2026-02-24 | 2026-02-25 |  | 2026-02-14 | 2026-02-20
109 | PSS-12 | AGE26AL | WTG 452 | F02 | Shreeji | 9 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | SHREERAM | 2026-01-26 | 2026-01-27 | 2026-01-26 | 2026-01-27 | shreeji | 2026-01-28 | 2026-01-28 |  | Sachi | 2026-01-29 |  | WTG 452 | ICECUBE | Done | 2026-02-01 | 2026-02-01 | 2026-02-12 | 2026-02-13 | 2026-02-21 |  | 2026-02-02 | 2026-02-22
110 | PSS-12 | AGE26AL | WTG 453 | F02 | Shreeji | 9 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | SHREERAM | 2026-01-17 | 2026-01-18 | 2026-01-17 | 2026-01-18 | Sachi | 2026-01-19 | 2026-01-19 |  | Sachi | 2026-01-23 |  | WTG 453 | ICECUBE | Done | 2026-01-24 | 2026-01-24 | 2026-02-12 | 2026-02-13 | 2026-02-20 |  | 2026-02-05 | 2026-02-22
111 | PSS-14 | AGE25CL | WTG 473 | F15 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | ODHAV | 2026-02-07 | 2026-02-08 | 2026-02-07 | 2026-02-08 | sachi | 2026-02-10 | 2026-02-10 |  | sachi | 2026-02-10 |  | WTG 473 | AKSHAR |  | 2026-02-24 | 2026-02-24
112 | PSS-14 | AGE25CL | WTG 474 | F15 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | ODHAV | 2026-01-24 | 2026-01-25 | 2026-01-24 | 2026-01-25 | Shreeji | 2026-01-27 | 2026-01-27 |  | Sachi | 2026-02-19 |  | WTG 474 | AKSHAR
113 | PSS-12 | AGE26AL | WTG 475 | F06 | Shreeji | 9 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | MSC | 2025-10-05 | 2025-10-21 | 2025-10-05 | 2025-10-21 | Sachi | 2026-01-02 | 2026-01-02 |  | Shreeji | 2026-01-07 |  | WTG 475 | ICECUBE | Done | 2026-01-09 | 2026-01-09 | 2026-01-12 | 2026-01-15 | 2026-01-30 |  | 2026-01-17 | 2026-01-31
114 | PSS-12 | AGE26AL | WTG 476 | F03 | Shreeji | 9 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | SHREERAM | 2025-12-01 | 2025-12-13 | 2025-12-01 | 2025-12-13 | Sachi | 2026-01-16 | 2026-01-16 |  | Sachi | 2026-01-16 |  | WTG 476 | AKSHAR | Done | 2026-01-17 | 2026-01-17 | 2026-01-27 | 2026-01-28 | 2026-02-11 |  | 2026-02-10
115 | PSS-12 | AGE26AL | WTG 477 | F03 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | MSC | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-20 | Sachi | 2026-01-21 | 2026-01-21 |  | Sachi | 2026-01-24 |  | WTG 477 | ICECUBE | Done | 2026-01-24 | 2026-01-24 | 2026-02-11 | 2026-02-12 | 2026-02-25 |  | 2026-02-01 | 2026-02-03
116 | PSS-12 | AGE26AL | WTG 478 | F03 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | ODHAV | 2025-12-28 | 2025-12-31 | 2025-12-28 | 2025-12-31 | Shreeji | 2026-01-10 | 2026-01-10 |  | Shreeji | 2026-01-10 | 2026-01-30 | WTG 478 | ICECUBE | Done | 2026-01-14 | 2026-01-14 | 2026-01-19 | 2026-01-22 | 2026-04-04 |  | 2026-01-19 | 2026-02-01
117 | PSS-12 | AGE26AL | WTG 496 | F06 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | BHAVANI | 2025-09-30 | 2025-10-05 | 2025-09-30 | 2025-12-11 | Shreeji | 2025-12-24 | 2025-12-24 |  | Shreeji | 2025-12-24 |  | WTG 496 | ICECUBE | Done | 2025-12-31 | 2026-01-03 | 2026-01-17 | 2026-01-18 | 2026-02-03 |  | 2026-02-02 | 2026-02-04
118 | PSS-12 | AGE26AL | WTG 497 | F06 | Shreeji | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | ODHAV | 2026-01-21 | 2026-01-22 | 2026-01-21 | 2026-01-22 | Sachi | 2026-01-26 | 2026-01-26 |  | Shreeji | 2026-02-06 |  | WTG 497 | AKSHAR | Done | 2026-02-10 | 2026-02-10 |  |  |  |  | 2026-02-16 | 2026-02-21
119 | PSS-12 | AGE26AL | WTG 498 | F06 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | BIPL | 2025-10-05 | 2025-10-08 | 2025-10-05 | 2025-10-08 | Shreeji | 2025-12-25 | 2025-12-25 |  | Shreeji | 2026-01-09 |  | WTG 498 | ICECUBE | Done | 2026-01-15 | 2026-01-15 | 2026-01-19 | 2026-01-23 | 2026-01-24 |  | 2026-01-19 | 2026-01-23
120 | PSS-12 | AGE26AL | WTG 499 | F03 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | SHREERAM | 2026-01-02 | 2026-01-03 | 2026-01-02 | 2026-01-03 | Sachi | 2026-01-10 | 2026-01-10 |  | Sachi | 2026-02-02 | 2026-02-21 | WTG 499 | AKSHAR | Done | 2026-02-07 | 2026-02-07 | 2026-02-09 | 2026-02-10 | 2026-02-25 |  | 2026-02-11 | 2026-02-21
121 | PSS-12 | AGE26AL | WTG 500 | F03 | Shreeji | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | MSC | 2025-12-24 | 2026-01-03 | 2025-12-24 | 2026-01-03 | Sachi | 2026-01-28 | 2026-01-30 |  | Sachi | 2026-01-31 | 2026-02-21 | WTG 500 | AKSHAR | Done | 2026-02-01 | 2026-02-02 | 2026-02-21 | 2026-02-22 | 2026-02-22 |  | 2026-02-03 | 2026-02-20
122 | PSS-12 | AGE26AL | WTG 517 | F06 | Shreeji | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | BHAVANI | 2026-01-23 | 2026-01-24 | 2026-01-23 | 2026-01-24 | Sachi | 2026-01-29 | 2026-01-29 |  | Sachi | 2026-01-29 |  | WTG 517 | AKSHAR | Done | 2026-02-01 | 2026-02-02 |  |  |  |  | 2026-02-04 | 2026-02-20
123 | PSS-12 | AGE26AL | WTG 518 | F05 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | SHREEJI | 2025-10-05 | 2025-10-10 | 2025-10-05 | 2025-10-10 | Sachi | 2025-12-27 | 2025-12-27 |  | Shreeji | 2025-12-24 | 2026-02-11 | WTG 518 | ICECUBE | Done | 2025-12-27 | 2025-12-27 | 2026-01-05 | 2026-01-06 | 2026-01-14 |  | 2026-01-04 | 2026-01-15
124 | PSS-12 | AGE26AL | WTG 519 | F05 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | SHREEJI | 2025-11-25 | 2025-12-26 | 2025-11-25 | 2025-11-29 | SACHI | 2026-01-12 | 2026-01-12 |  | Sachi | 2026-01-12 | 2026-02-21 | WTG 519 | ICECUBE | Done | 2026-01-15 | 2026-01-15 | 2026-01-19 | 2026-01-23 | 2026-02-02 |  | 2026-01-22 | 2026-01-24
125 | PSS-12 | AGE26AL | WTG 520 | F04 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | DNC | 2025-12-08 | 2025-12-14 | 2025-12-08 | 2025-12-14 | SACHI | 2026-01-14 | 2026-01-14 |  | Sachi | 2026-01-15 | 2026-02-02 | WTG 520 | AKSHAR | Done | 2026-01-16 | 2026-01-16 | 2026-01-17 | 2026-01-23 | 2026-03-03 |  | 2026-01-19 | 2026-01-27
126 | PSS-12 | AGE26AL | WTG 521 | F04 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | BHAVANI | 2025-11-20 | 2025-11-25 | 2025-11-20 | 2025-11-25 | Sachi | 2026-01-08 | 2026-01-08 |  | Sachi | 2026-01-08 | 2026-01-24 | WTG 521 | AKSHAR | Done | 2026-01-10 | 2026-01-10 | 2026-01-13 | 2026-01-14 | 2026-02-03 |  | 2026-01-14 | 2026-01-20
127 | PSS-12 | AGE26AL | WTG 533 | F05 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | SHREEJI | 2025-12-21 | 2025-12-22 | 2025-12-21 | 2025-12-22 | Sachi | 2026-01-08 | 2026-01-08 |  | Sachi | 2026-01-07 |  | WTG 533 | AKSHAR | Done | 2026-01-10 | 2026-01-11 | 2026-01-25 | 2026-01-26 | 2026-02-02 |  | 2026-01-11 | 2026-01-22
128 | PSS-12 | AGE26AL | WTG 534 | F05 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Shreeji | 1 | SHREEJI | 2025-10-02 | 2025-10-16 | 2025-10-02 | 2025-10-16 | Sachi | 2025-12-27 | 2025-12-27 |  | Shreeji | 2025-12-27 |  | WTG 534 | ICECUBE | Done | 2025-12-29 | 2025-12-28 | 2026-01-17 | 2026-01-18 | 2026-01-23 |  | 2025-12-31 | 2026-01-23
129 | PSS-12 | AGE26AL | WTG 535 | F05 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Shreeji | 1 | MSC | 2025-12-08 | 2025-12-09 | 2025-12-08 | 2025-12-09 | Sachi | 2026-01-02 | 2026-01-02 |  | Sachi | 2026-01-05 | 2026-02-21 | WTG 535 | AKSHAR | Done | 2026-01-07 | 2026-01-07 | 2026-01-16 | 2026-01-17 | 2026-02-02 |  | 2026-01-11 | 2026-01-20
130 | PSS-12 | AGE26AL | WTG 536 | F04 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Shreeji | 1 | MSC | 2025-12-07 | 2025-12-08 | 2025-12-07 | 2025-12-08 | Sachi | 2026-01-01 | 2026-01-01 |  | Sachi | 2025-12-16 |  | WTG 536 | AKSHAR | Done | 2026-01-07 | 2025-12-30 | 2026-01-07 | 2026-01-08 | 2026-01-15 |  | 2026-01-03 | 2026-01-12
131 | PSS-14 | AGE25CL | WTG 532 | F13 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Shreeji | 1 | DNC | 2025-12-25 | 2025-12-26 | 2025-12-25 | 2025-12-26 | Shreeji | 2026-01-18 | 2026-01-18 |  | Shreeji | 2026-02-23 |  | WTG 532 | AKSHAR
132 | PSS-14 | AGE25CL | WTG 516 | F13 | Sachi | 9 |  |  |  |  | Sachi | 1 | [14 empty] | WTG 516 | ICECUBE
133 | PSS-14 | AGE26AL | KH 53 | F07 | Shreeji | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Shreeji | 1 | HBG | 2025-11-22 | 2025-11-24 | 2025-11-22 | 2025-11-24 | Shreeji | 2026-02-05 | 2026-02-05 |  |  |  |  | KH 53 | ICECUBE
134 | PSS-14 | AGE26AL | KH 54 | F08 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | CEIPL | 2025-04-26 | 2025-04-27 | 2025-04-26 | 2025-04-27 | [7 empty] | KH 54 | ICECUBE
135 | PSS-14 | AGE26AL | KH 55 | F09 | Sachi | 9 | [8 empty] | BHAVANI | [11 empty] | KH 55 | ICECUBE
136 | PSS-14 | AGE26AL | KH 56 | F09 | Sachi | 9 | Shreeji | 1 | Shreeji | 1 |  |  |  |  | BHAVANI | 2026-02-12 |  | 2026-02-12 | 2026-02-13 | [7 empty] | KH 56 | AKSHAR
137 | PSS-14 | AGE26AL | KH 57 | F10 | Shreeji | 9 | Shreeji | 1 | Sachi | 1 |  |  | Sachi | 1 | SHREERAM | 2025-06-04 | 2025-06-05 | 2025-06-04 | 2025-06-05 | [7 empty] | KH 57 | ICECUBE
138 | PSS-14 | AGE26AL | KH 58 | F11 | Sachi | 9 | Sachi | 1 | Sachi | 1 |  |  | Sachi | 1 | HBG | 2026-01-01 | 2026-01-02 | 2026-01-01 | 2026-01-02 | SHREEJI | 2026-01-20 | 2026-01-20 |  | Shreeji | 2026-01-19 |  | KH 58 | ICECUBE |  | 2026-02-27 | 2026-02-27
139 | PSS-14 | AGE26AL | KH 59 | F11 | Sachi | 9 | Sachi | 1 | Sachi | 1 |  |  | Sachi | 1 | MSC | 2026-01-31 | 2026-02-01 | 2026-01-31 | 2026-02-01 | Sachi | 2026-02-12 | 2026-02-12 |  | Shreeji | 2026-02-16 |  | KH 59 | ICECUBE |  | 2026-02-27 | 2026-02-27
140 | PSS-14 | AGE26AL | KH 60 | F11 | Sachi | 9 | Sachi | 1 | Sachi | 1 |  |  | Sachi | 1 | ODHAV | 2026-01-07 | 2026-01-08 | 2026-01-07 | 2026-01-08 | Sachi | 2026-02-06 | 2026-02-06 |  | Sachi | 2026-02-06 |  | KH 60 | ICECUBE |  | 2026-02-27
141 | PSS-14 | AGE26AL | KH 61 | F11 | Sachi | 9 | Sachi | 1 | Sachi | 1 |  |  | Sachi | 1 | ODHAV | 2026-01-12 | 2026-01-13 | 2026-01-12 | 2026-01-13 | Sachi | 2026-02-23 | 2026-02-23 |  |  |  |  | KH 61 | ICECUBE |  | 2026-02-27 | 2026-02-27
142 | PSS-14 | AGE26AL | KH 556 | F06 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | MSC | 2026-01-02 | 2026-01-03 | 2026-01-02 | 2026-01-03 | [7 empty] | KH 556 | Pratibha
143 | PSS-14 | AGE26AL | KH 523 | F06 | Sachi | 9 | Sachi | 1 |  |  | Sachi | 1 |  |  | HBG | [11 empty] | KH 523 | AKSHAR
144 | PSS-14 | AGE26AL | KH 522 | F05 | Shreeji | 9 | Shreeji | 1 | Shreeji | 1 |  |  |  |  | MSC | 2026-02-05 | 2026-02-06 | 2026-02-05 | 2026-02-06 | [7 empty] | KH 522 | AKSHAR
145 | PSS-14 | AGE26AL | KH 521 | F05 | [22 empty] | KH 521 | AKSHAR
146 | PSS-14 | AGE26AL | KH 508 | F05 | Shreeji | 9 | Sachi | 1 | Sachi | 1 |  |  | Sachi | 1 | HBG | 2026-01-17 | 2026-01-18 | 2026-01-17 | 2026-01-18 | [7 empty] | KH 508 | AKSHAR
147 | PSS-14 | AGE26AL | KH 555 | F07 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | MSC | 2026-01-06 | 2026-01-07 | 2026-01-06 | 2026-01-07 |  |  |  |  | Shreeji | 2026-02-27 |  | KH 555 | AKSHAR
148 | PSS-14 | AGE26AL | KH 557 | F07 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | MSC | 2026-01-03 | 2026-01-04 | 2026-01-03 | 2026-01-04 | Shreeji | 2026-02-11 | 2026-02-11 |  | Shreeji | 2026-02-07 |  | KH 557 | AKSHAR
149 | PSS-14 | AGE26AL | KH 581 | F08 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | BHAVANI | 2025-12-31 | 2026-01-02 | 2025-12-31 | 2026-01-02 | Shreeji | 2026-02-16 | 2026-02-16 |  | Sachi | 2026-02-25 |  | KH 581 | AKSHAR
150 | PSS-14 | AGE26AL | KH 582 | F01 |  |  |  |  | Sachi | 1 | [16 empty] | KH 582 | ICECUBE
151 | PSS-14 | AGE26AL | KH 583 | F01 |  |  |  |  | Sachi | 1 |  |  |  |  | MSC | 2026-02-18 | 2026-02-20 | 2026-02-18 | 2026-02-20 | [7 empty] | KH 583 | AKSHAR
152 | PSS-14 | AGE26AL | KH 52 | F12 |  |  | Shreeji | 1 | [6 empty] | MSC | 2026-01-23 | 2026-01-24 | 2026-01-23 | 2026-01-24 | [7 empty] | KH 52 | AKSHAR
153 | PSS-14 | AGE26AL | KH 51 | F12 | Sachi | 9 | Sachi | 1 | Shreeji | 1 |  |  | Sachi | 1 | ODHAV | 2026-01-08 | 2026-01-09 | 2026-01-08 | 2026-01-09 | ShreeJi | 2026-02-07 | 2026-02-07 |  |  |  |  | KH 51 | AKSHAR
154 | PSS-14 | AGE26AL | KH 552 | F12 | [10 empty] | MSC | 2026-02-16 | 2026-02-18 | 2026-02-16 | 2026-02-18 | [7 empty] | KH 552 | AKSHAR
155 | PSS-14 | AGE26AL | KH 588 | F08 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Sachi | 1 | CEIPL | 2025-05-16 | 2025-05-19 | 2025-05-17 | 2025-05-19 | [5 empty] | 2025-05-29 |  | KH 588 | ICECUBE
156 | PSS-14 | AGE26AL | KH 589 | F08 | Sachi | 9 | Sachi | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | BPS | 2025-06-04 | 2025-06-09 | 2025-06-04 | 2025-06-09 |  |  |  |  | Sachi | 2026-02-13 |  | KH 589 | AKSHAR
157 | PSS-14 | AGE26AL | KH 590 | F01 | Sachi | 9 | Sachi | 1 | Shreeji | 1 |  |  | Sachi | 1 | MSC | 2025-12-04 | 2025-12-05 | 2025-12-04 | 2025-12-05 | Sachi | 2026-02-11 | 2026-02-11 |  | Sachi | 2026-02-11 |  | KH 590 | ICECUBE
158 | PSS-14 | AGE26AL | KH 591 | F01 | [8 empty] | Sachi | 1 | [12 empty] | KH 591 | ICECUBE
159 | PSS-14 | AGE26AL | KH 592 | F02 | Sachi | 9 | Shreeji | 1 | Shreeji | 1 | Sachi | 1 | Sachi | 1 | DNC | 2025-09-24 | 2025-09-25 | 2025-09-24 | 2025-09-25 | Shreeji | 2026-02-18 | 2026-02-18 |  |  |  |  | KH 592 | ICECUBE
160 | PSS-14 | AGE26AL | KH 550 | F12 | Shreeji | 9 | Shreeji | 1 | Sachi | 1 |  |  | Sachi | 1 | HBG | 2026-01-23 | 2026-01-24 | 2026-01-23 | 2026-01-24 | [7 empty] | KH 550 | AKSHAR
161 | PSS-14 | AGE26AL | KH 551 | F06 |  |  | Shreeji | 1 |  |  | Sachi | 1 |  |  | BIPL | 2026-02-10 | 2026-02-15 | 2026-02-10 | 2026-02-15 | [7 empty] | KH 551 | AERIS
162 | PSS-14 | AGE26AL | KH 579 | F07 | [6 empty] | Sachi | 1 |  |  | MSC | 2026-02-16 | 2026-02-18 | 2026-02-16 | 2026-02-18 | [7 empty] | KH 579 | AKSHAR
163 | PSS-14 | AGE26AL | KH 596 | F08 | Shreeji | 9 | Shreeji | 1 | Sachi | 1 | Sachi | 1 |  |  | SHREERAM | 2026-01-21 | 2026-01-22 | 2026-01-21 | 2026-01-22 | Shreeji | 2026-02-04 | 2026-02-04 |  | Sachi | 2026-02-05 |  | KH 596 | AKSHAR |  | 2026-02-22 | 2026-02-22
164 | PSS-14 | AGE26AL | KH 597 | F09 | Shreeji | 9 | Shreeji | 1 | Sachi | 1 |  |  |  |  | HBG | 2026-01-31 | 2026-02-01 | 2026-01-31 | 2026-02-01 | Shreeji | 2026-02-12 | 2026-02-12 |  | Shreeji | 2026-02-11 |  | KH 597 | AKSHAR |  | 2026-02-25 | 2026-02-25
165 | PSS-14 | AGE26AL | KH 598 | F01 | Sachi | 9 | Sachi | 1 | Shreeji | 1 |  |  | Sachi | 1 | SHREEJI | 2025-10-17 | 2025-10-24 | 2025-10-17 | 2025-10-24 | SACHI | 2026-01-20 | 2026-01-20 |  | Sachi | 2026-02-11 |  | KH 598 | AKSHAR
166 | PSS-14 | AGE26AL | KH 599 | F02 | Shreeji | 9 | Shreeji | 1 |  |  | Sachi | 1 |  |  | HBG | 2026-02-11 | 2026-02-12 | 2026-02-11 | 2026-02-12 | SACHI | 2026-02-26 | 2026-02-26 |  | Shreeji | 2026-02-24 |  | KH 599 | AKSHAR
167 | PSS-14 | AGE26AL | KH 600 | F02 | Sachi | 9 |  |  | Shreeji | 1 | Sachi | 1 |  |  | DNC | 2025-11-16 | 2025-11-29 | 2025-11-16 | 2025-11-29 | Sachi | 2026-02-20 | 2026-02-20 |  |  |  |  | KH 600 | AKSHAR
168 | PSS-14 | AGE26AL | KH 553 | F06 | Shreeji | 9 | [8 empty] | SHREERAM | 2026-02-06 | 2026-02-07 | 2026-02-06 | 2026-02-07 | [7 empty] | KH 553 | AERIS
169 | PSS-14 | AGE26AL | KH 580 | F07 | Sachi | 9 |  |  | Shreeji | 1 |  |  |  |  | HBG | 2025-11-07 | 2025-11-09 | 2025-11-07 | 2025-11-09 | Shreeji | 2026-02-10 | 2026-02-10 |  | Sachi | 2026-02-10 |  | KH 580 | ICECUBE
170 | PSS-14 | AGE26AL | KH 478 | F05 | [22 empty] | KH 478 | AKSHAR
171 | PSS-14 | AGE26AL | KH 604 | F09 | Sachi | 9 |  |  | Shreeji | 1 |  |  |  |  | SHREERAM | 2025-08-14 | 2025-08-16 | 2025-08-14 | 2026-08-16 | [7 empty] | KH 604 | AKSHAR
172 | PSS-14 | AGE26AL | KH 605 | F09 | Sachi | 9 |  |  | Shreeji | 1 |  |  |  |  | SHREERAM | 2025-09-25 | 2025-09-27 | 2025-09-25 | 2025-09-27 | Shreeji | 2026-02-26 | 2026-02-26 |  | Shreeji | 2026-02-26 |  | KH 605 | AKSHAR
173 | PSS-14 | AGE26AL | KH 606 | F02 | Sachi | 9 |  |  | Shreeji | 1 |  |  |  |  | BHAVANI | 2025-09-03 | 2025-09-05 | 2025-09-03 | 2025-09-05 | Sachi | 2026-02-24 | 2026-02-24 |  | Shreeji | 2026-02-24 |  | KH 606 | AKSHAR
174 | PSS-14 | AGE26AL | KH 607 | F03 | [22 empty] | KH 607 | AKSHAR
175 | PSS-14 | AGE26AL | KH 608 | F03 |  |  |  |  | Sachi | 1 |  |  |  |  | BHAVANI | 2026-01-14 | 2026-01-15 | 2026-01-14 | 2026-01-20 | [7 empty] | KH 608 | AERIS
176 | PSS-14 | AGE26AL | KH 509 | F05 | [22 empty] | KH 509 | AKSHAR
177 | PSS-14 | AGE26AL | KH 554 | F06 | [22 empty] | KH 554 | AKSHAR
178 | PSS-14 | AGE26AL | KH 611 | F10 | [10 empty] | BHAVANI | 2026-02-18 | 2026-02-20 | 2026-02-18 | [8 empty] | KH 611 | ICECUBE
179 | PSS-14 | AGE26AL | KH 612 | F10 | Sachi | 9 |  |  | Shreeji | 1 |  |  |  |  | SHREERAM | 2025-07-17 | 2025-07-18 | 2025-07-17 | 2025-07-18 | [7 empty] | KH 612 | AKSHAR
180 | PSS-14 | AGE26AL | KH 613 | F02 |  |  |  |  | Shreeji | 1 |  |  |  |  | SHREEJI | 2025-12-10 | 2026-02-19 | 2025-12-10 | 2026-02-19 | Shreeji | 2026-02-20 | 2026-02-20 |  | Shreeji | 2026-02-25 |  | KH 613 | ICECUBE
181 | PSS-14 | AGE26AL | KH 614 | F03 | [10 empty] | SHREERAM | 2026-02-22 | 2026-02-24 | 2026-02-22 | 2026-02-24 | [7 empty] | KH 614 | AKSHAR
182 | PSS-14 | AGE26AL | KH 615 | F03 | Sachi | 9 |  |  | Shreeji | 1 |  |  |  |  | SHREEJI | 2025-09-04 | 2025-09-05 | 2025-09-04 | 2025-09-05 | [7 empty] | KH 615 | ICECUBE
183 | PSS-14 | AGE26AL | KH 47 | F12 | [22 empty] | KH 47 | AKSHAR
184 | PSS-14 | AGE26AL | KH 617 | F10 | [10 empty] | SHREEJI | 2026-02-16 | 2026-02-18 | 2026-02-16 | 2026-02-18 | [7 empty] | KH 617 | AKSHAR
185 | PSS-14 | AGE26AL | KH 618 | F03 | [22 empty] | KH 618 | Pratibha
186 | PSS-14 | AGE26AL | KH 619 | F04 | Sachi | 9 |  |  | Shreeji | 1 |  |  |  |  | SHREEJI | 2025-12-26 | 2025-12-27 | 2025-12-26 | 2025-12-27 | Shreeji | 2026-02-13 | 2026-02-13 |  | Shreeji | 2026-02-14 |  | KH 619 | Pratibha
187 | PSS-14 | AGE26AL | KH 620 | F04 | [22 empty] | KH 620 | AKSHAR
188 | PSS-14 | AGE26AL | KH 621 | F11 | Sachi | 9 |  |  | Shreeji | 1 |  |  |  |  | SHREEJI | 2025-12-06 | 2025-12-28 | 2025-12-06 | 2025-12-28 | Sachi | 2026-02-18 | 2026-02-18 |  | Sachi | 2026-02-18 |  | KH 621 | ICECUBE |  | 2026-02-27 | 2026-02-27
189 | PSS-14 | AGE26AL | KH 622 | F04 | [22 empty] | KH 622 | ICECUBE
190 | PSS-14 | AGE26AL | KH 34 | F04 | [10 empty] | BHAVANI | 2026-01-16 | 2026-01-17 | 2026-01-16 | 2026-01-17 | Shreeji | 2026-02-17 | 2026-02-17 |  | Shreeji | 2026-02-17 |  | KH 34 | AERIS
191 | PSS-14 | AGE26AL | KH 35 | F04 | [22 empty] | KH 35 | AKSHAR
190 | PSS-14 | AGE26AL | KH 68 | F10 | [10 empty] | ODHAV | 2026-02-16 | 2026-02-18 | 2026-02-16 | 2026-02-18 | [7 empty] | KH 68 | AKSHAR
191 | PSS-09 | AGE25BL | WTG 556 | F1 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Shreeji | 1 | MSC | 2025-11-26 | 2025-11-27 | 2025-11-26 | 2025-11-27 | Sachi | 2025-12-15 | 2025-12-16 | Done | Shreeji | 2025-12-15 | 2026-01-22 | WTG 556 | AKSHAR | Done | 2025-12-18 | 2025-12-14 | 2025-12-15 | 2025-12-24 | 2025-12-25 |  | 2025-12-21 | 2025-12-26
192 | PSS-09 | AGE25BL | WTG 557 | F1 | Sachi | 9 | Sachi | 1 | Sachi | 1 | Sachi | 1 | Shreeji | 1 | MSC | 2025-11-14 | 2025-11-15 | 2025-11-14 | 2025-11-15 | Sachi | 2025-12-14 | 2025-12-14 | Done | Shreeji | 2025-12-16 | 2026-01-22 | WTG 557 | AKSHAR | Done | 2025-12-17 | 2025-12-17 | 2025-12-21 | 2025-12-23 | 2025-12-24 |  | 2025-12-20 | 2025-12-26
Note on H318: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CEIPL - upto PCC, BPS - from Anchor Cage

## 33KV - Summary
ADANI WIND 998.4MW (PH-III 192NO'S) UG CABLE PROGRESS STATUS
Sr. No. | Feeder | Agency Name | Excavation |  |  |  | HTCable Laying |  |  |  | Cable Joint |  |  |  | Cable Termination |  |  |  | Feeder (PSS-8) | FO Cable Laying | time axis 2025-04-01 to 2026-03-31
|  |  | Scope | Today | Cumulative | Balance | Scope | Today | Cumulative | Balance | Scope | Today | Cumulative | Balance | Scope | Today | Cumulative | Balance |  | Scope | Today | Cumulative | Balance
I | PSS-8
1 | FDR -10 | Winbee | 12245 | 0 | 2100 | 10145 | 17800 | 1525 | 10600 | 7200 | 20 | 0 | 1 | 19 | 10 | 0 | 4 | 6 | RING-01 | 10600 |  |  | 10600
2 | FDR- 11 | Bajrang | 11270 | 0 | 22430 | -11160 | 23325 | 0 | 23325 | 0 | 29 | 0 | 26 | 3 | 10 | 0 | 8 | 2 | RING-02 | 18685 |  | 18685 | 0
3 | FDR - 12 | Winbee | 7445 | 0 | 7500 | -55 | 7445 | 0 | 7445 | 0 | 9 | 0 | 11 | -2 | 4 | 0 | 4 | 0 | RING-03 | 13110 |  | 13110 | 0
4 | FDR - 13 | Malinath | 10354 | 0 | 13430 | -3076 | 13360 | 0 | 13360 | 0 | 16 | 0 | 16 | 0 | 10 | 0 | 10 | 0
PSS-8 Total Scope |  |  | 41314 | 0 | 45460 | -4146 | 61930 | 1525 | 54730 | 7200 | 74 | 0 | 54 | 20 | 34 | 0 | 26 | 8 | Total | 42395 | 0 | 31795 | 10600
Sr. No. | Feeder(PSS-5) | Agency Name | Excavation |  |  |  | HTCable Laying |  |  |  | Cable Joint |  |  |  | Cable Termination |  |  |  | Feeder(PSS-5) | FO Cable Laying
|  |  | Scope | Today | Cumulative | Balance | Scope | Today | Cumulative | Balance | Scope | Today | Cumulative | Balance | Scope | Today | Cumulative | Balance |  | Scope | Today | Cumulative | Balance
I | PSS-5
1 | FDR-1 | Akshar | 5496 |  | 5496 | 0 | 15917 | 0 | 15917 | 0 | 18 |  | 18 | 0 | 10 |  | 10 | 0 | RING-01 | 17340 | 0 | 17340 | 0
2 | FDR-2 | Akshar | 4173 |  | 4173 | 0 | 11016 | 0 | 11016 | 0 | 12 |  | 12 | 0 | 8 |  | 8 | 0 | RING-02 | 23190 | 0 | 23190 | 0
3 | FDR-3 | Sunlec | 7090 |  | 7090 | 0 | 11400 | 0 | 11400 | 0 | 15 |  | 15 | 0 | 10 |  | 10 | 0 | RING-03 | 7590 | 0 | 7590 | 0
4 | FDR-4 | Akshar | 4521 |  | 4521 | 0 | 6255 | 0 | 6255 | 0 | 6 |  | 6 | 0 | 10 |  | 10 | 0 | RING-04 | 9210 | 0 | 9210 | 0
5 | FDR-5 | Supreme | 6545 |  | 6545 | 0 | 14738 | 0 | 14738 | 0 | 19 |  | 19 | 0 | 10 |  | 10 | 0 | RING-05 | 17625 |  | 17625 | 0
6 | FDR-6 | Akshar | 5360 |  | 5360 | 0 | 10020 | 0 | 10020 | 0 | 11 |  | 11 | 0 | 10 |  | 10 | 0
7 | FDR-7 | Akshar | 5093 |  | 5093 | 0 | 13486 | 0 | 13486 | 0 | 16 |  | 16 | 0 | 10 |  | 10 | 0
8 | FDR-8 | Ice Cube | 7495 |  | 7495 | 0 | 20275 | 0 | 20275 | 0 | 25 |  | 25 | 0 | 10 |  | 10 | 0
PSS-5 Total Scope |  |  | 45773 | 0 | 45773 | 0 | 103107 | 0 | 103107 | 0 | 122 | 0 | 122 | 0 | 78 | 0 | 78 | 0 | Total | 74955 | 0 | 74955 | 0
Sr. No. | Feeder(PSS-11) | Agency Name | Excavation |  |  |  | HTCable Laying |  |  |  | Cable Joint |  |  |  | Cable Termination |  |  |  | Feeder (PSS-11) | FO Cable Laying
|  |  | Scope | Today | Cumulative | Balance | Scope | Today | Cumulative | Balance | Scope | Today | Cumulative | Balance | Scope | Today | Cumulative | Balance |  | Scope | Today | Cumulative | Balance
I | PSS-11
1 | FDR-1 | Akshar | 11960 | 0 | 1500 | 10460 | 20100 | 0 | 20100 | 0 | 24 | 0 | 27 | -3 | 10 | 0 | 10 | 0 | RING-01 | 19860 |  | 19860 | 0
2 | FDR-2 | Akshar | 7990 | 0 | 2300 | 5690 | 16030 | 0 | 16030 | 0 | 18 | 0 | 18 | 0 | 10 | 0 | 10 | 0 | RING-02 | 18135 |  | 18135 | 0
3 | FDR-3 | Akshar | 6760 | 0 | 1860 | 4900 | 12530 | 0 | 12530 | 0 | 14 | 0 | 14 | 0 | 10 | 0 | 10 | 0 | RING-03 | 14800 |  | 14800 | 0
4 | FDR-4 | Akshar | 9150 | 0 | 2882 | 6268 | 12690 | 0 | 12690 | 0 | 14 | 0 | 14 | 0 | 10 | 0 | 10 | 0 | RING-04 | 19100 |  | 19100 | 0
5 | FDR-5 | Akshar | 5280 | 0 | 1820 | 3460 | 5280 | 0 | 5280 | 0 | 5 | 0 | 6 | -1 | 6 | 0 | 6 | 0
6 | FDR-6 | Bajrang | 8970 | 0 | 2200 | 6770 | 8970 | 0 | 8970 | 0 | 11 | 0 | 11 | 0 | 6 | 0 | 6 | 0
7 | FDR-7 | Sunlec | 8500 | 0 | 4495 | 4005 | 19070 | 0 | 19070 | 0 | 23 | 0 | 28 | -5 | 10 | 0 | 10 | 0
8 | FDR-8 | Supreme | 10250 | 0 | 8829 | 1421 | 15330 | 0 | 15330 | 0 | 18 | 0 | 20 | -2 | 10 | 0 | 10 | 0
PSS-11 Total Scope |  |  | 68860 | 0 | 25886 | 42974 | 110000 | 0 | 110000 | 0 | 127 | 0 | 138 | -11 | 72 | 0 | 72 | 0 | Total | 71895 | 0 | 71895 | 0
Sr. No. | Feeder(PSS-12) | Agency Name | Excavation |  |  |  | HTCable Laying |  |  |  | Cable Joint |  |  |  | Cable Termination |  |  |  | Feeder (PSS-11) | FO Cable Laying
|  |  | Scope | Today | Cumulative | Balance | Scope | Today | Cumulative | Balance | Scope | Today | Cumulative | Balance | Scope | Today | Cumulative | Balance |  | Scope | Today | Cumulative | Balance
I | PSS-12
1 | FDR-1 | Sunlec | 4215 |  | 2800 | 1415 | 19345 | 0 | 19345 | 0 | 25 | 0 | 25 | 0 | 8 | 0 | 8 | 0 | RING-01 | 18925 |  | 18925 | 0
2 | FDR-2 | ICE Cube | 4107 |  | 4550 | -443 | 14995 | 0 | 14995 | 0 | 16 | 0 | 16 | 0 | 10 | 0 | 10 | 0 | RING-02 | 11490 |  | 11490 | 0
3 | FDR-3 | Akshar | 4400 |  | 3800 | 600 | 11420 | 0 | 11420 | 0 | 12 | 0 | 12 | 0 | 10 | 0 | 10 | 0 | RING-03 | 18785 |  | 18785 | 0
4 | FDR-4 | Akshar | 4210 |  | 3310 | 900 | 3905 | 0 | 3905 | 0 | 3 | 0 | 3 | 0 | 6 | 0 | 6 | 0
5 | FDR-5 | Supreme | 4368 |  | 4218 | 150 | 10995 | 0 | 11147 | -152 | 12 | 0 | 12 | 0 | 10 | 0 | 10 | 0
6 | FDR-6 | Decon | 5504 |  | 5000 | 504 | 16675 | 0 | 16675 | 0 | 20 | 0 | 20 | 0 | 10 | 0 | 10 | 0
PSS-12 Total Scope |  |  | 26804 | 0 | 23678 | 3126 | 77335 | 0 | 77487 | -152 | 88 | 0 | 88 | 0 | 54 | 0 | 54 | 0 | Total | 49200 | 0 | 49200 | 0
Sr. No. | Feeder(PSS-14) | Agency Name | Excavation |  |  |  | HTCable Laying |  |  |  | Cable Joint |  |  |  | Cable Termination |  |  |  | Feeder (PSS-11) | FO Cable Laying
|  |  | Scope | Today | Cumulative | Balance | Scope | Today | Cumulative | Balance | Scope | Today | Cumulative | Balance | Scope | Today | Cumulative | Balance |  | Scope | Today | Cumulative | Balance
I | PSS-14
1 | FDR-1 | Ice Cube | 6798 | 0 | 1700 | 5098 | 10040 | 0 | 4661 | 5379 | 10 | 0 | 0 | 10 | 10 | 0 |  | 10 | RING-01 | 20790 |  |  | 20790
2 | FDR-2 | Ice Cube | 6128 | 0 | 3300 | 2828 | 13560 | 0 | 5355 | 8205 | 15 | 0 | 0 | 15 | 10 | 0 |  | 10 | RING-02 | 17055 |  |  | 17055
3 | FDR-3 | Bajrang | 4741 | 0 |  | 4741 | 14315 | 0 | 0 | 14315 | 17 | 0 | 0 | 17 | 10 | 0 |  | 10 | RING-03 | 18090 |  |  | 18090
4 | FDR-4 | Sun Electrical | 5511 | 0 |  | 5511 | 19640 | 0 | 0 | 19640 | 24 | 0 | 0 | 24 | 10 | 0 |  | 10 | RING-04 | 16510 |  |  | 16510
5 | FDR-5 | Sunlec | 4461 | 0 |  | 4461 | 16600 | 0 | 0 | 16600 | 19 | 0 | 0 | 19 | 10 | 0 |  | 10 | RING-05 | 18780 |  |  | 18780
6 | FDR-6 | Sunlec | 5870 | 0 |  | 5870 | 16085 | 0 | 0 | 16085 | 19 | 0 | 0 | 19 | 10 | 0 |  | 10 | RING-06 | 25155 |  |  | 25155
7 | FDR-7 | Akshar | 5226 | 0 | 3300 | 1926 | 11345 | 0 | 8000 | 3345 | 12 | 0 | 0 | 12 | 10 | 0 |  | 10 | RING-07 | 14855 |  |  | 14855
8 | FDR-8 | Akshar | 6039 | 0 | 3300 | 2739 | 7905 | 0 | 5955 | 1950 | 8 | 0 | 0 | 8 | 10 | 0 |  | 10 | RING-08 | 11535 |  |  | 11535
9 | FDR-9 | Akshar | 5575 | 0 | 1200 | 4375 | 8060 | 0 | 7610 | 450 | 8 | 0 | 0 | 8 | 10 | 0 |  | 10
10 | FDR-10 | Decon | 5550 | 0 |  | 5550 | 9145 | 0 | 0 | 9145 | 10 | 0 | 0 | 10 | 10 | 0 |  | 10
11 | FDR-11 | Gopal J. Dabhi | 5061 | 0 | 2500 | 2561 | 12340 | 0 | 6266 | 6074 | 15 | 0 | 0 | 15 | 10 | 0 |  | 10
12 | FDR-12 | Akshar | 5865 | 0 | 500 | 5365 | 17200 | 0 | 1557 | 15643 | 19 | 0 | 0 | 19 | 10 | 0 |  | 10
13 | FDR-13 | Supreme | 10570 | 0 | 5350 | 5220 | 14310 | 0 | 8934 | 5376 | 18 | 0 | 0 | 18 | 10 | 0 |  | 10
14 | FDR-14 | Supreme | 5306 | 0 | 3750 | 1556 | 18590 | 0 | 16964 | 1626 | 22 | 0 | 0 | 22 | 10 | 0 |  | 10
15 | FDR-15 | Supreme | 3314 | 0 | 2400 | 914 | 11675 | 0 | 11675 | 0 | 14 | 0 | 0 | 14 | 6 | 0 |  | 6
PSS-14 Total Scope |  |  | 86015 | 0 | 27300 | 58715 | 200810 | 0 | 76977 | 123833 | 230 | 0 | 0 | 230 | 146 | 0 | 0 | 146 | Total | 142770 | 0 | 0 | 142770
Sr. No. | Feeder(PSS-09) | Agency Name | Excavation |  |  |  | HTCable Laying |  |  |  | Cable Joint |  |  |  | Cable Termination |  |  |  | Feeder(PSS-11) | FO Cable Laying
|  |  | Scope | Today | Cumulative | Balance | Scope | Today | Cumulative | Balance | Scope | Today | Cumulative | Balance | Scope | Today | Cumulative | Balance |  | Scope | Today | Cumulative | Balance
I | PSS-09
1 | FDR-1 | Akshar | 4211 |  | 3600 | 611 | 4350 |  | 4350 | 0 | 5 |  | 5 | 0 | 4 |  | 4 | 0 | Ring-1 | 2225 |  | 2225 | 0
PSS-14 Total Scope |  |  | 4211 | 0 | 3600 | 611 | 4350 | 0 | 4350 | 0 | 5 | 0 | 5 | 0 | 4 | 0 | 4 | 0 | Total | 2225 | 0 | 2225 | 0

## 33KV HT Cable
S # | CABLE FROM | CABLE TO | TOTAL LENGTH (METER) | TERMINATION END | JOINTING KIT | Today | Cumulative | Balance | Jointing Cumulative | Jointing Balance | Termination cumulative | Termination Balance
PSS-08
A | Feeder nos 10:33kV Switchgear 05-IC09
1 | WTG141:LBS(O/G) | WTG164:LBS(I/C) | 1425 | 2 | 1 |  | 1200 | 225 |  | 1 | 1 | 1
2 | WTG164:LBS(O/G) | WTG186:LBS(O/G) | 1410 | 2 | 1 |  | 1200 | 210 | 1 | 0 | 1 | 1
3 | WTG186:LBS(O/G) | Switchgear 05-IC09 | 7580 | 2 | 10 | 775 | 4200 | 3380 |  | 10 | 1 | 1
4 | WTG208:LBS(O/G) | WTG230:LBS(I/C) | 1460 | 2 | 1 |  |  | 1460 |  | 1 |  | 2
5 | WTG230:LBS(O/G) | Switchgear 05-IC09 | 5925 | 2 | 7 | 750 | 4000 | 1925 |  | 7 | 1 | 1
B | Feeder nos 11:33kV Switchgear 07-IC09
1 | WTG121:LBS(O/G) | WTG145:LBS(I/C) | 4580 | 2 | 6 |  | 4580 | 0 | 3 | 3 |  | 2
2 | WTG145:LBS(O/G) | Switchgear 07-IC09 | 7820 | 2 | 10 |  | 7820 | 0 | 10 | 0 | 2 | 0
3 | WTG123:LBS(O/G) | WTG143:LBS(I/C) | 2575 | 2 | 3 |  | 2575 | 0 | 3 | 0 | 2 | 0
4 | WTG143:LBS(O/G) | WTG144:LBS(I/C) | 1370 | 2 | 1 |  | 1370 | 0 | 1 | 0 | 2 | 0
5 | WTG144:LBS(O/G) | Switchgear 07-IC09 | 6980 | 2 | 9 |  | 6980 | 0 | 9 | 0 | 2 | 0
C | Feeder nos 12:33kV Switchgear 08-IC04
1 | WTG400:LBS(O/G) | WTG376:LBS(I/C) | 1830 | 2 | 2 |  | 1830 | 0 | 2 | 0 | 2 | 0
2 | WTG376:LBS(O/G) | Switchgear 08-IC04 | 5615 | 2 | 7 |  | 5615 | 0 | 9 | -2 | 2 | 0
D | Feeder nos 13:33kV Switchgear 07-IC03
1 | WTG352:LBS(O/G) | WTG351:LBS(I/C) | 1335 | 2 | 1 |  | 1335 | 0 | 1 | 0 | 2 | 0
2 | WTG351:LBS(O/G) | WTG326:LBS(I/C) | 1145 | 2 | 1 |  | 1145 | 0 | 1 | 0 | 2 | 0
3 | WTG326:LBS(O/G) | Switchgear 07-IC03 | 3785 | 2 | 5 |  | 3785 | 0 | 5 | 0 | 2 | 0
4 | WTG327:LBS(O/G) | WTG302:LBS(I/C) | 3100 | 2 | 4 |  | 3100 | 0 | 4 | 0 | 2 | 0
5 | WTG302:LBS(O/G) | Switchgear 07-IC03 | 3995 | 2 | 5 |  | 3995 | 0 | 5 | 0 | 2 | 0
Total |  |  | 61930 | 34 | 74 | 1525 | 54730 | 7200 | 54 | 20 | 26 | 8
PSS 5
S # | CABLE FROM | CABLE TO | TOTAL LENGTH (METER) | TERMINATION END | JOINTING KIT | Today | Cumulative | Balance | Jointing Cumulative | Jointing Balance | Termination cumulative | Termination Balance
A | Feeder nos 01:33kV Switchgear 05-IC01
1 | WTG551:LBS(O/G) | WTG002:LBS(I/C) | 1225 | 2 | 1 |  | 1225 | 0 | 1 | 0 | 2 | 0
2 | WTG002:LBS(O/G) | WTG132:LBS(O/G) | 1190 | 2 | 1 |  | 1190 | 0 | 1 | 0 | 2 | 0
3 | WTG132:LBS(O/G) | Switchgear 05-IC01 | 6179 | 2 | 7 |  | 6179 | 0 | 7 | 0 | 2 | 0
4 | WTG553:LBS(O/G) | WTG552:LBS(I/C) | 2595 | 2 | 3 |  | 2595 | 0 | 3 | 0 | 2 | 0
5 | WTG552:LBS(O/G) | Switchgear 05-IC01 | 4728 | 2 | 6 |  | 4728 | 0 | 6 | 0 | 2 | 0
B | Feeder nos 02:33kV Switchgear 05-IC14
1 | WTG152:LBS(O/G) | WTG133:LBS(I/C) | 2455 | 2 | 3 |  | 2455 | 0 | 3 | 0 | 2 | 0
2 | WTG133:LBS(O/G) | Switchgear 05-IC14 | 3590 | 2 | 4 |  | 3590 | 0 | 4 | 0 | 2 | 0
3 | WTG153:LBS(O/G) | WTG154:LBS(I/C) | 2232 | 2 | 2 |  | 2232 | 0 | 2 | 0 | 2 | 0
4 | WTG154:LBS(O/G) | Switchgear 05-IC14 | 2739 | 2 | 3 |  | 2739 | 0 | 3 | 0 | 2 | 0
C | Feeder nos 03:33kV Switchgear 07-IC14
1 | WTG131:LBS(O/G) | WTG175:LBS(I/C) | 3070 | 2 | 4 |  | 3070 | 0 | 4 | 0 | 2 | 0
2 | WTG176:LBS(O/G) | WTG175:LBS(I/C) | 1865 | 2 | 2 |  | 1865 | 0 | 2 | 0 | 2 | 0
3 | WTG175:LBS(O/G) | Switchgear 07-IC14 | 3655 | 2 | 5 |  | 3655 | 0 | 5 | 0 | 2 | 0
4 | WTG197:LBS(O/G) | WTG198:LBS(I/C) | 1375 | 2 | 1 |  | 1375 | 0 | 1 | 0 | 2 | 0
5 | WTG198:LBS(O/G) | Switchgear 07-IC14 | 1435 | 2 | 3 |  | 1435 | 0 | 3 | 0 | 2 | 0
D | Feeder nos 04:33kV Switchgear 08-IC01
1 | WTG178:LBS(O/G) | WTG177:LBS(I/C) | 1335 | 2 | 1 |  | 1335 | 0 | 1 | 0 | 2 | 0
2 | WTG177:LBS(O/G) | WTG199:LBS(I/C) | 1090 | 2 | 1 |  | 1090 | 0 | 1 | 0 | 2 | 0
3 | WTG199:LBS(O/G) | Switchgear 08-IC01 | 815 | 2 | 1 |  | 815 | 0 | 1 | 0 | 2 | 0
4 | WTG200:LBS(O/G) | WTG221:LBS(I/C) | 1860 | 2 | 2 |  | 1860 | 0 | 2 | 0 | 2 | 0
5 | WTG221:LBS(O/G) | Switchgear 08-IC01 | 1155 | 2 | 1 |  | 1155 | 0 | 1 | 0 | 2 | 0
E | Feeder nos 05:33kV Switchgear 07-IC01
1 | WTG554:LBS(O/G) | WTG155:LBS(I/C) | 2323 | 2 | 2 |  | 2323 | 0 | 2 | 0 | 2 | 0
2 | WTG155:LBS(O/G) | WTG555:LBS(I/C) | 1605 | 2 | 2 |  | 1605 | 0 | 2 | 0 | 2 | 0
3 | WTG555:LBS(O/G) | Switchgear 07-IC01 | 5335 | 2 | 7 |  | 5335 | 0 | 7 | 0 | 2 | 0
4 | WTG179:LBS(O/G) | WTG156:LBS(I/C) | 1525 | 2 | 2 |  | 1525 | 0 | 2 | 0 | 2 | 0
5 | WTG156:LBS(O/G) | Switchgear 07-IC01 | 3950 | 2 | 6 |  | 3950 | 0 | 6 | 0 | 2 | 0
F | Feeder nos 06:33kV Switchgear 06-IC14
1 | WTG267:LBS(O/G) | WTG266:LBS(I/C) | 1350 | 2 | 1 |  | 1350 | 0 | 1 | 0 | 2 | 0
2 | WTG266:LBS(O/G) | WTG243:LBS(I/C) | 1130 | 2 | 1 |  | 1130 | 0 | 1 | 0 | 2 | 0
3 | WTG243:LBS(O/G) | Switchgear 06-IC14 | 2090 | 2 | 2 |  | 2090 | 0 | 2 | 0 | 2 | 0
4 | WTG244:LBS(O/G) | WTG222:LBS(I/C) | 3115 | 2 | 4 |  | 3115 | 0 | 4 | 0 | 2 | 0
5 | WTG222:LBS(O/G) | Switchgear 06-IC14 | 2335 | 2 | 3 |  | 2335 | 0 | 3 | 0 | 2 | 0
G | Feeder nos 07:33kV Switchgear 08-IC14
1 | WTG316:LBS(O/G) | WTG315:LBS(I/C) | 1645 | 2 | 2 |  | 1645 | 0 | 2 | 0 | 2 | 0
2 | WTG314:LBS(O/G) | WTG315:LBS(I/C) | 1686 | 2 | 2 |  | 1686 | 0 | 2 | 0 | 2 | 0
3 | WTG315:LBS(O/G) | Switchgear 08-IC14 | 4880 | 2 | 6 |  | 4880 | 0 | 6 | 0 | 2 | 0
4 | WTG291:LBS(O/G) | WTG290:LBS(I/C) | 1345 | 2 | 1 |  | 1345 | 0 | 1 | 0 | 2 | 0
5 | WTG290:LBS(O/G) | Switchgear 08-IC14 | 3930 | 2 | 5 |  | 3930 | 0 | 5 | 0 | 2 | 0
H | Feeder nos 08:33kV Switchgear 06-IC01
1 | WTG292:LBS(O/G) | WTG268:LBS(I/C) | 2530 | 2 | 3 |  | 2530 | 0 | 3 | 0 | 2 | 0
2 | WTG268:LBS(O/G) | WTG245:LBS(I/C) | 2340 | 2 | 3 |  | 2340 | 0 | 3 | 0 | 2 | 0
3 | WTG245:LBS(O/G) | Switchgear 06-IC01 | 7765 | 2 | 10 |  | 7765 | 0 | 10 | 0 | 2 | 0
4 | WTG223:LBS(O/G) | WTG201:LBS(I/C) | 1915 | 2 | 2 |  | 1915 | 0 | 2 | 0 | 2 | 0
5 | WTG201:LBS(O/G) | Switchgear 06-IC01 | 5725 | 2 | 7 |  | 5725 | 0 | 7 | 0 | 2 | 0
Total |  |  | 103107 | 78 | 122 | 0 | 103107 | 0 | 122 | 0 | 78 | 0
PSS 11
SR. NO. | CABLE FROM | CABLE TO | TOTAL LENGTH (METER) | TERMINATION END | JOINTING KIT | Today | Cumulative | Balance | Jointing Cumulative | Jointing Balance | Termination cumulative | Termination Balance
A | Feeder nos 01:33kV Switchgear 06-IC01 |  | 20100 |  |  |  | 20100 |  | 27
1 | WTG328:HTP(O/G) | WTG329:HTP(I/C) | 1370 | 2 | 2 |  | 1370 | 0 | 2 | 0 | 2 | 0
2 | WTG329:HTP(O/G) | Switchgear 06-IC01 | 8280 | 2 | 11 |  | 8280 | 0 | 11 | 0 | 2 | 0
3 | WTG353:HTP(O/G) | WTG354:HTP(I/C) | 1360 | 2 | 2 |  | 1360 | 0 | 2 | 0 | 2 | 0
4 | WTG378:HTP(O/G) | WTG354:HTP(I/C) | 1730 | 2 | 3 |  | 1730 | 0 | 3 | 0 | 2 | 0
5 | WTG354:HTP(O/G) | Switchgear 06-IC01 | 7360 | 2 | 9 |  | 7360 | 0 | 9 | 0 | 2 | 0
B | Feeder nos 02:33kV Switchgear 05-IC17 |  | 16030 |  |  |  | 16030 |  | 18
1 | WTG380:HTP(O/G) | WTG379:HTPI(/C) | 1330 | 2 | 1 |  | 1330 | 0 | 1 | 0 | 2 | 0
2 | WTG379:HTP(O/G) | Switchgear 05-IC17 | 6470 | 2 | 8 |  | 6470 | 0 | 8 | 0 | 2 | 0
3 | WTG403:HTP(O/G) | WTG404:HTP(I/C) | 1310 | 2 | 1 |  | 1310 | 0 | 1 | 0 | 2 | 0
4 | WTG405:HTP(O/G) | WTG404:HTP(I/C) | 1350 | 2 | 1 |  | 1350 | 0 | 1 | 0 | 2 | 0
5 | WTG404:HTP(O/G) | Switchgear 05-IC14 | 5570 | 2 | 7 |  | 5570 | 0 | 7 | 0 | 2 | 0
C | Feeder nos 03:33kV Switchgear 05-IC01 |  | 12530 |  |  |  | 12530 |  | 14
1 | WTG429:HTP(O/G) | WTG430:HTP(I/C) | 1320 | 2 | 1 |  | 1320 | 0 | 1 | 0 | 2 | 0
2 | WTG431:HTP(O/G) | WTG430:HTP(I/C) | 1340 | 2 | 1 |  | 1340 | 0 | 1 | 0 | 2 | 0
3 | WTG430:HTP(O/G) | Switchgear 05-IC01 | 4720 | 2 | 6 |  | 4720 | 0 | 6 | 0 | 2 | 0
4 | WTG454:HTP(O/G) | WTG455:HTP(I/C) | 1300 | 2 | 1 |  | 1300 | 0 | 1 | 0 | 2 | 0
5 | WTG455:HTP(O/G) | Switchgear 05-IC01 | 3850 | 2 | 5 |  | 3850 | 0 | 5 | 0 | 2 | 0
D | Feeder nos 04:33kV Switchgear 08-IC17 |  | 12690 |  |  |  | 12690 |  | 14
1 | WTG456:HTP(O/G) | WTG481:HTP(I/C) | 3110 | 2 | 4 |  | 3110 | 0 | 4 | 0 | 2 | 0
2 | WTG481:HTP(O/G) | Switchgear 08-IC17 | 3710 | 2 | 4 |  | 3710 | 0 | 4 | 0 | 2 | 0
3 | WTG479:HTP(O/G) | WTG480:HTP(I/C) | 1320 | 2 | 1 |  | 1320 | 0 | 1 | 0 | 2 | 0
4 | WTG502:HTP(O/G) | WTG480:HTP(I/C) | 1720 | 2 | 2 |  | 1720 | 0 | 2 | 0 | 2 | 0
5 | WTG480:HTP(O/G) | Switchgear 08-IC17 | 2830 | 2 | 3 |  | 2830 | 0 | 3 | 0 | 2 | 0
E | Feeder nos 05:33kV Switchgear 07-IC17 |  | 5280 |  |  |  | 5280 |  | 6
1 | WTG504:HTP(O/G) | WTG503:HTP(I/C) | 1460 | 2 | 2 |  | 1460 | 0 | 2 | 0 | 2 | 0
2 | WTG523:HTP(O/G) | WTG503:HTP(I/C) | 1830 | 2 | 2 |  | 1830 | 0 | 2 | 0 | 2 | 0
3 | WTG503:HTP(O/G) | Switchgear 07-IC17 | 1990 | 2 | 2 |  | 1990 | 0 | 2 | 0 | 2 | 0
F | Feeder nos 06:33kV Switchgear 07-IC01 |  | 8970 |  |  |  | 8970 |  | 11
1 | WTG501:HTP(O/G) | WTG522:HTP(I/C) | 3160 | 2 | 4 |  | 3160 | 0 | 4 | 0 | 2 | 0
2 | WTG522:HTP(O/G) | WTG524:HTP(I/C) | 4830 | 2 | 6 |  | 4830 | 0 | 6 | 0 | 2 | 0
3 | WTG524:HTP(O/G) | Switchgear 07-IC01 | 980 | 2 | 1 |  | 980 | 0 | 1 | 0 | 2 | 0
G | Feeder nos 07:33kV Switchgear 08-IC01 |  | 19070 |  |  |  | 19070 |  | 28
1 | WTG381:HTP(O/G) | WTG382:HTP(I/C) | 1370 | 2 | 2 |  | 1370 | 0 | 2 | 0 | 2 | 0
2 | WTG382:HTP(O/G) | Switchgear 08-IC01 | 7760 | 2 | 12 |  | 7760 | 0 | 12 | 0 | 2 | 0
3 | WTG406:HTP(O/G) | WTG407:HTP(I/C) | 1370 | 2 | 2 |  | 1370 | 0 | 2 | 0 | 2 | 0
4 | WTG432:HTP(O/G) | WTG407:HTP(I/C) | 1740 | 2 | 2 |  | 1740 | 0 | 2 | 0 | 2 | 0
5 | WTG407:HTP(O/G) | Switchgear 08-IC01 | 6830 | 2 | 10 |  | 6830 | 0 | 10 | 0 | 2 | 0
H | Feeder nos 08:33kV Switchgear 06-IC17 |  | 15330 |  |  |  | 15330 |  | 20
1 | WTG457:HTP(O/G) | WTG433:HTP(I/C) | 1740 | 2 | 2 |  | 1740 | 0 | 2 | 0 | 2 | 0
2 | WTG433:HTP(O/G) | Switchgear 06-IC17 | 5940 | 2 | 9 |  | 5940 | 0 | 9 | 0 | 2 | 0
3 | WTG482:HTP(O/G) | WTG505:HTP(I/C) | 2940 | 2 | 3 |  | 2940 | 0 | 3 | 0 | 2 | 0
4 | WTG505:HTP(O/G) | WTG233:HTP(I/C) | 3800 | 2 | 5 |  | 3800 | 0 | 5 | 0 | 2 | 0
5 | WTG233:HTP(O/G) | Switchgear 06-IC17 | 910 | 2 | 1 |  | 910 | 0 | 1 | 0 | 2 | 0
Total |  |  | 110000 | 72 | 138 | 0 | 110000 | 0 | 138 | 0 | 72 | 0
PSS 12
SR. NO. | CABLE FROM | CABLE TO | TOTAL LENGTH (METER) | TERMINATION END | JOINTING KIT | Today | Cumulative | Balance | Jointing Cumulative | Jointing Balance | Termination cumulative | Termination Balance
A | Feeder nos 01:33kV Switchgear 01-IC17 |  | 19345 |  |  |  | 19345 |  | 25
1 | WTG377:LBS(O/G) | WTG402:LBS(I/C) | 3125 | 2 | 4 |  | 3125 | 0 | 4 | 0 | 2 | 0
2 | WTG402:LBS(O/G) | Switchgear 01-IC17 | 7700 | 2 | 10 |  | 7700 | 0 | 10 | 0 | 2 | 0
3 | WTG426:LBS(O/G) | WTG401:LBS(I/C) | 1710 | 2 | 2 |  | 1710 | 0 | 2 | 0 | 2 | 0
4 | WTG401:LBS(O/G) | Switchgear 01-IC17 | 6810 | 2 | 9 |  | 6810 | 0 | 9 | 0 | 2 | 0
B | Feeder nos 02:33kV Switchgear 01-IC02 |  | 14995 |  |  |  | 14995 |  | 16
1 | WTG428:LBS(O/G) | WTG427:LBS(I/C) | 1345 | 2 | 1 |  | 1345 | 0 | 1 | 0 | 2 | 0
2 | WTG427:LBS(O/G) | Switchgear 01-IC02 | 5940 | 2 | 7 |  | 5940 | 0 | 7 | 0 | 2 | 0
3 | WTG451:LBS(O/G) | WTG452:LBS(I/C) | 1310 | 2 | 1 |  | 1310 | 0 | 1 | 0 | 2 | 0
3 | WTG453:LBS(O/G) | WTG452:LBS(I/C) | 1350 | 2 | 1 |  | 1350 | 0 | 1 | 0 | 2 | 0
4 | WTG452:LBS(O/G) | Switchgear 01-IC02 | 5050 | 2 | 6 |  | 5050 | 0 | 6 | 0 | 2 | 0
C | Feeder nos 03:33kV Switchgear 03-IC17 |  | 11420 |  |  |  | 11420 |  | 12
1 | WTG476:LBS(O/G) | WTG477:LBS(I/C) | 1320 | 2 | 1 |  | 1320 | 0 | 1 | 0 | 2 | 0
2 | WTG478:LBS(O/G) | WTG477:LBS(I/C) | 1345 | 2 | 1 |  | 1345 | 0 | 1 | 0 | 2 | 0
3 | WTG477:LBS(O/G) | Switchgear 03-IC17 | 4175 | 2 | 5 |  | 4175 | 0 | 5 | 0 | 2 | 0
4 | WTG499:LBS(O/G) | WTG500:LBS(I/C) | 1305 | 2 | 1 |  | 1305 | 0 | 1 | 0 | 2 | 0
5 | WTG500:LBS(O/G) | Switchgear 03-IC17 | 3275 | 2 | 4 |  | 3275 | 0 | 4 | 0 | 2 | 0
D | Feeder nos 04:33kV Switchgear 03-IC02 |  | 3905 |  |  |  | 3905 |  | 3
1 | WTG520:LBS(O/G) | WTG521:LBS(I/C) | 1315 | 2 | 1 |  | 1315 | 0 | 1 | 0 | 2 | 0
2 | WTG521:LBS(O/G) | WTG536:LBS(I/C) | 2085 | 2 | 2 |  | 2085 | 0 | 2 | 0 | 2 | 0
3 | WTG536:LBS(O/G) | Switchgear 03-IC02 | 505 | 2 | 0 |  | 505 | 0 | 0 | 0 | 2 | 0
E | Feeder nos 05:33kV Switchgear 02-IC02 |  | 11147 |  |  |  | 11147 |  | 12
1 | WTG519:LBS(O/G) | WTG518:LBS(I/C) | 1345 | 2 | 1 |  | 1345 | 0 | 1 | 0 | 2 | 0
2 | WTG518:LBS(O/G) | Switchgear 02-IC02 | 3950 | 2 | 5 |  | 3950 | 0 | 5 | 0 | 2 | 0
3 | WTG535:LBS(O/G) | WTG534:LBS(I/C) | 1345 | 2 | 1 |  | 1345 | 0 | 1 | 0 | 2 | 0
4 | WTG533:LBS(O/G) | WTG534:LBS(I/C) | 1305 | 2 | 1 |  | 1305 | 0 | 1 | 0 | 2 | 0
5 | WTG534:LBS(O/G) | Switchgear 02-IC02 | 3202 | 2 | 4 |  | 3202 | 0 | 4 | 0 | 2 | 0
F | Feeder nos 06:33kV Switchgear 02-IC17 |  | 16675 |  |  |  | 16675 |  | 20
1 | WTG475:LBS(O/G) | WTG498:LBS(I/C) | 3120 | 2 | 4 |  | 3120 | 0 | 4 | 0 | 2 | 0
2 | WTG498:LBS(O/G) | Switchgear 02-IC17 | 5710 | 2 | 7 |  | 5710 | 0 | 7 | 0 | 2 | 0
3 | WTG496:LBS(O/G) | WTG497:LBS(I/C) | 1310 | 2 | 1 |  | 1310 | 0 | 1 | 0 | 2 | 0
4 | WTG517:LBS(O/G) | WTG497:LBS(I/C) | 1710 | 2 | 2 |  | 1710 | 0 | 2 | 0 | 2 | 0
5 | WTG497:LBS(O/G) | Switchgear 02-IC17 | 4825 | 2 | 6 |  | 4825 | 0 | 6 | 0 | 2 | 0
Total |  |  | 77487 | 54 | 88 | 0 | 77487 | 0 | 88 | 0 | 54 | 0
PSS 14
SR. NO. | CABLE FROM | CABLE TO | TOTAL LENGTH (METER) | TERMINATION END | JOINTING KIT | Today | Cumulative | Balance | Jointing Cumulative | Jointing Balance | Termination cumulative | Termination Balance
A | Feeder nos 01:33kV Switchgear 01-IC17 |  | 10040 |  |  |  | 4661 |  | 0 |  | 0
1 | KH582:LBS(O/G) | KH583:LBS(I/C) | 1950 | 2 | 2 |  | 600 | 1350 |  | 2 |  | 2
2 | KH590:LBS(O/G) | KH583:LBS(I/C) | 1270 | 2 | 1 |  | 600 | 670 |  | 1 |  | 2
3 | KH583:LBS(O/G) | Switchgear 01-IC17 | 3630 | 2 | 4 |  | 1558 | 2072 |  | 4 |  | 2
4 | KH591:LBS(O/G) | KH598:LBS(I/C) | 1295 | 2 | 1 |  | 777 | 518 |  | 1 |  | 2
5 | KH598:LBS(O/G) | Switchgear 01-IC17 | 1895 | 2 | 2 |  | 1126 | 769 |  | 2 |  | 2
B | Feeder nos 02:33kV Switchgear 01-IC02 |  | 13560 |  |  |  | 5355 |  | 0 |  | 0
1 | KH613:LBS(O/G) | KH600:LBS(I/C) | 2370 | 2 | 3 |  | 700 | 1670 |  | 3 |  | 2
2 | KH592:LBS(O/G) | KH599:LBS(I/C) | 1305 | 2 | 1 |  | 770 | 535 |  | 1 |  | 2
3 | KH600:LBS(O/G) | Switchgear 01-IC02 | 5015 | 2 | 6 |  | 1555 | 3460 |  | 6 |  | 2
4 | KH606:LBS(O/G) | KH599:LBS(I/C) | 1270 | 2 | 1 |  | 775 | 495 |  | 1 |  | 2
5 | KH599:LBS(O/G) | Switchgear 01-IC02 | 3600 | 2 | 4 |  | 1555 | 2045 |  | 4 |  | 2
C | Feeder nos 03:33kV Switchgear 01-IC01 |  | 14315 |  |  |  | 0 |  | 0 |  | 0
1 | KH618:LBS(O/G) | KH614:LBS(I/C) | 1270 | 2 | 1 |  |  | 1270 |  | 1 |  | 2
2 | KH615:LBS(O/G) | KH614:LBS(I/C) | 1625 | 2 | 2 |  |  | 1625 |  | 2 |  | 2
3 | KH614:LBS(O/G) | Switchgear 01-IC01 | 5330 | 2 | 7 |  |  | 5330 |  | 7 |  | 2
4 | KH608:LBS(O/G) | KH607:LBS(I/C) | 1625 | 2 | 2 |  |  | 1625 |  | 2 |  | 2
5 | KH607:LBS(O/G) | Switchgear 01-IC01 | 4465 | 2 | 5 |  |  | 4465 |  | 5 |  | 2
D | Feeder nos 04:33kV Switchgear 03-IC17 |  | 19640 |  |  |  | 0 |  | 0 |  | 0
1 | KH34:LBS(O/G) | KH35:LBS(I/C) | 1485 | 2 | 1 |  |  | 1485 |  | 1 |  | 2
2 | KH622:LBS(O/G) | KH619:LBS(I/C) | 2005 | 2 | 2 |  |  | 2005 |  | 2 |  | 2
3 | KH35:LBS(O/G) | Switchgear 03-IC17 | 8330 | 2 | 11 |  |  | 8330 |  | 11 |  | 2
4 | KH620:LBS(O/G) | KH619:LBS(I/C) | 1625 | 2 | 2 |  |  | 1625 |  | 2 |  | 2
5 | KH619:LBS(O/G) | Switchgear 03-IC17 | 6195 | 2 | 8 |  |  | 6195 |  | 8 |  | 2
E | Feeder nos 05:33kV Switchgear 04-IC02 |  | 16600 |  |  |  | 0 |  | 0 |  | 0
1 | KH521:LBS(O/G) | KH508:LBS(I/C) | 1330 | 2 | 1 |  |  | 1330 |  | 1 |  | 2
2 | KH478:LBS(O/G) | KH508:LBS(I/C) | 1230 | 2 | 1 |  |  | 1230 |  | 1 |  | 2
3 | KH508:LBS(O/G) | Switchgear 04-IC02 | 6790 | 2 | 9 |  |  | 6790 |  | 9 |  | 2
4 | KH522:LBS(O/G) | KH509:LBS(I/C) | 1330 | 2 | 1 |  |  | 1330 |  | 1 |  | 2
5 | KH509:LBS(O/G) | Switchgear 04-IC02 | 5920 | 2 | 7 |  |  | 5920 |  | 7 |  | 2
F | Feeder nos 06:33kV Switchgear 04-IC01 |  | 16085 |  |  |  | 0 |  | 0 |  | 0
1 | KH523:LBS(O/G) | KH554:LBS(I/C) | 1325 | 2 | 1 |  |  | 1325 |  | 1 |  | 2
2 | KH551:LBS(O/G) | KH554:LBS(I/C) | 1910 | 2 | 2 |  |  | 1910 |  | 2 |  | 2
3 | KH554:LBS(O/G) | Switchgear 04-IC01 | 5060 | 2 | 6 |  |  | 5060 |  | 6 |  | 2
4 | KH553:LBS(O/G) | KH556:LBS(I/C) | 2480 | 2 | 3 |  |  | 2480 |  | 3 |  | 2
5 | KH556:LBS(O/G) | Switchgear 04-IC01 | 5310 | 2 | 7 |  |  | 5310 |  | 7 |  | 2
G | Feeder nos 07:33kV Switchgear 02-IC17 |  | 11345 |  |  |  | 8000 |  | 0 |  | 0
1 | KH579:LBS(O/G) | KH555:LBS(I/C) | 1230 | 2 | 1 |  | 1100 | 130 |  | 1 |  | 2
2 | KH557:LBS(O/G) | KH555:LBS(I/C) | 1320 | 2 | 1 |  | 1200 | 120 |  | 1 |  | 2
3 | KH555:LBS(O/G) | Switchgear 02-IC17 | 4195 | 2 | 5 | 800 | 2300 | 1895 |  | 5 |  | 2
4 | KH53:LBS(O/G) | KH580:LBS(I/C) | 1280 | 2 | 1 |  | 1100 | 180 |  | 1 |  | 2
5 | KH580:LBS(O/G) | Switchgear 02-IC17 | 3320 | 2 | 4 | 800 | 2300 | 1020 |  | 4 |  | 2
H | Feeder nos 08:33kV Switchgear 02-IC02 |  | 7905 |  |  |  | 5955 |  | 0 |  | 0
1 | KH581:LBS(O/G) | KH588:LBS(I/C) | 1300 | 2 | 1 |  | 800 | 500 |  | 1 |  | 2
2 | KH54:LBS(O/G) | KH588:LBS(I/C) | 1270 | 2 | 1 |  | 780 | 490 |  | 1 |  | 2
3 | KH588:LBS(O/G) | Switchgear 02-IC02 | 2455 | 2 | 3 |  | 2000 | 455 |  | 3 |  | 2
4 | KH589:LBS(O/G | KH596:LBS(I/C) | 1305 | 2 | 1 |  | 800 | 505 |  | 1 |  | 2
5 | KH596:LBS(O/G) | Switchgear 02-IC02 | 1575 | 2 | 2 |  | 1575 | 0 |  | 2 |  | 2
I | Feeder nos 09:33kV Switchgear 03-IC02 |  | 8060 |  |  |  | 7610 |  | 0 |  | 0
1 | KH597:LBS(O/G) | KH604:LBS(I/C) | 1300 | 2 | 1 |  | 1300 | 0 |  | 1 |  | 2
2 | KH55:LBS(O/G) | KH604:LBS(I/C) | 1950 | 2 | 2 |  | 1800 | 150 |  | 2 |  | 2
3 | KH604:LBS(O/G) | Switchgear 03-IC02 | 700 | 2 | 0 |  | 700 | 0 |  | 0 |  | 2
4 | KH605:LBS(O/G) | KH56:LBS(I/C) | 2500 | 2 | 3 |  | 2200 | 300 |  | 3 |  | 2
5 | KH56:LBS(O/G) | Switchgear 03-IC02 | 1610 | 2 | 2 |  | 1610 | 0 |  | 2 |  | 2
J | Feeder nos 10:33kV Switchgear 03-IC01 |  | 9145 |  |  |  | 0 |  | 0 |  | 0
1 | KH68:LBS(O/G) | KH57:LBS(I/C) | 2125 | 2 | 2 |  |  | 2125 |  | 2 |  | 2
2 | KH617:LBS(O/G) | KH57:LBS(I/C) | 1625 | 2 | 2 |  |  | 1625 |  | 2 |  | 2
3 | KH57:LBS(O/G) | Switchgear 03-IC02 | 2280 | 2 | 3 |  |  | 2280 |  | 3 |  | 2
4 | KH612:LBS(O/G | KH611:LBS(I/C) | 1685 | 2 | 2 |  |  | 1685 |  | 2 |  | 2
5 | KH611:LBS(O/G) | Switchgear 03-IC02 | 1430 | 2 | 1 |  |  | 1430 |  | 1 |  | 2
K | Feeder nos 11:33kV Switchgear 04-IC17 |  | 12340 |  |  |  | 6266 |  | 0 |  | 0
1 | KH60:LBS(O/G) | KH59:LBS(I/C) | 2275 | 2 | 3 |  | 2091 | 184 |  | 3 |  | 2
2 | KH61:LBS(O/G) | KH59:LBS(I/C) | 1240 | 2 | 1 |  | 1194 | 46 |  | 1 |  | 2
3 | KH59:LBS(O/G) | Switchgear 04-IC17 | 4010 | 2 | 5 |  | 1226 | 2784 |  | 5 |  | 2
4 | KH621:LBS(O/G) | KH58:LBS(I/C) | 1655 | 2 | 2 |  | 1575 | 80 |  | 2 |  | 2
5 | KH58:LBS(O/G) | Switchgear 04-IC17 | 3160 | 2 | 4 |  | 180 | 2980 |  | 4 |  | 2
K | Feeder nos 12:33kV Switchgear 02-IC01 |  | 17200 |  |  |  | 1557 |  | 0 |  | 0
6 | KH550:LBS(O/G) | KH47:LBS(I/C) | 1335 | 2 | 1 |  |  | 1335 |  | 1 |  | 2
7 | KH552:LBS(O/G) | KH51:LBS(I/C) | 7430 | 2 | 9 |  |  | 7430 |  | 9 |  | 2
8 | KH47:LBS(O/G) | Switchgear 02-IC01 | 1840 | 2 | 2 |  | 779 | 1061 |  | 2 |  | 2
9 | KH51:LBS(O/G) | KH52:LBS(I/C) | 1435 | 2 | 1 |  |  | 1435 |  | 1 |  | 2
10 | KH52:LBS(O/G) | Switchgear 02-IC01 | 5160 | 2 | 6 |  | 778 | 4382 |  | 6 |  | 2
K | Feeder nos 13:33kV Switchgear 03-IC13 |  | 14310 |  |  |  | 8934 |  | 0 |  | 0
6 | WTG373:LBS(O/G) | WTG423:LBS(I/C) | 1955 | 2 | 2 |  | 1545 | 410 |  | 2 |  | 2
7 | WTG398:LBS(O/G) | WTG423:LBS(I/C) | 1540 | 2 | 2 |  | 770 | 770 |  | 2 |  | 2
8 | WTG423:LBS(O/G) | Switchgear 03-IC13 | 5390 | 2 | 7 |  | 5068 | 322 |  | 7 |  | 2
9 | WTG532:LBS(O/G) | WTG516:LBS(I/C) | 2355 | 2 | 3 |  |  | 2355 |  | 3 |  | 2
10 | WTG516:LBS(O/G) | Switchgear 03-IC13 | 3070 | 2 | 4 |  | 1551 | 1519 |  | 4 |  | 2
K | Feeder nos 14:33kV Switchgear 04-IC08 |  | 18590 |  |  |  | 16964 |  | 0 |  | 0
11 | WTG399:LBS(O/G) | WTG424:LBS(I/C) | 1725 | 2 | 2 |  | 774 | 951 |  | 2 |  | 2
12 | WTG425:LBS(O/G) | WTG424:LBS(I/C) | 1345 | 2 | 1 |  | 1000 | 345 |  | 1 |  | 2
13 | WTG424:LBS(O/G) | Switchgear 04-IC08 | 6660 | 2 | 8 |  | 6976 | -316 |  | 8 |  | 2
14 | WTG448:LBS(O/G) | WTG449:LBS(I/C) | 1310 | 2 | 1 |  | 1238 | 72 |  | 1 |  | 2
15 | WTG449:LBS(O/G) | Switchgear 04-IC08 | 7550 | 2 | 10 |  | 6976 | 574 |  | 10 |  | 2
K | Feeder nos 15:33kV Switchgear 02-IC13 |  | 11740 |  |  |  | 11744 |  | 0 |  | 0
11 | WTG473:LBS(O/G) | WTG474:LBS(I/C) | 1320 | 2 | 1 |  | 1280 | 40 |  | 1 |  | 2
12 | WTG450:LBS(O/G) | WTG474:LBS(I/C) | 1990 | 2 | 2 |  | 1990 | 0 |  | 2 |  | 2
13 | WTG474:LBS(O/G) | Switchgear 02-IC13 | 8430 | 2 | 11 |  | 8474 | -44 |  | 11 |  | 2
Total |  |  | 200875 | 146 | 230 | 1600 | 77046 | 123829 | 0 | 230 | 0 | 146
PSS 09
SR. NO. | CABLE FROM | CABLE TO | TOTAL LENGTH (METER) | TERMINATION END | JOINTING KIT | Today | Cumulative | Balance | Jointing Cumulative | Jointing Balance | Termination cumulative | Termination Balance
A | Feeder nos 01:33kV Switchgear 07-IC12
1 | WTG556:LBS(O/G) | WTG557:LBS(I/C) | 1070 | 2 | 1 |  | 1070 | 0 | 1 | 0 | 2 | 0
2 | WTG557:LBS(O/G) | Switchgear 07-IC12 | 3280 | 2 | 4 |  | 3280 | 0 | 4 | 0 | 2 | 0
Total |  |  | 4350 | 4 | 5 | 0 | 4350 | 0 | 5 | 0 | 4 | 0

## 33KV FO Cable (hidden)
PSS 8 |  |  |  |  | PSS 11 |  |  |  | PSS 12 |  |  |  | PSS 14
FO CABLE |  |  |  |  | FO CABLE |  |  |  | FO CABLE |  |  |  | FO CABLE
From Block | To Block | Total Length (meter) |  | Actual completion (meter) | From Block | To Block | Total Length (meter) | Actual completion (meter) | From WTG | To WTG | Total Length (meter) | Actual completion (meter) | From WTG | To WTG | Total Length (meter) | Actual completion (meter)
Ring-1 (F10) |  |  |  |  | Ring-1 (F1,F2) |  |  |  | Ring-1 (F1,F2) |  |  |  | Ring-1 (F5,F6)
| WTG 141 | 50 |  |  |  | WTG 328 | 50 |  |  | WTG 377 | 50 |  | PSS14 | KH 554 | 5070
WTG 141 | WTG 164 | 1320 |  |  | WTG 328 | WTG 329 | 1270 |  | WTG 377 | WTG 401 | 1845 |  | KH 554 | KH 556 | 1545
WTG 164 | WTG186 | 1310 |  |  | WTG 329 | WTG 353 | 1640 |  | WTG 401 | WTG 402 | 1245 |  | KH 556 | KH 553 | 2380
WTG186 | WTG208 | 1410 |  |  | WTG 353 | WTG 354 | 1260 |  | WTG 402 | WTG 426 | 2495 |  | KH 553 | KH 523 | 2250
WTG208 | WTG230 | 1350 |  |  | WTG 354 | WTG 378 | 1630 |  | WTG 426 | WTG 427 | 1215 |  | KH 523 | KH 551 | 2380
WTG230 | PSS8 | 5160 |  |  | WTG 378 | WTG 379 | 1270 |  | WTG 427 | WTG 428 | 1245 |  | KH 551 | KH 509 | 1130
Total Length (Ring-1) |  | 10600 |  | 0 | WTG 379 | WTG 380 | 1230 |  | WTG 428 | WTG 451 | 2495 |  | KH 509 | KH 522 | 1225
Ring-2 (F11) |  |  |  |  | WTG 380 | WTG 403 | 2550 |  | WTG 451 | WTG 452 | 1205 |  | KH 522 | KH 478 | 2400
| WTG 123 | 50 |  |  | WTG 403 | WTG 404 | 1210 |  | WTG 452 | WTG 453 | 1250 |  | KH 478 | KH 508 | 1135
WTG 123 | WTG 143 | 2470 |  |  | WTG 404 | WTG 405 | 1250 |  | WTG 453 | PSS12 | 5880 |  | KH 508 | KH 521 | 1225
WTG 143 | WTG 144 | 1270 |  |  | WTG 405 | PSS11 | 6500 |  | Total Length (Ring-1) |  | 18925 |  | KH 521 |  | 50
WTG 144 | WTG 145 | 1220 |  |  | Total Length (Ring-1) |  | 19860 |  | Ring-2 (F3,F4) |  |  |  | Total Length (Ring-1) |  | 20790
WTG 145 | WTG 121 | 4480 |  |  | Ring-2 (F3,F4) |  |  |  |  | WTG 476 | 50 |  | Ring-2 (F12,F7)
WTG 121 | PSS8 | 9195 |  |  |  | WTG 429 | 50 |  | WTG 476 | WTG 477 | 1220 |  | PSS14 | KH 580 | 3330
Total Length (Ring-2) |  | 18685 |  | 0 | WTG 429 | WTG 430 | 1215 |  | WTG 477 | WTG 478 | 1245 |  | KH 580 | KH 557 | 1215
Ring-3 (F12, F13) |  |  |  |  | WTG 430 | WTG 431 | 1245 |  | WTG 478 | WTG 499 | 2495 |  | KH 557 | KH 579 | 2375
PSS8 | WTG302 | 3240 |  |  | WTG 431 | WTG 454 | 2495 |  | WTG 499 | WTG 500 | 1205 |  | KH 579 | KH 555 | 1130
WTG302 | WTG 326 | 1870 |  |  | WTG 454 | WTG 455 | 1200 |  | WTG 500 | WTG 520 | 1615 |  | KH 555 | KH 53 | 2055
WTG 326 | WTG 327 | 1230 |  |  | WTG 455 | WTG 456 | 1355 |  | WTG 520 | WTG 521 | 1215 |  | KH 53 | KH 52 | 1150
WTG 327 | WTG 351 | 1885 |  |  | WTG 456 | WTG 479 | 2495 |  | WTG 521 | WTG 536 | 1985 |  | KH 52 | KH 51 | 1335
WTG 351 | WTG 352 | 1235 |  |  | WTG 479 | WTG 480 | 1215 |  | WTG 536 | PSS12 | 460 |  | KH 51 | KH 552 | 1740
WTG 352 | WTG 376 | 1870 |  |  | WTG 480 | WTG 481 | 1245 |  | Total Length (Ring-2) |  | 11490 |  | KH 552 | KH 47 | 1435
WTG 376 | WTG 400 | 1730 |  |  | WTG 481 | WTG 502 | 2495 |  | Ring-3 (F5,F6) |  |  |  | KH 47 | KH 550 | 1240
WTG 400 |  | 50 |  |  | WTG 502 | PSS11 | 3125 |  |  | WTG 475 | 50 |  | KH 550 |  | 50
Total Length (Ring-3) |  | 13110 |  | 0 | Total Length (Ring-2) |  | 18135 |  | WTG 475 | WTG 496 | 2500 |  | Total Length (Ring-2) |  | 17055 |  | Meter
[5 empty] | Ring-3 (F5,F6) |  |  |  | WTG 496 | WTG 497 | 1210 |  | Ring-3 (F4,F3)
Total Length (Ring-1+2+3 ) |  | 42395 |  | 0 |  | WTG 501 | 50 |  | WTG 497 | WTG 498 | 1245 |  | PSS14 | KH 607 | 4150
[5 empty] | WTG 501 | WTG 522 | 2955 |  | WTG 498 | WTG 517 | 2495 |  | KH 607 | KH608 | 1525
[5 empty] | WTG 522 | WTG 524 | 4725 |  | WTG 517 | WTG 518 | 1215 |  | KH608 | KH 614 | 1200
[5 empty] | WTG 524 | WTG 523 | 1215 |  | WTG 518 | WTG 519 | 1245 |  | KH 614 | KH 618 | 1175
PSS 05 |  |  |  |  | WTG 523 | WTG 504 | 2495 |  | WTG 519 | WTG 533 | 2495 |  | KH 618 | KH 615 | 2395
FO CABLE |  |  |  |  | WTG 504 | WTG 503 | 1355 |  | WTG 533 | WTG 534 | 1210 |  | KH 615 | KH 619 | 1200
From Block | To Block | Total Length (meter) | Actual completion (meter) |  | WTG 503 | PSS11 | 2005 |  | WTG 534 | WTG 535 | 1245 |  | KH 619 | KH 620 | 1520
Ring-1 (F6,F7) |  |  |  |  | Total Length (Ring-3) |  | 14800 |  | WTG 535 | PSS12 | 3875 |  | KH 620 | KH 622 | 2130
PSS05 | WTG 222 | 2625 |  |  | Ring-4 (F7,F8) |  |  |  | Total Length (Ring-3) |  | 18785 |  | KH 622 | KH 35 | 1560
WTG 222 | WTG 243 | 1855 |  |  | From Block | To Block | Total Length (meter) | Remarks | Total Length (Ring-1+2+3 ) |  | 49200 |  | KH 35 | KH 34 | 1185
WTG 243 | WTG 244 | 1245 |  |  |  | WTG 381 | 50 | [5 empty] | KH 34 |  | 50
WTG 244 | WTG 266 | 1865 |  |  | WTG 381 | WTG 382 | 1265 | [5 empty] | Total Length (Ring-3) |  | 18090 |  | Meter
WTG 266 | WTG 267 | 1250 |  |  | WTG 382 | WTG 406 | 1640 | [5 empty] | Ring-4 (F10,F11,F13)
WTG 267 | WTG 290 | 1850 |  |  | WTG 406 | WTG 407 | 1265 | [5 empty] | PSS14 | KH 612 | 2880
WTG 290 | WTG 291 | 1250 |  |  | WTG 407 | WTG 432 | 1635 | [5 empty] | KH 612 | KH 57 | 1205
WTG 291 | WTG 314 | 2500 |  |  | WTG 432 | WTG 433 | 1270 | [5 empty] | KH 57 | KH 532 | 1835
WTG 314 | WTG 315 | 1305 |  |  | WTG 433 | WTG 457 | 1635 | [5 empty] | KH 532 | KH 68 | 1145
WTG 315 | WTG 316 | 1545 |  |  | WTG 457 | WTG 482 | 2830 | [5 empty] | KH 68 | KH617 | 2290
WTG 316 |  | 50 |  |  | WTG 482 | WTG 505 | 2840 | [5 empty] | KH617 | KH 58 | 1205
Total Length (Ring-1) |  | 17340 | 0 |  | WTG 505 | WTG 233 | 3695 | [5 empty] | KH 58 | KH 621 | 1555
Ring-2 (F5,F8) |  |  |  |  | WTG 233 | PSS11 | 975 | [5 empty] | KH 621 | KH 59 | 1205
PSS05 | WTG 156 | 4265 |  |  | Total Length (Ring-4) |  | 19100 | [5 empty] | KH 59 | KH 61 | 1140
WTG 156 | WTG 155 | 2445 | [10 empty] | KH 61 | KH 60 | 2000
WTG 155 | WTG 554 | 2045 |  |  | Total Length (Ring-1+2+3+4 ) |  | 71895 | [5 empty] | KH 60 |  | 50
WTG 554 | WTG 555 | 1925 | [10 empty] | Total Length (Ring-4) |  | 16510 |  | Meter
WTG 555 | WTG 179 | 2225 | [10 empty] | Ring-5 (F1,F2)
WTG 179 | WTG 201 | 1735 | [10 empty] | PSS14 | KH 598 | 1500
WTG 201 | WTG 223 | 1820 | [10 empty] | KH 598 | KH 591 | 1195
WTG 223 | WTG 245 | 2005 | [10 empty] | KH 591 | KH 590 | 1845
WTG 245 | WTG 268 | 2240 | [10 empty] | KH 590 | KH 582 | 2910
WTG 268 | WTG 292 | 2435 | [10 empty] | KH 582 | KH583 | 1850
WTG 292 |  | 50 | [10 empty] | KH583 | KH 592 | 2390
Total Length (Ring-2) |  | 23190 | 0 | [9 empty] | KH 592 | KH 599 | 1200
Ring-3 (F4) | [12 empty] | KH 599 | KH 606 | 1175
PSS05 | WTG 221 | 1450 | [10 empty] | KH 606 | KH 600 | 2395
WTG 221 | WTG 200 | 1760 | [10 empty] | KH 600 | KH 613 | 2270
WTG 200 | WTG 199 | 1315 | [10 empty] | KH 613 |  | 50
[13 empty] | Total Length (Ring-5) |  | 18780
WTG 199 | WTG 178 | 1780 | [10 empty] | Ring-6 (F15,F13,F10,F09)
WTG 178 | WTG 177 | 1235 | [10 empty] | PSS14 | KH 56 | 1655
WTG 177 |  | 50 | [10 empty] | KH 56 | KH 605 | 2395
Total Length (Ring-3) |  | 7590 | 0 | [9 empty] | KH 605 | KH 611 | 1225
Ring-4 (F3) | [12 empty] | KH 611 | WTG 516 | 4170
PSS05 | WTG198 | 1095 | [10 empty] | WTG 516 | WTG423 | 4295
WTG198 | WTG 197 | 1280 | [10 empty] | WTG423 | WTG 373 | 1860
WTG 197 | WTG 176 | 2045 | [10 empty] | WTG 373 | WTG 398 | 2660
WTG 176 | WTG 175 | 1770 | [10 empty] | WTG 398 | WTG 450 | 3235
WTG 175 | WTG 131 | 2970 | [10 empty] | WTG 450 | WTG 473 | 2395
WTG 131 |  | 50 | [10 empty] | WTG 473 | WTG 474 | 1215
Total Length (Ring-4) |  | 9210 | 0 | [9 empty] | WTG 474 |  | 50
Ring-5 (F1,F2) | [12 empty] | Total Length (Ring-6) |  | 25155 |  | 25155
PSS05 | WTG 154 | 2970 | [10 empty] | Ring-7 (F14,F09)
WTG 154 | WTG152 | 2565 | [10 empty] | PSS14 | WTG 424 | 6670
WTG152 | WTG 153 | 1505 | [10 empty] | WTG 424 | WTG 399 | 1625
WTG 153 | WTG 133 | 1705 | [10 empty] | WTG 399 | WTG 425 | 2805
WTG 133 | WTG 553 | 2200 | [10 empty] | WTG 425 | WTG 448 | 2495
WTG 553 | WTG 552 | 2495 | [10 empty] | WTG 448 | WTG 449 | 1210
WTG 552 | WTG 132 | 1920 | [10 empty] | WTG 449 |  | 50
WTG 132 | WTG 002 | 1090 | [10 empty] | Total Length (Ring-7) |  | 14855 |  | 14855
WTG 002 | WTG 551 | 1125 | [10 empty] | Ring-8 (F08,F09)
WTG 551 |  | 50 | [10 empty] | PSS14 | KH 604 | 740
Total Length (Ring-5) |  | 17625 | 0 | [9 empty] | KH 604 | KH 597 | 1200
[13 empty] | KH 597 | KH 55 | 2400
Total Length (Ring-1+2+3+4+5 ) |  | 74955 | 0 | [9 empty] | KH 55 | KH 596 | 1175
[13 empty] | KH 596 | KH589 | 1200
[13 empty] | KH589 | KH54 | 2395
[13 empty] | KH54 | KH588 | 1175
[13 empty] | KH588 | KH581 | 1200
[13 empty] | KH581 |  | 50
[13 empty] | Total Length (Ring-8) |  | 11535
[13 empty] | Total Length (Ring-1+2+3+4+5+6+7+8 ) |  | 142770 |  | 142770

## Change loc. (hidden)
PSS-08 |  | PSS-05 |  | PSS-11 |  | PSS-12 |  | PSS-14
WTG 121 | WTG 230 | WTG 177 | WTG 002 | WTG 233A | WTG 382 | WTG 402 | WTG 402 | WTG 373 | KH 053 | KH 549
WTG 123 | WTG 208 | WTG 199 | WTG 551 | WTG 380 | WTG 406 | WTG 428 | WTG 428 | WTG 399 | KH 054 | KH 559
WTG 143 | WTG 186 | WTG 154 | WTG 552 | WTG 381 | WTG 407 | WTG 451 | WTG 451 | WTG 424 | KH 589 | KH 560
WTG 144 | WTG 164 | WTG 002 | WTG 131 | WTG 382 | WTG 381 | WTG 452 | WTG 452 | WTG 425 | KH 581 | KH 561
WTG 145 | WTG 141 | WTG 133 | WTG 132 | WTG 403 | WTG 432 | WTG 453 | WTG 453 | WTG 448 | KH 588 | KH 562
WTG 230 | WTG 121 | WTG 290 | WTG 175 | WTG 404 | WTG 433 | WTG 473 | WTG 476 | WTG 449 | KH 055 | KH 563
WTG 302 | WTG 123 | WTG 315 | WTG 152 | WTG 405 | WTG 457 | WTG 474 | WTG 477 | WTG 450 | KH 056 | KH 574
WTG 326 | WTG 143 | WTG 266 | WTG 133 | WTG 406 | WTG 482 | WTG 475 | WTG 478 | WTG 423 | KH 604 | KH 584
WTG 327 | WTG 144 | WTG 221 | WTG 553 | WTG 407 | WTG 505 | WTG 476 | WTG 500 | WTG 398 | KH 596 | KH 585
WTG 351 | WTG 145 | WTG 243 | WTG 153 | WTG 429 | WTG 233A | WTG 477 | WTG 499 | KH 053 | KH 597 | KH 586
WTG 376 | WTG 351 | WTG 131 | WTG 154 | WTG 430 | WTG 380 | WTG 478 | WTG 475 | KH 054 | KH 057 | KH 593
WTG 400 | WTG 376 | WTG 132 | WTG 198 | WTG 431 | WTG 404 | WTG 496 | WTG 496 | KH 055 | KH 058 | KH 594
WTG 208 | WTG 400 | WTG 152 | WTG 176 | WTG 432 | WTG 429 | WTG 497 | WTG 497 | KH 056 | KH 611 | KH 595
WTG 141 | WTG 326 | WTG 153 | WTG 197 | WTG 433 | WTG 405 | WTG 498 | WTG 498 | KH 057 | KH 612 | KH 601
WTG 164 | WTG 327 | WTG 155 | WTG 554 | WTG 454 | WTG 403 | WTG 499 | WTG 517 | KH 058 | KH 617 | KH 602
WTG 352 | WTG 302 | WTG 156 | WTG 555 | WTG 455 | WTG 456 | WTG 500 | WTG 518 | KH 059 | KH 059 | KH 603
WTG 186 | WTG 352 | WTG 175 | WTG 155 | WTG 456 | WTG 431 | WTG 517 | WTG 519 | KH 060 | KH 060 | KH 609
|  | WTG 176 | WTG 156 | WTG 479 | WTG 455 | WTG 518 | WTG 533 | KH 061 | KH 061 | KH 610
|  | WTG 178 | WTG 179 | WTG 480 | WTG 430 | WTG 519 | WTG 534 | KH 549 | KH 068 | KH 616
|  | WTG 179 | WTG 199 | WTG 481 | WTG 454 | WTG 520 | WTG 535 | KH 559 | KH 621
|  | WTG 197 | WTG 221 | WTG 482 | WTG 481 | WTG 521 | WTG 520 | KH 560 | KH 556
|  | WTG 198 | WTG 177 | WTG 501 | WTG 503 | WTG 533 | WTG 521 | KH 561 | KH 523
|  | WTG 200 | WTG 178 | WTG 502 | WTG 480 | WTG 534 | WTG 536 | KH 562 | KH 522
|  | WTG 201 | WTG 222 | WTG 503 | WTG 502 | WTG 535 | WTG 377 | KH 563 | KH 521
|  | WTG 222 | WTG 243 | WTG 504 | WTG 479 | WTG 536 | WTG 401 | KH 574 | KH 508
|  | WTG 223 | WTG 200 | WTG 505 | WTG 501 | WTG 532 | WTG 427 | KH 581 | KH 555
|  | WTG 244 | WTG 266 | WTG 522 | WTG 522 | WTG 516 | WTG 426 | KH 582 | KH 557
|  | WTG 245 | WTG 244 | WTG 523 | WTG 523 |  |  | KH 583 | KH 582
|  | WTG 267 | WTG 267 | WTG 524 | WTG 524 | PSS-12 |  | KH 584 | KH 590
|  | WTG 268 | WTG 314 | WTG 457 | WTG 504 |  |  | KH 585 | KH 583
|  | WTG 291 | WTG 290 |  | WTG 329 |  |  | KH 586 | KH 592
|  | WTG 292 | WTG 315 |  | WTG 328 |  |  | KH 588 | KH 600
|  | WTG 314 | WTG 291 |  | WTG 353 |  |  | KH 589 | KH 599
|  | WTG 316 | WTG 316 |  | WTG 354 |  |  | KH 590 | KH 607
|  | WTG 555 | WTG 292 |  | WTG 378 |  |  | KH 591 | KH 606
|  | WTG 554 | WTG 268 |  | WTG 379 |  |  | KH 592 | KH 608
|  | WTG 552 | WTG 223 |  |  |  |  | KH 593 | KH 615
|  | WTG 551 | WTG 201 |  |  |  |  | KH 594 | KH 614
|  | WTG 553 | WTG 245 |  |  |  |  | KH 595 | KH 613
[8 empty] | KH 596 | KH 618
[8 empty] | KH 597 | KH 034
[8 empty] | KH 598 | KH 035
[8 empty] | KH 599 | KH 619
[8 empty] | KH 600 | KH 622
[8 empty] | KH 601 | KH 620
[8 empty] | KH 602 | KH 605
[8 empty] | KH 603 | KH 598
[8 empty] | KH 604 | KH 591
[8 empty] | KH 605 | KH 052
[8 empty] | KH 606 | KH 051
[8 empty] | KH 607 | KH 552
[8 empty] | KH 608 | KH 550
[8 empty] | KH 609 | KH 551
[8 empty] | KH 610 | KH 579
[8 empty] | KH 611 | KH 553
[8 empty] | KH 612 | KH 580
[8 empty] | KH 613 | KH 478
[8 empty] | KH 614 | KH 509
[8 empty] | KH 615 | KH 554
[8 empty] | KH 616 | KH 047
[8 empty] | KH 617 | WTG 473
[8 empty] | KH 618 | WTG 474
[8 empty] | KH 619 | WTG 516
[8 empty] | KH 620 | WTG 532
[8 empty] | KH 621 | WTG 448
[8 empty] | KH 622 | WTG 424
[8 empty] | KH 034 | WTG 425
[8 empty] | KH 035 | WTG 423
[8 empty] | KH 068 | WTG 449
WTG 373
WTG 398
WTG 399
WTG 450

## Sheet1 (hidden)
PSS | Growth Plan Dtd. 27-Dec-24 |  |  |  | Growth Pla Dtd. 08-Feb-25 |  |  |  | Commissioning Plan ( MW) as per Growth Pla Dtd. 08-Feb-25
| SPV | WTGs | MW | ECOD | SPV | WTGs | MW | ECOD | 2025-06-25 | 2025-09-25 | 2025-12-25 | 2025-03-26 | Total
PSS-05 | AHEJ5L | 39 | 202.8 | 22 WTGs by Jun-25 | AHEJ5L | 39 | 202.8 | 22 WTGs by Jun-25 | 114.4 | 88.4 |  |  | 202.8
|  |  |  | 17 WTGs by Sep-25 |  |  |  | 17 WTGs by Sep-25
PSS-08 | AGE25CL | 10 | 52 | 10 WTGs by Jun-25 | ASEJ6PL | 9 | 46.8 | 9 WTGs by Jun-25 | 46.8 |  |  |  | 46.8
PSS-08 | ARE3L | 7 | 36.4 | 7 WTGs by Jun-25 | ARE3L | 8 | 41.6 | 3 WTGs by Apr-25 | 41.6 |  |  |  | 41.6
5 WTGs by Jun-25
PSS-07 | TBD | 20 | 104 | 20 Nos by Dec-25 | AGE25CL | 19 | 98.8 | 19 Nos by Mar-26 |  |  |  | 98.8 | 98.8
PSS-11 | TBD | 20 | 104 | 20 Nos by Dec-25 | AGE25CL | 15 | 78 | 15 Nos by Dec-25 |  |  | 78 |  | 78
PSS-11 | TBD | 20 | 104 | 20 Nos by Dec-25 | AGE25CL | 15 | 78 | 15 Nos by Dec-25 |  |  | 78 |  | 78
PSS-12 | TBD | 17 | 88.4 | 17 Nos by Dec-25 | AGE26AL | 27 | 140.4 | 27 Nos by Dec-25 |  |  | 140.4 |  | 140.4
PSS-14 | TBD | 60 | 312 | 60 Nos by Mar-26 | AGE26AL | 60 | 312 | 60 Nos by Mar-26 |  |  |  | 312 | 312
| Growth Plan Dtd. 27-Dec-24 WTGs: 193; Growth Plan Dtd. 27-Dec-24 MW: 1003.6; Growth Pla Dtd. 08-Feb-25 WTGs: 192; Growth Pla Dtd. 08-Feb-25 MW: 998.4 | 202.8 | 88.4 | 296.4 | 410.8 | 998.4

## Erection Status
S# | PSS no. | SPV | Location | CRANE | Raft Casting Finish | Backfilling Upto 08th Layer | Crane Assy Start date | Crane Assy Finish date | WTG Tower Ere Start date | WTG Tower Ere Finish date | NDT Start date | NDT Finish date | HB Start date | HB Finish date | Dismantling Start date | Dismantling Finish date | Remarks | Package Owner | Crane Lead | Vendor
1 | PSS-08 | ARE3L | WTG 326 | C4_SETHIA-SANY750MT | 2025-05-01 | Done | 2025-06-07 | 2025-06-10 | 2025-06-11 | 2025-06-13 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-20 | 2025-06-29 |  |  |  | SK ENGINEERING
2 | PSS-08 | ARE3L | WTG 327 | C3_BARKAT_SANY750MT | 2025-06-08 | Done | 2025-06-15 | 2025-06-20 | 2025-06-21 | 2025-06-23 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-07-01 | 2025-07-12 |  |  |  | YASH ENGG.
3 | PSS-08 | ARE3L | WTG 351 | C5_ADA_SANY750MT | 2025-05-05 | Done | 2025-06-12 | 2025-06-15 | 2025-06-21 | 2025-06-23 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-07-04 | 2025-07-12 |  |  |  | JS & SONS
4 | PSS-08 | ARE3L | WTG 302 | C7_ADA_SANY750MT | 2025-04-27 | Done | 2025-06-14 | 2025-06-21 | 2025-06-22 | 2025-06-24 | 2025-06-24 | 2025-06-26 | 2025-06-26 | 2025-07-01 | 2025-07-10 | 2025-07-22 |  |  |  | MK
5 | PSS-08 | ARE3L | WTG 352 | C2_ADA_SANY750MT | 2025-05-24 | Done | 2025-06-14 | 2025-06-17 | 2025-06-21 | 2025-06-23 | 2025-06-24 | 2025-06-24 | 2025-06-25 | 2025-07-03 | 2025-07-04 | 2025-07-24 |  |  |  | JS & SONS
6 | PSS-05 | AHEJ5L | WTG 291 | C9_ADA_SANY750MT | 2025-05-26 | Done | 2025-07-28 | 2025-07-31 | 2025-07-31 | 2025-08-02 | 2025-08-02 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 |  |  |  | JS & SONS
7 | PSS-05 | AHEJ5L | WTG 244 | C3_BARKAT_SANY750MT | 2025-06-23 | Done | 2025-07-28 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-04 | 2025-08-05 | 2025-08-07 | 2025-08-08 | 2025-08-20 |  |  |  | YASH ENGG.
8 | PSS-05 | AHEJ5L | WTG 222 | C3_BARKAT_SANY750MT | 2025-05-08 | Done | 2025-08-09 | 2025-08-11 | 2025-08-11 | 2025-08-13 | 2025-08-14 | 2025-08-14 | 2025-08-15 | 2025-08-17 | 2025-08-17 | 2025-08-19 |  |  |  | YASH ENGG.
9 | PSS-05 | AHEJ5L | WTG 267 | C9_ADA_SANY750MT | 2025-07-17 | Done | 2025-08-09 | 2025-08-11 | 2025-08-11 | 2025-08-13 | 2025-08-13 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-21 | 2025-08-22 |  |  |  | JS & SONS
10 | PSS-05 | AHEJ5L | WTG 243 | C5_SETHIA-SANY750MT | 2025-04-22 | Done | 2025-08-11 | 2025-08-14 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-22 | 2025-08-23 | 2025-08-26 |  |  |  | JS & SONS
11 | PSS-05 | AHEJ5L | WTG 315 | C5_SETHIA-SANY750MT | 2025-03-13 | Done | 2025-08-30 | 2025-09-01 | 2025-09-03 | 2025-09-04 | 2025-09-04 | 2025-09-05 | 2025-09-10 | 2025-09-12 | 2025-09-14 | 2025-09-16 |  |  |  | JS & SONS
12 | PSS-05 | AHEJ5L | WTG 292 | C5_SETHIA-SANY750MT | 2025-05-31 | Done | 2025-09-17 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-22 | 2025-09-23 | 2025-09-25 | 2025-09-25 | 2025-09-28
13 | PSS-05 | AHEJ5L | WTG 290 | C3_BARKAT_SANY750MT | 2025-03-31 | Done | 2025-08-23 | 2025-08-29 | 2025-08-30 | 2025-09-27 | 2025-09-27 | 2025-09-28 | 2025-09-28 | 2025-09-30 | 2025-10-01 | 2025-10-04
14 | PSS-05 | AHEJ5L | WTG 266 | C9_ADA_SANY750MT | 2025-03-24 | Done | 2025-08-28 | 2025-08-30 | 2025-08-30 | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-30
15 | PSS-05 | AHEJ5L | WTG 268 | C5_ADA_SANY750MT | 2025-06-26 | Done | 2025-09-15 | 2025-09-26 | 2025-09-26 | 2025-09-28 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-03 | 2025-10-08
16 | PSS-05 | AHEJ5L | WTG 201 | C6_ADA_SANY750MT | 2025-06-16 | Done | 2025-09-21 | 2025-09-25 | 2025-09-26 | 2025-09-29 | 2025-09-29 | 2025-09-30 | 2025-09-30 | 2025-10-03 | 2025-10-04 | 2025-10-07
17 | PSS-05 | AHEJ5L | WTG 179 | C1_ADA_SANY750MT | 2025-06-20 | Done | 2025-09-24 | 2025-09-29 | 2025-09-29 | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-10-02 | 2025-10-08 | 2025-10-08 | 2025-10-10
18 | PSS-05 | AHEJ5L | WTG 245 | C5_SETHIA-SANY750MT | 2025-05-29 | Done | 2025-09-28 | 2025-10-01 | 2025-10-01 | 2025-10-03 | 2025-10-03 | 2025-10-04 | 2025-10-04 | 2025-10-08 | 2025-10-08 | 2025-10-10
19 | PSS-05 | AHEJ5L | WTG 156 | C9_ADA_SANY750MT | 2025-06-12 | Done | 2025-10-01 | 2025-10-04 | 2025-10-05 | 2025-10-07 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-10 | 2025-10-12
20 | PSS-05 | AHEJ5L | WTG 200 | C1_SETHIA-SANY750MT | 2025-04-14 | Done | 2025-10-01 | 2025-10-06 | 2025-10-06 | 2025-10-09 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-13 | 2025-10-15 | 2025-10-16
21 | PSS-05 | AHEJ5L | WTG 155 | C3_BARKAT_SANY750MT | 2025-06-14 | Done | 2025-10-05 | 2025-10-07 | 2025-10-09 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-12 | 2025-10-14 | 2025-10-15 | 2025-10-15
22 | PSS-05 | AHEJ5L | WTG 178 | C4_SETHIA-SANY750MT | 2025-07-23 | Done | 2025-10-08 | 2025-10-10 | 2025-10-11 | 2025-10-13 | 2025-10-13 | 2025-10-14 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-18
23 | PSS-05 | AHEJ5L | WTG 002 | C1_ADA_SANY750MT | 2025-03-02 | Done | 2025-10-11 | 2025-10-14 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2025-10-18 | 2025-10-19 | 2025-10-25
24 | PSS-05 | AHEJ5L | WTG 223 | C6_ADA_SANY750MT | 2025-06-02 | Done | 2025-10-10 | 2025-10-12 | 2025-10-12 | 2025-10-15 | 2025-10-15 | 2025-10-17 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-22
25 | PSS-05 | AHEJ5L | WTG 132 | C5_SETHIA-SANY750MT | 2025-05-03 | Done | 2025-10-11 | 2025-10-14 | 2025-10-14 | 2025-10-15 | 2025-10-15 | 2025-10-16 | 2025-10-16 | 2025-10-19 | 2025-10-21 | 2025-10-22
26 | PSS-05 | AHEJ5L | WTG 314 | C3_BARKAT_SANY750MT | 2025-10-01 | Done | 2025-10-16 | 2025-10-19 | 2025-10-19 | 2025-10-21 | 2025-10-21 | 2025-10-22 | 2025-10-22 | 2025-10-24 | 2025-10-25 | 2025-10-28
27 | PSS-05 | AHEJ5L | WTG 316 | C8_ADA_SANY750MT | 2025-09-30 | Done | 2025-10-10 | 2025-10-13 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-19 | 2025-10-21 | 2025-10-22 | 2025-10-24 | 2025-10-31
28 | PSS-05 | AHEJ5L | WTG 176 | C9_ADA_SANY750MT | 2025-05-13 | Done | 2025-10-13 | 2025-10-15 | 2025-10-16 | 2025-10-18 | 2025-10-19 | 2025-10-19 | 2025-10-22 | 2025-10-26 | 2025-10-28 | 2025-11-05
29 | PSS-05 | AHEJ5L | WTG 177 | C1_SETHIA-SANY750MT | 2025-05-22 | Done | 2025-10-17 | 2025-10-19 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-25 | 2025-10-29 | 2025-10-30 | 2025-11-08
30 | PSS-05 | AHEJ5L | WTG 199 | C4_SETHIA-SANY750MT | 2025-04-20 | Done | 2025-10-18 | 2025-10-20 | 2025-10-22 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-26 | 2025-10-30 | 2025-11-07 | 2025-11-09
31 | PSS-08 | ASEJ6PL | WTG 400 | C10_ADA_SANY750MT | 2025-07-11 | Done | 2025-10-30 | 2025-11-07 | 2025-11-07 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-11 | 2025-11-13 | 2025-11-13 | 2025-11-15
32 | PSS-05 | AHEJ5L | WTG 175 | C3_BARKAT_SANY750MT | 2025-06-06 | Done | 2025-11-01 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-12 | 2025-11-13 | 2025-11-13 | 2025-11-16 | 2025-11-17 | 2025-11-19
33 | PSS-05 | AHEJ5L | WTG 152 | C5_ADA_SANY750MT | 2025-09-28 | Done | 2025-10-21 | 2025-10-24 | 2025-10-28 | 2025-11-09 | 2025-11-09 | 2025-11-11 | 2025-11-13 | 2025-11-13 | 2025-11-14 | 2025-11-17
34 | PSS-05 | AHEJ5L | WTG 133 | C5_SETHIA-SANY750MT | 2025-05-06 | Done | 2025-10-28 | 2025-10-31 | 2025-11-06 | 2025-11-08 | 2025-11-09 | 2025-11-11 | 2025-11-11 | 2025-11-13 | 2025-11-16 | 2025-11-18
35 | PSS-11 | AGE25CL | WTG 382 | C8_ADA_SANY750MT | 2025-03-14 | Done | 2025-11-08 | 2025-11-11 | 2025-11-12 | 2025-11-14 | 2025-11-14 | 2025-11-16 | 2025-11-16 | 2025-11-18 | 2025-11-19 | 2025-11-20
36 | PSS-05 | AHEJ5L | WTG 197 | C9_ADA_SANY750MT | 2025-06-17 | Done | 2025-11-08 | 2025-11-11 | 2025-11-12 | 2025-11-15 | 2025-11-15 | 2025-11-16 | 2025-11-16 | 2025-11-17 | 2025-11-19 | 2025-11-20
37 | PSS-05 | AHEJ5L | WTG 131 | C1_ADA_SANY750MT | 2025-09-01 | Done | 2025-10-26 | 2025-10-28 | 2025-10-30 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-14 | 2025-11-16 | 2025-11-17 | 2025-11-19
38 | PSS-08 | ASEJ6PL | WTG 376 | C4_SETHIA-SANY750MT | 2025-05-30 | Done | 2025-11-13 | 2025-11-15 | 2025-11-15 | 2025-11-17 | 2025-11-17 | 2025-11-18 | 2025-11-18 | 2025-11-20 | 2025-11-23 | 2025-11-23
39 | PSS-05 | AHEJ5L | WTG 153 | C6_ADA_SANY750MT | 2025-07-02 | Done | 2025-10-28 | 2025-10-30 | 2025-11-07 | 2025-11-10 | 2025-11-11 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-15 | 2025-11-16
40 | PSS-11 | AGE25CL | WTG 353 | C1_SETHIA-SANY750MT | 2025-06-14 | Done | 2025-11-09 | 2025-11-12 | 2025-11-16 | 2025-11-17 | 2025-11-17 | 2025-11-18 | 2025-11-18 | 2025-11-20 | 2025-11-21 | 2025-11-22
41 | PSS-05 | AHEJ5L | WTG 154 | C3_BARKAT_SANY750MT | 2025-11-13 | Done | 2025-11-19 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-23 | 2025-11-24 | 2025-11-24 | 2025-11-26 | 2025-11-28 | 2025-11-30
42 | PSS-08 | ASEJ6PL | WTG 145 | AC7_ADA_SANY750MT | 2025-04-05 | Done | 2025-08-31 | 2025-09-04 | 2025-09-05 | 2025-10-30 | 2025-10-30 | 2025-11-13 | 2025-11-14 | 2025-11-20 | 2025-11-21 | 2025-11-22
43 | PSS-05 | AHEJ5L | WTG 221 | AC9_ADA_SANY750MT | 2025-11-16 | Done | 2025-11-25 | 2025-11-27 | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-29 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02
44 | PSS-11 | AGE25CL | WTG 379 | AC5_ADA_SANY750MT | 2025-07-26 | Done | 2025-11-21 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-02 | 2025-12-05 | 2025-12-05 | 2025-12-07
45 | PSS-11 | AGE25CL | WTG 328 | AC10_ADA_SANY750MT | 2025-08-15 | Done | 2025-11-15 | 2025-11-19 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-24 | 2025-11-26
46 | PSS-11 | AGE25CL | WTG 406 | RC5_SETHIA-SANY750MT | 2025-06-01 | Done | 2025-11-21 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-26 | 2025-11-27 | 2025-11-27 | 2025-11-29 | 2025-11-30 | 2025-12-01
47 | PSS-11 | AGE25CL | WTG 378 | AC3_ADA_SANY750MT | 2025-06-22 | Done | 2025-11-20 | 2025-11-23 | 2025-11-24 | 2025-11-26 | 2025-11-26 | 2025-11-28 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-02
48 | PSS-11 | AGE25CL | WTG 381 | AC8_ADA_SANY750MT | 2025-05-03 | Done | 2025-11-26 | 2025-11-28 | 2025-11-29 | 2025-12-03 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-08 | 2025-12-10
49 | PSS-11 | AGE25CL | WTG 479 | RC4_SETHIA-SANY750MT | 2025-10-31 | Done | 2025-11-29 | 2025-12-01 | 2025-12-02 | 2025-12-05 | 2025-12-06 | 2025-12-06 | 2025-12-07 | 2025-12-09 | 2025-12-11 | 2025-12-12
50 | PSS-11 | AGE25CL | WTG 505 | AC6_ADA_SANY750MT | 2025-11-03 | Done | 2025-11-28 | 2025-12-01 | 2025-12-02 | 2025-12-06 | 2025-12-05 | 2025-12-07 | 2025-12-08 | 2025-12-10 | 2025-12-11 | 2025-12-11
51 | PSS-11 | AGE25CL | WTG 456 | RC1_SETHIA-SANY750MT | 2025-08-12 | Done | 2025-12-02 | 2025-12-05 | 2025-12-05 | 2025-12-07 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-11 | 2025-12-12 | 2025-12-13
52 | PSS-05 | AHEJ5L | WTG 554 | AC1_ADA_SANY750MT | 2025-11-11 | Done | 2025-11-26 | 2025-11-29 | 2025-11-29 | 2025-12-01 | 2025-12-01 | 2025-12-06 | 2025-12-07 | 2025-12-09 | 2025-12-10 | 2025-12-12
53 | PSS-11 | AGE25CL | WTG 457 | AC10_ADA_SANY750MT | 2025-11-24 | Done | 2025-12-06 | 2025-12-08 | 2025-12-08 | 2025-12-10 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15
54 | PSS-11 | AGE25CL | WTG 405 | AC2_ADA_SANY750MT | 2025-08-13 | Done | 2025-11-28 | 2025-12-02 | 2025-12-03 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-08 | 2025-12-10 | 2025-12-11 | 2025-12-12
55 | PSS-11 | AGE25CL | WTG 455 | AC9_ADA_SANY750MT | 2025-11-27 | Done | 2025-12-07 | 2025-12-09 | 2025-12-10 | 2025-12-13 | 2025-12-13 | 2025-12-14 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17
56 | PSS-05 | AHEJ5L | WTG 198 | RC3_BARKAT_SANY750MT | 2025-11-25 | Done | 2025-12-01 | 2025-12-04 | 2025-12-07 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15
57 | PSS-08 | ASEJ6PL | WTG 143 | AC7_ADA_SANY750MT | 2025-03-28 | Done | 2025-12-05 | 2025-12-08 | 2025-12-10 | 2025-12-11 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-21
58 | PSS-11 | AGE25CL | WTG 523 | AC3_ADA_SANY750MT | 2025-10-29 | Done | 2025-12-09 | 2025-12-11 | 2025-12-13 | 2025-12-15 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21 | 2025-12-22 | 2025-12-23
59 | PSS-11 | AGE25CL | WTG 433 | AC5_ADA_SANY750MT | 2025-11-24 | Done | 2025-12-08 | 2025-12-10 | 2025-12-11 | 2025-12-13 | 2025-12-17 | 2025-12-18 | 2025-12-18 | 2025-12-20 | 2025-12-21 | 2025-12-23
60 | PSS-11 | AGE25CL | WTG 431 | RC5_SETHIA-SANY750MT | 2025-08-09 | Done | 2025-12-08 | 2025-12-11 | 2025-12-13 | 2025-12-16 | 2025-12-19 | 2025-12-20 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-24
61 | PSS-11 | AGE25CL | WTG 502 | RC4_SETHIA-SANY750MT | 2025-11-26 | Done | 2025-12-11 | 2025-12-12 | 2025-12-16 | 2025-12-17 | 2025-12-19 | 2025-12-20 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-24
62 | PSS-11 | AGE25CL | WTG 504 | AC6_ADA_SANY750MT | 2025-11-30 | Done | 2025-12-11 | 2025-12-13 | 2025-12-15 | 2025-12-18 | 2025-12-20 | 2025-12-21 | 2025-12-21 | 2025-12-24 | 2025-12-26 | 2025-12-27
63 | PSS-11 | AGE25CL | WTG 524 | RC1_SETHIA-SANY750MT | 2025-11-13 | Done | 2025-12-14 | 2025-12-17 | 2025-12-18 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-23 | 2025-12-25 | 2025-12-26 | 2025-12-27
64 | PSS-09 | AGE25BL | WTG 557 | AC1_ADA_SANY750MT | 2025-12-02 | Done | 2025-12-14 | 2025-12-16 | 2025-12-17 | 2025-12-23 | 2025-12-23 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-26 | 2025-12-27
65 | PSS-11 | AGE25CL | WTG 380 | AC8_ADA_SANY750MT | 2025-11-30 | Done | 2025-12-10 | 2025-12-16 | 2025-12-17 | 2025-12-22 | 2025-12-22 | 2025-12-23 | 2025-12-23 | 2025-12-25 | 2025-12-26 | 2025-12-29
66 | PSS-11 | AGE25CL | WTG 503 | AC9_ADA_SANY750MT | 2025-10-24 | Done | 2025-12-18 | 2025-12-20 | 2025-12-21 | 2025-12-23 | 2025-12-24 | 2025-12-26 | 2025-12-26 | 2025-12-27 | 2025-12-28 | 2025-12-29
67 | PSS-11 | AGE25CL | WTG 407 | RC3_BARKAT_SANY750MT | 2025-12-08 | Done | 2025-12-19 | 2025-12-22 | 2025-12-22 | 2025-12-25 | 2025-12-25 | 2025-12-26 | 2025-12-26 | 2025-12-28 | 2025-12-29 | 2025-12-30
68 | PSS-12 | AGE26AL | WTG 518 | AC10_ADA_SANY750MT | 2025-10-19 | Done | 2025-12-17 | 2025-12-22 | 2025-12-22 | 2025-12-25 | 2025-12-26 | 2025-12-26 | 2025-12-27 | 2025-12-29 | 2025-12-30 | 2025-12-31
69 | PSS-11 | AGE25CL | WTG 522 | AC3_ADA_SANY750MT | 2025-11-11 | Done | 2025-12-23 | 2025-12-25 | 2025-12-28 | 2025-12-28 | 2025-12-28 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02
70 | PSS-11 | AGE25CL | WTG 481 | AC7_ADA_SANY750MT | 2025-12-12 | Done | 2025-12-22 | 2025-12-24 | 2025-12-24 | 2025-12-28 | 2025-12-28 | 2025-12-29 | 2025-12-29 | 2025-12-31 | 2026-01-01 | 2026-01-03
71 | PSS-11 | AGE25CL | WTG 432 | AC5_ADA_SANY750MT | 2025-12-16 | Done | 2025-12-25 | 2025-12-27 | 2025-12-27 | 2025-12-29 | 2025-12-29 | 2025-12-30 | 2025-12-30 | 2025-12-31 | 2026-01-02 | 2026-01-03
72 | PSS-11 | AGE25CL | WTG 404 | RC5_SETHIA-SANY750MT | 2025-07-09 | Done | 2025-12-25 | 2025-12-27 | 2025-12-28 | 2025-12-29 | 2025-12-29 | 2025-12-30 | 2025-12-30 | 2025-12-31 | 2026-01-02 | 2026-01-03
73 | PSS-08 | ASEJ6PL | WTG 123 | RC2_BARKAT_SANY650MT | 2025-03-12 | Done | 2025-12-09 | 2025-12-13 | 2025-12-18 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-29 | 2026-01-04 | 2026-01-05
74 | PSS-12 | AGE26AL | WTG 401 | RC4_SETHIA-SANY750MT | 2025-10-26 | Done | 2025-12-26 | 2025-12-27 | 2025-12-28 | 2025-12-31 | 2025-12-31 | 2026-01-03 | 2026-01-03 | 2026-01-05 | 2026-01-06 | 2026-01-07
75 | PSS-11 | AGE25CL | WTG 454 | RC1_SETHIA-SANY750MT | 2025-11-10 | Done | 2025-12-27 | 2025-12-30 | 2025-12-31 | 2026-01-02 | 2026-01-03 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07
76 | PSS-11 | AGE25CL | WTG 354 | AC9_ADA_SANY750MT | 2025-12-18 | Done | 2025-12-29 | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-03 | 2026-01-04 | 2026-01-04 | 2026-01-06 | 2026-01-07 | 2026-01-08
77 | PSS-09 | AGE25BL | WTG 556 | AC1_ADA_SANY750MT | 2025-12-08 | Done | 2025-12-29 | 2026-12-01 | 2026-01-02 | 2026-01-03 | 2026-01-03 | 2026-01-04 | 2026-01-04 | 2026-01-07 | 2026-01-08 | 2026-01-09
78 | PSS-11 | AGE25CL | WTG 429 | AC2_ADA_SANY750MT | 2025-11-23 | Done | 2025-12-18 | 2025-12-23 | 2025-12-24 | 2025-12-31 | 2025-12-31 | 2026-01-02 | 2026-01-03 | 2026-01-07 | 2026-01-07 | 2026-01-09
79 | PSS-12 | AGE26AL | WTG 520 | RC3_BARKAT_SANY750MT | 2025-12-21 | Done | 2025-12-30 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10
80 | PSS-12 | AGE26AL | WTG 521 | AC8_ADA_SANY750MT | 2025-11-21 | Done | 2025-12-31 | 2025-12-31 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-10 | 2026-01-12 | 2026-01-13
81 | PSS-11 | AGE25CL | WTG 403 | RC5_SETHIA-SANY750MT | 2025-12-27 | Done | 2026-01-04 | 2026-01-06 | 2026-01-07 | 2026-01-10 | 2026-01-10 | 2026-01-11 | 2026-01-11 | 2026-01-13 | 2026-01-20 | 2026-01-21
82 | PSS-11 | AGE25CL | WTG 501 | AC3_ADA_SANY750MT | 2025-12-14 | Done | 2026-01-02 | 2026-01-04 | 2026-01-06 | 2026-01-08 | 2026-01-08 | 2026-01-09 | 2026-01-09 | 2026-01-11 | 2026-01-12 | 2026-01-13
83 | PSS-05 | AHEJ5L | WTG 552 | AC1_ADA_SANY750MT | 2025-03-20 | Done | 2026-01-10 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-16 | 2026-01-17 | 2026-01-20 | 2026-01-21
84 | PSS-12 | AGE26AL | WTG 498 | AC10_ADA_SANY750MT | 2025-11-08 | Done | 2026-01-01 | 2026-01-03 | 2026-01-05 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-09 | 2026-01-12 | 2026-01-20 | 2026-01-21
85 | PSS-11 | AGE25CL | WTG 329 | AC9_ADA_SANY750MT | 2025-12-12 | Done | 2026-01-08 | 2026-01-10 | 2026-01-12 | 2026-01-13 | 2026-01-13 | 2026-01-15 | 2026-01-15 | 2026-01-16 | 2026-01-22 | 2026-01-23
86 | PSS-11 | AGE25CL | WTG 430 | RC1_SETHIA-SANY750MT | 2025-11-05 | Done | 2026-01-08 | 2026-01-12 | 2026-01-15 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-19 | 2026-01-20 | 2026-01-22 | 2026-01-23
87 | PSS-08 | ASEJ6PL | WTG 186 | AC5_ADA_SANY750MT | 2025-06-24 | Done | 2026-01-03 | 2026-01-06 | 2026-01-09 | 2026-01-11 | 2026-01-11 | 2026-01-13 | 2026-01-13 | 2026-01-15 | 2026-01-22 | 2026-01-23
88 | PSS-12 | AGE26AL | WTG 534 | AC7_ADA_SANY750MT | 2025-10-16 | Done | 2026-01-05 | 2026-01-07 | 2026-01-10 | 2026-01-13 | 2026-01-13 | 2026-01-15 | 2026-01-15 | 2026-01-16 | 2026-01-23 | 2026-01-24
89 | PSS-14 | AGE25CL | WTG 399 | RC2_BARKAT_SANY650MT | 2025-11-26 | Done | 2026-01-06 | 2026-01-08 | 2026-01-10 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-15 | 2026-01-17 | 2026-01-23 | 2026-01-24
90 | PSS-14 | AGE25CL | WTG 398 | RC4_SETHIA-SANY750MT | 2025-08-17 | Done | 2026-01-07 | 2026-01-10 | 2026-01-13 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-17 | 2026-01-21 | 2026-01-25 | 2026-01-25
91 | PSS-12 | AGE26AL | WTG 402 | AC2_ADA_SANY750MT | 2025-12-30 | Done | 2026-01-10 | 2026-01-12 | 2026-01-16 | 2026-01-19 | 2026-01-19 | 2026-01-20 | 2026-01-20 | 2026-01-21 | 2026-01-25 | 2026-01-25
92 | PSS-12 | AGE26AL | WTG 519 | RC3_BARKAT_SANY750MT | 2025-12-14 | Done | 2026-01-12 | 2026-01-15 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 1900-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-25 | 2026-01-26
93 | PSS-12 | AGE26AL | WTG 478 | AC3_ADA_SANY750MT | 2025-12-17 | Done | 2026-01-13 | 2026-01-15 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-21 | 2026-01-23 | 2026-01-25 | 2026-01-25
94 | PSS-11 | AGE25CL | WTG 233A | RC5_SETHIA-SANY750MT | 2025-12-28 | Done | 2026-01-21 | 2026-01-24 | 2026-01-24 | 2026-01-26 | 2026-01-28 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-30 | 2026-01-31
95 | PSS-12 | AGE26AL | WTG 536 | AC8_ADA_SANY750MT | 2025-12-22 | Done | 2026-01-13 | 2026-01-16 | 2026-01-19 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-23 | 2026-01-25 | 2026-01-30 | 2026-01-31
96 | PSS-12 | AGE26AL | WTG 475 | AC10_ADA_SANY750MT | 2025-11-22 | Done | 2026-01-21 | 2026-01-23 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31
97 | PSS-11 | AGE25CL | WTG 482 | AC9_ADA_SANY750MT | 2026-01-06 | Done | 2026-01-23 | 2026-01-25 | 2026-01-25 | 2026-01-25 | 2026-01-28 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-30 | 2026-01-31
98 | PSS-14 | AGE25CL | WTG 448 | AC6_ADA_SANY750MT | 2025-12-09 | Done | 2026-01-14 | 2026-01-16 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-02-03 | 2026-02-03
99 | PSS-08 | ASEJ6PL | WTG 144 | AC1_ADA_SANY750MT | 2025-06-25 | Done | 2026-01-21 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-29 | 2026-01-30 | 2026-01-30 | 2026-01-31 | 2026-02-03 | 2026-01-05
100 | PSS-11 | AGE25CL | WTG 480 | RC1_SETHIA-SANY750MT | 2026-01-09 | Done | 2026-01-24 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-07 | 2026-02-08
101 | PSS-12 | AGE26AL | WTG 496 | RC2_BARKAT_SANY650MT | 2025-10-17 | Done | 2026-01-24 | 2026-01-26 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-07 | 2026-02-07
102 | PSS-05 | AHEJ5L | WTG 551 | RC5_SETHIA-SANY750MT | 2026-01-15 | Done | 2026-01-31 | 2026-02-02 | 2026-02-03 | 2026-02-10 | 2026-02-10 | 2026-02-11 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14
103 | PSS-05 | AHEJ5L | WTG 555 | AC9_ADA_SANY750MT | 2026-01-19 | Done | 2026-01-31 | 2026-02-02 | 2026-02-03 | 2026-02-10 | 2026-02-10 | 2026-02-12 | 2026-02-12 | 2026-02-13 | 2026-02-13 | 2026-02-14
104 | PSS-05 | AHEJ5L | WTG 553 | RC1_SETHIA-SANY750MT | 2026-01-26 | Done | 2026-02-09 | 2026-02-10 | 2026-01-10 | 2026-02-11 | 2026-02-12 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16
105 | PSS-12 | AGE26AL | WTG 453 | AC3_ADA_SANY750MT | 2026-01-07 | Done | 2026-01-26 | 2026-01-27 | 2026-02-01 | 2026-02-11 | 2026-02-12 | 2026-02-14 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17
106 | PSS-12 | AGE26AL | WTG 535 | AC7_ADA_SANY750MT | 2025-12-24 | Done | 2026-01-24 | 2026-01-27 | 2026-02-01 | 2026-02-14 | 2026-02-14 | 2026-02-15 | 2026-02-15 | 2026-02-17 | 2026-02-18 | 2026-02-19
107 | PSS-12 | AGE26AL | WTG 499 | RC2_BARKAT_SANY650MT | 2026-01-17 | Done | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-15 | 2026-02-15 | 2026-02-16 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19
108 | PSS-12 | AGE26AL | WTG 476 | AC10_ADA_SANY750MT | 2025-12-26 | Done | 2026-01-31 | 2026-02-01 | 2026-02-07 | 2026-02-15 | 2026-02-15 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19
109 | PSS-12 | AGE26AL | WTG 500 | AC8_ADA_SANY750MT | 2026-01-03 | Done | 2026-01-31 | 2026-02-02 | 2026-02-07 | 2026-02-14 | 2026-02-15 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19
110 | PSS-12 | AGE26AL | WTG 533 | RC3_BARKAT_SANY750MT | 2026-01-04 | Done | 2026-01-26 | 2026-01-29 | 2026-02-07 | 2026-02-15 | 2026-02-15 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-20
111 | PSS-08 | ASEJ6PL | WTG 141 | AC5_ADA_SANY750MT | 2025-07-30 | Done | 2026-01-24 | 2026-01-27 | 2026-02-01 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-18 | 2026-02-20 | 2026-02-21 | 2026-02-22
112 | PSS-12 | AGE26AL | WTG 428 | AC2_ADA_SANY750MT | 2026-01-06 | Done | 2026-01-27 | 2026-01-29 | 2026-02-04 | 2026-02-14 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19
113 | PSS-12 | AGE26AL | WTG 426 | AC9_ADA_SANY750MT | 2026-02-08 | Done | 2026-02-15 | 2026-02-17 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23
114 | PSS-12 | AGE26AL | WTG 377 | RC5_SETHIA-SANY750MT | 2026-01-23 | Done | 2026-02-15 | 2026-02-17 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-19 | 2026-02-20 | 2026-02-22 | 2026-02-22 | 2026-02-23
115 | PSS-14 | AGE25CL | WTG 449 | AC6_ADA_SANY750MT | 2025-12-01 | Done | 2026-02-04 | 2026-02-05 | 2026-02-09 | 2026-02-18 | 2026-02-18 | 2026-02-19 | 2026-02-19 | 2026-02-21 | 2026-02-23 | 2026-02-24
116 | PSS-12 | AGE26AL | WTG 427 | RC1_SETHIA-SANY750MT | 2025-12-05 | Done | 2026-02-16 | 2026-02-19 | 2026-02-19 | 2026-02-21 | 2026-02-21 | 2026-02-22 | 2026-02-22 | 2026-02-24 | 2026-02-25 | 2026-02-26
117 | PSS-14 | AGE25CL | WTG 373 | RC4_SETHIA-SANY750MT | 2025-11-20 | Done | 2026-01-26 | 2026-01-27 | 2026-02-09 | 2026-02-18 | 2026-02-18 | 2026-02-19 | 2026-02-19 | 2026-02-23 | 2026-02-25 | 2026-02-26
118 | PSS-08 | ASEJ6PL | WTG 121 | AC1_ADA_SANY750MT | 2026-01-21 | Done | 2026-02-05 | 2026-02-09 | 2026-02-10 | 2026-02-16 | 2026-02-18 | 2026-02-18 | 2026-02-23 | 2026-02-25 | 2026-02-26 | 2026-02-27
119 | PSS-12 | AGE26AL | WTG 452 | AC3_ADA_SANY750MT | 2026-01-27 | Done | 2026-02-19 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-23 | 2026-02-24 | 2026-02-24 | 2026-02-28 |  |  | Nacelle cover erection plan
120 | PSS-14 | AGE25CL | WTG 423 | RC2_BARKAT_SANY650MT | 2025-11-14 | Done | 2026-02-19 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-25 | 2026-02-26 | 2026-02-26 |  |  |  | Blade preparation wip
121 | PSS-12 | AGE26AL | WTG 517 | AC7_ADA_SANY750MT | 2026-02-09 | Done | 2026-02-19 | 2026-02-21 | 2026-02-22 | 2026-02-24 | 2026-02-25 | 2026-02-27 | 2026-02-27 |  |  |  | Blade preparation wip
122 | PSS-12 | AGE26AL | WTG 451 | AC10_ADA_SANY750MT | 2026-02-06 | Done | 2026-02-20 | 2026-02-23 | 2026-02-24 | 2026-02-26 | 2026-02-26 | 2026-02-27 | 2026-02-28 |  |  |  | Blade erection delay due to blade not availablde at site
123 | PSS-12 | AGE26AL | WTG 497 | AC8_ADA_SANY750MT | 2026-02-12 | Done | 2026-02-20 | 2026-02-22 | 2026-02-24 | 2026-02-27 | 2026-02-27 | 2026-02-28 |  |  |  |  | HUB erection delay due to hub not availablde at site
124 | PSS-14 | AGE25CL | WTG 425 | RC3_BARKAT_SANY750MT | 2025-12-19 | Done | 2026-02-20 | 2026-02-22 | 2026-02-23 | 2026-02-25 | 2026-02-26 | [5 empty] | DT erectipn plan
125 | PSS-12 | AGE26AL | WTG 477 | AC2_ADA_SANY750MT | 2026-02-13 | Done | 2026-02-23 | 2026-02-26 | 2026-02-27 | [7 empty] | Tower erection wip
126 | PSS-08 | ASEJ6PL | WTG 208 | AC5_ADA_SANY750MT | 2025-08-26 | Done | 2026-02-22 | 2026-02-24 | [8 empty] | Tower preparation wip
127 | PSS-14 | AGE25CL | WTG 424 | RC5_SETHIA-SANY750MT | 2026-02-14 | Done | 2026-02-23 | 2026-02-26 | [8 empty] | Tower erection delay due to grouting curing
128 | PSS-14 | AGE26AL | KH 621 | AC6_ADA_SANY750MT | 2026-01-26 | Done | 2026-02-26 | [9 empty] | Crane Assembly wip
129 | PSS-14 | AGE26AL | KH 592 | RC1_SETHIA-SANY750MT | 2025-10-21 | Done | 2026-02-26 | [9 empty] | Crane Assembly wip
130 | PSS-14 | AGE26AL | KH 606 | RC4_SETHIA-SANY750MT | 2025-10-08 | Done | 2026-02-27 | [9 empty] | Crane Assembly wip
131 | PSS-14 | AGE26AL | KH 60 | AC1_ADA_SANY750MT | 2026-01-18 | Done | 2026-02-28 | [9 empty] | Crane Assembly wip
132 | PSS-08 | ASEJ6PL | WTG 230
133 | PSS-08 | ASEJ6PL | WTG 164
134 | PSS-14 | AGE25CL | WTG 450 |  | 2026-02-17
135 | PSS-14 | AGE25CL | WTG 473 |  | 2026-02-23
136 | PSS-14 | AGE25CL | WTG 474 |  | 2026-02-15
137 | PSS-14 | AGE25CL | WTG 532 |  | 2026-01-08
138 | PSS-14 | AGE25CL | WTG 516
139 | PSS-14 | AGE26AL | KH 53 |  | 2025-12-15
140 | PSS-14 | AGE26AL | KH 54 |  | 2025-05-13
141 | PSS-14 | AGE26AL | KH 55
142 | PSS-14 | AGE26AL | KH 56 |  | 2026-02-25
143 | PSS-14 | AGE26AL | KH 57 |  | 2025-06-26
144 | PSS-14 | AGE26AL | KH 58 |  | 2026-01-14
145 | PSS-14 | AGE26AL | KH 59 |  | 2026-02-23
146 | PSS-14 | AGE26AL | KH 61 |  | 2026-01-30
147 | PSS-14 | AGE26AL | KH 556 |  | 2026-01-29
148 | PSS-14 | AGE26AL | KH 523 |  | 2026-02-22
149 | PSS-14 | AGE26AL | KH 522 |  | 2026-02-21
150 | PSS-14 | AGE26AL | KH 521
151 | PSS-14 | AGE26AL | KH 508 |  | 2026-02-05
152 | PSS-14 | AGE26AL | KH 555 |  | 2026-02-03
153 | PSS-14 | AGE26AL | KH 557 |  | 2026-02-10
154 | PSS-14 | AGE26AL | KH 581 |  | 2026-01-10
155 | PSS-14 | AGE26AL | KH 582
156 | PSS-14 | AGE26AL | KH 583
157 | PSS-14 | AGE26AL | KH 52 |  | 2026-02-19
158 | PSS-14 | AGE26AL | KH 51 |  | 2026-01-26
159 | PSS-14 | AGE26AL | KH 552
160 | PSS-14 | AGE26AL | KH 588 |  | 2025-06-12
161 | PSS-14 | AGE26AL | KH 589 |  | 2025-08-11
162 | PSS-14 | AGE26AL | KH 590 |  | 2026-01-13
163 | PSS-14 | AGE26AL | KH 591
164 | PSS-14 | AGE26AL | KH 550 |  | 2026-02-02
165 | PSS-14 | AGE26AL | KH 551 |  | 2026-02-18
166 | PSS-14 | AGE26AL | KH 579 |  | 2026-02-27
167 | PSS-14 | AGE26AL | KH 596 |  | 2026-02-11
168 | PSS-14 | AGE26AL | KH 597 |  | 2026-02-16
169 | PSS-14 | AGE26AL | KH 598 |  | 2025-11-05
170 | PSS-14 | AGE26AL | KH 599 |  | 2026-02-24
171 | PSS-14 | AGE26AL | KH 600 |  | 2025-12-07
172 | PSS-14 | AGE26AL | KH 553
173 | PSS-14 | AGE26AL | KH 580 |  | 2026-01-05
174 | PSS-14 | AGE26AL | KH 478
175 | PSS-14 | AGE26AL | KH 604 |  | 2025-09-23
176 | PSS-14 | AGE26AL | KH 605 |  | 2025-10-13
177 | PSS-14 | AGE26AL | KH 607
178 | PSS-14 | AGE26AL | KH 608 |  | 2026-01-30
179 | PSS-14 | AGE26AL | KH 509
180 | PSS-14 | AGE26AL | KH 554
181 | PSS-14 | AGE26AL | KH 611
182 | PSS-14 | AGE26AL | KH 612 |  | 2025-08-29
183 | PSS-14 | AGE26AL | KH 613 |  | 2025-09-02
184 | PSS-14 | AGE26AL | KH 614
185 | PSS-14 | AGE26AL | KH 615 |  | 2025-11-23
186 | PSS-14 | AGE26AL | KH 47
187 | PSS-14 | AGE26AL | KH 617 |  | 2026-02-28
188 | PSS-14 | AGE26AL | KH 618
189 | PSS-14 | AGE26AL | KH 619 |  | 2025-11-16
190 | PSS-14 | AGE26AL | KH 620
191 | PSS-14 | AGE26AL | KH 622
192 | PSS-14 | AGE26AL | KH 34 |  | 2026-01-24
193 | PSS-14 | AGE26AL | KH 35
194 | PSS-14 | AGE26AL | KH 68
| PSS-10 | AGE26BL | WTG 434 | AC9_ADA_SANY750MT |  | Done | 2026-02-23 | 2026-02-25 | [8 empty] | Tower preparation wip
Formulas:
Raft Casting Finish = IF(XLOOKUP([Location],'WTG PH-III'!$D5:D198,'WTG PH-III'!$BV5:BV198,0,0,1)>0,XLOOKUP([Location],'WTG PH-III'!$D5:D198,'WTG PH-III'!$BV5:BV198,0,0,1),"")
Note on D58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 09-Sep-25 RC 2 Reached at Loc.143, Cabin unloading hold due to water logging & wet soil, Main crane breakdown from 5-Dec-25. AC-7 Reached at Loc.143 on 5-Dec-25.

## Manpower
MANPOWER SUMMARY
Sr No | Contractor Name | Type Of Contract | Area | Manpower Details | time axis 2025-01-01 to 2026-02-27
Day | time axis 2025-01-01 to 2026-02-27
|  |  |  | Total Manpower(P) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 195 | 195 | 195 | 205 | 205 | 130 | 300 | 300 | 300 | 320 | 320 | 320 | 380 | 390 | 390 | 430 | 430 | 430 | 430 | 500 | 515 | 550 | 555 | 565 | 565 | 565 | 565 | 565 | 565 | 565 | 565 | 565 | 565 | 565 | 565 | 595 | 625 | 625 | 625 | 645 | 645 | 645 | 645 | 665 | 665 | 665 | 665 | 665 | 705 | 705 | 705 | 705 | 535 | 535 | 535 | 535 | 535 | 535 | 570 | 570 | 575 | 585 | 620 | 690 | 690 | 690 | 690 | 690 | 690 | 725 | 725 | 720 | 710 | 705 | 700 | 690 | 765 | 765 | 765 | 765 | 765 | 795 | 820 | 820 | 820 | 820 | 820 | 820 | 820 | 820 | 820 | 820 | 820 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 785 | 775 | 775 | 775 | 775 | 775 | 775 | 895 | 940 | 940 | 940 | 1025 | 1080 | 1070 | 1350 | 1350 | 1350 | 1390 | 1390 | 1705 | 1705 | 1705 | 1705 | 1705 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1190 | 1185 | 1175 | 1175 | 1175 | 1175 | 1175 | 1140 | 1140 | 1135 | 1135 | 1135 | 1130 | 1120 | 1120 | 1105 | 1105 | 1095 | 1075 | 1010 | 980 | 980 | 980 | 890 | 885 | 885 | 885 | 885 | 885 | 920 | 920 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 1025 | 1025 | 1025 | 1025 | 1025 | 1025 | 1050 | 1050 | 990 | 1050 | 1050 | 1050 | 1050 | 1050 | 1030 | 1030 | 1030 | 1030 | 1030 | 1030 | 1030 | 1030 | 1000 | 1000 | 990 | 990 | 990 | 990 | 990 | 990 | 990 | 990 | 990 | 990 | 990 | 1055 | 1055 | 1055 | 1055 | 1025 | 1025 | 1025 | 1025 | 1025 | 1025 | 1025 | 1025 | 1025 | 1025 | 1025 | 1025 | 1025 | 1075 | 2139 | 2104 | 2119 | 2119 | 2184 | 2214 | 2226 | 2226 | 2231 | 2231 | 2231 | 2231 | 2231 | 2231 | 2231 | 2231 | 2231 | 2231 | 2231 | 2231 | 2231 | 2231 | 2231 | 2191 | 2191 | 2236 | 2266 | 2266 | 2296 | 2296 | 2296 | 2341 | 2341 | 2341 | 2341 | 2341 | 2341 | 2341 | 2341 | 2341 | 2341 | 2341 | 2341 | 2341 | 2341 | 2341 | 2331 | 2331 | 2331 | 2338 | 2338 | 2338 | 2339 | 2339 | 2339 | 2339 | 2354 | 2354 | 2354 | 2354 | 2354 | 2354 | 2514 | 2514 | 2514 | 2514 | 2514 | 2514 | 2514 | 2514 | 2527 | 2527 | 2497 | 2497 | 2497 | 2497 | 2497 | 2522 | 2522 | 2522 | 2522 | 2560 | 2560 | 2560 | 2560 | 2560 | 2560 | 2560 | 2560 | 2560 | 2560 | 2520 | 2520 | 2520 | 2520 | 2520 | 2520 | 2520 | 2520 | 2520 | 2480 | 2480 | 2480 | 2480 | 2480 | 2480 | 2480 | 2480 | 2480 | 2480 | 2480 | 2480 | 2480 | 2480 | 2475 | 2495 | 2490 | 2465 | 2465 | 2465 | 2465 | 2465 | 2465 | 2465 | 2465 | 2465 | 2465 | 2465 | 2465 | 2465 | 2465 | 2465 | 2465 | 2465 | 2465 | 2465 | 2465 | 2465 | 2465 | 2465 | 2465
|  |  |  | Total Manpower(A) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 161 | 161 | 161 | 165 | 167 | 55 | 249 | 249 | 253 | 249 | 249 | 251 | 131 | 276 | 278 | 283 | 331 | 165 | 179 | 223 | 393 | 379 | 328 | 285 | 36 | 270 | 193 | 267 | 267 | 263 | 283 | 279 | 269 | 158 | 267 | 331 | 411 | 386 | 390 | 375 | 350 | 350 | 365 | 356 | 368 | 388 | 372 | 160 | 394 | 387 | 380 | 380 | 409 | 398 | 393 | 375 | 373 | 361 | 360 | 367 | 407 | 173 | 420 | 520 | 504 | 486 | 504 | 504 | 562 | 598 | 578 | 568 | 274 | 602 | 600 | 388 | 592 | 628 | 605 | 599 | 329 | 315 | 107 | 247 | 294 | 324 | 324 | 497 | 517 | 515 | 513 | 540 | 531 | 500 | 504 | 526 | 265 | 525 | 509 | 555 | 555 | 539 | 547 | 338 | 578 | 606 | 596 | 601 | 646 | 659 | 436 | 702 | 709 | 772 | 786 | 985 | 961 | 846 | 1153 | 813 | 1299 | 1146 | 1322 | 1288 | 1153 | 1298 | 1324 | 1332 | 1326 | 1131 | 1174 | 881 | 1194 | 753 | 701 | 737 | 765 | 770 | 720 | 678 | 688 | 697 | 643 | 648 | 665 | 644 | 654 | 702 | 582 | 592 | 594 | 536 | 489 | 447 | 472 | 513 | 394 | 379 | 357 | 284 | 394 | 398 | 491 | 462 | 593 | 598 | 385 | 579 | 599 | 611 | 625 | 644 | 630 | 408 | 682 | 652 | 606 | 659 | 388 | 577 | 525 | 766 | 777 | 653 | 691 | 656 | 710 | 687 | 602 | 656 | 680 | 710 | 737 | 727 | 512 | 706 | 644 | 725 | 746 | 749 | 749 | 374 | 288 | 263 | 290 | 290 | 354 | 310 | 338 | 347 | 467 | 454 | 478 | 545 | 506 | 477 | 637 | 598 | 726 | 860 | 582 | 837 | 645 | 829 | 829 | 829 | 779 | 829 | 694 | 750 | 776 | 771 | 803 | 757 | 1629 | 1632 | 1632 | 1609 | 1639 | 1673 | 1678 | 1625 | 1444 | 1345 | 1332 | 1358 | 1487 | 1457 | 1475 | 1431 | 1446 | 1403 | 1459 | 1581 | 1495 | 1567 | 1511 | 1404 | 1540 | 1441 | 1509 | 1692 | 1768 | 1791 | 1766 | 1721 | 1742 | 1692 | 1735 | 1711 | 1530 | 1761 | 1779 | 1743 | 1722 | 1720 | 1720 | 1692 | 1684 | 1824 | 1785 | 1805 | 1813 | 1841 | 1869 | 1846 | 1855 | 1809 | 1841 | 1840 | 1932 | 1933 | 1946 | 1916 | 2027 | 1931 | 2050 | 2028 | 1950 | 1730 | 1930 | 1935 | 1918 | 1943 | 1944 | 1972 | 1877 | 1934 | 1962 | 1955 | 1966 | 2044 | 2066 | 2041 | 2011 | 2065 | 2064 | 2004 | 1995 | 2003 | 2007 | 1934 | 1962 | 2016 | 1991 | 1996 | 2000 | 1929 | 1985 | 2000 | 1902 | 2000 | 2084 | 2062 | 1987 | 2011 | 2010 | 2011 | 2011 | 2011 | 2011 | 2011 | 1988 | 1988 | 1988 | 1988 | 1988 | 1988 | 1912 | 1861 | 1997 | 1968 | 1933 | 1930 | 1929 | 1990 | 1995 | 2036 | 2033 | 1926 | 1919 | 1899 | 1862 | 1853 | 1871 | 1877 | 1860 | 1872 | 1824 | 1833 | 1822 | 1778 | 1774 | 1802 | 1828
1 | M/s Saritha Enterprise | Service | Stone Column | Manpower Details (P) | [35 empty] | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 |  | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 40 | 40 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
|  |  |  | Manpower Details (A) | [35 empty] | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 |  | 25 | 25 | 25 | 25 | 25 | 25 | 0 | 25 | 25 | 25 | 25 |  |  | 0 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 20 | 20 | 20 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 22 | 22 | 22 | 22 | 22 |  | 22 | 54 | 54 | 54 | 30 | 25 | 0 | 20 | 20 | 20 | 20 | 20 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 0 | 17 | 17 | 17 | 17 | 17 | 17 | 0 | 17 | 17 | 17 | 17 | 21 | 21 | 0 | 21 | 21 | 21 | 21 | 21 | 21 | 10 | 21 | 12 | 12 | 12 | 15 | 15 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 0 | 10 | 15 | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 10 | 15 | 15 | 15 | 15 | 15 | 15 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  | 10 | 10 | 10 | 10 | 10 | 10 |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 20 | 25 | 30 | 40 | 45 | 45 | 45 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
2 | M/s Freyssinet Menard India Pvt Ltd | Service | Stone Column | Manpower Details (P) | 2025-03-25: 30; 2025-03-26: 30; 2025-03-27: 30; 2025-03-28: 30; 2025-03-29: 30; 2025-03-30: 30; 2025-03-31: 30; 2025-04-01: 30; 2025-04-02: 30; 2025-04-03: 30; 2025-04-04: 30; 2025-04-05: 30; 2025-04-06: 30; 2025-04-07: 30; 2025-04-08: 30; 2025-04-09: 30; 2025-04-10: 30; 2025-04-11: 30; 2025-04-12: 30; 2025-04-13: 30; 2025-04-14: 30; 2025-04-15: 30; 2025-04-16: 30; 2025-04-17: 30; 2025-04-18: 30; 2025-04-19: 30; 2025-04-20: 30; 2025-04-21: 30; 2025-04-22: 30; 2025-04-23: 30; 2025-04-24: 30; 2025-04-25: 30; 2025-04-26: 30; 2025-04-27: 30; 2025-04-28: 30; 2025-04-29: 30; 2025-04-30: 30; 2025-05-01: 30; 2025-05-02: 30; 2025-05-03: 30; 2025-05-04: 30; 2025-05-05: 30; 2025-05-06: 30; 2025-05-07: 30; 2025-05-08: 30; 2025-05-09: 30; 2025-05-10: 30; 2025-05-11: 30; 2025-05-12: 30; 2025-05-13: 30; 2025-05-14: 30; 2025-05-15: 30; 2025-05-16: 30; 2025-05-17: 30; 2025-05-18: 30; 2025-05-19: 30; 2025-05-20: 30; 2025-05-21: 30; 2025-05-22: 30; 2025-05-23: 30; 2025-05-24: 30; 2025-05-25: 30; 2025-05-26: 30; 2025-05-27: 30; 2025-05-28: 30; 2025-05-29: 30; 2025-05-30: 30; 2025-05-31: 30; 2025-06-01: 30; 2025-06-02: 30; 2025-06-03: 30; 2025-06-04: 30; 2025-06-05: 30; 2025-06-06: 30; 2025-06-07: 30; 2025-06-08: 30; 2025-06-09: 30; 2025-06-10: 30; 2025-06-11: 30; 2025-06-12: 30; 2025-06-13: 30; 2025-06-14: 30; 2025-06-15: 30; 2025-06-16: 30; 2025-06-17: 30; 2025-06-18: 30; 2025-06-19: 30; 2025-06-20: 30; 2025-06-21: 30; 2025-06-22: 30; 2025-06-23: 30; 2025-06-24: 30; 2025-06-25: 30; 2025-06-26: 30; 2025-06-27: 30; 2025-06-28: 30; 2025-06-29: 30; 2025-06-30: 30; 2025-07-01: 30; 2025-07-02: 30; 2025-07-03: 30; 2025-07-04: 30; 2025-07-05: 30; 2025-07-06: 30; 2025-07-07: 30
|  |  |  | Manpower Details (A) | [83 empty] | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 0 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 35 | 35 | 35 | 35 | 35 | 0 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 0 | 35 | 35 |  | 35 | 35 | 35 | 35 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 35 | 35 | 0 | 35 | 35 | 35 | 35 | 11 | 11 | 0 | 35 | 11 | 11 | 11 | 11 | 11 | 0 | 11 | 11 | 11 | 11 | 11 | 11 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 0 | 11 | 11 | 11 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | M/s Bauer | Service | Stone Column | Manpower Details (P) | [35 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 110 | 110 | 110 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 180 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120
|  |  |  | Manpower Details (A) | [35 empty] | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 |  | 76 | 76 | 76 | 76 | 76 | 76 | 0 | 76 | 76 | 76 | 76 |  |  | 0 | 76 | 76 | 58 | 58 | 0 | 58 | 20 | 58 | 58 | 58 | 40 | 40 | 40 | 0 | 40 | 70 | 100 | 100 | 100 | 125 | 130 | 130 | 140 | 140 | 140 | 140 | 140 | 0 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 120 | 120 | 120 | 120 | 120 | 0 | 120 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 192 | 192 | 0 | 192 | 192 | 140 | 192 | 192 | 192 | 192 | 160 | 160 | 0 | 4 | 4 | 4 | 4 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 7 | 190 | 190 | 190 | 190 | 190 | 190 | 100 | 190 | 190 | 190 | 190 | 190 | 190 | 10 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 80 | 190 | 190 | 190 | 190 | 190 | 190 | 0 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 135 | 135 | 150 | 150 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 10 | 60 | 60 | 60 | 60 | 150 | 150 | 50 | 150 | 150 | 150 | 150 | 150 | 150 | 0 | 150 | 150 | 150 | 150 | 0 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 0 | 150 | 150 | 150 | 150 | 150 | 150 | 0 | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 0 | 150 | 150 | 150 | 120 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 110 | 110 | 110 | 110 |  | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 |  | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 |  | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 79 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 |  | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 70 | 70 | 70 | 70 | 70
4 | M/s Keller | Service | Stone Column | Manpower Details (P) | [35 empty] | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 80 | 80 | 80 | 80 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60
|  |  |  | Manpower Details (A) | [35 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 15 | 40 | 40 | 40 | 40 |  |  | 0 | 40 | 40 | 20 | 20 | 0 | 20 | 0 | 20 | 20 | 20 | 40 | 40 | 40 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 40 | 40 | 0 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 2 | 2 | 2 | 2 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 10 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 20 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 40 | 40 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 24 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 24 | 24 | 24 | 24 | 24 | 24 | 0 | 0 | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 25 | 25 | 25 | 25 | 25 | 25 | 24 | 24 | 24 | 24 | 24 | 35 | 35 | 35 | 35 |  | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 |  | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 |  | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 20 | 20 | 20 | 20 | 20 | 20 |  | 20 | 20 |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
5 | M/s Kamar | Service | Stone Column | Manpower Details (P) | [129 empty] | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Manpower Details (A) | [129 empty] | 26 | 26 | 12 | 12 | 12 | 12 | 12 | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | M/s Pinnacle India | Service | Stone Column | Manpower Details (P) | [130 empty] | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
|  |  |  | Manpower Details (A) | [130 empty] | 0 | 13 | 13 | 13 | 13 | 13 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 10 | 15 | 15 | 15 | 15 | 15 | 15 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 23 | 23 | 0 | 23 | 23 | 23 | 23 | 23 | 23 | 0 | 23 | 23 | 23 | 23 | 0 | 23 | 0 | 23 | 23 | 23 | 23 | 23 | 23 | 17 | 23 | 23 | 23 | 23 | 23 | 23 | 0 | 17 | 17 | 17 | 17 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 17 | 17 | 17 | 17 |  | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 |  | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 |  | 17 | 17 | 17 | 17 | 17 | 17 |  | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 |  | 17 | 17 |  | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
7 | M/s ITDC | Service | Stone Column | Manpower Details (P) | [54 empty] | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
|  |  |  | Manpower Details (A) | [54 empty] | 22 | 22 | 26 | 26 | 26 | 26 | 0 | 26 | 26 | 26 | 26 |  |  | 0 | 26 | 26 | 26 | 26 | 0 | 26 | 0 | 26 | 26 | 26 | 26 | 26 | 26 | 0 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 0 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 29 | 29 | 0 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 0 | 29 | 29 | 0 | 29 | 29 | 29 | 29 | 29 | 27 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 10 | 25 | 25 | 25 | 25 | 25 | 25 | 0 | 25 | 25 | 25 | 25 | 25 | 25 | 12 | 12 | 25 | 25 | 25 | 25 | 25 | 0 | 25 | 25 | 25 | 25 | 25 | 25 | 0 | 25 | 25 | 25 | 25 | 25 | 25 | 0 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 0 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 10 | 20 | 20 | 20 | 20 | 35 | 35 | 0 | 35 | 35 | 35 | 35 | 35 | 35 | 0 | 35 | 35 | 35 | 35 | 0 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 0 | 35 | 35 | 35 | 35 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 25 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 18 | 18 | 18 | 18 |  | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | 18 | 18 | 18 | 18 | 18 | 18
8 | M/s AB Infra | Service | FDN | Manpower Details (P) | [57 empty] | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 20 | 20 | 20 | 20 | 20 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Manpower Details (A) | 2025-02-27: 5; 2025-02-28: 5; 2025-03-01: 8; 2025-03-02: 12; 2025-03-03: 12; 2025-03-04: 12; 2025-03-05: 13; 2025-03-06: 13; 2025-03-07: 14; 2025-03-08: 18; 2025-03-09: 20; 2025-03-10: 23; 2025-03-11: 13; 2025-03-12: 29; 2025-03-13: 29; 2025-03-14: 0; 2025-03-15: 31; 2025-03-16: 43; 2025-03-17: 43; 2025-03-18: 43; 2025-03-19: 43; 2025-03-20: 43; 2025-03-21: 43; 2025-03-22: 43; 2025-03-23: 43; 2025-03-24: 43; 2025-03-25: 43; 2025-03-26: 43; 2025-03-27: 43; 2025-03-28: 43; 2025-03-29: 43; 2025-03-30: 31; 2025-03-31: 31; 2025-04-01: 33; 2025-04-02: 20; 2025-04-03: 20; 2025-04-04: 20; 2025-04-05: 4; 2025-04-06: 4; 2025-04-07: 4; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0; 2025-04-11: 10; 2025-04-12: 10; 2025-04-13: 8; 2025-04-14: 6; 2025-04-15: 10; 2025-04-16: 13; 2025-04-17: 0; 2025-04-18: 0; 2025-04-19: 0; 2025-04-20: 0; 2025-04-21: 0; 2025-04-22: 0; 2025-04-23: 0; 2025-04-24: 0; 2025-04-25: 0; 2025-04-26: 0; 2025-04-27: 0; 2025-04-28: 0; 2025-04-29: 0; 2025-04-30: 0; 2025-05-01: 0; 2025-05-02: 0; 2025-05-03: 0; 2025-05-04: 10; 2025-05-05: 15; 2025-05-06: 10; 2025-05-07: 15; 2025-05-08: 15; 2025-05-09: 0; 2025-05-10: 10; 2025-05-11: 16; 2025-05-12: 14; 2025-05-13: 26; 2025-05-14: 26; 2025-05-15: 26; 2025-05-16: 22; 2025-05-17: 26; 2025-05-18: 26; 2025-05-19: 24; 2025-05-20: 24; 2025-05-21: 22; 2025-05-22: 22; 2025-05-23: 13; 2025-05-24: 8; 2025-05-25: 13; 2025-05-26: 12; 2025-05-27: 20; 2025-05-28: 20; 2025-05-29: 20; 2025-05-30: 10; 2025-05-31: 10; 2025-06-01: 10; 2025-06-02: 10; 2025-06-03: 6; 2025-06-04: 5; 2025-06-05: 3; 2025-06-06: 2; 2025-06-07: 0; 2025-06-08: 0; 2025-06-09: 0; 2025-06-10: 0; 2025-06-11: 0; 2025-06-12: 0; 2025-06-13: 0; 2025-06-14: 0; 2025-06-15: 0; 2025-06-16: 0; 2025-06-17: 0; 2025-06-18: 0; 2025-06-19: 0; 2025-06-20: 0; 2025-06-21: 0; 2025-06-22: 0; 2025-06-23: 0; 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0; 2025-08-13: 0; 2025-08-14: 0; 2025-08-15: 0; 2025-08-16: 0; 2025-08-17: 0; 2025-08-18: 0; 2025-08-19: 0; 2025-08-20: 0; 2025-08-21: 0; 2025-08-22: 0; 2025-08-23: 0; 2025-08-24: 0; 2025-08-25: 0; 2025-08-26: 0; 2025-08-27: 0; 2025-08-28: 0; 2025-08-29: 0; 2025-08-30: 0; 2025-08-31: 0; 2025-09-01: 0; 2025-09-02: 0; 2025-09-03: 0; 2025-09-04: 0; 2025-09-05: 0; 2025-09-06: 0; 2025-09-07: 0; 2025-09-08: 0; 2025-09-09: 0; 2025-09-10: 0; 2025-09-11: 0; 2025-09-12: 0; 2025-09-13: 0; 2025-09-14: 0; 2025-09-15: 0; 2025-09-16: 0; 2025-09-17: 0; 2025-09-18: 0; 2025-09-19: 0; 2025-09-20: 0; 2025-09-21: 0; 2025-09-22: 0; 2025-09-23: 0; 2025-09-24: 0; 2025-09-25: 0; 2025-09-26: 0; 2025-09-27: 0; 2025-09-28: 0; 2025-09-29: 0; 2025-09-30: 0; 2025-10-01: 0; 2025-10-02: 0; 2025-10-03: 0; 2025-10-04: 0; 2025-10-05: 0; 2025-10-06: 0; 2025-10-07: 0; 2025-10-08: 0; 2025-10-09: 0; 2025-10-10: 0; 2025-10-11: 0; 2025-10-12: 0; 2025-10-13: 0; 2025-10-14: 0; 2025-10-15: 0; 2025-10-16: 0; 2025-10-17: 0; 2025-10-18: 0; 2025-10-19: 0; 2025-10-20: 0; 2025-10-21: 0; 2025-10-22: 0; 2025-10-23: 0; 2025-10-24: 0; 2025-10-25: 0; 2025-10-26: 0; 2025-10-27: 0; 2025-10-28: 0; 2025-10-29: 0; 2025-10-30: 0; 2025-10-31: 0
9 | M/s DNC | Service | FDN | Manpower Details (P) | [60 empty] | 20 | 20 | 20 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 30 | 30 | 30 | 30 | 30 | 30 | 25 | 25 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
|  |  |  | Manpower Details (A) | [60 empty] | 12 | 10 | 12 | 12 | 55 | 40 | 42 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 11 | 8 | 10 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 14 | 14 | 14 | 14 | 23 | 22 | 20 | 22 | 23 | 0 | 14 | 15 | 15 | 16 | 14 | 16 | 16 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 21 | 21 | 20 | 15 | 18 | 18 | 23 | 2 | 2 | 4 | 0 | 8 | 20 | 18 | 18 | 18 | 18 | 18 | 18 | 16 | 18 | 18 | 3 | 18 | 9 | 15 | 12 | 0 | 20 | 19 | 19 | 10 | 15 | 25 | 25 | 0 | 30 | 24 | 11 | 14 | 25 | 32 | 19 | 22 | 10 | 24 | 22 | 19 | 17 | 16 | 10 | 12 | 8 | 11 | 11 | 8 | 11 | 11 | 13 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 12 | 14 | 14 | 14 | 14 | 15 | 14 | 14 | 14 | 14 | 25 | 20 | 70 | 70 | 70 | 66 | 56 | 0 | 61 | 61 | 60 | 61 | 60 | 7 | 20 | 16 | 12 | 9 | 7 | 26 | 26 | 26 | 14 | 14 | 26 | 26 | 26 | 2 | 15 | 45 | 46 | 12 | 39 | 45 | 45 | 47 | 24 | 12 | 12 | 15 | 15 | 19 | 28 | 10 | 10 | 16 | 2 | 2 | 14 | 10 | 10 | 10 | 43 | 43 | 43 | 44 | 46 | 52 | 38 | 38 | 10 | 16 | 40 | 40 | 40 | 40 | 40 | 20 | 11 | 42 | 42 | 29 | 29 | 34 | 34 | 34 | 32 | 51 | 51 | 51 | 51 | 51 | 51 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 23 | 32 | 23 | 23 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 8 | 8 | 8 | 6 | 6 | 6
10 | M/s MSC | Service | FDN | Manpower Details (P) | [51 empty] | 10 | 10 | 10 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120
|  |  |  | Manpower Details (A) | [51 empty] | 4 | 4 | 4 | 35 | 35 | 35 | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 22 | 22 | 20 | 0 | 0 | 3 | 3 | 15 | 60 | 60 | 80 | 80 | 77 | 70 | 70 | 72 | 74 | 74 | 59 | 89 | 73 | 72 | 72 | 87 | 82 | 83 | 87 | 87 | 87 | 87 | 87 | 118 | 120 | 125 | 93 | 89 | 95 | 97 | 98 | 95 | 97 | 97 | 95 | 0 | 0 | 0 | 75 | 102 | 124 | 124 | 80 | 92 | 86 | 85 | 87 | 90 | 90 | 95 | 95 | 95 | 88 | 88 | 92 | 92 | 103 | 76 | 104 | 101 | 116 | 112 | 100 | 100 | 93 | 98 | 98 | 102 | 105 | 91 | 97 | 87 | 100 | 105 | 15 | 121 | 101 | 126 | 119 | 122 | 132 | 132 | 130 | 130 | 27 | 30 | 53 | 43 | 43 | 25 | 62 | 72 | 58 | 58 | 50 | 35 | 31 | 16 | 18 | 23 | 34 | 34 | 37 | 34 | 34 | 35 | 5 | 20 | 0 | 39 | 41 | 19 | 16 | 19 | 20 | 27 | 33 | 33 | 53 | 48 | 18 | 26 | 24 | 54 | 61 | 59 | 63 | 50 | 68 | 69 | 62 | 42 | 49 | 21 | 25 | 30 | 67 | 62 | 42 | 61 | 0 | 2 | 2 | 4 | 5 | 51 | 48 | 49 | 47 | 51 | 48 | 39 | 43 | 41 | 29 | 39 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 28 | 28 | 28 | 32 | 70 | 70 | 60 | 60 | 69 | 63 | 60 | 0 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 20 | 20 | 27 | 27 | 29 | 28 | 25 | 24 | 23 | 32 | 34 | 30 | 29 | 24 | 24 | 22 | 0 | 21 | 21 | 18 | 33 | 41 | 27 | 21 | 24 | 24 | 29 | 26 | 21 | 33 | 33 | 33 | 33 | 42 | 66 | 81 | 82 | 101 | 101 | 102 | 81 | 115 | 71 | 83 | 71 | 64 | 50 | 47 | 47 | 62 | 65 | 66 | 62 | 70 | 70 | 63 | 71 | 74 | 75 | 69 | 69 | 69 | 54 | 54 | 54 | 59 | 94 | 90 | 104 | 104 | 109 | 93 | 90 | 90 | 90 | 100 | 100 | 107 | 105 | 89 | 89 | 58 | 58 | 109 | 109 | 109 | 94 | 110 | 110 | 83 | 83 | 83 | 83 | 110 | 110 | 118 | 117 | 117 | 117 | 117 | 117 | 117 | 123 | 117 | 126 | 126 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 110 | 101 | 90 | 90 | 90 | 90 | 90 | 92 | 92 | 91 | 91 | 71 | 71 | 71 | 71 | 71 | 71 | 65 | 65 | 65 | 65 | 60 | 60 | 60 | 60 | 72 | 72
11 | M/s MECC | Service | FDN | Manpower Details (P) | [60 empty] | 20 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Manpower Details (A) | 2025-03-02: 15; 2025-03-03: 30; 2025-03-04: 30; 2025-03-05: 30; 2025-03-06: 30; 2025-03-07: 30; 2025-03-08: 30; 2025-03-09: 30; 2025-03-10: 30; 2025-03-11: 28; 2025-03-12: 8; 2025-03-13: 8; 2025-03-14: 0; 2025-03-15: 12; 2025-03-16: 12; 2025-03-17: 13; 2025-03-18: 13; 2025-03-19: 9; 2025-03-20: 14; 2025-03-21: 9; 2025-03-22: 6; 2025-03-23: 10; 2025-03-24: 4; 2025-03-25: 6; 2025-03-26: 5; 2025-03-27: 5; 2025-03-28: 1; 2025-03-29: 2; 2025-03-30: 1; 2025-03-31: 1; 2025-04-01: 1; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0; 2025-04-11: 0; 2025-04-12: 0; 2025-04-13: 0; 2025-04-14: 0; 2025-04-15: 0; 2025-04-16: 0; 2025-04-17: 0; 2025-04-18: 0; 2025-04-19: 0; 2025-04-20: 0; 2025-04-21: 0; 2025-04-22: 0; 2025-04-23: 0; 2025-04-24: 0; 2025-04-25: 0; 2025-04-26: 0; 2025-04-27: 0; 2025-04-28: 0; 2025-04-29: 0; 2025-04-30: 0; 2025-05-01: 0; 2025-05-02: 0; 2025-05-03: 0; 2025-05-04: 0; 2025-05-05: 0; 2025-05-06: 0; 2025-05-07: 0; 2025-05-08: 0; 2025-05-09: 0; 2025-05-10: 0; 2025-05-11: 0; 2025-05-12: 0; 2025-05-13: 0; 2025-05-14: 7; 2025-05-15: 7; 2025-05-16: 0; 2025-05-17: 0; 2025-05-18: 0; 2025-05-19: 0; 2025-05-20: 0; 2025-05-21: 9; 2025-05-22: 0; 2025-05-23: 0; 2025-05-24: 0; 2025-05-25: 0; 2025-05-26: 0; 2025-05-27: 0; 2025-05-28: 0; 2025-05-29: 0; 2025-05-30: 0; 2025-05-31: 0; 2025-06-01: 0; 2025-06-02: 0; 2025-06-03: 0; 2025-06-04: 0; 2025-06-05: 0; 2025-06-06: 0; 2025-06-07: 0; 2025-06-08: 0; 2025-06-09: 0; 2025-06-10: 0; 2025-06-11: 0; 2025-06-12: 0; 2025-06-13: 0; 2025-06-14: 0; 2025-06-15: 0; 2025-06-16: 0; 2025-06-17: 0; 2025-06-18: 0; 2025-06-19: 0; 2025-06-20: 0; 2025-06-21: 0; 2025-06-22: 0; 2025-06-23: 0; 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0; 2025-08-13: 0; 2025-08-14: 0; 2025-08-15: 0; 2025-08-16: 0; 2025-08-17: 0; 2025-08-18: 0; 2025-08-19: 0; 2025-08-20: 0; 2025-08-21: 0; 2025-08-22: 0; 2025-08-23: 0; 2025-08-24: 0; 2025-08-25: 0; 2025-08-26: 0; 2025-08-27: 0; 2025-08-28: 0; 2025-08-29: 0; 2025-08-30: 0; 2025-08-31: 0; 2025-09-01: 0; 2025-09-02: 0; 2025-09-03: 0; 2025-09-04: 0; 2025-09-05: 0; 2025-09-06: 0; 2025-09-07: 0; 2025-09-08: 0; 2025-09-09: 0; 2025-09-10: 0; 2025-09-11: 0; 2025-09-12: 0; 2025-09-13: 0; 2025-09-14: 0; 2025-09-15: 0; 2025-09-16: 0; 2025-09-17: 0; 2025-09-18: 0; 2025-09-19: 0; 2025-09-20: 0; 2025-09-21: 0; 2025-09-22: 0; 2025-09-23: 0; 2025-09-24: 0; 2025-09-25: 0; 2025-09-26: 0; 2025-09-27: 0; 2025-09-28: 0; 2025-09-29: 0; 2025-09-30: 0; 2025-10-01: 0; 2025-10-02: 0; 2025-10-03: 0; 2025-10-04: 0; 2025-10-05: 0; 2025-10-06: 0; 2025-10-07: 0; 2025-10-08: 0; 2025-10-09: 0; 2025-10-10: 0; 2025-10-11: 0; 2025-10-12: 0; 2025-10-13: 0; 2025-10-14: 0; 2025-10-15: 0; 2025-10-16: 0; 2025-10-17: 0; 2025-10-18: 0; 2025-10-19: 0; 2025-10-20: 0; 2025-10-21: 0; 2025-10-22: 0; 2025-10-23: 0; 2025-10-24: 0; 2025-10-25: 0; 2025-10-26: 0; 2025-10-27: 0; 2025-10-28: 0; 2025-10-29: 0; 2025-10-30: 0; 2025-10-31: 0
12 | M/s PSB Infra | Service | FDN | Manpower Details (P) | [60 empty] | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 30 | 30 | 30 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 30 | 25 | 20 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Manpower Details (A) | 2025-03-02: 5; 2025-03-03: 10; 2025-03-04: 10; 2025-03-05: 10; 2025-03-06: 15; 2025-03-07: 25; 2025-03-08: 30; 2025-03-09: 30; 2025-03-10: 30; 2025-03-11: 30; 2025-03-12: 33; 2025-03-13: 40; 2025-03-14: 0; 2025-03-15: 40; 2025-03-16: 40; 2025-03-17: 36; 2025-03-18: 36; 2025-03-19: 36; 2025-03-20: 36; 2025-03-21: 36; 2025-03-22: 36; 2025-03-23: 36; 2025-03-24: 36; 2025-03-25: 36; 2025-03-26: 36; 2025-03-27: 35; 2025-03-28: 42; 2025-03-29: 30; 2025-03-30: 30; 2025-03-31: 30; 2025-04-01: 30; 2025-04-02: 30; 2025-04-03: 30; 2025-04-04: 30; 2025-04-05: 30; 2025-04-06: 30; 2025-04-07: 30; 2025-04-08: 30; 2025-04-09: 30; 2025-04-10: 30; 2025-04-11: 30; 2025-04-12: 30; 2025-04-13: 25; 2025-04-14: 25; 2025-04-15: 6; 2025-04-16: 6; 2025-04-17: 6; 2025-04-18: 7; 2025-04-19: 31; 2025-04-20: 6; 2025-04-21: 6; 2025-04-22: 6; 2025-04-23: 0; 2025-04-24: 0; 2025-04-25: 0; 2025-04-26: 0; 2025-04-27: 8; 2025-04-28: 8; 2025-04-29: 4; 2025-04-30: 8; 2025-05-01: 0; 2025-05-02: 0; 2025-05-03: 0; 2025-05-04: 0; 2025-05-05: 0; 2025-05-06: 0; 2025-05-07: 21; 2025-05-08: 21; 2025-05-09: 0; 2025-05-10: 0; 2025-05-11: 0; 2025-05-12: 0; 2025-05-13: 0; 2025-05-14: 0; 2025-05-15: 0; 2025-05-16: 0; 2025-05-17: 0; 2025-05-18: 6; 2025-05-19: 4; 2025-05-20: 0; 2025-05-21: 0; 2025-05-22: 5; 2025-05-23: 0; 2025-05-24: 0; 2025-05-25: 0; 2025-05-26: 0; 2025-05-27: 6; 2025-05-28: 6; 2025-05-29: 6; 2025-05-30: 7; 2025-05-31: 7; 2025-06-01: 5; 2025-06-02: 0; 2025-06-03: 3; 2025-06-04: 3; 2025-06-05: 5; 2025-06-06: 5; 2025-06-07: 5; 2025-06-08: 5; 2025-06-09: 5; 2025-06-10: 0; 2025-06-11: 0; 2025-06-12: 0; 2025-06-13: 0; 2025-06-14: 0; 2025-06-15: 0; 2025-06-16: 0; 2025-06-17: 0; 2025-06-18: 0; 2025-06-19: 0; 2025-06-20: 0; 2025-06-21: 0; 2025-06-22: 0; 2025-06-23: 0; 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 4; 2025-07-11: 4; 2025-07-12: 4; 2025-07-13: 4; 2025-07-14: 4; 2025-07-15: 4; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0; 2025-08-13: 0; 2025-08-14: 0; 2025-08-15: 0; 2025-08-16: 0; 2025-08-17: 0; 2025-08-18: 0; 2025-08-19: 0; 2025-08-20: 0; 2025-08-21: 0; 2025-08-22: 0; 2025-08-23: 0; 2025-08-24: 0; 2025-08-25: 0; 2025-08-26: 0; 2025-08-27: 0; 2025-08-28: 4; 2025-08-29: 0; 2025-08-30: 0; 2025-08-31: 0; 2025-09-01: 0; 2025-09-02: 0; 2025-09-03: 0; 2025-09-04: 0; 2025-09-05: 0; 2025-09-06: 0; 2025-09-07: 0; 2025-09-08: 0; 2025-09-09: 0; 2025-09-10: 0; 2025-09-11: 0; 2025-09-12: 0; 2025-09-13: 0; 2025-09-14: 0; 2025-09-15: 0; 2025-09-16: 0; 2025-09-17: 0; 2025-09-18: 0; 2025-09-19: 0; 2025-09-20: 0; 2025-09-21: 0; 2025-09-22: 0; 2025-09-23: 0; 2025-09-24: 0; 2025-09-25: 0; 2025-09-26: 0; 2025-09-27: 0; 2025-09-28: 0; 2025-09-29: 0; 2025-09-30: 0; 2025-10-01: 0; 2025-10-02: 0; 2025-10-03: 0; 2025-10-04: 0; 2025-10-05: 0; 2025-10-06: 0; 2025-10-07: 0; 2025-10-08: 0; 2025-10-09: 0; 2025-10-10: 0; 2025-10-11: 0; 2025-10-12: 0; 2025-10-13: 0; 2025-10-14: 0; 2025-10-15: 0; 2025-10-16: 0; 2025-10-17: 0; 2025-10-18: 0; 2025-10-19: 0; 2025-10-20: 0; 2025-10-21: 0; 2025-10-22: 0; 2025-10-23: 0; 2025-10-24: 0; 2025-10-25: 0; 2025-10-26: 0; 2025-10-27: 0; 2025-10-28: 0; 2025-10-29: 0; 2025-10-30: 0; 2025-10-31: 0
13 | M/s MK Chaudhary | Service | FDN | Manpower Details (P) | [67 empty] | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Manpower Details (A) | 2025-03-09: 41; 2025-03-10: 41; 2025-03-11: 41; 2025-03-12: 41; 2025-03-13: 41; 2025-03-14: 0; 2025-03-15: 41; 2025-03-16: 41; 2025-03-17: 41; 2025-03-18: 41; 2025-03-19: 41; 2025-03-20: 41; 2025-03-21: 41; 2025-03-22: 41; 2025-03-23: 30; 2025-03-24: 30; 2025-03-25: 30; 2025-03-26: 30; 2025-03-27: 30; 2025-03-28: 30; 2025-03-29: 30; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0; 2025-04-11: 0; 2025-04-12: 0; 2025-04-13: 0; 2025-04-14: 0; 2025-04-15: 0; 2025-04-16: 0; 2025-04-17: 0; 2025-04-18: 0; 2025-04-19: 0; 2025-04-20: 0; 2025-04-21: 0; 2025-04-22: 0; 2025-04-23: 0; 2025-04-24: 0; 2025-04-25: 0; 2025-04-26: 0; 2025-04-27: 0; 2025-04-28: 0; 2025-04-29: 0; 2025-04-30: 0; 2025-05-01: 4; 2025-05-02: 4; 2025-05-03: 0; 2025-05-04: 0; 2025-05-05: 0; 2025-05-06: 0; 2025-05-07: 0; 2025-05-08: 0; 2025-05-09: 0; 2025-05-10: 0; 2025-05-11: 0; 2025-05-12: 0; 2025-05-13: 0; 2025-05-14: 0; 2025-05-15: 0; 2025-05-16: 0; 2025-05-17: 0; 2025-05-18: 0; 2025-05-19: 0; 2025-05-20: 0; 2025-05-21: 0; 2025-05-22: 0; 2025-05-23: 0; 2025-05-24: 0; 2025-05-25: 2; 2025-05-26: 2; 2025-05-27: 0; 2025-05-28: 0; 2025-05-29: 0; 2025-05-30: 0; 2025-05-31: 0; 2025-06-01: 0; 2025-06-02: 0; 2025-06-03: 0; 2025-06-04: 0; 2025-06-05: 0; 2025-06-06: 0; 2025-06-07: 0; 2025-06-08: 0; 2025-06-09: 0; 2025-06-10: 0; 2025-06-11: 0; 2025-06-12: 0; 2025-06-13: 0; 2025-06-14: 0; 2025-06-15: 0; 2025-06-16: 0; 2025-06-17: 0; 2025-06-18: 0; 2025-06-19: 0; 2025-06-20: 0; 2025-06-21: 0; 2025-06-22: 0; 2025-06-23: 0; 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0; 2025-08-13: 0; 2025-08-14: 0; 2025-08-15: 0; 2025-08-16: 0; 2025-08-17: 0; 2025-08-18: 0; 2025-08-19: 0; 2025-08-20: 0; 2025-08-21: 0; 2025-08-22: 0; 2025-08-23: 0; 2025-08-24: 0; 2025-08-25: 0; 2025-08-26: 0; 2025-08-27: 0; 2025-08-28: 0; 2025-08-29: 0; 2025-08-30: 0; 2025-08-31: 0; 2025-09-01: 0; 2025-09-02: 0; 2025-09-03: 0; 2025-09-04: 0; 2025-09-05: 0; 2025-09-06: 0; 2025-09-07: 0; 2025-09-08: 0; 2025-09-09: 0; 2025-09-10: 0; 2025-09-11: 0; 2025-09-12: 0; 2025-09-13: 0; 2025-09-14: 0; 2025-09-15: 0; 2025-09-16: 0; 2025-09-17: 0; 2025-09-18: 0; 2025-09-19: 0; 2025-09-20: 0; 2025-09-21: 0; 2025-09-22: 0; 2025-09-23: 0; 2025-09-24: 0; 2025-09-25: 0; 2025-09-26: 0; 2025-09-27: 0; 2025-09-28: 0; 2025-09-29: 0; 2025-09-30: 0; 2025-10-01: 0; 2025-10-02: 0; 2025-10-03: 0; 2025-10-04: 0; 2025-10-05: 0; 2025-10-06: 0; 2025-10-07: 0; 2025-10-08: 0; 2025-10-09: 0; 2025-10-10: 0; 2025-10-11: 0; 2025-10-12: 0; 2025-10-13: 0; 2025-10-14: 0; 2025-10-15: 0; 2025-10-16: 0; 2025-10-17: 0; 2025-10-18: 0; 2025-10-19: 0; 2025-10-20: 0; 2025-10-21: 0; 2025-10-22: 0; 2025-10-23: 0; 2025-10-24: 0; 2025-10-25: 0; 2025-10-26: 0; 2025-10-27: 0; 2025-10-28: 0; 2025-10-29: 0; 2025-10-30: 0; 2025-10-31: 0
14 | M/s Shreeram Constructions | Service | FDN | Manpower Details (P) | [53 empty] | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 10 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 20 | 20 | 20 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
|  |  |  | Manpower Details (A) | [53 empty] | 33 | 33 | 33 | 33 | 30 | 32 | 33 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 30 | 30 | 30 | 0 | 10 | 10 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 10 | 10 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 2 | 2 | 4 | 2 | 7 | 7 | 5 | 5 | 5 | 5 | 15 | 20 | 20 | 19 | 19 | 18 | 19 | 17 | 17 | 15 | 45 | 40 | 45 | 17 | 17 | 20 | 20 | 10 | 25 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 4 | 3 | 4 | 4 | 12 | 6 | 0 | 2 | 6 | 2 | 10 | 2 | 2 | 2 | 2 | 5 | 2 | 2 | 10 | 9 | 3 | 3 | 11 | 11 | 8 | 10 | 10 | 12 | 14 | 14 | 0 | 24 | 14 | 25 | 20 | 10 | 25 | 26 | 25 | 10 | 18 | 24 | 22 | 20 | 20 | 42 | 42 | 35 | 20 | 29 | 24 | 28 | 29 | 34 | 36 | 5 | 5 | 0 | 0 | 0 | 2 | 2 | 2 | 35 | 30 | 20 | 30 | 30 | 25 | 15 | 15 | 20 | 10 | 40 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 30 | 32 | 30 | 15 | 20 | 20 | 20 | 20 | 20 | 0 | 0 | 23 | 23 | 23 | 18 | 33 | 33 | 33 | 22 | 26 | 26 | 29 | 33 | 30 | 22 | 20 | 15 |  | 28 | 28 | 28 | 28 | 17 | 35 | 10 | 43 | 42 | 42 | 24 | 23 | 35 | 35 | 22 | 32 | 22 | 32 | 32 | 23 | 24 | 30 | 20 | 30 | 21 | 21 | 21 | 32 | 32 | 32 | 22 | 24 | 24 | 26 | 26 | 31 | 23 | 34 | 34 | 34 | 22 | 22 | 39 | 40 | 37 | 42 | 23 | 23 | 31 | 31 | 31 | 38 | 39 | 39 | 34 | 34 | 34 | 34 | 42 | 42 | 46 | 44 | 44 | 44 | 44 | 44 | 44 | 34 | 44 | 44 | 44 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 35 | 39 | 37 | 37 | 36 | 36 | 36 | 36 | 36 | 41 | 41 | 32 | 32 | 32 | 32 | 32 | 32 | 30 | 30 | 30 | 27 | 26 | 26 | 26 | 35 | 35 | 30
15 | M/s Tejas | Service | FDN | Manpower Details (P) | [69 empty] | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 30 | 20 | 20 | 20 | 20 | 15 | 15 | 15 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
|  |  |  | Manpower Details (A) | 2025-03-11: 10; 2025-03-12: 13; 2025-03-13: 13; 2025-03-14: 14; 2025-03-15: 12; 2025-03-16: 12; 2025-03-17: 15; 2025-03-18: 15; 2025-03-19: 15; 2025-03-20: 14; 2025-03-21: 25; 2025-03-22: 22; 2025-03-23: 24; 2025-03-24: 23; 2025-03-25: 24; 2025-03-26: 24; 2025-03-27: 24; 2025-03-28: 35; 2025-03-29: 8; 2025-03-30: 31; 2025-03-31: 31; 2025-04-01: 31; 2025-04-02: 31; 2025-04-03: 31; 2025-04-04: 31; 2025-04-05: 31; 2025-04-06: 31; 2025-04-07: 31; 2025-04-08: 31; 2025-04-09: 31; 2025-04-10: 31; 2025-04-11: 31; 2025-04-12: 31; 2025-04-13: 31; 2025-04-14: 31; 2025-04-15: 24; 2025-04-16: 31; 2025-04-17: 23; 2025-04-18: 23; 2025-04-19: 23; 2025-04-20: 23; 2025-04-21: 23; 2025-04-22: 23; 2025-04-23: 0; 2025-04-24: 0; 2025-04-25: 0; 2025-04-26: 0; 2025-04-27: 0; 2025-04-28: 0; 2025-04-29: 0; 2025-04-30: 0; 2025-05-01: 0; 2025-05-02: 0; 2025-05-03: 0; 2025-05-04: 0; 2025-05-05: 0; 2025-05-06: 0; 2025-05-07: 0; 2025-05-08: 0; 2025-05-09: 0; 2025-05-10: 0; 2025-05-11: 0; 2025-05-12: 0; 2025-05-13: 0; 2025-05-14: 0; 2025-05-15: 0; 2025-05-16: 0; 2025-05-17: 0; 2025-05-18: 0; 2025-05-19: 0; 2025-05-20: 0; 2025-05-21: 0; 2025-05-22: 0; 2025-05-23: 0; 2025-05-24: 0; 2025-05-25: 0; 2025-05-26: 0; 2025-05-27: 0; 2025-05-28: 0; 2025-05-29: 0; 2025-05-30: 0; 2025-05-31: 0; 2025-06-01: 0; 2025-06-02: 0; 2025-06-03: 0; 2025-06-04: 0; 2025-06-05: 0; 2025-06-06: 0; 2025-06-07: 0; 2025-06-08: 0; 2025-06-09: 0; 2025-06-10: 0; 2025-06-11: 0; 2025-06-12: 0; 2025-06-13: 0; 2025-06-14: 0; 2025-06-15: 0; 2025-06-16: 0; 2025-06-17: 0; 2025-06-18: 0; 2025-06-19: 0; 2025-06-20: 0; 2025-06-21: 0; 2025-06-22: 0; 2025-06-23: 0; 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0; 2025-08-13: 0; 2025-08-14: 0; 2025-08-15: 0; 2025-08-16: 0; 2025-08-17: 0; 2025-08-18: 0; 2025-08-19: 0; 2025-08-20: 0; 2025-08-21: 0; 2025-08-22: 0; 2025-08-23: 0; 2025-08-24: 0; 2025-08-25: 0; 2025-08-26: 0; 2025-08-27: 0; 2025-08-28: 0; 2025-08-29: 0; 2025-08-30: 0; 2025-08-31: 0; 2025-09-01: 0; 2025-09-02: 0; 2025-09-03: 5; 2025-09-04: 0; 2025-09-05: 0; 2025-09-06: 0; 2025-09-07: 0; 2025-09-08: 0; 2025-09-09: 0; 2025-09-10: 0; 2025-09-11: 0; 2025-09-12: 0; 2025-09-13: 0; 2025-09-14: 0; 2025-09-15: 0; 2025-09-16: 0; 2025-09-17: 0; 2025-09-18: 0; 2025-09-19: 0; 2025-09-20: 0; 2025-09-21: 0; 2025-09-22: 0; 2025-09-23: 0; 2025-09-24: 0; 2025-09-25: 0; 2025-09-26: 0; 2025-09-27: 0; 2025-09-28: 0; 2025-09-29: 0; 2025-09-30: 0; 2025-10-01: 0; 2025-10-02: 0; 2025-10-03: 0; 2025-10-04: 0; 2025-10-05: 0; 2025-10-06: 0; 2025-10-07: 0; 2025-10-08: 0; 2025-10-09: 0; 2025-10-10: 0; 2025-10-11: 0; 2025-10-12: 0; 2025-10-13: 0; 2025-10-14: 0; 2025-10-15: 0; 2025-10-16: 0; 2025-10-17: 0; 2025-10-18: 0; 2025-10-19: 0; 2025-10-20: 0; 2025-10-21: 0; 2025-10-22: 0; 2025-10-23: 0; 2025-10-24: 0; 2025-10-25: 0; 2025-10-26: 0; 2025-10-27: 0; 2025-10-28: 0; 2025-10-29: 0; 2025-10-30: 0; 2025-10-31: 0
16 | M/s Bhawani Construction | Service | FDN | Manpower Details (P) | [96 empty] | 10 | 10 | 10 | 10 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 40 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
|  |  |  | Manpower Details (A) | [96 empty] | 2 | 2 | 2 | 2 | 19 | 19 | 21 | 20 | 21 | 15 | 11 | 14 | 0 | 14 | 13 | 40 | 41 | 42 | 41 | 41 | 36 | 39 | 43 | 42 | 42 | 40 | 55 | 30 | 34 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 29 | 27 | 0 | 11 | 26 | 26 | 35 | 27 | 23 | 23 | 28 | 20 | 22 | 28 | 33 | 34 | 41 | 26 | 24 | 29 | 29 | 21 | 25 | 24 | 25 | 25 | 25 | 21 | 0 | 26 | 0 | 13 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 22 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 18 | 20 | 21 | 21 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 20 | 20 | 20 | 20 | 11 | 14 | 4 | 0 | 0 | 22 | 22 | 12 | 6 | 0 | 8 | 7 | 7 | 23 | 5 | 5 | 16 | 11 | 10 | 10 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 2 | 2 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 3 | 94 | 0 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 0 | 45 | 45 | 45 | 61 | 0 | 69 | 79 | 66 | 71 | 71 | 65 | 26 | 26 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 0 | 6 | 30 | 0 | 72 | 8 | 42 |  | 49 | 42 | 42 | 66 | 70 | 67 | 69 | 8 | 16 | 28 | 25 | 62 | 57 | 55 | 62 | 62 | 47 | 71 | 71 | 71 | 53 | 32 | 48 | 43 | 43 | 68 | 53 | 73 | 29 | 29 | 22 | 22 | 22 | 52 | 52 | 52 | 22 | 21 | 22 | 59 | 59 | 67 | 20 | 26 | 26 | 26 | 29 | 29 | 29 | 10 | 10 | 39 | 33 | 33 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 29 | 29 | 62 | 29 | 29 | 29 | 29 | 29 | 29 | 12 | 29 | 38 | 38 | [16 empty] | 45 | 23 | 23 | 23 | 23 | 23 | 23 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 25 | 30 | 30 | 30 | 32 | 32 | 46
17 | M/s ShreeJi Constructions | Service | FDN | Manpower Details (P) | [106 empty] | 35 | 35 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 50 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
|  |  |  | Manpower Details (A) | [106 empty] | 25 | 25 | 40 | 35 | 40 | 42 | 44 | 40 | 44 | 44 | 55 | 60 | 60 | 60 | 60 | 65 | 60 | 45 | 25 | 30 | 20 | 16 | 0 | 2 |  | 17 | 10 | 10 | 10 | 34 | 33 | 37 | 36 | 38 | 38 | 37 | 37 | 42 | 19 | 27 | 18 | 25 | 25 | 10 | 15 | 32 | 32 | 39 | 33 | 38 | 46 | 48 | 30 | 30 | 26 | 26 | 25 | 21 | 26 | 8 | 12 | 0 | 0 | 0 | 16 | 22 | 33 | 29 | 29 | 32 | 32 | 0 | 0 | 7 | 11 | 38 | 33 | 43 | 47 | 40 | 39 | 35 | 35 | 36 | 33 | 33 | 33 | 31 | 27 | 27 | 0 | 36 | 32 | 33 | 29 | 27 | 25 | 38 | 27 | 32 | 24 | 20 | 37 | 30 | 39 | 47 | 37 | 45 | 42 | 45 | 54 | 32 | 34 | 55 | 38 | 38 | 53 | 30 | 51 | 49 | 41 | 22 | 39 | 46 | 38 | 45 | 45 | 7 | 24 | 3 | 0 | 42 | 39 | 48 | 48 | 37 | 37 | 41 | 42 | 40 | 44 | 40 | 39 | 10 | 5 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 45 | 39 | 57 | 50 | 50 | 67 | 71 | 67 | 47 | 47 | 47 | 0 | 53 | 54 | 53 | 56 | 36 | 41 | 41 | 44 | 73 | 73 | 94 | 88 | 53 | 61 | 69 | 76 | 69 | 81 | 56 | 99 | 113 | 104 | 65 | 92 | 80 | 77 | 66 | 66 | 78 | 86 | 86 | 86 | 66 | 73 | 74 | 48 | 79 | 63 | 55 | 48 | 53 | 66 | 66 | 66 | 66 | 80 | 80 | 80 | 86 | 70 | 72 | 81 | 81 | 52 | 57 | 71 | 71 | 71 | 58 | 58 | 59 | 60 | 61 | 44 | 58 | 58 | 53 | 53 | 53 | 39 | 39 | 39 | 32 | 32 | 32 | 32 | 27 | 53 | 53 | 40 | 40 | 40 | 40 | 40 | 40 | 74 | 40 | 39 | 39 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 44 | 26 | 26 | 22 | 22 | 22 | 22 | 22 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 20 | 20 | 20 | 26 | 20 | 20 | 20 | 29 | 29 | 27
18 | M/s CEIPL | Service | FDN | Manpower Details (P) | [110 empty] | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 30 | 30 | 30 | 30 | 30 | 30 | 25 | 25 | 25 | 25 | 25 | 25 | 15 | 15 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
|  |  |  | Manpower Details (A) | 2025-04-21: 18; 2025-04-22: 18; 2025-04-23: 26; 2025-04-24: 21; 2025-04-25: 26; 2025-04-26: 26; 2025-04-27: 47; 2025-04-28: 49; 2025-04-29: 28; 2025-04-30: 47; 2025-05-01: 47; 2025-05-02: 70; 2025-05-03: 70; 2025-05-04: 65; 2025-05-05: 65; 2025-05-06: 65; 2025-05-07: 65; 2025-05-08: 65; 2025-05-09: 65; 2025-05-10: 65; 2025-05-11: 65; 2025-05-12: 65; 2025-05-13: 65; 2025-05-14: 65; 2025-05-15: 65; 2025-05-16: 28; 2025-05-17: 28; 2025-05-18: 22; 2025-05-19: 27; 2025-05-20: 23; 2025-05-21: 23; 2025-05-22: 24; 2025-05-23: 24; 2025-05-24: 26; 2025-05-25: 26; 2025-05-26: 29; 2025-05-27: 21; 2025-05-28: 25; 2025-05-29: 25; 2025-05-30: 22; 2025-05-31: 22; 2025-06-01: 22; 2025-06-02: 31; 2025-06-03: 30; 2025-06-04: 25; 2025-06-05: 25; 2025-06-06: 25; 2025-06-07: 25; 2025-06-08: 25; 2025-06-09: 25; 2025-06-10: 22; 2025-06-11: 26; 2025-06-12: 26; 2025-06-13: 26; 2025-06-14: 15; 2025-06-15: 13; 2025-06-16: 11; 2025-06-17: 18; 2025-06-18: 22; 2025-06-19: 25; 2025-06-20: 30; 2025-06-21: 34; 2025-06-22: 34; 2025-06-23: 24; 2025-06-24: 24; 2025-06-25: 25; 2025-06-26: 25; 2025-06-27: 23; 2025-06-28: 23; 2025-06-29: 23; 2025-06-30: 23; 2025-07-01: 23; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0; 2025-08-13: 0; 2025-08-14: 0; 2025-08-15: 0; 2025-08-16: 0; 2025-08-17: 0; 2025-08-18: 0; 2025-08-19: 0; 2025-08-20: 0; 2025-08-21: 0; 2025-08-22: 0; 2025-08-23: 0; 2025-08-24: 0; 2025-08-25: 0; 2025-08-26: 0; 2025-08-27: 0; 2025-08-28: 0; 2025-08-29: 0; 2025-08-30: 0; 2025-08-31: 0; 2025-09-01: 0; 2025-09-02: 0; 2025-09-03: 0; 2025-09-04: 0; 2025-09-05: 0; 2025-09-06: 0; 2025-09-07: 0; 2025-09-08: 0; 2025-09-09: 0; 2025-09-10: 0; 2025-09-11: 0; 2025-09-12: 0; 2025-09-13: 0; 2025-09-14: 0; 2025-09-15: 0; 2025-09-16: 0; 2025-09-17: 0; 2025-09-18: 0; 2025-09-19: 0; 2025-09-20: 0; 2025-09-21: 0; 2025-09-22: 0; 2025-09-23: 0; 2025-09-24: 0; 2025-09-25: 0; 2025-09-26: 0; 2025-09-27: 0; 2025-09-28: 0; 2025-09-29: 0; 2025-09-30: 0; 2025-10-01: 0; 2025-10-02: 0; 2025-10-03: 0; 2025-10-04: 0; 2025-10-05: 0; 2025-10-06: 0; 2025-10-07: 0; 2025-10-08: 0; 2025-10-09: 0; 2025-10-10: 0; 2025-10-11: 0; 2025-10-12: 0; 2025-10-13: 0; 2025-10-14: 0; 2025-10-15: 0; 2025-10-16: 0; 2025-10-17: 0; 2025-10-18: 0; 2025-10-19: 0; 2025-10-20: 0; 2025-10-21: 0; 2025-10-22: 0; 2025-10-23: 0; 2025-10-24: 0; 2025-10-25: 0; 2025-10-26: 0; 2025-10-27: 0; 2025-10-28: 0; 2025-10-29: 0; 2025-10-30: 0; 2025-10-31: 0
19 | M/s HBG | Service | FDN | Manpower Details (P) | [124 empty] | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  |  |  | Manpower Details (A) | [124 empty] | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 3 | 12 | 13 | 13 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 17 | 17 | 19 | 19 | 19 | 18 | 15 | 2 | 15 | 15 | 15 | 15 | 15 | 14 | 15 | 15 | 16 | 15 | 13 | 13 | 14 | 15 | 18 | 0 | 2 | 2 | 2 | 2 | 17 | 17 | 17 | 15 | 15 | 6 | 4 | 4 | 4 | 4 | 5 | 3 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 4 | 2 | 2 | 0 | 2 | 0 | 4 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 0 | 0 | 3 | 3 | 3 | 6 | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 14 | 19 | 3 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 6 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 13 | 13 | 20 | 17 | 20 | 12 | 21 | 24 | 24 | 20 | 20 | 17 | 0 | 30 | 15 | 20 | 20 | 5 | 8 | 6 | 13 | 16 | 15 | 19 | 19 | 19 | 2 | 2 | 15 | 31 | 30 | 28 | 25 | 28 | 24 | 38 | 24 | 6 | 16 | 14 | 14 | 14 | 7 | 12 | 12 | 20 | 11 | 20 | 4 | 0 | 11 | 14 | 15 | 14 | 13 | 18 | 18 | 18 | 13 | 13 | 13 | 20 | 20 | 20 | 19 | 19 | 17 | 17 | 9 | 9 | 9 | 14 | 14 | 6 | 6 | 6 | 6 | 3 | 3 | 9 | 9 | 9 | 43 | 54 | 54 | 44 | 44 | 44 | 44 | 12 | 12 | 16 | 38 | 38 | 38 | 38 | 38 | 38 | 6 | 38 | 16 | 16 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 30 | 37 | 37 | 39 | 39 | 39 | 39 | 39 | 34 | 34 | 39 | 39 | 39 | 39 | 39 | 39 | 40 | 40 | 40 | 33 | 39 | 39 | 39 | 29 | 29 | 46
20 | M/s Odhav | Service | FDN | Manpower Details (P) | [124 empty] | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110
|  |  |  | Manpower Details (A) | [124 empty] | 30 | 30 | 35 | 35 | 5 | 0 | 0 | 0 | 6 | 6 | 6 | 21 | 21 | 21 | 21 | 21 | 20 | 20 | 20 | 20 | 20 | 20 | 18 | 18 | 18 | 16 | 31 | 18 | 18 | 24 | 24 | 19 | 20 | 18 | 20 | 20 | 17 | 19 | 17 | 20 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 5 | 25 | 25 | 20 | 25 | 25 | 25 | 12 | 12 | 6 | 6 | 6 | 2 | 6 | 6 | 25 | 20 | 20 | 25 | 0 | 20 | 20 | 17 | 24 | 23 | 16 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 22 | 19 | 20 | 20 | 21 | 16 | 20 | 20 | 20 | 20 | 20 | 20 | 12 | 7 | 7 | 5 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 20 | 14 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 26 | 0 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 0 | 21 | 21 | 21 | 20 | 20 | 20 | 25 | 25 | 25 | 35 | 30 | 30 | 30 | 30 | 25 | 24 | 15 | 15 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 15 | 15 | 32 | 32 | 37 | 32 | 32 | 39 | 41 | 41 | 39 | 41 | 31 | 35 | 35 | 31 | 22 | 22 | 22 | 18 | 18 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 22 | 22 | 22 | 41 | 41 | 41 | 41 | 41 | 41 | 36 | 36 | 45 | 36 | 36 | 36 | 36 | 36 | 36 | 31 | 38 | 37 | 68 | 81 | 81 | 81 | 81 | 81 | 41 | 35 | 35 | 35 | 35 | 35 | 35 | 41 | 41 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 94 | 44 | 101 | 101 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 103 | 103 | 103 | 103 | 103 | 103 | 100 | 100 | 100 | 47 | 50 | 50 | 50 | 47 | 47 | 39
21 | M/s SVRE | Service | FDN | Manpower Details (P) | [48 empty] | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
|  |  |  | Manpower Details (A) | [48 empty] | 20 | 20 | 20 | 20 | 22 | 18 | 18 | 18 | 18 | 22 | 20 | 18 | 16 | 16 | 16 | 20 | 20 | 25 | 28 | 31 | 31 | 20 | 30 | 20 | 22 | 20 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 20 | 20 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 6 | 0 | 0 | 10 | 10 | 0 | 0 | 8 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 3 | 0 | 0 | 0 | 3 | 27 | 21 | 17 | 16 | 16 | 16 | 16 | 3 | 15 | 15 | 17 | 18 | 15 | 16 | 16 | 16 | 16 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 25 | 35 | 25 | 28 | 15 | 13 | 29 | 25 | 13 | 8 | 8 | 10 | 6 | 2 | 2 | 2 | 10 | 13 | 6 | 13 | 0 | 0 | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 7 | 2
22 | M/s BIPL | Service | FDN | Manpower Details (P) | 2025-06-07: 30; 2025-06-08: 30; 2025-06-09: 30; 2025-06-10: 30; 2025-06-11: 30; 2025-06-12: 30; 2025-06-13: 30; 2025-06-14: 30; 2025-06-15: 30; 2025-06-16: 30; 2025-06-17: 30; 2025-06-18: 30; 2025-06-19: 30; 2025-06-20: 30; 2025-06-21: 30; 2025-06-22: 30; 2025-06-23: 30; 2025-06-24: 30; 2025-06-25: 30; 2025-06-26: 30; 2025-06-27: 30; 2025-06-28: 30; 2025-06-29: 30; 2025-06-30: 30; 2025-08-24: 25; 2025-08-25: 25; 2025-08-26: 25; 2025-08-27: 25; 2025-08-28: 25; 2025-08-29: 25; 2025-08-30: 25; 2025-08-31: 25; 2025-09-01: 25; 2025-09-02: 25; 2025-09-03: 25; 2025-09-04: 25; 2025-09-05: 25; 2025-09-06: 25; 2025-09-07: 25; 2025-09-08: 25; 2025-09-09: 25; 2025-09-10: 25; 2025-09-11: 25; 2025-09-12: 25; 2025-09-13: 25; 2025-09-14: 25; 2025-09-15: 25; 2025-09-16: 25; 2025-09-17: 25; 2025-09-18: 25; 2025-09-19: 25; 2025-09-20: 25; 2025-09-21: 25; 2025-09-22: 25; 2025-09-23: 25; 2025-09-24: 25; 2025-09-25: 25; 2025-09-26: 25; 2025-09-27: 25; 2025-09-28: 25; 2025-09-29: 25; 2025-09-30: 25; 2025-10-01: 25; 2025-10-02: 25; 2025-10-03: 25; 2025-10-04: 25; 2025-10-05: 25; 2025-10-06: 25; 2025-10-07: 25; 2025-10-08: 25; 2025-10-09: 25; 2025-10-10: 25; 2025-10-11: 25; 2025-10-12: 25; 2025-10-13: 25; 2025-10-14: 25; 2025-10-15: 25; 2025-10-16: 25; 2025-10-17: 25; 2025-10-18: 25; 2025-10-19: 25; 2025-10-20: 25; 2025-10-21: 25; 2025-10-22: 25; 2025-10-23: 25; 2025-10-24: 25; 2025-10-25: 25; 2025-10-26: 25; 2025-10-27: 25; 2025-10-28: 25; 2025-10-29: 25; 2025-10-30: 25; 2025-10-31: 25; 2025-11-01: 25; 2025-11-02: 25; 2025-11-03: 25; 2025-11-04: 25; 2025-11-05: 25; 2025-11-06: 25; 2025-11-07: 25; 2025-11-08: 25; 2025-11-09: 25; 2025-11-10: 25; 2025-11-11: 25; 2025-11-12: 25; 2025-11-13: 25; 2025-11-14: 25; 2025-11-15: 25; 2025-11-16: 25; 2025-11-17: 25; 2025-11-18: 25; 2025-11-19: 25; 2025-11-20: 25; 2025-11-21: 25; 2025-11-22: 25; 2025-11-23: 25; 2025-11-24: 25; 2025-11-25: 25; 2025-11-26: 25; 2025-11-27: 25; 2025-11-28: 25; 2025-11-29: 25; 2025-11-30: 25; 2025-12-01: 25; 2025-12-02: 25; 2025-12-03: 25; 2025-12-04: 25; 2025-12-05: 25; 2025-12-06: 25; 2025-12-07: 25; 2025-12-08: 25; 2025-12-09: 25; 2025-12-10: 25; 2025-12-11: 25; 2025-12-12: 25; 2025-12-13: 25; 2025-12-14: 25; 2025-12-15: 25; 2025-12-16: 25; 2025-12-17: 25; 2025-12-18: 25; 2025-12-19: 25; 2025-12-20: 25; 2025-12-21: 25; 2025-12-22: 25; 2025-12-23: 25; 2025-12-24: 25; 2025-12-25: 25; 2025-12-26: 25; 2025-12-27: 25; 2025-12-28: 25; 2025-12-29: 25; 2025-12-30: 25; 2025-12-31: 25; 2026-01-01: 25; 2026-01-02: 25; 2026-01-03: 25; 2026-01-04: 25; 2026-01-05: 25; 2026-01-06: 25; 2026-01-07: 25; 2026-01-08: 25; 2026-01-09: 25; 2026-01-10: 25; 2026-01-11: 25; 2026-01-12: 25; 2026-01-13: 25; 2026-01-14: 25; 2026-01-15: 25; 2026-01-16: 25; 2026-01-17: 25; 2026-01-18: 25; 2026-01-19: 25; 2026-01-20: 25; 2026-01-21: 25; 2026-01-22: 25; 2026-01-23: 25; 2026-01-24: 25; 2026-01-25: 25; 2026-01-26: 25; 2026-01-27: 25; 2026-01-28: 25; 2026-01-29: 25; 2026-01-30: 25; 2026-01-31: 25; 2026-02-01: 25; 2026-02-02: 25; 2026-02-03: 25; 2026-02-04: 25; 2026-02-05: 25; 2026-02-06: 25; 2026-02-07: 25; 2026-02-08: 25; 2026-02-09: 25; 2026-02-10: 25; 2026-02-11: 25; 2026-02-12: 25; 2026-02-13: 25; 2026-02-14: 25; 2026-02-15: 25; 2026-02-16: 25; 2026-02-17: 25; 2026-02-18: 25; 2026-02-19: 25; 2026-02-20: 25; 2026-02-21: 25; 2026-02-22: 25; 2026-02-23: 25; 2026-02-24: 25; 2026-02-25: 25; 2026-02-26: 25; 2026-02-27: 25
|  |  |  | Manpower Details (A) | 2025-06-07: 24; 2025-06-08: 24; 2025-06-09: 24; 2025-06-10: 2; 2025-06-11: 2; 2025-06-12: 16; 2025-06-13: 3; 2025-06-14: 3; 2025-06-15: 3; 2025-06-16: 3; 2025-06-17: 0; 2025-06-18: 0; 2025-06-19: 0; 2025-06-20: 0; 2025-06-21: 0; 2025-06-22: 0; 2025-06-23: 0; 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-08-24: 15; 2025-08-25: 15; 2025-08-26: 14; 2025-08-27: 15; 2025-08-28: 10; 2025-08-29: 15; 2025-08-30: 14; 2025-08-31: 15; 2025-09-01: 12; 2025-09-02: 12; 2025-09-03: 15; 2025-09-04: 15; 2025-09-05: 17; 2025-09-06: 20; 2025-09-07: 0; 2025-09-08: 0; 2025-09-09: 0; 2025-09-10: 0; 2025-09-11: 0; 2025-09-12: 2; 2025-09-13: 2; 2025-09-14: 2; 2025-09-15: 2; 2025-09-16: 2; 2025-09-17: 2; 2025-09-18: 2; 2025-09-19: 2; 2025-09-20: 2; 2025-09-21: 2; 2025-09-22: 2; 2025-09-23: 0; 2025-09-24: 27; 2025-09-25: 27; 2025-09-26: 0; 2025-09-27: 29; 2025-09-28: 29; 2025-09-29: 29; 2025-09-30: 29; 2025-10-01: 29; 2025-10-02: 29; 2025-10-03: 29; 2025-10-04: 0; 2025-10-05: 0; 2025-10-06: 27; 2025-10-07: 27; 2025-10-08: 0; 2025-10-09: 5; 2025-10-10: 13; 2025-10-11: 12; 2025-10-12: 10; 2025-10-13: 10; 2025-10-14: 32; 2025-10-15: 32; 2025-10-16: 26; 2025-10-17: 20; 2025-10-18: 20; 2025-10-19: 23; 2025-10-20: 26; 2025-10-21: 26; 2025-10-22: 40; 2025-10-23: 38; 2025-10-24: 24; 2025-10-25: 24; 2025-10-26: 24; 2025-10-27: 19; 2025-10-28: 17; 2025-10-29: 22; 2025-10-30: 17; 2025-10-31: 20; 2025-11-01: 16; 2025-11-02: 17; 2025-11-03: 15; 2025-11-04: 18; 2025-11-05: 15; 2025-11-06: 15; 2025-11-07: 16; 2025-11-08: 19; 2025-11-09: 19; 2025-11-10: 16; 2025-11-11: 16; 2025-11-29: 8; 2025-11-30: 6; 2025-12-01: 6; 2025-12-02: 4; 2025-12-03: 4; 2025-12-04: 4; 2025-12-05: 4; 2025-12-06: 4; 2025-12-07: 4; 2025-12-08: 4; 2025-12-18: 7; 2025-12-19: 7; 2025-12-20: 7; 2025-12-21: 7; 2025-12-22: 7; 2026-01-07: 10; 2026-01-08: 10; 2026-01-09: 10; 2026-01-10: 10; 2026-01-11: 10; 2026-01-12: 10; 2026-01-13: 10; 2026-01-14: 10; 2026-01-15: 10; 2026-01-16: 51; 2026-01-17: 22; 2026-01-18: 21; 2026-01-19: 21; 2026-01-20: 21; 2026-01-21: 21; 2026-01-22: 21; 2026-01-23: 21; 2026-01-24: 21; 2026-01-25: 21; 2026-01-26: 21; 2026-01-27: 21; 2026-01-28: 21; 2026-01-29: 21; 2026-01-30: 21; 2026-01-31: 21; 2026-02-01: 8; 2026-02-02: 8; 2026-02-03: 8; 2026-02-04: 8; 2026-02-05: 8; 2026-02-06: 8; 2026-02-07: 8; 2026-02-08: 8; 2026-02-09: 8; 2026-02-10: 54; 2026-02-11: 54; 2026-02-12: 15; 2026-02-13: 15; 2026-02-14: 15; 2026-02-15: 15; 2026-02-16: 15; 2026-02-17: 15; 2026-02-18: 16; 2026-02-19: 16; 2026-02-20: 16; 2026-02-21: 7; 2026-02-22: 9; 2026-02-23: 9; 2026-02-24: 9; 2026-02-25: 8; 2026-02-26: 8; 2026-02-27: 8
23 | M/s BPS | Service | FDN | Manpower Details (P) | 2025-06-07: 30; 2025-06-08: 30; 2025-06-09: 30; 2025-06-10: 30; 2025-06-11: 30; 2025-06-12: 30; 2025-06-13: 30; 2025-06-14: 30; 2025-06-15: 30; 2025-06-16: 30; 2025-06-17: 30; 2025-06-18: 30; 2025-06-19: 30; 2025-06-20: 30; 2025-06-21: 30; 2025-06-22: 30; 2025-06-23: 30; 2025-06-24: 30; 2025-06-25: 30; 2025-06-26: 30; 2025-06-27: 30; 2025-06-28: 30; 2025-06-29: 30; 2025-06-30: 30; 2025-07-01: 30; 2025-07-02: 30; 2025-07-03: 30; 2025-07-04: 30; 2025-07-05: 30; 2025-07-06: 30; 2025-07-07: 30; 2025-07-08: 30; 2025-07-09: 30; 2025-07-10: 30; 2025-07-11: 30; 2025-07-12: 30; 2025-07-13: 30; 2025-07-14: 30; 2025-07-15: 30; 2025-07-16: 30; 2025-07-17: 30; 2025-07-18: 30; 2025-07-19: 30; 2025-07-20: 30; 2025-07-21: 30; 2025-07-22: 30; 2025-07-23: 30; 2025-07-24: 30; 2025-07-25: 30; 2025-07-26: 30; 2025-07-27: 30; 2025-07-28: 30; 2025-07-29: 30; 2025-07-30: 30; 2025-07-31: 30; 2025-08-01: 30; 2025-08-02: 30; 2025-08-03: 30; 2025-08-04: 30; 2025-08-05: 30; 2025-08-06: 30; 2025-08-07: 30; 2025-08-08: 30; 2025-08-09: 30; 2025-08-10: 30; 2025-08-11: 30; 2025-08-12: 30; 2025-08-13: 30; 2025-08-14: 30; 2025-08-15: 30; 2025-08-16: 30; 2025-08-17: 30; 2025-08-18: 30; 2025-08-19: 30; 2025-08-20: 30; 2025-08-21: 30; 2025-08-22: 30; 2025-08-23: 30; 2025-08-24: 30; 2025-08-25: 30; 2025-08-26: 30; 2025-08-27: 30; 2025-08-28: 30; 2025-08-29: 30; 2025-08-30: 30; 2025-08-31: 30; 2025-09-01: 30; 2025-09-02: 30; 2025-09-03: 30; 2025-09-04: 30; 2025-09-05: 30; 2025-09-06: 30; 2025-09-07: 30; 2025-09-08: 30; 2025-09-09: 30; 2025-09-10: 30; 2025-09-11: 30; 2025-09-12: 30; 2025-09-13: 30; 2025-09-14: 30; 2025-09-15: 30; 2025-09-16: 30; 2025-09-17: 30; 2025-09-18: 30; 2025-09-19: 30; 2025-09-20: 30; 2025-09-21: 30; 2025-09-22: 30; 2025-09-23: 30; 2025-09-24: 30; 2025-09-25: 30
|  |  |  | Manpower Details (A) | 2025-06-07: 24; 2025-06-08: 24; 2025-06-09: 24; 2025-06-10: 2; 2025-06-11: 2; 2025-06-12: 16; 2025-06-13: 3; 2025-06-14: 3; 2025-06-15: 3; 2025-06-16: 3; 2025-06-17: 0; 2025-06-18: 0; 2025-06-19: 0; 2025-06-20: 0; 2025-06-21: 0; 2025-06-22: 0; 2025-06-23: 0; 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 35; 2025-07-06: 35; 2025-07-07: 30; 2025-07-08: 20; 2025-07-09: 15; 2025-07-10: 15; 2025-07-11: 12; 2025-07-12: 7; 2025-07-13: 13; 2025-07-14: 13; 2025-07-15: 26; 2025-07-16: 26; 2025-07-17: 26; 2025-07-18: 29; 2025-07-19: 27; 2025-07-20: 24; 2025-07-21: 0; 2025-07-22: 18; 2025-07-23: 18; 2025-07-24: 20; 2025-07-25: 18; 2025-07-26: 17; 2025-07-27: 12; 2025-07-28: 20; 2025-07-29: 20; 2025-07-30: 24; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 19; 2025-08-03: 17; 2025-08-04: 19; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 24; 2025-08-10: 28; 2025-08-11: 13; 2025-08-12: 8; 2025-08-13: 2; 2025-08-14: 2; 2025-08-15: 0; 2025-08-16: 0; 2025-08-17: 2; 2025-08-18: 2; 2025-08-19: 7; 2025-08-20: 0; 2025-08-21: 4; 2025-08-22: 0; 2025-08-23: 0; 2025-08-24: 0; 2025-08-25: 0; 2025-08-26: 0; 2025-08-27: 0; 2025-08-28: 0; 2025-08-29: 0; 2025-08-30: 1; 2025-08-31: 2; 2025-09-01: 0; 2025-09-02: 0; 2025-09-03: 0; 2025-09-04: 0; 2025-09-05: 0; 2025-09-06: 0; 2025-09-07: 0; 2025-09-08: 0; 2025-09-09: 0; 2025-09-10: 0; 2025-09-11: 0; 2025-09-12: 2; 2025-09-13: 2; 2025-09-14: 2; 2025-09-15: 2; 2025-09-16: 2; 2025-09-17: 2; 2025-09-18: 2; 2025-09-19: 2; 2025-09-20: 2; 2025-09-21: 2; 2025-09-22: 2; 2025-09-23: 0; 2025-09-24: 0; 2025-09-25: 7; 2025-09-26: 0; 2025-09-27: 0; 2025-09-28: 0; 2025-09-29: 0; 2025-09-30: 0; 2025-10-01: 0; 2025-10-02: 0; 2025-10-03: 0; 2025-10-04: 0; 2025-10-05: 0; 2025-10-06: 0; 2025-10-07: 0; 2025-10-08: 0; 2025-10-09: 0; 2025-10-10: 0; 2025-10-11: 0; 2025-10-12: 0; 2025-10-13: 0; 2025-10-14: 0; 2025-10-15: 0; 2025-10-16: 0; 2025-10-17: 0; 2025-10-18: 0; 2025-10-19: 0; 2025-10-20: 0; 2025-10-21: 0; 2025-10-22: 0; 2025-10-23: 0; 2025-10-24: 0; 2025-10-25: 0; 2025-10-26: 0; 2025-10-27: 0; 2025-10-28: 0; 2025-10-29: 0; 2025-10-30: 0; 2025-10-31: 0
24 | (Civil) Departmental Manpower | Service | Foundation | Manpower Details (P) | 2025-11-05: 30; 2025-11-06: 30; 2025-11-07: 30; 2025-11-08: 30; 2025-11-09: 30; 2025-11-10: 60; 2025-11-11: 60; 2025-11-12: 60; 2025-11-13: 60; 2025-11-14: 60; 2025-11-15: 60; 2025-11-16: 60; 2025-11-17: 60; 2025-11-18: 60; 2025-11-19: 60; 2025-11-20: 60; 2025-11-21: 60; 2025-11-22: 60; 2025-11-23: 60; 2025-11-24: 60; 2025-11-25: 60; 2025-11-26: 60; 2025-11-27: 60; 2025-11-28: 60; 2025-11-29: 60; 2025-11-30: 60; 2025-12-01: 60; 2025-12-02: 60; 2025-12-03: 60; 2025-12-04: 60; 2025-12-05: 60; 2025-12-06: 60; 2025-12-07: 60; 2025-12-08: 60; 2025-12-09: 60; 2025-12-10: 60; 2025-12-11: 60; 2025-12-12: 60; 2025-12-13: 60; 2025-12-14: 60; 2025-12-15: 60; 2025-12-16: 60; 2025-12-17: 60; 2025-12-18: 60; 2025-12-19: 60; 2025-12-20: 60; 2025-12-21: 60; 2025-12-22: 60; 2025-12-23: 60; 2025-12-24: 60; 2025-12-25: 60; 2025-12-26: 60; 2025-12-27: 60; 2025-12-28: 60; 2025-12-29: 60; 2025-12-30: 90; 2025-12-31: 90; 2026-01-01: 90; 2026-01-02: 90; 2026-01-03: 90; 2026-01-04: 90; 2026-01-05: 90; 2026-01-06: 90; 2026-01-07: 90; 2026-01-08: 90; 2026-01-09: 90; 2026-01-10: 90; 2026-01-11: 90; 2026-01-12: 90; 2026-01-13: 90; 2026-01-14: 90; 2026-01-15: 90; 2026-01-16: 90; 2026-01-17: 90; 2026-01-18: 90; 2026-01-19: 90; 2026-01-20: 90; 2026-01-21: 90; 2026-01-22: 90; 2026-01-23: 90; 2026-01-24: 90; 2026-01-25: 90; 2026-01-26: 90; 2026-01-27: 90; 2026-01-28: 90; 2026-01-29: 90; 2026-01-30: 90; 2026-01-31: 90; 2026-02-01: 90; 2026-02-02: 90; 2026-02-03: 90; 2026-02-04: 90; 2026-02-05: 90; 2026-02-06: 90; 2026-02-07: 90; 2026-02-08: 90; 2026-02-09: 90; 2026-02-10: 90; 2026-02-11: 90; 2026-02-12: 90; 2026-02-13: 90; 2026-02-14: 90; 2026-02-15: 90; 2026-02-16: 90; 2026-02-17: 90; 2026-02-18: 90; 2026-02-19: 90; 2026-02-20: 90; 2026-02-21: 90; 2026-02-22: 90; 2026-02-23: 90; 2026-02-24: 90; 2026-02-25: 90; 2026-02-26: 90; 2026-02-27: 90
|  |  |  | Manpower Details (A) | 2025-11-05: 24; 2025-11-06: 24; 2025-11-07: 37; 2025-11-08: 37; 2025-11-09: 37; 2025-11-10: 56; 2025-11-11: 68; 2025-11-12: 42; 2025-11-13: 64; 2025-11-14: 64; 2025-11-15: 64; 2025-11-16: 64; 2025-11-17: 68; 2025-11-18: 77; 2025-11-19: 65; 2025-11-20: 65; 2025-11-21: 65; 2025-11-22: 65; 2025-11-23: 65; 2025-11-24: 67; 2025-11-25: 75; 2025-11-26: 69; 2025-11-27: 66; 2025-11-28: 66; 2025-11-29: 66; 2025-11-30: 66; 2025-12-01: 66; 2025-12-02: 48; 2025-12-03: 62; 2025-12-04: 53; 2025-12-05: 58; 2025-12-06: 64; 2025-12-07: 52; 2025-12-08: 61; 2025-12-09: 52; 2025-12-10: 60; 2025-12-11: 77; 2025-12-12: 54; 2025-12-13: 71; 2025-12-14: 74; 2025-12-15: 71; 2025-12-16: 71; 2025-12-17: 69; 2025-12-18: 72; 2025-12-19: 70; 2025-12-20: 70; 2025-12-21: 70; 2025-12-22: 79; 2025-12-23: 79; 2025-12-24: 79; 2025-12-25: 82; 2025-12-26: 79; 2025-12-27: 79; 2025-12-28: 79; 2025-12-29: 79; 2025-12-30: 88; 2025-12-31: 88; 2026-01-01: 77; 2026-01-02: 88; 2026-01-03: 77; 2026-01-04: 77; 2026-01-05: 89; 2026-01-06: 89; 2026-01-07: 89; 2026-01-08: 89; 2026-01-09: 89; 2026-01-10: 89; 2026-01-11: 89; 2026-01-12: 89; 2026-01-13: 89; 2026-01-14: 89; 2026-01-15: 89; 2026-01-16: 89; 2026-01-17: 89; 2026-01-18: 89; 2026-01-19: 89; 2026-01-20: 89; 2026-01-21: 89; 2026-01-22: 89; 2026-01-23: 89; 2026-01-24: 89; 2026-01-25: 89; 2026-01-26: 89; 2026-01-27: 89; 2026-01-28: 89; 2026-01-29: 89; 2026-01-30: 89; 2026-01-31: 89; 2026-02-01: 89; 2026-02-02: 89; 2026-02-03: 72; 2026-02-04: 72; 2026-02-05: 78; 2026-02-06: 78; 2026-02-07: 78; 2026-02-08: 78; 2026-02-09: 78; 2026-02-10: 78; 2026-02-11: 78; 2026-02-12: 65; 2026-02-13: 64; 2026-02-14: 64; 2026-02-15: 62; 2026-02-16: 58; 2026-02-17: 58; 2026-02-18: 56; 2026-02-19: 56; 2026-02-20: 56; 2026-02-21: 56; 2026-02-22: 56; 2026-02-23: 56; 2026-02-24: 56; 2026-02-25: 56; 2026-02-26: 56; 2026-02-27: 56
25 | M/s Akshar (33kv electrical) | Service | UG 3kV | Manpower Details (P) | [156 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60
|  |  |  | Manpower Details (A) | [156 empty] | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 16 | 16 | 16 | 11 | 11 | 11 | 16 | 16 | 16 | 16 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 20 | 20 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 35 | 35
26 | M/s Varsha solar (33kv electrical) | Service | UG 3kV | Manpower Details (P) | 2025-06-06: 20; 2025-06-07: 20; 2025-06-08: 20; 2025-06-09: 20; 2025-06-10: 20; 2025-06-11: 20; 2025-06-12: 20; 2025-06-13: 20; 2025-06-14: 20; 2025-06-15: 20; 2025-06-16: 20; 2025-06-17: 20; 2025-06-18: 20; 2025-06-19: 20; 2025-06-20: 20; 2025-06-21: 20; 2025-06-22: 20; 2025-06-23: 20; 2025-06-24: 20; 2025-06-25: 20; 2025-06-26: 20; 2025-06-27: 20; 2025-06-28: 20; 2025-06-29: 20; 2025-06-30: 20; 2025-07-01: 20; 2025-07-02: 20; 2025-07-03: 20; 2025-07-04: 20; 2025-07-05: 20; 2025-07-06: 20; 2025-07-07: 20; 2025-07-08: 20; 2025-07-09: 20; 2025-07-10: 20; 2025-07-11: 20; 2025-07-12: 20; 2025-07-13: 20; 2025-07-14: 20; 2025-07-15: 20; 2025-07-16: 20; 2025-07-17: 20; 2025-07-18: 20; 2025-07-19: 20; 2025-07-20: 20; 2025-07-21: 20; 2025-07-22: 20; 2025-07-23: 20; 2025-07-24: 20; 2025-07-25: 20; 2025-07-26: 20; 2025-07-27: 20; 2025-07-28: 20; 2025-07-29: 20; 2025-07-30: 20; 2025-07-31: 20; 2025-08-01: 20; 2025-08-02: 20; 2025-08-03: 20; 2025-08-04: 20; 2025-08-05: 20; 2025-08-06: 20; 2025-08-07: 20; 2025-08-08: 20; 2025-08-09: 20; 2025-08-10: 20; 2025-08-11: 20; 2025-08-12: 20; 2025-08-13: 20; 2025-08-14: 20; 2025-08-15: 20; 2025-08-16: 20; 2025-08-17: 20; 2025-08-18: 20; 2025-08-19: 20; 2025-08-20: 20; 2025-08-21: 20; 2025-08-22: 20; 2025-08-23: 20; 2025-08-24: 20; 2025-08-25: 20; 2025-08-26: 20; 2025-08-27: 20; 2025-08-28: 20; 2025-08-29: 20; 2025-08-30: 20; 2025-08-31: 20; 2025-09-01: 20; 2025-09-02: 20; 2025-09-03: 20; 2025-09-04: 20; 2025-09-05: 20; 2025-09-06: 20; 2025-09-07: 20; 2025-09-08: 20
|  |  |  | Manpower Details (A) | [156 empty] | 15 | 15 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | M/s Supreme (33kv electrical) | Service | UG 3kV | Manpower Details (P) | [156 empty] | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
|  |  |  | Manpower Details (A) | [156 empty] | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 13 | 13 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
28 | M/s Winbee (33kv electrical) | Service | UG 3kV | Manpower Details (P) | 2025-06-06: 10; 2025-06-07: 10; 2025-06-08: 10; 2025-06-09: 10; 2025-06-10: 10; 2025-06-11: 10; 2025-06-12: 10; 2025-06-13: 10; 2025-06-14: 10; 2025-06-15: 10; 2025-06-16: 10; 2025-06-17: 10; 2025-06-18: 10; 2025-06-19: 10; 2025-06-20: 10; 2025-06-21: 10; 2025-06-22: 10; 2025-06-23: 10; 2025-06-24: 10; 2025-06-25: 10; 2025-06-26: 10; 2025-06-27: 10; 2025-06-28: 10; 2025-06-29: 10; 2025-06-30: 10; 2025-07-01: 10; 2025-07-02: 10; 2025-07-03: 10; 2025-07-04: 10; 2025-07-05: 10; 2025-07-06: 10; 2025-07-07: 10; 2025-07-08: 10; 2025-07-09: 10; 2025-07-10: 10; 2025-07-11: 10; 2025-07-12: 10; 2025-07-13: 10; 2025-07-14: 10; 2025-07-15: 10; 2025-07-16: 10; 2025-07-17: 10; 2025-07-18: 10; 2025-07-19: 10; 2025-07-20: 10; 2025-07-21: 10; 2025-07-22: 10; 2025-07-23: 10; 2025-07-24: 10; 2025-07-25: 10; 2025-07-26: 10; 2025-07-27: 10; 2025-07-28: 10; 2025-07-29: 10; 2025-07-30: 10; 2025-07-31: 10; 2025-08-01: 10; 2025-08-02: 10; 2025-08-03: 10; 2025-08-04: 10; 2025-08-05: 10; 2025-08-06: 10; 2025-08-07: 10; 2025-08-08: 10; 2025-08-09: 10; 2025-08-10: 10; 2025-08-11: 10; 2025-08-12: 10; 2025-08-13: 10; 2025-08-14: 10; 2025-08-15: 10; 2025-08-16: 10; 2025-08-17: 10; 2025-08-18: 10; 2025-08-19: 10; 2025-08-20: 10; 2025-08-21: 10; 2025-08-22: 10; 2025-08-23: 10; 2025-08-24: 10; 2025-08-25: 10; 2025-08-26: 10; 2025-08-27: 10; 2025-08-28: 10; 2025-08-29: 10; 2025-08-30: 10; 2025-08-31: 10; 2025-09-01: 10; 2025-09-02: 10; 2025-09-03: 10; 2025-09-04: 10; 2025-09-05: 10; 2025-09-06: 10; 2025-09-07: 10; 2025-09-08: 10; 2025-09-09: 10; 2025-09-10: 10
|  |  |  | Manpower Details (A) | [156 empty] | 6 | 6 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | M/s Decon (33kv electrical) | Service | UG 3kV | Manpower Details (P) | [156 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
|  |  |  | Manpower Details (A) | [156 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
30 | M/s Ice Cube (33kv electrical) | Service | UG 3kV | Manpower Details (P) | [156 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
|  |  |  | Manpower Details (A) | [156 empty] | 3 | 3 | 0 | 5 | 5 | 10 | 10 | 10 | 10 | 10 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 12 | 12 | 12 | 20 | 20 | 20 | 20 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
31 | M/s Malinath (33kv electrical) | Service | UG 3kV | Manpower Details (P) | 2025-06-06: 10; 2025-06-07: 10; 2025-06-08: 10; 2025-06-09: 10; 2025-06-10: 10; 2025-06-11: 10; 2025-06-12: 10; 2025-06-13: 10; 2025-06-14: 10; 2025-06-15: 10; 2025-06-16: 10; 2025-06-17: 10; 2025-06-18: 10; 2025-06-19: 10; 2025-06-20: 10; 2025-06-21: 10; 2025-06-22: 10; 2025-06-23: 10; 2025-06-24: 10; 2025-06-25: 10; 2025-06-26: 10; 2025-06-27: 10; 2025-06-28: 10; 2025-06-29: 10; 2025-06-30: 10; 2025-07-01: 10; 2025-07-02: 10; 2025-07-03: 10; 2025-07-04: 10; 2025-07-05: 10; 2025-07-06: 10; 2025-07-07: 10; 2025-07-08: 10; 2025-07-09: 10; 2025-07-10: 10; 2025-07-11: 10; 2025-07-12: 10; 2025-07-13: 10; 2025-07-14: 10; 2025-07-15: 10; 2025-07-16: 10; 2025-07-17: 10; 2025-07-18: 10; 2025-07-19: 10; 2025-07-20: 10; 2025-07-21: 10; 2025-07-22: 10; 2025-07-23: 10; 2025-07-24: 10; 2025-07-25: 10; 2025-07-26: 10; 2025-07-27: 10; 2025-07-28: 10; 2025-07-29: 10; 2025-07-30: 10; 2025-07-31: 10; 2025-08-01: 10; 2025-08-02: 10; 2025-08-03: 10; 2025-08-04: 10; 2025-08-05: 10; 2025-08-06: 10; 2025-08-07: 10; 2025-08-08: 10; 2025-08-09: 10; 2025-08-10: 10; 2025-08-11: 10; 2025-08-12: 10; 2025-08-13: 10; 2025-08-14: 10; 2025-08-15: 10; 2025-08-16: 10; 2025-08-17: 10; 2025-08-18: 10; 2025-08-19: 10; 2025-08-20: 10; 2025-08-21: 10; 2025-08-22: 10; 2025-08-23: 10; 2025-08-24: 10; 2025-08-25: 10; 2025-08-26: 10; 2025-08-27: 10; 2025-08-28: 10; 2025-08-29: 10; 2025-08-30: 10; 2025-08-31: 10; 2025-09-01: 10; 2025-09-02: 10; 2025-09-03: 10; 2025-09-04: 10; 2025-09-05: 10; 2025-09-06: 10; 2025-09-07: 10; 2025-09-08: 10
|  |  |  | Manpower Details (A) | [156 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | M/s First Volt (33kv electrical) | Service | UG 3kV | Manpower Details (P) | 2025-06-06: 10; 2025-06-07: 10; 2025-06-08: 10; 2025-06-09: 10; 2025-06-10: 10; 2025-06-11: 10; 2025-06-12: 10; 2025-06-13: 10; 2025-06-14: 10; 2025-06-15: 10; 2025-06-16: 10; 2025-06-17: 10; 2025-06-18: 10; 2025-06-19: 10; 2025-06-20: 10; 2025-06-21: 10; 2025-06-22: 10; 2025-06-23: 10; 2025-06-24: 10; 2025-06-25: 10; 2025-06-26: 10; 2025-06-27: 10; 2025-06-28: 10; 2025-06-29: 10; 2025-06-30: 10; 2025-07-01: 10; 2025-07-02: 10
|  |  |  | Manpower Details (A) | [156 empty] | 2 | 2 | 4 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | M/s Bajarang Construction (33kv electrical) | Service | UG 3kV | Manpower Details (P) | [156 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
|  |  |  | Manpower Details (A) | [156 empty] | 8 | 8 | 8 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 12 | 12
34 | M/s Sunlec (33kv electrical) | Service | UG 3kV | Manpower Details (P) | [156 empty] | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
|  |  |  | Manpower Details (A) | [156 empty] | 12 | 12 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 8 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 25 | 25 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 32 | 32 | 32 | 32 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
35 | M/s Varsha Solar (USS Electrical) | Service | USS | Manpower Details (P) | 2025-07-16: 20; 2025-07-17: 20; 2025-07-18: 20; 2025-07-19: 20; 2025-07-20: 20; 2025-07-21: 20; 2025-07-22: 20; 2025-07-23: 20; 2025-07-24: 20; 2025-07-25: 20; 2025-07-26: 20; 2025-07-27: 20; 2025-07-28: 20; 2025-07-29: 20; 2025-07-30: 20; 2025-07-31: 20; 2025-08-01: 20; 2025-08-02: 20; 2025-08-03: 20; 2025-08-04: 20; 2025-08-05: 20; 2025-08-06: 20; 2025-08-07: 20; 2025-08-08: 20; 2025-08-09: 20; 2025-08-10: 20; 2025-08-11: 20; 2025-08-12: 20; 2025-08-13: 20; 2025-08-14: 20; 2025-08-15: 20; 2025-08-16: 20; 2025-08-17: 20; 2025-08-18: 20; 2025-08-19: 20; 2025-08-20: 20; 2025-08-21: 20; 2025-08-22: 20; 2025-08-23: 20; 2025-08-24: 20; 2025-08-25: 20; 2025-08-26: 20; 2025-08-27: 20; 2025-08-28: 20; 2025-08-29: 20; 2025-08-30: 20; 2025-08-31: 20; 2025-09-01: 20; 2025-09-02: 20; 2025-09-03: 20; 2025-09-04: 20; 2025-09-05: 20; 2025-09-06: 20; 2025-09-07: 20; 2025-09-08: 20; 2025-09-09: 20; 2025-09-10: 20; 2025-09-11: 20; 2025-09-12: 20; 2025-09-13: 20; 2025-09-14: 20; 2025-09-15: 20; 2025-09-16: 20; 2025-09-17: 20; 2025-09-18: 20; 2025-09-19: 20; 2025-09-20: 20; 2025-09-21: 20; 2025-09-22: 20; 2025-09-23: 20; 2025-09-24: 20; 2025-09-25: 20; 2025-09-26: 20; 2025-09-27: 20; 2025-09-28: 20; 2025-09-29: 20; 2025-09-30: 20; 2025-10-01: 20; 2025-10-02: 20; 2025-10-03: 20; 2025-10-04: 20; 2025-10-05: 20; 2025-10-06: 20; 2025-10-07: 20; 2025-10-08: 20; 2025-10-09: 20; 2025-10-10: 0; 2025-10-11: 0; 2025-10-12: 0; 2025-10-13: 0; 2025-10-14: 0; 2025-10-15: 0; 2025-10-16: 0; 2025-10-17: 0; 2025-10-18: 0; 2025-10-19: 0; 2025-10-20: 0; 2025-10-21: 0; 2025-10-22: 0; 2025-10-23: 0; 2025-10-24: 0; 2025-10-25: 0; 2025-10-26: 0; 2025-10-27: 0; 2025-10-28: 0; 2025-10-29: 0; 2025-10-30: 0; 2025-10-31: 0; 2025-11-01: 0; 2025-11-02: 0; 2025-11-03: 0; 2025-11-04: 0; 2025-11-05: 0; 2025-11-06: 0; 2025-11-07: 0; 2025-11-08: 0; 2025-11-09: 0; 2025-11-10: 0; 2025-11-11: 0; 2025-11-12: 0; 2025-11-13: 0; 2025-11-14: 0; 2025-11-15: 0; 2025-11-16: 0; 2025-11-17: 0; 2025-11-18: 0; 2025-11-19: 0; 2025-11-20: 0; 2025-11-21: 0; 2025-11-22: 0; 2025-11-23: 0; 2025-11-24: 0; 2025-11-25: 0; 2025-11-26: 0; 2025-11-27: 0; 2025-11-28: 0; 2025-11-29: 0; 2025-11-30: 0; 2025-12-01: 0; 2025-12-02: 0; 2025-12-03: 0; 2025-12-04: 0; 2025-12-05: 0; 2025-12-06: 0; 2025-12-07: 0; 2025-12-08: 0; 2025-12-09: 0; 2025-12-10: 0; 2025-12-11: 0; 2025-12-12: 0; 2025-12-13: 0; 2025-12-14: 0; 2025-12-15: 0; 2025-12-16: 0; 2025-12-17: 0; 2025-12-18: 0; 2025-12-19: 0; 2025-12-20: 0; 2025-12-21: 0; 2025-12-22: 0; 2025-12-23: 0; 2025-12-24: 0; 2025-12-25: 0; 2025-12-26: 0; 2025-12-27: 0; 2025-12-28: 0; 2025-12-29: 0; 2025-12-30: 0; 2025-12-31: 0; 2026-01-01: 0; 2026-01-02: 0; 2026-01-03: 0; 2026-01-04: 0; 2026-01-05: 0; 2026-01-06: 0; 2026-01-07: 0; 2026-01-08: 0; 2026-01-09: 0; 2026-01-10: 0; 2026-01-11: 0; 2026-01-12: 0; 2026-01-13: 0; 2026-01-14: 0; 2026-01-15: 0; 2026-01-16: 0; 2026-01-17: 0; 2026-01-18: 0; 2026-01-19: 0; 2026-01-20: 0; 2026-01-21: 0; 2026-01-22: 0; 2026-01-23: 0; 2026-01-24: 0; 2026-01-25: 0; 2026-01-26: 0; 2026-01-27: 0; 2026-01-28: 0; 2026-01-29: 0; 2026-01-30: 0; 2026-01-31: 0; 2026-02-01: 0; 2026-02-02: 0; 2026-02-03: 0; 2026-02-04: 0; 2026-02-05: 0; 2026-02-06: 0; 2026-02-07: 0; 2026-02-08: 0; 2026-02-09: 0; 2026-02-10: 0; 2026-02-11: 0; 2026-02-12: 0; 2026-02-13: 0; 2026-02-14: 0; 2026-02-15: 0; 2026-02-16: 0; 2026-02-17: 0; 2026-02-18: 0; 2026-02-19: 0; 2026-02-20: 0; 2026-02-21: 0; 2026-02-22: 0; 2026-02-23: 0; 2026-02-24: 0; 2026-02-25: 0; 2026-02-26: 0; 2026-02-27: 0
|  |  |  | Manpower Details (A) | 2025-07-16: 15; 2025-07-17: 15; 2025-07-18: 15; 2025-07-19: 15; 2025-07-20: 15; 2025-07-21: 15; 2025-07-22: 15; 2025-07-23: 15; 2025-07-24: 15; 2025-07-25: 15; 2025-07-26: 15; 2025-07-27: 15; 2025-07-28: 15; 2025-07-29: 15; 2025-07-30: 15; 2025-07-31: 15; 2025-08-01: 15; 2025-08-02: 15; 2025-08-03: 15; 2025-08-04: 15; 2025-08-05: 15; 2025-08-06: 15; 2025-08-07: 15; 2025-08-08: 15; 2025-08-09: 15; 2025-08-10: 15; 2025-08-11: 15; 2025-08-12: 15; 2025-08-13: 15; 2025-08-14: 15; 2025-08-15: 15; 2025-08-16: 15; 2025-08-17: 15; 2025-08-18: 15; 2025-08-19: 15; 2025-08-20: 15; 2025-08-21: 15; 2025-08-22: 15; 2025-08-23: 15; 2025-08-24: 15; 2025-08-25: 15; 2025-08-26: 15; 2025-08-27: 15; 2025-08-28: 15; 2025-08-29: 15; 2025-08-30: 15; 2025-08-31: 15; 2025-09-01: 15; 2025-09-02: 15; 2025-09-03: 15; 2025-09-04: 15; 2025-09-05: 15; 2025-09-06: 15; 2025-09-07: 15; 2025-09-08: 8; 2025-09-09: 8; 2025-09-10: 8; 2025-09-11: 8; 2025-09-12: 8; 2025-09-13: 8; 2025-09-14: 8; 2025-09-15: 8; 2025-09-16: 8; 2025-09-17: 8; 2025-09-18: 8; 2025-09-19: 8; 2025-09-20: 8; 2025-09-21: 8; 2025-09-22: 8; 2025-09-23: 8; 2025-09-24: 8; 2025-09-25: 8; 2025-09-26: 8; 2025-09-27: 8; 2025-09-28: 8; 2025-09-29: 8; 2025-09-30: 8; 2025-10-01: 8; 2025-10-02: 8; 2025-10-03: 8; 2025-10-04: 8; 2025-10-05: 8; 2025-10-06: 8; 2025-10-07: 8; 2025-10-08: 8; 2025-10-09: 8; 2025-10-10: 0; 2025-10-11: 0; 2025-10-12: 0; 2025-10-13: 0; 2025-10-14: 0; 2025-10-15: 0; 2025-10-16: 0; 2025-10-17: 0; 2025-10-18: 0; 2025-10-19: 0; 2025-10-20: 0; 2025-10-21: 0; 2025-10-22: 0; 2025-10-23: 0; 2025-10-24: 0; 2025-10-25: 0; 2025-10-26: 0; 2025-10-27: 0; 2025-10-28: 0; 2025-10-29: 0; 2025-10-30: 0; 2025-10-31: 0; 2025-11-01: 0; 2025-11-02: 0; 2025-11-03: 0; 2025-11-04: 0; 2025-11-05: 0; 2025-11-06: 0; 2025-11-07: 0; 2025-11-08: 0; 2025-11-09: 0; 2025-11-10: 0; 2025-11-11: 0; 2025-11-12: 0; 2025-11-13: 0; 2025-11-14: 0; 2025-11-15: 0; 2025-11-16: 0; 2025-11-17: 0; 2025-11-18: 0; 2025-11-19: 0; 2025-11-20: 0; 2025-11-21: 0; 2025-11-22: 0; 2025-11-23: 0; 2025-11-24: 0; 2025-11-25: 0; 2025-11-26: 0; 2025-11-27: 0; 2025-11-28: 0; 2025-11-29: 0; 2025-11-30: 0; 2025-12-01: 0; 2025-12-02: 0; 2025-12-03: 0; 2025-12-04: 0; 2025-12-05: 0; 2025-12-06: 0; 2025-12-07: 0; 2025-12-08: 0; 2025-12-09: 0; 2025-12-10: 0; 2025-12-11: 0; 2025-12-12: 0; 2025-12-13: 0; 2025-12-14: 0; 2025-12-15: 0; 2025-12-16: 0; 2025-12-17: 0; 2025-12-18: 0; 2025-12-19: 0; 2025-12-20: 0; 2025-12-21: 0; 2025-12-22: 0; 2025-12-23: 0; 2025-12-24: 0; 2025-12-25: 0; 2025-12-26: 0; 2025-12-27: 0; 2025-12-28: 0; 2025-12-29: 0; 2025-12-30: 0; 2025-12-31: 0; 2026-01-01: 0; 2026-01-02: 0; 2026-01-03: 0; 2026-01-04: 0; 2026-01-05: 0; 2026-01-06: 0; 2026-01-07: 0; 2026-01-08: 0; 2026-01-09: 0; 2026-01-10: 0; 2026-01-11: 0; 2026-01-12: 0; 2026-01-13: 0; 2026-01-14: 0; 2026-01-15: 0; 2026-01-16: 0; 2026-01-17: 0; 2026-01-18: 0; 2026-01-19: 0; 2026-01-20: 0; 2026-01-21: 0; 2026-01-22: 0; 2026-01-23: 0; 2026-01-24: 0; 2026-01-25: 0; 2026-01-26: 0; 2026-01-27: 0; 2026-01-28: 0; 2026-01-29: 0; 2026-01-30: 0; 2026-01-31: 0; 2026-02-01: 0; 2026-02-02: 0; 2026-02-03: 0; 2026-02-04: 0; 2026-02-05: 0; 2026-02-06: 0; 2026-02-07: 0; 2026-02-08: 0; 2026-02-09: 0; 2026-02-10: 0; 2026-02-11: 0; 2026-02-12: 0; 2026-02-13: 0; 2026-02-14: 0; 2026-02-15: 0; 2026-02-16: 0; 2026-02-17: 0; 2026-02-18: 0; 2026-02-19: 0; 2026-02-20: 0; 2026-02-21: 0; 2026-02-22: 0; 2026-02-23: 0; 2026-02-24: 0; 2026-02-25: 0; 2026-02-26: 0; 2026-02-27: 0
36 | M/s Akshar (USS Electrical) | Service | USS | Manpower Details (P) | 2025-07-16: 20; 2025-07-17: 20; 2025-07-18: 20; 2025-07-19: 20; 2025-07-20: 20; 2025-07-21: 20; 2025-07-22: 20; 2025-07-23: 20; 2025-07-24: 20; 2025-07-25: 20; 2025-07-26: 20; 2025-07-27: 20; 2025-07-28: 20; 2025-07-29: 20; 2025-07-30: 20; 2025-07-31: 20; 2025-09-22: 40; 2025-09-23: 40; 2025-09-24: 40; 2025-09-25: 40; 2025-09-26: 40; 2025-09-27: 40; 2025-09-28: 40; 2025-09-29: 40; 2025-09-30: 40; 2025-10-01: 40; 2025-10-02: 40; 2025-10-03: 40; 2025-10-04: 40; 2025-10-05: 40; 2025-10-06: 40; 2025-10-07: 40; 2025-10-08: 40; 2025-10-09: 40; 2025-10-10: 40; 2025-10-11: 40; 2025-10-12: 40; 2025-10-13: 40; 2025-10-14: 40; 2025-10-15: 40; 2025-10-16: 40; 2025-10-17: 40; 2025-10-18: 40; 2025-10-19: 40; 2025-10-20: 40; 2025-10-21: 40; 2025-10-22: 40; 2025-10-23: 40; 2025-10-24: 40; 2025-10-25: 40; 2025-10-26: 40; 2025-10-27: 40; 2025-10-28: 40; 2025-10-29: 40; 2025-10-30: 40; 2025-10-31: 40; 2025-11-01: 40; 2025-11-02: 40; 2025-11-03: 40; 2025-11-04: 40; 2025-11-05: 40; 2025-11-06: 40; 2025-11-07: 40; 2025-11-08: 40; 2025-11-09: 40; 2025-11-10: 40; 2025-11-11: 40; 2025-11-12: 40; 2025-11-13: 40; 2025-11-14: 40; 2025-11-15: 40; 2025-11-16: 40; 2025-11-17: 40; 2025-11-18: 40; 2025-11-19: 40; 2025-11-20: 40; 2025-11-21: 40; 2025-11-22: 40; 2025-11-23: 40; 2025-11-24: 40; 2025-11-25: 40; 2025-11-26: 40; 2025-11-27: 40; 2025-11-28: 40; 2025-11-29: 40; 2025-11-30: 40; 2025-12-01: 40; 2025-12-02: 40; 2025-12-03: 40; 2025-12-04: 40; 2025-12-05: 40; 2025-12-06: 40; 2025-12-07: 40; 2025-12-08: 40; 2025-12-09: 40; 2025-12-10: 40; 2025-12-11: 40; 2025-12-12: 40; 2025-12-13: 40; 2025-12-14: 40; 2025-12-15: 40; 2025-12-16: 40; 2025-12-17: 40; 2025-12-18: 40; 2025-12-19: 40; 2025-12-20: 40; 2025-12-21: 40; 2025-12-22: 40; 2025-12-23: 40; 2025-12-24: 40; 2025-12-25: 40; 2025-12-26: 40; 2025-12-27: 40; 2025-12-28: 40; 2025-12-29: 40; 2025-12-30: 40; 2025-12-31: 40; 2026-01-01: 40; 2026-01-02: 40; 2026-01-03: 40; 2026-01-04: 40; 2026-01-05: 40; 2026-01-06: 40; 2026-01-07: 40; 2026-01-08: 40; 2026-01-09: 40; 2026-01-10: 40; 2026-01-11: 40; 2026-01-12: 40; 2026-01-13: 40; 2026-01-14: 40; 2026-01-15: 40; 2026-01-16: 40; 2026-01-17: 40; 2026-01-18: 40; 2026-01-19: 40; 2026-01-20: 40; 2026-01-21: 40; 2026-01-22: 40; 2026-01-23: 40; 2026-01-24: 40; 2026-01-25: 40; 2026-01-26: 40; 2026-01-27: 40; 2026-01-28: 40; 2026-01-29: 40; 2026-01-30: 40; 2026-01-31: 40; 2026-02-01: 40; 2026-02-02: 40; 2026-02-03: 40; 2026-02-04: 40; 2026-02-05: 40; 2026-02-06: 40; 2026-02-07: 40; 2026-02-08: 40; 2026-02-09: 40; 2026-02-10: 40; 2026-02-11: 40; 2026-02-12: 40; 2026-02-13: 40; 2026-02-14: 40; 2026-02-15: 40; 2026-02-16: 40; 2026-02-17: 40; 2026-02-18: 40; 2026-02-19: 40; 2026-02-20: 40; 2026-02-21: 40; 2026-02-22: 40; 2026-02-23: 40; 2026-02-24: 40; 2026-02-25: 40; 2026-02-26: 40; 2026-02-27: 40
|  |  |  | Manpower Details (A) | 2025-07-16: 15; 2025-07-17: 15; 2025-07-18: 15; 2025-07-19: 15; 2025-07-20: 15; 2025-07-21: 15; 2025-07-22: 15; 2025-07-23: 15; 2025-07-24: 15; 2025-07-25: 15; 2025-07-26: 15; 2025-07-27: 15; 2025-07-28: 15; 2025-07-29: 15; 2025-07-30: 15; 2025-07-31: 15; 2025-09-22: 37; 2025-09-23: 37; 2025-09-24: 37; 2025-09-25: 20; 2025-09-26: 20; 2025-09-27: 20; 2025-09-28: 20; 2025-09-29: 20; 2025-09-30: 20; 2025-10-01: 20; 2025-10-02: 20; 2025-10-03: 20; 2025-10-04: 20; 2025-10-05: 20; 2025-10-06: 20; 2025-10-07: 20; 2025-10-08: 20; 2025-10-09: 20; 2025-10-10: 32; 2025-10-11: 32; 2025-10-12: 32; 2025-10-13: 30; 2025-10-14: 30; 2025-10-15: 30; 2025-10-16: 30; 2025-10-17: 30; 2025-10-18: 30; 2025-10-19: 30; 2025-10-20: 30; 2025-10-21: 30; 2025-10-22: 30; 2025-10-23: 30; 2025-10-24: 30; 2025-10-25: 30; 2025-10-26: 30; 2025-10-27: 30; 2025-10-28: 30; 2025-10-29: 32; 2025-10-30: 32; 2025-10-31: 32; 2025-11-01: 32; 2025-11-02: 32; 2025-11-03: 32; 2025-11-04: 32; 2025-11-05: 32; 2025-11-06: 32; 2025-11-07: 32; 2025-11-08: 32; 2025-11-09: 32; 2025-11-10: 32; 2025-11-11: 32; 2025-11-12: 32; 2025-11-13: 32; 2025-11-14: 32; 2025-11-15: 32; 2025-11-16: 32; 2025-11-17: 32; 2025-11-18: 32; 2025-11-19: 32; 2025-11-20: 32; 2025-11-21: 32; 2025-11-22: 32; 2025-11-23: 32; 2025-11-24: 32; 2025-11-25: 32; 2025-11-26: 32; 2025-11-27: 32; 2025-11-28: 32; 2025-11-29: 35; 2025-11-30: 35; 2025-12-01: 35; 2025-12-02: 35; 2025-12-03: 35; 2025-12-04: 35; 2025-12-05: 35; 2025-12-06: 35; 2025-12-07: 35; 2025-12-08: 35; 2025-12-09: 35; 2025-12-10: 35; 2025-12-11: 35; 2025-12-12: 35; 2025-12-13: 35; 2025-12-14: 35; 2025-12-15: 35; 2025-12-16: 35; 2025-12-17: 35; 2025-12-18: 35; 2025-12-19: 35; 2025-12-20: 35; 2025-12-21: 35; 2025-12-22: 35; 2025-12-23: 35; 2025-12-24: 34; 2025-12-25: 34; 2025-12-26: 34; 2025-12-27: 34; 2025-12-28: 34; 2025-12-29: 34; 2025-12-30: 34; 2025-12-31: 34; 2026-01-01: 34; 2026-01-02: 34; 2026-01-03: 34; 2026-01-04: 34; 2026-01-05: 34; 2026-01-06: 34; 2026-01-07: 34; 2026-01-08: 34; 2026-01-09: 34; 2026-01-10: 34; 2026-01-11: 34; 2026-01-12: 34; 2026-01-13: 34; 2026-01-14: 34; 2026-01-15: 34; 2026-01-16: 34; 2026-01-17: 34; 2026-01-18: 34; 2026-01-19: 38; 2026-01-20: 38; 2026-01-21: 38; 2026-01-22: 38; 2026-01-23: 38; 2026-01-24: 38; 2026-01-25: 38; 2026-01-26: 38; 2026-01-27: 38; 2026-01-28: 38; 2026-01-29: 38; 2026-01-30: 38; 2026-01-31: 38; 2026-02-01: 38; 2026-02-02: 38; 2026-02-03: 38; 2026-02-04: 40; 2026-02-05: 40; 2026-02-06: 40; 2026-02-07: 40; 2026-02-08: 40; 2026-02-09: 40; 2026-02-10: 40; 2026-02-11: 40; 2026-02-12: 40; 2026-02-13: 40; 2026-02-14: 40; 2026-02-15: 40; 2026-02-16: 40; 2026-02-17: 40; 2026-02-18: 40; 2026-02-19: 40; 2026-02-20: 40; 2026-02-21: 40; 2026-02-22: 40; 2026-02-23: 40; 2026-02-24: 40; 2026-02-25: 40; 2026-02-26: 40; 2026-02-27: 40
37 | M/s ICE cube (USS Electrical) | Service | USS | Manpower Details (P) | 2025-07-16: 20; 2025-07-17: 20; 2025-07-18: 20; 2025-07-19: 20; 2025-07-20: 20; 2025-07-21: 20; 2025-07-22: 20; 2025-07-23: 20; 2025-07-24: 20; 2025-07-25: 20; 2025-07-26: 20; 2025-07-27: 20; 2025-07-28: 20; 2025-07-29: 20; 2025-07-30: 20; 2025-07-31: 20; 2025-09-22: 25; 2025-09-23: 25; 2025-09-24: 25; 2025-09-25: 25; 2025-09-26: 25; 2025-09-27: 25; 2025-09-28: 25; 2025-09-29: 25; 2025-09-30: 25; 2025-10-01: 25; 2025-10-02: 25; 2025-10-03: 25; 2025-10-04: 25; 2025-10-05: 25; 2025-10-06: 25; 2025-10-07: 25; 2025-10-08: 25; 2025-10-09: 25; 2025-10-10: 25; 2025-10-11: 25; 2025-10-12: 25; 2025-10-13: 25; 2025-10-14: 25; 2025-10-15: 25; 2025-10-16: 25; 2025-10-17: 25; 2025-10-18: 25; 2025-10-19: 25; 2025-10-20: 25; 2025-10-21: 25; 2025-10-22: 25; 2025-10-23: 25; 2025-10-24: 25; 2025-10-25: 25; 2025-10-26: 25; 2025-10-27: 25; 2025-10-28: 25; 2025-10-29: 25; 2025-10-30: 25; 2025-10-31: 25; 2025-11-01: 25; 2025-11-02: 25; 2025-11-03: 25; 2025-11-04: 25; 2025-11-05: 25; 2025-11-06: 25; 2025-11-07: 25; 2025-11-08: 25; 2025-11-09: 25; 2025-11-10: 25; 2025-11-11: 25; 2025-11-12: 25; 2025-11-13: 25; 2025-11-14: 25; 2025-11-15: 25; 2025-11-16: 25; 2025-11-17: 25; 2025-11-18: 25; 2025-11-19: 25; 2025-11-20: 25; 2025-11-21: 25; 2025-11-22: 25; 2025-11-23: 25; 2025-11-24: 25; 2025-11-25: 25; 2025-11-26: 25; 2025-11-27: 25; 2025-11-28: 25; 2025-11-29: 25; 2025-11-30: 25; 2025-12-01: 25; 2025-12-02: 25; 2025-12-03: 25; 2025-12-04: 25; 2025-12-05: 25; 2025-12-06: 25; 2025-12-07: 25; 2025-12-08: 25; 2025-12-09: 25; 2025-12-10: 25; 2025-12-11: 25; 2025-12-12: 25; 2025-12-13: 25; 2025-12-14: 25; 2025-12-15: 25; 2025-12-16: 25; 2025-12-17: 25; 2025-12-18: 25; 2025-12-19: 25; 2025-12-20: 25; 2025-12-21: 25; 2025-12-22: 25; 2025-12-23: 25; 2025-12-24: 25; 2025-12-25: 25; 2025-12-26: 25; 2025-12-27: 25; 2025-12-28: 25; 2025-12-29: 25; 2025-12-30: 25; 2025-12-31: 25; 2026-01-01: 25; 2026-01-02: 25; 2026-01-03: 25; 2026-01-04: 25; 2026-01-05: 25; 2026-01-06: 25; 2026-01-07: 25; 2026-01-08: 25; 2026-01-09: 25; 2026-01-10: 25; 2026-01-11: 25; 2026-01-12: 25; 2026-01-13: 25; 2026-01-14: 25; 2026-01-15: 25; 2026-01-16: 25; 2026-01-17: 25; 2026-01-18: 25; 2026-01-19: 25; 2026-01-20: 25; 2026-01-21: 25; 2026-01-22: 25; 2026-01-23: 25; 2026-01-24: 25; 2026-01-25: 25; 2026-01-26: 25; 2026-01-27: 25; 2026-01-28: 25; 2026-01-29: 25; 2026-01-30: 25; 2026-01-31: 25; 2026-02-01: 25; 2026-02-02: 25; 2026-02-03: 25; 2026-02-04: 25; 2026-02-05: 25; 2026-02-06: 25; 2026-02-07: 25; 2026-02-08: 25; 2026-02-09: 25; 2026-02-10: 25; 2026-02-11: 25; 2026-02-12: 25; 2026-02-13: 25; 2026-02-14: 25; 2026-02-15: 25; 2026-02-16: 25; 2026-02-17: 25; 2026-02-18: 25; 2026-02-19: 25; 2026-02-20: 25; 2026-02-21: 25; 2026-02-22: 25; 2026-02-23: 25; 2026-02-24: 25; 2026-02-25: 25; 2026-02-26: 25; 2026-02-27: 25
|  |  |  | Manpower Details (A) | 2025-07-16: 15; 2025-07-17: 15; 2025-07-18: 15; 2025-07-19: 15; 2025-07-20: 15; 2025-07-21: 15; 2025-07-22: 15; 2025-07-23: 15; 2025-07-24: 15; 2025-07-25: 15; 2025-07-26: 15; 2025-07-27: 15; 2025-07-28: 15; 2025-07-29: 15; 2025-07-30: 15; 2025-07-31: 15; 2025-09-22: 25; 2025-09-23: 25; 2025-09-24: 25; 2025-09-25: 12; 2025-09-26: 12; 2025-09-27: 12; 2025-09-28: 12; 2025-09-29: 12; 2025-09-30: 12; 2025-10-01: 12; 2025-10-02: 12; 2025-10-03: 12; 2025-10-04: 12; 2025-10-05: 12; 2025-10-06: 12; 2025-10-07: 12; 2025-10-08: 12; 2025-10-09: 12; 2025-10-10: 25; 2025-10-11: 25; 2025-10-12: 25; 2025-10-13: 25; 2025-10-14: 25; 2025-10-15: 25; 2025-10-16: 25; 2025-10-17: 25; 2025-10-18: 25; 2025-10-19: 25; 2025-10-20: 25; 2025-10-21: 25; 2025-10-22: 25; 2025-10-23: 25; 2025-10-24: 25; 2025-10-25: 25; 2025-10-26: 25; 2025-10-27: 25; 2025-10-28: 25; 2025-10-29: 25; 2025-10-30: 25; 2025-10-31: 25; 2025-11-01: 25; 2025-11-02: 25; 2025-11-03: 25; 2025-11-04: 25; 2025-11-05: 25; 2025-11-06: 25; 2025-11-07: 25; 2025-11-08: 25; 2025-11-09: 25; 2025-11-10: 30; 2025-11-11: 30; 2025-11-12: 30; 2025-11-13: 30; 2025-11-14: 30; 2025-11-15: 30; 2025-11-16: 30; 2025-11-17: 30; 2025-11-18: 30; 2025-11-19: 30; 2025-11-20: 30; 2025-11-21: 30; 2025-11-22: 30; 2025-11-23: 30; 2025-11-24: 30; 2025-11-25: 30; 2025-11-26: 30; 2025-11-27: 30; 2025-11-28: 30; 2025-11-29: 25; 2025-11-30: 25; 2025-12-01: 25; 2025-12-02: 25; 2025-12-03: 25; 2025-12-04: 25; 2025-12-05: 25; 2025-12-06: 25; 2025-12-07: 25; 2025-12-08: 25; 2025-12-09: 25; 2025-12-10: 25; 2025-12-11: 25; 2025-12-12: 25; 2025-12-13: 25; 2025-12-14: 25; 2025-12-15: 25; 2025-12-16: 25; 2025-12-17: 25; 2025-12-18: 25; 2025-12-19: 25; 2025-12-20: 25; 2025-12-21: 25; 2025-12-22: 25; 2025-12-23: 25; 2025-12-24: 30; 2025-12-25: 30; 2025-12-26: 30; 2025-12-27: 30; 2025-12-28: 30; 2025-12-29: 30; 2025-12-30: 30; 2025-12-31: 30; 2026-01-01: 30; 2026-01-02: 30; 2026-01-03: 30; 2026-01-04: 30; 2026-01-05: 30; 2026-01-06: 30; 2026-01-07: 30; 2026-01-08: 30; 2026-01-09: 30; 2026-01-10: 30; 2026-01-11: 30; 2026-01-12: 30; 2026-01-13: 30; 2026-01-14: 30; 2026-01-15: 30; 2026-01-16: 30; 2026-01-17: 30; 2026-01-18: 30; 2026-01-19: 38; 2026-01-20: 38; 2026-01-21: 38; 2026-01-22: 38; 2026-01-23: 38; 2026-01-24: 38; 2026-01-25: 38; 2026-01-26: 38; 2026-01-27: 38; 2026-01-28: 38; 2026-01-29: 38; 2026-01-30: 38; 2026-01-31: 38; 2026-02-01: 38; 2026-02-02: 38; 2026-02-03: 38; 2026-02-04: 40; 2026-02-05: 40; 2026-02-06: 40; 2026-02-07: 40; 2026-02-08: 40; 2026-02-09: 40; 2026-02-10: 40; 2026-02-11: 40; 2026-02-12: 40; 2026-02-13: 40; 2026-02-14: 40; 2026-02-15: 40; 2026-02-16: 40; 2026-02-17: 40; 2026-02-18: 40; 2026-02-19: 40; 2026-02-20: 40; 2026-02-21: 40; 2026-02-22: 40; 2026-02-23: 40; 2026-02-24: 40; 2026-02-25: 40; 2026-02-26: 40; 2026-02-27: 40
38 | M/s Partibha (USS Electrical) | Service | USS | Manpower Details (P) | 2025-10-10: 10; 2025-10-11: 10; 2025-10-12: 10; 2025-10-13: 10; 2025-10-14: 10; 2025-10-15: 10; 2025-10-16: 10; 2025-10-17: 10; 2025-10-18: 15; 2025-10-19: 15; 2025-10-20: 15; 2025-10-21: 15; 2025-10-22: 15; 2025-10-23: 15; 2025-10-24: 15; 2025-10-25: 15; 2025-10-26: 15; 2025-10-27: 15; 2025-10-28: 15; 2025-10-29: 15; 2025-10-30: 15; 2025-10-31: 15; 2025-11-01: 15; 2025-11-02: 15; 2025-11-03: 15; 2025-11-04: 15; 2025-11-05: 15; 2025-11-06: 15; 2025-11-07: 15; 2025-11-08: 15; 2025-11-09: 15; 2025-11-10: 15; 2025-11-11: 15; 2025-11-12: 15; 2025-11-13: 15; 2025-11-14: 15; 2025-11-15: 15; 2025-11-16: 15; 2025-11-17: 15; 2025-11-18: 15; 2025-11-19: 15; 2025-11-20: 15; 2025-11-21: 15; 2025-11-22: 15; 2025-11-23: 15; 2025-11-24: 15; 2025-11-25: 15; 2025-11-26: 15; 2025-11-27: 15; 2025-11-28: 15; 2025-11-29: 15; 2025-11-30: 15; 2025-12-01: 15; 2025-12-02: 15; 2025-12-03: 15; 2025-12-04: 15; 2025-12-05: 15; 2025-12-06: 15; 2025-12-07: 15; 2025-12-08: 15; 2025-12-09: 15; 2025-12-10: 15; 2025-12-11: 15; 2025-12-12: 15; 2025-12-13: 15; 2025-12-14: 15; 2025-12-15: 15; 2025-12-16: 15; 2025-12-17: 15; 2025-12-18: 15; 2025-12-19: 15; 2025-12-20: 15; 2025-12-21: 15; 2025-12-22: 15; 2025-12-23: 15; 2025-12-24: 15; 2025-12-25: 15; 2025-12-26: 15; 2025-12-27: 15; 2025-12-28: 15; 2025-12-29: 15; 2025-12-30: 15; 2025-12-31: 15; 2026-01-01: 15; 2026-01-02: 15; 2026-01-03: 15; 2026-01-04: 15; 2026-01-05: 15; 2026-01-06: 15; 2026-01-07: 15; 2026-01-08: 15; 2026-01-09: 15; 2026-01-10: 15; 2026-01-11: 15; 2026-01-12: 15; 2026-01-13: 15; 2026-01-14: 15; 2026-01-15: 15; 2026-01-16: 15; 2026-01-17: 15; 2026-01-18: 15; 2026-01-19: 15; 2026-01-20: 15; 2026-01-21: 15; 2026-01-22: 15; 2026-01-23: 15; 2026-01-24: 15; 2026-01-25: 15; 2026-01-26: 15; 2026-01-27: 15; 2026-01-28: 15; 2026-01-29: 15; 2026-01-30: 15; 2026-01-31: 15; 2026-02-01: 15; 2026-02-02: 15; 2026-02-03: 15; 2026-02-04: 15; 2026-02-05: 15; 2026-02-06: 15; 2026-02-07: 15; 2026-02-08: 15; 2026-02-09: 15; 2026-02-10: 15; 2026-02-11: 15; 2026-02-12: 15; 2026-02-13: 15; 2026-02-14: 15; 2026-02-15: 15; 2026-02-16: 15; 2026-02-17: 15; 2026-02-18: 15; 2026-02-19: 15; 2026-02-20: 15; 2026-02-21: 15; 2026-02-22: 15; 2026-02-23: 15; 2026-02-24: 15; 2026-02-25: 15; 2026-02-26: 15; 2026-02-27: 15
|  |  |  | Manpower Details (A) | 2025-10-10: 8; 2025-10-11: 8; 2025-10-12: 8; 2025-10-13: 8; 2025-10-14: 8; 2025-10-15: 8; 2025-10-16: 8; 2025-10-17: 8; 2025-10-18: 15; 2025-10-19: 15; 2025-10-20: 15; 2025-10-21: 15; 2025-10-22: 15; 2025-10-23: 15; 2025-10-24: 15; 2025-10-25: 15; 2025-10-26: 15; 2025-10-27: 15; 2025-10-28: 15; 2025-10-29: 15; 2025-10-30: 15; 2025-10-31: 15; 2025-11-01: 15; 2025-11-02: 15; 2025-11-03: 15; 2025-11-04: 10; 2025-11-05: 10; 2025-11-06: 10; 2025-11-07: 10; 2025-11-08: 10; 2025-11-09: 10; 2025-11-10: 7; 2025-11-11: 7; 2025-11-12: 7; 2025-11-13: 7; 2025-11-14: 7; 2025-11-15: 7; 2025-11-16: 7; 2025-11-17: 7; 2025-11-18: 7; 2025-11-19: 7; 2025-11-20: 7; 2025-11-21: 7; 2025-11-22: 7; 2025-11-23: 7; 2025-11-24: 7; 2025-11-25: 7; 2025-11-26: 7; 2025-11-27: 7; 2025-11-28: 7; 2025-11-29: 10; 2025-11-30: 10; 2025-12-01: 10; 2025-12-02: 10; 2025-12-03: 10; 2025-12-04: 10; 2025-12-05: 10; 2025-12-06: 10; 2025-12-07: 10; 2025-12-08: 10; 2025-12-09: 10; 2025-12-10: 10; 2025-12-11: 10; 2025-12-12: 10; 2025-12-13: 10; 2025-12-14: 10; 2025-12-15: 10; 2025-12-16: 10; 2025-12-17: 10; 2025-12-18: 10; 2025-12-19: 10; 2025-12-20: 10; 2025-12-21: 10; 2025-12-22: 10; 2025-12-23: 10; 2025-12-24: 10; 2025-12-25: 10; 2025-12-26: 10; 2025-12-27: 10; 2025-12-28: 10; 2025-12-29: 10; 2025-12-30: 10; 2025-12-31: 10; 2026-01-01: 10; 2026-01-02: 10; 2026-01-03: 10; 2026-01-04: 10; 2026-01-05: 10; 2026-01-06: 10; 2026-01-07: 10; 2026-01-08: 10; 2026-01-09: 10; 2026-01-10: 10; 2026-01-11: 10; 2026-01-12: 10; 2026-01-13: 10; 2026-01-14: 10; 2026-01-15: 10; 2026-01-16: 10; 2026-01-17: 10; 2026-01-18: 10; 2026-01-19: 8; 2026-01-20: 8; 2026-01-21: 8; 2026-01-22: 8; 2026-01-23: 8; 2026-01-24: 8; 2026-01-25: 8; 2026-01-26: 8; 2026-01-27: 8; 2026-01-28: 8; 2026-01-29: 8; 2026-01-30: 8; 2026-01-31: 8; 2026-02-01: 8; 2026-02-02: 8; 2026-02-03: 8; 2026-02-04: 6; 2026-02-05: 6; 2026-02-06: 6; 2026-02-07: 6; 2026-02-08: 6; 2026-02-09: 6; 2026-02-10: 6; 2026-02-11: 6; 2026-02-12: 6; 2026-02-13: 6; 2026-02-14: 6; 2026-02-15: 6; 2026-02-16: 6; 2026-02-17: 6; 2026-02-18: 6; 2026-02-19: 6; 2026-02-20: 6; 2026-02-21: 6; 2026-02-22: 6; 2026-02-23: 6; 2026-02-24: 6; 2026-02-25: 6; 2026-02-26: 6; 2026-02-27: 6
39 | M/s GP Projects (CranePad) | Service | CranePad | Manpower Details (P) | [160 empty] | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
|  |  |  | Manpower Details (A) | [160 empty] | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
40 | M/s Harsh Earthmovers (CranePad) | Service | CranePad | Manpower Details (P) | [160 empty] | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
|  |  |  | Manpower Details (A) | [160 empty] | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
41 | M/s Odhav (CranePad) | Service | CranePad | Manpower Details (P) | [160 empty] | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
|  |  |  | Manpower Details (A) | [160 empty] | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
42 | M/s S S Jadeja (CranePad) | Service | CranePad | Manpower Details (P) | [160 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
|  |  |  | Manpower Details (A) | [160 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
43 | M/s Varudi (CranePad) | Service | CranePad | Manpower Details (P) | [160 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
|  |  |  | Manpower Details (A) | [160 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
44 | M/s shethia ( WTG Erection) | Service | Crane Package | Manpower Details (P) | 2025-10-10: 60; 2025-10-11: 60; 2025-10-12: 60; 2025-10-13: 60; 2025-10-14: 60; 2025-10-15: 60; 2025-10-16: 60; 2025-10-17: 60; 2025-10-18: 60; 2025-10-19: 60; 2025-10-20: 60; 2025-10-21: 60; 2025-10-22: 60; 2025-10-23: 60; 2025-10-24: 60; 2025-10-25: 60; 2025-10-26: 60; 2025-10-27: 60; 2025-10-28: 60; 2025-10-29: 60; 2025-10-30: 60; 2025-10-31: 60; 2025-11-01: 60; 2025-11-02: 60; 2025-11-03: 60; 2025-11-04: 60; 2025-11-05: 60; 2025-11-06: 60; 2025-11-07: 60; 2025-11-08: 60; 2025-11-09: 60; 2025-11-10: 60; 2025-11-11: 60; 2025-11-12: 60; 2025-11-13: 60; 2025-11-14: 60; 2025-11-15: 60; 2025-11-16: 60; 2025-11-17: 60; 2025-11-18: 60; 2025-11-19: 60; 2025-11-20: 60; 2025-11-21: 60; 2025-11-22: 60; 2025-11-23: 60; 2025-11-24: 60; 2025-11-25: 60; 2025-11-26: 60; 2025-11-27: 60; 2025-11-28: 60; 2025-11-29: 60; 2025-11-30: 60; 2025-12-01: 60; 2025-12-02: 60; 2025-12-03: 60; 2025-12-04: 60; 2025-12-05: 60; 2025-12-06: 60; 2025-12-07: 60; 2025-12-08: 60; 2025-12-09: 60; 2025-12-10: 60; 2025-12-11: 60; 2025-12-12: 60; 2025-12-13: 60; 2025-12-14: 60; 2025-12-15: 60; 2025-12-16: 60; 2025-12-17: 60; 2025-12-18: 60; 2025-12-19: 60; 2025-12-20: 60; 2025-12-21: 60; 2025-12-22: 60; 2025-12-23: 60; 2025-12-24: 60; 2025-12-25: 60; 2025-12-26: 60; 2025-12-27: 60; 2025-12-28: 60; 2025-12-29: 60; 2025-12-30: 60; 2025-12-31: 60; 2026-01-01: 60; 2026-01-02: 60; 2026-01-03: 60; 2026-01-04: 60; 2026-01-05: 60; 2026-01-06: 60; 2026-01-07: 60; 2026-01-08: 60; 2026-01-09: 60; 2026-01-10: 60; 2026-01-11: 60; 2026-01-12: 60; 2026-01-13: 60; 2026-01-14: 60; 2026-01-15: 60; 2026-01-16: 60; 2026-01-17: 60; 2026-01-18: 60; 2026-01-19: 60; 2026-01-20: 60; 2026-01-21: 60; 2026-01-22: 60; 2026-01-23: 60; 2026-01-24: 60; 2026-01-25: 60; 2026-01-26: 60; 2026-01-27: 60; 2026-01-28: 60; 2026-01-29: 60; 2026-01-30: 60; 2026-01-31: 60; 2026-02-01: 60; 2026-02-02: 60; 2026-02-03: 60; 2026-02-04: 60; 2026-02-05: 60; 2026-02-06: 60; 2026-02-07: 60; 2026-02-08: 60; 2026-02-09: 60; 2026-02-10: 60; 2026-02-11: 60; 2026-02-12: 60; 2026-02-13: 60; 2026-02-14: 60; 2026-02-15: 60; 2026-02-16: 60; 2026-02-17: 60; 2026-02-18: 60; 2026-02-19: 60; 2026-02-20: 60; 2026-02-21: 60; 2026-02-22: 60; 2026-02-23: 60; 2026-02-24: 60; 2026-02-25: 60; 2026-02-26: 60; 2026-02-27: 60
|  |  |  | Manpower Details (A) | 2025-10-10: 56; 2025-10-11: 56; 2025-10-12: 56; 2025-10-13: 56; 2025-10-14: 56; 2025-10-15: 56; 2025-10-16: 56; 2025-10-17: 56; 2025-10-18: 56; 2025-10-19: 56; 2025-10-20: 56; 2025-10-21: 56; 2025-10-22: 56; 2025-10-23: 56; 2025-10-24: 56; 2025-10-25: 56; 2025-10-26: 56; 2025-10-27: 56; 2025-10-28: 56; 2025-10-29: 56; 2025-10-30: 56; 2025-10-31: 56; 2025-11-01: 56; 2025-11-02: 56; 2025-11-03: 56; 2025-11-04: 44; 2025-11-05: 44; 2025-11-06: 44; 2025-11-07: 44; 2025-11-08: 44; 2025-11-09: 44; 2025-11-10: 44; 2025-11-11: 44; 2025-11-12: 44; 2025-11-13: 44; 2025-11-14: 44; 2025-11-15: 44; 2025-11-16: 44; 2025-11-17: 44; 2025-11-18: 44; 2025-11-19: 44; 2025-11-20: 44; 2025-11-21: 44; 2025-11-22: 44; 2025-11-23: 44; 2025-11-24: 56; 2025-11-25: 56; 2025-11-26: 56; 2025-11-27: 56; 2025-11-28: 56; 2025-11-29: 56; 2025-11-30: 56; 2025-12-01: 56; 2025-12-02: 56; 2025-12-03: 56; 2025-12-04: 56; 2025-12-05: 56; 2025-12-06: 56; 2025-12-07: 56; 2025-12-08: 56; 2025-12-09: 56; 2025-12-10: 56; 2025-12-11: 56; 2025-12-12: 56; 2025-12-13: 56; 2025-12-14: 56; 2025-12-15: 56; 2025-12-16: 56; 2025-12-17: 56; 2025-12-18: 56; 2025-12-19: 56; 2025-12-20: 56; 2025-12-21: 56; 2025-12-22: 56; 2025-12-23: 56; 2025-12-24: 56; 2025-12-25: 56; 2025-12-26: 56; 2025-12-27: 56; 2025-12-28: 56; 2025-12-29: 56; 2025-12-30: 56; 2025-12-31: 56; 2026-01-01: 56; 2026-01-02: 56; 2026-01-03: 56; 2026-01-04: 56; 2026-01-05: 56; 2026-01-06: 56; 2026-01-07: 56; 2026-01-08: 56; 2026-01-09: 56; 2026-01-10: 56; 2026-01-11: 56; 2026-01-12: 56; 2026-01-13: 56; 2026-01-14: 56; 2026-01-15: 56; 2026-01-16: 56; 2026-01-17: 56; 2026-01-18: 56; 2026-01-19: 56; 2026-01-20: 56; 2026-01-21: 56; 2026-01-22: 56; 2026-01-23: 56; 2026-01-24: 56; 2026-01-25: 56; 2026-01-26: 56; 2026-01-27: 56; 2026-01-28: 56; 2026-01-29: 56; 2026-01-30: 56; 2026-01-31: 56; 2026-02-01: 56; 2026-02-02: 56; 2026-02-03: 56; 2026-02-04: 56; 2026-02-05: 56; 2026-02-06: 56; 2026-02-07: 56; 2026-02-08: 56; 2026-02-09: 56; 2026-02-10: 56; 2026-02-11: 56; 2026-02-12: 56; 2026-02-13: 56; 2026-02-14: 56; 2026-02-15: 56; 2026-02-16: 56; 2026-02-17: 56; 2026-02-18: 56; 2026-02-19: 56; 2026-02-20: 56; 2026-02-21: 56; 2026-02-22: 56; 2026-02-23: 56; 2026-02-24: 56; 2026-02-25: 56; 2026-02-26: 56; 2026-02-27: 56
45 | M/s Barkat ( WTG Erection) | Service | Crane Package | Manpower Details (P) | 2025-10-10: 30; 2025-10-11: 30; 2025-10-12: 30; 2025-10-13: 30; 2025-10-14: 30; 2025-10-15: 30; 2025-10-16: 30; 2025-10-17: 30; 2025-10-18: 30; 2025-10-19: 30; 2025-10-20: 30; 2025-10-21: 30; 2025-10-22: 30; 2025-10-23: 30; 2025-10-24: 30; 2025-10-25: 30; 2025-10-26: 30; 2025-10-27: 30; 2025-10-28: 30; 2025-10-29: 30; 2025-10-30: 30; 2025-10-31: 30; 2025-11-01: 30; 2025-11-02: 30; 2025-11-03: 30; 2025-11-04: 30; 2025-11-05: 30; 2025-11-06: 30; 2025-11-07: 30; 2025-11-08: 30; 2025-11-09: 30; 2025-11-10: 30; 2025-11-11: 30; 2025-11-12: 30; 2025-11-13: 30; 2025-11-14: 30; 2025-11-15: 30; 2025-11-16: 30; 2025-11-17: 30; 2025-11-18: 30; 2025-11-19: 30; 2025-11-20: 30; 2025-11-21: 30; 2025-11-22: 30; 2025-11-23: 30; 2025-11-24: 30; 2025-11-25: 30; 2025-11-26: 30; 2025-11-27: 30; 2025-11-28: 30; 2025-11-29: 30; 2025-11-30: 30; 2025-12-01: 30; 2025-12-02: 30; 2025-12-03: 30; 2025-12-04: 30; 2025-12-05: 30; 2025-12-06: 30; 2025-12-07: 30; 2025-12-08: 30; 2025-12-09: 30; 2025-12-10: 30; 2025-12-11: 30; 2025-12-12: 30; 2025-12-13: 30; 2025-12-14: 30; 2025-12-15: 30; 2025-12-16: 30; 2025-12-17: 30; 2025-12-18: 30; 2025-12-19: 30; 2025-12-20: 30; 2025-12-21: 30; 2025-12-22: 30; 2025-12-23: 30; 2025-12-24: 30; 2025-12-25: 30; 2025-12-26: 30; 2025-12-27: 30; 2025-12-28: 30; 2025-12-29: 30; 2025-12-30: 30; 2025-12-31: 30; 2026-01-01: 30; 2026-01-02: 30; 2026-01-03: 30; 2026-01-04: 30; 2026-01-05: 30; 2026-01-06: 30; 2026-01-07: 30; 2026-01-08: 30; 2026-01-09: 30; 2026-01-10: 30; 2026-01-11: 30; 2026-01-12: 30; 2026-01-13: 30; 2026-01-14: 30; 2026-01-15: 30; 2026-01-16: 30; 2026-01-17: 30; 2026-01-18: 30; 2026-01-19: 30; 2026-01-20: 30; 2026-01-21: 30; 2026-01-22: 30; 2026-01-23: 30; 2026-01-24: 30; 2026-01-25: 30; 2026-01-26: 30; 2026-01-27: 30; 2026-01-28: 30; 2026-01-29: 30; 2026-01-30: 30; 2026-01-31: 30; 2026-02-01: 30; 2026-02-02: 30; 2026-02-03: 30; 2026-02-04: 30; 2026-02-05: 30; 2026-02-06: 30; 2026-02-07: 30; 2026-02-08: 30; 2026-02-09: 30; 2026-02-10: 30; 2026-02-11: 30; 2026-02-12: 30; 2026-02-13: 30; 2026-02-14: 30; 2026-02-15: 30; 2026-02-16: 30; 2026-02-17: 30; 2026-02-18: 30; 2026-02-19: 30; 2026-02-20: 30; 2026-02-21: 30; 2026-02-22: 30; 2026-02-23: 30; 2026-02-24: 30; 2026-02-25: 30; 2026-02-26: 30; 2026-02-27: 30
|  |  |  | Manpower Details (A) | 2025-10-10: 26; 2025-10-11: 26; 2025-10-12: 26; 2025-10-13: 26; 2025-10-14: 26; 2025-10-15: 26; 2025-10-16: 26; 2025-10-17: 26; 2025-10-18: 26; 2025-10-19: 26; 2025-10-20: 26; 2025-10-21: 26; 2025-10-22: 26; 2025-10-23: 26; 2025-10-24: 26; 2025-10-25: 26; 2025-10-26: 26; 2025-10-27: 26; 2025-10-28: 26; 2025-10-29: 26; 2025-10-30: 26; 2025-10-31: 26; 2025-11-01: 26; 2025-11-02: 26; 2025-11-03: 26; 2025-11-04: 30; 2025-11-05: 30; 2025-11-06: 30; 2025-11-07: 30; 2025-11-08: 30; 2025-11-09: 30; 2025-11-10: 30; 2025-11-11: 30; 2025-11-12: 30; 2025-11-13: 30; 2025-11-14: 30; 2025-11-15: 30; 2025-11-16: 30; 2025-11-17: 30; 2025-11-18: 30; 2025-11-19: 30; 2025-11-20: 30; 2025-11-21: 30; 2025-11-22: 30; 2025-11-23: 30; 2025-11-24: 30; 2025-11-25: 30; 2025-11-26: 30; 2025-11-27: 30; 2025-11-28: 30; 2025-11-29: 30; 2025-11-30: 30; 2025-12-01: 30; 2025-12-02: 30; 2025-12-03: 30; 2025-12-04: 30; 2025-12-05: 30; 2025-12-06: 30; 2025-12-07: 30; 2025-12-08: 30; 2025-12-09: 30; 2025-12-10: 30; 2025-12-11: 30; 2025-12-12: 30; 2025-12-13: 30; 2025-12-14: 30; 2025-12-15: 30; 2025-12-16: 30; 2025-12-17: 30; 2025-12-18: 30; 2025-12-19: 30; 2025-12-20: 30; 2025-12-21: 30; 2025-12-22: 30; 2025-12-23: 30; 2025-12-24: 30; 2025-12-25: 30; 2025-12-26: 30; 2025-12-27: 30; 2025-12-28: 30; 2025-12-29: 30; 2025-12-30: 30; 2025-12-31: 30; 2026-01-01: 30; 2026-01-02: 30; 2026-01-03: 30; 2026-01-04: 30; 2026-01-05: 30; 2026-01-06: 30; 2026-01-07: 30; 2026-01-08: 30; 2026-01-09: 30; 2026-01-10: 30; 2026-01-11: 30; 2026-01-12: 30; 2026-01-13: 30; 2026-01-14: 30; 2026-01-15: 30; 2026-01-16: 30; 2026-01-17: 30; 2026-01-18: 30; 2026-01-19: 30; 2026-01-20: 30; 2026-01-21: 30; 2026-01-22: 30; 2026-01-23: 30; 2026-01-24: 30; 2026-01-25: 30; 2026-01-26: 30; 2026-01-27: 30; 2026-01-28: 30; 2026-01-29: 30; 2026-01-30: 30; 2026-01-31: 30; 2026-02-01: 30; 2026-02-02: 30; 2026-02-03: 30; 2026-02-04: 30; 2026-02-05: 30; 2026-02-06: 30; 2026-02-07: 30; 2026-02-08: 30; 2026-02-09: 30; 2026-02-10: 30; 2026-02-11: 30; 2026-02-12: 30; 2026-02-13: 30; 2026-02-14: 30; 2026-02-15: 30; 2026-02-16: 30; 2026-02-17: 30; 2026-02-18: 30; 2026-02-19: 30; 2026-02-20: 30; 2026-02-21: 30; 2026-02-22: 30; 2026-02-23: 30; 2026-02-24: 30; 2026-02-25: 30; 2026-02-26: 30; 2026-02-27: 30
46 | M/s D&D Enterprise ( WTG Erection) | Service | Crane Package | Manpower Details (P) | 2025-10-10: 110; 2025-10-11: 110; 2025-10-12: 110; 2025-10-13: 110; 2025-10-14: 110; 2025-10-15: 110; 2025-10-16: 110; 2025-10-17: 110; 2025-10-18: 110; 2025-10-19: 110; 2025-10-20: 110; 2025-10-21: 110; 2025-10-22: 110; 2025-10-23: 110; 2025-10-24: 110; 2025-10-25: 110; 2025-10-26: 110; 2025-10-27: 110; 2025-10-28: 110; 2025-10-29: 110; 2025-10-30: 110; 2025-10-31: 110; 2025-11-01: 110; 2025-11-02: 110; 2025-11-03: 110; 2025-11-04: 110; 2025-11-05: 110; 2025-11-06: 110; 2025-11-07: 110; 2025-11-08: 110; 2025-11-09: 110; 2025-11-10: 110; 2025-11-11: 110; 2025-11-12: 110; 2025-11-13: 110; 2025-11-14: 110; 2025-11-15: 110; 2025-11-16: 110; 2025-11-17: 110; 2025-11-18: 110; 2025-11-19: 110; 2025-11-20: 110; 2025-11-21: 110; 2025-11-22: 110; 2025-11-23: 110; 2025-11-24: 110; 2025-11-25: 110; 2025-11-26: 110; 2025-11-27: 110; 2025-11-28: 110; 2025-11-29: 110; 2025-11-30: 110; 2025-12-01: 110; 2025-12-02: 110; 2025-12-03: 110; 2025-12-04: 110; 2025-12-05: 110; 2025-12-06: 110; 2025-12-07: 110; 2025-12-08: 110; 2025-12-09: 110; 2025-12-10: 110; 2025-12-11: 110; 2025-12-12: 110; 2025-12-13: 110; 2025-12-14: 110; 2025-12-15: 110; 2025-12-16: 110; 2025-12-17: 110; 2025-12-18: 110; 2025-12-19: 110; 2025-12-20: 110; 2025-12-21: 110; 2025-12-22: 110; 2025-12-23: 110; 2025-12-24: 110; 2025-12-25: 110; 2025-12-26: 110; 2025-12-27: 110; 2025-12-28: 110; 2025-12-29: 110; 2025-12-30: 110; 2025-12-31: 110; 2026-01-01: 110; 2026-01-02: 110; 2026-01-03: 110; 2026-01-04: 110; 2026-01-05: 110; 2026-01-06: 110; 2026-01-07: 110; 2026-01-08: 110; 2026-01-09: 110; 2026-01-10: 110; 2026-01-11: 110; 2026-01-12: 110; 2026-01-13: 110; 2026-01-14: 110; 2026-01-15: 110; 2026-01-16: 110; 2026-01-17: 110; 2026-01-18: 110; 2026-01-19: 110; 2026-01-20: 110; 2026-01-21: 110; 2026-01-22: 110; 2026-01-23: 110; 2026-01-24: 110; 2026-01-25: 110; 2026-01-26: 110; 2026-01-27: 110; 2026-01-28: 110; 2026-01-29: 110; 2026-01-30: 110; 2026-01-31: 110; 2026-02-01: 110; 2026-02-02: 110; 2026-02-03: 110; 2026-02-04: 110; 2026-02-05: 110; 2026-02-06: 110; 2026-02-07: 110; 2026-02-08: 110; 2026-02-09: 110; 2026-02-10: 110; 2026-02-11: 110; 2026-02-12: 110; 2026-02-13: 110; 2026-02-14: 110; 2026-02-15: 110; 2026-02-16: 110; 2026-02-17: 110; 2026-02-18: 110; 2026-02-19: 110; 2026-02-20: 110; 2026-02-21: 110; 2026-02-22: 110; 2026-02-23: 110; 2026-02-24: 110; 2026-02-25: 110; 2026-02-26: 110; 2026-02-27: 110
|  |  |  | Manpower Details (A) | 2025-10-10: 108; 2025-10-11: 108; 2025-10-12: 108; 2025-10-13: 108; 2025-10-14: 108; 2025-10-15: 108; 2025-10-16: 108; 2025-10-17: 108; 2025-10-18: 108; 2025-10-19: 108; 2025-10-20: 108; 2025-10-21: 108; 2025-10-22: 108; 2025-10-23: 108; 2025-10-24: 108; 2025-10-25: 108; 2025-10-26: 108; 2025-10-27: 108; 2025-10-28: 108; 2025-10-29: 108; 2025-10-30: 108; 2025-10-31: 108; 2025-11-01: 108; 2025-11-02: 108; 2025-11-03: 108; 2025-11-04: 79; 2025-11-05: 79; 2025-11-06: 79; 2025-11-07: 79; 2025-11-08: 79; 2025-11-09: 79; 2025-11-10: 79; 2025-11-11: 79; 2025-11-12: 79; 2025-11-13: 79; 2025-11-14: 79; 2025-11-15: 79; 2025-11-16: 79; 2025-11-17: 79; 2025-11-18: 79; 2025-11-19: 79; 2025-11-20: 79; 2025-11-21: 79; 2025-11-22: 79; 2025-11-23: 79; 2025-11-24: 108; 2025-11-25: 108; 2025-11-26: 108; 2025-11-27: 108; 2025-11-28: 108; 2025-11-29: 108; 2025-11-30: 108; 2025-12-01: 108; 2025-12-02: 108; 2025-12-03: 108; 2025-12-04: 108; 2025-12-05: 108; 2025-12-06: 108; 2025-12-07: 108; 2025-12-08: 108; 2025-12-09: 108; 2025-12-10: 108; 2025-12-11: 108; 2025-12-12: 108; 2025-12-13: 108; 2025-12-14: 108; 2025-12-15: 108; 2025-12-16: 108; 2025-12-17: 108; 2025-12-18: 108; 2025-12-19: 108; 2025-12-20: 108; 2025-12-21: 108; 2025-12-22: 108; 2025-12-23: 108; 2025-12-24: 108; 2025-12-25: 108; 2025-12-26: 108; 2025-12-27: 108; 2025-12-28: 108; 2025-12-29: 108; 2025-12-30: 108; 2025-12-31: 108; 2026-01-01: 108; 2026-01-02: 108; 2026-01-03: 108; 2026-01-04: 108; 2026-01-05: 108; 2026-01-06: 108; 2026-01-07: 108; 2026-01-08: 108; 2026-01-09: 108; 2026-01-10: 108; 2026-01-11: 108; 2026-01-12: 108; 2026-01-13: 108; 2026-01-14: 108; 2026-01-15: 108; 2026-01-16: 108; 2026-01-17: 108; 2026-01-18: 108; 2026-01-19: 108; 2026-01-20: 108; 2026-01-21: 108; 2026-01-22: 108; 2026-01-23: 108; 2026-01-24: 108; 2026-01-25: 108; 2026-01-26: 108; 2026-01-27: 108; 2026-01-28: 108; 2026-01-29: 108; 2026-01-30: 108; 2026-01-31: 108; 2026-02-01: 108; 2026-02-02: 108; 2026-02-03: 108; 2026-02-04: 108; 2026-02-05: 108; 2026-02-06: 108; 2026-02-07: 108; 2026-02-08: 108; 2026-02-09: 108; 2026-02-10: 108; 2026-02-11: 108; 2026-02-12: 108; 2026-02-13: 108; 2026-02-14: 108; 2026-02-15: 108; 2026-02-16: 108; 2026-02-17: 108; 2026-02-18: 108; 2026-02-19: 108; 2026-02-20: 108; 2026-02-21: 108; 2026-02-22: 108; 2026-02-23: 108; 2026-02-24: 108; 2026-02-25: 108; 2026-02-26: 108; 2026-02-27: 108
47 | M/s Ambika ( WTG Erection) | Service | Crane Package | Manpower Details (P) | 2025-10-10: 30; 2025-10-11: 30; 2025-10-12: 30; 2025-10-13: 30; 2025-10-14: 30; 2025-10-15: 30; 2025-10-16: 30; 2025-10-17: 30; 2025-10-18: 30; 2025-10-19: 30; 2025-10-20: 30; 2025-10-21: 30; 2025-10-22: 30; 2025-10-23: 30; 2025-10-24: 30; 2025-10-25: 30; 2025-10-26: 30; 2025-10-27: 30; 2025-10-28: 30; 2025-10-29: 30; 2025-10-30: 30; 2025-10-31: 30; 2025-11-01: 30; 2025-11-02: 30; 2025-11-03: 30; 2025-11-04: 30; 2025-11-05: 30; 2025-11-06: 30; 2025-11-07: 30; 2025-11-08: 30; 2025-11-09: 30; 2025-11-10: 30; 2025-11-11: 30; 2025-11-12: 30; 2025-11-13: 30; 2025-11-14: 30; 2025-11-15: 30; 2025-11-16: 30; 2025-11-17: 30; 2025-11-18: 30; 2025-11-19: 30; 2025-11-20: 30; 2025-11-21: 30; 2025-11-22: 30; 2025-11-23: 30; 2025-11-24: 30; 2025-11-25: 30; 2025-11-26: 30; 2025-11-27: 30; 2025-11-28: 30; 2025-11-29: 30; 2025-11-30: 30; 2025-12-01: 30; 2025-12-02: 30; 2025-12-03: 30; 2025-12-04: 30; 2025-12-05: 30; 2025-12-06: 30; 2025-12-07: 30; 2025-12-08: 30; 2025-12-09: 30; 2025-12-10: 30; 2025-12-11: 30; 2025-12-12: 30; 2025-12-13: 30; 2025-12-14: 30; 2025-12-15: 30; 2025-12-16: 30; 2025-12-17: 30; 2025-12-18: 30; 2025-12-19: 30; 2025-12-20: 30; 2025-12-21: 30; 2025-12-22: 30; 2025-12-23: 30; 2025-12-24: 30; 2025-12-25: 30; 2025-12-26: 30; 2025-12-27: 30; 2025-12-28: 30; 2025-12-29: 30; 2025-12-30: 30; 2025-12-31: 30; 2026-01-01: 30; 2026-01-02: 30; 2026-01-03: 30; 2026-01-04: 30; 2026-01-05: 30; 2026-01-06: 30; 2026-01-07: 30; 2026-01-08: 30; 2026-01-09: 30; 2026-01-10: 30; 2026-01-11: 30; 2026-01-12: 30; 2026-01-13: 30; 2026-01-14: 30; 2026-01-15: 30; 2026-01-16: 30; 2026-01-17: 30; 2026-01-18: 30; 2026-01-19: 30; 2026-01-20: 30; 2026-01-21: 30; 2026-01-22: 30; 2026-01-23: 30; 2026-01-24: 30; 2026-01-25: 30; 2026-01-26: 30; 2026-01-27: 30; 2026-01-28: 30; 2026-01-29: 30; 2026-01-30: 30; 2026-01-31: 30; 2026-02-01: 30; 2026-02-02: 30; 2026-02-03: 30; 2026-02-04: 30; 2026-02-05: 30; 2026-02-06: 30; 2026-02-07: 30; 2026-02-08: 30; 2026-02-09: 30; 2026-02-10: 30; 2026-02-11: 30; 2026-02-12: 30; 2026-02-13: 30; 2026-02-14: 30; 2026-02-15: 30; 2026-02-16: 30; 2026-02-17: 30; 2026-02-18: 30; 2026-02-19: 30; 2026-02-20: 30; 2026-02-21: 30; 2026-02-22: 30; 2026-02-23: 30; 2026-02-24: 30; 2026-02-25: 30; 2026-02-26: 30; 2026-02-27: 30
|  |  |  | Manpower Details (A) | 2025-10-10: 28; 2025-10-11: 28; 2025-10-12: 28; 2025-10-13: 28; 2025-10-14: 28; 2025-10-15: 28; 2025-10-16: 28; 2025-10-17: 28; 2025-10-18: 28; 2025-10-19: 28; 2025-10-20: 28; 2025-10-21: 28; 2025-10-22: 28; 2025-10-23: 28; 2025-10-24: 28; 2025-10-25: 28; 2025-10-26: 28; 2025-10-27: 28; 2025-10-28: 28; 2025-10-29: 28; 2025-10-30: 28; 2025-10-31: 28; 2025-11-01: 28; 2025-11-02: 28; 2025-11-03: 28; 2025-11-04: 21; 2025-11-05: 21; 2025-11-06: 21; 2025-11-07: 21; 2025-11-08: 21; 2025-11-09: 21; 2025-11-10: 21; 2025-11-11: 21; 2025-11-12: 21; 2025-11-13: 21; 2025-11-14: 21; 2025-11-15: 21; 2025-11-16: 21; 2025-11-17: 21; 2025-11-18: 21; 2025-11-19: 21; 2025-11-20: 21; 2025-11-21: 21; 2025-11-22: 21; 2025-11-23: 21; 2025-11-24: 28; 2025-11-25: 28; 2025-11-26: 28; 2025-11-27: 28; 2025-11-28: 28; 2025-11-29: 28; 2025-11-30: 28; 2025-12-01: 28; 2025-12-02: 28; 2025-12-03: 28; 2025-12-04: 28; 2025-12-05: 28; 2025-12-06: 28; 2025-12-07: 28; 2025-12-08: 28; 2025-12-09: 28; 2025-12-10: 28; 2025-12-11: 28; 2025-12-12: 28; 2025-12-13: 28; 2025-12-14: 28; 2025-12-15: 28; 2025-12-16: 28; 2025-12-17: 28; 2025-12-18: 28; 2025-12-19: 28; 2025-12-20: 28; 2025-12-21: 28; 2025-12-22: 28; 2025-12-23: 28; 2025-12-24: 28; 2025-12-25: 28; 2025-12-26: 28; 2025-12-27: 28; 2025-12-28: 28; 2025-12-29: 28; 2025-12-30: 28; 2025-12-31: 28; 2026-01-01: 28; 2026-01-02: 28; 2026-01-03: 28; 2026-01-04: 28; 2026-01-05: 28; 2026-01-06: 28; 2026-01-07: 28; 2026-01-08: 28; 2026-01-09: 28; 2026-01-10: 28; 2026-01-11: 28; 2026-01-12: 28; 2026-01-13: 28; 2026-01-14: 28; 2026-01-15: 28; 2026-01-16: 28; 2026-01-17: 28; 2026-01-18: 28; 2026-01-19: 28; 2026-01-20: 28; 2026-01-21: 28; 2026-01-22: 28; 2026-01-23: 28; 2026-01-24: 28; 2026-01-25: 28; 2026-01-26: 28; 2026-01-27: 28; 2026-01-28: 28; 2026-01-29: 28; 2026-01-30: 28; 2026-01-31: 28; 2026-02-01: 28; 2026-02-02: 28; 2026-02-03: 28; 2026-02-04: 28; 2026-02-05: 28; 2026-02-06: 28; 2026-02-07: 28; 2026-02-08: 28; 2026-02-09: 28; 2026-02-10: 28; 2026-02-11: 28; 2026-02-12: 28; 2026-02-13: 28; 2026-02-14: 28; 2026-02-15: 28; 2026-02-16: 28; 2026-02-17: 28; 2026-02-18: 28; 2026-02-19: 28; 2026-02-20: 28; 2026-02-21: 28; 2026-02-22: 28; 2026-02-23: 28; 2026-02-24: 28; 2026-02-25: 28; 2026-02-26: 28; 2026-02-27: 28
48 | M/s Pune Logistics ( WTG Erection) | Service | Crane Package | Manpower Details (P) | 2025-10-10: 120; 2025-10-11: 120; 2025-10-12: 120; 2025-10-13: 120; 2025-10-14: 120; 2025-10-15: 120; 2025-10-16: 120; 2025-10-17: 120; 2025-10-18: 120; 2025-10-19: 120; 2025-10-20: 120; 2025-10-21: 120; 2025-10-22: 120; 2025-10-23: 120; 2025-10-24: 120; 2025-10-25: 120; 2025-10-26: 120; 2025-10-27: 120; 2025-10-28: 120; 2025-10-29: 120; 2025-10-30: 120; 2025-10-31: 120; 2025-11-01: 120; 2025-11-02: 120; 2025-11-03: 120; 2025-11-04: 120; 2025-11-05: 120; 2025-11-06: 120; 2025-11-07: 120; 2025-11-08: 120; 2025-11-09: 120; 2025-11-10: 120; 2025-11-11: 120; 2025-11-12: 120; 2025-11-13: 120; 2025-11-14: 120; 2025-11-15: 120; 2025-11-16: 120; 2025-11-17: 120; 2025-11-18: 120; 2025-11-19: 120; 2025-11-20: 120; 2025-11-21: 120; 2025-11-22: 120; 2025-11-23: 120; 2025-11-24: 120; 2025-11-25: 120; 2025-11-26: 120; 2025-11-27: 120; 2025-11-28: 120; 2025-11-29: 120; 2025-11-30: 120; 2025-12-01: 120; 2025-12-02: 120; 2025-12-03: 120; 2025-12-04: 120; 2025-12-05: 120; 2025-12-06: 120; 2025-12-07: 120; 2025-12-08: 120; 2025-12-09: 120; 2025-12-10: 120; 2025-12-11: 120; 2025-12-12: 120; 2025-12-13: 120; 2025-12-14: 120; 2025-12-15: 120; 2025-12-16: 120; 2025-12-17: 120; 2025-12-18: 120; 2025-12-19: 120; 2025-12-20: 120; 2025-12-21: 120; 2025-12-22: 120; 2025-12-23: 120; 2025-12-24: 120; 2025-12-25: 120; 2025-12-26: 120; 2025-12-27: 120; 2025-12-28: 120; 2025-12-29: 120; 2025-12-30: 120; 2025-12-31: 120; 2026-01-01: 120; 2026-01-02: 120; 2026-01-03: 120; 2026-01-04: 120; 2026-01-05: 120; 2026-01-06: 120; 2026-01-07: 120; 2026-01-08: 120; 2026-01-09: 120; 2026-01-10: 120; 2026-01-11: 120; 2026-01-12: 120; 2026-01-13: 120; 2026-01-14: 120; 2026-01-15: 120; 2026-01-16: 120; 2026-01-17: 120; 2026-01-18: 120; 2026-01-19: 120; 2026-01-20: 120; 2026-01-21: 120; 2026-01-22: 120; 2026-01-23: 120; 2026-01-24: 120; 2026-01-25: 120; 2026-01-26: 120; 2026-01-27: 120; 2026-01-28: 120; 2026-01-29: 120; 2026-01-30: 120; 2026-01-31: 120; 2026-02-01: 120; 2026-02-02: 120; 2026-02-03: 120; 2026-02-04: 120; 2026-02-05: 120; 2026-02-06: 120; 2026-02-07: 120; 2026-02-08: 120; 2026-02-09: 120; 2026-02-10: 120; 2026-02-11: 120; 2026-02-12: 120; 2026-02-13: 120; 2026-02-14: 120; 2026-02-15: 120; 2026-02-16: 120; 2026-02-17: 120; 2026-02-18: 120; 2026-02-19: 120; 2026-02-20: 120; 2026-02-21: 120; 2026-02-22: 120; 2026-02-23: 120; 2026-02-24: 120; 2026-02-25: 120; 2026-02-26: 120; 2026-02-27: 120
|  |  |  | Manpower Details (A) | 2025-10-10: 115; 2025-10-11: 115; 2025-10-12: 115; 2025-10-13: 115; 2025-10-14: 115; 2025-10-15: 115; 2025-10-16: 115; 2025-10-17: 115; 2025-10-18: 78; 2025-10-19: 76; 2025-10-20: 70; 2025-10-21: 77; 2025-10-22: 78; 2025-10-23: 78; 2025-10-24: 78; 2025-10-25: 78; 2025-10-26: 78; 2025-10-27: 78; 2025-10-28: 78; 2025-10-29: 78; 2025-10-30: 78; 2025-10-31: 78; 2025-11-01: 78; 2025-11-02: 78; 2025-11-03: 78; 2025-11-04: 99; 2025-11-05: 99; 2025-11-06: 99; 2025-11-07: 99; 2025-11-08: 99; 2025-11-09: 99; 2025-11-10: 99; 2025-11-11: 99; 2025-11-12: 99; 2025-11-13: 99; 2025-11-14: 99; 2025-11-15: 99; 2025-11-16: 99; 2025-11-17: 99; 2025-11-18: 99; 2025-11-19: 99; 2025-11-20: 99; 2025-11-21: 99; 2025-11-22: 99; 2025-11-23: 99; 2025-11-24: 115; 2025-11-25: 115; 2025-11-26: 115; 2025-11-27: 115; 2025-11-28: 115; 2025-11-29: 115; 2025-11-30: 115; 2025-12-01: 115; 2025-12-02: 115; 2025-12-03: 115; 2025-12-04: 115; 2025-12-05: 115; 2025-12-06: 115; 2025-12-07: 115; 2025-12-08: 115; 2025-12-09: 115; 2025-12-10: 115; 2025-12-11: 115; 2025-12-12: 115; 2025-12-13: 115; 2025-12-14: 115; 2025-12-15: 115; 2025-12-16: 115; 2025-12-17: 115; 2025-12-18: 115; 2025-12-19: 115; 2025-12-20: 115; 2025-12-21: 115; 2025-12-22: 115; 2025-12-23: 115; 2025-12-24: 115; 2025-12-25: 115; 2025-12-26: 115; 2025-12-27: 115; 2025-12-28: 115; 2025-12-29: 115; 2025-12-30: 115; 2025-12-31: 115; 2026-01-01: 115; 2026-01-02: 115; 2026-01-03: 115; 2026-01-04: 115; 2026-01-05: 115; 2026-01-06: 115; 2026-01-07: 115; 2026-01-08: 115; 2026-01-09: 115; 2026-01-10: 115; 2026-01-11: 115; 2026-01-12: 115; 2026-01-13: 115; 2026-01-14: 115; 2026-01-15: 115; 2026-01-16: 115; 2026-01-17: 115; 2026-01-18: 115; 2026-01-19: 115; 2026-01-20: 115; 2026-01-21: 115; 2026-01-22: 115; 2026-01-23: 115; 2026-01-24: 115; 2026-01-25: 115; 2026-01-26: 115; 2026-01-27: 115; 2026-01-28: 115; 2026-01-29: 115; 2026-01-30: 115; 2026-01-31: 115; 2026-02-01: 115; 2026-02-02: 115; 2026-02-03: 115; 2026-02-04: 115; 2026-02-05: 115; 2026-02-06: 115; 2026-02-07: 115; 2026-02-08: 115; 2026-02-09: 115; 2026-02-10: 115; 2026-02-11: 115; 2026-02-12: 115; 2026-02-13: 115; 2026-02-14: 115; 2026-02-15: 115; 2026-02-16: 115; 2026-02-17: 115; 2026-02-18: 115; 2026-02-19: 115; 2026-02-20: 115; 2026-02-21: 115; 2026-02-22: 115; 2026-02-23: 115; 2026-02-24: 115; 2026-02-25: 115; 2026-02-26: 115; 2026-02-27: 115
49 | M/s Saini crane & logistics | Service | Material Handling | Manpower Details (P) | 2025-10-10: 10; 2025-10-11: 10; 2025-10-12: 10; 2025-10-13: 10; 2025-10-14: 10; 2025-10-15: 10; 2025-10-16: 10; 2025-10-17: 10; 2025-10-18: 10; 2025-10-19: 10; 2025-10-20: 10; 2025-10-21: 10; 2025-10-22: 10; 2025-10-23: 10; 2025-10-24: 10; 2025-10-25: 10; 2025-10-26: 10; 2025-10-27: 10; 2025-10-28: 10; 2025-10-29: 10; 2025-10-30: 10; 2025-10-31: 10; 2025-11-01: 10; 2025-11-02: 10; 2025-11-03: 10; 2025-11-04: 10; 2025-11-05: 10; 2025-11-06: 10; 2025-11-07: 10; 2025-11-08: 10; 2025-11-09: 10; 2025-11-10: 10; 2025-11-11: 10; 2025-11-12: 10; 2025-11-13: 10; 2025-11-14: 10; 2025-11-15: 10; 2025-11-16: 10; 2025-11-17: 10; 2025-11-18: 10; 2025-11-19: 10; 2025-11-20: 10; 2025-11-21: 10; 2025-11-22: 10; 2025-11-23: 10; 2025-11-24: 10; 2025-11-25: 10; 2025-11-26: 10; 2025-11-27: 10; 2025-11-28: 10; 2025-11-29: 10; 2025-11-30: 10; 2025-12-01: 10; 2025-12-02: 10; 2025-12-03: 10; 2025-12-04: 10; 2025-12-05: 10; 2025-12-06: 10; 2025-12-07: 10; 2025-12-08: 10; 2025-12-09: 10; 2025-12-10: 10; 2025-12-11: 10; 2025-12-12: 10; 2025-12-13: 10; 2025-12-14: 10; 2025-12-15: 10; 2025-12-16: 10; 2025-12-17: 10; 2025-12-18: 10; 2025-12-19: 10; 2025-12-20: 10; 2025-12-21: 10; 2025-12-22: 10; 2025-12-23: 10; 2025-12-24: 10; 2025-12-25: 10; 2025-12-26: 10; 2025-12-27: 10; 2025-12-28: 10; 2025-12-29: 10; 2025-12-30: 10; 2025-12-31: 10; 2026-01-01: 10; 2026-01-02: 10; 2026-01-03: 10; 2026-01-04: 10; 2026-01-05: 10; 2026-01-06: 10; 2026-01-07: 10; 2026-01-08: 10; 2026-01-09: 10; 2026-01-10: 10; 2026-01-11: 10; 2026-01-12: 10; 2026-01-13: 10; 2026-01-14: 10; 2026-01-15: 10; 2026-01-16: 10; 2026-01-17: 10; 2026-01-18: 10; 2026-01-19: 10; 2026-01-20: 10; 2026-01-21: 10; 2026-01-22: 10; 2026-01-23: 10; 2026-01-24: 10; 2026-01-25: 10; 2026-01-26: 10; 2026-01-27: 10; 2026-01-28: 10; 2026-01-29: 10; 2026-01-30: 10; 2026-01-31: 10; 2026-02-01: 10; 2026-02-02: 10; 2026-02-03: 10; 2026-02-04: 10; 2026-02-05: 10; 2026-02-06: 10; 2026-02-07: 10; 2026-02-08: 10; 2026-02-09: 10; 2026-02-10: 10; 2026-02-11: 10; 2026-02-12: 10; 2026-02-13: 10; 2026-02-14: 10; 2026-02-15: 10; 2026-02-16: 10; 2026-02-17: 10; 2026-02-18: 10; 2026-02-19: 10; 2026-02-20: 10; 2026-02-21: 10; 2026-02-22: 10; 2026-02-23: 10; 2026-02-24: 10; 2026-02-25: 10; 2026-02-26: 10; 2026-02-27: 10
|  |  |  | Manpower Details (A) | 2025-10-10: 12; 2025-10-11: 12; 2025-10-12: 12; 2025-10-13: 12; 2025-10-14: 12; 2025-10-15: 12; 2025-10-16: 12; 2025-10-17: 12; 2025-10-18: 12; 2025-10-19: 12; 2025-10-20: 12; 2025-10-21: 12; 2025-10-22: 12; 2025-10-23: 12; 2025-10-24: 12; 2025-10-25: 12; 2025-10-26: 12; 2025-10-27: 12; 2025-10-28: 12; 2025-10-29: 12; 2025-10-30: 12; 2025-10-31: 12; 2025-11-01: 12; 2025-11-02: 12; 2025-11-03: 12; 2025-11-04: 12; 2025-11-05: 12; 2025-11-06: 12; 2025-11-07: 12; 2025-11-08: 12; 2025-11-09: 12; 2025-11-10: 12; 2025-11-11: 12; 2025-11-12: 12; 2025-11-13: 12; 2025-11-14: 12; 2025-11-15: 12; 2025-11-16: 12; 2025-11-17: 12; 2025-11-18: 12; 2025-11-19: 12; 2025-11-20: 12; 2025-11-21: 12; 2025-11-22: 12; 2025-11-23: 12; 2025-11-24: 12; 2025-11-25: 12; 2025-11-26: 12; 2025-11-27: 12; 2025-11-28: 12; 2025-11-29: 12; 2025-11-30: 12; 2025-12-01: 12; 2025-12-02: 12; 2025-12-03: 12; 2025-12-04: 12; 2025-12-05: 12; 2025-12-06: 12; 2025-12-07: 12; 2025-12-08: 12; 2025-12-09: 12; 2025-12-10: 12; 2025-12-11: 12; 2025-12-12: 12; 2025-12-13: 12; 2025-12-14: 12; 2025-12-15: 12; 2025-12-16: 12; 2025-12-17: 12; 2025-12-18: 12; 2025-12-19: 12; 2025-12-20: 12; 2025-12-21: 12; 2025-12-22: 12; 2025-12-23: 12; 2025-12-24: 12; 2025-12-25: 12; 2025-12-26: 12; 2025-12-27: 12; 2025-12-28: 12; 2025-12-29: 12; 2025-12-30: 12; 2025-12-31: 12; 2026-01-01: 12; 2026-01-02: 12; 2026-01-03: 12; 2026-01-04: 12; 2026-01-05: 12; 2026-01-06: 12; 2026-01-07: 12; 2026-01-08: 12; 2026-01-09: 12; 2026-01-10: 12; 2026-01-11: 12; 2026-01-12: 12; 2026-01-13: 12; 2026-01-14: 12; 2026-01-15: 12; 2026-01-16: 12; 2026-01-17: 12; 2026-01-18: 12; 2026-01-19: 12; 2026-01-20: 12; 2026-01-21: 12; 2026-01-22: 12; 2026-01-23: 12; 2026-01-24: 12; 2026-01-25: 12; 2026-01-26: 12; 2026-01-27: 12; 2026-01-28: 12; 2026-01-29: 12; 2026-01-30: 12; 2026-01-31: 12; 2026-02-01: 12; 2026-02-02: 12; 2026-02-03: 12; 2026-02-04: 12; 2026-02-05: 12; 2026-02-06: 12; 2026-02-07: 12; 2026-02-08: 12; 2026-02-09: 12; 2026-02-10: 12; 2026-02-11: 12; 2026-02-12: 12; 2026-02-13: 12; 2026-02-14: 12; 2026-02-15: 12; 2026-02-16: 12; 2026-02-17: 12; 2026-02-18: 12; 2026-02-19: 12; 2026-02-20: 12; 2026-02-21: 12; 2026-02-22: 12; 2026-02-23: 12; 2026-02-24: 12; 2026-02-25: 12; 2026-02-26: 12; 2026-02-27: 12
50 | Raghuveer Sing & Sons | Service | Erection/Material Handling | Manpower Details (P) | 2025-10-10: 30; 2025-10-11: 30; 2025-10-12: 30; 2025-10-13: 30; 2025-10-14: 30; 2025-10-15: 30; 2025-10-16: 30; 2025-10-17: 30; 2025-10-18: 30; 2025-10-19: 30; 2025-10-20: 30; 2025-10-21: 30; 2025-10-22: 30; 2025-10-23: 30; 2025-10-24: 30; 2025-10-25: 30; 2025-10-26: 30; 2025-10-27: 30; 2025-10-28: 30; 2025-10-29: 30; 2025-10-30: 30; 2025-10-31: 30; 2025-11-01: 30; 2025-11-02: 30; 2025-11-03: 30; 2025-11-04: 30; 2025-11-05: 30; 2025-11-06: 30; 2025-11-07: 30; 2025-11-08: 30; 2025-11-09: 30; 2025-11-10: 30; 2025-11-11: 30; 2025-11-12: 30; 2025-11-13: 30; 2025-11-14: 30; 2025-11-15: 30; 2025-11-16: 30; 2025-11-17: 30; 2025-11-18: 30; 2025-11-19: 30; 2025-11-20: 30; 2025-11-21: 30; 2025-11-22: 30; 2025-11-23: 30; 2025-11-24: 30; 2025-11-25: 30; 2025-11-26: 30; 2025-11-27: 30; 2025-11-28: 30; 2025-11-29: 30; 2025-11-30: 30; 2025-12-01: 30; 2025-12-02: 30; 2025-12-03: 30; 2025-12-04: 30; 2025-12-05: 30; 2025-12-06: 30; 2025-12-07: 30; 2025-12-08: 30; 2025-12-09: 30; 2025-12-10: 30; 2025-12-11: 30; 2025-12-12: 30; 2025-12-13: 30; 2025-12-14: 30; 2025-12-15: 30; 2025-12-16: 30; 2025-12-17: 30; 2025-12-18: 30; 2025-12-19: 30; 2025-12-20: 30; 2025-12-21: 30; 2025-12-22: 30; 2025-12-23: 30; 2025-12-24: 30; 2025-12-25: 30; 2025-12-26: 30; 2025-12-27: 30; 2025-12-28: 30; 2025-12-29: 30; 2025-12-30: 30; 2025-12-31: 30; 2026-01-01: 30; 2026-01-02: 30; 2026-01-03: 30; 2026-01-04: 30; 2026-01-05: 30; 2026-01-06: 30; 2026-01-07: 30; 2026-01-08: 30; 2026-01-09: 30; 2026-01-10: 30; 2026-01-11: 30; 2026-01-12: 30; 2026-01-13: 30; 2026-01-14: 30; 2026-01-15: 30; 2026-01-16: 30; 2026-01-17: 30; 2026-01-18: 30; 2026-01-19: 30; 2026-01-20: 30; 2026-01-21: 30; 2026-01-22: 30; 2026-01-23: 30; 2026-01-24: 30; 2026-01-25: 30; 2026-01-26: 30; 2026-01-27: 30; 2026-01-28: 30; 2026-01-29: 30; 2026-01-30: 30; 2026-01-31: 30; 2026-02-01: 30; 2026-02-02: 30; 2026-02-03: 30; 2026-02-04: 30; 2026-02-05: 30; 2026-02-06: 30; 2026-02-07: 30; 2026-02-08: 30; 2026-02-09: 30; 2026-02-10: 30; 2026-02-11: 30; 2026-02-12: 30; 2026-02-13: 30; 2026-02-14: 30; 2026-02-15: 30; 2026-02-16: 30; 2026-02-17: 30; 2026-02-18: 30; 2026-02-19: 30; 2026-02-20: 30; 2026-02-21: 30; 2026-02-22: 30; 2026-02-23: 30; 2026-02-24: 30; 2026-02-25: 30; 2026-02-26: 30; 2026-02-27: 30
|  |  |  | Manpower Details (A) | 2025-10-10: 18; 2025-10-11: 18; 2025-10-12: 18; 2025-10-13: 18; 2025-10-14: 18; 2025-10-15: 18; 2025-10-16: 18; 2025-10-17: 18; 2025-10-18: 18; 2025-10-19: 18; 2025-10-20: 18; 2025-10-21: 18; 2025-10-22: 18; 2025-10-23: 18; 2025-10-24: 18; 2025-10-25: 18; 2025-10-26: 18; 2025-10-27: 18; 2025-10-28: 18; 2025-10-29: 18; 2025-10-30: 18; 2025-10-31: 18; 2025-11-01: 18; 2025-11-02: 18; 2025-11-03: 18; 2025-11-04: 18; 2025-11-05: 18; 2025-11-06: 18; 2025-11-07: 18; 2025-11-08: 18; 2025-11-09: 18; 2025-11-10: 18; 2025-11-11: 18; 2025-11-12: 18; 2025-11-13: 18; 2025-11-14: 18; 2025-11-15: 18; 2025-11-16: 18; 2025-11-17: 18; 2025-11-18: 18; 2025-11-19: 18; 2025-11-20: 18; 2025-11-21: 18; 2025-11-22: 18; 2025-11-23: 18; 2025-11-24: 18; 2025-11-25: 18; 2025-11-26: 18; 2025-11-27: 18; 2025-11-28: 18; 2025-11-29: 18; 2025-11-30: 18; 2025-12-01: 18; 2025-12-02: 18; 2025-12-03: 18; 2025-12-04: 18; 2025-12-05: 18; 2025-12-06: 18; 2025-12-07: 18; 2025-12-08: 18; 2025-12-09: 18; 2025-12-10: 18; 2025-12-11: 18; 2025-12-12: 18; 2025-12-13: 18; 2025-12-14: 18; 2025-12-15: 18; 2025-12-16: 18; 2025-12-17: 18; 2025-12-18: 18; 2025-12-19: 18; 2025-12-20: 18; 2025-12-21: 18; 2025-12-22: 18; 2025-12-23: 18; 2025-12-24: 18; 2025-12-25: 18; 2025-12-26: 18; 2025-12-27: 18; 2025-12-28: 18; 2025-12-29: 18; 2025-12-30: 18; 2025-12-31: 18; 2026-01-01: 18; 2026-01-02: 18; 2026-01-03: 18; 2026-01-04: 18; 2026-01-05: 18; 2026-01-06: 18; 2026-01-07: 18; 2026-01-08: 18; 2026-01-09: 18; 2026-01-10: 18; 2026-01-11: 18; 2026-01-12: 18; 2026-01-13: 18; 2026-01-14: 18; 2026-01-15: 18; 2026-01-16: 18; 2026-01-17: 18; 2026-01-18: 18; 2026-01-19: 18; 2026-01-20: 18; 2026-01-21: 18; 2026-01-22: 18; 2026-01-23: 18; 2026-01-24: 18; 2026-01-25: 18; 2026-01-26: 18; 2026-01-27: 18; 2026-01-28: 18; 2026-01-29: 18; 2026-01-30: 18; 2026-01-31: 18; 2026-02-01: 18; 2026-02-02: 18; 2026-02-03: 18; 2026-02-04: 18; 2026-02-05: 18; 2026-02-06: 18; 2026-02-07: 18; 2026-02-08: 18; 2026-02-09: 18; 2026-02-10: 18; 2026-02-11: 18; 2026-02-12: 18; 2026-02-13: 18; 2026-02-14: 18; 2026-02-15: 18; 2026-02-16: 18; 2026-02-17: 18; 2026-02-18: 18; 2026-02-19: 18; 2026-02-20: 18; 2026-02-21: 18; 2026-02-22: 18; 2026-02-23: 18; 2026-02-24: 18; 2026-02-25: 18; 2026-02-26: 18; 2026-02-27: 18
51 | Tara Chand Infra logistics sol. Ltd. | Service | Erection/Material Handling | Manpower Details (P) | 2025-10-10: 20; 2025-10-11: 20; 2025-10-12: 20; 2025-10-13: 20; 2025-10-14: 20; 2025-10-15: 20; 2025-10-16: 20; 2025-10-17: 20; 2025-10-18: 20; 2025-10-19: 20; 2025-10-20: 20; 2025-10-21: 20; 2025-10-22: 20; 2025-10-23: 20; 2025-10-24: 20; 2025-10-25: 20; 2025-10-26: 20; 2025-10-27: 20; 2025-10-28: 20; 2025-10-29: 20; 2025-10-30: 20; 2025-10-31: 20; 2025-11-01: 20; 2025-11-02: 20; 2025-11-03: 20; 2025-11-04: 20; 2025-11-05: 20; 2025-11-06: 20; 2025-11-07: 20; 2025-11-08: 20; 2025-11-09: 20; 2025-11-10: 20; 2025-11-11: 20; 2025-11-12: 20; 2025-11-13: 20; 2025-11-14: 20; 2025-11-15: 20; 2025-11-16: 20; 2025-11-17: 20; 2025-11-18: 20; 2025-11-19: 20; 2025-11-20: 20; 2025-11-21: 20; 2025-11-22: 20; 2025-11-23: 20; 2025-11-24: 20; 2025-11-25: 20; 2025-11-26: 20; 2025-11-27: 20; 2025-11-28: 20; 2025-11-29: 20; 2025-11-30: 20; 2025-12-01: 20; 2025-12-02: 20; 2025-12-03: 20; 2025-12-04: 20; 2025-12-05: 20; 2025-12-06: 20; 2025-12-07: 20; 2025-12-08: 20; 2025-12-09: 20; 2025-12-10: 20; 2025-12-11: 20; 2025-12-12: 20; 2025-12-13: 20; 2025-12-14: 20; 2025-12-15: 20; 2025-12-16: 20; 2025-12-17: 20; 2025-12-18: 20; 2025-12-19: 20; 2025-12-20: 20; 2025-12-21: 20; 2025-12-22: 20; 2025-12-23: 20; 2025-12-24: 20; 2025-12-25: 20; 2025-12-26: 20; 2025-12-27: 20; 2025-12-28: 20; 2025-12-29: 20; 2025-12-30: 20; 2025-12-31: 20; 2026-01-01: 20; 2026-01-02: 20; 2026-01-03: 20; 2026-01-04: 20; 2026-01-05: 20; 2026-01-06: 20; 2026-01-07: 20; 2026-01-08: 20; 2026-01-09: 20; 2026-01-10: 20; 2026-01-11: 20; 2026-01-12: 20; 2026-01-13: 20; 2026-01-14: 20; 2026-01-15: 20; 2026-01-16: 20; 2026-01-17: 20; 2026-01-18: 20; 2026-01-19: 20; 2026-01-20: 20; 2026-01-21: 20; 2026-01-22: 20; 2026-01-23: 20; 2026-01-24: 20; 2026-01-25: 20; 2026-01-26: 20; 2026-01-27: 20; 2026-01-28: 20; 2026-01-29: 20; 2026-01-30: 20; 2026-01-31: 20; 2026-02-01: 20; 2026-02-02: 20; 2026-02-03: 20; 2026-02-04: 20; 2026-02-05: 20; 2026-02-06: 20; 2026-02-07: 20; 2026-02-08: 20; 2026-02-09: 20; 2026-02-10: 20; 2026-02-11: 20; 2026-02-12: 20; 2026-02-13: 20; 2026-02-14: 20; 2026-02-15: 20; 2026-02-16: 20; 2026-02-17: 20; 2026-02-18: 20; 2026-02-19: 20; 2026-02-20: 20; 2026-02-21: 20; 2026-02-22: 20; 2026-02-23: 20; 2026-02-24: 20; 2026-02-25: 20; 2026-02-26: 20; 2026-02-27: 20
|  |  |  | Manpower Details (A) | 2025-10-10: 17; 2025-10-11: 17; 2025-10-12: 17; 2025-10-13: 17; 2025-10-14: 17; 2025-10-15: 14; 2025-10-16: 12; 2025-10-17: 12; 2025-10-18: 10; 2025-10-19: 10; 2025-10-20: 10; 2025-10-21: 10; 2025-10-22: 10; 2025-10-23: 10; 2025-10-24: 10; 2025-10-25: 10; 2025-10-26: 10; 2025-10-27: 10; 2025-10-28: 10; 2025-10-29: 10; 2025-10-30: 10; 2025-10-31: 10; 2025-11-01: 10; 2025-11-02: 10; 2025-11-03: 10; 2025-11-04: 10; 2025-11-05: 10; 2025-11-06: 10; 2025-11-07: 10; 2025-11-08: 10; 2025-11-09: 10; 2025-11-10: 10; 2025-11-11: 10; 2025-11-12: 10; 2025-11-13: 10; 2025-11-14: 10; 2025-11-15: 10; 2025-11-16: 10; 2025-11-17: 10; 2025-11-18: 10; 2025-11-19: 10; 2025-11-20: 10; 2025-11-21: 10; 2025-11-22: 10; 2025-11-23: 10; 2025-11-24: 10; 2025-11-25: 10; 2025-11-26: 10; 2025-11-27: 10; 2025-11-28: 13; 2025-11-29: 13; 2025-11-30: 13; 2025-12-01: 13; 2025-12-02: 13; 2025-12-03: 13; 2025-12-04: 13; 2025-12-05: 13; 2025-12-06: 13; 2025-12-07: 13; 2025-12-08: 13; 2025-12-09: 13; 2025-12-10: 13; 2025-12-11: 13; 2025-12-12: 13; 2025-12-13: 13; 2025-12-14: 13; 2025-12-15: 13; 2025-12-16: 13; 2025-12-17: 13; 2025-12-18: 13; 2025-12-19: 13; 2025-12-20: 13; 2025-12-21: 13; 2025-12-22: 13; 2025-12-23: 13; 2025-12-24: 13; 2025-12-25: 13; 2025-12-26: 13; 2025-12-27: 13; 2025-12-28: 13; 2025-12-29: 13; 2025-12-30: 13; 2025-12-31: 13; 2026-01-01: 13; 2026-01-02: 13; 2026-01-03: 13; 2026-01-04: 13; 2026-01-05: 13; 2026-01-06: 13; 2026-01-07: 13; 2026-01-08: 13; 2026-01-09: 13; 2026-01-10: 13; 2026-01-11: 13; 2026-01-12: 13; 2026-01-13: 13; 2026-01-14: 13; 2026-01-15: 13; 2026-01-16: 13; 2026-01-17: 13; 2026-01-18: 13; 2026-01-19: 13; 2026-01-20: 13; 2026-01-21: 13; 2026-01-22: 13; 2026-01-23: 13; 2026-01-24: 13; 2026-01-25: 13; 2026-01-26: 13; 2026-01-27: 13; 2026-01-28: 13; 2026-01-29: 13; 2026-01-30: 13; 2026-01-31: 13; 2026-02-01: 13; 2026-02-02: 13; 2026-02-03: 13; 2026-02-04: 13; 2026-02-05: 13; 2026-02-06: 13; 2026-02-07: 13; 2026-02-08: 13; 2026-02-09: 13; 2026-02-10: 13; 2026-02-11: 13; 2026-02-12: 13; 2026-02-13: 13; 2026-02-14: 13; 2026-02-15: 13; 2026-02-16: 13; 2026-02-17: 13; 2026-02-18: 13; 2026-02-19: 13; 2026-02-20: 13; 2026-02-21: 13; 2026-02-22: 13; 2026-02-23: 13; 2026-02-24: 13; 2026-02-25: 13; 2026-02-26: 13; 2026-02-27: 13
52 | SS Logistics | Service | Erection/Material Handling | Manpower Details (P) | 2025-10-10: 4; 2025-10-11: 4; 2025-10-12: 4; 2025-10-13: 4; 2025-10-14: 4; 2025-10-15: 4; 2025-10-16: 4; 2025-10-17: 4; 2025-10-18: 4; 2025-10-19: 4; 2025-10-20: 4; 2025-10-21: 4; 2025-10-22: 4; 2025-10-23: 4; 2025-10-24: 4; 2025-10-25: 4; 2025-10-26: 4; 2025-10-27: 4; 2025-10-28: 4; 2025-10-29: 4; 2025-10-30: 4; 2025-10-31: 4; 2025-11-01: 4; 2025-11-02: 4; 2025-11-03: 4; 2025-11-04: 4; 2025-11-05: 4; 2025-11-06: 4; 2025-11-07: 4; 2025-11-08: 4; 2025-11-09: 4; 2025-11-10: 4; 2025-11-11: 4; 2025-11-12: 4; 2025-11-13: 4; 2025-11-14: 4; 2025-11-15: 4; 2025-11-16: 4; 2025-11-17: 4; 2025-11-18: 4; 2025-11-19: 4; 2025-11-20: 4; 2025-11-21: 4; 2025-11-22: 4; 2025-11-23: 4; 2025-11-24: 4; 2025-11-25: 4; 2025-11-26: 4; 2025-11-27: 4; 2025-11-28: 4; 2025-11-29: 4; 2025-11-30: 4; 2025-12-01: 4; 2025-12-02: 4; 2025-12-03: 4; 2025-12-04: 4; 2025-12-05: 4; 2025-12-06: 4; 2025-12-07: 4; 2025-12-08: 4; 2025-12-09: 4; 2025-12-10: 4; 2025-12-11: 4; 2025-12-12: 4; 2025-12-13: 4; 2025-12-14: 4; 2025-12-15: 4; 2025-12-16: 4; 2025-12-17: 4; 2025-12-18: 4; 2025-12-19: 4; 2025-12-20: 4; 2025-12-21: 4; 2025-12-22: 4; 2025-12-23: 4; 2025-12-24: 4; 2025-12-25: 4; 2025-12-26: 4; 2025-12-27: 4; 2025-12-28: 4; 2025-12-29: 4; 2025-12-30: 4; 2025-12-31: 4; 2026-01-01: 4; 2026-01-02: 4; 2026-01-03: 4; 2026-01-04: 4; 2026-01-05: 4; 2026-01-06: 4; 2026-01-07: 4; 2026-01-08: 4; 2026-01-09: 4; 2026-01-10: 4; 2026-01-11: 4; 2026-01-12: 4; 2026-01-13: 4; 2026-01-14: 4; 2026-01-15: 4; 2026-01-16: 4; 2026-01-17: 4; 2026-01-18: 4; 2026-01-19: 4; 2026-01-20: 4; 2026-01-21: 4; 2026-01-22: 4; 2026-01-23: 4; 2026-01-24: 4; 2026-01-25: 4; 2026-01-26: 4; 2026-01-27: 4; 2026-01-28: 4; 2026-01-29: 4; 2026-01-30: 4; 2026-01-31: 4; 2026-02-01: 4; 2026-02-02: 4; 2026-02-03: 4; 2026-02-04: 4; 2026-02-05: 4; 2026-02-06: 4; 2026-02-07: 4; 2026-02-08: 4; 2026-02-09: 4; 2026-02-10: 4; 2026-02-11: 4; 2026-02-12: 4; 2026-02-13: 4; 2026-02-14: 4; 2026-02-15: 4; 2026-02-16: 4; 2026-02-17: 4; 2026-02-18: 4; 2026-02-19: 4; 2026-02-20: 4; 2026-02-21: 4; 2026-02-22: 4; 2026-02-23: 4; 2026-02-24: 4; 2026-02-25: 4; 2026-02-26: 4; 2026-02-27: 4
|  |  |  | Manpower Details (A) | 2025-10-10: 4; 2025-10-11: 4; 2025-10-12: 4; 2025-10-13: 4; 2025-10-14: 4; 2025-10-15: 4; 2025-10-16: 4; 2025-10-17: 4; 2025-10-18: 4; 2025-10-19: 4; 2025-10-20: 4; 2025-10-21: 4; 2025-10-22: 4; 2025-10-23: 4; 2025-10-24: 4; 2025-10-25: 4; 2025-10-26: 4; 2025-10-27: 4; 2025-10-28: 4; 2025-10-29: 4; 2025-10-30: 4; 2025-10-31: 4; 2025-11-01: 4; 2025-11-02: 4; 2025-11-03: 4; 2025-11-04: 4; 2025-11-05: 4; 2025-11-06: 4; 2025-11-07: 4; 2025-11-08: 4; 2025-11-09: 4; 2025-11-10: 4; 2025-11-11: 4; 2025-11-12: 4; 2025-11-13: 4; 2025-11-14: 4; 2025-11-15: 4; 2025-11-16: 4; 2025-11-17: 4; 2025-11-18: 4; 2025-11-19: 4; 2025-11-20: 4; 2025-11-21: 4; 2025-11-22: 4; 2025-11-23: 4; 2025-11-24: 4; 2025-11-25: 4; 2025-11-26: 4; 2025-11-27: 4; 2025-11-28: 4; 2025-11-29: 4; 2025-11-30: 4; 2025-12-01: 4; 2025-12-02: 4; 2025-12-03: 4; 2025-12-04: 4; 2025-12-05: 4; 2025-12-06: 4; 2025-12-07: 4; 2025-12-08: 4; 2025-12-09: 4; 2025-12-10: 4; 2025-12-11: 4; 2025-12-12: 4; 2025-12-13: 4; 2025-12-14: 4; 2025-12-15: 4; 2025-12-16: 4; 2025-12-17: 4; 2025-12-18: 4; 2025-12-19: 4; 2025-12-20: 4; 2025-12-21: 4; 2025-12-22: 4; 2025-12-23: 4; 2025-12-24: 4; 2025-12-25: 4; 2025-12-26: 4; 2025-12-27: 4; 2025-12-28: 4; 2025-12-29: 4; 2025-12-30: 4; 2025-12-31: 4; 2026-01-01: 4; 2026-01-02: 4; 2026-01-03: 4; 2026-01-04: 4; 2026-01-05: 4; 2026-01-06: 4; 2026-01-07: 4; 2026-01-08: 4; 2026-01-09: 4; 2026-01-10: 4; 2026-01-11: 4; 2026-01-12: 4; 2026-01-13: 4; 2026-01-14: 4; 2026-01-15: 4; 2026-01-16: 4; 2026-01-17: 4; 2026-01-18: 4; 2026-01-19: 4; 2026-01-20: 4; 2026-01-21: 4; 2026-01-22: 4; 2026-01-23: 4; 2026-01-24: 4; 2026-01-25: 4; 2026-01-26: 4; 2026-01-27: 4; 2026-01-28: 4; 2026-01-29: 4; 2026-01-30: 4; 2026-01-31: 4; 2026-02-01: 4; 2026-02-02: 4; 2026-02-03: 4; 2026-02-04: 4; 2026-02-05: 4; 2026-02-06: 4; 2026-02-07: 4; 2026-02-08: 4; 2026-02-09: 4; 2026-02-10: 4; 2026-02-11: 4; 2026-02-12: 4; 2026-02-13: 4; 2026-02-14: 4; 2026-02-15: 4; 2026-02-16: 4; 2026-02-17: 4; 2026-02-18: 4; 2026-02-19: 4; 2026-02-20: 4; 2026-02-21: 4; 2026-02-22: 4; 2026-02-23: 4; 2026-02-24: 4; 2026-02-25: 4; 2026-02-26: 4; 2026-02-27: 4
53 | Safar Cranes india Pvt. Ltd. | Service | Erection/Material Handling | Manpower Details (P) | 2025-10-16: 2; 2025-10-17: 2; 2025-10-18: 2; 2025-10-19: 2; 2025-10-20: 2; 2025-10-21: 2; 2025-10-22: 2; 2025-10-23: 2; 2025-10-24: 2; 2025-10-25: 2; 2025-10-26: 2; 2025-10-27: 2; 2025-10-28: 2; 2025-10-29: 2; 2025-10-30: 2; 2025-10-31: 2; 2025-11-01: 2; 2025-11-02: 2; 2025-11-03: 2; 2025-11-04: 2; 2025-11-05: 2; 2025-11-06: 2; 2025-11-07: 2; 2025-11-08: 2; 2025-11-09: 2; 2025-11-10: 2; 2025-11-11: 2; 2025-11-12: 2; 2025-11-13: 2; 2025-11-14: 2; 2025-11-15: 2; 2025-11-16: 2; 2025-11-17: 2; 2025-11-18: 2; 2025-11-19: 2; 2025-11-20: 2; 2025-11-21: 2; 2025-11-22: 2; 2025-11-23: 2; 2025-11-24: 2; 2025-11-25: 2; 2025-11-26: 2; 2025-11-27: 2; 2025-11-28: 2; 2025-11-29: 2; 2025-11-30: 2; 2025-12-01: 2; 2025-12-02: 2; 2025-12-03: 2; 2025-12-04: 2; 2025-12-05: 2; 2025-12-06: 2; 2025-12-07: 2; 2025-12-08: 2; 2025-12-09: 2; 2025-12-10: 2; 2025-12-11: 2; 2025-12-12: 2; 2025-12-13: 2; 2025-12-14: 2; 2025-12-15: 2; 2025-12-16: 2; 2025-12-17: 2; 2025-12-18: 2; 2025-12-19: 2; 2025-12-20: 2; 2025-12-21: 2; 2025-12-22: 2; 2025-12-23: 2; 2025-12-24: 2; 2025-12-25: 2; 2025-12-26: 2; 2025-12-27: 2; 2025-12-28: 2; 2025-12-29: 2; 2025-12-30: 2; 2025-12-31: 2; 2026-01-01: 2; 2026-01-02: 2; 2026-01-03: 2; 2026-01-04: 2; 2026-01-05: 2; 2026-01-06: 2; 2026-01-07: 2; 2026-01-08: 2; 2026-01-09: 2; 2026-01-10: 2; 2026-01-11: 2; 2026-01-12: 2; 2026-01-13: 2; 2026-01-14: 2; 2026-01-15: 2; 2026-01-16: 2; 2026-01-17: 2; 2026-01-18: 2; 2026-01-19: 2; 2026-01-20: 2; 2026-01-21: 2; 2026-01-22: 2; 2026-01-23: 2; 2026-01-24: 2; 2026-01-25: 2; 2026-01-26: 2; 2026-01-27: 2; 2026-01-28: 2; 2026-01-29: 2; 2026-01-30: 2; 2026-01-31: 2; 2026-02-01: 2; 2026-02-02: 2; 2026-02-03: 2; 2026-02-04: 2; 2026-02-05: 2; 2026-02-06: 2; 2026-02-07: 2; 2026-02-08: 2; 2026-02-09: 2; 2026-02-10: 2; 2026-02-11: 2; 2026-02-12: 2; 2026-02-13: 2; 2026-02-14: 2; 2026-02-15: 2; 2026-02-16: 2; 2026-02-17: 2; 2026-02-18: 2; 2026-02-19: 2; 2026-02-20: 2; 2026-02-21: 2; 2026-02-22: 2; 2026-02-23: 2; 2026-02-24: 2; 2026-02-25: 2; 2026-02-26: 2; 2026-02-27: 2
|  |  |  | Manpower Details (A) | 2025-10-16: 2; 2025-10-17: 2; 2025-10-18: 2; 2025-10-19: 2; 2025-10-20: 2; 2025-10-21: 2; 2025-10-22: 2; 2025-10-23: 2; 2025-10-24: 2; 2025-10-25: 2; 2025-10-26: 2; 2025-10-27: 2; 2025-10-28: 2; 2025-10-29: 2; 2025-10-30: 2; 2025-10-31: 2; 2025-11-01: 2; 2025-11-02: 2; 2025-11-03: 2; 2025-11-04: 2; 2025-11-05: 2; 2025-11-06: 2; 2025-11-07: 2; 2025-11-08: 2; 2025-11-09: 2; 2025-11-10: 2; 2025-11-11: 2; 2025-11-12: 2; 2025-11-13: 2; 2025-11-14: 2; 2025-11-15: 2; 2025-11-16: 2; 2025-11-17: 2; 2025-11-18: 2; 2025-11-19: 2; 2025-11-20: 2; 2025-11-21: 2; 2025-11-22: 2; 2025-11-23: 2; 2025-11-24: 2; 2025-11-25: 2; 2025-11-26: 2; 2025-11-27: 2; 2025-11-28: 2; 2025-11-29: 2; 2025-11-30: 2; 2025-12-01: 2; 2025-12-02: 2; 2025-12-03: 2; 2025-12-04: 2; 2025-12-05: 2; 2025-12-06: 2; 2025-12-07: 2; 2025-12-08: 2; 2025-12-09: 2; 2025-12-10: 2; 2025-12-11: 2; 2025-12-12: 2; 2025-12-13: 2; 2025-12-14: 2; 2025-12-15: 2; 2025-12-16: 2; 2025-12-17: 2; 2025-12-18: 2; 2025-12-19: 2; 2025-12-20: 2; 2025-12-21: 2; 2025-12-22: 2; 2025-12-23: 2; 2025-12-24: 2; 2025-12-25: 2; 2025-12-26: 2; 2025-12-27: 2; 2025-12-28: 2; 2025-12-29: 2; 2025-12-30: 2; 2025-12-31: 2; 2026-01-01: 2; 2026-01-02: 2; 2026-01-03: 2; 2026-01-04: 2; 2026-01-05: 2; 2026-01-06: 2; 2026-01-07: 2; 2026-01-08: 2; 2026-01-09: 2; 2026-01-10: 2; 2026-01-11: 2; 2026-01-12: 2; 2026-01-13: 2; 2026-01-14: 2; 2026-01-15: 2; 2026-01-16: 2; 2026-01-17: 2; 2026-01-18: 2; 2026-01-19: 2; 2026-01-20: 2; 2026-01-21: 2; 2026-01-22: 2; 2026-01-23: 2; 2026-01-24: 2; 2026-01-25: 2; 2026-01-26: 2; 2026-01-27: 2; 2026-01-28: 2; 2026-01-29: 2; 2026-01-30: 2; 2026-01-31: 2; 2026-02-01: 2; 2026-02-02: 2; 2026-02-03: 2; 2026-02-04: 2; 2026-02-05: 2; 2026-02-06: 2; 2026-02-07: 2; 2026-02-08: 2; 2026-02-09: 2; 2026-02-10: 2; 2026-02-11: 2; 2026-02-12: 2; 2026-02-13: 2; 2026-02-14: 2; 2026-02-15: 2; 2026-02-16: 2; 2026-02-17: 2; 2026-02-18: 2; 2026-02-19: 2; 2026-02-20: 2; 2026-02-21: 2; 2026-02-22: 2; 2026-02-23: 2; 2026-02-24: 2; 2026-02-25: 2; 2026-02-26: 2; 2026-02-27: 2
54 | Jain Trailer Services(I) pvt.LTD. | Service | Erection/Material Handling | Manpower Details (P) | 2025-10-10: 90; 2025-10-11: 90; 2025-10-12: 90; 2025-10-13: 90; 2025-10-14: 90; 2025-10-15: 120; 2025-10-16: 120; 2025-10-17: 120; 2025-10-18: 120; 2025-10-19: 120; 2025-10-20: 120; 2025-10-21: 120; 2025-10-22: 120; 2025-10-23: 120; 2025-10-24: 120; 2025-10-25: 120; 2025-10-26: 120; 2025-10-27: 120; 2025-10-28: 120; 2025-10-29: 120; 2025-10-30: 120; 2025-10-31: 120; 2025-11-01: 120; 2025-11-02: 120; 2025-11-03: 120; 2025-11-04: 120; 2025-11-05: 120; 2025-11-06: 120; 2025-11-07: 120; 2025-11-08: 120; 2025-11-09: 120; 2025-11-10: 120; 2025-11-11: 120; 2025-11-12: 120; 2025-11-13: 120; 2025-11-14: 120; 2025-11-15: 120; 2025-11-16: 120; 2025-11-17: 120; 2025-11-18: 120; 2025-11-19: 120; 2025-11-20: 120; 2025-11-21: 120; 2025-11-22: 120; 2025-11-23: 120; 2025-11-24: 120; 2025-11-25: 120; 2025-11-26: 120; 2025-11-27: 120; 2025-11-28: 120; 2025-11-29: 120; 2025-11-30: 120; 2025-12-01: 120; 2025-12-02: 120; 2025-12-03: 120; 2025-12-04: 120; 2025-12-05: 120; 2025-12-06: 120; 2025-12-07: 120; 2025-12-08: 120; 2025-12-09: 120; 2025-12-10: 120; 2025-12-11: 120; 2025-12-12: 120; 2025-12-13: 120; 2025-12-14: 120; 2025-12-15: 120; 2025-12-16: 120; 2025-12-17: 120; 2025-12-18: 120; 2025-12-19: 120; 2025-12-20: 120; 2025-12-21: 120; 2025-12-22: 120; 2025-12-23: 120; 2025-12-24: 120; 2025-12-25: 120; 2025-12-26: 120; 2025-12-27: 120; 2025-12-28: 120; 2025-12-29: 120; 2025-12-30: 120; 2025-12-31: 120; 2026-01-01: 120; 2026-01-02: 120; 2026-01-03: 120; 2026-01-04: 120; 2026-01-05: 120; 2026-01-06: 120; 2026-01-07: 120; 2026-01-08: 120; 2026-01-09: 120; 2026-01-10: 120; 2026-01-11: 120; 2026-01-12: 120; 2026-01-13: 120; 2026-01-14: 120; 2026-01-15: 120; 2026-01-16: 120; 2026-01-17: 120; 2026-01-18: 120; 2026-01-19: 120; 2026-01-20: 120; 2026-01-21: 120; 2026-01-22: 120; 2026-01-23: 120; 2026-01-24: 120; 2026-01-25: 120; 2026-01-26: 120; 2026-01-27: 120; 2026-01-28: 120; 2026-01-29: 120; 2026-01-30: 120; 2026-01-31: 120; 2026-02-01: 120; 2026-02-02: 120; 2026-02-03: 120; 2026-02-04: 120; 2026-02-05: 120; 2026-02-06: 120; 2026-02-07: 120; 2026-02-08: 120; 2026-02-09: 120; 2026-02-10: 120; 2026-02-11: 120; 2026-02-12: 120; 2026-02-13: 120; 2026-02-14: 120; 2026-02-15: 120; 2026-02-16: 120; 2026-02-17: 120; 2026-02-18: 120; 2026-02-19: 120; 2026-02-20: 120; 2026-02-21: 120; 2026-02-22: 120; 2026-02-23: 120; 2026-02-24: 120; 2026-02-25: 120; 2026-02-26: 120; 2026-02-27: 120
|  |  |  | Manpower Details (A) | 2025-10-10: 75; 2025-10-11: 75; 2025-10-12: 75; 2025-10-13: 75; 2025-10-14: 75; 2025-10-15: 115; 2025-10-16: 115; 2025-10-17: 115; 2025-10-18: 115; 2025-10-19: 115; 2025-10-20: 115; 2025-10-21: 115; 2025-10-22: 115; 2025-10-23: 115; 2025-10-24: 115; 2025-10-25: 115; 2025-10-26: 115; 2025-10-27: 115; 2025-10-28: 115; 2025-10-29: 115; 2025-10-30: 115; 2025-10-31: 115; 2025-11-01: 115; 2025-11-02: 115; 2025-11-03: 115; 2025-11-04: 115; 2025-11-05: 115; 2025-11-06: 115; 2025-11-07: 115; 2025-11-08: 115; 2025-11-09: 115; 2025-11-10: 115; 2025-11-11: 115; 2025-11-12: 115; 2025-11-13: 115; 2025-11-14: 115; 2025-11-15: 115; 2025-11-16: 115; 2025-11-17: 115; 2025-11-18: 115; 2025-11-19: 115; 2025-11-20: 115; 2025-11-21: 115; 2025-11-22: 115; 2025-11-23: 115; 2025-11-24: 115; 2025-11-25: 115; 2025-11-26: 115; 2025-11-27: 115; 2025-11-28: 115; 2025-11-29: 115; 2025-11-30: 115; 2025-12-01: 115; 2025-12-02: 115; 2025-12-03: 115; 2025-12-04: 118; 2025-12-05: 118; 2025-12-06: 118; 2025-12-07: 118; 2025-12-08: 118; 2025-12-09: 118; 2025-12-10: 118; 2025-12-11: 118; 2025-12-12: 118; 2025-12-13: 118; 2025-12-14: 118; 2025-12-15: 118; 2025-12-16: 118; 2025-12-17: 118; 2025-12-18: 118; 2025-12-19: 118; 2025-12-20: 118; 2025-12-21: 118; 2025-12-22: 118; 2025-12-23: 118; 2025-12-24: 118; 2025-12-25: 118; 2025-12-26: 118; 2025-12-27: 118; 2025-12-28: 118; 2025-12-29: 118; 2025-12-30: 118; 2025-12-31: 118; 2026-01-01: 118; 2026-01-02: 118; 2026-01-03: 118; 2026-01-04: 118; 2026-01-05: 118; 2026-01-06: 118; 2026-01-07: 118; 2026-01-08: 118; 2026-01-09: 118; 2026-01-10: 118; 2026-01-11: 118; 2026-01-12: 118; 2026-01-13: 118; 2026-01-14: 118; 2026-01-15: 118; 2026-01-16: 118; 2026-01-17: 118; 2026-01-18: 118; 2026-01-19: 118; 2026-01-20: 118; 2026-01-21: 118; 2026-01-22: 118; 2026-01-23: 118; 2026-01-24: 118; 2026-01-25: 118; 2026-01-26: 118; 2026-01-27: 118; 2026-01-28: 118; 2026-01-29: 118; 2026-01-30: 118; 2026-01-31: 118; 2026-02-01: 118; 2026-02-02: 118; 2026-02-03: 118; 2026-02-04: 118; 2026-02-05: 118; 2026-02-06: 118; 2026-02-07: 118; 2026-02-08: 118; 2026-02-09: 118; 2026-02-10: 118; 2026-02-11: 118; 2026-02-12: 118; 2026-02-13: 118; 2026-02-14: 118; 2026-02-15: 118; 2026-02-16: 118; 2026-02-17: 118; 2026-02-18: 118; 2026-02-19: 118; 2026-02-20: 118; 2026-02-21: 118; 2026-02-22: 118; 2026-02-23: 118; 2026-02-24: 118; 2026-02-25: 118; 2026-02-26: 118; 2026-02-27: 118
55 | Dhairya Construction | Service | Erection/Material Handling | Manpower Details (P) | 2025-10-10: 30; 2025-10-11: 30; 2025-10-12: 30; 2025-10-13: 30; 2025-10-14: 30; 2025-10-15: 30; 2025-10-16: 30; 2025-10-17: 30; 2025-10-18: 30; 2025-10-19: 30; 2025-10-20: 30; 2025-10-21: 30; 2025-10-22: 30; 2025-10-23: 30; 2025-10-24: 30; 2025-10-25: 30; 2025-10-26: 30; 2025-10-27: 30; 2025-10-28: 30; 2025-10-29: 30; 2025-10-30: 30; 2025-10-31: 30; 2025-11-01: 30; 2025-11-02: 30; 2025-11-03: 30; 2025-11-04: 30; 2025-11-05: 30; 2025-11-06: 30; 2025-11-07: 30; 2025-11-08: 30; 2025-11-09: 30; 2025-11-10: 30; 2025-11-11: 30; 2025-11-12: 30; 2025-11-13: 30; 2025-11-14: 30; 2025-11-15: 30; 2025-11-16: 30; 2025-11-17: 30; 2025-11-18: 30; 2025-11-19: 30; 2025-11-20: 30; 2025-11-21: 30; 2025-11-22: 30; 2025-11-23: 30; 2025-11-24: 30; 2025-11-25: 30; 2025-11-26: 30; 2025-11-27: 30; 2025-11-28: 30; 2025-11-29: 30; 2025-11-30: 30; 2025-12-01: 30; 2025-12-02: 30; 2025-12-03: 30; 2025-12-04: 30; 2025-12-05: 30; 2025-12-06: 30; 2025-12-07: 30; 2025-12-08: 30; 2025-12-09: 30; 2025-12-10: 30; 2025-12-11: 30; 2025-12-12: 30; 2025-12-13: 30; 2025-12-14: 30; 2025-12-15: 30; 2025-12-16: 30; 2025-12-17: 30; 2025-12-18: 30; 2025-12-19: 30; 2025-12-20: 30; 2025-12-21: 30; 2025-12-22: 30; 2025-12-23: 30; 2025-12-24: 30; 2025-12-25: 30; 2025-12-26: 30; 2025-12-27: 30; 2025-12-28: 30; 2025-12-29: 30; 2025-12-30: 30; 2025-12-31: 30; 2026-01-01: 30; 2026-01-02: 30; 2026-01-03: 30; 2026-01-04: 30; 2026-01-05: 30; 2026-01-06: 30; 2026-01-07: 30; 2026-01-08: 30; 2026-01-09: 30; 2026-01-10: 30; 2026-01-11: 30; 2026-01-12: 30; 2026-01-13: 30; 2026-01-14: 30; 2026-01-15: 30; 2026-01-16: 30; 2026-01-17: 30; 2026-01-18: 30; 2026-01-19: 30; 2026-01-20: 30; 2026-01-21: 30; 2026-01-22: 30; 2026-01-23: 30; 2026-01-24: 30; 2026-01-25: 30; 2026-01-26: 30; 2026-01-27: 30; 2026-01-28: 30; 2026-01-29: 30; 2026-01-30: 30; 2026-01-31: 30; 2026-02-01: 30; 2026-02-02: 30; 2026-02-03: 30; 2026-02-04: 30; 2026-02-05: 30; 2026-02-06: 30; 2026-02-07: 30; 2026-02-08: 30; 2026-02-09: 30; 2026-02-10: 30; 2026-02-11: 30; 2026-02-12: 30; 2026-02-13: 30; 2026-02-14: 30; 2026-02-15: 30; 2026-02-16: 30; 2026-02-17: 30; 2026-02-18: 30; 2026-02-19: 30; 2026-02-20: 30; 2026-02-21: 30; 2026-02-22: 30; 2026-02-23: 30; 2026-02-24: 30; 2026-02-25: 30; 2026-02-26: 30; 2026-02-27: 30
|  |  |  | Manpower Details (A) | 2025-10-10: 21; 2025-10-11: 21; 2025-10-12: 21; 2025-10-13: 21; 2025-10-14: 21; 2025-10-15: 24; 2025-10-16: 24; 2025-10-17: 24; 2025-10-18: 24; 2025-10-19: 24; 2025-10-20: 24; 2025-10-21: 26; 2025-10-22: 26; 2025-10-23: 26; 2025-10-24: 26; 2025-10-25: 26; 2025-10-26: 28; 2025-10-27: 29; 2025-10-28: 27; 2025-10-29: 27; 2025-10-30: 27; 2025-10-31: 28; 2025-11-01: 28; 2025-11-02: 28; 2025-11-03: 29; 2025-11-04: 29; 2025-11-05: 29; 2025-11-06: 29; 2025-11-07: 31; 2025-11-08: 31; 2025-11-09: 31; 2025-11-10: 31; 2025-11-11: 30; 2025-11-12: 30; 2025-11-13: 30; 2025-11-14: 30; 2025-11-15: 30; 2025-11-16: 30; 2025-11-17: 30; 2025-11-18: 30; 2025-11-19: 30; 2025-11-20: 30; 2025-11-21: 30; 2025-11-22: 30; 2025-11-23: 30; 2025-11-24: 30; 2025-11-25: 30; 2025-11-26: 30; 2025-11-27: 30; 2025-11-28: 30; 2025-11-29: 30; 2025-11-30: 30; 2025-12-01: 30; 2025-12-02: 30; 2025-12-03: 30; 2025-12-04: 30; 2025-12-05: 30; 2025-12-06: 30; 2025-12-07: 30; 2025-12-08: 30; 2025-12-09: 30; 2025-12-10: 30; 2025-12-11: 30; 2025-12-12: 30; 2025-12-13: 30; 2025-12-14: 30; 2025-12-15: 30; 2025-12-16: 30; 2025-12-17: 30; 2025-12-18: 30; 2025-12-19: 30; 2025-12-20: 30; 2025-12-21: 30; 2025-12-22: 30; 2025-12-23: 30; 2025-12-24: 30; 2025-12-25: 30; 2025-12-26: 30; 2025-12-27: 30; 2025-12-28: 30; 2025-12-29: 30; 2025-12-30: 30; 2025-12-31: 30; 2026-01-01: 30; 2026-01-02: 30; 2026-01-03: 30; 2026-01-04: 30; 2026-01-05: 30; 2026-01-06: 30; 2026-01-07: 30; 2026-01-08: 30; 2026-01-09: 30; 2026-01-10: 30; 2026-01-11: 30; 2026-01-12: 30; 2026-01-13: 30; 2026-01-14: 30; 2026-01-15: 30; 2026-01-16: 30; 2026-01-17: 30; 2026-01-18: 30; 2026-01-19: 30; 2026-01-20: 30; 2026-01-21: 30; 2026-01-22: 30; 2026-01-23: 30; 2026-01-24: 30; 2026-01-25: 30; 2026-01-26: 30; 2026-01-27: 30; 2026-01-28: 30; 2026-01-29: 30; 2026-01-30: 30; 2026-01-31: 30; 2026-02-01: 30; 2026-02-02: 30; 2026-02-03: 30; 2026-02-04: 30; 2026-02-05: 30; 2026-02-06: 30; 2026-02-07: 30; 2026-02-08: 30; 2026-02-09: 30; 2026-02-10: 30; 2026-02-11: 30; 2026-02-12: 30; 2026-02-13: 30; 2026-02-14: 30; 2026-02-15: 30; 2026-02-16: 30; 2026-02-17: 30; 2026-02-18: 30; 2026-02-19: 30; 2026-02-20: 30; 2026-02-21: 30; 2026-02-22: 30; 2026-02-23: 30; 2026-02-24: 30; 2026-02-25: 30; 2026-02-26: 30; 2026-02-27: 30
56 | Perennial Energy pvt. Ltd | Service | Erection/Material Handling | Manpower Details (P) | 2025-10-10: 5; 2025-10-11: 5; 2025-10-12: 5; 2025-10-13: 5; 2025-10-14: 5; 2025-10-15: 5; 2025-10-16: 15; 2025-10-17: 15; 2025-10-18: 15; 2025-10-19: 15; 2025-10-20: 15; 2025-10-21: 15; 2025-10-22: 15; 2025-10-23: 15; 2025-10-24: 15; 2025-10-25: 15; 2025-10-26: 15; 2025-10-27: 15; 2025-10-28: 15; 2025-10-29: 15; 2025-10-30: 15; 2025-10-31: 15; 2025-11-01: 15; 2025-11-02: 15; 2025-11-03: 15; 2025-11-04: 15; 2025-11-05: 15; 2025-11-06: 15; 2025-11-07: 15; 2025-11-08: 15; 2025-11-09: 15; 2025-11-10: 15; 2025-11-11: 15; 2025-11-12: 15; 2025-11-13: 15; 2025-11-14: 15; 2025-11-15: 15; 2025-11-16: 15; 2025-11-17: 15; 2025-11-18: 15; 2025-11-19: 15; 2025-11-20: 15; 2025-11-21: 15; 2025-11-22: 15; 2025-11-23: 15; 2025-11-24: 15; 2025-11-25: 15; 2025-11-26: 15; 2025-11-27: 15; 2025-11-28: 15; 2025-11-29: 15; 2025-11-30: 15; 2025-12-01: 15; 2025-12-02: 15; 2025-12-03: 15; 2025-12-04: 15; 2025-12-05: 15; 2025-12-06: 15; 2025-12-07: 15; 2025-12-08: 15; 2025-12-09: 15; 2025-12-10: 15; 2025-12-11: 15; 2025-12-12: 15; 2025-12-13: 15; 2025-12-14: 15; 2025-12-15: 15; 2025-12-16: 15; 2025-12-17: 15; 2025-12-18: 15; 2025-12-19: 15; 2025-12-20: 15; 2025-12-21: 15; 2025-12-22: 15; 2025-12-23: 15; 2025-12-24: 15; 2025-12-25: 15; 2025-12-26: 15; 2025-12-27: 15; 2025-12-28: 15; 2025-12-29: 15; 2025-12-30: 15; 2025-12-31: 15; 2026-01-01: 15; 2026-01-02: 15; 2026-01-03: 15; 2026-01-04: 15; 2026-01-05: 15; 2026-01-06: 15; 2026-01-07: 15; 2026-01-08: 15; 2026-01-09: 15; 2026-01-10: 15; 2026-01-11: 15; 2026-01-12: 15; 2026-01-13: 15; 2026-01-14: 15; 2026-01-15: 15; 2026-01-16: 15; 2026-01-17: 15; 2026-01-18: 15; 2026-01-19: 15; 2026-01-20: 15; 2026-01-21: 15; 2026-01-22: 15; 2026-01-23: 15; 2026-01-24: 15; 2026-01-25: 15; 2026-01-26: 15; 2026-01-27: 15; 2026-01-28: 15; 2026-01-29: 15; 2026-01-30: 15; 2026-01-31: 15; 2026-02-01: 15; 2026-02-02: 15; 2026-02-03: 15; 2026-02-04: 15; 2026-02-05: 15; 2026-02-06: 15; 2026-02-07: 15; 2026-02-08: 15; 2026-02-09: 15; 2026-02-10: 15; 2026-02-11: 15; 2026-02-12: 15; 2026-02-13: 15; 2026-02-14: 15; 2026-02-15: 15; 2026-02-16: 15; 2026-02-17: 15; 2026-02-18: 15; 2026-02-19: 15; 2026-02-20: 15; 2026-02-21: 15; 2026-02-22: 15; 2026-02-23: 15; 2026-02-24: 15; 2026-02-25: 15; 2026-02-26: 15; 2026-02-27: 15
|  |  |  | Manpower Details (A) | 2025-10-10: 4; 2025-10-11: 4; 2025-10-12: 4; 2025-10-13: 4; 2025-10-14: 4; 2025-10-15: 4; 2025-10-16: 14; 2025-10-17: 14; 2025-10-18: 12; 2025-10-19: 12; 2025-10-20: 12; 2025-10-21: 12; 2025-10-22: 12; 2025-10-23: 12; 2025-10-24: 12; 2025-10-25: 12; 2025-10-26: 12; 2025-10-27: 12; 2025-10-28: 14; 2025-10-29: 14; 2025-10-30: 14; 2025-10-31: 14; 2025-11-01: 14; 2025-11-02: 14; 2025-11-03: 14; 2025-11-04: 14; 2025-11-05: 14; 2025-11-06: 14; 2025-11-07: 16; 2025-11-08: 16; 2025-11-09: 16; 2025-11-10: 16; 2025-11-11: 16; 2025-11-12: 16; 2025-11-13: 16; 2025-11-14: 16; 2025-11-15: 16; 2025-11-16: 16; 2025-11-17: 16; 2025-11-18: 16; 2025-11-19: 16; 2025-11-20: 16; 2025-11-21: 16; 2025-11-22: 16; 2025-11-23: 16; 2025-11-24: 16; 2025-11-25: 16; 2025-11-26: 16; 2025-11-27: 16; 2025-11-28: 19; 2025-11-29: 19; 2025-11-30: 19; 2025-12-01: 19; 2025-12-02: 19; 2025-12-03: 19; 2025-12-04: 15; 2025-12-05: 15; 2025-12-06: 15; 2025-12-07: 15; 2025-12-08: 15; 2025-12-09: 15; 2025-12-10: 15; 2025-12-11: 15; 2025-12-12: 15; 2025-12-13: 15; 2025-12-14: 15; 2025-12-15: 15; 2025-12-16: 15; 2025-12-17: 15; 2025-12-18: 15; 2025-12-19: 15; 2025-12-20: 15; 2025-12-21: 15; 2025-12-22: 15; 2025-12-23: 15; 2025-12-24: 15; 2025-12-25: 15; 2025-12-26: 15; 2025-12-27: 15; 2025-12-28: 15; 2025-12-29: 15; 2025-12-30: 15; 2025-12-31: 15; 2026-01-01: 15; 2026-01-02: 15; 2026-01-03: 15; 2026-01-04: 15; 2026-01-05: 15; 2026-01-06: 15; 2026-01-07: 15; 2026-01-08: 15; 2026-01-09: 15; 2026-01-10: 15; 2026-01-11: 15; 2026-01-12: 15; 2026-01-13: 15; 2026-01-14: 15; 2026-01-15: 15; 2026-01-16: 15; 2026-01-17: 15; 2026-01-18: 15; 2026-01-19: 15; 2026-01-20: 15; 2026-01-21: 15; 2026-01-22: 15; 2026-01-23: 15; 2026-01-24: 15; 2026-01-25: 15; 2026-01-26: 15; 2026-01-27: 15; 2026-01-28: 15; 2026-01-29: 15; 2026-01-30: 15; 2026-01-31: 15; 2026-02-01: 15; 2026-02-02: 15; 2026-02-03: 15; 2026-02-04: 15; 2026-02-05: 15; 2026-02-06: 15; 2026-02-07: 15; 2026-02-08: 15; 2026-02-09: 15; 2026-02-10: 15; 2026-02-11: 15; 2026-02-12: 15; 2026-02-13: 15; 2026-02-14: 15; 2026-02-15: 15; 2026-02-16: 15; 2026-02-17: 15; 2026-02-18: 15; 2026-02-19: 15; 2026-02-20: 15; 2026-02-21: 15; 2026-02-22: 15; 2026-02-23: 15; 2026-02-24: 15; 2026-02-25: 15; 2026-02-26: 15; 2026-02-27: 15
24 | L C Construction khavda | Service | Erection/Material Handling | Manpower Details (P) | 2025-11-07: 30; 2025-11-08: 30; 2025-11-09: 30; 2025-11-10: 30; 2025-11-11: 30; 2025-11-12: 30; 2025-11-13: 30; 2025-11-14: 30; 2025-11-15: 30; 2025-11-16: 30; 2025-11-17: 30; 2025-11-18: 30; 2025-11-19: 30; 2025-11-20: 30; 2025-11-21: 30; 2025-11-22: 30; 2025-11-23: 30; 2025-11-24: 30; 2025-11-25: 30; 2025-11-26: 30; 2025-11-27: 30; 2025-11-28: 30; 2025-11-29: 30; 2025-11-30: 30; 2025-12-01: 30; 2025-12-02: 30; 2025-12-03: 30; 2025-12-04: 30; 2025-12-05: 30; 2025-12-06: 30; 2025-12-07: 30; 2025-12-08: 30; 2025-12-09: 30; 2025-12-10: 30; 2025-12-11: 30; 2025-12-12: 30; 2025-12-13: 30; 2025-12-14: 30; 2025-12-15: 30; 2025-12-16: 30; 2025-12-17: 30; 2025-12-18: 30; 2025-12-19: 30; 2025-12-20: 30; 2025-12-21: 30; 2025-12-22: 30; 2025-12-23: 30; 2025-12-24: 30; 2025-12-25: 30; 2025-12-26: 30; 2025-12-27: 30; 2025-12-28: 30; 2025-12-29: 30; 2025-12-30: 30; 2025-12-31: 30; 2026-01-01: 30; 2026-01-02: 30; 2026-01-03: 30; 2026-01-04: 30; 2026-01-05: 30; 2026-01-06: 30; 2026-01-07: 30; 2026-01-08: 30; 2026-01-09: 30; 2026-01-10: 30; 2026-01-11: 30; 2026-01-12: 30; 2026-01-13: 30; 2026-01-14: 30; 2026-01-15: 30; 2026-01-16: 30; 2026-01-17: 30; 2026-01-18: 30; 2026-01-19: 30; 2026-01-20: 30; 2026-01-21: 30; 2026-01-22: 30; 2026-01-23: 30; 2026-01-24: 30; 2026-01-25: 30; 2026-01-26: 30; 2026-01-27: 30; 2026-01-28: 30; 2026-01-29: 30; 2026-01-30: 30; 2026-01-31: 30; 2026-02-01: 30; 2026-02-02: 30; 2026-02-03: 30; 2026-02-04: 30; 2026-02-05: 30; 2026-02-06: 30; 2026-02-07: 30; 2026-02-08: 30; 2026-02-09: 30; 2026-02-10: 30; 2026-02-11: 30; 2026-02-12: 30; 2026-02-13: 30; 2026-02-14: 30; 2026-02-15: 30; 2026-02-16: 30; 2026-02-17: 30; 2026-02-18: 30; 2026-02-19: 30; 2026-02-20: 30; 2026-02-21: 30; 2026-02-22: 30; 2026-02-23: 30; 2026-02-24: 30; 2026-02-25: 30; 2026-02-26: 30; 2026-02-27: 30
|  |  |  | Manpower Details (A) | 2025-11-07: 23; 2025-11-08: 23; 2025-11-09: 23; 2025-11-10: 23; 2025-11-11: 23; 2025-11-12: 23; 2025-11-13: 23; 2025-11-14: 23; 2025-11-15: 23; 2025-11-16: 23; 2025-11-17: 23; 2025-11-18: 23; 2025-11-19: 23; 2025-11-20: 23; 2025-11-21: 23; 2025-11-22: 23; 2025-11-23: 23; 2025-11-24: 23; 2025-11-25: 23; 2025-11-26: 23; 2025-11-27: 23; 2025-11-28: 23; 2025-11-29: 23; 2025-11-30: 23; 2025-12-01: 23; 2025-12-02: 23; 2025-12-03: 23; 2025-12-04: 23; 2025-12-05: 23; 2025-12-06: 23; 2025-12-07: 23; 2025-12-08: 23; 2025-12-09: 23; 2025-12-10: 23; 2025-12-11: 23; 2025-12-12: 23; 2025-12-13: 23; 2025-12-14: 23; 2025-12-15: 23; 2025-12-16: 23; 2025-12-17: 23; 2025-12-18: 23; 2025-12-19: 23; 2025-12-20: 23; 2025-12-21: 23; 2025-12-22: 23; 2025-12-23: 23; 2025-12-24: 23; 2025-12-25: 23; 2025-12-26: 23; 2025-12-27: 23; 2025-12-28: 23; 2025-12-29: 23; 2025-12-30: 23; 2025-12-31: 23; 2026-01-01: 23; 2026-01-02: 23; 2026-01-03: 23; 2026-01-04: 23; 2026-01-05: 23; 2026-01-06: 23; 2026-01-07: 23; 2026-01-08: 23; 2026-01-09: 23; 2026-01-10: 23; 2026-01-11: 23; 2026-01-12: 23; 2026-01-13: 23; 2026-01-14: 23; 2026-01-15: 23; 2026-01-16: 23; 2026-01-17: 23; 2026-01-18: 23; 2026-01-19: 23; 2026-01-20: 23; 2026-01-21: 23; 2026-01-22: 23; 2026-01-23: 23; 2026-01-24: 23; 2026-01-25: 23; 2026-01-26: 23; 2026-01-27: 23; 2026-01-28: 23; 2026-01-29: 23; 2026-01-30: 23; 2026-01-31: 23; 2026-02-01: 23; 2026-02-02: 23; 2026-02-03: 23; 2026-02-04: 23; 2026-02-05: 23; 2026-02-06: 23; 2026-02-07: 23; 2026-02-08: 23; 2026-02-09: 23; 2026-02-10: 23; 2026-02-11: 23; 2026-02-12: 23; 2026-02-13: 23; 2026-02-14: 23; 2026-02-15: 23; 2026-02-16: 23; 2026-02-17: 23; 2026-02-18: 23; 2026-02-19: 23; 2026-02-20: 23; 2026-02-21: 23; 2026-02-22: 23; 2026-02-23: 23; 2026-02-24: 23; 2026-02-25: 23; 2026-02-26: 23; 2026-02-27: 23
57 | M/s SK Engg (Erection) | Service | Erection | Manpower Details (P) | [161 empty] | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160
|  |  |  | Manpower Details (A) | [161 empty] | 40 | 40 | 36 | 39 | 40 | 38 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 38 | 40 | 38 | 18 | 40 | 18 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 8 | 9 | 3 | 9 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 50 | 42 | 47 | 0 | 0 | 0 | 0 | 54 | 55 | 51 | 33 | 16 | 46 | 45 | 44 | 42 | 45 | 42 | 48 | 48 | 48 | 86 | 42 | 70 | 23 | 23 | 20 | 23 | 51 | 34 | 29 | 28 | 28 | 41 | 41 | 41 | 41 | 31 | 31 | 31 | 31 | 31 | 31 | 47 | 51 | 57 | 44 | 47 | 56 | 107 | 109 | 108 | 100 | 94 | 96 | 87 | 87 | 93 | 107 | 82 | 72 | 89 | 85 | 97 | 92 | 98 | 89 | 114 | 114 | 100 | 101 | 101 | 101 | 101 | 53 | 53 | 126 | 126 | 126 | 126 | 98 | 83 | 83 | 96 | 106 | 103 | 102 | 119 | 114 | 119 | 120 | 120 | 103 | 111 | 109 | 114 | 106 | 102 | 120 | 120 | 133 | 118 | 132 | 123 | 123 | 123 | 124 | 128 | 129 | 143 | 126 | 127 | 133 | 127 | 130 | 127 | 133 | 122 | 135 | 135 | 150 | 148 | 148 | 148 | 148 | 149 | 146 | 147 | 147 | 147 | 151 | 146 | 146 | 149 | 140 | 145 | 136 | 136 | 146 | 146 | 146 | 146 | 144 | 146 | 138 | 133 | 138 | 138 | 131 | 129 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 107 | 98 | 100 | 100 | 113 | 96 | 96 | 103 | 108 | 97 | 97 | 100 | 92 | 102 | 104 | 104 | 92 | 97 | 90 | 89 | 89 | 100 | 97 | 92 | 83 | 89 | 101
58 | M/s J S & Sons (Erection) | Service | Erection | Manpower Details (P) | [163 empty] | 40 | 40 | 40 | 40 | 40 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 80 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160
|  |  |  | Manpower Details (A) | [163 empty] | 32 | 30 | 23 | 54 | 36 | 78 | 63 | 75 | 73 | 76 | 74 | 77 | 77 | 76 | 76 | 74 | 75 | 76 | 77 | 79 | 79 | 78 | 74 | 74 | 64 | 91 | 91 | 68 | 70 | 84 | 76 | 90 | 90 | 44 | 45 | 38 | 38 | 38 | 36 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 19 | 20 | 36 | 19 | 17 | 18 | 22 | 39 | 35 | 37 | 34 | 32 | 35 | 34 | 31 | 28 | 31 | 34 | 68 | 68 | 69 | 69 | 56 | 57 | 51 | 80 | 76 | 77 | 75 | 60 | 65 | 69 | 70 | 40 | 36 | 41 | 47 | 45 | 48 | 45 | 39 | 40 | 40 | 39 | 39 | 39 | 41 | 41 | 38 | 40 | 0 | 4 | 10 | 46 | 45 | 87 | 76 | 92 | 73 | 76 | 76 | 76 | 76 | 76 | 76 | 92 | 90 | 86 | 90 | 82 | 69 | 137 | 126 | 120 | 123 | 107 | 107 | 110 | 110 | 96 | 114 | 112 | 112 | 111 | 111 | 110 | 109 | 106 | 104 | 126 | 126 | 117 | 124 | 124 | 124 | 124 | 70 | 70 | 120 | 120 | 120 | 120 | 82 | 88 | 88 | 73 | 92 | 99 | 99 | 117 | 113 | 107 | 112 | 112 | 106 | 106 | 116 | 100 | 116 | 122 | 132 | 117 | 118 | 115 | 115 | 147 | 150 | 150 | 146 | 142 | 154 | 152 | 157 | 161 | 160 | 150 | 152 | 153 | 148 | 145 | 149 | 159 | 153 | 155 | 155 | 144 | 145 | 155 | 155 | 155 | 157 | 157 | 154 | 147 | 147 | 141 | 143 | 153 | 150 | 155 | 133 | 144 | 140 | 144 | 143 | 144 | 148 | 147 | 148 | 148 | 162 | 146 | 146 | 151 | 146 | 146 | 146 | 146 | 146 | 143 | 143 | 143 | 143 | 143 | 143 | 112 | 64 | 143 | 143 | 89 | 102 | 102 | 130 | 141 | 142 | 142 | 135 | 135 | 139 | 102 | 106 | 135 | 130 | 125 | 143 | 143 | 141 | 132 | 123 | 127 | 115 | 131
59 | M/s I R (Erection) | Service | Erection | Manpower Details (P) | 2025-06-13: 40; 2025-06-14: 40; 2025-06-15: 40; 2025-06-16: 40; 2025-06-17: 40; 2025-06-18: 80; 2025-06-19: 80; 2025-06-20: 80; 2025-06-21: 80; 2025-06-22: 80; 2025-06-23: 80; 2025-06-24: 80; 2025-06-25: 80; 2025-06-26: 80; 2025-06-27: 80; 2025-06-28: 80; 2025-06-29: 80; 2025-06-30: 80; 2025-10-10: 40; 2025-10-11: 40; 2025-10-12: 40; 2025-10-13: 40; 2025-10-14: 40; 2025-10-15: 40; 2025-10-16: 40; 2025-10-17: 40; 2025-10-18: 40; 2025-10-19: 40; 2025-10-20: 40; 2025-10-21: 40; 2025-10-22: 40; 2025-10-23: 40; 2025-10-24: 40; 2025-10-25: 40; 2025-10-26: 40; 2025-10-27: 40; 2025-10-28: 40; 2025-10-29: 40; 2025-10-30: 40; 2025-10-31: 40; 2025-11-01: 40; 2025-11-02: 40; 2025-11-03: 40; 2025-11-04: 40; 2025-11-05: 80; 2025-11-06: 80; 2025-11-07: 80; 2025-11-08: 80; 2025-11-09: 80; 2025-11-10: 80; 2025-11-11: 80; 2025-11-12: 80; 2025-11-13: 80; 2025-11-14: 80; 2025-11-15: 80; 2025-11-16: 80; 2025-11-17: 80; 2025-11-18: 80; 2025-11-19: 80; 2025-11-20: 80; 2025-11-21: 80; 2025-11-22: 80; 2025-11-23: 80; 2025-11-24: 80; 2025-11-25: 80; 2025-11-26: 80; 2025-11-27: 80; 2025-11-28: 80; 2025-11-29: 80; 2025-11-30: 80; 2025-12-01: 80; 2025-12-02: 80; 2025-12-03: 80; 2025-12-04: 80; 2025-12-05: 80; 2025-12-06: 80; 2025-12-07: 80; 2025-12-08: 80; 2025-12-09: 80; 2025-12-10: 80; 2025-12-11: 80; 2025-12-12: 80; 2025-12-13: 80; 2025-12-14: 80; 2025-12-15: 80; 2025-12-16: 80; 2025-12-17: 80; 2025-12-18: 80; 2025-12-19: 80; 2025-12-20: 80; 2025-12-21: 80; 2025-12-22: 80; 2025-12-23: 80; 2025-12-24: 80; 2025-12-25: 80; 2025-12-26: 80; 2025-12-27: 80; 2025-12-28: 80; 2025-12-29: 80; 2025-12-30: 80; 2025-12-31: 80; 2026-01-01: 80; 2026-01-02: 80; 2026-01-03: 80; 2026-01-04: 80; 2026-01-05: 80; 2026-01-06: 80; 2026-01-07: 80; 2026-01-08: 80; 2026-01-09: 80; 2026-01-10: 80; 2026-01-11: 80; 2026-01-12: 80; 2026-01-13: 80; 2026-01-14: 80; 2026-01-15: 80; 2026-01-16: 80; 2026-01-17: 80; 2026-01-18: 80; 2026-01-19: 80; 2026-01-20: 80; 2026-01-21: 80; 2026-01-22: 80; 2026-01-23: 80; 2026-01-24: 80; 2026-01-25: 80; 2026-01-26: 80; 2026-01-27: 80; 2026-01-28: 80; 2026-01-29: 80; 2026-01-30: 80; 2026-01-31: 80; 2026-02-01: 80; 2026-02-02: 80; 2026-02-03: 80; 2026-02-04: 80; 2026-02-05: 80; 2026-02-06: 80; 2026-02-07: 80; 2026-02-08: 80; 2026-02-09: 80; 2026-02-10: 80; 2026-02-11: 80; 2026-02-12: 80; 2026-02-13: 80; 2026-02-14: 80; 2026-02-15: 80; 2026-02-16: 80; 2026-02-17: 80; 2026-02-18: 80; 2026-02-19: 80; 2026-02-20: 80; 2026-02-21: 80; 2026-02-22: 80; 2026-02-23: 80; 2026-02-24: 80; 2026-02-25: 80; 2026-02-26: 80; 2026-02-27: 80
|  |  |  | Manpower Details (A) | 2025-06-13: 32; 2025-06-14: 30; 2025-06-15: 23; 2025-06-16: 54; 2025-06-17: 36; 2025-06-18: 78; 2025-06-19: 63; 2025-06-20: 75; 2025-06-21: 73; 2025-06-22: 76; 2025-06-23: 74; 2025-06-24: 77; 2025-06-25: 77; 2025-06-26: 76; 2025-06-27: 76; 2025-06-28: 74; 2025-06-29: 75; 2025-06-30: 76; 2025-10-10: 33; 2025-10-11: 39; 2025-10-12: 39; 2025-10-13: 39; 2025-10-14: 39; 2025-10-15: 39; 2025-10-16: 29; 2025-10-17: 29; 2025-10-18: 35; 2025-10-19: 34; 2025-10-20: 32; 2025-10-21: 32; 2025-10-22: 34; 2025-10-23: 32; 2025-10-24: 31; 2025-10-25: 33; 2025-10-26: 32; 2025-10-27: 32; 2025-10-28: 44; 2025-10-29: 44; 2025-10-30: 35; 2025-10-31: 36; 2025-11-01: 36; 2025-11-02: 36; 2025-11-03: 36; 2025-11-04: 52; 2025-11-05: 52; 2025-11-06: 78; 2025-11-07: 78; 2025-11-08: 78; 2025-11-09: 78; 2025-11-10: 66; 2025-11-11: 63; 2025-11-12: 63; 2025-11-13: 62; 2025-11-14: 64; 2025-11-15: 61; 2025-11-16: 63; 2025-11-17: 58; 2025-11-18: 38; 2025-11-19: 53; 2025-11-20: 57; 2025-11-21: 57; 2025-11-22: 53; 2025-11-23: 50; 2025-11-24: 63; 2025-11-25: 65; 2025-11-26: 60; 2025-11-27: 60; 2025-11-28: 58; 2025-11-29: 59; 2025-11-30: 59; 2025-12-01: 59; 2025-12-02: 59; 2025-12-03: 57; 2025-12-04: 56; 2025-12-05: 56; 2025-12-06: 57; 2025-12-07: 66; 2025-12-08: 58; 2025-12-09: 149; 2025-12-10: 53; 2025-12-11: 58; 2025-12-12: 63; 2025-12-13: 45; 2025-12-14: 44; 2025-12-15: 48; 2025-12-16: 49; 2025-12-17: 54; 2025-12-18: 52; 2025-12-19: 57; 2025-12-20: 48; 2025-12-21: 57; 2025-12-22: 57; 2025-12-23: 54; 2025-12-24: 57; 2025-12-25: 53; 2025-12-26: 53; 2025-12-27: 57; 2025-12-28: 56; 2025-12-29: 56; 2025-12-30: 50; 2025-12-31: 55; 2026-01-01: 55; 2026-01-02: 49; 2026-01-03: 50; 2026-01-04: 50; 2026-01-05: 49; 2026-01-06: 51; 2026-01-07: 52; 2026-01-08: 52; 2026-01-09: 52; 2026-01-10: 52; 2026-01-11: 45; 2026-01-12: 50; 2026-01-13: 54; 2026-01-14: 54; 2026-01-15: 54; 2026-01-16: 54; 2026-01-17: 57; 2026-01-18: 57; 2026-01-19: 61; 2026-01-20: 55; 2026-01-21: 61; 2026-01-22: 61; 2026-01-23: 61; 2026-01-24: 61; 2026-01-25: 61; 2026-01-26: 60; 2026-01-27: 60; 2026-01-28: 60; 2026-01-29: 60; 2026-01-30: 60; 2026-01-31: 60; 2026-02-01: 70; 2026-02-02: 56; 2026-02-03: 60; 2026-02-04: 60; 2026-02-05: 60; 2026-02-06: 70; 2026-02-07: 70; 2026-02-08: 70; 2026-02-09: 66; 2026-02-10: 70; 2026-02-11: 71; 2026-02-12: 74; 2026-02-13: 74; 2026-02-14: 70; 2026-02-15: 73; 2026-02-16: 58; 2026-02-17: 41; 2026-02-18: 60; 2026-02-19: 55; 2026-02-20: 60; 2026-02-21: 60; 2026-02-22: 70; 2026-02-23: 66; 2026-02-24: 61; 2026-02-25: 62; 2026-02-26: 61; 2026-02-27: 61
60 | M/s Maa Khamakya (Erection) | Service | Erection | Manpower Details (P) | [166 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 0 | 70 | 70 | 70 | 70 | 70 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
|  |  |  | Manpower Details (A) | [166 empty] | 35 | 33 | 38 | 33 | 31 | 30 | 30 | 28 | 30 | 32 | 31 | 31 | 31 | 31 | 39 | 39 | 39 | 32 | 33 | 33 | 33 | 37 | 34 | 34 | 35 | 35 | 39 | 36 | 30 | 30 | 39 | 34 | 32 | 38 | 36 | 34 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 56 | 0 | 0 | 33 | 35 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 37 | 37 | 37 | 37 | 36 | 37 | 30 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 34 | 34 | 72 | 37 | 37 | 74 | 74 | 74 | 74 | 57 | 73 | 72 | 72 | 72 | 72 | 72 | 72 | 76 | 75 | 75 | 76 | 75 | 76 | 83 | 81 | 83 | 49 | 37 | 40 | 41 | 41 | 45 | 28 | 26 | 18 | 25 | 22 | 30 | 28 | 26 | 26 | 36 | 36 | 37 | 35 | 35 | 35 | 35 | 31 | 31 | 49 | 49 | 49 | 49 | 52 | 40 | 40 | 41 | 38 | 28 | 29 | 31 | 43 | 43 | 27 | 27 | 56 | 53 | 62 | 56 | 60 | 58 | 55 | 62 | 62 | 53 | 53 | 57 | 53 | 53 | 51 | 60 | 47 | 47 | 47 | 47 | 50 | 44 | 42 | 43 | 41 | 42 | 43 | 47 | 62 | 57 | 57 | 36 | 57 | 57 | 57 | 57 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 40 | 44 | 47 | 42 | 42 | 42 | 42 | 39 | 40 | 38 | 41 | 38 | 38 | 38 | 53 | 52 | 54 | 52 | 52 | 52 | 52 | 52 | 48 | 48 | 48 | 48 | 48 | 48 | 64 | 60 | 62 | 62 | 50 | 42 | 42 | 49 | 40 | 42 | 52 | 50 | 55 | 26 | 30 | 30 | 56 | 57 | 57 | 56 | 56 | 53 | 56 | 47 | 41 | 33 | 37
61 | M/s Yash Engg (Erection) | Service | Erection | Manpower Details (P) | [168 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  |  |  | Manpower Details (A) | [168 empty] | 32 | 33 | 35 | 30 | 32 | 31 | 36 | 38 | 42 | 40 | 37 | 38 | 36 | 33 | 37 | 34 | 35 | 35 | 35 | 42 | 41 | 41 | 31 | 35 | 49 | 36 | 14 | 14 | 4 | 4 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 26 | 28 | 28 | 28 | 31 | 30 | 32 | 32 | 30 | 29 | 31 | 29 | 30 | 29 | 27 | 29 | 29 | 30 | 28 | 28 | 34 | 33 | 39 | 36 | 37 | 7 | 34 | 20 | 27 | 35 | 34 | 29 | 38 | 38 | 38 | 38 | 38 | 39 | 41 | 40 | 36 | 37 | 37 | 39 | 39 | 39 | 35 | 34 | 32 | 33 | 34 | 33 | 33 | 33 | 22 | 28 | 27 | 27 | 27 | 17 | 17 | 17 | 17 | 17 | 17 | 15 | 17 | 17 | 16 | 20 | 20 | 17 | 17 | 17 | 16 | 16 | 16 | 14 | 14 | 18 | 18 | 17 | 14 | 22 | 15 | 15 | 14 | 14 | 15 | 18 | 18 | 18 | 25 | 25 | 25 | 25 | 22 | 22 | 26 | 26 | 26 | 26 | 8 | 17 | 17 | 16 | 8 | 16 | 34 | 34 | 20 | 20 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 25 | 27 | 30 | 32 | 32 | 25 | 31 | 31 | 34 | 33 | 33 | 25 | 25 | 26 | 21 | 22 | 23 | 21 | 24 | 22 | 21 | 15 | 18 | 18 | 18 | 22 | 18 | 19 | 19 | 19 | 14 | 14 | 15 | 15 | 15 | 15 | 9 | 11 | 10 | 7 | 14 | 14 | 14 | 14 | 12 | 12 | 12 | 10 | 12 | 12 | 11 | 16 | 20 | 21 | 20 | 20 | 20 | 20 | 20 | 18 | 18 | 18 | 18 | 18 | 18 | 20 | 18 | 19 | 19 | 31 | 22 | 22 | 30 | 31 | 29 | 26 | 29 | 30 | 28 | 30 | 30 | 29 | 30 | 32 | 32 | 32 | 26 | 31 | 22 | 28 | 29 | 20
62 | M/s Vidhi Wind (Erection) | Service | Erection | Manpower Details (P) | 2025-08-18: 40; 2025-08-19: 40; 2025-08-20: 40; 2025-08-21: 40; 2025-08-22: 40; 2025-08-23: 40; 2025-08-24: 40; 2025-08-25: 40; 2025-08-26: 40; 2025-08-27: 40; 2025-08-28: 40; 2025-08-29: 40; 2025-08-30: 40; 2025-08-31: 40; 2025-09-01: 40; 2025-09-02: 40; 2025-09-03: 40; 2025-09-04: 40; 2025-09-05: 40; 2025-09-06: 40; 2025-09-07: 40; 2025-09-08: 40; 2025-09-09: 40; 2025-09-10: 40; 2025-09-11: 40; 2025-09-12: 40; 2025-09-13: 40; 2025-09-14: 40; 2025-09-15: 40; 2025-09-16: 40; 2025-09-17: 40; 2025-09-18: 40; 2025-09-19: 40; 2025-09-20: 40; 2025-09-21: 40; 2025-09-22: 40; 2025-09-23: 40; 2025-09-24: 40; 2025-09-25: 40; 2025-09-26: 40; 2025-09-27: 40; 2025-09-28: 40; 2025-09-29: 40; 2025-09-30: 40; 2025-10-01: 40; 2025-10-02: 40; 2025-10-03: 40; 2025-10-04: 40; 2025-10-05: 40; 2025-10-06: 40; 2025-10-07: 40; 2025-10-08: 40; 2025-10-09: 40; 2025-10-10: 80; 2025-10-11: 40; 2025-10-12: 40; 2025-10-13: 40; 2025-10-14: 40; 2025-10-15: 40; 2025-10-16: 40; 2025-10-17: 40; 2025-10-18: 40; 2025-10-19: 40; 2025-10-20: 40; 2025-10-21: 40; 2025-10-22: 40; 2025-10-23: 40; 2025-10-24: 40; 2025-10-25: 40; 2025-10-26: 40; 2025-10-27: 40; 2025-10-28: 40; 2025-10-29: 40; 2025-10-30: 40; 2025-10-31: 40; 2025-11-01: 40; 2025-11-02: 40; 2025-11-03: 40; 2025-11-04: 40; 2025-11-05: 40; 2025-11-06: 40; 2025-11-07: 40; 2025-11-08: 40; 2025-11-09: 40; 2025-11-10: 40; 2025-11-11: 40; 2025-11-12: 40; 2025-11-13: 40; 2025-11-14: 40; 2025-11-15: 40; 2025-11-16: 40; 2025-11-17: 40; 2025-11-18: 40; 2025-11-19: 40; 2025-11-20: 40; 2025-11-21: 40; 2025-11-22: 40; 2025-11-23: 40; 2025-11-24: 40; 2025-11-25: 40; 2025-11-26: 40; 2025-11-27: 40; 2025-11-28: 40; 2025-11-29: 40; 2025-11-30: 40; 2025-12-01: 40; 2025-12-02: 40; 2025-12-03: 40; 2025-12-04: 40; 2025-12-05: 40; 2025-12-06: 40; 2025-12-07: 40; 2025-12-08: 40; 2025-12-09: 40; 2025-12-10: 40; 2025-12-11: 110; 2025-12-12: 110; 2025-12-13: 110; 2025-12-14: 110; 2025-12-15: 110; 2025-12-16: 110; 2025-12-17: 110; 2025-12-18: 110; 2025-12-19: 110; 2025-12-20: 110; 2025-12-21: 110; 2025-12-22: 110; 2025-12-23: 110; 2025-12-24: 110; 2025-12-25: 110; 2025-12-26: 110; 2025-12-27: 110; 2025-12-28: 110; 2025-12-29: 110; 2025-12-30: 110; 2025-12-31: 110; 2026-01-01: 110; 2026-01-02: 110; 2026-01-03: 110; 2026-01-04: 110; 2026-01-05: 110; 2026-01-06: 110; 2026-01-07: 110; 2026-01-08: 110; 2026-01-09: 110; 2026-01-10: 110; 2026-01-11: 110; 2026-01-12: 110; 2026-01-13: 110; 2026-01-14: 110; 2026-01-15: 110; 2026-01-16: 110; 2026-01-17: 110; 2026-01-18: 110; 2026-01-19: 110; 2026-01-20: 110; 2026-01-21: 110; 2026-01-22: 110; 2026-01-23: 110; 2026-01-24: 110; 2026-01-25: 110; 2026-01-26: 110; 2026-01-27: 110; 2026-01-28: 110; 2026-01-29: 110; 2026-01-30: 110; 2026-01-31: 110; 2026-02-01: 110; 2026-02-02: 110; 2026-02-03: 110; 2026-02-04: 110; 2026-02-05: 110; 2026-02-06: 110; 2026-02-07: 110; 2026-02-08: 110; 2026-02-09: 110; 2026-02-10: 110; 2026-02-11: 110; 2026-02-12: 110; 2026-02-13: 110; 2026-02-14: 110; 2026-02-15: 110; 2026-02-16: 110; 2026-02-17: 110; 2026-02-18: 110; 2026-02-19: 110; 2026-02-20: 110; 2026-02-21: 110; 2026-02-22: 110; 2026-02-23: 110; 2026-02-24: 110; 2026-02-25: 110; 2026-02-26: 110; 2026-02-27: 110
|  |  |  | Manpower Details (A) | 2025-08-18: 40; 2025-08-19: 40; 2025-08-20: 0; 2025-08-21: 17; 2025-08-22: 44; 2025-08-23: 28; 2025-08-24: 35; 2025-08-25: 32; 2025-08-26: 30; 2025-08-27: 32; 2025-08-28: 28; 2025-08-29: 7; 2025-08-30: 14; 2025-08-31: 17; 2025-09-01: 0; 2025-09-02: 0; 2025-09-03: 27; 2025-09-04: 37; 2025-09-05: 37; 2025-09-06: 34; 2025-09-07: 36; 2025-09-08: 34; 2025-09-09: 36; 2025-09-10: 37; 2025-09-11: 37; 2025-09-12: 37; 2025-09-13: 37; 2025-09-14: 37; 2025-09-15: 40; 2025-09-16: 40; 2025-09-17: 40; 2025-09-18: 38; 2025-09-19: 40; 2025-09-20: 49; 2025-09-21: 40; 2025-09-22: 66; 2025-09-23: 38; 2025-09-24: 33; 2025-09-25: 37; 2025-09-26: 37; 2025-09-27: 37; 2025-09-28: 37; 2025-09-29: 37; 2025-09-30: 37; 2025-10-01: 37; 2025-10-02: 37; 2025-10-03: 37; 2025-10-04: 52; 2025-10-05: 37; 2025-10-06: 36; 2025-10-07: 40; 2025-10-08: 34; 2025-10-09: 34; 2025-10-10: 36; 2025-10-11: 26; 2025-10-12: 36; 2025-10-13: 49; 2025-10-14: 57; 2025-10-15: 54; 2025-10-16: 68; 2025-10-17: 68; 2025-10-18: 41; 2025-10-19: 38; 2025-10-20: 50; 2025-10-21: 49; 2025-10-22: 51; 2025-10-23: 37; 2025-10-24: 35; 2025-10-25: 38; 2025-10-26: 37; 2025-10-27: 45; 2025-10-28: 30; 2025-10-29: 30; 2025-10-30: 30; 2025-10-31: 30; 2025-11-01: 30; 2025-11-02: 63; 2025-11-03: 30; 2025-11-04: 65; 2025-11-05: 65; 2025-11-06: 60; 2025-11-07: 61; 2025-11-08: 61; 2025-11-09: 61; 2025-11-10: 56; 2025-11-11: 71; 2025-11-12: 71; 2025-11-13: 49; 2025-11-14: 63; 2025-11-15: 62; 2025-11-16: 68; 2025-11-17: 62; 2025-11-18: 61; 2025-11-19: 60; 2025-11-20: 62; 2025-11-21: 62; 2025-11-22: 61; 2025-11-23: 61; 2025-11-24: 61; 2025-11-25: 61; 2025-11-26: 63; 2025-11-27: 63; 2025-11-28: 74; 2025-11-29: 69; 2025-11-30: 78; 2025-12-01: 77; 2025-12-02: 77; 2025-12-03: 77; 2025-12-04: 82; 2025-12-05: 82; 2025-12-06: 78; 2025-12-07: 76; 2025-12-08: 66; 2025-12-09: 73; 2025-12-10: 72; 2025-12-11: 103; 2025-12-12: 96; 2025-12-13: 72; 2025-12-14: 70; 2025-12-15: 73; 2025-12-16: 75; 2025-12-17: 70; 2025-12-18: 77; 2025-12-19: 72; 2025-12-20: 90; 2025-12-21: 92; 2025-12-22: 92; 2025-12-23: 79; 2025-12-24: 92; 2025-12-25: 92; 2025-12-26: 77; 2025-12-27: 94; 2025-12-28: 79; 2025-12-29: 79; 2025-12-30: 80; 2025-12-31: 86; 2026-01-01: 86; 2026-01-02: 75; 2026-01-03: 89; 2026-01-04: 87; 2026-01-05: 83; 2026-01-06: 78; 2026-01-07: 79; 2026-01-08: 70; 2026-01-09: 79; 2026-01-10: 79; 2026-01-11: 75; 2026-01-12: 70; 2026-01-13: 78; 2026-01-14: 79; 2026-01-15: 78; 2026-01-16: 78; 2026-01-17: 76; 2026-01-18: 76; 2026-01-19: 80; 2026-01-20: 77; 2026-01-21: 80; 2026-01-22: 80; 2026-01-23: 80; 2026-01-24: 80; 2026-01-25: 80; 2026-01-26: 75; 2026-01-27: 75; 2026-01-28: 75; 2026-01-29: 75; 2026-01-30: 75; 2026-01-31: 75; 2026-02-01: 73; 2026-02-02: 44; 2026-02-03: 79; 2026-02-04: 79; 2026-02-05: 72; 2026-02-06: 85; 2026-02-07: 85; 2026-02-08: 79; 2026-02-09: 76; 2026-02-10: 84; 2026-02-11: 81; 2026-02-12: 81; 2026-02-13: 81; 2026-02-14: 80; 2026-02-15: 73; 2026-02-16: 79; 2026-02-17: 73; 2026-02-18: 74; 2026-02-19: 74; 2026-02-20: 74; 2026-02-21: 74; 2026-02-22: 66; 2026-02-23: 70; 2026-02-24: 72; 2026-02-25: 71; 2026-02-26: 96; 2026-02-27: 81
63 | M/s Prateek plant service (Erection) | Service | Erection | Manpower Details (P) | 2025-06-13: 40; 2025-06-14: 40; 2025-06-15: 40; 2025-06-16: 40; 2025-06-17: 40; 2025-06-18: 80; 2025-06-19: 80; 2025-06-20: 80; 2025-06-21: 80; 2025-06-22: 80; 2025-06-23: 80; 2025-06-24: 80; 2025-06-25: 80; 2025-06-26: 80; 2025-06-27: 80; 2025-06-28: 80; 2025-06-29: 80; 2025-06-30: 80; 2025-10-10: 10; 2025-10-11: 10; 2025-10-12: 10; 2025-10-13: 10; 2025-10-14: 10; 2025-10-15: 10; 2025-10-16: 10; 2025-10-17: 10; 2025-10-18: 10; 2025-10-19: 10; 2025-10-20: 10; 2025-10-21: 10; 2025-10-22: 10; 2025-10-23: 10; 2025-10-24: 10; 2025-10-25: 10; 2025-10-26: 10; 2025-10-27: 10; 2025-10-28: 10; 2025-10-29: 10; 2025-10-30: 10; 2025-10-31: 10; 2025-11-01: 10; 2025-11-02: 10; 2025-11-03: 10; 2025-11-04: 10; 2025-11-05: 10; 2025-11-06: 10; 2025-11-07: 10; 2025-11-08: 10; 2025-11-09: 10; 2025-11-10: 10; 2025-11-11: 10; 2025-11-12: 10; 2025-11-13: 10; 2025-11-14: 10; 2025-11-15: 10; 2025-11-16: 10; 2025-11-17: 10; 2025-11-18: 10; 2025-11-19: 10; 2025-11-20: 10; 2025-11-21: 10; 2025-11-22: 10; 2025-11-23: 10; 2025-11-24: 10; 2025-11-25: 10; 2025-11-26: 10; 2025-11-27: 10; 2025-11-28: 10; 2025-11-29: 10; 2025-11-30: 10; 2025-12-01: 10; 2025-12-02: 10; 2025-12-03: 10; 2025-12-04: 10; 2025-12-05: 10; 2025-12-06: 10; 2025-12-07: 10; 2025-12-08: 10; 2025-12-09: 10; 2025-12-10: 10; 2025-12-11: 10; 2025-12-12: 10; 2025-12-13: 10; 2025-12-14: 10; 2025-12-15: 10; 2025-12-16: 10; 2025-12-17: 10; 2025-12-18: 10; 2025-12-19: 10; 2025-12-20: 10; 2025-12-21: 10; 2025-12-22: 10; 2025-12-23: 10; 2025-12-24: 10; 2025-12-25: 10; 2025-12-26: 10; 2025-12-27: 10; 2025-12-28: 10; 2025-12-29: 10; 2025-12-30: 10; 2025-12-31: 10; 2026-01-01: 10; 2026-01-02: 10; 2026-01-03: 10; 2026-01-04: 10; 2026-01-05: 10; 2026-01-06: 10; 2026-01-07: 10; 2026-01-08: 10; 2026-01-09: 10; 2026-01-10: 10; 2026-01-11: 10; 2026-01-12: 10; 2026-01-13: 10; 2026-01-14: 10; 2026-01-15: 10; 2026-01-16: 10; 2026-01-17: 10; 2026-01-18: 10; 2026-01-19: 10; 2026-01-20: 10; 2026-01-21: 10; 2026-01-22: 10; 2026-01-23: 10; 2026-01-24: 10; 2026-01-25: 10; 2026-01-26: 10; 2026-01-27: 10; 2026-01-28: 10; 2026-01-29: 10; 2026-01-30: 10; 2026-01-31: 10; 2026-02-01: 10; 2026-02-02: 10; 2026-02-03: 10; 2026-02-04: 10; 2026-02-05: 10; 2026-02-06: 10; 2026-02-07: 10; 2026-02-08: 10; 2026-02-09: 10; 2026-02-10: 10; 2026-02-11: 10; 2026-02-12: 10; 2026-02-13: 10; 2026-02-14: 10; 2026-02-15: 10; 2026-02-16: 10; 2026-02-17: 10; 2026-02-18: 10; 2026-02-19: 10; 2026-02-20: 10; 2026-02-21: 10; 2026-02-22: 10; 2026-02-23: 10; 2026-02-24: 10; 2026-02-25: 10; 2026-02-26: 10; 2026-02-27: 10
|  |  |  | Manpower Details (A) | 2025-06-13: 32; 2025-06-14: 30; 2025-06-15: 23; 2025-06-16: 54; 2025-06-17: 36; 2025-06-18: 78; 2025-06-19: 63; 2025-06-20: 75; 2025-06-21: 73; 2025-06-22: 76; 2025-06-23: 74; 2025-06-24: 77; 2025-06-25: 77; 2025-06-26: 76; 2025-06-27: 76; 2025-06-28: 74; 2025-06-29: 75; 2025-06-30: 76; 2025-10-10: 6; 2025-10-11: 6; 2025-10-12: 5; 2025-10-13: 7; 2025-10-14: 7; 2025-10-15: 7; 2025-10-16: 8; 2025-10-17: 8; 2025-10-18: 0; 2025-10-19: 0; 2025-10-20: 0; 2025-10-21: 0; 2025-10-22: 0; 2025-10-23: 0; 2025-10-24: 0; 2025-10-25: 0; 2025-10-26: 0; 2025-10-27: 0; 2025-10-28: 7; 2025-10-29: 7; 2025-10-30: 7; 2025-10-31: 8; 2025-11-01: 8; 2025-11-02: 8; 2025-11-03: 8; 2025-11-04: 8; 2025-11-05: 8; 2025-11-06: 8; 2025-11-07: 8; 2025-11-08: 8; 2025-11-09: 8; 2025-11-10: 8; 2025-11-11: 8; 2025-11-12: 8; 2025-11-13: 8; 2025-11-14: 8; 2025-11-15: 8; 2025-11-16: 8; 2025-11-17: 8; 2025-11-18: 8; 2025-11-19: 8; 2025-11-20: 8; 2025-11-21: 8; 2025-11-22: 8; 2025-11-23: 8; 2025-11-24: 8; 2025-11-25: 8; 2025-11-26: 8; 2025-11-27: 8; 2025-11-28: 8; 2025-11-29: 8; 2025-11-30: 8; 2025-12-01: 8; 2025-12-02: 8; 2025-12-03: 8; 2025-12-04: 8; 2025-12-05: 8; 2025-12-06: 8; 2025-12-07: 8; 2025-12-08: 8; 2025-12-09: 8; 2025-12-10: 8; 2025-12-11: 8; 2025-12-12: 8; 2025-12-13: 8; 2025-12-14: 8; 2025-12-15: 8; 2025-12-16: 8; 2025-12-17: 8; 2025-12-18: 8; 2025-12-19: 8; 2025-12-20: 8; 2025-12-21: 8; 2025-12-22: 8; 2025-12-23: 8; 2025-12-24: 8; 2025-12-25: 8; 2025-12-26: 8; 2025-12-27: 8; 2025-12-28: 8; 2025-12-29: 8; 2025-12-30: 8; 2025-12-31: 8; 2026-01-01: 8; 2026-01-02: 8; 2026-01-03: 8; 2026-01-04: 8; 2026-01-05: 8; 2026-01-06: 8; 2026-01-07: 8; 2026-01-08: 8; 2026-01-09: 8; 2026-01-10: 8; 2026-01-11: 8; 2026-01-12: 8; 2026-01-13: 8; 2026-01-14: 8; 2026-01-15: 8; 2026-01-16: 8; 2026-01-17: 8; 2026-01-18: 8; 2026-01-19: 8; 2026-01-20: 8; 2026-01-21: 8; 2026-01-22: 8; 2026-01-23: 8; 2026-01-24: 8; 2026-01-25: 8; 2026-01-26: 8; 2026-01-27: 8; 2026-01-28: 8; 2026-01-29: 8; 2026-01-30: 8; 2026-01-31: 8; 2026-02-01: 8; 2026-02-02: 8; 2026-02-03: 8; 2026-02-04: 8; 2026-02-05: 8; 2026-02-06: 9; 2026-02-07: 9; 2026-02-08: 9; 2026-02-09: 9; 2026-02-10: 9; 2026-02-11: 9; 2026-02-12: 9; 2026-02-13: 9; 2026-02-14: 9; 2026-02-15: 9; 2026-02-16: 9; 2026-02-17: 9; 2026-02-18: 9; 2026-02-19: 9; 2026-02-21: 9; 2026-02-22: 9; 2026-02-23: 9; 2026-02-26: 9; 2026-02-27: 9
64 | M/s ABS Equipment (Erection) | Service | Erection | Manpower Details (P) | 2025-06-13: 40; 2025-06-14: 40; 2025-06-15: 40; 2025-06-16: 40; 2025-06-17: 40; 2025-06-18: 80; 2025-06-19: 80; 2025-06-20: 80; 2025-06-21: 80; 2025-06-22: 80; 2025-06-23: 80; 2025-06-24: 80; 2025-06-25: 80; 2025-06-26: 80; 2025-06-27: 80; 2025-06-28: 80; 2025-06-29: 80; 2025-06-30: 80; 2025-10-10: 70; 2025-10-11: 70; 2025-10-12: 70; 2025-10-13: 70; 2025-10-14: 70; 2025-10-15: 70; 2025-10-16: 70; 2025-10-17: 70; 2025-10-18: 70; 2025-10-19: 70; 2025-10-20: 70; 2025-10-21: 70; 2025-10-22: 70; 2025-10-23: 70; 2025-10-24: 70; 2025-10-25: 70; 2025-10-26: 70; 2025-10-27: 70; 2025-10-28: 70; 2025-10-29: 70; 2025-10-30: 70; 2025-10-31: 70; 2025-11-01: 70; 2025-11-02: 70; 2025-11-03: 70; 2025-11-04: 70; 2025-11-05: 70; 2025-11-06: 70; 2025-11-07: 70; 2025-11-08: 70; 2025-11-09: 70; 2025-11-10: 70; 2025-11-11: 70; 2025-11-12: 70; 2025-11-13: 70; 2025-11-14: 70; 2025-11-15: 70; 2025-11-16: 70; 2025-11-17: 70; 2025-11-18: 70; 2025-11-19: 70; 2025-11-20: 70; 2025-11-21: 70; 2025-11-22: 70; 2025-11-23: 70; 2025-11-24: 70; 2025-11-25: 70; 2025-11-26: 70; 2025-11-27: 70; 2025-11-28: 70; 2025-11-29: 70; 2025-11-30: 70; 2025-12-01: 70; 2025-12-02: 70; 2025-12-03: 70; 2025-12-04: 70; 2025-12-05: 70; 2025-12-06: 70; 2025-12-07: 70; 2025-12-08: 70; 2025-12-09: 70; 2025-12-10: 70; 2025-12-11: 70; 2025-12-12: 70; 2025-12-13: 70; 2025-12-14: 70; 2025-12-15: 70; 2025-12-16: 70; 2025-12-17: 70; 2025-12-18: 70; 2025-12-19: 70; 2025-12-20: 70; 2025-12-21: 70; 2025-12-22: 70; 2025-12-23: 70; 2025-12-24: 70; 2025-12-25: 70; 2025-12-26: 70; 2025-12-27: 70; 2025-12-28: 70; 2025-12-29: 70; 2025-12-30: 70; 2025-12-31: 70; 2026-01-01: 70; 2026-01-02: 70; 2026-01-03: 70; 2026-01-04: 70; 2026-01-05: 70; 2026-01-06: 70; 2026-01-07: 70; 2026-01-08: 70; 2026-01-09: 70; 2026-01-10: 70; 2026-01-11: 70; 2026-01-12: 70; 2026-01-13: 70; 2026-01-14: 70; 2026-01-15: 70; 2026-01-16: 70; 2026-01-17: 70; 2026-01-18: 70; 2026-01-19: 70; 2026-01-20: 70; 2026-01-21: 70; 2026-01-22: 70; 2026-01-23: 70; 2026-01-24: 70; 2026-01-25: 70; 2026-01-26: 70; 2026-01-27: 70; 2026-01-28: 70; 2026-01-29: 70; 2026-01-30: 70; 2026-01-31: 70; 2026-02-01: 70; 2026-02-02: 70; 2026-02-03: 70; 2026-02-04: 70; 2026-02-05: 70; 2026-02-06: 70; 2026-02-07: 70; 2026-02-08: 70; 2026-02-09: 70; 2026-02-10: 70; 2026-02-11: 70; 2026-02-12: 70; 2026-02-13: 70; 2026-02-14: 70; 2026-02-15: 70; 2026-02-16: 70; 2026-02-17: 70; 2026-02-18: 70; 2026-02-19: 70; 2026-02-20: 70; 2026-02-21: 70; 2026-02-22: 70; 2026-02-23: 70; 2026-02-24: 70; 2026-02-25: 70; 2026-02-26: 70; 2026-02-27: 70
|  |  |  | Manpower Details (A) | 2025-06-13: 32; 2025-06-14: 30; 2025-06-15: 23; 2025-06-16: 54; 2025-06-17: 36; 2025-06-18: 78; 2025-06-19: 63; 2025-06-20: 75; 2025-06-21: 73; 2025-06-22: 76; 2025-06-23: 74; 2025-06-24: 77; 2025-06-25: 77; 2025-06-26: 76; 2025-06-27: 76; 2025-06-28: 74; 2025-06-29: 75; 2025-06-30: 76; 2025-10-10: 66; 2025-10-11: 66; 2025-10-12: 66; 2025-10-13: 66; 2025-10-14: 66; 2025-10-15: 66; 2025-10-16: 68; 2025-10-17: 68; 2025-10-18: 68; 2025-10-19: 0; 2025-10-20: 68; 2025-10-21: 68; 2025-10-22: 68; 2025-10-23: 68; 2025-10-24: 68; 2025-10-25: 68; 2025-10-26: 68; 2025-10-27: 68; 2025-10-28: 66; 2025-10-29: 66; 2025-10-30: 66; 2025-10-31: 66; 2025-11-01: 66; 2025-11-02: 66; 2025-11-03: 66; 2025-11-04: 57; 2025-11-05: 57; 2025-11-06: 57; 2025-11-07: 57; 2025-11-08: 57; 2025-11-09: 57; 2025-11-10: 63; 2025-11-11: 63; 2025-11-12: 63; 2025-11-13: 63; 2025-11-14: 63; 2025-11-15: 63; 2025-11-16: 63; 2025-11-17: 63; 2025-11-18: 63; 2025-11-19: 63; 2025-11-20: 63; 2025-11-21: 63; 2025-11-22: 63; 2025-11-23: 63; 2025-11-24: 63; 2025-11-25: 63; 2025-11-26: 63; 2025-11-27: 63; 2025-11-28: 63; 2025-11-29: 63; 2025-11-30: 63; 2025-12-01: 63; 2025-12-02: 63; 2025-12-03: 63; 2025-12-04: 63; 2025-12-05: 63; 2025-12-06: 63; 2025-12-07: 63; 2025-12-08: 63; 2025-12-09: 63; 2025-12-10: 63; 2025-12-11: 63; 2025-12-12: 63; 2025-12-13: 63; 2025-12-14: 63; 2025-12-15: 63; 2025-12-16: 63; 2025-12-17: 63; 2025-12-18: 63; 2025-12-19: 63; 2025-12-20: 63; 2025-12-21: 63; 2025-12-22: 63; 2025-12-23: 63; 2025-12-24: 63; 2025-12-25: 63; 2025-12-26: 63; 2025-12-27: 63; 2025-12-28: 63; 2025-12-29: 63; 2025-12-30: 63; 2025-12-31: 63; 2026-01-01: 63; 2026-01-02: 63; 2026-01-03: 63; 2026-01-04: 63; 2026-01-05: 63; 2026-01-06: 63; 2026-01-07: 63; 2026-01-08: 63; 2026-01-09: 63; 2026-01-10: 63; 2026-01-11: 63; 2026-01-12: 63; 2026-01-13: 64; 2026-01-14: 64; 2026-01-15: 64; 2026-01-16: 64; 2026-01-17: 64; 2026-01-18: 64; 2026-01-19: 64; 2026-01-20: 64; 2026-01-21: 64; 2026-01-22: 64; 2026-01-23: 64; 2026-01-24: 64; 2026-01-25: 64; 2026-01-26: 60; 2026-01-27: 60; 2026-01-28: 60; 2026-01-29: 60; 2026-01-30: 60; 2026-01-31: 60; 2026-02-01: 60; 2026-02-02: 60; 2026-02-03: 60; 2026-02-04: 60; 2026-02-05: 60; 2026-02-06: 49; 2026-02-07: 49; 2026-02-08: 63; 2026-02-09: 63; 2026-02-10: 63; 2026-02-11: 64; 2026-02-12: 64; 2026-02-13: 63; 2026-02-14: 64; 2026-02-15: 63; 2026-02-16: 63; 2026-02-17: 64; 2026-02-18: 62; 2026-02-19: 60; 2026-02-20: 60; 2026-02-21: 60; 2026-02-22: 64; 2026-02-23: 64; 2026-02-24: 64; 2026-02-25: 64; 2026-02-26: 64; 2026-02-27: 65
65 | M/s Tritorc equipment (Erection) | Service | Erection | Manpower Details (P) | 2025-06-13: 40; 2025-06-14: 40; 2025-06-15: 40; 2025-06-16: 40; 2025-06-17: 40; 2025-06-18: 80; 2025-06-19: 80; 2025-06-20: 80; 2025-06-21: 80; 2025-06-22: 80; 2025-06-23: 80; 2025-06-24: 80; 2025-06-25: 80; 2025-06-26: 80; 2025-06-27: 80; 2025-06-28: 80; 2025-06-29: 80; 2025-06-30: 80; 2025-10-10: 30; 2025-10-11: 30; 2025-10-12: 30; 2025-10-13: 30; 2025-10-14: 30; 2025-10-15: 30; 2025-10-16: 30; 2025-10-17: 30; 2025-10-18: 30; 2025-10-19: 30; 2025-10-20: 30; 2025-10-21: 30; 2025-10-22: 30; 2025-10-23: 30; 2025-10-24: 30; 2025-10-25: 30; 2025-10-26: 30; 2025-10-27: 30; 2025-10-28: 30; 2025-10-29: 30; 2025-10-30: 30; 2025-10-31: 30; 2025-11-01: 30; 2025-11-02: 30; 2025-11-03: 30; 2025-11-04: 30; 2025-11-05: 30; 2025-11-06: 30; 2025-11-07: 30; 2025-11-08: 30; 2025-11-09: 30; 2025-11-10: 30; 2025-11-11: 30; 2025-11-12: 30; 2025-11-13: 30; 2025-11-14: 30; 2025-11-15: 30; 2025-11-16: 30; 2025-11-17: 30; 2025-11-18: 30; 2025-11-19: 30; 2025-11-20: 30; 2025-11-21: 30; 2025-11-22: 30; 2025-11-23: 30; 2025-11-24: 30; 2025-11-25: 30; 2025-11-26: 30; 2025-11-27: 30; 2025-11-28: 30; 2025-11-29: 30; 2025-11-30: 30; 2025-12-01: 30; 2025-12-02: 30; 2025-12-03: 30; 2025-12-04: 30; 2025-12-05: 30; 2025-12-06: 30; 2025-12-07: 30; 2025-12-08: 30; 2025-12-09: 30; 2025-12-10: 30; 2025-12-11: 30; 2025-12-12: 30; 2025-12-13: 30; 2025-12-14: 30; 2025-12-15: 30; 2025-12-16: 30; 2025-12-17: 30; 2025-12-18: 30; 2025-12-19: 30; 2025-12-20: 30; 2025-12-21: 30; 2025-12-22: 30; 2025-12-23: 30; 2025-12-24: 30; 2025-12-25: 30; 2025-12-26: 30; 2025-12-27: 30; 2025-12-28: 30; 2025-12-29: 30; 2025-12-30: 30; 2025-12-31: 30; 2026-01-01: 30; 2026-01-02: 30; 2026-01-03: 30; 2026-01-04: 30; 2026-01-05: 30; 2026-01-06: 30; 2026-01-07: 30; 2026-01-08: 30; 2026-01-09: 30; 2026-01-10: 30; 2026-01-11: 30; 2026-01-12: 30; 2026-01-13: 30; 2026-01-14: 30; 2026-01-15: 30; 2026-01-16: 30; 2026-01-17: 30; 2026-01-18: 30; 2026-01-19: 30; 2026-01-20: 30; 2026-01-21: 30; 2026-01-22: 30; 2026-01-23: 30; 2026-01-24: 30; 2026-01-25: 30; 2026-01-26: 30; 2026-01-27: 30; 2026-01-28: 30; 2026-01-29: 30; 2026-01-30: 30; 2026-01-31: 30; 2026-02-01: 30; 2026-02-02: 30; 2026-02-03: 30; 2026-02-04: 30; 2026-02-05: 30; 2026-02-06: 30; 2026-02-07: 30; 2026-02-08: 30; 2026-02-09: 30; 2026-02-10: 30; 2026-02-11: 30; 2026-02-12: 30; 2026-02-13: 30; 2026-02-14: 30; 2026-02-15: 30; 2026-02-16: 30; 2026-02-17: 30; 2026-02-18: 30; 2026-02-19: 30; 2026-02-20: 30; 2026-02-21: 30; 2026-02-22: 30; 2026-02-23: 30; 2026-02-24: 30; 2026-02-25: 30; 2026-02-26: 30; 2026-02-27: 30
|  |  |  | Manpower Details (A) | 2025-06-13: 32; 2025-06-14: 30; 2025-06-15: 23; 2025-06-16: 54; 2025-06-17: 36; 2025-06-18: 78; 2025-06-19: 63; 2025-06-20: 75; 2025-06-21: 73; 2025-06-22: 76; 2025-06-23: 74; 2025-06-24: 77; 2025-06-25: 77; 2025-06-26: 76; 2025-06-27: 76; 2025-06-28: 74; 2025-06-29: 75; 2025-06-30: 76; 2025-10-10: 27; 2025-10-11: 27; 2025-10-12: 27; 2025-10-13: 27; 2025-10-14: 27; 2025-10-15: 27; 2025-10-16: 24; 2025-10-17: 24; 2025-10-18: 29; 2025-10-19: 0; 2025-10-20: 24; 2025-10-21: 24; 2025-10-22: 24; 2025-10-23: 24; 2025-10-24: 24; 2025-10-25: 24; 2025-10-26: 24; 2025-10-27: 24; 2025-10-28: 27; 2025-10-29: 27; 2025-10-30: 27; 2025-10-31: 27; 2025-11-01: 27; 2025-11-02: 27; 2025-11-03: 27; 2025-11-04: 20; 2025-11-05: 20; 2025-11-06: 20; 2025-11-07: 20; 2025-11-08: 20; 2025-11-09: 20; 2025-11-10: 24; 2025-11-11: 24; 2025-11-12: 24; 2025-11-13: 24; 2025-11-14: 24; 2025-11-15: 24; 2025-11-16: 24; 2025-11-17: 24; 2025-11-18: 24; 2025-11-19: 24; 2025-11-20: 24; 2025-11-21: 24; 2025-11-22: 24; 2025-11-23: 24; 2025-11-24: 24; 2025-11-25: 24; 2025-11-26: 24; 2025-11-27: 24; 2025-11-28: 24; 2025-11-29: 24; 2025-11-30: 24; 2025-12-01: 24; 2025-12-02: 24; 2025-12-03: 24; 2025-12-04: 24; 2025-12-05: 24; 2025-12-06: 24; 2025-12-07: 24; 2025-12-08: 24; 2025-12-09: 24; 2025-12-10: 24; 2025-12-11: 24; 2025-12-12: 24; 2025-12-13: 24; 2025-12-14: 24; 2025-12-15: 24; 2025-12-16: 24; 2025-12-17: 24; 2025-12-18: 24; 2025-12-19: 24; 2025-12-20: 24; 2025-12-21: 24; 2025-12-22: 24; 2025-12-23: 24; 2025-12-24: 24; 2025-12-25: 24; 2025-12-26: 24; 2025-12-27: 24; 2025-12-28: 24; 2025-12-29: 24; 2025-12-30: 24; 2025-12-31: 24; 2026-01-01: 24; 2026-01-02: 24; 2026-01-03: 24; 2026-01-04: 24; 2026-01-05: 24; 2026-01-06: 24; 2026-01-07: 24; 2026-01-08: 24; 2026-01-09: 24; 2026-01-10: 24; 2026-01-11: 24; 2026-01-12: 24; 2026-01-13: 29; 2026-01-14: 29; 2026-01-15: 29; 2026-01-16: 29; 2026-01-17: 29; 2026-01-18: 29; 2026-01-19: 29; 2026-01-20: 29; 2026-01-21: 29; 2026-01-22: 29; 2026-01-23: 29; 2026-01-24: 29; 2026-01-25: 29; 2026-01-26: 27; 2026-01-27: 27; 2026-01-28: 27; 2026-01-29: 27; 2026-01-30: 27; 2026-01-31: 27; 2026-02-01: 27; 2026-02-02: 27; 2026-02-03: 27; 2026-02-04: 27; 2026-02-05: 27; 2026-02-06: 27; 2026-02-07: 27; 2026-02-08: 28; 2026-02-09: 27; 2026-02-10: 31; 2026-02-11: 32; 2026-02-12: 32; 2026-02-13: 31; 2026-02-14: 30; 2026-02-15: 31; 2026-02-16: 31; 2026-02-17: 32; 2026-02-18: 31; 2026-02-19: 31; 2026-02-20: 31; 2026-02-21: 31; 2026-02-22: 32; 2026-02-23: 32; 2026-02-24: 32; 2026-02-25: 31; 2026-02-26: 31; 2026-02-27: 32
65 | M/s X-Tore (Erection) | Service | Erection | Manpower Details (P) | 2025-06-13: 40; 2025-06-14: 40; 2025-06-15: 40; 2025-06-16: 40; 2025-06-17: 40; 2025-06-18: 80; 2025-06-19: 80; 2025-06-20: 80; 2025-06-21: 80; 2025-06-22: 80; 2025-06-23: 80; 2025-06-24: 80; 2025-06-25: 80; 2025-06-26: 80; 2025-06-27: 80; 2025-06-28: 80; 2025-06-29: 80; 2025-06-30: 80; 2025-12-30: 8; 2025-12-31: 8; 2026-01-01: 8; 2026-01-02: 8; 2026-01-03: 8; 2026-01-04: 8; 2026-01-05: 8; 2026-01-06: 8; 2026-01-07: 8; 2026-01-08: 8; 2026-01-09: 8; 2026-01-10: 8; 2026-01-11: 8; 2026-01-12: 8; 2026-01-13: 8; 2026-01-14: 8; 2026-01-15: 8; 2026-01-16: 8; 2026-01-17: 8; 2026-01-18: 8; 2026-01-19: 8; 2026-01-20: 8; 2026-01-21: 8; 2026-01-22: 8; 2026-01-23: 8; 2026-01-24: 8; 2026-01-25: 8; 2026-01-26: 8; 2026-01-27: 8; 2026-01-28: 8; 2026-01-29: 8; 2026-01-30: 8; 2026-01-31: 8; 2026-02-01: 8; 2026-02-02: 8; 2026-02-03: 8; 2026-02-04: 8; 2026-02-05: 8; 2026-02-06: 8; 2026-02-07: 8; 2026-02-08: 8; 2026-02-09: 8; 2026-02-10: 8; 2026-02-11: 8; 2026-02-12: 8; 2026-02-13: 8; 2026-02-14: 8; 2026-02-15: 8; 2026-02-16: 8; 2026-02-17: 8; 2026-02-18: 8; 2026-02-19: 8; 2026-02-20: 8; 2026-02-21: 8; 2026-02-22: 8; 2026-02-23: 8; 2026-02-24: 8; 2026-02-25: 8; 2026-02-26: 8; 2026-02-27: 8
|  |  |  | Manpower Details (A) | 2025-06-13: 32; 2025-06-14: 30; 2025-06-15: 23; 2025-06-16: 54; 2025-06-17: 36; 2025-06-18: 78; 2025-06-19: 63; 2025-06-20: 75; 2025-06-21: 73; 2025-06-22: 76; 2025-06-23: 74; 2025-06-24: 77; 2025-06-25: 77; 2025-06-26: 76; 2025-06-27: 76; 2025-06-28: 74; 2025-06-29: 75; 2025-06-30: 76; 2025-12-30: 7; 2025-12-31: 7; 2026-01-01: 7; 2026-01-02: 7; 2026-01-03: 7; 2026-01-04: 7; 2026-01-05: 7; 2026-01-06: 7; 2026-01-07: 7; 2026-01-08: 7; 2026-01-09: 7; 2026-01-10: 7; 2026-01-11: 7; 2026-01-12: 7; 2026-01-13: 7; 2026-01-14: 7; 2026-01-15: 7; 2026-01-16: 7; 2026-01-17: 7; 2026-01-18: 7; 2026-01-19: 7; 2026-01-20: 7; 2026-01-21: 7; 2026-01-22: 7; 2026-01-23: 7; 2026-01-24: 7; 2026-01-25: 7; 2026-01-26: 7; 2026-01-27: 7; 2026-01-28: 7; 2026-01-29: 7; 2026-01-30: 7; 2026-01-31: 7; 2026-02-01: 7; 2026-02-02: 7; 2026-02-03: 7; 2026-02-04: 7; 2026-02-05: 7; 2026-02-06: 7; 2026-02-07: 6; 2026-02-08: 6; 2026-02-09: 6; 2026-02-10: 6; 2026-02-11: 6; 2026-02-12: 6; 2026-02-13: 4; 2026-02-14: 4; 2026-02-15: 4; 2026-02-16: 4; 2026-02-17: 4; 2026-02-18: 4; 2026-02-19: 4; 2026-02-20: 4; 2026-02-21: 4; 2026-02-22: 4; 2026-02-23: 4; 2026-02-24: 4; 2026-02-25: 6; 2026-02-26: 6; 2026-02-27: 6
66 | M/s H.S Engineering (logistics) | Service | Logistics | Manpower Details (P) | 2025-06-13: 40; 2025-06-14: 40; 2025-06-15: 40; 2025-06-16: 40; 2025-06-17: 40; 2025-06-18: 80; 2025-06-19: 80; 2025-06-20: 80; 2025-06-21: 80; 2025-06-22: 80; 2025-06-23: 80; 2025-06-24: 80; 2025-06-25: 80; 2025-06-26: 80; 2025-06-27: 80; 2025-06-28: 80; 2025-06-29: 80; 2025-06-30: 80; 2025-10-10: 35; 2025-10-11: 35; 2025-10-12: 35; 2025-10-13: 35; 2025-10-14: 35; 2025-10-15: 35; 2025-10-16: 35; 2025-10-17: 35; 2025-10-18: 35; 2025-10-19: 35; 2025-10-20: 35; 2025-10-21: 35; 2025-10-22: 35; 2025-10-23: 35; 2025-10-24: 35; 2025-10-25: 35; 2025-10-26: 35; 2025-10-27: 35; 2025-10-28: 35; 2025-10-29: 35; 2025-10-30: 35; 2025-10-31: 35; 2025-11-01: 35; 2025-11-02: 35; 2025-11-03: 35; 2025-11-04: 35; 2025-11-05: 35; 2025-11-06: 35; 2025-11-07: 35; 2025-11-08: 35; 2025-11-09: 35; 2025-11-10: 35; 2025-11-11: 35; 2025-11-12: 35; 2025-11-13: 35; 2025-11-14: 35; 2025-11-15: 35; 2025-11-16: 35; 2025-11-17: 35; 2025-11-18: 35; 2025-11-19: 35; 2025-11-20: 35; 2025-11-21: 35; 2025-11-22: 35; 2025-11-23: 35; 2025-11-24: 35; 2025-11-25: 35; 2025-11-26: 35; 2025-11-27: 35; 2025-11-28: 35; 2025-11-29: 35; 2025-11-30: 35; 2025-12-01: 35; 2025-12-02: 35; 2025-12-03: 35; 2025-12-04: 35; 2025-12-05: 35; 2025-12-06: 35; 2025-12-07: 35; 2025-12-08: 35; 2025-12-09: 35; 2025-12-10: 35; 2025-12-11: 35; 2025-12-12: 35; 2025-12-13: 35; 2025-12-14: 35; 2025-12-15: 35; 2025-12-16: 35; 2025-12-17: 35; 2025-12-18: 35; 2025-12-19: 35; 2025-12-20: 35; 2025-12-21: 35; 2025-12-22: 35; 2025-12-23: 35; 2025-12-24: 35; 2025-12-25: 35; 2025-12-26: 35; 2025-12-27: 35; 2025-12-28: 35; 2025-12-29: 35; 2025-12-30: 35; 2025-12-31: 35; 2026-01-01: 35; 2026-01-02: 35; 2026-01-03: 35; 2026-01-04: 35; 2026-01-05: 35; 2026-01-06: 35; 2026-01-07: 35; 2026-01-08: 35; 2026-01-09: 35; 2026-01-10: 35; 2026-01-11: 35; 2026-01-12: 35; 2026-01-13: 35; 2026-01-14: 35; 2026-01-15: 35; 2026-01-16: 35; 2026-01-17: 35; 2026-01-18: 35; 2026-01-19: 35; 2026-01-20: 35; 2026-01-21: 35; 2026-01-22: 35; 2026-01-23: 35; 2026-01-24: 35; 2026-01-25: 35; 2026-01-26: 35; 2026-01-27: 35; 2026-01-28: 35; 2026-01-29: 35; 2026-01-30: 35; 2026-01-31: 35; 2026-02-01: 35; 2026-02-02: 35; 2026-02-03: 35; 2026-02-04: 35; 2026-02-05: 35; 2026-02-06: 35; 2026-02-07: 35; 2026-02-08: 35; 2026-02-09: 35; 2026-02-10: 35; 2026-02-11: 35; 2026-02-12: 35; 2026-02-13: 35; 2026-02-14: 35; 2026-02-15: 35; 2026-02-16: 35; 2026-02-17: 35; 2026-02-18: 35; 2026-02-19: 35; 2026-02-20: 35; 2026-02-21: 35; 2026-02-22: 35; 2026-02-23: 35; 2026-02-24: 35; 2026-02-25: 35; 2026-02-26: 35; 2026-02-27: 35
|  |  |  | Manpower Details (A) | 2025-06-13: 32; 2025-06-14: 30; 2025-06-15: 23; 2025-06-16: 54; 2025-06-17: 36; 2025-06-18: 78; 2025-06-19: 63; 2025-06-20: 75; 2025-06-21: 73; 2025-06-22: 76; 2025-06-23: 74; 2025-06-24: 77; 2025-06-25: 77; 2025-06-26: 76; 2025-06-27: 76; 2025-06-28: 74; 2025-06-29: 75; 2025-06-30: 76; 2025-10-10: 32; 2025-10-11: 32; 2025-10-12: 32; 2025-10-13: 32; 2025-10-14: 32; 2025-10-15: 32; 2025-10-16: 20; 2025-10-17: 20; 2025-10-18: 0; 2025-10-19: 0; 2025-10-20: 35; 2025-10-21: 35; 2025-10-22: 35; 2025-10-23: 35; 2025-10-24: 35; 2025-10-25: 35; 2025-10-26: 35; 2025-10-27: 35; 2025-10-28: 32; 2025-10-29: 32; 2025-10-30: 32; 2025-10-31: 32; 2025-11-01: 32; 2025-11-02: 32; 2025-11-03: 32; 2025-11-04: 32; 2025-11-05: 32; 2025-11-06: 32; 2025-11-07: 32; 2025-11-08: 32; 2025-11-09: 32; 2025-11-10: 32; 2025-11-11: 32; 2025-11-12: 32; 2025-11-13: 32; 2025-11-14: 32; 2025-11-15: 32; 2025-11-16: 32; 2025-11-17: 32; 2025-11-18: 32; 2025-11-19: 32; 2025-11-20: 32; 2025-11-21: 32; 2025-11-22: 32; 2025-11-23: 32; 2025-11-24: 32; 2025-11-25: 32; 2025-11-26: 32; 2025-11-27: 32; 2025-11-28: 32; 2025-11-29: 32; 2025-11-30: 32; 2025-12-01: 32; 2025-12-02: 32; 2025-12-03: 32; 2025-12-04: 32; 2025-12-05: 32; 2025-12-06: 32; 2025-12-07: 32; 2025-12-08: 32; 2025-12-09: 32; 2025-12-10: 32; 2025-12-11: 32; 2025-12-12: 32; 2025-12-13: 32; 2025-12-14: 32; 2025-12-15: 32; 2025-12-16: 32; 2025-12-17: 32; 2025-12-18: 32; 2025-12-19: 32; 2025-12-20: 32; 2025-12-21: 32; 2025-12-22: 32; 2025-12-23: 32; 2025-12-24: 32; 2025-12-25: 32; 2025-12-26: 32; 2025-12-27: 32; 2025-12-28: 32; 2025-12-29: 32; 2025-12-30: 32; 2025-12-31: 32; 2026-01-01: 32; 2026-01-02: 32; 2026-01-03: 32; 2026-01-04: 32; 2026-01-05: 32; 2026-01-06: 32; 2026-01-07: 32; 2026-01-08: 32; 2026-01-09: 32; 2026-01-10: 32; 2026-01-11: 32; 2026-01-12: 32; 2026-01-13: 35; 2026-01-14: 35; 2026-01-15: 35; 2026-01-16: 35; 2026-01-17: 35; 2026-01-18: 35; 2026-01-19: 35; 2026-01-20: 35; 2026-01-21: 35; 2026-01-22: 35; 2026-01-23: 35; 2026-01-24: 35; 2026-01-25: 35; 2026-01-26: 33; 2026-01-27: 33; 2026-01-28: 33; 2026-01-29: 33; 2026-01-30: 33; 2026-01-31: 33; 2026-02-01: 33; 2026-02-02: 33; 2026-02-03: 33; 2026-02-04: 33; 2026-02-05: 33; 2026-02-06: 33; 2026-02-07: 33; 2026-02-08: 33; 2026-02-09: 33; 2026-02-10: 33; 2026-02-11: 33; 2026-02-12: 33; 2026-02-13: 33; 2026-02-14: 35; 2026-02-15: 33; 2026-02-16: 33; 2026-02-17: 30; 2026-02-18: 30; 2026-02-19: 30; 2026-02-20: 30; 2026-02-21: 30; 2026-02-22: 30; 2026-02-23: 35; 2026-02-24: 35; 2026-02-25: 35; 2026-02-26: 35; 2026-02-27: 35

## Issues
WIND PROJECT KHAVDA PH-III CRITICAL ISSUES
S.No | Issue No | Title | Location | Details | Issue start Date | Closure Date | Days affected | Open | 2 | Scope | Responsible | Remarks/ Resolution | IMPACT ON
[8 empty] | Closed | 183
1 | Khavada/PH-III/01 | Stone Column | WTG 379 | location hold due to RIG shifted to PSS area | 2025-02-05 | 2025-03-24 | 47 | Closed |  | Vendor | Kamar |  | Stone Column
2 | Khavada/PH-III/02 | Stone Column | WTG 378 | Both location hold due to RIG shifted to PSS area | 2025-02-05 | 2025-04-01 | 55 | Closed |  | Vendor | Kamar | work start by menard | Stone Column
3 | Khavada/PH-III/03 | Stone Column | ALL | Saritha R1,R2,R4 & R5 rigs not working due to financial crisis | 2025-03-04 | 2025-03-25 | 21 | Closed |  | Vendor | Saritha |  | Stone Column
4 | Khavada/PH-III/04 | Stone Column | ALL | Stone column drawing required as given sequence | 2025-03-07 | 2025-09-05 |  | Closed |  | Vendor | Engineering Team |  | Stone Column
5 | Khavada/PH-III/05 | Stone Column | WTG 198 | Location hold due to High trasmission line crossing | 2025-03-08 | 2025-04-10 | 33 | Closed |  | Vendor | Bauer | Column shifted from transmission line | Stone Column
6 | Khavada/PH-III/06 | Stone Column | WTG 329 | RIG breakdown | 2025-03-18 | 2025-03-21 | 3 | Closed |  | Vendor | ITDC |  | Stone Column
7 | Khavada/PH-III/07 | Stone Column | WTG 329 | Material feeding pipe isolator repairing work WIP | 2025-03-24 | 2025-03-26 | 2 | Closed |  | Vendor | ITDC |  | Stone Column
8 | Khavada/PH-III/08 | Stone Column | WTG 380 | Breakdown due to PUMP issue | 2025-03-30 | 2025-05-19 |  | Closed |  | Vendor | Saritha |  | Stone Column
9 | Khavada/PH-III/09 | Stone Column | WTG 291 | Power pack sensor issue | 2025-03-31 | 2025-04-02 | 2 | Closed |  | Vendor | Bauer |  | Stone Column
10 | Khavada/PH-III/10 | Stone Column | WTG 175 | Breakdown due to issue DG | 2025-04-01 | 2025-04-26 |  | Closed |  | Vendor | Saritha |  | Stone Column
11 | Khavada/PH-III/11 | Stone Column | WTG 329 | Rig shifted to new loc due to hard strata ( after completion of 120 no of columns) | 2025-04-01 | 2025-05-05 | 34 | Closed |  | Vendor | ITDC | Menard Continue the location | Stone Column
12 | Khavada/PH-III/12 | Stone Column | ALL | Saritha R1,R2,R4 & R5 rigs not working due to financial crisis | 2025-04-03 | 2025-04-25 |  | Closed |  | Vendor | Saritha |  | Stone Column
13 | Khavada/PH-III/13 | Stone Column | WTG 554 & WTG 555 | Work hold because conflict of land b/w reliance & adani | 2025-04-04 | 2025-08-22 |  | Closed |  |  | Adani-Land |  | Stone Column
14 | Khavada/PH-III/14 | FDN | WTG 551 | Steel binding work hold due to conflict of land b/w reliance & adani | 2025-04-04 | 2025-08-22 |  | Closed |  |  | Adani-Land |  | FDN
15 | Khavada/PH-III/15 | FDN | WTG 553 | Unable to start further activity for FDN due to conflict of of land b/w reliance & adani | 2025-04-04 | 2025-08-22 |  | Closed |  |  | Adani-Land |  | FDN
16 | Khavada/PH-III/16 | Stone Column | WTG 155 | Crane-03 Pump issue | 2025-04-07 | 2025-04-10 | 3 | Closed |  | Vendor | Bauer |  | Stone Column
17 | Khavada/PH-III/17 | Stone Column | WTG KH059 | Stone column work hampered due to road not available for aggregate shifting | 2025-04-10 | 2025-04-11 |  | Closed |  | Vendor | Bauer |  | Stone Column
18 | Khavada/PH-III/18 | Stone Column | WTG 473 | Stone column work hampered due to road not available for aggregate shifting | 2025-04-10 | 2025-04-11 |  | Closed |  | Vendor | ITDC |  | Stone Column
19 | Khavada/PH-III/19 | Stone Column | WTG 155 | Crane-03 under maintenance | 2025-04-11 | 2025-05-06 | 25 | Closed |  | Vendor | Bauer |  | Stone Column
20 | Khavada/PH-III/20 | Stone Column | WTG 353 | Fund issue | 2025-04-16 | 2025-04-28 | 12 | Closed |  | Vendor | Menard |  | Stone Column
21 | Khavada/PH-III/21 | Stone Column | WTG 400 | RIG Breakdown | 2025-05-03 | 2025-05-07 |  | Closed |  | Vendor | Keller |  | Stone Column
22 | Khavada/PH-III/22 | Stone Column | WTG 473 | Vibro needle isolator damage | 2025-05-04 | 2025-05-10 |  | Closed |  | Vendor | ITDC |  | Stone Column
23 | Khavada/PH-III/23 | PHASE 3 | All Locations | WTG Stone column & FDN work hampered due to Storm | 2025-05-08 | 2025-05-12 |  | Closed |  | Vendor | AGEL |  | Phase 3
24 | Khavada/PH-III/24 | PHASE 3 | Bauer | Manpower Left the siite due to Geo-Political issue. | 2025-05-09 | 2025-05-15 |  | Closed |  | Vendor | AGEL |  | Phase 3
25 | Khavada/PH-III/25 | PHASE 3 | Menard | Manpower Left the site due to Geo-Political issue. | 2025-05-09 | 2025-05-27 |  | Closed |  | Vendor | AGEL |  | Phase 3
26 | Khavada/PH-III/26 | PHASE 3 | Keller | Manpower Left the siite due to Geo-Political issue. | 2025-05-09 | 2025-05-15 |  | Closed |  | Vendor | AGEL |  | Phase 3
27 | Khavada/PH-III/27 | PHASE 3 | WTG 473 | Vibro needle isolator damage | 2025-05-15 | 2025-05-19 |  | Closed |  | Vendor | ITDC |  | Phase 3
28 | Khavada/PH-III/28 | PHASE 3 | WTG FDN | Work hampering due to Anchor cage material not available | 2025-05-18 | 2025-06-10 |  | Closed |  | AGEL | Adani |  | Phase 3
29 | Khavada/PH-III/29 | PHASE 3 | Saritha | R2 - Rig Breakdown due to bin door problem | 2025-06-04 | 2025-07-30 |  | Closed |  | AGEL | Saritha |  | Phase 3
30 | Khavada/PH-III/30 | PHASE 3 | Saritha | R1 -Rig Breakdown due to gear box problem | 2025-06-08 | 2025-07-30 |  | Closed |  | AGEL | Saritha |  | Phase 3
31 | Khavada/PH-III/31 | PHASE 3 | CranePad | Crane Pad work hampered due to water logging due to Rain | 2025-06-10 | 2025-11-15 |  | Closed |  | Vendor | AGEL |  | Phase 3
32 | Khavada/PH-III/32 | PHASE 3 | WTG328 | Rig Breakdown | 2025-06-12 | 2025-06-13 |  | Closed |  | AGEL | Menard |  | Phase 3
33 | Khavada/PH-III/33 | PHASE 3 | HT Cable (33 Kv UG cable) | Work hampering due to HT cable not available | 2025-06-13 | 2025-07-16 |  | Closed |  | AGEL |  |  | Phase 3
34 | Khavada/PH-III/34 | PHASE 3 | WTG 144 | Water Logging, Dewatering WIP for Raft Casting | 2025-06-14 | 2025-06-24 |  | Closed |  | Vendor | HBG |  | Phase 3
35 | Khavada/PH-III/35 | PHASE 3 | HT Cable (33 Kv UG cable) | Due to waterlogging in trench area, HT cable laying work hampered | 2025-07-16 | 2025-09-02 |  | Closed |  | AGEL |  |  | Phase 3
36 | Khavada/PH-III/36 | PHASE 3 | Keller R3 | Keller R3 Breakdown, In Maintanance after completion of ph-2 loc (WTG375) | 2025-06-16 | 2025-07-04 |  | Closed |  | Vendor | Keller | R3 Rig de hired | Phase 3
37 | Khavada/PH-III/37 | PHASE 3 | All Locations | All area work getting hampered due to Rain | 2025-06-16 | 2025-06-18 |  | Closed |  | AGEL | AGEL |  | Phase 3
38 | Khavada/PH-III/38 | PHASE 3 | WTG 403 | Rig idle due to waterlogged at site | 2025-06-17 | 2025-06-18 |  | Closed |  | AGEL | Saritha |  | Phase 3
39 | Khavada/PH-III/39 | PHASE 3 | WTG 456 | Rig idle due to waterlogged at site | 2025-06-17 | 2025-06-18 |  | Closed |  | AGEL | Saritha |  | Phase 3
40 | Khavada/PH-III/40 | PHASE 3 | WTG FDN | Work Hampering due to Wet Soil issue | 2025-06-19 | 2025-06-23 |  | Closed |  | AGEL | AGEL |  | Phase 3
41 | Khavada/PH-III/41 | PHASE 3 | KH 34 | Rig idle due to waterlogged at site | 2025-06-19 | 2025-10-28 |  | Closed |  | AGEL | Saritha |  | Phase 3
42 | Khavada/PH-III/42 | PHASE 3 | WTG 186 | Water Logging, Dewatering WIP for Raft Casting | 2025-06-20 | 2025-06-23 |  | Closed |  | Vendor | DNC |  | Phase 3
43 | Khavada/PH-III/43 | PHASE 3 | KH6155 | Work stopped due to aggregate not available & internal shifting not possible due to road access issue. | 2025-06-20 | 2025-06-23 |  | Closed |  | Vendor | Bauer |  | Phase 3
44 | Khavada/PH-III/44 | PHASE 3 | WTG 403 | Rig idle due to waterlogged at site | 2025-06-22 | 2025-08-28 |  | Closed |  | AGEL | Saritha |  | Phase 3
45 | Khavada/PH-III/45 | PHASE 3 | Stone Column | Low Productivity due to Rain & Water Log condition, Soil Wet Area | 2025-06-24 | 2025-08-30 |  | Closed |  | Vendor | AGEL | Deewatering Completed | Phase 3
46 | Khavada/PH-III/46 | PHASE 3 | All Locations | Work hampered due to Rain & Water logging | 2025-06-26 | 2025-11-16 |  | Closed |  | Vendor | AGEL |  | Phase 3
47 | Khavada/PH-III/47 | PHASE 3 | WTG 400 | Dewatering required to execute steel binding work | 2025-06-26 | 2025-07-09 |  | Closed |  | Vendor | ShreeJi |  | Phase 3
48 | Khavada/PH-III/48 | PHASE 3 | ITDC | ITDC Rig brekadown,No Productivity | 2025-06-27 | 2025-07-01 |  | Closed |  | Vendor | ITDC |  | Phase 3
49 | Khavada/PH-III/49 | PHASE 3 | WTG 481 | Rig idle due to waterlogged at site | 2025-07-05 | 2025-08-08 |  | Closed |  | AGEL | Saritha |  | Phase 3
50 | Khavada/PH-III/50 | PHASE 3 | USS Precast | Precast work order issue - Shreeji, Production hold | 2025-07-05 | 2025-08-05 |  | Closed |  | AGEL | ShreeJi |  | USS Precast
51 | Khavada/PH-III/51 | PHASE 3 | USS Precast | Precast work order issue - Sachi, Production hold | 2025-07-05 | 2025-08-05 |  | Closed |  | AGEL | Sachi |  | USS Precast
52 | Khavada/PH-III/52 | PHASE 3 | WTG 455 | Rig idle due to waterlogged at site | 2025-07-06 | 2025-08-03 |  | Closed |  | AGEL | Saritha |  | Phase 3
53 | Khavada/PH-III/53 | PHASE 3 | WTG 449 | Vibro needle isolator damage & Dismantling wip | 2025-07-09 | 2025-07-19 |  | Closed |  | AGEL | ITDC |  | Stone Column
54 | Khavada/PH-III/54 | PHASE 3 | WTG 477 & WTG 428 | Keller RIG maintenance WIP | 2025-07-16 | 2025-07-28 |  | Closed |  | AGEL | Keller |  | Stone Column
55 | Khavada/PH-III/55 | PHASE 3 | WTG 449 | Hydraulic oil leakage | 2025-07-24 | 2025-07-29 |  | Closed |  | AGEL | ITDC |  | Stone Column
56 | Khavada/PH-III/56 | PHASE 3 | USS Precast | Precast work hold due to land rectification wip - Shreeji | 2025-08-10 | 2025-10-18 |  | Closed |  | AGEL | ShreeJi |  | USS Precast
57 | Khavada/PH-III/57 | PHASE 3 | WTG - 402, 427, 428, 452, 453, 476, 477, 478, 499, 500, 520, 521 | Further work restricted due to eCPT failure | 2025-09-01 | 2025-10-18 |  | Closed |  | Vendor | AGEL |  | Phase 3
58 | Khavada/PH-III/58 | PHASE 3 | KH 34,KH 60, KH 61, KH 68. | Due to change in Co-ordinates, Road access need to be provided. | 2025-09-01 | 2025-10-05 |  | Closed |  | Vendor | AGEL |  | Phase 3
59 | Khavada/PH-III/59 | PHASE 3 | WTG 536, WTG 450 | Approach road not provided for location & due to recent rain road work also hampered | 2025-09-01 | 2025-09-30 |  | Closed |  | Vendor | AGEL |  | Phase 3
60 | Khavada/PH-III/60 | PHASE 3 | KH 35, WTG 516, WTG 532 | Due to change in Co-ordinates, Road access need to be provided. | 2025-09-01 | 2025-12-09 |  | Closed |  | AGEL | AGEL | INFRA TEAM | Phase 3
61 | Khavada/PH-III/61 | PHASE 3 | KH 622 | Due to change in Co-ordinates, Road access need to be provided. | 2025-09-01 | 2025-11-25 |  | Closed |  | AGEL | AGEL | INFRA TEAM | Phase 3
62 | Khavada/PH-III/62 | PHASE 3 | KH 522,KH 51,KH552 | Approach road not provided for location & due to recent rain road work also hampered | 2025-09-01 | 2025-12-04 |  | Closed |  | AGEL | AGEL | INFRA TEAM | Phase 3
63 | Khavada/PH-III/63 | PHASE 3 | KH 47, KH 550, KH 553, KH 478, KH508, | Approach road not provided for location & due to recent rain road work also hampered | 2025-09-01 | 2025-12-27 |  | Closed |  | AGEL | AGEL | INFRA TEAM | Phase 3
64 | Khavada/PH-III/64 | PHASE 3 | KH 523, KH 552, KH 478 | Approach road not provided for location | 2025-09-01 | 2026-01-13 |  | Closed |  | AGEL | AGEL | INFRA TEAM | Phase 3
65 | Khavada/PH-III/65 | PHASE 3 | KH 551 | Approach road not provided for location | 2025-09-01 | 2026-01-31 |  | Closed |  | AGEL | AGEL | INFRA TEAM | Phase 3
66 | Khavada/PH-III/66 | PHASE 3 | KH 622 | Approach road not provided for location | 2025-09-01 | 2026-02-25 |  | Closed |  | AGEL | AGEL | INFRA TEAM | Phase 3
67 | Khavada/PH-III/67 | PHASE 3 | KH 521 | Approach road not provided for location | 2025-09-01 |  |  | Open |  | AGEL | AGEL | INFRA TEAM | Phase 3
68 | Khavada/PH-III/68 | PHASE 3 | WTG 290 | WTG De-erection wip due to FDN flange levelling not proper | 2025-09-02 | 2025-09-05 |  | Closed |  | AGEL | AGEL |  | WTG Erection
69 | Khavada/PH-III/69 | PHASE 3 | WTG 403 | RIG Breakdown, hydraulic pipe failure | 2025-09-02 | 2025-11-03 |  | Closed |  | AGEL | Saritha |  | Stone Column
70 | Khavada/PH-III/70 | PHASE 3 | WTG 582 | RIG stopped due to internal issue - pinnacle | 2025-09-02 | 2025-09-27 |  | Closed |  | AGEL | Pinnacle |  | Stone Column
71 | Khavada/PH-III/71 | PHASE 3 | WTG 377 | Stone column work stopped due to water logged & heavy rain | 2025-09-05 | 2025-10-18 |  | Closed |  | Vendor | ITDC | Dewatering Required | Phase 3
72 | Khavada/PH-III/72 | PHASE 3 | WTG KH 615 | Raft casting work hampered due to heavy rain & water logged, (In finishing stage) | 2025-09-06 | 2025-11-17 |  | Closed |  | Vendor | ShreeJi | Dewatering Required/Mud Mat Required | Phase 3
73 | Khavada/PH-III/73 | PHASE 3 | WTG 266 | Re-grouting to be done due to flange levelling issue after removing old grouting | 2025-09-05 | 2025-09-23 |  | Closed |  | AGEL | C&B |  | WTG Erection
74 | Khavada/PH-III/74 | PHASE 3 | WTG 290 | Re-grouting to be done due to flange levelling issue after removing old grouting | 2025-09-05 | 2025-09-26 |  | Closed |  | AGEL | AB Infra |  | WTG Erection
75 | Khavada/PH-III/75 | PHASE 3 | Wind All Area | All WTG works are hampered at all location due to rain & soil wet condition | 2025-09-07 | 2025-11-15 |  | Closed |  | Vendor | AGEL | Dewatering Required | Phase 3
76 | Khavada/PH-III/76 | PHASE 3 | WTG 426 | Stone column work stopped due to water logged & heavy rain | 2025-09-07 | 2025-09-12 |  | Closed |  | Vendor | Bauer | Dewatering Required | Phase 3
77 | Khavada/PH-III/77 | PHASE 3 | WTG 501 | Stone column work stopped due to water logged & heavy rain | 2025-09-07 | 2025-09-15 |  | Closed |  | Vendor | Keller | Dewatering Required | Phase 3
78 | Khavada/PH-III/78 | PHASE 3 | WTG 502 | Stone column work stopped due to water logged & heavy rain | 2025-09-07 | 2025-09-10 |  | Closed |  | Vendor | Keller |  | Phase 3
79 | Khavada/PH-III/79 | PHASE 3 | WTG 533 | Stone column work stopped due to water logged & heavy rain | 2025-09-07 | 2025-09-09 |  | Closed |  | Vendor | Bauer |  | Phase 3
80 | Khavada/PH-III/80 | PHASE 3 | WTG 536 | Stone column work is on hold because the harmonic filter (PSS-12) is only 58 meters from the WTG center | 2025-09-25 | 2025-10-02 |  | Closed |  | AGEL | AGEL | Engineering team | Phase 3
81 | Khavada/PH-III/81 | PHASE 3 | WTG 377 | Stone column work is on hold due to an internal ITDC issue. | 2025-10-24 | 2025-11-12 |  | Closed |  | Vendor | ITDC |  | Phase 3
82 | Khavada/PH-III/82 | PHASE 3 | WTG 145 | DT, nacelle, and blade materials could not reach the site because the pathway was damaged by rain | 2025-10-31 | 2025-11-12 |  | Closed |  | AGEL | - | Civil Team | Phase 3
83 | Khavada/PH-III/83 | PHASE 3 | PSS-11 WTG Location | WTG roads in PSS-11 area are damaged, immediate rectification reruired. | 2025-10-31 | 2025-12-31 |  | Closed |  | AGEL | INFRA |  | Phase 3
84 | Khavada/PH-III/84 | PHASE 3 | PSS-11 WTG Location | UG cable Work hampered due to Rain & Water logging PSS 11 Area | 2025-11-03 | 2025-11-30 |  | Closed |  | AGEL | Nature | UG Team | Phase 3
85 | Khavada/PH-III/85 | PHASE 3 | WTG 197 | Cabin movement to WTG 197 delayed due to rain and incomplete pathway | 2025-11-05 | 2025-11-08 |  | Closed |  | AGEL |  | Civil Team | Phase 3
86 | Khavada/PH-III/86 | PHASE 3 | WTG 378 | Cabin movement to WTG 378 delayed due to rain and incomplete pathway | 2025-11-16 | 2025-11-19 |  | Closed |  | AGEL |  | INFRA TEAM | Phase 3
87 | Khavada/PH-III/87 | PHASE 3 | WTG 429 | Due to continues transit mixture transportation pathway is damaged due to wet soil condition, it leads increase the time line of raft casting | 2025-11-17 | 2025-11-23 |  | Closed |  | AGEL |  | INFRA TEAM | Phase 3
88 | Khavada/PH-III/88 | PHASE 3 | WTG 406 | RC-5 crane marching delay due to lcation 406 pathaway not ready | 2025-11-18 | 2025-11-21 |  | Closed |  | AGEL |  | Civil & infraTeam | Phase 3
89 | Khavada/PH-III/89 | PHASE 3 | WTG 379 | AC-5 crane marching delay due to lcation 379 crade pade & pathaway not ready | 2025-11-18 | 2025-11-21 |  | Closed |  | AGEL |  | Civil & infraTeam | Phase 3
90 | Khavada/PH-III/90 | PHASE 3 | WTG 404 | crane marching delay due to loation 404 crane pad & pathaway not ready | 2025-11-18 | 2025-12-21 |  | Closed |  | AGEL |  | Civil & infraTeam | Phase 3
91 | Khavada/PH-III/91 | PHASE 3 | WTG 154 | RC-3 crane marching delay due to lcation 154 entrance requeid | 2025-11-18 | 2025-11-19 |  | Closed |  | AGEL |  | Civil & infraTeam | Phase 3
92 | Khavada/PH-III/92 | PHASE 3 | WTG 554 | AC-1 crane marching delay due to lcation 554 crane pad & pathaway not ready | 2025-11-18 | 2025-11-26 |  | Closed |  | AGEL |  | Civil & infraTeam | Phase 3
93 | Khavada/PH-III/93 | PHASE 3 | WTG 381 | AC-8 crane marching delay due to lcation 381 pathaway not ready | 2025-11-20 | 2025-11-26 |  | Closed |  | AGEL |  | INFRA TEAM | Phase 3
94 | Khavada/PH-III/94 | PHASE 3 | WTG 221 | AC-9 crane marching delay due to lcation 221 pathaway not ready | 2025-11-20 | 2025-11-25 |  | Closed |  | AGEL |  | INFRA TEAM | Phase 3
95 | Khavada/PH-III/95 | PHASE 3 | WTG 431 | Crane marching delay due to location Soil wet condition | 2025-11-30 | 2025-12-11 |  | Closed |  | AGEL |  | Civil & infraTeam | Phase 3
96 | Khavada/PH-III/96 | PHASE 3 | WTG 455 | Crane marching delay due to location Soil wet condition | 2025-11-30 | 2025-12-07 |  | Closed |  | AGEL |  | Civil & infraTeam | Phase 3
97 | Khavada/PH-III/97 | PHASE 3 | WTG 523 | Crane marching delay due to location Soil wet condition | 2025-11-30 | 2025-12-11 |  | Closed |  | AGEL |  | Civil & infraTeam | Phase 3
98 | Khavada/PH-III/98 | PHASE 3 | WTG 143 | RC2_BARKAT_SANY650MT Main crane Breckdown | 2025-12-05 | 2025-12-09 |  | Closed |  | Barkat |  | Barkat | Phase 3
99 | Khavada/PH-III/99 | PHASE 3 | PSS-11 WTG Location | WTG erection work is hampered due to non-availability of WTG material at site. | 2025-12-12 | 2026-01-29 |  | Closed |  | AGEL |  | AGEL | Phase 3
100 | Khavada/PH-III/100 | PHASE 3 | WTG 429 | crane marching delay due to pathaway not ready | 2025-12-12 | 2025-12-18 |  | Closed |  | AGEL |  | Civil & infraTeam | Phase 3
101 | Khavada/PH-III/101 | PHASE 3 | PSS-11 | Foundation work is hampered due to not-availability of steel set | 2025-12-17 | 2025-12-28 |  | Closed |  | AGEL |  | Civil & infraTeam | Phase 3
102 | Khavada/PH-III/102 | PHASE 3 | PSS-12&14 WTG Location | Foundation work is hampered due to not-availability of steel set | 2025-12-17 | 2026-02-05 |  | Closed |  | AGEL |  | Civil & infraTeam | Phase 3
103 | Khavada/PH-III/103 | PHASE 3 | PSS-11 | USS precast erection work is hampered due to HT & DT precast shortage at site | 2025-12-20 | 2026-01-09 |  | Closed |  | Vendor |  | Vendor | Phase 3
104 | Khavada/PH-III/104 | PHASE 3 | PSS-12&14 WTG Location | USS precast erection work is hampered due to HT & DT precast shortage at site | 2025-12-20 | 2026-01-13 |  | Closed |  | Vendor |  | Vendor | Phase 3
105 | Khavada/PH-III/105 | PHASE 3 | WTG KH 47 | Stone column work is on hold due to an internal PINNACLE rig breckdown | 2025-12-25 | 2025-12-31 |  | Closed |  | Vendor | PINNACLE | PINNACLE | Phase 3
106 | Khavada/PH-III/106 | PHASE 3 | KH 621 | Foundation work is hampered due to non-availability of steel at KH 621 | 2025-12-28 | 2026-01-09 |  | Closed |  | AGEL |  | AGEL | Phase 3
107 | Khavada/PH-III/107 | PHASE 3 | WTG 123 | RC2_BARKAT_SANY650MT Main crane Breckdown | 2025-12-30 | 2026-01-04 |  | Closed |  | Barkat |  | Barkat | Phase 3
108 | Khavada/PH-III/108 | PHASE 3 | WTG 424 | Foundation work is hampered due to non-availability of steel at Location | 2025-12-31 | 2026-01-19 |  | Closed |  | AGEL |  | AGEL | Phase 3
109 | Khavada/PH-III/109 | PHASE 3 | KH557 | Foundation work is hampered due to non-availability of steel at Location | 2026-01-04 | 2026-01-19 |  | Closed |  | AGEL |  | AGEL | Phase 3
110 | Khavada/PH-III/110 | PHASE 3 | KH 555 | Foundation work is hampered due to non-availability of steel at Location | 2026-01-04 | 2026-01-19 |  | Closed |  | AGEL |  | AGEL | Phase 3
111 | Khavada/PH-III/111 | PHASE 3 | KH 51 | Foundation work is hampered due to non-availability of steel at KH 51 | 2026-01-09 | 2026-01-12 |  | Closed |  | AGEL |  | AGEL | Phase 3
112 | Khavada/PH-III/112 | PHASE 3 | WTG 452 | Foundation work is hampered due to non-availability of steel at Location | 2026-01-10 | 2026-01-18 |  | Closed |  | AGEL |  | AGEL | Phase 3
113 | Khavada/PH-III/113 | PHASE 3 | WTG 498 | Boom down delay due to Nacelle extract not available at site | 2026-01-12 | 2026-01-20 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
114 | Khavada/PH-III/114 | PHASE 3 | KH 61 | Foundation work is hampered due to non-availability of steel at Location | 2026-01-13 | 2026-01-19 |  | Closed |  | AGEL |  | AGEL | Phase 3
115 | Khavada/PH-III/115 | PHASE 3 | WTG 403 | Boom down delay due to Nacelle extract not available at site | 2026-01-13 | 2026-01-20 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
116 | Khavada/PH-III/116 | PHASE 3 | WTG 186 | Boom down delay due to Nacelle extract not available at site | 2026-01-15 | 2026-01-22 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
117 | Khavada/PH-III/117 | PHASE 3 | WTG 430 | Tower erection delay due to S2 not available at site | 2026-01-15 | 2026-01-17 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
118 | Khavada/PH-III/118 | PHASE 3 | WTG 478 | Erection delay due to WTG KIT Not available at site | 2026-01-15 | 2026-01-18 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
119 | Khavada/PH-III/119 | PHASE 3 | WTG 519 | Erection delay due to WTG KIT Not available at site | 2026-01-15 | 2026-01-18 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
120 | Khavada/PH-III/120 | PHASE 3 | KH 608 | Foundation work is hampered due to non-availability of steel at Location | 2026-01-15 | 2026-01-21 |  | Closed |  | AGEL |  | AGEL | Phase 3
121 | Khavada/PH-III/121 | PHASE 3 | WTG 534 | Boom down delay due to Nacelle extract not available at site | 2026-01-16 | 2026-01-23 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
122 | Khavada/PH-III/122 | PHASE 3 | WTG 329 | Boom down delay due to Nacelle extract not available at site | 2026-01-16 | 2026-01-21 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
123 | Khavada/PH-III/123 | PHASE 3 | WTG 448 | Erection delay due to WTG KIT Not available at site | 2026-01-16 | 2026-01-20 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
124 | Khavada/PH-III/124 | PHASE 3 | WTG 536 | Erection delay due to WTG KIT & S5 Not available at site | 2026-01-16 | 2026-01-18 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
125 | Khavada/PH-III/125 | PHASE 3 | WTG 399 | Boom down delay due to Nacelle extract not available at site | 2026-01-17 | 2026-01-23 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
126 | Khavada/PH-III/126 | PHASE 3 | WTG 552 | Boom down delay due to Nacelle extract not available at site | 2026-01-17 | 2026-01-20 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
127 | Khavada/PH-III/127 | PHASE 3 | WTG 398 | Blade erection delay due to Blade set inter-carting trailer required | 2026-01-17 | 2026-01-19 |  | Closed |  | AGEL |  | AGEL | Phase 3
128 | Khavada/PH-III/128 | PHASE 3 | KH 34 | Foundation work is hampered due to non-availability of steel at Location | 2026-01-19 | 2026-01-19 |  | Closed |  | AGEL |  | AGEL | Phase 3
129 | Khavada/PH-III/129 | PHASE 3 | WTG 430 | Boom down delay due to Nacelle extract not available at site | 2026-01-20 | 2026-01-21 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
130 | Khavada/PH-III/130 | PHASE 3 | WTG 477 | Foundation work is hampered due to non-availability of steel at Location | 2026-01-20 | 2026-01-26 |  | Closed |  | AGEL |  | AGEL | Phase 3
131 | Khavada/PH-III/131 | PHASE 3 | KH 596 | Foundation work is hampered due to non-availability of steel at Location | 2026-01-22 | 2026-01-26 |  | Closed |  | AGEL |  | AGEL | Phase 3
132 | Khavada/PH-III/132 | PHASE 3 | WTG 398 | Boom down delay due to Nacelle extract not available at site | 2026-01-21 | 2026-01-26 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
133 | Khavada/PH-III/133 | PHASE 3 | WTG 402 | Boom down delay due to Nacelle extract not available at site | 2026-01-21 | 2026-01-26 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
134 | Khavada/PH-III/134 | PHASE 3 | WTG 519 | Boom down delay due to Nacelle extract not available at site | 2026-01-22 | 2026-01-26 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
135 | Khavada/PH-III/135 | PHASE 3 | WTG 373 | Tower erection delay due to S5 Not available | 2026-01-27 | 2026-02-09 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
136 | Khavada/PH-III/136 | PHASE 3 | WTG 428 | Tower erection delay due to S5 Not available | 2026-01-29 | 2026-02-04 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
137 | Khavada/PH-III/137 | PHASE 3 | WTG 533 | Tower erection delay due to S5 Not available | 2026-01-29 | 2026-02-07 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
138 | Khavada/PH-III/138 | PHASE 3 | WTG 448 | Boom down delay due to Nacelle extract not available at site | 2026-01-29 | 2026-02-03 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
139 | Khavada/PH-III/139 | PHASE 3 | WTG 424 | Raft casting work has been hindered because ACC has not fulfilled the concrete requirement | 2026-01-29 | 2026-02-14 |  | Closed |  | ACC | ACC | ACC | Phase 3
140 | Khavada/PH-III/140 | PHASE 3 | WTG 480 | Boom down delay due to Nacelle extract not available at site | 2026-01-31 | 2026-02-06 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
141 | Khavada/PH-III/141 | PHASE 3 | WTG 141 | Tower erection delay due to S2 Not available | 2026-02-01 | 2026-02-12 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
142 | Khavada/PH-III/142 | PHASE 3 | WTG 535 | Tower erection delay due to S2 Not available | 2026-02-01 | 2026-02-04 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
143 | Khavada/PH-III/143 | PHASE 3 | WTG 453 | Tower erection delay due to S4 Not available | 2026-02-01 | 2026-02-03 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
144 | Khavada/PH-III/144 | PHASE 3 | WTG 476 | Tower erection delay due to S5 Not available | 2026-02-01 | 2026-02-07 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
145 | Khavada/PH-III/145 | PHASE 3 | WTG 500 | Tower erection delay due to S5 Not available | 2026-02-02 | 2026-02-07 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
146 | Khavada/PH-III/146 | PHASE 3 | WTG 551 | Tower erection delay due to S4 Not available | 2026-02-03 | 2026-02-04 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
147 | Khavada/PH-III/147 | PHASE 3 | WTG 453 | Tower erection delay due to S1 Not available | 2026-02-04 | 2026-02-11 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
148 | Khavada/PH-III/148 | PHASE 3 | WTG 535 | Tower erection delay due to S1 Not available | 2026-02-04 | 2026-02-13 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
149 | Khavada/PH-III/149 | PHASE 3 | WTG 449 | Tower erection delay due to S5 Not available | 2026-02-05 | 2026-02-09 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
150 | Khavada/PH-III/150 | PHASE 3 | WTG 551 | Tower erection delay due to S1 Not available | 2026-02-06 | 2026-02-10 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
151 | Khavada/PH-III/151 | PHASE 3 | WTG 428 | Tower erection delay due to S1 Not available | 2026-02-06 | 2026-02-14 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
152 | Khavada/PH-III/152 | PHASE 3 | WTG 555 | Tower erection delay due to S1 Not available | 2026-02-06 | 2026-02-10 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
153 | Khavada/PH-III/153 | PHASE 3 | WTG 533 | Tower erection delay due to S2 & S1 Not available | 2026-02-07 | 2026-02-11 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
154 | Khavada/PH-III/154 | PHASE 3 | WTG 450 | Raft casting work has been hindered because ACC has not fulfilled the concrete requirement | 2026-02-07 | 2026-02-17 |  | Closed |  | ACC | ACC | ACC | Phase 3
155 | Khavada/PH-III/155 | PHASE 3 | WTG 474 | Raft casting work has been hindered because ACC has not fulfilled the concrete requirement | 2026-02-07 | 2026-02-14 |  | Closed |  | ACC | ACC | ACC | Phase 3
156 | Khavada/PH-III/156 | PHASE 3 | KH 597 | Raft casting work has been hindered because ACC has not fulfilled the concrete requirement | 2026-02-07 | 2026-02-15 |  | Closed |  | ACC | ACC | ACC | Phase 3
157 | Khavada/PH-III/157 | PHASE 3 | WTG 476 | Tower erection delay due to S2 & S1 Not available | 2026-02-08 | 2026-02-10 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
158 | Khavada/PH-III/158 | PHASE 3 | WTG 121 | Tower erection delay due to S5 Not available | 2026-02-09 | 2026-02-10 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
159 | Khavada/PH-III/159 | PHASE 3 | WTG 373 | Tower erection delay due to S3 & S1 Not available | 2026-02-09 | 2026-02-16 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
160 | Khavada/PH-III/160 | PHASE 3 | WTG 500 | Tower erection delay due to S2 & S1 Not available | 2026-02-09 | 2026-02-10 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
161 | Khavada/PH-III/161 | PHASE 3 | WTG 476 | Tower erection delay due to S1 Not available | 2026-02-10 | 2026-02-15 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
162 | Khavada/PH-III/162 | PHASE 3 | WTG 121 | Tower erection delay due to S2 Not available | 2026-02-10 | 2026-02-12 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
163 | Khavada/PH-III/163 | PHASE 3 | WTG 533 | Tower erection delay due to S1 Not available | 2026-02-11 | 2026-02-15 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
164 | Khavada/PH-III/164 | PHASE 3 | WTG 533 | Tower erection delay due to S1 Not available | 2026-02-11 | 2026-02-11 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
165 | Khavada/PH-III/165 | PHASE 3 | WTG 500 | Tower erection delay due to S1 Not available | 2026-02-11 | 2026-02-14 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
166 | Khavada/PH-III/166 | PHASE 3 | WTG 449 | Tower erection delay due to ( S2 Not available) | 2026-02-11 | 2026-02-15 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
167 | Khavada/PH-III/167 | PHASE 3 | WTG 121 | Tower erection delay due to S1 Not available | 2026-02-13 | 2026-02-15 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
168 | Khavada/PH-III/168 | PHASE 3 | WTG 141 | Tower erection delay due to S1 Not available | 2026-02-13 | 2026-02-15 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
169 | Khavada/PH-III/169 | PHASE 3 | WTG 499 | Tower erection delay due to ( S3,S2 & S1 Not available) | 2026-02-13 | 2026-02-15 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
170 | Khavada/PH-III/170 | PHASE 3 | KH 52 | Raft casting work has been hindered because ACC has not fulfilled the concrete requirement | 2026-02-13 | 2026-02-18 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
171 | Khavada/PH-III/171 | PHASE 3 | WTG 449 | Tower erection delay due to ( S1 Not available) | 2026-02-16 | 2026-02-18 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
172 | Khavada/PH-III/172 | PHASE 3 | WTG 373 | Tower erection delay due to S1 Not available | 2026-02-16 | 2026-02-18 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
173 | Khavada/PH-III/173 | PHASE 3 | KH 523 | Raft casting work has been hindered because ACC has not fulfilled the concrete requirement | 2026-02-17 | 2026-02-21 |  | Closed |  | ACC | ACC | ACC | Phase 3
174 | Khavada/PH-III/174 | PHASE 3 | WTG 473 | Raft casting work has been hindered because ACC has not fulfilled the concrete requirement | 2026-02-18 | 2026-02-22 |  | Closed |  | ACC | ACC | ACC | Phase 3
175 | Khavada/PH-III/175 | PHASE 3 | WTG 449 | Blade erection delay due to not available at site | 2026-02-19 | 2026-02-21 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
176 | Khavada/PH-III/176 | PHASE 3 | KH 599 | Raft casting work has been hindered because ACC has not fulfilled the concrete requirement | 2026-02-19 | 2026-02-23 |  | Closed |  | ACC | ACC | ACC | Phase 3
177 | Khavada/PH-III/177 | PHASE 3 | WTG 373 | Blade erection delay due to not available at site | 2026-02-19 | 2026-02-22 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
178 | Khavada/PH-III/178 | PHASE 3 | KH 59 | Raft casting work has been hindered because ACC has not fulfilled the concrete requirement | 2026-02-20 | 2026-02-22 |  | Closed |  | ACC | ACC | ACC | Phase 3
179 | Khavada/PH-III/179 | PHASE 3 | KH 522 | Raft casting work has been hindered because ACC has not fulfilled the concrete requirement | 2026-02-20 | 2026-02-20 |  | Closed |  | ACC | ACC | ACC | Phase 3
180 | Khavada/PH-III/180 | PHASE 3 | KH 553 | Raft casting work has been hindered because ACC has not fulfilled the concrete requirement | 2026-02-20 |  |  | Open |  | ACC | ACC | ACC | Phase 3
181 | Khavada/PH-III/181 | PHASE 3 | WTG 451 | Tower erection delay due to S4,S2,S1 not available at site | 2026-02-24 | 2026-02-25 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
182 | Khavada/PH-III/182 | PHASE 3 | WTG 208 | Tower erection delay due to S5,S4, not available at site | 2026-02-24 | 2026-02-25 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
183 | Khavada/PH-III/183 | PHASE 3 | WTG 208 | Tower erection delay due to S3,S2,S1 not available at site | 2026-02-25 | 2026-02-28 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
184 | Khavada/PH-III/184 | PHASE 3 | WTG 434 | Tower erection delay due to S5,S4,S3,S1 not available at site | 2026-02-25 | 2026-02-28 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
185 | Khavada/PH-III/185 | PHASE 3 | WTG 477 | Tower erection delay due to S5,S4,S1 not available at site | 2026-02-26 | 2026-02-27 |  | Closed |  | AGEL | ANIL | ANIL | Phase 3
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Stone column location start by Menard (Scope-119 no. of stone column)

## Supply
PH-III Material Supply Status | [5 empty] | Physical Available Stock | [7 empty] | 64 | 66 | 70 | 67 | 67 | 58 | 61 | 58 | 125
S.No | Description | UoM | Scope | Recieved | Balance | Erection Completed | Balance Avilable | S. No | SUB Station | SPV | Locations | Block | Feeder | S5 | S4 | S3 | S2 | S1 | Nacelle | DT | Hub | Blade | Agency |  | Total Received | Phase-I | Phase-II | Phase-III
A | CIVIL | [8 empty] | zero point |  |  |  | 13 | 11 | 11 | 12 | 11 | 2 | 3 | 6 | 2 |  | 71
1 | Anchor Flange | Set | 194 | 192 | 2 | 177 | 15 |  |  | (WTG 151) | [8 empty] | 17 | 12 | 8 |  |  | 37 | 446 | 54 | 200 | 192
2 | Anchor Bolt | Set | 194 | 193 | 1 | 173 | 20 | [17 empty] | 447 | 54 | 200 | 193
3 | Steel | Set | 194 | 176 | 18 | 173 | 3 |  |  | Phase I |  |  |  | 1 | 1 | 1 | 1 | 1 |  |  |  | 13 |  |  | 442 | 54 | 200 | 188
B | MECHANICAL | [6 empty] | 1 | PSS-9 | ARE48L | WTG 389 | S7 |  | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 |  |  | 9
1 | Tower-S5 | No's | 194 | 126 | 68 | 119 | 7 | 2 | PSS-9 | ARE48L | WTG 413 | S7 |  | 2 | 2 | 2 | 3 | 2 | 1 | 2 | 1 | 3 |  | 18 | 380 | 54 | 200 | 126
2 | Tower-S4 | No's | 194 | 128 | 66 | 119 | 9 | 3 | PSS-9 | ARE48L | WTG 363 | S7 |  | 1 | 3 | 3 | 2 | 3 | 1 | 1 | 1 | 3 | 2DT | 18 | 382 | 54 | 200 | 128
3 | Tower-S3 | No's | 194 | 127 | 67 | 119 | 8 | 4 | PSS-9 | ARE48L | WTG 438 | S7 |  | 2 | 2 | 4 | 1 | 2 | 1 | 1 | 1 | 3 |  | 17 | 381 | 54 | 200 | 127
4 | Tower-S2 | No's | 194 | 128 | 66 | 119 | 9 | 5 | PSS-9 | ARE48L | WTG 388 | S7 |  | 5 | 3 | 4 | 3 | 3 | 1 | 1 | 1 | 3 |  | 24 | 382 | 54 | 200 | 128
5 | Tower-S1 | No's | 194 | 127 | 67 | 119 | 8 | 6 | PSS-9 | ARE48L | WTG 440 | S7 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 |  | 11 | 381 | 54 | 200 | 127
6 | Nacelle | No's | 194 | 128 | 66 | 119 | 9 | 7 | PSS-9 | ARE48L | WTG 415 | S7 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 |  | 11 | 382 | 54 | 200 | 128
7 | Drive Turbine | No's | 194 | 140 | 54 | 119 | 21 | 8 | PSS-9 | ARE48L | WTG 365 | S7 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 |  | 11 | 394 | 54 | 200 | 140
8 | Hub | No's | 194 | 121 | 73 | 119 | 2 | 9 | PSS-9 | ARE48L | WTG 342 | S7 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 6 |  | 14 | 375 | 54 | 200 | 121
9 | Bottom Platform | No's | 194 | 117 | 77 | 119 | -2 | 10 | PSS-9 | ARE48L | WTG 414 | S8 |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 3 |  | 10 | 371 | 54 | 200 | 117
10 | Blades | Set | 194 | 120 | 74 | 119 | 1 | 11 | PSS-9 | ARE48L | WTG 317 | S8 |  | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 3 |  | 14 | 374 | 54 | 200 | 120
11 | Kit | Set | 194 | 134 | 60 | 119 | 15 | 12 | PSS-9 | ARE48L | WTG 439 | S8 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 |  | 11 | 388 | 54 | 200 | 134
C | ELECTRICAL | [6 empty] | 13 | PSS-9 | ARE48L | WTG 364 | S8 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 |  | 11
1 | Transformer | No's | 194 | 171 | 23 | 117 | 54 | 14 | PSS-9 | ARE48L | WTG 341 | S7 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 |  | 11 | 427 | 54 | 200 | 173
2 | HT Panel | No's | 194 | 140 | 54 | 117 | 23 | 15 | PSS-9 | ARE48L | WTG 339 | S8 |  | 8 | 13 | 11 | 11 | 13 | 9 | 11 | 10 | 11 |  | 97 | 415 | 54 | 200 | 161
3 | HT Cable | Km | 645 | 556 | 89 | 422.301 | 133.699 | 16 | PSS-9 | ARE48L | WTG 391 | S8 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 |  | 11 | 1245 | 70 | 619 | 556
4 | FO Cable | Km | 490 | 323 | 167 | 227.845 | 95.155 | 17 | PSS-9 | ARE48L | WTG 340 | S7 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 |  | 11 | 803 | 70 | 410 | 323
[8 empty] | 18 | PSS-9 | ARE48L | WTG 390 | S8 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 6 |  | 15
[8 empty] | 19 | PSS-9 | ARE48L | WTG 489 | S7 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 |  | 11
[8 empty] | 20 | PSS-9 | ARE48L | WTG 463 | S8 |  | 3 | 3 | 2 | 5 | 3 | 1 | 1 | 1 | 3 |  | 22
[8 empty] | 21 | PSS-9 | ARE48L | WTG 464 | S7 |  | 2 | 2 | 3 | 2 | 2 | 1 | 1 | 1 | 3 |  | 17
[8 empty] | 22 | PSS-9 | ARE48L | WTG 488 | S8 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 |  | 11
[8 empty] | 23 | PSS-9 | ARE48L | WTG 465 | S8 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 |  | 11
[8 empty] | 24 | PSS-13 | ARE41L | WTG 237 | A7 |  | 1 |  | 1 |  | 1 | [5 empty] | 3
[8 empty] | 25 | PSS-13 | ARE41L | WTG 148 | A7 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 |  | 11
[8 empty] | 26 | PSS-13 | ARE41L | WTG 170 | A7 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 |  | 11
[8 empty] | 27 | PSS-13 | ARE41L | WTG 191 | A7 | [11 empty] | 0
[8 empty] | 28 | PSS-13 | ARE41L | WTG 169 | A7 | [11 empty] | 0
[8 empty] | 29 | PSS-13 | ARE41L | WTG 215 | A7 | [11 empty] | 0
[8 empty] | 30 | PSS-13 | ARE41L | WTG 192 | A7 | [11 empty] | 0
[8 empty] | 31 | PSS-13 | ARE41L | WTG 236 | A7 | [11 empty] | 0
[8 empty] | 32 | PSS-13 | ARE41L | WTG 214 | A7 | [11 empty] | 0
[8 empty] | 33 | PSS-13 | ARE41L | WTG 257 | A7 |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 |  |  | 7
[8 empty] | 34 | PSS-13 | ARE41L | WTG 281 | A7 | [7 empty] | 1 | 1 |  |  | 2
[8 empty] | 35 | PSS-13 | ARE41L | WTG 357 | A6 | [11 empty] | 0
[8 empty] | 36 | PSS-13 | ARE41L | WTG 332 | A6 | [11 empty] | 0
[8 empty] | 37 | PSS-13 | ARE41L | WTG 258 | A6 | [11 empty] | 0
[8 empty] | 38 | PSS-13 | ARE41L | WTG 306 | A12 | [11 empty] | 0
[8 empty] | 39 | PSS-13 | ARE41L | WTG 282 | A12 | [11 empty] | 0
[8 empty] | 40 | PSS-13 | ARE41L | WTG 355 | A12 | [11 empty] | 0
[8 empty] | 41 | PSS-13 | ARE41L | WTG 307 | A12 | [11 empty] | 0
[8 empty] | 42 | PSS-13 | ARE41L | WTG 283 | A12 | [11 empty] | 0
[8 empty] | 43 | PSS-13 | ARE41L | WTG 356 | A12 | [11 empty] | 0
[8 empty] | 44 | PSS-13 | ARE41L | WTG 259 | A12 | [11 empty] | 0
[8 empty] | 45 | PSS-13 | ARE41L | WTG 331 | A12 | [11 empty] | 0
[8 empty] | 46 | PSS-13 | ARE41L | WTG 330 | A12 | [11 empty] | 0
[8 empty] | 47 | PSS-13 | ARE41L | WTG 305 | A11 | [11 empty] | 0
[8 empty] | 48 | PSS-4 | AGE24L | WTG 147 | A11 | [11 empty] | 0
[8 empty] | 49 | PSS-4 | ACL | WTG 072 | A11 | [11 empty] | 0
[8 empty] | 50 | PSS-4 | AGE24L | WTG 146 | A11 | [11 empty] | 0
[8 empty] | 51 | PSS-4 | AGE24L | WTG 125 | A11 | [11 empty] | 0
[8 empty] | 52 | PSS-4 | AGE24L | WTG 126 | A11 | [11 empty] | 0
[8 empty] | 53 | PSS-4 | AGE24L | WTG 108 | A11 | [11 empty] | 0
[8 empty] | 54 | PSS-4 | AGE24L | WTG 107 | A11 | [11 empty] | 0
[8 empty] | 55 | PSS-4 | AGE24L | WTG 106 | A11 | [11 empty] | 0
[8 empty] | 56 | PSS-4 | AGE24L | WTG 089 | A11 | [11 empty] | 0
[8 empty] | 57 | PSS-4 | ACL | WTG 088 | A11 | [11 empty] | 0
[8 empty] | 58 | PSS-4 | ACL | WTG 071 | A7 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 |  | 11
[8 empty] | 59 | PSS-4 | AHEJ5L | WTG 055 | A4 | [11 empty] | 0
[8 empty] | 60 | PSS-4 | AHEJ5L | WTG 054 | A4 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 |  | 11
[8 empty] | 61 | PSS-4 | ACL | WTG 039 | A4 | [11 empty] | 0
[8 empty] | 62 | PSS-4 | ACL | WTG 025 | A4 | [11 empty] | 0
[8 empty] | 63 | PSS-4 | AKPL | WTG 013 | A4 | [11 empty] | 0
[8 empty] | 64 | PSS-4 | AKPL | WTG 001 | A4 | [11 empty] | 0
[8 empty] | 65 | PSS-4 | ACL | WTG 070 | A3 | [11 empty] | 0
[8 empty] | 66 | PSS-4 | AGE24L | WTG 124 | A4 | [11 empty] | 0
[8 empty] | 67 | PSS-4 | AGE24L | WTG 090 | A3 | [11 empty] | 0
[8 empty] | 68 | PSS-4 | AGE24L | WTG 110 | A4 | [11 empty] | 0
[8 empty] | 69 | PSS-4 | AGE24L | WTG 109 | A2 | [11 empty] | 0
[8 empty] | 70 | PSS-4 | AGE24L | WTG 093 | A2 | [11 empty] | 0
[8 empty] | 71 | PSS-4 | AGE24L | WTG 092 | A1 | [11 empty] | 0
[8 empty] | 72 | PSS-4 | AGE24L | WTG 091 | A1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 |  | 11
[8 empty] | 73 | PSS-4 | AGE24L | WTG 075 | A1 | [11 empty] | 0
[8 empty] | 74 | PSS-4 | AGE24L | WTG 074 | A1 | [11 empty] | 0
[8 empty] | 75 | PSS-4 | AGE24L | WTG 073 | A3 | [11 empty] | 0
[8 empty] | 76 | PSS-4 | AGE24L | WTG 058 | A4 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 6 |  | 14
[8 empty] | 77 | PSS-4 | ACL | WTG 056 | A4 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 |  | 11
[8 empty] | 78 | PSS-4 | AKPL | WTG 041 | A5 | [11 empty] | 0
[8 empty] | 79 | PSS-4 | AHEJ5L | WTG 053 | A4 | [11 empty] | 0
[8 empty] | 80 | PSS-4 | AKPL | WTG 028 | A5 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 |  | 11
[8 empty] | 81 | PSS-4 | AKPL | WTG 027 | A5 | [11 empty] | 0
[8 empty] | 82 | PSS-4 | AKPL | WTG 015 | A4 | [11 empty] | 0
[8 empty] | 83 | PSS-4 | AHEJ5L | WTG 052 | A5 | [11 empty] | 0
[8 empty] | 84 | PSS-4 | ACL | WTG 038 | A5 | [11 empty] | 0
[8 empty] | 85 | PSS-4 | AHEJ5L | WTG 037 | A4 | [11 empty] | 0
[8 empty] | 86 | PSS-4 | AKPL | WTG 024 | A5 | [11 empty] | 0
[8 empty] | 87 | PSS-4 | AHEJ5L | WTG 023 | A4 | [11 empty] | 0
[8 empty] | 88 | PSS-4 | AKPL | WTG 012 | A2 | [11 empty] | 0
[8 empty] | 89 | PSS-4 | AHEJ5L | WTG 068 | A1 | [11 empty] | 0
[8 empty] | 90 | PSS-4 | AHEJ5L | WTG 051 | A2 | [11 empty] | 0
[8 empty] | 91 | PSS-4 | AHEJ5L | WTG 036 | A2 | [11 empty] | 0
[8 empty] | 92 | PSS-4 | AHEJ5L | WTG 011 | A2 | [11 empty] | 0
[8 empty] | 93 | PSS-4 | ACL | WTG 040 | A1 | [11 empty] | 0
[8 empty] | 94 | PSS-4 | ACL | WTG 026 | A1 | [11 empty] | 0
[8 empty] | 95 | PSS-4 | AKPL | WTG 014 | A1 | [11 empty] | 0
[8 empty] | 96 | PSS-4 | AHEJ5L | WTG 069 | A1 | [11 empty] | 0
[8 empty] | 97 | PSS-4 | AGE24L | WTG 057 | A1 | [11 empty] | 0
[8 empty] | 98 | PSS-4 | AHEJ5L | WTG 043 | A1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 |  | 11
[8 empty] | 99 | PSS-4 | AKPL | WTG 042 | A16 | [11 empty] | 0
[8 empty] | 100 | PSS-8 | AGE25CL | WTG 122 | A16 | [11 empty] | 0
[8 empty] | 101 | PSS-8 | AGE25CL | WTG 105 | A16 | [11 empty] | 0
[8 empty] | 102 | PSS-8 | AGE25CL | WTG 104 | A16 | [11 empty] | 0
[8 empty] | 103 | PSS-4 | ACL | WTG 087 | A16 | [11 empty] | 0
[8 empty] | 104 | PSS-4 | ACL | WTG 086 | A2 | [11 empty] | 0
[8 empty] | 105 | PSS-8 | ARE41L | WTG 235 | A2 | [11 empty] | 0
[8 empty] | 106 | PSS-8 | ARE41L | WTG 213 | A2 | [11 empty] | 0
[8 empty] | 107 | PSS-8 | ARE41L | WTG 234 | A3 | [11 empty] | 0
[8 empty] | 108 | PSS-8 | ARE41L | WTG 212 | A3 | [11 empty] | 0
[8 empty] | 109 | PSS-8 | ARE41L | WTG 304 | A3 | [11 empty] | 0
[8 empty] | 110 | PSS-8 | ARE41L | WTG 280 | A3 | [11 empty] | 0
[8 empty] | 111 | PSS-4 | ACL | WTG 022 | A3 | [11 empty] | 0
[8 empty] | 112 | PSS-8 | ARE41L | WTG 303 | A3 | [11 empty] | 0
[8 empty] | 113 | PSS-8 | ARE41L | WTG 279 | A3 | [11 empty] | 0
[8 empty] | 114 | PSS-8 | AHEJ5L | WTG 278 | A3 | [11 empty] | 0
[8 empty] | 115 | PSS-8 | AHEJ5L | WTG 301 | A4 | [11 empty] | 0
[8 empty] | 116 | PSS-8 | ARE41L | WTG 256 | A2 | [11 empty] | 0
[8 empty] | 117 | PSS-8 | ARE41L | WTG 168 | A2 | [11 empty] | 0
[8 empty] | 118 | PSS-8 | ARE41L | WTG 190 | A12 | [11 empty] | 0
[8 empty] | 119 | PSS-8 | ARE41L | WTG 189 | A18 | [11 empty] | 0
[8 empty] | 120 | PSS-8 | ARE41L | WTG 167 | A12 | [11 empty] | 0
[8 empty] | 121 | PSS-4 | ACL | WTG 035 | A18 | [11 empty] | 0
[8 empty] | 122 | PSS-4 | ACL | WTG 050 | A18 | [11 empty] | 0
[8 empty] | 123 | PSS-4 | ACL | WTG 067 | A15 | [11 empty] | 0
[8 empty] | 124 | PSS-4 | ACL | WTG 085 | A15 | [11 empty] | 0
[8 empty] | 125 | PSS-4 | ACL | WTG 103 | A15 | [11 empty] | 0
[8 empty] | 126 | PSS-8 | ARE41L | WTG 166 | A15 | [11 empty] | 0
[8 empty] | 127 | PSS-8 | ARE41L | WTG 188 | A15 | [11 empty] | 0
[8 empty] | 128 | PSS-8 | ARE41L | WTG 211 | A6 | [11 empty] | 0
[8 empty] | 129 | PSS-8 | ARE41L | WTG 233 | A6 | [11 empty] | 0
[8 empty] | 130 | PSS-8 | ARE41L | WTG 255 | A6 | [11 empty] | 0
[8 empty] | 131 | PSS-4 | ACL | WTG 066 | A6 | [11 empty] | 0
[8 empty] | 132 | PSS-8 | ARE41L | WTG 187 | A6 | [11 empty] | 0
[8 empty] | 133 | PSS-8 | ARE41L | WTG 210 | A3 | [11 empty] | 0
[8 empty] | 134 | PSS-8 | ARE41L | WTG 232 | A1 | [11 empty] | 0
[8 empty] | 135 | PSS-8 | ARE41L | WTG 254 | A1 | [11 empty] | 0
[8 empty] | 136 | PSS-8 | ARE41L | WTG 209 | A1 | [11 empty] | 0
[8 empty] | 137 | PSS-8 | ARE41L | WTG 231 | A16 | [11 empty] | 0
[8 empty] | 138 | PSS-8 | ARE41L | WTG 253 | A16 | [11 empty] | 0
[8 empty] | 139 | PSS-8 | AHEJ5L | WTG 277 | A16 | [11 empty] | 0
[8 empty] | 140 | PSS-4 | ACL | WTG 119 | A16 | [11 empty] | 0
[8 empty] | 141 | PSS-4 | ACL | WTG 141 | A15 | [11 empty] | 0
[8 empty] | 142 | PSS-4 | ACL | WTG 164 | A15 | [11 empty] | 0
[8 empty] | 143 | PSS-4 | ACL | WTG 186 | A15 | [11 empty] | 0
[8 empty] | 144 | PSS-4 | ACL | WTG 208 | A6 | [11 empty] | 0
[8 empty] | 145 | PSS-4 | ACL | WTG 230 | A6 | [11 empty] | 0
[8 empty] | 146 | PSS-8 | AHEJ5L | WTG 252 | A1 | [11 empty] | 0
[8 empty] | 147 | PSS-8 | AHEJ5L | WTG 276 | A16 | [11 empty] | 0
[8 empty] | 148 | PSS-8 | AHEJ5L | WTG 300 | A16 | [11 empty] | 0
[8 empty] | 149 | PSS-8 | AHEJ5L | WTG 325 | A16 | [11 empty] | 0
[8 empty] | 150 | PSS-8 | AHEJ5L | WTG 350 | A16 | [11 empty] | 0
[8 empty] | 151 | PSS-8 | AHEJ5L | WTG 375 | A16 | [11 empty] | 0
[8 empty] | 152 | PSS-8 | AHEJ5L | WTG 299 | A15 | [11 empty] | 0
[8 empty] | 153 | PSS-8 | AHEJ5L | WTG 324 | A15 | [11 empty] | 0
[8 empty] | 154 | PSS-8 | AHEJ5L | WTG 349 | A15 | [11 empty] | 0
[8 empty] | 155 | PSS-8 | AHEJ5L | WTG 374 | A15 | [11 empty] | 0
[8 empty] | 156 | PSS-10 | AGE26BL | WTG 362 | A15 | [11 empty] | 0
[8 empty] | 157 | PSS-10 | AGE26BL | WTG 387 | A15 | [11 empty] | 0
[8 empty] | 158 | PSS-10 | AGE26BL | WTG 412 | A15 | [11 empty] | 0
[8 empty] | 159 | PSS-10 | AGE26BL | WTG 361 | A15 | [11 empty] | 0
[8 empty] | 160 | PSS-10 | AGE26BL | WTG 386 | A18 | [11 empty] | 0
[8 empty] | 161 | PSS-10 | AGE26BL | WTG 411 | A18 | [11 empty] | 0
[8 empty] | 162 | PSS-10 | AGE26BL | WTG 437 | A18 | [11 empty] | 0
[8 empty] | 163 | PSS-10 | AGE26BL | WTG 462 | A16 | [11 empty] | 0
[8 empty] | 164 | PSS-10 | AGE26BL | WTG 487 | A16 | [11 empty] | 0
[8 empty] | 165 | PSS-10 | AGE26BL | WTG 360 | A16 | [11 empty] | 0
[8 empty] | 166 | PSS-10 | AGE26BL | WTG 385 | A15 | [11 empty] | 0
[8 empty] | 167 | PSS-10 | AGE26BL | WTG 410 | A15 | [11 empty] | 0
[8 empty] | 168 | PSS-10 | AGE26BL | WTG 436 | A15 | [11 empty] | 0
[8 empty] | 169 | PSS-10 | AGE26BL | WTG 461 | A15 | [11 empty] | 0
[8 empty] | 170 | PSS-10 | AGE26BL | WTG 486 | A15 | [11 empty] | 0
[8 empty] | 171 | PSS-10 | AGE26BL | WTG 460 | [12 empty] | 0
[8 empty] | 172 | PSS-10 | AGE26BL | WTG 485 | [12 empty] | 0
[8 empty] | 173 | PSS-10 | AGE26BL | WTG 508 | [12 empty] | 0
[8 empty] | 174 | PSS-10 | AGE26BL | WTG 383 | [12 empty] | 0
[8 empty] | 175 | PSS-10 | AGE26BL | WTG 384 | [12 empty] | 0
[8 empty] | 176 | PSS-10 | AGE26BL | WTG 408 | [12 empty] | 0
[8 empty] | 177 | PSS-10 | AGE26BL | WTG 409 | [12 empty] | 0
[8 empty] | 178 | PSS-10 | AGE26BL | WTG 434 | [12 empty] | 0
[8 empty] | 179 | PSS-10 | AGE26BL | WTG 435 | [12 empty] | 0
[8 empty] | 180 | PSS-10 | AGE26BL | WTG 458 | [12 empty] | 0
[8 empty] | 181 | PSS-10 | AGE26BL | WTG 459 | [12 empty] | 0
[8 empty] | 182 | PSS-10 | AGE26BL | WTG 483 | [12 empty] | 0
[8 empty] | 183 | PSS-10 | AGE26BL | WTG 484 | S6 | [11 empty] | 0
[8 empty] | 184 | PSS-10 | AGE26BL | WTG 506 | S6 | [11 empty] | 0
[8 empty] | 185 | PSS-10 | AGE26BL | WTG 507 | S6 | [11 empty] | 0
[8 empty] | 186 | PSS-4 | ACL | WTG 101 | S6 | [11 empty] | 0
[8 empty] | 187 | PSS-4 | ACL | KHAVD02 | S6 | [11 empty] | 0
[8 empty] | 188 | PSS-4 | ACL | KHAVD03 | S6 | [11 empty] | 0
[8 empty] | 189 | PSS-4 | ACL | KHAVD05 | S6 | [11 empty] | 0
[8 empty] | 190 | PSS-4 | ACL | KHAVD06 | S6 | [11 empty] | 0
[8 empty] | 191 | PSS-4 | ARE41L | KHAVD01 | S6 | [11 empty] | 0
[8 empty] | 192 | PSS-4 | ARE41L | KHAVD04 | S5 | [11 empty] | 0
[8 empty] | 193 | PSS-4 | ARE41L | KHAVD07 | S6 | [11 empty] | 0
[8 empty] | 194 | PSS-4 | ARE41L | KHAVD08 | S6 | [11 empty] | 0
[8 empty] | 195 | PSS-4 | ARE41L | KHAVD09 | S6 | [11 empty] | 0
[8 empty] | 196 | PSS-4 | ARE41L | KHAVD10 | S6 | [11 empty] | 0
[8 empty] | 197 | PSS-4 | ARE41L | KHAVD11 | S6 | [11 empty] | 0
[8 empty] | 198 | PSS-4 | ARE41L | KHAVD12 | S5 | [11 empty] | 0
[8 empty] | 199 | PSS-4 | ARE41L | KHAVD13 | S6 | [11 empty] | 0
[8 empty] | 200 | PSS-4 | ARE41L | KHAVD14 | S6 | [11 empty] | 0
[9 empty] | PSS-8 | AGE25CL | WTG 145
[9 empty] | PSS-8 | AGE25CL | WTG 123
[9 empty] | PSS-8 | AGE25CL | WTG 144
[9 empty] | PSS-8 | AGE25CL | WTG 121
[9 empty] | PSS-8 | AGE25CL | WTG 143
[9 empty] | PSS-8 | AGE25CL | WTG 084
[9 empty] | PSS-8 | AGE25CL | WTG 102
[9 empty] | PSS-8 | AGE25CL | WTG 120
[9 empty] | PSS-8 | AGE25CL | WTG 142
[9 empty] | PSS-8 | AGE25CL | WTG 165
[9 empty] | TBF | TBD | WTG 379
[9 empty] | TBF | TBD | WTG 354
[9 empty] | TBF | TBD | WTG 378
[9 empty] | TBF | TBD | WTG 329
[9 empty] | TBF | TBD | WTG 328
[9 empty] | TBF | TBD | WTG 377
[9 empty] | TBF | TBD | WTG 353
[9 empty] | TBF | TBD | WTG 352
[9 empty] | TBF | TBD | WTG 327
[9 empty] | TBF | TBD | WTG 302
[9 empty] | TBF | TBD | WTG 326
[9 empty] | TBF | TBD | WTG 351
[9 empty] | TBF | TBD | WTG 376
[9 empty] | TBF | TBD | WTG 400
[9 empty] | TBF | TBD | WTG 399
[9 empty] | TBF | TBD | WTG 398
[9 empty] | TBF | TBD | WTG 373
Note on Y6: Dev Patel: 336-03 129-03 238-02 216-01 261-01 338-03

## MANPOWERR (hidden)
|  |  |  | 2025-02-25 | 2025-03-25 | 2025-04-25 | 2025-05-25 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2026-01-25 | 2026-02-25 | 2026-03-25
[18 empty] | 1 | 2 | 1 | 1 | 1 | 8
[18 empty] | 2 | 2 | 1 | 1 | 1 | 1
| RIGs |  |  | 2025-02-25: 17; 2025-03-25: 19; 2025-04-25: 19; 2025-05-25: 19; 2025-06-25: 19
| FDN Gangs |  |  |  | 12 | 24 | 24 | 24 | 0 | 0 | 0 | 15 | 24 | 3 | 3 |  |  |  |  | 22
| USS Precast |  |  | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 1
civil | USS Installation Gangs |  |  | 2025-04-25: 2; 2025-05-25: 4; 2025-06-25: 4; 2025-07-25: 0; 2025-08-25: 0; 2025-09-25: 0; 2025-10-25: 2; 2025-11-25: 2
| USS Erection Gangs | [5 empty] | 8 | 11 | 0 | 0 | 0 | 5 | 13 | 13 | 13 | 2
| UG cables Gangs | [5 empty] | 6 | 6 | 0 | 0 | 0 | 3 | 6 | 6 | 6 | 6 |  | CIVIL | 4 | 4 | 2 | 4 | 2 | 16
| CranePad Gangs |  |  |  |  | 2 | 9 | 7 | 0 | 0 | 0 | 7 | 7 | 7 | 7
| WTG Erection Gangs | [5 empty] | 6 | 15 | 15 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Loading/Unloading Gangs |  |  | 3 | 3 | 5 | 5 | 5 | 2 | 2 | 2 | 3 | 5 | 5 | 5 | 5 | 3
Equipement Operator
| USS Fencing |  |  | 2025-05-25: 6; 2025-06-25: 8; 2025-10-25: 4; 2025-11-25: 10; 2025-12-25: 10; 2026-01-25: 10
| Testing & Comissioning | [5 empty] | 1 | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 2.5 | 3 | 2 | 0.5
| Plan Manpower | Manpower per Gangs | Days Count
| Stone Column | 30 | Per Rig | 510 | 570 | 570 | 570 | 570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FDN | 40 | Per FDN | 0 | 480 | 960 | 960 | 960 | 0 | 0 | 0 | 600 | 960 | 120 | 120 | 0 | 0
| USS precast | 30 | Per day | 15 | 30 | 30 | 30 | 30 | 15 | 15 | 15 | 15 | 30 | 0 | 0 | 0 | 0
| USS Installation | 10 | 2 Days | 0 | 0 | 20 | 40 | 40 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0
| USS Erection | 15 |  | 0 | 0 | 0 | 120 | 165 | 0 | 0 | 0 | 75 | 195 | 195 | 195 | 30 | 0
| UG Cable | 20 |  | 0 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 60 | 120 | 120 | 120 | 120 | 0
| CranePad | 5 |  | 0 | 0 | 10 | 45 | 35 | 0 | 0 | 0 | 35 | 35 | 35 | 35 | 0 | 0
| WTG Erection | 45 |  | 0 | 0 | 0 | 270 | 675 | 675 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 0
| Logistics Manpower | 10 |  | 30 | 30 | 50 | 50 | 50 | 20 | 20 | 20 | 30 | 50 | 50 | 50 | 50 | 30
| Equipements Manpower | 25 |  | 20 | 20 | 20 | 170 | 395 | 395 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 20
| USS Fencing | 4 |  | 0 | 0 | 0 | 24 | 32 | 0 | 0 | 0 | 16 | 40 | 40 | 40 | 0 | 0
| Testing & Comissioning | 15 | 1 Day | 0 | 0 | 0 | 15 | 30 | 7.5 | 7.5 | 7.5 | 7.5 | 30 | 37.5 | 45 | 30 | 7.5
|  |  |  | 575 | 1130 | 1660 | 2414 | 3102 | 1112.5 | 762.5 | 762.5 | 1578.5 | 2200 | 1317.5 | 1325 | 950 | 57.5
[5 empty] | Total Manpower |  | 18947
Note on E6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 15 Set

## Sheet4 (hidden)
MACHINEREIES
Machinery Details | 2025-02-25 | 2025-03-25 | 2025-04-25 | 2025-05-25 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2026-01-25 | 2026-02-25 | 2026-03-25
JCB | 17 | 25 | 31 | 43 | 52 | 17 | 11 | 12 | 17 | 27 | 17 | 16 | 15 | 0
Rigs | 17 | 19 | 19 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HYDRA | 5 | 8 | 13 | 23 | 33 | 17 | 12 | 12 | 17 | 22 | 16 | 16 | 12 | 0
TRAILER | 6 | 14 | 21 | 95 | 195 | 170 | 115 | 115 | 125 | 131 | 119 | 119 | 115 | 0
DUMPER | 8 | 13 | 18 | 18 | 18 | 0 | 0 | 0 | 3 | 10 | 0 | 0 | 0 | 0
DG | 17 | 31 | 31 | 43 | 61 | 30 | 20 | 20 | 32 | 32 | 20 | 20 | 20 | 0
Excavator | 0 | 7 | 12 | 12 | 12 | 0 | 0 | 0 | 7 | 12 | 0 | 0 | 0 | 0
Boom Placer | 0 | 6 | 12 | 12 | 12 | 0 | 0 | 0 | 6 | 8 | 0 | 0 | 0 | 0
Tanker | 0 | 5 | 10 | 10 | 10 | 0 | 0 | 0 | 3 | 10 | 0 | 0 | 0 | 0
Crane 120Mt | 0 | 3 | 8 | 9 | 9 | 0 | 0 | 0 | 4 | 5 | 0 | 0 | 0 | 0
Trailor (Self) | 0 | 2 | 5 | 5 | 5 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0
Tractor | 0 | 3 | 9 | 12 | 12 | 2 | 0 | 2 | 6 | 8 | 5 | 4 | 3 | 0
Trailer for Roller | 0 | 1 | 3 | 3 | 3 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0
Roller | 0 | 3 | 12 | 13 | 13 | 2 | 0 | 1 | 3 | 8 | 2 | 1 | 0 | 0
Cement Mixture | 0 | 6 | 12 | 12 | 12 | 0 | 0 | 0 | 6 | 8 | 0 | 0 | 0 | 0
Auger | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 0 | 0
Grader | 0 | 1 | 2 | 3 | 3 | 1 | 0 | 1 | 1 | 2 | 2 | 1 | 0 | 0
Crane Package | 0 | 0 | 0 | 6 | 15 | 15 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0
Crane 110T/150T | 0 | 0 | 0 | 12 | 30 | 30 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0
Man Lifter | 0 | 0 | 0 | 6 | 15 | 15 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0
MLT | 0 | 0 | 0 | 14 | 32 | 32 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 0
Crane 250T | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Crane 150T | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Total | 70 | 147 | 218 | 376 | 567 | 335 | 224 | 229 | 300 | 356 | 249 | 245 | 231 | 0
MANPOWER
Manpower Details | 2025-02-25 | 2025-03-25 | 2025-04-25 | 2025-05-25 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2026-01-25 | 2026-02-25 | 2026-03-25
Stone Column | 510 | 570 | 570 | 570 | 570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FDN | 0 | 480 | 960 | 960 | 960 | 0 | 0 | 0 | 600 | 960 | 120 | 120 | 0 | 0
USS precast | 15 | 30 | 30 | 30 | 30 | 15 | 15 | 15 | 15 | 30 | 0 | 0 | 0 | 0
USS Installation | 0 | 0 | 20 | 40 | 40 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0
USS Erection | 0 | 0 | 0 | 120 | 165 | 0 | 0 | 0 | 75 | 195 | 195 | 195 | 30 | 0
UG Cable | 0 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 60 | 120 | 120 | 120 | 120 | 0
CranePad | 0 | 0 | 10 | 45 | 35 | 0 | 0 | 0 | 35 | 35 | 35 | 35 | 0 | 0
WTG Erection | 0 | 0 | 0 | 270 | 675 | 675 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 0
Logistics Manpower | 30 | 30 | 50 | 50 | 50 | 20 | 20 | 20 | 30 | 50 | 50 | 50 | 50 | 30
Equipements Manpower | 20 | 20 | 20 | 170 | 395 | 395 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 20
USS Fencing | 0 | 0 | 0 | 24 | 32 | 0 | 0 | 0 | 16 | 40 | 40 | 40 | 0 | 0
Testing & Comissioning | 0 | 0 | 0 | 15 | 30 | 7.5 | 7.5 | 7.5 | 7.5 | 30 | 37.5 | 45 | 30 | 7.5

## MACHINES (hidden)
| 2025-02-25 | 2025-03-25 | 2025-04-25 | 2025-05-25 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2026-01-25 | 2026-02-25 | 2026-03-25 | Machinery Details | 2025-02-25 | 2025-03-25 | 2025-04-25 | 2025-05-25 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2026-01-25 | 2026-02-25 | 2026-03-25
Stone Column | [14 empty] | JCB | 17 | 25 | 31 | 43 | 52 | 17 | 11 | 12 | 17 | 27 | 17 | 16 | 15 | 0
JCB | 2025-02-25: 17; 2025-03-25: 19; 2025-04-25: 19; 2025-05-25: 19; 2025-06-25: 19 | Rigs | 17 | 19 | 19 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rigs | 2025-02-25: 17; 2025-03-25: 19; 2025-04-25: 19; 2025-05-25: 19; 2025-06-25: 19 | HYDRA | 5 | 8 | 13 | 23 | 33 | 17 | 12 | 12 | 17 | 22 | 16 | 16 | 12 | 0
HYDRA | 2025-02-25: 5; 2025-03-25: 5; 2025-04-25: 5; 2025-05-25: 5; 2025-06-25: 5 | TRAILER | 6 | 14 | 21 | 95 | 195 | 170 | 115 | 115 | 125 | 131 | 119 | 119 | 115 | 0
TRAILER | 2025-02-25: 6; 2025-03-25: 6; 2025-04-25: 6; 2025-05-25: 6; 2025-06-25: 6 | DUMPER | 8 | 13 | 18 | 18 | 18 | 0 | 0 | 0 | 3 | 10 | 0 | 0 | 0 | 0
DUMPER | 2025-02-25: 8; 2025-03-25: 8; 2025-04-25: 8; 2025-05-25: 8; 2025-06-25: 8 | DG | 17 | 31 | 31 | 43 | 61 | 30 | 20 | 20 | 32 | 32 | 20 | 20 | 20 | 0
DG | 2025-02-25: 17; 2025-03-25: 19; 2025-04-25: 19; 2025-05-25: 19; 2025-06-25: 19 | Excavator | 0 | 7 | 12 | 12 | 12 | 0 | 0 | 0 | 7 | 12 | 0 | 0 | 0 | 0
| 2025-02-25: 70; 2025-03-25: 76; 2025-04-25: 76; 2025-05-25: 76; 2025-06-25: 76 | Boom Placer | 0 | 6 | 12 | 12 | 12 | 0 | 0 | 0 | 6 | 8 | 0 | 0 | 0 | 0
[15 empty] | Tanker | 0 | 5 | 10 | 10 | 10 | 0 | 0 | 0 | 3 | 10 | 0 | 0 | 0 | 0
FDN | 2025-03-25: 12; 2025-04-25: 45; 2025-05-25: 45; 2025-06-25: 45; 2025-10-25: 15; 2025-11-25: 30 | Crane 120Mt | 0 | 3 | 8 | 9 | 9 | 0 | 0 | 0 | 4 | 5 | 0 | 0 | 0 | 0
Excavator | 2025-03-25: 7; 2025-04-25: 12; 2025-05-25: 12; 2025-06-25: 12; 2025-10-25: 7; 2025-11-25: 12 | Trailor (Self) | 0 | 2 | 5 | 5 | 5 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0
JCB | 2025-03-25: 5; 2025-04-25: 10; 2025-05-25: 10; 2025-06-25: 10; 2025-10-25: 3; 2025-11-25: 10 | Tractor | 0 | 3 | 9 | 12 | 12 | 2 | 0 | 2 | 6 | 8 | 5 | 4 | 3 | 0
Trailer | 2025-03-25: 7; 2025-04-25: 12; 2025-05-25: 12; 2025-06-25: 12; 2025-10-25: 7; 2025-11-25: 10 | Roller Trailer | 0 | 1 | 3 | 3 | 3 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0
Hydra | 2025-03-25: 3; 2025-04-25: 8; 2025-05-25: 8; 2025-06-25: 8; 2025-10-25: 4; 2025-11-25: 6 | Roller | 0 | 3 | 12 | 13 | 13 | 2 | 0 | 1 | 3 | 8 | 2 | 1 | 0 | 0
Boom Placer | 2025-03-25: 6; 2025-04-25: 12; 2025-05-25: 12; 2025-06-25: 12; 2025-10-25: 6; 2025-11-25: 8 | Cement Mixture | 0 | 6 | 12 | 12 | 12 | 0 | 0 | 0 | 6 | 8 | 0 | 0 | 0 | 0
Dumper | 2025-03-25: 5; 2025-04-25: 10; 2025-05-25: 10; 2025-06-25: 10; 2025-10-25: 3; 2025-11-25: 10 | Auger | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 0 | 0
Tanker | 2025-03-25: 5; 2025-04-25: 10; 2025-05-25: 10; 2025-06-25: 10; 2025-10-25: 3; 2025-11-25: 10 | Grader | 0 | 1 | 2 | 3 | 3 | 1 | 0 | 1 | 1 | 2 | 2 | 1 | 0 | 0
Crane 120Mt | 2025-03-25: 2; 2025-04-25: 5; 2025-05-25: 5; 2025-06-25: 5; 2025-10-25: 2; 2025-11-25: 3 | Crane Package | 0 | 0 | 0 | 6 | 15 | 15 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0
Trailor (Self) | 2025-03-25: 2; 2025-04-25: 5; 2025-05-25: 5; 2025-06-25: 5; 2025-10-25: 2; 2025-11-25: 3 | Crane 110T/150T | 0 | 0 | 0 | 12 | 30 | 30 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0
Tractor | 2025-03-25: 1; 2025-04-25: 5; 2025-05-25: 5; 2025-06-25: 5; 2025-10-25: 2; 2025-11-25: 3 | Man Lifter | 0 | 0 | 0 | 6 | 15 | 15 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0
Rollwr Trailer | 2025-03-25: 1; 2025-04-25: 3; 2025-05-25: 3; 2025-06-25: 3; 2025-10-25: 1; 2025-11-25: 2 | MLT | 0 | 0 | 0 | 14 | 32 | 32 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 0
Roller | 2025-03-25: 2; 2025-04-25: 9; 2025-05-25: 9; 2025-06-25: 9; 2025-10-25: 2; 2025-11-25: 6 | Crane 250T | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
DG | 2025-03-25: 12; 2025-04-25: 12; 2025-05-25: 12; 2025-06-25: 12; 2025-10-25: 12; 2025-11-25: 12 | Crane 150T | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Cement Mixture | 2025-03-25: 6; 2025-04-25: 12; 2025-05-25: 12; 2025-06-25: 12; 2025-10-25: 6; 2025-11-25: 8
|  | 64 | 125 | 125 | 125 | 0 | 0 | 0 | 60 | 103
USS Civil | 2025-04-25: 35; 2025-05-25: 56; 2025-06-25: 56; 2025-10-25: 20; 2025-11-25: 25
Trailer | 2025-03-25: 1; 2025-04-25: 3; 2025-05-25: 4; 2025-06-25: 4; 2025-10-25: 2; 2025-11-25: 2
Hydra
Crane 120Mt | 2025-03-25: 1; 2025-04-25: 3; 2025-05-25: 4; 2025-06-25: 4; 2025-10-25: 2; 2025-11-25: 2
|  | 2 | 6 | 8 | 8 | 0 | 0 | 0 | 4 | 4
USS Electrical | 2025-05-25: 24; 2025-06-25: 33; 2025-10-25: 15; 2025-11-25: 40; 2025-12-25: 40; 2026-01-25: 40
Trailer | 2025-05-25: 2; 2025-06-25: 3; 2025-10-25: 1; 2025-11-25: 4; 2025-12-25: 4; 2026-01-25: 4
Hydra | 2025-05-25: 2; 2025-06-25: 3; 2025-10-25: 1; 2025-11-25: 4; 2025-12-25: 4; 2026-01-25: 4
JCB
Auger | 2025-05-25: 2; 2025-06-25: 2; 2025-10-25: 1; 2025-11-25: 2; 2025-12-25: 2; 2026-01-25: 2
|  |  |  | 6 | 8 | 0 | 0 | 0 | 3 | 10 | 10 | 10
33 KV
JCB | 2025-05-25: 4; 2025-06-25: 4; 2025-10-25: 2; 2025-11-25: 4; 2025-12-25: 4; 2026-01-25: 4; 2026-02-25: 4
Tractor | 2025-05-25: 3; 2025-06-25: 3; 2025-10-25: 2; 2025-11-25: 3; 2025-12-25: 3; 2026-01-25: 3; 2026-02-25: 3
|  |  |  | 19 | 23 | 0 | 0 | 0 | 10 | 27 | 27 | 27 | 7
CranePad |  | 2 | 28 | 45 | 47 | 14 |  | 1 | 11 | 20 | 21 | 3
Roller |  | 1 | 3 | 4 | 4 | 2 |  | 1 | 1 | 2 | 2 | 1
Grader |  | 1 | 2 | 3 | 3 | 1 |  | 1 | 1 | 2 | 2 | 1
JCB |  | 1 | 2 | 3 | 3 | 1 |  | 1 | 1 | 2 | 2 | 1
Excavator
Tractor |  | 2 | 4 | 4 | 4 | 2 |  | 2 | 2 | 2 | 2 | 1
|  | 5 | 11 | 14 | 14 | 6 | 0 | 5 | 5 | 8 | 8 | 4
WTG Erection |  |  |  | 6 | 33 | 8 | 5 | 5 | 15 | 30 | 30 | 30 | 30
Crane Package |  |  |  | 6 | 15 | 15 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Crane 110T/150T |  |  | 2 | 12 | 30 | 30 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Hydra |  |  | 1 | 6 | 15 | 15 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Trailer |  |  | 11 | 66 | 165 | 165 | 110 | 110 | 110 | 110 | 110 | 110 | 110
Man Lifter |  |  | 1 | 6 | 15 | 15 | 10 | 10 | 10 | 10 | 10 | 10 | 10
DG |  |  | 2 | 12 | 30 | 30 | 20 | 20 | 20 | 20 | 20 | 20 | 20
JCB |  |  | 1 | 6 | 15 | 15 | 10 | 10 | 10 | 10 | 10 | 10 | 10
MLT |  |  | 2 | 12 | 30 | 30 | 20 | 20 | 20 | 20 | 20 | 20 | 20
|  |  | 20 | 120 | 300 | 300 | 200 | 200 | 200 | 200 | 200 | 200 | 200
Logistics
Crane 250T |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Crane 150T |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Hydra |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
JCB | bar: 2025-05-25 to 2026-02-25
MLT |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Trailer |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
|  |  |  | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
| 70 | 147 | 238 | 382 | 568 | 320 | 214 | 219 | 296 | 366 | 259 | 255 | 221 | 0
| 0 | 0 | 0 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 0

## Equipments (hidden)
Equipments Details |  |  |  | 0
Sr no | Vendor Name | Area | Date | time axis 2025-01-01 to 2025-06-05
Day | time axis 2025-01-01 to 2025-06-05
|  |  | Total Equipments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 27 | 27 | 27 | 34 | 34 | 34 | 42 | 34 | 43 | 51 | 59 | 59 | 59 | 59 | 59 | 59 | 60 | 60 | 60 | 60 | 68 | 66 | 66 | 72 | 73 | 83 | 92 | 92 | 97 | 98 | 107 | 106 | 134 | 129 | 138 | 138 | 145 | 145 | 145 | 156 | 156 | 171 | 171 | 171 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 142 | 142 | 142 | 159 | 168 | 187 | 189 | 189 | 210 | 210 | 210 | 212 | 212 | 212 | 182 | 182 | 182 | 189 | 189 | 189 | 190 | 180 | 180 | 180 | 180 | 180 | 180 | 202 | 203 | 204 | 204 | 212 | 212 | 212 | 212 | 212 | 212 | 212 | 212 | 212 | 212 | 258 | 258 | 258 | 258 | 258 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285
1 | M/s Saritha Enterprise | Stone Column | Crane | 2025-01-15: 1; 2025-01-16: 1; 2025-01-17: 1; 2025-01-18: 1; 2025-01-19: 1; 2025-01-20: 1; 2025-01-21: 1; 2025-01-22: 1; 2025-01-23: 1; 2025-01-24: 1; 2025-01-25: 1; 2025-01-26: 1; 2025-01-27: 1; 2025-01-28: 1; 2025-01-29: 1; 2025-01-30: 1; 2025-01-31: 1; 2025-02-01: 1; 2025-02-02: 1; 2025-02-03: 1; 2025-02-04: 1; 2025-02-05: 1; 2025-02-06: 1; 2025-02-07: 1; 2025-02-08: 1; 2025-02-09: 1; 2025-02-10: 1; 2025-02-11: 1; 2025-02-12: 1; 2025-02-13: 1; 2025-02-14: 1; 2025-02-15: 1; 2025-02-16: 1; 2025-02-17: 1; 2025-02-18: 1; 2025-03-25: 1; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 4; 2025-03-30: 4; 2025-03-31: 4; 2025-04-01: 4; 2025-04-02: 4; 2025-04-03: 4; 2025-05-01: 4; 2025-05-02: 4; 2025-05-03: 4; 2025-05-04: 4; 2025-05-05: 4; 2025-05-06: 4; 2025-05-07: 4; 2025-05-08: 4; 2025-05-09: 4; 2025-05-10: 4; 2025-05-11: 4; 2025-05-12: 4; 2025-05-13: 4; 2025-05-14: 4; 2025-05-15: 4; 2025-05-16: 4; 2025-05-17: 4; 2025-05-18: 4; 2025-05-19: 4; 2025-05-20: 4; 2025-05-21: 4; 2025-05-22: 4; 2025-05-23: 4; 2025-05-24: 4; 2025-05-25: 4; 2025-05-26: 4; 2025-05-27: 4; 2025-05-28: 4; 2025-05-29: 4; 2025-05-30: 4; 2025-05-31: 4; 2025-06-01: 4; 2025-06-02: 4; 2025-06-03: 4; 2025-06-04: 4; 2025-06-05: 4
1 | M/s Saritha Enterprise | Stone Column | Air Compressor | 2025-01-15: 1; 2025-01-16: 1; 2025-01-17: 1; 2025-01-18: 1; 2025-01-19: 1; 2025-01-20: 1; 2025-01-21: 1; 2025-01-22: 1; 2025-01-23: 1; 2025-01-24: 1; 2025-01-25: 1; 2025-01-26: 1; 2025-01-27: 1; 2025-01-28: 1; 2025-01-29: 1; 2025-01-30: 1; 2025-01-31: 1; 2025-02-01: 1; 2025-02-02: 1; 2025-02-03: 1; 2025-02-04: 1; 2025-02-05: 1; 2025-02-06: 1; 2025-02-07: 1; 2025-02-08: 1; 2025-02-09: 1; 2025-02-10: 1; 2025-02-11: 1; 2025-02-12: 1; 2025-02-13: 1; 2025-02-14: 1; 2025-02-15: 1; 2025-02-16: 1; 2025-02-17: 1; 2025-02-18: 1; 2025-03-25: 1; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 4; 2025-03-30: 4; 2025-03-31: 4; 2025-04-01: 4; 2025-04-02: 4; 2025-04-03: 4; 2025-05-01: 4; 2025-05-02: 4; 2025-05-03: 4; 2025-05-04: 4; 2025-05-05: 4; 2025-05-06: 4; 2025-05-07: 4; 2025-05-08: 4; 2025-05-09: 4; 2025-05-10: 4; 2025-05-11: 4; 2025-05-12: 4; 2025-05-13: 4; 2025-05-14: 4; 2025-05-15: 4; 2025-05-16: 4; 2025-05-17: 4; 2025-05-18: 4; 2025-05-19: 4; 2025-05-20: 4; 2025-05-21: 4; 2025-05-22: 4; 2025-05-23: 4; 2025-05-24: 4; 2025-05-25: 4; 2025-05-26: 4; 2025-05-27: 4; 2025-05-28: 4; 2025-05-29: 4; 2025-05-30: 4; 2025-05-31: 4; 2025-06-01: 4; 2025-06-02: 4; 2025-06-03: 4; 2025-06-04: 4; 2025-06-05: 4
1 | M/s Saritha Enterprise | Stone Column | Power Pack | 2025-01-15: 1; 2025-01-16: 1; 2025-01-17: 1; 2025-01-18: 1; 2025-01-19: 1; 2025-01-20: 1; 2025-01-21: 1; 2025-01-22: 1; 2025-01-23: 1; 2025-01-24: 1; 2025-01-25: 1; 2025-01-26: 1; 2025-01-27: 1; 2025-01-28: 1; 2025-01-29: 1; 2025-01-30: 1; 2025-01-31: 1; 2025-02-01: 1; 2025-02-02: 1; 2025-02-03: 1; 2025-02-04: 1; 2025-02-05: 1; 2025-02-06: 1; 2025-02-07: 1; 2025-02-08: 1; 2025-02-09: 1; 2025-02-10: 1; 2025-02-11: 1; 2025-02-12: 1; 2025-02-13: 1; 2025-02-14: 1; 2025-02-15: 1; 2025-02-16: 1; 2025-02-17: 1; 2025-02-18: 1; 2025-03-25: 1; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 4; 2025-03-30: 4; 2025-03-31: 4; 2025-04-01: 4; 2025-04-02: 4; 2025-04-03: 4; 2025-05-01: 4; 2025-05-02: 4; 2025-05-03: 4; 2025-05-04: 4; 2025-05-05: 4; 2025-05-06: 4; 2025-05-07: 4; 2025-05-08: 4; 2025-05-09: 4; 2025-05-10: 4; 2025-05-11: 4; 2025-05-12: 4; 2025-05-13: 4; 2025-05-14: 4; 2025-05-15: 4; 2025-05-16: 4; 2025-05-17: 4; 2025-05-18: 4; 2025-05-19: 4; 2025-05-20: 4; 2025-05-21: 4; 2025-05-22: 4; 2025-05-23: 4; 2025-05-24: 4; 2025-05-25: 4; 2025-05-26: 4; 2025-05-27: 4; 2025-05-28: 4; 2025-05-29: 4; 2025-05-30: 4; 2025-05-31: 4; 2025-06-01: 4; 2025-06-02: 4; 2025-06-03: 4; 2025-06-04: 4; 2025-06-05: 4
1 | M/s Saritha Enterprise | Stone Column | Vibro | 2025-01-15: 1; 2025-01-16: 1; 2025-01-17: 1; 2025-01-18: 1; 2025-01-19: 1; 2025-01-20: 1; 2025-01-21: 1; 2025-01-22: 1; 2025-01-23: 1; 2025-01-24: 1; 2025-01-25: 1; 2025-01-26: 1; 2025-01-27: 1; 2025-01-28: 1; 2025-01-29: 1; 2025-01-30: 1; 2025-01-31: 1; 2025-02-01: 1; 2025-02-02: 1; 2025-02-03: 1; 2025-02-04: 1; 2025-02-05: 1; 2025-02-06: 1; 2025-02-07: 1; 2025-02-08: 1; 2025-02-09: 1; 2025-02-10: 1; 2025-02-11: 1; 2025-02-12: 1; 2025-02-13: 1; 2025-02-14: 1; 2025-02-15: 1; 2025-02-16: 1; 2025-02-17: 1; 2025-02-18: 1; 2025-03-25: 1; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 4; 2025-03-30: 4; 2025-03-31: 4; 2025-04-01: 4; 2025-04-02: 4; 2025-04-03: 4; 2025-05-01: 4; 2025-05-02: 4; 2025-05-03: 4; 2025-05-04: 4; 2025-05-05: 4; 2025-05-06: 4; 2025-05-07: 4; 2025-05-08: 4; 2025-05-09: 4; 2025-05-10: 4; 2025-05-11: 4; 2025-05-12: 4; 2025-05-13: 4; 2025-05-14: 4; 2025-05-15: 4; 2025-05-16: 4; 2025-05-17: 4; 2025-05-18: 4; 2025-05-19: 4; 2025-05-20: 4; 2025-05-21: 4; 2025-05-22: 4; 2025-05-23: 4; 2025-05-24: 4; 2025-05-25: 4; 2025-05-26: 4; 2025-05-27: 4; 2025-05-28: 4; 2025-05-29: 4; 2025-05-30: 4; 2025-05-31: 4; 2025-06-01: 4; 2025-06-02: 4; 2025-06-03: 4; 2025-06-04: 4; 2025-06-05: 4
1 | M/s Saritha Enterprise | Stone Column | DG | 2025-01-15: 1; 2025-01-16: 1; 2025-01-17: 1; 2025-01-18: 1; 2025-01-19: 1; 2025-01-20: 1; 2025-01-21: 1; 2025-01-22: 1; 2025-01-23: 1; 2025-01-24: 1; 2025-01-25: 1; 2025-01-26: 1; 2025-01-27: 1; 2025-01-28: 1; 2025-01-29: 1; 2025-01-30: 1; 2025-01-31: 1; 2025-02-01: 1; 2025-02-02: 1; 2025-02-03: 1; 2025-02-04: 1; 2025-02-05: 1; 2025-02-06: 1; 2025-02-07: 1; 2025-02-08: 1; 2025-02-09: 1; 2025-02-10: 1; 2025-02-11: 1; 2025-02-12: 1; 2025-02-13: 1; 2025-02-14: 1; 2025-02-15: 1; 2025-02-16: 1; 2025-02-17: 1; 2025-02-18: 1; 2025-03-25: 1; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 4; 2025-03-30: 4; 2025-03-31: 4; 2025-04-01: 4; 2025-04-02: 4; 2025-04-03: 4; 2025-05-01: 4; 2025-05-02: 4; 2025-05-03: 4; 2025-05-04: 4; 2025-05-05: 4; 2025-05-06: 4; 2025-05-07: 4; 2025-05-08: 4; 2025-05-09: 4; 2025-05-10: 4; 2025-05-11: 4; 2025-05-12: 4; 2025-05-13: 4; 2025-05-14: 4; 2025-05-15: 4; 2025-05-16: 4; 2025-05-17: 4; 2025-05-18: 4; 2025-05-19: 4; 2025-05-20: 4; 2025-05-21: 4; 2025-05-22: 4; 2025-05-23: 4; 2025-05-24: 4; 2025-05-25: 4; 2025-05-26: 4; 2025-05-27: 4; 2025-05-28: 4; 2025-05-29: 4; 2025-05-30: 4; 2025-05-31: 4; 2025-06-01: 4; 2025-06-02: 4; 2025-06-03: 4; 2025-06-04: 4; 2025-06-05: 4
1 | M/s Saritha Enterprise | Stone Column | JCB / Loader / Excavator | 2025-01-15: 1; 2025-01-16: 1; 2025-01-17: 1; 2025-01-18: 1; 2025-01-19: 1; 2025-01-20: 1; 2025-01-21: 1; 2025-01-22: 1; 2025-01-23: 1; 2025-01-24: 1; 2025-01-25: 1; 2025-01-26: 1; 2025-01-27: 1; 2025-01-28: 1; 2025-01-29: 1; 2025-01-30: 1; 2025-01-31: 1; 2025-02-01: 1; 2025-02-02: 1; 2025-02-03: 1; 2025-02-04: 1; 2025-02-05: 1; 2025-02-06: 1; 2025-02-07: 1; 2025-02-08: 1; 2025-02-09: 1; 2025-02-10: 1; 2025-02-11: 1; 2025-02-12: 1; 2025-02-13: 1; 2025-02-14: 1; 2025-02-15: 1; 2025-02-16: 1; 2025-02-17: 1; 2025-02-18: 1; 2025-03-25: 1; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 4; 2025-03-30: 4; 2025-03-31: 4; 2025-04-01: 4; 2025-04-02: 4; 2025-04-03: 4; 2025-05-01: 4; 2025-05-02: 4; 2025-05-03: 4; 2025-05-04: 4; 2025-05-05: 4; 2025-05-06: 4; 2025-05-07: 4; 2025-05-08: 4; 2025-05-09: 4; 2025-05-10: 4; 2025-05-11: 4; 2025-05-12: 4; 2025-05-13: 4; 2025-05-14: 4; 2025-05-15: 4; 2025-05-16: 4; 2025-05-17: 4; 2025-05-18: 4; 2025-05-19: 4; 2025-05-20: 4; 2025-05-21: 4; 2025-05-22: 4; 2025-05-23: 4; 2025-05-24: 4; 2025-05-25: 4; 2025-05-26: 4; 2025-05-27: 4; 2025-05-28: 4; 2025-05-29: 4; 2025-05-30: 4; 2025-05-31: 4; 2025-06-01: 4; 2025-06-02: 4; 2025-06-03: 4; 2025-06-04: 4; 2025-06-05: 4
1 | M/s Saritha Enterprise | Stone Column | Pick&Carry | bar: 2025-01-15 to 2025-02-18; 2025-03-25 to 2025-04-03; 2025-05-01 to 2025-06-05
1 | M/s Saritha Enterprise | Stone Column | Dumper | bar: 2025-01-15 to 2025-02-18; 2025-03-25 to 2025-04-03; 2025-05-01 to 2025-06-05
1 | M/s Saritha Enterprise | Stone Column | Light Mast | 2025-01-15: 1; 2025-01-16: 1; 2025-01-17: 1; 2025-01-18: 1; 2025-01-19: 1; 2025-01-20: 1; 2025-01-21: 1; 2025-01-22: 1; 2025-01-23: 1; 2025-01-24: 1; 2025-01-25: 1; 2025-01-26: 1; 2025-01-27: 1; 2025-01-28: 1; 2025-01-29: 1; 2025-01-30: 1; 2025-01-31: 1; 2025-02-01: 1; 2025-02-02: 1; 2025-02-03: 1; 2025-02-04: 1; 2025-02-05: 1; 2025-02-06: 1; 2025-02-07: 1; 2025-02-08: 1; 2025-02-09: 1; 2025-02-10: 1; 2025-02-11: 1; 2025-02-12: 1; 2025-02-13: 1; 2025-02-14: 1; 2025-02-15: 1; 2025-02-16: 1; 2025-02-17: 1; 2025-02-18: 1; 2025-03-25: 1; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 4; 2025-03-30: 4; 2025-03-31: 4; 2025-04-01: 4; 2025-04-02: 4; 2025-04-03: 4; 2025-05-01: 4; 2025-05-02: 4; 2025-05-03: 4; 2025-05-04: 4; 2025-05-05: 4; 2025-05-06: 4; 2025-05-07: 4; 2025-05-08: 4; 2025-05-09: 4; 2025-05-10: 4; 2025-05-11: 4; 2025-05-12: 4; 2025-05-13: 4; 2025-05-14: 4; 2025-05-15: 4; 2025-05-16: 4; 2025-05-17: 4; 2025-05-18: 4; 2025-05-19: 4; 2025-05-20: 4; 2025-05-21: 4; 2025-05-22: 4; 2025-05-23: 4; 2025-05-24: 4; 2025-05-25: 4; 2025-05-26: 4; 2025-05-27: 4; 2025-05-28: 4; 2025-05-29: 4; 2025-05-30: 4; 2025-05-31: 4; 2025-06-01: 4; 2025-06-02: 4; 2025-06-03: 4; 2025-06-04: 4; 2025-06-05: 4
2 | M/s Menard India | Stone Column | Crane | bar: 2025-03-24 to 2025-06-05
2 | M/s Menard India | Stone Column | Air Compressor | bar: 2025-03-24 to 2025-06-05
2 | M/s Menard India | Stone Column | Power Pack | bar: 2025-03-24 to 2025-06-05
2 | M/s Menard India | Stone Column | Vibro | bar: 2025-03-24 to 2025-06-05
2 | M/s Menard India | Stone Column | DG | bar: 2025-03-24 to 2025-06-05
2 | M/s Menard India | Stone Column | JCB / Loader / Excavator | bar: 2025-03-24 to 2025-06-05
2 | M/s Menard India | Stone Column | Pick&Carry | bar: 2025-03-24 to 2025-06-05
2 | M/s Menard India | Stone Column | Dumper | bar: 2025-03-24 to 2025-06-05
2 | M/s Menard India | Stone Column | Light Mast | bar: 2025-03-24 to 2025-06-05
3 | M/s Bauer | Stone Column | Crane | [14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
3 | M/s Bauer | Stone Column | Air Compressor | [14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
3 | M/s Bauer | Stone Column | Power Pack | [14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
3 | M/s Bauer | Stone Column | Vibro | [14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
3 | M/s Bauer | Stone Column | DG | [14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
3 | M/s Bauer | Stone Column | JCB / Loader / Excavator | [14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
3 | M/s Bauer | Stone Column | Pick&Carry | [14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
3 | M/s Bauer | Stone Column | Dumper | bar: 2025-01-15 to 2025-06-05
3 | M/s Bauer | Stone Column | Light Mast | [14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
4 | M/s Kamar | Stone Column | Crane | 2025-01-29: 1; 2025-01-30: 1; 2025-01-31: 1; 2025-02-01: 2; 2025-02-02: 2; 2025-02-03: 2; 2025-02-04: 2
4 | M/s Kamar | Stone Column | Air Compressor | 2025-01-29: 1; 2025-01-30: 1; 2025-01-31: 1; 2025-02-01: 2; 2025-02-02: 2; 2025-02-03: 2; 2025-02-04: 2
4 | M/s Kamar | Stone Column | Power Pack | 2025-01-29: 1; 2025-01-30: 1; 2025-01-31: 1; 2025-02-01: 2; 2025-02-02: 2; 2025-02-03: 2; 2025-02-04: 2
4 | M/s Kamar | Stone Column | Vibro | 2025-01-29: 1; 2025-01-30: 1; 2025-01-31: 1; 2025-02-01: 2; 2025-02-02: 2; 2025-02-03: 2; 2025-02-04: 2
4 | M/s Kamar | Stone Column | DG | 2025-01-29: 1; 2025-01-30: 1; 2025-01-31: 1; 2025-02-01: 2; 2025-02-02: 2; 2025-02-03: 2; 2025-02-04: 2
4 | M/s Kamar | Stone Column | JCB / Loader / Excavator | 2025-01-29: 1; 2025-01-30: 1; 2025-01-31: 1; 2025-02-01: 2; 2025-02-02: 2; 2025-02-03: 2; 2025-02-04: 2
4 | M/s Kamar | Stone Column | Pick&Carry | bar: 2025-01-29 to 2025-02-04
4 | M/s Kamar | Stone Column | Dumper | bar: 2025-01-29 to 2025-02-04
4 | M/s Kamar | Stone Column | Light Mast | 2025-01-29: 1; 2025-01-30: 1; 2025-01-31: 1; 2025-02-01: 2; 2025-02-02: 2; 2025-02-03: 2; 2025-02-04: 2
5 | M/s Keller | Stone Column | Crane | [36 empty] | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
5 | M/s Keller | Stone Column | Air Compressor | [36 empty] | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
5 | M/s Keller | Stone Column | Power Pack | [36 empty] | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
5 | M/s Keller | Stone Column | Vibro | [36 empty] | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
5 | M/s Keller | Stone Column | DG | [36 empty] | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
5 | M/s Keller | Stone Column | JCB / Loader / Excavator | [36 empty] | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
5 | M/s Keller | Stone Column | Pick&Carry | [36 empty] | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
5 | M/s Keller | Stone Column | Dumper | [36 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
5 | M/s Keller | Stone Column | Light Mast | [36 empty] | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
6 | M/s ITDC | Stone Column | Crane | bar: 2025-02-24 to 2025-06-05
6 | M/s ITDC | Stone Column | Air Compressor | bar: 2025-02-24 to 2025-06-05
6 | M/s ITDC | Stone Column | Power Pack | bar: 2025-02-24 to 2025-06-05
6 | M/s ITDC | Stone Column | Vibro | bar: 2025-02-24 to 2025-06-05
6 | M/s ITDC | Stone Column | DG | [54 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
6 | M/s ITDC | Stone Column | JCB / Loader / Excavator | bar: 2025-02-24 to 2025-06-05
6 | M/s ITDC | Stone Column | Trailer | bar: 2025-04-18 to 2025-06-05
6 | M/s ITDC | Stone Column | Pick&Carry | bar: 2025-02-24 to 2025-06-05
6 | M/s ITDC | Stone Column | Dumper | bar: 2025-02-24 to 2025-06-05
6 | M/s ITDC | Stone Column | Light Mast | bar: 2025-02-24 to 2025-06-05
7 | M/s AB Infra | FDN | Excavator | bar: 2025-02-26 to 2025-02-28; 2025-04-10 to 2025-06-05
7 | M/s AB Infra | FDN | Dumper | [56 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
7 | M/s AB Infra | FDN | Boom Placer | bar: 2025-03-04 to 2025-06-05
7 | M/s AB Infra | FDN | Roller (10t & 5t) | bar: 2025-02-28 to 2025-06-05
7 | M/s AB Infra | FDN | Road Gradar
7 | M/s AB Infra | FDN | JCB | bar: 2025-02-26 to 2025-06-05
7 | M/s AB Infra | FDN | Trailer | bar: 2025-03-02 to 2025-06-05
7 | M/s AB Infra | FDN | Water Tanker
7 | M/s AB Infra | FDN | Tractor | bar: 2025-02-28 to 2025-06-05
7 | M/s AB Infra | FDN | Vibrator | [62 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
7 | M/s AB Infra | FDN | DG | bar: 2025-02-28 to 2025-06-05
8 | M/s DNC | FDN | Excavator | bar: 2025-02-28 to 2025-03-20
8 | M/s DNC | FDN | Dumper | bar: 2025-02-28 to 2025-03-20
8 | M/s DNC | FDN | Roller (10t & 5t) | bar: 2025-03-03 to 2025-03-20
8 | M/s DNC | FDN | Boom Placer | bar: 2025-03-03 to 2025-03-20
8 | M/s DNC | FDN | Road Gradar | bar: 2025-03-03 to 2025-03-20
8 | M/s DNC | FDN | JCB | bar: 2025-02-28 to 2025-03-20
8 | M/s DNC | FDN | Trailer | bar: 2025-03-03 to 2025-03-20
8 | M/s DNC | FDN | Water Tanker | bar: 2025-03-03 to 2025-03-20
8 | M/s DNC | FDN | Tractor | bar: 2025-02-28 to 2025-03-20
8 | M/s DNC | FDN | Vibrator | 2025-03-03: 8; 2025-03-04: 8; 2025-03-05: 8; 2025-03-06: 8; 2025-03-07: 8; 2025-03-08: 8; 2025-03-09: 8; 2025-03-10: 8; 2025-03-11: 8; 2025-03-12: 8; 2025-03-13: 8; 2025-03-14: 8; 2025-03-15: 8; 2025-03-16: 8; 2025-03-17: 8; 2025-03-18: 8; 2025-03-19: 8; 2025-03-20: 8
8 | M/s DNC | FDN | DG | 2025-02-28: 1; 2025-03-01: 1; 2025-03-02: 1; 2025-03-03: 2; 2025-03-04: 2; 2025-03-05: 2; 2025-03-06: 2; 2025-03-07: 2; 2025-03-08: 2; 2025-03-09: 2; 2025-03-10: 2; 2025-03-11: 2; 2025-03-12: 2; 2025-03-13: 2; 2025-03-14: 2; 2025-03-15: 2; 2025-03-16: 2; 2025-03-17: 2; 2025-03-18: 2; 2025-03-19: 2; 2025-03-20: 2
9 | M/s MSC | FDN | Excavator | 2025-02-21: 1; 2025-02-22: 1; 2025-02-23: 1; 2025-02-24: 1; 2025-02-25: 1; 2025-02-26: 1; 2025-02-27: 1; 2025-02-28: 1; 2025-03-01: 1; 2025-03-02: 1; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 1; 2025-03-30: 1; 2025-03-31: 1; 2025-04-01: 1; 2025-04-02: 1; 2025-04-03: 1; 2025-04-04: 1; 2025-04-05: 1; 2025-04-06: 1; 2025-04-07: 1; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1; 2025-04-11: 2; 2025-04-12: 2; 2025-04-13: 2; 2025-04-14: 2; 2025-04-15: 2; 2025-04-16: 2; 2025-04-17: 2; 2025-04-18: 2; 2025-04-19: 2; 2025-04-20: 2; 2025-04-21: 2; 2025-04-22: 2; 2025-04-23: 2; 2025-04-24: 2; 2025-04-25: 2; 2025-04-26: 2; 2025-04-27: 2; 2025-04-28: 2; 2025-04-29: 2; 2025-04-30: 2; 2025-05-01: 2; 2025-05-02: 2; 2025-05-03: 2; 2025-05-04: 2; 2025-05-05: 2; 2025-05-06: 2; 2025-05-07: 2; 2025-05-08: 2; 2025-05-09: 2; 2025-05-10: 2; 2025-05-11: 2; 2025-05-12: 2; 2025-05-13: 2; 2025-05-14: 2; 2025-05-15: 2; 2025-05-16: 2; 2025-05-17: 2; 2025-05-18: 2; 2025-05-19: 2; 2025-05-20: 2; 2025-05-21: 2; 2025-05-22: 2; 2025-05-23: 2; 2025-05-24: 2; 2025-05-25: 2; 2025-05-26: 2; 2025-05-27: 2; 2025-05-28: 2; 2025-05-29: 2; 2025-05-30: 2; 2025-05-31: 2; 2025-06-01: 2; 2025-06-02: 2; 2025-06-03: 2; 2025-06-04: 2; 2025-06-05: 2
9 | M/s MSC | FDN | Dumper | bar: 2025-02-21 to 2025-03-02; 2025-03-26 to 2025-06-05
9 | M/s MSC | FDN | Boom Placer | bar: 2025-03-02; 2025-03-26 to 2025-06-05
9 | M/s MSC | FDN | Roller (10t & 5t) | bar: 2025-02-22 to 2025-03-02; 2025-03-26 to 2025-06-05
9 | M/s MSC | FDN | Road Gradar | bar: 2025-02-21 to 2025-03-02; 2025-03-26 to 2025-06-05
9 | M/s MSC | FDN | JCB | bar: 2025-02-21 to 2025-03-02; 2025-03-26 to 2025-06-05
9 | M/s MSC | FDN | Trailer | bar: 2025-02-26 to 2025-03-02; 2025-03-26 to 2025-06-05
9 | M/s MSC | FDN | Water Tanker | bar: 2025-02-28 to 2025-03-02; 2025-03-26 to 2025-06-05
9 | M/s MSC | FDN | Tractor | bar: 2025-02-21 to 2025-03-02; 2025-03-26 to 2025-06-05
9 | M/s MSC | FDN | Vibrator | 2025-03-02: 8; 2025-03-26: 8; 2025-03-27: 8; 2025-03-28: 8; 2025-03-29: 8; 2025-03-30: 8; 2025-03-31: 8; 2025-04-01: 8; 2025-04-02: 8; 2025-04-03: 8; 2025-04-04: 8; 2025-04-05: 8; 2025-04-06: 8; 2025-04-07: 8; 2025-04-08: 8; 2025-04-09: 8; 2025-04-10: 8; 2025-04-11: 8; 2025-04-12: 8; 2025-04-13: 8; 2025-04-14: 8; 2025-04-15: 8; 2025-04-16: 8; 2025-04-17: 8; 2025-04-18: 8; 2025-04-19: 8; 2025-04-20: 8; 2025-04-21: 8; 2025-04-22: 8; 2025-04-23: 8; 2025-04-24: 8; 2025-04-25: 8; 2025-04-26: 8; 2025-04-27: 8; 2025-04-28: 8; 2025-04-29: 8; 2025-04-30: 8; 2025-05-01: 8; 2025-05-02: 8; 2025-05-03: 8; 2025-05-04: 8; 2025-05-05: 8; 2025-05-06: 8; 2025-05-07: 8; 2025-05-08: 8; 2025-05-09: 8; 2025-05-10: 8; 2025-05-11: 8; 2025-05-12: 8; 2025-05-13: 8; 2025-05-14: 8; 2025-05-15: 8; 2025-05-16: 8; 2025-05-17: 8; 2025-05-18: 8; 2025-05-19: 8; 2025-05-20: 8; 2025-05-21: 8; 2025-05-22: 8; 2025-05-23: 8; 2025-05-24: 8; 2025-05-25: 8; 2025-05-26: 8; 2025-05-27: 8; 2025-05-28: 8; 2025-05-29: 8; 2025-05-30: 8; 2025-05-31: 8; 2025-06-01: 8; 2025-06-02: 8; 2025-06-03: 8; 2025-06-04: 8; 2025-06-05: 8
9 | M/s MSC | FDN | DG | 2025-02-21: 1; 2025-02-22: 1; 2025-02-23: 1; 2025-02-24: 1; 2025-02-25: 1; 2025-02-26: 1; 2025-02-27: 2; 2025-02-28: 2; 2025-03-01: 2; 2025-03-02: 2; 2025-03-26: 2; 2025-03-27: 2; 2025-03-28: 2; 2025-03-29: 2; 2025-03-30: 2; 2025-03-31: 2; 2025-04-01: 2; 2025-04-02: 2; 2025-04-03: 2; 2025-04-04: 2; 2025-04-05: 2; 2025-04-06: 2; 2025-04-07: 2; 2025-04-08: 2; 2025-04-09: 2; 2025-04-10: 2; 2025-04-11: 2; 2025-04-12: 2; 2025-04-13: 2; 2025-04-14: 2; 2025-04-15: 2; 2025-04-16: 2; 2025-04-17: 2; 2025-04-18: 2; 2025-04-19: 2; 2025-04-20: 2; 2025-04-21: 2; 2025-04-22: 2; 2025-04-23: 2; 2025-04-24: 2; 2025-04-25: 2; 2025-04-26: 2; 2025-04-27: 2; 2025-04-28: 2; 2025-04-29: 2; 2025-04-30: 2; 2025-05-01: 2; 2025-05-02: 2; 2025-05-03: 2; 2025-05-04: 2; 2025-05-05: 2; 2025-05-06: 2; 2025-05-07: 2; 2025-05-08: 2; 2025-05-09: 2; 2025-05-10: 2; 2025-05-11: 2; 2025-05-12: 2; 2025-05-13: 2; 2025-05-14: 2; 2025-05-15: 2; 2025-05-16: 2; 2025-05-17: 2; 2025-05-18: 2; 2025-05-19: 2; 2025-05-20: 2; 2025-05-21: 2; 2025-05-22: 2; 2025-05-23: 2; 2025-05-24: 2; 2025-05-25: 2; 2025-05-26: 2; 2025-05-27: 2; 2025-05-28: 2; 2025-05-29: 2; 2025-05-30: 2; 2025-05-31: 2; 2025-06-01: 2; 2025-06-02: 2; 2025-06-03: 2; 2025-06-04: 2; 2025-06-05: 2
10 | M/s MECC | FDN | Excavator | bar: 2025-03-02 to 2025-04-10
10 | M/s MECC | FDN | Dumper | 2025-03-02: 2; 2025-03-03: 2; 2025-03-04: 2; 2025-03-05: 2; 2025-03-06: 2; 2025-03-07: 2; 2025-03-08: 2; 2025-03-09: 2; 2025-03-10: 2; 2025-03-11: 2; 2025-03-12: 2; 2025-03-13: 2; 2025-03-14: 2; 2025-03-15: 2; 2025-03-16: 2; 2025-03-17: 2; 2025-03-18: 2; 2025-03-19: 2; 2025-03-20: 2; 2025-03-21: 2; 2025-03-22: 2; 2025-03-23: 2; 2025-03-24: 2; 2025-03-25: 2; 2025-03-26: 2; 2025-03-27: 2; 2025-03-28: 2; 2025-03-29: 2; 2025-03-30: 2; 2025-03-31: 2; 2025-04-01: 2; 2025-04-02: 2; 2025-04-03: 2; 2025-04-04: 2; 2025-04-05: 2; 2025-04-06: 2; 2025-04-07: 2; 2025-04-08: 2; 2025-04-09: 2; 2025-04-10: 2
10 | M/s MECC | FDN | Boom Placer | bar: 2025-03-11 to 2025-04-10
10 | M/s MECC | FDN | Roller (10t & 5t) | bar: 2025-03-02 to 2025-04-10
10 | M/s MECC | FDN | Road Gradar
10 | M/s MECC | FDN | JCB | bar: 2025-03-02 to 2025-04-10
10 | M/s MECC | FDN | Trailer
10 | M/s MECC | FDN | Water Tanker | bar: 2025-03-02 to 2025-04-10
10 | M/s MECC | FDN | Tractor
10 | M/s MECC | FDN | Vibrator | 2025-03-11: 4; 2025-03-12: 4; 2025-03-13: 4; 2025-03-14: 4; 2025-03-15: 4; 2025-03-16: 4; 2025-03-17: 4; 2025-03-18: 4; 2025-03-19: 4; 2025-03-20: 4; 2025-03-21: 4; 2025-03-22: 4; 2025-03-23: 4; 2025-03-24: 4; 2025-03-25: 4; 2025-03-26: 4; 2025-03-27: 4; 2025-03-28: 4; 2025-03-29: 4; 2025-03-30: 4; 2025-03-31: 4; 2025-04-01: 4; 2025-04-02: 4; 2025-04-03: 4; 2025-04-04: 4; 2025-04-05: 4; 2025-04-06: 4; 2025-04-07: 4; 2025-04-08: 4; 2025-04-09: 4; 2025-04-10: 4
10 | M/s MECC | FDN | DG | bar: 2025-03-02 to 2025-04-10
11 | M/s PSB Infra | FDN | Excavator | bar: 2025-02-14 to 2025-06-05
11 | M/s PSB Infra | FDN | Dumper | bar: 2025-03-02 to 2025-06-05
11 | M/s PSB Infra | FDN | Boom Placer
11 | M/s PSB Infra | FDN | Roller (10t & 5t) | bar: 2025-03-02 to 2025-06-05
11 | M/s PSB Infra | FDN | Road Gradar | bar: 2025-03-02 to 2025-06-05
11 | M/s PSB Infra | FDN | JCB | bar: 2025-03-02 to 2025-06-05
11 | M/s PSB Infra | FDN | Trailer | bar: 2025-03-02 to 2025-06-05
11 | M/s PSB Infra | FDN | Water Tanker
11 | M/s PSB Infra | FDN | Tractor
11 | M/s PSB Infra | FDN | Vibrator | [60 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
11 | M/s PSB Infra | FDN | DG | [60 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
12 | M/s ShreeRam Constructions | FDN | Excavator | bar: 2025-02-23 to 2025-03-13
12 | M/s ShreeRam Constructions | FDN | Dumper | 2025-02-23: 2; 2025-02-24: 2; 2025-02-25: 2; 2025-02-26: 2; 2025-02-27: 2; 2025-02-28: 2; 2025-03-01: 2; 2025-03-02: 2; 2025-03-03: 2; 2025-03-04: 2; 2025-03-05: 2; 2025-03-06: 2; 2025-03-07: 2; 2025-03-08: 2; 2025-03-09: 2; 2025-03-10: 2; 2025-03-11: 2; 2025-03-12: 2; 2025-03-13: 2
12 | M/s ShreeRam Constructions | FDN | Boom Placer
12 | M/s ShreeRam Constructions | FDN | Roller (10t & 5t) | bar: 2025-02-23 to 2025-03-13
12 | M/s ShreeRam Constructions | FDN | Road Gradar
12 | M/s ShreeRam Constructions | FDN | JCB | bar: 2025-02-23 to 2025-03-13
12 | M/s ShreeRam Constructions | FDN | Trailer
12 | M/s ShreeRam Constructions | FDN | Water Tanker
12 | M/s ShreeRam Constructions | FDN | Tractor
12 | M/s ShreeRam Constructions | FDN | Vibrator | 2025-02-23: 4; 2025-02-24: 4; 2025-02-25: 4; 2025-02-26: 4; 2025-02-27: 4; 2025-02-28: 4; 2025-03-01: 4; 2025-03-02: 4; 2025-03-03: 4; 2025-03-04: 4; 2025-03-05: 4; 2025-03-06: 4; 2025-03-07: 4; 2025-03-08: 4; 2025-03-09: 4; 2025-03-10: 4; 2025-03-11: 4; 2025-03-12: 4; 2025-03-13: 4
12 | M/s ShreeRam Constructions | FDN | DG | bar: 2025-02-23 to 2025-03-13
13 | M/s SVRE | FDN | Excavator | bar: 2025-02-18 to 2025-06-05
13 | M/s SVRE | FDN | Dumper | bar: 2025-02-18 to 2025-06-05
13 | M/s SVRE | FDN | Roller (10t & 5t)
13 | M/s SVRE | FDN | Boom Placer
13 | M/s SVRE | FDN | Road Gradar
13 | M/s SVRE | FDN | JCB | bar: 2025-02-18 to 2025-06-05
13 | M/s SVRE | FDN | Trailer | bar: 2025-02-18 to 2025-06-05
13 | M/s SVRE | FDN | Water Tanker | bar: 2025-02-18 to 2025-06-05
13 | M/s SVRE | FDN | Tractor
13 | M/s SVRE | FDN | Vibrator | [48 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
13 | M/s SVRE | FDN | DG | bar: 2025-02-18 to 2025-06-05
14 | M/s MK Chaudhary | FDN | Excavator | bar: 2025-03-09 to 2025-06-05
14 | M/s MK Chaudhary | FDN | Dumper | bar: 2025-03-09 to 2025-06-05
14 | M/s MK Chaudhary | FDN | Boom Placer
14 | M/s MK Chaudhary | FDN | Roller (10t & 5t)
14 | M/s MK Chaudhary | FDN | Road Gradar
14 | M/s MK Chaudhary | FDN | JCB | bar: 2025-03-09 to 2025-06-05
14 | M/s MK Chaudhary | FDN | Trailer
14 | M/s MK Chaudhary | FDN | Water Tanker | bar: 2025-03-09 to 2025-06-05
14 | M/s MK Chaudhary | FDN | Tractor | bar: 2025-03-09 to 2025-06-05
14 | M/s MK Chaudhary | FDN | Vibrator | 2025-03-09: 4; 2025-03-10: 4; 2025-03-11: 4; 2025-03-12: 4; 2025-03-13: 4; 2025-03-14: 4; 2025-03-15: 4; 2025-03-16: 4; 2025-03-17: 4; 2025-03-18: 4; 2025-03-19: 4; 2025-03-20: 4; 2025-03-21: 4; 2025-03-22: 4; 2025-03-23: 4; 2025-03-24: 4; 2025-03-25: 4; 2025-03-26: 4; 2025-03-27: 4; 2025-03-28: 4; 2025-03-29: 4; 2025-03-30: 4; 2025-03-31: 4; 2025-04-01: 4; 2025-04-02: 4; 2025-04-03: 4; 2025-04-04: 4; 2025-04-05: 4; 2025-04-06: 4; 2025-04-07: 4; 2025-04-08: 4; 2025-04-09: 4; 2025-04-10: 4; 2025-04-11: 4; 2025-04-12: 4; 2025-04-13: 4; 2025-04-14: 4; 2025-04-15: 4; 2025-04-16: 4; 2025-04-17: 4; 2025-04-18: 4; 2025-04-19: 4; 2025-04-20: 4; 2025-04-21: 4; 2025-04-22: 4; 2025-04-23: 4; 2025-04-24: 4; 2025-04-25: 4; 2025-04-26: 4; 2025-04-27: 4; 2025-04-28: 4; 2025-04-29: 4; 2025-04-30: 4; 2025-05-01: 4; 2025-05-02: 4; 2025-05-03: 4; 2025-05-04: 4; 2025-05-05: 4; 2025-05-06: 4; 2025-05-07: 4; 2025-05-08: 4; 2025-05-09: 4; 2025-05-10: 4; 2025-05-11: 4; 2025-05-12: 4; 2025-05-13: 4; 2025-05-14: 4; 2025-05-15: 4; 2025-05-16: 4; 2025-05-17: 4; 2025-05-18: 4; 2025-05-19: 4; 2025-05-20: 4; 2025-05-21: 4; 2025-05-22: 4; 2025-05-23: 4; 2025-05-24: 4; 2025-05-25: 4; 2025-05-26: 4; 2025-05-27: 4; 2025-05-28: 4; 2025-05-29: 4; 2025-05-30: 4; 2025-05-31: 4; 2025-06-01: 4; 2025-06-02: 4; 2025-06-03: 4; 2025-06-04: 4; 2025-06-05: 4
14 | M/s MK Chaudhary | FDN | DG | 2025-03-09: 2; 2025-03-10: 2; 2025-03-11: 2; 2025-03-12: 2; 2025-03-13: 2; 2025-03-14: 2; 2025-03-15: 2; 2025-03-16: 2; 2025-03-17: 2; 2025-03-18: 2; 2025-03-19: 2; 2025-03-20: 2; 2025-03-21: 2; 2025-03-22: 2; 2025-03-23: 2; 2025-03-24: 2; 2025-03-25: 2; 2025-03-26: 2; 2025-03-27: 2; 2025-03-28: 2; 2025-03-29: 2; 2025-03-30: 2; 2025-03-31: 2; 2025-04-01: 2; 2025-04-02: 2; 2025-04-03: 2; 2025-04-04: 2; 2025-04-05: 2; 2025-04-06: 2; 2025-04-07: 2; 2025-04-08: 2; 2025-04-09: 2; 2025-04-10: 2; 2025-04-11: 2; 2025-04-12: 2; 2025-04-13: 2; 2025-04-14: 2; 2025-04-15: 2; 2025-04-16: 2; 2025-04-17: 2; 2025-04-18: 2; 2025-04-19: 2; 2025-04-20: 2; 2025-04-21: 2; 2025-04-22: 2; 2025-04-23: 2; 2025-04-24: 2; 2025-04-25: 2; 2025-04-26: 2; 2025-04-27: 2; 2025-04-28: 2; 2025-04-29: 2; 2025-04-30: 2; 2025-05-01: 2; 2025-05-02: 2; 2025-05-03: 2; 2025-05-04: 2; 2025-05-05: 2; 2025-05-06: 2; 2025-05-07: 2; 2025-05-08: 2; 2025-05-09: 2; 2025-05-10: 2; 2025-05-11: 2; 2025-05-12: 2; 2025-05-13: 2; 2025-05-14: 2; 2025-05-15: 2; 2025-05-16: 2; 2025-05-17: 2; 2025-05-18: 2; 2025-05-19: 2; 2025-05-20: 2; 2025-05-21: 2; 2025-05-22: 2; 2025-05-23: 2; 2025-05-24: 2; 2025-05-25: 2; 2025-05-26: 2; 2025-05-27: 2; 2025-05-28: 2; 2025-05-29: 2; 2025-05-30: 2; 2025-05-31: 2; 2025-06-01: 2; 2025-06-02: 2; 2025-06-03: 2; 2025-06-04: 2; 2025-06-05: 2
15 | M/s Bhawani Construction | FDN | Excavator | bar: 2025-04-07 to 2025-06-05
15 | M/s Bhawani Construction | FDN | Dumper
15 | M/s Bhawani Construction | FDN | Boom Placer
15 | M/s Bhawani Construction | FDN | Roller (10t & 5t)
15 | M/s Bhawani Construction | FDN | Road Gradar
15 | M/s Bhawani Construction | FDN | JCB | bar: 2025-04-11 to 2025-06-05
15 | M/s Bhawani Construction | FDN | Trailer
15 | M/s Bhawani Construction | FDN | Water Tanker
15 | M/s Bhawani Construction | FDN | Tractor
15 | M/s Bhawani Construction | FDN | Vibrator
15 | M/s Bhawani Construction | FDN | DG
16 | M/s ShreeJi Construction | FDN | Excavator | bar: 2025-04-17 to 2025-06-05
16 | M/s ShreeJi Construction | FDN | Dumper | 2025-04-17: 2; 2025-04-18: 2; 2025-04-19: 2; 2025-04-20: 2; 2025-04-21: 2; 2025-04-22: 2; 2025-04-23: 2; 2025-04-24: 2; 2025-04-25: 2; 2025-04-26: 2; 2025-04-27: 2; 2025-04-28: 2; 2025-04-29: 2; 2025-04-30: 2; 2025-05-01: 2; 2025-05-02: 2; 2025-05-03: 2; 2025-05-04: 2; 2025-05-05: 2; 2025-05-06: 2; 2025-05-07: 2; 2025-05-08: 2; 2025-05-09: 2; 2025-05-10: 2; 2025-05-11: 2; 2025-05-12: 2; 2025-05-13: 2; 2025-05-14: 2; 2025-05-15: 2; 2025-05-16: 2; 2025-05-17: 2; 2025-05-18: 2; 2025-05-19: 2; 2025-05-20: 2; 2025-05-21: 2; 2025-05-22: 2; 2025-05-23: 2; 2025-05-24: 2; 2025-05-25: 2; 2025-05-26: 2; 2025-05-27: 2; 2025-05-28: 2; 2025-05-29: 2; 2025-05-30: 2; 2025-05-31: 2; 2025-06-01: 2; 2025-06-02: 2; 2025-06-03: 2; 2025-06-04: 2; 2025-06-05: 2
16 | M/s ShreeJi Construction | FDN | Boom Placer | bar: 2025-04-17 to 2025-06-05
16 | M/s ShreeJi Construction | FDN | Roller (10t & 5t) | bar: 2025-04-17 to 2025-06-05
16 | M/s ShreeJi Construction | FDN | Road Gradar
16 | M/s ShreeJi Construction | FDN | JCB | 2025-04-17: 2; 2025-04-18: 2; 2025-04-19: 2; 2025-04-20: 2; 2025-04-21: 2; 2025-04-22: 2; 2025-04-23: 2; 2025-04-24: 2; 2025-04-25: 2; 2025-04-26: 2; 2025-04-27: 2; 2025-04-28: 2; 2025-04-29: 2; 2025-04-30: 2; 2025-05-01: 2; 2025-05-02: 2; 2025-05-03: 2; 2025-05-04: 2; 2025-05-05: 2; 2025-05-06: 2; 2025-05-07: 2; 2025-05-08: 2; 2025-05-09: 2; 2025-05-10: 2; 2025-05-11: 2; 2025-05-12: 2; 2025-05-13: 2; 2025-05-14: 2; 2025-05-15: 2; 2025-05-16: 2; 2025-05-17: 2; 2025-05-18: 2; 2025-05-19: 2; 2025-05-20: 2; 2025-05-21: 2; 2025-05-22: 2; 2025-05-23: 2; 2025-05-24: 2; 2025-05-25: 2; 2025-05-26: 2; 2025-05-27: 2; 2025-05-28: 2; 2025-05-29: 2; 2025-05-30: 2; 2025-05-31: 2; 2025-06-01: 2; 2025-06-02: 2; 2025-06-03: 2; 2025-06-04: 2; 2025-06-05: 2
16 | M/s ShreeJi Construction | FDN | Trailer | 2025-04-17: 3; 2025-04-18: 3; 2025-04-19: 3; 2025-04-20: 3; 2025-04-21: 3; 2025-04-22: 3; 2025-04-23: 3; 2025-04-24: 3; 2025-04-25: 3; 2025-04-26: 3; 2025-04-27: 3; 2025-04-28: 3; 2025-04-29: 3; 2025-04-30: 3; 2025-05-01: 3; 2025-05-02: 3; 2025-05-03: 3; 2025-05-04: 3; 2025-05-05: 3; 2025-05-06: 3; 2025-05-07: 3; 2025-05-08: 3; 2025-05-09: 3; 2025-05-10: 3; 2025-05-11: 3; 2025-05-12: 3; 2025-05-13: 3; 2025-05-14: 3; 2025-05-15: 3; 2025-05-16: 3; 2025-05-17: 3; 2025-05-18: 3; 2025-05-19: 3; 2025-05-20: 3; 2025-05-21: 3; 2025-05-22: 3; 2025-05-23: 3; 2025-05-24: 3; 2025-05-25: 3; 2025-05-26: 3; 2025-05-27: 3; 2025-05-28: 3; 2025-05-29: 3; 2025-05-30: 3; 2025-05-31: 3; 2025-06-01: 3; 2025-06-02: 3; 2025-06-03: 3; 2025-06-04: 3; 2025-06-05: 3
16 | M/s ShreeJi Construction | FDN | Water Tanker | bar: 2025-04-17 to 2025-06-05
16 | M/s ShreeJi Construction | FDN | Tractor | bar: 2025-04-17 to 2025-06-05
16 | M/s ShreeJi Construction | FDN | Vibrator | 2025-04-17: 6; 2025-04-18: 6; 2025-04-19: 6; 2025-04-20: 6; 2025-04-21: 6; 2025-04-22: 6; 2025-04-23: 6; 2025-04-24: 6; 2025-04-25: 6; 2025-04-26: 6; 2025-04-27: 6; 2025-04-28: 6; 2025-04-29: 6; 2025-04-30: 6; 2025-05-01: 6; 2025-05-02: 6; 2025-05-03: 6; 2025-05-04: 6; 2025-05-05: 6; 2025-05-06: 6; 2025-05-07: 6; 2025-05-08: 6; 2025-05-09: 6; 2025-05-10: 6; 2025-05-11: 6; 2025-05-12: 6; 2025-05-13: 6; 2025-05-14: 6; 2025-05-15: 6; 2025-05-16: 6; 2025-05-17: 6; 2025-05-18: 6; 2025-05-19: 6; 2025-05-20: 6; 2025-05-21: 6; 2025-05-22: 6; 2025-05-23: 6; 2025-05-24: 6; 2025-05-25: 6; 2025-05-26: 6; 2025-05-27: 6; 2025-05-28: 6; 2025-05-29: 6; 2025-05-30: 6; 2025-05-31: 6; 2025-06-01: 6; 2025-06-02: 6; 2025-06-03: 6; 2025-06-04: 6; 2025-06-05: 6
16 | M/s ShreeJi Construction | FDN | DG | 2025-04-17: 4; 2025-04-18: 4; 2025-04-19: 4; 2025-04-20: 4; 2025-04-21: 4; 2025-04-22: 4; 2025-04-23: 4; 2025-04-24: 4; 2025-04-25: 4; 2025-04-26: 4; 2025-04-27: 4; 2025-04-28: 4; 2025-04-29: 4; 2025-04-30: 4; 2025-05-01: 4; 2025-05-02: 4; 2025-05-03: 4; 2025-05-04: 4; 2025-05-05: 4; 2025-05-06: 4; 2025-05-07: 4; 2025-05-08: 4; 2025-05-09: 4; 2025-05-10: 4; 2025-05-11: 4; 2025-05-12: 4; 2025-05-13: 4; 2025-05-14: 4; 2025-05-15: 4; 2025-05-16: 4; 2025-05-17: 4; 2025-05-18: 4; 2025-05-19: 4; 2025-05-20: 4; 2025-05-21: 4; 2025-05-22: 4; 2025-05-23: 4; 2025-05-24: 4; 2025-05-25: 4; 2025-05-26: 4; 2025-05-27: 4; 2025-05-28: 4; 2025-05-29: 4; 2025-05-30: 4; 2025-05-31: 4; 2025-06-01: 4; 2025-06-02: 4; 2025-06-03: 4; 2025-06-04: 4; 2025-06-05: 4
17 | M/s CEIPL | FDN | Excavator | bar: 2025-04-21 to 2025-06-05
17 | M/s CEIPL | FDN | Dumper
17 | M/s CEIPL | FDN | Boom Placer
17 | M/s CEIPL | FDN | Roller (10t & 5t)
17 | M/s CEIPL | FDN | Road Gradar
17 | M/s CEIPL | FDN | JCB | bar: 2025-04-21 to 2025-06-05
17 | M/s CEIPL | FDN | Trailer | bar: 2025-04-21 to 2025-06-05
17 | M/s CEIPL | FDN | Water Tanker | bar: 2025-04-21 to 2025-06-05
17 | M/s CEIPL | FDN | Tractor | bar: 2025-04-21 to 2025-06-05
17 | M/s CEIPL | FDN | Vibrator | 2025-04-21: 2; 2025-04-22: 2; 2025-04-23: 2; 2025-04-24: 2; 2025-04-25: 2; 2025-04-26: 2; 2025-04-27: 2; 2025-04-28: 2; 2025-04-29: 2; 2025-04-30: 2; 2025-05-01: 2; 2025-05-02: 2; 2025-05-03: 2; 2025-05-04: 2; 2025-05-05: 2; 2025-05-06: 2; 2025-05-07: 2; 2025-05-08: 2; 2025-05-09: 2; 2025-05-10: 2; 2025-05-11: 2; 2025-05-12: 2; 2025-05-13: 2; 2025-05-14: 2; 2025-05-15: 2; 2025-05-16: 2; 2025-05-17: 2; 2025-05-18: 2; 2025-05-19: 2; 2025-05-20: 2; 2025-05-21: 2; 2025-05-22: 2; 2025-05-23: 2; 2025-05-24: 2; 2025-05-25: 2; 2025-05-26: 2; 2025-05-27: 2; 2025-05-28: 2; 2025-05-29: 2; 2025-05-30: 2; 2025-05-31: 2; 2025-06-01: 2; 2025-06-02: 2; 2025-06-03: 2; 2025-06-04: 2; 2025-06-05: 2
17 | M/s CEIPL | FDN | DG | bar: 2025-04-21 to 2025-06-05
18 | M/s HBG | FDN | Excavator | bar: 2025-05-06 to 2025-06-05
18 | M/s HBG | FDN | Dumper | 2025-05-06: 2; 2025-05-07: 2; 2025-05-08: 2; 2025-05-09: 2; 2025-05-10: 2; 2025-05-11: 2; 2025-05-12: 2; 2025-05-13: 2; 2025-05-14: 2; 2025-05-15: 2; 2025-05-16: 2; 2025-05-17: 2; 2025-05-18: 2; 2025-05-19: 2; 2025-05-20: 2; 2025-05-21: 2; 2025-05-22: 2; 2025-05-23: 2; 2025-05-24: 2; 2025-05-25: 2; 2025-05-26: 2; 2025-05-27: 2; 2025-05-28: 2; 2025-05-29: 2; 2025-05-30: 2; 2025-05-31: 2; 2025-06-01: 2; 2025-06-02: 2; 2025-06-03: 2; 2025-06-04: 2; 2025-06-05: 2
18 | M/s HBG | FDN | Boom Placer | 2025-05-06: 0; 2025-05-07: 0; 2025-05-08: 0; 2025-05-09: 0; 2025-05-10: 0; 2025-05-11: 0; 2025-05-12: 0; 2025-05-13: 0; 2025-05-14: 0; 2025-05-15: 0; 2025-05-16: 0; 2025-05-17: 0; 2025-05-18: 0; 2025-05-19: 0; 2025-05-20: 0; 2025-05-21: 0; 2025-05-22: 0; 2025-05-23: 0; 2025-05-24: 0; 2025-05-25: 0; 2025-05-26: 0; 2025-05-27: 0; 2025-05-28: 0; 2025-05-29: 0; 2025-05-30: 0; 2025-05-31: 0; 2025-06-01: 0; 2025-06-02: 0; 2025-06-03: 0; 2025-06-04: 0; 2025-06-05: 0
18 | M/s HBG | FDN | Roller (10t & 5t) | 2025-05-06: 0; 2025-05-07: 0; 2025-05-08: 0; 2025-05-09: 0; 2025-05-10: 0; 2025-05-11: 0; 2025-05-12: 0; 2025-05-13: 0; 2025-05-14: 0; 2025-05-15: 0; 2025-05-16: 0; 2025-05-17: 0; 2025-05-18: 0; 2025-05-19: 0; 2025-05-20: 0; 2025-05-21: 0; 2025-05-22: 0; 2025-05-23: 0; 2025-05-24: 0; 2025-05-25: 0; 2025-05-26: 0; 2025-05-27: 0; 2025-05-28: 0; 2025-05-29: 0; 2025-05-30: 0; 2025-05-31: 0; 2025-06-01: 0; 2025-06-02: 0; 2025-06-03: 0; 2025-06-04: 0; 2025-06-05: 0
18 | M/s HBG | FDN | Road Gradar
18 | M/s HBG | FDN | JCB | bar: 2025-05-06 to 2025-06-05
18 | M/s HBG | FDN | Trailer
18 | M/s HBG | FDN | Water Tanker | bar: 2025-05-06 to 2025-06-05
18 | M/s HBG | FDN | Tractor | bar: 2025-05-06 to 2025-06-05
18 | M/s HBG | FDN | Vibrator | 2025-05-06: 2; 2025-05-07: 2; 2025-05-08: 2; 2025-05-09: 2; 2025-05-10: 2; 2025-05-11: 2; 2025-05-12: 2; 2025-05-13: 2; 2025-05-14: 2; 2025-05-15: 2; 2025-05-16: 2; 2025-05-17: 2; 2025-05-18: 2; 2025-05-19: 2; 2025-05-20: 2; 2025-05-21: 2; 2025-05-22: 2; 2025-05-23: 2; 2025-05-24: 2; 2025-05-25: 2; 2025-05-26: 2; 2025-05-27: 2; 2025-05-28: 2; 2025-05-29: 2; 2025-05-30: 2; 2025-05-31: 2; 2025-06-01: 2; 2025-06-02: 2; 2025-06-03: 2; 2025-06-04: 2; 2025-06-05: 2
18 | M/s HBG | FDN | DG | 2025-05-06: 2; 2025-05-07: 2; 2025-05-08: 2; 2025-05-09: 2; 2025-05-10: 2; 2025-05-11: 2; 2025-05-12: 2; 2025-05-13: 2; 2025-05-14: 2; 2025-05-15: 2; 2025-05-16: 2; 2025-05-17: 2; 2025-05-18: 2; 2025-05-19: 2; 2025-05-20: 2; 2025-05-21: 2; 2025-05-22: 2; 2025-05-23: 2; 2025-05-24: 2; 2025-05-25: 2; 2025-05-26: 2; 2025-05-27: 2; 2025-05-28: 2; 2025-05-29: 2; 2025-05-30: 2; 2025-05-31: 2; 2025-06-01: 2; 2025-06-02: 2; 2025-06-03: 2; 2025-06-04: 2; 2025-06-05: 2
19 | M/s Odhav | FDN | Excavator | 2025-05-06: 2; 2025-05-07: 2; 2025-05-08: 2; 2025-05-09: 2; 2025-05-10: 2; 2025-05-11: 2; 2025-05-12: 2; 2025-05-13: 2; 2025-05-14: 2; 2025-05-15: 2; 2025-05-16: 2; 2025-05-17: 2; 2025-05-18: 2; 2025-05-19: 2; 2025-05-20: 2; 2025-05-21: 2; 2025-05-22: 2; 2025-05-23: 2; 2025-05-24: 2; 2025-05-25: 2; 2025-05-26: 2; 2025-05-27: 2; 2025-05-28: 2; 2025-05-29: 2; 2025-05-30: 2; 2025-05-31: 2; 2025-06-01: 2; 2025-06-02: 2; 2025-06-03: 2; 2025-06-04: 2; 2025-06-05: 2
19 | M/s Odhav | FDN | Dumper | 2025-05-06: 3; 2025-05-07: 3; 2025-05-08: 3; 2025-05-09: 3; 2025-05-10: 3; 2025-05-11: 3; 2025-05-12: 3; 2025-05-13: 3; 2025-05-14: 3; 2025-05-15: 3; 2025-05-16: 3; 2025-05-17: 3; 2025-05-18: 3; 2025-05-19: 3; 2025-05-20: 3; 2025-05-21: 3; 2025-05-22: 3; 2025-05-23: 3; 2025-05-24: 3; 2025-05-25: 3; 2025-05-26: 3; 2025-05-27: 3; 2025-05-28: 3; 2025-05-29: 3; 2025-05-30: 3; 2025-05-31: 3; 2025-06-01: 3; 2025-06-02: 3; 2025-06-03: 3; 2025-06-04: 3; 2025-06-05: 3
19 | M/s Odhav | FDN | Boom Placer | bar: 2025-05-06 to 2025-06-05
19 | M/s Odhav | FDN | Roller (10t & 5t) | bar: 2025-05-06 to 2025-06-05
19 | M/s Odhav | FDN | Road Gradar
19 | M/s Odhav | FDN | JCB | bar: 2025-05-06 to 2025-06-05
19 | M/s Odhav | FDN | Trailer | bar: 2025-05-06 to 2025-06-05
19 | M/s Odhav | FDN | Water Tanker | 2025-05-06: 2; 2025-05-07: 2; 2025-05-08: 2; 2025-05-09: 2; 2025-05-10: 2; 2025-05-11: 2; 2025-05-12: 2; 2025-05-13: 2; 2025-05-14: 2; 2025-05-15: 2; 2025-05-16: 2; 2025-05-17: 2; 2025-05-18: 2; 2025-05-19: 2; 2025-05-20: 2; 2025-05-21: 2; 2025-05-22: 2; 2025-05-23: 2; 2025-05-24: 2; 2025-05-25: 2; 2025-05-26: 2; 2025-05-27: 2; 2025-05-28: 2; 2025-05-29: 2; 2025-05-30: 2; 2025-05-31: 2; 2025-06-01: 2; 2025-06-02: 2; 2025-06-03: 2; 2025-06-04: 2; 2025-06-05: 2
19 | M/s Odhav | FDN | Tractor | bar: 2025-05-06 to 2025-06-05
19 | M/s Odhav | FDN | Vibrator | 2025-05-06: 3; 2025-05-07: 3; 2025-05-08: 3; 2025-05-09: 3; 2025-05-10: 3; 2025-05-11: 3; 2025-05-12: 3; 2025-05-13: 3; 2025-05-14: 3; 2025-05-15: 3; 2025-05-16: 3; 2025-05-17: 3; 2025-05-18: 3; 2025-05-19: 3; 2025-05-20: 3; 2025-05-21: 3; 2025-05-22: 3; 2025-05-23: 3; 2025-05-24: 3; 2025-05-25: 3; 2025-05-26: 3; 2025-05-27: 3; 2025-05-28: 3; 2025-05-29: 3; 2025-05-30: 3; 2025-05-31: 3; 2025-06-01: 3; 2025-06-02: 3; 2025-06-03: 3; 2025-06-04: 3; 2025-06-05: 3
19 | M/s Odhav | FDN | DG | 2025-05-06: 2; 2025-05-07: 2; 2025-05-08: 2; 2025-05-09: 2; 2025-05-10: 2; 2025-05-11: 2; 2025-05-12: 2; 2025-05-13: 2; 2025-05-14: 2; 2025-05-15: 2; 2025-05-16: 2; 2025-05-17: 2; 2025-05-18: 2; 2025-05-19: 2; 2025-05-20: 2; 2025-05-21: 2; 2025-05-22: 2; 2025-05-23: 2; 2025-05-24: 2; 2025-05-25: 2; 2025-05-26: 2; 2025-05-27: 2; 2025-05-28: 2; 2025-05-29: 2; 2025-05-30: 2; 2025-05-31: 2; 2025-06-01: 2; 2025-06-02: 2; 2025-06-03: 2; 2025-06-04: 2; 2025-06-05: 2
20 | M/s Tejas | FDN | Excavator | bar: 2025-03-11 to 2025-06-05
20 | M/s Tejas | FDN | Dumper | bar: 2025-03-11 to 2025-06-05
20 | M/s Tejas | FDN | Boom Placer | bar: 2025-03-11 to 2025-06-05
20 | M/s Tejas | FDN | Roller (10t & 5t) | bar: 2025-03-11 to 2025-06-05
20 | M/s Tejas | FDN | Road Gradar
20 | M/s Tejas | FDN | JCB | bar: 2025-03-11 to 2025-06-05
20 | M/s Tejas | FDN | Trailer
20 | M/s Tejas | FDN | Water Tanker | bar: 2025-03-11 to 2025-06-05
20 | M/s Tejas | FDN | Tractor | bar: 2025-03-11 to 2025-06-05
20 | M/s Tejas | FDN | Vibrator | 2025-03-11: 2; 2025-03-12: 2; 2025-03-13: 2; 2025-03-14: 2; 2025-03-15: 2; 2025-03-16: 2; 2025-03-17: 2; 2025-03-18: 2; 2025-03-19: 2; 2025-03-20: 2; 2025-03-21: 2; 2025-03-22: 2; 2025-03-23: 2; 2025-03-24: 2; 2025-03-25: 2; 2025-03-26: 2; 2025-03-27: 2; 2025-03-28: 2; 2025-03-29: 2; 2025-03-30: 2; 2025-03-31: 2; 2025-04-01: 2; 2025-04-02: 2; 2025-04-03: 2; 2025-04-04: 2; 2025-04-05: 2; 2025-04-06: 2; 2025-04-07: 2; 2025-04-08: 2; 2025-04-09: 2; 2025-04-10: 2; 2025-04-11: 2; 2025-04-12: 2; 2025-04-13: 2; 2025-04-14: 2; 2025-04-15: 2; 2025-04-16: 2; 2025-04-17: 2; 2025-04-18: 2; 2025-04-19: 2; 2025-04-20: 2; 2025-04-21: 2; 2025-04-22: 2; 2025-04-23: 2; 2025-04-24: 2; 2025-04-25: 2; 2025-04-26: 2; 2025-04-27: 2; 2025-04-28: 2; 2025-04-29: 2; 2025-04-30: 2; 2025-05-01: 2; 2025-05-02: 2; 2025-05-03: 2; 2025-05-04: 2; 2025-05-05: 2; 2025-05-06: 2; 2025-05-07: 2; 2025-05-08: 2; 2025-05-09: 2; 2025-05-10: 2; 2025-05-11: 2; 2025-05-12: 2; 2025-05-13: 2; 2025-05-14: 2; 2025-05-15: 2; 2025-05-16: 2; 2025-05-17: 2; 2025-05-18: 2; 2025-05-19: 2; 2025-05-20: 2; 2025-05-21: 2; 2025-05-22: 2; 2025-05-23: 2; 2025-05-24: 2; 2025-05-25: 2; 2025-05-26: 2; 2025-05-27: 2; 2025-05-28: 2; 2025-05-29: 2; 2025-05-30: 2; 2025-05-31: 2; 2025-06-01: 2; 2025-06-02: 2; 2025-06-03: 2; 2025-06-04: 2; 2025-06-05: 2
20 | M/s Tejas | FDN | DG | bar: 2025-03-11 to 2025-06-05

## Rain Fall
S.No | Date | START TIME | END TIME | Remarks
1 | 2025-06-15 | 03:00 A.M. | 04:00 A.M. | Low to Moderate
2 | 2025-06-16 | 9:15 P.M. | 10:15 P.M. | Heavy
3 |  | 10:15 P.M. | 1:00 A.M. | low
4 | 2025-06-26 | 22:00 | 0:30 | Heavy
5 | 2025-06-27 | 17:00 | 17:30 | Moderate
6 | 2025-06-27 | 9:30 | 23:00 | Slow
7 | 2025-06-28 | 17:15 | 18:00 | Moderate
8 |  | 22:20 | 23:15 | moderate
9 | 2025-07-01 | 0:10 | 0:30 | Slow
10 | 2025-07-02 | 4:00 | 5:00 | Slow
11 | 2025-07-04 | 17:10 | 18:20 | Heavy to Moderate
12 | 2025-07-06 | 11:50 | 12:30 | SLow
13 |  | 22:40 | 3:30 | Heavy
14 | 2025-07-07 | 9:00 | 11:00 | Moderate
15 | 2025-07-08 | 17:30 | 18:20 | Moderate
16 | 2025-07-14 | 19:30 | 19:40 | Heavy
17 | 2025-07-19 | 8:00:00AM | 1:00:00PM | Heavy
18 | 2025-07-20 | 3:00:00PM | 4:00:00PM | Medium
19 | 2025-07-21 | 8:00:00AM | 10:00:00AM | Medium
20 | 2025-07-21 | 11:00 | 14:30 | Medium
21 | 2025-08-14 | 4:35 | 5:00 | Moderate
22 | 2025-08-16 | 16:35 | 5:00 | Heavy
23 | 2025-08-17 | 22:20 | 3:00 | Heavy
24 | 2025-07-21 | 11:00 | 14:30 | Medium
25 | 2025-08-18 | 17:00 | 18:05 | Moderate
26 | 2025-08-18 | 23:10 | 0:00 | Moderate
27 | 2025-08-19 | 3:20 | 4:40 | Moderate
28 | 2025-08-19 | 16:20 | 20:40 | Heavy
29 | 2025-08-19 | 21:00 | 23:55 | Rain
30 | 2025-08-20 | 16:30 | 19:50 | Moderate
31 | 2025-08-21 | 17:00 | 0:10 | Heavy
32 | 2025-08-22 | 18:00 | 18:40 | Drizzling
33 | 2025-08-23 | 19:00 | 7:25PM | Slow
34 | 2025-08-24 | 2:00 | 2:30 | Medium
35 | 2025-09-04 | 19:30 | 20:45 | Heavy to Moderate
36 | 2025-09-06 | 19:30 | 21:00 | Heavy to Moderate
37 | 2025-09-06 | 21:10 | 0:00 | Heavy
38 | 2025-09-07 | 1:00 | 8:00 | Heavy
39 | 2025-09-07 | 8:30 | 23:00 | Heavy
40 | 2025-09-08 | 14:00 | 17:00 | Slow
41 | 2025-09-08 | 19:30 | 23:35 | moderate to heavy
42 | 2025-09-09 | 4:00 | 8:30 | moderate to slow
43 | 2025-09-09 | 12:30 | 13:30 | Medium
44 | 2025-10-01 | 3:30 | 4:30 | moderate to slow
45 | 2025-10-01 | 9:30 | 10:30 | moderate to slow
46 | 2025-10-02 | 18:30 | 20:30 | moderate to slow
47 | 2025-11-03 | 9:00 | 11:00 | moderate to slow

## 200WTG PH-II
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 |  | 110 | 111 | 112 | 113 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180
WTG FDN VENDOR | Sr. No. | SUB Station | SPV | 1: Locations; 2: USS FDN (FDN/Precast); 3: Feeder; 4: Stone Column Contractor; 5: Soil Test Status; 6: WTG Coordinates; 8: Soil Test; 14: Stone Column; 23: Plate Load Test; 30: Excavation; 37: Gravel Bed (Stone Blanket); 44: PCC; 51: Anchor Cage Assembly; 58: Steel bending; 65: Raft casting; 73: Backfilling & Compaction; 80: Grouting; 89: USS Column Works; 96: WTG Connecting Road; 103: TURNING Development |  | Crane Pad(40*40 M) & Boom Assembly Area Devlopment | [6 empty] | WTG Erection | [6 empty] | USS Erection Works | [6 empty] | MCC | [6 empty] | Pre-comm | [6 empty] | USS Testing Works | [6 empty] | HT Cable Laying & Terminations | [6 empty] | CEA Approval | [6 empty] | WTG Ready To Charge (CFT) | [6 empty] | WTG Commissioining | [6 empty] | Remarks
[9 empty] | E | N | Soil Test Plan Start Date (Nos) | Soil Test Plan Finish Date (Nos) | Fore Cast Finish Date | Soil Test Actual Start Date (Nos) | Soil Test Actual FInish Date (Nos) | Impact days due to hindrance | Stone Column Scope (Nos) | Stone Column Completed (Nos) | Stone Column Plan Start Date | Stone Column Plan Finish Date | Stone Column Forecast Completion | Stone Column Actual Start Date | Stone Column Actual Finish Date | No of Days | Impact days due to hindrance | Scope | PLT Plan Start Date | PLT Plan Finish Date | PLT Forecast Completion Date | PLT Actual Start Date | PLT Actual Finish Date | Impact days due to hindrance | Excavation Plan Start Date | Excavation Plan Finish Date | Excavation Forecast Completion | Excavation Actual Start Date | Excavation Actual FInish Date | No of Days | Impact days due to hindrance | Gravel Bed Plan Start Date | Gravel Bed Plan Finish Date | Gravel Bed Forecast Completion | Gravel Bed Actual Start Date | Gravel Bed Actual Finish Date | No of Days | Impact days due to hindrance | PCC Plan Start Date | PCC Plan Finish Date | Forecast Completion | PCC Actual Start Date | PCC Actual Finish Date | No of Days | Impact days due to hindrance | Anchor Cage Plan Start Date | Anchor Cage Plan Finish Date | Forecast Completion | Anchor Cage Actual Start Date | Anchor Cage Actual Finish Date | No of Days | Impact day due to hindrance | Steel Binding Plan Start Date | Steel Binding Plan Finish Date | Forecast Completion | Steel Binding Actual Start Date | Steel Binding Actual FInish Date | No of Days | Impact day due to hindrance | Raft Casting Plan Start Date | Raft Casting Plan Finish Date | Forecast Completion | Raft Casting Actual Start Date | Raft Casting Actual Finish Date | No of Days | No of Days Excavation & Raft Casting | Impact day due to hindrance | Backfilling Plan Start Date | Backfilling Plan Finish Date | Forecast Completion | Backfilling Actual Start Date | Backfilling Actual Finish Date | No of Days | Impact day due to hindrance | Grouting Plan Start Date | Grouting Plan Finish Date | Forecast Completion | Grouting Actual Start Date | Grouting Actual Finish Date | No of Days |  | Excavation to Casting (excl. curing) | Impact day due to hindrance | USS Civil Plan Start Date | USS Civil Plan Finish Date | Forecast Completion | USS Civil Actual Start Date | USS Civil Actual Finish Date | No of Days | Impact day due to hindrance | Road Plan Start Date | Road Plan Finish Date | Forecast Completion | Road Actual Start Date | Road Actual Finish Date | No of Days | Impact day due to hindrance | Turning Devlopment Plan Start Date | Turning Devlopment Finish Start Date | Forecast Completion | Turning Devlopment Actual Start Date | Turning Devlopment Actual Finish Date | No of Days | Impact day due to hindrance | Vendor | Crane Pad Plan Start Date | Crane Pad Plan Finish Date | Forecast Completion | Crane Pad Actual Start Date | Crane Pad Actual Finish Date | No of Days | Impact day due to hindrance | WTG Ere Plan Start Date | WTG Ere Plan Finish Date | Forecast Completion | WTG Ere Actual Start Date | WTG Ere Actual End Date | No of Days | Impact day due to hindrance | USS Ere Plan Start Date | USS Ere Plan Finish Date | Forecast Completion | USS Ere Actual Start Date | USS Ere Actual Finish Date | No of Days | Impact day due to hindrance | MCC Plan Start Date | MCC Plan Finish Date | Forecast Completion | MCC Actual Start Date | MCC Actual Finish Date | No of Days | Impact day due to hindrance | Pre-Comm Plan Start Date | Pre-Comm Plan Finish Date | Forecast Completion | Pre-Comm Actual Start Date | Pre-Comm Actual Finish Date | No of Days | Impact day due to hindrance | USS Testing Plan Start Date | USS Testing Plan Finish Date | Forecast Completion | USS Testing Actual Start Date | USS Testing Actual Finish Date | No of Days | Impact day due to hindrance | HT Cable Plan Start Date | HT Cable Plan Finish Date | Forecast Completion | HT Cable Actual Start Date | HT Cable Actual Finish Date | No of Days | Impact day due to hindrance | CEA Approval Plan Start Date | CEA Approval Plan Finish Date | Forecast Completion | CEA Approval Actual Start Date | CEA Approval Actual Finish Date | No of Days | Impact day due to hindrance | Grid-Conne Plan Start Date | Grid-Conne Plan Finish Date | Forecast Completion | Grid-Conne Actual Start Date | Grid-Conne Actual Finish Date | No of Days | Impact day due to hindrance | WTG Comm Plan Start Date | WTG Comm Plan Finish Date | Forecast Completion | WTG Comm Actual Start Date | WTG Comm Actual Finish Date | No of Days | Impact day due to hindrance
200 |  |  |  | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 0 | 200 | 200 | 0 | 44885 | 45081 | 200 | 200 | 0 | 200 | 200 |  | 0 | 46 | 46 | 46 | 0 | 46 | 46 | 3 | 200 | 200 | 0 | 199 | 199 |  |  | 200 | 200 | 0 | 199 | 199 |  | 6 | 200 | 200 | 0 | 199 | 199 |  | 3 | 200 | 200 | 0 | 199 | 199 |  | 2 | 200 | 200 | 0 | 199 | 199 |  | 8 | 200 | 200 | 0 | 199 | 199 |  |  | 1 | 200 | 200 | 0 | 199 | 198 |  | 0 | 200 | 200 | 0 | 199 | 199 |  |  |  | 0 | 200 | 200 | 0 | 200 | 200 |  | 0 | 200 | 200 | 0 | 200 | 200 |  | 0 | 200 | 200 | 0 | 200 | 199 |  | 0 | 200 | 200 | 200 | 0 | 199 | 199 |  | 3 | 200 | 200 | 0 | 199 | 198 |  | 0 | 200 | 200 | 0 | 199 | 198 |  | 4 | 200 | 200 | 0 | 198 | 198 |  | 7 | 200 | 200 | 0 | 198 | 198 |  | 19 | 200 | 200 | 0 | 198 | 198 |  | 4 | 200 | 200 | 0 | 200 | 200 |  | 0 | 200 | 200 |  | 200 | 200 |  |  | 200 | 200 | 0 | 199 | 199 |  | 7 | 200 | 200 | 0 | 198 | 198 |  | 4
HBG | 1 | PSS-9 | ARE48L | WTG 389 | Precast | F2 | Bauer | Done | 545090 | 2659277 | 2023-12-12 | 2024-01-24 |  | 2023-12-12 | 2024-01-24 |  | 207 | 199 | 2024-03-13 | 2024-03-22 |  | 2024-03-05 | 2024-03-11 | 7 |  | Yes | 2024-05-20 | 2024-05-30 |  | 2024-05-28 | 2024-06-03 |  | 2024-04-07 | 2024-04-07 |  | 2024-06-12 | 2024-06-17 | 6 |  | 2024-04-08 | 2024-04-08 |  | 2024-06-17 | 2024-06-28 | 12 |  | 2024-04-09 | 2024-04-09 |  | 2024-10-15 | 2024-10-15 | 1 |  | 2024-04-10 | 2024-04-11 |  | 2024-10-16 | 2024-10-17 | 2 |  | 2024-04-13 | 2024-04-20 |  | 2024-10-19 | 2024-11-04 | 17 |  | 2024-04-23 | 2024-04-24 |  | 2024-11-09 | 2024-11-10 | 2 | 152 |  | 2024-04-26 | 2024-05-02 |  | 2024-11-18 | 2024-12-06 | 19 |  | 2024-04-26 | 2024-05-02 |  | 2024-11-19 | 2024-11-19 | 1 |  |  |  | 2024-04-20 | 2024-05-04 |  | 2024-11-25 | 2024-11-28 | 4 |  | 2024-03-22 | 2024-03-28 |  | 2024-03-07 | 2024-03-17 | 11 |  | 2024-03-22 | 2024-03-28 |  | 2024-04-23 | 2024-05-01 | 9 |  | GP | 2024-05-06 | 2024-05-12 |  | 2024-04-23 | 2024-05-01 | 9 |  | 2024-06-04 | 2024-06-09 |  | 2024-11-10 | 2024-11-30 | 21 |  | 2024-05-26 | 2024-06-01 |  | 2024-12-02 | 2024-12-08 | 7 |  | 2024-06-11 | 2024-06-19 |  | 2024-12-08 | 2024-12-16 | 9 |  | 2024-06-20 | 2024-06-22 |  | 2024-12-19 | 2024-12-23 | 5 |  | 2024-06-07 | 2024-06-09 |  | 2024-12-09 | 2024-12-09 | 1 |  | 2024-05-26 | 2024-06-01 |  | 2024-05-26 | 2024-06-01 | 7 |  | 2024-06-05 | 2024-06-20 |  | 2024-11-14 | 2024-12-05 | 22 |  | 2024-06-09 | 2024-06-12 |  | 2024-12-11 | 2024-12-15 | 5 |  | 2024-06-22 | 2024-06-23 |  | 2024-12-24 | 2024-12-25 | 2 |  |  | 2024-06-01
MSC | 2 | PSS-9 | ARE48L | WTG 413 | Precast | F2 | Bauer | Done | 545741 | 2659960 | 2023-12-12 | 2024-01-24 |  | 2023-12-12 | 2024-01-24 |  | 211 | 211 | 2024-02-22 | 2024-03-02 |  | 2024-02-03 | 2024-02-12 | 10 | [8 empty] | 2024-03-28 | 2024-03-28 |  | 2024-05-07 | 2024-05-14 | 8 |  | 2024-03-29 | 2024-03-29 |  | 2024-05-15 | 2024-05-17 | 3 |  | 2024-03-30 | 2024-03-30 |  | 2024-05-25 | 2024-05-25 | 1 |  | 2024-03-31 | 2024-04-01 |  | 2024-05-27 | 2024-06-07 | 12 |  | 2024-04-03 | 2024-04-10 |  | 2024-06-08 | 2024-06-17 | 10 |  | 2024-04-13 | 2024-04-14 |  | 2024-06-20 | 2024-06-21 | 2 | 46 |  | 2024-04-16 | 2024-04-22 |  | 2024-07-01 | 2024-11-13 | 136 |  | 2024-04-16 | 2024-04-22 |  | 2024-07-02 | 2024-07-02 | 1 |  |  |  | 2024-04-10 | 2024-04-24 |  | 2024-09-18 | 2024-09-29 | 12 |  | 2024-03-06 | 2024-03-12 |  | 2024-02-23 | 2024-03-04 | 11 |  | 2024-03-06 | 2024-03-12 |  | 2024-04-22 | 2024-04-30 | 9 |  | GP | 2024-04-22 | 2024-04-28 |  | 2024-04-22 | 2024-04-30 | 9 |  | 2024-05-16 | 2024-05-21 |  | 2024-08-01 | 2024-08-18 | 18 |  | 2024-05-10 | 2024-05-16 |  | 2024-10-03 | 2024-10-15 | 13 |  | 2024-05-23 | 2024-05-31 |  | 2024-08-23 | 2024-09-27 | 36 |  | 2024-06-01 | 2024-06-03 |  | 2024-09-30 | 2024-10-08 | 9 |  | 2024-05-22 | 2024-05-24 |  | 2024-10-16 | 2024-10-25 | 10 | Delay due to internal panel issue | 2024-05-10 | 2024-05-16 |  | 2024-05-10 | 2024-05-16 | 7 |  | 2024-05-03 | 2024-05-18 |  | 2024-09-30 | 2024-10-28 | 29 |  | 2024-05-24 | 2024-05-27 |  | 2024-10-25 | 2024-11-18 | 25 | Balance Civil works in progress (Fencing, Hand rail, Final layer Back filling) | 2024-06-03 | 2024-06-04 |  | 2024-11-18 | 2024-11-21 | 4 |  |  | 2024-06-01
HBG | 3 | PSS-9 | ARE48L | WTG 363 | Precast | F1 | Bauer | Done | 544255 | 2659542 | 2023-12-18 | 2024-01-25 |  | 2023-12-18 | 2024-01-25 |  | 205 | 205 | 2024-03-04 | 2024-03-13 |  | 2024-02-25 | 2024-03-05 | 10 | [8 empty] | 2024-04-03 | 2024-04-03 |  | 2024-05-24 | 2024-05-30 | 7 |  | 2024-04-04 | 2024-04-04 |  | 2024-05-31 | 2024-06-09 | 10 |  | 2024-04-05 | 2024-04-05 |  | 2024-06-14 | 2024-06-14 | 1 |  | 2024-04-06 | 2024-04-07 |  | 2024-06-15 | 2024-06-16 | 2 |  | 2024-04-09 | 2024-04-16 |  | 2024-06-17 | 2024-07-01 | 15 |  | 2024-04-19 | 2024-04-20 |  | 2024-07-02 | 2024-07-03 | 2 | 41 |  | 2024-04-22 | 2024-04-28 |  | 2024-07-22 | 2024-11-25 | 127 |  | 2024-04-22 | 2024-04-28 |  | 2024-07-17 | 2024-07-17 | 1 |  |  |  | 2024-04-16 | 2024-04-30 |  | 2024-09-11 | 2024-10-09 | 29 |  | 2024-03-14 | 2024-03-20 |  | 2024-02-23 | 2024-03-04 | 11 |  | 2024-03-14 | 2024-03-20 |  | 2024-04-11 | 2024-04-19 | 9 |  | Swastik | 2024-04-30 | 2024-05-06 |  | 2024-04-11 | 2024-04-19 | 9 |  | 2024-05-25 | 2024-05-30 |  | 2024-08-02 | 2024-08-16 | 15 |  | 2024-05-19 | 2024-05-25 |  | 2024-10-06 | 2024-10-20 | 15 |  | 2024-06-01 | 2024-06-09 |  | 2024-08-22 | 2024-09-29 | 39 |  | 2024-06-10 | 2024-06-12 |  | 2024-10-03 | 2024-10-10 | 8 |  | 2024-05-31 | 2024-06-02 |  | 2024-10-24 | 2024-10-24 | 1 |  | 2024-05-19 | 2024-05-25 |  | 2024-05-16 | 2024-05-22 | 7 |  | 2024-05-03 | 2024-05-18 |  | 2024-09-30 | 2024-10-28 | 29 |  | 2024-06-02 | 2024-06-05 |  | 2024-11-06 | 2024-11-18 | 13 | Balance Civil works in progress (Fencing, Hand rail, Final layer Back filling) | 2024-06-12 | 2024-06-13 |  | 2024-11-18 | 2024-11-25 | 8 |  |  | 2024-06-01
MECC | 4 | PSS-9 | ARE48L | WTG 438 | Precast | F2 | Bauer | Done | 546576 | 2659695 | 2023-12-10 | 2024-01-24 |  | 2023-12-10 | 2024-01-24 |  | 199 | 199 | 2024-02-19 | 2024-02-28 |  | 2024-03-29 | 2024-04-06 | 9 | [8 empty] | 2024-03-25 | 2024-03-25 |  | 2024-05-07 | 2024-05-11 | 5 |  | 2024-03-26 | 2024-03-26 |  | 2024-05-12 | 2024-05-13 | 2 |  | 2024-03-27 | 2024-03-27 |  | 2024-05-14 | 2024-05-14 | 1 |  | 2024-03-28 | 2024-03-29 |  | 2024-05-18 | 2024-05-19 | 2 |  | 2024-03-31 | 2024-04-07 |  | 2024-05-20 | 2024-06-10 | 22 |  | 2024-04-10 | 2024-04-11 |  | 2024-06-10 | 2024-06-11 | 2 | 36 |  | 2024-04-13 | 2024-04-19 |  | 2024-06-23 | 2024-11-15 | 146 |  | 2024-04-13 | 2024-04-19 |  | 2024-06-27 | 2024-06-27 | 1 |  |  |  | 2024-04-07 | 2024-04-21 |  | 2024-08-13 | 2024-09-05 | 24 |  | 2024-03-06 | 2024-03-12 |  | 2024-03-06 | 2024-03-15 | 10 |  | 2024-03-06 | 2024-03-12 |  | 2024-05-08 | 2024-05-20 | 13 |  | GP | 2024-04-19 | 2024-04-25 |  | 2024-05-08 | 2024-05-20 | 13 |  | 2024-05-14 | 2024-05-19 |  | 2024-07-04 | 2024-07-28 | 25 |  | 2024-05-02 | 2024-05-08 |  | 2024-09-06 | 2024-09-30 | 25 |  | 2024-05-21 | 2024-05-29 |  | 2024-07-29 | 2024-08-09 | 12 |  | 2024-05-30 | 2024-06-01 |  | 2024-08-10 | 2024-08-16 | 7 |  | 2024-05-14 | 2024-05-16 |  | 2024-10-15 | 2024-10-25 | 11 | Delay due to internal panel issue | 2024-05-02 | 2024-05-08 |  | 2024-05-02 | 2024-05-08 | 7 |  | 2024-05-03 | 2024-05-18 |  | 2024-09-30 | 2024-10-28 | 29 |  | 2024-05-16 | 2024-05-19 |  | 2024-10-25 | 2024-11-18 | 25 | Balance Civil works in progress (Fencing, Hand rail, Final layer Back filling) | 2024-06-01 | 2024-06-02 |  | 2024-11-18 | 2024-11-22 | 5 |  |  | 2024-06-01
MSC | 5 | PSS-9 | ARE48L | WTG 388 | Precast | F1 | Sarita infra | Done | 544899 | 2660264 | 2023-12-15 | 2024-01-25 |  | 2023-12-15 | 2024-01-25 |  | 199 | 199 | 2024-02-20 | 2024-02-29 |  | 2024-03-06 | 2024-03-20 | 15 | [8 empty] | 2024-03-26 | 2024-03-26 |  | 2024-04-30 | 2024-05-02 | 3 |  | 2024-03-27 | 2024-03-27 |  | 2024-05-03 | 2024-05-05 | 3 |  | 2024-03-28 | 2024-03-28 |  | 2024-05-08 | 2024-05-08 | 1 |  | 2024-03-29 | 2024-03-30 |  | 2024-05-17 | 2024-05-19 | 3 |  | 2024-04-01 | 2024-04-08 |  | 2024-05-20 | 2024-06-04 | 16 |  | 2024-04-11 | 2024-04-12 |  | 2024-06-26 | 2024-06-27 | 2 | 59 |  | 2024-04-14 | 2024-04-20 |  | 2024-07-04 | 2024-11-21 | 141 |  | 2024-04-14 | 2024-04-20 |  | 2024-07-06 | 2024-07-06 | 1 |  |  |  | 2024-04-08 | 2024-04-22 |  | 2024-10-01 | 2024-10-18 | 18 |  | 2024-03-06 | 2024-03-12 |  | 2024-02-23 | 2024-03-02 | 9 |  | 2024-03-06 | 2024-03-12 |  | 2024-05-07 | 2024-05-15 | 9 |  | Swastik | 2024-04-20 | 2024-04-26 |  | 2024-05-07 | 2024-05-15 | 9 |  | 2024-05-14 | 2024-05-19 |  | 2024-08-17 | 2024-09-11 | 26 |  | 2024-05-03 | 2024-05-09 |  | 2024-10-13 | 2024-10-27 | 15 |  | 2024-05-21 | 2024-05-29 |  | 2024-09-14 | 2024-10-27 | 44 |  | 2024-05-30 | 2024-06-01 |  | 2024-10-28 | 2024-10-31 | 4 |  | 2024-05-15 | 2024-05-17 |  | 2024-11-08 | 2024-11-09 | 2 |  | 2024-05-03 | 2024-05-09 |  | 2024-04-27 | 2024-05-10 | 14 |  | 2024-05-03 | 2024-05-18 |  | 2024-09-30 | 2024-10-28 | 29 |  | 2024-05-17 | 2024-05-20 |  | 2024-11-12 | 2024-11-18 | 7 |  | 2024-06-01 | 2024-06-02 |  | 2024-11-18 | 2024-11-24 | 7 |  |  | 2024-06-01
MSC | 6 | PSS-9 | ARE48L | WTG 440 | Precast | F4 | Sarita infra | Done | 546957 | 2657722 | 2023-12-09 | 2024-01-11 |  | 2023-12-09 | 2024-01-11 |  | 199 | 199 | 2024-03-03 | 2024-03-12 |  | 2024-03-23 | 2024-04-16 | 25 | [8 empty] | 2024-04-02 | 2024-04-02 |  | 2024-05-22 | 2024-05-26 | 5 |  | 2024-04-03 | 2024-04-03 |  | 2024-06-02 | 2024-06-09 | 8 |  | 2024-04-04 | 2024-04-04 |  | 2024-06-13 | 2024-06-13 | 1 |  | 2024-04-05 | 2024-04-06 |  | 2024-06-20 | 2024-06-22 | 3 |  | 2024-04-08 | 2024-04-15 |  | 2024-06-24 | 2024-07-07 | 14 |  | 2024-04-18 | 2024-04-19 |  | 2024-07-08 | 2024-07-11 | 4 | 51 |  | 2024-04-21 | 2024-04-27 |  | 2024-07-31 | 2024-11-19 | 112 |  | 2024-04-21 | 2024-04-27 |  | 2024-08-02 | 2024-08-02 | 1 |  |  |  | 2024-04-15 | 2024-04-29 |  | 2024-09-16 | 2024-10-11 | 26 |  | 2024-03-14 | 2024-03-20 |  | Completed | Completed | #VALUE! |  | 2024-03-14 | 2024-03-20 |  | 2024-05-08 | 2024-05-28 | 21 |  | Vaibhav | 2024-04-29 | 2024-05-05 |  | 2024-05-08 | 2024-05-28 | 21 |  | 2024-05-27 | 2024-06-01 |  | 2024-08-16 | 2024-09-08 | 24 |  | 2024-05-18 | 2024-05-24 |  | 2024-10-06 | 2024-10-28 | 23 | ` | 2024-06-03 | 2024-06-11 |  | 2024-09-12 | 2024-09-26 | 15 |  | 2024-06-12 | 2024-06-14 |  | 2024-09-27 | 2024-09-30 | 4 |  | 2024-05-30 | 2024-06-01 |  | 2024-10-24 | 2024-10-24 | 1 |  | 2024-05-18 | 2024-05-24 |  | 2024-05-18 | 2024-05-24 | 7 |  | 2024-06-05 | 2024-06-20 |  | 2024-09-30 | 2024-10-28 | 29 |  | 2024-06-01 | 2024-06-04 |  | 2024-11-06 | 2024-11-18 | 13 | Balance Civil works in progress (Fencing, Hand rail, Final layer Back filling) | 2024-06-20 | 2024-06-21 |  | 2024-11-18 | 2024-11-24 | 7 |  |  | 2024-06-01
MSC | 7 | PSS-9 | ARE48L | WTG 415 | FDN | F4 | Bauer | Done | 546122 | 2657987 | 2023-12-17 | 2024-01-24 |  | 2023-12-17 | 2024-01-24 |  | 211 | 199 | 2024-03-23 | 2024-04-01 |  | 2024-03-15 | 2024-03-30 | 16 | [8 empty] | 2024-04-12 | 2024-04-12 |  | 2024-07-01 | 2024-07-04 | 4 |  | 2024-04-13 | 2024-04-13 |  | 2024-07-05 | 2024-07-05 | 1 |  | 2024-04-14 | 2024-04-14 |  | 2024-11-17 | 2024-11-17 | 1 |  | 2024-04-15 | 2024-04-16 |  | 2024-11-19 | 2024-11-20 | 2 |  | 2024-04-18 | 2024-04-25 |  | 2024-11-21 | 2024-11-30 | 10 |  | 2024-04-28 | 2024-04-29 |  | 2024-11-30 | 2024-11-30 | 1 | 153 |  | 2024-05-01 | 2024-05-07 |  | 2024-12-04 | 2025-02-08 | 67 |  | 2024-05-01 | 2024-05-07 |  | 2024-12-03 | 2024-12-03 | 1 |  |  |  | 2024-04-25 | 2024-05-09 |  | 2024-11-25 | 2024-12-04 | 10 |  | 2024-03-30 | 2024-04-05 |  | Completed | Completed | #VALUE! |  | 2024-03-30 | 2024-04-05 |  | 2024-04-26 | 2024-05-04 | 9 |  | Vaibhav | 2024-05-13 | 2024-05-19 |  | 2024-04-26 | 2024-05-04 | 9 |  | 2024-06-10 | 2024-06-15 |  | 2024-12-17 | 2024-12-27 | 11 |  | 2024-06-03 | 2024-06-09 |  | 2024-12-18 | 2024-12-28 | 11 |  | 2024-06-17 | 2024-06-25 |  | 2024-12-29 | 2024-12-31 | 3 |  | 2024-06-26 | 2024-06-28 |  | 2024-12-30 | 2024-12-31 | 2 |  | 2024-06-15 | 2024-06-17 |  | 2024-12-29 | 2024-12-29 | 1 |  | 2024-06-03 | 2024-06-09 |  | 2024-06-03 | 2024-06-09 | 7 |  | 2024-06-05 | 2024-06-20 |  | 2024-11-14 | 2024-12-05 | 22 |  | 2024-06-17 | 2024-06-20 |  | 2024-12-30 | 2024-12-31 | 2 |  | 2024-06-28 | 2024-06-29 |  | 2025-01-01 | 2025-01-01 | 1 |  |  | 2024-06-01
MSC | 8 | PSS-9 | ARE48L | WTG 365 | FDN | F5 | Sarita infra | Done | 544636 | 2657570 | 2023-12-22 | 2024-01-25 |  | 2023-12-22 | 2024-01-25 |  | 199 | 199 | 2024-02-08 | 2024-02-17 |  | 2024-03-23 | 2024-04-10 | 19 | [8 empty] | 2024-03-19 | 2024-03-19 |  | 2024-04-13 | 2024-04-18 | 6 |  | 2024-03-20 | 2024-03-20 |  | 2024-04-19 | 2024-04-19 | 1 |  | 2024-03-21 | 2024-03-21 |  | 2024-04-21 | 2024-04-21 | 1 |  | 2024-03-22 | 2024-03-23 |  | 2024-04-24 | 2024-04-25 | 2 |  | 2024-03-25 | 2024-04-01 |  | 2024-04-26 | 2024-05-06 | 11 |  | 2024-04-04 | 2024-04-05 |  | 2024-05-08 | 2024-05-09 | 2 | 27 |  | 2024-04-07 | 2024-04-12 |  | 2024-05-27 | 2024-12-10 | 198 |  | 2024-04-13 | 2024-04-13 |  | 2024-06-23 | 2024-06-23 | 1 |  |  |  | 2024-04-01 | 2024-04-15 |  | 2024-08-14 | 2024-11-30 | 109 |  | 2024-02-27 | 2024-03-04 |  | 2024-02-20 | 2024-03-18 | 28 |  | 2024-02-27 | 2024-03-04 |  | 2024-05-02 | 2024-06-28 | 58 |  | Radhe Radhe | 2024-04-11 | 2024-04-17 |  | 2024-05-02 | 2024-06-28 | 58 |  | 2024-05-05 | 2024-05-10 |  | 2024-07-24 | 2024-08-13 | 21 |  | 2024-04-23 | 2024-04-29 |  | 2024-11-30 | 2024-12-03 | 4 |  | 2024-05-12 | 2024-05-20 |  | 2024-08-22 | 2024-09-17 | 27 |  | 2024-05-21 | 2024-05-23 |  | 2024-09-18 | 2024-10-02 | 15 |  | 2024-05-05 | 2024-05-07 |  | 2024-12-04 | 2024-12-04 | 1 |  | 2024-04-23 | 2024-04-29 |  | 2024-04-23 | 2024-04-29 | 7 |  | 2024-04-14 | 2024-04-29 |  | 2024-09-30 | 2024-10-28 | 29 |  | 2024-05-07 | 2024-05-10 |  | 2024-12-06 | 2024-12-09 | 4 |  | 2024-05-23 | 2024-05-24 |  | 2024-12-15 | 2024-12-17 | 3 |  |  | 2024-06-01
MSC | 9 | PSS-9 | ARE48L | WTG 342 | FDN | F5 | Sarita infra | Done | 543984 | 2656888 | 2024-01-23 | 2024-02-17 |  | 2024-01-23 | 2024-02-17 |  | 253 | 253 | 2024-04-05 | 2024-04-14 |  | 2024-07-03 | 2024-09-14 | 74 | [8 empty] | 2024-04-20 | 2024-04-20 |  | 2024-09-17 | 2024-09-21 | 5 |  | 2024-04-21 | 2024-04-21 |  | 2024-09-23 | 2024-09-24 | 2 |  | 2024-04-22 | 2024-04-22 |  | 2024-09-25 | 2024-09-25 | 1 |  | 2024-04-23 | 2024-04-24 |  | 2024-09-27 | 2024-09-27 | 1 |  | 2024-04-26 | 2024-05-03 |  | 2024-09-29 | 2024-10-06 | 8 |  | 2024-05-07 | 2024-05-08 |  | 2024-10-08 | 2024-10-09 | 2 | 23 |  | 2024-05-10 | 2024-05-16 |  | 2024-10-15 | 2024-12-14 | 61 |  | 2024-05-10 | 2024-05-16 |  | 2024-10-23 | 2024-10-23 | 1 |  |  |  | 2024-05-03 | 2024-05-17 |  | 2024-11-16 | 2024-11-24 | 9 |  | 2024-04-07 | 2024-04-13 |  | 2024-03-07 | 2024-03-23 | 17 |  | 2024-04-07 | 2024-04-13 |  | 2024-05-14 | 2024-06-17 | 35 |  | Kesav | 2024-05-29 | 2024-06-04 |  | 2024-05-14 | 2024-06-17 | 35 |  | 2024-06-23 | 2024-06-28 |  | 2024-10-26 | 2024-11-06 | 12 |  | 2024-06-19 | 2024-06-25 |  | 2024-11-27 | 2024-12-02 | 6 |  | 2024-06-30 | 2024-07-08 |  | 2024-11-18 | 2024-11-26 | 9 |  | 2024-07-09 | 2024-07-11 |  | 2024-11-27 | 2024-11-30 | 4 |  | 2024-07-01 | 2024-07-03 |  | 2024-12-08 | 2024-12-08 | 1 |  | 2024-06-19 | 2024-06-25 |  | 2024-06-16 | 2024-06-22 | 7 |  | 2024-06-05 | 2024-06-20 |  | 2024-11-14 | 2024-12-05 | 22 |  | 2024-07-03 | 2024-07-06 |  | 2024-12-11 | 2024-12-15 | 5 |  | 2024-07-11 | 2024-07-12 |  | 2024-12-19 | 2024-12-20 | 2 |  |  | 2024-06-01
HBG | 10 | PSS-9 | ARE48L | WTG 414 | Precast | F2 | Bauer | Done | 545932 | 2658973 | 2023-12-11 | 2024-01-24 |  | 2023-12-11 | 2024-01-24 |  | 245 | 239 | 2024-03-15 | 2024-03-24 |  | 2024-03-12 | 2024-03-19 | 8 |  | Yes | 2024-04-29 | 2024-05-05 |  | 2024-05-27 | 2024-06-10 |  | 2024-04-09 | 2024-04-09 |  | 2024-10-17 | 2024-10-23 | 7 |  | 2024-04-10 | 2024-04-10 |  | 2024-10-25 | 2024-10-26 | 2 |  | 2024-04-11 | 2024-04-11 |  | 2024-10-28 | 2024-10-28 | 1 |  | 2024-04-12 | 2024-04-13 |  | 2024-10-29 | 2024-10-31 | 3 |  | 2024-04-15 | 2024-04-22 |  | 2024-11-04 | 2024-11-16 | 13 |  | 2024-04-25 | 2024-04-26 |  | 2024-11-17 | 2024-11-18 | 2 | 33 |  | 2024-04-28 | 2024-05-04 |  | 2024-11-23 | 2024-12-25 | 33 |  | 2024-04-28 | 2024-05-04 |  | 2024-11-25 | 2024-11-25 | 1 |  |  |  | 2024-04-22 | 2024-05-06 |  | 2024-09-24 | 2024-10-21 | 28 |  | 2024-03-22 | 2024-03-28 |  | 2024-02-23 | 2024-03-06 | 13 |  | 2024-03-22 | 2024-03-28 |  | 2024-05-10 | 2024-05-23 | 14 |  | GP | 2024-05-08 | 2024-05-14 |  | 2024-05-10 | 2024-05-23 | 14 |  | 2024-06-03 | 2024-06-08 |  | 2024-12-05 | 2024-12-15 | 11 |  | 2024-06-02 | 2024-06-08 |  | 2024-12-03 | 2024-12-20 | 18 |  | 2024-06-10 | 2024-06-18 |  | 2024-12-17 | 2024-12-27 | 11 |  | 2024-06-19 | 2024-06-21 |  | 2024-12-25 | 2024-12-27 | 3 |  | 2024-06-14 | 2024-06-16 |  | 2024-12-21 | 2024-12-21 | 1 |  | 2024-06-02 | 2024-06-08 |  | 2024-06-02 | 2024-06-22 | 21 |  | 2024-06-05 | 2024-06-20 |  | 2024-11-14 | 2024-12-05 | 22 |  | 2024-06-16 | 2024-06-19 |  | 2024-12-20 | 2024-12-24 | 5 |  | 2024-06-21 | 2024-06-22 |  | 2024-12-25 | 2024-12-26 | 2 |  |  | 2024-06-01
HBG | 11 | PSS-9 | ARE48L | WTG 317 | Precast | F5 | Bauer | Done | 543150 | 2657152 | 2024-01-22 | 2024-02-03 |  | 2024-01-22 | 2024-02-03 |  | 253 | 253 | 2024-04-03 | 2024-04-12 |  | 2024-06-10 | 2024-07-22 | 43 | [8 empty] | 2024-04-18 | 2024-04-18 |  | 2024-07-27 | 2024-07-31 | 5 |  | 2024-04-19 | 2024-04-19 |  | 2024-07-31 | 2024-08-02 | 3 |  | 2024-04-20 | 2024-04-20 |  | 2024-08-02 | 2024-08-02 | 1 |  | 2024-04-21 | 2024-04-22 |  | 2024-08-05 | 2024-08-05 | 1 |  | 2024-04-24 | 2024-05-01 |  | 2024-08-07 | 2024-08-20 | 14 |  | 2024-05-04 | 2024-05-05 |  | 2024-08-21 | 2024-08-22 | 2 | 27 |  | 2024-05-07 | 2024-05-13 |  | 2024-10-01 | 2024-12-07 | 68 |  | 2024-05-07 | 2024-05-13 |  | 2024-09-17 | 2024-09-17 | 1 |  |  |  | 2024-05-01 | 2024-05-15 |  | 2024-10-25 | 2024-11-12 | 19 |  | 2024-03-30 | 2024-04-05 |  | 2024-02-28 | 2024-04-05 | 38 |  | 2024-03-30 | 2024-04-05 |  | 2024-05-16 | 2024-06-28 | 44 |  | Kesav | 2024-05-22 | 2024-05-28 |  | 2024-05-16 | 2024-06-28 | 44 |  | 2024-06-19 | 2024-06-24 |  | 2024-10-04 | 2024-10-14 | 11 |  | 2024-06-12 | 2024-06-18 |  | 2024-11-14 | 2024-11-28 | 15 |  | 2024-06-26 | 2024-07-04 |  | 2024-10-15 | 2024-11-12 | 29 |  | 2024-07-05 | 2024-07-07 |  | 2024-11-14 | 2024-11-17 | 4 |  | 2024-06-24 | 2024-06-26 |  | 2024-11-28 | 2024-12-01 | 4 |  | 2024-06-12 | 2024-06-18 |  | 2024-06-09 | 2024-06-15 | 7 |  | 2024-06-05 | 2024-06-20 |  | 2024-11-14 | 2024-12-05 | 22 |  | 2024-06-26 | 2024-06-29 |  | 2024-11-29 | 2024-12-05 | 7 |  | 2024-07-07 | 2024-07-08 |  | 2024-12-15 | 2024-12-17 | 3 |  |  | 2024-06-01
MECC | 12 | PSS-9 | ARE48L | WTG 439 | Precast | F2 | Bauer | Done | 546766 | 2658709 | 2023-12-11 | 2024-01-24 |  | 2023-12-11 | 2024-01-24 |  | 253 | 253 | 2024-03-14 | 2024-03-23 |  | 2024-03-06 | 2024-03-15 | 10 |  | Yes | 2024-04-08 | 2024-04-14 |  | 2024-04-11 | 2024-04-19 |  | 2024-04-08 | 2024-04-08 |  | 2024-05-24 | 2024-05-27 | 4 |  | 2024-04-09 | 2024-04-09 |  | 2024-05-28 | 2024-05-29 | 2 |  | 2024-04-10 | 2024-04-10 |  | 2024-05-29 | 2024-05-29 | 1 |  | 2024-04-11 | 2024-04-12 |  | 2024-06-15 | 2024-06-16 | 2 |  | 2024-04-14 | 2024-04-21 |  | 2024-06-17 | 2024-07-04 | 18 |  | 2024-04-24 | 2024-04-25 |  | 2024-07-06 | 2024-07-07 | 2 | 45 |  | 2024-04-27 | 2024-05-03 |  | 2024-08-13 | 2024-11-15 | 95 |  | 2024-04-27 | 2024-05-03 |  | 2024-08-05 | 2024-08-05 | 1 |  |  |  | 2024-04-21 | 2024-05-05 |  | 2024-09-24 | 2024-10-11 | 18 |  | 2024-03-22 | 2024-03-28 |  | 2024-02-20 | 2024-03-24 | 34 |  | 2024-03-22 | 2024-03-28 |  | 2024-05-07 | 2024-05-15 | 9 |  | Radhe Radhe | 2024-05-07 | 2024-05-13 |  | 2024-05-07 | 2024-05-15 | 9 |  | 2024-06-05 | 2024-06-10 |  | 2024-08-21 | 2024-09-15 | 26 |  | 2024-05-27 | 2024-06-02 |  | 2024-10-08 | 2024-10-25 | 18 |  | 2024-06-12 | 2024-06-20 |  | 2024-09-18 | 2024-09-28 | 11 |  | 2024-06-21 | 2024-06-23 |  | 2024-09-29 | 2024-10-16 | 18 |  | 2024-06-08 | 2024-06-10 |  | 2024-10-30 | 2024-10-30 | 1 |  | 2024-05-27 | 2024-06-02 |  | 2024-05-24 | 2024-05-30 | 7 |  | 2024-06-05 | 2024-06-20 |  | 2024-09-30 | 2024-10-28 | 29 |  | 2024-06-10 | 2024-06-13 |  | 2024-11-12 | 2024-11-18 | 7 |  | 2024-06-23 | 2024-06-24 |  | 2024-11-18 | 2024-11-21 | 4 |  |  | 2024-06-01
MSC | 13 | PSS-9 | ARE48L | WTG 364 | Precast | F5 | Sarita infra | Done | 544446 | 2658556 | 2023-12-23 | 2024-01-25 |  | 2023-12-23 | 2024-01-25 |  | 221 | 211 | 2024-03-12 | 2024-03-21 |  | 2024-02-24 | 2024-03-21 | 27 | [8 empty] | 2024-04-06 | 2024-04-06 |  | 2024-06-02 | 2024-06-27 | 26 |  | 2024-04-07 | 2024-04-07 |  | 2024-06-29 | 2024-07-01 | 3 |  | 2024-04-08 | 2024-04-08 |  | 2024-08-24 | 2024-08-24 | 1 |  | 2024-04-09 | 2024-04-10 |  | 2024-08-25 | 2024-08-25 | 1 |  | 2024-04-12 | 2024-04-19 |  | 2024-09-19 | 2024-09-25 | 7 |  | 2024-04-22 | 2024-04-23 |  | 2024-09-26 | 2024-09-27 | 2 | 118 |  | 2024-04-25 | 2024-05-01 |  | 2024-10-03 | 2024-12-07 | 66 |  | 2024-04-25 | 2024-05-01 |  | 2024-10-04 | 2024-10-04 | 1 |  |  |  | 2024-04-19 | 2024-05-03 |  | 2024-11-04 | 2024-11-19 | 16 |  | 2024-03-22 | 2024-03-28 |  | Completed | Completed | #VALUE! |  | 2024-03-22 | 2024-03-28 |  | 2024-04-23 | 2024-05-01 | 9 |  | Vaibhav | 2024-05-05 | 2024-05-11 |  | 2024-04-23 | 2024-05-01 | 9 |  | 2024-06-01 | 2024-06-06 |  | 2024-10-09 | 2024-10-23 | 15 |  | 2024-05-25 | 2024-05-31 |  | 2024-11-20 | 2024-11-26 | 7 |  | 2024-06-08 | 2024-06-16 |  | 2024-10-28 | 2024-11-14 | 18 |  | 2024-06-17 | 2024-06-19 |  | 2024-11-28 | 2024-12-01 | 4 |  | 2024-06-06 | 2024-06-08 |  | 2024-11-28 | 2024-11-28 | 1 |  | 2024-05-25 | 2024-05-31 |  | 2024-05-25 | 2024-05-31 | 7 |  | 2024-06-05 | 2024-06-20 |  | 2024-11-14 | 2024-12-05 | 22 |  | 2024-06-08 | 2024-06-11 |  | 2024-11-29 | 2024-12-05 | 7 |  | 2024-06-20 | 2024-06-21 |  | 2024-12-15 | 2024-12-16 | 2 |  |  | 2024-06-01
MSC | 14 | PSS-9 | ARE48L | WTG 341 | Precast | F5 | Bauer | Done | 543794 | 2657874 | 2024-01-27 | 2024-02-03 |  | 2024-01-27 | 2024-02-03 |  | 243 | 243 | 2024-03-02 | 2024-03-11 |  | 2024-04-08 | 2024-04-19 | 12 | [8 empty] | 2024-04-01 | 2024-04-01 |  | 2024-05-17 | 2024-05-30 | 14 |  | 2024-04-02 | 2024-04-02 |  | 2024-05-31 | 2024-06-02 | 3 |  | 2024-04-03 | 2024-04-03 |  | 2024-06-03 | 2024-06-03 | 1 |  | 2024-04-04 | 2024-04-05 |  | 2024-06-11 | 2024-06-16 | 6 |  | 2024-04-07 | 2024-04-14 |  | 2024-06-17 | 2024-06-27 | 11 |  | 2024-04-17 | 2024-04-18 |  | 2024-06-30 | 2024-06-30 | 1 | 45 |  | 2024-04-20 | 2024-04-26 |  | 2024-07-31 | 2024-10-22 | 84 |  | 2024-04-20 | 2024-04-26 |  | 2024-08-03 | 2024-08-03 | 1 |  |  |  | 2024-04-14 | 2024-04-28 |  | 2024-09-24 | 2024-10-19 | 26 |  | 2024-03-14 | 2024-03-20 |  | 2024-02-28 | 2024-03-18 | 20 |  | 2024-03-14 | 2024-03-20 |  | 2024-05-09 | 2024-06-02 | 25 |  | Swastik | 2024-04-28 | 2024-05-04 |  | 2024-05-09 | 2024-06-02 | 25 |  | 2024-05-26 | 2024-05-31 |  | 2024-08-18 | 2024-09-15 | 29 |  | 2024-05-17 | 2024-05-23 |  | 2024-10-22 | 2024-10-28 | 7 |  | 2024-06-02 | 2024-06-10 |  | 2024-09-18 | 2024-09-26 | 9 |  | 2024-06-11 | 2024-06-13 |  | 2024-09-27 | 2024-09-30 | 4 |  | 2024-05-29 | 2024-05-31 |  | 2024-11-07 | 2024-11-07 | 1 |  | 2024-05-17 | 2024-05-23 |  | 2024-05-17 | 2024-05-27 | 11 |  | 2024-05-03 | 2024-05-18 |  | 2024-09-30 | 2024-10-28 | 29 |  | 2024-05-31 | 2024-06-03 |  | 2024-11-12 | 2024-11-18 | 7 |  | 2024-06-13 | 2024-06-14 |  | 2024-11-18 | 2024-11-23 | 6 |  |  | 2024-06-01
HBG | 15 | PSS-9 | ARE48L | WTG 339 | Precast | F1 | Sarita infra | Done | 543413 | 2659846 | 2023-12-19 | 2024-02-03 |  | 2023-12-19 | 2024-02-03 |  | 253 | 253 | 2024-03-26 | 2024-04-04 |  | 2024-05-23 | 2024-06-27 | 36 |  | Yes | 2024-06-05 | 2024-06-17 |  | 2024-06-07 | 2024-06-28 |  | 2024-04-15 | 2024-04-15 |  | 2024-07-08 | 2024-07-16 | 9 |  | 2024-04-16 | 2024-04-16 |  | 2024-07-17 | 2024-07-17 | 1 |  | 2024-04-17 | 2024-04-17 |  | 2024-07-18 | 2024-07-18 | 1 |  | 2024-04-18 | 2024-04-19 |  | 2024-07-22 | 2024-07-24 | 3 |  | 2024-04-21 | 2024-04-28 |  | 2024-07-25 | 2024-08-06 | 13 |  | 2024-05-01 | 2024-05-02 |  | 2024-08-12 | 2024-08-13 | 2 | 37 |  | 2024-05-04 | 2024-05-10 |  | 2024-08-24 | 2024-11-23 | 92 |  | 2024-05-04 | 2024-05-10 |  | 2024-09-13 | 2024-09-13 | 1 |  |  |  | 2024-04-28 | 2024-05-12 |  | 2024-09-19 | 2024-10-15 | 27 |  | 2024-03-30 | 2024-04-05 |  | 2024-03-02 | 2024-03-06 | 5 |  | 2024-03-30 | 2024-04-05 |  | 2024-04-10 | 2024-04-18 | 9 |  | Swastik | 2024-05-21 | 2024-05-27 |  | 2024-04-10 | 2024-04-18 | 9 |  | 2024-06-12 | 2024-06-17 |  | 2024-09-27 | 2024-10-06 | 10 |  | 2024-06-11 | 2024-06-17 |  | 2024-10-28 | 2024-11-03 | 7 |  | 2024-06-19 | 2024-06-27 |  | 2024-10-10 | 2024-11-08 | 30 |  | 2024-06-28 | 2024-06-30 |  | 2024-11-09 | 2024-11-14 | 6 |  | 2024-06-23 | 2024-06-25 |  | 2024-11-07 | 2024-11-07 | 1 |  | 2024-06-11 | 2024-06-17 |  | 2024-06-11 | 2024-06-17 | 7 |  | 2024-06-05 | 2024-06-20 |  | 2024-11-14 | 2024-12-05 | 22 |  | 2024-06-25 | 2024-06-28 |  | 2024-11-12 | 2024-11-18 | 7 |  | 2024-06-30 | 2024-07-01 |  | 2024-12-15 | 2024-12-18 | 4 |  |  | 2024-06-01
MSC | 16 | PSS-9 | ARE48L | WTG 391 | FDN | F4 | Bauer | Done | 545471 | 2657305 | 2023-12-15 | 2024-01-25 |  | 2023-12-15 | 2024-01-25 |  | 223 | 223 | 2024-02-09 | 2024-02-18 |  | 2024-03-21 | 2024-04-01 | 12 | [8 empty] | 2024-03-20 | 2024-03-20 |  | 2024-04-22 | 2024-04-25 | 4 |  | 2024-03-21 | 2024-03-21 |  | 2024-04-27 | 2024-04-28 | 2 |  | 2024-03-22 | 2024-03-22 |  | 2024-04-30 | 2024-04-30 | 1 |  | 2024-03-23 | 2024-03-24 |  | 2024-05-05 | 2024-05-07 | 3 |  | 2024-03-26 | 2024-04-02 |  | 2024-05-07 | 2024-05-21 | 15 |  | 2024-04-05 | 2024-04-06 |  | 2024-05-22 | 2024-05-23 | 2 | 32 |  | 2024-04-08 | 2024-04-14 |  | 2024-06-20 | 2024-12-13 | 177 |  | 2024-04-08 | 2024-04-14 |  | 2024-06-24 | 2024-06-24 | 1 |  |  |  | 2024-04-02 | 2024-04-16 |  | 2024-11-21 | 2024-11-27 | 7 |  | 2024-02-27 | 2024-03-04 |  | 2024-02-20 | 2024-03-18 | 28 |  | 2024-02-27 | 2024-03-04 |  | 2024-06-07 | 2024-06-28 | 22 |  | Radhe Radhe | 2024-04-12 | 2024-04-18 |  | 2024-06-07 | 2024-06-28 | 22 |  | 2024-05-05 | 2024-05-10 |  | 2024-07-08 | 2024-07-30 | 23 |  | 2024-04-24 | 2024-04-30 |  | 2024-11-29 | 2024-12-02 | 4 |  | 2024-05-12 | 2024-05-20 |  | 2024-08-04 | 2024-09-12 | 40 |  | 2024-05-21 | 2024-05-23 |  | 2024-09-13 | 2024-11-29 | 78 | hold due to shortage of material. | 2024-05-06 | 2024-05-08 |  | 2024-12-04 | 2024-12-04 | 1 |  | 2024-04-24 | 2024-04-30 |  | 2024-04-24 | 2024-04-30 | 7 |  | 2024-04-15 | 2024-04-30 |  | 2024-09-30 | 2024-10-28 | 29 |  | 2024-05-08 | 2024-05-11 |  | 2024-12-06 | 2024-12-09 | 4 |  | 2024-05-23 | 2024-05-24 |  | 2024-12-15 | 2024-12-18 | 4 |  |  | 2024-06-01
HBG | 17 | PSS-9 | ARE48L | WTG 340 | Precast | F1 | Bauer | Done | 543604 | 2658860 | 2024-01-24 | 2024-02-10 |  | 2024-01-24 | 2024-02-10 |  | 253 | 253 | 2024-04-04 | 2024-04-13 |  | 2024-05-30 | 2024-07-31 | 63 | [8 empty] | 2024-04-19 | 2024-04-19 |  | 2024-08-04 | 2024-08-10 | 7 |  | 2024-04-20 | 2024-04-20 |  | 2024-08-13 | 2024-08-14 | 2 |  | 2024-04-21 | 2024-04-21 |  | 2024-08-16 | 2024-08-16 | 1 |  | 2024-04-22 | 2024-04-23 |  | 2024-08-20 | 2024-08-21 | 2 |  | 2024-04-25 | 2024-05-02 |  | 2024-08-23 | 2024-09-27 | 36 | Delay due to rains | 2024-05-05 | 2024-05-06 |  | 2024-09-29 | 2024-09-30 | 2 | 58 |  | 2024-05-08 | 2024-05-14 |  | 2024-10-10 | 2024-12-06 | 58 |  | 2024-05-08 | 2024-05-14 |  | 2024-10-10 | 2024-10-10 | 1 |  |  |  | 2024-05-02 | 2024-05-16 |  | 2024-11-12 | 2024-11-22 | 11 |  | 2024-03-30 | 2024-04-05 |  | Completed | Completed | #VALUE! |  | 2024-03-30 | 2024-04-05 |  | 2024-04-30 | 2024-05-08 | 9 |  | Vaibhav | 2024-05-23 | 2024-05-29 |  | 2024-04-30 | 2024-05-08 | 9 |  | 2024-06-22 | 2024-06-27 |  | 2024-10-17 | 2024-10-26 | 10 |  | 2024-06-18 | 2024-06-24 |  | 2024-11-23 | 2024-11-26 | 4 |  | 2024-06-29 | 2024-07-07 |  | 2024-10-28 | 2024-11-25 | 29 |  | 2024-07-08 | 2024-07-10 |  | 2024-11-28 | 2024-11-30 | 3 |  | 2024-06-30 | 2024-07-02 |  | 2024-11-28 | 2024-11-28 | 1 |  | 2024-06-18 | 2024-06-24 |  | 2024-06-18 | 2024-06-28 | 11 |  | 2024-06-05 | 2024-06-20 |  | 2024-11-14 | 2024-12-05 | 22 |  | 2024-07-02 | 2024-07-05 |  | 2024-11-29 | 2024-12-05 | 7 |  | 2024-07-10 | 2024-07-11 |  | 2024-12-15 | 2024-12-17 | 3 |  |  | 2024-06-01
HBG | 18 | PSS-9 | ARE48L | WTG 390 | Precast | F4 | Bauer | Done | 545280 | 2658291 | 2023-12-15 | 2024-01-24 |  | 2023-12-15 | 2024-01-24 |  | 199 | 199 | 2024-03-25 | 2024-04-03 |  | 2024-04-02 | 2024-04-06 | 5 |  | Yes | 2024-04-15 | 2024-04-21 |  | 2024-05-22 | 2024-06-03 |  | 2024-04-14 | 2024-04-14 |  | 2024-06-28 | 2024-07-01 | 4 |  | 2024-04-15 | 2024-04-15 |  | 2024-07-05 | 2024-07-05 | 1 |  | 2024-04-16 | 2024-04-16 |  | 2024-07-07 | 2024-07-07 | 1 |  | 2024-04-17 | 2024-04-18 |  | 2024-07-12 | 2024-07-12 | 1 |  | 2024-04-20 | 2024-04-27 |  | 2024-07-12 | 2024-07-21 | 10 |  | 2024-04-30 | 2024-05-01 |  | 2024-08-08 | 2024-08-09 | 2 | 43 |  | 2024-05-03 | 2024-05-09 |  | 2024-08-16 | 2024-11-22 | 99 |  | 2024-05-03 | 2024-05-09 |  | 2024-08-23 | 2024-08-23 | 1 |  |  |  | 2024-04-27 | 2024-05-11 |  | 2024-10-08 | 2024-10-23 | 16 |  | 2024-03-30 | 2024-04-05 |  | Completed | Completed | #VALUE! |  | 2024-03-30 | 2024-04-05 |  | 2024-04-24 | 2024-05-02 | 9 |  | Vaibhav | 2024-05-15 | 2024-05-21 |  | 2024-04-24 | 2024-05-02 | 9 |  | 2024-06-14 | 2024-06-19 |  | 2024-09-11 | 2024-09-29 | 19 |  | 2024-06-10 | 2024-06-16 |  | 2024-10-27 | 2024-11-11 | 16 |  | 2024-06-21 | 2024-06-29 |  | 2024-10-03 | 2024-10-09 | 7 |  | 2024-06-30 | 2024-07-02 |  | 2024-10-10 | 2024-10-18 | 9 |  | 2024-06-22 | 2024-06-24 |  | 2024-11-11 | 2024-11-11 | 1 |  | 2024-06-10 | 2024-06-16 |  | 2024-06-10 | 2024-06-18 | 9 |  | 2024-06-05 | 2024-06-20 |  | 2024-09-30 | 2024-10-28 | 29 |  | 2024-06-24 | 2024-06-27 |  | 2024-11-12 | 2024-11-18 | 7 |  | 2024-07-02 | 2024-07-03 |  | 2024-11-18 | 2024-11-23 | 6 |  |  | 2024-06-01
MECC | 19 | PSS-9 | ARE48L | WTG 489 | Precast | F3 | Bauer | Done | 548252 | 2659126 | 2023-11-16 | 2024-01-01 |  | 2023-11-16 | 2024-01-01 |  | 223 | 223 | 2024-03-01 | 2024-03-10 |  | 2024-02-25 | 2024-03-05 | 10 | [8 empty] | 2024-03-31 | 2024-03-31 |  | 2024-05-14 | 2024-05-17 | 4 |  | 2024-04-01 | 2024-04-01 |  | 2024-05-18 | 2024-05-22 | 5 |  | 2024-04-02 | 2024-04-02 |  | 2024-05-25 | 2024-05-25 | 1 |  | 2024-04-03 | 2024-04-04 |  | 2024-05-29 | 2024-06-03 | 6 |  | 2024-04-06 | 2024-04-13 |  | 2024-06-04 | 2024-06-16 | 13 |  | 2024-04-16 | 2024-04-17 |  | 2024-06-18 | 2024-06-19 | 2 | 37 |  | 2024-04-19 | 2024-04-25 |  | 2024-07-03 | 2024-11-19 | 140 |  | 2024-04-19 | 2024-04-25 |  | 2024-07-02 | 2024-07-02 | 1 |  |  |  | 2024-04-13 | 2024-04-27 |  | 2024-08-22 | 2024-11-03 | 74 |  | 2024-03-14 | 2024-03-20 |  | 2024-02-20 | 2024-03-24 | 34 |  | 2024-03-14 | 2024-03-20 |  | 2024-05-02 | 2024-05-10 | 9 |  | Radhe Radhe | 2024-04-27 | 2024-05-03 |  | 2024-05-02 | 2024-05-10 | 9 |  | 2024-05-23 | 2024-05-28 |  | 2024-07-26 | 2024-08-14 | 20 |  | 2024-05-11 | 2024-05-17 |  | 2024-11-05 | 2024-11-16 | 12 |  | 2024-05-30 | 2024-06-07 |  | 2024-08-22 | 2024-09-12 | 22 |  | 2024-06-08 | 2024-06-10 |  | 2024-09-13 | 2024-09-19 | 7 |  | 2024-05-23 | 2024-05-25 |  | 2024-11-12 | 2024-11-12 | 1 |  | 2024-05-11 | 2024-05-17 |  | 2024-04-25 | 2024-05-07 | 13 |  | 2024-05-03 | 2024-05-18 |  | 2024-09-30 | 2024-10-28 | 29 |  | 2024-05-25 | 2024-05-28 |  | 2024-11-18 | 2024-11-22 | 5 |  | 2024-06-10 | 2024-06-11 |  | 2024-11-22 | 2024-11-24 | 3 |  |  | 2024-09-01
HBG | 20 | PSS-9 | ARE48L | WTG 463 | Precast | F3 | Sarita infra | Done | 547227 | 2660377 | 2023-12-09 | 2024-01-24 |  | 2023-12-09 | 2024-01-24 |  | 199 | 199 | 2024-02-21 | 2024-03-01 |  | 2024-02-21 | 2024-03-05 | 14 | [8 empty] | 2024-03-27 | 2024-03-27 |  | 2024-05-05 | 2024-05-18 | 14 |  | 2024-03-28 | 2024-03-28 |  | 2024-05-20 | 2024-05-22 | 3 |  | 2024-03-29 | 2024-03-29 |  | 2024-05-22 | 2024-05-22 | 1 |  | 2024-03-30 | 2024-03-31 |  | 2024-05-27 | 2024-05-29 | 3 |  | 2024-04-02 | 2024-04-09 |  | 2024-05-30 | 2024-06-14 | 16 |  | 2024-04-12 | 2024-04-13 |  | 2024-06-16 | 2024-06-16 | 1 | 43 |  | 2024-04-15 | 2024-04-21 |  | 2024-06-27 | 2024-11-19 | 146 |  | 2024-04-15 | 2024-04-21 |  | 2024-06-30 | 2024-06-30 | 1 |  |  |  | 2024-04-09 | 2024-04-23 |  | 2024-08-18 | 2024-10-26 | 70 |  | 2024-03-06 | 2024-03-12 |  | 2024-02-20 | 2024-03-04 | 14 |  | 2024-03-06 | 2024-03-12 |  | 2024-04-27 | 2024-05-05 | 9 |  | Radhe Radhe | 2024-04-21 | 2024-04-27 |  | 2024-04-27 | 2024-05-05 | 9 |  | 2024-05-15 | 2024-05-20 |  | 2024-07-25 | 2024-08-13 | 20 |  | 2024-05-09 | 2024-05-15 |  | 2024-10-30 | 2024-11-06 | 8 |  | 2024-05-22 | 2024-05-30 |  | 2024-08-16 | 2024-10-22 | 68 |  | 2024-05-31 | 2024-06-02 |  | 2024-10-23 | 2024-10-28 | 6 |  | 2024-05-21 | 2024-05-23 |  | 2024-11-10 | 2024-11-10 | 1 |  | 2024-05-09 | 2024-05-15 |  | 2024-05-06 | 2024-05-12 | 7 |  | 2024-05-03 | 2024-05-18 |  | 2024-09-30 | 2024-10-28 | 29 |  | 2024-05-23 | 2024-05-26 |  | 2024-11-12 | 2024-11-18 | 7 |  | 2024-06-02 | 2024-06-03 |  | 2024-11-18 | 2024-11-24 | 7 |  |  | 2024-09-01
MECC | 21 | PSS-9 | ARE48L | WTG 464 | Precast | F3 | Bauer | Done | 547418 | 2659391 | 2023-12-11 | 2024-01-01 |  | 2023-12-11 | 2024-01-01 |  | 211 | 211 | 2024-02-11 | 2024-02-20 |  | 2024-02-12 | 2024-02-24 | 13 |  | Yes | 2024-03-20 | 2024-03-27 |  | 2024-03-27 | 2024-03-28 |  | 2024-03-22 | 2024-03-22 |  | 2024-04-11 | 2024-04-18 | 8 |  | 2024-03-23 | 2024-03-23 |  | 2024-04-19 | 2024-04-21 | 3 |  | 2024-03-24 | 2024-03-24 |  | 2024-04-25 | 2024-04-25 | 1 |  | 2024-03-25 | 2024-03-26 |  | 2024-05-08 | 2024-05-11 | 4 |  | 2024-03-28 | 2024-04-04 |  | 2024-05-12 | 2024-05-30 | 19 |  | 2024-04-07 | 2024-04-08 |  | 2024-05-31 | 2024-06-01 | 2 | 52 |  | 2024-04-10 | 2024-04-16 |  | 2024-06-13 | 2024-11-17 | 158 |  | 2024-04-10 | 2024-04-16 |  | 2024-06-21 | 2024-06-21 | 1 |  |  |  | 2024-04-04 | 2024-04-18 |  | 2024-08-17 | 2024-10-03 | 48 |  | 2024-02-27 | 2024-03-04 |  | 2024-02-24 | 2024-03-24 | 30 |  | 2024-02-27 | 2024-03-04 |  | 2024-04-09 | 2024-04-17 | 9 |  | Radhe Radhe | 2024-04-14 | 2024-04-20 |  | 2024-04-09 | 2024-04-17 | 9 |  | 2024-05-07 | 2024-05-12 |  | 2024-07-03 | 2024-07-21 | 19 |  | 2024-05-01 | 2024-05-07 |  | 2024-09-30 | 2024-10-23 | 24 |  | 2024-05-14 | 2024-05-22 |  | 2024-07-22 | 2024-08-09 | 19 |  | 2024-05-23 | 2024-05-25 |  | 2024-08-10 | 2024-08-16 | 7 |  | 2024-05-13 | 2024-05-15 |  | 2024-10-23 | 2024-10-23 | 1 |  | 2024-05-01 | 2024-05-07 |  | 2024-05-02 | 2024-05-07 | 6 |  | 2024-05-03 | 2024-05-18 |  | 2024-09-30 | 2024-10-28 | 29 |  | 2024-05-15 | 2024-05-18 |  | 2024-10-25 | 2024-11-18 | 25 | Balance Civil works in progress (Fencing, Hand rail, Final layer Back filling) | 2024-05-25 | 2024-05-26 |  | 2024-11-18 | 2024-11-23 | 6 |  |  | 2024-09-01
HBG | 22 | PSS-9 | ARE48L | WTG 488 | Precast | F3 | Sarita infra | Done | 548062 | 2660112 | 2023-11-16 | 2024-01-01 |  | 2023-11-16 | 2024-01-01 |  | 211 | 211 | 2024-02-10 | 2024-02-19 |  | 2024-02-07 | 2024-02-17 | 11 |  | Yes | 2024-04-04 | 2024-04-07 |  | 2024-04-04 | 2024-04-06 |  | 2024-03-21 | 2024-03-21 |  | 2024-04-19 | 2024-05-01 | 13 |  | 2024-03-22 | 2024-03-22 |  | 2024-05-01 | 2024-05-02 | 2 |  | 2024-03-23 | 2024-03-23 |  | 2024-05-04 | 2024-05-05 | 2 |  | 2024-03-24 | 2024-03-25 |  | 2024-05-06 | 2024-05-07 | 2 |  | 2024-03-27 | 2024-04-03 |  | 2024-05-07 | 2024-05-25 | 19 |  | 2024-04-06 | 2024-04-07 |  | 2024-05-27 | 2024-05-27 | 1 | 39 |  | 2024-04-09 | 2024-04-15 |  | 2024-06-10 | 2024-11-21 | 165 |  | 2024-04-09 | 2024-04-15 |  | 2024-06-21 | 2024-06-21 | 1 |  |  |  | 2024-04-03 | 2024-04-17 |  | 2024-10-21 | 2024-10-29 | 9 |  | 2024-02-27 | 2024-03-04 |  | 2024-02-20 | 2024-03-04 | 14 |  | 2024-02-27 | 2024-03-04 |  | 2024-04-09 | 2024-04-17 | 9 |  | Radhe Radhe | 2024-04-13 | 2024-04-19 |  | 2024-04-09 | 2024-04-17 | 9 |  | 2024-05-06 | 2024-05-11 |  | 2024-09-27 | 2024-10-06 | 10 |  | 2024-04-25 | 2024-05-01 |  | 2024-11-03 | 2024-11-10 | 8 |  | 2024-05-13 | 2024-05-21 |  | 2024-10-10 | 2024-10-17 | 8 |  | 2024-05-22 | 2024-05-24 |  | 2024-10-18 | 2024-10-26 | 9 | hold due to stud fouling with hub casting and may affect the pitching for blade | 2024-05-07 | 2024-05-09 |  | 2024-11-11 | 2024-11-11 | 1 |  | 2024-04-25 | 2024-05-01 |  | 2024-04-22 | 2024-04-28 | 7 |  | 2024-05-03 | 2024-05-18 |  | 2024-09-30 | 2024-10-28 | 29 |  | 2024-05-09 | 2024-05-12 |  | 2024-11-12 | 2024-11-18 | 7 |  | 2024-05-24 | 2024-05-25 |  | 2024-11-18 | 2024-11-22 | 5 |  |  | 2024-09-01
MECC | 23 | PSS-9 | ARE48L | WTG 465 | Precast | F3 | Bauer | Done | 547608 | 2658405 | 2023-11-28 | 2024-01-01 |  | 2023-11-28 | 2024-01-01 |  | 253 | 253 | 2024-03-24 | 2024-04-02 |  | 2024-04-01 | 2024-04-05 | 5 |  | Yes | 2024-04-20 | 2024-04-27 |  | 2024-04-20 | 2024-05-19 |  | 2024-04-13 | 2024-04-13 |  | 2024-05-30 | 2024-06-12 | 14 |  | 2024-04-14 | 2024-04-14 |  | 2024-06-12 | 2024-06-13 | 2 |  | 2024-04-15 | 2024-04-15 |  | 2024-06-14 | 2024-06-14 | 1 |  | 2024-04-16 | 2024-04-17 |  | 2024-06-15 | 2024-06-16 | 2 |  | 2024-04-19 | 2024-04-26 |  | 2024-06-15 | 2024-06-25 | 11 |  | 2024-04-29 | 2024-04-30 |  | 2024-06-28 | 2024-06-29 | 2 | 31 |  | 2024-05-02 | 2024-05-08 |  | 2024-07-31 | 2024-11-18 | 111 |  | 2024-05-02 | 2024-05-08 |  | 2024-08-03 | 2024-08-03 | 1 |  |  |  | 2024-04-26 | 2024-05-10 |  | 2024-09-18 | 2024-10-13 | 26 |  | 2024-03-30 | 2024-04-05 |  | 2024-02-20 | 2024-03-24 | 34 |  | 2024-03-30 | 2024-04-05 |  | 2024-05-03 | 2024-06-02 | 31 |  | Radhe Radhe | 2024-05-14 | 2024-05-20 |  | 2024-05-03 | 2024-06-02 | 31 |  | 2024-06-13 | 2024-06-18 |  | 2024-08-17 | 2024-09-13 | 28 |  | 2024-06-04 | 2024-06-10 |  | 2024-10-08 | 2024-10-21 | 14 |  | 2024-06-20 | 2024-06-26 |  | 2024-09-16 | 2024-10-02 | 17 |  | 2024-06-27 | 2024-06-28 |  | 2024-10-03 | 2024-10-14 | 12 |  | 2024-06-12 | 2024-06-14 |  | 2024-10-22 | 2024-10-22 | 1 |  | 2024-06-04 | 2024-06-10 |  | 2024-06-01 | 2024-06-28 | 28 |  | 2024-06-05 | 2024-06-20 |  | 2024-09-30 | 2024-10-28 | 29 |  | 2024-06-14 | 2024-06-17 |  | 2024-10-25 | 2024-11-18 | 25 | Balance Civil works in progress (Fencing, Hand rail, Final layer Back filling) | 2024-06-28 | 2024-06-29 |  | 2024-11-18 | 2024-11-22 | 5 |  |  | 2024-09-01
HBG | 24 | PSS-13 | ARE41L | WTG 237 | FDN | F2 | Sarita infra | Done | 538545 | 2668875 | 2023-04-21 | 2023-04-22 |  | 2023-04-21 | 2023-04-22 |  | 219 | 219 | 2024-02-24 | 2024-03-04 |  | 2023-12-25 | 2024-02-10 | 48 | [8 empty] | 2024-04-04 | 2024-04-04 |  | 2024-02-24 | 2024-02-27 | 4 |  | 2024-04-05 | 2024-04-05 |  | 2024-02-29 | 2024-03-02 | 3 |  | 2024-04-06 | 2024-04-06 |  | 2024-03-03 | 2024-03-03 | 1 |  | 2024-04-07 | 2024-04-08 |  | 2024-03-06 | 2024-03-07 | 2 |  | 2024-05-17 | 2024-05-24 |  | 2024-03-13 | 2024-03-27 | 15 |  | 2024-05-27 | 2024-05-28 |  | 2024-04-05 | 2024-04-05 | 1 | 42 |  | 2024-05-30 | 2024-06-05 |  | 2024-04-14 | 2025-01-23 | 285 |  | 2024-05-30 | 2024-06-05 |  | 2024-05-31 | 2024-05-31 | 1 |  |  |  | 2024-05-24 | 2024-06-07 |  | 2024-07-20 | 2025-01-09 | 174 |  | 2024-03-12 | 2024-03-18 |  | Completed | Completed | #VALUE! |  | 2024-03-12 | 2024-03-18 |  | 2024-11-06 | 2024-11-13 | 8 |  | Ontogeny / SS Jadeja | 2024-06-03 | 2024-06-09 |  | 2024-11-06 | 2024-11-13 | 8 |  | 2024-06-23 | 2024-06-28 |  | 2024-11-15 | 2024-11-25 | 11 |  | 2024-06-15 | 2024-06-21 |  | 2024-12-30 | 2025-01-15 | 17 |  | 2024-06-30 | 2024-07-08 |  | 2024-12-01 | 2024-12-09 | 9 |  | 2024-07-09 | 2024-07-11 |  | 2024-12-11 | 2024-12-19 | 9 |  | 2024-06-27 | 2024-06-29 |  | 2025-01-13 | 2025-01-13 | 1 |  | 2024-06-15 | 2024-06-21 |  | 2024-05-12 | 2024-09-08 | 120 |  | 2024-06-05 | 2024-06-20 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-06-29 | 2024-07-02 |  | 2025-01-15 | 2025-01-21 | 7 |  | 2024-07-11 | 2024-07-12 |  | 2025-01-27 | 2025-01-28 | 2 |  |  | 2024-09-01
KAILASHNATH | 25 | PSS-13 | ARE41L | WTG 148 | Precast | F1 | Sarita infra | Done | 535385 | 2669026 | 2023-06-04 | 2023-06-05 |  | 2023-06-04 | 2023-06-05 |  | 199 | 199 | 2024-02-23 | 2024-03-03 |  | 2023-10-05 | 2023-10-20 | 16 | [8 empty] | 2024-04-03 | 2024-04-03 |  | 2024-02-26 | 2024-02-27 | 2 |  | 2024-04-04 | 2024-04-04 |  | 2024-02-29 | 2024-03-02 | 3 |  | 2024-04-05 | 2024-04-05 |  | 2024-03-03 | 2024-03-03 | 1 |  | 2024-04-06 | 2024-04-07 |  | 2024-03-07 | 2024-03-08 | 2 |  | 2024-05-16 | 2024-05-23 |  | 2024-03-12 | 2024-03-27 | 16 |  | 2024-05-26 | 2024-05-27 |  | 2024-04-01 | 2024-04-02 | 2 | 37 |  | 2024-05-29 | 2024-06-04 |  | 2024-04-12 | 2024-12-31 | 264 |  | 2024-05-29 | 2024-06-04 |  | 2024-04-27 | 2024-04-27 | 1 |  |  |  | 2024-05-23 | 2024-06-06 |  | 2024-11-27 | 2024-12-04 | 8 |  | 2024-03-12 | 2024-03-18 |  | Completed | Completed | #VALUE! |  | 2024-03-12 | 2024-03-18 |  | 2024-06-06 | 2024-06-18 | 13 |  | GP | 2024-06-02 | 2024-06-08 |  | 2024-06-06 | 2024-06-18 | 13 |  | 2024-06-21 | 2024-06-26 |  | 2024-07-01 | 2024-07-20 | 20 |  | 2024-06-14 | 2024-06-20 |  | 2024-12-12 | 2024-12-20 | 9 |  | 2024-06-28 | 2024-07-06 |  | 2024-07-21 | 2024-08-02 | 13 |  | 2024-07-07 | 2024-07-09 |  | 2024-08-03 | 2024-08-08 | 6 |  | 2024-06-26 | 2024-06-28 |  | 2024-12-26 | 2024-12-26 | 1 |  | 2024-06-14 | 2024-06-20 |  | 2024-05-12 | 2024-05-18 | 7 |  | 2024-06-05 | 2024-06-20 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-06-28 | 2024-07-01 |  | 2024-12-31 | 2025-01-06 | 7 |  | 2024-07-09 | 2024-07-10 |  | 2025-01-26 | 2025-01-26 | 1 |  |  | 2024-09-01
RAVIRAJ | 26 | PSS-13 | ARE41L | WTG 170 | Precast | F1 | Bauer | Done | 536037 | 2669708 | 2023-06-01 | 2023-06-02 |  | 2023-06-01 | 2023-06-02 |  | 219 | 219 | 2024-02-25 | 2024-03-05 |  | 2024-01-15 | 2024-01-25 | 11 | [8 empty] | 2024-04-05 | 2024-04-05 |  | 2024-03-02 | 2024-03-04 | 3 |  | 2024-04-06 | 2024-04-06 |  | 2024-03-05 | 2024-03-07 | 3 |  | 2024-04-07 | 2024-04-07 |  | 2024-03-07 | 2024-03-07 | 1 |  | 2024-04-08 | 2024-04-09 |  | 2024-03-08 | 2024-03-09 | 2 |  | 2024-05-18 | 2024-05-25 |  | 2024-03-29 | 2024-04-30 | 33 |  | 2024-05-28 | 2024-05-29 |  | 2024-05-01 | 2024-05-01 | 1 | 61 |  | 2024-05-31 | 2024-06-06 |  | 2024-05-08 | 2024-12-29 | 236 |  | 2024-05-31 | 2024-06-06 |  | 2024-06-03 | 2024-06-03 | 1 |  |  |  | 2024-05-25 | 2024-06-08 |  | 2024-11-26 | 2024-12-08 | 13 |  | 2024-03-12 | 2024-03-18 |  | Completed | Completed | #VALUE! |  | 2024-03-12 | 2024-03-18 |  | 2024-06-08 | 2024-06-19 | 12 |  | Vipin | 2024-06-04 | 2024-06-10 |  | 2024-06-08 | 2024-06-19 | 12 |  | 2024-06-27 | 2024-07-02 |  | 2024-07-02 | 2024-07-19 | 18 |  | 2024-06-16 | 2024-06-22 |  | 2024-12-10 | 2024-12-20 | 11 |  | 2024-07-04 | 2024-07-12 |  | 2024-07-20 | 2024-08-14 | 26 |  | 2024-07-13 | 2024-07-15 |  | 2024-08-14 | 2024-12-27 | 136 | hold due to shortage of material. | 2024-06-28 | 2024-06-30 |  | 2024-12-27 | 2024-12-27 | 1 |  | 2024-06-16 | 2024-06-22 |  | 2024-05-12 | 2024-05-18 | 7 |  | 2024-07-01 | 2024-07-16 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-06-30 | 2024-07-03 |  | 2024-12-31 | 2025-01-06 | 7 |  | 2024-07-16 | 2024-07-17 |  | 2025-01-26 | 2025-01-27 | 2 |  |  | 2024-09-01
AB INFRA | 27 | PSS-13 | ARE41L | WTG 191 | FDN | F1 | Bauer | Done | 536680 | 2670430 | 2023-06-02 | 2023-06-03 |  | 2023-06-02 | 2023-06-03 |  | 199 | 199 | 2024-02-26 | 2024-03-06 |  | 2024-02-09 | 2024-02-15 | 7 | [8 empty] | 2024-04-06 | 2024-04-06 |  | 2024-04-09 | 2024-04-12 | 4 |  | 2024-04-07 | 2024-04-07 |  | 2024-04-17 | 2024-04-20 | 4 |  | 2024-04-08 | 2024-04-08 |  | 2024-04-21 | 2024-04-21 | 1 |  | 2024-04-09 | 2024-04-10 |  | 2024-05-11 | 2024-05-12 | 2 |  | 2024-05-19 | 2024-05-26 |  | 2024-05-13 | 2024-08-17 | 97 |  | 2024-05-29 | 2024-05-30 |  | 2024-12-27 | 2024-12-28 | 2 | 264 |  | 2024-06-01 | 2024-06-07 |  | 2025-01-04 | 2025-01-26 | 23 |  | 2024-06-01 | 2024-06-07 |  | 2025-01-03 | 2025-01-03 | 1 |  |  |  | 2024-05-26 | 2024-06-09 |  | 2024-12-07 | 2024-12-25 | 19 |  | 2024-03-12 | 2024-03-18 |  | Completed | Completed | #VALUE! |  | 2024-03-12 | 2024-03-18 |  | 2025-01-04 | 2025-01-12 | 9 |  | GP (Reuse) | 2024-06-05 | 2024-06-11 |  | 2024-12-30 | 2025-01-13 | 15 |  | 2024-06-28 | 2024-07-03 |  | 2025-01-13 | 2025-01-19 | 7 |  | 2024-06-22 | 2024-06-28 |  | 2024-12-26 | 2025-01-23 | 29 |  | 2024-07-05 | 2024-07-13 |  | 2025-01-22 | 2025-01-29 | 8 |  | 2024-07-14 | 2024-07-16 |  | 2025-01-30 | 2025-01-31 | 2 |  | 2024-07-04 | 2024-07-06 |  | 2025-01-16 | 2025-01-16 | 1 |  | 2024-06-22 | 2024-06-28 |  | 2024-05-12 | 2024-05-18 | 7 |  | 2024-07-01 | 2024-07-16 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-07-06 | 2024-07-09 |  | 2025-01-24 | 2025-01-29 | 6 |  | 2024-07-16 | 2024-07-17 |  | 2025-02-14 | 2025-02-14 | 1 |  |  | 2024-09-01
ABE/UNIQUE INF | 28 | PSS-13 | ARE41L | WTG 169 | FDN | F1 | Bauer | Done | 535847 | 2670695 | 2023-06-03 | 2023-06-04 |  | 2023-06-03 | 2023-06-04 |  | 163 | 163 | 2024-03-08 | 2024-03-17 |  | 2024-01-27 | 2024-02-01 | 6 | [8 empty] | 2024-04-12 | 2024-04-12 |  | 2024-05-09 | 2024-05-16 | 8 |  | 2024-04-13 | 2024-04-13 |  | 2024-05-25 | 2024-05-30 | 6 |  | 2024-04-14 | 2024-04-14 |  | 2024-06-04 | 2024-06-04 | 1 |  | 2024-04-15 | 2024-04-16 |  | 2024-10-14 | 2024-10-20 | 7 |  | 2024-05-23 | 2024-05-30 |  | 2024-10-21 | 2024-11-17 | 28 |  | 2024-06-02 | 2024-06-03 |  | 2024-11-20 | 2024-11-20 | 1 | 196 |  | 2024-06-05 | 2024-06-11 |  | 2024-11-29 | 2025-02-01 | 65 |  | 2024-06-05 | 2024-06-11 |  | 2024-12-03 | 2024-12-03 | 1 |  |  |  | 2024-05-30 | 2024-06-13 |  | 2024-12-05 | 2024-12-17 | 13 |  | 2024-03-20 | 2024-03-26 |  | Completed | Completed | #VALUE! |  | 2024-03-20 | 2024-03-26 |  | Completed | Completed | #VALUE! |  | Vaibhav | 2024-06-13 | 2024-06-19 |  | 2024-10-25 | 2024-12-16 | 53 |  | 2024-07-07 | 2024-07-12 |  | 2024-12-18 | 2024-12-28 | 11 |  | 2024-07-01 | 2024-07-07 |  | 2024-12-22 | 2025-01-07 | 17 |  | 2024-07-14 | 2024-07-22 |  | 2025-01-10 | 2025-01-21 | 12 |  | 2024-07-23 | 2024-07-25 |  | 2025-01-21 | 2025-01-22 | 2 |  | 2024-07-13 | 2024-07-15 |  | 2025-01-08 | 2025-01-08 | 1 |  | 2024-07-01 | 2024-07-07 |  | 2024-05-12 | 2024-05-18 | 7 |  | 2024-07-01 | 2024-07-16 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-07-15 | 2024-07-18 |  | 2025-01-15 | 2025-01-21 | 7 |  | 2024-07-25 | 2024-07-26 |  | 2025-02-14 | 2025-02-14 | 1 |  |  | 2024-09-01
MECC/UNIQUE INF | 29 | PSS-13 | ARE41L | WTG 215 | FDN | F2 | Menard | Done | 537711 | 2669139 | 2023-04-21 | 2023-04-22 |  | 2023-04-21 | 2023-04-22 |  | 219 | 219 | 2024-03-17 | 2024-03-26 |  | 2024-02-20 | 2024-02-29 | 10 | [8 empty] | 2024-04-16 | 2024-04-16 |  | 2024-03-13 | 2024-03-15 | 3 |  | 2024-04-17 | 2024-04-17 |  | 2024-06-15 | 2024-06-22 | 8 |  | 2024-04-18 | 2024-04-18 |  | 2024-06-23 | 2024-06-23 | 1 |  | 2024-04-19 | 2024-04-20 |  | 2024-07-01 | 2024-07-04 | 4 |  | 2024-05-25 | 2024-06-01 |  | 2024-07-06 | 2024-11-12 | 130 | Delay due to rains & manpower left from site | 2024-06-04 | 2024-06-05 |  | 2024-11-14 | 2024-11-15 | 2 | 248 |  | 2024-06-07 | 2024-06-13 |  | 2024-12-16 | 2025-01-26 | 42 |  | 2024-06-07 | 2024-06-13 |  | 2024-12-03 | 2024-12-03 | 1 |  |  |  | 2024-06-01 | 2024-06-15 |  | 2024-12-18 | 2025-01-03 | 17 |  | 2024-03-28 | 2024-04-03 |  | Completed | Completed | #VALUE! |  | 2024-03-28 | 2024-04-03 |  | Completed | Completed | #VALUE! |  | GP | 2024-06-19 | 2024-06-25 |  | 2024-11-11 | 2024-12-22 | 42 |  | 2024-07-17 | 2024-07-22 |  | 2024-12-29 | 2025-01-08 | 11 |  | 2024-07-08 | 2024-07-14 |  | 2024-12-27 | 2025-01-18 | 23 |  | 2024-07-24 | 2024-08-01 |  | 2025-01-13 | 2025-01-19 | 7 |  | 2024-08-02 | 2024-08-04 |  | 2025-01-18 | 2025-01-21 | 4 |  | 2024-07-20 | 2024-07-22 |  | 2025-01-18 | 2025-01-18 | 1 |  | 2024-07-08 | 2024-07-14 |  | 2024-05-12 | 2024-05-21 | 10 |  | 2024-07-01 | 2024-07-16 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-07-22 | 2024-07-25 |  | 2025-01-13 | 2025-01-21 | 9 |  | 2024-08-04 | 2024-08-05 |  | 2025-01-27 | 2025-01-28 | 2 |  | Upto PCC - MECC Anchor Cage - Unique | 2024-09-01
SHREEJI | 30 | PSS-13 | ARE41L | WTG 192 | Precast | F1 | Bauer | Done | 536870 | 2669444 | 2023-05-29 | 2023-05-30 |  | 2023-05-29 | 2023-05-30 |  | 199 | 199 | 2024-03-19 | 2024-03-28 |  | 2024-02-02 | 2024-02-08 | 7 |  | Yes | 2024-04-22 | 2024-04-30 |  | 2024-04-24 | 2024-05-19 |  | 2024-04-18 | 2024-04-18 |  | 2024-10-25 | 2024-10-28 | 4 |  | 2024-04-19 | 2024-04-19 |  | 2024-10-28 | 2024-10-29 | 2 |  | 2024-04-20 | 2024-04-20 |  | 2024-10-29 | 2024-10-29 | 1 |  | 2024-04-21 | 2024-04-22 |  | 2024-10-30 | 2024-11-02 | 4 |  | 2024-05-27 | 2024-06-03 |  | 2024-11-03 | 2024-11-11 | 9 |  | 2024-06-06 | 2024-06-07 |  | 2024-11-12 | 2024-11-13 | 2 | 20 |  | 2024-06-09 | 2024-06-15 |  | 2024-11-23 | 2025-01-25 | 64 |  | 2024-06-09 | 2024-06-15 |  | 2024-11-26 | 2024-11-26 | 1 |  |  |  | 2024-06-03 | 2024-06-17 |  | 2024-12-13 | 2024-12-18 | 6 |  | 2024-03-28 | 2024-04-03 |  | Completed | Completed | #VALUE! |  | 2024-03-28 | 2024-04-03 |  | Completed | Completed | #VALUE! |  | GP | 2024-06-21 | 2024-06-27 |  | 2024-12-07 | 2024-12-29 | 23 |  | 2024-07-16 | 2024-07-21 |  | 2024-12-30 | 2025-01-10 | 12 |  | 2024-07-10 | 2024-07-16 |  | 2024-12-22 | 2025-01-10 | 20 |  | 2024-07-23 | 2024-07-31 |  | 2025-01-13 | 2025-01-20 | 8 |  | 2024-08-01 | 2024-08-03 |  | 2025-01-20 | 2025-01-23 | 4 |  | 2024-07-22 | 2024-07-24 |  | 2025-01-10 | 2025-01-10 | 1 |  | 2024-07-10 | 2024-07-16 |  | 2024-05-12 | 2024-05-18 | 7 |  | 2024-07-01 | 2024-07-16 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-07-24 | 2024-07-27 |  | 2025-01-15 | 2025-01-21 | 7 |  | 2024-08-03 | 2024-08-04 |  | 2025-01-26 | 2025-01-26 | 1 |  |  | 2024-09-01
ABE/UNIQUE INF | 31 | PSS-13 | ARE41L | WTG 236 | Precast | F2 | Menard | Done | 538355 | 2669861 | 2023-04-28 | 2023-04-29 |  | 2023-04-28 | 2023-04-29 |  | 219 | 219 | 2024-03-06 | 2024-03-15 |  | 2024-04-05 | 2024-04-15 | 11 | [8 empty] | 2024-04-10 | 2024-04-10 |  | 2024-04-30 | 2024-05-02 | 3 |  | 2024-04-11 | 2024-04-11 |  | 2024-05-11 | 2024-05-21 | 11 |  | 2024-04-12 | 2024-04-12 |  | 2024-05-23 | 2024-05-23 | 1 |  | 2024-04-13 | 2024-04-14 |  | 2024-06-17 | 2024-06-25 | 9 |  | 2024-05-21 | 2024-05-28 |  | 2024-10-10 | 2024-11-03 | 25 |  | 2024-05-31 | 2024-06-01 |  | 2024-11-07 | 2024-11-09 | 3 | 194 |  | 2024-06-03 | 2024-06-09 |  | 2024-12-05 | 2025-01-08 | 35 |  | 2024-06-03 | 2024-06-09 |  | 2024-12-01 | 2024-12-01 | 1 |  |  |  | 2024-05-28 | 2024-06-11 |  | 2024-11-23 | 2024-12-24 | 32 |  | 2024-03-20 | 2024-03-26 |  | Completed | Completed | #VALUE! |  | 2024-03-20 | 2024-03-26 |  | Completed | Completed | #VALUE! |  | SS Jadeja | 2024-06-11 | 2024-06-17 |  | 2024-11-24 | 2024-11-30 | 7 |  | 2024-07-02 | 2024-07-07 |  | 2024-11-30 | 2024-12-16 | 17 |  | 2024-06-24 | 2024-06-30 |  | 2024-12-27 | 2025-01-06 | 11 |  | 2024-07-09 | 2024-07-17 |  | 2024-12-28 | 2025-01-16 | 20 |  | 2024-07-18 | 2024-07-20 |  | 2025-01-17 | 2025-01-17 | 1 |  | 2024-07-06 | 2024-07-08 |  | 2025-01-10 | 2025-01-10 | 1 |  | 2024-06-24 | 2024-06-30 |  | 2024-07-12 | 2024-10-20 | 101 |  | 2024-07-01 | 2024-07-16 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-07-08 | 2024-07-11 |  | 2025-01-13 | 2025-01-21 | 9 |  | 2024-07-20 | 2024-07-21 |  | 2025-01-27 | 2025-01-28 | 2 |  |  | 2024-09-01
AB INFRA | 32 | PSS-13 | ARE41L | WTG 214 | Precast | F2 | Menard | Done | 537522 | 2670126 | 2023-06-02 | 2023-06-03 |  | 2023-06-02 | 2023-06-03 |  | 199 | 199 | 2024-03-05 | 2024-03-14 |  | 2024-03-22 | 2024-04-03 | 13 | [8 empty] | 2024-04-09 | 2024-04-09 |  | 2024-04-22 | 2024-05-03 | 12 |  | 2024-04-10 | 2024-04-10 |  | 2024-05-07 | 2024-05-15 | 9 |  | 2024-04-11 | 2024-04-11 |  | 2024-05-15 | 2024-05-15 | 1 |  | 2024-04-12 | 2024-04-13 |  | 2024-06-07 | 2024-06-10 | 4 |  | 2024-05-20 | 2024-05-27 |  | 2024-06-13 | 2024-10-28 | 138 | Delay due to rains & manpower left from site | 2024-05-30 | 2024-05-31 |  | 2024-10-29 | 2024-10-30 | 2 | 192 |  | 2024-06-02 | 2024-06-08 |  | 2024-11-22 | 2025-01-22 | 62 |  | 2024-06-02 | 2024-06-08 |  | 2024-11-25 | 2024-11-25 | 1 |  |  |  | 2024-05-27 | 2024-06-10 |  | 2024-11-24 | 2024-12-11 | 18 |  | 2024-03-20 | 2024-03-26 |  | Completed | Completed | #VALUE! |  | 2024-03-20 | 2024-03-26 |  | Completed | Completed | #VALUE! |  | Vaibhav | 2024-06-10 | 2024-06-16 |  | 2024-11-26 | 2024-12-07 | 12 |  | 2024-06-30 | 2024-07-05 |  | 2024-12-08 | 2024-12-18 | 11 |  | 2024-06-23 | 2024-06-29 |  | 2024-12-18 | 2024-12-24 | 7 |  | 2024-07-07 | 2024-07-15 |  | 2024-12-20 | 2024-12-26 | 7 |  | 2024-07-16 | 2024-07-18 |  | 2024-12-27 | 2024-12-29 | 3 |  | 2024-07-05 | 2024-07-07 |  | 2024-12-29 | 2024-12-29 | 1 |  | 2024-06-23 | 2024-06-29 |  | 2024-05-12 | 2024-05-19 | 8 |  | 2024-07-01 | 2024-07-16 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-07-07 | 2024-07-10 |  | 2024-12-31 | 2025-01-06 | 7 |  | 2024-07-18 | 2024-07-19 |  | 2025-01-26 | 2025-01-28 | 3 |  |  | 2024-09-01
SHREEJI | 33 | PSS-13 | ARE41L | WTG 257 | Precast | F5 | Menard | Done | 539006 | 2670543 | 2023-06-01 | 2023-06-02 |  | 2023-06-01 | 2023-06-02 |  | 163 | 163 | 2024-03-27 | 2024-04-05 |  | 2024-03-04 | 2024-03-08 | 5 |  | Yes | 2024-05-08 | 2024-05-15 |  | 2024-05-08 | 2024-05-25 |  | 2024-04-21 | 2024-04-21 |  | 2024-11-03 | 2024-11-05 | 3 |  | 2024-04-22 | 2024-04-22 |  | 2024-11-06 | 2024-11-08 | 3 |  | 2024-04-23 | 2024-04-23 |  | 2024-11-10 | 2024-11-10 | 1 |  | 2024-04-24 | 2024-04-25 |  | 2024-11-18 | 2024-11-18 | 1 |  | 2024-05-28 | 2024-06-04 |  | 2024-11-19 | 2024-11-30 | 12 |  | 2024-06-07 | 2024-06-08 |  | 2024-11-30 | 2024-12-01 | 2 | 29 |  | 2024-06-10 | 2024-06-16 |  | 2024-12-06 | 2025-01-21 | 47 |  | 2024-06-10 | 2024-06-16 |  | 2024-12-08 | 2024-12-08 | 1 |  |  |  | 2024-06-04 | 2024-06-18 |  | 2024-11-23 | 2024-12-16 | 24 |  | 2024-04-05 | 2024-04-11 |  | 2024-02-28 | 2024-03-11 | 13 |  | 2024-04-05 | 2024-04-11 |  | Completed | Completed | #VALUE! |  | Ontogeny | 2024-06-26 | 2024-07-02 |  | 2024-05-16 | 2024-06-08 | 24 |  | 2024-07-18 | 2024-07-23 |  | 2024-12-18 | 2024-12-27 | 10 |  | 2024-07-16 | 2024-07-22 |  | 2024-12-21 | 2025-01-04 | 15 |  | 2024-07-25 | 2024-08-02 |  | 2025-01-03 | 2025-01-10 | 8 |  | 2024-08-03 | 2024-08-05 |  | 2025-01-11 | 2025-01-14 | 4 |  | 2024-07-28 | 2024-07-30 |  | 2025-01-10 | 2025-01-10 | 1 |  | 2024-07-16 | 2024-07-22 |  | 2024-05-12 | 2024-09-17 | 129 |  | 2024-07-01 | 2024-07-16 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-07-30 | 2024-08-02 |  | 2025-01-13 | 2025-01-21 | 9 |  | 2024-08-05 | 2024-08-06 |  | 2025-01-26 | 2025-01-27 | 2 |  |  | 2024-09-01
SHREEJI | 34 | PSS-13 | ARE41L | WTG 281 | Precast | F5 | Menard | Done | 539840 | 2670278 | 2024-01-03 | 2024-01-30 |  | 2024-01-03 | 2024-01-30 |  | 199 | 199 | 2024-03-07 | 2024-03-16 |  | 2024-04-26 | 2024-05-04 | 9 | [8 empty] | 2024-04-11 | 2024-04-11 |  | 2024-05-25 | 2024-05-27 | 3 |  | 2024-04-12 | 2024-04-12 |  | 2024-05-28 | 2024-05-29 | 2 |  | 2024-04-13 | 2024-04-13 |  | 2024-05-30 | 2024-05-30 | 1 |  | 2024-04-14 | 2024-04-15 |  | 2024-06-05 | 2024-06-06 | 2 |  | 2024-05-22 | 2024-05-29 |  | 2024-06-07 | 2024-07-31 | 55 |  | 2024-06-01 | 2024-06-02 |  | 2024-08-11 | 2024-08-12 | 2 | 80 |  | 2024-06-04 | 2024-06-10 |  | 2024-08-24 | 2025-01-21 | 151 |  | 2024-06-04 | 2024-06-10 |  | 2024-08-27 | 2024-08-27 | 1 |  |  |  | 2024-05-29 | 2024-06-12 |  | 2024-11-17 | 2024-12-04 | 18 |  | 2024-03-20 | 2024-03-26 |  | Completed | Completed | #VALUE! |  | 2024-03-20 | 2024-03-26 |  | 2024-10-25 | 2024-11-13 | 20 |  | Radhe Radhe | 2024-06-12 | 2024-06-18 |  | 2024-10-25 | 2024-11-13 | 20 |  | 2024-07-06 | 2024-07-11 |  | 2024-11-14 | 2024-11-27 | 14 |  | 2024-06-30 | 2024-07-06 |  | 2024-12-09 | 2024-12-17 | 9 |  | 2024-07-13 | 2024-07-21 |  | 2024-12-01 | 2024-12-07 | 7 |  | 2024-07-22 | 2024-07-24 |  | 2024-12-11 | 2024-12-14 | 4 |  | 2024-07-12 | 2024-07-14 |  | 2024-12-30 | 2024-12-30 | 1 |  | 2024-06-30 | 2024-07-06 |  | 2024-05-12 | 2024-05-23 | 12 |  | 2024-07-01 | 2024-07-16 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-07-14 | 2024-07-17 |  | 2025-01-13 | 2025-01-21 | 9 |  | 2024-07-24 | 2024-07-25 |  | 2025-01-26 | 2025-01-27 | 2 |  |  | 2024-09-01
SHREEJI | 35 | PSS-13 | ARE41L | WTG 357 | Precast | F4 | Menard | Done | 542736 | 2667432 | 2023-01-10 | 2023-01-11 |  | 2023-01-10 | 2023-01-11 |  | 219 | 219 | 2024-03-28 | 2024-04-06 |  | 2024-04-18 | 2024-04-26 | 9 | [8 empty] | 2024-04-22 | 2024-04-22 |  | 2024-11-27 | 2024-11-29 | 3 |  | 2024-04-23 | 2024-04-23 |  | 2024-11-30 | 2024-12-01 | 2 |  | 2024-04-24 | 2024-04-24 |  | 2024-12-02 | 2024-12-02 | 1 |  | 2024-04-25 | 2024-04-26 |  | 2024-12-05 | 2024-12-05 | 1 |  | 2024-05-29 | 2024-06-05 |  | 2024-12-06 | 2024-12-16 | 11 |  | 2024-06-08 | 2024-06-09 |  | 2024-12-19 | 2024-12-20 | 2 | 24 |  | 2024-06-11 | 2024-06-17 |  | 2024-12-24 | 2025-01-26 | 34 |  | 2024-06-11 | 2024-06-17 |  | 2024-12-28 | 2024-12-28 | 1 |  |  |  | 2024-06-05 | 2024-06-19 |  | 2024-12-02 | 2024-12-15 | 14 |  | 2024-04-05 | 2024-04-11 |  | Completed | Completed | #VALUE! |  | 2024-04-05 | 2024-04-11 |  | Completed | Completed | #VALUE! |  | Odhav | 2024-06-27 | 2024-07-03 |  | 2025-01-04 | 2025-02-05 | 33 |  | 2024-07-26 | 2024-07-31 |  | 2025-02-08 | 2025-02-17 | 10 |  | 2024-07-17 | 2024-07-23 |  | 2024-12-20 | 2025-01-15 | 27 |  | 2024-08-02 | 2024-08-10 |  | 2025-02-23 | 2025-02-27 | 5 |  | 2024-08-11 | 2024-08-13 |  | 2025-02-28 | 2025-03-01 | 2 |  | 2024-07-29 | 2024-07-31 |  | 2025-01-16 | 2025-01-16 | 1 |  | 2024-07-17 | 2024-07-23 |  | 2024-05-16 | 2024-05-24 | 9 |  | 2024-07-01 | 2024-07-16 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-07-31 | 2024-08-03 |  | 2025-01-24 | 2025-01-30 | 7 |  | 2024-08-13 | 2024-08-14 |  | 2025-03-06 | 2025-03-06 | 1 |  |  | 2024-09-01
SHREEJI | 36 | PSS-13 | ARE41L | WTG 332 | Precast | F4 | Menard | Done | 541895 | 2667737 | 2023-01-10 | 2023-01-11 |  | 2023-01-10 | 2023-01-11 |  | 199 | 199 | 2024-03-29 | 2024-04-07 |  | 2024-04-26 | 2024-05-04 | 9 | [8 empty] | 2024-04-23 | 2024-04-23 |  | 2024-10-22 | 2024-10-25 | 4 |  | 2024-04-24 | 2024-04-24 |  | 2024-10-26 | 2024-11-06 | 12 |  | 2024-04-25 | 2024-04-25 |  | 2024-11-13 | 2024-11-13 | 1 |  | 2024-04-26 | 2024-04-27 |  | 2024-11-16 | 2024-11-17 | 2 |  | 2024-05-30 | 2024-06-06 |  | 2024-11-18 | 2024-11-27 | 10 |  | 2024-06-09 | 2024-06-10 |  | 2024-11-28 | 2024-11-29 | 2 | 39 |  | 2024-06-12 | 2024-06-18 |  | 2024-12-05 | 2025-01-26 | 53 |  | 2024-06-12 | 2024-06-18 |  | 2024-12-11 | 2024-12-11 | 1 |  |  |  | 2024-06-06 | 2024-06-20 |  | 2024-12-05 | 2024-12-14 | 10 |  | 2024-04-05 | 2024-04-11 |  | Completed | Completed | #VALUE! |  | 2024-04-05 | 2024-04-11 |  | 2024-12-30 | 2025-01-10 | 12 |  | Odhav | 2024-06-28 | 2024-07-04 |  | 2024-12-08 | 2025-01-15 | 39 |  | 2024-07-27 | 2024-08-01 |  | 2025-02-22 | 2025-03-03 | 10 |  | 2024-07-18 | 2024-07-24 |  | 2024-12-16 | 2024-12-29 | 14 |  | 2024-08-03 | 2024-08-11 |  | 2025-03-04 | 2025-03-08 | 5 |  | 2024-08-12 | 2024-08-14 |  | 2025-03-09 | 2025-03-09 | 1 |  | 2024-07-30 | 2024-08-01 |  | 2025-01-03 | 2025-01-03 | 1 |  | 2024-07-18 | 2024-07-24 |  | 2024-05-16 | 2024-09-15 | 123 |  | 2024-07-25 | 2024-08-09 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-08-01 | 2024-08-04 |  | 2025-01-13 | 2025-01-21 | 9 |  | 2024-08-14 | 2024-08-15 |  | 2025-03-11 | 2025-03-12 | 2 |  |  | 2024-09-01
SHREEJI | 37 | PSS-13 | ARE41L | WTG 258 | Precast | F3 | Bauer | Done | 539196 | 2669557 | 2024-01-02 | 2024-01-29 |  | 2024-01-02 | 2024-01-29 |  | 211 | 211 | 2024-03-30 | 2024-04-08 |  | 2024-04-17 | 2024-04-25 | 9 | [8 empty] | 2024-04-24 | 2024-04-24 |  | 2024-09-18 | 2024-09-25 | 8 |  | 2024-04-25 | 2024-04-25 |  | 2024-10-02 | 2024-10-09 | 8 |  | 2024-04-26 | 2024-04-26 |  | 2024-10-13 | 2024-10-13 | 1 |  | 2024-04-27 | 2024-04-28 |  | 2024-10-14 | 2024-10-15 | 2 |  | 2024-05-31 | 2024-06-07 |  | 2024-10-16 | 2024-10-25 | 10 |  | 2024-06-10 | 2024-06-11 |  | 2024-10-25 | 2024-10-26 | 2 | 39 |  | 2024-06-13 | 2024-06-19 |  | 2024-11-19 | 2025-01-22 | 65 |  | 2024-06-13 | 2024-06-19 |  | 2024-11-20 | 2024-11-20 | 1 |  |  |  | 2024-06-07 | 2024-06-21 |  | 2024-11-19 | 2024-12-13 | 25 |  | 2024-04-05 | 2024-04-11 |  | 2024-02-28 | 2024-03-11 | 13 |  | 2024-04-05 | 2024-04-11 |  | Completed | Completed | #VALUE! |  | Adani (Self Resue) | 2024-06-29 | 2024-07-05 |  | 2024-12-14 | 2024-12-28 | 15 |  | 2024-07-25 | 2024-07-30 |  | 2024-12-30 | 2025-01-09 | 11 |  | 2024-07-24 | 2024-07-30 |  | 2024-12-16 | 2024-12-29 | 14 |  | 2024-08-01 | 2024-08-09 |  | 2025-01-11 | 2025-01-22 | 12 |  | 2024-08-10 | 2024-08-12 |  | 2025-01-23 | 2025-01-23 | 1 |  | 2024-08-05 | 2024-08-07 |  | 2025-01-06 | 2025-01-06 | 1 |  | 2024-07-24 | 2024-07-30 |  | 2024-05-25 | 2024-05-31 | 7 |  | 2024-07-01 | 2024-07-16 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-08-07 | 2024-08-10 |  | 2025-01-13 | 2025-01-21 | 9 |  | 2024-08-12 | 2024-08-13 |  | 2025-02-15 | 2025-02-16 | 2 |  |  | 2024-09-01
SHREEJI | 38 | PSS-13 | ARE41L | WTG 306 | Precast | F3 | Menard | Done | 540871 | 2668988 | 2023-12-28 | 2024-01-28 |  | 2023-12-28 | 2024-01-28 |  | 211 | 211 | 2024-03-16 | 2024-03-25 |  | 2024-05-07 | 2024-05-18 | 12 | [8 empty] | 2024-04-15 | 2024-04-15 |  | 2024-05-31 | 2024-06-02 | 3 |  | 2024-04-16 | 2024-04-16 |  | 2024-06-03 | 2024-06-04 | 2 |  | 2024-04-17 | 2024-04-17 |  | 2024-06-05 | 2024-06-05 | 1 |  | 2024-04-18 | 2024-04-19 |  | 2024-06-22 | 2024-06-24 | 3 |  | 2024-05-24 | 2024-05-31 |  | 2024-06-25 | 2024-08-25 | 62 | Delay due to rains | 2024-06-03 | 2024-06-04 |  | 2024-10-16 | 2024-10-24 | 9 | 147 | During casting road is damaged and Rain. Due to partial casting other process to be implmention done | 2024-06-06 | 2024-06-12 |  | 2024-11-05 | 2025-01-22 | 79 |  | 2024-06-06 | 2024-06-12 |  | 2024-11-07 | 2024-11-07 | 1 |  |  |  | 2024-05-31 | 2024-06-14 |  | 2024-11-23 | 2024-12-21 | 29 |  | 2024-03-28 | 2024-04-03 |  | Completed | Completed | #VALUE! |  | 2024-03-28 | 2024-04-03 |  | 2024-11-11 | 2024-11-18 | 8 |  | Vaibhav | 2024-06-18 | 2024-06-24 |  | 2024-11-11 | 2024-11-18 | 8 |  | 2024-07-09 | 2024-07-14 |  | 2024-11-26 | 2024-12-15 | 20 |  | 2024-07-02 | 2024-07-08 |  | 2024-12-23 | 2025-01-05 | 14 |  | 2024-07-16 | 2024-07-24 |  | 2024-12-24 | 2025-01-08 | 16 |  | 2024-07-25 | 2024-07-27 |  | 2025-01-10 | 2025-01-11 | 2 |  | 2024-07-14 | 2024-07-16 |  | 2025-01-10 | 2025-01-10 | 1 |  | 2024-07-02 | 2024-07-08 |  | 2024-05-25 | 2024-05-31 | 7 |  | 2024-07-01 | 2024-07-16 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-07-16 | 2024-07-19 |  | 2025-01-15 | 2025-01-21 | 7 |  | 2024-07-27 | 2024-07-28 |  | 2025-01-27 | 2025-01-27 | 1 |  |  | 2024-09-01
MSC | 39 | PSS-13 | ARE41L | WTG 282 | Precast | F3 | Sarita infra | Done | 540030 | 2669292 | 2023-12-29 | 2024-01-28 |  | 2023-12-29 | 2024-01-28 |  | 253 | 253 | 2024-04-20 | 2024-04-29 |  | 2024-07-20 | 2024-10-15 | 88 | [8 empty] | 2024-05-05 | 2024-05-05 |  | 2024-12-02 | 2024-12-09 | 8 |  | 2024-05-06 | 2024-05-06 |  | 2024-12-09 | 2024-12-10 | 2 |  | 2024-05-07 | 2024-05-07 |  | 2024-12-18 | 2024-12-18 | 1 |  | 2024-05-08 | 2024-05-09 |  | 2024-12-21 | 2024-12-22 | 2 |  | 2024-06-07 | 2024-06-14 |  | 2024-12-26 | 2024-12-29 | 4 |  | 2024-06-17 | 2024-06-18 |  | 2024-12-30 | 2024-12-30 | 1 | 29 |  | 2024-06-20 | 2024-06-26 |  | 2025-01-07 | 2025-01-19 | 13 |  | 2024-06-20 | 2024-06-26 |  | 2025-01-06 | 2025-01-06 | 1 |  |  |  | 2024-06-14 | 2024-06-28 |  | 2024-12-05 | 2025-01-06 | 33 |  | 2024-04-21 | 2024-04-27 |  | Completed | Completed | #VALUE! |  | 2024-04-21 | 2024-04-27 |  | 2025-01-08 | 2025-01-18 | 11 |  | Odhav | 2024-07-20 | 2024-07-26 |  | 2024-10-26 | 2025-01-05 | 72 |  | 2024-08-14 | 2024-08-19 |  | 2025-01-19 | 2025-01-28 | 10 |  | 2024-08-10 | 2024-08-16 |  | 2024-12-30 | 2025-01-14 | 16 |  | 2024-08-21 | 2024-08-29 |  | 2025-01-30 | 2025-02-04 | 6 |  | 2024-08-30 | 2024-09-01 |  | 2025-02-05 | 2025-02-06 | 2 |  | 2024-08-22 | 2024-08-24 |  | 2025-02-05 | 2025-02-05 | 1 |  | 2024-08-10 | 2024-08-16 |  | 2024-07-28 | 2024-10-15 | 80 |  | 2024-07-25 | 2024-08-09 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-08-24 | 2024-08-27 |  | 2025-02-07 | 2025-02-07 | 1 |  | 2024-09-01 | 2024-09-02 |  | 2025-02-16 | 2025-02-16 | 1 |  |  | 2024-09-01
SHREERAM | 40 | PSS-13 | ARE41L | WTG 355 | Precast | F5 | Sarita infra | Done | 542356 | 2669405 | 2023-12-31 | 2024-01-29 |  | 2023-12-31 | 2024-01-29 |  | 223 | 223 | 2024-04-19 | 2024-04-28 |  | 2024-07-13 | 2024-08-20 | 39 | [8 empty] | 2024-05-04 | 2024-05-04 |  | 2024-12-01 | 2024-12-05 | 5 |  | 2024-05-05 | 2024-05-05 |  | 2024-12-07 | 2024-12-09 | 3 |  | 2024-05-06 | 2024-05-06 |  | 2024-12-09 | 2024-12-09 | 1 |  | 2024-05-07 | 2024-05-08 |  | 2024-12-21 | 2024-12-23 | 3 |  | 2024-06-06 | 2024-06-13 |  | 2024-12-23 | 2024-12-31 | 9 |  | 2024-06-16 | 2024-06-17 |  | 2025-01-06 | 2025-01-08 | 3 | 39 |  | 2024-06-19 | 2024-06-25 |  | 2025-01-15 | 2025-03-01 | 46 |  | 2024-06-19 | 2024-06-25 |  | 2025-01-21 | 2025-01-21 | 1 |  |  |  | 2024-06-13 | 2024-06-27 |  | 2025-01-27 | 2025-01-30 | 4 |  | 2024-04-13 | 2024-04-19 |  | Completed | Completed | #VALUE! |  | 2024-04-13 | 2024-04-19 |  | 2025-01-16 | 2025-01-23 | 8 |  | Odhav | 2024-07-14 | 2024-07-20 |  | 2024-12-15 | 2025-01-16 | 33 |  | 2024-08-13 | 2024-08-18 |  | 2025-01-24 | 2025-02-04 | 12 |  | 2024-08-09 | 2024-08-15 |  | 2025-01-31 | 2025-02-07 | 8 |  | 2024-08-20 | 2024-08-28 |  | 2025-02-06 | 2025-02-10 | 5 |  | 2024-08-29 | 2024-08-31 |  | 2025-02-11 | 2025-02-13 | 3 |  | 2024-08-21 | 2024-08-23 |  | 2025-02-05 | 2025-02-05 | 1 |  | 2024-08-09 | 2024-08-15 |  | 2024-05-12 | 2024-05-22 | 11 |  | 2024-07-25 | 2024-08-09 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-08-23 | 2024-08-26 |  | 2025-02-07 | 2025-02-07 | 1 |  | 2024-08-31 | 2024-09-01 |  | 2025-02-16 | 2025-02-16 | 1 |  |  | 2024-09-01
ABE / SHREE JI | 41 | PSS-13 | ARE41L | WTG 307 | Precast | F4 | Sarita infra | Done | 541061 | 2668001 | 2023-12-26 | 2024-01-27 |  | 2023-12-26 | 2024-01-27 |  | 223 | 223 | 2024-04-09 | 2024-04-18 |  | 2024-10-16 | 2024-10-26 | 11 | [8 empty] | 2024-04-29 | 2024-04-29 |  | 2024-11-09 | 2024-11-14 | 6 |  | 2024-04-30 | 2024-04-30 |  | 2024-11-17 | 2024-11-18 | 2 |  | 2024-05-01 | 2024-05-01 |  | 2024-11-19 | 2024-11-19 | 1 |  | 2024-05-02 | 2024-05-03 |  | 2024-12-02 | 2024-12-03 | 2 |  | 2024-06-03 | 2024-06-10 |  | 2024-12-04 | 2024-12-13 | 10 |  | 2024-06-13 | 2024-06-14 |  | 2024-12-17 | 2024-12-18 | 2 | 40 |  | 2024-06-16 | 2024-06-22 |  | 2024-12-22 | 2025-01-26 | 36 |  | 2024-06-16 | 2024-06-22 |  | 2024-12-24 | 2024-12-24 | 1 |  |  |  | 2024-06-10 | 2024-06-24 |  | 2024-12-13 | 2024-12-19 | 7 |  | 2024-04-13 | 2024-04-19 |  | Completed | Completed | #VALUE! |  | 2024-04-13 | 2024-04-19 |  | Completed | Completed | #VALUE! |  | Odhav | 2024-07-06 | 2024-07-12 |  | 2024-12-26 | 2025-01-02 | 8 |  | 2024-08-05 | 2024-08-06 |  | 2025-01-04 | 2025-01-16 | 13 |  | 2024-08-01 | 2024-08-07 |  | 2024-12-24 | 2025-01-20 | 28 |  | 2024-08-12 | 2024-08-20 |  | 2025-01-20 | 2025-01-25 | 6 |  | 2024-08-21 | 2024-08-23 |  | 2025-01-26 | 2025-01-27 | 2 |  | 2024-08-13 | 2024-08-15 |  | 2025-01-15 | 2025-01-15 | 1 |  | 2024-08-01 | 2024-08-07 |  | 2024-05-16 | 2024-07-22 | 68 |  | 2024-07-25 | 2024-08-09 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-08-15 | 2024-08-18 |  | 2025-01-24 | 2025-01-30 | 7 |  | 2024-08-23 | 2024-08-24 |  | 2025-03-05 | 2025-03-05 | 1 |  |  | 2024-09-01
UNIQUE INF | 42 | PSS-13 | ARE41L | WTG 283 | Precast | F3 | Menard | Done | 540220 | 2668306 | 2024-01-01 | 2024-01-29 |  | 2024-01-01 | 2024-01-29 |  | 211 | 211 | 2024-03-18 | 2024-03-27 |  | 2024-04-16 | 2024-04-24 | 9 | [8 empty] | 2024-04-17 | 2024-04-17 |  | 2024-10-14 | 2024-10-25 | 12 |  | 2024-04-18 | 2024-04-18 |  | 2024-10-28 | 2024-11-06 | 10 |  | 2024-04-19 | 2024-04-19 |  | 2024-11-09 | 2024-11-09 | 1 |  | 2024-04-20 | 2024-04-21 |  | 2024-11-13 | 2024-11-13 | 1 |  | 2024-05-26 | 2024-06-02 |  | 2024-11-14 | 2024-11-26 | 13 |  | 2024-06-05 | 2024-06-06 |  | 2024-11-27 | 2024-11-28 | 2 | 46 |  | 2024-06-08 | 2024-06-14 |  | 2024-12-09 | 2025-01-28 | 51 |  | 2024-06-08 | 2024-06-14 |  | 2024-12-05 | 2024-12-05 | 1 |  |  |  | 2024-06-02 | 2024-06-16 |  | 2024-12-08 | 2024-12-11 | 4 |  | 2024-03-28 | 2024-04-03 |  | Completed | Completed | #VALUE! |  | 2024-03-28 | 2024-04-03 |  | Completed | Completed | #VALUE! |  | SS Jadeja | 2024-06-20 | 2024-06-26 |  | 2024-11-22 | 2024-12-22 | 31 |  | 2024-07-18 | 2024-07-23 |  | 2024-12-23 | 2025-01-02 | 11 |  | 2024-07-09 | 2024-07-15 |  | 2024-12-17 | 2025-01-08 | 23 |  | 2024-07-25 | 2024-08-02 |  | 2025-01-08 | 2025-01-19 | 12 |  | 2024-08-03 | 2024-08-05 |  | 2025-01-18 | 2025-01-20 | 3 |  | 2024-07-21 | 2024-07-23 |  | 2025-01-04 | 2025-01-04 | 1 |  | 2024-07-09 | 2024-07-15 |  | 2024-05-25 | 2024-05-31 | 7 |  | 2024-07-01 | 2024-07-16 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-07-23 | 2024-07-26 |  | 2025-01-13 | 2025-01-21 | 9 |  | 2024-08-05 | 2024-08-06 |  | 2025-02-15 | 2025-02-16 | 2 |  |  | 2024-09-01
MSC/SHREE JI | 43 | PSS-13 | ARE41L | WTG 356 | Precast | F4 | Bauer | Done | 542546 | 2668419 | 2023-12-26 | 2024-01-27 |  | 2023-12-26 | 2024-01-27 |  | 211 | 211 | 2024-04-21 | 2024-04-30 |  | 2024-04-29 | 2024-05-04 | 6 | [8 empty] | 2024-05-06 | 2024-05-06 |  | 2024-07-13 | 2024-07-17 | 5 |  | 2024-05-07 | 2024-05-07 |  | 2025-01-08 | 2025-01-09 | 2 | Sludge removing WIP | 2024-05-08 | 2024-05-08 |  | 2025-01-09 | 2025-01-09 | 1 |  | 2024-05-09 | 2024-05-10 |  | 2025-01-12 | 2025-01-12 | 1 |  | 2024-06-08 | 2024-06-15 |  | 2025-01-13 | 2025-01-18 | 6 |  | 2024-06-18 | 2024-06-19 |  | 2025-01-20 | 2025-01-20 | 1 | 192 |  | 2024-06-21 | 2024-06-27 |  | 2025-01-24 | 2025-02-20 | 28 |  | 2024-06-21 | 2024-06-27 |  | 2025-01-28 | 2025-01-28 | 1 |  |  |  | 2024-06-15 | 2024-06-29 |  | 2025-01-30 | 2025-02-07 | 9 |  | 2024-04-21 | 2024-04-27 |  | 2024-03-03 | 2024-03-11 | 9 |  | 2024-04-21 | 2024-04-27 |  | 2025-01-22 | 2025-02-05 | 15 |  | Odhav | 2024-07-21 | 2024-07-27 |  | 2024-11-12 | 2025-02-03 | 84 |  | 2024-08-12 | 2024-08-17 |  | 2025-02-06 | 2025-02-20 | 15 |  | 2024-08-11 | 2024-08-17 |  | 2025-02-07 | 2025-02-13 | 7 |  | 2024-08-19 | 2024-08-27 |  | 2025-02-23 | 2025-02-27 | 5 |  | 2024-08-28 | 2024-08-30 |  | 2025-02-28 | 2025-03-01 | 2 |  | 2024-08-23 | 2024-08-25 |  | 2025-02-26 | 2025-02-26 | 1 |  | 2024-08-11 | 2024-08-17 |  | 2024-05-16 | 2024-05-24 | 9 |  | 2024-07-25 | 2024-08-09 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-08-25 | 2024-08-28 |  | 2025-02-28 | 2025-03-03 | 4 |  | 2024-08-30 | 2024-08-31 |  | 2025-03-07 | 2025-03-07 | 1 |  |  | 2024-09-01
MSC | 44 | PSS-13 | ARE41L | WTG 259 | FDN | F3 | Sarita infra | Done | 539386 | 2668570 | 2024-01-02 | 2024-01-29 |  | 2024-01-02 | 2024-01-29 |  | 253 | 253 | 2024-04-18 | 2024-04-27 |  | 2024-08-22 | 2024-10-07 | 47 |  | Yes | 2024-10-17 | 2024-10-24 |  | 2024-10-14 | 2024-11-23 |  | 2024-05-03 | 2024-05-03 |  | 2024-12-05 | 2024-12-07 | 3 |  | 2024-05-04 | 2024-05-04 |  | 2024-12-07 | 2024-12-07 | 1 |  | 2024-05-05 | 2024-05-05 |  | 2024-12-08 | 2024-12-08 | 1 |  | 2024-05-06 | 2024-05-07 |  | 2024-12-09 | 2024-12-09 | 1 |  | 2024-06-05 | 2024-06-12 |  | 2024-12-21 | 2024-12-24 | 4 |  | 2024-06-15 | 2024-06-16 |  | 2024-12-24 | 2024-12-25 | 2 | 21 |  | 2024-06-18 | 2024-06-24 |  | 2025-01-01 | 2025-01-28 | 28 |  | 2024-06-18 | 2024-06-24 |  | 2024-12-31 | 2024-12-31 | 1 |  |  |  | 2024-06-12 | 2024-06-26 |  | 2024-12-07 | 2024-12-12 | 6 |  | 2024-04-13 | 2024-04-19 |  | Completed | Completed | #VALUE! |  | 2024-04-13 | 2024-04-19 |  | 2025-01-02 | 2025-01-08 | 7 |  | Odhav | 2024-07-13 | 2024-07-19 |  | 2024-12-29 | 2025-01-07 | 10 |  | 2024-08-05 | 2024-08-10 |  | 2025-01-09 | 2025-01-20 | 12 |  | 2024-08-03 | 2024-08-09 |  | 2024-12-20 | 2025-01-15 | 27 |  | 2024-08-12 | 2024-08-20 |  | 2025-01-23 | 2025-02-04 | 13 |  | 2024-08-21 | 2024-08-23 |  | 2025-02-05 | 2025-02-06 | 2 |  | 2024-08-15 | 2024-08-17 |  | 2025-01-13 | 2025-01-13 | 1 |  | 2024-08-03 | 2024-08-09 |  | 2024-05-25 | 2024-05-31 | 7 |  | 2024-07-25 | 2024-08-09 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-08-17 | 2024-08-20 |  | 2025-01-15 | 2025-01-21 | 7 |  | 2024-08-23 | 2024-08-24 |  | 2025-02-15 | 2025-02-16 | 2 |  |  | 2024-09-01
SHREEJI | 45 | PSS-13 | ARE41L | WTG 331 | Precast | F4 | Bauer | Done | 541705 | 2668723 | 2023-12-26 | 2024-01-27 |  | 2023-12-26 | 2024-01-27 |  | 211 | 211 | 2024-04-07 | 2024-04-16 |  | 2024-05-06 | 2024-05-21 | 16 | [8 empty] | 2024-04-27 | 2024-04-27 |  | 2024-06-22 | 2024-06-28 | 7 |  | 2024-04-28 | 2024-04-28 |  | 2024-12-02 | 2024-12-04 | 3 |  | 2024-04-29 | 2024-04-29 |  | 2024-12-10 | 2024-12-10 | 1 |  | 2024-04-30 | 2024-05-01 |  | 2024-12-14 | 2024-12-15 | 2 |  | 2024-06-01 | 2024-06-08 |  | 2024-12-15 | 2024-12-26 | 12 |  | 2024-06-11 | 2024-06-12 |  | 2024-12-27 | 2024-12-28 | 2 | 190 |  | 2024-06-14 | 2024-06-20 |  | 2025-01-06 | 2025-01-31 | 26 |  | 2024-06-14 | 2024-06-20 |  | 2025-01-04 | 2025-01-04 | 1 |  |  |  | 2024-06-08 | 2024-06-22 |  | 2024-12-09 | 2024-12-26 | 18 |  | 2024-04-13 | 2024-04-19 |  | Completed | Completed | #VALUE! |  | 2024-04-13 | 2024-04-19 |  | 2025-01-05 | 2025-01-13 | 9 |  | Odhav | 2024-07-04 | 2024-07-10 |  | 2024-10-26 | 2024-12-27 | 63 |  | 2024-07-27 | 2024-08-01 |  | 2025-01-14 | 2025-01-27 | 14 |  | 2024-07-25 | 2024-07-31 |  | 2024-12-30 | 2025-01-28 | 30 |  | 2024-08-03 | 2024-08-11 |  | 2025-01-30 | 2025-02-05 | 7 |  | 2024-08-12 | 2024-08-14 |  | 2025-02-06 | 2025-02-07 | 2 |  | 2024-08-06 | 2024-08-08 |  | 2025-01-14 | 2025-01-14 | 1 |  | 2024-07-25 | 2024-07-31 |  | 2024-06-16 | 2024-08-17 | 63 |  | 2024-07-25 | 2024-08-09 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-08-08 | 2024-08-11 |  | 2025-01-15 | 2025-01-30 | 16 |  | 2024-08-14 | 2024-08-15 |  | 2025-03-05 | 2025-03-05 | 1 |  |  | 2024-09-01
SHREEJI | 46 | PSS-13 | ARE41L | WTG 330 | Precast | F5 | Menard | Done | 541515 | 2669709 | 2023-12-29 | 2024-01-28 |  | 2023-12-29 | 2024-01-28 |  | 253 | 253 | 2024-04-08 | 2024-04-17 |  | 2024-05-06 | 2024-05-24 | 19 | [8 empty] | 2024-04-28 | 2024-04-28 |  | 2024-06-04 | 2024-06-13 | 10 |  | 2024-04-29 | 2024-04-29 |  | 2024-06-14 | 2024-06-16 | 3 |  | 2024-04-30 | 2024-04-30 |  | 2024-06-20 | 2024-06-20 | 1 |  | 2024-05-01 | 2024-05-02 |  | 2024-11-20 | 2024-11-22 | 3 |  | 2024-06-02 | 2024-06-09 |  | 2024-11-23 | 2024-12-03 | 11 |  | 2024-06-12 | 2024-06-13 |  | 2024-12-05 | 2024-12-06 | 2 | 186 |  | 2024-06-15 | 2024-06-21 |  | 2024-12-16 | 2025-01-29 | 45 |  | 2024-06-15 | 2024-06-21 |  | 2024-12-18 | 2024-12-18 | 1 |  |  |  | 2024-06-09 | 2024-06-23 |  | 2024-12-16 | 2024-12-22 | 7 |  | 2024-04-13 | 2024-04-19 |  | Completed | Completed | #VALUE! |  | 2024-04-13 | 2024-04-19 |  | 2024-12-20 | 2024-12-28 | 9 |  | HARSH | 2024-07-05 | 2024-07-11 |  | 2024-12-08 | 2025-01-01 | 25 |  | 2024-08-04 | 2024-08-09 |  | 2025-01-01 | 2025-01-16 | 16 |  | 2024-07-26 | 2024-08-01 |  | 2024-12-23 | 2025-01-09 | 18 |  | 2024-08-11 | 2024-08-19 |  | 2025-01-20 | 2025-01-28 | 9 |  | 2024-08-20 | 2024-08-22 |  | 2025-01-30 | 2025-01-31 | 2 |  | 2024-08-07 | 2024-08-09 |  | 2025-01-12 | 2025-01-12 | 1 |  | 2024-07-26 | 2024-08-01 |  | 2024-06-12 | 2024-11-05 | 147 |  | 2024-07-25 | 2024-08-09 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-08-09 | 2024-08-12 |  | 2025-01-15 | 2025-01-29 | 15 |  | 2024-08-22 | 2024-08-23 |  | 2025-02-15 | 2025-02-16 | 2 |  |  | 2024-09-01
MECC | 47 | PSS-13 | ARE41L | WTG 305 | FDN | F5 | Sarita infra | Done | 540681 | 2669974 | 2023-12-31 | 2024-01-28 |  | 2023-12-31 | 2024-01-28 |  | 211 | 211 | 2024-04-10 | 2024-04-19 |  | 2024-06-22 | 2024-07-06 | 15 | [8 empty] | 2024-04-30 | 2024-04-30 |  | 2024-11-15 | 2024-11-20 | 6 |  | 2024-05-01 | 2024-05-01 |  | 2024-12-06 | 2024-12-08 | 3 |  | 2024-05-02 | 2024-05-02 |  | 2024-12-09 | 2024-12-09 | 1 |  | 2024-05-03 | 2024-05-04 |  | 2024-12-11 | 2024-12-12 | 2 |  | 2024-06-04 | 2024-06-11 |  | 2024-12-13 | 2024-12-29 | 17 |  | 2024-06-14 | 2024-06-15 |  | 2024-12-30 | 2025-01-01 | 3 | 48 |  | 2024-06-17 | 2024-06-23 |  | 2025-01-07 | 2025-02-27 | 52 |  | 2024-06-17 | 2024-06-23 |  | 2025-01-12 | 2025-01-12 | 1 |  |  |  | 2024-06-11 | 2024-06-25 |  | 2024-12-08 | 2024-12-23 | 16 |  | 2024-04-13 | 2024-04-19 |  | Completed | Completed | #VALUE! |  | 2024-04-13 | 2024-04-19 |  | 2025-01-04 | 2025-01-12 | 9 |  | Vipin | 2024-07-12 | 2024-07-18 |  | 2024-05-10 | 2024-06-09 | 31 |  | 2024-08-03 | 2024-08-08 |  | 2025-01-18 | 2025-01-28 | 11 |  | 2024-08-02 | 2024-08-08 |  | 2024-12-28 | 2025-01-14 | 18 |  | 2024-08-10 | 2024-08-18 |  | 2025-02-03 | 2025-02-06 | 4 |  | 2024-08-19 | 2024-08-21 |  | 2025-02-07 | 2025-02-10 | 4 |  | 2024-08-14 | 2024-08-16 |  | 2025-01-11 | 2025-01-11 | 1 |  | 2024-08-02 | 2024-08-08 |  | 2024-05-12 | 2024-05-25 | 14 |  | 2024-07-25 | 2024-08-09 |  | 2024-11-30 | 2024-12-28 | 29 |  | 2024-08-16 | 2024-08-19 |  | 2025-01-15 | 2025-01-29 | 15 |  | 2024-08-21 | 2024-08-22 |  | 2025-02-15 | 2025-02-16 | 2 | Issue in gear box |  | 2024-09-01
MSC | 48 | PSS-4 | AKPL | WTG 147 | Precast | F14 | Sarita infra | Done | 535196 | 2670013 | 2023-06-03 | 2023-06-04 |  | 2023-06-03 | 2023-06-04 |  | 219 | 219 | 2024-02-28 | 2024-03-08 |  | 2023-10-04 | 2023-10-20 | 17 | [8 empty] | 2024-07-23 | 2024-07-23 |  | 2024-11-19 | 2024-11-21 | 3 |  | 2024-07-24 | 2024-07-24 |  | 2024-11-21 | 2024-11-22 | 2 |  | 2024-07-25 | 2024-07-25 |  | 2024-11-22 | 2024-11-22 | 1 |  | 2024-07-26 | 2024-07-27 |  | 2024-11-28 | 2024-11-28 | 1 |  | 2024-07-29 | 2024-08-07 |  | 2024-12-01 | 2024-12-07 | 7 |  | 2024-08-10 | 2024-08-11 |  | 2024-12-08 | 2024-12-08 | 1 | 20 |  | 2024-08-12 | 2024-08-18 |  | 2024-12-10 | 2025-02-28 | 81 |  | 2024-08-12 | 2024-08-18 |  | 2024-12-11 | 2024-12-11 | 1 |  |  |  | 2024-08-05 | 2024-08-19 |  | 2024-11-22 | 2025-01-27 | 67 |  | 2024-08-08 | 2024-08-14 |  | Completed | Completed | #VALUE! |  | 2024-08-08 | 2024-08-14 |  | Completed | Completed | #VALUE! |  | Vaibhav | 2024-08-15 | 2024-08-21 |  | 2024-12-14 | 2024-12-23 | 10 |  | 2024-09-02 | 2024-09-07 |  | 2024-12-17 | 2025-01-13 | 28 |  | 2024-09-08 | 2024-09-14 |  | 2025-01-29 | 2025-03-06 | 37 |  | 2024-09-10 | 2024-09-19 |  | 2025-02-27 | 2025-03-07 | 9 |  | 2024-09-21 | 2024-09-23 |  | 2025-03-08 | 2025-03-13 | 6 | Loc. Hold | 2024-09-20 | 2024-09-21 |  | 2025-03-05 | 2025-03-05 | 1 |  | 2024-09-04 | 2024-09-10 |  | 2024-12-12 | 2025-01-31 | 51 |  | 2024-09-12 | 2024-09-27 |  | 2025-01-01 | 2025-02-06 | 37 |  | 2024-09-21 | 2024-09-24 |  | 2025-03-10 | 2025-03-11 | 2 |  | 2024-09-27 | 2024-09-28 |  | 2025-03-11 | 2025-03-13 | 3 |  |  | 2024-12-01
DNC | 49 | PSS-4 | AGE24L | WTG 072 | Precast | F12 | Sarita infra | Done | 532037 | 2670165 | 2023-06-07 | 2023-06-08 |  | 2023-06-07 | 2023-06-08 |  | 163 | 163 | 2024-05-28 | 2024-06-06 |  | 2024-05-21 | 2024-06-25 | 36 | [8 empty] | 2024-09-14 | 2024-09-14 |  | 2024-10-19 | 2024-10-20 | 2 |  | 2024-09-15 | 2024-09-15 |  | 2024-10-23 | 2024-10-24 | 2 |  | 2024-09-16 | 2024-09-16 |  | 2024-10-25 | 2024-10-25 | 1 |  | 2024-09-17 | 2024-09-18 |  | 2024-10-29 | 2024-10-30 | 2 |  | 2024-09-20 | 2024-09-29 |  | 2024-11-04 | 2024-11-26 | 23 |  | 2024-10-10 | 2024-10-11 |  | 2024-11-27 | 2024-11-27 | 1 | 40 |  | 2024-10-12 | 2024-10-18 |  | 2024-12-08 | 2025-03-10 | 93 |  | 2024-10-12 | 2024-10-18 |  | 2024-12-19 | 2024-12-19 | 1 |  |  |  | 2024-09-27 | 2024-10-11 |  | 2025-01-14 | 2025-01-17 | 4 |  | 2024-09-09 | 2024-09-15 |  | Completed | Completed | #VALUE! |  | 2024-09-09 | 2024-09-15 |  | Completed | Completed | #VALUE! |  | GP | 2024-09-16 | 2024-09-22 |  | 2024-12-06 | 2024-12-17 | 12 |  | 2024-11-02 | 2024-11-07 |  | 2024-12-26 | 2025-01-04 | 10 |  | 2024-10-19 | 2024-10-25 |  | 2025-01-24 | 2025-02-23 | 31 |  | 2024-11-10 | 2024-11-19 |  | 2025-02-16 | 2025-02-20 | 5 |  | 2024-11-21 | 2024-11-23 |  | 2025-02-21 | 2025-02-23 | 3 |  | 2024-10-31 | 2024-11-01 |  | 2025-02-25 | 2025-02-25 | 1 |  | 2024-10-19 | 2024-10-25 |  | 2024-12-11 | 2024-12-12 | 2 |  | 2024-11-01 | 2024-11-16 |  | 2024-12-16 | 2025-01-09 | 25 |  | 2024-11-01 | 2024-11-04 |  | 2025-03-07 | 2025-03-09 | 3 |  | 2024-11-23 | 2024-11-24 |  | 2025-03-10 | 2025-03-11 | 2 |  |  | 2024-12-01
AB INFRA | 50 | PSS-4 | AKPL | WTG 146 | Precast | F14 | Sarita infra | Done | 535006 | 2670999 | 2023-06-04 | 2023-06-05 |  | 2023-06-04 | 2023-06-05 |  | 163 | 163 | 2024-03-08 | 2024-03-17 |  | 2023-12-11 | 2023-12-21 | 11 | [8 empty] | 2024-07-29 | 2024-07-29 |  | 2024-10-11 | 2024-10-13 | 3 |  | 2024-07-30 | 2024-07-30 |  | 2024-10-14 | 2024-10-18 | 5 |  | 2024-07-31 | 2024-07-31 |  | 2024-10-18 | 2024-10-19 | 2 |  | 2024-08-01 | 2024-08-02 |  | 2024-10-21 | 2024-10-22 | 2 |  | 2024-08-04 | 2024-08-13 |  | 2024-10-24 | 2024-12-10 | 48 |  | 2024-08-16 | 2024-08-17 |  | 2024-12-14 | 2024-12-15 | 2 | 66 |  | 2024-08-18 | 2024-08-24 |  | 2024-12-28 | 2025-03-11 | 74 |  | 2024-08-18 | 2024-08-24 |  | 2024-12-26 | 2024-12-26 | 1 |  |  |  | 2024-08-11 | 2024-08-25 |  | 2024-10-20 | 2025-02-01 | 105 |  | 2024-08-16 | 2024-08-22 |  | Completed | Completed | #VALUE! |  | 2024-08-16 | 2024-08-22 |  | Completed | Completed | #VALUE! |  | SS Jadeja | 2024-08-23 | 2024-08-29 |  | 2024-11-09 | 2024-12-08 | 30 |  | 2024-09-11 | 2024-09-16 |  | 2024-12-04 | 2025-02-03 | 62 |  | 2024-09-07 | 2024-09-13 |  | 2025-02-13 | 2025-03-05 | 21 |  | 2024-09-19 | 2024-09-28 |  | 2025-02-10 | 2025-02-16 | 7 |  | 2024-09-30 | 2024-10-02 |  | 2025-02-17 | 2025-02-18 | 2 |  | 2024-09-19 | 2024-09-20 |  | 2025-03-05 | 2025-03-05 | 1 |  | 2024-09-04 | 2024-09-10 |  | 2024-11-30 | 2025-02-15 | 78 |  | 2024-09-12 | 2024-09-27 |  | 2025-01-01 | 2025-02-06 | 37 |  | 2024-09-20 | 2024-09-23 |  | 2025-03-10 | 2025-03-11 | 2 |  | 2024-10-02 | 2024-10-03 |  | 2025-03-11 | 2025-03-13 | 3 |  |  | 2024-12-01
AB INFRA | 51 | PSS-4 | AKPL | WTG 125 | Precast | F14 | Sarita infra | Done | 534362 | 2670278 | 2023-06-05 | 2023-06-06 |  | 2023-06-05 | 2023-06-06 |  | 199 | 199 | 2024-03-09 | 2024-03-18 |  | 2023-10-21 | 2023-11-02 | 13 | [8 empty] | 2024-07-29 | 2024-07-29 |  | 2024-10-23 | 2024-10-25 | 3 |  | 2024-07-30 | 2024-07-30 |  | 2024-11-04 | 2024-11-06 | 3 |  | 2024-07-31 | 2024-07-31 |  | 2024-11-06 | 2024-11-06 | 1 |  | 2024-08-01 | 2024-08-02 |  | 2024-11-08 | 2024-11-10 | 3 |  | 2024-08-04 | 2024-08-13 |  | 2024-11-19 | 2024-12-09 | 21 |  | 2024-08-16 | 2024-08-17 |  | 2024-12-09 | 2024-12-10 | 2 | 49 |  | 2024-08-18 | 2024-08-24 |  | 2024-12-13 | 2025-02-16 | 66 |  | 2024-08-18 | 2024-08-24 |  | 2024-12-20 | 2024-12-20 | 1 |  |  |  | 2024-08-11 | 2024-08-25 |  | 2024-12-23 | 2025-01-25 | 34 |  | 2024-08-16 | 2024-08-22 |  | Completed | Completed | #VALUE! |  | 2024-08-16 | 2024-08-22 |  | Completed | Completed | #VALUE! |  | Vaibhav | 2024-08-23 | 2024-08-29 |  | 2024-11-20 | 2024-12-23 | 34 |  | 2024-09-11 | 2024-09-16 |  | 2024-12-17 | 2025-01-07 | 22 |  | 2024-09-08 | 2024-09-14 |  | 2025-01-28 | 2025-02-28 | 32 |  | 2024-09-19 | 2024-09-28 |  | 2025-02-11 | 2025-02-17 | 7 |  | 2024-09-30 | 2024-10-02 |  | 2025-02-18 | 2025-02-20 | 3 |  | 2024-09-20 | 2024-09-21 |  | 2025-03-05 | 2025-03-05 | 1 |  | 2024-09-04 | 2024-09-10 |  | 2024-12-31 | 2025-02-15 | 47 |  | 2024-09-12 | 2024-09-27 |  | 2025-01-01 | 2025-02-06 | 37 |  | 2024-09-21 | 2024-09-24 |  | 2025-03-10 | 2025-03-11 | 2 |  | 2024-10-02 | 2024-10-03 |  | 2025-03-11 | 2025-03-13 | 3 |  |  | 2024-12-01
MSC | 52 | PSS-4 | AKPL | WTG 126 | Precast | F14 | Sarita infra | Done | 534552 | 2669291 | 2023-06-05 | 2023-06-06 |  | 2023-06-05 | 2023-06-06 |  | 199 | 199 | 2024-03-10 | 2024-03-19 |  | 2023-11-01 | 2023-11-11 | 11 | [8 empty] | 2024-07-29 | 2024-07-29 |  | 2024-11-22 | 2024-11-23 | 2 |  | 2024-07-30 | 2024-07-30 |  | 2024-11-23 | 2024-11-24 | 2 |  | 2024-07-31 | 2024-07-31 |  | 2024-11-24 | 2024-11-24 | 1 |  | 2024-08-01 | 2024-08-02 |  | 2024-12-05 | 2024-12-05 | 1 |  | 2024-08-04 | 2024-08-13 |  | 2024-12-06 | 2024-12-12 | 7 |  | 2024-08-16 | 2024-08-17 |  | 2024-12-13 | 2024-12-14 | 2 | 23 |  | 2024-08-18 | 2024-08-24 |  | 2024-12-17 | 2025-02-27 | 73 |  | 2024-08-18 | 2024-08-24 |  | 2024-12-18 | 2024-12-18 | 1 |  |  |  | 2024-08-11 | 2024-08-25 |  | 2024-11-23 | 2025-02-04 | 74 |  | 2024-08-16 | 2024-08-22 |  | Completed | Completed | #VALUE! |  | 2024-08-16 | 2024-08-22 |  | 2025-01-01 | 2025-01-08 | 8 |  | GP | 2024-08-23 | 2024-08-29 |  | 2024-12-24 | 2024-12-29 | 6 |  | 2024-09-11 | 2024-09-16 |  | 2025-01-17 | 2025-01-26 | 10 |  | 2024-09-16 | 2024-09-22 |  | 2025-02-08 | 2025-03-04 | 25 |  | 2024-09-19 | 2024-09-28 |  | 2025-02-05 | 2025-02-13 | 9 |  | 2024-09-30 | 2024-10-02 |  | 2025-02-14 | 2025-02-20 | 7 | Hold due to non available of material | 2024-09-28 | 2024-09-29 |  | 2025-03-05 | 2025-03-05 | 1 |  | 2024-09-12 | 2024-09-18 |  | 2024-12-21 | 2024-12-23 | 3 |  | 2024-09-12 | 2024-09-27 |  | 2025-01-01 | 2025-02-06 | 37 |  | 2024-09-29 | 2024-10-02 |  | 2025-03-10 | 2025-03-11 | 2 |  | 2024-10-02 | 2024-10-03 |  | 2025-03-11 | 2025-03-13 | 3 |  |  | 2024-12-01
ODHAV | 53 | PSS-4 | AKPL | WTG 108 | Precast | F13 | Sarita infra | Done | 533711 | 2669596 | 2023-06-05 | 2023-06-06 |  | 2023-06-05 | 2023-06-06 |  | 219 | 219 | 2024-03-11 | 2024-03-20 |  | 2023-12-27 | 2024-01-25 | 30 | [8 empty] | 2024-07-29 | 2024-07-29 |  | 2024-11-12 | 2024-11-14 | 3 |  | 2024-07-30 | 2024-07-30 |  | 2024-11-18 | 2024-11-24 | 7 |  | 2024-07-31 | 2024-07-31 |  | 2024-11-25 | 2024-11-25 | 1 |  | 2024-08-01 | 2024-08-02 |  | 2024-12-06 | 2024-12-07 | 2 |  | 2024-08-04 | 2024-08-13 |  | 2024-12-16 | 2025-01-06 | 22 |  | 2024-08-16 | 2024-08-17 |  | 2025-01-07 | 2025-01-08 | 2 | 58 |  | 2024-08-18 | 2024-08-24 |  | 2025-01-16 | 2025-03-29 | 73 |  | 2024-08-18 | 2024-08-24 |  | 2025-01-22 | 2025-01-22 | 1 |  |  |  | 2024-08-11 | 2024-08-25 |  | 2025-02-01 | 2025-02-04 | 4 |  | 2024-08-16 | 2024-08-22 |  | Completed | Completed | #VALUE! |  | 2024-08-16 | 2024-08-22 |  | 2025-01-02 | 2025-01-12 | 11 |  | GP | 2024-08-23 | 2024-08-29 |  | 2024-12-22 | 2024-12-31 | 10 |  | 2024-09-11 | 2024-09-16 |  | 2025-02-12 | 2025-02-20 | 9 |  | 2024-09-15 | 2024-09-21 |  | 2025-02-13 | 2025-03-02 | 18 |  | 2024-09-19 | 2024-09-28 |  | 2025-03-02 | 2025-03-06 | 5 |  | 2024-09-30 | 2024-10-02 |  | 2025-03-07 | 2025-03-13 | 7 | Loc. Hold | 2024-09-27 | 2024-09-28 |  | 2025-03-06 | 2025-03-06 | 1 |  | 2024-09-12 | 2024-09-18 |  | 2024-12-19 | 2025-01-03 | 16 |  | 2024-09-12 | 2024-09-27 |  | 2025-01-01 | 2025-02-06 | 37 |  | 2024-09-28 | 2024-10-01 |  | 2025-03-10 | 2025-03-11 | 2 |  | 2024-10-02 | 2024-10-03 |  | 2025-03-12 | 2025-03-14 | 3 |  |  | 2024-12-01
ODHAV | 54 | PSS-4 | AKPL | WTG 107 | FDN | F13 | Sarita infra | Done | 533522 | 2670582 | 2023-06-06 | 2023-06-07 |  | 2023-06-06 | 2023-06-07 |  | 163 | 163 | 2024-03-20 | 2024-03-29 |  | 2023-11-03 | 2023-11-11 | 9 | [8 empty] | 2024-08-04 | 2024-08-04 |  | 2024-11-08 | 2024-11-12 | 5 |  | 2024-08-05 | 2024-08-05 |  | 2024-11-18 | 2024-11-24 | 7 |  | 2024-08-06 | 2024-08-06 |  | 2024-11-28 | 2024-11-28 | 1 |  | 2024-08-07 | 2024-08-08 |  | 2024-12-21 | 2024-12-21 | 1 | No techincal staff available | 2024-08-10 | 2024-08-19 |  | 2025-01-10 | 2025-01-20 | 11 |  | 2024-08-22 | 2024-08-23 |  | 2025-01-21 | 2025-01-21 | 1 | 75 |  | 2024-08-24 | 2024-08-30 |  | 2025-01-26 | 2025-03-28 | 62 |  | 2024-08-24 | 2024-08-30 |  | 2025-01-31 | 2025-01-31 | 1 |  |  |  | 2024-08-17 | 2024-08-31 |  | 2024-12-08 | 2025-02-20 | 75 |  | 2024-08-24 | 2024-08-30 |  | Completed | Completed | #VALUE! |  | 2024-08-24 | 2024-08-30 |  | Completed | Completed | #VALUE! |  | Vaibhav | 2024-08-31 | 2024-09-06 |  | 2024-11-24 | 2025-01-10 | 48 |  | 2024-09-20 | 2024-09-25 |  | 2025-02-02 | 2025-02-09 | 8 |  | 2024-09-16 | 2024-09-22 |  | 2025-02-23 | 2025-03-02 | 8 |  | 2024-09-28 | 2024-10-07 |  | 2025-02-19 | 2025-03-01 | 11 |  | 2024-10-09 | 2024-10-11 |  | 2025-03-02 | 2025-03-04 | 3 |  | 2024-09-28 | 2024-09-29 |  | 2025-03-06 | 2025-03-06 | 1 |  | 2024-09-12 | 2024-09-18 |  | 2025-01-02 | 2025-02-02 | 32 |  | 2024-09-12 | 2024-09-27 |  | 2025-01-01 | 2025-02-06 | 37 |  | 2024-09-29 | 2024-10-02 |  | 2025-03-10 | 2025-03-11 | 2 |  | 2024-10-11 | 2024-10-12 |  | 2025-03-12 | 2025-03-14 | 3 |  |  | 2024-12-01
MSC | 55 | PSS-4 | AKPL | WTG 106 | Precast | F13 | Sarita infra | Done | 533332 | 2671568 | 2024-01-06 | 2024-01-30 |  | 2024-01-06 | 2024-01-30 |  | 253 | 253 | 2024-03-21 | 2024-03-30 |  | 2024-06-27 | 2024-07-13 | 17 | [8 empty] | 2024-08-04 | 2024-08-04 |  | 2024-11-13 | 2024-11-15 | 3 |  | 2024-08-05 | 2024-08-05 |  | 2024-11-24 | 2024-11-25 | 2 |  | 2024-08-06 | 2024-08-06 |  | 2024-11-27 | 2024-11-27 | 1 |  | 2024-08-07 | 2024-08-08 |  | 2024-12-07 | 2024-12-08 | 2 |  | 2024-08-10 | 2024-08-19 |  | 2024-12-12 | 2024-12-16 | 5 |  | 2024-08-22 | 2024-08-23 |  | 2024-12-16 | 2024-12-16 | 1 | 34 |  | 2024-08-24 | 2024-08-30 |  | 2024-12-19 | 2025-03-13 | 85 |  | 2024-08-24 | 2024-08-30 |  | 2024-12-21 | 2024-12-21 | 1 |  |  |  | 2024-08-17 | 2024-08-31 |  | 2024-11-25 | 2025-02-23 | 91 |  | 2024-08-24 | 2024-08-30 |  | Completed | Completed | #VALUE! |  | 2024-08-24 | 2024-08-30 |  | 2024-12-25 | 2025-01-03 | 10 |  | GP | 2024-08-31 | 2024-09-06 |  | 2024-12-23 | 2024-12-31 | 9 |  | 2024-09-20 | 2024-09-25 |  | 2025-01-16 | 2025-01-24 | 9 |  | 2024-09-24 | 2024-09-30 |  | 2025-02-28 | 2025-03-04 | 5 |  | 2024-09-28 | 2024-10-07 |  | 2025-02-22 | 2025-03-05 | 12 |  | 2024-10-09 | 2024-10-11 |  | 2025-03-06 | 2025-03-08 | 3 |  | 2024-10-06 | 2024-10-07 |  | 2025-03-05 | 2025-03-05 | 1 |  | 2024-09-20 | 2024-09-26 |  | 2024-12-11 | 2025-02-04 | 56 |  | 2024-09-12 | 2024-09-27 |  | 2025-01-01 | 2025-02-06 | 37 |  | 2024-10-07 | 2024-10-10 |  | 2025-03-10 | 2025-03-11 | 2 |  | 2024-10-11 | 2024-10-12 |  | 2025-03-12 | 2025-03-14 | 3 |  |  | 2024-12-01
DNC | 56 | PSS-4 | AKPL | WTG 089 | Precast | F13 | Sarita infra | Done | 532688 | 2670847 | 2023-06-06 | 2023-06-07 |  | 2023-06-06 | 2023-06-07 |  | 163 | 163 | 2024-02-27 | 2024-03-07 |  | 2023-11-16 | 2023-11-25 | 10 | [8 empty] | 2024-07-23 | 2024-07-23 |  | 2024-05-10 | 2024-05-12 | 3 |  | 2024-07-24 | 2024-07-24 |  | 2024-05-14 | 2024-05-16 | 3 |  | 2024-07-25 | 2024-07-25 |  | 2024-05-18 | 2024-05-18 | 1 |  | 2024-07-26 | 2024-07-27 |  | 2024-10-23 | 2024-10-23 | 1 |  | 2024-07-29 | 2024-08-07 |  | 2024-10-26 | 2024-11-11 | 17 |  | 2024-08-10 | 2024-08-11 |  | 2024-11-13 | 2024-11-13 | 1 | 188 |  | 2024-08-12 | 2024-08-18 |  | 2024-11-26 | 2025-03-13 | 108 |  | 2024-08-12 | 2024-08-18 |  | 2024-11-24 | 2024-11-24 | 1 |  |  |  | 2024-08-05 | 2024-08-19 |  | 2024-11-27 | 2025-01-30 | 65 |  | 2024-08-08 | 2024-08-14 |  | Completed | Completed | #VALUE! |  | 2024-08-08 | 2024-08-14 |  | 2024-10-26 | 2024-11-29 | 35 |  | GP | 2024-08-15 | 2024-08-21 |  | 2024-10-26 | 2024-11-29 | 35 |  | 2024-09-02 | 2024-09-07 |  | 2024-12-16 | 2024-12-25 | 10 |  | 2024-08-31 | 2024-09-06 |  | 2025-02-09 | 2025-03-05 | 25 |  | 2024-09-10 | 2024-09-19 |  | 2025-01-26 | 2025-02-02 | 8 |  | 2024-09-21 | 2024-09-23 |  | 2025-02-02 | 2025-02-04 | 3 |  | 2024-09-12 | 2024-09-13 |  | 2025-03-08 | 2025-03-08 | 1 |  | 2024-08-27 | 2024-09-02 |  | 2024-12-31 | 2025-02-14 | 46 |  | 2024-09-12 | 2024-09-27 |  | 2025-01-01 | 2025-02-06 | 37 |  | 2024-09-13 | 2024-09-16 |  | 2025-03-10 | 2025-03-11 | 2 |  | 2024-09-27 | 2024-09-28 |  | 2025-03-12 | 2025-03-14 | 3 |  |  | 2024-12-01
DNC | 57 | PSS-4 | AGE24L | WTG 088 | Precast | F12 | Bauer | Done | 532499 | 2671833 | 2024-01-09 | 2024-01-31 |  | 2024-01-09 | 2024-01-31 |  | 253 | 253 | 2024-05-29 | 2024-06-07 |  | 2024-10-08 | 2024-10-22 | 15 | [8 empty] | 2024-09-15 | 2024-09-15 |  | 2024-11-02 | 2024-11-05 | 4 |  | 2024-09-16 | 2024-09-16 |  | 2024-11-14 | 2024-11-15 | 2 |  | 2024-09-17 | 2024-09-17 |  | 2024-11-16 | 2024-11-16 | 1 |  | 2024-09-18 | 2024-09-19 |  | 2024-11-21 | 2024-11-23 | 3 |  | 2024-09-21 | 2024-09-30 |  | 2024-11-25 | 2024-11-30 | 6 |  | 2024-10-11 | 2024-10-12 |  | 2024-12-01 | 2024-12-02 | 2 | 31 |  | 2024-10-13 | 2024-10-19 |  | 2024-12-12 | 2025-03-10 | 89 |  | 2024-10-13 | 2024-10-19 |  | 2024-12-13 | 2024-12-13 | 1 |  |  |  | 2024-09-28 | 2024-10-12 |  | 2024-12-14 | 2025-01-18 | 36 |  | 2024-09-10 | 2024-09-16 |  | Completed | Completed | #VALUE! |  | 2024-09-10 | 2024-09-16 |  | Completed | Completed | #VALUE! |  | GP | 2024-09-17 | 2024-09-23 |  | 2024-11-16 | 2024-12-24 | 39 |  | 2024-11-03 | 2024-11-08 |  | 2025-01-06 | 2025-01-14 | 9 |  | 2024-10-25 | 2024-10-31 |  | 2025-02-12 | 2025-02-27 | 16 |  | 2024-11-11 | 2024-11-20 |  | 2025-02-05 | 2025-02-13 | 9 |  | 2024-11-22 | 2024-11-24 |  | 2025-02-14 | 2025-02-18 | 5 |  | 2024-11-06 | 2024-11-07 |  | 2025-02-28 | 2025-02-28 | 1 |  | 2024-10-25 | 2024-10-31 |  | 2024-12-06 | 2024-12-12 | 7 |  | 2024-11-01 | 2024-11-16 |  | 2024-12-16 | 2025-01-09 | 25 |  | 2024-11-07 | 2024-11-10 |  | 2025-03-07 | 2025-03-09 | 3 |  | 2024-11-24 | 2024-11-25 |  | 2025-03-10 | 2025-03-11 | 2 |  |  | 2024-12-01
DNC | 58 | PSS-4 | AGE24L | WTG 071 | Precast | F12 | Sarita infra | Done | 531847 | 2671151 | 2023-06-08 | 2023-06-09 |  | 2023-06-08 | 2023-06-09 |  | 199 | 199 | 2024-05-27 | 2024-06-05 |  | 2023-11-28 | 2023-12-13 | 16 | [8 empty] | 2024-09-13 | 2024-09-13 |  | 2024-04-23 | 2024-04-26 | 4 |  | 2024-09-14 | 2024-09-14 |  | 2024-04-27 | 2024-04-28 | 2 |  | 2024-09-15 | 2024-09-15 |  | 2024-04-29 | 2024-04-29 | 1 |  | 2024-09-16 | 2024-09-17 |  | 2024-05-02 | 2024-05-03 | 2 |  | 2024-09-19 | 2024-09-28 |  | 2024-05-07 | 2024-06-22 | 47 |  | 2024-10-09 | 2024-10-10 |  | 2024-06-23 | 2024-06-24 | 2 | 63 |  | 2024-10-11 | 2024-10-17 |  | 2024-08-05 | 2025-03-10 | 218 |  | 2024-10-11 | 2024-10-17 |  | 2024-08-09 | 2024-08-09 | 1 |  |  |  | 2024-09-26 | 2024-10-10 |  | 2024-11-19 | 2024-12-29 | 41 |  | 2024-09-08 | 2024-09-14 |  | Completed | Completed | #VALUE! |  | 2024-09-08 | 2024-09-14 |  | 2024-10-03 | 2024-10-12 | 10 |  | GP | 2024-09-15 | 2024-09-21 |  | 2024-10-03 | 2024-10-12 | 10 |  | 2024-11-01 | 2024-11-06 |  | 2024-10-13 | 2024-10-20 | 8 |  | 2024-10-18 | 2024-10-24 |  | 2024-12-28 | 2025-02-24 | 59 |  | 2024-11-09 | 2024-11-18 |  | 2024-10-23 | 2024-11-25 | 34 |  | 2024-11-20 | 2024-11-22 |  | 2024-12-12 | 2024-12-20 | 9 |  | 2024-10-30 | 2024-10-31 |  | 2025-03-01 | 2025-03-01 | 1 |  | 2024-10-18 | 2024-10-24 |  | 2024-12-23 | 2025-02-04 | 44 |  | 2024-11-01 | 2024-11-16 |  | 2024-12-16 | 2025-01-09 | 25 |  | 2024-10-31 | 2024-11-03 |  | 2025-03-07 | 2025-03-09 | 3 |  | 2024-11-22 | 2024-11-23 |  | 2025-03-10 | 2025-03-12 | 3 |  |  | 2024-12-01
DNC | 59 | PSS-4 | AHEJ5L | WTG 055 | Precast | F11 | Sarita infra | Done | 531204 | 2670430 | 2023-06-08 | 2023-06-09 |  | 2023-06-08 | 2023-06-09 |  | 163 | 163 | 2024-05-07 | 2024-05-16 |  | 2024-05-07 | 2024-05-17 | 11 | [8 empty] | 2024-09-18 | 2024-09-18 |  | 2024-05-25 | 2024-05-27 | 3 |  | 2024-09-19 | 2024-09-19 |  | 2024-05-29 | 2024-05-30 | 2 |  | 2024-09-20 | 2024-09-20 |  | 2024-06-01 | 2024-06-01 | 1 |  | 2024-09-21 | 2024-09-22 |  | 2024-09-18 | 2024-09-25 | 8 |  | 2024-09-24 | 2024-10-01 |  | 2024-09-26 | 2024-11-08 | 44 |  | 2024-10-04 | 2024-10-05 |  | 2024-11-10 | 2024-11-11 | 2 | 171 |  | 2024-10-07 | 2024-10-13 |  | 2024-11-21 | 2025-05-18 | 179 |  | 2024-10-07 | 2024-10-13 |  | 2024-11-21 | 2024-11-22 | 2 |  |  |  | 2024-10-01 | 2024-10-15 |  | 2024-11-24 | 2025-01-31 | 69 |  | 2024-09-02 | 2024-09-08 |  | Completed | Completed | #VALUE! |  | 2024-09-02 | 2024-09-08 |  | Completed | Completed | #VALUE! |  | SS Jadeja | 2024-10-11 | 2024-10-17 |  | 2024-11-12 | 2024-12-04 | 23 |  | 2024-10-27 | 2024-11-01 |  | 2024-12-06 | 2024-12-16 | 11 |  | 2024-10-23 | 2024-10-29 |  | 2025-02-03 | 2025-03-02 | 28 |  | 2024-11-03 | 2024-11-12 |  | 2024-12-24 | 2024-12-31 | 8 |  | 2024-11-13 | 2024-11-15 |  | 2024-12-31 | 2025-01-04 | 5 |  | 2024-11-04 | 2024-11-05 |  | 2025-03-15 | 2025-03-15 | 1 |  | 2024-10-23 | 2024-10-29 |  | 2025-01-27 | 2025-02-18 | 23 |  | 2024-11-01 | 2024-11-16 |  | 2025-01-01 | 2025-02-06 | 37 |  | 2024-11-05 | 2024-11-08 |  | 2025-03-26 | 2025-03-29 | 4 |  | 2024-11-16 | 2024-11-17 |  | 2025-04-17 | 2025-04-17 | 1 |  |  | 2024-12-01
DNC | 60 | PSS-4 | AHEJ5L | WTG 054 | Precast | F11 | Sarita infra | Done | 531014 | 2671416 | 2024-01-12 | 2024-02-01 |  | 2024-01-12 | 2024-02-01 |  | 199 | 199 | 2024-05-06 | 2024-05-15 |  | 2023-12-14 | 2023-12-25 | 12 | [8 empty] | 2024-09-17 | 2024-09-17 |  | 2024-04-30 | 2024-05-04 | 5 |  | 2024-09-18 | 2024-09-18 |  | 2024-05-05 | 2024-05-05 | 1 |  | 2024-09-19 | 2024-09-19 |  | 2024-05-08 | 2024-05-08 | 1 |  | 2024-09-20 | 2024-09-21 |  | 2024-05-14 | 2024-05-15 | 2 |  | 2024-09-23 | 2024-09-30 |  | 2024-05-22 | 2024-07-30 | 70 |  | 2024-10-03 | 2024-10-04 |  | 2024-08-01 | 2024-08-02 | 2 | 95 |  | 2024-10-06 | 2024-10-12 |  | 2024-08-10 | 2025-03-12 | 215 |  | 2024-10-06 | 2024-10-12 |  | 2024-08-16 | 2024-08-16 | 1 |  |  |  | 2024-09-30 | 2024-10-14 |  | 2024-12-20 | 2025-01-15 | 27 |  | 2024-09-02 | 2024-09-08 |  | Completed | Completed | #VALUE! |  | 2024-09-02 | 2024-09-08 |  | 2024-10-22 | 2024-11-10 | 20 |  | Vaibhav | 2024-10-10 | 2024-10-16 |  | 2024-10-22 | 2024-11-10 | 20 |  | 2024-10-26 | 2024-10-31 |  | 2024-11-10 | 2024-11-17 | 8 |  | 2024-10-22 | 2024-10-28 |  | 2025-02-03 | 2025-03-01 | 27 |  | 2024-11-02 | 2024-11-11 |  | 2024-11-25 | 2024-12-06 | 12 |  | 2024-11-12 | 2024-11-14 |  | 2024-12-07 | 2024-12-11 | 5 |  | 2024-11-03 | 2024-11-04 |  | 2025-03-10 | 2025-03-10 | 1 |  | 2024-10-22 | 2024-10-28 |  | 2025-02-16 | 2025-02-26 | 11 |  | 2024-10-05 | 2024-10-20 |  | 2025-01-01 | 2025-02-06 | 37 |  | 2024-11-04 | 2024-11-07 |  | 2025-03-26 | 2025-03-29 | 4 |  | 2024-11-14 | 2024-11-15 |  | 2025-04-17 | 2025-04-17 | 1 |  |  | 2024-12-01
UNIQUE INF | 61 | PSS-4 | AGE24L | WTG 039 | Precast | F10 | Menard | Done | 530174 | 2671720 | 2024-01-14 | 2024-02-01 |  | 2024-01-14 | 2024-02-01 |  | 211 | 211 | 2024-06-07 | 2024-06-16 |  | 2024-06-29 | 2024-11-07 | 132 |  | Yes | 2024-12-02 | 2024-12-11 |  | 2024-11-26 | 2024-12-11 |  | 2024-09-18 | 2024-09-18 |  | 2024-12-28 | 2024-12-31 | 4 |  | 2024-09-19 | 2024-09-19 |  | 2025-01-01 | 2025-01-03 | 3 |  | 2024-09-20 | 2024-09-20 |  | 2025-01-05 | 2025-01-05 | 1 |  | 2024-09-21 | 2024-09-22 |  | 2025-01-10 | 2025-01-10 | 1 |  | 2024-09-24 | 2024-10-03 |  | 2025-01-11 | 2025-01-23 | 13 |  | 2024-10-12 | 2024-10-13 |  | 2025-01-26 | 2025-01-27 | 2 | 31 |  | 2024-10-14 | 2024-10-20 |  | 2025-02-02 | 2025-04-20 | 78 |  | 2024-10-14 | 2024-10-20 |  | 2025-02-01 | 2025-02-01 | 1 |  |  |  | 2024-10-01 | 2024-10-15 |  | 2025-02-09 | 2025-03-03 | 23 |  | 2024-09-21 | 2024-09-27 |  | 2024-05-16 | 2024-05-23 | 8 |  | 2024-09-21 | 2024-09-27 |  | 2025-02-04 | 2025-02-11 | 8 |  | SS Jadeja (Reuse) | 2024-09-28 | 2024-10-04 |  | 2025-02-04 | 2025-02-11 | 8 |  | 2024-11-09 | 2024-11-14 |  | 2025-02-11 | 2025-02-23 | 13 |  | 2024-10-26 | 2024-11-01 |  | 2025-03-05 | 2025-03-18 | 14 |  | 2024-11-17 | 2024-11-26 |  | 2025-03-14 | 2025-03-26 | 13 |  | 2024-11-28 | 2024-11-30 |  | 2025-03-27 | 2025-03-29 | 3 |  | 2024-11-07 | 2024-11-08 |  | 2025-03-18 | 2025-03-18 | 1 |  | 2024-10-26 | 2024-11-01 |  | 2025-01-24 | 2025-02-24 | 32 |  | 2024-11-01 | 2024-11-16 |  | 2025-01-15 | 2025-02-06 | 23 |  | 2024-11-08 | 2024-11-11 |  | 2025-03-24 | 2025-03-25 | 2 |  | 2024-11-30 | 2024-12-01 |  | 2025-03-31 | 2025-04-01 | 2 |  |  | 2024-12-01
DNC | 62 | PSS-4 | AGE24L | WTG 025 | Precast | F10 | Sarita infra | Done | 529341 | 2671985 | 2024-01-13 | 2024-02-01 |  | 2024-01-13 | 2024-02-01 |  | 199 | 199 | 2024-06-08 | 2024-06-17 |  | 2024-12-11 | 2024-12-19 | 9 | [8 empty] | 2024-09-19 | 2024-09-19 |  | 2024-12-23 | 2024-12-24 | 2 |  | 2024-09-20 | 2024-09-20 |  | 2025-01-05 | 2025-01-06 | 2 |  | 2024-09-21 | 2024-09-21 |  | 2025-01-06 | 2025-01-06 | 1 |  | 2024-09-22 | 2024-09-23 |  | 2025-01-08 | 2025-01-09 | 2 |  | 2024-09-25 | 2024-10-04 |  | 2025-01-09 | 2025-01-16 | 8 |  | 2024-10-13 | 2024-10-14 |  | 2025-01-17 | 2025-01-17 | 1 | 26 |  | 2024-10-15 | 2024-10-21 |  | 2025-01-24 | 2025-04-15 | 82 |  | 2024-10-15 | 2024-10-21 |  | 2025-01-27 | 2025-01-27 | 1 |  |  |  | 2024-10-02 | 2024-10-16 |  | 2024-12-28 | 2025-02-25 | 60 |  | 2024-09-22 | 2024-09-28 |  | 2024-05-17 | 2024-05-23 | 7 |  | 2024-09-22 | 2024-09-28 |  | 2025-02-03 | 2025-02-16 | 14 |  | SS Jadeja (Reuse) | 2024-09-29 | 2024-10-05 |  | 2025-01-29 | 2025-02-16 | 19 |  | 2024-11-10 | 2024-11-15 |  | 2025-02-22 | 2025-03-02 | 9 |  | 2024-10-27 | 2024-11-02 |  | 2025-03-02 | 2025-03-15 | 14 |  | 2024-11-18 | 2024-11-27 |  | 2025-03-04 | 2025-03-19 | 16 |  | 2024-11-29 | 2024-12-01 |  | 2025-03-24 | 2025-03-26 | 3 |  | 2024-11-08 | 2024-11-09 |  | 2025-03-16 | 2025-03-16 | 1 |  | 2024-10-27 | 2024-11-02 |  | 2025-01-10 | 2025-01-19 | 10 |  | 2024-11-01 | 2024-11-16 |  | 2025-01-15 | 2025-02-06 | 23 |  | 2024-11-09 | 2024-11-12 |  | 2025-03-24 | 2025-03-25 | 2 |  | 2024-12-01 | 2024-12-02 |  | 2025-03-31 | 2025-04-01 | 2 |  |  | 2024-12-01
HBG | 63 | PSS-4 | AGE24L | WTG 013 | Precast | F9 | Sarita infra | Done | 528500 | 2672290 | 2024-01-15 | 2024-02-02 |  | 2024-01-15 | 2024-02-02 |  | 253 | 253 | 2024-06-15 | 2024-06-24 |  | 2024-11-23 | 2024-12-10 | 18 | [8 empty] | 2024-09-14 | 2024-09-14 |  | 2024-12-14 | 2024-12-17 | 4 |  | 2024-09-15 | 2024-09-15 |  | 2024-12-20 | 2024-12-21 | 2 |  | 2024-09-16 | 2024-09-16 |  | 2024-12-22 | 2024-12-22 | 1 |  | 2024-09-17 | 2024-09-18 |  | 2024-12-30 | 2024-12-30 | 1 |  | 2024-09-24 | 2024-10-01 |  | 2025-01-13 | 2025-01-24 | 12 |  | 2024-10-04 | 2024-10-05 |  | 2025-01-25 | 2025-01-26 | 2 | 44 |  | 2024-10-07 | 2024-10-13 |  | 2025-02-01 | 2025-04-06 | 65 |  | 2024-10-07 | 2024-10-13 |  | 2025-02-02 | 2025-02-02 | 1 |  |  |  | 2024-10-01 | 2024-10-15 |  | 2024-12-20 | 2025-02-27 | 70 |  | 2024-09-19 | 2024-09-25 |  | 2024-05-21 | 2024-06-04 | 15 |  | 2024-09-19 | 2024-09-25 |  | 2025-01-28 | 2025-02-10 | 14 |  | GP | 2024-10-11 | 2024-10-17 |  | 2024-12-18 | 2025-02-10 | 55 | WET SURFACE | 2024-10-29 | 2024-11-03 |  | 2025-02-13 | 2025-02-24 | 12 |  | 2024-10-23 | 2024-10-29 |  | 2025-03-07 | 2025-03-22 | 16 |  | 2024-11-05 | 2024-11-14 |  | 2025-03-06 | 2025-03-13 | 8 |  | 2024-11-15 | 2024-11-17 |  | 2025-03-24 | 2025-03-25 | 2 |  | 2024-11-04 | 2024-11-05 |  | 2025-03-23 | 2025-03-23 | 1 |  | 2024-10-27 | 2024-11-02 |  | 2025-01-01 | 2025-02-26 | 57 |  | 2024-11-01 | 2024-11-16 |  | 2025-01-15 | 2025-02-06 | 23 |  | 2024-11-05 | 2024-11-08 |  | 2025-03-24 | 2025-03-25 | 2 |  | 2024-11-17 | 2024-11-18 |  | 2025-03-31 | 2025-04-01 | 2 |  |  | 2024-12-01
UNIQUE INF | 64 | PSS-4 | AGE24L | WTG 001 | Precast | F9 | Menard | Done | 527856 | 2671568 | 2024-01-16 | 2024-02-01 |  | 2024-01-16 | 2024-02-01 |  | 211 | 211 | 2024-06-27 | 2024-07-06 |  | 2024-06-12 | 2024-06-17 | 6 | [8 empty] | 2024-09-28 | 2024-09-28 |  | 2024-10-23 | 2024-10-27 | 5 |  | 2024-09-29 | 2024-09-29 |  | 2024-11-03 | 2024-11-07 | 5 |  | 2024-09-30 | 2024-09-30 |  | 2024-11-13 | 2024-11-13 | 1 |  | 2024-10-01 | 2024-10-02 |  | 2024-11-16 | 2024-11-17 | 2 |  | 2024-10-12 | 2024-10-19 |  | 2024-11-19 | 2024-11-30 | 12 |  | 2024-10-22 | 2024-10-23 |  | 2024-12-01 | 2024-12-02 | 2 | 41 |  | 2024-10-25 | 2024-10-31 |  | 2024-12-09 | 2025-03-11 | 93 |  | 2024-10-25 | 2024-10-31 |  | 2024-12-06 | 2024-12-06 | 1 |  |  |  | 2024-10-19 | 2024-11-02 |  | 2024-10-23 | 2025-01-20 | 90 |  | 2024-10-05 | 2024-10-11 |  | 2024-06-09 | 2024-06-15 | 7 |  | 2024-10-05 | 2024-10-11 |  | 2024-11-19 | 2024-11-28 | 10 |  | SS Jadeja | 2024-10-29 | 2024-11-04 |  | 2024-11-10 | 2024-12-09 | 30 |  | 2024-11-26 | 2024-12-01 |  | 2024-12-25 | 2025-01-08 | 15 |  | 2024-11-10 | 2024-11-16 |  | 2025-02-04 | 2025-03-15 | 40 |  | 2024-12-03 | 2024-12-09 |  | 2025-03-13 | 2025-03-25 | 13 |  | 2024-12-10 | 2024-12-12 |  | 2025-03-27 | 2025-03-28 | 2 |  | 2024-11-22 | 2024-11-23 |  | 2025-03-20 | 2025-03-20 | 1 |  | 2024-11-12 | 2024-11-18 |  | 2024-12-04 | 2025-01-08 | 36 |  | 2024-11-20 | 2024-12-05 |  | 2025-01-15 | 2025-02-06 | 23 |  | 2024-11-23 | 2024-11-26 |  | 2025-03-24 | 2025-03-25 | 2 |  | 2024-12-12 | 2024-12-13 |  | 2025-03-31 | 2025-04-01 | 2 |  |  | 2024-12-01
DNC | 65 | PSS-4 | AGE24L | WTG 070 | Precast | F12 | Bauer | Done | 531658 | 2672138 | 2024-01-14 | 2024-02-02 |  | 2024-01-14 | 2024-02-02 |  | 253 | 253 | 2024-06-09 | 2024-06-18 |  | 2024-05-30 | 2024-06-14 | 16 | [8 empty] | 2024-09-20 | 2024-09-20 |  | 2024-09-19 | 2024-09-25 | 7 |  | 2024-09-21 | 2024-09-21 |  | 2025-01-14 | 2025-01-15 | 2 | Due to water seepage wrok getting delayed | 2024-09-22 | 2024-09-22 |  | 2025-01-15 | 2025-01-15 | 1 |  | 2024-09-23 | 2024-09-24 |  | 2025-01-16 | 2025-01-16 | 1 |  | 2024-09-26 | 2024-10-05 |  | 2025-01-17 | 2025-01-21 | 5 |  | 2024-10-14 | 2024-10-15 |  | 2025-01-22 | 2025-01-22 | 1 | 126 |  | 2024-10-16 | 2024-10-22 |  | 2025-02-02 | 2025-03-10 | 37 |  | 2024-10-16 | 2024-10-22 |  | 2025-01-31 | 2025-01-31 | 1 |  |  |  | 2024-10-03 | 2024-10-17 |  | 2025-01-26 | 2025-02-10 | 16 |  | 2024-09-23 | 2024-09-29 |  | 2024-05-27 | 2024-06-03 | 8 |  | 2024-09-23 | 2024-09-29 |  | 2025-01-24 | 2025-02-08 | 16 |  | GP (Reuse) | 2024-09-30 | 2024-10-06 |  | 2025-01-12 | 2025-02-07 | 27 |  | 2024-11-11 | 2024-11-16 |  | 2025-02-09 | 2025-02-22 | 14 |  | 2024-11-02 | 2024-11-08 |  | 2025-02-18 | 2025-03-01 | 12 |  | 2024-11-19 | 2024-11-28 |  | 2025-02-27 | 2025-03-07 | 9 |  | 2024-11-30 | 2024-12-02 |  | 2025-03-08 | 2025-03-09 | 2 |  | 2024-11-14 | 2024-11-15 |  | 2025-03-02 | 2025-03-02 | 1 |  | 2024-11-02 | 2024-11-08 |  | 2024-12-06 | 2024-12-29 | 24 |  | 2024-11-01 | 2024-11-16 |  | 2024-12-16 | 2025-01-09 | 25 |  | 2024-11-15 | 2024-11-18 |  | 2025-03-07 | 2025-03-09 | 3 |  | 2024-12-02 | 2024-12-03 |  | 2025-03-10 | 2025-03-11 | 2 |  |  | 2024-12-01
UNIQUE INF | 66 | PSS-4 | AKPL | WTG 124 | Precast | F14 | Sarita infra | Done | 534173 | 2671264 | 2023-06-07 | 2023-06-08 |  | 2023-06-07 | 2023-06-08 |  | 163 | 163 | 2024-03-22 | 2024-03-31 |  | 2023-12-23 | 2024-01-02 | 11 |  | Yes | 2024-06-03 | 2024-06-15 |  | 2024-06-05 | 2024-06-28 |  | 2024-08-04 | 2024-08-04 |  | 2024-11-10 | 2024-11-13 | 4 |  | 2024-08-05 | 2024-08-05 |  | 2024-11-21 | 2024-11-24 | 4 |  | 2024-08-06 | 2024-08-06 |  | 2024-11-25 | 2024-11-25 | 1 |  | 2024-08-07 | 2024-08-08 |  | 2024-11-28 | 2024-11-28 | 1 |  | 2024-08-10 | 2024-08-19 |  | 2024-11-28 | 2024-12-13 | 16 |  | 2024-08-22 | 2024-08-23 |  | 2024-12-15 | 2024-12-17 | 3 | 38 |  | 2024-08-24 | 2024-08-30 |  | 2024-12-22 | 2025-03-13 | 82 |  | 2024-08-24 | 2024-08-30 |  | 2024-12-27 | 2024-12-27 | 1 |  |  |  | 2024-08-17 | 2024-08-31 |  | 2024-12-22 | 2025-01-20 | 30 |  | 2024-08-24 | 2024-08-30 |  | Completed | Completed | #VALUE! |  | 2024-08-24 | 2024-08-30 |  | Completed | Completed | #VALUE! |  | SS Jadeja | 2024-08-31 | 2024-09-06 |  | 2024-12-16 | 2025-01-07 | 23 |  | 2024-09-20 | 2024-09-25 |  | 2025-01-11 | 2025-01-26 | 16 |  | 2024-09-23 | 2024-09-29 |  | 2025-02-04 | 2025-03-06 | 31 |  | 2024-09-28 | 2024-10-07 |  | 2025-02-16 | 2025-02-20 | 5 |  | 2024-10-09 | 2024-10-11 |  | 2025-02-21 | 2025-02-23 | 3 |  | 2024-10-05 | 2024-10-06 |  | 2025-03-07 | 2025-03-07 | 1 |  | 2024-09-20 | 2024-09-26 |  | 2024-12-10 | 2025-02-15 | 68 |  | 2024-09-12 | 2024-09-27 |  | 2025-01-01 | 2025-02-06 | 37 |  | 2024-10-06 | 2024-10-09 |  | 2025-03-10 | 2025-03-11 | 2 |  | 2024-10-11 | 2024-10-12 |  | 2025-03-11 | 2025-03-13 | 3 |  |  | 2024-12-01
DNC | 67 | PSS-4 | AKPL | WTG 090 | Precast | F13 | Bauer | Done | 532878 | 2669860 | 2023-06-06 | 2023-06-07 |  | 2023-06-06 | 2023-06-07 |  | 219 | 219 | 2024-03-23 | 2024-04-01 |  | 2024-05-17 | 2024-05-30 | 14 | [8 empty] | 2024-08-04 | 2024-08-04 |  | 2024-10-24 | 2024-10-25 | 2 |  | 2024-08-05 | 2024-08-05 |  | 2024-10-25 | 2024-10-25 | 1 |  | 2024-08-06 | 2024-08-06 |  | 2024-10-26 | 2024-10-26 | 1 |  | 2024-08-07 | 2024-08-08 |  | 2024-11-02 | 2024-11-04 | 3 |  | 2024-08-10 | 2024-08-19 |  | 2024-11-11 | 2024-11-20 | 10 |  | 2024-08-22 | 2024-08-23 |  | 2024-11-21 | 2024-11-22 | 2 | 30 |  | 2024-08-24 | 2024-08-30 |  | 2024-12-03 | 2025-03-13 | 101 |  | 2024-08-24 | 2024-08-30 |  | 2024-12-01 | 2024-12-01 | 1 |  |  |  | 2024-08-17 | 2024-08-31 |  | 2024-11-27 | 2025-01-28 | 63 |  | 2024-08-24 | 2024-08-30 |  | Completed | Completed | #VALUE! |  | 2024-08-24 | 2024-08-30 |  | 2024-11-05 | 2024-11-15 | 11 |  | SS Jadeja | 2024-08-31 | 2024-09-06 |  | 2024-11-05 | 2024-11-10 | 6 |  | 2024-09-20 | 2024-09-25 |  | 2024-11-20 | 2024-12-26 | 37 |  | 2024-09-24 | 2024-09-30 |  | 2025-02-03 | 2025-03-05 | 31 |  | 2024-09-28 | 2024-10-07 |  | 2025-02-07 | 2025-02-13 | 7 |  | 2024-10-09 | 2024-10-11 |  | 2025-02-14 | 2025-02-17 | 4 |  | 2024-10-06 | 2024-10-07 |  | 2025-03-08 | 2025-03-08 | 1 |  | 2024-09-20 | 2024-09-26 |  | 2024-12-29 | 2025-01-25 | 28 |  | 2024-09-12 | 2024-09-27 |  | 2025-01-01 | 2025-02-06 | 37 |  | 2024-10-07 | 2024-10-10 |  | 2025-03-10 | 2025-03-11 | 2 |  | 2024-10-11 | 2024-10-12 |  | 2025-03-12 | 2025-03-14 | 3 |  |  | 2024-12-01
MSC | 68 | PSS-4 | ACL | WTG 110 | Precast | F17 | Menard | Done | 534090 | 2667623 | 2023-01-02 | 2023-01-03 |  | 2023-01-02 | 2023-01-03 |  | 199 | 199 | 2024-04-01 | 2024-04-10 |  | 2023-10-07 | 2023-10-14 | 8 |  | Yes | 2024-06-13 | 2024-06-24 |  | 2024-10-15 | 2024-10-24 |  | 2024-08-10 | 2024-08-10 |  | 2024-11-15 | 2024-11-16 | 2 |  | 2024-08-11 | 2024-08-11 |  | 2024-11-18 | 2024-11-19 | 2 |  | 2024-08-12 | 2024-08-12 |  | 2024-11-20 | 2024-11-20 | 1 |  | 2024-08-13 | 2024-08-14 |  | 2024-11-23 | 2024-11-23 | 1 |  | 2024-08-16 | 2024-08-25 |  | 2024-11-26 | 2024-12-03 | 8 |  | 2024-08-28 | 2024-08-29 |  | 2024-12-04 | 2024-12-04 | 1 | 20 |  | 2024-08-30 | 2024-09-05 |  | 2024-12-06 | 2025-02-19 | 76 |  | 2024-08-30 | 2024-09-05 |  | 2024-12-07 | 2024-12-07 | 1 |  |  |  | 2024-08-23 | 2024-09-06 |  | 2024-12-27 | 2025-01-11 | 16 |  | 2024-09-01 | 2024-09-07 |  | Completed | Completed | #VALUE! |  | 2024-09-01 | 2024-09-07 |  | Completed | Completed | #VALUE! |  | GP | 2024-09-08 | 2024-09-14 |  | 2024-12-02 | 2024-12-09 | 8 |  | 2024-09-29 | 2024-10-04 |  | 2024-12-25 | 2025-01-05 | 12 |  | 2024-10-02 | 2024-10-08 |  | 2025-01-20 | 2025-02-11 | 23 |  | 2024-09-28 | 2024-10-07 |  | 2025-01-10 | 2025-01-26 | 17 | Team divert to PSS-13 Location for priority | 2024-10-09 | 2024-10-11 |  | 2025-01-28 | 2025-01-30 | 3 |  | 2024-10-14 | 2024-10-15 |  | 2025-02-21 | 2025-02-21 | 1 |  | 2024-09-20 | 2024-09-26 |  | 2024-12-03 | 2025-02-01 | 61 |  | 2024-10-05 | 2024-10-20 |  | 2024-12-16 | 2025-01-09 | 25 |  | 2024-10-15 | 2024-10-18 |  | 2025-02-28 | 2025-03-07 | 8 |  | 2024-10-20 | 2024-10-21 |  | 2025-03-09 | 2025-03-10 | 2 |  |  | 2024-12-01
MSC | 69 | PSS-4 | ACL | WTG 109 | Precast | F17 | Sarita infra | Done | 533901 | 2668609 | 2023-01-02 | 2023-01-03 |  | 2023-01-02 | 2023-01-03 |  | 199 | 199 | 2024-04-02 | 2024-04-11 |  | 2023-10-21 | 2023-10-31 | 11 | [8 empty] | 2024-08-10 | 2024-08-10 |  | 2024-10-11 | 2024-10-13 | 3 |  | 2024-08-11 | 2024-08-11 |  | 2024-10-14 | 2024-11-05 | 23 | Due to rain pathways is in wet condition waiting for dry cond. | 2024-08-12 | 2024-08-12 |  | 2024-11-08 | 2024-11-08 | 1 |  | 2024-08-13 | 2024-08-14 |  | 2024-11-09 | 2024-11-10 | 2 |  | 2024-08-16 | 2024-08-25 |  | 2024-11-11 | 2024-11-18 | 8 |  | 2024-08-28 | 2024-08-29 |  | 2024-11-19 | 2024-11-19 | 1 | 40 |  | 2024-08-30 | 2024-09-05 |  | 2024-11-22 | 2025-02-12 | 83 |  | 2024-08-30 | 2024-09-05 |  | 2024-11-25 | 2024-11-25 | 1 |  |  |  | 2024-08-23 | 2024-09-06 |  | 2024-12-28 | 2025-01-02 | 6 |  | 2024-09-01 | 2024-09-07 |  | Completed | Completed | #VALUE! |  | 2024-09-01 | 2024-09-07 |  | 2024-12-02 | 2024-12-10 | 9 |  | GP | 2024-09-08 | 2024-09-14 |  | 2024-11-18 | 2024-12-01 | 14 |  | 2024-09-29 | 2024-10-04 |  | 2024-12-14 | 2024-12-22 | 9 |  | 2024-10-01 | 2024-10-07 |  | 2025-01-07 | 2025-02-24 | 49 |  | 2024-10-07 | 2024-10-16 |  | 2025-01-03 | 2025-01-08 | 6 |  | 2024-10-18 | 2024-10-20 |  | 2025-01-10 | 2025-01-11 | 2 |  | 2024-10-13 | 2024-10-14 |  | 2025-02-27 | 2025-02-28 | 2 |  | 2024-09-28 | 2024-10-04 |  | 2024-12-01 | 2025-01-30 | 61 |  | 2024-10-05 | 2024-10-20 |  | 2024-12-16 | 2025-01-09 | 25 |  | 2024-10-14 | 2024-10-17 |  | 2025-02-28 | 2025-03-07 | 8 |  | 2024-10-20 | 2024-10-21 |  | 2025-03-09 | 2025-03-11 | 3 |  |  | 2024-12-01
MSC | 70 | PSS-4 | ACL | WTG 093 | Precast | F17 | Menard | Done | 533446 | 2666901 | 2023-01-03 | 2023-01-04 |  | 2023-01-03 | 2023-01-04 |  | 219 | 219 | 2024-04-03 | 2024-04-12 |  | 2023-10-28 | 2023-11-11 | 15 | [8 empty] | 2024-08-10 | 2024-08-10 |  | 2024-10-08 | 2024-10-10 | 3 |  | 2024-08-11 | 2024-08-11 |  | 2024-10-11 | 2024-10-13 | 3 |  | 2024-08-12 | 2024-08-12 |  | 2024-10-24 | 2024-10-24 | 1 |  | 2024-08-13 | 2024-08-14 |  | 2024-10-25 | 2024-10-25 | 1 |  | 2024-08-16 | 2024-08-25 |  | 2024-10-26 | 2024-11-05 | 11 |  | 2024-08-28 | 2024-08-29 |  | 2024-11-05 | 2024-11-06 | 2 | 30 |  | 2024-08-30 | 2024-09-05 |  | 2024-11-18 | 2025-03-07 | 110 |  | 2024-08-30 | 2024-09-05 |  | 2024-11-21 | 2024-11-21 | 1 |  |  |  | 2024-08-23 | 2024-09-06 |  | 2024-11-24 | 2025-01-01 | 39 |  | 2024-09-01 | 2024-09-07 |  | Completed | Completed | #VALUE! |  | 2024-09-01 | 2024-09-07 |  | 2024-11-06 | 2024-11-17 | 12 |  | GP | 2024-09-08 | 2024-09-14 |  | 2024-11-06 | 2024-11-17 | 12 |  | 2024-09-29 | 2024-10-04 |  | 2024-11-20 | 2024-12-01 | 12 |  | 2024-10-02 | 2024-10-08 |  | 2024-12-28 | 2025-02-18 | 53 |  | 2024-10-07 | 2024-10-16 |  | 2024-12-15 | 2024-12-22 | 8 |  | 2024-10-18 | 2024-10-20 |  | 2024-12-23 | 2024-12-27 | 5 |  | 2024-10-14 | 2024-10-15 |  | 2025-02-27 | 2025-02-27 | 1 |  | 2024-09-28 | 2024-10-04 |  | 2024-12-01 | 2025-02-01 | 63 |  | 2024-10-05 | 2024-10-20 |  | 2024-12-16 | 2025-01-09 | 25 |  | 2024-10-15 | 2024-10-18 |  | 2025-02-28 | 2025-03-07 | 8 |  | 2024-10-20 | 2024-10-21 |  | 2025-03-09 | 2025-03-10 | 2 |  |  | 2024-12-01
BALAJI & Co | 71 | PSS-4 | ACL | WTG 092 | FDN | F17 | Menard | Done | 533257 | 2667888 | 2023-01-01 | 2023-01-02 |  | 2023-01-01 | 2023-01-02 |  | 219 | 219 | 2024-04-04 | 2024-04-13 |  | 2023-10-18 | 2023-10-27 | 10 | [8 empty] | 2024-08-10 | 2024-08-10 |  | 2024-09-23 | 2024-10-01 | 9 |  | 2024-08-11 | 2024-08-11 |  | 2024-10-22 | 2024-10-25 | 4 |  | 2024-08-12 | 2024-08-12 |  | 2024-10-25 | 2024-10-25 | 1 |  | 2024-08-13 | 2024-08-14 |  | 2024-10-27 | 2024-10-29 | 3 |  | 2024-08-16 | 2024-08-25 |  | 2024-10-30 | 2024-11-14 | 16 |  | 2024-08-28 | 2024-08-29 |  | 2024-11-15 | 2024-11-16 | 2 | 55 |  | 2024-08-30 | 2024-09-05 |  | 2024-11-01 | 2025-03-08 | 128 |  | 2024-08-30 | 2024-09-05 |  | 2024-11-27 | 2024-11-27 | 1 |  |  |  | 2024-08-23 | 2024-09-06 |  | 2024-12-30 | 2025-01-02 | 4 |  | 2024-09-01 | 2024-09-07 |  | Completed | Completed | #VALUE! |  | 2024-09-01 | 2024-09-07 |  | 2024-11-15 | 2024-11-30 | 16 |  | GP | 2024-09-08 | 2024-09-14 |  | 2024-11-15 | 2024-11-30 | 16 |  | 2024-09-29 | 2024-10-04 |  | 2024-12-07 | 2024-12-14 | 8 |  | 2024-10-10 | 2024-10-16 |  | 2025-01-06 | 2025-02-17 | 43 |  | 2024-10-07 | 2024-10-16 |  | 2025-01-02 | 2025-01-08 | 7 |  | 2024-10-18 | 2024-10-20 |  | 2025-01-09 | 2025-01-10 | 2 |  | 2024-10-22 | 2024-10-23 |  | 2025-02-25 | 2025-02-25 | 1 |  | 2024-09-28 | 2024-10-04 |  | 2024-12-06 | 2025-02-08 | 65 |  | 2024-10-05 | 2024-10-20 |  | 2024-12-16 | 2025-01-09 | 25 |  | 2024-10-23 | 2024-10-26 |  | 2025-02-28 | 2025-03-07 | 8 |  | 2024-10-26 | 2024-10-27 |  | 2025-03-09 | 2025-03-11 | 3 |  |  | 2024-12-01
HBG | 72 | PSS-4 | ACL | WTG 091 | Precast | F17 | Menard | Done | 533067 | 2668874 | 2023-01-01 | 2023-01-02 |  | 2023-01-01 | 2023-01-02 |  | 199 | 199 | 2024-02-25 | 2024-03-05 |  | 2024-03-15 | 2024-03-27 | 13 | [8 empty] | 2024-07-23 | 2024-07-23 |  | 2024-04-08 | 2024-04-10 | 3 |  | 2024-07-24 | 2024-07-24 |  | 2024-04-12 | 2024-04-13 | 2 |  | 2024-07-25 | 2024-07-25 |  | 2024-04-13 | 2024-04-13 | 1 |  | 2024-07-26 | 2024-07-27 |  | 2024-04-15 | 2024-04-18 | 4 |  | 2024-07-29 | 2024-08-07 |  | 2024-04-19 | 2024-05-03 | 15 |  | 2024-08-10 | 2024-08-11 |  | 2024-05-06 | 2024-05-07 | 2 | 30 |  | 2024-08-12 | 2024-08-18 |  | 2024-06-17 | 2025-03-07 | 264 |  | 2024-08-19 | 2024-08-19 |  | 2024-06-24 | 2024-06-24 | 1 |  |  |  | 2024-08-05 | 2024-08-19 |  | 2024-12-04 | 2024-12-29 | 26 |  | 2024-08-08 | 2024-08-14 |  | Completed | Completed | #VALUE! |  | 2024-08-08 | 2024-08-14 |  | 2024-06-02 | 2024-06-16 | 15 |  | GP | 2024-08-15 | 2024-08-21 |  | 2024-06-02 | 2024-06-16 | 15 |  | 2024-09-02 | 2024-09-07 |  | 2024-09-19 | 2024-10-02 | 14 |  | 2024-08-31 | 2024-09-06 |  | 2025-01-17 | 2025-02-15 | 30 |  | 2024-09-10 | 2024-09-19 |  | 2024-10-04 | 2024-11-11 | 39 |  | 2024-09-21 | 2024-09-23 |  | 2024-11-12 | 2024-11-17 | 6 |  | 2024-09-12 | 2024-09-13 |  | 2025-02-22 | 2025-02-22 | 1 |  | 2024-08-27 | 2024-09-02 |  | 2024-11-30 | 2025-02-02 | 65 |  | 2024-09-12 | 2024-09-27 |  | 2024-12-16 | 2025-01-09 | 25 |  | 2024-09-13 | 2024-09-16 |  | 2025-02-28 | 2025-03-07 | 8 |  | 2024-09-27 | 2024-09-28 |  | 2025-03-09 | 2025-03-10 | 2 |  |  | 2024-12-01
BALAJI & Co | 73 | PSS-4 | ACL | WTG 075 | FDN | F16 | Menard | Done | 532605 | 2667206 | 2022-12-31 | 2023-01-01 |  | 2022-12-31 | 2023-01-01 |  | 199 | 199 | 2024-04-13 | 2024-04-22 |  | 2023-11-15 | 2023-11-24 | 10 | [8 empty] | 2024-08-16 | 2024-08-16 |  | 2024-10-04 | 2024-10-08 | 5 |  | 2024-08-17 | 2024-08-17 |  | 2024-11-08 | 2024-11-09 | 2 |  | 2024-08-18 | 2024-08-18 |  | 2024-11-12 | 2024-11-12 | 1 |  | 2024-08-19 | 2024-08-20 |  | 2024-11-16 | 2024-11-17 | 2 |  | 2024-08-22 | 2024-08-31 |  | 2024-11-18 | 2024-11-25 | 8 |  | 2024-09-03 | 2024-09-04 |  | 2024-11-25 | 2024-11-26 | 2 | 54 |  | 2024-09-05 | 2024-09-11 |  | 2024-11-01 | 2025-03-07 | 127 |  | 2024-09-05 | 2024-09-11 |  | 2024-12-01 | 2024-12-01 | 1 |  |  |  | 2024-08-29 | 2024-09-12 |  | 2025-01-02 | 2025-01-07 | 6 |  | 2024-09-09 | 2024-09-15 |  | Completed | Completed | #VALUE! |  | 2024-09-09 | 2024-09-15 |  | Completed | Completed | #VALUE! |  | GP | 2024-09-16 | 2024-09-22 |  | 2024-11-19 | 2024-12-14 | 26 |  | 2024-10-08 | 2024-10-13 |  | 2024-12-18 | 2024-12-27 | 10 |  | 2024-10-09 | 2024-10-15 |  | 2025-01-08 | 2025-02-12 | 36 |  | 2024-10-07 | 2024-10-16 |  | 2025-01-11 | 2025-02-08 | 29 | Team divert to PSS-13 Location for priority | 2024-10-18 | 2024-10-20 |  | 2025-02-09 | 2025-02-11 | 3 |  | 2024-10-21 | 2024-10-22 |  | 2025-02-27 | 2025-02-28 | 2 |  | 2024-09-28 | 2024-10-04 |  | 2024-12-07 | 2025-01-31 | 56 |  | 2024-10-05 | 2024-10-20 |  | 2024-12-16 | 2025-01-09 | 25 |  | 2024-10-22 | 2024-10-25 |  | 2025-02-28 | 2025-03-07 | 8 |  | 2024-10-25 | 2024-10-26 |  | 2025-03-08 | 2025-03-09 | 2 |  |  | 2024-12-01
DNC | 74 | PSS-4 | ACL | WTG 074 | Precast | F16 | Menard | Done | 532416 | 2668192 | 2022-12-30 | 2022-12-31 |  | 2022-12-30 | 2022-12-31 |  | 209 | 209 | 2024-04-14 | 2024-04-23 |  | 2024-01-11 | 2024-01-27 | 17 |  | Yes | 2024-04-16 | 2024-04-21 |  | 2024-04-17 | 2024-05-05 |  | 2024-08-16 | 2024-08-16 |  | 2024-11-21 | 2024-11-23 | 3 |  | 2024-08-17 | 2024-08-17 |  | 2024-11-25 | 2024-11-27 | 3 |  | 2024-08-18 | 2024-08-18 |  | 2024-12-01 | 2024-12-03 | 3 | Hold due to not supply concrete properly | 2024-08-19 | 2024-08-20 |  | 2024-12-04 | 2024-12-04 | 1 |  | 2024-08-22 | 2024-08-31 |  | 2024-12-05 | 2024-12-12 | 8 |  | 2024-09-03 | 2024-09-04 |  | 2024-12-14 | 2024-12-15 | 2 | 25 |  | 2024-09-05 | 2024-09-11 |  | 2024-12-25 | 2025-03-07 | 73 |  | 2024-09-05 | 2024-09-11 |  | 2024-12-25 | 2024-12-25 | 1 |  |  |  | 2024-08-29 | 2024-09-12 |  | 2024-12-27 | 2025-01-22 | 27 |  | 2024-09-09 | 2024-09-15 |  | Completed | Completed | #VALUE! |  | 2024-09-09 | 2024-09-15 |  | Completed | Completed | #VALUE! |  | GP | 2024-09-16 | 2024-09-22 |  | 2024-12-20 | 2025-01-05 | 17 |  | 2024-10-08 | 2024-10-13 |  | 2025-01-07 | 2025-01-14 | 8 |  | 2024-10-10 | 2024-10-16 |  | 2025-01-24 | 2025-02-21 | 29 |  | 2024-10-07 | 2024-10-16 |  | 2025-01-24 | 2025-02-01 | 9 |  | 2024-10-18 | 2024-10-20 |  | 2025-02-01 | 2025-02-03 | 3 |  | 2024-10-22 | 2024-10-23 |  | 2025-02-26 | 2025-02-26 | 1 |  | 2024-10-06 | 2024-10-12 |  | 2024-12-30 | 2025-01-20 | 22 |  | 2024-10-05 | 2024-10-20 |  | 2024-12-16 | 2025-01-09 | 25 |  | 2024-10-23 | 2024-10-26 |  | 2025-02-28 | 2025-03-07 | 8 |  | 2024-10-26 | 2024-10-27 |  | 2025-03-08 | 2025-03-11 | 4 |  |  | 2024-12-01
DNC | 75 | PSS-4 | ACL | WTG 073 | Precast | F16 | Menard | Done | 532226 | 2669178 | 2022-12-31 | 2023-01-01 |  | 2022-12-31 | 2023-01-01 |  | 253 | 253 | 2024-04-15 | 2024-04-24 |  | 2024-04-09 | 2024-04-29 | 21 | [8 empty] | 2024-08-16 | 2024-08-16 |  | 2024-12-18 | 2024-12-21 | 4 |  | 2024-08-17 | 2024-08-17 |  | 2024-12-22 | 2024-12-24 | 3 |  | 2024-08-18 | 2024-08-18 |  | 2024-12-27 | 2024-12-27 | 1 |  | 2024-08-19 | 2024-08-20 |  | 2024-12-30 | 2024-12-30 | 1 |  | 2024-08-22 | 2024-08-31 |  | 2024-12-31 | 2025-01-06 | 7 |  | 2024-09-03 | 2024-09-04 |  | 2025-01-10 | 2025-01-10 | 1 | 24 |  | 2024-09-05 | 2024-09-11 |  | 2025-01-16 | 2025-03-03 | 47 |  | 2024-09-05 | 2024-09-11 |  | 2025-01-30 | 2025-01-30 | 1 |  |  |  | 2024-08-29 | 2024-09-12 |  | 2024-12-26 | 2025-01-18 | 24 |  | 2024-09-09 | 2024-09-15 |  | Completed | Completed | #VALUE! |  | 2024-09-09 | 2024-09-15 |  | 2025-01-24 | 2025-02-01 | 9 |  | GP (Reuse) | 2024-09-16 | 2024-09-22 |  | 2024-12-30 | 2025-01-25 | 27 |  | 2024-10-08 | 2024-10-13 |  | 2025-02-03 | 2025-02-12 | 10 |  | 2024-10-18 | 2024-10-24 |  | 2025-02-06 | 2025-02-21 | 16 |  | 2024-10-16 | 2024-10-25 |  | 2025-02-16 | 2025-02-23 | 8 |  | 2024-10-27 | 2024-10-29 |  | 2025-02-23 | 2025-02-25 | 3 |  | 2024-10-30 | 2024-10-31 |  | 2025-02-27 | 2025-02-27 | 1 |  | 2024-10-06 | 2024-10-12 |  | 2024-12-28 | 2025-01-25 | 29 |  | 2024-10-05 | 2024-10-20 |  | 2024-12-16 | 2025-01-09 | 25 |  | 2024-10-31 | 2024-11-03 |  | 2025-02-28 | 2025-03-07 | 8 |  | 2024-11-03 | 2024-11-04 |  | 2025-03-08 | 2025-03-09 | 2 |  |  | 2024-12-01
MECC | 76 | PSS-4 | ACL | WTG 058 | FDN | F16 | Menard | Done | 531772 | 2667470 | 2022-12-31 | 2023-01-01 |  | 2022-12-31 | 2023-01-01 |  | 253 | 253 | 2024-02-26 | 2024-03-06 |  | 2024-02-14 | 2024-02-26 | 13 | [8 empty] | 2024-07-23 | 2024-07-23 |  | 2024-04-07 | 2024-04-09 | 3 |  | 2024-07-24 | 2024-07-24 |  | 2024-04-10 | 2024-04-10 | 1 |  | 2024-07-25 | 2024-07-25 |  | 2024-04-11 | 2024-04-11 | 1 |  | 2024-07-26 | 2024-07-27 |  | 2024-04-12 | 2024-04-14 | 3 |  | 2024-07-29 | 2024-08-07 |  | 2024-04-16 | 2024-05-10 | 25 |  | 2024-08-10 | 2024-08-11 |  | 2024-05-11 | 2024-05-12 | 2 | 36 |  | 2024-08-12 | 2024-08-18 |  | 2024-06-05 | 2025-03-07 | 276 |  | 2024-08-19 | 2024-08-19 |  | 2024-06-06 | 2024-06-06 | 1 |  |  |  | 2024-08-05 | 2024-08-19 |  | 2024-06-25 | 2025-01-12 | 202 |  | 2024-08-08 | 2024-08-14 |  | Completed | Completed | #VALUE! |  | 2024-08-08 | 2024-08-14 |  | 2024-05-22 | 2024-06-09 | 19 |  | GP | 2024-08-15 | 2024-08-21 |  | 2024-05-22 | 2024-06-09 | 19 |  | 2024-09-02 | 2024-09-07 |  | 2024-10-17 | 2024-10-27 | 11 |  | 2024-08-30 | 2024-09-05 |  | 2025-01-25 | 2025-02-07 | 14 |  | 2024-09-10 | 2024-09-19 |  | 2024-11-20 | 2024-11-26 | 7 |  | 2024-09-21 | 2024-09-23 |  | 2024-12-04 | 2024-12-08 | 5 |  | 2024-09-11 | 2024-09-12 |  | 2025-02-27 | 2025-02-27 | 1 |  | 2024-08-27 | 2024-09-02 |  | 2024-12-27 | 2025-01-02 | 7 |  | 2024-09-12 | 2024-09-27 |  | 2024-12-16 | 2025-01-09 | 25 |  | 2024-09-12 | 2024-09-15 |  | 2025-02-28 | 2025-03-07 | 8 |  | 2024-09-27 | 2024-09-28 |  | 2025-03-08 | 2025-03-09 | 2 |  |  | 2024-12-01
DNC | 77 | PSS-4 | AGE24L | WTG 056 | Precast | F12 | Menard | Done | 531393 | 2669443 | 2023-06-10 | 2023-06-11 |  | 2023-06-10 | 2023-06-11 |  | 199 | 199 | 2024-05-26 | 2024-06-04 |  | 2024-03-08 | 2024-03-14 | 7 | [8 empty] | 2024-09-12 | 2024-09-12 |  | 2024-04-12 | 2024-04-14 | 3 |  | 2024-09-13 | 2024-09-13 |  | 2024-04-16 | 2024-04-18 | 3 |  | 2024-09-14 | 2024-09-14 |  | 2024-04-19 | 2024-04-19 | 1 |  | 2024-09-15 | 2024-09-16 |  | 2024-04-22 | 2024-04-24 | 3 |  | 2024-09-18 | 2024-09-27 |  | 2024-04-26 | 2024-06-07 | 43 |  | 2024-10-08 | 2024-10-09 |  | 2024-06-08 | 2024-06-09 | 2 | 59 |  | 2024-10-10 | 2024-10-16 |  | 2024-06-30 | 2025-02-27 | 243 |  | 2024-10-10 | 2024-10-16 |  | 2024-07-06 | 2024-07-07 | 2 |  |  |  | 2024-09-25 | 2024-10-09 |  | 2024-11-20 | 2025-01-15 | 57 |  | 2024-09-07 | 2024-09-13 |  | Completed | Completed | #VALUE! |  | 2024-09-07 | 2024-09-13 |  | 2024-09-25 | 2024-10-04 | 10 |  | GP | 2024-09-14 | 2024-09-20 |  | 2024-09-25 | 2024-10-04 | 10 |  | 2024-10-31 | 2024-11-05 |  | 2024-10-05 | 2024-10-19 | 15 |  | 2024-10-17 | 2024-10-23 |  | 2024-12-28 | 2025-02-26 | 61 |  | 2024-11-08 | 2024-11-17 |  | 2024-10-21 | 2024-11-17 | 28 |  | 2024-11-19 | 2024-11-21 |  | 2024-11-19 | 2024-12-07 | 19 |  | 2024-10-29 | 2024-10-30 |  | 2025-02-28 | 2025-03-02 | 3 |  | 2024-10-17 | 2024-10-23 |  | 2024-12-04 | 2024-12-28 | 25 |  | 2024-11-01 | 2024-11-16 |  | 2024-12-16 | 2025-01-09 | 25 |  | 2024-10-30 | 2024-11-02 |  | 2025-03-07 | 2025-03-09 | 3 |  | 2024-11-21 | 2024-11-22 |  | 2025-03-11 | 2025-03-12 | 2 |  |  | 2024-12-01
MSC | 78 | PSS-4 | AGE24L | WTG 041 | Precast | F15 | Menard | Done | 530552 | 2669748 | 2023-06-10 | 2023-06-11 |  | 2023-06-10 | 2023-06-11 |  | 199 | 199 | 2024-06-06 | 2024-06-15 |  | 2024-05-27 | 2024-06-11 | 16 | [8 empty] | 2024-09-08 | 2024-09-08 |  | 2024-09-30 | 2024-10-05 | 6 |  | 2024-09-09 | 2024-09-09 |  | 2024-10-07 | 2024-10-07 | 1 |  | 2024-09-10 | 2024-09-10 |  | 2024-10-13 | 2024-10-13 | 1 |  | 2024-09-11 | 2024-09-12 |  | 2024-10-19 | 2024-10-20 | 2 |  | 2024-09-16 | 2024-09-23 |  | 2024-10-21 | 2024-10-26 | 6 |  | 2024-09-26 | 2024-09-27 |  | 2024-10-27 | 2024-10-28 | 2 | 29 |  | 2024-09-29 | 2024-10-05 |  | 2024-11-08 | 2025-02-12 | 97 |  | 2024-09-29 | 2024-10-05 |  | 2024-11-11 | 2024-11-11 | 1 |  |  |  | 2024-09-23 | 2024-10-07 |  | 2024-11-21 | 2025-01-14 | 55 |  | 2024-09-11 | 2024-09-17 |  | Completed | Completed | #VALUE! |  | 2024-09-11 | 2024-09-17 |  | 2024-10-19 | 2024-11-10 | 23 |  | SS Jadeja | 2024-10-03 | 2024-10-09 |  | 2024-10-19 | 2024-11-10 | 23 |  | 2024-10-20 | 2024-10-25 |  | 2024-11-01 | 2024-12-02 | 32 |  | 2024-10-15 | 2024-10-21 |  | 2024-12-28 | 2025-02-27 | 62 |  | 2024-10-27 | 2024-11-05 |  | 2024-12-08 | 2024-12-17 | 10 |  | 2024-11-06 | 2024-11-08 |  | 2024-12-31 | 2025-01-03 | 4 |  | 2024-10-27 | 2024-10-28 |  | 2025-03-01 | 2025-03-01 | 1 |  | 2024-10-19 | 2024-10-25 |  | 2024-12-11 | 2025-01-20 | 41 |  | 2024-10-05 | 2024-10-20 |  | 2024-12-16 | 2025-01-09 | 25 |  | 2024-10-28 | 2024-10-31 |  | 2025-03-07 | 2025-03-09 | 3 |  | 2024-11-08 | 2024-11-09 |  | 2025-03-09 | 2025-03-10 | 2 |  |  | 2024-12-01
DNC | 79 | PSS-4 | AHEJ5L | WTG 053 | Precast | F11 | Bauer | Done | 530825 | 2672402 | 2024-01-12 | 2024-02-01 |  | 2024-01-12 | 2024-02-01 |  | 253 | 253 | 2024-05-29 | 2024-06-07 |  | 2024-11-25 | 2024-12-09 | 15 | [8 empty] | 2024-10-12 | 2024-10-12 |  | 2024-12-12 | 2024-12-14 | 3 |  | 2024-10-13 | 2024-10-13 |  | 2024-12-16 | 2024-12-16 | 1 |  | 2024-10-14 | 2024-10-14 |  | 2024-12-17 | 2024-12-17 | 1 |  | 2024-10-15 | 2024-10-16 |  | 2024-12-20 | 2024-12-20 | 1 |  | 2024-10-26 | 2024-11-02 |  | 2024-12-21 | 2024-12-28 | 8 |  | 2024-11-05 | 2024-11-06 |  | 2024-12-28 | 2024-12-29 | 2 | 18 |  | 2024-11-08 | 2024-11-14 |  | 2025-01-10 | 2025-03-11 | 61 |  | 2024-11-08 | 2024-11-14 |  | 2025-01-17 | 2025-01-17 | 1 |  |  |  | 2024-11-02 | 2024-11-16 |  | 2024-12-16 | 2025-01-30 | 46 |  | 2024-10-04 | 2024-10-10 |  | 2024-05-18 | 2024-05-28 | 11 |  | 2024-10-04 | 2024-10-10 |  | 2025-01-20 | 2025-01-26 | 7 |  | GP | 2024-11-12 | 2024-11-18 |  | 2024-12-26 | 2025-01-22 | 28 |  | 2024-12-02 | 2024-12-07 |  | 2025-01-27 | 2025-02-03 | 8 |  | 2024-11-24 | 2024-11-30 |  | 2025-02-05 | 2025-03-02 | 26 |  | 2024-12-09 | 2024-12-15 |  | 2025-03-12 | 2025-03-25 | 14 |  | 2024-12-16 | 2024-12-18 |  | 2025-03-28 | 2025-03-30 | 3 |  | 2024-12-06 | 2024-12-07 |  | 2025-03-18 | 2025-03-18 | 1 |  | 2024-11-24 | 2024-11-30 |  | 2025-01-27 | 2025-02-18 | 23 |  | 2024-11-20 | 2024-12-05 |  | 2025-01-01 | 2025-02-06 | 37 |  | 2024-12-07 | 2024-12-10 |  | 2025-03-26 | 2025-03-29 | 4 |  | 2024-12-18 | 2024-12-19 |  | 2025-04-17 | 2025-04-17 | 1 |  |  | 2024-12-01
MSC | 80 | PSS-4 | AGE24L | WTG 028 | Precast | F15 | Menard | Done | 529908 | 2669026 | 2023-06-09 | 2023-06-10 |  | 2023-06-09 | 2023-06-10 |  | 163 | 163 | 2024-06-05 | 2024-06-14 |  | 2024-05-14 | 2024-05-25 | 12 | [8 empty] | 2024-09-04 | 2024-09-04 |  | 2024-09-28 | 2024-10-01 | 4 |  | 2024-09-05 | 2024-09-05 |  | 2024-10-03 | 2024-10-05 | 3 |  | 2024-09-06 | 2024-09-06 |  | 2024-10-06 | 2024-10-06 | 1 |  | 2024-09-07 | 2024-09-08 |  | 2024-10-08 | 2024-10-09 | 2 |  | 2024-09-10 | 2024-09-17 |  | 2024-10-10 | 2024-10-19 | 10 |  | 2024-09-20 | 2024-09-21 |  | 2024-10-20 | 2024-10-21 | 2 | 24 |  | 2024-09-23 | 2024-09-29 |  | 2024-11-06 | 2025-02-20 | 107 |  | 2024-09-23 | 2024-09-29 |  | 2024-11-06 | 2024-11-06 | 1 |  |  |  | 2024-09-17 | 2024-10-01 |  | 2024-11-23 | 2025-01-14 | 53 |  | 2024-09-03 | 2024-09-09 |  | 2024-05-10 | 2024-05-16 | 7 |  | 2024-09-03 | 2024-09-09 |  | 2024-10-20 | 2024-10-30 | 11 |  | GP | 2024-09-27 | 2024-10-03 |  | 2024-10-20 | 2024-10-30 | 11 |  | 2024-10-13 | 2024-10-18 |  | 2024-11-02 | 2024-11-19 | 18 |  | 2024-10-09 | 2024-10-15 |  | 2025-01-10 | 2025-02-23 | 45 |  | 2024-10-20 | 2024-10-29 |  | 2024-11-28 | 2024-12-05 | 8 |  | 2024-10-30 | 2024-11-01 |  | 2024-12-06 | 2024-12-10 | 5 |  | 2024-10-21 | 2024-10-22 |  | 2025-03-01 | 2025-03-01 | 1 |  | 2024-10-11 | 2024-10-17 |  | 2024-12-06 | 2024-12-12 | 7 |  | 2024-10-05 | 2024-10-20 |  | 2024-12-16 | 2025-01-09 | 25 |  | 2024-10-22 | 2024-10-25 |  | 2025-03-07 | 2025-03-09 | 3 |  | 2024-11-01 | 2024-11-02 |  | 2025-03-09 | 2025-03-11 | 3 |  |  | 2024-12-01
MSC | 81 | PSS-4 | AGE24L | WTG 027 | Precast | F15 | Bauer | Done | 529719 | 2670012 | 2023-06-09 | 2023-06-10 |  | 2023-06-09 | 2023-06-10 |  | 219 | 219 | 2024-06-26 | 2024-07-05 |  | 2024-12-31 | 2025-01-11 | 12 | [8 empty] | 2024-09-26 | 2024-09-26 |  | 2025-01-19 | 2025-01-22 | 4 |  | 2024-09-27 | 2024-09-27 |  | 2025-01-22 | 2025-01-23 | 2 |  | 2024-09-28 | 2024-09-28 |  | 2025-01-23 | 2025-01-23 | 1 |  | 2024-09-29 | 2024-09-30 |  | 2025-01-27 | 2025-01-27 | 1 |  | 2024-10-10 | 2024-10-17 |  | 2025-01-27 | 2025-01-30 | 4 |  | 2024-10-20 | 2024-10-21 |  | 2025-01-31 | 2025-01-31 | 1 | 13 |  | 2024-10-23 | 2024-10-29 |  | 2025-02-10 | 2025-03-09 | 28 |  | 2024-10-23 | 2024-10-29 |  | 2025-02-09 | 2025-02-09 | 1 |  |  |  | 2024-10-17 | 2024-10-31 |  | 2025-01-22 | 2025-01-29 | 8 |  | 2024-10-05 | 2024-10-11 |  | Completed | 2024-05-15 | #VALUE! |  | 2024-10-05 | 2024-10-11 |  | 2025-02-04 | 2025-02-20 | 17 |  | GP (Reuse) | 2024-10-27 | 2024-11-02 |  | 2025-02-04 | 2025-02-20 | 17 |  | 2024-11-16 | 2024-11-21 |  | 2025-02-21 | 2025-03-01 | 9 |  | 2024-11-08 | 2024-11-14 |  | 2025-02-11 | 2025-02-22 | 12 |  | 2024-11-23 | 2024-12-02 |  | 2025-03-11 | 2025-03-13 | 3 |  | 2024-12-03 | 2024-12-05 |  | 2025-03-14 | 2025-03-15 | 2 |  | 2024-11-20 | 2024-11-21 |  | 2025-03-02 | 2025-03-02 | 1 |  | 2024-11-12 | 2024-11-18 |  | 2024-12-28 | 2025-01-27 | 31 |  | 2024-11-01 | 2024-11-16 |  | 2024-12-16 | 2025-01-09 | 25 |  | 2024-11-21 | 2024-11-24 |  | 2025-03-07 | 2025-03-09 | 3 |  | 2024-12-05 | 2024-12-06 |  | 2025-03-10 | 2025-03-13 | 4 |  |  | 2024-12-01
UNIQUE INF | 82 | PSS-4 | AGE24L | WTG 015 | Precast | F15 | Menard | Done | 528878 | 2670317 | 2023-06-11 | 2023-06-12 |  | 2023-06-11 | 2023-06-12 |  | 219 | 219 | 2024-06-17 | 2024-06-26 |  | 2024-06-18 | 2024-06-28 | 11 | [8 empty] | 2024-09-20 | 2024-09-20 |  | 2024-10-06 | 2024-10-08 | 3 |  | 2024-09-21 | 2024-09-21 |  | 2024-10-19 | 2024-10-21 | 3 |  | 2024-09-22 | 2024-09-22 |  | 2024-11-02 | 2024-11-02 | 1 |  | 2024-09-23 | 2024-09-24 |  | 2024-11-05 | 2024-11-06 | 2 |  | 2024-10-02 | 2024-10-09 |  | 2024-11-06 | 2024-11-19 | 14 |  | 2024-10-12 | 2024-10-13 |  | 2024-11-22 | 2024-11-23 | 2 | 49 |  | 2024-10-15 | 2024-10-21 |  | 2024-12-07 | 2025-03-10 | 94 |  | 2024-10-15 | 2024-10-21 |  | 2024-11-30 | 2024-11-30 | 1 |  |  |  | 2024-10-09 | 2024-10-23 |  | 2024-10-24 | 2025-01-16 | 85 |  | 2024-09-27 | 2024-10-03 |  | 2024-05-09 | 2024-05-12 | 4 |  | 2024-09-27 | 2024-10-03 |  | 2024-10-19 | 2024-10-30 | 12 |  | SS Jadeja | 2024-10-19 | 2024-10-25 |  | 2024-10-19 | 2024-10-30 | 12 |  | 2024-11-07 | 2024-11-12 |  | 2024-11-15 | 2024-12-21 | 37 |  | 2024-10-31 | 2024-11-06 |  | 2025-01-22 | 2025-02-18 | 28 |  | 2024-11-14 | 2024-11-23 |  | 2025-02-22 | 2025-02-28 | 7 |  | 2024-11-24 | 2024-11-26 |  | 2025-03-01 | 2025-03-04 | 4 |  | 2024-11-12 | 2024-11-13 |  | 2025-03-01 | 2025-03-01 | 1 |  | 2024-11-04 | 2024-11-10 |  | 2024-12-07 | 2024-12-27 | 21 |  | 2024-11-01 | 2024-11-16 |  | 2024-12-16 | 2025-01-09 | 25 |  | 2024-11-13 | 2024-11-16 |  | 2025-03-07 | 2025-03-09 | 3 |  | 2024-11-26 | 2024-11-27 |  | 2025-03-12 | 2025-03-14 | 3 |  |  | 2024-12-01
DNC | 83 | PSS-4 | ACL | WTG 052 | Precast | F5 | Bauer | Done | 530635 | 2673389 | 2024-01-18 | 2024-02-02 |  | 2024-01-18 | 2024-02-02 |  | 253 | 253 | 2024-05-28 | 2024-06-06 |  | 2024-06-27 | 2024-11-26 | 153 | [8 empty] | 2024-10-11 | 2024-10-11 |  | 2024-12-10 | 2024-12-11 | 2 |  | 2024-10-12 | 2024-10-12 |  | 2024-12-12 | 2024-12-12 | 1 |  | 2024-10-13 | 2024-10-13 |  | 2024-12-16 | 2024-12-16 | 1 |  | 2024-10-14 | 2024-10-15 |  | 2024-12-23 | 2024-12-24 | 2 |  | 2024-10-25 | 2024-11-01 |  | 2024-12-25 | 2024-12-30 | 6 |  | 2024-11-04 | 2024-11-05 |  | 2024-12-30 | 2025-01-01 | 3 | 23 |  | 2024-11-07 | 2024-11-13 |  | 2025-01-05 | 2025-03-13 | 68 |  | 2024-11-07 | 2024-11-13 |  | 2025-01-12 | 2025-01-12 | 1 |  |  |  | 2024-11-01 | 2024-11-15 |  | 2024-12-16 | 2025-01-27 | 43 |  | 2024-10-04 | 2024-10-10 |  | 2024-05-26 | 2024-06-15 | 21 |  | 2024-10-04 | 2024-10-10 |  | 2025-01-18 | 2025-01-24 | 7 |  | GP (Reuse) | 2024-11-11 | 2024-11-17 |  | 2025-01-08 | 2025-01-23 | 16 |  | 2024-12-01 | 2024-12-06 |  | 2025-01-29 | 2025-02-06 | 9 |  | 2024-11-23 | 2024-11-29 |  | 2025-02-12 | 2025-03-08 | 25 |  | 2024-12-08 | 2024-12-17 |  | 2025-03-04 | 2025-03-13 | 10 |  | 2024-12-18 | 2024-12-20 |  | 2025-03-14 | 2025-03-17 | 4 |  | 2024-12-05 | 2024-12-06 |  | 2025-03-18 | 2025-03-18 | 1 |  | 2024-11-23 | 2024-11-29 |  | 2025-01-07 | 2025-01-12 | 6 |  | 2024-11-20 | 2024-12-05 |  | 2025-01-30 | 2025-02-19 | 21 |  | 2024-12-06 | 2024-12-09 |  | 2025-03-17 | 2025-03-19 | 3 |  | 2024-12-20 | 2024-12-21 |  | 2025-03-19 | 2025-03-20 | 2 |  |  | 2024-12-01
UNIQUE INF | 84 | PSS-4 | AGE24L | WTG 038 | Precast | F10 | Bauer | Done | 529984 | 2672707 | 2024-01-19 | 2024-02-03 |  | 2024-01-19 | 2024-02-03 |  | 211 | 211 | 2024-06-10 | 2024-06-19 |  | 2024-06-05 | 2024-06-12 | 8 | [8 empty] | 2024-09-21 | 2024-09-21 |  | 2024-10-23 | 2024-10-27 | 5 |  | 2024-09-22 | 2024-09-22 |  | 2024-11-09 | 2024-11-13 | 5 |  | 2024-09-23 | 2024-09-23 |  | 2024-11-29 | 2024-11-30 | 2 |  | 2024-09-24 | 2024-09-25 |  | 2024-12-03 | 2024-12-03 | 1 |  | 2024-09-27 | 2024-10-06 |  | 2024-12-04 | 2024-12-14 | 11 |  | 2024-10-15 | 2024-10-16 |  | 2024-12-20 | 2024-12-21 | 2 | 60 |  | 2024-10-17 | 2024-10-23 |  | 2024-12-27 | 2025-04-01 | 96 |  | 2024-10-17 | 2024-10-23 |  | 2024-12-31 | 2024-12-31 | 1 |  |  |  | 2024-10-04 | 2024-10-18 |  | 2025-01-04 | 2025-02-21 | 49 |  | 2024-09-24 | 2024-09-30 |  | 2024-05-17 | 2024-05-22 | 6 |  | 2024-09-24 | 2024-09-30 |  | 2025-01-11 | 2025-01-17 | 7 |  | SS Jadeja | 2024-10-01 | 2024-10-07 |  | 2024-12-06 | 2025-01-17 | 43 |  | 2024-11-12 | 2024-11-17 |  | 2025-01-31 | 2025-02-09 | 10 |  | 2024-11-03 | 2024-11-09 |  | 2025-02-22 | 2025-03-10 | 17 |  | 2024-11-20 | 2024-11-29 |  | 2025-03-15 | 2025-03-25 | 11 |  | 2024-12-01 | 2024-12-03 |  | 2025-03-27 | 2025-04-01 | 6 |  | 2024-11-15 | 2024-11-16 |  | 2025-03-16 | 2025-03-16 | 1 |  | 2024-11-03 | 2024-11-09 |  | 2025-01-23 | 2025-02-07 | 16 |  | 2024-11-01 | 2024-11-16 |  | 2025-01-15 | 2025-02-06 | 23 |  | 2024-11-16 | 2024-11-19 |  | 2025-03-24 | 2025-03-25 | 2 |  | 2024-12-03 | 2024-12-04 |  | 2025-03-31 | 2025-04-01 | 2 |  |  | 2024-12-01
UNIQUE INF | 85 | PSS-4 | AHEJ5L | WTG 037 | Precast | F6 | Bauer | Done | 529795 | 2673693 | 2024-01-16 | 2024-02-01 |  | 2024-01-16 | 2024-02-01 |  | 253 | 253 | 2024-05-19 | 2024-05-28 |  | 2024-06-15 | 2024-06-27 | 13 |  | Yes | 2024-11-20 | 2024-11-30 |  | 2024-11-10 | 2024-11-30 |  | 2024-10-05 | 2024-10-05 |  | 2024-12-08 | 2024-12-12 | 5 |  | 2024-10-06 | 2024-10-06 |  | 2024-12-13 | 2024-12-17 | 5 |  | 2024-10-07 | 2024-10-07 |  | 2024-12-18 | 2024-12-18 | 1 |  | 2024-10-08 | 2024-10-09 |  | 2024-12-21 | 2024-12-22 | 2 |  | 2024-10-17 | 2024-10-24 |  | 2024-12-29 | 2025-01-05 | 8 |  | 2024-10-27 | 2024-10-28 |  | 2025-01-06 | 2025-01-07 | 2 | 31 |  | 2024-10-30 | 2024-11-05 |  | 2025-01-10 | 2025-04-30 | 111 |  | 2024-10-30 | 2024-11-05 |  | 2025-01-15 | 2025-01-15 | 1 |  |  |  | 2024-10-24 | 2024-11-07 |  | 2025-01-06 | 2025-01-24 | 19 |  | 2024-09-26 | 2024-10-02 |  | 2024-05-28 | 2024-06-20 | 24 |  | 2024-09-26 | 2024-10-02 |  | 2025-01-17 | 2025-02-05 | 20 |  | SS Jadeja | 2024-11-03 | 2024-11-09 |  | 2025-01-08 | 2025-01-16 | 9 |  | 2024-11-22 | 2024-11-27 |  | 2025-02-08 | 2025-02-14 | 7 |  | 2024-11-15 | 2024-11-21 |  | 2025-01-30 | 2025-03-10 | 40 |  | 2024-11-29 | 2024-12-08 |  | 2025-03-26 | 2025-03-30 | 5 |  | 2024-12-09 | 2024-12-11 |  | 2025-03-31 | 2025-04-02 | 3 |  | 2024-11-27 | 2024-11-28 |  | 2025-03-22 | 2025-03-22 | 1 |  | 2024-11-15 | 2024-11-21 |  | 2024-12-18 | 2025-03-10 | 83 |  | 2024-11-01 | 2024-11-16 |  | 2025-01-01 | 2025-02-06 | 37 |  | 2024-11-28 | 2024-12-01 |  | 2025-03-26 | 2025-03-29 | 4 |  | 2024-12-11 | 2024-12-12 |  | 2025-04-17 | 2025-04-18 | 2 |  |  | 2024-12-01
MSC | 86 | PSS-4 | AGE24L | WTG 024 | Precast | F9 | Bauer | Done | 529151 | 2672972 | 2024-01-19 | 2024-02-02 |  | 2024-01-19 | 2024-02-02 |  | 253 | 253 | 2024-06-18 | 2024-06-27 |  | 2024-06-12 | 2024-06-24 | 13 |  | Yes | 2024-12-15 | 2024-12-24 |  | 2024-12-11 | 2025-01-03 |  | 2024-09-22 | 2024-09-22 |  | 2025-01-24 | 2025-01-25 | 2 |  | 2024-09-23 | 2024-09-23 |  | 2025-01-25 | 2025-01-26 | 2 |  | 2024-09-24 | 2024-09-24 |  | 2025-01-26 | 2025-01-26 | 1 |  | 2024-09-25 | 2024-09-26 |  | 2025-02-01 | 2025-02-02 | 2 |  | 2024-10-04 | 2024-10-11 |  | 2025-02-02 | 2025-02-07 | 6 |  | 2024-10-14 | 2024-10-15 |  | 2025-02-08 | 2025-02-09 | 2 | 17 |  | 2024-10-17 | 2024-10-23 |  | 2025-02-12 | 2025-04-13 | 61 |  | 2024-10-17 | 2024-10-23 |  | 2025-02-13 | 2025-02-13 | 1 |  |  |  | 2024-10-11 | 2024-10-25 |  | 2025-01-28 | 2025-02-25 | 29 |  | 2024-09-27 | 2024-10-03 |  | 2024-05-20 | 2024-05-27 | 8 |  | 2024-09-27 | 2024-10-03 |  | 2025-02-12 | 2025-02-23 | 12 |  | GP | 2024-10-21 | 2024-10-27 |  | 2025-02-12 | 2025-02-23 | 12 |  | 2024-11-09 | 2024-11-14 |  | 2025-02-24 | 2025-03-06 | 11 |  | 2024-11-02 | 2024-11-08 |  | 2025-03-07 | 2025-03-22 | 16 |  | 2024-11-16 | 2024-11-25 |  | 2025-03-23 | 2025-03-26 | 4 |  | 2024-11-26 | 2024-11-28 |  | 2025-03-27 | 2025-03-28 | 2 |  | 2024-11-14 | 2024-11-15 |  | 2025-03-23 | 2025-03-23 | 1 |  | 2024-11-04 | 2024-11-10 |  | 2024-12-17 | 2024-12-31 | 15 |  | 2024-11-01 | 2024-11-16 |  | 2025-01-15 | 2025-02-06 | 23 |  | 2024-11-15 | 2024-11-18 |  | 2025-03-24 | 2025-03-25 | 2 |  | 2024-11-28 | 2024-11-29 |  | 2025-03-31 | 2025-04-01 | 2 |  |  | 2024-12-01
AB INFRA | 87 | PSS-4 | AHEJ5L | WTG 023 | Precast | F6 | Bauer | Done | 528962 | 2673958 | 2024-01-18 | 2024-02-02 |  | 2024-01-18 | 2024-02-02 |  | 253 | 253 | 2024-05-17 | 2024-05-26 |  | 2024-11-26 | 2024-12-04 | 9 | [8 empty] | 2024-09-29 | 2024-09-29 |  | 2024-12-09 | 2024-12-11 | 3 |  | 2024-09-30 | 2024-09-30 |  | 2024-12-11 | 2024-12-12 | 2 |  | 2024-10-01 | 2024-10-01 |  | 2024-12-12 | 2024-12-12 | 1 |  | 2024-10-02 | 2024-10-03 |  | 2024-12-15 | 2024-12-16 | 2 |  | 2024-10-09 | 2024-10-16 |  | 2024-12-27 | 2025-01-16 | 21 |  | 2024-10-19 | 2024-10-20 |  | 2025-01-17 | 2025-01-18 | 2 | 41 |  | 2024-10-22 | 2024-10-28 |  | 2025-02-10 | 2025-04-08 | 58 |  | 2024-10-22 | 2024-10-28 |  | 2025-02-09 | 2025-02-09 | 1 |  |  |  | 2024-10-16 | 2024-10-30 |  | 2024-12-17 | 2025-03-04 | 78 |  | 2024-09-18 | 2024-09-24 |  | 2024-05-26 | 2024-06-02 | 8 |  | 2024-09-18 | 2024-09-24 |  | 2025-02-02 | 2025-02-10 | 9 |  | Varudi | 2024-10-26 | 2024-11-01 |  | 2025-01-31 | 2025-02-09 | 10 |  | 2024-11-13 | 2024-11-18 |  | 2025-02-12 | 2025-02-23 | 12 |  | 2024-11-07 | 2024-11-13 |  | 2025-03-10 | 2025-03-22 | 13 |  | 2024-11-20 | 2024-11-29 |  | 2025-03-26 | 2025-03-30 | 5 |  | 2024-11-30 | 2024-12-02 |  | 2025-03-31 | 2025-04-05 | 6 |  | 2024-11-19 | 2024-11-20 |  | 2025-03-25 | 2025-03-25 | 1 |  | 2024-11-07 | 2024-11-13 |  | 2024-12-15 | 2024-12-30 | 16 |  | 2024-11-01 | 2024-11-16 |  | 2025-01-01 | 2025-02-06 | 37 |  | 2024-11-20 | 2024-11-23 |  | 2025-03-26 | 2025-03-29 | 4 |  | 2024-12-02 | 2024-12-03 |  | 2025-04-17 | 2025-04-17 | 1 |  |  | 2024-12-01
UNIQUE INF | 88 | PSS-4 | AGE24L | WTG 012 | Precast | F9 | Sarita infra | Done | 528311 | 2673276 | 2024-01-17 | 2024-02-02 |  | 2024-01-17 | 2024-02-02 |  | 253 | 253 | 2024-06-07 | 2024-06-16 |  | 2024-09-23 | 2024-11-22 | 61 | [8 empty] | 2024-09-10 | 2024-09-10 |  | 2024-12-02 | 2024-12-04 | 3 |  | 2024-09-11 | 2024-09-11 |  | 2024-12-04 | 2024-12-06 | 3 |  | 2024-09-12 | 2024-09-12 |  | 2024-12-08 | 2024-12-08 | 1 |  | 2024-09-13 | 2024-09-14 |  | 2024-12-11 | 2024-12-11 | 1 |  | 2024-09-18 | 2024-09-25 |  | 2024-12-26 | 2025-01-10 | 16 |  | 2024-09-28 | 2024-09-29 |  | 2025-01-13 | 2025-01-13 | 1 | 43 |  | 2024-10-01 | 2024-10-07 |  | 2025-01-18 | 2025-04-22 | 95 |  | 2024-10-01 | 2024-10-07 |  | 2025-01-23 | 2025-01-23 | 1 |  |  |  | 2024-09-25 | 2024-10-09 |  | 2024-12-14 | 2025-02-25 | 74 |  | 2024-09-11 | 2024-09-17 |  | 2024-05-20 | 2024-05-28 | 9 |  | 2024-09-11 | 2024-09-17 |  | 2025-01-22 | 2025-01-31 | 10 |  | GP | 2024-10-05 | 2024-10-11 |  | 2025-01-10 | 2025-01-25 | 16 |  | 2024-10-22 | 2024-10-27 |  | 2025-02-05 | 2025-02-12 | 8 |  | 2024-10-17 | 2024-10-23 |  | 2025-03-06 | 2025-03-15 | 10 |  | 2024-10-29 | 2024-11-07 |  | 2025-03-15 | 2025-03-22 | 8 |  | 2024-11-08 | 2024-11-10 |  | 2025-03-24 | 2025-03-25 | 2 |  | 2024-10-29 | 2024-10-30 |  | 2025-03-27 | 2025-03-27 | 1 |  | 2024-10-19 | 2024-10-25 |  | 2024-12-05 | 2024-12-11 | 7 |  | 2024-10-05 | 2024-10-20 |  | 2025-01-15 | 2025-02-06 | 23 |  | 2024-10-30 | 2024-11-02 |  | 2025-03-24 | 2025-03-25 | 2 |  | 2024-11-10 | 2024-11-11 |  | 2025-03-31 | 2025-04-01 | 2 |  |  | 2024-12-01
BALAJI & Co | 89 | PSS-4 | ACL | WTG 068 | Precast | F5 | Bauer | Done | 531279 | 2674110 | 2024-02-03 | 2024-02-04 |  | 2024-02-03 | 2024-02-04 |  | 253 | 253 | 2024-05-30 | 2024-06-08 |  | 2024-11-25 | 2024-12-02 | 8 | [8 empty] | 2024-10-17 | 2024-10-17 |  | 2024-12-06 | 2024-12-09 | 4 |  | 2024-10-18 | 2024-10-18 |  | 2024-12-11 | 2024-12-12 | 2 |  | 2024-10-19 | 2024-10-19 |  | 2024-12-12 | 2024-12-12 | 1 |  | 2024-10-20 | 2024-10-21 |  | 2024-12-16 | 2024-12-16 | 1 |  | 2024-11-02 | 2024-11-09 |  | 2024-12-26 | 2024-12-31 | 6 |  | 2024-11-12 | 2024-11-13 |  | 2025-01-01 | 2025-01-02 | 2 | 28 |  | 2024-11-15 | 2024-11-21 |  | 2025-01-06 | 2025-03-10 | 64 |  | 2024-11-15 | 2024-11-21 |  | 2025-01-07 | 2025-01-07 | 1 |  |  |  | 2024-11-09 | 2024-11-23 |  | 2024-12-06 | 2025-02-11 | 68 |  | 2024-10-12 | 2024-10-18 |  | Completed | Completed | #VALUE! |  | 2024-10-12 | 2024-10-18 |  | 2025-01-05 | 2025-01-15 | 11 |  | Odhav | 2024-11-19 | 2024-11-25 |  | 2024-12-20 | 2025-01-17 | 29 |  | 2024-12-17 | 2024-12-22 |  | 2025-01-29 | 2025-02-05 | 8 |  | 2024-12-01 | 2024-12-07 |  | 2025-02-17 | 2025-03-08 | 20 |  | 2024-12-24 | 2024-12-30 |  | 2025-02-10 | 2025-02-17 | 8 |  | 2024-12-31 | 2025-01-02 |  | 2025-02-17 | 2025-02-21 | 5 |  | 2024-12-13 | 2024-12-14 |  | 2025-03-13 | 2025-03-13 | 1 |  | 2024-12-01 | 2024-12-07 |  | 2024-12-17 | 2025-03-13 | 87 |  | 2024-11-20 | 2024-12-05 |  | 2025-01-30 | 2025-02-19 | 21 |  | 2024-12-14 | 2024-12-17 |  | 2025-03-17 | 2025-03-18 | 2 |  | 2025-01-02 | 2025-01-03 |  | 2025-03-19 | 2025-03-19 | 1 |  |  | 2024-12-01
POWER CORP | 90 | PSS-4 | ACL | WTG 051 | Precast | F5 | Bauer | Done | 530446 | 2674375 | 2024-01-20 | 2024-02-02 |  | 2024-01-20 | 2024-02-02 |  | 211 | 211 | 2024-05-20 | 2024-05-29 |  | 2024-11-13 | 2024-11-21 | 9 | [8 empty] | 2024-10-06 | 2024-10-06 |  | 2024-12-07 | 2024-12-10 | 4 |  | 2024-10-07 | 2024-10-07 |  | 2024-12-12 | 2024-12-16 | 5 |  | 2024-10-08 | 2024-10-08 |  | 2024-12-19 | 2024-12-19 | 1 |  | 2024-10-09 | 2024-10-10 |  | 2024-12-22 | 2024-12-22 | 1 |  | 2024-10-18 | 2024-10-25 |  | 2024-12-31 | 2025-01-18 | 19 |  | 2024-10-28 | 2024-10-29 |  | 2025-01-18 | 2025-01-19 | 2 | 44 |  | 2024-10-31 | 2024-11-06 |  | 2025-01-31 | 2025-03-15 | 44 |  | 2024-10-31 | 2024-11-06 |  | 2025-01-27 | 2025-01-27 | 1 |  |  |  | 2024-10-25 | 2024-11-08 |  | 2024-12-11 | 2025-02-08 | 60 |  | 2024-09-26 | 2024-10-02 |  | Completed | Completed | #VALUE! |  | 2024-09-26 | 2024-10-02 |  | 2025-01-12 | 2025-01-22 | 11 |  | SS Jadeja | 2024-11-04 | 2024-11-10 |  | 2025-01-10 | 2025-02-02 | 24 |  | 2024-11-23 | 2024-11-28 |  | 2025-02-07 | 2025-02-14 | 8 |  | 2024-11-16 | 2024-11-22 |  | 2025-02-19 | 2025-03-07 | 17 |  | 2024-11-30 | 2024-12-09 |  | 2025-03-12 | 2025-03-17 | 6 |  | 2024-12-10 | 2024-12-12 |  | 2025-03-18 | 2025-03-19 | 2 |  | 2024-11-28 | 2024-11-29 |  | 2025-03-13 | 2025-03-13 | 1 |  | 2024-11-16 | 2024-11-22 |  | 2025-01-25 | 2025-03-09 | 44 |  | 2024-11-01 | 2024-11-16 |  | 2025-01-30 | 2025-02-19 | 21 |  | 2024-11-29 | 2024-12-02 |  | 2025-03-17 | 2025-03-18 | 2 |  | 2024-12-12 | 2024-12-13 |  | 2025-03-19 | 2025-03-19 | 1 |  |  | 2024-12-01
MSC | 91 | PSS-4 | ACL | WTG 036 | Precast | F5 | Bauer | Done | 529606 | 2674680 | 2024-01-20 | 2024-02-02 |  | 2024-01-20 | 2024-02-02 |  | 253 | 253 | 2024-05-18 | 2024-05-27 |  | 2024-11-04 | 2024-11-13 | 10 |  | Yes | 2024-12-03 | 2024-12-12 |  | 2024-11-28 | 2024-12-19 |  | 2024-09-30 | 2024-09-30 |  | 2025-01-03 | 2025-01-04 | 2 |  | 2024-10-01 | 2024-10-01 |  | 2025-01-05 | 2025-01-06 | 2 |  | 2024-10-02 | 2024-10-02 |  | 2025-01-06 | 2025-01-06 | 1 |  | 2024-10-03 | 2024-10-04 |  | 2025-01-07 | 2025-01-08 | 2 |  | 2024-10-10 | 2024-10-17 |  | 2025-01-15 | 2025-01-19 | 5 |  | 2024-10-20 | 2024-10-21 |  | 2025-01-19 | 2025-01-20 | 2 | 18 |  | 2024-10-23 | 2024-10-29 |  | 2025-01-26 | 2025-03-22 | 56 |  | 2024-10-23 | 2024-10-29 |  | 2025-02-01 | 2025-02-01 | 1 |  |  |  | 2024-10-17 | 2024-10-31 |  | 2025-01-05 | 2025-01-29 | 25 |  | 2024-09-18 | 2024-09-24 |  | Completed | Completed | #VALUE! |  | 2024-09-18 | 2024-09-24 |  | 2025-02-05 | 2025-02-15 | 11 |  | Kesav | 2024-10-27 | 2024-11-02 |  | 2025-02-05 | 2025-02-22 | 18 |  | 2024-11-14 | 2024-11-19 |  | 2025-02-15 | 2025-02-23 | 9 |  | 2024-11-08 | 2024-11-14 |  | 2025-02-11 | 2025-03-08 | 26 |  | 2024-11-21 | 2024-11-30 |  | 2025-03-04 | 2025-03-07 | 4 |  | 2024-12-01 | 2024-12-03 |  | 2025-03-08 | 2025-03-16 | 9 | Loc. Hold (because of priority base other loc.) | 2024-11-20 | 2024-11-21 |  | 2025-03-14 | 2025-03-14 | 1 |  | 2024-11-08 | 2024-11-14 |  | 2025-01-02 | 2025-01-27 | 26 |  | 2024-11-01 | 2024-11-16 |  | 2025-01-30 | 2025-02-19 | 21 |  | 2024-11-21 | 2024-11-24 |  | 2025-03-17 | 2025-03-18 | 2 |  | 2024-12-03 | 2024-12-04 |  | 2025-03-19 | 2025-03-19 | 1 |  |  | 2024-12-01
UNIQUE INF | 92 | PSS-4 | AHEJ5L | WTG 011 | Precast | F6 | Bauer | Done | 528121 | 2674262 | 2024-01-18 | 2024-02-02 |  | 2024-01-18 | 2024-02-02 |  | 211 | 211 | 2024-05-09 | 2024-05-18 |  | 2024-06-25 | 2024-10-19 | 117 | [8 empty] | 2024-09-24 | 2024-09-24 |  | 2024-11-28 | 2024-12-04 | 7 |  | 2024-09-25 | 2024-09-25 |  | 2024-12-10 | 2024-12-11 | 2 |  | 2024-09-26 | 2024-09-26 |  | 2024-12-13 | 2024-12-13 | 1 |  | 2024-09-27 | 2024-09-28 |  | 2024-12-14 | 2024-12-15 | 2 |  | 2024-10-02 | 2024-10-09 |  | 2024-12-15 | 2024-12-25 | 11 |  | 2024-10-12 | 2024-10-13 |  | 2024-12-25 | 2024-12-26 | 2 | 29 |  | 2024-10-15 | 2024-10-21 |  | 2025-01-11 | 2025-02-26 | 47 |  | 2024-10-15 | 2024-10-21 |  | 2025-01-03 | 2025-01-03 | 1 |  |  |  | 2024-10-09 | 2024-10-23 |  | 2024-12-15 | 2025-01-27 | 44 |  | 2024-09-10 | 2024-09-16 |  | 2024-06-15 | 2024-06-20 | 6 |  | 2024-09-10 | 2024-09-16 |  | 2025-01-06 | 2025-01-14 | 9 |  | GP | 2024-10-19 | 2024-10-25 |  | 2025-01-12 | 2025-01-17 | 6 |  | 2024-11-05 | 2024-11-10 |  | 2025-01-17 | 2025-01-26 | 10 |  | 2024-10-31 | 2024-11-06 |  | 2025-02-06 | 2025-03-13 | 36 |  | 2024-11-12 | 2024-11-21 |  | 2025-02-18 | 2025-02-24 | 7 |  | 2024-11-22 | 2024-11-24 |  | 2025-02-26 | 2025-02-27 | 2 |  | 2024-11-12 | 2024-11-13 |  | 2025-03-26 | 2025-03-26 | 1 |  | 2024-10-31 | 2024-11-06 |  | 2024-12-07 | 2024-12-28 | 22 |  | 2024-11-01 | 2024-11-16 |  | 2025-01-01 | 2025-02-06 | 37 |  | 2024-11-13 | 2024-11-16 |  | 2025-03-26 | 2025-03-29 | 4 |  | 2024-11-24 | 2024-11-25 |  | 2025-04-17 | 2025-04-22 | 6 | Delay due to USS-VCB tripped in fault |  | 2024-12-01
HBG | 93 | PSS-4 | AGE24L | WTG 040 | Precast | F10 | Bauer | Done | 530363 | 2670734 | 2023-06-09 | 2023-06-10 |  | 2023-06-09 | 2023-06-10 |  | 199 | 199 | 2024-06-19 | 2024-06-28 |  | 2024-12-20 | 2024-12-30 | 11 | [8 empty] | 2024-09-24 | 2024-09-24 |  | 2025-01-02 | 2025-01-08 | 7 |  | 2024-09-25 | 2024-09-25 |  | 2025-01-10 | 2025-01-11 | 2 |  | 2024-09-26 | 2024-09-26 |  | 2025-01-11 | 2025-01-11 | 1 |  | 2024-09-27 | 2024-09-28 |  | 2025-01-19 | 2025-01-19 | 1 |  | 2024-09-30 | 2024-10-09 |  | 2025-01-20 | 2025-02-08 | 20 |  | 2024-10-16 | 2024-10-17 |  | 2025-02-08 | 2025-02-09 | 2 | 39 |  | 2024-10-18 | 2024-10-24 |  | 2025-02-24 | 2025-04-08 | 44 |  | 2024-10-18 | 2024-10-24 |  | 2025-02-25 | 2025-02-25 | 1 |  |  |  | 2024-10-07 | 2024-10-21 |  | 2025-01-10 | 2025-02-18 | 40 |  | 2024-10-05 | 2024-10-11 |  | 2024-05-15 | 2024-05-25 | 11 |  | 2024-10-05 | 2024-10-11 |  | 2025-02-15 | 2025-02-26 | 12 |  | SS Jadeja (Reuse) | 2024-10-12 | 2024-10-18 |  | 2025-02-14 | 2025-02-26 | 13 |  | 2024-11-18 | 2024-11-23 |  | 2025-02-28 | 2025-03-09 | 10 |  | 2024-11-04 | 2024-11-10 |  | 2025-02-22 | 2025-03-10 | 17 |  | 2024-11-26 | 2024-12-05 |  | 2025-03-11 | 2025-03-22 | 12 |  | 2024-12-07 | 2024-12-09 |  | 2025-03-24 | 2025-03-26 | 3 |  | 2024-11-16 | 2024-11-17 |  | 2025-03-18 | 2025-03-18 | 1 |  | 2024-11-04 | 2024-11-10 |  | 2024-12-30 | 2025-02-16 | 49 |  | 2024-11-01 | 2024-11-16 |  | 2025-01-15 | 2025-02-06 | 23 |  | 2024-11-17 | 2024-11-20 |  | 2025-03-24 | 2025-03-25 | 2 |  | 2024-12-09 | 2024-12-10 |  | 2025-03-31 | 2025-04-01 | 2 |  |  | 2024-12-01
HBG | 94 | PSS-4 | AGE24L | WTG 026 | Precast | F10 | Bauer | Done | 529530 | 2670999 | 2024-01-15 | 2024-02-02 |  | 2024-01-15 | 2024-02-02 |  | 253 | 253 | 2024-06-21 | 2024-06-30 |  | 2024-12-10 | 2024-12-18 | 9 | [8 empty] | 2024-09-26 | 2024-09-26 |  | 2024-12-28 | 2024-12-31 | 4 |  | 2024-09-27 | 2024-09-27 |  | 2025-01-14 | 2025-01-15 | 2 |  | 2024-09-28 | 2024-09-28 |  | 2025-01-16 | 2025-01-16 | 1 |  | 2024-09-29 | 2024-09-30 |  | 2025-01-25 | 2025-01-25 | 1 |  | 2024-10-02 | 2024-10-11 |  | 2025-01-26 | 2025-02-03 | 9 |  | 2024-10-17 | 2024-10-18 |  | 2025-02-03 | 2025-02-04 | 2 | 39 |  | 2024-10-19 | 2024-10-25 |  | 2025-02-14 | 2025-04-05 | 51 |  | 2024-10-19 | 2024-10-25 |  | 2025-02-10 | 2025-02-10 | 1 |  |  |  | 2024-10-09 | 2024-10-23 |  | 2024-12-30 | 2025-02-27 | 60 |  | 2024-10-07 | 2024-10-13 |  | 2024-05-18 | 2024-05-27 | 10 |  | 2024-10-07 | 2024-10-13 |  | 2025-02-13 | 2025-02-24 | 12 |  | SS Jadeja (Reuse) | 2024-10-14 | 2024-10-20 |  | 2025-02-13 | 2025-02-24 | 12 |  | 2024-11-19 | 2024-11-24 |  | 2025-02-25 | 2025-03-07 | 11 |  | 2024-11-11 | 2024-11-17 |  | 2025-03-05 | 2025-03-21 | 17 |  | 2024-11-27 | 2024-12-06 |  | 2025-03-12 | 2025-03-25 | 14 |  | 2024-12-08 | 2024-12-10 |  | 2025-03-27 | 2025-03-28 | 2 |  | 2024-11-23 | 2024-11-24 |  | 2025-03-23 | 2025-03-23 | 1 |  | 2024-11-11 | 2024-11-17 |  | 2024-12-13 | 2025-02-01 | 51 |  | 2024-11-01 | 2024-11-16 |  | 2025-01-15 | 2025-02-06 | 23 |  | 2024-11-24 | 2024-11-27 |  | 2025-03-24 | 2025-03-25 | 2 |  | 2024-12-10 | 2024-12-11 |  | 2025-03-31 | 2025-04-01 | 2 |  |  | 2024-12-01
MSC | 95 | PSS-4 | AGE24L | WTG 014 | Precast | F9 | Sarita infra | Done | 528689 | 2671303 | 2024-01-16 | 2024-02-01 |  | 2024-01-16 | 2024-02-01 |  | 253 | 253 | 2024-06-16 | 2024-06-25 |  | 2024-12-21 | 2025-01-08 | 19 |  | Yes | 2024-07-10 | 2024-07-25 |  | 2025-01-14 | 2025-01-21 |  | 2024-09-16 | 2024-09-16 |  | 2025-01-27 | 2025-01-28 | 2 |  | 2024-09-17 | 2024-09-17 |  | 2025-01-28 | 2025-01-28 | 1 |  | 2024-09-18 | 2024-09-18 |  | 2025-01-29 | 2025-01-29 | 1 |  | 2024-09-19 | 2024-09-20 |  | 2025-02-01 | 2025-02-01 | 1 |  | 2024-09-26 | 2024-10-03 |  | 2025-02-02 | 2025-02-05 | 4 |  | 2024-10-06 | 2024-10-07 |  | 2025-02-06 | 2025-02-06 | 1 | 11 |  | 2024-10-09 | 2024-10-15 |  | 2025-02-10 | 2025-04-05 | 55 |  | 2024-10-09 | 2024-10-15 |  | 2025-02-10 | 2025-02-10 | 1 |  |  |  | 2024-10-03 | 2024-10-17 |  | 2025-01-27 | 2025-02-19 | 24 |  | 2024-09-19 | 2024-09-25 |  | 2024-05-19 | 2024-06-05 | 18 |  | 2024-09-19 | 2024-09-25 |  | 2025-02-12 | 2025-02-22 | 11 |  | GP | 2024-10-13 | 2024-10-19 |  | 2025-02-12 | 2025-02-20 | 9 |  | 2024-10-31 | 2024-11-05 |  | 2025-02-25 | 2025-03-06 | 10 |  | 2024-10-25 | 2024-10-31 |  | 2025-02-20 | 2025-03-10 | 19 |  | 2024-11-07 | 2024-11-16 |  | 2025-03-12 | 2025-03-22 | 11 |  | 2024-11-17 | 2024-11-19 |  | 2025-03-24 | 2025-03-26 | 3 |  | 2024-11-06 | 2024-11-07 |  | 2025-03-20 | 2025-03-20 | 1 |  | 2024-10-27 | 2024-11-02 |  | 2024-12-17 | 2024-12-29 | 13 |  | 2024-11-01 | 2024-11-16 |  | 2025-01-15 | 2025-02-06 | 23 |  | 2024-11-07 | 2024-11-10 |  | 2025-03-24 | 2025-03-25 | 2 |  | 2024-11-19 | 2024-11-20 |  | 2025-03-31 | 2025-04-01 | 2 |  |  | 2024-12-01
BALAJI & Co | 96 | PSS-4 | ACL | WTG 069 | Precast | F5 | Bauer | Done | 531469 | 2673124 | 2024-01-12 | 2024-02-01 |  | 2024-01-12 | 2024-02-01 |  | 253 | 253 | 2024-05-31 | 2024-06-09 |  | 2024-09-24 | 2024-10-07 | 14 | [8 empty] | 2024-10-18 | 2024-10-18 |  | 2024-11-24 | 2024-11-28 | 5 |  | 2024-10-19 | 2024-10-19 |  | 2024-11-29 | 2024-11-30 | 2 |  | 2024-10-20 | 2024-10-20 |  | 2024-12-02 | 2024-12-02 | 1 |  | 2024-10-21 | 2024-10-22 |  | 2024-12-05 | 2024-12-05 | 1 |  | 2024-11-03 | 2024-11-10 |  | 2024-12-06 | 2024-12-11 | 6 |  | 2024-11-13 | 2024-11-14 |  | 2024-12-13 | 2024-12-14 | 2 | 21 |  | 2024-11-16 | 2024-11-22 |  | 2024-12-24 | 2025-03-10 | 77 |  | 2024-11-16 | 2024-11-22 |  | 2024-12-19 | 2024-12-19 | 1 |  |  |  | 2024-11-10 | 2024-11-24 |  | 2024-12-25 | 2025-01-20 | 27 |  | 2024-10-12 | 2024-10-18 |  | 2024-05-21 | 2024-05-26 | 6 |  | 2024-10-12 | 2024-10-18 |  | 2025-01-02 | 2025-01-10 | 9 |  | SS Jadeja | 2024-11-20 | 2024-11-26 |  | 2024-12-15 | 2025-01-10 | 27 |  | 2024-12-17 | 2024-12-22 |  | 2025-01-11 | 2025-02-07 | 28 |  | 2024-12-02 | 2024-12-08 |  | 2025-02-14 | 2025-03-07 | 22 |  | 2024-12-24 | 2024-12-30 |  | 2025-03-08 | 2025-03-17 | 10 |  | 2024-12-31 | 2025-01-02 |  | 2025-03-17 | 2025-03-18 | 2 |  | 2024-12-14 | 2024-12-15 |  | 2025-03-13 | 2025-03-13 | 1 |  | 2024-12-02 | 2024-12-08 |  | 2025-01-16 | 2025-03-08 | 52 |  | 2024-11-20 | 2024-12-05 |  | 2025-01-30 | 2025-02-19 | 21 |  | 2024-12-15 | 2024-12-18 |  | 2025-03-17 | 2025-03-18 | 2 |  | 2025-01-02 | 2025-01-03 |  | 2025-03-19 | 2025-03-19 | 1 |  |  | 2024-12-01
Unique/MSC | 97 | PSS-4 | ACL | WTG 057 | Precast | F16 | Menard | Done | 531582 | 2668457 | 2022-12-30 | 2022-12-31 |  | 2022-12-30 | 2022-12-31 |  | 241 | 241 | 2024-04-16 | 2024-04-25 |  | 2024-01-29 | 2024-02-13 | 16 |  | Yes | 2024-09-25 | 2024-10-04 |  | 2024-09-30 | 2024-10-07 |  | 2024-08-16 | 2024-08-16 |  | 2024-11-08 | 2024-11-10 | 3 |  | 2024-08-17 | 2024-08-17 |  | 2024-11-11 | 2024-11-14 | 4 |  | 2024-08-18 | 2024-08-18 |  | 2024-11-14 | 2024-11-14 | 1 |  | 2024-08-19 | 2024-08-20 |  | 2024-11-15 | 2024-11-16 | 2 |  | 2024-08-22 | 2024-08-31 |  | 2024-11-16 | 2024-11-24 | 9 |  | 2024-09-03 | 2024-09-04 |  | 2024-11-25 | 2024-11-25 | 1 | 18 |  | 2024-09-05 | 2024-09-11 |  | 2024-11-28 | 2025-02-21 | 86 |  | 2024-09-05 | 2024-09-11 |  | 2024-11-28 | 2024-11-28 | 1 |  |  |  | 2024-08-29 | 2024-09-12 |  | 2025-01-04 | 2025-01-11 | 8 |  | 2024-09-09 | 2024-09-15 |  | Completed | Completed | #VALUE! |  | 2024-09-09 | 2024-09-15 |  | 2024-10-20 | 2024-11-07 | 19 |  | GP | 2024-09-16 | 2024-09-22 |  | 2024-10-20 | 2024-11-07 | 19 |  | 2024-10-08 | 2024-10-13 |  | 2024-11-01 | 2024-12-11 | 41 |  | 2024-10-17 | 2024-10-23 |  | 2025-01-22 | 2025-02-23 | 33 |  | 2024-10-16 | 2024-10-25 |  | 2024-12-16 | 2024-12-22 | 7 |  | 2024-10-27 | 2024-10-29 |  | 2024-12-23 | 2024-12-29 | 7 |  | 2024-10-29 | 2024-10-30 |  | 2025-02-28 | 2025-02-28 | 1 |  | 2024-10-06 | 2024-10-12 |  | 2024-12-22 | 2025-02-07 | 48 |  | 2024-10-05 | 2024-10-20 |  | 2024-12-16 | 2025-01-09 | 25 |  | 2024-10-30 | 2024-11-02 |  | 2025-02-28 | 2025-03-07 | 8 |  | 2024-11-02 | 2024-11-03 |  | 2025-03-08 | 2025-03-11 | 4 |  | 1. Upto Gravel work by Unique Infra | 2024-12-01
DNC | 98 | PSS-4 | AHEJ5L | WTG 043 | Precast | F11 | Sarita infra | Done | 530931 | 2667775 | 2022-12-30 | 2022-12-31 |  | 2022-12-30 | 2022-12-31 |  | 188 | 188 | 2024-05-08 | 2024-05-17 |  | 2024-04-01 | 2024-05-06 | 36 | [8 empty] | 2024-09-23 | 2024-09-23 |  | 2024-06-02 | 2024-06-04 | 3 |  | 2024-09-24 | 2024-09-24 |  | 2024-06-06 | 2024-06-11 | 6 |  | 2024-09-25 | 2024-09-25 |  | 2024-06-12 | 2024-06-12 | 1 |  | 2024-09-26 | 2024-09-27 |  | 2024-08-13 | 2024-08-14 | 2 |  | 2024-10-01 | 2024-10-08 |  | 2024-08-14 | 2024-09-25 | 43 | Delay due to rains & manpower left from site, departmental manpower engaged for steel binding | 2024-10-11 | 2024-10-12 |  | 2024-09-27 | 2024-09-28 | 2 | 119 |  | 2024-10-14 | 2024-10-20 |  | 2024-10-08 | 2025-03-13 | 157 |  | 2024-10-08 | 2024-10-22 |  | 2024-10-11 | 2024-10-11 | 1 |  |  |  | 2024-10-08 | 2024-10-22 |  | 2025-01-02 | 2025-02-13 | 43 |  | 2024-09-10 | 2024-09-16 |  | 2024-05-12 | 2024-05-17 | 6 |  | 2024-09-10 | 2024-09-16 |  | 2024-10-04 | 2024-10-19 | 16 |  | Vaibhav | 2024-10-18 | 2024-10-24 |  | 2024-10-04 | 2024-10-19 | 16 |  | 2024-11-04 | 2024-11-09 |  | 2024-10-21 | 2024-10-29 | 9 |  | 2024-10-30 | 2024-11-05 |  | 2025-02-24 | 2025-03-10 | 15 |  | 2024-11-11 | 2024-11-20 |  | 2024-11-22 | 2024-11-29 | 8 |  | 2024-11-21 | 2024-11-23 |  | 2024-12-01 | 2024-12-12 | 12 | hold due to replacement of material. | 2024-11-11 | 2024-11-12 |  | 2025-03-26 | 2025-03-26 | 1 |  | 2024-10-30 | 2024-11-05 |  | 2024-12-26 | 2025-01-27 | 33 |  | 2024-11-01 | 2024-11-16 |  | 2025-01-01 | 2025-02-06 | 37 |  | 2024-11-12 | 2024-11-15 |  | 2025-03-26 | 2025-03-29 | 4 |  | 2024-11-23 | 2024-11-24 |  | 2025-04-17 | 2025-04-18 | 2 |  | 1. 34No's Column done by Menard and 3No's Columns are partially done | 2024-12-01
HBG | 99 | PSS-4 | AGE24L | WTG 042 | Precast | F15 | Menard | Done | 530742 | 2668761 | 2022-12-30 | 2022-12-31 |  | 2022-12-30 | 2022-12-31 |  | 163 | 163 | 2024-06-04 | 2024-06-13 |  | 2024-04-30 | 2024-05-11 | 12 | [8 empty] | 2024-09-02 | 2024-09-02 |  | 2024-10-29 | 2024-10-31 | 3 |  | 2024-09-03 | 2024-09-03 |  | 2024-12-04 | 2024-12-05 | 2 |  | 2024-09-04 | 2024-09-04 |  | 2024-12-07 | 2024-12-07 | 1 |  | 2024-09-05 | 2024-09-06 |  | 2024-12-15 | 2024-12-16 | 2 |  | 2024-09-08 | 2024-09-15 |  | 2024-12-16 | 2024-12-28 | 13 |  | 2024-09-18 | 2024-09-19 |  | 2024-12-28 | 2024-12-29 | 2 | 62 |  | 2024-09-21 | 2024-09-27 |  | 2025-01-03 | 2025-03-08 | 65 |  | 2024-09-21 | 2024-09-27 |  | 2025-01-02 | 2025-01-02 | 1 |  |  |  | 2024-09-15 | 2024-09-29 |  | 2024-12-04 | 2025-02-08 | 67 |  | 2024-09-03 | 2024-09-09 |  | 2024-05-10 | 2024-05-15 | 6 |  | 2024-09-03 | 2024-09-09 |  | 2025-01-05 | 2025-01-11 | 7 |  | SS Jadeja | 2024-09-25 | 2024-10-01 |  | 2024-11-19 | 2025-01-09 | 52 |  | 2024-10-11 | 2024-10-16 |  | 2025-01-12 | 2025-01-25 | 14 |  | 2024-10-07 | 2024-10-13 |  | 2025-02-20 | 2025-03-01 | 10 |  | 2024-10-18 | 2024-10-27 |  | 2025-02-16 | 2025-03-09 | 22 | delay due to hub lock | 2024-10-28 | 2024-10-30 |  | 2025-03-09 | 2025-03-10 | 2 |  | 2024-10-19 | 2024-10-20 |  | 2025-03-02 | 2025-03-02 | 1 |  | 2024-10-11 | 2024-10-17 |  | 2024-12-17 | 2025-02-05 | 51 |  | 2024-10-05 | 2024-10-20 |  | 2024-12-16 | 2025-01-09 | 25 |  | 2024-10-20 | 2024-10-23 |  | 2025-03-07 | 2025-03-09 | 3 |  | 2024-10-30 | 2024-10-31 |  | 2025-03-09 | 2025-03-13 | 5 |  |  | 2024-12-01
BALAJI & Co | 100 | PSS-8 | ARE3L | WTG 122 | Precast | F1 | Bauer | Done | 533794 | 2673237 | 2024-02-03 | 2024-02-16 |  | 2024-02-03 | 2024-02-16 |  | 211 | 211 | 2024-04-20 | 2024-04-28 |  | 2024-12-04 | 2024-12-08 | 5 | [8 empty] | 2024-05-08 | 2024-05-09 |  | 2024-12-12 | 2024-12-17 | 6 |  | 2024-05-10 | 2024-05-11 |  | 2024-12-20 | 2024-12-23 | 4 |  | 2024-05-12 | 2024-05-12 |  | 2024-12-24 | 2024-12-24 | 1 |  | 2024-05-13 | 2024-05-14 |  | 2024-12-26 | 2024-12-26 | 1 |  | 2024-05-15 | 2024-05-22 |  | 2025-01-02 | 2025-01-10 | 9 |  | 2024-05-23 | 2024-05-24 |  | 2025-01-11 | 2025-01-12 | 2 | 32 |  | 2024-05-26 | 2024-06-01 |  | 2025-01-20 | 2025-05-03 | 104 |  | 2024-05-26 | 2024-06-01 |  | 2025-01-24 | 2025-01-24 | 1 |  |  |  | 2024-05-20 | 2024-06-03 |  | 2025-02-22 | 2025-04-02 | 40 |  | 2024-12-15 | 2024-12-21 |  | Completed | Completed | #VALUE! |  | 2024-12-14 | 2024-12-19 |  | 2025-01-10 | 2025-01-18 | 9 |  | Odhav | 2024-12-20 | 2024-12-26 |  | 2024-12-13 | 2024-12-22 | 10 |  | 2025-01-02 | 2025-01-09 |  | 2025-01-29 | 2025-02-09 | 12 |  | 2024-06-05 | 2024-06-13 |  | 2025-04-18 | 2025-05-06 | 19 | Google Loc.-Charge plan in June | 2025-01-11 | 2025-01-16 |  | 2025-03-31 | 2025-04-13 | 14 | Loc hold due to material issue | 2025-01-17 | 2025-01-20 |  | 2025-04-13 | 2025-04-19 | 7 |  | 2024-06-15 | 2024-06-17 |  | 2025-05-27 | 2025-05-27 | 1 |  | 2024-12-23 | 2024-12-30 |  | 2025-02-07 | 2025-02-19 | 13 |  | 2025-01-03 | 2025-01-18 |  | 2025-05-31 | 2025-06-19 | 20 |  | 2024-12-30 | 2025-01-02 |  | 2025-06-23 | 2025-07-15 | 23 |  | 2025-01-20 | 2025-01-21 |  | 2025-07-18 | 2025-07-19 | 2 |  |  | 2025-03-01
BPS | 101 | PSS-8 | ARE3L | WTG 105 | Precast | F1 | Bauer | Done | 533142 | 2672555 | 2024-01-09 | 2024-01-31 |  | 2024-01-09 | 2024-01-31 |  | 253 | 253 | 2024-04-22 | 2024-04-30 |  | 2024-12-09 | 2024-12-14 | 6 |  | Yes | 2024-05-20 | 2024-06-07 |  | 2025-02-22 | 2025-04-27 | Delay due to saritha financial crisis | 2024-05-10 | 2024-05-11 |  | 2025-05-02 | 2025-05-03 | 2 |  | 2024-05-12 | 2024-05-13 |  | 2025-05-05 | 2025-05-06 | 2 |  | 2024-05-14 | 2024-05-14 |  | 2025-05-07 | 2025-05-07 | 1 |  | 2024-05-15 | 2024-05-16 |  | 2025-05-17 | 2025-05-18 | 2 |  | 2024-05-17 | 2024-05-24 |  | 2025-05-19 | 2025-05-27 | 9 |  | 2024-05-25 | 2024-05-26 |  | 2025-05-28 | 2025-05-28 | 1 | 27 |  | 2024-05-28 | 2024-06-03 |  | 2025-06-01 | 2025-08-17 | 78 |  | 2024-05-28 | 2024-06-03 |  | 2025-06-01 | 2025-06-01 | 1 |  |  |  | 2024-05-22 | 2024-06-05 |  | 2025-06-02 | 2025-06-11 | 10 |  | 2024-12-17 | 2024-12-23 |  | 2024-05-24 | 2024-06-03 | 11 |  | 2024-12-14 | 2024-12-19 |  | 2025-01-02 | 2025-01-18 | 17 |  | SS Jadeja | 2024-12-20 | 2024-12-26 |  | 2025-01-02 | 2025-01-18 | 17 |  | 2025-01-02 | 2025-01-09 |  | 2025-06-15 | 2025-06-25 | 11 |  | 2024-06-07 | 2024-06-15 |  | 2025-06-11 | 2025-06-18 | 8 | Google Loc.-Charge plan in June | 2025-01-11 | 2025-01-16 |  | 2025-06-23 | 2025-06-30 | 8 |  | 2025-01-17 | 2025-01-20 |  | 2025-07-01 | 2025-07-02 | 2 | Hold because of DG not reach at location due to water logged from 2-Jul'25 | 2024-06-17 | 2024-06-19 |  | 2025-06-25 | 2025-06-25 | 1 |  | 2024-12-23 | 2024-12-30 |  | 2025-02-10 | 2025-05-31 | 111 |  | 2025-01-03 | 2025-01-18 |  | 2025-05-31 | 2025-06-19 | 20 |  | 2024-12-30 | 2025-01-02 |  | 2025-06-23 | 2025-07-15 | 23 |  | 2025-01-20 | 2025-01-21 |  | 2025-07-21 | 2025-07-22 | 2 |  |  | 2025-03-01
DNC | 102 | PSS-8 | ARE3L | WTG 104 | Precast | F1 | Bauer | Done | 532953 | 2673541 | 2024-02-01 | 2024-02-04 |  | 2024-02-01 | 2024-02-04 |  | 211 | 211 | 2024-04-24 | 2024-05-02 |  | 2024-08-02 | 2024-08-10 | 9 | [8 empty] | 2024-05-12 | 2024-05-13 |  | 2024-11-17 | 2024-11-18 | 2 |  | 2024-05-14 | 2024-05-15 |  | 2024-11-18 | 2024-11-18 | 1 |  | 2024-05-16 | 2024-05-16 |  | 2024-11-18 | 2024-11-19 | 2 |  | 2024-05-17 | 2024-05-18 |  | 2024-11-29 | 2024-11-29 | 1 |  | 2024-05-19 | 2024-05-26 |  | 2024-11-30 | 2024-12-06 | 7 |  | 2024-05-27 | 2024-05-28 |  | 2024-12-07 | 2024-12-07 | 1 | 21 |  | 2024-05-30 | 2024-06-05 |  | 2024-12-10 | 2025-05-02 | 144 |  | 2024-05-30 | 2024-06-05 |  | 2024-12-20 | 2024-12-20 | 1 |  |  |  | 2024-05-24 | 2024-06-07 |  | 2025-02-08 | 2025-03-27 | 48 |  | 2024-12-10 | 2024-12-16 |  | Completed | Completed | #VALUE! |  | 2024-11-20 | 2024-11-25 |  | Completed | Completed | #VALUE! |  | SS Jadeja | 2024-11-20 | 2024-11-25 |  | 2024-12-05 | 2024-12-19 | 15 |  | 2025-01-03 | 2025-01-10 |  | 2024-12-30 | 2025-01-14 | 16 |  | 2024-06-09 | 2024-06-17 |  | 2025-04-18 | 2025-05-11 | 24 | Google Loc.-Charge plan in June | 2025-01-12 | 2025-01-17 |  | 2025-06-01 | 2025-06-12 | 12 | Cable & manpower issue | 2025-01-18 | 2025-01-21 |  | 2025-06-13 | 2025-06-14 | 2 |  | 2024-06-19 | 2024-06-21 |  | 2025-05-27 | 2025-05-27 | 1 |  | 2024-12-24 | 2024-12-31 |  | 2025-02-04 | 2025-02-19 | 16 |  | 2025-01-03 | 2025-01-18 |  | 2025-05-31 | 2025-06-19 | 20 |  | 2024-12-31 | 2025-01-03 |  | 2025-06-23 | 2025-07-15 | 23 |  | 2025-01-21 | 2025-01-22 |  | 2025-07-18 | 2025-07-19 | 2 |  |  | 2025-03-01
HBG | 103 | PSS-4 | ACL | WTG 087 | Precast | F4 | Bauer | Done | 532309 | 2672820 | 2024-01-09 | 2024-01-31 |  | 2024-01-09 | 2024-01-31 |  | 253 | 253 | 2024-06-20 | 2024-06-29 |  | 2024-08-21 | 2024-09-23 | 34 | [8 empty] | 2024-09-25 | 2024-09-25 |  | 2024-11-04 | 2024-11-09 | 6 |  | 2024-09-26 | 2024-09-26 |  | 2024-11-18 | 2024-11-20 | 3 |  | 2024-09-27 | 2024-09-27 |  | 2024-11-24 | 2024-11-24 | 1 |  | 2024-09-28 | 2024-09-29 |  | 2024-11-29 | 2024-11-30 | 2 |  | 2024-10-01 | 2024-10-10 |  | 2024-12-01 | 2024-12-10 | 10 |  | 2024-10-18 | 2024-10-19 |  | 2024-12-11 | 2024-12-12 | 2 | 39 |  | 2024-10-20 | 2024-10-26 |  | 2024-12-23 | 2025-03-26 | 94 |  | 2024-10-20 | 2024-10-26 |  | 2024-12-21 | 2024-12-21 | 1 |  |  |  | 2024-10-08 | 2024-10-22 |  | 2024-11-24 | 2025-02-08 | 77 |  | 2024-10-06 | 2024-10-12 |  | 2024-05-21 | 2024-05-27 | 7 |  | 2024-10-06 | 2024-10-12 |  | 2025-01-03 | 2025-01-09 | 7 |  | SS Jadeja | 2024-10-13 | 2024-10-19 |  | 2024-12-16 | 2025-01-04 | 20 |  | 2024-11-20 | 2024-11-25 |  | 2025-01-17 | 2025-01-25 | 9 |  | 2024-11-10 | 2024-11-16 |  | 2025-02-09 | 2025-03-09 | 29 |  | 2024-11-28 | 2024-12-07 |  | 2025-03-11 | 2025-03-18 | 8 |  | 2024-12-09 | 2024-12-11 |  | 2025-03-18 | 2025-03-20 | 3 |  | 2024-11-22 | 2024-11-23 |  | 2025-03-15 | 2025-03-15 | 1 |  | 2024-11-10 | 2024-11-16 |  | 2024-12-28 | 2025-03-10 | 73 |  | 2024-11-01 | 2024-11-16 |  | 2025-01-30 | 2025-02-19 | 21 |  | 2024-11-23 | 2024-11-26 |  | 2025-03-17 | 2025-03-19 | 3 |  | 2024-12-11 | 2024-12-12 |  | 2025-03-20 | 2025-03-21 | 2 |  |  | 2025-03-01
HBG | 104 | PSS-4 | ACL | WTG 086 | Precast | F4 | Bauer | Done | 532120 | 2673806 | 2024-02-01 | 2024-02-04 |  | 2024-02-01 | 2024-02-04 |  | 253 | 253 | 2024-06-22 | 2024-07-01 |  | 2024-08-12 | 2024-08-21 | 10 |  | Yes | 2024-10-12 | 2024-10-20 |  | 2024-10-14 | 2024-10-25 |  | 2024-09-27 | 2024-09-27 |  | 2024-11-08 | 2024-11-13 | 6 |  | 2024-09-28 | 2024-09-28 |  | 2024-11-15 | 2024-11-15 | 1 |  | 2024-09-29 | 2024-09-29 |  | 2024-11-17 | 2024-11-17 | 1 |  | 2024-09-30 | 2024-10-01 |  | 2024-11-19 | 2024-11-20 | 2 |  | 2024-10-03 | 2024-10-12 |  | 2024-11-21 | 2024-11-28 | 8 |  | 2024-10-19 | 2024-10-20 |  | 2024-11-29 | 2024-11-30 | 2 | 23 |  | 2024-10-21 | 2024-10-27 |  | 2024-12-04 | 2025-03-21 | 108 |  | 2024-10-21 | 2024-10-27 |  | 2024-12-08 | 2024-12-08 | 1 |  |  |  | 2024-10-10 | 2024-10-24 |  | 2024-12-08 | 2025-01-31 | 55 |  | 2024-10-08 | 2024-10-14 |  | Completed | Completed | #VALUE! |  | 2024-10-08 | 2024-10-14 |  | 2025-01-02 | 2025-01-11 | 10 |  | SS Jadeja | 2024-10-15 | 2024-10-21 |  | 2024-12-14 | 2024-12-27 | 14 |  | 2024-11-21 | 2024-11-26 |  | 2025-01-11 | 2025-02-17 | 38 |  | 2024-11-12 | 2024-11-18 |  | 2025-02-20 | 2025-03-08 | 17 |  | 2024-11-29 | 2024-12-08 |  | 2025-03-04 | 2025-03-11 | 8 |  | 2024-12-10 | 2024-12-12 |  | 2025-03-12 | 2025-03-17 | 6 |  | 2024-11-24 | 2024-11-25 |  | 2025-03-14 | 2025-03-14 | 1 |  | 2024-11-12 | 2024-11-18 |  | 2024-12-11 | 2025-03-15 | 95 |  | 2024-11-01 | 2024-11-16 |  | 2025-01-30 | 2025-02-19 | 21 |  | 2024-11-25 | 2024-11-28 |  | 2025-03-17 | 2025-03-18 | 2 |  | 2024-12-12 | 2024-12-13 |  | 2025-03-19 | 2025-03-20 | 2 |  |  | 2025-03-01
SHREEJI | 105 | PSS-8 | ARE41L | WTG 235 | Precast | F4 | Menard | Done | 538165 | 2670847 | 2023-05-31 | 2023-06-01 |  | 2023-05-31 | 2023-06-01 |  | 163 | 163 | 2024-04-27 | 2024-05-05 |  | 2024-03-13 | 2024-03-21 | 9 |  | Yes | 2024-05-09 | 2024-05-23 |  | 2024-10-26 | 2024-11-26 |  | 2024-05-15 | 2024-05-16 |  | 2024-12-08 | 2024-12-09 | 2 |  | 2024-05-17 | 2024-05-18 |  | 2024-12-09 | 2024-12-11 | 3 |  | 2024-05-19 | 2024-05-19 |  | 2024-12-13 | 2024-12-14 | 2 |  | 2024-05-20 | 2024-05-21 |  | 2024-12-19 | 2024-12-19 | 1 |  | 2024-05-22 | 2024-05-29 |  | 2024-12-24 | 2024-12-31 | 8 |  | 2024-05-30 | 2024-05-31 |  | 2025-01-01 | 2025-01-02 | 2 | 26 |  | 2024-06-02 | 2024-06-08 |  | 2025-01-07 | 2025-06-07 | 152 |  | 2024-06-02 | 2024-06-08 |  | 2025-01-17 | 2025-01-17 | 1 |  |  |  | 2024-05-27 | 2024-06-10 |  | 2024-12-13 | 2025-04-15 | 124 |  | 2024-12-11 | 2024-12-18 |  | Completed | Completed | #VALUE! |  | 2024-12-16 | 2024-12-21 |  | 2025-02-02 | 2025-02-17 | 16 |  | Odhav | 2024-12-22 | 2024-12-28 |  | 2024-10-25 | 2025-01-23 | 91 |  | 2025-01-04 | 2025-01-11 |  | 2025-03-28 | 2025-04-20 | 24 |  | 2024-06-12 | 2024-06-20 |  | 2025-04-30 | 2025-05-13 | 14 |  | 2025-01-13 | 2025-01-18 |  | 2025-04-21 | 2025-04-24 | 4 |  | 2025-01-19 | 2025-01-22 |  | 2025-04-25 | 2025-04-26 | 2 |  | 2024-06-22 | 2024-06-24 |  | 2025-05-28 | 2025-05-28 | 1 |  | 2024-12-25 | 2025-01-01 |  | 2025-04-01 | 2025-06-02 | 63 |  | 2025-01-03 | 2025-01-18 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-01-01 | 2025-01-04 |  | 2025-07-30 | 2025-08-20 | 22 |  | 2025-01-22 | 2025-01-23 |  | 2025-08-21 | 2025-08-23 | 3 |  |  | 2025-03-01
HBG | 106 | PSS-8 | ARE41L | WTG 213 | Precast | F4 | Bauer | Done | 537332 | 2671112 | 2024-01-05 | 2024-01-30 |  | 2024-01-05 | 2024-01-30 |  | 211 | 211 | 2024-05-03 | 2024-05-11 |  | 2024-06-01 | 2024-06-08 | 8 | [8 empty] | 2024-05-17 | 2024-05-18 |  | 2024-12-09 | 2024-12-11 | 3 |  | 2024-05-19 | 2024-05-20 |  | 2024-12-26 | 2024-12-27 | 2 |  | 2024-05-21 | 2024-05-21 |  | 2024-12-28 | 2024-12-28 | 1 |  | 2024-05-22 | 2024-05-23 |  | 2025-01-04 | 2025-01-05 | 2 |  | 2024-05-24 | 2024-05-31 |  | 2025-01-05 | 2025-01-13 | 9 |  | 2024-06-01 | 2024-06-02 |  | 2025-01-13 | 2025-01-14 | 2 | 37 |  | 2024-06-04 | 2024-06-10 |  | 2025-01-18 | 2025-08-07 | 202 |  | 2024-06-04 | 2024-06-10 |  | 2025-01-23 | 2025-01-23 | 1 |  |  |  | 2024-05-29 | 2024-06-12 |  | 2024-12-09 | 2025-04-02 | 115 |  | 2024-12-13 | 2024-12-20 |  | Completed | Completed | #VALUE! |  | 2024-12-17 | 2024-12-22 |  | 2025-02-12 | 2025-02-12 | 1 |  | Odhav | 2024-12-23 | 2024-12-29 |  | 2024-12-11 | 2024-12-30 | 20 |  | 2025-01-05 | 2025-01-12 |  | 2025-03-12 | 2025-03-25 | 14 |  | 2024-06-14 | 2024-06-22 |  | 2025-05-18 | 2025-06-13 | 27 |  | 2025-01-14 | 2025-01-19 |  | 2025-04-06 | 2025-04-09 | 4 |  | 2025-01-20 | 2025-01-23 |  | 2025-04-10 | 2025-04-12 | 3 |  | 2024-06-24 | 2024-06-26 |  | 2025-06-11 | 2025-06-11 | 1 |  | 2024-12-26 | 2025-01-02 |  | 2025-03-29 | 2025-05-22 | 55 |  | 2025-01-03 | 2025-01-18 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-01-02 | 2025-01-05 |  | 2025-07-30 | 2025-08-20 | 22 |  | 2025-01-23 | 2025-01-24 |  | 2025-08-21 | 2025-08-22 | 2 |  |  | 2025-03-01
SHREEJI | 107 | PSS-8 | ARE41L | WTG 234 | Precast | F4 | Menard | Done | 537975 | 2671833 | 2024-01-02 | 2024-01-29 |  | 2024-01-02 | 2024-01-29 |  | 199 | 199 | 2024-05-04 | 2024-05-12 |  | 2024-11-16 | 2024-12-07 | 22 | [8 empty] | 2024-05-19 | 2024-05-20 |  | 2025-02-21 | 2025-02-25 | 5 |  | 2024-05-21 | 2024-05-22 |  | 2025-02-25 | 2025-02-26 | 2 |  | 2024-05-23 | 2024-05-23 |  | 2025-02-26 | 2025-02-26 | 1 |  | 2024-05-24 | 2024-05-25 |  | 2025-02-28 | 2025-02-28 | 1 |  | 2024-05-26 | 2024-06-02 |  | 2025-03-02 | 2025-03-09 | 8 |  | 2024-06-03 | 2024-06-04 |  | 2025-03-09 | 2025-03-10 | 2 | 18 |  | 2024-06-06 | 2024-06-12 |  | 2025-03-19 | 2025-06-07 | 81 |  | 2024-06-06 | 2024-06-12 |  | 2025-03-20 | 2025-03-20 | 1 |  |  |  | 2024-05-31 | 2024-06-14 |  | 2025-02-21 | 2025-04-10 | 49 |  | 2024-12-21 | 2024-12-28 |  | Completed | Completed | #VALUE! |  | 2024-12-18 | 2024-12-23 |  | 2025-01-02 | 2025-01-08 | 7 |  | Odhav | 2024-12-24 | 2024-12-30 |  | 2025-01-02 | 2025-01-07 | 6 |  | 2025-01-06 | 2025-01-13 |  | 2025-04-22 | 2025-05-08 | 17 |  | 2024-06-16 | 2024-06-24 |  | 2025-05-17 | 2025-06-10 | 25 |  | 2025-01-15 | 2025-01-20 |  | 2025-06-07 | 2025-06-12 | 6 |  | 2025-01-21 | 2025-01-24 |  | 2025-06-13 | 2025-06-14 | 2 |  | 2024-06-26 | 2024-06-28 |  | 2025-07-14 | 2025-07-14 | 1 |  | 2024-12-27 | 2025-01-03 |  | 2025-04-07 | 2025-05-27 | 51 |  | 2025-01-03 | 2025-01-18 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-01-03 | 2025-01-06 |  | 2025-07-30 | 2025-08-20 | 22 |  | 2025-01-24 | 2025-01-25 |  | 2025-08-21 | 2025-08-22 | 2 |  |  | 2025-03-01
SHREEJI | 108 | PSS-8 | ARE41L | WTG 212 | Precast | F3 | Menard | Done | 537142 | 2672098 | 2024-01-04 | 2024-01-30 |  | 2024-01-04 | 2024-01-30 |  | 199 | 199 | 2024-09-15 | 2024-09-23 |  | 2024-11-09 | 2024-11-15 | 7 |  | Yes | 2024-12-08 | 2024-12-17 |  | 2024-11-30 | 2024-12-25 |  | 2024-10-24 | 2024-10-25 |  | 2025-01-10 | 2025-01-13 | 4 |  | 2024-10-26 | 2024-10-27 |  | 2025-01-15 | 2025-01-16 | 2 |  | 2024-10-28 | 2024-10-28 |  | 2025-01-16 | 2025-01-16 | 1 |  | 2024-10-29 | 2024-10-30 |  | 2025-01-18 | 2025-01-18 | 1 |  | 2024-10-31 | 2024-11-07 |  | 2025-01-19 | 2025-01-24 | 6 |  | 2024-11-08 | 2024-11-09 |  | 2025-01-24 | 2025-01-25 | 2 | 16 |  | 2024-11-11 | 2024-11-17 |  | 2025-02-14 | 2025-06-30 | 137 |  | 2024-11-11 | 2024-11-17 |  | 2025-01-30 | 2025-01-30 | 1 |  |  |  | 2024-11-05 | 2024-11-19 |  | 2025-03-02 | 2025-04-04 | 34 |  | 2024-12-17 | 2024-12-23 |  | Completed | Completed | #VALUE! |  | 2024-12-20 | 2024-12-25 |  | 2025-04-02 | 2025-04-19 | 18 |  | Odhav | 2024-12-26 | 2025-01-01 |  | 2024-05-10 | 2024-07-02 | 54 |  | 2025-01-08 | 2025-01-15 |  | 2025-04-25 | 2025-06-11 | 48 |  | 2024-11-21 | 2024-11-29 |  | 2025-05-16 | 2025-06-10 | 26 |  | 2025-01-17 | 2025-01-22 |  | 2025-06-17 | 2025-06-26 | 10 |  | 2025-01-23 | 2025-01-26 |  | 2025-06-26 | 2025-07-03 | 8 |  | 2024-12-01 | 2024-12-03 |  | 2025-06-12 | 2025-06-12 | 1 |  | 2024-12-29 | 2025-01-05 |  | 2025-04-15 | 2025-06-05 | 52 |  | 2025-01-03 | 2025-01-18 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-01-05 | 2025-01-08 |  | 2025-06-23 | 2025-07-15 | 23 |  | 2025-01-26 | 2025-01-27 |  | 2025-07-17 | 2025-07-18 | 2 |  |  | 2025-03-01
SHREEJI | 109 | PSS-8 | ARE41L | WTG 304 | Precast | F9 | Bauer | Done | 540491 | 2670960 | 2023-12-31 | 2024-01-28 |  | 2023-12-31 | 2024-01-28 |  | 211 | 211 | 2024-04-27 | 2024-05-09 |  | 2024-04-27 | 2024-05-09 | 13 | [8 empty] | 2024-10-26 | 2024-10-27 |  | 2024-11-20 | 2024-11-22 | 3 |  | 2024-10-28 | 2024-10-29 |  | 2024-11-23 | 2024-11-24 | 2 |  | 2024-10-30 | 2024-10-30 |  | 2024-11-25 | 2024-11-25 | 1 |  | 2024-10-31 | 2024-11-01 |  | 2024-11-25 | 2024-11-26 | 2 |  | 2024-11-02 | 2024-11-09 |  | 2024-11-27 | 2024-12-11 | 15 |  | 2024-11-10 | 2024-11-11 |  | 2024-12-11 | 2024-12-12 | 2 | 23 |  | 2024-11-13 | 2024-11-19 |  | 2024-12-18 | 2025-06-12 | 177 |  | 2024-11-13 | 2024-11-19 |  | 2024-12-21 | 2024-12-21 | 1 |  |  |  | 2024-11-07 | 2024-11-21 |  | 2025-03-02 | 2025-04-24 | 54 |  | 2024-12-20 | 2024-12-26 |  | Completed | Completed | #VALUE! |  | 2024-12-21 | 2024-12-26 |  | Completed | Completed | #VALUE! |  | Vipin | 2024-12-27 | 2025-01-02 |  | 2024-12-16 | 2025-01-19 | 35 |  | 2025-01-09 | 2025-01-16 |  | 2025-01-30 | 2025-02-06 | 8 |  | 2024-11-23 | 2024-12-01 |  | 2025-05-20 | 2025-07-18 | 60 |  | 2025-01-18 | 2025-01-23 |  | 2025-04-05 | 2025-04-08 | 4 |  | 2025-01-24 | 2025-01-27 |  | 2025-04-09 | 2025-04-20 | 12 | Pre-Comm hold due to 2 nos. blade bolt broken | 2024-12-03 | 2024-12-05 |  | 2025-07-16 | 2025-07-16 | 1 |  | 2024-12-30 | 2025-01-06 |  | 2025-05-05 | 2025-05-14 | 10 |  | 2025-01-03 | 2025-01-18 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-01-06 | 2025-01-09 |  | 2025-07-26 | 2025-08-20 | 26 |  | 2025-01-27 | 2025-01-28 |  | 2025-08-21 | 2025-08-22 | 2 |  |  | 2025-03-01
DNC | 110 | PSS-8 | ARE41L | WTG 280 | Precast | F9 | Bauer | Done | 539650 | 2671264 | 2024-01-03 | 2024-01-29 |  | 2024-01-03 | 2024-01-29 |  | 199 | 199 | 2024-05-13 | 2024-05-24 |  | 2024-05-13 | 2024-05-24 | 12 | [8 empty] | 2024-10-15 | 2024-10-16 |  | 2025-01-25 | 2025-01-30 | 6 |  | 2024-10-17 | 2024-10-18 |  | 2025-01-30 | 2025-01-31 | 2 |  | 2024-10-19 | 2024-10-19 |  | 2025-01-31 | 2025-01-31 | 1 |  | 2024-10-20 | 2024-10-21 |  | 2025-02-01 | 2025-02-01 | 1 |  | 2024-10-22 | 2024-10-29 |  | 2025-02-01 | 2025-02-05 | 5 |  | 2024-10-30 | 2024-10-31 |  | 2025-02-05 | 2025-02-06 | 2 | 13 |  | 2024-11-02 | 2024-11-08 |  | 2025-02-12 | 2025-08-14 | 184 |  | 2024-11-02 | 2024-11-08 |  | 2025-02-15 | 2025-02-15 | 1 |  |  |  | 2024-10-27 | 2024-11-10 |  | 2025-02-02 | 2025-03-04 | 31 |  | 2024-12-12 | 2024-12-19 |  | Completed | Completed | #VALUE! |  | 2024-12-24 | 2024-12-29 |  | 2025-05-18 | 2025-05-30 | 13 |  | Vipin | 2024-12-30 | 2025-01-05 |  | 2024-12-15 | 2025-01-09 | 26 |  | 2025-01-12 | 2025-01-19 |  | 2025-06-19 | 2025-07-04 | 16 |  | 2024-11-12 | 2024-11-20 |  | 2025-05-20 | 2025-06-09 | 21 |  | 2025-01-21 | 2025-01-26 |  | 2025-07-10 | 2025-07-20 | 11 |  | 2025-01-27 | 2025-01-30 |  | 2025-07-21 | 2025-07-27 | 7 |  | 2024-11-22 | 2024-11-24 |  | 2025-06-10 | 2025-06-10 | 1 |  | 2025-01-02 | 2025-01-09 |  | 2025-05-04 | 2025-06-02 | 30 |  | 2025-01-03 | 2025-01-18 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-01-09 | 2025-01-12 |  | 2025-07-26 | 2025-08-20 | 26 |  | 2025-01-30 | 2025-01-31 |  | 2025-08-21 | 2025-08-21 | 1 |  |  | 2025-03-01
ODHAV | 111 | PSS-4 | AHEJ5L | WTG 022 | Precast | F3 | Bauer | Done | 528773 | 2674944 | 2024-01-21 | 2024-02-03 |  | 2024-01-21 | 2024-02-03 |  | 253 | 253 | 2024-09-12 | 2024-09-21 |  | 2024-10-23 | 2024-11-02 | 11 | [8 empty] | 2024-10-07 | 2024-10-07 |  | 2024-11-27 | 2024-12-01 | 5 |  | 2024-10-08 | 2024-10-08 |  | 2024-12-24 | 2024-12-27 | 4 |  | 2024-10-09 | 2024-10-09 |  | 2025-01-18 | 2025-01-18 | 1 | Delay due to seepage | 2024-10-10 | 2024-10-11 |  | 2025-01-24 | 2025-01-24 | 1 |  | 2024-10-13 | 2024-10-22 |  | 2025-01-25 | 2025-02-05 | 12 |  | 2024-10-24 | 2024-10-25 |  | 2025-02-07 | 2025-02-07 | 1 | 73 |  | 2024-10-26 | 2024-11-01 |  | 2025-03-01 | 2025-03-20 | 20 |  | 2024-10-26 | 2024-11-01 |  | 2025-02-25 | 2025-02-25 | 1 |  |  |  | 2024-10-20 | 2024-11-03 |  | 2024-12-22 | 2025-02-24 | 65 |  | 2024-10-19 | 2024-10-25 |  | 2024-05-18 | 2024-06-06 | 20 |  | 2024-10-19 | 2024-10-25 |  | 2025-02-15 | 2025-02-25 | 11 |  | Varudi | 2024-10-26 | 2024-11-01 |  | 2025-01-31 | 2025-02-19 | 20 |  | 2024-11-27 | 2024-12-02 |  | 2025-02-27 | 2025-03-12 | 14 |  | 2024-11-18 | 2024-11-24 |  | 2025-03-18 | 2025-03-26 | 9 |  | 2024-12-05 | 2024-12-14 |  | 2025-03-26 | 2025-03-30 | 5 |  | 2024-12-16 | 2024-12-18 |  | 2025-04-02 | 2025-04-04 | 3 |  | 2024-11-30 | 2024-12-01 |  | 2025-03-27 | 2025-03-27 | 1 |  | 2024-11-12 | 2024-11-18 |  | 2024-12-07 | 2024-12-25 | 19 |  | 2024-11-20 | 2024-12-05 |  | 2025-01-01 | 2025-02-06 | 37 |  | 2024-12-01 | 2024-12-04 |  | 2025-04-04 | 2025-04-15 | 12 |  | 2024-12-18 | 2024-12-19 |  | 2025-04-17 | 2025-04-17 | 1 |  |  | 2025-03-01
SHREEJI | 112 | PSS-8 | ARE41L | WTG 303 | Precast | F9 | Menard | Done | 540301 | 2671946 | 2023-12-28 | 2024-01-27 |  | 2023-12-28 | 2024-01-27 |  | 199 | 199 | 2024-05-20 | 2024-05-25 |  | 2024-05-20 | 2024-05-25 | 6 | [8 empty] | 2024-05-25 | 2024-05-26 |  | 2024-06-01 | 2024-06-04 | 4 |  | 2024-05-27 | 2024-05-28 |  | 2024-06-05 | 2024-06-17 | 13 |  | 2024-05-29 | 2024-05-29 |  | 2024-06-19 | 2024-06-19 | 1 |  | 2024-05-30 | 2024-05-31 |  | 2024-10-27 | 2024-10-28 | 2 |  | 2024-06-01 | 2024-06-08 |  | 2024-10-28 | 2024-11-14 | 18 |  | 2024-06-09 | 2024-06-10 |  | 2024-11-15 | 2024-11-16 | 2 | 169 |  | 2024-06-12 | 2024-06-19 |  | 2024-11-30 | 2025-06-22 | 205 |  | 2024-06-12 | 2024-06-19 |  | 2024-11-29 | 2024-11-29 | 1 |  |  |  | 2024-06-05 | 2024-06-22 |  | 2024-11-17 | 2025-03-17 | 121 |  | 2024-11-03 | 2024-11-09 |  | Completed | Completed | #VALUE! |  | 2024-12-26 | 2024-12-31 |  | Completed | Completed | #VALUE! |  | SHREE Con. | 2025-01-01 | 2025-01-07 |  | 2024-11-23 | 2025-01-15 | 54 |  | 2025-01-14 | 2025-01-21 |  | 2025-01-21 | 2025-01-30 | 10 |  | 2024-06-24 | 2024-07-02 |  | 2025-05-02 | 2025-05-14 | 13 |  | 2025-01-23 | 2025-01-28 |  | 2025-03-31 | 2025-04-04 | 5 |  | 2025-01-29 | 2025-02-01 |  | 2025-04-05 | 2025-04-07 | 3 |  | 2024-07-04 | 2024-07-06 |  | 2025-06-04 | 2025-06-04 | 1 |  | 2025-01-04 | 2025-01-11 |  | 2025-05-04 | 2025-05-13 | 10 |  | 2025-01-03 | 2025-01-18 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-01-11 | 2025-01-14 |  | 2025-07-26 | 2025-08-20 | 26 |  | 2025-02-01 | 2025-02-02 |  | 2025-08-20 | 2025-08-22 | 3 |  |  | 2025-03-01
PERENNIAL | 113 | PSS-8 | ARE41L | WTG 279 | Precast | F9 | Menard | Done | 539460 | 2672251 | 2023-12-30 | 2024-01-28 |  | 2023-12-30 | 2024-01-28 |  | 199 | 199 | 2024-09-20 | 2024-09-25 |  | 2024-12-18 | 2025-01-07 | 21 | [8 empty] | 2024-10-23 | 2024-10-24 |  | 2025-01-11 | 2025-01-15 | 5 |  | 2024-10-25 | 2024-10-26 |  | 2025-01-23 | 2025-01-27 | 5 |  | 2024-10-27 | 2024-10-27 |  | 2025-02-04 | 2025-02-04 | 1 |  | 2024-10-28 | 2024-10-29 |  | 2025-02-11 | 2025-02-11 | 1 |  | 2024-10-30 | 2024-11-06 |  | 2025-02-14 | 2025-02-27 | 14 |  | 2024-11-07 | 2024-11-08 |  | 2025-02-27 | 2025-02-28 | 2 | 49 |  | 2024-11-10 | 2024-11-16 |  | 2025-03-16 | 2025-08-12 | 150 |  | 2024-11-10 | 2024-11-16 |  | 2025-03-07 | 2025-03-07 | 1 |  |  |  | 2024-11-04 | 2024-11-18 |  | 2025-03-11 | 2025-05-01 | 52 |  | 2024-12-05 | 2024-12-11 |  | Completed | Completed | #VALUE! |  | 2024-12-22 | 2024-12-27 |  | 2025-06-12 | 2025-06-20 | 9 |  | Odhav (Reuse) | 2024-12-28 | 2025-01-03 |  | 2025-01-15 | 2025-03-31 | 76 |  | 2025-01-10 | 2025-01-17 |  | 2025-06-25 | 2025-07-17 | 23 |  | 2024-11-20 | 2024-11-28 |  | 2025-06-04 | 2025-07-25 | 52 |  | 2025-01-19 | 2025-01-24 |  | 2025-07-21 | 2025-07-28 | 8 |  | 2025-01-25 | 2025-01-28 |  | 2025-07-29 | 2025-07-31 | 3 |  | 2024-11-30 | 2024-12-02 |  | 2025-07-18 | 2025-07-18 | 1 |  | 2024-12-31 | 2025-01-07 |  | 2025-05-04 | 2025-05-15 | 12 |  | 2025-01-03 | 2025-01-18 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-01-07 | 2025-01-10 |  | 2025-07-26 | 2025-08-20 | 26 |  | 2025-01-28 | 2025-01-29 |  | 2025-08-21 | 2025-08-22 | 2 |  |  | 2025-03-01
DNC | 114 | PSS-8 | AHEJ5L | WTG 278 | Precast | F6 | Menard | Done | 539270 | 2673237 | 2024-01-10 | 2024-01-31 |  | 2024-01-10 | 2024-01-31 |  | 253 | 253 | 2024-05-27 | 2024-06-01 |  | 2024-05-27 | 2024-06-01 | 6 |  | Yes | 2024-12-30 | 2025-01-08 |  | 2025-02-19 | 2025-03-10 |  | 2024-10-29 | 2024-10-30 |  | 2025-03-15 | 2025-03-17 | 3 |  | 2024-10-31 | 2024-11-01 |  | 2025-03-17 | 2025-03-18 | 2 |  | 2024-11-02 | 2024-11-02 |  | 2025-03-18 | 2025-03-18 | 1 |  | 2024-11-03 | 2024-11-04 |  | 2025-03-20 | 2025-03-20 | 1 |  | 2024-11-05 | 2024-11-12 |  | 2025-03-21 | 2025-03-29 | 9 |  | 2024-11-13 | 2024-11-14 |  | 2025-03-30 | 2025-03-31 | 2 | 17 |  | 2024-11-16 | 2024-11-22 |  | 2025-04-30 | 2026-01-10 | 256 |  | 2024-11-16 | 2024-11-22 |  | 2025-04-16 | 2025-04-16 | 1 |  |  |  | 2024-11-10 | 2024-11-24 |  | 2025-03-21 | 2025-05-05 | 46 |  | 2024-12-15 | 2024-12-21 |  | 2025-04-22 | 2025-05-03 | 12 |  | 2024-12-22 | 2024-12-27 |  | 2025-05-04 | 2025-12-27 | 238 |  | Odhav | 2024-12-28 | 2025-01-03 |  | 2025-05-04 | 2025-12-27 | 238 |  | 2025-01-10 | 2025-01-17 |  | 2025-12-28 | 2026-01-07 | 11 |  | 2024-11-26 | 2024-12-04 |  | 2025-06-09 | 2026-01-08 | 214 |  | 2025-01-19 | 2025-01-24 |  | 2026-01-11 | 2026-01-17 | 7 |  | 2025-01-25 | 2025-01-28 |  | 2026-01-17 | 2026-01-19 | 3 |  | 2024-12-06 | 2024-12-08 |  | 2025-11-10 | 2025-11-10 | 1 |  | 2024-12-31 | 2025-01-07 |  | 2025-04-10 | 2025-04-22 | 13 |  | 2025-01-03 | 2025-01-18 |  | 2025-05-31 | 2025-06-28 | 29 |  | 2025-01-07 | 2025-01-10 |  | 2026-01-13 | 2026-01-19 |  |  | 2025-01-28 | 2025-01-29 |  | 2026-01-31 | 2026-02-11 | 12 |  |  | 2025-03-01
SHREERAM | 115 | PSS-8 | AHEJ5L | WTG 301 | Precast | F6 | Menard | Done | 539921 | 2673919 | 2024-01-12 | 2024-02-01 |  | 2024-01-12 | 2024-02-01 |  | 253 | 253 | 2024-10-01 | 2024-10-09 |  | 2025-01-13 | 2025-01-22 | 10 | [8 empty] | 2024-10-31 | 2024-11-01 |  | 2025-01-25 | 2025-01-31 | 7 |  | 2024-11-02 | 2024-11-03 |  | 2025-02-05 | 2025-02-07 | 3 |  | 2024-11-04 | 2024-11-04 |  | 2025-02-07 | 2025-02-07 | 1 |  | 2024-11-05 | 2024-11-06 |  | 2025-02-08 | 2025-02-08 | 1 |  | 2024-11-07 | 2024-11-14 |  | 2025-02-10 | 2025-02-18 | 9 |  | 2024-11-15 | 2024-11-16 |  | 2025-02-19 | 2025-02-20 | 2 | 27 |  | 2024-11-18 | 2024-11-24 |  | 2025-03-05 | 2025-05-29 | 86 |  | 2024-11-18 | 2024-11-24 |  | 2025-03-01 | 2025-03-02 | 2 |  |  |  | 2024-11-12 | 2024-11-26 |  | 2025-02-12 | 2025-05-04 | 82 |  | 2025-01-01 | 2025-01-06 |  | 2025-04-15 | 2025-04-27 | 13 |  | 2024-12-23 | 2024-12-28 |  | 2025-04-27 | 2025-05-26 | 30 |  | Odhav (Reuse) | 2024-12-29 | 2025-01-04 |  | 2025-04-27 | 2025-05-26 | 30 |  | 2025-01-11 | 2025-01-18 |  | 2025-07-11 | 2025-08-02 | 23 |  | 2024-11-28 | 2024-12-06 |  | 2025-05-03 | 2025-05-20 | 18 |  | 2025-01-20 | 2025-01-25 |  | 2025-08-04 | 2025-08-12 | 9 |  | 2025-01-26 | 2025-01-29 |  | 2025-08-13 | 2025-08-14 | 2 |  | 2024-12-08 | 2024-12-10 |  | 2025-08-08 | 2025-08-08 | 1 |  | 2025-01-01 | 2025-01-08 |  | 2025-02-09 | 2025-04-01 | 52 |  | 2025-01-03 | 2025-01-18 |  | 2025-05-31 | 2025-06-28 | 29 |  | 2025-01-08 | 2025-01-11 |  | 2025-09-02 | 2025-09-20 | 19 |  | 2025-01-29 | 2025-01-30 |  | 2025-09-26 | 2025-09-30 | 5 |  |  | 2025-03-01
SHREEJI | 116 | PSS-8 | ARE41L | WTG 256 | Precast | F9 | Menard | Done | 538816 | 2671529 | 2024-01-01 | 2024-01-28 |  | 2024-01-01 | 2024-01-28 |  | 199 | 199 | 2024-09-20 | 2024-09-26 |  | 2024-12-07 | 2024-12-17 | 11 |  | Yes | 2024-10-10 | 2024-10-28 |  | 2025-02-25 | 2025-03-09 |  | 2024-10-04 | 2024-10-05 |  | 2025-03-13 | 2025-03-14 | 2 |  | 2024-10-06 | 2024-10-07 |  | 2025-03-14 | 2025-03-16 | 3 |  | 2024-10-08 | 2024-10-08 |  | 2025-03-17 | 2025-03-17 | 1 |  | 2024-10-09 | 2024-10-10 |  | 2025-03-20 | 2025-03-20 | 1 |  | 2024-10-11 | 2024-10-18 |  | 2025-03-21 | 2025-03-25 | 5 |  | 2024-10-19 | 2024-10-20 |  | 2025-03-25 | 2025-03-26 | 2 | 14 |  | 2024-10-22 | 2024-10-28 |  | 2025-04-02 | 2025-06-02 | 62 |  | 2024-10-22 | 2024-10-28 |  | 2025-04-14 | 2025-04-14 | 1 |  |  |  | 2024-10-16 | 2024-10-30 |  | 2025-04-23 | 2025-05-05 | 13 |  | 2025-01-03 | 2025-01-09 |  | Completed | Completed | #VALUE! |  | 2024-12-24 | 2024-12-29 |  | 2025-03-20 | 2025-04-08 | 20 |  | ODHAV (Reuse) | 2024-12-30 | 2025-01-05 |  | 2025-03-20 | 2025-04-08 | 20 |  | 2025-01-12 | 2025-01-19 |  | 2025-07-10 | 2025-07-23 | 14 |  | 2024-11-01 | 2024-11-09 |  | 2025-05-23 | 2025-06-23 | 32 |  | 2025-01-21 | 2025-01-26 |  | 2025-07-24 | 2025-08-04 | 12 |  | 2025-01-27 | 2025-01-30 |  | 2025-08-05 | 2025-08-07 | 3 |  | 2024-11-11 | 2024-11-13 |  | 2025-07-10 | 2025-07-10 | 1 |  | 2025-01-02 | 2025-01-09 |  | 2025-04-14 | 2025-05-14 | 31 |  | 2025-01-03 | 2025-01-18 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-01-09 | 2025-01-12 |  | 2025-07-26 | 2025-08-20 | 26 |  | 2025-01-30 | 2025-01-31 |  | 2025-08-21 | 2025-08-21 | 1 |  |  | 2025-03-01
SVRE | 117 | PSS-8 | ARE41L | WTG 168 | Precast | F2 | Bauer | Done | 535657 | 2671681 | 2024-01-07 | 2024-01-31 |  | 2024-01-07 | 2024-01-31 |  | 199 | 199 | 2024-09-24 | 2024-09-30 |  | 2024-12-16 | 2024-12-21 | 6 | [8 empty] | 2024-10-06 | 2024-10-07 |  | 2024-12-31 | 2025-01-03 | 4 |  | 2024-10-08 | 2024-10-09 |  | 2025-01-06 | 2025-01-06 | 1 |  | 2024-10-10 | 2024-10-10 |  | 2025-01-08 | 2025-01-08 | 1 |  | 2024-10-11 | 2024-10-12 |  | 2025-01-11 | 2025-01-14 | 4 |  | 2024-10-13 | 2024-10-20 |  | 2025-01-15 | 2025-01-30 | 16 |  | 2024-10-21 | 2024-10-22 |  | 2025-01-31 | 2025-01-31 | 1 | 32 |  | 2024-10-24 | 2024-10-30 |  | 2025-02-11 | 2025-05-13 | 92 |  | 2024-10-24 | 2024-10-30 |  | 2025-02-07 | 2025-02-07 | 1 |  |  |  | 2024-10-18 | 2024-11-01 |  | 2025-02-05 | 2025-03-09 | 33 |  | 2025-01-09 | 2025-01-15 |  | 2024-12-10 | 2024-12-19 | 10 |  | 2024-12-25 | 2024-12-30 |  | 2025-01-22 | 2025-02-08 | 18 |  | HARSH | 2024-12-31 | 2025-01-06 |  | 2024-12-29 | 2025-01-27 | 30 |  | 2025-01-13 | 2025-01-20 |  | 2025-03-17 | 2025-03-29 | 13 |  | 2024-11-03 | 2024-11-11 |  | 2025-06-05 | 2025-08-07 | 64 |  | 2025-01-22 | 2025-01-27 |  | 2025-04-05 | 2025-04-08 | 4 |  | 2025-01-28 | 2025-01-31 |  | 2025-04-09 | 2025-04-20 | 12 | Pre-Comm hold due to 2 nos. blade bolt broken | 2024-11-13 | 2024-11-15 |  | 2025-07-12 | 2025-07-12 | 1 |  | 2025-01-03 | 2025-01-10 |  | 2025-01-24 | 2025-05-05 | 102 |  | 2025-01-03 | 2025-01-18 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-01-10 | 2025-01-13 |  | 2025-08-05 | 2025-08-24 | 20 |  | 2025-01-31 | 2025-02-01 |  | 2025-08-26 | 2025-08-27 | 2 |  |  | 2025-03-01
SHREEJI | 118 | PSS-8 | ARE41L | WTG 190 | Precast | F3 | Menard | Done | 536491 | 2671416 | 2024-01-07 | 2024-01-31 |  | 2024-01-07 | 2024-01-31 |  | 199 | 199 | 2024-09-26 | 2024-10-03 |  | 2024-12-03 | 2024-12-11 | 9 | [8 empty] | 2024-10-08 | 2024-10-09 |  | 2024-12-14 | 2024-12-23 | 10 |  | 2024-10-10 | 2024-10-11 |  | 2024-12-23 | 2024-12-25 | 3 |  | 2024-10-12 | 2024-10-12 |  | 2024-12-25 | 2024-12-25 | 1 |  | 2024-10-13 | 2024-10-14 |  | 2024-12-31 | 2024-12-31 | 1 |  | 2024-10-15 | 2024-10-22 |  | 2025-01-03 | 2025-01-09 | 7 |  | 2024-10-23 | 2024-10-24 |  | 2025-01-10 | 2025-01-11 | 2 | 29 |  | 2024-10-26 | 2024-11-01 |  | 2025-01-18 | 2025-05-14 | 117 |  | 2024-10-26 | 2024-11-01 |  | 2025-01-20 | 2025-01-20 | 1 |  |  |  | 2024-10-20 | 2024-11-03 |  | 2025-01-14 | 2025-04-27 | 104 |  | 2025-01-11 | 2025-01-23 |  | 2025-01-09 | 2025-01-29 | 21 |  | 2024-12-26 | 2024-12-31 |  | 2025-02-10 | 2025-02-24 | 15 |  | GP | 2025-01-01 | 2025-01-07 |  | 2025-01-13 | 2025-02-15 | 34 |  | 2025-01-14 | 2025-01-21 |  | 2025-03-10 | 2025-03-26 | 17 |  | 2024-11-05 | 2024-11-13 |  | 2025-04-30 | 2025-05-14 | 15 |  | 2025-01-23 | 2025-01-28 |  | 2025-04-15 | 2025-06-06 | 53 | Work hold,Termination team not available | 2025-01-29 | 2025-02-01 |  | 2025-06-07 | 2025-06-25 | 19 | Hold due to wind sensor not available | 2024-11-15 | 2024-11-17 |  | 2025-05-23 | 2025-05-23 | 1 |  | 2025-01-04 | 2025-01-11 |  | 2025-02-09 | 2025-03-05 | 25 |  | 2025-01-03 | 2025-01-18 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-01-11 | 2025-01-14 |  | 2025-06-23 | 2025-07-15 | 23 |  | 2025-02-01 | 2025-02-02 |  | 2025-07-18 | 2025-07-18 | 1 |  |  | 2025-03-01
DNC | 119 | PSS-8 | ARE41L | WTG 189 | Precast | F3 | Menard | Done | 536301 | 2672403 | 2024-04-27 | 2024-05-01 |  | 2024-04-27 | 2024-05-01 |  | 199 | 199 | 2024-09-28 | 2024-10-07 |  | 2024-11-14 | 2024-11-26 | 13 |  | Yes | 2024-12-18 | 2024-12-27 |  | 2024-12-24 | 2025-01-15 |  | 2024-10-10 | 2024-10-11 |  | 2025-01-22 | 2025-01-24 | 3 |  | 2024-10-12 | 2024-10-13 |  | 2025-01-24 | 2025-01-25 | 2 |  | 2024-10-14 | 2024-10-14 |  | 2025-01-26 | 2025-01-26 | 1 |  | 2024-10-15 | 2024-10-16 |  | 2025-01-28 | 2025-01-28 | 1 |  | 2024-10-17 | 2024-10-24 |  | 2025-01-28 | 2025-01-31 | 4 |  | 2024-10-25 | 2024-10-26 |  | 2025-02-01 | 2025-02-01 | 1 | 11 |  | 2024-10-28 | 2024-11-03 |  | 2025-02-06 | 2025-06-10 | 125 |  | 2024-10-28 | 2024-11-03 |  | 2025-02-10 | 2025-02-10 | 1 |  |  |  | 2024-10-22 | 2024-11-05 |  | 2025-01-24 | 2025-05-12 | 109 |  | 2025-01-16 | 2025-01-22 |  | Completed | Completed | #VALUE! |  | 2024-12-28 | 2025-01-02 |  | 2025-03-21 | 2025-04-03 | 14 |  | SS Jadeja | 2025-01-03 | 2025-01-09 |  | 2025-01-11 | 2025-04-04 | 84 |  | 2025-01-16 | 2025-01-23 |  | 2025-04-05 | 2025-05-02 | 28 |  | 2024-11-07 | 2024-11-15 |  | 2025-05-18 | 2025-06-17 | 31 |  | 2025-01-25 | 2025-01-30 |  | 2025-05-08 | 2025-05-17 | 10 |  | 2025-01-31 | 2025-02-03 |  | 2025-05-18 | 2025-05-19 | 2 |  | 2024-11-17 | 2024-11-19 |  | 2025-06-11 | 2025-06-11 | 1 |  | 2025-01-06 | 2025-01-13 |  | 2025-03-08 | 2025-04-04 | 28 |  | 2025-01-03 | 2025-01-18 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-01-13 | 2025-01-16 |  | 2025-06-23 | 2025-07-15 | 23 |  | 2025-02-03 | 2025-02-04 |  | 2025-07-17 | 2025-07-18 | 2 |  |  | 2025-03-01
AB INFRA | 120 | PSS-8 | ARE41L | WTG 167 | Precast | F2 | Bauer | Done | 535468 | 2672667 | 2024-04-28 | 2024-05-01 |  | 2024-04-28 | 2024-05-01 |  | 199 | 199 | 2024-10-03 | 2024-10-10 |  | 2024-12-02 | 2024-12-16 | 15 | [8 empty] | 2024-10-16 | 2024-10-17 |  | 2024-12-20 | 2024-12-24 | 5 |  | 2024-10-18 | 2024-10-19 |  | 2024-12-25 | 2024-12-25 | 1 |  | 2024-10-20 | 2024-10-20 |  | 2024-12-26 | 2024-12-26 | 1 |  | 2024-10-21 | 2024-10-22 |  | 2024-12-29 | 2024-12-31 | 3 |  | 2024-10-23 | 2024-10-30 |  | 2025-01-09 | 2025-01-28 | 20 | Unskilled manpower | 2024-10-31 | 2024-11-01 |  | 2025-01-28 | 2025-01-29 | 2 | 41 |  | 2024-11-03 | 2024-11-09 |  | 2025-02-03 | 2025-05-05 | 92 |  | 2024-11-03 | 2024-11-09 |  | 2025-02-01 | 2025-02-01 | 1 |  |  |  | 2024-10-28 | 2024-11-11 |  | 2025-02-12 | 2025-03-08 | 25 |  | 2025-01-18 | 2025-01-24 |  | 2025-01-22 | 2025-02-10 | 20 |  | 2024-12-29 | 2025-01-03 |  | 2025-04-02 | 2025-04-14 | 13 |  | Odhav (Reuse) | 2025-01-04 | 2025-01-10 |  | 2025-02-16 | 2025-04-04 | 48 |  | 2025-01-17 | 2025-01-24 |  | 2025-08-25 | 2025-10-20 | 57 |  | 2024-11-13 | 2024-11-21 |  | 2025-05-24 | 2025-07-29 | 67 |  | 2025-01-26 | 2025-01-31 |  | 2025-10-24 | 2025-10-27 | 4 |  | 2025-02-01 | 2025-02-04 |  | 2025-10-27 | 2025-10-28 | 2 |  | 2024-11-23 | 2024-11-25 |  | 2025-08-11 | 2025-08-11 | 1 |  | 2025-01-07 | 2025-01-14 |  | 2025-02-16 | 2025-06-05 | 110 |  | 2025-01-03 | 2025-01-18 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-01-14 | 2025-01-17 |  | 2025-08-17 | 2025-08-24 | 8 |  | 2025-02-04 | 2025-02-05 |  | 2025-10-28 | 2025-11-05 | 9 |  |  | 2025-03-01
BALAJI & Co | 121 | PSS-4 | ACL | WTG 035 | Precast | F2 | Bauer | Done | 529416 | 2675666 | 2024-05-05 | 2024-05-16 |  | 2024-05-05 | 2024-05-16 |  | 199 | 199 | 2024-09-13 | 2024-09-22 |  | 2024-11-19 | 2024-11-23 | 5 | [8 empty] | 2024-10-08 | 2024-10-08 |  | 2024-12-28 | 2025-01-03 | 7 |  | 2024-10-09 | 2024-10-09 |  | 2025-01-15 | 2025-01-16 | 2 |  | 2024-10-10 | 2024-10-10 |  | 2025-01-16 | 2025-01-16 | 1 |  | 2024-10-11 | 2024-10-12 |  | 2025-01-17 | 2025-01-17 | 1 |  | 2024-10-14 | 2024-10-23 |  | 2025-01-17 | 2025-01-22 | 6 |  | 2024-10-25 | 2024-10-26 |  | 2025-01-22 | 2025-01-23 | 2 | 27 |  | 2024-10-27 | 2024-11-02 |  | 2025-01-26 | 2025-04-01 | 66 |  | 2024-10-27 | 2024-11-02 |  | 2025-02-04 | 2025-02-04 | 1 |  |  |  | 2024-10-21 | 2024-11-04 |  | 2025-02-12 | 2025-02-21 | 10 |  | 2024-10-20 | 2024-10-26 |  | 2025-02-01 | 2025-02-16 | 16 |  | 2024-10-20 | 2024-10-26 |  | 2025-02-07 | 2025-02-28 | 22 |  | Kesav | 2024-10-27 | 2024-11-02 |  | 2025-02-05 | 2025-02-28 | 24 |  | 2024-11-28 | 2024-12-03 |  | 2025-03-04 | 2025-03-17 | 14 |  | 2024-11-19 | 2024-11-25 |  | 2025-03-10 | 2025-03-23 | 14 |  | 2024-12-06 | 2024-12-15 |  | 2025-03-26 | 2025-03-28 | 3 |  | 2024-12-17 | 2024-12-19 |  | 2025-03-29 | 2025-03-30 | 2 |  | 2024-12-01 | 2024-12-02 |  | 2025-03-25 | 2025-03-25 | 1 |  | 2024-11-18 | 2024-11-24 |  | 2024-12-06 | 2024-12-18 | 13 |  | 2024-11-20 | 2024-12-05 |  | 2025-02-26 | 2025-03-17 | 20 |  | 2024-12-02 | 2024-12-05 |  | 2025-04-16 | 2025-04-27 | 12 |  | 2024-12-19 | 2024-12-20 |  | 2025-04-27 | 2025-04-27 | 1 |  |  | 2025-03-01
AB INFRA | 122 | PSS-4 | ACL | WTG 050 | Precast | F4 | Bauer | Done | 530257 | 2675362 | 2024-05-05 | 2024-05-18 |  | 2024-05-05 | 2024-05-18 |  | 199 | 199 | 2024-09-14 | 2024-09-23 |  | 2024-11-14 | 2024-11-18 | 5 | [8 empty] | 2024-10-09 | 2024-10-09 |  | 2024-11-28 | 2024-12-06 | 9 |  | 2024-10-10 | 2024-10-10 |  | 2024-12-07 | 2025-01-14 | 39 | Delay due to water logging | 2024-10-11 | 2024-10-11 |  | 2025-01-14 | 2025-01-14 | 1 |  | 2024-10-12 | 2024-10-13 |  | 2025-02-05 | 2025-02-05 | 1 |  | 2024-10-15 | 2024-10-24 |  | 2025-02-06 | 2025-02-16 | 11 |  | 2024-10-26 | 2024-10-27 |  | 2025-02-17 | 2025-02-17 | 1 | 82 |  | 2024-10-28 | 2024-11-03 |  | 2025-03-01 | 2025-04-20 | 51 |  | 2024-10-28 | 2024-11-03 |  | 2025-02-25 | 2025-02-25 | 1 |  |  |  | 2024-10-22 | 2024-11-05 |  | 2025-03-10 | 2025-03-13 | 4 |  | 2024-10-21 | 2024-10-27 |  | 2025-02-01 | 2025-02-18 | 18 |  | 2024-10-21 | 2024-10-27 |  | 2025-02-17 | 2025-03-03 | 15 |  | Adani (Self Resue) | 2024-10-28 | 2024-11-03 |  | 2025-02-17 | 2025-03-07 | 19 |  | 2024-11-29 | 2024-12-04 |  | 2025-03-17 | 2025-04-02 | 17 |  | 2024-11-20 | 2024-11-26 |  | 2025-03-27 | 2025-04-06 | 11 |  | 2024-12-07 | 2024-12-16 |  | 2025-04-09 | 2025-04-14 | 6 |  | 2024-12-18 | 2024-12-20 |  | 2025-04-15 | 2025-04-16 | 2 |  | 2024-12-02 | 2024-12-03 |  | 2025-04-05 | 2025-04-05 | 1 |  | 2024-11-19 | 2024-11-25 |  | 2024-12-06 | 2025-01-27 | 53 |  | 2024-11-20 | 2024-12-05 |  | 2025-01-30 | 2025-02-19 | 21 |  | 2024-12-03 | 2024-12-06 |  | 2025-04-16 | 2025-04-27 | 12 |  | 2024-12-20 | 2024-12-21 |  | 2025-04-27 | 2025-04-27 | 1 |  |  | 2025-03-01
MSC | 123 | PSS-4 | ACL | WTG 067 | Precast | F2 | Bauer | Done | 531090 | 2675097 | 2024-05-04 | 2024-05-18 |  | 2024-05-04 | 2024-05-18 |  | 199 | 199 | 2024-09-15 | 2024-09-24 |  | 2024-11-06 | 2024-11-13 | 8 | [8 empty] | 2024-10-10 | 2024-10-10 |  | 2024-11-25 | 2024-12-01 | 7 |  | 2024-10-11 | 2024-10-11 |  | 2024-12-02 | 2024-12-03 | 2 |  | 2024-10-12 | 2024-10-12 |  | 2024-12-03 | 2024-12-03 | 1 |  | 2024-10-13 | 2024-10-14 |  | 2025-01-08 | 2025-01-09 | 2 |  | 2024-10-16 | 2024-10-25 |  | 2025-01-10 | 2025-01-14 | 5 |  | 2024-10-27 | 2024-10-28 |  | 2025-01-15 | 2025-01-16 | 2 | 53 |  | 2024-10-29 | 2024-11-04 |  | 2025-01-22 | 2025-03-03 | 41 |  | 2024-10-29 | 2024-11-04 |  | 2025-01-22 | 2025-01-22 | 1 |  |  |  | 2024-10-23 | 2024-11-06 |  | 2024-12-01 | 2025-02-25 | 87 |  | 2024-10-22 | 2024-10-28 |  | 2024-12-29 | 2025-01-08 | 11 |  | 2024-10-22 | 2024-10-28 |  | 2025-01-09 | 2025-01-22 | 14 |  | GP (Reuse) | 2024-10-29 | 2024-11-04 |  | 2025-01-09 | 2025-02-12 | 35 |  | 2024-11-30 | 2024-12-05 |  | 2025-02-17 | 2025-02-24 | 8 |  | 2024-11-26 | 2024-12-02 |  | 2025-03-10 | 2025-03-24 | 15 |  | 2024-12-08 | 2024-12-17 |  | 2025-04-16 | 2025-04-21 | 6 |  | 2024-12-19 | 2024-12-21 |  | 2025-04-22 | 2025-04-23 | 2 |  | 2024-12-08 | 2024-12-09 |  | 2025-03-30 | 2025-03-30 | 1 | After ten delta , SFRA test -testing team not done USS testing | 2024-11-20 | 2024-11-26 |  | 2024-12-10 | 2025-02-28 | 81 |  | 2024-11-20 | 2024-12-05 |  | 2025-02-26 | 2025-03-17 | 20 |  | 2024-12-09 | 2024-12-12 |  | 2025-04-07 | 2025-04-27 | 21 |  | 2024-12-21 | 2024-12-22 |  | 2025-04-27 | 2025-04-27 | 1 |  |  | 2025-03-01
DNC | 124 | PSS-4 | ACL | WTG 085 | Precast | F4 | Bauer | Done | 531930 | 2674792 | 2024-05-03 | 2024-05-16 |  | 2024-05-03 | 2024-05-16 |  | 199 | 199 | 2024-09-24 | 2024-10-03 |  | 2024-10-29 | 2024-11-06 | 9 | [8 empty] | 2024-10-19 | 2024-10-19 |  | 2024-11-24 | 2024-11-25 | 2 |  | 2024-10-20 | 2024-10-20 |  | 2024-11-25 | 2024-11-26 | 2 |  | 2024-10-21 | 2024-10-21 |  | 2024-11-26 | 2024-11-26 | 1 |  | 2024-10-22 | 2024-10-23 |  | 2024-12-01 | 2024-12-02 | 2 |  | 2024-10-25 | 2024-11-03 |  | 2024-12-03 | 2024-12-31 | 29 | Work getting slow due to shortage of manpower | 2024-11-05 | 2024-11-06 |  | 2025-01-03 | 2025-01-04 | 2 | 42 |  | 2024-11-07 | 2024-11-13 |  | 2025-01-12 | 2025-04-05 | 84 |  | 2024-11-07 | 2024-11-13 |  | 2025-01-20 | 2025-01-20 | 1 |  |  |  | 2024-11-01 | 2024-11-15 |  | 2025-02-23 | 2025-02-25 | 3 |  | 2024-11-02 | 2024-11-08 |  | 2024-12-28 | 2025-01-10 | 14 |  | 2024-11-02 | 2024-11-08 |  | 2025-01-22 | 2025-01-27 | 6 |  | GP | 2024-11-09 | 2024-11-15 |  | 2025-01-14 | 2025-01-22 | 9 |  | 2024-12-06 | 2024-12-11 |  | 2025-01-28 | 2025-02-07 | 11 |  | 2024-11-27 | 2024-12-03 |  | 2025-03-06 | 2025-03-19 | 14 |  | 2024-12-14 | 2024-12-23 |  | 2025-03-08 | 2025-03-21 | 14 |  | 2024-12-25 | 2024-12-27 |  | 2025-03-21 | 2025-03-22 | 2 |  | 2024-12-09 | 2024-12-10 |  | 2025-03-19 | 2025-03-19 | 1 |  | 2024-11-20 | 2024-11-26 |  | 2024-12-06 | 2025-01-25 | 51 |  | 2024-11-20 | 2024-12-05 |  | 2025-01-30 | 2025-02-19 | 21 |  | 2024-12-10 | 2024-12-13 |  | 2025-03-19 | 2025-03-19 | 1 |  | 2024-12-27 | 2024-12-28 |  | 2025-03-23 | 2025-03-23 | 1 |  |  | 2025-03-01
DNC | 125 | PSS-4 | ACL | WTG 103 | Precast | F4 | Bauer | Done | 532763 | 2674527 | 2024-05-04 | 2024-05-18 |  | 2024-05-04 | 2024-05-18 |  | 199 | 199 | 2024-09-25 | 2024-10-04 |  | 2024-10-23 | 2024-10-28 | 6 | [8 empty] | 2024-10-20 | 2024-10-20 |  | 2024-12-02 | 2024-12-04 | 3 |  | 2024-10-21 | 2024-10-21 |  | 2024-12-05 | 2024-12-06 | 2 |  | 2024-10-22 | 2024-10-22 |  | 2024-12-09 | 2024-12-09 | 1 |  | 2024-10-23 | 2024-10-24 |  | 2024-12-11 | 2024-12-11 | 1 |  | 2024-10-26 | 2024-11-04 |  | 2024-12-12 | 2024-12-17 | 6 |  | 2024-11-06 | 2024-11-07 |  | 2024-12-18 | 2024-12-19 | 2 | 18 |  | 2024-11-08 | 2024-11-14 |  | 2024-12-23 | 2025-03-28 | 96 |  | 2024-11-08 | 2024-11-14 |  | 2024-12-23 | 2024-12-23 | 1 |  |  |  | 2024-11-02 | 2024-11-16 |  | 2024-12-26 | 2025-01-16 | 22 |  | 2024-11-03 | 2024-11-09 |  | Completed | Completed | #VALUE! |  | 2024-11-03 | 2024-11-09 |  | 2025-01-10 | 2025-01-24 | 15 |  | Varudi | 2024-11-10 | 2024-11-16 |  | 2025-01-03 | 2025-01-24 | 22 |  | 2024-12-07 | 2024-12-12 |  | 2025-02-11 | 2025-02-23 | 13 |  | 2024-11-28 | 2024-12-04 |  | 2025-01-31 | 2025-03-08 | 37 |  | 2024-12-15 | 2024-12-24 |  | 2025-03-04 | 2025-03-13 | 10 |  | 2024-12-26 | 2024-12-28 |  | 2025-03-14 | 2025-03-17 | 4 |  | 2024-12-10 | 2024-12-11 |  | 2025-03-14 | 2025-03-14 | 1 |  | 2024-11-27 | 2024-12-03 |  | 2024-12-05 | 2025-02-19 | 77 |  | 2024-11-20 | 2024-12-05 |  | 2025-01-30 | 2025-02-19 | 21 |  | 2024-12-11 | 2024-12-14 |  | 2025-03-17 | 2025-03-18 | 2 |  | 2024-12-28 | 2024-12-29 |  | 2025-03-19 | 2025-03-20 | 2 |  |  | 2025-03-01
AB INFRA | 126 | PSS-8 | ARE41L | WTG 166 | Precast | F2 | Bauer | Done | 535278 | 2673654 | 2024-05-06 | 2024-05-18 |  | 2024-05-06 | 2024-05-18 |  | 199 | 199 | 2024-12-15 | 2024-12-23 |  | 2024-12-18 | 2024-12-25 | 8 | [8 empty] | 2025-01-01 | 2025-01-02 |  | 2024-12-31 | 2025-01-03 | 4 |  | 2025-01-03 | 2025-01-04 |  | 2025-01-03 | 2025-01-04 | 2 |  | 2025-01-05 | 2025-01-05 |  | 2025-01-05 | 2025-01-05 | 1 |  | 2025-01-06 | 2025-01-07 |  | 2025-01-08 | 2025-01-09 | 2 |  | 2025-01-08 | 2025-01-15 |  | 2025-01-19 | 2025-02-01 | 14 |  | 2025-01-16 | 2025-01-17 |  | 2025-02-02 | 2025-02-02 | 1 | 34 |  | 2025-01-19 | 2025-01-26 |  | 2025-02-07 | 2025-05-10 | 93 |  | 2025-01-19 | 2025-01-26 |  | 2025-02-07 | 2025-02-07 | 1 |  |  |  | 2025-01-12 | 2025-01-29 |  | 2025-02-18 | 2025-04-04 | 46 |  | 2025-01-24 | 2025-01-30 |  | 2025-01-07 | 2025-01-21 | 15 |  | 2025-01-01 | 2025-01-06 |  | 2025-02-07 | 2025-02-25 | 19 |  | HARSH | 2025-01-07 | 2025-01-13 |  | 2025-01-11 | 2025-02-11 | 32 |  | 2025-01-20 | 2025-01-27 |  | 2025-03-13 | 2025-04-22 | 41 |  | 2025-01-31 | 2025-02-08 |  | 2025-04-30 | 2025-05-15 | 16 |  | 2025-01-29 | 2025-02-03 |  | 2025-04-26 | 2025-05-05 | 10 |  | 2025-02-04 | 2025-02-07 |  | 2025-05-06 | 2025-05-07 | 2 |  | 2025-02-10 | 2025-02-12 |  | 2025-06-06 | 2025-06-06 | 1 |  | 2025-01-10 | 2025-01-17 |  | 2025-02-21 | 2025-04-22 | 61 |  | 2025-01-03 | 2025-01-18 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-02-12 | 2025-02-15 |  | 2025-08-09 | 2025-08-24 | 16 |  | 2025-02-15 | 2025-02-16 |  | 2025-08-26 | 2025-08-27 | 2 |  |  | 2025-03-01
BPS | 127 | PSS-8 | ARE41L | WTG 188 | Precast | F2 | Bauer | Done | 536111 | 2673389 | 2024-04-28 | 2024-05-01 |  | 2024-04-28 | 2024-05-01 |  | 253 | 253 | 2024-12-17 | 2024-12-24 |  | 2025-01-11 | 2025-01-25 | 15 |  | Yes | 2025-01-05 | 2025-01-20 |  | 2025-03-24 | 2025-04-09 |  | 2025-01-03 | 2025-01-04 |  | 2025-04-12 | 2025-04-13 | 2 |  | 2025-01-05 | 2025-01-06 |  | 2025-04-14 | 2025-04-15 | 2 |  | 2025-01-07 | 2025-01-07 |  | 2025-04-15 | 2025-04-15 | 1 |  | 2025-01-08 | 2025-01-09 |  | 2025-04-16 | 2025-04-16 | 1 |  | 2025-01-10 | 2025-01-17 |  | 2025-04-17 | 2025-04-21 | 5 |  | 2025-01-18 | 2025-01-19 |  | 2025-04-22 | 2025-04-23 | 2 | 12 |  | 2025-01-21 | 2025-01-28 |  | 2025-05-01 | 2025-08-13 | 105 |  | 2025-01-21 | 2025-01-28 |  | 2025-04-27 | 2025-04-27 | 1 |  |  |  | 2025-01-14 | 2025-01-31 |  | 2025-04-19 | 2025-04-24 | 6 |  | 2025-01-26 | 2025-02-02 |  | 2025-04-14 | 2025-04-27 | 14 |  | 2025-01-03 | 2025-01-08 |  | 2025-04-28 | 2025-05-10 | 13 |  | GP (Reuse) | 2025-01-09 | 2025-01-15 |  | 2025-04-28 | 2025-05-10 | 13 |  | 2025-01-22 | 2025-01-29 |  | 2025-07-15 | 2025-07-31 | 17 |  | 2025-02-02 | 2025-02-10 |  | 2025-05-24 | 2025-07-28 | 66 |  | 2025-01-31 | 2025-02-05 |  | 2025-08-02 | 2025-08-09 | 8 |  | 2025-02-06 | 2025-02-09 |  | 2025-08-10 | 2025-08-11 | 2 |  | 2025-02-12 | 2025-02-14 |  | 2025-08-06 | 2025-08-06 | 1 |  | 2025-01-12 | 2025-01-19 |  | 2025-02-08 | 2025-04-22 | 74 |  | 2025-01-03 | 2025-01-18 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-02-14 | 2025-02-17 |  | 2025-08-09 | 2025-08-24 | 16 |  | 2025-02-17 | 2025-02-18 |  | 2025-08-26 | 2025-08-27 | 2 |  |  | 2025-03-01
SHREEJI | 128 | PSS-8 | ARE41L | WTG 211 | Precast | F3 | Menard | Done | 536952 | 2673085 | 2024-04-26 | 2024-05-01 |  | 2024-04-26 | 2024-05-01 |  | 199 | 199 | 2024-12-19 | 2024-12-26 |  | 2024-12-12 | 2024-12-18 | 7 | [8 empty] | 2025-01-05 | 2025-01-06 |  | 2024-12-25 | 2024-12-29 | 5 |  | 2025-01-07 | 2025-01-08 |  | 2024-12-29 | 2024-12-30 | 2 |  | 2025-01-09 | 2025-01-09 |  | 2024-12-31 | 2024-12-31 | 1 |  | 2025-01-10 | 2025-01-11 |  | 2025-01-03 | 2025-01-03 | 1 |  | 2025-01-12 | 2025-01-19 |  | 2025-01-04 | 2025-01-11 | 8 |  | 2025-01-20 | 2025-01-21 |  | 2025-01-12 | 2025-01-12 | 1 | 19 |  | 2025-01-23 | 2025-01-30 |  | 2025-01-17 | 2025-06-16 | 151 |  | 2025-01-23 | 2025-01-30 |  | 2025-01-22 | 2025-01-22 | 1 |  |  |  | 2025-01-16 | 2025-02-02 |  | 2025-01-19 | 2025-04-20 | 92 |  | 2025-02-02 | 2025-02-08 |  | 2024-12-30 | 2025-01-12 | 14 |  | 2024-12-30 | 2025-01-04 |  | 2025-02-13 | 2025-03-14 | 30 |  | Odhav | 2025-01-05 | 2025-01-11 |  | 2025-02-03 | 2025-03-14 | 40 |  | 2025-01-18 | 2025-01-25 |  | 2025-03-29 | 2025-04-22 | 25 |  | 2025-02-04 | 2025-02-12 |  | 2025-05-21 | 2025-06-17 | 28 |  | 2025-01-27 | 2025-02-01 |  | 2025-05-25 | 2025-06-05 | 12 |  | 2025-02-02 | 2025-02-05 |  | 2025-06-07 | 2025-06-14 | 8 |  | 2025-02-14 | 2025-02-16 |  | 2025-06-20 | 2025-06-20 | 1 |  | 2025-01-08 | 2025-01-15 |  | 2025-02-06 | 2025-06-05 | 120 |  | 2025-01-03 | 2025-01-18 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-02-16 | 2025-02-19 |  | 2025-06-23 | 2025-07-15 | 23 |  | 2025-02-19 | 2025-02-20 |  | 2025-07-17 | 2025-07-18 | 2 |  |  | 2025-03-01
PERENNIAL | 129 | PSS-8 | ARE41L | WTG 233 | Precast | F4 | Menard | Done | 537785 | 2672820 | 2024-04-26 | 2024-05-01 |  | 2024-04-26 | 2024-05-01 |  | 253 | 253 | 2024-12-21 | 2024-12-28 |  | 2025-03-10 | 2025-03-22 | 13 |  | Yes | 2025-01-02 | 2025-01-15 |  | 2025-04-01 | 2025-04-17 |  | 2025-01-07 | 2025-01-08 |  | 2025-04-23 | 2025-04-25 | 3 |  | 2025-01-09 | 2025-01-10 |  | 2025-04-25 | 2025-04-27 | 3 |  | 2025-01-11 | 2025-01-11 |  | 2025-04-27 | 2025-04-27 | 1 |  | 2025-01-12 | 2025-01-13 |  | 2025-04-30 | 2025-04-30 | 1 |  | 2025-01-14 | 2025-01-21 |  | 2025-05-07 | 2025-05-14 | 8 |  | 2025-01-22 | 2025-01-23 |  | 2025-05-14 | 2025-05-15 | 2 | 23 |  | 2025-01-25 | 2025-02-01 |  | 2025-07-25 | 2025-06-10 | -44 |  | 2025-01-25 | 2025-02-01 |  | 2025-06-14 | 2025-06-14 | 1 |  |  |  | 2025-01-18 | 2025-02-04 |  | 2025-04-27 | 2025-07-16 | 81 |  | 2025-02-04 | 2025-02-10 |  | 2025-04-05 | 2025-04-16 | 12 |  | 2024-12-30 | 2025-01-04 |  | 2025-04-20 | 2025-05-30 | 41 |  | Adani (Self Resue) | 2025-01-05 | 2025-01-11 |  | 2025-04-20 | 2025-05-30 | 41 |  | 2025-01-18 | 2025-01-25 |  | 2025-07-11 | 2025-07-22 | 12 |  | 2025-02-06 | 2025-02-14 |  | 2025-06-09 | 2025-08-07 | 60 |  | 2025-01-27 | 2025-02-01 |  | 2025-07-24 | 2025-08-05 | 13 |  | 2025-02-02 | 2025-02-05 |  | 2025-08-06 | 2025-08-07 | 2 |  | 2025-02-16 | 2025-02-18 |  | 2025-08-05 | 2025-08-05 | 1 |  | 2025-01-08 | 2025-01-15 |  | 2025-03-28 | 2025-05-22 | 56 |  | 2025-01-03 | 2025-01-18 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-02-18 | 2025-02-21 |  | 2025-08-05 | 2025-08-20 | 16 |  | 2025-02-21 | 2025-02-22 |  | 2025-08-21 | 2025-08-22 | 2 |  |  | 2025-03-01
C & B | 130 | PSS-8 | ARE41L | WTG 255 | Precast | F4 | Menard | Done | 538626 | 2672515 | 2024-04-27 | 2024-05-01 |  | 2024-04-27 | 2024-05-01 |  | 199 | 199 | 2024-12-22 | 2024-12-29 |  | 2025-01-08 | 2025-01-14 | 7 | [8 empty] | 2025-01-09 | 2025-01-10 |  | 2025-02-14 | 2025-02-15 | 2 |  | 2025-01-11 | 2025-01-12 |  | 2025-02-15 | 2025-02-16 | 2 |  | 2025-01-13 | 2025-01-13 |  | 2025-02-16 | 2025-02-16 | 1 |  | 2025-01-14 | 2025-01-15 |  | 2025-02-19 | 2025-02-19 | 1 |  | 2025-01-16 | 2025-01-23 |  | 2025-02-20 | 2025-03-03 | 12 |  | 2025-01-24 | 2025-01-25 |  | 2025-03-04 | 2025-03-05 | 2 | 20 |  | 2025-01-27 | 2025-02-03 |  | 2025-03-13 | 2025-05-26 | 75 |  | 2025-01-27 | 2025-02-03 |  | 2025-03-11 | 2025-03-11 | 1 |  |  |  | 2025-01-20 | 2025-02-06 |  | 2025-02-24 | 2025-04-15 | 51 |  | 2025-02-08 | 2025-02-14 |  | Completed | Completed | #VALUE! |  | 2024-12-31 | 2025-01-05 |  | 2025-05-02 | 2025-05-20 | 19 |  | Odhav (Reuse) | 2025-01-06 | 2025-01-12 |  | 2025-01-13 | 2025-02-03 | 22 |  | 2025-01-19 | 2025-01-26 |  | 2025-05-21 | 2025-06-12 | 23 |  | 2025-02-08 | 2025-02-16 |  | 2025-05-22 | 2025-06-22 | 32 |  | 2025-01-28 | 2025-02-02 |  | 2025-06-19 | 2025-06-27 | 9 |  | 2025-02-03 | 2025-02-06 |  | 2025-06-28 | 2025-07-01 | 4 |  | 2025-02-18 | 2025-02-20 |  | 2025-07-12 | 2025-07-12 | 1 |  | 2025-01-09 | 2025-01-16 |  | 2025-03-04 | 2025-06-02 | 91 |  | 2025-01-03 | 2025-01-18 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-02-20 | 2025-02-23 |  | 2025-07-30 | 2025-08-20 | 22 |  | 2025-02-23 | 2025-02-24 |  | 2025-08-23 | 2025-08-24 | 2 |  |  | 2025-03-01
UNIQUE INF | 131 | PSS-4 | ACL | WTG 066 | Precast | F2 | Bauer | Done | 530900 | 2676083 | 2024-05-04 | 2024-05-18 |  | 2024-05-04 | 2024-05-18 |  | 199 | 199 | 2024-09-26 | 2024-10-05 |  | 2025-01-07 | 2025-01-15 | 9 | [8 empty] | 2024-10-21 | 2024-10-21 |  | 2025-01-21 | 2025-01-30 | 10 |  | 2024-10-22 | 2024-10-22 |  | 2025-01-31 | 2025-02-01 | 2 |  | 2024-10-23 | 2024-10-23 |  | 2025-02-02 | 2025-02-02 | 1 |  | 2024-10-24 | 2024-10-25 |  | 2025-02-03 | 2025-02-03 | 1 |  | 2024-10-27 | 2024-11-05 |  | 2025-02-03 | 2025-02-10 | 8 |  | 2024-11-07 | 2024-11-08 |  | 2025-02-10 | 2025-02-11 | 2 | 22 |  | 2024-11-09 | 2024-11-15 |  | 2025-02-16 | 2025-05-26 | 100 |  | 2024-11-09 | 2024-11-15 |  | 2025-02-25 | 2025-02-25 | 1 |  |  |  | 2024-11-03 | 2024-11-17 |  | 2025-01-22 | 2025-02-27 | 37 |  | 2024-11-04 | 2024-11-10 |  | 2025-02-01 | 2025-02-20 | 20 |  | 2024-11-04 | 2024-11-10 |  | 2025-02-13 | 2025-02-23 | 11 |  | Adani (Self Resue) | 2024-11-11 | 2024-11-17 |  | 2025-02-13 | 2025-02-25 | 13 |  | 2024-12-08 | 2024-12-13 |  | 2025-02-27 | 2025-03-13 | 15 |  | 2024-12-04 | 2024-12-10 |  | 2025-03-10 | 2025-03-26 | 17 |  | 2024-12-16 | 2024-12-25 |  | 2025-03-28 | 2025-04-03 | 7 |  | 2024-12-27 | 2024-12-29 |  | 2025-04-08 | 2025-04-20 | 13 | Pre-Comm hold due to 2 nos. blade bolt broken | 2024-12-16 | 2024-12-17 |  | 2025-03-31 | 2025-03-31 | 1 | After ten delta , SFRA test -testing team not done USS testing | 2024-11-28 | 2024-12-04 |  | 2024-12-08 | 2024-12-18 | 11 |  | 2024-11-20 | 2024-12-05 |  | 2025-02-26 | 2025-03-17 | 20 |  | 2024-12-17 | 2024-12-20 |  | 2025-04-07 | 2025-04-27 | 21 |  | 2024-12-29 | 2024-12-30 |  | 2025-04-27 | 2025-04-27 | 1 |  |  | 2025-03-01
POWER CORP/Odhav | 132 | PSS-8 | ARE41L | WTG 187 | Precast | F2 | Bauer | Done | 535921 | 2674375 | 2024-04-29 | 2024-05-01 |  | 2024-04-29 | 2024-05-01 |  | 199 | 199 | 2024-12-10 | 2024-12-18 |  | 2025-01-28 | 2025-02-03 | 7 | [8 empty] | 2025-01-11 | 2025-01-12 |  | 2025-02-14 | 2025-03-03 | 18 |  | 2025-01-13 | 2025-01-14 |  | 2025-03-04 | 2025-03-06 | 3 |  | 2025-01-15 | 2025-01-15 |  | 2025-03-06 | 2025-03-06 | 1 |  | 2025-01-16 | 2025-01-17 |  | 2025-03-09 | 2025-03-10 | 2 |  | 2025-01-18 | 2025-01-25 |  | 2025-03-15 | 2025-03-23 | 9 |  | 2025-01-26 | 2025-01-27 |  | 2025-03-24 | 2025-03-25 | 2 | 40 |  | 2025-01-29 | 2025-02-05 |  | 2025-04-07 | 2025-05-07 | 31 |  | 2025-01-29 | 2025-02-05 |  | 2025-04-03 | 2025-04-03 | 1 |  |  |  | 2025-01-22 | 2025-02-08 |  | 2025-03-19 | 2025-04-24 | 37 |  | 2025-02-08 | 2025-02-14 |  | 2025-03-28 | 2025-04-10 | 14 |  | 2025-01-01 | 2025-01-06 |  | 2025-04-12 | 2025-04-27 | 16 |  | GP (Reuse) | 2025-01-07 | 2025-01-13 |  | 2025-04-12 | 2025-04-28 | 17 |  | 2025-01-20 | 2025-01-27 |  | 2025-06-25 | 2025-07-16 | 22 |  | 2025-02-10 | 2025-02-18 |  | 2025-06-08 | 2025-07-29 | 52 |  | 2025-01-29 | 2025-02-03 |  | 2025-07-21 | 2025-07-27 | 7 |  | 2025-02-04 | 2025-02-07 |  | 2025-07-28 | 2025-07-29 | 2 |  | 2025-02-20 | 2025-02-22 |  | 2025-07-29 | 2025-07-29 | 1 |  | 2025-01-10 | 2025-01-17 |  | 2025-02-08 | 2025-05-05 | 87 |  | 2025-01-03 | 2025-01-18 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-02-22 | 2025-02-25 |  | 2025-08-05 | 2025-08-24 | 20 |  | 2025-02-25 | 2025-02-26 |  | 2025-08-26 | 2025-08-27 | 2 |  |  | 2025-03-01
POWER CORP | 133 | PSS-8 | ARE41L | WTG 210 | Precast | F3 | Menard | Done | 536762 | 2674071 | 2024-04-25 | 2024-04-27 |  | 2024-04-25 | 2024-04-27 |  | 199 | 199 | 2024-12-20 | 2024-12-28 |  | 2024-12-18 | 2024-12-25 | 8 | [8 empty] | 2025-01-13 | 2025-01-14 |  | 2024-12-31 | 2025-01-02 | 3 |  | 2025-01-15 | 2025-01-16 |  | 2025-01-05 | 2025-01-07 | 3 |  | 2025-01-17 | 2025-01-17 |  | 2025-01-16 | 2025-01-16 | 1 |  | 2025-01-18 | 2025-01-19 |  | 2025-01-24 | 2025-01-24 | 1 |  | 2025-01-20 | 2025-01-27 |  | 2025-01-26 | 2025-02-04 | 10 |  | 2025-01-28 | 2025-01-29 |  | 2025-02-05 | 2025-02-05 | 1 | 37 |  | 2025-01-31 | 2025-02-07 |  | 2025-03-01 | 2025-05-31 | 92 |  | 2025-01-31 | 2025-02-07 |  | 2025-02-21 | 2025-02-21 | 1 |  |  |  | 2025-01-24 | 2025-02-10 |  | 2025-01-08 | 2025-04-30 | 113 |  | 2025-01-14 | 2025-01-20 |  | 2024-12-29 | 2025-01-20 | 23 |  | 2025-01-02 | 2025-01-07 |  | 2025-02-12 | 2025-03-10 | 27 |  | Odhav | 2025-01-08 | 2025-01-14 |  | 2025-02-02 | 2025-03-09 | 36 |  | 2025-01-21 | 2025-01-28 |  | 2025-06-14 | 2025-06-23 | 10 |  | 2025-02-12 | 2025-02-20 |  | 2025-05-17 | 2025-06-21 | 36 |  | 2025-01-30 | 2025-02-04 |  | 2025-06-23 | 2025-06-28 | 6 |  | 2025-02-05 | 2025-02-08 |  | 2025-07-01 | 2025-07-05 | 5 |  | 2025-02-22 | 2025-02-24 |  | 2025-06-18 | 2025-06-18 | 1 |  | 2025-01-11 | 2025-01-18 |  | 2025-02-06 | 2025-03-06 | 29 |  | 2025-01-03 | 2025-01-18 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-02-24 | 2025-02-27 |  | 2025-06-23 | 2025-07-15 | 23 |  | 2025-02-27 | 2025-02-28 |  | 2025-07-17 | 2025-07-18 | 2 |  |  | 2025-03-01
SHREERAM | 134 | PSS-8 | ARE41L | WTG 232 | Precast | F5 | Menard | Done | 537596 | 2673806 | 2024-04-25 | 2024-04-27 |  | 2024-04-25 | 2024-04-27 |  | 199 | 199 | 2024-12-22 | 2024-12-29 |  | 2024-12-26 | 2024-12-30 | 5 | [8 empty] | 2025-01-15 | 2025-01-16 |  | 2024-12-31 | 2025-01-03 | 4 |  | 2025-01-17 | 2025-01-18 |  | 2025-01-05 | 2025-01-06 | 2 |  | 2025-01-19 | 2025-01-19 |  | 2025-01-09 | 2025-01-09 | 1 |  | 2025-01-20 | 2025-01-21 |  | 2025-01-11 | 2025-01-12 | 2 |  | 2025-01-22 | 2025-01-29 |  | 2025-01-15 | 2025-01-31 | 17 |  | 2025-01-30 | 2025-01-31 |  | 2025-02-01 | 2025-02-01 | 1 | 33 |  | 2025-02-02 | 2025-02-09 |  | 2025-02-10 | 2025-08-05 | 177 |  | 2025-02-02 | 2025-02-09 |  | 2025-02-06 | 2025-02-06 | 1 |  |  |  | 2025-01-26 | 2025-02-12 |  | 2025-01-28 | 2025-04-20 | 83 |  | 2025-01-14 | 2025-01-20 |  | 2024-11-18 | 2024-12-31 | 44 |  | 2025-01-03 | 2025-01-08 |  | 2025-03-22 | 2025-04-08 | 18 |  | ODHAV (Reuse) | 2025-01-09 | 2025-01-15 |  | 2025-03-22 | 2025-04-08 | 18 |  | 2025-01-22 | 2025-01-29 |  | 2025-05-15 | 2025-06-13 | 30 |  | 2025-02-14 | 2025-02-22 |  | 2025-05-18 | 2025-06-05 | 19 |  | 2025-01-31 | 2025-02-05 |  | 2025-06-19 | 2025-07-09 | 21 |  | 2025-02-06 | 2025-02-09 |  | 2025-07-10 | 2025-07-13 | 4 |  | 2025-02-24 | 2025-02-26 |  | 2025-07-24 | 2025-07-24 | 1 |  | 2025-01-12 | 2025-01-19 |  | 2025-02-18 | 2025-03-20 | 31 |  | 2025-01-03 | 2025-01-18 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-02-26 | 2025-03-01 |  | 2025-08-05 | 2025-08-24 | 20 |  | 2025-03-01 | 2025-03-02 |  | 2025-08-24 | 2025-08-26 | 3 |  |  | 2025-03-01
DNC | 135 | PSS-8 | ARE41L | WTG 254 | Precast | F5 | Menard | Done | 538436 | 2673502 | 2024-04-25 | 2024-04-27 |  | 2024-04-25 | 2024-04-27 |  | 253 | 253 | 2024-12-24 | 2024-12-31 |  | 2025-01-02 | 2025-01-11 | 10 | [8 empty] | 2025-01-17 | 2025-01-18 |  | 2025-02-02 | 2025-02-03 | 2 |  | 2025-01-19 | 2025-01-20 |  | 2025-02-03 | 2025-02-04 | 2 |  | 2025-01-21 | 2025-01-21 |  | 2025-02-04 | 2025-02-04 | 1 |  | 2025-01-22 | 2025-01-23 |  | 2025-02-05 | 2025-02-05 | 1 |  | 2025-01-24 | 2025-01-31 |  | 2025-02-06 | 2025-02-12 | 7 |  | 2025-02-01 | 2025-02-02 |  | 2025-02-12 | 2025-02-13 | 2 | 12 |  | 2025-02-04 | 2025-02-11 |  | 2025-02-18 | 2025-06-19 | 122 |  | 2025-02-04 | 2025-02-11 |  | 2025-02-17 | 2025-02-17 | 1 |  |  |  | 2025-01-28 | 2025-02-14 |  | 2025-02-06 | 2025-05-07 | 91 |  | 2025-01-15 | 2025-01-21 |  | 2024-12-28 | 2025-01-11 | 15 |  | 2025-01-05 | 2025-01-10 |  | 2025-07-05 | 2025-07-12 | 8 |  | Odhav | 2025-01-11 | 2025-01-17 |  | 2025-01-12 | 2025-01-18 | 7 |  | 2025-01-24 | 2025-01-31 |  | 2025-07-12 | 2025-07-25 | 14 |  | 2025-02-16 | 2025-02-24 |  | 2025-06-05 | 2025-08-01 | 58 |  | 2025-02-02 | 2025-02-07 |  | 2025-07-29 | 2025-08-05 | 8 |  | 2025-02-08 | 2025-02-11 |  | 2025-08-06 | 2025-08-08 | 3 | Delay due to material issue | 2025-02-26 | 2025-02-28 |  | 2025-07-28 | 2025-07-28 | 1 |  | 2025-01-14 | 2025-01-21 |  | 2025-02-04 | 2025-03-22 | 47 |  | 2025-01-03 | 2025-01-18 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-02-28 | 2025-03-03 |  | 2025-08-05 | 2025-08-24 | 20 |  | 2025-03-03 | 2025-03-04 |  | 2025-08-24 | 2025-08-25 | 2 |  |  | 2025-03-01
DNC | 136 | PSS-8 | ARE41L | WTG 209 | Precast | F5 | Bauer | Done | 536572 | 2675057 | 2024-04-25 | 2024-04-30 |  | 2024-04-25 | 2024-04-30 |  | 253 | 253 | 2025-01-01 | 2025-01-08 |  | 2025-02-06 | 2025-02-15 | 10 | [8 empty] | 2025-01-19 | 2025-01-20 |  | 2025-02-19 | 2025-02-21 | 3 |  | 2025-01-21 | 2025-01-22 |  | 2025-02-24 | 2025-02-25 | 2 |  | 2025-01-23 | 2025-01-23 |  | 2025-02-25 | 2025-02-25 | 1 |  | 2025-01-24 | 2025-01-25 |  | 2025-02-26 | 2025-02-26 | 45715 |  | 2025-01-26 | 2025-02-02 |  | 2025-02-27 | 2025-03-03 | 5 |  | 2025-02-03 | 2025-02-04 |  | 2025-03-04 | 2025-03-04 | 1 | 14 |  | 2025-02-06 | 2025-02-13 |  | 2025-03-12 | 2025-06-07 | 88 |  | 2025-02-06 | 2025-02-13 |  | 2025-03-13 | 2025-03-13 | 1 |  |  |  | 2025-01-30 | 2025-02-16 |  | 2025-02-22 | 2025-05-07 | 75 |  | 2025-01-16 | 2025-01-22 |  | Completed | Completed | #VALUE! |  | 2025-01-06 | 2025-01-11 |  | 2025-07-02 | 2025-07-23 | 22 |  | Odhav | 2025-01-12 | 2025-01-18 |  | 2025-03-15 | 2025-04-04 | 21 |  | 2025-01-25 | 2025-02-01 |  | 2025-07-24 | 2025-08-06 | 14 |  | 2025-02-18 | 2025-02-26 |  | 2025-05-28 | 2025-07-25 | 59 |  | 2025-02-03 | 2025-02-08 |  | 2025-08-07 | 2025-08-18 | 12 |  | 2025-02-09 | 2025-02-12 |  | 2025-08-19 | 2025-08-24 | 6 |  | 2025-02-28 | 2025-03-02 |  | 2025-08-07 | 2025-08-07 | 1 |  | 2025-01-15 | 2025-01-22 |  | 2025-02-18 | 2025-02-28 | 11 |  | 2025-02-08 | 2025-02-23 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-03-02 | 2025-03-05 |  | 2025-08-09 | 2025-08-24 | 16 |  | 2025-03-05 | 2025-03-06 |  | 2025-08-25 | 2025-08-26 | 2 |  |  | 2025-03-01
DNC | 137 | PSS-8 | ARE41L | WTG 231 | Precast | F5 | Bauer | Done | 537406 | 2674792 | 2024-04-28 | 2024-05-01 |  | 2024-04-28 | 2024-05-01 |  | 253 | 253 | 2025-01-03 | 2025-01-11 |  | 2025-02-07 | 2025-02-18 | 12 |  | Yes | 2025-01-16 | 2025-01-31 |  | 2025-03-20 | 2025-03-30 |  | 2025-01-21 | 2025-01-22 |  | 2025-04-02 | 2025-04-05 | 4 |  | 2025-01-23 | 2025-01-24 |  | 2025-04-06 | 2025-04-07 | 2 |  | 2025-01-25 | 2025-01-25 |  | 2025-04-07 | 2025-04-07 | 1 |  | 2025-01-26 | 2025-01-27 |  | 2025-04-09 | 2025-04-09 | 1 |  | 2025-01-28 | 2025-02-04 |  | 2025-04-10 | 2025-04-15 | 6 |  | 2025-02-05 | 2025-02-06 |  | 2025-04-15 | 2025-04-16 | 2 | 15 |  | 2025-02-08 | 2025-02-15 |  | 2025-04-23 | 2025-08-02 | 102 |  | 2025-02-08 | 2025-02-15 |  | 2025-04-19 | 2025-04-19 | 1 |  |  |  | 2025-02-01 | 2025-02-18 |  | 2025-04-05 | 2025-04-20 | 16 |  | 2025-01-16 | 2025-01-22 |  | 2025-04-21 | 2025-05-02 | 12 |  | 2025-01-09 | 2025-01-14 |  | 2025-07-01 | 2025-07-25 | 25 |  | Odhav -> GP Project | 2025-01-15 | 2025-01-21 |  | 2025-06-04 | 2025-07-25 | 52 |  | 2025-01-28 | 2025-02-04 |  | 2025-07-31 | 2025-08-16 | 17 |  | 2025-02-20 | 2025-02-28 |  | 2025-05-18 | 2025-05-20 | 3 |  | 2025-02-06 | 2025-02-11 |  | 2025-08-17 | 2025-08-22 | 6 |  | 2025-02-12 | 2025-02-15 |  | 2025-08-23 | 2025-08-25 | 3 |  | 2025-03-02 | 2025-03-04 |  | 2025-07-26 | 2025-07-26 | 1 |  | 2025-01-18 | 2025-01-25 |  | 2025-02-18 | 2025-02-28 | 11 |  | 2025-02-08 | 2025-02-23 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-03-04 | 2025-03-07 |  | 2025-08-17 | 2025-08-24 | 8 |  | 2025-03-07 | 2025-03-08 |  | 2025-08-25 | 2025-08-25 | 1 |  |  | 2025-03-01
MSC | 138 | PSS-8 | ARE41L | WTG 253 | Precast | F5 | Bauer | Done | 538246 | 2674488 | 2024-04-24 | 2024-04-30 |  | 2024-04-24 | 2024-04-30 |  | 253 | 253 | 2025-01-08 | 2025-01-16 |  | 2025-01-21 | 2025-02-05 | 16 | [8 empty] | 2025-01-23 | 2025-01-24 |  | 2025-02-17 | 2025-02-18 | 2 |  | 2025-01-25 | 2025-01-26 |  | 2025-02-18 | 2025-02-18 | 1 |  | 2025-01-27 | 2025-01-27 |  | 2025-02-18 | 2025-02-18 | 1 |  | 2025-01-28 | 2025-01-29 |  | 2025-02-22 | 2025-02-22 | 1 |  | 2025-01-30 | 2025-02-06 |  | 2025-02-23 | 2025-03-06 | 12 |  | 2025-02-07 | 2025-02-08 |  | 2025-03-06 | 2025-03-07 | 2 | 19 |  | 2025-02-10 | 2025-02-17 |  | 2025-03-25 | 2025-08-10 | 139 |  | 2025-02-10 | 2025-02-17 |  | 2025-03-22 | 2025-03-22 | 1 |  |  |  | 2025-02-03 | 2025-02-20 |  | 2025-02-17 | 2025-03-10 | 22 |  | 2025-01-17 | 2025-01-23 |  | 2025-03-01 | 2025-03-20 | 20 |  | 2025-01-11 | 2025-01-16 |  | 2025-04-01 | 2025-04-18 | 18 |  | Odhav (Reuse) | 2025-01-17 | 2025-01-23 |  | 2025-03-20 | 2025-04-12 | 24 |  | 2025-01-30 | 2025-02-06 |  | 2025-07-19 | 2025-08-05 | 18 |  | 2025-02-22 | 2025-03-02 |  | 2025-05-03 | 2025-05-15 | 13 |  | 2025-02-08 | 2025-02-13 |  | 2025-08-05 | 2025-08-16 | 12 |  | 2025-02-14 | 2025-02-17 |  | 2025-08-17 | 2025-08-21 | 5 |  | 2025-03-04 | 2025-03-06 |  | 2025-07-25 | 2025-07-25 | 1 |  | 2025-01-20 | 2025-01-27 |  | 2025-02-05 | 2025-04-04 | 59 |  | 2025-02-08 | 2025-02-23 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-03-06 | 2025-03-09 |  | 2025-08-09 | 2025-08-24 | 16 |  | 2025-03-09 | 2025-03-10 |  | 2025-08-24 | 2025-08-25 | 2 |  |  | 2025-03-01
ODHAV | 139 | PSS-8 | AHEJ5L | WTG 277 | Precast | F6 | Menard | Done | 539080 | 2674223 | 2024-04-24 | 2024-04-30 |  | 2024-04-24 | 2024-04-30 |  | 253 | 253 | 2025-01-06 | 2025-01-15 |  | 2025-01-15 | 2025-01-24 | 10 | [8 empty] | 2025-01-25 | 2025-01-26 |  | 2025-01-29 | 2025-02-04 | 7 |  | 2025-01-27 | 2025-01-28 |  | 2025-02-04 | 2025-02-05 | 2 |  | 2025-01-29 | 2025-01-29 |  | 2025-02-05 | 2025-02-05 | 1 |  | 2025-01-30 | 2025-01-31 |  | 2025-02-07 | 2025-02-07 | 1 |  | 2025-02-01 | 2025-02-08 |  | 2025-02-08 | 2025-02-17 | 10 |  | 2025-02-09 | 2025-02-10 |  | 2025-02-18 | 2025-02-18 | 1 | 21 |  | 2025-02-12 | 2025-02-19 |  | 2025-03-23 | 2025-04-28 | 37 |  | 2025-02-12 | 2025-02-19 |  | 2025-02-28 | 2025-02-28 | 1 |  |  |  | 2025-02-05 | 2025-02-22 |  | 2025-02-08 | 2025-04-20 | 72 |  | 2025-01-17 | 2025-01-23 |  | 2025-01-18 | 2025-02-02 | 16 |  | 2025-01-07 | 2025-01-12 |  | 2025-03-02 | 2025-03-28 | 27 |  | Odhav | 2025-01-13 | 2025-01-19 |  | 2025-02-22 | 2025-03-29 | 36 |  | 2025-01-26 | 2025-02-02 |  | 2025-06-25 | 2025-07-16 | 22 |  | 2025-02-24 | 2025-03-04 |  | 2025-06-14 | 2025-09-05 | 84 |  | 2025-02-04 | 2025-02-09 |  | 2025-07-18 | 2025-07-25 | 8 |  | 2025-02-10 | 2025-02-13 |  | 2025-07-26 | 2025-07-29 | 4 |  | 2025-03-06 | 2025-03-08 |  | 2025-09-06 | 2025-09-06 | 1 |  | 2025-01-16 | 2025-01-23 |  | 2025-02-05 | 2025-05-05 | 90 |  | 2025-02-08 | 2025-02-23 |  | 2025-05-31 | 2025-06-28 | 29 |  | 2025-03-08 | 2025-03-11 |  | 2025-09-19 | 2025-09-20 | 2 |  | 2025-03-11 | 2025-03-12 |  | 2025-09-26 | 2025-09-30 | 5 |  |  | 2025-03-01
DNC | 140 | PSS-4 | ACL | WTG 119 | Precast | F2 | Bauer | Done | 533158 | 2676590 | 2024-05-01 | 2024-05-16 |  | 2024-05-01 | 2024-05-16 |  | 253 | 253 | 2024-09-27 | 2024-10-06 |  | 2025-01-24 | 2025-02-01 | 9 |  | Yes | 2024-10-15 | 2024-10-30 |  | 2025-02-05 | 2025-02-23 |  | 2024-10-22 | 2024-10-22 |  | 2025-03-08 | 2025-03-09 | 2 |  | 2024-10-23 | 2024-10-23 |  | 2025-03-10 | 2025-03-11 | 2 |  | 2024-10-24 | 2024-10-24 |  | 2025-03-11 | 2025-03-11 | 1 |  | 2024-10-25 | 2024-10-26 |  | 2025-03-12 | 2025-03-13 | 2 |  | 2024-10-28 | 2024-11-06 |  | 2025-03-13 | 2025-03-21 | 9 |  | 2024-11-08 | 2024-11-09 |  | 2025-03-22 | 2025-03-23 | 2 | 16 |  | 2024-11-10 | 2024-11-16 |  | 2025-04-01 | 2025-06-07 | 68 |  | 2024-11-10 | 2024-11-16 |  | 2025-03-28 | 2025-03-28 | 1 |  |  |  | 2024-11-04 | 2024-11-18 |  | 2025-03-17 | 2025-03-20 | 4 |  | 2024-11-05 | 2024-11-11 |  | 2025-02-05 | 2025-02-28 | 24 |  | 2024-11-05 | 2024-11-11 |  | 2025-04-01 | 2025-04-12 | 12 |  | Varudi (Reuse) | 2024-11-12 | 2024-11-18 |  | 2025-03-08 | 2025-04-10 | 34 |  | 2024-12-09 | 2024-12-14 |  | 2025-04-25 | 2025-05-23 | 29 |  | 2024-12-05 | 2024-12-11 |  | 2025-03-29 | 2025-04-02 | 5 |  | 2024-12-17 | 2024-12-26 |  | 2025-06-01 | 2025-06-04 | 4 |  | 2024-12-28 | 2024-12-30 |  | 2025-06-05 | 2025-06-08 | 4 |  | 2024-12-17 | 2024-12-18 |  | 2025-04-03 | 2025-04-03 | 1 |  | 2024-11-28 | 2024-12-04 |  | 2025-01-23 | 2025-02-05 | 14 |  | 2024-11-20 | 2024-12-05 |  | 2025-02-26 | 2025-03-17 | 20 |  | 2024-12-18 | 2024-12-21 |  | 2025-05-26 | 2025-06-08 | 14 |  | 2024-12-30 | 2024-12-31 |  | 2025-06-26 | 2025-06-26 | 1 |  |  | 2025-03-01
AB INFRA | 141 | PSS-8 | AHEJ5L | WTG 252 | Precast | F7 | Bauer | Done | 538179 | 2675639 | 2024-04-24 | 2024-04-30 |  | 2024-04-24 | 2024-04-30 |  | 253 | 253 | 2025-01-09 | 2025-01-17 |  | 2025-02-12 | 2025-02-20 | 9 |  | Yes | 2025-01-18 | 2025-02-01 |  | 2025-03-02 | 2025-03-18 |  | 2025-01-27 | 2025-01-28 |  | 2025-03-25 | 2025-03-27 | 3 |  | 2025-01-29 | 2025-01-30 |  | 2025-03-27 | 2025-03-28 | 2 |  | 2025-01-31 | 2025-01-31 |  | 2025-03-29 | 2025-03-29 | 1 |  | 2025-02-01 | 2025-02-02 |  | 2025-04-03 | 2025-04-04 | 2 |  | 2025-02-03 | 2025-02-10 |  | 2025-04-05 | 2025-04-13 | 9 |  | 2025-02-11 | 2025-02-12 |  | 2025-04-14 | 2025-04-15 | 2 | 22 |  | 2025-02-14 | 2025-02-21 |  | 2025-04-21 | 2025-05-13 | 23 |  | 2025-02-14 | 2025-02-21 |  | 2025-04-21 | 2025-04-21 | 1 |  |  |  | 2025-02-07 | 2025-02-24 |  | 2025-03-25 | 2025-04-20 | 27 |  | 2025-01-18 | 2025-01-24 |  | 2025-05-01 | 2025-05-17 | 17 |  | 2025-01-07 | 2025-01-12 |  | 2025-06-21 | 2025-08-05 | 46 |  | SS Jadeja-> GP Project | 2025-01-13 | 2025-01-19 |  | 2025-06-21 | 2025-08-05 | 46 |  | 2025-01-26 | 2025-02-02 |  | 2025-08-09 | 2025-08-28 | 20 |  | 2025-02-26 | 2025-03-06 |  | 2025-05-26 | 2025-08-09 | 76 |  | 2025-02-04 | 2025-02-09 |  | 2025-08-30 | 2025-09-07 | 9 |  | 2025-02-10 | 2025-02-13 |  | 2025-09-08 | 2025-09-15 | 8 |  | 2025-03-08 | 2025-03-10 |  | 2025-08-09 | 2025-08-09 | 1 |  | 2025-01-16 | 2025-01-23 |  | 2025-04-01 | 2025-04-16 | 16 |  | 2025-02-08 | 2025-02-23 |  | 2025-05-31 | 2025-06-28 | 29 |  | 2025-03-10 | 2025-03-13 |  | 2025-09-02 | 2025-09-20 | 19 |  | 2025-03-13 | 2025-03-14 |  | 2025-09-26 | 2025-09-30 | 5 |  |  | 2025-03-01
MECC | 142 | PSS-8 | AHEJ5L | WTG 276 | Precast | F7 | Bauer | Done | 538890 | 2675209 | 2024-04-18 | 2024-04-28 |  | 2024-04-18 | 2024-04-28 |  | 253 | 253 | 2025-01-13 | 2025-01-19 |  | 2025-02-21 | 2025-03-04 | 12 | [8 empty] | 2025-01-29 | 2025-01-30 |  | 2025-03-07 | 2025-03-09 | 3 |  | 2025-01-31 | 2025-02-01 |  | 2025-03-09 | 2025-03-10 | 2 |  | 2025-02-02 | 2025-02-02 |  | 2025-03-10 | 2025-03-10 | 1 |  | 2025-02-03 | 2025-02-04 |  | 2025-03-11 | 2025-03-12 | 2 |  | 2025-02-05 | 2025-02-12 |  | 2025-03-15 | 2025-03-26 | 12 |  | 2025-02-13 | 2025-02-14 |  | 2025-03-29 | 2025-03-30 | 2 | 24 |  | 2025-02-16 | 2025-02-23 |  | 2025-04-09 | 2025-05-18 | 40 |  | 2025-02-16 | 2025-02-23 |  | 2025-04-11 | 2025-04-11 | 1 |  |  |  | 2025-02-09 | 2025-02-26 |  | 2025-04-13 | 2025-04-24 | 12 |  | 2025-01-18 | 2025-01-24 |  | 2025-05-01 | 2025-05-17 | 17 |  | 2025-01-07 | 2025-01-12 |  | 2025-05-20 | 2025-06-10 | 22 |  | Adani (Self Resue) | 2025-01-13 | 2025-01-19 |  | 2025-05-20 | 2025-06-02 | 14 |  | 2025-01-26 | 2025-02-02 |  | 2025-08-26 | 2025-09-06 | 12 |  | 2025-02-28 | 2025-03-08 |  | 2025-06-04 | 2025-09-03 | 92 |  | 2025-02-04 | 2025-02-09 |  | 2025-09-08 | 2025-09-30 | 23 |  | 2025-02-10 | 2025-02-13 |  | 2025-10-01 | 2025-10-03 | 3 |  | 2025-03-10 | 2025-03-12 |  | 2025-09-03 | 2025-09-03 | 1 |  | 2025-01-16 | 2025-01-23 |  | 2025-04-01 | 2025-04-16 | 16 |  | 2025-02-08 | 2025-02-23 |  | 2025-05-31 | 2025-06-28 | 29 |  | 2025-03-12 | 2025-03-15 |  | 2025-10-29 | 2025-11-01 | 4 |  | 2025-03-15 | 2025-03-16 |  | 2025-11-04 | 2025-11-10 | 7 |  |  | 2025-03-01
SHREEJI | 143 | PSS-8 | AHEJ5L | WTG 300 | Precast | F6 | Menard/Bauer | Done | 539731 | 2674905 | 2024-04-18 | 2024-04-28 |  | 2024-04-18 | 2024-04-28 |  | 223 | 223 | 2025-01-13 | 2025-01-19 |  | 2025-01-25 | 2025-03-28 | 63 | [8 empty] | 2025-01-31 | 2025-02-01 |  | 2025-03-30 | 2025-03-31 | 2 |  | 2025-02-02 | 2025-02-03 |  | 2025-04-01 | 2025-04-02 | 2 |  | 2025-02-04 | 2025-02-04 |  | 2025-04-02 | 2025-04-02 | 1 |  | 2025-02-05 | 2025-02-06 |  | 2025-04-03 | 2025-04-03 | 1 |  | 2025-02-07 | 2025-02-14 |  | 2025-04-03 | 2025-04-09 | 7 |  | 2025-02-15 | 2025-02-16 |  | 2025-04-10 | 2025-04-11 | 2 | 13 |  | 2025-02-18 | 2025-02-25 |  | 2025-04-14 | 2025-09-10 | 150 |  | 2025-02-18 | 2025-02-25 |  | 2025-04-16 | 2025-04-16 | 1 |  |  |  | 2025-02-11 | 2025-02-28 |  | 2025-03-31 | 2025-05-14 | 45 |  | 2025-01-19 | 2025-01-25 |  | 2025-05-15 | 2025-06-30 | 47 |  | 2025-01-08 | 2025-01-13 |  | 2025-07-12 | 2025-07-31 | 20 |  | Adani (Self Resue) | 2025-01-14 | 2025-01-20 |  | 2025-06-02 | 2025-07-31 | 60 |  | 2025-01-27 | 2025-02-03 |  | 2025-08-03 | 2025-08-20 | 18 |  | 2025-03-02 | 2025-03-10 |  | 2025-06-14 | 2025-09-10 | 89 |  | 2025-02-05 | 2025-02-10 |  | 2025-08-22 | 2025-08-31 | 10 |  | 2025-02-11 | 2025-02-14 |  | 2025-09-01 | 2025-09-02 | 2 |  | 2025-03-12 | 2025-03-14 |  | 2025-09-10 | 2025-09-10 | 1 |  | 2025-01-17 | 2025-01-24 |  | 2025-02-07 | 2025-03-25 | 47 |  | 2025-02-08 | 2025-02-23 |  | 2025-05-31 | 2025-06-28 | 29 |  | 2025-03-14 | 2025-03-17 |  | 2025-09-19 | 2025-09-20 | 2 |  | 2025-03-17 | 2025-03-18 |  | 2025-09-26 | 2025-09-30 | 5 |  |  | 2025-03-01
DNC | 144 | PSS-8 | AHEJ5L | WTG 325 | Precast | F6 | Menard | Done | 540564 | 2674640 | 2024-04-21 | 2024-04-28 |  | 2024-04-21 | 2024-04-28 |  | 223 | 223 | 2025-01-12 | 2025-01-20 |  | 2025-01-27 | 2025-02-11 | 16 | [8 empty] | 2025-02-02 | 2025-02-03 |  | 2025-02-14 | 2025-02-15 | 2 |  | 2025-02-04 | 2025-02-05 |  | 2025-02-15 | 2025-02-16 | 2 |  | 2025-02-06 | 2025-02-06 |  | 2025-02-16 | 2025-02-16 | 1 |  | 2025-02-07 | 2025-02-08 |  | 2025-02-18 | 2025-02-18 | 1 |  | 2025-02-09 | 2025-02-16 |  | 2025-02-18 | 2025-02-22 | 5 |  | 2025-02-17 | 2025-02-18 |  | 2025-02-22 | 2025-02-23 | 2 | 10 |  | 2025-02-20 | 2025-02-27 |  | 2025-03-20 | 2025-07-17 | 120 |  | 2025-02-20 | 2025-02-27 |  | 2025-02-27 | 2025-02-27 | 1 |  |  |  | 2025-02-13 | 2025-03-02 |  | 2025-02-23 | 2025-05-05 | 72 |  | 2025-01-19 | 2025-01-25 |  | 2025-03-20 | 2025-04-07 | 19 |  | 2025-01-08 | 2025-01-13 |  | 2025-04-11 | 2025-04-29 | 19 |  | HARSH (Reuse) | 2025-01-14 | 2025-01-20 |  | 2025-04-11 | 2025-04-29 | 19 |  | 2025-01-27 | 2025-02-03 |  | 2025-07-22 | 2025-08-07 | 17 |  | 2025-03-04 | 2025-03-12 |  | 2025-05-31 | 2025-06-18 | 19 |  | 2025-02-05 | 2025-02-10 |  | 2025-08-10 | 2025-08-20 | 11 |  | 2025-02-11 | 2025-02-14 |  | 2025-08-21 | 2025-08-31 | 11 |  | 2025-03-14 | 2025-03-16 |  | 2025-06-13 | 2025-06-13 | 1 |  | 2025-01-17 | 2025-01-24 |  | 2025-02-06 | 2025-03-28 | 51 |  | 2025-02-08 | 2025-02-23 |  | 2025-05-31 | 2025-06-28 | 29 |  | 2025-03-16 | 2025-03-19 |  | 2025-09-02 | 2025-09-20 | 19 |  | 2025-03-19 | 2025-03-20 |  | 2025-09-26 | 2025-09-30 | 5 |  |  | 2025-03-01
HBG | 145 | PSS-8 | AHEJ5L | WTG 350 | Precast | F8 | Bauer | Done | 541405 | 2674336 | 2024-04-19 | 2024-04-28 |  | 2024-04-19 | 2024-04-28 |  | 253 | 253 | 2025-01-16 | 2025-01-23 |  | 2025-02-22 | 2025-03-02 | 9 | [8 empty] | 2025-02-03 | 2025-02-04 |  | 2025-03-06 | 2025-03-10 | 5 |  | 2025-02-05 | 2025-02-06 |  | 2025-03-10 | 2025-03-11 | 2 |  | 2025-02-07 | 2025-02-07 |  | 2025-03-12 | 2025-03-12 | 1 |  | 2025-02-08 | 2025-02-09 |  | 2025-03-15 | 2025-03-15 | 1 |  | 2025-02-10 | 2025-02-17 |  | 2025-03-16 | 2025-03-23 | 8 |  | 2025-02-18 | 2025-02-19 |  | 2025-03-23 | 2025-03-24 | 2 | 19 |  | 2025-02-21 | 2025-02-28 |  | 2025-03-29 | 2025-07-16 | 110 |  | 2025-02-21 | 2025-02-28 |  | 2025-03-30 | 2025-03-30 | 1 |  |  |  | 2025-02-14 | 2025-03-03 |  | 2025-03-31 | 2025-05-05 | 36 |  | 2025-01-20 | 2025-01-26 |  | 2025-05-02 | 2025-05-16 | 15 |  | 2025-01-09 | 2025-01-14 |  | 2025-05-20 | 2025-06-20 | 32 |  | GP | 2025-01-15 | 2025-01-21 |  | 2025-05-18 | 2025-06-20 | 34 |  | 2025-01-28 | 2025-02-04 |  | 2025-07-29 | 2025-08-15 | 18 |  | 2025-03-05 | 2025-03-13 |  | 2025-08-11 | 2025-10-03 | 54 |  | 2025-02-06 | 2025-02-11 |  | 2025-08-19 | 2025-08-28 | 10 |  | 2025-02-12 | 2025-02-15 |  | 2025-08-29 | 2025-08-31 | 3 |  | 2025-03-15 | 2025-03-17 |  | 2025-09-03 | 2025-09-03 | 1 |  | 2025-01-18 | 2025-01-25 |  | 2025-02-16 | 2025-04-25 | 69 |  | 2025-02-08 | 2025-02-23 |  | 2025-05-31 | 2025-06-28 | 29 |  | 2025-03-17 | 2025-03-20 |  | 2025-10-05 | 2025-10-06 | 2 |  | 2025-03-20 | 2025-03-21 |  | 2025-10-31 | 2025-11-07 | 8 |  |  | 2025-03-01
SVRE | 146 | PSS-8 | AHEJ5L | WTG 375 | Precast | F8 | Sarita infra/Keller | Done | 542239 | 2674071 | 2024-04-20 | 2024-04-28 |  | 2024-04-20 | 2024-04-28 |  | 369 | 369 | 2025-01-17 | 2025-01-25 |  | 2025-01-31 | 2025-03-05 | 34 |  | Yes | 2025-01-27 | 2025-02-10 |  | 2025-03-25 | 2025-04-25 |  | 2025-02-04 | 2025-02-05 |  | 2025-06-22 | 2025-06-26 | 5 |  | 2025-02-06 | 2025-02-07 |  | 2025-07-14 | 2025-07-14 | 1 | Delay due to slush removing work | 2025-02-08 | 2025-02-08 |  | 2025-07-16 | 2025-07-16 | 1 |  | 2025-02-09 | 2025-02-10 |  | 2025-07-17 | 2025-07-17 | 1 |  | 2025-02-11 | 2025-02-18 |  | 2025-07-18 | 2025-08-02 | 16 |  | 2025-02-19 | 2025-02-20 |  | 2025-08-03 | 2025-08-04 | 2 | 44 |  | 2025-02-22 | 2025-03-01 |  | 2025-08-07 | 2025-08-18 | 12 |  | 2025-02-22 | 2025-03-01 |  | 2025-08-09 | 2025-08-09 | 1 |  |  |  | 2025-02-15 | 2025-03-04 |  | 2025-05-30 | 2025-06-02 | 4 |  | 2025-01-21 | 2025-01-27 |  | 2025-05-02 | 2025-07-31 | 91 |  | 2025-01-10 | 2025-01-15 |  | 2025-07-03 | 2025-08-02 | 31 |  | Odhav | 2025-01-16 | 2025-01-22 |  | 2025-07-03 | 2025-08-02 | 31 |  | 2025-01-29 | 2025-02-05 |  | 2025-08-16 | 2025-09-03 | 19 |  | 2025-03-06 | 2025-03-14 |  | 2025-06-07 | 2025-10-03 | 119 |  | 2025-02-07 | 2025-02-12 |  | 2025-09-04 | 2025-09-15 | 12 |  | 2025-02-13 | 2025-02-16 |  | 2025-09-16 | 2025-09-17 | 2 |  | 2025-03-16 | 2025-03-18 |  | 2025-09-13 | 2025-09-13 | 1 |  | 2025-01-19 | 2025-01-26 |  | 2025-02-07 | 2025-04-27 | 80 |  | 2025-02-08 | 2025-02-23 |  | 2025-05-31 | 2025-06-28 | 29 |  | 2025-03-18 | 2025-03-21 |  | 2025-10-05 | 2025-10-06 | 2 |  | 2025-03-21 | 2025-03-22 |  | 2025-11-01 | 2025-11-07 | 7 |  |  | 2025-03-01
ODHAV | 147 | PSS-8 | AHEJ5L | WTG 299 | Precast | F7 | Bauer | Done | 539541 | 2675891 | 2024-04-23 | 2024-04-30 |  | 2024-04-23 | 2024-04-30 |  | 253 | 253 | 2025-01-18 | 2025-01-25 |  | 2025-03-13 | 2025-03-27 | 15 | [8 empty] | 2025-02-05 | 2025-02-06 |  | 2025-03-30 | 2025-04-03 | 5 |  | 2025-02-07 | 2025-02-08 |  | 2025-04-04 | 2025-04-05 | 2 |  | 2025-02-09 | 2025-02-09 |  | 2025-04-06 | 2025-04-06 | 1 |  | 2025-02-10 | 2025-02-11 |  | 2025-04-07 | 2025-04-09 | 3 |  | 2025-02-12 | 2025-02-19 |  | 2025-04-09 | 2025-04-17 | 9 |  | 2025-02-20 | 2025-02-21 |  | 2025-04-18 | 2025-04-19 | 2 | 21 |  | 2025-02-23 | 2025-03-02 |  | 2025-04-24 | 2025-07-02 | 70 |  | 2025-02-23 | 2025-03-02 |  | 2025-04-23 | 2025-04-23 | 1 |  |  |  | 2025-02-16 | 2025-03-05 |  | 2025-04-20 | 2025-05-05 | 16 |  | 2025-01-21 | 2025-01-27 |  | 2025-04-29 | 2025-08-02 | 96 |  | 2025-01-11 | 2025-01-16 |  | 2025-08-04 | 2025-08-12 | 9 |  | Kesav-> GP Project | 2025-01-17 | 2025-01-23 |  | 2025-08-04 | 2025-08-12 | 9 |  | 2025-01-30 | 2025-02-06 |  | 2025-08-13 | 2025-09-02 | 21 |  | 2025-03-07 | 2025-03-15 |  | 2025-05-31 | 2025-06-14 | 15 |  | 2025-02-08 | 2025-02-13 |  | 2025-09-02 | 2025-09-13 | 12 |  | 2025-02-14 | 2025-02-17 |  | 2025-09-13 | 2025-09-15 | 3 |  | 2025-03-17 | 2025-03-19 |  | 2025-06-16 | 2025-06-16 | 1 |  | 2025-01-20 | 2025-01-27 |  | 2025-04-03 | 2025-04-28 | 26 |  | 2025-02-08 | 2025-02-23 |  | 2025-05-31 | 2025-06-28 | 29 |  | 2025-03-19 | 2025-03-22 |  | 2025-09-19 | 2025-09-21 | 3 |  | 2025-03-22 | 2025-03-23 |  | 2025-09-26 | 2025-09-30 | 5 |  |  | 2025-03-01
C & B | 148 | PSS-8 | AHEJ5L | WTG 324 | Precast | F7 | Menard | Done | 540374 | 2675627 | 2024-04-22 | 2024-04-30 |  | 2024-04-22 | 2024-04-30 |  | 253 | 253 | 2024-12-24 | 2025-01-02 |  | 2025-02-27 | 2025-03-08 | 10 | [8 empty] | 2025-01-12 | 2025-01-13 |  | 2025-03-15 | 2025-03-20 | 6 |  | 2025-01-14 | 2025-01-15 |  | 2025-03-21 | 2025-03-21 | 1 |  | 2025-01-16 | 2025-01-16 |  | 2025-03-22 | 2025-03-22 | 1 |  | 2025-01-17 | 2025-01-18 |  | 2025-03-26 | 2025-03-27 | 2 |  | 2025-01-19 | 2025-01-26 |  | 2025-03-27 | 2025-04-07 | 12 |  | 2025-01-27 | 2025-01-28 |  | 2025-04-07 | 2025-04-08 | 2 | 25 |  | 2025-01-30 | 2025-02-06 |  | 2025-04-11 | 2025-06-13 | 64 |  | 2025-01-30 | 2025-02-06 |  | 2025-04-11 | 2025-04-11 | 1 |  |  |  | 2025-01-23 | 2025-02-09 |  | 2025-03-25 | 2025-04-10 | 17 |  | 2025-01-22 | 2025-01-28 |  | 2025-04-23 | 2025-05-07 | 15 |  | 2025-01-12 | 2025-01-17 |  | 2025-05-07 | 2025-05-21 | 15 |  | HARSH (Reuse) | 2025-01-18 | 2025-01-24 |  | 2025-05-07 | 2025-05-21 | 15 |  | 2025-01-31 | 2025-02-07 |  | 2025-07-06 | 2025-08-01 | 27 |  | 2025-02-11 | 2025-02-19 |  | 2025-05-31 | 2025-09-10 | 103 |  | 2025-02-09 | 2025-02-14 |  | 2025-08-08 | 2025-08-13 | 6 |  | 2025-02-15 | 2025-02-18 |  | 2025-08-14 | 2025-08-17 | 4 |  | 2025-02-21 | 2025-02-23 |  | 2025-06-13 | 2025-06-13 | 1 |  | 2025-01-21 | 2025-01-28 |  | 2025-04-05 | 2025-04-16 | 12 |  | 2025-02-08 | 2025-02-23 |  | 2025-05-31 | 2025-06-28 | 29 |  | 2025-02-23 | 2025-02-26 |  | 2025-09-02 | 2025-09-03 | 2 |  | 2025-02-26 | 2025-02-27 |  | 2025-11-04 | 2025-11-10 | 7 |  |  | 2025-03-01
MECC | 149 | PSS-8 | AHEJ5L | WTG 349 | Precast | F7 | Menard | Done | 541215 | 2675322 | 2024-04-21 | 2024-04-28 |  | 2024-04-21 | 2024-04-28 |  | 253 | 253 | 2024-12-28 | 2025-01-06 |  | 2025-02-06 | 2025-02-25 | 20 |  | Yes | 2025-01-08 | 2025-01-22 |  | 2025-03-09 | 2025-03-23 |  | 2025-01-16 | 2025-01-17 |  | 2025-03-28 | 2025-03-29 | 2 |  | 2025-01-18 | 2025-01-19 |  | 2025-03-30 | 2025-03-30 | 1 |  | 2025-01-20 | 2025-01-20 |  | 2025-03-31 | 2025-03-31 | 1 |  | 2025-01-21 | 2025-01-22 |  | 2025-04-01 | 2025-04-03 | 3 |  | 2025-01-23 | 2025-01-30 |  | 2025-04-03 | 2025-04-14 | 12 |  | 2025-01-31 | 2025-02-01 |  | 2025-04-15 | 2025-04-16 | 2 | 20 |  | 2025-02-03 | 2025-02-10 |  | 2025-04-27 | 2025-05-25 | 29 |  | 2025-02-03 | 2025-02-10 |  | 2025-04-20 | 2025-04-20 | 1 |  |  |  | 2025-01-27 | 2025-02-13 |  | 2025-04-17 | 2025-05-31 | 45 |  | 2025-01-23 | 2025-01-29 |  | 2025-04-22 | 2025-07-28 | 98 |  | 2025-01-14 | 2025-01-19 |  | 2025-08-02 | 2025-08-16 | 15 |  | Kesav-> GP Project | 2025-01-20 | 2025-01-26 |  | 2025-08-02 | 2025-08-16 | 15 |  | 2025-02-02 | 2025-02-09 |  | 2025-08-17 | 2025-09-10 | 25 |  | 2025-02-15 | 2025-02-23 |  | 2025-05-28 | 2025-08-06 | 71 |  | 2025-02-11 | 2025-02-16 |  | 2025-09-07 | 2025-09-19 | 13 |  | 2025-02-17 | 2025-02-20 |  | 2025-09-20 | 2025-09-22 | 3 |  | 2025-02-25 | 2025-02-27 |  | 2025-09-13 | 2025-09-13 | 1 |  | 2025-01-23 | 2025-01-30 |  | 2025-04-07 | 2025-04-30 | 24 |  | 2025-02-08 | 2025-02-23 |  | 2025-05-31 | 2025-06-28 | 29 |  | 2025-02-27 | 2025-03-02 |  | 2025-09-02 | 2025-09-04 | 3 |  | 2025-03-02 | 2025-03-03 |  | 2025-11-04 | 2025-11-10 | 7 |  |  | 2025-03-01
DNC | 150 | PSS-8 | AHEJ5L | WTG 374 | Precast | F8 | Bauer | Done | 542049 | 2675057 | 2024-04-21 | 2024-04-28 |  | 2024-04-21 | 2024-04-28 |  | 253 | 253 | 2025-01-02 | 2025-01-10 |  | 2025-03-03 | 2025-03-12 | 10 | [8 empty] | 2025-01-20 | 2025-01-21 |  | 2025-03-22 | 2025-03-24 | 3 |  | 2025-01-22 | 2025-01-23 |  | 2025-03-25 | 2025-03-26 | 2 |  | 2025-01-24 | 2025-01-24 |  | 2025-03-27 | 2025-03-27 | 1 |  | 2025-01-25 | 2025-01-26 |  | 2025-04-04 | 2025-04-04 | 1 | Delay due to crane problem | 2025-01-27 | 2025-02-03 |  | 2025-04-04 | 2025-04-12 | 9 |  | 2025-02-04 | 2025-02-05 |  | 2025-04-12 | 2025-04-13 | 2 | 23 |  | 2025-02-07 | 2025-02-14 |  | 2025-04-27 | 2025-10-29 | 186 |  | 2025-02-07 | 2025-02-14 |  | 2025-04-18 | 2025-04-18 | 1 |  |  |  | 2025-01-31 | 2025-02-17 |  | 2025-03-26 | 2025-05-29 | 65 |  | 2025-01-23 | 2025-01-29 |  | 2025-05-05 | 2025-07-30 | 87 |  | 2025-01-17 | 2025-01-22 |  | 2025-08-02 | 2025-08-20 | 19 |  | SS Jadeja | 2025-01-23 | 2025-01-29 |  | 2025-06-03 | 2025-08-31 | 90 |  | 2025-02-05 | 2025-02-12 |  | 2025-09-03 | 2025-09-25 | 23 |  | 2025-02-19 | 2025-02-27 |  | 2025-09-01 | 2025-10-03 | 33 |  | 2025-02-14 | 2025-02-19 |  | 2025-09-26 | 2025-10-10 | 15 |  | 2025-02-20 | 2025-02-23 |  | 2025-10-11 | 2025-10-12 | 2 |  | 2025-03-01 | 2025-03-03 |  | 2025-09-08 | 2025-09-08 | 1 |  | 2025-01-26 | 2025-02-02 |  | 2025-02-08 | 2025-04-24 | 76 |  | 2025-02-08 | 2025-02-23 |  | 2025-05-31 | 2025-06-28 | 29 |  | 2025-03-03 | 2025-03-06 |  | 2025-10-05 | 2025-10-06 | 2 |  | 2025-03-06 | 2025-03-07 |  | 2025-10-31 | 2025-11-07 | 8 |  |  | 2025-03-01
SHREEJI | 151 | PSS-10 | AGE26BL | WTG 362 | Precast | F6 | Kamar | Done | 543687 | 2662501 | 2024-05-11 | 2024-05-17 |  | 2024-05-11 | 2024-05-17 |  | 253 | 253 | 2025-01-06 | 2025-01-14 |  | 2025-01-07 | 2025-01-24 | 18 | [8 empty] | 2025-01-24 | 2025-01-25 |  | 2025-02-07 | 2025-02-12 | 6 |  | 2025-01-26 | 2025-01-27 |  | 2025-02-13 | 2025-02-15 | 3 |  | 2025-01-28 | 2025-01-28 |  | 2025-02-15 | 2025-02-15 | 1 |  | 2025-01-29 | 2025-01-30 |  | 2025-02-17 | 2025-02-17 | 1 |  | 2025-01-31 | 2025-02-07 |  | 2025-02-18 | 2025-02-24 | 7 |  | 2025-02-08 | 2025-02-09 |  | 2025-02-25 | 2025-02-25 | 1 | 19 |  | 2025-02-11 | 2025-02-18 |  | 2025-03-06 | 2025-04-19 | 45 |  | 2025-02-11 | 2025-02-18 |  | 2025-03-02 | 2025-03-02 | 1 |  |  |  | 2025-02-04 | 2025-02-21 |  | 2025-02-17 | 2025-03-01 | 13 |  | 2024-12-07 | 2024-12-13 |  | 2025-03-10 | 2025-03-18 | 9 |  | 2025-01-06 | 2025-01-11 |  | 2025-03-25 | 2025-04-02 | 9 |  | GP (Reuse) | 2025-01-12 | 2025-01-18 |  | 2025-03-16 | 2025-03-25 | 10 |  | 2025-01-25 | 2025-02-02 |  | 2025-04-03 | 2025-04-21 | 19 |  | 2025-02-23 | 2025-03-03 |  | 2025-04-02 | 2025-04-11 | 10 |  | 2025-02-04 | 2025-02-09 |  | 2025-04-26 | 2025-05-05 | 10 |  | 2025-02-10 | 2025-02-13 |  | 2025-05-06 | 2025-05-08 | 3 |  | 2025-03-05 | 2025-03-07 |  | 2025-04-12 | 2025-04-12 | 1 |  | 2025-01-15 | 2025-01-22 |  | 2025-01-17 | 2025-04-22 | 96 |  | 2025-02-08 | 2025-02-23 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-03-07 | 2025-03-10 |  | 2025-05-01 | 2025-05-06 | 6 |  | 2025-03-10 | 2025-03-11 |  | 2025-06-06 | 2025-06-07 | 2 |  |  | 2025-03-01
SHREEJI | 152 | PSS-10 | AGE26BL | WTG 387 | Precast | F6 | Kamar | Done | 544521 | 2662236 | 2024-06-02 | 2024-06-09 |  | 2024-06-02 | 2024-06-09 |  | 253 | 253 | 2025-01-10 | 2025-01-18 |  | 2025-01-06 | 2025-01-23 | 18 | [8 empty] | 2025-01-28 | 2025-01-29 |  | 2025-01-26 | 2025-01-29 | 4 |  | 2025-01-30 | 2025-01-31 |  | 2025-01-29 | 2025-01-31 | 3 |  | 2025-02-01 | 2025-02-01 |  | 2025-01-31 | 2025-02-01 | 2 |  | 2025-02-02 | 2025-02-03 |  | 2025-02-03 | 2025-02-04 | 2 |  | 2025-02-04 | 2025-02-11 |  | 2025-02-04 | 2025-02-10 | 7 |  | 2025-02-12 | 2025-02-13 |  | 2025-02-10 | 2025-02-11 | 2 | 17 |  | 2025-02-15 | 2025-02-22 |  | 2025-02-28 | 2025-05-04 | 66 |  | 2025-02-15 | 2025-02-22 |  | 2025-02-25 | 2025-02-25 | 1 |  |  |  | 2025-02-08 | 2025-02-25 |  | 2025-01-27 | 2025-03-03 | 36 |  | 2024-12-09 | 2024-12-15 |  | 2025-02-12 | 2025-02-25 | 14 |  | 2025-01-07 | 2025-01-12 |  | 2025-02-20 | 2025-03-03 | 12 |  | GP | 2025-01-13 | 2025-01-19 |  | 2025-02-18 | 2025-03-03 | 14 |  | 2025-01-26 | 2025-02-03 |  | 2025-03-19 | 2025-04-01 | 14 |  | 2025-02-27 | 2025-03-07 |  | 2025-04-02 | 2025-04-15 | 14 |  | 2025-02-05 | 2025-02-10 |  | 2025-04-04 | 2025-04-18 | 15 |  | 2025-02-11 | 2025-02-14 |  | 2025-04-18 | 2025-04-19 | 2 |  | 2025-03-09 | 2025-03-11 |  | 2025-04-17 | 2025-04-17 | 1 |  | 2025-01-16 | 2025-01-23 |  | 2025-02-21 | 2025-04-22 | 61 |  | 2025-02-08 | 2025-02-23 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-03-11 | 2025-03-14 |  | 2025-05-01 | 2025-05-06 | 6 |  | 2025-03-14 | 2025-03-15 |  | 2025-06-06 | 2025-06-10 | 5 | Delay due to feeder trip |  | 2025-03-01
MSC | 153 | PSS-10 | AGE26BL | WTG 412 | Precast | F6 | Keller | Done | 545363 | 2661932 | 2024-05-12 | 2024-05-17 |  | 2024-05-12 | 2024-05-17 |  | 199 | 199 | 2024-10-11 | 2024-10-18 |  | 2024-12-23 | 2024-12-29 | 7 | [8 empty] | 2024-10-28 | 2024-10-29 |  | 2025-01-07 | 2025-01-08 | 2 |  | 2024-10-30 | 2024-10-31 |  | 2025-01-09 | 2025-01-09 | 1 |  | 2024-11-01 | 2024-11-01 |  | 2025-01-09 | 2025-01-09 | 1 |  | 2024-11-02 | 2024-11-03 |  | 2025-01-15 | 2025-01-16 | 2 |  | 2024-11-04 | 2024-11-11 |  | 2025-01-20 | 2025-01-23 | 4 |  | 2024-11-12 | 2024-11-13 |  | 2025-01-24 | 2025-01-24 | 1 | 18 |  | 2024-11-15 | 2024-11-22 |  | 2025-02-02 | 2025-06-18 | 137 |  | 2024-11-15 | 2024-11-22 |  | 2025-02-25 | 2025-02-25 | 1 |  |  |  | 2024-11-08 | 2024-11-25 |  | 2025-01-07 | 2025-02-09 | 34 |  | 2024-12-14 | 2024-12-20 |  | 2025-01-29 | 2025-02-12 | 15 |  | 2025-01-08 | 2025-01-13 |  | 2025-02-04 | 2025-02-20 | 17 |  | GP | 2025-01-14 | 2025-01-20 |  | 2025-02-02 | 2025-02-17 | 16 |  | 2025-01-27 | 2025-02-04 |  | 2025-03-12 | 2025-04-01 | 21 |  | 2024-11-27 | 2024-12-05 |  | 2025-04-01 | 2025-04-14 | 14 |  | 2025-02-06 | 2025-02-11 |  | 2025-04-04 | 2025-04-16 | 13 |  | 2025-02-12 | 2025-02-15 |  | 2025-04-17 | 2025-04-21 | 5 |  | 2024-12-07 | 2024-12-09 |  | 2025-04-24 | 2025-04-24 | 1 |  | 2025-01-17 | 2025-01-24 |  | 2025-03-06 | 2025-04-22 | 48 |  | 2025-02-08 | 2025-02-23 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-01-24 | 2025-01-27 |  | 2025-05-01 | 2025-05-11 | 11 |  | 2025-02-23 | 2025-02-24 |  | 2025-06-06 | 2025-06-06 | 1 |  |  | 2025-03-01
UNIQUE INF | 154 | PSS-10 | AGE26BL | WTG 361 | Precast | F5 | Kamar | Done | 543497 | 2663487 | 2024-05-11 | 2024-05-17 |  | 2024-05-11 | 2024-05-17 |  | 199 | 199 | 2024-10-05 | 2024-10-14 |  | 2024-12-17 | 2024-12-31 | 15 | [8 empty] | 2024-10-24 | 2024-10-25 |  | 2025-01-18 | 2025-01-22 | 5 |  | 2024-10-26 | 2024-10-27 |  | 2025-01-27 | 2025-01-30 | 4 |  | 2024-10-28 | 2024-10-28 |  | 2025-01-30 | 2025-01-30 | 1 |  | 2024-10-29 | 2024-10-30 |  | 2025-02-06 | 2025-02-07 | 2 |  | 2024-10-31 | 2024-11-07 |  | 2025-02-09 | 2025-03-10 | 30 | Unskilled manpower | 2024-11-08 | 2024-11-09 |  | 2025-03-11 | 2025-03-12 | 2 | 54 |  | 2024-11-11 | 2024-11-18 |  | 2025-03-18 | 2025-08-02 | 138 |  | 2024-11-11 | 2024-11-18 |  | 2025-03-22 | 2025-03-22 | 1 |  |  |  | 2024-11-04 | 2024-11-21 |  | 2025-01-29 | 2025-02-08 | 11 |  | 2024-12-16 | 2024-12-22 |  | Completed | Completed | #VALUE! |  | 2025-01-13 | 2025-01-18 |  | Completed | Completed | #VALUE! |  | GP (Reuse) | 2025-01-19 | 2025-01-25 |  | 2025-03-18 | 2025-03-31 | 14 |  | 2025-02-01 | 2025-02-09 |  | 2025-04-04 | 2025-04-25 | 22 |  | 2024-11-23 | 2024-12-01 |  | 2025-04-20 | 2025-05-01 | 12 |  | 2025-02-11 | 2025-02-16 |  | 2025-05-05 | 2025-05-20 | 16 |  | 2025-02-17 | 2025-02-20 |  | 2025-05-21 | 2025-05-22 | 2 |  | 2024-12-03 | 2024-12-05 |  | 2025-05-03 | 2025-05-03 | 1 |  | 2025-01-22 | 2025-01-29 |  | 2025-01-17 | 2025-02-02 | 17 |  | 2025-02-08 | 2025-02-23 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-01-29 | 2025-02-01 |  | 2025-06-12 | 2025-06-27 | 16 |  | 2025-02-23 | 2025-02-24 |  | 2025-06-29 | 2025-06-29 | 1 |  |  | 2025-03-01
MSC | 155 | PSS-10 | AGE26BL | WTG 386 | Precast | F5 | Kamar | Done | 544331 | 2663223 | 2024-05-12 | 2024-05-17 |  | 2024-05-12 | 2024-05-17 |  | 199 | 199 | 2024-10-01 | 2024-10-10 |  | 2024-12-13 | 2024-12-31 | 19 | [8 empty] | 2024-10-20 | 2024-10-21 |  | 2025-02-24 | 2025-02-27 | 4 |  | 2024-10-22 | 2024-10-23 |  | 2025-02-27 | 2025-02-28 | 2 |  | 2024-10-24 | 2024-10-24 |  | 2025-02-28 | 2025-02-28 | 1 |  | 2024-10-25 | 2024-10-26 |  | 2025-03-01 | 2025-03-01 | 1 |  | 2024-10-27 | 2024-11-03 |  | 2025-03-02 | 2025-03-09 | 8 |  | 2024-11-04 | 2024-11-05 |  | 2025-03-10 | 2025-03-10 | 1 | 15 |  | 2024-11-07 | 2024-11-14 |  | 2025-03-19 | 2025-05-30 | 73 |  | 2024-11-07 | 2024-11-14 |  | 2025-03-24 | 2025-03-24 | 1 |  |  |  | 2024-10-31 | 2024-11-17 |  | 2025-03-05 | 2025-03-08 | 4 |  | 2024-12-21 | 2024-12-27 |  | Completed | Completed | #VALUE! |  | 2025-01-09 | 2025-01-14 |  | 2025-02-12 | 2025-02-24 | 13 |  | GP | 2025-01-15 | 2025-01-21 |  | 2025-02-11 | 2025-02-24 | 14 |  | 2025-01-28 | 2025-02-05 |  | 2025-05-13 | 2025-06-05 | 24 |  | 2024-11-19 | 2024-11-27 |  | 2025-05-02 | 2025-05-15 | 14 |  | 2025-02-07 | 2025-02-12 |  | 2025-06-08 | 2025-06-14 | 7 |  | 2025-02-13 | 2025-02-16 |  | 2025-06-14 | 2025-06-17 | 4 |  | 2024-11-29 | 2024-12-01 |  | 2025-05-27 | 2025-05-27 | 1 |  | 2025-01-18 | 2025-01-25 |  | 2025-01-16 | 2025-02-01 | 17 |  | 2025-02-08 | 2025-02-23 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-01-25 | 2025-01-28 |  | 2025-06-12 | 2025-06-27 | 16 |  | 2025-02-23 | 2025-02-24 |  | 2025-06-29 | 2025-06-29 | 1 |  |  | 2025-03-01
MSC | 156 | PSS-10 | AGE26BL | WTG 411 | Precast | F4 | Keller | Done | 545173 | 2662919 | 2024-05-11 | 2024-05-17 |  | 2024-05-11 | 2024-05-17 |  | 253 | 253 | 2024-10-31 | 2024-11-06 |  | 2024-12-28 | 2025-01-04 | 8 |  | Yes | 2024-11-08 | 2024-11-22 |  | 2025-02-10 | 2025-02-24 |  | 2024-11-16 | 2024-11-17 |  | 2025-03-02 | 2025-03-03 | 2 |  | 2024-11-18 | 2024-11-19 |  | 2025-03-03 | 2025-03-03 | 1 |  | 2024-11-20 | 2024-11-20 |  | 2025-03-03 | 2025-03-03 | 1 |  | 2024-11-21 | 2024-11-22 |  | 2025-03-04 | 2025-03-04 | 1 |  | 2024-11-23 | 2024-11-30 |  | 2025-03-05 | 2025-03-18 | 14 |  | 2024-12-01 | 2024-12-02 |  | 2025-03-20 | 2025-03-21 | 2 | 20 |  | 2024-12-04 | 2024-12-11 |  | 2025-03-25 | 2025-06-20 | 88 |  | 2024-12-04 | 2024-12-11 |  | 2025-03-25 | 2025-03-25 | 1 |  |  |  | 2024-11-27 | 2024-12-14 |  | 2025-03-03 | 2025-03-18 | 16 |  | 2024-12-23 | 2024-12-29 |  | Completed | Completed | #VALUE! |  | 2025-01-11 | 2025-01-16 |  | 2025-02-25 | 2025-03-15 | 19 |  | GP | 2025-01-17 | 2025-01-23 |  | 2025-02-25 | 2025-03-17 | 21 |  | 2025-01-30 | 2025-02-07 |  | 2025-05-13 | 2025-06-08 | 27 |  | 2024-12-16 | 2024-12-24 |  | 2025-04-02 | 2025-04-14 | 13 |  | 2025-02-09 | 2025-02-14 |  | 2025-06-08 | 2025-06-15 | 8 |  | 2025-02-15 | 2025-02-18 |  | 2025-06-15 | 2025-06-18 | 4 |  | 2024-12-26 | 2024-12-28 |  | 2025-04-15 | 2025-04-15 | 1 |  | 2025-01-20 | 2025-01-27 |  | 2025-01-16 | 2025-03-04 | 48 |  | 2025-02-08 | 2025-02-23 |  | 2025-02-28 | 2025-03-17 | 18 |  | 2025-01-27 | 2025-01-30 |  | 2025-06-12 | 2025-06-27 | 16 |  | 2025-02-23 | 2025-02-24 |  | 2025-06-28 | 2025-06-29 | 2 |  |  | 2025-03-01
SHREEJI | 157 | PSS-10 | AGE26BL | WTG 437 | Precast | F3 | Keller | Done | 546007 | 2662654 | 2024-06-04 | 2024-06-09 |  | 2024-06-04 | 2024-06-09 |  | 199 | 199 | 2024-10-25 | 2024-11-04 |  | 2024-12-21 | 2024-12-27 | 7 |  | Yes | 2024-11-10 | 2024-11-25 |  | 2025-01-11 | 2025-01-22 |  | 2024-11-14 | 2024-11-15 |  | 2025-03-09 | 2025-03-10 | 2 |  | 2024-11-16 | 2024-11-17 |  | 2025-03-10 | 2025-03-11 | 2 |  | 2024-11-18 | 2024-11-18 |  | 2025-03-12 | 2025-03-12 | 1 |  | 2024-11-19 | 2024-11-20 |  | 2025-03-18 | 2025-03-19 | 2 |  | 2024-11-21 | 2024-11-28 |  | 2025-03-20 | 2025-03-27 | 8 |  | 2024-11-29 | 2024-11-30 |  | 2025-03-28 | 2025-03-28 | 1 | 20 |  | 2024-12-02 | 2024-12-09 |  | 2025-04-03 | 2025-05-02 | 30 |  | 2024-12-02 | 2024-12-09 |  | 2025-04-09 | 2025-04-09 | 1 |  |  |  | 2024-11-25 | 2024-12-12 |  | 2025-04-06 | 2025-04-10 | 5 |  | 2024-12-28 | 2025-01-03 |  | Completed | Completed | #VALUE! |  | 2025-01-16 | 2025-01-21 |  | 2025-04-22 | 2025-05-02 | 11 |  | GP | 2025-01-22 | 2025-01-28 |  | 2025-02-04 | 2025-03-20 | 45 |  | 2025-02-04 | 2025-02-12 |  | 2025-05-21 | 2025-06-27 | 38 |  | 2024-12-14 | 2024-12-22 |  | 2025-04-11 | 2025-04-30 | 20 |  | 2025-02-14 | 2025-02-19 |  | 2025-07-01 | 2025-07-09 | 9 |  | 2025-02-20 | 2025-02-23 |  | 2025-07-10 | 2025-07-14 | 5 |  | 2024-12-24 | 2024-12-26 |  | 2025-05-01 | 2025-05-01 | 1 |  | 2025-01-25 | 2025-02-01 |  | 2025-01-15 | 2025-04-22 | 98 |  | 2025-02-08 | 2025-02-23 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-02-01 | 2025-02-04 |  | 2025-07-05 | 2025-07-21 | 17 |  | 2025-02-23 | 2025-02-24 |  | 2025-07-22 | 2025-07-24 | 3 |  |  | 2025-03-01
MECC | 158 | PSS-10 | AGE26BL | WTG 462 | Precast | F6 | Keller | Done | 546849 | 2662350 | 2024-05-13 | 2024-05-17 |  | 2024-05-13 | 2024-05-17 |  | 253 | 253 | 2024-10-23 | 2024-10-30 |  | 2024-12-30 | 2025-01-09 | 11 |  | Yes | 2024-11-03 | 2024-11-17 |  | 2025-01-29 | 2025-02-03 |  | 2024-11-10 | 2024-11-11 |  | 2025-02-09 | 2025-02-13 | 5 |  | 2024-11-12 | 2024-11-13 |  | 2025-02-13 | 2025-02-14 | 2 |  | 2024-11-14 | 2024-11-14 |  | 2025-02-15 | 2025-02-15 | 1 |  | 2024-11-15 | 2024-11-16 |  | 2025-02-18 | 2025-02-18 | 1 |  | 2024-11-17 | 2024-11-24 |  | 2025-02-20 | 2025-03-05 | 14 |  | 2024-11-25 | 2024-11-26 |  | 2025-03-07 | 2025-03-08 | 2 | 28 |  | 2024-11-28 | 2024-12-05 |  | 2025-03-19 | 2025-05-24 | 67 |  | 2024-11-28 | 2024-12-05 |  | 2025-03-20 | 2025-03-20 | 1 |  |  |  | 2024-11-21 | 2024-12-08 |  | 2025-03-23 | 2025-03-27 | 5 |  | 2024-12-29 | 2025-01-04 |  | Completed | Completed | #VALUE! |  | 2025-01-18 | 2025-01-23 |  | 2025-03-01 | 2025-03-18 | 18 |  | GP | 2025-01-24 | 2025-01-30 |  | 2025-02-19 | 2025-03-18 | 28 |  | 2025-02-06 | 2025-02-14 |  | 2025-04-23 | 2025-05-05 | 13 |  | 2024-12-10 | 2024-12-18 |  | 2025-04-07 | 2025-04-16 | 10 |  | 2025-02-16 | 2025-02-21 |  | 2025-05-06 | 2025-05-30 | 25 | Work start by 25-May | 2025-02-22 | 2025-02-25 |  | 2025-06-01 | 2025-06-02 | 2 |  | 2024-12-20 | 2024-12-22 |  | 2025-04-18 | 2025-04-18 | 1 |  | 2025-01-27 | 2025-02-03 |  | 2025-03-21 | 2025-04-23 | 34 |  | 2025-02-08 | 2025-02-23 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-02-03 | 2025-02-06 |  | 2025-05-01 | 2025-05-11 | 11 |  | 2025-02-25 | 2025-02-26 |  | 2025-06-06 | 2025-06-06 | 1 |  |  | 2025-03-01
SHREEJI | 159 | PSS-10 | AGE26BL | WTG 487 | Precast | F6 | Keller | Done | 547683 | 2662085 | 2024-05-23 | 2024-06-09 |  | 2024-05-23 | 2024-06-09 |  | 303 | 303 | 2024-12-01 | 2024-12-08 |  | 2024-12-11 | 2024-12-20 | 10 |  | Yes | 2024-12-23 | 2024-12-31 |  | 2024-12-25 | 2025-01-12 | Additional stone column finish on 06-feb-25 | 2024-12-18 | 2024-12-19 |  | 2025-02-14 | 2025-02-18 | 5 |  | 2024-12-20 | 2024-12-21 |  | 2025-02-20 | 2025-02-21 | 2 |  | 2024-12-22 | 2024-12-22 |  | 2025-02-22 | 2025-02-22 | 1 |  | 2024-12-23 | 2024-12-24 |  | 2025-02-23 | 2025-02-23 | 1 |  | 2024-12-25 | 2025-01-01 |  | 2025-02-24 | 2025-03-04 | 9 |  | 2025-01-02 | 2025-01-03 |  | 2025-03-06 | 2025-03-07 | 2 | 22 |  | 2025-01-05 | 2025-01-12 |  | 2025-03-13 | 2025-05-25 | 74 |  | 2025-01-05 | 2025-01-12 |  | 2025-03-15 | 2025-03-15 | 1 |  |  |  | 2024-12-29 | 2025-01-15 |  | 2025-02-14 | 2025-02-27 | 14 |  | 2025-01-04 | 2025-01-10 |  | 2025-03-10 | 2025-03-31 | 22 |  | 2025-01-23 | 2025-01-28 |  | 2025-03-29 | 2025-03-31 | 3 |  | GP | 2025-01-29 | 2025-02-04 |  | 2025-03-10 | 2025-03-31 | 22 |  | 2025-02-11 | 2025-02-19 |  | 2025-04-05 | 2025-05-04 | 30 |  | 2025-01-17 | 2025-01-25 |  | 2025-04-08 | 2025-04-20 | 13 |  | 2025-02-21 | 2025-02-26 |  | 2025-05-06 | 2025-05-24 | 19 |  | 2025-02-27 | 2025-03-02 |  | 2025-05-24 | 2025-05-25 | 2 |  | 2025-01-27 | 2025-01-29 |  | 2025-04-21 | 2025-04-21 | 1 |  | 2025-02-01 | 2025-02-08 |  | 2025-03-22 | 2025-04-22 | 32 |  | 2025-02-08 | 2025-02-23 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-02-08 | 2025-02-11 |  | 2025-05-01 | 2025-05-11 | 11 |  | 2025-03-02 | 2025-03-03 |  | 2025-06-06 | 2025-06-06 | 1 |  |  | 2025-03-01
PERENNIAL | 160 | PSS-10 | AGE26BL | WTG 360 | Precast | F5 | Menard | Done | 543307 | 2664474 | 2023-01-11 | 2023-01-12 |  | 2023-01-11 | 2023-01-12 |  | 199 | 199 | 2024-11-27 | 2024-12-06 |  | 2023-10-02 | 2023-10-07 | 6 | [8 empty] | 2024-12-16 | 2024-12-17 |  | 2024-11-29 | 2024-12-10 | 12 |  | 2024-12-18 | 2024-12-19 |  | 2024-12-17 | 2024-12-26 | 10 |  | 2024-12-20 | 2024-12-20 |  | 2024-12-28 | 2024-12-28 | 1 |  | 2024-12-21 | 2024-12-22 |  | 2025-01-04 | 2025-01-05 | 2 |  | 2024-12-23 | 2024-12-30 |  | 2025-01-09 | 2025-01-24 | 16 |  | 2024-12-31 | 2025-01-01 |  | 2025-01-24 | 2025-01-25 | 2 | 58 |  | 2025-01-03 | 2025-01-10 |  | 2025-03-27 | 2025-04-23 | 28 |  | 2025-01-03 | 2025-01-10 |  | 2025-02-07 | 2025-02-07 | 1 |  |  |  | 2024-12-27 | 2025-01-13 |  | 2024-12-13 | 2025-02-14 | 64 |  | 2025-01-06 | 2025-01-12 |  | Completed | Completed | #VALUE! |  | 2025-01-25 | 2025-01-30 |  | 2025-02-14 | 2025-02-26 | 13 |  | GP | 2025-01-31 | 2025-02-06 |  | 2025-02-14 | 2025-03-11 | 26 |  | 2025-02-13 | 2025-02-21 |  | 2025-03-05 | 2025-03-14 | 10 |  | 2025-01-15 | 2025-01-23 |  | 2025-04-03 | 2025-04-20 | 18 |  | 2025-02-23 | 2025-02-28 |  | 2025-03-31 | 2025-04-04 | 5 |  | 2025-03-01 | 2025-03-04 |  | 2025-04-05 | 2025-04-07 | 3 |  | 2025-01-25 | 2025-01-27 |  | 2025-04-28 | 2025-04-28 | 1 |  | 2025-02-03 | 2025-02-10 |  | 2025-01-16 | 2025-02-02 | 18 |  | 2025-02-08 | 2025-02-23 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-02-10 | 2025-02-13 |  | 2025-06-12 | 2025-06-27 | 16 |  | 2025-03-04 | 2025-03-05 |  | 2025-06-29 | 2025-06-29 | 1 |  |  | 2025-03-01
SHREEJI | 161 | PSS-10 | AGE26BL | 1: WTG 385; 2: Precast; 3: F5; 4: Kamar/Bauer; 5: Done; 6: 544141; 7: 2664209; 8: 2024-05-10; 9: 2024-05-17; 11: 2024-05-10; 12: 2024-05-17; 14: 253; 15: 253; 16: 2024-11-24; 17: 2024-12-02; 19: 2026-01-09; 20: 2026-02-20; 21: 43; 23: Yes; 24: 2024-12-05; 25: 2024-12-20; 27: 22-01-2025/ 24-12-2025; 28: 03-02-2025 14-01-26; 29: PLT Fail; 30: 2024-12-12; 31: 2024-12-13; 37: 2024-12-14; 38: 2024-12-15; 44: 2024-12-16; 45: 2024-12-16; 51: 2024-12-17; 52: 2024-12-18; 58: 2024-12-19; 59: 2024-12-26; 65: 2024-12-27; 66: 2024-12-28; 73: 2024-12-30; 74: 2025-01-06; 80: 2024-12-30; 81: 2025-01-06; 89: 2024-12-23; 90: 2025-01-09; 92: 2025-04-27; 93: 2025-04-29; 94: 3; 96: 2025-01-18; 97: 2025-01-24; 99: Completed; 100: Completed; 101: #VALUE!; 103: 2025-02-06; 104: 2025-02-11; 106: 2025-05-20 | GP (Reuse) | 2025-02-12 | 2025-02-18 | [5 empty] | 2025-02-25 | 2025-03-05 | [5 empty] | 2025-01-11 | 2025-01-19 |  | 2025-06-11 |  |  |  | 2025-03-07 | 2025-03-12 | [5 empty] | 2025-03-13 | 2025-03-16 | [5 empty] | 2025-01-21 | 2025-01-23 | [5 empty] | 2025-02-15 | 2025-02-22 |  | 2025-01-16 | 2025-04-04 | 79 |  | 2025-03-05 | 2025-03-20 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-02-22 | 2025-02-25 |  | 2025-06-12 | 2025-06-27 | 16 | CFT apply only for HT panel | 2025-03-20 | 2025-03-21 | [6 empty] | 2025-03-01
MSC | 162 | PSS-10 | AGE26BL | WTG 410 | Precast | F4 | Bauer | Done | 544982 | 2663905 | 2024-05-11 | 2024-05-17 |  | 2024-05-11 | 2024-05-17 |  | 199 | 199 | 2024-11-22 | 2024-11-30 |  | 2025-01-23 | 2025-01-29 | 7 | [8 empty] | 2024-12-10 | 2024-12-11 |  | 2025-02-01 | 2025-02-03 | 3 |  | 2024-12-12 | 2024-12-13 |  | 2025-02-03 | 2025-02-04 | 2 |  | 2024-12-14 | 2024-12-14 |  | 2025-02-05 | 2025-02-05 | 1 |  | 2024-12-15 | 2024-12-16 |  | 2025-02-07 | 2025-02-07 | 1 |  | 2024-12-17 | 2024-12-24 |  | 2025-02-07 | 2025-02-11 | 5 |  | 2024-12-25 | 2024-12-26 |  | 2025-02-12 | 2025-02-12 | 1 | 12 |  | 2024-12-28 | 2025-01-04 |  | 2025-02-27 | 2025-06-22 | 116 |  | 2024-12-28 | 2025-01-04 |  | 2025-02-26 | 2025-02-26 | 1 |  |  |  | 2024-12-21 | 2025-01-07 |  | 2025-02-12 | 2025-03-10 | 27 |  | 2025-01-19 | 2025-01-25 |  | Completed | Completed | #VALUE! |  | 2025-02-07 | 2025-02-12 |  | 2025-03-06 | 2025-03-19 | 14 |  | GP (Reuse) | 2025-02-13 | 2025-02-19 |  | 2025-03-08 | 2025-03-20 | 13 |  | 2025-02-26 | 2025-03-06 |  | 2025-04-06 | 2025-06-23 | 79 |  | 2025-01-09 | 2025-01-17 |  | 2025-04-10 | 2025-04-20 | 11 |  | 2025-03-08 | 2025-03-13 |  | 2025-06-23 | 2025-06-28 | 6 |  | 2025-03-14 | 2025-03-17 |  | 2025-06-29 | 2025-06-29 | 1 |  | 2025-01-19 | 2025-01-21 |  | 2025-04-21 | 2025-04-21 | 1 |  | 2025-02-16 | 2025-02-23 |  | 2025-02-20 | 2025-04-22 | 62 |  | 2025-03-05 | 2025-03-20 |  | 2025-02-28 | 2025-03-17 | 18 |  | 2025-02-23 | 2025-02-26 |  | 2025-06-12 | 2025-06-27 | 16 |  | 2025-03-20 | 2025-03-21 |  | 2025-06-28 | 2025-06-29 | 2 |  |  | 2025-03-01
HBG | 163 | PSS-10 | AGE26BL | WTG 436 | Precast | F4 | Bauer | Done | 545817 | 2663640 | 2024-05-12 | 2024-05-17 |  | 2024-05-12 | 2024-05-17 |  | 253 | 253 | 2024-11-20 | 2024-11-28 |  | 2025-01-13 | 2025-01-21 | 9 | [8 empty] | 2024-12-06 | 2024-12-07 |  | 2025-01-25 | 2025-02-04 | 11 |  | 2024-12-08 | 2024-12-09 |  | 2025-02-08 | 2025-02-10 | 3 |  | 2024-12-10 | 2024-12-10 |  | 2025-02-11 | 2025-02-11 | 1 |  | 2024-12-11 | 2024-12-12 |  | 2025-02-12 | 2025-02-13 | 2 |  | 2024-12-13 | 2024-12-20 |  | 2025-02-14 | 2025-02-22 | 9 |  | 2024-12-21 | 2024-12-22 |  | 2025-02-23 | 2025-02-24 | 2 | 31 |  | 2024-12-24 | 2024-12-31 |  | 2025-03-15 | 2025-04-21 | 38 |  | 2024-12-24 | 2024-12-31 |  | 2025-03-02 | 2025-03-02 | 1 |  |  |  | 2024-12-17 | 2025-01-03 |  | 2025-04-09 | 2025-04-13 | 5 |  | 2025-01-14 | 2025-01-20 |  | Completed | Completed | #VALUE! |  | 2025-02-02 | 2025-02-07 |  | 2025-04-15 | 2025-04-30 | 16 |  | GP | 2025-02-08 | 2025-02-14 |  | 2025-02-09 | 2025-03-07 | 27 |  | 2025-02-21 | 2025-03-01 |  | 2025-05-20 | 2025-06-11 | 23 |  | 2025-01-05 | 2025-01-13 |  | 2025-04-18 | 2025-04-30 | 13 |  | 2025-03-03 | 2025-03-08 |  | 2025-06-13 | 2025-06-20 | 8 |  | 2025-03-09 | 2025-03-12 |  | 2025-06-21 | 2025-06-24 | 4 |  | 2025-01-15 | 2025-01-17 |  | 2025-05-01 | 2025-05-01 | 1 |  | 2025-02-11 | 2025-02-18 |  | 2025-03-24 | 2025-04-20 | 28 |  | 2025-03-05 | 2025-03-20 |  | 2025-02-28 | 2025-03-17 | 18 |  | 2025-02-18 | 2025-02-21 |  | 2025-06-12 | 2025-06-27 | 16 |  | 2025-03-20 | 2025-03-21 |  | 2025-06-28 | 2025-06-28 | 1 |  |  | 2025-03-01
HBG | 164 | PSS-10 | AGE26BL | WTG 461 | Precast | F3 | Keller | Done | 546658 | 2663336 | 2024-05-13 | 2024-05-17 |  | 2024-05-13 | 2024-05-17 |  | 253 | 253 | 2024-10-12 | 2024-10-20 |  | 2025-01-06 | 2025-01-21 | 16 | [8 empty] | 2024-11-01 | 2024-11-01 |  | 2025-02-11 | 2025-02-18 | 8 |  | 2024-11-02 | 2024-11-02 |  | 2025-02-18 | 2025-02-19 | 2 |  | 2024-11-03 | 2024-11-03 |  | 2025-02-20 | 2025-02-20 | 1 |  | 2024-11-04 | 2024-11-05 |  | 2025-02-25 | 2025-02-25 | 1 |  | 2024-11-07 | 2024-11-16 |  | 2025-03-02 | 2025-03-09 | 8 |  | 2024-11-18 | 2024-11-19 |  | 2025-03-09 | 2025-03-10 | 2 | 28 |  | 2024-11-20 | 2024-11-26 |  | 2025-03-16 | 2025-05-08 | 54 |  | 2024-11-20 | 2024-11-26 |  | 2025-03-21 | 2025-03-21 | 1 |  |  |  | 2024-11-14 | 2024-11-28 |  | 2025-04-06 | 2025-04-18 | 13 |  | 2025-01-15 | 2025-01-21 |  | Completed | Completed | #VALUE! |  | 2025-02-03 | 2025-02-08 |  | 2025-04-22 | 2025-05-24 | 33 |  | SS Jadeja | 2025-02-09 | 2025-02-15 |  | 2025-04-18 | 2025-05-24 | 37 |  | 2025-02-22 | 2025-03-02 |  | 2025-06-13 | 2025-06-25 | 13 |  | 2024-11-30 | 2024-12-08 |  | 2025-04-11 | 2025-05-02 | 22 |  | 2025-03-04 | 2025-03-09 |  | 2025-06-29 | 2025-07-06 | 8 |  | 2025-03-10 | 2025-03-13 |  | 2025-07-10 | 2025-07-11 | 2 |  | 2024-12-10 | 2024-12-12 |  | 2025-05-04 | 2025-05-04 | 1 |  | 2025-02-12 | 2025-02-19 |  | 2025-02-24 | 2025-02-25 | 2 |  | 2025-03-05 | 2025-03-20 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-02-19 | 2025-02-22 |  | 2025-07-05 | 2025-07-21 | 17 |  | 2025-03-20 | 2025-03-21 |  | 2025-07-22 | 2025-07-24 | 3 |  |  | 2025-03-01
SHREERAM | 165 | PSS-10 | AGE26BL | WTG 486 | Precast | F3 | Sarita infra | Done | 547493 | 2663071 | 2024-05-14 | 2024-05-17 |  | 2024-05-14 | 2024-05-17 |  | 253 | 253 | 2024-10-13 | 2024-10-21 |  | 2025-02-03 | 2025-03-06 | 32 | [8 empty] | 2024-11-03 | 2024-11-03 |  | 2025-03-10 | 2025-03-16 | 7 |  | 2024-11-04 | 2024-11-04 |  | 2025-03-16 | 2025-03-17 | 2 |  | 2024-11-05 | 2024-11-05 |  | 2025-03-17 | 2025-03-17 | 1 |  | 2024-11-06 | 2024-11-07 |  | 2025-03-20 | 2025-03-20 | 1 |  | 2024-11-09 | 2024-11-18 |  | 2025-03-26 | 2025-04-05 | 11 |  | 2024-11-20 | 2024-11-21 |  | 2025-04-06 | 2025-04-07 | 2 | 29 |  | 2024-11-22 | 2024-11-28 |  | 2025-04-13 | 2025-05-26 | 44 |  | 2024-11-22 | 2024-11-28 |  | 2025-04-11 | 2025-04-11 | 1 |  |  |  | 2024-11-16 | 2024-11-30 |  | 2025-04-09 | 2025-04-18 | 10 |  | 2025-01-18 | 2025-01-23 |  | Completed | Completed | #VALUE! |  | 2025-02-05 | 2025-02-10 |  | 2025-05-21 | 2025-06-13 | 24 |  | SS Jadeja | 2025-02-11 | 2025-02-17 |  | 2025-05-29 | 2025-06-12 | 15 |  | 2025-02-24 | 2025-03-04 |  | 2025-06-15 | 2025-06-28 | 14 |  | 2024-12-02 | 2024-12-10 |  | 2025-05-30 | 2025-06-05 | 7 |  | 2025-03-06 | 2025-03-11 |  | 2025-07-01 | 2025-07-09 | 9 |  | 2025-03-12 | 2025-03-15 |  | 2025-07-10 | 2025-07-13 | 4 |  | 2024-12-12 | 2024-12-14 |  | 2025-06-07 | 2025-06-07 | 1 |  | 2025-02-14 | 2025-02-21 |  | 2025-03-02 | 2025-04-21 | 51 |  | 2025-03-05 | 2025-03-20 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-02-21 | 2025-02-24 |  | 2025-07-05 | 2025-07-21 | 17 |  | 2025-03-20 | 2025-03-21 |  | 2025-07-22 | 2025-07-24 | 3 |  |  | 2025-03-01
SHREEJI | 166 | PSS-10 | AGE26BL | WTG 460 | Precast | F3 | Bauer | Done | 546468 | 2664322 | 2024-05-13 | 2024-05-17 |  | 2024-05-13 | 2024-05-17 |  | 253 | 369 | 2024-10-17 | 2024-10-24 |  | 2025-01-07 | 2025-01-16 | 10 |  | Yes | 2024-10-30 | 2024-11-14 |  | 2025-02-05 | 2025-02-14 |  | 2024-11-05 | 2024-11-05 |  | 2025-03-27 | 2025-03-29 | 3 |  | 2024-11-06 | 2024-11-06 |  | 2025-03-30 | 2025-03-31 | 2 |  | 2024-11-07 | 2024-11-07 |  | 2025-04-01 | 2025-04-01 | 1 |  | 2024-11-08 | 2024-11-09 |  | 2025-04-03 | 2025-04-04 | 2 |  | 2024-11-11 | 2024-11-20 |  | 2025-04-04 | 2025-04-07 | 4 |  | 2024-11-22 | 2024-11-23 |  | 2025-04-09 | 2025-04-10 | 2 | 15 |  | 2024-11-24 | 2024-11-30 |  | 2025-04-13 | 2025-05-06 | 24 |  | 2024-11-24 | 2024-11-30 |  | 2025-04-12 | 2025-04-13 |  |  |  |  | 2024-11-18 | 2024-12-02 |  | 2025-03-31 | 2025-04-06 | 7 |  | 2025-02-04 | 2025-02-10 |  | 2025-02-22 | 2025-03-10 | 17 |  | 2025-02-23 | 2025-02-28 |  | 2025-04-04 | 2025-04-19 | 16 |  | SS Jadeja | 2025-03-01 | 2025-03-07 |  | 2025-03-28 | 2025-04-29 | 33 |  | 2025-03-14 | 2025-03-22 |  | 2025-06-07 | 2025-06-16 | 10 |  | 2024-12-04 | 2024-12-12 |  | 2025-04-11 | 2025-04-30 | 20 |  | 2025-03-24 | 2025-03-29 |  | 2025-06-20 | 2025-06-29 | 10 |  | 2025-03-30 | 2025-04-02 |  | 2025-06-30 | 2025-07-04 | 5 |  | 2024-12-14 | 2024-12-16 |  | 2025-05-03 | 2025-05-03 | 1 |  | 2025-03-04 | 2025-03-11 |  | 2025-01-15 | 2025-04-18 | 94 |  | 2025-03-05 | 2025-03-20 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-03-11 | 2025-03-14 |  | 2025-07-05 | 2025-07-21 | 17 |  | 2025-04-02 | 2025-04-03 |  | 2025-07-22 | 2025-07-24 | 3 |  |  | 2025-03-01
MECC | 167 | PSS-10 | AGE26BL | WTG 485 | Precast | F3 | Bauer | Done | 547302 | 2664057 | 2024-05-15 | 2024-06-09 |  | 2024-05-15 | 2024-06-09 |  | 253 | 253 | 2024-10-19 | 2024-10-26 |  | 2025-01-17 | 2025-01-29 | 13 | [8 empty] | 2024-11-07 | 2024-11-07 |  | 2025-02-01 | 2025-02-04 | 4 |  | 2024-11-08 | 2024-11-08 |  | 2025-02-05 | 2025-02-06 | 2 |  | 2024-11-09 | 2024-11-09 |  | 2025-02-06 | 2025-02-06 | 1 |  | 2024-11-10 | 2024-11-11 |  | 2025-02-12 | 2025-02-13 | 2 |  | 2024-11-13 | 2024-11-22 |  | 2025-02-14 | 2025-02-22 | 9 |  | 2024-11-24 | 2024-11-25 |  | 2025-02-24 | 2025-02-25 | 2 | 25 |  | 2024-11-26 | 2024-12-02 |  | 2025-03-05 | 2025-05-24 | 81 |  | 2024-11-26 | 2024-12-02 |  | 2025-03-04 | 2025-03-04 | 1 |  |  |  | 2024-11-20 | 2024-12-04 |  | 2025-03-23 | 2025-03-25 | 3 |  | 2025-02-04 | 2025-02-10 |  | Completed | Completed | #VALUE! |  | 2025-02-23 | 2025-02-28 |  | Completed | Completed | #VALUE! |  | SS Jadeja | 2025-03-01 | 2025-03-07 |  | 2025-03-17 | 2025-03-31 | 15 |  | 2025-03-14 | 2025-03-22 |  | 2025-05-20 | 2025-06-11 | 23 |  | 2024-12-06 | 2024-12-14 |  | 2025-04-08 | 2025-04-30 | 23 |  | 2025-03-24 | 2025-03-29 |  | 2025-06-17 | 2025-06-24 | 8 |  | 2025-03-30 | 2025-04-02 |  | 2025-06-24 | 2025-06-27 | 4 |  | 2024-12-16 | 2024-12-18 |  | 2025-05-01 | 2025-05-01 | 1 |  | 2025-03-04 | 2025-03-11 |  | 2025-01-15 | 2025-02-03 | 20 |  | 2025-03-05 | 2025-03-20 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-03-11 | 2025-03-14 |  | 2025-07-05 | 2025-07-21 | 17 |  | 2025-04-02 | 2025-04-03 |  | 2025-07-23 | 2025-07-24 | 2 |  |  | 2025-03-01
MECC | 168 | PSS-10 | AGE26BL | WTG 508 | Precast | F2 | Sarita infra | Done | 548144 | 2663753 | 2024-05-23 | 2024-06-09 |  | 2024-05-23 | 2024-06-09 |  | 199 | 199 | 2024-10-20 | 2024-10-28 |  | 2024-11-11 | 2024-11-19 | 9 | [8 empty] | 2024-11-09 | 2024-11-09 |  | 2025-01-15 | 2025-01-16 | 2 |  | 2024-11-10 | 2024-11-10 |  | 2025-01-17 | 2025-01-22 | 6 | Water seephage | 2024-11-11 | 2024-11-11 |  | 2025-01-23 | 2025-01-23 | 1 |  | 2024-11-12 | 2024-11-13 |  | 2025-01-25 | 2025-01-25 | 1 |  | 2024-11-15 | 2024-11-24 |  | 2025-01-28 | 2025-02-15 | 19 |  | 2024-11-26 | 2024-11-27 |  | 2025-02-15 | 2025-02-17 | 3 | 34 |  | 2024-11-28 | 2024-12-04 |  | 2025-02-27 | 2025-05-23 | 86 |  | 2024-11-28 | 2024-12-04 |  | 2025-03-01 | 2025-03-01 | 1 |  |  |  | 2024-11-22 | 2024-12-06 |  | 2025-03-05 | 2025-03-11 | 7 |  | 2024-12-12 | 2024-12-18 |  | 2025-02-22 | 2025-03-05 | 12 |  | 2025-01-17 | 2025-01-22 |  | 2025-03-04 | 2025-03-17 | 14 |  | SS Jadeja | 2025-01-23 | 2025-01-29 |  | 2025-03-02 | 2025-03-15 | 14 |  | 2025-02-05 | 2025-02-13 |  | 2025-03-17 | 2025-03-28 | 12 |  | 2024-12-08 | 2024-12-16 |  | 2025-04-10 | 2025-04-15 | 6 |  | 2025-02-15 | 2025-02-20 |  | 2025-04-05 | 2025-04-11 | 7 |  | 2025-02-21 | 2025-02-24 |  | 2025-04-13 | 2025-04-14 | 2 |  | 2024-12-18 | 2024-12-20 |  | 2025-04-17 | 2025-04-17 | 1 |  | 2025-01-26 | 2025-02-02 |  | 2025-03-27 | 2025-04-30 | 35 |  | 2025-02-08 | 2025-02-23 |  | 2025-02-28 | 2025-03-17 | 18 |  | 2025-02-02 | 2025-02-05 |  | 2025-05-01 | 2025-05-07 | 7 |  | 2025-02-24 | 2025-02-25 |  | 2025-06-05 | 2025-06-05 | 1 |  |  | 2025-03-01
TEJAS | 169 | PSS-10 | AGE26BL | WTG 383 | Precast | F1 | Sarita infra | Done | 543760 | 2666181 | 2024-05-08 | 2024-05-17 |  | 2024-05-08 | 2024-05-17 |  | 199 | 199 | 2024-10-23 | 2024-10-31 |  | 2024-12-13 | 2024-12-18 | 6 | [8 empty] | 2024-11-11 | 2024-11-11 |  | 2024-12-27 | 2025-01-06 | 11 |  | 2024-11-12 | 2024-11-12 |  | 2025-01-07 | 2025-01-09 | 3 |  | 2024-11-13 | 2024-11-13 |  | 2025-01-11 | 2025-01-11 | 1 |  | 2024-11-14 | 2024-11-15 |  | 2025-01-20 | 2025-01-20 | 1 |  | 2024-11-17 | 2024-11-26 |  | 2025-01-20 | 2025-02-20 | 32 |  | 2024-11-28 | 2024-11-29 |  | 2025-02-21 | 2025-02-22 | 2 | 58 |  | 2024-11-30 | 2024-12-06 |  | 2025-03-02 | 2025-05-26 | 86 |  | 2024-11-30 | 2024-12-06 |  | 2025-03-01 | 2025-03-01 | 1 |  |  |  | 2024-11-24 | 2024-12-08 |  | 2025-03-03 | 2025-03-23 | 21 |  | 2025-02-02 | 2025-02-08 |  | 2025-02-07 | 2025-02-21 | 15 |  | 2025-02-21 | 2025-02-26 |  | 2025-02-22 | 2025-03-11 | 18 |  | Odhav (Reuse) | 2025-02-27 | 2025-03-05 |  | 2025-02-22 | 2025-03-11 | 18 |  | 2025-03-12 | 2025-03-20 |  | 2025-03-23 | 2025-04-22 | 31 |  | 2024-12-10 | 2024-12-18 |  | 2025-04-08 | 2025-04-26 | 19 |  | 2025-03-22 | 2025-03-27 |  | 2025-04-24 | 2025-04-27 | 4 |  | 2025-03-28 | 2025-03-31 |  | 2025-04-28 | 2025-04-30 | 3 |  | 2024-12-20 | 2024-12-22 |  | 2025-04-28 | 2025-04-28 | 1 |  | 2025-03-02 | 2025-03-09 |  | 2025-02-22 | 2025-03-06 | 13 |  | 2025-03-05 | 2025-03-20 |  | 2025-02-28 | 2025-03-17 | 18 |  | 2025-03-09 | 2025-03-12 |  | 2025-05-01 | 2025-05-08 | 8 |  | 2025-03-31 | 2025-04-01 |  | 2025-06-28 | 2025-06-29 | 2 |  |  | 2025-03-01
SHREEJI | 170 | PSS-10 | AGE26BL | WTG 384 | Precast | F5 | Sarita infra | Done | 543951 | 2665195 | 2024-05-09 | 2024-05-17 |  | 2024-05-09 | 2024-05-17 |  | 253 | 253 | 2024-12-15 | 2024-12-23 |  | 2025-01-13 | 2025-01-22 | 10 | [8 empty] | 2024-12-31 | 2025-01-01 |  | 2025-02-04 | 2025-02-08 | 5 |  | 2025-01-02 | 2025-01-03 |  | 2025-02-08 | 2025-02-09 | 2 |  | 2025-01-04 | 2025-01-04 |  | 2025-02-10 | 2025-02-10 | 1 |  | 2025-01-05 | 2025-01-06 |  | 2025-02-11 | 2025-02-11 | 1 |  | 2025-01-07 | 2025-01-14 |  | 2025-02-12 | 2025-02-17 | 6 |  | 2025-01-15 | 2025-01-16 |  | 2025-02-18 | 2025-02-18 | 1 | 15 |  | 2025-01-18 | 2025-01-25 |  | 2025-03-01 | 2025-06-20 | 112 |  | 2025-01-18 | 2025-01-25 |  | 2025-02-22 | 2025-02-22 | 1 |  |  |  | 2025-01-11 | 2025-01-28 |  | 2025-02-04 | 2025-02-13 | 10 |  | 2025-02-02 | 2025-02-08 |  | 2025-02-15 | 2025-03-03 | 17 |  | 2025-02-21 | 2025-02-26 |  | 2025-02-20 | 2025-03-03 | 12 |  | GP | 2025-02-27 | 2025-03-05 |  | 2025-02-14 | 2025-03-03 | 18 |  | 2025-03-12 | 2025-03-20 |  | 2025-04-24 | 2025-05-18 | 25 |  | 2025-01-30 | 2025-02-07 |  | 2025-04-04 | 2025-04-30 | 27 |  | 2025-03-22 | 2025-03-27 |  | 2025-05-26 | 2025-06-06 | 12 |  | 2025-03-28 | 2025-03-31 |  | 2025-06-07 | 2025-06-11 | 5 |  | 2025-02-09 | 2025-02-11 |  | 2025-05-03 | 2025-05-03 | 1 |  | 2025-03-02 | 2025-03-09 |  | 2025-01-16 | 2025-02-01 | 17 |  | 2025-03-05 | 2025-03-20 |  | 2025-03-31 | 2025-04-30 | 31 |  | 2025-03-09 | 2025-03-12 |  | 2025-06-12 | 2025-06-27 | 16 |  | 2025-03-31 | 2025-04-01 |  | 2025-06-29 | 2025-06-29 | 1 |  |  | 2025-03-01
UNIQUE INF | 171 | PSS-10 | AGE26BL | WTG 408 | Precast | F1 | Sarita infra | Done | 544602 | 2665877 | 2024-05-09 | 2024-05-17 |  | 2024-05-09 | 2024-05-17 |  | 253 | 253 | 2024-12-13 | 2024-12-21 |  | 2024-12-12 | 2024-12-28 | 17 | [8 empty] | 2024-12-29 | 2024-12-30 |  | 2025-01-07 | 2025-01-13 | 7 |  | 2024-12-31 | 2025-01-01 |  | 2025-02-03 | 2025-02-06 | 4 |  | 2025-01-02 | 2025-01-02 |  | 2025-02-08 | 2025-02-08 | 1 |  | 2025-01-03 | 2025-01-04 |  | 2025-02-10 | 2025-02-10 | 1 |  | 2025-01-05 | 2025-01-12 |  | 2025-02-10 | 2025-02-21 | 12 |  | 2025-01-13 | 2025-01-14 |  | 2025-02-21 | 2025-02-22 | 2 | 47 |  | 2025-01-16 | 2025-01-23 |  | 2025-02-28 | 2025-08-04 | 158 |  | 2025-01-16 | 2025-01-23 |  | 2025-03-01 | 2025-03-01 | 1 |  |  |  | 2025-01-09 | 2025-01-26 |  | 2025-02-07 | 2025-03-21 | 43 |  | 2025-01-31 | 2025-02-06 |  | 2025-02-15 | 2025-03-03 | 17 |  | 2025-02-19 | 2025-02-24 |  | 2025-03-02 | 2025-03-20 | 19 |  | Odhav (Reuse) | 2025-02-25 | 2025-03-03 |  | 2025-03-02 | 2025-03-20 | 19 |  | 2025-03-10 | 2025-03-18 |  | 2025-04-25 | 2025-06-10 | 47 |  | 2025-01-28 | 2025-02-05 |  | 2025-04-09 | 2025-04-21 | 13 |  | 2025-03-20 | 2025-03-25 |  | 2025-06-13 | 2025-06-17 | 5 |  | 2025-03-26 | 2025-03-29 |  | 2025-06-18 | 2025-06-20 | 3 |  | 2025-02-07 | 2025-02-09 |  | 2025-04-22 | 2025-04-22 | 1 |  | 2025-02-28 | 2025-03-07 |  | 2025-02-22 | 2025-03-06 | 13 |  | 2025-03-05 | 2025-03-20 |  | 2025-02-28 | 2025-03-17 | 18 |  | 2025-03-07 | 2025-03-10 |  | 2025-05-01 | 2025-05-06 | 6 |  | 2025-03-29 | 2025-03-30 |  | 2025-06-28 | 2025-06-28 | 1 |  |  | 2025-03-01
MSC | 172 | PSS-10 | AGE26BL | WTG 409 | Precast | F4 | Sarita infra | Done | 544792 | 2664891 | 2024-05-10 | 2024-05-17 |  | 2024-05-10 | 2024-05-17 |  | 253 | 253 | 2024-12-11 | 2024-12-17 |  | 2024-12-30 | 2025-01-25 | 27 | [8 empty] | 2024-12-27 | 2024-12-28 |  | 2025-02-09 | 2025-02-11 | 3 |  | 2024-12-29 | 2024-12-30 |  | 2025-02-11 | 2025-02-11 | 1 |  | 2024-12-31 | 2024-12-31 |  | 2025-02-11 | 2025-02-11 | 1 |  | 2025-01-01 | 2025-01-02 |  | 2025-02-15 | 2025-02-15 | 1 |  | 2025-01-03 | 2025-01-10 |  | 2025-02-16 | 2025-02-19 | 4 |  | 2025-01-11 | 2025-01-12 |  | 2025-02-20 | 2025-02-20 | 1 | 12 |  | 2025-01-14 | 2025-01-21 |  | 2025-03-04 | 2025-06-10 | 99 |  | 2025-01-14 | 2025-01-21 |  | 2025-03-03 | 2025-03-03 | 1 |  |  |  | 2025-01-07 | 2025-01-24 |  | 2025-02-12 | 2025-02-15 | 4 |  | 2025-01-31 | 2025-02-06 |  | Completed | Completed | #VALUE! |  | 2025-02-19 | 2025-02-24 |  | 2025-02-18 | 2025-03-09 | 20 |  | GP (Reuse) | 2025-02-25 | 2025-03-03 |  | 2025-02-15 | 2025-03-06 | 20 |  | 2025-03-10 | 2025-03-18 |  | 2025-03-11 | 2025-04-03 | 24 |  | 2025-01-26 | 2025-02-03 |  | 2025-04-10 | 2025-04-23 | 14 |  | 2025-03-20 | 2025-03-25 |  | 2025-04-05 | 2025-04-21 | 17 |  | 2025-03-26 | 2025-03-29 |  | 2025-04-22 | 2025-04-23 | 2 |  | 2025-02-05 | 2025-02-07 |  | 2025-04-21 | 2025-04-21 | 1 |  | 2025-02-28 | 2025-03-07 |  | 2025-01-16 | 2025-01-30 | 15 |  | 2025-03-05 | 2025-03-20 |  | 2025-02-28 | 2025-03-17 | 18 |  | 2025-03-07 | 2025-03-10 |  | 2025-06-12 | 2025-06-27 | 16 |  | 2025-03-29 | 2025-03-30 |  | 2025-06-28 | 2025-06-28 | 1 |  |  | 2025-03-01
Shreeji | 173 | PSS-10 | AGE26BL | WTG 434 | Precast | F1 | Sarita/Bauer | Done | 545436 | 2665613 | 2024-05-13 | 2024-05-17 |  | 2024-05-13 | 2024-05-17 |  | 253 | 369 | 2024-12-10 | 2024-12-17 |  | 2025-01-02 | 2025-01-11 | 10 |  | Yes | 2024-12-20 | 2025-01-04 |  | 08-02-2025 / 11-12-25 | 19-02-2025 31-12-25 |  | 2024-12-25 | 2024-12-26 |  | 2026-01-07 | 2026-01-17 | 11 |  | 2024-12-27 | 2024-12-28 |  | 2026-01-17 | 2026-01-20 | 4 |  | 2024-12-29 | 2024-12-29 |  | 2026-01-20 | 2026-01-20 | 1 |  | 2024-12-30 | 2024-12-31 |  | 2026-01-22 | 2026-01-22 | 1 |  | 2025-01-01 | 2025-01-08 |  | 2026-01-24 | 2026-01-31 | 8 |  | 2025-01-09 | 2025-01-10 |  | 2026-01-31 | 2026-02-01 | 2 | 26 |  | 2025-01-12 | 2025-01-19 |  | 2026-02-07 |  |  |  | 2025-01-12 | 2025-01-19 |  | 2026-02-08 | 2026-02-08 | 1 |  |  |  | 2025-01-05 | 2025-01-22 |  | 2025-04-26 | 2025-04-28 | 3 |  | 2025-01-30 | 2025-02-05 |  | 2025-03-06 | 2025-03-19 | 14 |  | 2025-02-18 | 2025-02-23 |  | 2025-03-25 | 2026-02-23 | 336 |  | Odhav (Reuse) | 2025-02-24 | 2025-03-02 |  | 2025-03-11 | 2025-03-25 | 15 |  | 2025-03-09 | 2025-03-17 |  | 2026-02-23 |  |  |  | 2025-01-24 | 2025-02-01 | [5 empty] | 2025-03-19 | 2025-03-24 | [5 empty] | 2025-03-25 | 2025-03-28 | [5 empty] | 2025-02-03 | 2025-02-05 | [5 empty] | 2025-02-27 | 2025-03-06 |  | 2025-03-05 | 2025-05-01 | 58 |  | 2025-03-05 | 2025-03-20 |  | 2025-02-28 | 2025-03-17 | 18 |  | 2025-03-06 | 2025-03-09 | [5 empty] | 2025-03-28 | 2025-03-29 | [6 empty] | 2025-03-01
MSC | 174 | PSS-10 | AGE26BL | WTG 435 | Precast | F4 | Bauer | Done | 545626 | 2664626 | 2024-05-12 | 2024-05-17 |  | 2024-05-12 | 2024-05-17 |  | 253 | 253 | 2024-12-07 | 2024-12-15 |  | 2025-01-30 | 2025-02-12 | 14 | [8 empty] | 2024-12-23 | 2024-12-24 |  | 2025-02-14 | 2025-02-16 | 3 |  | 2024-12-25 | 2024-12-26 |  | 2025-02-16 | 2025-02-16 | 1 |  | 2024-12-27 | 2024-12-27 |  | 2025-02-16 | 2025-02-16 | 1 |  | 2024-12-28 | 2024-12-29 |  | 2025-02-18 | 2025-02-18 | 1 |  | 2024-12-30 | 2025-01-06 |  | 2025-02-19 | 2025-02-23 | 5 |  | 2025-01-07 | 2025-01-08 |  | 2025-02-23 | 2025-02-23 | 1 | 10 |  | 2025-01-10 | 2025-01-17 |  | 2025-03-05 | 2025-06-11 | 99 |  | 2025-01-10 | 2025-01-17 |  | 2025-03-08 | 2025-03-08 | 1 |  |  |  | 2025-01-03 | 2025-01-20 |  | 2025-02-25 | 2025-02-27 | 3 |  | 2024-01-29 | 2025-02-04 |  | Completed | Completed | #VALUE! |  | 2025-02-17 | 2025-02-22 |  | Completed | Completed | #VALUE! |  | GP (Reuse) | 2025-02-23 | 2025-03-01 |  | 2025-02-23 | 2025-03-13 | 19 |  | 2025-03-08 | 2025-03-16 |  | 2025-04-27 | 2025-05-18 | 22 |  | 2025-01-22 | 2025-01-30 |  | 2025-04-04 | 2025-04-13 | 10 |  | 2025-03-18 | 2025-03-23 |  | 2025-05-22 | 2025-05-28 | 7 |  | 2025-03-24 | 2025-03-27 |  | 2025-05-29 | 2025-05-30 | 2 |  | 2025-02-01 | 2025-02-03 |  | 2025-04-14 | 2025-04-14 | 1 |  | 2025-02-26 | 2025-03-05 |  | 2025-01-16 | 2025-03-04 | 48 |  | 2025-03-05 | 2025-03-20 |  | 2025-02-28 | 2025-03-17 | 18 |  | 2025-03-05 | 2025-03-08 |  | 2025-06-12 | 2025-06-27 | 16 |  | 2025-03-27 | 2025-03-28 |  | 2025-06-28 | 2025-06-28 | 1 |  |  | 2025-03-01
MSC | 175 | PSS-10 | AGE26BL | WTG 458 | Precast | F1 | Sarita infra | Done | 546087 | 2666295 | 2024-05-23 | 2024-06-21 |  | 2024-05-23 | 2024-06-21 |  | 253 | 253 | 2024-12-03 | 2024-12-10 |  | 2024-12-19 | 2024-12-30 | 12 | [8 empty] | 2024-12-21 | 2024-12-22 |  | 2025-02-05 | 2025-02-07 | 3 |  | 2024-12-23 | 2024-12-24 |  | 2025-02-07 | 2025-02-08 | 2 |  | 2024-12-25 | 2024-12-25 |  | 2025-02-08 | 2025-02-08 | 1 |  | 2024-12-26 | 2024-12-27 |  | 2025-02-09 | 2025-02-09 | 1 |  | 2024-12-28 | 2025-01-04 |  | 2025-02-09 | 2025-02-13 | 5 |  | 2025-01-05 | 2025-01-06 |  | 2025-02-14 | 2025-02-14 | 1 | 10 |  | 2025-01-08 | 2025-01-15 |  | 2025-02-20 | 2025-06-17 | 118 |  | 2025-01-08 | 2025-01-15 |  | 2025-02-26 | 2025-02-26 | 1 |  |  |  | 2025-01-01 | 2025-01-18 |  | 2025-02-06 | 2025-02-11 | 6 |  | 2024-01-29 | 2025-02-04 |  | Completed | Completed | #VALUE! |  | 2025-02-17 | 2025-02-22 |  | 2025-02-14 | 2025-03-02 | 17 |  | Odhav | 2025-02-23 | 2025-03-01 |  | 2025-02-12 | 2025-02-28 | 17 |  | 2025-03-08 | 2025-03-16 |  | 2025-03-09 | 2025-04-23 | 46 |  | 2025-01-20 | 2025-01-28 |  | 2025-04-04 | 2025-04-15 | 12 |  | 2025-03-18 | 2025-03-23 |  | 2025-04-28 | 2025-05-05 | 8 |  | 2025-03-24 | 2025-03-27 |  | 2025-05-06 | 2025-05-07 | 2 |  | 2025-01-30 | 2025-02-01 |  | 2025-04-16 | 2025-04-16 | 1 |  | 2025-02-26 | 2025-03-05 |  | 2025-03-18 | 2025-05-01 | 45 |  | 2025-03-05 | 2025-03-20 |  | 2025-02-28 | 2025-03-17 | 18 |  | 2025-03-05 | 2025-03-08 |  | 2025-05-01 | 2025-05-06 | 6 |  | 2025-03-27 | 2025-03-28 |  | 2025-06-28 | 2025-06-28 | 1 |  |  | 2025-03-01
SHREEJI | 176 | PSS-10 | AGE26BL | WTG 459 | Precast | F1 | Sarita infra | Done | 546278 | 2665308 | 2024-05-14 | 2024-05-17 |  | 2024-05-14 | 2024-05-17 |  | 199 | 199 | 2024-12-01 | 2024-12-08 |  | 2024-11-30 | 2024-12-11 | 12 | [8 empty] | 2024-12-19 | 2024-12-20 |  | 2025-01-07 | 2025-01-13 | 7 |  | 2024-12-21 | 2024-12-22 |  | 2025-01-19 | 2025-01-22 | 4 |  | 2024-12-23 | 2024-12-23 |  | 2025-01-22 | 2025-01-22 | 1 |  | 2024-12-24 | 2024-12-25 |  | 2025-01-25 | 2025-01-25 | 1 |  | 2024-12-26 | 2025-01-02 |  | 2025-01-26 | 2025-02-02 | 8 |  | 2025-01-03 | 2025-01-04 |  | 2025-02-03 | 2025-02-04 | 2 | 29 |  | 2025-01-06 | 2025-01-13 |  | 2025-02-18 | 2025-04-29 | 71 |  | 2025-01-06 | 2025-01-13 |  | 2025-02-09 | 2025-02-09 | 1 |  |  |  | 2024-12-30 | 2025-01-16 |  | 2025-02-02 | 2025-02-11 | 10 |  | 2025-01-28 | 2025-02-03 |  | 2025-02-07 | 2025-02-18 | 12 |  | 2025-02-16 | 2025-02-21 |  | 2025-02-18 | 2025-03-10 | 21 |  | Odhav | 2025-02-22 | 2025-02-28 |  | 2025-02-18 | 2025-02-27 | 10 |  | 2025-03-07 | 2025-03-15 |  | 2025-03-19 | 2025-04-01 | 14 |  | 2025-01-18 | 2025-01-26 |  | 2025-04-10 | 2025-04-17 | 8 |  | 2025-03-17 | 2025-03-22 |  | 2025-04-04 | 2025-04-26 | 23 |  | 2025-03-23 | 2025-03-26 |  | 2025-04-27 | 2025-04-30 | 4 |  | 2025-01-28 | 2025-01-30 |  | 2025-04-28 | 2025-04-28 | 1 |  | 2025-02-25 | 2025-03-04 |  | 2025-03-22 | 2025-04-22 | 32 |  | 2025-03-05 | 2025-03-20 |  | 2025-02-28 | 2025-03-17 | 18 |  | 2025-03-04 | 2025-03-07 |  | 2025-05-01 | 2025-05-30 | 30 |  | 2025-03-26 | 2025-03-27 |  | 2025-06-28 | 2025-06-28 | 1 |  |  | 2025-03-01
C & B | 177 | PSS-10 | AGE26BL | WTG 483 | Precast | F2 | Sarita infra | Done | 546921 | 2666030 | 2024-05-23 | 2024-06-21 |  | 2024-05-23 | 2024-06-21 |  | 199 | 199 | 2024-11-30 | 2024-12-07 |  | 2024-11-11 | 2024-11-21 | 11 | [8 empty] | 2024-12-17 | 2024-12-18 |  | 2024-12-10 | 2024-12-12 | 3 |  | 2024-12-19 | 2024-12-20 |  | 2024-12-14 | 2024-12-21 | 8 |  | 2024-12-21 | 2024-12-21 |  | 2024-12-21 | 2024-12-22 | 2 |  | 2024-12-22 | 2024-12-23 |  | 2024-12-27 | 2024-12-30 | 4 |  | 2024-12-24 | 2024-12-31 |  | 2025-01-02 | 2025-01-22 | 21 |  | 2025-01-01 | 2025-01-02 |  | 2025-01-23 | 2025-01-24 | 2 | 46 |  | 2025-01-04 | 2025-01-11 |  | 2025-02-13 | 2025-04-06 | 53 |  | 2025-01-04 | 2025-01-11 |  | 2025-02-08 | 2025-02-08 | 1 |  |  |  | 2024-12-28 | 2025-01-14 |  | 2025-01-02 | 2025-03-16 | 74 |  | 2025-01-28 | 2025-02-03 |  | Completed | Completed | #VALUE! |  | 2025-02-16 | 2025-02-21 |  | 2025-02-02 | 2025-02-18 | 17 |  | Odhav | 2025-02-22 | 2025-02-28 |  | 2025-01-22 | 2025-02-15 | 25 |  | 2025-03-07 | 2025-03-15 |  | 2025-02-19 | 2025-03-03 | 13 |  | 2025-01-16 | 2025-01-24 |  | 2025-03-28 | 2025-04-11 | 15 |  | 2025-03-17 | 2025-03-22 |  | 2025-03-31 | 2025-04-05 | 6 |  | 2025-03-23 | 2025-03-26 |  | 2025-04-06 | 2025-04-12 | 7 | hold due to ES required (self test not done) | 2025-01-26 | 2025-01-28 |  | 2025-04-24 | 2025-04-24 | 1 |  | 2025-02-25 | 2025-03-04 |  | 2025-03-24 | 2025-04-15 | 23 |  | 2025-03-05 | 2025-03-20 |  | 2025-02-28 | 2025-03-17 | 18 |  | 2025-03-04 | 2025-03-07 |  | 2025-05-01 | 2025-05-08 | 8 |  | 2025-03-26 | 2025-03-27 |  | 2025-06-05 | 2025-06-05 | 1 |  |  | 2025-03-01
C & B | 178 | PSS-10 | AGE26BL | WTG 484 | Precast | F2 | Sarita infra | Done | 547112 | 2665044 | 2024-05-15 | 2024-05-18 |  | 2024-05-15 | 2024-05-18 |  | 253 | 253 | 2024-11-29 | 2024-12-05 |  | 2024-11-22 | 2024-11-28 | 7 | [8 empty] | 2024-12-15 | 2024-12-16 |  | 2024-12-23 | 2024-12-27 | 5 |  | 2024-12-17 | 2024-12-18 |  | 2024-12-27 | 2024-12-28 | 2 |  | 2024-12-19 | 2024-12-19 |  | 2025-01-05 | 2025-01-05 | 1 |  | 2024-12-20 | 2024-12-21 |  | 2025-01-21 | 2025-01-21 | 1 |  | 2024-12-22 | 2024-12-29 |  | 2025-01-24 | 2025-02-09 | 17 |  | 2024-12-30 | 2024-12-31 |  | 2025-02-09 | 2025-02-10 | 2 | 50 |  | 2025-01-02 | 2025-01-09 |  | 2025-02-15 | 2025-04-20 | 65 |  | 2025-01-02 | 2025-01-09 |  | 2025-02-25 | 2025-02-25 | 1 |  |  |  | 2024-12-26 | 2025-01-12 |  | 2025-01-02 | 2025-03-11 | 69 |  | 2025-01-27 | 2025-02-02 |  | Completed | Completed | #VALUE! |  | 2025-02-15 | 2025-02-20 |  | 2025-02-02 | 2025-02-14 | 13 |  | Odhav | 2025-02-21 | 2025-02-27 |  | 2025-02-02 | 2025-02-17 | 16 |  | 2025-03-06 | 2025-03-14 |  | 2025-03-05 | 2025-03-17 | 13 |  | 2025-01-14 | 2025-01-22 |  | 2025-03-23 | 2025-04-01 | 10 |  | 2025-03-16 | 2025-03-21 |  | 2025-04-03 | 2025-04-13 | 11 |  | 2025-03-22 | 2025-03-25 |  | 2025-04-13 | 2025-04-15 | 3 |  | 2025-01-24 | 2025-01-26 |  | 2025-04-27 | 2025-04-27 | 1 |  | 2025-02-24 | 2025-03-03 |  | 2025-02-26 | 2025-04-20 | 54 |  | 2025-03-05 | 2025-03-20 |  | 2025-02-28 | 2025-03-17 | 18 |  | 2025-03-03 | 2025-03-06 |  | 2025-05-01 | 2025-05-06 | 6 |  | 2025-03-25 | 2025-03-26 |  | 2025-06-05 | 2025-06-05 | 1 |  |  | 2025-03-01
SHREEJI | 179 | PSS-10 | AGE26BL | WTG 506 | Precast | F2 | Sarita infra | Done | 547763 | 2665726 | 2024-05-22 | 2024-06-09 |  | 2024-05-22 | 2024-06-09 |  | 199 | 199 | 2024-11-27 | 2024-12-02 |  | 2024-11-04 | 2024-11-10 | 7 |  | Yes | 2024-12-10 | 2024-12-25 |  | 2025-02-15 | 2025-02-27 |  | 2024-12-13 | 2024-12-14 |  | 2025-03-03 | 2025-03-06 | 4 |  | 2024-12-15 | 2024-12-16 |  | 2025-03-07 | 2025-03-07 | 1 |  | 2024-12-17 | 2024-12-17 |  | 2025-03-08 | 2025-03-08 | 1 |  | 2024-12-18 | 2024-12-19 |  | 2025-03-10 | 2025-03-10 | 1 |  | 2024-12-20 | 2024-12-27 |  | 2025-03-11 | 2025-03-17 | 7 |  | 2024-12-28 | 2024-12-29 |  | 2025-03-17 | 2025-03-18 | 2 | 16 |  | 2024-12-31 | 2025-01-07 |  | 2025-03-25 | 2025-04-08 | 15 |  | 2024-12-31 | 2025-01-07 |  | 2025-03-22 | 2025-03-22 | 1 |  |  |  | 2024-12-24 | 2025-01-10 |  | 2025-03-08 | 2025-03-23 | 16 |  | 2025-01-27 | 2025-02-02 |  | Completed | Completed | #VALUE! |  | 2025-02-15 | 2025-02-20 |  | 2025-02-11 | 2025-02-19 | 9 |  | Odhav | 2025-02-21 | 2025-02-27 |  | 2025-02-12 | 2025-02-19 | 8 |  | 2025-03-06 | 2025-03-14 |  | 2025-04-23 | 2025-05-15 | 23 |  | 2025-01-12 | 2025-01-20 |  | 2025-03-28 | 2025-04-03 | 7 |  | 2025-03-16 | 2025-03-21 |  | 2025-05-18 | 2025-05-28 | 11 |  | 2025-03-22 | 2025-03-25 |  | 2025-05-29 | 2025-05-29 | 1 |  | 2025-01-22 | 2025-01-24 |  | 2025-04-24 | 2025-04-24 | 1 |  | 2025-02-24 | 2025-03-03 |  | 2025-03-23 | 2025-04-30 | 39 |  | 2025-03-05 | 2025-03-20 |  | 2025-02-28 | 2025-03-17 | 18 |  | 2025-03-03 | 2025-03-06 |  | 2025-05-01 | 2025-05-06 | 6 |  | 2025-03-25 | 2025-03-26 |  | 2025-06-06 | 2025-06-06 | 1 |  |  | 2025-03-01
BPS | 180 | PSS-10 | AGE26BL | WTG 507 | Precast | F2 | Sarita infra | Done | 547954 | 2664740 | 2024-05-23 | 2024-06-09 |  | 2024-05-23 | 2024-06-09 |  | 253 | 253 | 2024-11-23 | 2024-11-30 |  | 2024-11-28 | 2024-12-07 | 10 | [8 empty] | 2024-12-11 | 2024-12-12 |  | 2025-01-05 | 2025-01-09 | 5 |  | 2024-12-13 | 2024-12-14 |  | 2025-01-29 | 2025-02-03 | 6 |  | 2024-12-15 | 2024-12-15 |  | 2025-02-07 | 2025-02-07 | 1 |  | 2024-12-16 | 2024-12-17 |  | 2025-02-15 | 2025-02-15 | 1 |  | 2024-12-18 | 2024-12-25 |  | 2025-02-16 | 2025-03-03 | 16 |  | 2024-12-26 | 2024-12-27 |  | 2025-03-05 | 2025-03-06 | 2 | 61 |  | 2024-12-29 | 2025-01-05 |  | 2025-03-26 | 2025-07-04 | 101 |  | 2024-12-29 | 2025-01-05 |  | 2025-03-21 | 2025-03-21 | 1 |  |  |  | 2024-12-22 | 2025-01-08 |  | 2025-03-22 | 2025-04-06 | 16 |  | 2025-01-26 | 2025-02-01 |  | 2025-02-10 | 2025-03-03 | 22 |  | 2025-02-14 | 2025-02-19 |  | Completed | Completed | #VALUE! |  | Odhav (Reuse) | 2025-02-20 | 2025-02-26 |  | 2025-03-02 | 2025-03-18 | 17 |  | 2025-03-05 | 2025-03-13 |  | 2025-03-30 | 2025-04-21 | 23 |  | 2025-01-10 | 2025-01-18 |  | 2025-04-03 | 2025-04-21 | 19 |  | 2025-03-15 | 2025-03-20 |  | 2025-04-21 | 2025-04-28 | 8 |  | 2025-03-21 | 2025-03-24 |  | 2025-04-29 | 2025-04-30 | 2 |  | 2025-01-20 | 2025-01-22 |  | 2025-04-22 | 2025-04-22 | 1 |  | 2025-02-23 | 2025-03-02 |  | 2025-02-25 | 2025-04-21 | 56 |  | 2025-03-05 | 2025-03-20 |  | 2025-02-28 | 2025-03-17 | 18 |  | 2025-03-02 | 2025-03-05 |  | 2025-05-01 | 2025-05-06 | 6 |  | 2025-03-24 | 2025-03-25 |  | 2025-06-05 | 2025-06-05 | 1 |  |  | 2025-03-01
UNIQUE INF | 181 | PSS-4 | ACL | WTG 101 | Precast | F2 | Bauer | Done | 532357 | 2676691 | 2024-05-03 | 2024-05-16 |  | 2024-05-03 | 2024-05-16 |  | 253 | 253 | 2024-10-19 | 2024-10-28 |  | 2025-01-16 | 2025-01-23 | 8 | [8 empty] | 2024-11-13 | 2024-11-13 |  | 2025-01-31 | 2025-02-05 | 6 |  | 2024-11-14 | 2024-11-14 |  | 2025-02-05 | 2025-02-08 | 4 |  | 2024-11-15 | 2024-11-15 |  | 2025-02-08 | 2025-02-08 | 1 |  | 2024-11-16 | 2024-11-17 |  | 2025-02-12 | 2025-02-12 | 1 |  | 2024-11-19 | 2024-11-28 |  | 2025-02-12 | 2025-02-22 | 11 |  | 2024-11-30 | 2024-12-01 |  | 2025-02-26 | 2025-02-26 | 1 | 27 |  | 2024-12-02 | 2024-12-08 |  | 2025-04-01 | 2025-05-31 | 61 |  | 2024-12-02 | 2024-12-08 |  | 2025-03-08 | 2025-03-08 | 1 |  |  |  | 2024-11-26 | 2024-12-10 |  | 2025-02-08 | 2025-02-28 | 21 |  | 2024-12-01 | 2024-12-07 |  | 2025-01-26 | 2025-04-03 | 68 |  | 2024-12-01 | 2024-12-07 |  | Completed | Completed | #VALUE! |  | Varudi (Reuse) | 2024-12-08 | 2024-12-14 |  | 2025-01-30 | 2025-04-07 | 68 | Reuse loc & also approach road work delay | 2024-12-25 | 2024-12-30 |  | 2025-04-08 | 2025-04-24 | 17 |  | 2024-12-21 | 2024-12-27 |  | 2025-03-07 | 2025-03-28 | 22 |  | 2025-01-02 | 2025-01-11 |  | 2025-05-25 | 2025-05-29 | 5 |  | 2025-01-13 | 2025-01-15 |  | 2025-05-30 | 2025-06-01 | 3 |  | 2025-01-02 | 2025-01-03 |  | 2025-04-03 | 2025-04-03 | 1 |  | 2024-12-14 | 2024-12-20 |  | 2024-12-05 | 2025-01-20 | 47 |  | 2024-11-20 | 2024-12-05 |  | 2025-02-26 | 2025-03-17 | 20 |  | 2025-01-03 | 2025-01-06 |  | 2025-05-26 | 2025-06-08 | 14 |  | 2025-01-15 | 2025-01-16 |  | 2025-06-23 | 2025-06-23 | 1 |  |  | 2025-03-01
UNIQUE INF | 182 | PSS-4 | AHEJ5L | WTG 538 | Precast | F3 | Bauer | Done | 528834 | 2674442 | 2024-05-22 | 2024-05-31 |  | 2024-05-22 | 2024-05-31 |  | 253 | 253 | 2024-10-20 | 2024-10-29 |  | 2024-12-10 | 2024-12-18 | 9 |  | Yes | 2024-11-05 | 2024-11-20 |  | 2025-01-05 | 2025-02-24 |  | 2024-11-14 | 2024-11-14 |  | 2025-03-05 | 2025-03-06 | 2 |  | 2024-11-15 | 2024-11-15 |  | 2025-03-06 | 2025-03-08 | 3 |  | 2024-11-16 | 2024-11-16 |  | 2025-03-09 | 2025-03-09 | 1 |  | 2024-11-17 | 2024-11-18 |  | 2025-03-15 | 2025-03-15 | 1 |  | 2024-11-20 | 2024-11-29 |  | 2025-03-15 | 2025-03-26 | 12 |  | 2024-12-01 | 2024-12-02 |  | 2025-03-27 | 2025-03-28 | 2 | 24 |  | 2024-12-03 | 2024-12-09 |  | 2025-04-03 | 2025-05-06 | 34 |  | 2024-12-03 | 2024-12-09 |  | 2025-04-03 | 2025-04-03 | 1 |  |  |  | 2024-11-27 | 2024-12-11 |  | 2025-03-22 | 2025-04-06 | 16 |  | 2024-12-02 | 2024-12-08 |  | 2025-01-05 | 2025-01-16 | 12 |  | 2024-12-02 | 2024-12-08 |  | 2025-03-28 | 2025-04-08 | 12 |  | HARSH (Reuse) | 2024-12-09 | 2024-12-15 |  | 2025-01-09 | 2025-04-08 | 90 |  | 2024-12-26 | 2024-12-31 |  | 2025-05-02 | 2025-06-05 | 35 |  | 2024-12-22 | 2024-12-28 |  | 2025-04-08 | 2025-04-16 | 9 |  | 2025-01-03 | 2025-01-12 |  | 2025-06-06 | 2025-06-11 | 6 |  | 2025-01-14 | 2025-01-16 |  | 2025-06-14 | 2025-06-18 | 5 |  | 2025-01-03 | 2025-01-04 |  | 2025-05-22 | 2025-05-22 | 1 |  | 2024-12-21 | 2024-12-27 |  | 2024-12-07 | 2025-01-22 | 47 |  | 2024-11-20 | 2024-12-05 |  | 2025-01-01 | 2025-02-06 | 37 |  | 2025-01-04 | 2025-01-07 |  | 2025-06-08 | 2025-06-16 | 9 |  | 2025-01-16 | 2025-01-17 |  | 2025-06-24 | 2025-06-24 | 1 |  |  | 2025-03-01
UNIQUE INF | 183 | PSS-4 | AHEJ5L | WTG 540 | Precast | F3 | Bauer | Done | 529055 | 2673449 | 2024-05-07 | 2024-05-18 |  | 2024-05-07 | 2024-05-18 |  | 199 | 199 | 2024-10-21 | 2024-10-30 |  | 2024-12-05 | 2024-12-09 | 5 | [8 empty] | 2024-11-15 | 2024-11-15 |  | 2024-12-12 | 2024-12-15 | 4 |  | 2024-11-16 | 2024-11-16 |  | 2024-12-24 | 2024-12-26 | 3 |  | 2024-11-17 | 2024-11-17 |  | 2024-12-29 | 2024-12-29 | 1 |  | 2024-11-18 | 2024-11-19 |  | 2025-01-10 | 2025-01-11 | 2 |  | 2024-11-21 | 2024-11-30 |  | 2025-01-11 | 2025-01-17 | 7 |  | 2024-12-02 | 2024-12-03 |  | 2025-01-20 | 2025-01-21 | 2 | 41 |  | 2024-12-04 | 2024-12-10 |  | 2025-01-24 | 2025-04-24 | 91 |  | 2024-12-04 | 2024-12-10 |  | 2025-01-25 | 2025-01-25 | 1 |  |  |  | 2024-11-28 | 2024-12-12 |  | 2025-02-13 | 2025-02-24 | 12 |  | 2024-12-03 | 2024-12-09 |  | 2024-11-22 | 2025-01-15 | 55 |  | 2024-12-03 | 2024-12-09 |  | 2025-02-07 | 2025-02-19 | 13 |  | HARSH | 2024-12-10 | 2024-12-16 |  | 2025-01-17 | 2025-02-10 | 25 |  | 2024-12-27 | 2025-01-01 |  | 2025-02-22 | 2025-03-06 | 13 |  | 2024-12-28 | 2025-01-03 |  | 2025-03-28 | 2025-04-01 | 5 |  | 2025-01-04 | 2025-01-13 |  | 2025-03-26 | 2025-03-30 | 5 |  | 2025-01-15 | 2025-01-17 |  | 2025-04-02 | 2025-04-04 | 3 |  | 2025-01-09 | 2025-01-10 |  | 2025-04-02 | 2025-04-02 | 1 |  | 2024-12-22 | 2024-12-28 |  | 2024-12-13 | 2025-02-25 | 75 |  | 2025-01-03 | 2025-01-18 |  | 2025-01-01 | 2025-02-06 | 37 |  | 2025-01-10 | 2025-01-13 |  | 2025-04-04 | 2025-04-15 | 12 |  | 2025-01-18 | 2025-01-19 |  | 2025-04-17 | 2025-04-17 | 1 |  |  | 2025-03-01
BALAJI & Co | 184 | PSS-4 | AHEJ5L | WTG 537 | Precast | F3 | Bauer | Done | 527896 | 2674802 | 2024-06-05 | 2024-06-21 |  | 2024-06-05 | 2024-06-21 |  | 253 | 253 | 2024-10-30 | 2024-11-08 |  | 2024-12-30 | 2025-01-06 | 8 | [8 empty] | 2024-11-24 | 2024-11-24 |  | 2025-01-14 | 2025-01-24 | 11 |  | 2024-11-25 | 2024-11-25 |  | 2025-01-24 | 2025-01-27 | 4 |  | 2024-11-26 | 2024-11-26 |  | 2025-01-27 | 2025-01-27 | 1 |  | 2024-11-27 | 2024-11-28 |  | 2025-01-28 | 2025-01-28 | 1 |  | 2024-11-30 | 2024-12-09 |  | 2025-01-29 | 2025-02-03 | 6 |  | 2024-12-11 | 2024-12-12 |  | 2025-02-04 | 2025-02-05 | 2 | 23 |  | 2024-12-13 | 2024-12-19 |  | 2025-02-20 | 2025-04-08 | 48 |  | 2024-12-13 | 2024-12-19 |  | 2025-02-10 | 2025-02-10 | 1 |  |  |  | 2024-12-07 | 2024-12-21 |  | 2025-02-14 | 2025-02-24 | 11 |  | 2024-12-14 | 2024-12-20 |  | 2024-11-11 | 2025-01-25 | 76 |  | 2024-12-14 | 2024-12-20 |  | 2025-02-10 | 2025-02-28 | 19 |  | HARSH | 2024-12-21 | 2024-12-27 |  | 2025-01-11 | 2025-02-19 | 40 | Due to wet surface | 2025-01-02 | 2025-01-07 |  | 2025-03-08 | 2025-03-31 | 24 |  | 2024-12-29 | 2025-01-04 |  | 2025-03-06 | 2025-03-27 | 22 |  | 2025-01-10 | 2025-01-19 |  | 2025-03-28 | 2025-04-08 | 12 |  | 2025-01-21 | 2025-01-23 |  | 2025-04-08 | 2025-04-12 | 5 | Hold due to lift cable damage | 2025-01-10 | 2025-01-11 |  | 2025-04-03 | 2025-04-03 | 1 |  | 2024-12-23 | 2024-12-29 |  | 2024-12-06 | 2025-01-07 | 33 |  | 2025-01-03 | 2025-01-18 |  | 2025-01-01 | 2025-02-06 | 37 |  | 2025-01-11 | 2025-01-14 |  | 2025-04-04 | 2025-04-15 | 12 |  | 2025-01-23 | 2025-01-24 |  | 2025-04-17 | 2025-04-17 | 1 |  |  | 2025-03-01
DNC | 185 | PSS-4 | ARE41L | WTG 539 | Precast | F7 | Bauer | Done | 528039 | 2673689 | 2024-05-26 | 2024-06-21 |  | 2024-05-26 | 2024-06-21 |  | 253 | 253 | 2024-10-31 | 2024-11-09 |  | 2024-12-19 | 2024-12-30 | 12 | [8 empty] | 2024-11-25 | 2024-11-25 |  | 2025-01-14 | 2025-01-18 | 5 |  | 2024-11-26 | 2024-11-26 |  | 2025-01-19 | 2025-01-20 | 2 |  | 2024-11-27 | 2024-11-27 |  | 2025-01-21 | 2025-01-21 | 1 |  | 2024-11-28 | 2024-11-29 |  | 2025-01-22 | 2025-01-22 | 1 |  | 2024-12-01 | 2024-12-10 |  | 2025-01-23 | 2025-01-27 | 5 |  | 2024-12-12 | 2024-12-13 |  | 2025-01-28 | 2025-01-28 | 1 | 15 |  | 2024-12-14 | 2024-12-20 |  | 2025-02-07 | 2025-03-30 | 52 |  | 2024-12-14 | 2024-12-20 |  | 2025-02-07 | 2025-02-07 | 1 |  |  |  | 2024-12-08 | 2024-12-22 |  | 2025-01-23 | 2025-02-23 | 32 |  | 2024-12-15 | 2024-12-21 |  | 2024-11-28 | 2025-01-25 | 59 |  | 2024-12-15 | 2024-12-21 |  | 2025-02-02 | 2025-02-13 | 12 |  | HARSH | 2024-12-22 | 2024-12-28 |  | 2025-01-07 | 2025-02-04 | 29 |  | 2025-01-03 | 2025-01-08 |  | 2025-02-25 | 2025-03-07 | 11 |  | 2024-12-30 | 2025-01-05 |  | 2025-02-27 | 2025-03-19 | 21 |  | 2025-01-11 | 2025-01-20 |  | 2025-03-10 | 2025-03-21 | 12 |  | 2025-01-22 | 2025-01-24 |  | 2025-03-21 | 2025-03-23 | 3 |  | 2025-01-11 | 2025-01-12 |  | 2025-03-17 | 2025-03-17 | 1 |  | 2024-12-29 | 2025-01-04 |  | 2024-12-08 | 2025-01-20 | 44 |  | 2025-01-03 | 2025-01-18 |  | 2025-01-01 | 2025-02-06 | 37 |  | 2025-01-12 | 2025-01-15 |  | 2025-03-20 | 2025-03-22 | 3 |  | 2025-01-24 | 2025-01-25 |  | 2025-03-23 | 2025-03-23 | 1 |  |  | 2025-03-01
MSC | 186 | PSS-4 | ARE41L | WTG 541 | Precast | F7 | Bauer | Done | 528160 | 2672746 | 2024-05-07 | 2024-05-18 |  | 2024-05-07 | 2024-05-18 |  | 199 | 199 | 2024-10-19 | 2024-10-28 |  | 2024-11-18 | 2024-11-30 | 13 |  | Yes | 2024-12-30 | 2025-01-08 |  | 2024-12-19 | 2025-01-13 |  | 2024-11-13 | 2024-11-13 |  | 2025-01-17 | 2025-01-19 | 3 |  | 2024-11-14 | 2024-11-14 |  | 2025-01-20 | 2025-01-21 | 2 |  | 2024-11-15 | 2024-11-15 |  | 2025-01-21 | 2025-01-21 | 1 |  | 2024-11-16 | 2024-11-17 |  | 2025-01-23 | 2025-01-23 | 1 |  | 2024-11-19 | 2024-11-26 |  | 2025-01-24 | 2025-01-27 | 4 |  | 2024-11-29 | 2024-11-30 |  | 2025-01-27 | 2025-01-28 | 2 | 12 |  | 2024-12-01 | 2024-12-07 |  | 2025-02-04 | 2025-03-11 | 36 |  | 2024-12-01 | 2024-12-07 |  | 2025-02-02 | 2025-02-02 | 1 |  |  |  | 2024-11-26 | 2024-12-10 |  | 2025-01-21 | 2025-02-21 | 32 |  | 2024-12-08 | 2024-12-14 |  | 2024-11-10 | 2025-01-11 | 63 |  | 2024-12-08 | 2024-12-14 |  | 2025-01-22 | 2025-01-31 | 10 |  | SS Jadeja | 2024-12-08 | 2024-12-14 |  | 2025-01-13 | 2025-01-24 | 12 |  | 2024-12-22 | 2024-12-27 |  | 2025-02-07 | 2025-02-20 | 14 |  | 2024-12-21 | 2024-12-27 |  | 2025-03-01 | 2025-03-10 | 10 |  | 2024-12-30 | 2025-01-08 |  | 2025-03-03 | 2025-03-13 | 11 |  | 2025-01-10 | 2025-01-12 |  | 2025-03-19 | 2025-03-20 | 2 |  | 2025-01-02 | 2025-01-03 |  | 2025-03-11 | 2025-03-11 | 1 |  | 2024-12-12 | 2024-12-18 |  | 2024-12-18 | 2025-02-09 | 54 |  | 2024-11-20 | 2024-12-05 |  | 2025-02-26 | 2025-03-17 | 20 |  | 2025-01-03 | 2025-01-06 |  | 2025-03-20 | 2025-03-21 | 2 |  | 2025-01-12 | 2025-01-13 |  | 2025-03-21 | 2025-03-23 | 3 |  |  | 2025-03-01
MECC | 187 | PSS-4 | ARE41L | WTG 542 | Precast | F7 | Bauer | Done | 528281 | 2671843 | 2024-05-26 | 2024-06-02 |  | 2024-05-26 | 2024-06-02 |  | 253 | 253 | 2024-10-20 | 2024-10-29 |  | 2024-12-02 | 2024-12-13 | 12 | [8 empty] | 2024-11-14 | 2024-11-14 |  | 2024-12-16 | 2024-12-20 | 5 |  | 2024-11-15 | 2024-11-15 |  | 2024-12-23 | 2024-12-24 | 2 |  | 2024-11-16 | 2024-11-16 |  | 2024-12-24 | 2024-12-24 | 1 |  | 2024-11-17 | 2024-11-18 |  | 2024-12-27 | 2024-12-27 | 1 |  | 2024-11-20 | 2024-11-27 |  | 2025-01-02 | 2025-01-14 | 13 |  | 2024-11-30 | 2024-12-01 |  | 2025-01-14 | 2025-01-15 | 2 | 31 |  | 2024-12-02 | 2024-12-08 |  | 2025-01-20 | 2025-04-05 | 76 |  | 2024-12-02 | 2024-12-08 |  | 2025-01-27 | 2025-01-27 | 1 |  |  |  | 2024-11-27 | 2024-12-11 |  | 2024-12-21 | 2025-02-19 | 61 |  | 2024-12-09 | 2024-12-15 |  | 2024-11-11 | 2025-01-07 | 58 |  | 2024-12-09 | 2024-12-15 |  | 2025-01-15 | 2025-01-30 | 16 |  | SS Jadeja | 2024-12-09 | 2024-12-15 |  | 2025-01-15 | 2025-02-10 | 27 |  | 2024-12-23 | 2024-12-28 |  | 2025-02-25 | 2025-03-06 | 10 |  | 2024-12-22 | 2024-12-28 |  | 2025-02-28 | 2025-03-13 | 14 |  | 2024-12-31 | 2025-01-09 |  | 2025-03-13 | 2025-03-19 | 7 |  | 2025-01-11 | 2025-01-13 |  | 2025-03-21 | 2025-03-21 | 1 |  | 2025-01-03 | 2025-01-04 |  | 2025-03-11 | 2025-03-11 | 1 |  | 2024-12-13 | 2024-12-19 |  | 2024-12-10 | 2024-12-17 | 8 |  | 2024-11-20 | 2024-12-05 |  | 2025-02-26 | 2025-03-17 | 20 |  | 2025-01-04 | 2025-01-07 |  | 2025-03-20 | 2025-03-21 | 2 |  | 2025-01-13 | 2025-01-14 |  | 2025-03-21 | 2025-03-23 | 3 |  |  | 2025-03-01
MSC | 188 | PSS-4 | ARE41L | WTG 543 | Precast | F7 | Bauer | Done | 528071 | 2670633 | 2024-05-24 | 2024-06-03 |  | 2024-05-24 | 2024-06-03 |  | 253 | 253 | 2024-10-21 | 2024-10-30 |  | 2024-12-13 | 2024-12-19 | 7 | [8 empty] | 2024-11-15 | 2024-11-15 |  | 2024-12-29 | 2024-12-31 | 3 |  | 2024-11-16 | 2024-11-16 |  | 2024-12-31 | 2025-01-01 | 2 |  | 2024-11-17 | 2024-11-17 |  | 2025-01-01 | 2025-01-01 | 1 |  | 2024-11-18 | 2024-11-19 |  | 2025-01-04 | 2025-01-04 | 1 |  | 2024-11-21 | 2024-11-28 |  | 2025-01-04 | 2025-01-08 | 5 |  | 2024-12-01 | 2024-12-02 |  | 2025-01-10 | 2025-01-10 | 1 | 13 |  | 2024-12-03 | 2024-12-09 |  | 2025-01-15 | 2025-03-11 | 56 |  | 2024-12-03 | 2024-12-09 |  | 2025-01-18 | 2025-01-18 | 1 |  |  |  | 2024-11-28 | 2024-12-12 |  | 2025-01-01 | 2025-02-20 | 51 |  | 2024-12-10 | 2024-12-16 |  | 2024-11-15 | 2025-01-04 | 51 |  | 2024-12-10 | 2024-12-16 |  | 2025-01-27 | 2025-02-05 | 10 |  | SS Jadeja (Reuse) | 2024-12-10 | 2024-12-16 |  | 2025-02-03 | 2025-02-13 | 11 |  | 2024-12-24 | 2024-12-29 |  | 2025-02-14 | 2025-02-24 | 11 |  | 2024-12-23 | 2024-12-29 |  | 2025-02-28 | 2025-03-13 | 14 |  | 2025-01-01 | 2025-01-10 |  | 2025-03-04 | 2025-03-07 | 4 |  | 2025-01-12 | 2025-01-14 |  | 2025-03-08 | 2025-03-19 | 12 | Loc. Hold & start by 18 mar 24 | 2025-01-04 | 2025-01-05 |  | 2025-03-11 | 2025-03-11 | 1 |  | 2024-12-19 | 2024-12-25 |  | 2024-12-09 | 2024-12-19 | 11 |  | 2024-11-20 | 2024-12-05 |  | 2025-02-26 | 2025-03-17 | 20 |  | 2025-01-05 | 2025-01-08 |  | 2025-03-20 | 2025-03-21 | 2 |  | 2025-01-14 | 2025-01-15 |  | 2025-03-21 | 2025-03-22 | 2 |  |  | 2025-03-01
MSC | 189 | PSS-4 | ARE41L | WTG 544 | Precast | F7 | Bauer | Done | 529124 | 2669653 | 2024-05-25 | 2024-06-21 |  | 2024-05-25 | 2024-06-21 |  | 253 | 253 | 2024-10-22 | 2024-10-31 |  | 2024-12-19 | 2024-12-30 | 12 |  | Yes | 2024-11-12 | 2024-11-27 |  | 2025-01-13 | 2025-02-01 |  | 2024-11-16 | 2024-11-16 |  | 2025-02-06 | 2025-02-09 | 4 |  | 2024-11-17 | 2024-11-17 |  | 2025-02-09 | 2025-02-10 | 2 |  | 2024-11-18 | 2024-11-18 |  | 2025-02-10 | 2025-02-10 | 1 |  | 2024-11-19 | 2024-11-20 |  | 2025-02-12 | 2025-02-12 | 1 |  | 2024-11-22 | 2024-11-29 |  | 2025-02-13 | 2025-02-16 | 4 |  | 2024-12-02 | 2024-12-03 |  | 2025-02-17 | 2025-02-17 | 1 | 12 |  | 2024-12-04 | 2024-12-10 |  | 2025-02-25 | 2025-04-05 | 40 |  | 2024-12-04 | 2024-12-10 |  | 2025-03-01 | 2025-03-01 | 1 |  |  |  | 2024-11-29 | 2024-12-13 |  | 2025-02-11 | 2025-02-23 | 13 |  | 2024-12-11 | 2024-12-17 |  | 2024-11-19 | 2025-01-05 | 48 |  | 2024-12-11 | 2024-12-17 |  | 2025-02-10 | 2025-02-28 | 19 |  | SS Jadeja (Reuse) | 2024-12-11 | 2024-12-17 |  | 2025-02-10 | 2025-02-28 | 19 |  | 2024-12-25 | 2024-12-30 |  | 2025-03-03 | 2025-03-20 | 18 |  | 2024-12-24 | 2024-12-30 |  | 2025-03-05 | 2025-03-20 | 16 |  | 2025-01-02 | 2025-01-11 |  | 2025-03-22 | 2025-03-23 | 2 |  | 2025-01-13 | 2025-01-15 |  | 2025-03-23 | 2025-03-23 | 1 |  | 2025-01-05 | 2025-01-06 |  | 2025-03-22 | 2025-03-22 | 1 |  | 2024-12-20 | 2024-12-26 |  | 2024-12-09 | 2024-12-23 | 15 |  | 2024-11-20 | 2024-12-05 |  | 2025-02-26 | 2025-03-17 | 20 |  | 2025-01-06 | 2025-01-09 |  | 2025-03-20 | 2025-03-21 | 2 |  | 2025-01-15 | 2025-01-16 |  | 2025-03-23 | 2025-03-24 | 2 |  |  | 2025-03-01
MSC | 190 | PSS-4 | ARE41L | WTG 545 | Precast | F8 | Bauer | Done | 530202 | 2668348 | 2024-05-25 | 2024-05-26 |  | 2024-05-25 | 2024-06-15 |  | 253 | 253 | 2024-10-23 | 2024-11-01 |  | 2024-12-31 | 2025-01-07 | 8 | [8 empty] | 2024-11-17 | 2024-11-17 |  | 2025-01-10 | 2025-01-11 | 2 |  | 2024-11-18 | 2024-11-18 |  | 2025-01-11 | 2025-01-12 | 2 |  | 2024-11-19 | 2024-11-19 |  | 2025-01-12 | 2025-01-12 | 1 |  | 2024-11-20 | 2024-11-21 |  | 2025-01-14 | 2025-01-15 | 2 |  | 2024-11-23 | 2024-11-30 |  | 2025-01-26 | 2025-01-29 | 4 |  | 2024-12-03 | 2024-12-04 |  | 2025-01-30 | 2025-01-30 | 1 | 21 |  | 2024-12-05 | 2024-12-11 |  | 2025-02-04 | 2025-03-11 | 36 |  | 2024-12-05 | 2024-12-11 |  | 2025-02-05 | 2025-02-05 | 1 |  |  |  | 2024-11-30 | 2024-12-14 |  | 2025-01-15 | 2025-02-03 | 20 |  | 2024-12-12 | 2024-12-18 |  | 2024-11-19 | 2025-01-05 | 48 |  | 2024-12-12 | 2024-12-18 |  | 2025-01-22 | 2025-02-08 | 18 |  | SS Jadeja | 2024-12-12 | 2024-12-18 |  | 2025-01-15 | 2025-02-10 | 27 |  | 2024-12-26 | 2024-12-31 |  | 2025-02-20 | 2025-02-28 | 9 |  | 2024-12-25 | 2024-12-31 |  | 2025-02-06 | 2025-03-14 | 37 |  | 2025-01-03 | 2025-01-12 |  | 2025-03-04 | 2025-03-09 | 6 |  | 2025-01-14 | 2025-01-16 |  | 2025-03-07 | 2025-03-21 | 15 | Loc. Hold, start by 18 mar | 2025-01-06 | 2025-01-07 |  | 2025-03-11 | 2025-03-11 | 1 |  | 2024-12-26 | 2025-01-01 |  | 2024-12-07 | 2025-01-28 | 53 |  | 2024-11-20 | 2024-12-05 |  | 2025-02-26 | 2025-03-17 | 20 |  | 2025-01-07 | 2025-01-10 |  | 2025-03-21 | 2025-03-22 | 2 |  | 2025-01-16 | 2025-01-17 |  | 2025-03-23 | 2025-03-23 | 1 |  |  | 2025-03-01
MSC | 191 | PSS-4 | ARE41L | WTG 546 | Precast | F8 | Bauer | Done | 531377 | 2666842 | 2024-05-25 | 2024-06-21 |  | 2024-05-25 | 2024-06-21 |  | 253 | 253 | 2024-10-24 | 2024-11-02 |  | 2024-12-28 | 2025-01-08 | 12 | [8 empty] | 2024-11-18 | 2024-11-18 |  | 2025-01-12 | 2025-01-15 | 4 |  | 2024-11-19 | 2024-11-19 |  | 2025-01-15 | 2025-01-16 | 2 |  | 2024-11-20 | 2024-11-20 |  | 2025-01-16 | 2025-01-16 | 1 |  | 2024-11-21 | 2024-11-22 |  | 2025-01-17 | 2025-01-17 | 1 |  | 2024-11-24 | 2024-12-01 |  | 2025-01-18 | 2025-01-24 | 7 |  | 2024-12-04 | 2024-12-05 |  | 2025-01-26 | 2025-01-26 | 1 | 15 |  | 2024-12-06 | 2024-12-12 |  | 2025-01-29 | 2025-04-06 | 68 |  | 2024-12-06 | 2024-12-12 |  | 2025-02-01 | 2025-02-01 | 1 |  |  |  | 2024-12-01 | 2024-12-15 |  | 2025-01-15 | 2025-01-31 | 17 |  | 2024-12-13 | 2024-12-19 |  | 2024-11-20 | 2025-01-05 | 47 |  | 2024-12-13 | 2024-12-19 |  | 2025-01-27 | 2025-02-04 | 9 |  | GP (Reuse) | 2024-12-13 | 2024-12-19 |  | 2025-01-29 | 2025-02-15 | 18 |  | 2024-12-27 | 2025-01-01 |  | 2025-02-03 | 2025-03-19 | 45 |  | 2024-12-26 | 2025-01-01 |  | 2025-02-06 | 2025-03-09 | 32 |  | 2025-01-04 | 2025-01-13 |  | 2025-03-22 | 2025-03-23 | 2 |  | 2025-01-15 | 2025-01-17 |  | 2025-03-23 | 2025-03-23 | 1 |  | 2025-01-07 | 2025-01-08 |  | 2025-03-18 | 2025-03-18 | 1 |  | 2024-12-27 | 2025-01-02 |  | 2024-12-07 | 2024-12-29 | 23 |  | 2025-01-03 | 2025-01-18 |  | 2025-02-26 | 2025-03-17 | 20 |  | 2025-01-08 | 2025-01-11 |  | 2025-03-21 | 2025-03-22 | 2 |  | 2025-01-18 | 2025-01-19 |  | 2025-03-23 | 2025-03-24 | 2 |  |  | 2025-03-01
MECC | 192 | PSS-4 | ARE41L | WTG 547 | Precast | F8 | Bauer | Done | 532064 | 2665994 | 2024-05-26 | 2024-06-04 |  | 2024-05-26 | 2024-06-04 |  | 253 | 253 | 2024-10-25 | 2024-11-03 |  | 2024-12-20 | 2024-12-27 | 8 | [8 empty] | 2024-11-19 | 2024-11-19 |  | 2024-12-29 | 2025-01-02 | 5 |  | 2024-11-20 | 2024-11-20 |  | 2025-01-12 | 2025-01-12 | 1 |  | 2024-11-21 | 2024-11-21 |  | 2025-01-12 | 2025-01-12 | 1 |  | 2024-11-22 | 2024-11-23 |  | 2025-01-14 | 2025-01-14 | 1 |  | 2024-11-25 | 2024-12-02 |  | 2025-01-22 | 2025-02-01 | 11 |  | 2024-12-05 | 2024-12-06 |  | 2025-02-02 | 2025-02-03 | 2 | 37 |  | 2024-12-07 | 2024-12-13 |  | 2025-02-08 | 2025-04-05 | 57 |  | 2024-12-07 | 2024-12-13 |  | 2025-02-07 | 2025-02-07 | 1 |  |  |  | 2024-12-02 | 2024-12-16 |  | 2025-01-26 | 2025-02-02 | 8 |  | 2024-12-14 | 2024-12-20 |  | 2024-11-12 | 2025-01-05 | 55 |  | 2024-12-14 | 2024-12-20 |  | 2025-02-02 | 2025-02-12 | 11 |  | SS Jadeja | 2024-12-14 | 2024-12-20 |  | 2025-02-03 | 2025-02-16 | 14 |  | 2024-12-28 | 2025-01-02 |  | 2025-03-02 | 2025-03-11 | 10 |  | 2024-12-27 | 2025-01-02 |  | 2025-02-06 | 2025-03-14 | 37 |  | 2025-01-05 | 2025-01-14 |  | 2025-03-13 | 2025-03-21 | 9 |  | 2025-01-16 | 2025-01-18 |  | 2025-03-22 | 2025-03-23 | 2 |  | 2025-01-08 | 2025-01-09 |  | 2025-03-15 | 2025-03-15 | 1 |  | 2025-01-02 | 2025-01-08 |  | 2024-12-09 | 2025-01-12 | 35 |  | 2025-01-03 | 2025-01-18 |  | 2025-02-26 | 2025-03-17 | 20 |  | 2025-01-09 | 2025-01-12 |  | 2025-03-21 | 2025-03-22 | 2 |  | 2025-01-18 | 2025-01-19 |  | 2025-03-23 | 2025-03-23 | 1 |  |  | 2025-03-01
MSC | 193 | PSS-4 | ARE41L | WTG 548 | Precast | F8 | Bauer | Done | 532429 | 2665543 | 2024-05-24 | 2024-06-21 |  | 2024-05-24 | 2024-06-21 |  | 253 | 253 | 2024-10-26 | 2024-11-04 |  | 2024-12-13 | 2024-12-19 | 7 | [8 empty] | 2024-11-20 | 2024-11-20 |  | 2024-12-23 | 2024-12-26 | 4 |  | 2024-11-21 | 2024-11-21 |  | 2024-12-27 | 2024-12-28 | 2 |  | 2024-11-22 | 2024-11-22 |  | 2024-12-28 | 2024-12-28 | 1 |  | 2024-11-23 | 2024-11-24 |  | 2024-12-29 | 2024-12-29 | 1 |  | 2024-11-26 | 2024-12-03 |  | 2024-12-30 | 2025-01-04 | 6 |  | 2024-12-06 | 2024-12-07 |  | 2025-01-04 | 2025-01-05 | 2 | 14 |  | 2024-12-08 | 2024-12-14 |  | 2025-01-10 | 2025-03-14 | 64 |  | 2024-12-08 | 2024-12-14 |  | 2025-01-16 | 2025-01-16 | 1 |  |  |  | 2024-12-03 | 2024-12-17 |  | 2024-12-26 | 2025-01-30 | 36 |  | 2024-12-15 | 2024-12-21 |  | Completed | Completed | #VALUE! |  | 2024-12-15 | 2024-12-21 |  | Completed | Completed | #VALUE! |  | Kesav | 2024-12-15 | 2024-12-21 |  | 2025-01-08 | 2025-02-02 | 26 |  | 2024-12-29 | 2025-01-03 |  | 2025-02-02 | 2025-02-08 | 7 |  | 2024-12-28 | 2025-01-03 |  | 2025-02-17 | 2025-02-28 | 12 |  | 2025-01-06 | 2025-01-15 |  | 2025-02-17 | 2025-02-23 | 7 |  | 2025-01-17 | 2025-01-19 |  | 2025-02-23 | 2025-02-26 | 4 |  | 2025-01-09 | 2025-01-10 |  | 2025-03-09 | 2025-03-09 | 1 |  | 2025-01-03 | 2025-01-09 |  | 2024-12-09 | 2024-12-30 | 22 |  | 2025-01-03 | 2025-01-18 |  | 2025-02-26 | 2025-03-17 | 20 |  | 2025-01-10 | 2025-01-13 |  | 2025-03-21 | 2025-03-22 | 2 |  | 2025-01-19 | 2025-01-20 |  | 2025-03-23 | 2025-03-23 | 1 |  |  | 2025-03-01
MSC | 194 | PSS-4 | ARE41L | WTG 549 | Precast | F8 | Bauer | Done | 533162 | 2665366 | 2024-05-24 | 2024-06-21 |  | 2024-05-24 | 2024-06-21 |  | 253 | 253 | 2024-10-27 | 2024-11-05 |  | 2024-12-04 | 2024-12-12 | 9 | [8 empty] | 2024-11-21 | 2024-11-21 |  | 2024-12-13 | 2024-12-21 | 9 |  | 2024-11-22 | 2024-11-22 |  | 2024-12-21 | 2024-12-22 | 2 |  | 2024-11-23 | 2024-11-23 |  | 2024-12-29 | 2024-12-29 | 1 |  | 2024-11-24 | 2024-11-25 |  | 2025-01-01 | 2025-01-01 | 1 |  | 2024-11-27 | 2024-12-04 |  | 2025-01-03 | 2025-01-13 | 11 |  | 2024-12-07 | 2024-12-08 |  | 2025-01-13 | 2025-01-14 | 2 | 33 |  | 2024-12-09 | 2024-12-15 |  | 2025-01-10 | 2025-03-15 | 65 |  | 2024-12-09 | 2024-12-15 |  | 2025-01-17 | 2025-01-17 | 1 |  |  |  | 2024-12-04 | 2024-12-18 |  | 2025-02-18 | 2025-02-24 | 7 |  | 2024-12-16 | 2024-12-22 |  | 2025-01-02 | 2025-01-14 | 13 |  | 2024-12-16 | 2024-12-22 |  | 2025-01-21 | 2025-02-04 | 15 |  | Kesav | 2024-12-16 | 2024-12-22 |  | 2025-01-13 | 2025-02-06 | 25 |  | 2024-12-30 | 2025-01-04 |  | 2025-02-10 | 2025-02-17 | 8 |  | 2024-12-29 | 2025-01-04 |  | 2025-02-25 | 2025-03-13 | 17 |  | 2025-01-07 | 2025-01-16 |  | 2025-03-01 | 2025-03-06 | 6 |  | 2025-01-18 | 2025-01-20 |  | 2025-03-07 | 2025-03-23 | 17 | Loc. Hold start by 22mar | 2025-01-10 | 2025-01-11 |  | 2025-03-19 | 2025-03-19 | 1 |  | 2025-01-09 | 2025-01-15 |  | 2024-12-12 | 2025-01-15 | 35 |  | 2025-01-03 | 2025-01-18 |  | 2025-02-26 | 2025-03-17 | 20 |  | 2025-01-15 | 2025-01-18 |  | 2025-03-21 | 2025-03-22 | 2 |  | 2025-01-20 | 2025-01-21 |  | 2025-03-23 | 2025-03-23 | 1 |  |  | 2025-03-01
HBG | 195 | PSS-4 | AHEJ5L | WTG 550 | Precast | F3 | Keller | Done | 526457 | 2674820 | 2024-05-24 | 2024-06-21 |  | 2024-05-24 | 2024-06-21 |  | 253 | 253 | 2024-10-28 | 2024-11-06 |  | 2025-03-08 | 2025-03-19 | 12 | [8 empty] | 2024-11-22 | 2024-11-22 |  | 2025-03-21 | 2025-03-23 | 3 |  | 2024-11-23 | 2024-11-23 |  | 2025-03-24 | 2025-03-25 | 2 |  | 2024-11-24 | 2024-11-24 |  | 2025-03-27 | 2025-03-27 | 1 |  | 2024-11-25 | 2024-11-26 |  | 2025-04-03 | 2025-04-04 | 2 |  | 2024-11-28 | 2024-12-05 |  | 2025-04-04 | 2025-04-17 | 14 |  | 2024-12-08 | 2024-12-09 |  | 2025-04-17 | 2025-04-18 | 2 | 29 |  | 2024-12-10 | 2024-12-16 |  | 2025-04-27 | 2025-07-23 | 88 |  | 2024-12-10 | 2024-12-16 |  | 2025-04-22 | 2025-04-22 | 1 |  |  |  | 2024-12-05 | 2024-12-19 |  | 2025-03-27 | 2025-03-29 | 3 |  | 2024-12-17 | 2024-12-23 |  | 2025-04-12 | 2025-04-22 | 11 |  | 2024-12-17 | 2024-12-23 |  | 2025-04-22 | 2025-05-04 | 13 |  | Adani (Self Resue) | 2024-12-17 | 2024-12-23 |  | 2025-04-22 | 2025-05-04 | 13 |  | 2024-12-31 | 2025-01-05 |  | 2025-05-15 | 2025-06-13 | 30 |  | 2024-12-30 | 2025-01-05 |  | 2025-04-18 | 2025-05-02 | 15 |  | 2025-01-08 | 2025-01-17 |  | 2025-06-13 | 2025-06-18 | 6 |  | 2025-01-19 | 2025-01-21 |  | 2025-06-18 | 2025-06-21 | 4 |  | 2025-01-11 | 2025-01-12 |  | 2025-05-31 | 2025-05-31 | 1 |  | 2025-01-10 | 2025-01-16 |  | 2025-02-01 | 2025-02-25 | 25 |  | 2025-01-03 | 2025-01-18 |  | 2025-02-26 | 2025-03-17 | 20 |  | 2025-01-16 | 2025-01-19 |  | 2025-06-08 | 2025-06-16 | 9 |  | 2025-01-21 | 2025-01-22 |  | 2025-06-26 | 2025-06-26 | 1 |  |  | 2025-03-01
HBG | 196 | PSS-4 | ACL | WTG 084 | Precast | F1 | Bauer | Done | 531741 | 2675779 | 2024-05-03 | 2024-05-16 |  | 2024-05-03 | 2024-05-16 |  | 253 | 253 | 2024-11-11 | 2024-11-17 |  | 2025-01-27 | 2025-02-07 | 12 | [8 empty] | 2024-12-01 | 2024-12-02 |  | 2025-02-13 | 2025-02-16 | 4 |  | 2024-12-03 | 2024-12-04 |  | 2025-02-20 | 2025-02-21 | 2 |  | 2024-12-05 | 2024-12-05 |  | 2025-02-22 | 2025-02-22 | 1 |  | 2024-12-06 | 2024-12-07 |  | 2025-02-25 | 2025-02-25 | 1 |  | 2024-12-08 | 2024-12-18 |  | 2025-02-27 | 2025-03-16 | 18 |  | 2024-12-19 | 2024-12-20 |  | 2025-03-18 | 2025-03-19 | 2 | 35 |  | 2024-12-21 | 2025-01-15 |  | 2025-03-30 | 2025-04-21 | 23 |  | 2024-12-21 | 2024-12-26 |  | 2025-03-25 | 2025-03-25 | 1 |  |  |  | 2024-12-27 | 2025-01-06 |  | 2025-03-04 | 2025-03-18 | 15 |  | 2024-12-19 | 2024-12-25 |  | 2025-01-15 | 2025-02-02 | 19 |  | 2025-01-03 | 2025-01-08 |  | 2025-02-18 | 2025-03-03 | 14 |  | Varudi | 2025-01-09 | 2025-01-15 |  | 2025-02-19 | 2025-03-10 | 20 |  | 2025-01-22 | 2025-02-01 |  | 2025-04-24 | 2025-06-12 | 50 |  | 2025-01-08 | 2025-01-16 |  | 2025-03-26 | 2025-04-06 | 12 |  | 2025-02-03 | 2025-02-08 |  | 2025-06-13 | 2025-06-17 | 5 |  | 2025-02-09 | 2025-02-12 |  | 2025-06-18 | 2025-06-21 | 4 |  | 2025-01-18 | 2025-01-20 |  | 2025-04-07 | 2025-04-07 | 1 |  | 2025-01-12 | 2025-01-19 |  | 2024-11-30 | 2025-03-28 | 119 |  | 2025-02-08 | 2025-02-23 |  | 2025-02-26 | 2025-03-17 | 20 |  | 2025-01-20 | 2025-01-23 |  | 2025-04-16 | 2025-04-23 | 8 |  | 2025-02-23 | 2025-02-24 |  | 2025-06-23 | 2025-06-23 | 1 | Troubleshooting Issue |  | 2025-03-01
UNIQUE INF / ODHAV | 197 | PSS-4 | ACL | WTG 102 | Precast | F1 | Bauer | Done | 532574 | 2675514 | 2024-05-01 | 2024-05-16 |  | 2024-05-01 | 2024-05-16 |  | 199 | 199 | 2024-11-13 | 2024-11-20 |  | 2025-01-20 | 2025-01-25 | 6 | [8 empty] | 2024-12-03 | 2024-12-04 |  | 2025-02-03 | 2025-02-14 | 12 |  | 2024-12-05 | 2024-12-06 |  | 2025-02-16 | 2025-02-18 | 3 |  | 2024-12-07 | 2024-12-07 |  | 2025-02-19 | 2025-02-19 | 1 |  | 2024-12-08 | 2024-12-09 |  | 2025-02-22 | 2025-02-22 | 1 |  | 2024-12-10 | 2024-12-20 |  | 2025-02-22 | 2025-03-01 | 8 |  | 2024-12-21 | 2024-12-22 |  | 2025-03-02 | 2025-03-02 | 1 | 28 |  | 2024-12-23 | 2025-01-17 |  | 2025-03-10 | 2025-04-12 | 34 |  | 2024-12-23 | 2024-12-28 |  | 2025-03-12 | 2025-03-12 | 1 |  |  |  | 2024-12-29 | 2025-01-08 |  | 2025-03-04 | 2025-03-09 | 6 |  | 2024-12-20 | 2024-12-26 |  | 2025-01-08 | 2025-01-20 | 13 |  | 2025-01-04 | 2025-01-09 |  | 2025-01-30 | 2025-02-08 | 10 |  | Varudi | 2025-01-10 | 2025-01-16 |  | 2025-01-26 | 2025-02-08 | 14 |  | 2025-01-23 | 2025-02-02 |  | 2025-04-23 | 2025-05-08 | 16 |  | 2025-01-10 | 2025-01-18 |  | 2025-03-24 | 2025-04-12 | 20 |  | 2025-02-04 | 2025-02-09 |  | 2025-06-01 | 2025-06-08 | 8 |  | 2025-02-10 | 2025-02-13 |  | 2025-06-08 | 2025-06-12 | 5 |  | 2025-01-20 | 2025-01-22 |  | 2025-04-10 | 2025-04-10 | 1 |  | 2025-01-13 | 2025-01-20 |  | 2024-12-07 | 2024-12-18 | 12 |  | 2025-02-08 | 2025-02-23 |  | 2025-02-26 | 2025-03-17 | 20 |  | 2025-01-22 | 2025-01-25 |  | 2025-05-26 | 2025-06-08 | 14 |  | 2025-02-23 | 2025-02-24 |  | 2025-06-23 | 2025-06-23 | 1 |  |  | 2025-03-01
AB INFRA | 198 | PSS-4 | ACL | WTG 120 | Precast | F1 | Bauer | Done | 533414 | 2675209 | 2024-05-01 | 2024-05-16 |  | 2024-05-01 | 2024-05-16 |  | 253 | 253 | 2024-11-15 | 2024-11-22 |  | 2025-01-08 | 2025-01-17 | 10 | [8 empty] | 2024-12-05 | 2024-12-06 |  | 2025-02-15 | 2025-02-18 | 4 |  | 2024-12-07 | 2024-12-08 |  | 2025-02-18 | 2025-02-18 | 1 |  | 2024-12-09 | 2024-12-09 |  | 2025-02-19 | 2025-02-19 | 1 |  | 2024-12-10 | 2024-12-11 |  | 2025-02-20 | 2025-02-20 | 1 |  | 2024-12-12 | 2024-12-22 |  | 2025-02-23 | 2025-03-07 | 13 |  | 2024-12-23 | 2024-12-24 |  | 2025-03-08 | 2025-03-08 | 1 | 22 |  | 2024-12-25 | 2025-01-19 |  | 2025-03-21 | 2025-04-27 | 38 |  | 2024-12-25 | 2024-12-30 |  | 2025-03-16 | 2025-03-16 | 1 |  |  |  | 2024-12-31 | 2025-01-10 |  | 2025-02-18 | 2025-03-03 | 14 |  | 2024-12-21 | 2024-12-27 |  | 2025-01-10 | 2025-03-30 | 80 |  | 2025-01-05 | 2025-01-10 |  | Completed | Completed | #VALUE! |  | GP (Reuse) | 2025-01-11 | 2025-01-17 |  | 2025-02-14 | 2025-03-10 | 25 |  | 2025-01-24 | 2025-02-03 |  | 2025-04-02 | 2025-04-21 | 20 |  | 2025-01-12 | 2025-01-20 |  | 2025-03-23 | 2025-04-04 | 13 |  | 2025-02-05 | 2025-02-10 |  | 2025-04-24 | 2025-05-02 | 9 |  | 2025-02-11 | 2025-02-14 |  | 2025-05-03 | 2025-05-04 | 2 |  | 2025-01-22 | 2025-01-24 |  | 2025-04-05 | 2025-04-05 | 1 |  | 2025-01-14 | 2025-01-21 |  | 2024-12-07 | 2025-01-02 | 27 |  | 2025-02-08 | 2025-02-23 |  | 2025-02-26 | 2025-03-17 | 20 |  | 2025-01-24 | 2025-01-27 |  | 2025-05-26 | 2025-06-08 | 14 |  | 2025-02-23 | 2025-02-24 |  | 2025-06-23 | 2025-06-23 | 1 |  |  | 2025-03-01
AB INFRA | 199 | PSS-4 | ACL | WTG 142 | Precast | F1 | Bauer | Done | 534247 | 2674944 | 2024-04-30 | 2024-05-16 |  | 2024-04-30 | 2024-05-16 |  | 253 | 253 | 2024-11-18 | 2024-11-25 |  | 2025-01-02 | 2025-01-08 | 7 | [8 empty] | 2024-12-07 | 2024-12-08 |  | 2025-01-15 | 2025-01-19 | 5 |  | 2024-12-09 | 2024-12-10 |  | 2025-01-19 | 2025-01-22 | 4 |  | 2024-12-11 | 2024-12-11 |  | 2025-02-10 | 2025-02-10 | 1 | Shortage of manpower | 2024-12-12 | 2024-12-13 |  | 2025-02-14 | 2025-02-14 | 1 |  | 2024-12-14 | 2024-12-24 |  | 2025-02-14 | 2025-02-26 | 13 |  | 2024-12-25 | 2024-12-26 |  | 2025-02-26 | 2025-02-27 | 2 | 44 |  | 2024-12-27 | 2025-01-21 |  | 2025-03-12 | 2025-04-19 | 39 |  | 2024-12-27 | 2025-01-01 |  | 2025-03-02 | 2025-03-02 | 1 |  |  |  | 2025-01-02 | 2025-01-12 |  | 2025-02-09 | 2025-03-03 | 23 |  | 2024-12-22 | 2024-12-28 |  | 2025-01-10 | 2025-02-04 | 26 |  | 2025-01-03 | 2025-01-08 |  | 2025-02-23 | 2025-03-16 | 22 |  | GP | 2025-01-09 | 2025-01-15 |  | 2025-02-21 | 2025-03-11 | 19 |  | 2025-01-22 | 2025-02-01 |  | 2025-03-22 | 2025-04-04 | 14 |  | 2025-01-14 | 2025-01-22 |  | 2025-03-24 | 2025-04-04 | 12 |  | 2025-02-03 | 2025-02-08 |  | 2025-04-11 | 2025-04-16 | 6 |  | 2025-02-09 | 2025-02-12 |  | 2025-04-17 | 2025-04-18 | 2 |  | 2025-01-24 | 2025-01-26 |  | 2025-04-04 | 2025-04-04 | 1 |  | 2025-01-12 | 2025-01-19 |  | 2024-12-29 | 2025-01-25 | 28 |  | 2025-02-08 | 2025-02-23 |  | 2025-02-26 | 2025-03-17 | 20 |  | 2025-01-26 | 2025-01-29 |  | 2025-04-16 | 2025-04-27 | 12 |  | 2025-02-23 | 2025-02-24 |  | 2025-04-27 | 2025-04-27 | 1 |  |  | 2025-03-01
UNIQUE INF | 200 | PSS-4 | ACL | WTG 165 | Precast | F1 | Bauer | Done | 535088 | 2674640 | 2024-04-29 | 2024-05-01 |  | 2024-04-29 | 2024-05-01 |  | 253 | 253 | 2024-11-20 | 2024-11-28 |  | 2024-12-23 | 2024-12-31 | 9 |  | Yes | 2024-12-10 | 2024-12-25 |  | 2025-01-22 | 2025-01-31 |  | 2024-12-09 | 2024-12-10 |  | 2025-02-07 | 2025-02-13 | 7 |  | 2024-12-11 | 2024-12-12 |  | 2025-02-13 | 2025-02-15 | 3 |  | 2024-12-13 | 2024-12-13 |  | 2025-02-15 | 2025-02-15 | 1 |  | 2024-12-14 | 2024-12-15 |  | 2025-02-18 | 2025-02-18 | 1 |  | 2024-12-16 | 2024-12-26 |  | 2025-02-19 | 2025-02-28 | 10 |  | 2024-12-27 | 2024-12-28 |  | 2025-03-01 | 2025-03-02 | 2 | 24 |  | 2024-12-29 | 2025-01-23 |  | 2025-03-19 | 2025-05-24 | 67 |  | 2024-12-29 | 2025-01-03 |  | 2025-03-16 | 2025-03-16 | 1 |  |  |  | 2025-01-04 | 2025-01-14 |  | 2025-02-25 | 2025-02-28 | 4 |  | 2024-12-22 | 2024-12-28 |  | 2025-01-01 | 2025-01-13 | 13 |  | 2025-01-04 | 2025-01-09 |  | 2025-03-29 | 2025-04-05 | 8 |  | GP | 2025-01-10 | 2025-01-16 |  | 2025-01-11 | 2025-01-23 | 13 |  | 2025-01-23 | 2025-02-02 |  | 2025-04-06 | 2025-04-28 | 23 |  | 2025-01-16 | 2025-01-24 |  | 2025-03-21 | 2025-03-29 | 9 |  | 2025-02-04 | 2025-02-09 |  | 2025-05-16 | 2025-05-23 | 8 |  | 2025-02-10 | 2025-02-13 |  | 2025-05-24 | 2025-05-26 | 3 |  | 2025-01-26 | 2025-01-28 |  | 2025-04-07 | 2025-04-07 | 1 |  | 2025-01-13 | 2025-01-20 |  | 2024-12-27 | 2025-01-12 | 17 |  | 2025-02-08 | 2025-02-23 |  | 2025-02-26 | 2025-03-17 | 20 |  | 2025-01-28 | 2025-01-31 |  | 2025-05-26 | 2025-06-08 | 14 |  | 2025-02-23 | 2025-02-24 |  | 2025-06-23 | 2025-06-23 | 1 |  |  | 2025-03-01
Formulas:
CEA Approval Plan Finish Date = [CEA Approval]+15
WTG Ready To Charge (CFT) = MAX([HT Cable Plan Finish Date],[USS Testing Plan Finish Date],[USS Ere Plan Finish Date])
Grid-Conne Plan Finish Date = [WTG Ready To Charge (CFT)]+3
WTG Commissioining = MAX([Grid-Conne Plan Finish Date],[CEA Approval Plan Finish Date],[Pre-Comm Plan Finish Date])
WTG Comm Plan Finish Date = [WTG Commissioining]+1
CEA Approval = [WTG Ready To Charge (CFT)]-23
WTG Ere Plan Finish Date = [WTG Erection]+7
USS Erection Works = [USS Civil Plan Finish Date]+2
USS Ere Plan Finish Date = [USS Erection Works]+8
MCC = [WTG Ere Plan Finish Date]+2
MCC Plan Finish Date = [MCC]+5
Pre-comm = [MCC Plan Finish Date]+1
Pre-Comm Plan Finish Date = [Pre-comm]+3
USS Testing Works = [USS Ere Plan Finish Date]+2
USS Testing Plan Finish Date = [USS Testing Works]+2
HT Cable Laying & Terminations = [WTG Erection]-10
HT Cable Plan Finish Date = [HT Cable Laying & Terminations]+7
WTG Erection = [WTG Ere Plan Finish Date]-8
Note on S165: Darshik Dholakiya: Keller start sc Date 9-Feb-26
Note on AE165: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: pinnacle start PLT Date 24-12-2025
Note on AE177: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: pinnacle start PLT Date 11-12-2025
Note on A201: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PCC done by UNIQUE INF

## PH I-II-III (hidden)
S.No | Description | PH I | PH II | PH III
I | WTG CIVIL & MECH |  |  |  | Total
1 | Soil Test | 54 | 200 | 194 | 448
2 | Stone Column Drawing's Status | 54 | 200 | 194 | 448
3 | Stone Column | 54 | 200 | 192 | 446
4 | Plateload test | 8 | 46 | 61 | 115
5 | Excavation | 54 | 199 | 187 | 440
6 | PCC | 54 | 199 | 180 | 433
7 | Anchor Cage & Assembly | 54 | 199 | 177 | 430
8 | Steel Binding works | 54 | 199 | 173 | 426
9 | Raft Casting | 54 | 199 | 172 | 425
10 | Backfilling | 54 | 199 | 76 | 329
11 | Grouting | 54 | 199 | 163 | 416
12 | USS & Transformer Foundation | 54 | 200 | 148 | 402
13 | WTG Connecting Road | 54 | 200 | 193 | 447
14 | Crane Pad | 54 | 199 | 153 | 406
15 | WTG Erection | 54 | 198 | 119 | 371
16 | MCC | 54 | 198 | 113 | 365
17 | Pre-Comm | 54 | 198 | 108 | 360
18 | WTG Commissioining | 54 | 198 | 82 | 334
II | WTG ELECTRICAL (USS, Trafo & 33kV) |  |  |  | 0
19 | USS Erection | 54 | 198 | 117 | 369
20 | USS Testing | 194 | 198 | 114 | 506
| UG | 70 | 619 | 426 | 1115

## CranePad (hidden)
Sr. No. | SUB Station | SPV | Locations | Vendor | Road | Turning | Crane Pad Status |  | Status | Remarks
|  |  | 194 | 194 | 139 | 105 | Completed | 139 |  | 0
[7 empty] | WIP | 42
1 | PSS-11 | AGE25CL | WTG 233A | Bipin | Completed | Completed | Completed
2 | PSS-11 | AGE25CL | WTG 329 | Odhav | Completed | Completed | Completed
3 | PSS-11 | AGE25CL | WTG 353 | Odhav | Completed | Completed | Completed
4 | PSS-11 | AGE25CL | WTG 354 | Odhav(Reuse) | Completed | Completed | Completed
5 | PSS-14 | AGE25CL | WTG 373 | Vaibhav | Completed |  | Completed
6 | PSS-12 | AGE25CL | WTG 377 | GP Project | Completed |  | Completed
7 | PSS-11 | AGE25CL | WTG 378 | Odhav | Completed | Completed | Completed
8 | PSS-11 | AGE25CL | WTG 379 | Odhav | Completed | Completed | Completed
9 | PSS-11 | AGE25CL | WTG 328 | Odhav | Completed | Completed | Completed
10 | PSS-11 | AGE25CL | WTG 380 | Odhav | Completed | Completed | Completed
11 | PSS-11 | AGE25CL | WTG 381 | GP Project | Completed | Completed | Completed
12 | PSS-11 | AGE25CL | WTG 382 | GP Project | Completed | Completed | Completed
13 | PSS-14 | AGE25CL | WTG 399 | Odhav | Completed | Completed | Completed
14 | PSS-12 | AGE25CL | WTG 401 | Vaibhav | Completed | Completed | Completed
15 | PSS-12 | AGE26AL | WTG 402 | GP Project | Completed | Completed | Completed
16 | PSS-11 | AGE25CL | WTG 403 | Odhav | Completed | Completed | Completed
17 | PSS-11 | AGE25CL | WTG 404 | Odhav | Completed | Completed | Completed
18 | PSS-11 | AGE25CL | WTG 405 | GP Project | Completed | Completed | Completed
19 | PSS-11 | AGE25CL | WTG 406 | GP Project | Completed | Completed | Completed
20 | PSS-11 | AGE25CL | WTG 407 | Odhav | Completed | Completed | Completed
21 | PSS-14 | AGE25CL | WTG 424 | Odhav | Completed |  | Completed
22 | PSS-14 | AGE25CL | WTG 425 | Odhav | Completed |  | Completed
23 | PSS-12 | AGE25CL | WTG 426 | GP Project | Completed |  | Completed
24 | PSS-12 | AGE25CL | WTG 427 | GP Project | Completed |  | Completed
25 | PSS-12 | AGE26AL | WTG 428 | Odhav | Completed |  | Completed
26 | PSS-11 | AGE25CL | WTG 429 | SS Jadeja | Completed | Completed | Completed
27 | PSS-11 | AGE25CL | WTG 430 | GP Project | Completed | Completed | Completed
28 | PSS-11 | AGE25CL | WTG 431 | GP Project | Completed | Completed | Completed
29 | PSS-11 | AGE25CL | WTG 432 | Odhav | Completed | Completed | Completed
30 | PSS-11 | AGE25CL | WTG 433 | Odhav | Completed | Completed | Completed
31 | PSS-14 | AGE25CL | WTG 448 | GP Project | Completed | Completed | Completed
32 | PSS-14 | AGE25CL | WTG 449 | GP Project | Completed |  | Completed
33 | PSS-14 | AGE25CL | WTG 450 | GP Project(Reuse) |  |  | WIP
34 | PSS-12 | AGE26AL | WTG 451 | GP Project |  |  | WIP
35 | PSS-12 | AGE26AL | WTG 452 | Odhav |  |  | WIP
36 | PSS-12 | AGE26AL | WTG 453 | Odhav | Completed |  | Completed
37 | PSS-11 | AGE25CL | WTG 454 | SS Jadeja | Completed | Completed | Completed
38 | PSS-11 | AGE25CL | WTG 455 | SS Jadeja | Completed | Completed | Completed
39 | PSS-11 | AGE25CL | WTG 456 | GP Project | Completed | Completed | Completed
40 | PSS-14 | AGE26AL | WTG 473 | Odhav(Reuse) |  |  | WIP
41 | PSS-14 | AGE26AL | WTG 474 | Odhav(Reuse) |  |  | WIP
42 | PSS-12 | AGE26AL | WTG 475 | Odhav | Completed |  | Completed
43 | PSS-12 | AGE26AL | WTG 476 | SS Jadeja | Completed |  | Completed
44 | PSS-12 | AGE26AL | WTG 477 | Bipin |  |  | WIP
45 | PSS-12 | AGE26AL | WTG 478 | SS Jadeja | Completed | Completed | Completed
46 | PSS-11 | AGE25CL | WTG 479 | SS Jadeja | Completed | Completed | Completed
47 | PSS-11 | AGE25CL | WTG 480 | Vaibhav | Completed |  | Completed
48 | PSS-11 | AGE25CL | WTG 481 | SS Jadeja | Completed | Completed | Completed
49 | PSS-11 | AGE25CL | WTG 482 | Bipin | Completed |  | Completed
50 | PSS-12 | AGE26AL | WTG 496 | Bipin | Completed | Completed | Completed
51 | PSS-12 | AGE26AL | WTG 497 | Bipin |  |  | WIP
52 | PSS-12 | AGE26AL | WTG 498 | SS Jadeja | Completed | Completed | Completed
53 | PSS-12 | AGE26AL | WTG 499 | SS Jadeja | Completed |  | Completed
54 | PSS-12 | AGE26AL | WTG 500 | SS Jadeja | Completed |  | Completed
55 | PSS-11 | AGE25CL | WTG 501 | Vaibhav | Completed | Completed | Completed
56 | PSS-11 | AGE25CL | WTG 502 | GP Project | Completed | Completed | Completed
57 | PSS-11 | AGE25CL | WTG 503 | GP Project | Completed | Completed | Completed
58 | PSS-11 | AGE25CL | WTG 504 | GP Project | Completed | Completed | Completed
59 | PSS-11 | AGE25CL | WTG 505 | Bipin | Completed | Completed | Completed
60 | PSS-12 | AGE26AL | WTG 517 | Vaibhav | Completed |  | Completed
61 | PSS-12 | AGE26AL | WTG 518 | Vaibhav | Completed | Completed | Completed
62 | PSS-12 | AGE26AL | WTG 519 | Vaibhav | Completed | Completed | Completed
63 | PSS-12 | AGE26AL | WTG 520 | Harsh | Completed | Completed | Completed
64 | PSS-12 | AGE26AL | WTG 521 | Harsh | Completed | Completed | Completed
65 | PSS-11 | AGE25CL | WTG 522 | Vaibhav | Completed | Completed | Completed
66 | PSS-11 | AGE25CL | WTG 523 | GP Project | Completed | Completed | Completed
67 | PSS-11 | AGE25CL | WTG 524 | Vaibhav | Completed | Completed | Completed
68 | PSS-12 | AGE26AL | WTG 533 | Harsh | Completed | Completed | Completed
69 | PSS-12 | AGE26AL | WTG 534 | Varudi | Completed | Completed | Completed
70 | PSS-12 | AGE26AL | WTG 535 | Varudi | Completed | Completed | Completed
71 | PSS-12 | AGE26AL | WTG 536 | Varudi | Completed | Completed | Completed
72 | PSS-11 | AGE25CL | WTG 457 | Bipin | Completed | Completed | Completed
73 | PSS-14 | AGE26AL | WTG 532 | GP Project(Reuse) |  |  | WIP
74 | PSS-14 | AGE26AL | WTG 516 | GP Project(Reuse) |  |  | WIP
75 | PSS-14 | AGE25CL | WTG 423 | GP Project | Completed |  | Completed
76 | PSS-14 | AGE25CL | WTG 398 | Vaibhav | Completed | Completed | Completed
77 | PSS-14 | AGE26AL | KH 53 | GP Project |  |  | WIP
78 | PSS-14 | AGE26AL | KH 54 | GP Project | Completed | Completed | Completed
79 | PSS-14 | AGE26AL | KH 55 | SS Jadeja |  |  | WIP
80 | PSS-14 | AGE26AL | KH 56 | Keshav
81 | PSS-14 | AGE26AL | KH 57 | GP Project(Reuse) |  |  | WIP
82 | PSS-14 | AGE26AL | KH 58 | Varudi |  |  | WIP
83 | PSS-14 | AGE26AL | KH 59 | Varudi(Reuse)
84 | PSS-14 | AGE26AL | KH 60 | Varudi |  |  | WIP
85 | PSS-14 | AGE26AL | KH 61 | Varudi
86 | PSS-14 | AGE26AL | KH 556 | GP Project(Reuse) |  |  | WIP
87 | PSS-14 | AGE26AL | KH 523 | Bipin(Reuse)
88 | PSS-14 | AGE26AL | KH 522 | SS Jadeja(Reuse) |  |  | WIP
89 | PSS-14 | AGE26AL | KH 521 | GP Project(Reuse)
90 | PSS-14 | AGE26AL | KH 508 | GP Project(Reuse)
91 | PSS-14 | AGE26AL | KH 555 | GP Project | Completed |  | Completed
92 | PSS-14 | AGE26AL | KH 557 | Odhav |  |  | WIP
93 | PSS-14 | AGE26AL | KH 581 | GP Project | Completed |  | Completed
94 | PSS-14 | AGE26AL | KH 582 | Keshav(Reuse) |  |  | WIP
95 | PSS-14 | AGE26AL | KH 583 | Bipin(Reuse) |  |  | WIP
96 | PSS-14 | AGE26AL | KH 52 | Bipin(Reuse) |  |  | WIP
97 | PSS-14 | AGE26AL | KH 51 | Harsh | Completed |  | Completed
98 | PSS-14 | AGE26AL | KH 552 | GP Project(Reuse) |  |  | WIP
99 | PSS-14 | AGE26AL | KH 588 | GP Project(Reuse) |  |  | WIP
100 | PSS-14 | AGE26AL | KH 589 | Keshav | Completed | Completed | Completed
101 | PSS-14 | AGE26AL | KH 590 | SS Jadeja | Completed |  | Completed
102 | PSS-14 | AGE26AL | KH 591 | Bipin(Reuse) |  |  | WIP
103 | PSS-14 | AGE26AL | KH 592 | Harsh | Completed |  | Completed
104 | PSS-14 | AGE26AL | KH 550 | SS Jadeja(Reuse) |  |  | WIP
105 | PSS-14 | AGE26AL | KH 551 | SS Jadeja(Reuse) |  |  | WIP
106 | PSS-14 | AGE26AL | KH 579 | Odhav(Reuse) |  |  | WIP
107 | PSS-14 | AGE26AL | KH 596 | SS Jadeja(Reuse) |  |  | WIP
108 | PSS-14 | AGE26AL | KH 597 | Keshav(Reuse) |  |  | WIP
109 | PSS-14 | AGE26AL | KH 598 | Keshav | Completed |  | Completed
110 | PSS-14 | AGE26AL | KH 599 | Harsh(Reuse) |  |  | WIP
111 | PSS-14 | AGE26AL | KH 600 | Harsh | Completed |  | Completed
112 | PSS-14 | AGE26AL | KH 553 | SS Jadeja(Reuse) | Completed |  | Completed
113 | PSS-14 | AGE26AL | KH 580 | Harsh |  |  | WIP
114 | PSS-14 | AGE26AL | KH 478 | Odhav(Reuse)
115 | PSS-14 | AGE26AL | KH 604 | Keshav | Completed |  | Completed
116 | PSS-14 | AGE26AL | KH 605 | Bipin | Completed |  | Completed
117 | PSS-14 | AGE26AL | KH 606 | SS Jadeja | Completed | Completed | Completed
118 | PSS-14 | AGE26AL | KH 607 | Harsh(Reuse) |  |  | WIP
119 | PSS-14 | AGE26AL | KH 608 | Harsh |  |  | WIP
120 | PSS-14 | AGE26AL | KH 509 | GP Project(Reuse) |  |  | WIP
121 | PSS-14 | AGE26AL | KH 554 | Odhav(Reuse) |  |  | WIP
122 | PSS-14 | AGE26AL | KH 611 | Varudi
123 | PSS-14 | AGE26AL | KH 612 | Bipin | Completed | Completed | Completed
124 | PSS-14 | AGE26AL | KH 613 | SS Jadeja | Completed | Completed | Completed
125 | PSS-14 | AGE26AL | KH 614 | Harsh(Reuse) |  |  | WIP
126 | PSS-14 | AGE26AL | KH 615 | Harsh |  |  | WIP
127 | PSS-14 | AGE26AL | KH 47 | GP Project(Reuse) |  |  | WIP
128 | PSS-14 | AGE26AL | KH 617 | Bipin |  |  | WIP
129 | PSS-14 | AGE26AL | KH 618 | Vaibhav
130 | PSS-14 | AGE26AL | KH 619 | Vaibhav(Reuse) |  |  | WIP
131 | PSS-14 | AGE26AL | KH 620 | Varudi(Reuse)
132 | PSS-14 | AGE26AL | KH 621 | SS Jadeja |  |  | WIP
133 | PSS-14 | AGE26AL | KH 622 | SS Jadeja(Reuse)
134 | PSS-14 | AGE26AL | KH 34 | SS Jadeja |  |  | WIP
135 | PSS-14 | AGE26AL | KH 35 | Vaibhav(Reuse)
136 | PSS-14 | AGE26AL | KH 68 | Bipin
137 | PSS-05 | AHEJ5L | WTG 177 | Varudi | Completed | Completed | Completed
138 | PSS-05 | AHEJ5L | WTG 199 | SS Jadeja | Completed | Completed | Completed
139 | PSS-05 | AHEJ5L | WTG 154 | Varudi | Completed | Completed | Completed
140 | PSS-05 | AHEJ5L | WTG 002 | SS Jadeja | Completed | Completed | Completed
141 | PSS-05 | AHEJ5L | WTG 133 | GP Project | Completed | Completed | Completed
142 | PSS-05 | AHEJ5L | WTG 290 | GP Project | Completed | Completed | Completed
143 | PSS-05 | AHEJ5L | WTG 315 | GP Project | Completed | Completed | Completed
144 | PSS-05 | AHEJ5L | WTG 266 | GP Project | Completed | Completed | Completed
145 | PSS-05 | AHEJ5L | WTG 221 | GP Project | Completed | Completed | Completed
146 | PSS-05 | AHEJ5L | WTG 243 | GP Project | Completed | Completed | Completed
147 | PSS-05 | AHEJ5L | WTG 131 | GP Project | Completed | Completed | Completed
148 | PSS-05 | AHEJ5L | WTG 132 | GP Project | Completed | Completed | Completed
149 | PSS-05 | AHEJ5L | WTG 152 | GP Project | Completed | Completed | Completed
150 | PSS-05 | AHEJ5L | WTG 153 | GP Project | Completed | Completed | Completed
151 | PSS-05 | AHEJ5L | WTG 155 | GP Project | Completed | Completed | Completed
152 | PSS-05 | AHEJ5L | WTG 156 | GP Project | Completed | Completed | Completed
153 | PSS-05 | AHEJ5L | WTG 175 | GP Project | Completed | Completed | Completed
154 | PSS-05 | AHEJ5L | WTG 176 | GP Project | Completed | Completed | Completed
155 | PSS-05 | AHEJ5L | WTG 178 | GP Project | Completed | Completed | Completed
156 | PSS-05 | AHEJ5L | WTG 179 | GP Project | Completed | Completed | Completed
157 | PSS-05 | AHEJ5L | WTG 197 | GP Project | Completed | Completed | Completed
158 | PSS-05 | AHEJ5L | WTG 198 | Varudi | Completed | Completed | Completed
159 | PSS-05 | AHEJ5L | WTG 200 | Varudi | Completed | Completed | Completed
160 | PSS-05 | AHEJ5L | WTG 201 | Varudi | Completed | Completed | Completed
161 | PSS-05 | AHEJ5L | WTG 222 | Varudi | Completed | Completed | Completed
162 | PSS-05 | AHEJ5L | WTG 223 | Varudi | Completed | Completed | Completed
163 | PSS-05 | AHEJ5L | WTG 244 | GP Project | Completed | Completed | Completed
164 | PSS-05 | AHEJ5L | WTG 245 | GP Project | Completed | Completed | Completed
165 | PSS-05 | AHEJ5L | WTG 267 | Varudi | Completed | Completed | Completed
166 | PSS-05 | AHEJ5L | WTG 268 | GP Project | Completed | Completed | Completed
167 | PSS-05 | AHEJ5L | WTG 291 | GP Project | Completed | Completed | Completed
168 | PSS-05 | AHEJ5L | WTG 292 | GP Project | Completed | Completed | Completed
169 | PSS-05 | AHEJ5L | WTG 314 | GP Project | Completed | Completed | Completed
170 | PSS-05 | AHEJ5L | WTG 316 | GP Project | Completed | Completed | Completed
171 | PSS-05 | AHEJ5L | WTG 555 | GP Project(Reuse) | Completed |  | Completed
172 | PSS-05 | AHEJ5L | WTG 554 | GP Project(Reuse) | Completed | Completed | Completed
173 | PSS-05 | AHEJ5L | WTG 552 | GP Project | Completed | Completed | Completed
174 | PSS-05 | AHEJ5L | WTG 551 | GP Project | Completed |  | Completed
175 | PSS-05 | AHEJ5L | WTG 553 | GP Project(Reuse) | Completed |  | Completed
176 | PSS-08 | ASEJ6PL | WTG 121 | GP Project | Completed | Completed | Completed
177 | PSS-08 | ASEJ6PL | WTG 123 | GP Project(Reuse) | Completed | Completed | Completed
178 | PSS-08 | ASEJ6PL | WTG 143 | GP Project | Completed | Completed | Completed
179 | PSS-08 | ASEJ6PL | WTG 144 | GP Project | Completed |  | Completed
180 | PSS-08 | ASEJ6PL | WTG 145 | GP Project | Completed | Completed | Completed
181 | PSS-08 | ASEJ6PL | WTG 230 | GP Project | Completed |  | Completed
182 | PSS-08 | ARE3L | WTG 302 | Odhav | Completed | Completed | Completed
183 | PSS-08 | ARE3L | WTG 326 | Harsh | Completed | Completed | Completed
184 | PSS-08 | ARE3L | WTG 327 | Harsh | Completed | Completed | Completed
185 | PSS-08 | ARE3L | WTG 351 | Harsh | Completed | Completed | Completed
186 | PSS-08 | ASEJ6PL | WTG 376 | Odhav | Completed | Completed | Completed
187 | PSS-08 | ASEJ6PL | WTG 400 | Odhav | Completed | Completed | Completed
188 | PSS-08 | ASEJ6PL | WTG 208 | GP Project | Completed |  | Completed
189 | PSS-08 | ASEJ6PL | WTG 141 | GP Project | Completed |  | Completed
190 | PSS-08 | ASEJ6PL | WTG 164 | GP Project |  |  | WIP
191 | PSS-08 | ARE3L | WTG 352 | Odhav | Completed | Completed | Completed
192 | PSS-08 | ASEJ6PL | WTG 186 | GP Project | Completed | Completed | Completed
193 | PSS-09 | AGE25BL | WTG 556 | GP Project(Reuse) | Completed | Completed | Completed
194 | PSS-09 | AGE25BL | WTG 557 | GP Project(Reuse) | Completed | Completed | Completed

## Precast Summary Details (hidden)
Precast | 500 | 144 | 48 | 14 | 91 | 27 | 0 | 3 | 0 | 0
Date | HT Column |  | HT Slab |  | DT Slab |  | Staircase |  | BOT
| ShreeJi | Sachi | ShreeJi | Sachi | ShreeJi | Sachi | ShreeJi | Sachi | ShreeJi | Sachi
2025-03-10
2025-03-11
2025-03-12
2025-03-13 | [5 empty] | 1
2025-03-14
2025-03-15
2025-03-16
2025-03-17 | [5 empty] | 1
2025-03-18
2025-03-19
2025-03-20
2025-03-21
2025-03-22
2025-03-23
2025-03-24
2025-03-25 | [5 empty] | 1
2025-03-26
2025-03-27
2025-03-28
2025-03-29
2025-03-30
2025-03-31
2025-04-01
2025-04-02
2025-04-03
2025-04-04
2025-04-05
2025-04-06
2025-04-07
2025-04-08
2025-04-09 |  |  |  |  | 2
2025-04-10 |  |  |  |  | 2 | 1
2025-04-11 |  |  |  |  | 2
2025-04-12 |  |  |  |  | 3
2025-04-13
2025-04-14 | 6 |  |  |  | 3 | 1
2025-04-15 | 8 | 6 |  |  | 2
2025-04-16 |  | 6 |  |  | 3
2025-04-17 | 16 | 6 |  |  | 3
2025-04-18 | 8 | 8 |  |  | 3
2025-04-19 |  |  |  |  | 2
2025-04-20 | 11 | 7 |  |  | 1
2025-04-21 | 8 |  |  |  | 1 | 1
2025-04-22 |  | 7 |  |  | 2
2025-04-23 | 7 |  |  |  | 2
2025-04-24 | 8 | 7 |  |  | 1 | 1
2025-04-25 | 8 |  |  |  | 2
2025-04-26 |  |  |  |  | 3
2025-04-27 | 8 | 7
2025-04-28 | 8 |  |  |  |  | 1
2025-04-29 | 8 | 6
2025-04-30 | 8 |  |  |  | 1 | 1
2025-05-01 | 8 |  | 1 |  | 2
2025-05-02 |  |  |  | 1
2025-05-03 |  |  | 2 |  | 1
2025-05-04 |  |  |  |  | 1
2025-05-05
2025-05-06 | 5 | 7 | 1 | 1 | 1
2025-05-07 | 8 |  | 1 | 1 | 2
2025-05-08 |  |  |  | 1 |  | 1
2025-05-09 | 8 | 7 | 1 | 1 | 2
2025-05-10 | 8
2025-05-11 | 8 |  | 1
2025-05-12 |  |  |  |  | 2
2025-05-13 | 8 |  | 1 |  | 1
2025-05-14 | 8 | 7 | 1 | 1 | 2
2025-05-15 | 8 |  |  |  | 1 | 1
2025-05-16 |  |  |  |  | 1
2025-05-17 | 8 |  |  |  | 2 | 1
2025-05-18 | 8 | 7 |  | 1 | 1
2025-05-19 |  |  |  | 1
2025-05-20 |  | 7 |  | 1
2025-05-21 |  | 7 |  | 1
2025-05-22 | 8 |  | 1 | 1 | 2
2025-05-23 | 8 | 5 | 1
2025-05-24 |  | 5 |  | 1 |  | 1
2025-05-25 | 8 |  | 1 |  | 1
2025-05-26 |  | 6 | 1
2025-05-27 |  | 6 |  | 1 |  | 1 |  | 2
2025-05-28 |  | 7 | 2 |  | 2
2025-05-29 |  | 7 | 2 | 1 | 2 |  |  | 1
2025-05-30 |  |  | 1 |  | 2 | 1
2025-05-31 |  |  | 1 |  | 2 | 1
2025-06-01
2025-06-02
2025-06-03
2025-06-04 | [5 empty] | 1
2025-06-05 | [5 empty] | 1
2025-06-06 |  |  | 1 |  |  | 1
2025-06-07
2025-06-08 | [5 empty] | 1
2025-06-09 |  | 6 | 1
2025-06-10 | [5 empty] | 1
2025-06-11 |  |  | 1 |  |  | 1
2025-06-12 |  |  | 1 |  |  | 1
2025-06-13 | [5 empty] | 1
2025-06-14 |  |  | 1 |  |  | 1
2025-06-15 | [5 empty] | 1
2025-06-16
2025-06-17
2025-06-18
2025-06-19 | 8 |  | 1
2025-06-20 | 8 |  | 1
2025-06-21 | 8 |  | 1
2025-06-22
2025-06-23 | 8 |  | 1
2025-06-24 | 8 |  | 1
2025-06-25 | 8 |  | 1 |  |  | 1
2025-06-26 | 8
2025-06-27
2025-06-28
2025-06-29 | 8
2025-06-30
2025-07-01
2025-07-02
2025-07-03
2025-07-04
2025-07-05
2025-07-06
2025-07-07
2025-07-08
2025-07-09
2025-07-10
2025-07-11
2025-07-12
2025-07-13
2025-07-14
2025-07-15
2025-07-16
2025-07-17
2025-07-18
2025-07-19
2025-07-20
2025-07-21
2025-07-22
2025-07-23
2025-07-24
2025-07-25
2025-07-26
2025-07-27
2025-07-28
2025-07-29
2025-07-30
2025-07-31
2025-08-01
2025-08-02
2025-08-03
2025-08-04
2025-08-05
2025-08-06
2025-08-07
2025-08-08
2025-08-09
2025-08-10
2025-08-11
2025-08-12
2025-08-13
2025-08-14
2025-08-15
2025-08-16
2025-08-17
2025-08-18
2025-08-19
2025-08-20
2025-08-21
2025-08-22
2025-08-23
2025-08-24
2025-08-25
2025-08-26
2025-08-27
2025-08-28
2025-08-29
2025-08-30
2025-08-31
2025-09-01
2025-09-02
2025-09-03
2025-09-04
2025-09-05
2025-09-06
2025-09-07
2025-09-08
2025-09-09
2025-09-10
2025-09-11
2025-09-12
2025-09-13
2025-09-14
2025-09-15
2025-09-16
2025-09-17
2025-09-18
2025-09-19
2025-09-20
2025-09-21
2025-09-22
2025-09-23
2025-09-24
2025-09-25
2025-09-26
2025-09-27
2025-09-28
2025-09-29
2025-09-30
2025-10-01
2025-10-02
2025-10-03
2025-10-04
2025-10-05
2025-10-06
2025-10-07
2025-10-08
2025-10-09
2025-10-10
2025-10-11
2025-10-12
2025-10-13
2025-10-14
2025-10-15
2025-10-16
2025-10-17
2025-10-18 | 8
2025-10-19 | 8
2025-10-20
2025-10-21 | 8
2025-10-22 | 8
2025-10-23
2025-10-24 | 8
2025-10-25 | 8
2025-10-26 | 8
2025-10-27 | 8
2025-10-28
2025-10-29 | 8
2025-10-30 | 8
2025-10-31 | 8
2025-11-01 | 8
2025-11-02
2025-11-03
2025-11-04
2025-11-05
2025-11-06 | 7
2025-11-07 | 8 |  | 1 |  | 1
2025-11-08 | 8 |  | 1
2025-11-09
2025-11-10 | 8
2025-11-11 | 8
2025-11-12 | 8
2025-11-13
2025-11-14 | 8 |  | 1 |  | 2
2025-11-15 | 8 |  | 1
2025-11-16
2025-11-17 | 8 |  | 1
2025-11-18 | 8
2025-11-19 | 8 |  | 1
2025-11-20 |  |  | 1
2025-11-21 | 8 |  | 1
2025-11-22
2025-11-23
2025-11-24
2025-11-25 |  |  | 1
2025-11-26
2025-11-27
2025-11-28 |  |  | 1
2025-11-29 |  |  | 1 |  | 1
2025-11-30
2025-12-01 |  |  |  |  | 1
2025-12-02
2025-12-03 |  |  |  |  | 1
2025-12-04
2025-12-05 |  |  |  |  | 1
2025-12-06 | 8
2025-12-07 |  |  |  |  | 1
2025-12-08
2025-12-09 |  |  |  |  | 1
2025-12-10 |  |  | 1 |  | 1
2025-12-11 |  |  | 1 |  | 1
2025-12-12 |  |  | 1
2025-12-13 | 8 |  |  |  | 2
2025-12-14
2025-12-15 |  |  | 1
2025-12-16 |  |  |  |  | 1
2025-12-17 |  |  | 1 |  | 1
2025-12-18 |  |  |  |  | 1
2025-12-19 | 8 |  |  |  | 1
2025-12-20
2025-12-21 |  |  |  |  | 1
2025-12-22
2025-12-23
2025-12-24
2025-12-25
2025-12-26
2025-12-27 |  |  | 1 |  | 2
2025-12-28
2025-12-29 |  |  | 1 |  | 1
2025-12-30
2025-12-31
2026-01-01
2026-01-02
2026-01-03
2026-01-04
2026-01-05
2026-01-06 |  |  |  |  | 1
2026-01-07 |  |  |  |  | 1
2026-01-08
2026-01-09
2026-01-10
2026-01-11
2026-01-12
2026-01-13
2026-01-14
2026-01-15
2026-01-16
2026-01-17
2026-01-18
2026-01-19
2026-01-20
2026-01-21
2026-01-22
2026-01-23
2026-01-24
2026-01-25
2026-01-26
2026-01-27
2026-01-28
2026-01-29
2026-01-30
2026-01-31
2026-02-01
2026-02-02
2026-02-03
2026-02-04
2026-02-05
2026-02-06
2026-02-07
2026-02-08
2026-02-09
2026-02-10
2026-02-11
2026-02-12
2026-02-13
2026-02-14
2026-02-15
2026-02-16
2026-02-17
2026-02-18
2026-02-19
2026-02-20
2026-02-21
2026-02-22
2026-02-23
2026-02-24
2026-02-25
2026-02-26
2026-02-27
2026-02-28
2026-03-01
2026-03-02
2026-03-03
2026-03-04
2026-03-05
2026-03-06
2026-03-07
2026-03-08
2026-03-09
2026-03-10
2026-03-11
2026-03-12
2026-03-13
2026-03-14
2026-03-15
2026-03-16
2026-03-17
2026-03-18
2026-03-19
2026-03-20
2026-03-21
2026-03-22
2026-03-23
2026-03-24
2026-03-25
2026-03-26
2026-03-27
2026-03-28
2026-03-29
2026-03-30
2026-03-31
| 644 |  | 62 |  | 118 |  | 3 |  | 0
Balance | 1084 |  | 130 |  | 74 |  | 189 |  | 192

## 33KV - Summary (2) (hidden)
| Scope | Today | Cumulative | Balance
FDR -10
Excavation
HTCable Laying
Cable Joint
Cable Termination
FO Cable Laying
FDR- 11
Excavation
HTCable Laying
Cable Joint
Cable Termination
FO Cable Laying
FDR - 12
Excavation
HTCable Laying
Cable Joint
Cable Termination
FO Cable Laying
FDR - 13
Excavation
HTCable Laying
Cable Joint
Cable Termination
FO Cable Laying

## Progress Analysis (hidden)
Stone Column Works | No. of Days / Count | Cum. Total | Cum. % | Foundation Works | No. of Days / Count | Cum. Total | Cum. % | Erection Works | No. of Days / Count | Cum. Total | Cum. %
Average No. of Days | #DIV/0! |  |  | Average No. of Days | #DIV/0! |  |  | Average No. of Days | #DIV/0!
Best Case | 0 |  |  | Best Case | 0 |  |  | Best Case | 0
Worst Case | 0 |  |  | Worst Case | 0 |  |  | Worst Case | 0
0 to 5 days | 0 | 0 | #DIV/0! | 0 to 15 days | 0 | 0 | #DIV/0! | 0 to 8 days | 0 | 0 | #DIV/0!
6 to 10 days | 0 | 0 | #DIV/0! | 16 to 20 days | 0 | 0 | #DIV/0! | 9 to 12 days | 0 | 0 | #DIV/0!
11 to 15 days | 0 | 0 | #DIV/0! | 21 to 25 days | 0 | 0 | #DIV/0! | 13 to 15 days | 0 | 0 | #DIV/0!
16 to 20 days | 0 | 0 | #DIV/0! | 26 to 30 days | 0 | 0 | #DIV/0! | 16 to 20 days | 0 | 0 | #DIV/0!
More than 20 days | 0 | 0 | #DIV/0! | 31 to 35 days | 0 | 0 | #DIV/0! | More than 20 days | 0 | 0 | #DIV/0!
|  |  |  | More than 35 days | 0 | 0 | #DIV/0!

## EQUIPMENT MOBILIZATION (hidden)
S.No | Location | Vendor | ID | Mobilization date | Exit Date | Re-Mobilization date | Remarks
1 | 131 | Bauer | R3 | 2025-01-15
2 | 121 | Saritha | R1 | 2025-01-15
3 | 314 | Bauer | R8 | 2025-01-16
4 |  | Bauer | R6 | 2025-02-07
5 |  | Bauer | R7 | 2025-02-19
6 |  | Bauer | R2 | 2025-02-04
7 |  | Kamar | R1 | 2025-02-01
8 |  | Kamar | R2 | 2025-01-29
9 |  | Keller | R2 | 2025-02-06
10 |  | Keller | R2 | 2025-02-08
11 |  | ITDC | R1 | 2025-02-24
12 |  | Keller | R4 | 2025-04-06