## Summary DPR
Hyper Links
|  |  | 400KV Substation & Transmission Line Progress Report | [7 empty] | Sr. No | Sheet Name | Link
Project Name: 400kv Substation -RE Park Khavda |  | Date: | 2026-02-27 | [7 empty] | 1 | PSS-6 DPR | PSS-6 DPR'!A1
Location : PSS -6 | [10 empty] | 2 | PSS-6 & TL Manpower | PSS-6 Manpower & Machinery'!A1
[11 empty] | 3 | 400kv TL Visual Chart | 400kv TL Visual Chart'!A1
Weather Conditions - Today | Forecast |  | Manpower: | 154 | [6 empty] | 4 | 400kv TL Stringing | 400kv TL Stringing'!A1
Morning : 20'C Partly cloudy | 19'C Partly cloudy |  | PSS: | 154 | [6 empty] | 5 | 400kv Tower Erection | 400kv TL Tower Erection'!A1
Afternoon: 33'C Sunny | 32'C Sunny |  | TL: | 0 | [6 empty] | 6 | Issues | Issues!A1
Remarks:
[16 empty] | Inc SVG & HF |  |  |  | Exc SVG & HF
[16 empty] | Actual |  |  |  | Actual
Activity | Duration | Schedule Start | Schedule Finish | UOM | Scope | Actual | Balance | Actual/ Forecast Start | Actual/ Forecast Finish | Remarks | [5 empty] | 98.07% |  |  |  | 98.56%
PSS-06 Priority 1 Progress
Stone Column | 28 | 2024-01-18 | 2024-02-14 | Nos | 522 | 522 | 0 | 2024-01-18 | 2024-02-14 | Completed. |  |  |  | 0.0010917 | 3.057% | 100% | 98.07% | 0.0012887 | 3.608% | 100% | 98.56%
GIS Building Civil Work-Upto Slab | 56 | 2025-02-10 | 2025-04-06 | Lot | 1 | 1 | 0 | 2025-02-10 | 2025-05-02 | Completed. |  |  |  |  | 6.114% | 100% |  |  | 7.216% | 100%
MCR Building Civil Work-Upto Slab | 50 | 2025-02-16 | 2025-04-06 | Lot | 1 | 1 | 0 | 2025-02-16 | 2025-06-04 | Completed. |  |  |  |  | 5.459% | 100% |  |  | 6.443% | 100%
SGR - 01 Civil Work-Upto Slab | 44 | 2025-02-26 | 2025-04-10 | Lot | 1 | 1 | 0 | 2025-03-18 | 2025-07-12 | Completed. |  |  |  |  | 4.803% | 100% |  |  | 5.67% | 100%
Power Transformer - 01 Civil Work | 46 | 2025-02-18 | 2025-04-04 | Nos | 1 | 1 | 0 | 2025-04-04 | 2025-07-17 | completed. |  |  |  |  | 5.022% | 100% |  |  | 5.928% | 100%
Power Transformer - 02 Civil Work | 44 | 2025-02-20 | 2025-04-04 | Nos | 1 | 1 | 0 | 2025-03-29 | 2025-07-20 | completed. |  |  |  |  | 4.803% | 100% |  |  | 5.67% | 100%
SVG Civil Work (Exc. Fencing) | 35 | 2025-03-05 | 2025-04-08 | Set | 7 | 7 | 0 | 2025-06-09 | 2025-12-15 | completed. |  |  |  |  | 3.821% | 100%
Harmonic Filter Civil Work | 56 | 2025-03-20 | 2025-05-14 | Set | 4 | 4 | 0 | 2025-04-07 | 2025-12-11 | completed. |  |  |  |  | 6.114% | 100%
GIB & Equipment Civil Work | 24 | 2025-03-12 | 2025-04-04 | Nos | 52 | 52 | 0 | 2025-05-30 | 2025-12-12 | Completed. |  |  |  |  | 2.62% | 100% |  |  | 3.093% | 100%
Firewall-01 | 47 | 2025-02-27 | 2025-04-14 | Nos | 1 | 0.993 | 0.0070023 | 2025-03-29 | 2025-11-28 | Completed. |  |  |  |  | 5.131% | 99.3% |  |  | 6.057% | 99.3%
GIS PEB Erection | 21 | 2025-04-10 | 2025-04-30 | Lot | 1 | 1 | 0 | 2025-05-14 | 2025-06-22 | Completed. |  |  |  |  | 3.293% | 100% |  |  | 2.706% | 100%
MCR PEB Erection | 21 | 2025-04-10 | 2025-04-30 | Lot | 1 | 1 | 0 | 2025-06-09 | 2025-07-20 | Completed. |  |  |  |  | 3.293% | 100% |  |  | 2.706% | 100%
SGR - 01 PEB Erection | 22 | 2025-04-17 | 2025-05-08 | Lot | 1 | 1 | 0 | 2025-07-17 | 2025-12-27 | Completed. |  |  |  |  | 3.402% | 100% |  |  | 2.835% | 100%
Power Transformer - 01 Erection | 40 | 2025-04-26 | 2025-06-04 | Nos | 1 | 1.0625 | -0.0625 | 2025-06-10 | 2025-12-18 | Erection Completed on 24-Nov-25 |  |  |  |  | 4.367% | 106.2% |  |  | 5.155% | 106.2%
Power Transformer - 02 Erection | 40 | 2025-05-01 | 2025-06-09 | Nos | 1 | 1 | 0 | 2025-07-11 | 2025-12-13 | Erection Completed on 13-Dec-25 |  |  |  |  | 4.367% | 100% |  |  | 5.155% | 100%
SGR - 01 Panel Erection | 29 | 2025-05-09 | 2025-06-06 | Set | 4 | 4 | 0 | 2025-08-22 | 2025-09-06 | Completed. |  |  |  |  | 3.166% | 100% |  |  | 3.737% | 100%
GIS Main Bay Area (Inside Building) – Erection | 42 | 2025-05-13 | 2025-06-23 | Bays | 6 | 6 | 0 | 2025-07-02 | 2025-08-22 | Completed. |  |  |  |  | 6.585% | 100% |  |  | 9.412% | 100%
GIB & GAB (Outside Building) – Erection | 86 | 2025-03-31 | 2025-06-24 | Rm | 625 | 625 | 0 | 2025-09-02 | 2025-11-21 | Completed. |  |  |  |  | 5.389% | 100% |  |  | 7.082% | 100%
CRP – Area | 35 | 2025-05-07 | 2025-06-10 | Lot | 1 | 0.95833 | 0.041667 | 2025-07-15 |  | Erection Completed on 14-Nov-25 |  |  |  |  | 3.821% | 95.83% |  |  | 4.51% | 95.83%
MCR Panel Erection | 30 | 2025-05-15 | 2025-06-13 | Lot | 1 | 1 | 0 | 2025-07-17 | 2025-08-05 | Completed. |  |  |  |  | 3.275% | 100% |  |  | 3.866% | 100%
Equipment Erection | 25 | 2025-04-29 | 2025-05-23 | Nos | 39 | 39 | 0 | 2025-10-31 | 2025-11-27 | Completed. |  |  |  |  | 2.229% | 100% |  |  | 3.222% | 100%
SVG – Erection | 25 | 2025-06-01 | 2025-06-25 | Set | 7 | 7 | 0 | 2025-07-11 | [6 empty] | 2.729% | 100%
Harmonic Filter | 24 | 2025-05-23 | 2025-06-15 | Set | 4 | 4.0004 | -0.00035398 | 2025-06-23 | [6 empty] | 2.62% | 100%
Gantry Tower Erection | 29 | 2025-05-15 | 2025-06-12 | Nos | 2 | 2 | 0 | 2025-09-02 | 2025-11-20 | Completed. |  |  |  |  | 1.166% | 100% |  |  | 3.737% | 100%
Testing & ready for charging | 17 | 2025-06-24 | 2025-07-10 | Lot | 1 | 0.3 | 0.7 | 2025-09-05 |  | HV Test Completed |  |  |  |  | 2.856% | 30% |  |  | 2.191% | 30%
| 916 |  |  |  | 1 | 0.98069 | 0.019308
SGR - 02 Civil Work-Upto Slab | 46 | 2025-04-03 | 2025-05-18 | Lot | 1 | 1 | 5.3486e-07 | 2025-02-26 | [5 empty] | 0.0017699 | 8.142% | 100% | 60.87%
Power Transformer – 03 Civil Work | 62 | 2025-03-12 | 2025-05-12 | Nos | 1 | 1.0001 | -6.6041e-05 | 2025-02-20 |  | Main Foundation Completed |  |  |  |  | 10.97% | 100%
Power Transformer – 04 Civil Work | 61 | 2025-03-15 | 2025-05-14 | Nos | 1 | 1.0002 | -0.00017985 | 2025-02-18 |  | Main Foundation Completed |  |  |  |  | 10.8% | 100%
SVG Civil Work (Exc. Fencing) | 35 | 2025-03-05 | 2025-04-08 | Set | 8 | 3.0588 | 4.9412 | 2025-06-09 | [6 empty] | 6.195% | 38.24%
Harmonic Filter Civil Work | 56 | 2025-03-20 | 2025-05-14 | Nos | 4 | 2 | 2 | 2025-04-07 | 2025-12-11 | Completed. |  |  |  |  | 9.912% | 50%
Equipment Foundations | 24 | 2025-03-12 | 2025-04-04 | Nos | 12 | 12 | 0 | 2025-09-01 | 2025-12-12 | Completed. |  |  |  |  | 4.248% | 100%
Firewall-02 | 80 | 2025-03-15 | 2025-06-02 | Nos | 1 | 0.73754 | 0.26246 | 2025-03-09 | [6 empty] | 14.16% | 73.75%
SGR-02 PEB Erection | 31 | 2025-05-23 | 2025-06-22 | Lot | 1 | 0.55556 | 0.44444 | [7 empty] | 5.487% | 55.56%
Power Transformer – 03 Erection | 40 | 2025-06-04 | 2025-07-13 | Nos | 1 | 0.44444 | 0.55556 | [7 empty] | 7.08% | 44.44%
Power Transformer - 04 Erection | 40 | 2025-06-16 | 2025-07-25 | Nos | 1 | 0.33333 | 0.66667 | [7 empty] | 7.08% | 33.33%
SGR - 02 Panel Erection | 29 | 2025-06-22 | 2025-07-20 | Set | 4 | 0.25 | 3.75 | [7 empty] | 5.133% | 6.25%
SVG | 25 | 2025-06-01 | 2025-06-25 | Set | 8 | 0.125 | 7.875 | [7 empty] | 4.425% | 1.562%
Harmonic Filter | 24 | 2025-05-23 | 2025-06-15 | Set | 4 | 0 | 4 | [7 empty] | 4.248% | 0%
Ready for charging | 12 | 2025-07-20 | 2025-07-31 | Lot | 1 | 0 | 1 | 2025-12-22 | [6 empty] | 2.124% | 0%
| 565 |  |  |  | 1 | 0.60874 | 0.39126
400kv Transmission Line DPR
Description | UoM | Scope | Completed | Balance | Plan |  | Actual |  | Remarks | Vendor
[5 empty] | Start | End | Start | End
Foundation | Nos. | 28 | 28 | 0 | 2024-04-14 | 2025-02-02 | Completed
Tower Erection | Nos. | 28 | 28 | 0 | 2024-10-04 | 2025-03-25 | 2024-10-04 | 2025-04-23
Stringing | KM | 9.137 | 9.137 | 0 | 2025-03-01 | 2025-03-28 | 2025-03-31 | Completed
OPGW | KM | 9.137 | 9.137 | 0 | 2025-03-10 | 2025-03-30 | 2025-04-29 | Completed
Earthing | Nos. | 28 | 28 | 0 | 2025-03-20 | 2025-03-31 | 2025-03-16 | 2025-04-24

## PSS-6 DPR
| Khavda ¦ PSS-06 Progress status |  |  | 2023-10-15 | 2024-05-01 | [8 empty] | Progress As On
| Description of Activity | Priority | Duration | Plan |  | Actual/ Forecast |  | SO Vendor Name | UOM | Scope | Plan till Date | Actual till date | Balance Qty | 2026-02-27 | time axis 2025-02-01 to 2026-05-17
|  |  |  | Start | Finish | Start | Finish | [6 empty] | Remarks |  |  | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | time axis 1899-12-31 to 1901-04-07
|  |  | 197 | 2025-01-18 | 2025-08-02 | 2024-01-18
A | Stone Column Works | P1 | 28 | 2025-01-18 | 2025-02-14 | 2024-01-18 | 2024-02-14 | [8 empty] | A | A | A | A | A | A | A | A | bar: 1899-12-31 to 1901-04-07
Stone Column Works | GIS | P1 | 7 | 2025-01-18 | 2025-01-24 | 2024-01-18 | 2024-01-29 | M/s Saritha | Nos | 254 | 254 | 254 | 0 | Completed
Stone Column Works | Power Transformer -1 | P1 | 2 | 2025-01-25 | 2025-01-26 | 2024-01-27 | 2024-01-29 | M/s Saritha | Nos | 33 | 33 | 33 | 0 | Completed
Stone Column Works | Power Transformer -2 | P1 | 3 | 2025-01-26 | 2025-01-28 | 2024-01-29 | 2024-01-30 | M/s Saritha | Nos | 53 | 53 | 53 | 0 | Completed
Stone Column Works | Power Transformer -3 | P1 | 2 | 2025-01-28 | 2025-01-29 | 2024-01-30 | 2024-01-31 | M/s Saritha | Nos | 33 | 33 | 33 | 0 | Completed
Stone Column Works | Power Transformer -4 | P1 | 3 | 2025-01-29 | 2025-01-31 | 2024-01-31 | 2024-02-13 | M/s Saritha | Nos | 53 | 53 | 53 | 0 | Completed
Stone Column Works | Fire Wall | P1 | 2 | 2025-02-01 | 2025-02-02 | 2024-02-11 | 2024-02-13 | M/s Saritha | Nos | 46 | 46 | 46 | 0 | Completed
Stone Column Works | Gantry Tower | P1 | 2 | 2025-02-03 | 2025-02-14 | 2024-01-25 | 2024-02-14 | M/s Saritha | Nos | 50 | 50 | 50 | 0 | Completed
B | Civil Works |  | 144 | 2025-02-10 | 2025-07-03 | 2025-01-27
GIS Building-Civil | GIS Building | P1 | 86 | 2025-02-10 | 2025-05-06 | 2025-01-27
GIS Building-Civil | Excavation | P1 | 4 | 2025-02-10 | 2025-02-13 | 2025-01-27 | 2025-02-13 | M/s DNC | Cum | 2071.9 | 2071.9 | 2071.9 | 0 | Completed
GIS Building-Civil | Stone Blanket | P1 | 2 | 2025-02-22 | 2025-02-23 | 2025-02-12 | 2025-02-20 | M/s DNC | Cum | 499.2 | 499.2 | 499.2 | 0 | Completed
GIS Building-Civil | PCC | P1 | 2 | 2025-02-24 | 2025-02-25 | 2025-02-25 | 2025-02-26 | M/s DNC | Cum | 29.5 | 29.5 | 29.5 | 0 | Completed | [9 empty] | 1900-01-16: 14; 1900-01-17: 15
GIS Building-Civil | Raft Shuttering & Reinforcement | P1 | 4 | 2025-02-25 | 2025-02-28 | 2025-02-27 | 2025-03-19 | M/s DNC | Nos | 29 | 29 | 29 | 0 | Completed | [9 empty] | 1900-01-18: 1; 1900-01-19: 2; 1900-01-20: 1; 1900-01-21: 2; 1900-01-22: 2; 1900-01-23: 2; 1900-01-24: 1; 1900-01-25: 1; 1900-01-27: 2; 1900-01-28: 1; 1900-01-29: 2; 1900-01-31: 1; 1900-02-01: 2; 1900-02-03: 2; 1900-02-04: 1; 1900-02-05: 2; 1900-02-06: 2; 1900-02-07: 2
GIS Building-Civil | Raft - Casting | P1 | 5 | 2025-02-27 | 2025-03-03 | 2025-03-10 | 2025-03-19 | M/s DNC | Nos | 29 | 29 | 29 | 0 | Completed | [9 empty] | 1900-01-29: 2; 1900-01-30: 8; 1900-01-31: 2; 1900-02-03: 8; 1900-02-04: 3; 1900-02-05: 2; 1900-02-06: 2; 1900-02-07: 2
GIS Building-Civil | Column up to NGL | P1 | 6 | 2025-02-28 | 2025-03-05 | 2025-03-19 | 2025-03-25 | M/s DNC | Nos | 35 | 35 | 35 | 0 | Completed | [9 empty] | 1900-02-09: 5; 1900-02-10: 2; 1900-02-11: 2; 1900-02-12: 13; 1900-02-13: 13
GIS Building-Civil | Backfilling & Compaction | P1 | 2 | 2025-03-06 | 2025-03-07 | 2025-03-28 | 2025-04-05 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-02-16: 0.3; 1900-02-19: 0.3; 1900-02-20: 0.3; 1900-02-21: 0.05; 1900-02-24: 0.05
GIS Building-Civil | Tie Beam | P1 | 2 | 2025-03-07 | 2025-03-08 | 2025-04-02 | 2025-04-03 | M/s DNC | Nos | 40 | 40 | 40 | 0 | Completed | [9 empty] | 1900-02-27: 10; 1900-02-28: 17; 1900-03-01: 13
GIS Building-Civil | Columns Up to FFL | P1 | 8 | 2025-03-08 | 2025-03-15 | 2025-04-09 | 2025-04-11 | M/s DNC | Nos | 35 | 35 | 35 | 0 | Completed | [9 empty] | 1900-02-28: 7; 1900-03-01: 15; 1900-03-02: 13
GIS Building-Civil | Backfilling Up to FGL | P1 | 2 | 2025-03-16 | 2025-03-17 | 2025-04-11 | 2025-04-12 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-03-02: 0.4; 1900-03-03: 0.6
GIS Building-Civil | Slab Stagging & Shuttering | P1 | 9 | 2025-03-18 | 2025-03-26 | 2025-04-14 | 2025-04-22 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-03-05: 0.1; 1900-03-06: 0.4; 1900-03-09: 0.1; 1900-03-11: 0.05; 1900-03-12: 0.25; 1900-03-13: 0.1
GIS Building-Civil | Reinforcement & Bolts Fixing | P1 | 9 | 2025-03-27 | 2025-04-04 | 2025-04-17 | 2025-05-01 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-03-08: 0.1; 1900-03-10: 0.1; 1900-03-11: 0.15; 1900-03-12: 0.15; 1900-03-14: 0.1; 1900-03-15: 0.05; 1900-03-16: 0.05; 1900-03-17: 0.1; 1900-03-18: 0.1; 1900-03-21: 0.05; 1900-03-22: 0.05
GIS Building-Civil | Slab casting & Final Lift Bolt casting | P1 | 2 | 2025-04-05 | 2025-04-06 | 2025-05-02 | 2025-05-02 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-03-23
GIS Building-Civil | Handover to PEB Vendor | P1 |  |  | 2025-04-10 |  | 2025-05-09 | [6 empty] | Completed
GIS Building-Civil | Ironite Flooring - GIS Inside | P1 | 2 | 2025-05-01 | 2025-05-02 | 2025-06-04 | 2025-06-07 | M/s DNC | Sqm | 227.95 | 227.95 | 227.95 | 0 | Completed | [9 empty] | 1900-04-25: 50; 1900-04-26: 90; 1900-04-27: 52; 1900-04-28: 35.95
GIS Building-Civil | Epoxy Painting - 1st Coat | P1 | 1 | 2025-05-04 | 2025-05-04 | 2025-06-26 | 2025-06-29 | M/s DNC | Sqm | 227.95 | 227.95 | 227.95 | 0 | Completed | [9 empty] | 1900-05-20: 227.95
GIS Building-Civil | Epoxy Painting - 2nd Coat | P1 | 1 | 2025-05-05 | 2025-05-05 |  |  | M/s DNC | Sqm | 227.95 | 227.95 | 0 | 227.95
GIS Building-Civil | Ironite Flooring - CRP Room | P1 | 2 | 2025-05-01 | 2025-05-02 | 2025-06-04 | 2025-06-07 | M/s DNC | Sqm | 95.261 | 95.261 | 95.26 | 0.001 | Completed | [9 empty] | 1900-04-25: 22.96; 1900-04-26: 20; 1900-04-27: 24; 1900-04-28: 28.3
GIS Building-Civil | Epoxy Painting - 1st Coat | P1 | 1 | 2025-05-04 | 2025-05-04 | 2025-06-30 | 2025-06-30 | M/s DNC | Sqm | 95.261 | 95.261 | 95.26 | 0.001 | Completed | [9 empty] | 1900-05-21: 95.26
GIS Building-Civil | Epoxy Painting - 2nd Coat | P2 | 1 | 2025-05-05 | 2025-05-05 |  |  | M/s DNC | Sqm | 95.261 | 95.261 | 0 | 95.261
GIS Building-Civil | Handover to Electrical Vendor | P1 |  |  | 2025-05-06 |  | 2025-07-04 | [6 empty] | Completed
GIS Building-Civil | Staircase | P2
GIS Building-Civil | Excavation |  | 2 | 2025-04-13 | 2025-04-14 | 2025-06-02 | 2025-06-02 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-04-23
GIS Building-Civil | Base Slab -Formwork & shuttering | P2 | 1 | 2025-04-14 | 2025-04-15 | 2025-06-22 | 2025-06-23 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-05-13: 0.3; 1900-05-14: 0.7
GIS Building-Civil | Base Slab -Reinforcement | P2 | 4 | 2025-04-15 | 2025-04-18 | 2025-06-23 | 2025-06-24 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-05-14: 0.4; 1900-05-15: 0.6
GIS Building-Civil | Base Slab - Casting | P2 | 2 | 2025-04-19 | 2025-04-20 | 2025-06-24 | 2025-06-24 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-05-15
GIS Building-Civil | Base Slab - Tiling & Flooring | P2 | 2 | 2025-04-21 | 2025-04-22 |  |  | M/s DNC | Lot | 0 | 0 | 0 | 0
GIS Building-Civil | Handrails | P2 | 2 | 2025-04-22 | 2025-04-23 | 2025-07-07 | 2025-10-12 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-05-28: 0.7; 1900-08-22: 0.05; 1900-08-23: 0.05; 1900-08-26: 0.05; 1900-08-27: 0.05; 1900-08-30: 0.05; 1900-09-02: 0.05
GIS - PEB Erection | GIS - PEB Erection | P1 |  | 2025-04-10 | 2025-05-02 | 2025-05-14
GIS - PEB Erection | Erection of Primary Members | P1 | 13 | 2025-04-10 | 2025-04-22 | 2025-05-14 | 2025-05-24 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-03-26: 5%; 1900-03-27: 5%; 1900-04-06: 5%; 1900-04-07: 5%; 1900-04-08: 5%; 1900-04-09: 10%; 1900-04-10: 10%; 1900-04-11: 10%; 1900-04-12: 10%; 1900-04-13: 25%; 1900-04-14: 10%
GIS - PEB Erection | Erection of Secondary Members | P1 | 12 | 2025-04-12 | 2025-04-23 | 2025-05-20 | 2025-06-12 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-04-10: 5%; 1900-04-11: 5%; 1900-04-12: 20%; 1900-04-13: 15%; 1900-04-14: 5%; 1900-04-15: 5%; 1900-04-19: 10%; 1900-04-22: 5%; 1900-04-23: 5%; 1900-04-24: 5%; 1900-04-26: 5%; 1900-04-27: 5%; 1900-05-03: 10%
GIS - PEB Erection | Alignment and Levelling of Structures | P1 | 4 | 2025-04-24 | 2025-04-27 | 2025-05-30 | 2025-06-03 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-04-20: 50%; 1900-04-23: 20%; 1900-04-24: 30%
GIS - PEB Erection | Installation of Roof Panel | P1 | 15 | 2025-04-16 | 2025-04-30 | 2025-06-04 | 2025-06-05 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-04-25: 15%; 1900-04-26: 85%
GIS - PEB Erection | Installation of Wall Panel | P1 | 15 | 2025-04-16 | 2025-04-30 | 2025-06-06 | 2025-06-15 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-04-27: 0.05; 1900-04-28: 0.1; 1900-04-29: 0.05; 1900-04-30: 0.1; 1900-05-01: 0.1; 1900-05-02: 0.05; 1900-05-03: 0.05; 1900-05-04: 0.3; 1900-05-05: 0.1; 1900-05-06: 0.1
GIS - PEB Erection | Installation of Doors | P1 | 5 | 2025-04-26 | 2025-04-30 | 2025-06-23 | 2025-06-24 | M/s Bnal | Nos | 5 | 5 | 5 | 0 | Completed | [9 empty] | 1900-05-14: 2; 1900-05-15: 3
GIS - PEB Erection | Installation of Glass Wall | P1 | 3 | 2025-04-26 | 2025-04-28 | 2025-06-21 | 2025-06-23 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-05-11: 0.2; 1900-05-12: 0.3; 1900-05-13: 0.2; 1900-05-14: 0.3
GIS - PEB Erection | Installation of Rolling Shutter | P1 | 3 | 2025-04-28 | 2025-04-30 | 2025-06-15 | 2025-06-16 | M/s Bnal | Nos | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-05-06: 0.8; 1900-05-07: 0.2
GIS - PEB Erection | Canopy Works | P1 | 2 | 2025-05-01 | 2025-05-02 | 2025-06-22 | 2025-07-09 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-05-13: 0.3; 1900-05-14: 0.3; 1900-05-22: 0.3; 1900-05-30: 10%
GIS - PEB Erection | Front Handover to Civil (for Flooring Works) | P1 |  |  | 2025-04-30 |  | 2025-06-04 | [6 empty] | Completed
GIS - PEB Erection | Roof Flashing -Ridge Cap, Gutter & Downspout etc.. | P2 | 4 | 2025-04-26 | 2025-04-29 | 2025-06-20 | 2026-01-25 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-05-11: 0.1; 1900-05-12: 0.1; 1900-05-13: 0.1; 1900-11-02: 30%; 1900-12-15: 10%; 1900-12-16: 10%
GIS - PEB Erection | Wall Cladding & Flashing | P2 | 4 | 2025-04-27 | 2025-04-30 | 2025-06-20 | 2026-01-28 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-12-10 to 1900-12-19
GIS - PEB Erection | Leak & Waterproofing Tests | P2 | 1 | 2025-05-01 | 2025-05-01 | 2025-07-19 | 2025-07-19 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed
GIS - PEB Erection | EOT Crane - 7.5 MT | P1
GIS - PEB Erection | Rail Fixing & Alignment | P1 | 1 | 2025-04-23 | 2025-04-23 | 2025-06-08 | 2025-06-12 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-05-02: 0.5; 1900-05-03: 0.5
GIS - PEB Erection | EOT Bridge Girder, Winch erection | P1 | 1 | 2025-04-24 | 2025-04-24 | 2025-06-15 | 2025-06-18 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-05-06: 0.3; 1900-05-07: 0.2; 1900-05-08: 0.3; 1900-05-09: 0.2
GIS - PEB Erection | Control Panel erection & Testing | P1 | 1 | 2025-04-25 | 2025-04-25 | 2025-06-16 | 2025-06-20 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-05-08: 0.2; 1900-05-09: 0.3; 1900-05-10: 0.1; 1900-05-11: 0.4
GIS - PEB Erection | Load Test | P1 | 1 | 2025-05-01 | 2025-05-01 | 2025-06-21 | 2025-06-21 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-05-12
MCR Building- Civil | MCR Building | P1 | 86 | 2025-02-16 | 2025-05-12 | 2025-02-19
MCR Building- Civil | Excavation | P1 | 3 | 2025-02-16 | 2025-02-18 | 2025-02-19 | 2025-02-23 | M/s DNC | Cum | 1320.5 | 1320.5 | 1320.5 | 0 | Completed
MCR Building- Civil | Stone Blanket | P1 | 3 | 2025-02-19 | 2025-02-21 | 2025-02-24 | 2025-03-02 | M/s DNC | Cum | 249.1125 | 249.1125 | 249.1125 | 0 | Completed
MCR Building- Civil | PCC | P1 | 3 | 2025-02-22 | 2025-02-24 | 2025-03-03 | 2025-03-04 | M/s DNC | Nos | 7 | 7 | 7 | 0 | Completed
MCR Building- Civil | Raft Shuttering & Reinforcement | P1 | 9 | 2025-02-23 | 2025-03-03 | 2025-03-05 | 2025-04-05 | M/s DNC | Nos | 7 | 7 | 7 | 0 | Completed | [9 empty] | 1900-01-24: 1; 1900-02-04: 0.5; 1900-02-05: 0.5; 1900-02-08: 1; 1900-02-09: 1; 1900-02-15: 1; 1900-02-20: 1; 1900-02-24: 1
MCR Building- Civil | Raft - Casting | P1 | 7 | 2025-02-26 | 2025-03-04 | 2025-03-17 | 2025-04-05 | M/s DNC | Nos | 7 | 7 | 7 | 0 | Completed | bar: 1900-02-05; 1900-02-07; 1900-02-10 to 1900-02-11; 1900-02-16; 1900-02-21; 1900-02-24
MCR Building- Civil | Grade Beam - Shuttering & Casting | P1 | 5 | 2025-03-05 | 2025-03-09 | 2025-03-18 | 2025-04-05 | M/s DNC | Nos | 29 | 29 | 29 | 0 | Completed | [9 empty] | 1900-02-07: 2; 1900-02-08: 3; 1900-02-09: 5; 1900-02-12: 5; 1900-02-16: 5; 1900-02-21: 7; 1900-02-24: 2
MCR Building- Civil | Column up to NGL | P1 | 6 | 2025-03-10 | 2025-03-15 | 2025-03-27 | 2025-04-07 | M/s DNC | Nos | 29 | 29 | 29 | 0 | Completed | [9 empty] | 1900-02-15: 5; 1900-02-16: 5; 1900-02-18: 5; 1900-02-19: 4; 1900-02-20: 4; 1900-02-25: 4; 1900-02-26: 2
MCR Building- Civil | Backfilling & Compaction | P1 | 4 | 2025-03-16 | 2025-03-19 | 2025-04-05 | 2025-04-08 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-02-24: 0.8; 1900-02-26: 0.1; 1900-02-27: 0.1
MCR Building- Civil | Tie Beam | P1 | 3 | 2025-03-20 | 2025-03-22 | 2025-04-09 | 2025-04-14 | M/s DNC | Nos | 29 | 29 | 29 | 0 | Completed | [9 empty] | 1900-03-02: 11; 1900-03-03: 6; 1900-03-04: 7; 1900-03-05: 5
MCR Building- Civil | Columns | P1 | 5 | 2025-03-17 | 2025-03-21 | 2025-04-11 | 2025-04-15 | M/s DNC | Nos | 29 | 29 | 29 | 0 | Completed | [9 empty] | 1900-03-03: 12; 1900-03-04: 12; 1900-03-06: 5
MCR Building- Civil | Slab Stagging & Shuttering | P1 | 7 | 2025-03-21 | 2025-03-27 | 2025-04-21 | 2025-05-20 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-03-12: 0.1; 1900-03-14: 0.05; 1900-03-15: 0.05; 1900-03-16: 0.3; 1900-03-18: 0.05; 1900-03-19: 0.05; 1900-03-25: 1%; 1900-03-26: 2%; 1900-03-27: 5%; 1900-03-28: 5%; 1900-03-29: 5%; 1900-03-30: 3%; 1900-03-31: 1%; 1900-04-03: 1%; 1900-04-06: 2%; 1900-04-07: 2%; 1900-04-08: 2%; 1900-04-09: 6%; 1900-04-10: 5%
MCR Building- Civil | Reinforcement & Bolts Fixing | P1 | 7 | 2025-03-28 | 2025-04-03 | 2025-04-25 | 2025-06-02 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-03-27: 10%; 1900-03-28: 10%; 1900-03-29: 10%; 1900-04-11: 2.5%; 1900-04-12: 2.5%; 1900-04-13: 2.5%; 1900-04-14: 2.5%; 1900-04-18: 10%; 1900-04-19: 10%; 1900-04-20: 30%; 1900-04-22: 5%; 1900-04-23: 5%
MCR Building- Civil | Slab casting & Final Lift Bolt casting | P1 | 3 | 2025-04-04 | 2025-04-06 | 2025-06-03 | 2025-06-03 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-04-24
MCR Building- Civil | Handover to PEB Vendor | P1 |  |  | 2025-04-10 |  | 2025-06-08 | [6 empty] | completed
MCR Building- Civil | Finishing Works
MCR Building- Civil | Internal Partition Brick Walls - Battery Room | P1 | 2 | 2025-05-01 | 2025-05-02 | 2025-06-08 | 2025-06-20 | M/s DNc | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-04-29: 0.1; 1900-04-30: 0.4; 1900-05-02: 0.1; 1900-05-03: 0.05; 1900-05-04: 0.2; 1900-05-11: 0.15
MCR Building- Civil | Internal Partition Brick Walls - Toilet Room | P1 | 2 | 2025-05-03 | 2025-05-04 | 2025-06-10 | 2025-07-27 | M/s DNc | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-05-01: 0.05; 1900-05-02: 0.1; 1900-05-03: 0.3; 1900-05-22: 0.15; 1900-05-24: 0.2; 1900-06-16: 0.1; 1900-06-17: 0.1
MCR Building- Civil | Internal Partition Brick Walls - Pantry Room | P1 | 2 | 2025-05-05 | 2025-05-06 | 2025-06-10 | 2025-07-04 | M/s DNc | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-05-01: 0.05; 1900-05-02: 0.1; 1900-05-03: 0.3; 1900-05-22: 0.15; 1900-05-23: 0.3; 1900-05-25: 0.1
MCR Building- Civil | EWC Installation | P1 | 1 | 2025-05-04 | 2025-05-04 | 2025-12-27 | 2025-12-27 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-17: 100%
MCR Building- Civil | Wall-Mounted Urinals | P1 | 1 | 2025-05-05 | 2025-05-05 | 2025-12-28 | 2025-12-28 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-18: 100%
MCR Building- Civil | Wash basin | P1 | 1 | 2025-05-05 | 2025-05-05 | 2025-12-29 | 2025-12-29 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-19: 100%
MCR Building- Civil | Tile Work- SCADA | P1 | 1 | 2025-05-06 | 2025-05-06 | 2025-07-07 | 2025-07-11 | M/s DNc | Lot | 1 | 1 | 0.95 | 0.05 | Completed | [9 empty] | 1900-05-28: 0.05; 1900-05-29: 0.3; 1900-05-30: 0.4; 1900-05-31: 0.1; 1900-06-01: 0.1
MCR Building- Civil | Tile Work- Toilet | P1 | 1 | 2025-05-07 | 2025-05-07 | 2025-11-16 | 2025-12-21 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-07: 10%; 1900-10-11: 50%; 1900-11-04: 20%; 1900-11-11: 20%
MCR Building- Civil | Tile Work- Battery Room | P1 | 1 | 2025-05-07 | 2025-05-07 | 2025-06-30 | 2025-07-07 | M/s DNc | Sqm | 129.83 | 129.83 | 129.829 | 0.00097368 | Completed | [9 empty] | 1900-05-21: 25.966; 1900-05-22: 12.983; 1900-05-24: 6.4915; 1900-05-25: 12.983; 1900-05-26: 25.966; 1900-05-27: 25.966; 1900-05-28: 19.4735
MCR Building- Civil | Tile Work- Electrical Lab Room | P1 | 1 | 2025-05-08 | 2025-05-08 | 2025-07-13 | 2025-07-14 | M/s DNc | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-06-03: 0.4; 1900-06-04: 0.6
MCR Building- Civil | Tile Work- IT, Manager | P1 | 1 | 2025-05-08 | 2025-05-08 | 2025-07-14 | 2025-07-17 | M/s DNc | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-06-04: 0.5; 1900-06-07: 0.5
MCR Building- Civil | Tile Work- Pantry Rooms | P1 | 1 | 2025-05-08 | 2025-05-08 | 2025-07-20 | 2025-07-22 | M/s DNc | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-06-10: 0.2; 1900-06-11: 0.5; 1900-06-12: 0.3
MCR Building- Civil | Tile Work- Conference Rooms | P1 | 1 | 2025-05-08 | 2025-05-08 | 2025-07-12 | 2025-07-13 | M/s DNc | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-06-03
MCR Building- Civil | False Ceiling- SCADA Room | P1 | 1 | 2025-05-08 | 2025-05-08 | 2025-07-14 | 2025-07-19 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-06-04: 0.1; 1900-06-05: 0.4; 1900-06-07: 0.2; 1900-06-09: 0.3
MCR Building- Civil | False Ceiling- Toilet, Room | P1 | 1 | 2025-05-08 | 2025-05-08 | 2025-08-08 | 2025-08-09 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-06-29: 0.5; 1900-06-30: 0.5
MCR Building- Civil | False Ceiling- CRP Room | P1 | 1 | 2025-05-08 | 2025-05-08 | 2025-07-11 | 2025-07-13 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-06-05
MCR Building- Civil | False Ceiling- Electrical Lab Room | P1 | 2 | 2025-05-09 | 2025-05-10 | 2026-07-16 | 2025-08-01 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-06-07: 0.1; 1900-06-12: 0.4; 1900-06-22: 0.5
MCR Building- Civil | False Ceiling- IT, Manager Room | P1 | 1 | 2025-05-10 | 2025-05-10 | 2025-08-02 | 2025-08-03 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-06-23: 0.5; 1900-06-24: 0.5
MCR Building- Civil | False Ceiling- Pantry, Room | P1 | 1 | 2025-05-10 | 2025-05-10 | 2025-08-04 | 2025-08-05 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-06-25: 0.5; 1900-06-26: 0.5
MCR Building- Civil | False Ceiling- DB Rooms | P1 | 1 | 2025-05-10 | 2025-05-10 | 2025-08-01 | 2025-08-02 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-06-22: 0.5; 1900-06-23: 0.5
MCR Building- Civil | Ironite Flooring- LT SGR | P1 | 1 | 2025-05-11 | 2025-05-11 | 2025-06-04 | 2025-06-04 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-04-25
MCR Building- Civil | Ironite Flooring- AHU | P1 | 1 | 2025-05-11 | 2025-05-11 | 2025-06-04 | 2025-06-04 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-04-25
MCR Building- Civil | Ironite Flooring- AUX Rooms | P1 | 1 | 2025-05-11 | 2025-05-11 | 2025-06-04 | 2025-06-04 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-04-25
MCR Building- Civil | Ironite Flooring- DG Area | P1 | 1 | 2025-05-11 | 2025-05-11 | 2025-06-04 | 2025-06-04 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-04-25
MCR Building- Civil | Epoxy Painting - 1st Coat - LT SGR | P1 | 1 | 2025-05-12 | 2025-05-12 | 2025-07-02 | 2025-07-02 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-05-23
MCR Building- Civil | Epoxy Painting - 2nd Coat - LT SGR | P1 | 1 | 2025-05-12 | 2025-05-12 |  |  |  | Lot | 1 | 1 | 0 | 1
MCR Building- Civil | Epoxy Painting - 1st Coat- DB Room | P1 | 1 | 2025-05-12 | 2025-05-12 | 2025-07-02 | 2025-07-02 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-05-23
MCR Building- Civil | Epoxy Painting - 2nd Coat- DB Room | P1 | 1 | 2025-05-11 | 2025-05-11 |  |  |  | Lot | 1 | 1 | 0 | 1
MCR Building- Civil | Staircase | P1 | 9
MCR Building- Civil | Base Slab -Formwork & shuttering | P1 | 1 | 2025-04-07 | 2025-04-08 | 2025-12-04 | 2025-12-05 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-25: 50%; 1900-10-26: 50%
MCR Building- Civil | Base Slab -Reinforcement | P1 | 4 | 2025-04-08 | 2025-04-11 | 2025-12-05 | 2025-12-10 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-26: 50%; 1900-10-31: 50%
MCR Building- Civil | Base Slab - Casting | P1 | 2 | 2025-04-12 | 2025-04-13 | 2025-12-13 | 2025-12-16 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-03: 50%; 1900-11-06: 50%
MCR Building- Civil | Base Slab - Tiling & Flooring | P1 | 0 | 2025-04-14 | 2025-04-13 | NA | NA | M/s DNC | Lot | 1 | 1 | 0 | 1
MCR Building- Civil | Handrails | P1 | 2 | 2025-04-13 | 2025-04-14 | 2026-01-31 | 2026-01-31 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-12-22: 100%
MCR- PEB | MCR- PEB | P1 | 28 | 2025-04-10 | 2025-05-07 | 2025-06-09
MCR- PEB | Erection of Primary Members | P1 | 13 | 2025-04-10 | 2025-04-22 | 2025-06-09 | 2025-06-16 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-04-30: 0.1; 1900-05-01: 0.3; 1900-05-02: 0.1; 1900-05-03: 0.1; 1900-05-04: 0.05; 1900-05-05: 0.1; 1900-05-06: 0.05; 1900-05-07: 0.2
MCR- PEB | Erection of Secondary Members | P1 | 12 | 2025-04-12 | 2025-04-23 | 2025-06-12 | 2025-07-05 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-05-03: 0.2; 1900-05-04: 0.05; 1900-05-06: 0.05; 1900-05-07: 0.05; 1900-05-08: 0.3; 1900-05-10: 0.05; 1900-05-11: 0.02; 1900-05-12: 0.025; 1900-05-13: 0.025; 1900-05-24: 0.13; 1900-05-26: 0.1
MCR- PEB | Alignment and Levelling of Structures | P1 | 4 | 2025-04-24 | 2025-04-27 | 2025-06-14 | 2025-06-17 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-05-05: 0.15; 1900-05-06: 0.15; 1900-05-07: 0.05; 1900-05-08: 0.65
MCR- PEB | Installation of Roof Panel | P1 | 15 | 2025-04-16 | 2025-04-30 | 2025-06-15 | 2025-06-19 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-05-06: 0.1; 1900-05-08: 0.45; 1900-05-09: 0.3; 1900-05-10: 0.15
MCR- PEB | Installation of Wall Panel | P1 | 15 | 2025-04-16 | 2025-04-30 | 2025-06-20 | 2025-07-14 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-05-11: 0.5; 1900-05-12: 0.3; 1900-05-13: 0.1; 1900-05-21: 0.05; 1900-06-04: 0.05
MCR- PEB | Installation of Doors | P1 | 3 | 2025-04-26 | 2025-04-28 | 2025-07-17 | 2025-09-03 | M/s Bnal | Nos | 21 | 21 | 21 | 0 | Completed | [9 empty] | 1900-06-14: 2; 1900-06-15: 6; 1900-06-16: 6; 1900-06-17: 1; 1900-07-04: 2; 1900-07-24: 2; 1900-07-25: 2
MCR- PEB | Installation of Windows | P1 | 3 | 2025-04-28 | 2025-04-30 | 2025-09-03 | 2025-09-03 | M/s Bnal | Nos | 1 | 1 | 1 | 0 | Completed | bar: 1900-07-25
MCR- PEB | Installation of Rolling Shutter & Openings | P1 | 3 | 2025-04-28 | 2025-04-30 | 2025-07-17 | 2025-07-20 | M/s Bnal | Nos | 3 | 3 | 3 | 0 | Completed | [9 empty] | 1900-06-07: 2; 1900-06-10: 1
MCR- PEB | Installation of Internal Partition Walls | P1 | 10 | 2025-04-28 | 2025-05-07 | 2025-06-23 | 2025-07-08 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-05-14: 0.1; 1900-05-15: 0.05; 1900-05-16: 0.1; 1900-05-17: 0.05; 1900-05-21: 0.3; 1900-05-23: 0.3; 1900-05-29: 0.1
MCR- PEB | Front Handover to Electrical | P1 |  |  | 2025-05-01 | 2025-07-14 | 2025-08-02 | [6 empty] | Completed
MCR- PEB | Roof Flashing -Ridge Cap, Gutter & Downspout etc.. | P1 | 9 | 2025-04-26 | 2025-05-04 | 2025-06-22 | 2026-01-25 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-05-13: 0.11; 1900-05-16: 0.04; 1900-05-21: O.05; 1900-05-23: 0.1; 1900-05-24: 0.05; 1900-05-28: 0.05; 1900-05-29: 0.1; 1900-12-08: 15%; 1900-12-09: 15%; 1900-12-12: 5%; 1900-12-13: 5%; 1900-12-14: 5%; 1900-12-15: 5%; 1900-12-16: 5%
MCR- PEB | Wall Flashing | P1 | 6 | 2025-04-28 | 2025-05-03 | 2025-06-22 | 2026-01-27 | M/s Bnal | Lot | 1 | 1 | 1.001 | -0.001 | Completed | [9 empty] | 1900-12-08: 0.1; 1900-12-09: 0.1%; 1900-12-10: 5%; 1900-12-11: 5%; 1900-12-12: 5%; 1900-12-13: 10%; 1900-12-14: 5%; 1900-12-15: 5%; 1900-12-16: 5%; 1900-12-18: 10%
MCR- PEB | Leak & Waterproofing Tests | P1 | 1 | 2025-05-04 | 2025-05-04 | 2025-08-18 | 2025-08-18 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed
SGR - 01 Civil | SGR - 01 Civil | P1 | 3 | 2025-02-26 | 2025-05-05 | 2025-03-18
SGR - 01 Civil | Excavation | P1 | 3 | 2025-02-26 | 2025-02-28 | 2025-03-18 | 2025-03-20 | M/s DNC | Cum | 1654.8 | 1654.8 | 1654.8 | 0 | Completed | 1 | [8 empty] | 1900-02-06: 600; 1900-02-07: 630; 1900-02-08: 424.8
SGR - 01 Civil | Stone Blanket | P1 | 4 | 2025-03-02 | 2025-03-05 | 2025-03-31 | 2025-04-12 | M/s DNC | Cum | 389.5125 | 389.5125 | 389.51 | 0.0025 | Completed | 0.99999 | [8 empty] | 1900-02-20: 10; 1900-02-21: 90; 1900-02-23: 100; 1900-03-03: 179.51
SGR - 01 Civil | Raft - PCC | P1 | 3 | 2025-03-05 | 2025-03-07 | 2025-04-05 | 2025-04-17 | M/s DNC | Nos | 18 | 18 | 18 | 0 | Completed | 1 | [8 empty] | 1900-02-24: 5; 1900-02-25: 5; 1900-03-06: 2; 1900-03-08: 6
SGR - 01 Civil | Raft - Casting | P1 | 6 | 2025-03-07 | 2025-03-12 | 2025-04-05 | 2025-06-11 | M/s DNC | Nos | 18 | 18 | 18 | 0 | Completed | 1 | [8 empty] | 1900-03-07: 2; 1900-03-09: 2; 1900-03-12: 2; 1900-03-25: 2; 1900-03-28: 2; 1900-03-29: 2; 1900-04-13: 2; 1900-05-02: 4
SGR - 01 Civil | Grade Beam - PCC | P1 | 3 | 2025-03-05 | 2025-03-07 | 2025-04-05 | 2025-05-08 | M/s DNC | Nos | 49 | 49 | 49 | 0 | Completed | 1 | [8 empty] | 1900-02-24: 13; 1900-02-25: 13; 1900-03-07: 2; 1900-03-09: 8; 1900-03-13: 11; 1900-03-29: 2
SGR - 01 Civil | Grade Beam - Shuttering & Casting | P1 | 6 | 2025-03-12 | 2025-03-17 | 2025-04-05 | 2025-06-11 | M/s DNC | Nos | 49 | 49 | 49 | 0 | Completed | 1 | [8 empty] | 1900-03-07: 6; 1900-03-09: 6; 1900-03-12: 5; 1900-03-25: 6; 1900-05-02: 26
SGR - 01 Civil | Columns up to NGL | P1 | 4 | 2025-03-17 | 2025-03-20 | 2025-04-25 | 2025-06-14 | M/s DNC | Nos | 54 | 54 | 54 | 0 | Completed | 1 | [8 empty] | 1900-03-30: 12; 1900-04-16: 14; 1900-04-26: 14; 1900-05-05: 14
SGR - 01 Civil | Tie Beam | P1 | 3 | 2025-03-20 | 2025-03-22 | 2025-06-09 | 2025-06-23 | M/s DNC | Nos | 30 | 30 | 30 | 0 | Completed | 1 | [8 empty] | 1900-05-01: 10; 1900-05-02: 5; 1900-05-09: 3; 1900-05-14: 12
SGR - 01 Civil | Columns Up to FFL | P1 | 3 | 2025-03-22 | 2025-03-24 | 2025-06-11 | 2025-06-24 | M/s DNC | Nos | 54 | 54 | 54 | 0 | Completed | 1 | [8 empty] | 1900-05-02: 5; 1900-05-03: 15; 1900-05-04: 13; 1900-05-15: 21
SGR - 01 Civil | Backfilling & Compaction | P1 | 3 | 2025-03-24 | 2025-03-26 | 2025-06-03 | 2025-06-25 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-04-24: 0.4; 1900-04-29: 0.1; 1900-05-02: 0.1; 1900-05-03: 0.05; 1900-05-04: 0.05; 1900-05-07: 0.05; 1900-05-08: 0.05; 1900-05-11: 0.1; 1900-05-14: 0.05; 1900-05-16: 0.05
SGR - 01 Civil | Slab Stagging & Shuttering | P1 | 8 | 2025-03-26 | 2025-04-02 | 2025-06-14 | 2025-07-11 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-05-05: 0.05; 1900-05-06: 0.05; 1900-05-07: 0.2; 1900-05-08: 0.2; 1900-05-13: 0.1; 1900-05-14: 0.1; 1900-05-21: 0.1; 1900-05-23: 0.1; 1900-06-01: 0.1
SGR - 01 Civil | Reinforcement & Bolts Fixing | P1 | 7 | 2025-04-02 | 2025-04-08 | 2025-06-17 | 2025-07-11 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-05-08: 0.1; 1900-05-11: 0.05; 1900-05-12: 0.05; 1900-05-13: 0.03; 1900-05-14: 0.12; 1900-05-15: 0.05; 1900-05-16: 0.05; 1900-05-19: 0.05; 1900-05-30: 0.3; 1900-06-01: 0.2
SGR - 01 Civil | Slab casting & Final Lift Bolt casting | P1 | 2 | 2025-04-09 | 2025-04-10 | 2025-07-12 | 2025-07-12 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | 1 | bar: 1900-06-02
SGR - 01 Civil | Handover to PEB Vendor | P1 |  |  | 2025-04-17 |  | 2025-07-19
SGR - 01 Civil | Ironite Flooring | P1 | 3 | 2025-04-30 | 2025-05-02 | 2025-07-15 | 2025-08-02 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-06-05: 0.2; 1900-06-08: 0.1; 1900-06-21: 0.3; 1900-06-22: 0.1; 1900-06-23: 0.3
SGR - 01 Civil | Handover to Electrical Vendor | P2 |  |  | 2025-05-05 |  | 2025-08-22
SGR - 01 Civil | Staircase | P1
SGR - 01 Civil | Base Slab -Formwork & shuttering | P1 | 1 | 2025-04-17 | 2025-04-18 | 2025-11-10 | 2025-11-12 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-01: 0.1; 1900-10-03: 0.9
SGR - 01 Civil | Base Slab -Reinforcement | P1 | 4 | 2025-04-18 | 2025-04-21 | 2025-11-12 | 2025-11-18 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-03: 0.2; 1900-10-04: 0.2; 1900-10-05: 0.1; 1900-10-09: 0.5
SGR - 01 Civil | Base Slab - Casting | P1 | 2 | 2025-04-22 | 2025-04-23 | 2025-11-13 | 2025-11-23 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-05: 0.5; 1900-10-14: 0.5
SGR - 01 Civil | Handrails | P1 | 2 | 2025-04-25 | 2025-04-26 | 2026-02-02 | 2026-02-02 |  | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-12-24
SGR - 01 Civil | Ramp | P1
SGR - 01 Civil | PCC | P1 | 1 | 2025-04-18 | 2025-04-19 | 2026-01-17 | 2026-01-18 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-12-08: 0.5; 1900-12-09: 50%
SGR - 01 Civil | Shuttering & Reinforcement | P1 | 4 | 2025-04-19 | 2025-04-22 | 2026-01-18 |  | M/s DNC | Lot | 1 | 1 | 0.5 | 0.5 | [10 empty] | 1900-12-09: 0.5
SGR - 01 Civil | Wall Casting | P1 | 2 | 2025-04-23 | 2025-04-24 | 2026-01-19 |  | M/s DNC | Lot | 1 | 1 | 0 | 1
SGR - 01 Civil | Flooring | P1 | 2 | 2025-04-25 | 2025-04-26 |  |  | M/s DNC | Lot | 1 | 1 | 0 | 1
SGR - 01 Civil | AHU Duct foundation-SGR-01 | P1
SGR - 01 Civil | Excavation | P1 | 2 | 2025-04-18 | 2025-04-19 | 2025-11-28 | 2025-11-28 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-19: 100%
SGR - 01 Civil | PCC | P1 | 2 | 2025-04-21 | 2025-04-22 | 2025-11-28 | 2025-11-28 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-19: 100%
SGR - 01 Civil | Raft | P1 | 4 | 2025-04-23 | 2025-04-26 | 2025-12-03 | 2025-12-05 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-24: 50%; 1900-10-26: 50%
SGR - 01 Civil | Column | P1 | 4 | 2025-04-26 | 2025-04-29 | 2025-12-07 | 2025-12-20 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-05: 50%; 1900-11-10: 50%
SGR - 01 Civil | Slab casting | P1 | 6 | 2025-04-29 | 2025-05-04 | 2026-01-04 | 2026-01-05 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-26: 100%
SGR-01 PEB | SGR -01 PEB | P1 | 25 | 2025-04-17 | 2025-05-11 | 2025-07-31 | bar: 1899-12-31 to 1900-07-22
SGR-01 PEB | Erection of Primary Members | P1 | 7 | 2025-04-17 | 2025-04-23 | 2025-07-31 | 2025-08-04 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-06-22: 0.3; 1900-06-23: 0.1; 1900-06-24: 0.25; 1900-06-25: 0.35
SGR-01 PEB | Erection of Secondary Members | P1 | 6 | 2025-04-24 | 2025-04-29 | 2025-08-04 | 2025-08-10 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-06-25: 0.1; 1900-06-26: 0.1; 1900-06-27: 0.05; 1900-06-28: 0.2; 1900-06-29: 0.15; 1900-06-30: 0.2; 1900-07-01: 0.2
SGR-01 PEB | Alignment and Levelling of Structures | P1 | 5 | 2025-04-30 | 2025-05-04 | 2025-08-09 | 2025-08-10 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-06-30: 0.5; 1900-07-01: 0.5
SGR-01 PEB | Installation of Roof Panel | P1 | 10 | 2025-04-25 | 2025-05-04 | 2025-08-11 | 2025-08-13 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-07-02: 0.5; 1900-07-04: 0.5
SGR-01 PEB | Installation of Wall Panel | P1 | 10 | 2025-04-25 | 2025-05-04 | 2025-08-14 | 2025-08-21 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-07-05: 0.1; 1900-07-06: 0.3; 1900-07-07: 0.3; 1900-07-08: 0.1; 1900-07-09: 0.05; 1900-07-10: 0.05; 1900-07-11: 0.05; 1900-07-12: 0.05
SGR-01 PEB | Canopy Works | P1 | 1 | 2025-05-05 | 2025-05-05 | 2025-08-14 | 2026-01-09 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-07-05: 0.5; 1900-11-29: 0.3; 1900-11-30: 0.2
SGR-01 PEB | Front Handover to Civil (for Flooring Works) | P1 |  |  | 2025-05-05 |  | 2025-07-15
SGR-01 PEB | Installation of Doors | P1 | 4 | 2025-05-05 | 2025-05-08 | 2025-12-01 | 2025-12-05 | M/s Bnal | Nos | 2 | 2 | 2 | 0 | Completed | 0.5 | bar: 1900-10-22; 1900-10-26
SGR-01 PEB | Installation of Rolling Shutter | P1 | 4 | 2025-05-05 | 2025-05-08 | 2025-09-06 | 2025-12-27 | M/s Bnal | Nos | 2 | 2 | 2 | 0 | Completed | 0.5 | bar: 1900-07-29; 1900-11-17
SGR-01 PEB | Flashing and Finishing Work Etc. | P1 | 5 | 2025-05-06 | 2025-05-10 | 2025-08-20 | 2026-02-04 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-07-11: 0.05; 1900-07-12: 0.05; 1900-07-17: 0.1; 1900-07-18: 0.1; 1900-10-19: 20%; 1900-12-09: 10%; 1900-12-10: 10%; 1900-12-26: 0.3
SGR-01 PEB | AHU Works | P1
SGR-01 PEB | Duct Assembly & Erection | P1 | 5 | 2025-05-05 | 2025-05-09 | 2025-08-18 | 2025-12-05 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-07-09: 30%; 1900-07-10: 20%; 1900-07-11: 30%; 1900-10-26: 20%
SGR-01 PEB | Duct Installation with grills | P1 | 2 | 2025-05-10 | 2025-05-11 | 2025-08-20 |  | M/s Hyosung | Lot | 1 | 1 | 0.6 | 0.4 | [10 empty] | 1900-07-11: 30%; 1900-07-12: 30%
SGR - 02 Civil | SGR - 02 Civil | P2 | 83 | 2025-04-03 | 2025-06-24 | 2025-02-26 | bar: 1900-02-22 to 1900-07-22
SGR - 02 Civil | Excavation | P2 | 3 | 2025-04-03 | 2025-04-05 | 2025-02-26 | 2025-03-01 | M/s DNC | Cum | 1654.8 | 1654.8 | 1654.8 | 0 | Completed | 1
SGR - 02 Civil | Stone Blanket | P2 | 3 | 2025-04-05 | 2025-04-07 | 2025-03-17 | 2025-11-06 | M/s DNC | Cum | 389.5125 | 389.5125 | 389.51 | 0.0025 | Completed | 0.99999 | [8 empty] | 1900-02-05: 37; 1900-02-06: 30; 1900-02-16: 23; 1900-02-19: 60; 1900-02-21: 20; 1900-05-11: 130; 1900-09-27: 89.51
SGR - 02 Civil | Raft-PCC | P2 | 3 | 2025-04-07 | 2025-04-09 | 2025-03-22 | 2025-12-14 | M/s DNC | Nos | 18 | 18 | 18 | 0 | Completed | 1 | [8 empty] | 1900-02-10: 1; 1900-02-11: 1; 1900-02-12: 1; 1900-02-19: 2; 1900-02-21: 2; 1900-05-11: 4; 1900-06-17: 2; 1900-06-18: 2; 1900-10-26: 1; 1900-11-04: 2
SGR - 02 Civil | Raft - Casting | P2 | 8 | 2025-04-09 | 2025-04-16 | 2025-06-12 | 2025-12-17 | M/s DNC | Nos | 18 | 18 | 18 | 0 | Completed | 1 | [8 empty] | 1900-05-10: 3; 1900-05-14: 3; 1900-05-16: 1; 1900-06-14: 2; 1900-06-15: 2; 1900-06-23: 1; 1900-06-25: 1; 1900-06-27: 1; 1900-09-27: 1; 1900-11-05: 1; 1900-11-07: 2
SGR - 02 Civil | Grade Beam - Shuttering & Casting | P2 | 8 | 2025-04-16 | 2025-04-23 | 2025-06-19 | 2025-12-17 | M/s DNC | Nos | 49 | 49 | 49 | 0 | Completed | 1 | [8 empty] | 1900-05-10: 5; 1900-05-14: 9; 1900-05-16: 3; 1900-06-14: 6; 1900-06-15: 6; 1900-06-25: 3; 1900-06-27: 3; 1900-11-05: 3; 1900-11-07: 11
SGR - 02 Civil | Columns up to NGL | P2 | 7 | 2025-04-23 | 2025-04-29 | 2025-06-23 | 2025-12-20 | M/s DNC | Nos | 54 | 54 | 54 | 0 | Completed | 1 | [8 empty] | 1900-06-13: 14; 1900-06-14: 1; 1900-06-15: 6; 1900-06-19: 3; 1900-06-21: 8; 1900-07-20: 6; 1900-07-21: 4; 1900-10-25: 5; 1900-11-10: 7
SGR - 02 Civil | Backfilling & Compaction | P2 | 2 | 2025-04-29 | 2025-04-30 | 2025-12-20 | 2025-12-28 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-11-10: 30%; 1900-11-11: 20%; 1900-11-18: 50%
SGR - 02 Civil | Tie Beam | P2 | 2 | 2025-04-30 | 2025-05-01 | 2025-12-21 | 2025-12-29 | M/s DNC | Nos | 30 | 30 | 30 | 0 | Completed | 1 | [8 empty] | 1900-11-11: 9; 1900-11-13: 6; 1900-11-15: 5; 1900-11-17: 5; 1900-11-19: 5
SGR - 02 Civil | Columns Up to FFL | P2 | 3 | 2025-05-01 | 2025-05-03 | 2025-12-26 | 2026-01-05 | M/s DNC | Nos | 54 | 54 | 54 | 0 | Completed | 1 | [8 empty] | 1900-11-16: 10; 1900-11-17: 5; 1900-11-18: 10; 1900-11-19: 5; 1900-11-20: 10; 1900-11-21: 5; 1900-11-24: 2; 1900-11-25: 2; 1900-11-26: 5
SGR - 02 Civil | Slab Stagging & Shuttering | P2 | 8 | 2025-05-03 | 2025-05-10 | 2026-01-03 | 2026-01-20 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-11-24: 5%; 1900-11-25: 5%; 1900-11-26: 10%; 1900-11-27: 5%; 1900-11-28: 5%; 1900-11-29: 10%; 1900-11-30: 5%; 1900-12-01: 5%; 1900-12-02: 5%; 1900-12-03: 10%; 1900-12-04: 5%; 1900-12-05: 5%; 1900-12-06: 5%; 1900-12-11: 20%
SGR - 02 Civil | Reinforcement & Bolts Fixing | P2 | 8 | 2025-05-09 | 2025-05-16 | 2026-01-11 | 2026-01-30 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-12-02: 3%; 1900-12-03: 3%; 1900-12-04: 3%; 1900-12-05: 3%; 1900-12-06: 3%; 1900-12-07: 3%; 1900-12-08: 5%; 1900-12-09: 5%; 1900-12-10: 5%; 1900-12-11: 2%; 1900-12-12: 5%; 1900-12-13: 5%; 1900-12-14: 5%; 1900-12-15: 5%; 1900-12-16: 5%; 1900-12-18: 10%; 1900-12-19: 10%; 1900-12-20: 10%; 1900-12-21: 10%
SGR - 02 Civil | Slab casting & Final Lift Bolt casting | P2 | 2 | 2025-05-17 | 2025-05-18 | 2026-02-01 | 2026-02-01 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-12-23: 100%
SGR - 02 Civil | Handover to PEB Vendor | P2 |  |  | 2025-05-22
SGR - 02 Civil | Ironite Flooring | P2 | 3 | 2025-06-19 | 2025-06-21 | 2026-02-02 | 2026-02-05 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-12-24: 20%; 1900-12-25: 20%; 1900-12-26: 30%; 1900-12-27: 30%
SGR - 02 Civil | Handover to Electrical Vendor | P2 |  |  | 2025-06-24
SGR - 02 Civil | Staircase | P2
SGR - 02 Civil | Base Slab -Formwork & shuttering | P2 | 1 | 2025-05-22 | 2025-05-23 | 2026-02-16 |  | M/s DNC | Nos | 2 | 2 | 1 | 1 | bar: 1901-01-07
SGR - 02 Civil | Base Slab -Reinforcement | P2 | 4 | 2025-05-23 | 2025-05-26 | 2026-02-17 |  | M/s DNC | Nos | 2 | 2 | 1 | 1 | bar: 1901-01-08
SGR - 02 Civil | Base Slab - Casting | P2 | 2 | 2025-05-27 | 2025-05-28 | 2026-02-18 |  | M/s DNC | Nos | 2 | 2 | 1 | 1 | bar: 1901-01-09
SGR - 02 Civil | Base Slab - Tiling & Flooring | P2 | 2 | 2025-05-29 | 2025-05-30 |  |  | M/s DNC | Nos | 2 | 2 | 0 | 2
SGR - 02 Civil | Handrails | P2 | 2 | 2025-05-30 | 2025-05-31 |  |  | M/s DNC | Nos | 2 | 2 | 0 | 2
SGR - 02 Civil | Ramp | P2
SGR - 02 Civil | PCC | P2 | 1 | 2025-05-23 | 2025-05-24 |  |  | M/s DNC | Lot | 1 | 1 | 0 | 1
SGR - 02 Civil | Shuttering & Reinforcement | P2 | 4 | 2025-05-24 | 2025-05-27 |  |  | M/s DNC | Lot | 1 | 1 | 0 | 1
SGR - 02 Civil | Wall Casting | P2 | 2 | 2025-05-28 | 2025-05-29 |  |  | M/s DNC | Lot | 1 | 1 | 0 | 1
SGR - 02 Civil | Flooring | P2 | 2 | 2025-05-30 | 2025-05-31 |  |  | M/s DNC | Lot | 1 | 1 | 0 | 1
SGR - 02 Civil | AHU Duct foundation-SGR-01 | P2
SGR - 02 Civil | Excavation | P2 | 2 | 2025-05-23 | 2025-05-24 |  |  | M/s DNC | Lot | 1 | 1 | 0 | 1
SGR - 02 Civil | PCC | P2 | 2 | 2025-05-26 | 2025-05-27 |  |  | M/s DNC | Lot | 1 | 1 | 0 | 1
SGR - 02 Civil | Raft | P2 | 4 | 2025-05-28 | 2025-05-31 |  |  | M/s DNC | Lot | 1 | 1 | 0 | 1
SGR - 02 Civil | Column | P2 | 4 | 2025-05-30 | 2025-06-02 |  |  | M/s DNC | Lot | 1 | 1 | 0 | 1
SGR - 02 Civil | Slab casting | P2 | 6 | 2025-05-31 | 2025-06-05 |  |  | M/s DNC | Lot | 1 | 1 | 0 | 1
SGR - 02 PEB | SGR - 02 PEB | P2 | 42 | 2025-05-23 | 2025-07-03 | bar: 1899-12-31 to 1900-07-22
SGR - 02 PEB | Erection of Primary Members | P2 | 7 | 2025-05-23 | 2025-05-29 | 2026-02-06 | 2026-02-08 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [5 empty] | 20% | 10% | 10% | 1900-12-28: 0.2; 1900-12-29: 0.2; 1900-12-30: 0.2
SGR - 02 PEB | Erection of Secondary Members | P2 | 6 | 2025-05-30 | 2025-06-04 | 2026-02-08 | 2026-02-21 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-12-30: 30%; 1900-12-31: 30%; 1901-01-01: 10%; 1901-01-02: 10%; 1901-01-10: 0.1; 1901-01-12: 0.1
SGR - 02 PEB | Alignment and Levelling of Structures | P2 | 5 | 2025-06-05 | 2025-06-09 | 2026-02-21 | 2026-02-21 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1901-01-12: 100%
SGR - 02 PEB | Installation of Roof Panel | P2 | 6 | 2025-06-10 | 2025-06-15 | 2026-02-21 | 2026-02-26 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1901-01-12: 20%; 1901-01-13: 20%; 1901-01-14: 10%; 1901-01-15: 10%; 1901-01-16: 10%; 1901-01-17: 30%
SGR - 02 PEB | Installation of Wall Panel | P2 | 6 | 2025-06-13 | 2025-06-18 | 2026-02-23 | 2026-02-26 | M/s Bnal | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1901-01-14: 20%; 1901-01-15: 20%; 1901-01-16: 30%; 1901-01-17: 30%
SGR - 02 PEB | Canopy Works | P2 | 2 | 2025-06-16 | 2025-06-17 |  |  | M/s Bnal | Lot | 1 | 1 | 0 | 1
SGR - 02 PEB | Front Handover to Civil (for Flooring Works) | P2 |  |  | 2025-06-19
SGR - 02 PEB | Installation of Doors | P2 | 4 | 2025-06-19 | 2025-06-22 |  |  | M/s Bnal | Lot | 2 | 2 | 0 | 2 |  | 0
SGR - 02 PEB | Installation of Rolling Shutter | P2 | 4 | 2025-06-19 | 2025-06-22 |  |  | M/s Bnal | Lot | 2 | 2 | 0 | 2 |  | 0
SGR - 02 PEB | Flashing and Finishing Work Etc. | P2 | 12 | 2025-06-22 | 2025-07-03 |  |  | M/s Bnal | Lot | 1 | 1 | 0 | 1
SGR - 02 PEB | AHU Works | P2 | [5 empty] | M/s Bnal
SGR - 02 PEB | Duct Assembly & Erection | P2 | 5 | 2025-06-19 | 2025-06-23 | 2026-02-16 |  | M/s Bnal | Lot | 1 | 1 | 0.4 | 0.6 | [10 empty] | 1901-01-07: 20%; 1901-01-08: 20%
SGR - 02 PEB | Duct Installation with grills | P2 | 2 | 2025-06-24 | 2025-06-25 |  |  | M/s Bnal | Lot | 1 | 1 | 0 | 1
Power Trafo -01 Civil | Power Transformer - 01 | P1 | 55 | 2025-02-18 | 2025-04-13 | 2025-04-04 | bar: 1900-03-01 to 1900-07-22
Power Trafo -01 Civil | Excavation | P1 | 1 | 2025-02-18 | 2025-02-18 | 2025-04-04 | 2025-04-04 | M/s DNC | Cum | 135.761 | 135.761 | 135.76 | 0.001025 | Completed | [9 empty] | 1900-02-23: 135.76
Power Trafo -01 Civil | Stone Blanketing | P1 | 2 | 2025-02-19 | 2025-02-20 | 2025-04-05 | 2025-04-05 | M/s DNC | Cum | 32.7135 | 32.7135 | 32.7135 | 0 | Completed | [9 empty] | 1900-02-24: 32.7135
Power Trafo -01 Civil | PCC | P1 | 3 | 2025-02-21 | 2025-02-23 | 2025-04-05 | 2025-04-05 | M/s DNC | Cum | 4.907 | 4.907 | 4.907 | 2.5e-05 | Completed | [9 empty] | 1900-02-24: 4.907
Power Trafo -01 Civil | Raft | P1 | 4 | 2025-02-24 | 2025-02-27 | 2025-04-07 | 2025-04-09 | M/s DNC | Cum | 34.5758 | 34.5758 | 34.58 | -0.0042 | Completed | [9 empty] | 1900-02-28: 34.58
Power Trafo -01 Civil | Pedestal 1st Lift | P1 | 5 | 2025-02-28 | 2025-03-04 | 2025-04-11 | 2025-04-19 | M/s DNC | Cum | 13.38 | 13.38 | 13.38 | 0 | Completed | [9 empty] | 1900-03-06: 6.68; 1900-03-10: 3.5; 1900-03-11: 3.2
Power Trafo -01 Civil | Backfilling up to NGL | P1 | 1 | 2025-03-04 | 2025-03-04 | 2025-04-22 | 2025-04-22 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-03-13
Power Trafo -01 Civil | Pedestal 2nd Lift | P1 | 6 | 2025-03-05 | 2025-03-10 | 2025-05-07 | 2025-05-24 | M/s DNC | Cum | 24.9 | 24.9 | 24.9 | 0 | Completed | [9 empty] | 1900-04-14: 24.9
Power Trafo -01 Civil | Rail Fixing | P1 | 3 | 2025-03-11 | 2025-03-13 | 2025-05-27 | 2025-05-29 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-04-17: 0.2; 1900-04-18: 0.1; 1900-04-19: 0.7
Power Trafo -01 Civil | Pedestal final Lift | P1 | 3 | 2025-03-14 | 2025-03-16 | 2025-05-29 | 2025-06-01 | M/s DNC | Cum | 3.64 | 3.64 | 3.64 | 0 | Completed | [9 empty] | 1900-04-22: 3.64
Power Trafo -01 Civil | Backfilling | P1 | 2 | 2025-03-17 | 2025-03-18 | 2025-06-02 | 2025-06-02 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-04-23
Power Trafo -01 Civil | Handover to Transformer Unloading & Erection | P1 |  |  | 2025-04-07 |  | 2025-06-09 | [6 empty] | Completed
Power Trafo -01 Civil | Backfilling | P1 | 2 | 2025-03-17 | 2025-03-18 | 2025-06-13 | 2025-06-17 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-05-04: 0.2; 1900-05-05: 0.2; 1900-05-06: 0.1; 1900-05-07: 0.2; 1900-05-08: 0.3
Power Trafo -01 Civil | Peripheral Rubble Soling | P1 | 4 | 2025-03-19 | 2025-03-22 | 2025-06-20 | 2025-06-23 | M/s DNC | Cum | 63.93 | 63.93 | 63.93 | 0 | Completed | [9 empty] | 1900-05-11: 30.03; 1900-05-14: 32.9
Power Trafo -01 Civil | Peripheral Area PCC | P1 | 4 | 2025-03-23 | 2025-03-26 | 2025-06-23 | 2025-06-23 | M/s DNC | Cum | 18.881 | 18.881 | 18.88 | 0.001 | Completed | [9 empty] | 1900-05-14: 18.88
Power Trafo -01 Civil | Peripheral Area Raft | P1 | 5 | 2025-03-27 | 2025-03-31 | 2025-06-23 | 2025-06-24 | M/s DNC | Cum | 31.47 | 31.47 | 31.47 | 0 | Completed | [9 empty] | 1900-05-15: 31.47
Power Trafo -01 Civil | Radiator Bank and Support | P1 | 5 | 2025-03-31 | 2025-04-04 | 2025-06-25 | 2025-07-31 | M/s DNC | Nos | 79 | 79 | 79 | 0 | Completed | [9 empty] | 1900-05-17: 5; 1900-06-07: 30; 1900-06-09: 25; 1900-06-13: 17; 1900-06-21: 2
Power Trafo -01 Civil | NIFPS Foundation | P1 | 5 | 2025-04-04 | 2025-04-08 | 2025-11-27 | 2025-11-28 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-18: 50%; 1900-10-19: 50%
Power Trafo -01 Civil | Peripheral Wall - Completion | P1 | 4 | 2025-04-10 | 2025-04-13 | 2025-07-24 | 2025-08-14 | M/s DNC | RM | 91.94 | 91.94 | 91.94 | 0 | Completed | [9 empty] | 1900-06-16: 30.04; 1900-06-19: 40; 1900-06-23: 10; 1900-07-05: 11.9
Power Trafo - 02 Civil | Power Transformer - 02 | P1 | 54 | 2025-02-20 | 2025-04-14 | 2025-03-29 | bar: 1900-04-24 to 1900-07-22
Power Trafo - 02 Civil | Excavation | P1 | 1 | 2025-02-20 | 2025-02-20 | 2025-03-29 | 2025-03-29 | M/s DNC | Cum | 158.5 | 158.5 | 158.5 | 0 | Completed | [9 empty] | 1900-02-17: 158.5
Power Trafo - 02 Civil | Stone Blanketing | P1 | 2 | 2025-02-21 | 2025-02-22 | 2025-03-30 | 2025-03-30 | M/s DNC | Cum | 38.194 | 38.194 | 38.194 | 0 | Completed | [9 empty] | 1900-02-18: 38.194
Power Trafo - 02 Civil | PCC | P1 | 3 | 2025-02-23 | 2025-02-25 | 2025-03-31 | 2025-03-31 | M/s DNC | Cum | 4.907 | 4.907 | 4.907 | 2.5e-05 | Completed | [9 empty] | 1900-02-19: 4.907
Power Trafo - 02 Civil | Raft | P1 | 4 | 2025-02-26 | 2025-03-01 | 2025-04-01 | 2025-04-05 | M/s DNC | Cum | 34.5757 | 34.5757 | 34.58 | -0.00425 | Completed | [9 empty] | 1900-02-24: 34.58
Power Trafo - 02 Civil | Pedestal 1st Lift | P1 | 7 | 2025-03-02 | 2025-03-08 | 2025-04-05 | 2025-04-11 | M/s DNC | Cum | 13.2803 | 13.2803 | 13.28 | 0.000335 | Completed | [9 empty] | 1900-03-02: 13.28
Power Trafo - 02 Civil | Backfilling up to NGL | P1 | 1 | 2025-03-09 | 2025-03-09 | 2025-04-16 | 2025-04-16 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-03-07
Power Trafo - 02 Civil | Pedestal 2nd Lift | P1 | 6 | 2025-03-09 | 2025-03-14 | 2025-04-11 | 2025-05-08 | M/s DNC | Cum | 24.8832 | 24.8832 | 24.8832 | 0 | Completed | [9 empty] | 1900-03-29: 24.8832
Power Trafo - 02 Civil | Rail Fixing | P1 | 4 | 2025-03-15 | 2025-03-18 | 2025-05-24 | 2025-05-26 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-04-14: 0.2; 1900-04-15: 0.25; 1900-04-16: 0.55
Power Trafo - 02 Civil | Pedestal final Lift | P1 | 4 | 2025-03-19 | 2025-03-22 | 2025-05-27 | 2025-05-27 | M/s DNC | Cum | 3.6431 | 3.6431 | 3.64 | 0.0030919 | Completed | [9 empty] | 1900-04-17: 3.64
Power Trafo - 02 Civil | Backfilling | P1 | 1 | 2025-03-23 | 2025-03-23 | 2025-05-28 | 2025-05-28 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-04-18
Power Trafo - 02 Civil | Handover to Transformer Unloading & Erection | P1 |  |  | 2025-04-08 |  | 2025-06-04 | [6 empty] | Completed
Power Trafo - 02 Civil | Backfilling | P1 | 2 | 2025-03-23 | 2025-03-24 | 2025-06-08 | 2025-06-09 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-04-29: 0.5; 1900-04-30: 0.5
Power Trafo - 02 Civil | Peripheral Rubble Soiling | P1 | 2 | 2025-03-25 | 2025-03-26 | 2025-06-10 | 2025-06-14 | M/s DNC | Cum | 62.93 | 62.93 | 62.93 | 0 | Completed | [9 empty] | 1900-05-01: 10; 1900-05-02: 5; 1900-05-03: 5; 1900-05-04: 20; 1900-05-05: 22.93
Power Trafo - 02 Civil | Peripheral Area PCC | P1 | 2 | 2025-03-27 | 2025-03-28 | 2025-06-14 | 2025-06-14 | M/s DNC | Cum | 18.881 | 18.881 | 18.88 | 0.001 | Completed | [9 empty] | 1900-05-05: 18.88
Power Trafo - 02 Civil | Peripheral Area Raft | P1 | 4 | 2025-03-29 | 2025-04-01 | 2025-06-15 | 2025-06-19 | M/s DNC | Cum | 31.47 | 31.47 | 31.47 | 0 | Completed | [9 empty] | 1900-05-08: 15.77; 1900-05-10: 15.7
Power Trafo - 02 Civil | Radiator Bank and Support | P1 | 4 | 2025-04-01 | 2025-04-04 | 2025-06-18 | 2025-06-23 | M/s DNC | Nos | 79 | 79 | 79 | 0 | Completed | 2025-11-28 | [8 empty] | 1900-05-09: 8; 1900-05-10: 5; 1900-05-11: 7; 1900-05-12: 22; 1900-05-13: 24; 1900-05-14: 13
Power Trafo - 02 Civil | NIFPS Foundation | P1 | 5 | 2025-04-04 | 2025-04-08 | 2025-11-27 | 2025-11-28 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-18: 50%; 1900-10-19: 50%
Power Trafo - 02 Civil | Peripheral Wall - Completion | P1 | 4 | 2025-04-11 | 2025-04-14 | 2025-07-21 | 2025-08-14 | M/s DNC | RM | 91.94 | 91.94 | 91.94 | 0 | Completed | [9 empty] | 1900-06-14: 32.04; 1900-07-05: 59.9
Power Trafo -03 Civil | Power Transformer - 03 | P2 | 62 | 2025-03-12 | 2025-05-12 | 2025-02-18 | bar: 1900-04-28 to 1900-07-22
Power Trafo -03 Civil | Excavation | P2 | 1 | 2025-03-12 | 2025-03-12 | 2025-02-20 | 2025-02-23 | M/s DNC | Cum | 135.761 | 135.761 | 135.761 | 0 | Completed | 1 | [8 empty] | 1900-01-11: 67.8805; 1900-01-14: 67.8805
Power Trafo -03 Civil | Stone Blanketing | P2 | 2 | 2025-03-13 | 2025-03-14 | 2025-02-25 | 2025-02-26 | M/s DNC | Cum | 126.5152 | 126.5152 | 126.52 | -0.0048 | Completed | 1 | [8 empty] | 1900-01-16: 100; 1900-01-17: 26.52
Power Trafo -03 Civil | PCC | P2 | 3 | 2025-03-15 | 2025-03-17 | 2025-02-28 | 2025-02-28 | M/s DNC | Cum | 4.907 | 4.907 | 4.91 | -0.002975 | Completed | 1.0006 | [8 empty] | 1900-01-19: 4.91
Power Trafo -03 Civil | Raft | P2 | 4 | 2025-03-18 | 2025-03-21 | 2025-05-12 | 2025-06-06 | M/s DNC | Cum | 34.5758 | 34.5758 | 34.58 | -0.0042 | Completed | 1.0001 | [8 empty] | 1900-04-27: 34.58
Power Trafo -03 Civil | Pedestal 1st Lift | P2 | 7 | 2025-03-22 | 2025-03-28 | 2025-06-08 | 2025-06-25 | M/s DNC | Cum | 13.28 | 13.28 | 13.28 | 0 | Completed | 1 | [8 empty] | 1900-05-16: 13.28
Power Trafo -03 Civil | Pedestal 2nd Lift | P2 | 6 | 2025-03-29 | 2025-04-03 | 2025-09-03 | 2025-11-13 | M/s DNC | Cum | 24.9 | 24.9 | 24.9 | 0 | Completed | 1 | [8 empty] | 1900-10-04: 24.9
Power Trafo -03 Civil | Rail Fixing | P2 | 6 | 2025-04-04 | 2025-04-09 | 2025-11-14 | 2025-11-15 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-10-05: 0.5; 1900-10-06: 0.5
Power Trafo -03 Civil | Pedestal final Lift | P2 | 5 | 2025-04-10 | 2025-04-14 | 2025-11-21 | 2025-11-25 | M/s DNC | Cum | 3.64 | 3.64 | 3.64 | 0 | Completed | 1 | [8 empty] | 1900-10-16: 3.64
Power Trafo -03 Civil | Backfilling | P2 | 1 | 2025-04-15 | 2025-04-15 | 2025-11-26 | 2025-11-26 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-10-17: 100%
Power Trafo -03 Civil | Handover to Transformer Unloading & Erection | P2 |  |  | 2025-05-05 |  | 2025-12-03 | [6 empty] | Completed
Power Trafo -03 Civil | Excavation | P2 | 3 | 2025-04-15 | 2025-04-17 | 2025-12-31 | 2025-12-31 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-11-21: 100%
Power Trafo -03 Civil | Peripheral Rubble Soling | P2 | 3 | 2025-04-18 | 2025-04-20 | 2025-12-31 | 2025-12-31 | M/s DNC | Cum | 62.93 | 62.93 | 62.93 | 0 | Completed | 1 | [8 empty] | 1900-11-21: 62.93
Power Trafo -03 Civil | Peripheral Area PCC | P2 | 3 | 2025-04-21 | 2025-04-23 | 2026-01-11 | 2026-01-18 | M/s DNC | Cum | 18.881 | 18.881 | 18.881 | 0 | completed | 1 | [8 empty] | 1900-12-02: 9.4405; 1900-12-09: 9.4405
Power Trafo -03 Civil | Peripheral Area Raft | P2 | 5 | 2025-04-24 | 2025-04-28 | 2026-01-12 | 2026-01-23 | M/s DNC | Cum | 31.47 | 31.47 | 31.475 | -0.005 | completed | 1.0002 | [8 empty] | 1900-12-07: 15.735; 1900-12-08: 0.04; 1900-12-11: 2.7; 1900-12-12: 3; 1900-12-13: 5; 1900-12-14: 5
Power Trafo -03 Civil | Radiator Bank and Support | P2 | 5 | 2025-04-28 | 2025-05-02 | 2026-01-17 | 2026-02-13 | M/s DNC | Nos | 79 | 79 | 79 | 0 | completed | 1 | [8 empty] | 1900-12-08: 7; 1900-12-09: 12; 1900-12-10: 22; 1900-12-12: 7; 1900-12-13: 7; 1900-12-14: 7; 1900-12-15: 7; 1900-12-16: 3; 1901-01-04: 7
Power Trafo -03 Civil | NIFPS Foundation | P2 | 4 | 2025-05-02 | 2025-05-05 |  |  | M/s DNC | Lot | 1 | 1 | 0 | 1
Power Trafo -03 Civil | Peripheral Wall - Completion | P2 | 7 | 2025-05-06 | 2025-05-12 | 2026-01-24 | 2026-02-15 | M/s DNC | RM | 91.94 | 91.94 | 91.9 | 0.04 | completed | [8 empty] | 20 | 1900-12-15: 10; 1900-12-16: 10; 1900-12-17: 10; 1900-12-18: 10; 1900-12-19: 10; 1900-12-20: 10; 1901-01-02: 5; 1901-01-06: 6.9
Power Trafo - 04 Civil | Power Transformer - 04 | P2 | 61 | 2025-03-15 | 2025-05-14 | 2025-02-18 | bar: 1900-04-30 to 1900-07-22
Power Trafo - 04 Civil | Excavation | P2 | 1 | 2025-03-15 | 2025-03-15 | 2025-02-18 | 2025-02-21 | M/s DNC | Cum | 158.5 | 158.5 | 158.5 | 0 | Completed | 1 | [8 empty] | 1900-01-09: 79.25; 1900-01-12: 79.25
Power Trafo - 04 Civil | Stone Blanketing | P2 | 2 | 2025-03-16 | 2025-03-17 | 2025-02-25 | 2025-02-27 | M/s DNC | Cum | 126.9438 | 126.9438 | 126.94 | 0.003813 | Completed | 0.99997 | [8 empty] | 1900-01-16: 120; 1900-01-18: 6.94
Power Trafo - 04 Civil | PCC | P2 | 4 | 2025-03-18 | 2025-03-21 | 2025-02-28 | 2025-02-28 | M/s DNC | Cum | 4.907 | 4.907 | 4.91 | -0.002975 | Completed | 1.0006 | [8 empty] | 1900-01-19: 4.91
Power Trafo - 04 Civil | Raft | P2 | 5 | 2025-03-22 | 2025-03-26 | 2025-03-28 | 2025-03-31 | M/s DNC | Cum | 34.5757 | 34.5757 | 34.576 | -0.00025 | Completed | 1 | [8 empty] | 1900-02-19: 34.576
Power Trafo - 04 Civil | Pedestal 1st Lift | P2 | 6 | 2025-03-27 | 2025-04-01 | 2025-06-03 | 2025-06-08 | M/s DNC | Cum | 13.2803 | 13.2803 | 13.28 | 0.000335 | Completed | 0.99997 | [8 empty] | 1900-04-29: 13.28
Power Trafo - 04 Civil | Pedestal 2nd Lift | P2 | 5 | 2025-04-02 | 2025-04-06 | 2025-08-26 | 2025-08-28 | M/s DNC | Cum | 24.8832 | 24.8832 | 24.8832 | 0 | Completed | 1 | [8 empty] | 1900-07-19: 24.8832
Power Trafo - 04 Civil | Rail Fixing | P2 | 4 | 2025-04-07 | 2025-04-10 | 2025-08-31 | 2025-09-03 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-07-22: 0.3; 1900-07-23: 0.2; 1900-07-24: 0.3; 1900-07-25: 0.2
Power Trafo - 04 Civil | Pedestal final Lift | P2 | 4 | 2025-04-11 | 2025-04-14 | 2025-09-06 | 2025-09-06 | M/s DNC | Cum | 3.6431 | 3.6431 | 3.6431 | 0 | Completed | 1 | [8 empty] | 1900-07-28: 3.6431
Power Trafo - 04 Civil | Backfilling | P2 | 1 | 2025-04-15 | 2025-04-15 | 2025-11-26 | 2025-11-26 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-10-17: 100%
Power Trafo - 04 Civil | Handover to Transformer Unloading & Erection | P2 |  |  | 2025-05-07 |  | 2025-09-13
Power Trafo - 04 Civil | Excavation | P2 | 3 | 2025-04-15 | 2025-04-17 | 2025-12-26 | 2025-12-26 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-11-16: 100%
Power Trafo - 04 Civil | Peripheral Rubble Soling | P2 | 4 | 2025-04-18 | 2025-04-21 | 2025-12-26 | 2025-12-26 | M/s DNC | Cum | 62.93 | 62.93 | 62.93 | 0 | Completed | 1 | [8 empty] | 1900-11-16: 62.93
Power Trafo - 04 Civil | Peripheral Area PCC | P2 | 4 | 2025-04-22 | 2025-04-25 | 2025-12-30 | 2025-12-30 | M/s DNC | Cum | 18.881 | 18.881 | 18.9 | -0.019 | Completed | 1.001 | [8 empty] | 1900-11-20: 18.9
Power Trafo - 04 Civil | Peripheral Area Raft | P2 | 5 | 2025-04-26 | 2025-04-30 | 2026-01-03 | 2026-01-04 | M/s DNC | Cum | 31.47 | 31.47 | 31.5 | -0.03 | Completed | 1.001 | [8 empty] | 1900-11-24: 1500%; 1900-11-25: 16.5
Power Trafo - 04 Civil | Radiator Bank and Support | P2 | 5 | 2025-04-30 | 2025-05-04 | 2026-01-05 | 2026-01-13 | M/s DNC | Nos | 79 | 79 | 79 | 0 | Completed | 1 | [8 empty] | 1900-11-26: 20; 1900-11-27: 10; 1900-11-28: 15; 1900-11-29: 9; 1900-11-30: 10; 1900-12-01: 6; 1900-12-04: 9
Power Trafo - 04 Civil | NIFPS Foundation | P2 | 5 | 2025-05-05 | 2025-05-09 |  |  | M/s DNC | Lot | 1 | 1 | 0 | 1
Power Trafo - 04 Civil | Peripheral Wall - Completion | P2 | 5 | 2025-05-10 | 2025-05-14 | 2026-01-13 | 2026-01-25 | M/s DNC | RM | 91.94 | 91.94 | 91.955 | -0.015 | Completed | [9 empty] | 1900-12-06: 45.97; 1900-12-10: 22.985; 1900-12-13: 4; 1900-12-14: 5; 1900-12-15: 4; 1900-12-16: 10
Fire Wall - 01 | Fire Wall - 01 | P1 | 47 | 2025-02-27 | 2025-04-14 | 2025-03-29 | 2025-11-28 | bar: 1900-05-01 to 1900-07-22
Fire Wall - 01 | Excavation | P1 | 2 | 2025-02-27 | 2025-02-28 | 2025-03-29 | 2025-03-29 | M/s DNC | Cum | 180.4 | 180.4 | 180.4 | 0 | Completed | 1 | [8 empty] | 1900-02-17: 180.4
Fire Wall - 01 | Stone Blanket | P1 | 3 | 2025-03-01 | 2025-03-03 | 2025-03-31 | 2025-04-01 | M/s DNC | Cum | 71.632 | 71.632 | 71.632 | 0 | Completed | 1 | [8 empty] | 1900-02-19: 35; 1900-02-20: 36.632
Fire Wall - 01 | PCC | P1 | 2 | 2025-03-04 | 2025-03-05 | 2025-04-01 | 2025-04-01 | M/s DNC | Cum | 6.5 | 6.5 | 6.502 | -0.002 | Completed | 1.0003 | [8 empty] | 1900-02-20: 0.864
Fire Wall - 01 | Raft | P1 | 3 | 2025-03-06 | 2025-03-08 | 2025-04-05 | 2025-04-07 | M/s DNC | Cum | 54.1 | 54.1 | 54.1 | 0 | Completed | 1 | [8 empty] | 1900-02-26: 54.1
Fire Wall - 01 | Column | P1 | 3 | 2025-03-09 | 2025-03-11 | 2025-04-08 | 2025-04-18 | M/s DNC | Nos | 5 | 5 | 5 | 0 | Completed | 1 | [8 empty] | 1900-03-09: 5
Fire Wall - 01 | Brickwork | P1 | 3 | 2025-03-12 | 2025-03-14 | 2025-04-26 | 2025-05-06 | M/s DNC | Sqm | 26.866 | 26.866 | 26.9 | -0.034 | Completed | 1.0013 | [8 empty] | 1900-03-17: 2.5; 1900-03-18: 2.5; 1900-03-24: 5; 1900-03-25: 5; 1900-03-26: 4; 1900-03-27: 7.9
Fire Wall - 01 | Beam - Level EL +2.875m | P1 | 3 | 2025-03-15 | 2025-03-17 | 2025-06-06 | 2025-07-24 | M/s DNC | Cum | 4.416 | 4.416 | 4.4 | 0.016 | Completed | 0.99638 | [8 empty] | 1900-06-14: 4.4
Fire Wall - 01 | Column | P1 | 3 | 2025-03-18 | 2025-03-20 | 2025-07-31 | 2025-08-12 | M/s DNC | Nos | 5 | 5 | 5 | 0 | Completed | 1 | [8 empty] | 1900-06-25: 2.5; 1900-07-03: 2.5
Fire Wall - 01 | Brickwork | P1 | 3 | 2025-03-21 | 2025-03-23 | 2025-08-24 | 2025-08-30 | M/s DNC | Sqm | 16.472 | 16.472 | 16.436 | 0.036 | Completed | 0.99781 | [8 empty] | 1900-07-07: 4.118; 1900-07-08: 2.059; 1900-07-17: 2.059; 1900-07-19: 2.2; 1900-07-20: 3; 1900-07-21: 3
Fire Wall - 01 | Beam - Level EL +5.750m | P1 | 4 | 2025-03-24 | 2025-03-27 | 2025-09-03 | 2025-10-30 | M/s DNC | Cum | 4.416 | 4.416 | 4.416 | 0 | Completed | 1 | [8 empty] | 1900-09-20: 4.416
Fire Wall - 01 | Column | P1 | 4 | 2025-03-28 | 2025-03-31 | 2025-10-31 | 2025-11-05 | M/s DNC | Nos | 5 | 5 | 5 | 0 | Completed | 1 | [8 empty] | 1900-09-26: 5
Fire Wall - 01 | Brickwork | P1 | 4 | 2025-04-01 | 2025-04-04 | 2025-11-06 | 2025-11-18 | M/s DNC | Sqm | 16.614 | 16.614 | 15 | 1.614 | Completed | 0.90285 | [8 empty] | 1900-09-27: 4; 1900-09-28: 4; 1900-09-29: 1; 1900-09-30: 2; 1900-10-05: 3; 1900-10-06: 1
Fire Wall - 01 | Top Coping EL +9.600m | P1 | 2 | 2025-04-05 | 2025-04-06 | 2025-11-22 | 2025-11-24 | M/s DNC | Cum | 2.208 | 2.208 | 2.2 | 0.008 | Completed | 0.99638 | [8 empty] | 1900-10-15: 2.2
Fire Wall - 01 | Plastering | P1 | 4 | 2025-04-07 | 2025-04-10 | 2025-05-06 | 2025-11-22 | M/s DNC | Sqm | 487.007 | 487.007 | 487 | 0.007 | Completed | 0.99999 | [8 empty] | 1900-03-27: 22; 1900-03-28: 21; 1900-10-04: 60; 1900-10-05: 40; 1900-10-06: 30; 1900-10-11: 100; 1900-10-12: 100; 1900-10-13: 114
Fire Wall - 01 | Painting | P1 | 4 | 2025-04-11 | 2025-04-14 | 2025-11-21 | 2025-11-28 | M/s DNC | Sqm | 487.007 | 487.007 | 487 | 0.007 | Completed | 0.99999 | [8 empty] | 1900-10-12: 200; 1900-10-19: 287
Fire Wall - 02 | Fire Wall - 02 | P2 | 80 | 2025-03-15 | 2025-06-02 | 2025-03-09 | bar: 1900-04-28 to 1900-07-22
Fire Wall - 02 | Excavation | P2 | 1 | 2025-03-15 | 2025-03-15 | 2025-03-09 | 2025-03-10 | M/s DNC | Cum | 180.4 | 180.4 | 180.4 | 0 | Completed | 1 | [8 empty] | 1900-01-28: 90.2; 1900-01-29: 90.2
Fire Wall - 02 | Stone Blanket | P2 | 3 | 2025-03-16 | 2025-03-18 | 2025-03-16 | 2025-03-17 | M/s DNC | Cum | 71.632 | 71.632 | 71.6 | 0.032 | Completed | 0.99955 | [8 empty] | 1900-02-04: 41.6; 1900-02-05: 30
Fire Wall - 02 | PCC | P2 | 1 | 2025-03-19 | 2025-03-19 | 2025-03-18 | 2025-03-18 | M/s DNC | Cum | 6.5 | 6.5 | 6.464 | 0.036 | Completed | 0.99446 | [8 empty] | 1900-02-06: 0.864
Fire Wall - 02 | Raft | P2 | 4 | 2025-03-20 | 2025-03-23 | 2025-03-29 | 2025-03-29 | M/s DNC | Cum | 54.1 | 54.1 | 54.1 | 0 | Completed | 1 | [8 empty] | 1900-02-17: 54.1
Fire Wall - 02 | Column | P2 | 6 | 2025-03-24 | 2025-03-29 | 2025-06-03 | 2025-06-06 | M/s DNC | Nos | 5 | 5 | 5 | 0 | Completed | 1 | [8 empty] | 1900-04-27: 5
Fire Wall - 02 | Brickwork | P2 | 5 | 2025-03-30 | 2025-04-03 | 2025-06-17 | 2025-07-12 | M/s DNC | Cum | 26.866 | 26.866 | 26.9 | -0.034 | Completed | 1.0013 | [8 empty] | 1900-05-08: 1.3; 1900-06-02: 25.6
Fire Wall - 02 | Beam - Level EL +2.875m | P2 | 5 | 2025-04-04 | 2025-04-08 | 2025-11-02 | 2025-11-03 | M/s DNC | Cum | 4.416 | 4.416 | 4.416 | 0 | Completed | 1 | [8 empty] | 1900-09-24: 4.416
Fire Wall - 02 | Column | P2 | 8 | 2025-04-09 | 2025-04-16 | 2025-12-26 | 2025-12-29 | M/s DNC | Nos | 5 | 5 | 5 | 0 | Completed | 1 | [8 empty] | 1900-11-16: 2; 1900-11-19: 3
Fire Wall - 02 | Brickwork | P2 | 8 | 2025-04-17 | 2025-04-24 | 2025-12-31 | 2026-01-27 | M/s DNC | Cum | 16.472 | 16.472 | 16.5 | -0.028 | Completed | 1.0017 | [8 empty] | 1900-11-04: 6.5; 1900-12-17: 5; 1900-12-18: 5
Fire Wall - 02 | Beam - Level EL +5.750m | P2 | 9 | 2025-04-25 | 2025-05-03 | 2026-02-04 | 2026-02-06 | M/s DNC | Cum | 4.416 | 4.416 | 4.4 | 0.016 | Completed | 0.99638 | [8 empty] | 1900-12-26: 1.1; 1900-12-27: 1.1; 1900-12-28: 2.2
Fire Wall - 02 | Column | P2 | 9 | 2025-05-04 | 2025-05-12 | 2026-02-11 | 2026-02-21 | M/s DNC | Nos | 5 | 5 | 5 | 0 | Completed | 1 | [8 empty] | 1901-01-02: 2; 1901-01-06: 0.5; 1901-01-12: 2.5
Fire Wall - 02 | Brickwork | P2 | 4 | 2025-05-13 | 2025-05-16 |  |  | M/s DNC | Cum | 16.614 | 16.614 | 0 | 16.614 |  | 0
Fire Wall - 02 | Top Coping EL +9.600m | P2 | 3 | 2025-05-17 | 2025-05-19 |  |  | M/s DNC | Cum | 2.208 | 2.208 | 0 | 2.208 |  | 0
Fire Wall - 02 | Plastering | P2 | 8 | 2025-05-20 | 2025-05-27 |  |  | M/s DNC | Sqm | 487.001 | 487.001 | 34 | 453.001 |  | 0.069815 | [8 empty] | 1900-07-25: 14; 1900-07-26: 20
Fire Wall - 02 | Painting | P2 | 5 | 2025-05-29 | 2025-06-02 |  |  | M/s DNC | Sqm | 487.001 | 487.001 | 0 | 487.001 |  | 0
Outdoor Eq. Found. | Outdoor Equipment Foundations |  | 44 | 2025-03-02 | 2025-04-14 | 2025-02-27 | bar: 1900-03-03 to 1900-07-22
Gantry tower | Gantry Tower | P1
Gantry tower | Excavation | P1 | 2 | 2025-03-02 | 2025-03-03 | 2025-02-27 | 2025-03-20 | M/s DNC | Nos | 2 | 2 | 2 | 0 | Completed | bar: 1900-01-18; 1900-02-08
Gantry tower | Rubble soling | P1 | 2 | 2025-03-04 | 2025-03-05 | 2025-02-28 | 2025-03-21 | M/s DNC | Nos | 2 | 2 | 2 | 0 | Completed | bar: 1900-01-19; 1900-02-09
Gantry tower | PCC | P1 | 2 | 2025-03-06 | 2025-03-07 | 2025-03-01 | 2025-03-25 | M/s DNC | Nos | 2 | 2 | 2 | 0 | Completed | bar: 1900-01-20; 1900-02-13
Gantry tower | Raft | P1 | 7 | 2025-03-08 | 2025-03-14 | 2025-04-01 | 2025-04-05 | M/s DNC | Nos | 2 | 2 | 2 | 0 | Completed | bar: 1900-02-20; 1900-02-24
Gantry tower | Column-1st Lift | P1 | 5 | 2025-03-15 | 2025-03-19 | 2025-04-06 | 2025-04-10 | M/s DNC | Nos | 8 | 8 | 8 | 0 | Completed | [9 empty] | 1900-02-27: 4; 1900-03-02: 4
Gantry tower | Column - Bolt | P1 | 7 | 2025-03-20 | 2025-03-26 | 2025-07-31 | 2025-08-08 | M/s DNC | Nos | 8 | 8 | 8 | 0 | Completed | [9 empty] | 1900-06-29: 8
Gantry tower | Plinth Beam | P1 | 5 | 2025-03-28 | 2025-04-01 | 2025-06-09 | 2025-06-23 | M/s DNC | Nos | 8 | 8 | 8 | 0 | Completed | [9 empty] | 1900-05-12: 4; 1900-05-14: 4
Gantry tower | Backfilling- Compaction | P1 | 1 | 2025-03-27 | 2025-03-27 | 2025-04-09 | 2025-11-03 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-02-28: 0.3; 1900-05-13: 0.2; 1900-09-24: 50%
High Light Mast | High Light Mast | P1
High Light Mast | Excavation | P1 | 5 | 2025-03-04 | 2025-03-08 | 2025-03-19 | 2025-09-01 | M/s DNC | Nos | 5 | 5 | 5 | 0 | Completed | bar: 1900-02-07; 1900-02-23 to 1900-02-24; 1900-07-18; 1900-07-23
High Light Mast | Rubble soling | P1 | 9 | 2025-03-05 | 2025-03-13 | 2025-03-20 | 2025-09-02 | M/s DNC | Nos | 5 | 5 | 5 | 0 | Completed | bar: 1900-02-08; 1900-02-23 to 1900-02-24; 1900-07-18; 1900-07-24
High Light Mast | PCC | P1 | 9 | 2025-03-06 | 2025-03-14 | 2025-03-20 | 2025-09-02 | M/s DNC | Nos | 5 | 5 | 5 | 0 | Completed | [9 empty] | 1900-02-08: 1; 1900-02-26: 2; 1900-07-20: 1; 1900-07-24: 1
High Light Mast | Raft | P1 | 12 | 2025-03-07 | 2025-03-18 | 2025-03-27 | 2025-09-05 | M/s DNC | Nos | 5 | 5 | 5 | 0 | completed | bar: 1900-02-15; 1900-03-02; 1900-03-04; 1900-07-22; 1900-07-27
High Light Mast | Column | P1 | 11 | 2025-03-11 | 2025-03-21 | 2025-03-28 | 2025-11-20 | M/s DNC | Nos | 5 | 5 | 5 | 0 | completed | [9 empty] | 1900-02-24: 1; 1900-03-04: 0.5; 1900-03-07: 0.5; 1900-03-25: 0.5; 1900-07-23: 1; 1900-10-09: 0.5; 1900-10-10: 0.5; 1900-10-11: 0.5
High Light Mast | Backfilling- Compaction | P1 | 8 | 2025-03-18 | 2025-03-25 | 2025-07-03 | 2025-11-25 | M/s DNC | Lot | 1 | 1 | 1 | 0 | completed | [9 empty] | 1900-10-16: 40%
High Light Mast | High Mast Erection | P1 | 7 | 2025-03-26 | 2025-04-01 | 2025-05-02 | 2025-12-04 | M/s Hyosung | Nos | 5 | 5 | 5 | 0 | completed | bar: 1900-03-23; 1900-04-12; 1900-10-24 to 1900-10-25
AIS Eq. Line Side | AIS Equipment - Line Side | P1
AIS Eq. Line Side | Excavation | P1 | 5 | 2025-03-06 | 2025-03-10 | 2025-06-14 | 2025-09-04 | M/s DNC | Nos | 15 | 15 | 15 | 0 | completed | [9 empty] | 1900-05-05: 6; 1900-07-04: 3; 1900-07-20: 3; 1900-07-26: 3
AIS Eq. Line Side | Rubble soling | P1 | 9 | 2025-03-07 | 2025-03-15 | 2025-06-14 | 2025-11-01 | M/s DNC | Nos | 15 | 15 | 15 | 0 | completed | [9 empty] | 1900-05-05: 6; 1900-07-04: 3; 1900-07-21: 3; 1900-09-22: 3
AIS Eq. Line Side | PCC | P1 | 9 | 2025-03-08 | 2025-03-16 | 2025-06-20 | 2025-11-03 | M/s DNC | Nos | 15 | 15 | 15 | 0 | completed | [9 empty] | 1900-05-11: 6; 1900-07-04: 3; 1900-07-21: 3; 1900-09-24: 3
AIS Eq. Line Side | Raft | P1 | 12 | 2025-03-09 | 2025-03-20 | 2025-08-14 | 2025-11-06 | M/s DNC | Nos | 15 | 15 | 15 | 0 | completed | [9 empty] | 1900-07-05: 3; 1900-07-06: 3; 1900-07-23: 3; 1900-09-25: 3; 1900-09-27: 3
AIS Eq. Line Side | Column-1st Lift | P1 | 11 | 2025-03-13 | 2025-03-23 | 2025-08-17 | 2025-11-14 | M/s DNC | Nos | 24 | 24 | 24 | 0 | Completed | [9 empty] | 1900-07-08: 6; 1900-07-22: 3; 1900-09-24: 3; 1900-10-05: 12
AIS Eq. Line Side | Column - Bolt | P1 | 12 | 2025-03-15 | 2025-03-26 | 2025-08-22 | 2025-11-19 | M/s DNC | Lot | 24 | 24 | 24 | 0 | Completed | [9 empty] | 1900-07-15: 2; 1900-07-22: 4; 1900-07-26: 3; 1900-10-06: 3; 1900-10-10: 12
AIS Eq. Line Side | Backfilling- Compaction | P1 | 6 | 2025-03-20 | 2025-03-25 | 2025-09-01 | 2025-12-18 | M/s DNC | Nos | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-07-23: 0.1; 1900-10-05: 0.1; 1900-10-06: 0.2; 1900-10-26: 10%; 1900-11-04: 30%
AIS Eq. Trafo Side | AIS Equipment - Trafo Side | P1
AIS Eq. Trafo Side | Excavation | P1 | 7 | 2025-03-08 | 2025-03-14 | 2025-08-14 | 2025-11-21 | M/s DNC | Nos | 24 | 24 | 24 | 0 | Completed | [9 empty] | 1900-07-07: 3; 1900-07-18: 6; 1900-07-22: 3; 1900-10-04: 3; 1900-10-11: 3; 1900-10-12: 6
AIS Eq. Trafo Side | Rubble soling | P1 | 10 | 2025-03-10 | 2025-03-19 | 2025-08-14 | 2025-11-22 | M/s DNC | Nos | 24 | 24 | 24 | 0 | Completed | [9 empty] | 1900-07-07: 3; 1900-07-18: 6; 1900-07-22: 3; 1900-10-04: 3; 1900-10-11: 3; 1900-10-13: 6
AIS Eq. Trafo Side | PCC | P1 | 10 | 2025-03-11 | 2025-03-20 | 2025-08-14 | 2025-11-22 | M/s DNC | Nos | 24 | 24 | 24 | 0 | Completed | [9 empty] | 1900-07-07: 3; 1900-07-18: 6; 1900-07-22: 3; 1900-10-04: 3; 1900-10-13: 9
AIS Eq. Trafo Side | Raft | P1 | 14 | 2025-03-12 | 2025-03-25 | 2025-08-17 | 2025-11-23 | M/s DNC | Nos | 24 | 24 | 24 | 0 | Completed | [9 empty] | 1900-07-08: 3; 1900-07-21: 3; 1900-07-25: 3; 1900-10-06: 3; 1900-10-14: 12
AIS Eq. Trafo Side | Column-1st Lift | P1 | 16 | 2025-03-16 | 2025-03-31 | 2025-08-17 | 2025-12-12 | M/s DNC | Nos | 24 | 24 | 24 | 0 | Completed | [9 empty] | 1900-07-08: 3; 1900-07-22: 3; 1900-07-26: 3; 1900-10-07: 3; 1900-10-14: 6; 1900-10-25: 1; 1900-10-27: 1; 1900-11-02: 4
AIS Eq. Trafo Side | Column - Bolt | P1 | 16 | 2025-03-18 | 2025-04-02 | 2025-08-25 | 2025-12-12 | M/s DNC | Nos | 24 | 24 | 24 | 0 | Completed | [9 empty] | 1900-07-18: 3; 1900-07-24: 3; 1900-07-27: 3; 1900-10-07: 3; 1900-10-25: 4; 1900-10-26: 4; 1900-11-02: 4
AIS Eq. Trafo Side | Backfilling- Compaction | P1 | 10 | 2025-03-26 | 2025-04-04 | 2025-12-09 | 2025-12-23 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-30: 40%; 1900-10-31: 10%; 1900-11-01: 30%; 1900-11-04: 10%; 1900-11-13: 10%
GIB & GAB Found. | GIB & GAB Foundations | P1
GIB & GAB Found. | Excavation | P1 | 4 | 2025-03-10 | 2025-03-13 | 2025-05-30 | 2025-08-27 | M/s DNC | Nos | 25 | 25 | 25 | 0 | Completed | [9 empty] | 1900-04-20: 0.4; 1900-04-21: 0.6; 1900-04-22: 2; 1900-04-30: 2; 1900-06-04: 5; 1900-06-22: 3; 1900-06-27: 1; 1900-06-28: 1; 1900-07-03: 2; 1900-07-04: 2; 1900-07-08: 3; 1900-07-13: 2; 1900-07-18: 1
GIB & GAB Found. | Rubble soling | P1 | 4 | 2025-03-11 | 2025-03-14 | 2025-06-08 | 2025-08-27 | M/s DNC | Nos | 25 | 25 | 25 | 0 | Completed | [9 empty] | 1900-04-29: 3; 1900-04-30: 2; 1900-06-21: 5; 1900-06-22: 3; 1900-06-27: 1; 1900-06-28: 1; 1900-07-03: 2; 1900-07-04: 2; 1900-07-08: 3; 1900-07-13: 2; 1900-07-18: 1
GIB & GAB Found. | PCC | P1 | 5 | 2025-03-12 | 2025-03-16 | 2025-06-09 | 2025-08-28 | M/s DNC | Nos | 25 | 25 | 25 | 0 | Completed | [9 empty] | 1900-04-30: 5; 1900-06-21: 5; 1900-06-22: 3; 1900-06-27: 1; 1900-06-28: 1; 1900-07-03: 2; 1900-07-04: 2; 1900-07-08: 3; 1900-07-13: 2; 1900-07-19: 1
GIB & GAB Found. | Raft | P1 | 6 | 2025-03-13 | 2025-03-18 | 2025-06-10 | 2025-08-30 | M/s DNC | Nos | 25 | 25 | 25 | 0 | Completed | [9 empty] | 1900-05-05: 5; 1900-06-23: 3; 1900-06-24: 3; 1900-06-27: 1; 1900-06-29: 2; 1900-07-05: 2; 1900-07-06: 3; 1900-07-10: 3; 1900-07-15: 2; 1900-07-21: 1
GIB & GAB Found. | Column - Upto NGL | P1 | 7 | 2025-03-17 | 2025-03-23 | 2025-06-24 | 2025-08-31 | M/s DNC | Nos | 51 | 51 | 51 | 0 | Completed | [9 empty] | 1900-05-17: 4; 1900-06-21: 3; 1900-06-23: 1; 1900-06-27: 5; 1900-06-28: 2; 1900-06-29: 5; 1900-07-02: 4; 1900-07-03: 5; 1900-07-04: 4; 1900-07-05: 3; 1900-07-08: 5; 1900-07-17: 3; 1900-07-20: 2; 1900-07-22: 5
GIB & GAB Found. | Column - Final Lift | P1 | 7 | 2025-03-21 | 2025-03-27 | 2025-07-30 | 2025-09-01 | M/s DNC | Nos | 51 | 51 | 51 | 0 | Completed | [9 empty] | 1900-06-22: 7; 1900-06-24: 1; 1900-06-27: 5; 1900-06-29: 2; 1900-07-03: 6; 1900-07-04: 5; 1900-07-05: 4; 1900-07-06: 2; 1900-07-07: 3; 1900-07-08: 6; 1900-07-18: 3; 1900-07-20: 2; 1900-07-23: 5
GIB & GAB Found. | Backfilling- Compaction | P1 | 5 | 2025-03-21 | 2025-03-25 | 2025-08-07 | 2025-12-17 | M/s DNC | Lot | 1 | 1 | 1.01 | -0.01 | Completed | [9 empty] | 1900-06-28: 0.2; 1900-07-07: 0.01; 1900-07-08: 0.1; 1900-07-21: 0.05; 1900-07-22: 0.05; 1900-07-23: 0.1; 1900-10-05: 10%; 1900-10-06: 10%; 1900-10-07: 10%; 1900-11-04: 10%
33kv HT cable Box | 33kv HT cable Box culvert- PTR-1 & 2to SGR-1
33kv HT cable Box | Excavation | P1 | 1 | 2025-03-16 | 2025-03-16 | 2025-09-03 | 2025-12-02 | M/s DNC | Nos | 2 | 2 | 2 | 0 | Completed | [9 empty] | 1900-07-25: 1; 1900-09-30: 0.5; 1900-10-23: 0.5
33kv HT cable Box | PCC | P1 | 1 | 2025-03-16 | 2025-03-16 | 2025-09-03 | 2025-12-02 | M/s DNC | Nos | 2 | 2 | 2 | 0 | Completed | [9 empty] | 1900-07-25: 1; 1900-09-30: 0.5; 1900-10-23: 0.5
33kv HT cable Box | Precast culvert | P1 | 3 | 2025-03-17 | 2025-03-19 | 2025-11-18 | 2025-12-04 | M/s DNC | Nos | 2 | 2 | 2 | 0 | Completed | [9 empty] | 1900-10-09: 0.5; 1900-10-10: 0.5; 1900-10-25: 1
33kv HT cable Box | Culvert- RCC Raft (If Applicable) |  | 0 | 2025-03-17 | 2025-03-16 |  |  |  | Nos |  | 0 | 0 | 0
33kv HT cable Box | Culvert - RCC- Wall (If Applicable) |  | 0 | 2025-03-18 | 2025-03-17 |  |  |  | Nos |  | 0 | 0 | 0
33kv HT cable Box | Culvert - RCC- Slab (If Applicable) |  | 0 | 2025-03-19 | 2025-03-18 |  |  |  | Nos |  | 0 | 0 | 0
33kv HT cable Box | Pull Pit- RCC Raft | P1 | 4 | 2025-03-17 | 2025-03-20 | 2025-10-31 | 2025-12-02 | M/s DNC | Nos | 2 | 2 | 2 | 0 | Completed | [9 empty] | 1900-09-22: 1; 1900-09-30: 0.25; 1900-10-02: 0.25; 1900-10-23: 0.5
33kv HT cable Box | Pull Pit - RCC- Wall | P1 | 4 | 2025-03-18 | 2025-03-21 | 2025-11-02 | 2025-12-04 | M/s DNC | Nos | 2 | 2 | 2 | 0 | Completed | [9 empty] | 1900-09-24: 1; 1900-09-30: 0.25; 1900-10-02: 0.25; 1900-10-25: 0.5
33kv HT cable Box | Pull Pit- RCC Slab | P1 | 4 | 2025-03-20 | 2025-03-23 | 2025-11-06 |  | M/s DNC | Nos | 2 | 2 | 1 | 1 | Completed | [9 empty] | 1900-09-27: 0.05; 1900-09-28: 0.1; 1900-09-29: 0.1; 1900-09-30: 0.1; 1900-10-01: 0.35; 1900-10-02: 0.3
33kv HT cable Box | Backfilling | P1 | 1 | 2025-03-24 | 2025-03-24 |  |  |  | Lot | 1 | 1 | 0 | 1
33kv HT cable Box | 33kv HT cable Box culvert- Firewall to SGR-1(For Control Cables)
33kv HT cable Box | Excavation | P1 | 1 | 2025-03-28 | 2025-03-28 | 2025-11-16 | 2025-12-02 |  | Nos | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-07: 50%; 1900-10-23: 0.5
33kv HT cable Box | PCC | P1 | 1 | 2025-03-28 | 2025-03-28 | 2025-11-16 | 2025-12-02 |  | Nos | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-07: 50%; 1900-10-23: 0.5
33kv HT cable Box | Precast culvert | P1 | 3 | 2025-03-29 | 2025-03-31 | 2025-12-03 | 2025-12-04 |  | Nos | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-24: 0.5; 1900-10-25: 0.5
33kv HT cable Box | Culvert- RCC Raft (If Applicable) |  | 3 | 2025-03-29 | 2025-03-31 |  |  |  | Nos |  | 0 | 0 | 0
33kv HT cable Box | Culvert - RCC- Wall (If Applicable) |  | 3 | 2025-03-30 | 2025-04-01 |  |  |  | Nos |  | 0 | 0 | 0
33kv HT cable Box | Culvert - RCC- Slab (If Applicable) |  | 2 | 2025-03-31 | 2025-04-01 |  |  |  | Nos |  | 0 | 0 | 0
33kv HT cable Box | Pull Pit- RCC Raft | P1 | 4 | 2025-03-29 | 2025-04-01 | 2025-11-19 | 2025-12-03 |  | Nos | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-10: 50%; 1900-10-24: 0.5
33kv HT cable Box | Pull Pit - RCC- Wall | P1 | 4 | 2025-03-30 | 2025-04-02 | 2025-11-22 | 2025-12-10 |  | Nos | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-13: 50%; 1900-10-31: 50%
33kv HT cable Box | Pull Pit- RCC Slab | P1 | 4 | 2025-04-01 | 2025-04-04 | 2025-11-23 |  |  | Nos | 1 | 1 | 0.5 | 0.5 | [10 empty] | 1900-10-14: 50%
33kv HT cable Box | Backfilling | P1 | 1 | 2025-04-05 | 2025-04-05 |  |  |  | Lot | 1 | 1 | 0 | 1
CTS-Firewall-1 side | Cable Tray supports - SGR 1 to Cable Culverts | P1
CTS-Firewall-1 side | Auguring | P1 | 5 | 2025-03-25 | 2025-03-29 | 2025-11-24 | 2025-12-03 |  | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-15: 50%; 1900-10-23: 50%
CTS-Firewall-1 side | Pile Casting with channel | P1 | 5 | 2025-03-27 | 2025-03-31 | 2025-11-25 | 2025-12-04 |  | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-16: 50%; 1900-10-23: 50%
CTS-SGR1-cable culvert | Cable Tray supports - Firewall-1 Side | P1
CTS-SGR1-cable culvert | Auguring | P1 | 4 | 2025-03-12 | 2025-03-15 | 2025-12-04 | 2025-12-04 |  | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-25: 100%
CTS-SGR1-cable culvert | Pile Casting | P1 | 4 | 2025-03-13 | 2025-03-16 | 2025-12-04 | 2025-12-04 |  | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-25: 100%
CTS-SGR1-cable culvert | Column Casting | P1 | 4 | 2025-03-15 | 2025-03-18 | 2025-12-05 | 2025-12-05 |  | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-26: 100%
CTS-GIS TO PTR 1&2 | Cable Tray supports - GIS to PTR-1 & 2 | P1
CTS-GIS TO PTR 1&3 | Auguring | P1 | 4 | 2025-04-01 | 2025-04-04 | 2025-11-27 | 2025-11-28 |  | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-18: 50%; 1900-10-19: 50%
CTS-GIS TO PTR 1&4 | Pile Casting | P1 | 4 | 2025-04-03 | 2025-04-06 | 2025-11-28 | 2025-11-30 |  | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-19: 50%; 1900-10-21: 50%
CTS-GIS TO PTR 1&5 | Column Casting | P1 | 4 | 2025-04-05 | 2025-04-08 | 2025-12-02 | 2025-12-05 |  | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-23: 0.5; 1900-10-26: 0.5
CTS-GIS to line side Eq. | Cable Tray supports - GIS to Line side Equipment's | P1
CTS-GIS to line side Eq. | Auguring | P1 | 4 | 2025-04-01 | 2025-04-04 | 2025-12-02 | 2025-12-02 |  | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-23: 100%
CTS-GIS to line side Eq. | Pile Casting | P1 | 4 | 2025-04-03 | 2025-04-06 | 2025-12-03 | 2025-12-05 |  | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-24: 50%; 1900-10-26: 50%
CTS-GIS to line side Eq. | Column Casting | P1 | 3 | 2025-04-05 | 2025-04-07 | 2025-12-05 | 2025-12-06 |  | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-26: 50%; 1900-10-27: 50%
33kv HT cable Box | 33kv HT cable Box culvert- PTR-3 & 4 to SGR-2
33kv HT cable Box | Excavation | P2 | 1 | 2025-03-23 | 2025-03-23 | 2026-02-09 | 2026-02-16 |  | Nos | 2 | 2 | 2 | 0 | Completed | bar: 1900-12-31; 1901-01-07
33kv HT cable Box | PCC | P2 | 1 | 2025-03-23 | 2025-03-23 | 2026-02-10 | 2026-02-16 |  | Nos | 2 | 2 | 2 | 0 | Completed | bar: 1901-01-01; 1901-01-07
33kv HT cable Box | Precast culvert | P2 | 3 | 2025-03-24 | 2025-03-26 | 2026-02-12 | 2026-02-12 |  | Nos | 2 | 2 | 2 | 0 | Completed | [9 empty] | 1901-01-03: 200%
33kv HT cable Box | Culvert- RCC Raft (If Applicable) | P2 | 3 | 2025-03-24 | 2025-03-26 |  |  |  | Nos |  | 0 | 0 | 0
33kv HT cable Box | Culvert - RCC- Wall (If Applicable) | P2 | 3 | 2025-03-25 | 2025-03-27 |  |  |  | Nos |  | 0 | 0 | 0
33kv HT cable Box | Culvert - RCC- Slab (If Applicable) | P2 | 2 | 2025-03-26 | 2025-03-27 |  |  |  | Nos |  | 0 | 0 | 0
33kv HT cable Box | Pull Pit- RCC Raft | P2 | 4 | 2025-03-24 | 2025-03-27 | 2026-02-18 |  |  | Nos | 2 | 2 | 1 | 1 | [10 empty] | 1901-01-09: 0.2; 1901-01-10: 0.2; 1901-01-11: 0.2; 1901-01-12: 0.2; 1901-01-13: 0.2
33kv HT cable Box | Pull Pit - RCC- Wall | P2 | 4 | 2025-03-25 | 2025-03-28 | 2026-02-20 |  |  | Nos | 2 | 2 | 1 | 1 | bar: 1901-01-11
33kv HT cable Box | Pull Pit- RCC Slab | P2 | 4 | 2025-03-27 | 2025-03-30 | 2026-02-24 |  |  | Nos | 2 | 2 | 0.9 | 1.1 | [10 empty] | 1901-01-15: 0.3; 1901-01-16: 0.3; 1901-01-17: 0.3
33kv HT cable Box | Backfilling | P2 | 1 | 2025-03-31 | 2025-03-31 |  |  |  | Lot | 1 | 1 | 0 | 1
33kv HT cable Box | 33kv HT cable Box culvert- Firewall -2 to SGR-2(For Control Cables)
33kv HT cable Box | Excavation | P2 | 1 | 2025-04-04 | 2025-04-04 |  |  | M/s DNC | Nos | 1 | 1 | 0 | 1
33kv HT cable Box | PCC | P2 | 1 | 2025-04-04 | 2025-04-04 |  |  | M/s DNC | Nos | 1 | 1 | 0 | 1
33kv HT cable Box | Precast culvert | P2 | 3 | 2025-04-05 | 2025-04-07 |  |  | M/s DNC | Nos | 1 | 1 | 0 | 1 | Completed
33kv HT cable Box | Culvert- RCC Raft (If Applicable) | P2 | 3 | 2025-04-05 | 2025-04-07 |  |  | M/s DNC | Nos |  | 0 | 0 | 0
33kv HT cable Box | Culvert - RCC- Wall (If Applicable) | P2 | 3 | 2025-04-06 | 2025-04-08 |  |  | M/s DNC | Nos |  | 0 | 0 | 0
33kv HT cable Box | Culvert - RCC- Slab (If Applicable) | P2 | 2 | 2025-04-07 | 2025-04-08 |  |  | M/s DNC | Nos |  | 0 | 0 | 0
33kv HT cable Box | Pull Pit- RCC Raft | P2 | 4 | 2025-04-05 | 2025-04-08 |  |  | M/s DNC | Nos | 1 | 1 | 0 | 1
33kv HT cable Box | Pull Pit - RCC- Wall | P2 | 4 | 2025-04-06 | 2025-04-09 |  |  | M/s DNC | Nos | 1 | 1 | 0 | 1
33kv HT cable Box | Pull Pit- RCC Slab | P2 | 4 | 2025-04-08 | 2025-04-11 |  |  | M/s DNC | Nos | 1 | 1 | 0 | 1
33kv HT cable Box | Backfilling | P2 | 1 | 2025-04-12 | 2025-04-12 |  |  | M/s DNC | Lot | 1 | 1 | 0 | 1
CTS-Firewall-2 Side | Cable Tray supports - SGR 2 - Cable Culverts
CTS-Firewall-2 Side | Auguring | P2 | 5 | 2025-04-08 | 2025-04-12 |  |  |  | Nos |  | 0 | 0 | 0
CTS-Firewall-2 Side | Pile Casting with channel | P2 | 5 | 2025-04-10 | 2025-04-14 |  |  |  | Nos |  | 0 | 0 | 0
CTS-SGR2-cable culvert | Cable Tray supports - Firewall-2 Side | P2
CTS-SGR2-cable culvert | Auguring | P2 | 2 | 2025-03-15 | 2025-03-16 |  |  |  | Nos |  | 0 | 0 | 0
CTS-SGR2-cable culvert | Pile Casting | P2 | 3 | 2025-03-17 | 2025-03-19 |  |  |  | Nos |  | 0 | 0 | 0
CTS-SGR2-cable culvert | Column Casting | P2 | 3 | 2025-03-19 | 2025-03-21 |  |  |  | Nos |  | 0 | 0 | 0
CTS-GIS to PTR-3&4 | Cable Tray supports - GIS to PTR- 3 & 4 | P2
CTS-GIS to PTR-3&4 | Auguring | P2 | 3 | 2025-04-04 | 2025-04-06 | 2026-01-18 | 2026-01-21 | M/s DNC | Lot | 1 | 1 | 0 | 1 | Completed | [9 empty] | 1900-12-09: 30%; 1900-12-10: 20%; 1900-12-11: 40%; 1900-12-12: 10%
CTS-GIS to PTR-3&4 | Pile Casting | P2 | 3 | 2025-04-06 | 2025-04-08 | 2026-01-19 | 2026-01-23 | M/s DNC | Lot | 1 | 1 | 0 | 1 | Completed | [9 empty] | 1900-12-10: 30%; 1900-12-13: 40%; 1900-12-14: 30%
CTS-GIS to PTR-3&4 | Column Casting | P2 | 3 | 2025-04-07 | 2025-04-09 | 2026-01-24 | 2026-01-28 | M/s DNC | Lot | 1 | 1 | 0 | 1 | Completed | [9 empty] | 1900-12-15: 20%; 1900-12-16: 20%; 1900-12-17: 20%; 1900-12-18: 20%; 1900-12-19: 20%
WMS Foundation | WMS Foundation | P1
WMS Foundation | Excavation | P1 | 1 | 2025-03-19 | 2025-03-19 | 2025-12-15 | 2025-12-15 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-05: 100%
WMS Foundation | PCC | P1 | 1 | 2025-03-19 | 2025-03-19 | 2025-12-15 | 2025-12-15 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-05: 100%
WMS Foundation | Raft | P1 | 3 | 2025-03-20 | 2025-03-22 | 2025-12-16 | 2025-12-16 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-06: 100%
WMS Foundation | Column | P1 | 3 | 2025-03-23 | 2025-03-25 | 2025-12-17 | 2025-12-17 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-07: 100%
WMS Foundation | Backfilling- Compaction | P1 | 1 | 2025-03-26 | 2025-03-26 | 2025-12-17 | 2025-12-17 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-07: 100%
WMS Foundation | Supports - Casting | P1 | 5 | 2025-03-20 | 2025-03-24 | 2025-12-18 | 2025-12-18 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-08: 100%
SVG -P1 Civil | SVG (P1) Foundations | P1 | 26 | 2025-03-05 | 2025-03-30 | 2025-06-09 |  |  | Set | 7 | 7 | 7.5 | -0.5 | bar: 1899-12-31 to 1900-07-22
SVG -P1 Civil | Excavation | P1 | 10 | 2025-03-05 | 2025-03-14 | 2025-06-09 | 2025-06-09 | M/s DNC | Nos | 0 | 0 | 0 | 0 | Completed
SVG -P1 Civil | Rubble soling | P1 | 10 | 2025-03-07 | 2025-03-16 | 2025-06-09 | 2025-07-10 | M/s DNC | Nos | 7 | 7 | 7 | 0 | Completed | [9 empty] | 1900-04-30: 0.5; 1900-05-23: 3; 1900-05-24: 1; 1900-05-28: 2; 1900-05-29: 1
SVG -P1 Civil | PCC | P1 | 16 | 2025-03-09 | 2025-03-24 | 2025-07-04 | 2025-08-30 | M/s DNC | Nos | 7 | 7 | 7 | 0 | Completed | [9 empty] | 1900-05-25: 1; 1900-07-10: 1; 1900-07-13: 2; 1900-07-15: 0.5; 1900-07-19: 0.5; 1900-07-20: 1; 1900-07-21: 1
SVG -P1 Civil | Container Foundations | P1 | 20 | 2025-03-11 | 2025-03-30 | 2025-08-20 | 2025-09-05 | M/s DNC | Nos | 56 | 56 | 56 | 0 | completed | [9 empty] | 1900-07-13: 4; 1900-07-14: 4; 1900-07-16: 8; 1900-07-18: 8; 1900-07-19: 8; 1900-07-22: 8; 1900-07-23: 8; 1900-07-27: 8
SVG -P1 Civil | Heat Exchanger foundations | P1 | 15 | 2025-03-14 | 2025-03-28 | 2025-11-10 | 2026-01-18 | M/s DNC | Nos | 7 | 7 | 7 | 0 | completed | [9 empty] | 1900-10-06: 1; 1900-10-09: 2; 1900-10-30: 1; 1900-12-03: 1; 1900-12-09: 2
SVG -P1 Civil | Brick Wall (Fence Support Wall & Rector Supports) | P1 | 15 | 2025-03-15 | 2025-03-29 | 2025-07-09 | 2025-12-03 | M/s DNC | Nos | 28 | 28 | 28 | 0 | Completed | [9 empty] | 1900-05-30: 1; 1900-06-01: 1; 1900-07-11: 1; 1900-07-12: 1; 1900-07-13: 3; 1900-07-14: 3; 1900-07-15: 2; 1900-07-16: 2; 1900-07-17: 2; 1900-07-18: 2; 1900-07-22: 1; 1900-07-23: 1; 1900-07-25: 1; 1900-07-27: 1; 1900-07-28: 1; 1900-10-03: 2; 1900-10-24: 3
SVG -P1 Civil | P3 & P4 Foundations (H-pole Supports ) | P1 | 10 | 2025-03-18 | 2025-03-27 | 2025-09-03 | 2026-01-19 | M/s DNC | Nos | 14 | 14 | 14 | 0 | Completed | [9 empty] | 1900-07-26: 2; 1900-10-15: 2; 1900-11-16: 2; 1900-12-03: 2; 1900-12-09: 3; 1900-12-10: 3
SVG -P1 Civil | Handover to SVG Erection Vendor | P1 |  |  | 2025-03-27 |  | 2025-09-12
SVG -P2 Civil | SVG (P2) Foundations | P2 | 34 | 2025-03-15 | 2025-04-17 |  |  |  | Set | 8.0588 | 8.0588 | 3.0588 | 5 | bar: 1899-12-31 to 1900-07-22
SVG -P2 Civil | Excavation | P2 | 10 | 2025-03-15 | 2025-03-24 | 2026-01-18 | 2026-01-21 | M/s DNC | Lot | 1 | 1 | 1 | 0 | completed | [9 empty] | 1900-12-09: 40%; 1900-12-10: 20%; 1900-12-11: 20%; 1900-12-12: 20%
SVG -P2 Civil | Rubble soling | P2 | 10 | 2025-03-17 | 2025-03-26 | 2026-01-18 |  | M/s DNC | Nos | 8 | 8 | 6 | 2 | [10 empty] | 1900-12-09: 2; 1900-12-10: 2; 1900-12-14: 1; 1900-12-27: 1
SVG -P2 Civil | PCC | P2 | 15 | 2025-03-19 | 2025-04-02 | 2026-01-20 |  | M/s DNC | Nos | 8 | 8 | 4 | 4 | [10 empty] | 1900-12-11: 1; 1900-12-12: 1; 1900-12-13: 1; 1900-12-26: 1; 1901-01-09: 2
SVG -P2 Civil | Container Foundations | P2 | 20 | 2025-03-21 | 2025-04-09 | 2026-02-16 |  | M/s DNC | Nos | 64 | 64 | 32 | 32 | [10 empty] | 1901-01-07: 8; 1901-01-09: 8; 1901-01-10: 8; 1901-01-14: 4; 1901-01-15: 4
SVG -P2 Civil | Heat Exchanger foundations | P2 | 20 | 2025-03-26 | 2025-04-14 |  |  | M/s DNC | Nos | 8 | 8 | 0 | 8
SVG -P2 Civil | Brick Wall (Fence Support Wall & Rector Supports) | P2 | 20 | 2025-03-27 | 2025-04-15 | 2026-02-15 |  | M/s DNC | Nos | 32 | 32 | 9 | 23 | [10 empty] | 1901-01-06: 3; 1901-01-07: 3; 1901-01-08: 3
SVG -P2 Civil | P3 & P4 Foundations (H-pole Supports ) | P2 | 10 | 2025-03-30 | 2025-04-08 |  |  | M/s DNC | Nos | 16 | 16 | 0 | 16
SVG -P2 Civil | Handover to SVG Erection Vendor | P2 |  |  | 2025-04-17 |  | 1900-01-08
Harmonic Filter-P1 Civil | Harmonic Filter (P1) Foundations | P1 | 53 | 2025-03-20 | 2025-05-11 | 2025-04-07 |  |  |  | 4.8776 | 4.8776 | 4.6751 | 0.20253 | bar: 1900-03-28 to 1900-07-22
Harmonic Filter-P1 Civil | Excavation | P1 | 9 | 2025-03-20 | 2025-03-28 | 2025-04-07 | 2025-06-12 | M/s DNC | Nos | 4 | 4 | 4 | 0 | Completed | bar: 1900-02-26; 1900-03-07; 1900-03-27; 1900-05-03
Harmonic Filter-P1 Civil | GSB | P1 | 9 | 2025-03-21 | 2025-03-29 | 2025-04-09 | 2025-08-06 | M/s DNC | Nos | 4 | 4 | 4 | 0 | Completed | [9 empty] | 1900-02-28: 0.5; 1900-03-08: 0.4; 1900-03-09: 0.3; 1900-03-23: 0.4; 1900-03-24: 0.4; 1900-05-15: 0.5; 1900-05-16: 0.5; 1900-06-26: 0.5; 1900-06-27: 0.5
Harmonic Filter-P1 Civil | PCC | P1 | 10 | 2025-03-22 | 2025-03-31 | 2025-04-21 | 2025-08-13 | M/s DNC | Nos | 4 | 4 | 4 | 0 | Completed | bar: 1900-03-12; 1900-03-26; 1900-05-17; 1900-07-04
Harmonic Filter-P1 Civil | Raft | P1 | 30 | 2025-03-27 | 2025-04-25 | 2025-05-06 | 2025-12-11 | M/s DNC | Nos | 4 | 4 | 4 | 0 | Completed | bar: 1900-05-11; 1900-06-16; 1900-07-17; 1900-11-01
Harmonic Filter-P1 Civil | Backfilling & Compaction | P1 | 11 | 2025-04-30 | 2025-05-10 | 2025-12-19 | 2026-01-27 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-09: 20%; 1900-11-11: 20%; 1900-12-09: 5%; 1900-12-10: 5%; 1900-12-11: 5%; 1900-12-12: 5%; 1900-12-13: 10%; 1900-12-14: 10%; 1900-12-15: 5%; 1900-12-16: 10%; 1900-12-18: 5%
Harmonic Filter-P1 Civil | Handover to Harmonic filter Erection Vendor | P1 |  |  | 2025-05-11 |  | 2025-06-21
Harmonic Filter-P2 Civil | Harmonic Filter (P2) Foundations | P2 | 54 | 2025-03-29 | 2025-05-21 |  |  |  |  | 5.2308 | 5.2308 | 4.3077 | 0.92308 | bar: 1899-12-31 to 1900-07-22
Harmonic Filter-P2 Civil | Excavation | P2 | 9 | 2025-03-29 | 2025-04-06 | 2026-02-17 | 2026-02-18 | M/s HSB | Nos | 4 | 4 | 4 | 0 | [10 empty] | 1901-01-08: 2; 1901-01-09: 2
Harmonic Filter-P2 Civil | Rubble soling | P2 | 9 | 2025-03-30 | 2025-04-07 | 2026-02-17 | 2026-02-18 | M/s HSB | Nos | 4 | 4 | 4 | 0 | [10 empty] | 1901-01-08: 2; 1901-01-09: 2
Harmonic Filter-P2 Civil | PCC | P2 | 15 | 2025-04-02 | 2025-04-16 | 2026-02-17 | 2026-02-18 | M/s HSB | Nos | 4 | 4 | 4 | 0 | [10 empty] | 1901-01-08: 2; 1901-01-09: 2
Harmonic Filter-P2 Civil | Raft | P2 | 30 | 2025-04-07 | 2025-05-06 | 2026-02-17 |  | M/s HSB | Nos | 4 | 4 | 2 | 2 | [10 empty] | 1901-01-08: 0.5; 1901-01-09: 0.5; 1901-01-14: 1
Harmonic Filter-P2 Civil | Backfilling & Compaction | P2 | 13 | 2025-05-08 | 2025-05-20 |  |  | M/s HSB | Lot | 1 | 1 | 0 | 1
Harmonic Filter-P2 Civil | Handover to Harmonic filter Erection Vendor | P2 |  |  | 2025-05-21 |  | 1899-12-31
Burnt Oil Tank | Burnt Oil Tank | P1 | 22 | 2025-05-03 | 2025-05-24 | bar: 1899-12-31 to 1900-07-22
Burnt Oil Tank | Excavation | P1 | 6 | 2025-05-03 | 2025-05-08 | 2025-11-18 | 2025-11-18 | M/s DNC | Nos | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-09: 100%
Burnt Oil Tank | Rubble soling | P1 | 5 | 2025-05-05 | 2025-05-09 | 2025-11-18 | 2025-11-18 | M/s DNC | Nos | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-09: 100%
Burnt Oil Tank | PCC | P1 | 3 | 2025-05-07 | 2025-05-09 | 2025-11-19 | 2025-11-19 | M/s DNC | Nos | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-10: 100%
Burnt Oil Tank | Raft | P1 | 5 | 2025-05-09 | 2025-05-13 | 2025-11-25 | 2025-11-29 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-16: 50%; 1900-10-20: 50%
Burnt Oil Tank | RCC Wall | P1 | 8 | 2025-05-13 | 2025-05-20 | 2025-11-29 | 2025-12-03 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-24: 100%
Burnt Oil Tank | Columns Up to NGL | P1 | 8 | 2025-05-13 | 2025-05-20 | 2025-12-01 | 2025-12-05 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-26: 100%
Burnt Oil Tank | Slab casting | P1 | 5 | 2025-05-15 | 2025-05-19 | 2025-12-08 | 2025-12-26 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-16: 100%
Burnt Oil Tank | Hume Pipe Laying | P1 | 6 | 2025-05-17 | 2025-05-22 | 2025-12-21 | 2025-12-25 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-11: 50%; 1900-11-15: 50%
Burnt Oil Tank | Chamber Interconnection | P1 | 6 | 2025-05-19 | 2025-05-24 | 2025-12-26 | 2025-12-26 | M/s DNC | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-16: 100%
Balance Civil Works | Balance Works | P2 | 26 | 2025-05-20 | 2025-06-14 | 2025-05-02 | bar: 1899-12-31 to 1900-07-22
Balance Civil Works | Backfilling & levelling under GIS , MCR & SGR | P2 | 10 | 2025-05-20 | 2025-05-29 |  |  | M/s DNC | Lot | 1 | 1 | 0 | 1
Balance Civil Works | Roads | P2 | 25 | 2025-05-20 | 2025-06-13 |  |  | M/s DNC | RM | 995.332 | 995.332 | 0 | 995.332
Balance Civil Works | Drains | P2 | 25 | 2025-05-20 | 2025-06-13 | 2026-02-18 |  | M/s DNC | RM | 875 | 875 | 270 | 605 | [10 empty] | 1901-01-09: 120; 1901-01-10: 50; 1901-01-12: 100
Balance Civil Works | Hume Pipes | P1 | 25 | 2025-05-20 | 2025-06-13 |  |  | M/s DNC | Lot | 1 | 1 | 0 | 1
Balance Civil Works | Gravel Filling | P1 | 19 | 2025-05-27 | 2025-06-14 | 2025-12-24 |  | M/s DNC | Lot | 1 | 1 | 0.3 | 0.7 | [10 empty] | 1900-11-14: 30%
Balance Civil Works | Fencing Works | P1 | [5 empty] | M/s DNC
Balance Civil Works | Fencing- Auguring | P1 | 8 | 2025-05-27 | 2025-06-03 | 2026-02-25 |  | M/s DNC | RM | 995.332 | 995.332 | 200 | 795.332 | [10 empty] | 1901-01-16: 100; 1901-01-17: 100
Balance Civil Works | Fencing- Pole casting |  | 8 | 2025-05-28 | 2025-06-04 | 2026-02-26 |  | M/s DNC | Nos | 83 | 83 | 10 | 73 | [10 empty] | 1901-01-17: 10
Balance Civil Works | Fencing- Mesh Installation | P1 | 9 | 2025-05-31 | 2025-06-08 |  |  | M/s DNC | RM | 995.332 | 995.332 | 0 | 995.332
Balance Civil Works | Gates | P1 | 5 | 2025-06-06 | 2025-06-10 |  |  | M/s DNC | Nos | 11 | 11 | 0 | 11
Balance Civil Works | Yard Backfilling | P1 | 12 | 2025-05-20 | 2025-05-31 | 2025-05-02 |  | M/s DNC | Lot | 1 | 1 | 0.16 | 0.84 | [10 empty] | 1900-05-22: 0.2; 1900-10-05: 1%; 1900-10-06: 1%; 1900-10-07: 1%; 1900-10-26: 5%; 1900-11-15: 10%; 1900-11-30: 0.01; 1900-12-01: 0.01; 1900-12-02: 0.01; 1900-12-03: 0.01; 1900-12-09: 0.01; 1900-12-10: 0.01; 1901-01-11: 0.05; 1901-01-12: 0.05
Parking Shed | Parking Shed | P2 | 26 | 2025-05-20 | 2025-06-14 | bar: 1900-05-02 to 1900-07-22
Parking Shed | Excavation | P2 | 1 | 2025-05-20 | 2025-05-20 |  |  |  | Nos | 16 | 16 | 0 | 16
Parking Shed | Rubble soling | P2 | 1 | 2025-05-21 | 2025-05-21 |  |  |  | Nos | 16 | 16 | 0 | 16
Parking Shed | PCC | P2 | 2 | 2025-05-22 | 2025-05-23 |  |  |  | Nos | 16 | 16 | 0 | 16
Parking Shed | Footings | P2 | 5 | 2025-05-24 | 2025-05-28 |  |  |  | Nos | 16 | 16 | 0 | 16
Parking Shed | Pedestals | P2 | 5 | 2025-05-29 | 2025-06-02 |  |  |  | Nos | 16 | 16 | 0 | 16
Parking Shed | Structure & Erection | P2 | 5 | 2025-06-04 | 2025-06-08 |  |  |  | Lot | 1 | 1 | 0 | 1
Parking Shed | Roof Sheeting | P2 | 4 | 2025-06-09 | 2025-06-12 |  |  |  | Lot | 1 | 1 | 0 | 1
Parking Shed | Flooring Work | P2 | 2 | 2025-06-13 | 2025-06-14 |  |  |  | Lot | 1 | 1 | 0 | 1
C | Electrical Erection Works |  | 125 | 2025-03-31 | 2025-08-02 | 2025-05-04 | bar: 1900-05-02 to 1900-07-22
Earthing | Earthing |  | 64 | 2025-04-22 | 2025-06-24 | 2025-05-04 | bar: 1900-05-02 to 1900-07-22
Earthing | 40 mm Dia Earthing Rod - Main Grid Earthing & Riser |  | 62 | 2025-04-22 | 2025-06-22 | 2025-05-04 |  | M/s Hyosung | Rm | 10725 | 10725 | 10165 | 560 | [10 empty] | 1900-03-25: 40; 1900-03-26: 20; 1900-03-27: 40; 1900-03-28: 20; 1900-03-29: 50; 1900-03-30: 20; 1900-03-31: 35; 1900-04-01: 75; 1900-04-02: 100; 1900-04-03: 20; 1900-04-04: 20; 1900-04-07: 90; 1900-04-08: 60; 1900-04-09: 30; 1900-04-12: 40; 1900-04-13: 60; 1900-04-14: 25; 1900-04-15: 60; 1900-04-17: 50; 1900-04-18: 70; 1900-04-19: 100; 1900-04-20: 120; 1900-04-22: 80; 1900-04-23: 100; 1900-04-24: 130; 1900-04-25: 45; 1900-04-26: 150; 1900-04-27: 60; 1900-04-28: 50; 1900-04-29: 40; 1900-04-30: 200; 1900-05-01: 160; 1900-05-02: 150; 1900-05-03: 150; 1900-05-04: 100; 1900-05-05: 120; 1900-05-06: 120; 1900-05-09: 50; 1900-05-10: 100; 1900-05-11: 120; 1900-05-12: 60; 1900-05-13: 80; 1900-05-14: 120; 1900-05-15: 240; 1900-05-16: 300; 1900-05-17: 260; 1900-05-21: 150; 1900-05-22: 100; 1900-05-29: 50; 1900-05-30: 100; 1900-05-31: 100; 1900-06-01: 100; 1900-06-02: 100; 1900-06-03: 100; 1900-06-04: 100; 1900-06-05: 100; 1900-06-06: 100; 1900-06-07: 100; 1900-06-08: 100; 1900-07-03: 70; 1900-07-04: 80; 1900-07-05: 110; 1900-07-06: 80; 1900-07-07: 70; 1900-07-08: 90; 1900-07-09: 70; 1900-07-10: 100; 1900-07-12: 100; 1900-07-18: 120; 1900-07-19: 100; 1900-07-20: 80; 1900-07-23: 120; 1900-07-24: 80; 1900-07-25: 110; 1900-10-06: 100; 1900-10-09: 100; 1900-10-15: 100; 1900-10-20: 500; 1900-10-21: 390; 1900-10-22: 100; 1900-10-23: 900; 1900-10-25: 300; 1900-11-17: 200; 1900-11-21: 225; 1900-12-07: 140; 1900-12-08: 100; 1900-12-09: 80; 1900-12-10: 120
Earthing | 40mm Dia GIS Grid |  | 62 | 2025-04-22 | 2025-06-22 | 2025-06-20 | 2025-06-30 | M/s Hyosung | Rm | 495 | 495 | 495 | 0 | Completed | [9 empty] | 1900-05-13: 60; 1900-05-14: 80; 1900-05-16: 60; 1900-05-17: 75; 1900-05-21: 100; 1900-05-22: 120
Earthing | 75 x 12 mm GI Flat Bar Earth |  | 32 | 2025-05-22 | 2025-06-22 | 2025-07-23 |  | M/s Hyosung | Rm | 950 | 950 | 800 | 150 | [10 empty] | 1900-06-14: 20; 1900-06-15: 40; 1900-06-16: 30; 1900-06-17: 40; 1900-06-18: 40; 1900-06-19: 20; 1900-06-20: 20; 1900-06-21: 20; 1900-06-22: 20; 1900-06-25: 50; 1900-06-26: 50; 1900-06-27: 50; 1900-06-28: 50; 1900-07-01: 80; 1900-07-02: 30; 1900-07-23: 40; 1900-07-25: 60; 1900-10-15: 100; 1900-10-21: 40
Earthing | 50 x 6 mm GI Flat Bar Earth |  | 32 | 2025-05-22 | 2025-06-22 | 2025-07-28 |  | M/s Hyosung | Rm | 915 | 915 | 810 | 105 | [10 empty] | 1900-06-22: 40; 1900-06-23: 30; 1900-06-24: 40; 1900-06-25: 40; 1900-06-26: 30; 1900-06-27: 50; 1900-06-28: 20; 1900-06-29: 25; 1900-06-30: 15; 1900-07-01: 30; 1900-07-02: 20; 1900-07-03: 30; 1900-07-04: 30; 1900-07-05: 40; 1900-07-06: 15; 1900-07-07: 15; 1900-07-08: 20; 1900-07-24: 80; 1900-07-25: 40; 1900-10-05: 100; 1900-10-15: 100
Earthing | Earth Electrode Pits 40mm Dia - 3m Long |  | 4 | 2025-06-21 | 2025-06-24 | 2025-11-14 |  | M/s Hyosung | Nos | 137 | 137 | 101 | 36 | [10 empty] | 1900-10-06: 7; 1900-10-15: 8; 1900-10-21: 15; 1900-10-23: 10; 1900-10-25: 10; 1900-11-18: 27; 1900-11-21: 24
Earthing | Earth Electrode Pit 65mm Dia - 3m Long |  | 4 | 2025-06-21 | 2025-06-24 | 2025-12-02 |  | M/s Hyosung | Nos | 18 | 18 | 16 | 2 | [10 empty] | 1900-10-23: 8; 1900-10-25: 4; 1900-11-20: 4
Earthing | Chambers |  | 4 | 2025-06-21 | 2025-06-24 |  |  | M/s Hyosung | Nos | 155 | 155 | 30 | 125 | [10 empty] | 1900-11-17: 15; 1900-11-21: 15
Power Trafo - 01 Elec | Power Transformer - 01 | P1 | 40 | 2025-04-26 | 2025-06-04 | 2025-06-10 | bar: 1900-05-02 to 1900-07-22
Power Trafo - 01 Elec | Transformer tank Unloading at plinth | P1 | 2 | 2025-04-26 | 2025-04-27 | 2025-06-10 | 2025-06-13 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-05-01: 0.3; 1900-05-02: 0.5; 1900-05-03: 0.1; 1900-05-04: 0.1
Power Trafo - 01 Elec | Cooling System-A type frame & Support (top & bottom header) | P1 | 3 | 2025-04-28 | 2025-04-30 | 2025-08-03 | 2025-08-06 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-06-24: 0.3; 1900-06-25: 0.3; 1900-06-26: 0.2; 1900-06-27: 0.2
Power Trafo - 01 Elec | Radiators, & Conservator erection | P1 | 3 | 2025-05-01 | 2025-05-03 | 2025-08-07 | 2025-08-13 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-06-28: 0.5; 1900-06-29: 0.2; 1900-07-04: 0.3
Power Trafo - 01 Elec | Marshalling box, DM box, FCC box erection | P1 | 2 | 2025-05-04 | 2025-05-05 | 2025-08-02 | 2025-08-03 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-06-23: 0.4; 1900-06-24: 0.6
Power Trafo - 01 Elec | Bushing - Testing (before erection-Tan Delta & CT test) | P1 | 3 | 2025-05-06 | 2025-05-08 | 2025-06-26 | 2025-06-26 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | bar: 1900-05-17
Power Trafo - 01 Elec | Bushing Coating, Bushing erection | P1 | 3 | 2025-05-09 | 2025-05-11 | 2025-07-12 | 2025-08-03 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-06-02: 0.5; 1900-06-24: 0.5
Power Trafo - 01 Elec | LV Box & support erection | P1 | 3 | 2025-05-12 | 2025-05-14 | 2025-08-08 | 2025-08-08 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | bar: 1900-06-29
Power Trafo - 01 Elec | Pressure test (24Hrs + 24Hrs) | P1 | 3 | 2025-05-15 | 2025-05-17 | 2025-08-12 | 2025-08-13 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | bar: 1900-07-04
Power Trafo - 01 Elec | Vacuuming | P1 | 3 | 2025-05-18 | 2025-05-20 | 2025-08-13 | 2025-08-16 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-07-04: 0.2; 1900-07-05: 0.3; 1900-07-06: 0.3; 1900-07-07: 0.2
Power Trafo - 01 Elec | Pressure test (24Hrs ) | P1 | 1 | 2025-05-21 | 2025-05-21 | 2025-08-16 | 2025-08-17 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | bar: 1900-07-08
Power Trafo - 01 Elec | Vacuuming | P1 | 1 | 2025-05-22 | 2025-05-22 | 2025-08-18 | 2025-08-20 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-07-09: 0.3; 1900-07-10: 0.3; 1900-07-11: 0.4
Power Trafo - 01 Elec | Tank Oil Filling | P1 | 2 | 2025-05-23 | 2025-05-24 | 2025-09-04 | 2025-09-06 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-07-26: 0.3; 1900-07-27: 0.4; 1900-07-28: 0.3
Power Trafo - 01 Elec | Filtration | P1 | 4 | 2025-05-25 | 2025-05-28 | 2025-09-06 | 2025-11-24 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-09-21: 20%; 1900-09-22: 10%; 1900-09-23: 10%; 1900-09-24: 10%; 1900-09-26: 10%; 1900-09-30: 2%; 1900-10-01: 3%; 1900-10-14: 0.15; 1900-10-15: 0.2
Power Trafo - 01 Elec | Internal Cabling & termination (FCC, MBox, DM box) | P1 | 4 | 2025-05-29 | 2025-06-01 | 2025-08-16 | 2025-08-18 | M/s TBEA | Run | 61 | 61 | 61 | 0 | Completed | 1
Power Trafo - 01 Elec | MB Box to RTD | P1 | 4 | 2025-05-29 | 2025-06-01 | 2025-08-16 | 2025-08-18 | M/s TBEA | Run | 4 | 4 | 4 | 0 | Completed | [9 empty] | 1900-07-07: 2; 1900-07-08: 1; 1900-07-09: 1
Power Trafo - 01 Elec | MB Box to Bushing CT | P1 | 4 | 2025-05-29 | 2025-06-01 | 2025-08-16 | 2025-08-18 | M/s TBEA | Run | 27 | 27 | 27 | 0 | Completed | [9 empty] | 1900-07-07: 12; 1900-07-08: 13; 1900-07-09: 2
Power Trafo - 01 Elec | MB Box to Buchholz Relay | P1 | 4 | 2025-05-29 | 2025-06-01 | 2025-08-16 | 2025-08-17 | M/s TBEA | Run | 2 | 2 | 2 | 0 | Completed | [9 empty] | 1900-07-08: 2
Power Trafo - 01 Elec | MB box to PRV (Trip Signal) | P1 | 4 | 2025-05-29 | 2025-06-01 | 2025-08-16 | 2025-08-17 | M/s TBEA | Run | 3 | 3 | 3 | 0 | Completed | [9 empty] | 1900-07-08: 3
Power Trafo - 01 Elec | FCC to MB box - AC & DC cable | P1 | 4 | 2025-05-29 | 2025-06-01 | 2025-08-16 | 2025-08-18 | M/s TBEA | Run | 2 | 2 | 2 | 0 | Completed | bar: 1900-07-08 to 1900-07-09
Power Trafo - 01 Elec | FCC to Fan Motors | P1 | 4 | 2025-05-29 | 2025-06-01 | 2025-08-16 | 2025-08-18 | M/s TBEA | Run | 18 | 18 | 18 | 0 | Completed | [9 empty] | 1900-07-07: 7; 1900-07-08: 10; 1900-07-09: 1
Power Trafo - 01 Elec | FCC to Pump | P1 | 4 | 2025-05-29 | 2025-06-01 | 2025-08-16 | 2025-08-18 | M/s TBEA | Run | 4 | 4 | 4 | 0 | Completed | [9 empty] | 1900-07-08: 3; 1900-07-09: 1
Power Trafo - 01 Elec | FCC to OLTC (DM Box) | P1 | 4 | 2025-05-29 | 2025-06-01 | 2025-08-16 | 2025-08-18 | M/s TBEA | Run | 1 | 1 | 1 | 0 | Completed | bar: 1900-07-09
Power Trafo - 01 Elec | Outdoor Cabling & termination (FCC, MBox, DM box & RTCC) | P1 | 4 | 2025-05-29 | 2025-06-01 |  |  | M/s TBEA | Run | 19 | 19 | 19 | 0 | Completed | 1
Power Trafo - 01 Elec | FCC to RTCC | P1 | 4 | 2025-05-29 | 2025-06-01 | 2025-12-09 | 2025-12-10 | M/s TBEA | Run | 6 | 6 | 6 | 0 | Completed | [9 empty] | 1900-10-30: 3; 1900-10-31: 3
Power Trafo - 01 Elec | MB to RTCC | P1 | 4 | 2025-05-29 | 2025-06-01 | 2025-12-09 | 2025-12-10 | M/s TBEA | Run | 2 | 2 | 2 | 0 | Completed | bar: 1900-10-30 to 1900-10-31
Power Trafo - 01 Elec | RTCC to DM box | P1 | 4 | 2025-05-29 | 2025-06-01 | 2025-12-09 | 2025-12-10 | M/s TBEA | Run | 4 | 4 | 4 | 0 | Completed | [9 empty] | 1900-10-30: 2; 1900-10-31: 2
Power Trafo - 01 Elec | FCC to AC, DC DB panel | P1 | 4 | 2025-05-29 | 2025-06-01 | 2025-12-09 | 2025-12-10 | M/s TBEA | Run | 4 | 4 | 4 | 0 | Completed | [9 empty] | 1900-10-30: 2; 1900-10-31: 2
Power Trafo - 01 Elec | RTCC to DC & DB | P1 | 4 | 2025-05-29 | 2025-06-01 | 2025-12-09 | 2025-12-10 | M/s TBEA | Run | 2 | 2 | 2 | 0 | Completed | bar: 1900-10-30 to 1900-10-31
Power Trafo - 01 Elec | RTCC to AC & DB panel | P1 | 4 | 2025-05-29 | 2025-06-01 | 2025-12-09 | 2025-12-10 | M/s TBEA | Run | 1 | 1 | 1 | 0 | Completed | bar: 1900-10-31
Power Trafo - 01 Elec | Testing | P1 | 4 | 2025-05-29 | 2025-06-01 |  |  | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1
Power Trafo - 01 Elec | Tan Delta - PTR core | P1 | 3 | 2025-06-02 | 2025-06-04 | 2025-12-04 | 2025-12-04 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-25: 100%
Power Trafo - 01 Elec | Tan Delta - Bushing ( After Erection) | P1 | 3 | 2025-06-02 | 2025-06-04 | 2025-12-04 | 2025-12-04 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-25: 100%
Power Trafo - 01 Elec | Short & Open Circuit Test | P1 | 3 | 2025-06-02 | 2025-06-04 | 2025-12-03 | 2025-12-03 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-24: 100%
Power Trafo - 01 Elec | Magnetic Balance | P1 | 3 | 2025-06-02 | 2025-06-04 | 2025-12-03 | 2025-12-03 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-24: 100%
Power Trafo - 01 Elec | IR Test | P1 | 3 | 2025-06-02 | 2025-06-04 | 2025-12-04 | 2025-12-04 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-25: 100%
Power Trafo - 01 Elec | Vector Group Test | P1 | 3 | 2025-06-02 | 2025-06-04 | 2025-12-03 | 2025-12-03 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-24: 100%
Power Trafo - 01 Elec | SFRA Test | P1 | 3 | 2025-06-02 | 2025-06-04 | 2025-12-03 | 2025-12-03 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-24: 100%
Power Trafo - 01 Elec | CT Test | P1 | 3 | 2025-06-02 | 2025-06-04 | 2025-12-02 | 2025-12-02 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-23: 100%
Power Trafo - 01 Elec | Pre commissioning | P1 | 3 | 2025-06-02 | 2025-06-04 | 2025-12-04 | 2025-12-04 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-10-25: 100%
Power Trafo - 01 Elec | NIFPS Panel Erection | P1 | 7 | 2025-05-15 | 2025-05-21 | 2025-12-03 | 2025-12-03 | M/s TBEA | Nos | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-24: 100%
Power Trafo - 01 Elec | NIFPS Pipe Fixing | P1 | 7 | 2025-05-15 | 2025-05-21 | 2025-12-04 | 2025-12-18 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-25: 10%; 1900-10-28: 10%; 1900-10-29: 30%; 1900-10-31: 20%; 1900-11-08: 30%
Power Trafo - 02 Elec | Power Transformer - 02 | P1 | 40 | 2025-05-01 | 2025-06-09 | 2025-06-07 | bar: 1900-04-29 to 1900-07-22
Power Trafo - 02 Elec | Transformer tank Unloading at plinth | P1 | 2 | 2025-05-01 | 2025-05-02 | 2025-06-07 | 2025-06-07 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | bar: 1900-04-28
Power Trafo - 02 Elec | Cooling System -A type frame & Support (top & bottom header) | P1 | 3 | 2025-05-03 | 2025-05-05 | 2025-07-14 | 2025-07-15 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | bar: 1900-06-05
Power Trafo - 02 Elec | Radiators, Fan, Buchholz & Conservator erection | P1 | 3 | 2025-05-06 | 2025-05-08 | 2025-07-21 | 2025-07-25 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-06-11: 0.2; 1900-06-12: 0.3; 1900-06-13: 0.1; 1900-06-14: 0.1; 1900-06-15: 0.3
Power Trafo - 02 Elec | Marshalling box, DM box, FCC box erection | P1 | 2 | 2025-05-09 | 2025-05-10 | 2025-07-26 | 2025-07-31 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | bar: 1900-06-21
Power Trafo - 02 Elec | Bushing - Testing (before erection-Tan Delta & CT test) | P1 | 3 | 2025-05-11 | 2025-05-13 | 2025-06-26 | 2025-06-26 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | bar: 1900-05-17
Power Trafo - 02 Elec | Bushing Coating, Bushing erection | P1 | 3 | 2025-05-14 | 2025-05-16 | 2025-07-12 | 2025-07-12 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | bar: 1900-05-17
Power Trafo - 02 Elec | LV Box & support erection | P1 | 3 | 2025-05-17 | 2025-05-19 | 2025-07-28 | 2025-07-28 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | bar: 1900-06-16
Power Trafo - 02 Elec | Pressure test (24Hrs + 24Hrs) | P1 | 2 | 2025-05-20 | 2025-05-21 | 2025-07-31 | 2025-08-01 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-06-21: 0.5; 1900-06-22: 0.5
Power Trafo - 02 Elec | Vacuuming | P1 | 4 | 2025-05-22 | 2025-05-25 | 2025-11-22 | 2025-11-24 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-10-14: 30%; 1900-10-15: 20%
Power Trafo - 02 Elec | Pressure test (24Hrs ) | P1 | 1 | 2025-05-26 | 2025-05-26 | 2025-11-24 | 2025-11-25 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | bar: 1900-10-16
Power Trafo - 02 Elec | Vacuuming | P1 | 1 | 2025-05-27 | 2025-05-27 | 2025-11-26 | 2025-11-28 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-10-17: 20%; 1900-10-18: 30%; 1900-10-19: 50%
Power Trafo - 02 Elec | Tank Oil Filling | P1 | 2 | 2025-05-28 | 2025-05-29 | 2025-11-29 | 2025-12-01 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-10-20: 40%; 1900-10-21: 50%; 1900-10-22: 10%
Power Trafo - 02 Elec | Filtration | P1 | 4 | 2025-05-30 | 2025-06-02 | 2025-12-03 | 2025-12-13 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-10-24: 30%; 1900-10-25: 30%; 1900-11-02: 20%; 1900-11-03: 0.2
Power Trafo - 02 Elec | Internal Cabling & termination (FCC, MBox, DM box) | P1 | 4 | 2025-06-03 | 2025-06-06 |  |  | M/s TBEA | Run | 61 | 61 | 61 | 0 | Completed | 1
Power Trafo - 02 Elec | MB Box to RTD | P1 | 4 | 2025-06-03 | 2025-06-06 | 2025-08-21 | 2025-09-03 | M/s TBEA | Run | 4 | 4 | 4 | 0 | Completed | [9 empty] | 1900-07-23: 2; 1900-07-25: 2
Power Trafo - 02 Elec | MB Box to Bushing CT | P1 | 4 | 2025-06-03 | 2025-06-06 | 2025-09-02 | 2025-09-04 | M/s TBEA | Run | 27 | 27 | 27 | 0 | Completed | [9 empty] | 1900-07-24: 6; 1900-07-25: 12; 1900-07-26: 9
Power Trafo - 02 Elec | MB Box to Buchholz Relay | P1 | 4 | 2025-06-03 | 2025-06-06 | 2025-09-03 | 2025-09-03 | M/s TBEA | Run | 2 | 2 | 2 | 0 | Completed | [9 empty] | 1900-07-25: 2
Power Trafo - 02 Elec | MB box to PRV (Trip Signal) | P1 | 4 | 2025-06-03 | 2025-06-06 | 2025-09-03 | 2025-09-04 | M/s TBEA | Run | 3 | 3 | 3 | 0 | Completed | [9 empty] | 1900-07-26: 3
Power Trafo - 02 Elec | FCC to MB box - AC & DC cable | P1 | 4 | 2025-06-03 | 2025-06-06 | 2025-08-21 | 2025-09-03 | M/s TBEA | Run | 2 | 2 | 2 | 0 | Completed | bar: 1900-07-25
Power Trafo - 02 Elec | FCC to Fan Motors | P1 | 4 | 2025-06-03 | 2025-06-06 | 2025-08-26 | 2025-09-02 | M/s TBEA | Run | 18 | 18 | 18 | 0 | Completed | [9 empty] | 1900-07-19: 3; 1900-07-20: 6; 1900-07-23: 4; 1900-07-24: 5
Power Trafo - 02 Elec | FCC to Pump | P1 | 4 | 2025-06-03 | 2025-06-06 | 2025-08-26 | 2025-09-01 | M/s TBEA | Run | 4 | 4 | 4 | 0 | Completed | [9 empty] | 1900-07-23: 4
Power Trafo - 02 Elec | FCC to OLTC (DM Box) | P1 | 4 | 2025-06-03 | 2025-06-06 | 2025-08-26 | 2025-09-01 | M/s TBEA | Run | 1 | 1 | 1 | 0 | Completed | bar: 1900-07-23
Power Trafo - 02 Elec | Outdoor Cabling & termination (FCC, MBox, DM box & RTCC) | P1 | 4 | 2025-05-29 | 2025-06-01 |  |  | M/s TBEA | Run | 19 | 19 | 19 | 0 | Completed
Power Trafo - 02 Elec | FCC to RTCC | P1 | 4 | 2025-05-29 | 2025-06-01 | 2025-12-09 | 2025-12-10 | M/s TBEA | Run | 6 | 6 | 6 | 0 | Completed | [9 empty] | 1900-10-30: 3; 1900-10-31: 3
Power Trafo - 02 Elec | MB to RTCC | P1 | 4 | 2025-05-29 | 2025-06-01 | 2025-12-09 | 2025-12-10 | M/s TBEA | Run | 2 | 2 | 2 | 0 | Completed | bar: 1900-10-30 to 1900-10-31
Power Trafo - 02 Elec | RTCC to DM box | P1 | 4 | 2025-05-29 | 2025-06-01 | 2025-12-10 | 2025-12-10 | M/s TBEA | Run | 4 | 4 | 4 | 0 | Completed | [9 empty] | 1900-10-30: 2; 1900-10-31: 2
Power Trafo - 02 Elec | FCC to AC, DC DB panel | P1 | 4 | 2025-05-29 | 2025-06-01 | 2025-12-10 | 2025-12-11 | M/s TBEA | Run | 4 | 4 | 4 | 0 | Completed | [9 empty] | 1900-10-30: 2; 1900-10-31: 2
Power Trafo - 02 Elec | RTCC to DC & DB | P1 | 4 | 2025-05-29 | 2025-06-01 | 2025-12-10 | 2025-12-11 | M/s TBEA | Run | 2 | 2 | 2 | 0 | Completed | bar: 1900-10-30 to 1900-10-31
Power Trafo - 02 Elec | RTCC to AC & DB panel | P1 | 4 | 2025-05-29 | 2025-06-01 | 2025-12-10 | 2025-12-11 | M/s TBEA | Run | 1 | 1 | 1 | 0 | Completed | bar: 1900-10-31
Power Trafo - 02 Elec | Testing | P1 | 4 | 2025-05-29 | 2025-06-01 |  |  | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed
Power Trafo - 02 Elec | Tan Delta - PTR core | P1 | 3 | 2025-06-07 | 2025-06-09 | 2025-12-15 | 2025-12-15 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-05: 100%
Power Trafo - 02 Elec | Tan Delta - Bushing ( After Erection) | P1 | 3 | 2025-06-07 | 2025-06-09 | 2025-12-14 | 2025-12-14 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-04: 100%
Power Trafo - 02 Elec | Short & Open Circuit Test | P1 | 3 | 2025-06-07 | 2025-06-09 | 2025-12-14 | 2025-12-14 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-04: 100%
Power Trafo - 02 Elec | Magnetic Balance | P1 | 3 | 2025-06-07 | 2025-06-09 | 2025-12-14 | 2025-12-14 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-04: 100%
Power Trafo - 02 Elec | IR Test | P1 | 3 | 2025-06-07 | 2025-06-09 | 2025-12-14 | 2025-12-14 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-04: 100%
Power Trafo - 02 Elec | Vector Group Test | P1 | 3 | 2025-06-07 | 2025-06-09 | 2025-12-14 | 2025-12-14 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-04: 100%
Power Trafo - 02 Elec | SFRA Test | P1 | 3 | 2025-06-07 | 2025-06-09 | 2025-12-15 | 2025-12-15 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-05: 100%
Power Trafo - 02 Elec | CT Test | P1 | 3 | 2025-06-07 | 2025-06-09 | 2025-12-14 | 2025-12-14 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-04: 100%
Power Trafo - 02 Elec | Pre commissioning | P1 | 3 | 2025-06-07 | 2025-06-09 | 2025-12-14 | 2025-12-14 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-11-04: 100%
Power Trafo - 02 Elec | NIFPS Panel Erection | P1 | 7 | 2025-05-20 | 2025-05-26 | 2025-12-03 | 2025-12-03 | M/s TBEA | Nos | 1 | 1 | 1 | 0 | Completed | bar: 1900-10-24
Power Trafo - 02 Elec | NIFPS Pipe Fixing | P1 | 7 | 2025-05-20 | 2025-05-26 | 2025-12-14 | 2025-12-18 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-04: 20%; 1900-11-05: 30%; 1900-11-08: 50%
Power Trafo - 03 Elec | Power Transformer - 03 | P2 | 40 | 2025-06-04 | 2025-07-13 | bar: 1899-12-31 to 1900-07-22
Power Trafo - 03 Elec | Transformer tank Unloading at plinth | P2 | 2 | 2025-06-04 | 2025-06-05 | 2026-01-10 | 2026-01-13 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-12-01: 0.4; 1900-12-02: 0.3; 1900-12-03: 0.2; 1900-12-04: 0.1
Power Trafo - 03 Elec | Cooling System-A type frame & Support (top & bottom header) | P2 | 3 | 2025-06-06 | 2025-06-08 | 2026-01-29 | 2026-01-29 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-12-20: 100%
Power Trafo - 03 Elec | Radiators, Fan, Buchholz & Conservator erection | P2 | 3 | 2025-06-09 | 2025-06-11 | 2026-02-02 | 2026-02-04 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-12-24: 0.2; 1900-12-25: 0.2; 1900-12-26: 0.6
Power Trafo - 03 Elec | Marshalling box | P2 | 3 | 2025-06-12 | 2025-06-14 | 2026-02-19 | 2026-02-19 | M/s TBEA | Nos | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1901-01-10: 100%
Power Trafo - 03 Elec | DM box | P2 | 3 | 2025-06-12 | 2025-06-14 | 2026-02-19 | 2026-02-19 | M/s TBEA | Nos | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1901-01-10: 100%
Power Trafo - 03 Elec | FCC box erection | P2 | 3 | 2025-06-12 | 2025-06-14 | 2026-02-19 | 2026-02-19 | M/s TBEA | Nos | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1901-01-10: 100%
Power Trafo - 03 Elec | Bushing - Testing (before erection-Tan Delta & CT test) | P2 | 3 | 2025-06-15 | 2025-06-17 | 2026-02-06 | 2026-02-06 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [6 empty] | 100% |  |  | 1901-01-10: 100%
Power Trafo - 03 Elec | Bushing Coating, Bushing erection | P2 | 3 | 2025-06-18 | 2025-06-20 | 2026-02-07 | 2026-02-07 | M/s TBEA | Lot | 1 | 1 | 0 | 1 | Completed | [7 empty] | 100%
Power Trafo - 03 Elec | LV Box & support erection | P2 | 3 | 2025-06-21 | 2025-06-23 | 2026-02-23 | 2026-02-23 | M/s TBEA | Lot | 1 | 1 | 0 | 1 | Completed
Power Trafo - 03 Elec | Pressure test (24Hrs + 24Hrs) | P2 | 2 | 2025-06-24 | 2025-06-25 | 2026-02-09 | 2026-02-09 | M/s TBEA | Lot | 1 | 1 | 0 | 1 | Completed | [9 empty] | 1900-12-31: 100%
Power Trafo - 03 Elec | Vacuuming | P2 | 3 | 2025-06-26 | 2025-06-28 | 2026-02-10 | 2026-02-14 | M/s TBEA | Lot | 1 | 1 | 0 | 1 | Completed | [9 empty] | 1901-01-01: 30%; 1901-01-02: 30%; 1901-01-03: 30%; 1901-01-05: 0.1
Power Trafo - 03 Elec | Pressure test (24Hrs ) | P2 | 1 | 2025-06-29 | 2025-06-29 | 2026-02-14 | 2026-02-16 | M/s TBEA | Lot | 1 | 1 | 0.5 | 0.5 | Completed | [9 empty] | 1901-01-05: 20%; 1901-01-06: 30%; 1901-01-07: 0.5
Power Trafo - 03 Elec | Vacuuming | P2 | 1 | 2025-06-30 | 2025-06-30 | 2026-02-15 | 2026-02-18 | M/s TBEA | Lot | 1 | 1 | 0.7 | 0.3 | Completed | [9 empty] | 1901-01-06: 30%; 1901-01-07: 0.4; 1901-01-09: 0.3
Power Trafo - 03 Elec | Tank Oil Filling | P2 | 2 | 2025-07-01 | 2025-07-02 | 2026-02-20 | 2026-02-22 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1901-01-11: 50%; 1901-01-13: 0.5
Power Trafo - 03 Elec | Filtration | P2 | 4 | 2025-07-03 | 2025-07-06 | 2026-02-23 |  | M/s TBEA | Lot | 1 | 1 | 0.3 | 0.7 | [10 empty] | 1901-01-13: 30%
Power Trafo - 03 Elec | Internal Cabling & termination (FCC, MBox, DM box) | P2 | 4 | 2025-07-07 | 2025-07-10 |  |  |  | Run | 61 | 61 | 0 | 61
Power Trafo - 03 Elec | MB Box to RTD | P2 | 4 | 2025-07-07 | 2025-07-10 | 2026-02-20 | 2026-02-20 | M/s TBEA | Run | 4 | 4 | 4 | 0 | Completed | [9 empty] | 1901-01-11: 4
Power Trafo - 03 Elec | MB Box to Bushing CT | P2 | 4 | 2025-07-07 | 2025-07-10 | 2026-02-20 | 2026-02-20 | M/s TBEA | Run | 27 | 27 | 27 | 0 | Completed | [9 empty] | 1901-01-11: 27
Power Trafo - 03 Elec | MB Box to Buchholz Relay | P2 | 4 | 2025-07-07 | 2025-07-10 | 2026-02-20 | 2026-02-20 | M/s TBEA | Run | 2 | 2 | 2 | 0 | Completed | [9 empty] | 1901-01-11: 2
Power Trafo - 03 Elec | MB box to PRV (Trip Signal) | P2 | 4 | 2025-07-07 | 2025-07-10 | 2026-02-20 | 2026-02-20 | M/s TBEA | Run | 3 | 3 | 3 | 0 | Completed | [9 empty] | 1901-01-11: 3
Power Trafo - 03 Elec | FCC to MB box - AC & DC cable | P2 | 4 | 2025-07-07 | 2025-07-10 | 2026-02-20 | 2026-02-20 | M/s TBEA | Run | 2 | 2 | 2 | 0 | Completed | [9 empty] | 1901-01-11: 2
Power Trafo - 03 Elec | FCC to Fan Motors | P2 | 4 | 2025-07-07 | 2025-07-10 | 2026-02-20 | 2026-02-20 | M/s TBEA | Run | 18 | 18 | 18 | 0 | Completed | [9 empty] | 1901-01-11: 18
Power Trafo - 03 Elec | FCC to Pump | P2 | 4 | 2025-07-07 | 2025-07-10 | 2026-02-20 | 2026-02-20 | M/s TBEA | Run | 4 | 4 | 4 | 0 | Completed | [9 empty] | 1901-01-11: 4
Power Trafo - 03 Elec | FCC to OLTC (DM Box) | P2 | 4 | 2025-07-07 | 2025-07-10 | 2026-02-20 | 2026-02-20 | M/s TBEA | Run | 1 | 1 | 1 | 0 | Completed | bar: 1901-01-11
Power Trafo - 03 Elec | Outdoor Cabling & termination (FCC, MBox, DM box & RTCC) | P2 | 4 | 2025-07-08 | 2025-07-11
Power Trafo - 03 Elec | FCC to RTCC | P2 | 4 | 2025-07-08 | 2025-07-11 | 2026-02-21 | 2026-02-21 | M/s TBEA | Run | 6 | 6 | 6 | 0 | Completed | [9 empty] | 1901-01-12: 6
Power Trafo - 03 Elec | MB to RTCC | P2 | 4 | 2025-07-08 | 2025-07-11 | 2026-02-21 | 2026-02-21 | M/s TBEA | Run | 2 | 2 | 2 | 0 | Completed | [9 empty] | 1901-01-12: 2
Power Trafo - 03 Elec | RTCC to DM box | P2 | 4 | 2025-07-08 | 2025-07-11 | 2026-02-21 | 2026-02-21 | M/s TBEA | Run | 4 | 4 | 4 | 0 | Completed | [9 empty] | 1901-01-12: 4
Power Trafo - 03 Elec | FCC to AC, DC DB panel | P2 | 4 | 2025-07-08 | 2025-07-11 | 2026-02-21 | 2026-02-21 | M/s TBEA | Run | 4 | 4 | 4 | 0 | Completed | [9 empty] | 1901-01-12: 4
Power Trafo - 03 Elec | RTCC to DC & DB | P2 | 4 | 2025-07-08 | 2025-07-11 | 2026-02-21 | 2026-02-21 | M/s TBEA | Run | 2 | 2 | 2 | 0 | Completed | [9 empty] | 1901-01-12: 2
Power Trafo - 03 Elec | RTCC to AC & DB panel | P2 | 4 | 2025-07-08 | 2025-07-11 | 2026-02-21 | 2026-02-21 | M/s TBEA | Run | 1 | 1 | 1 | 0 | Completed | bar: 1901-01-12
Power Trafo - 03 Elec | Testing | P2 | 4 | 2025-07-08 | 2025-07-11 |  |  |  | Lot | 1 | 1 | 0 | 1
Power Trafo - 03 Elec | Tan Delta - PTR core | P2 | 3 | 2025-07-11 | 2025-07-13 |  |  | M/s TBEA | Lot | 1 | 1 | 0 | 1
Power Trafo - 03 Elec | Tan Delta - Bushing ( After Erection) | P2 | 3 | 2025-07-11 | 2025-07-13 |  |  | M/s TBEA | Lot | 1 | 1 | 0 | 1
Power Trafo - 03 Elec | Short & Open Circuit Test | P2 | 3 | 2025-07-11 | 2025-07-13 |  |  | M/s TBEA | Lot | 1 | 1 | 0 | 1
Power Trafo - 03 Elec | Magnetic Balance | P2 | 3 | 2025-07-11 | 2025-07-13 |  |  | M/s TBEA | Lot | 1 | 1 | 0 | 1
Power Trafo - 03 Elec | IR Test | P2 | 3 | 2025-07-11 | 2025-07-13 |  |  | M/s TBEA | Lot | 1 | 1 | 0 | 1
Power Trafo - 03 Elec | Vector Group Test | P2 | 3 | 2025-07-11 | 2025-07-13 |  |  | M/s TBEA | Lot | 1 | 1 | 0 | 1
Power Trafo - 03 Elec | SFRA Test | P2 | 3 | 2025-07-11 | 2025-07-13 |  |  | M/s TBEA | Lot | 1 | 1 | 0 | 1
Power Trafo - 03 Elec | CT Test | P2 | 3 | 2025-07-11 | 2025-07-13 |  |  | M/s TBEA | Lot | 1 | 1 | 0 | 1
Power Trafo - 03 Elec | Pre commissioning | P2 | 3 | 2025-07-11 | 2025-07-13 |  |  | M/s TBEA | Lot | 1 | 1 | 0 | 1
Power Trafo - 03 Elec | NIFPS Panel Erection | P2 | 7 | 2025-06-23 | 2025-06-29 |  |  | M/s TBEA | Nos | 1 | 1 | 0 | 1
Power Trafo - 03 Elec | NIFPS Pipe Fixing | P2 | 7 | 2025-06-23 | 2025-06-29 |  |  | M/s TBEA | Lot | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | Power Transformer - 04 | P2 | 40 | 2025-06-16 | 2025-07-25 | bar: 1899-12-31 to 1900-07-22
Power Trafo - 04 Elec | Transformer tank Unloading at plinth | P2 | 2 | 2025-06-16 | 2025-06-17 | 2026-01-17 | 2026-01-22 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-12-09: 10%; 1900-12-10: 10%; 1900-12-11: 40%; 1900-12-13: 40%
Power Trafo - 04 Elec | Cooling System-A type frame & Support (top & bottom header) | P2 | 3 | 2025-06-18 | 2025-06-20 | 2026-02-16 | 2026-02-16 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1901-01-07: 100%
Power Trafo - 04 Elec | Radiators, & Conservator erection | P2 | 3 | 2025-06-21 | 2025-06-23 | 2026-02-26 |  | M/s TBEA | Lot | 1 | 1 | 0.5 | 0.5 | [10 empty] | 1901-01-17: 50%
Power Trafo - 04 Elec | Marshalling box | P2 | 3 | 2025-06-24 | 2025-06-26 | 2026-02-26 | 2026-02-26 | M/s TBEA | Nos | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | DM box | P2 | 3 | 2025-06-24 | 2025-06-26 |  |  | M/s TBEA | Nos | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | FCC box erection | P2 | 3 | 2025-06-24 | 2025-06-26 | 2026-02-27 | 2026-02-27 | M/s TBEA | Nos | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-01-18: 100%
Power Trafo - 04 Elec | Bushing - Testing (before erection-Tan Delta & CT test) | P2 | 3 | 2025-06-27 | 2025-06-29 | 2026-01-03 | 2026-01-03 | M/s TBEA | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-24: 100%
Power Trafo - 04 Elec | Bushing Coating, Bushing erection | P2 | 3 | 2025-06-30 | 2025-07-02 |  |  | M/s TBEA | Lot | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | LV Box & support erection | P2 | 3 | 2025-07-03 | 2025-07-05 |  |  | M/s TBEA | Lot | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | Pressure test (24Hrs + 24Hrs) | P2 | 2 | 2025-07-06 | 2025-07-07 |  |  | M/s TBEA | Lot | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | Vacuuming | P2 | 3 | 2025-07-08 | 2025-07-10 |  |  | M/s TBEA | Lot | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | Pressure test (24Hrs ) | P2 | 1 | 2025-07-11 | 2025-07-11 |  |  | M/s TBEA | Lot | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | Vacuuming | P2 | 1 | 2025-07-12 | 2025-07-12 |  |  | M/s TBEA | Lot | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | Tank Oil Filling | P2 | 2 | 2025-07-13 | 2025-07-14 |  |  | M/s TBEA | Lot | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | Filtration | P2 | 4 | 2025-07-15 | 2025-07-18 |  |  |  | Lot | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | Internal Cabling & termination (FCC, MBox, DM box) | P2 | 4 | 2025-07-19 | 2025-07-22 |  |  |  | Run | 61 | 61 | 0 | 61
Power Trafo - 04 Elec | MB Box to RTD | P2 | 4 | 2025-07-19 | 2025-07-22 |  |  |  | Run | 4 | 4 | 0 | 4
Power Trafo - 04 Elec | MB Box to Bushing CT | P2 | 4 | 2025-07-19 | 2025-07-22 |  |  |  | Run | 27 | 27 | 0 | 27
Power Trafo - 04 Elec | MB Box to Buchholz Relay | P2 | 4 | 2025-07-19 | 2025-07-22 |  |  |  | Run | 2 | 2 | 0 | 2
Power Trafo - 04 Elec | MB box to PRV (Trip Signal) | P2 | 4 | 2025-07-19 | 2025-07-22 |  |  |  | Run | 3 | 3 | 0 | 3
Power Trafo - 04 Elec | FCC to MB box - AC & DC cable | P2 | 4 | 2025-07-19 | 2025-07-22 |  |  |  | Run | 2 | 2 | 0 | 2
Power Trafo - 04 Elec | FCC to Fan Motors | P2 | 4 | 2025-07-19 | 2025-07-22 |  |  |  | Run | 18 | 18 | 0 | 18
Power Trafo - 04 Elec | FCC to Pump | P2 | 4 | 2025-07-19 | 2025-07-22 |  |  |  | Run | 4 | 4 | 0 | 4
Power Trafo - 04 Elec | FCC to OLTC (DM Box) | P2 | 4 | 2025-07-19 | 2025-07-22 |  |  |  | Run | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | Outdoor Cabling & termination (FCC, MBox, DM box & RTCC) | P2 | 4 | 2025-07-08 | 2025-07-11 |  |  |  | Run | 19 | 19 | 0 | 19
Power Trafo - 04 Elec | FCC to RTCC | P2 | 4 | 2025-07-08 | 2025-07-11 |  |  |  | Run | 6 | 6 | 0 | 6
Power Trafo - 04 Elec | MB to RTCC | P2 | 4 | 2025-07-08 | 2025-07-11 |  |  |  | Run | 2 | 2 | 0 | 2
Power Trafo - 04 Elec | RTCC to DM box | P2 | 4 | 2025-07-08 | 2025-07-11 |  |  |  | Run | 4 | 4 | 0 | 4
Power Trafo - 04 Elec | FCC to AC, DC DB panel | P2 | 4 | 2025-07-08 | 2025-07-11 |  |  |  | Run | 4 | 4 | 0 | 4
Power Trafo - 04 Elec | RTCC to DC & DB | P2 | 4 | 2025-07-08 | 2025-07-11 |  |  |  | Run | 2 | 2 | 0 | 2
Power Trafo - 04 Elec | RTCC to AC & DB panel | P2 | 4 | 2025-07-08 | 2025-07-11 |  |  |  | Run | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | Testing | P2 | 4 | 2025-07-08 | 2025-07-11 |  |  |  | Lot | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | Tan Delta - PTR core | P2 | 3 | 2025-07-23 | 2025-07-25 |  |  |  | Lot | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | Tan Delta - Bushing ( After Erection) | P2 | 3 | 2025-07-23 | 2025-07-25 |  |  |  | Lot | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | Short & Open Circuit Test | P2 | 3 | 2025-07-23 | 2025-07-25 |  |  |  | Lot | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | Magnetic Balance | P2 | 3 | 2025-07-23 | 2025-07-25 |  |  |  | Lot | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | IR Test | P2 | 3 | 2025-07-23 | 2025-07-25 |  |  |  | Lot | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | Vector Group Test | P2 | 3 | 2025-07-23 | 2025-07-25 |  |  |  | Lot | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | SFRA Test | P2 | 3 | 2025-07-23 | 2025-07-25 |  |  |  | Lot | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | CT Test | P2 | 3 | 2025-07-23 | 2025-07-25 |  |  |  | Lot | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | Pre commissioning | P2 | 3 | 2025-07-23 | 2025-07-25 |  |  |  | Lot | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | NIFPS Panel Erection | P2 | 7 | 2025-06-23 | 2025-06-29 |  |  |  | Nos | 1 | 1 | 0 | 1
Power Trafo - 04 Elec | NIFPS Pipe Fixing | P2 | 7 | 2025-06-23 | 2025-06-29 |  |  |  | Lot | 1 | 1 | 0 | 1
SGR - 01 Electrical | SGR - 01 - M/s Trisquare | P1 | 42 | 2025-05-04 | 2025-06-14 | 2025-08-23 | bar: 1899-12-31 to 1900-07-22
SGR - 01 Electrical | Switch Board -1 Panel Installation & Coupling | P1 | 4 | 2025-05-04 | 2025-05-07 | 2025-08-23 | 2025-09-01 | M/s Hyosung | Nos | 26 | 26 | 26 | 0 | completed | 1 | [8 empty] | 1900-07-21: 8; 1900-07-22: 9; 1900-07-23: 9
SGR - 01 Electrical | Switch Board -2 Panel Installation & Coupling | P1 | 4 | 2025-05-08 | 2025-05-11 | 2025-09-02 | 2025-09-05 | M/s Hyosung | Nos | 26 | 26 | 26 | 0 | completed | 1 | [8 empty] | 1900-07-24: 8; 1900-07-25: 7; 1900-07-26: 9; 1900-07-27: 2
SGR - 01 Electrical | Switch Board -3 Panel Installation & Coupling | P1 | 4 | 2025-05-08 | 2025-05-11 | 2025-09-05 | 2025-10-06 | M/s Hyosung | Nos | 26 | 26 | 26 | 0 | completed | 1 | [8 empty] | 1900-07-27: 10; 1900-07-28: 11; 1900-07-29: 2; 1900-08-26: 1; 1900-08-27: 2
SGR - 01 Electrical | Switch Board -4 Panel Installation & Coupling | P1 | 4 | 2025-05-12 | 2025-05-15 | 2025-08-24 | 2025-08-29 | M/s Hyosung | Nos | 26 | 26 | 26 | 0 | completed | 1 | [8 empty] | 1900-07-16: 4; 1900-07-17: 5; 1900-07-18: 3; 1900-07-19: 6; 1900-07-20: 5
SGR - 01 Electrical | Switch Board -01 Inter Panel Wiring | P1 | 4 | 2025-05-12 | 2025-05-15 | 2025-09-14 | 2025-09-16 | M/s Hyosung | Nos | 26 | 26 | 26 | 0 | completed | 1 | [8 empty] | 1900-08-05: 10; 1900-08-06: 12; 1900-08-07: 4
SGR - 01 Electrical | Switch Board -02 Inter Panel Wiring | P1 | 4 | 2025-05-16 | 2025-05-19 | 2025-09-11 | 2025-09-14 | M/s Hyosung | Nos | 26 | 26 | 26 | 0 | completed | 1 | [8 empty] | 1900-08-02: 3; 1900-08-03: 11; 1900-08-04: 10; 1900-08-05: 2
SGR - 01 Electrical | Switch Board -03 Inter Panel Wiring | P1 | 4 | 2025-05-16 | 2025-05-19 | 2025-09-16 | 2025-10-05 | M/s Hyosung | Nos | 26 | 26 | 26 | 0 | completed | 1 | [8 empty] | 1900-08-07: 4; 1900-08-08: 5; 1900-08-09: 8; 1900-08-10: 6; 1900-08-24: 2; 1900-08-26: 1
SGR - 01 Electrical | Switch Board -04 Inter Panel Wiring | P1 | 4 | 2025-05-20 | 2025-05-23 | 2025-09-09 | 2025-09-11 | M/s Hyosung | Nos | 26 | 26 | 26 | 0 | completed | 1 | [8 empty] | 1900-07-31: 9; 1900-08-01: 9; 1900-08-02: 8
SGR - 01 Electrical | Busbar coupling & Torquing | P1 | 2 | 2025-05-12 | 2025-05-13 | 2025-10-07 | 2025-10-09 | M/s Hyosung | Set | 4 | 4 | 4 | 0 | completed | [9 empty] | 1900-08-28: 2; 1900-08-29: 1; 1900-08-30: 1
SGR - 01 Electrical | Testing of CT | P1 | 5 | 2025-05-20 | 2025-05-24 | 2025-10-21 | 2025-11-15 | M/s Hyosung | Set | 4 | 4 | 4 | 0 | completed | [9 empty] | 1900-09-11: 0.3; 1900-09-12: 0.4; 1900-09-13: 0.3; 1900-09-14: 0.3; 1900-09-15: 0.3; 1900-09-17: 0.3; 1900-09-18: 0.3; 1900-09-19: 0.3; 1900-09-20: 0.2; 1900-09-21: 0.3; 1900-09-22: 0.2; 1900-09-25: 0.1; 1900-09-26: 0.1; 1900-09-27: 0.1; 1900-09-28: 0.1; 1900-09-29: 0.1; 1900-09-30: 0.1; 1900-10-05: 0.1; 1900-10-06: 0.1
SGR - 01 Electrical | Testing of CB | P1 | 5 | 2025-05-24 | 2025-05-28 | 2025-10-21 | 2025-10-31 | M/s Hyosung | Set | 4 | 4 | 4 | 0 | completed | [9 empty] | 1900-09-11: 0.4; 1900-09-12: 0.4; 1900-09-13: 0.4; 1900-09-14: 0.4; 1900-09-15: 0.4; 1900-09-17: 0.4; 1900-09-18: 0.4; 1900-09-19: 0.4; 1900-09-20: 0.4; 1900-09-21: 0.4
SGR - 01 Electrical | Testing of Hipot | P1 | 5 | 2025-05-28 | 2025-06-01 | 2025-11-05 | 2025-11-06 | M/s Hyosung | Set | 4 | 4 | 4 | 0 | completed | [9 empty] | 1900-09-26: 2; 1900-09-27: 2
SGR - 01 Electrical | SCADA Panel Installation | P1 | 3 | 2025-05-16 | 2025-05-18 | 2025-10-04 | 2025-10-06 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | completed | [9 empty] | 1900-08-25: 0.4; 1900-08-26: 0.2; 1900-08-27: 0.4
SGR - 01 Electrical | SCADA Cable Laying & Termination | P1 | 7 | 2025-05-19 | 2025-05-25 | 2025-10-14 | 2025-11-14 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | completed | [9 empty] | 1900-08-25: 10%; 1900-09-04: 10%; 1900-09-05: 10%; 1900-09-06: 10%; 1900-09-07: 10%; 1900-09-08: 10%; 1900-09-09: 10%; 1900-09-10: 10%; 1900-09-11: 10%; 1900-10-05: 10%
SGR - 01 Electrical | SCADA Configuration & I/O Check | P1 | 6 | 2025-05-26 | 2025-05-31 | 2025-10-31 | 2025-11-03 | M/s Adaptive | Lot | 1 | 1 | 1 | 0 | completed | [9 empty] | 1900-09-21: 30%; 1900-09-22: 30%; 1900-09-23: 10%; 1900-09-24: 30%
SGR - 01 Electrical | SCADA Testing | P1 | 6 | 2025-06-01 | 2025-06-06 | 2025-11-01 | 2025-11-03 | M/s Adaptive | Lot | 1 | 1 | 1 | 0 | completed | [9 empty] | 1900-08-22: 0.4; 1900-08-25: 0.1; 1900-09-24: 50%
SGR - 01 Electrical | SUB DCDB Erection | P1 | 2 | 2025-05-16 | 2025-05-17 | 2025-09-06 | 2025-09-06 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | completed | bar: 1900-07-28
SGR - 01 Electrical | DC LDB Erection | P1 | 2 | 2025-05-16 | 2025-05-17 | 2025-09-06 | 2025-09-06 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | completed | bar: 1900-07-28
SGR - 01 Electrical | SUB ACDB Erection | P1 | 2 | 2025-05-16 | 2025-05-17 | 2025-09-05 | 2025-09-05 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | completed | bar: 1900-07-27
SGR - 01 Electrical | AC LDB Erection | P1 | 2 | 2025-05-16 | 2025-05-17 | 2025-09-05 | 2025-09-05 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | completed | bar: 1900-07-27
SGR - 01 Electrical | 33kv Relay Testing | P1 | 14 | 2025-06-01 | 2025-06-14 | 2025-11-04 | 2025-11-23 | M/s Hyosung | Nos | 80 | 80 | 80 | 0 | completed | 1 | [8 empty] | 1900-08-26: 5; 1900-09-28: 5; 1900-09-29: 6; 1900-09-30: 5; 1900-10-01: 6; 1900-10-02: 6; 1900-10-03: 6; 1900-10-04: 6; 1900-10-05: 6; 1900-10-06: 5; 1900-10-09: 19; 1900-10-14: 5
SGR - 01 Electrical | SGR-1 to Aux Trafo -1 Cable Laying & termination | P1 | 3 | 2025-05-18 | 2025-05-20 | 2025-12-18 | 2025-12-18 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | completed | [9 empty] | 1900-11-08: 100%
SGR - 01 Electrical | Remote DB for 33kv- Erection Local push Buttons | P1 | 2 | 2025-05-16 | 2025-05-17 | 2025-09-15 | 2025-11-12 | M/s Hyosung | Nos | 4 | 4 | 4 | 0 | completed | [9 empty] | 1900-08-06: 3; 1900-10-03: 1
SGR - 01 Electrical | HAVC Panel | P1 | 2 | 2025-05-12 | 2025-05-13 | 2025-09-06 | 2025-09-06 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | completed | bar: 1900-07-28
SGR - 01 Electrical | AHU Commissioning | P1 | 1 | 2025-05-17 | 2025-05-17 |  |  |  | Lot | 1 | 1 | 0 | 1
SGR - 02 Electrical | SGR - 02 | P2 | 42 | 2025-06-22 | 2025-08-02 | bar: 1899-12-31 to 1900-07-22
SGR - 02 Electrical | Switch Board -5 Panel Installation & Coupling | P2 | 4 | 2025-06-22 | 2025-06-25 |  |  | M/s Hyosung | Nos | 26 | 26 | 0 | 26 |  | 0
SGR - 02 Electrical | Switch Board -6 Panel Installation & Coupling | P2 | 4 | 2025-06-26 | 2025-06-29 | 2026-02-26 | 2026-02-27 | M/s Hyosung | Nos | 26 | 26 | 26 | 0 | completed | 1 | [8 empty] | 1901-01-17: 10; 1901-01-18: 16
SGR - 02 Electrical | Switch Board -7 Panel Installation & Coupling | P2 | 4 | 2025-06-26 | 2025-06-29 | 2026-02-23 | 2026-02-26 | M/s Hyosung | Nos | 26 | 26 | 26 | 0 | completed | 1 | [8 empty] | 1901-01-14: 10; 1901-01-15: 5; 1901-01-16: 9; 1901-01-17: 2
SGR - 02 Electrical | Switch Board -8 Panel Installation & Coupling | P2 | 4 | 2025-06-30 | 2025-07-03 | 2026-02-16 | 2026-02-23 | M/s Hyosung | Nos | 26 | 26 | 26 | 0 | completed | 1 | [8 empty] | 1901-01-07: 3; 1901-01-08: 2; 1901-01-09: 2; 1901-01-10: 6; 1901-01-11: 3; 1901-01-13: 5; 1901-01-14: 5
SGR - 02 Electrical | Switch Board -01 Inter Panel Wiring | P2 | 4 | 2025-06-30 | 2025-07-03 |  |  | M/s Hyosung | Nos | 26 | 26 | 0 | 26 |  | 0
SGR - 02 Electrical | Switch Board -02 Inter Panel Wiring | P2 | 4 | 2025-07-04 | 2025-07-07 | 2026-02-26 | 2026-02-27 | M/s Hyosung | Nos | 26 | 26 | 26 | 0 | completed | 1 | [8 empty] | 1901-01-17: 13; 1901-01-18: 13
SGR - 02 Electrical | Switch Board -03 Inter Panel Wiring | P2 | 4 | 2025-07-04 | 2025-07-07 | 2026-02-24 | 2026-02-25 | M/s Hyosung | Nos | 26 | 26 | 26 | 0 | completed | 1 | [8 empty] | 1901-01-15: 13; 1901-01-16: 13
SGR - 02 Electrical | Switch Board -04 Inter Panel Wiring | P2 | 4 | 2025-07-08 | 2025-07-11 | 2026-02-23 | 2026-02-24 | M/s Hyosung | Nos | 26 | 26 | 26 | 0 | completed | 1 | [8 empty] | 1901-01-14: 13; 1901-01-15: 13
SGR - 02 Electrical | Busbar coupling & Torquing | P2 | 2 | 2025-06-30 | 2025-07-01 | 2026-02-17 |  | M/s Hyosung | Set | 4 | 4 | 3 | 1 | [10 empty] | 1901-01-08: 0.4; 1901-01-09: 0; 1901-01-10: 0.1; 1901-01-11: 0.5; 1901-01-12: 0.5; 1901-01-13: 0.5; 1901-01-14: 0.5; 1901-01-15: 0.5
SGR - 02 Electrical | Testing of CT | P2 | 5 | 2025-07-08 | 2025-07-12 |  |  | M/s Hyosung | Set | 4 | 4 | 0 | 4
SGR - 02 Electrical | Testing of CB | P2 | 5 | 2025-07-12 | 2025-07-16 |  |  | M/s Hyosung | Set | 4 | 4 | 0 | 4
SGR - 02 Electrical | Testing of Hipot | P2 | 5 | 2025-07-16 | 2025-07-20 |  |  | M/s Hyosung | Set | 4 | 4 | 0 | 4
SGR - 02 Electrical | SCADA Panel Installation | P2 | 3 | 2025-07-04 | 2025-07-06 |  |  | M/s Hyosung | Nos | 1 | 1 | 0 | 1
SGR - 02 Electrical | SCADA Cable Laying & Termination | P2 | 7 | 2025-07-07 | 2025-07-13 |  |  | M/s Hyosung | Lot | 1 | 1 | 0 | 1
SGR - 02 Electrical | SCADA Configuration & I/O Check | P2 | 6 | 2025-07-14 | 2025-07-19 |  |  | M/s Hyosung | Lot | 1 | 1 | 0 | 1
SGR - 02 Electrical | SCADA Testing | P2 | 6 | 2025-07-20 | 2025-07-25 |  |  | M/s Hyosung | Lot | 1 | 1 | 0 | 1
SGR - 02 Electrical | SUB DCDB Erection | P2 | 2 | 2025-07-04 | 2025-07-05 |  |  | M/s Hyosung | Lot | 1 | 1 | 0 | 1
SGR - 02 Electrical | DC LDB Erection | P2 | 2 | 2025-07-04 | 2025-07-05 |  |  | M/s Hyosung | Lot | 1 | 1 | 0 | 1
SGR - 02 Electrical | SUB ACDB Erection | P2 | 2 | 2025-07-04 | 2025-07-05 |  |  | M/s Hyosung | Lot | 1 | 1 | 0 | 1
SGR - 02 Electrical | AC LDB Erection | P2 | 2 | 2025-07-04 | 2025-07-05 |  |  | M/s Hyosung | Lot | 1 | 1 | 0 | 1
SGR - 02 Electrical | 33kv Relay Testing | P2 | 14 | 2025-07-20 | 2025-08-02 |  |  | M/s Hyosung | Nos | 80 | 80 | 0 | 80
SGR - 02 Electrical | SGR-2 to Aux Trafo -2 Cable Laying & termination | P2 | 3 | 2025-07-06 | 2025-07-08 |  |  | M/s Hyosung | Lot | 1 | 1 | 0 | 1
SGR - 02 Electrical | Remote DB for 33kv- Erection Local push Buttons | P2 | 2 | 2025-07-04 | 2025-07-05 |  |  | M/s Hyosung | Lot | 4 | 4 | 0 | 4
SGR - 02 Electrical | HAVC Panel | P2 | 2 | 2025-06-30 | 2025-07-01 |  |  | M/s Hyosung | Lot | 1 | 1 | 0 | 1
SGR - 02 Electrical | AHU Commissioning | P2 | 1 | 2025-07-05 | 2025-07-05 |  |  | M/s Hyosung | Lot | 1 | 1 | 0 | 1
GIS Eq. Erection -Elec | Main Bay Area (Inside Building) - Erection | P1 | 42 | 2025-05-08 | 2025-06-18 | 2025-06-17 | bar: 1899-12-31 to 1900-07-22
GIS Eq. Erection -Elec | AHU Works | P1
GIS Eq. Erection -Elec | Duct Assembly & Erection | P1 | 3 | 2025-05-03 | 2025-05-05 | 2025-06-17 | 2025-06-19 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-05-08: 0.2; 1900-05-09: 0.5; 1900-05-10: 0.3
GIS Eq. Erection -Elec | Duct Installation with grills | P1 | 2 | 2025-05-06 | 2025-05-07 | 2025-06-20 | 2025-06-21 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-05-11: 50%; 1900-05-12: 50%
GIS Eq. Erection -Elec | Commissioning | P1 | 1 | 2025-05-08 | 2025-05-08 | 2025-11-20 | 2025-11-20 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-11: 100%
GIS Eq. Erection -Elec | GIS Erection | P1
GIS Eq. Erection -Elec | Center Line Marking | P1 | 2 | 2025-05-08 | 2025-05-09 | 2025-07-02 | 2025-07-03 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-05-23: 50%; 1900-05-24: 50%
GIS Eq. Erection -Elec | Circuit Breakers & CT Installation | P1 | 8 | 2025-05-10 | 2025-05-17 | 2025-07-04 | 2025-07-07 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-05-25: 0.3; 1900-05-26: 0.3; 1900-05-27: 0.3; 1900-05-28: 0.1
GIS Eq. Erection -Elec | DS-ES for all Six bays | P1 | 8 | 2025-05-18 | 2025-05-25 | 2025-07-09 | 2025-08-07 | M/s Hyosung | Lot | 1 | 1 | 1.01 | -0.01 | Completed | [9 empty] | 1900-05-30: 0.1; 1900-06-01: 0.05; 1900-06-04: 0.05; 1900-06-06: 0.05; 1900-06-08: 0.05; 1900-06-10: 0.05; 1900-06-12: 0.05; 1900-06-14: 0.05; 1900-06-16: 0.05; 1900-06-19: 0.05; 1900-06-21: 0.05; 1900-06-23: 0.05; 1900-06-25: 0.05; 1900-06-27: 0.01; 1900-06-28: 0.3
GIS Eq. Erection -Elec | HS-ES for all Six bays | P1 | 8 | 2025-05-26 | 2025-06-02 | 2025-07-12 | 2025-08-07 | M/s Hyosung | Lot | 1 | 1 | 0.96 | 0.04 | Completed | [9 empty] | 1900-06-02: 0.05; 1900-06-03: 0.05; 1900-06-05: 0.05; 1900-06-07: 0.05; 1900-06-09: 0.05; 1900-06-10: 0.05; 1900-06-12: 0.05; 1900-06-14: 0.05; 1900-06-17: 0.05; 1900-06-19: 0.05; 1900-06-20: 0.05; 1900-06-22: 0.05; 1900-06-24: 0.05; 1900-06-27: 0.01; 1900-06-28: 0.3
GIS Eq. Erection -Elec | Inspection & Maintenance Platform Installation | P1 | 6 | 2025-06-03 | 2025-06-08 | 2025-10-16 | 2025-10-19 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | completed | [9 empty] | 1900-09-06: 25%; 1900-09-07: 25%; 1900-09-08: 25%; 1900-09-09: 25%
GIS Eq. Erection -Elec | GIS Main Bus Installation | P1 | 5 | 2025-06-03 | 2025-06-07 | 2025-08-05 | 2025-08-20 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-06-26: 0.1; 1900-06-27: 0.1; 1900-06-29: 0.1; 1900-06-30: 0.2; 1900-07-01: 0.2; 1900-07-02: 0.1; 1900-07-09: 0.01; 1900-07-10: 0.01; 1900-07-11: 0.18
GIS Eq. Erection -Elec | Bus VT Installation | P1 | 6 | 2025-06-08 | 2025-06-13 | 2025-08-18 | 2025-08-23 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | completed | [9 empty] | 1900-07-09: 0.3; 1900-07-10: 0.2; 1900-07-13: 0.2; 1900-07-14: 0.3
GIS Eq. Erection -Elec | Vacuuming | P1 | 19 | 2025-05-26 | 2025-06-13 | 2025-07-28 | 2025-11-21 | M/s Hyosung | Comp | 207 | 207 | 207 | 0 | completed | [9 empty] | 1900-06-19: 6; 1900-06-21: 6; 1900-06-22: 4; 1900-06-24: 4; 1900-06-26: 4; 1900-06-27: 2; 1900-06-28: 6; 1900-06-29: 4; 1900-06-30: 4; 1900-07-01: 4; 1900-07-02: 4; 1900-07-03: 4; 1900-07-04: 4; 1900-07-05: 4; 1900-07-06: 4; 1900-07-07: 4; 1900-07-08: 6; 1900-07-09: 6; 1900-07-10: 10; 1900-07-11: 12; 1900-07-12: 10; 1900-07-13: 12; 1900-07-14: 8; 1900-07-15: 12; 1900-07-16: 11; 1900-07-17: 12; 1900-07-18: 10; 1900-10-04: 3; 1900-10-05: 4; 1900-10-06: 3; 1900-10-12: 20
GIS Eq. Erection -Elec | Dew Point Test | P1 | 19 | 2025-05-27 | 2025-06-14 | 2025-07-29 | 2025-11-22 | M/s Hyosung | Comp | 207 | 207 | 207 | 0 | completed | [9 empty] | 1900-06-19: 6; 1900-06-21: 6; 1900-06-22: 4; 1900-06-24: 4; 1900-06-26: 4; 1900-06-27: 2; 1900-06-28: 6; 1900-06-29: 4; 1900-06-30: 4; 1900-07-01: 4; 1900-07-02: 4; 1900-07-03: 4; 1900-07-04: 4; 1900-07-05: 4; 1900-07-06: 4; 1900-07-07: 4; 1900-07-08: 6; 1900-07-09: 6; 1900-07-10: 10; 1900-07-11: 12; 1900-07-12: 10; 1900-07-13: 12; 1900-07-14: 8; 1900-07-15: 12; 1900-07-16: 11; 1900-07-17: 12; 1900-07-18: 10; 1900-10-04: 3; 1900-10-05: 4; 1900-10-06: 3; 1900-10-13: 20
GIS Eq. Erection -Elec | SF6 Gas Filling (Partially & Fully ) | P1 | 20 | 2025-05-29 | 2025-06-17 | 2025-07-31 | 2025-11-23 | M/s Hyosung | Comp | 207 | 207 | 207 | 0 | (Partially Started 0n 31-Jul-25) | [9 empty] | 1900-07-18: 28; 1900-07-19: 25; 1900-07-20: 26; 1900-07-21: 26; 1900-07-22: 24; 1900-07-23: 26; 1900-07-24: 22; 1900-10-05: 3; 1900-10-06: 4; 1900-10-14: 23
GIS Eq. Erection -Elec | Gas Analysis & Leakage checking | P1 | 18 | 2025-06-01 | 2025-06-18 | 2025-11-23 | 2025-11-23 | M/s Hyosung | Comp | 207 | 207 | 207 | 0 | Completed | [9 empty] | 1900-10-14: 207
GIS Eq. Erection -Elec | LCC Panel Erection | P1 | 9 | 2025-05-10 | 2025-05-18 | 2025-07-14 | 2025-07-16 | M/s Hyosung | Nos | 6 | 6 | 6 | 0 | Completed | [9 empty] | 1900-06-04: 3; 1900-06-06: 3
GIS Eq. Erection -Elec | Cable Tray Support & Cable Tray Installation | P1 | 6 | 2025-06-03 | 2025-06-08 | 2025-08-12 | 2025-08-17 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-07-03: 0.2; 1900-07-04: 0.2; 1900-07-05: 0.2; 1900-07-06: 0.1; 1900-07-07: 0.1; 1900-07-08: 0.2
GIS Eq. Erection -Elec | Equipment Testing | P1 | 11 | 2025-06-07 | 2025-06-17 | 2025-08-17 | 2025-11-18 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-07-08: 0.05; 1900-07-09: 0.05; 1900-07-10: 0.05; 1900-07-11: 0.05; 1900-07-15: 0.2; 1900-10-09: 10%
GIB & GAB Erection | GIB & GAB (Gas insulated Air Bushing) - Erection | P1 | 86 | 2025-03-31 | 2025-06-24 |  |  |  |  | 53 | 53 | 53 | 0 | bar: 1899-12-31 to 1900-07-22
GIB & GAB Erection | GIB Support Structure erection - Trafo Side | P1 | 7 | 2025-03-31 | 2025-04-06 | 2025-09-02 | 2025-11-15 | M/s Hyosung | Nos | 53 | 53 | 53 | 0 | completed | [9 empty] | 1900-07-23: 10; 1900-07-24: 11; 1900-07-25: 4; 1900-09-28: 5; 1900-09-29: 6; 1900-10-05: 10; 1900-10-06: 7
GIB & GAB Erection | GIB Duct & Busbar Installation - PT1, PT2, PT3 & PT4 | P1 | 10 | 2025-05-05 | 2025-05-14 | 2025-09-04 | 2025-11-19 | M/s Hyosung | Rm | 558 | 558 | 558 | 0 | completed | [9 empty] | 1900-07-26: 11; 1900-07-27: 30; 1900-07-28: 30; 1900-09-28: 50; 1900-09-29: 100; 1900-09-30: 60; 1900-10-05: 90; 1900-10-06: 85; 1900-10-08: 50; 1900-10-10: 52
GIB & GAB Erection | GIB Support Structure erection - Line Side | P1 | 3 | 2025-03-31 | 2025-04-02 | 2025-11-18 | 2025-11-19 | M/s Hyosung | Nos | 8 | 8 | 8 | 0 | completed | [9 empty] | 1900-10-10: 8
GIB & GAB Erection | GIB Duct & Busbar Installation - Line Side | P1 | 11 | 2025-05-06 | 2025-05-16 | 2025-11-19 | 2025-11-21 | M/s Hyosung | Rm | 64 | 64 | 64 | 0 | completed | [9 empty] | 1900-10-10: 40; 1900-10-12: 24
GIB & GAB Erection | GAB Installation | P1 | 20 | 2025-06-05 | 2025-06-24 | 2025-11-07 | 2025-11-21 | M/s Hyosung | Nos | 15 | 15 | 15 | 0 | completed | [9 empty] | 1900-09-28: 1; 1900-09-29: 1; 1900-09-30: 1; 1900-10-01: 1; 1900-10-02: 2; 1900-10-08: 3; 1900-10-10: 3; 1900-10-12: 3
CRP - Area | CRP - Area | P1 | 35 | 2025-05-07 | 2025-06-10 | 2025-07-15 | bar: 1899-12-31 to 1900-07-22
CRP - Area | DTPC | P1 | 12 | 2025-05-07 | 2025-05-18 | 2025-08-06 | 2025-08-06 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | 1 | bar: 1900-06-27
CRP - Area | PMU Panel | P1 | 12 | 2025-05-07 | 2025-05-18 | 2025-07-17 | 2025-07-17 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | 1 | bar: 1900-06-07
CRP - Area | FOTE Panel | P1 | 12 | 2025-05-07 | 2025-05-18 | 2025-08-06 | 2025-08-06 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | 1 | bar: 1900-06-27
CRP - Area | PLCC | P1 | 12 | 2025-05-07 | 2025-05-18 | 2025-08-06 | 2025-08-06 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | 1 | bar: 1900-06-27
CRP - Area | Tariff Metering (ABT) | P1 | 12 | 2025-05-07 | 2025-05-18 | 2025-07-17 | 2025-07-17 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | 1 | bar: 1900-06-07
CRP - Area | RTCC | P1 & P2 | 12 | 2025-05-07 | 2025-05-18 | 2025-07-21 | 2025-11-14 | M/s Hyosung | Nos | 4 | 4 | 4 | 0 | Completed | 1 | [8 empty] | 1900-06-11: 1; 1900-07-06: 1; 1900-10-05: 2
CRP - Area | NIFPS | P1 & P2 | 12 | 2025-05-07 | 2025-05-18 | 2025-12-15 |  | M/s Hyosung | Nos | 4 | 4 | 2 | 2 |  | 0.5 | [8 empty] | 1900-11-05: 2
CRP - Area | CRP | P1 | 12 | 2025-05-07 | 2025-05-18 | 2025-07-15 | 2025-07-16 | M/s Hyosung | Nos | 15 | 15 | 15 | 0 | Completed | 1 | [8 empty] | 1900-06-05: 10; 1900-06-06: 5
CRP - Area | HVAC DB | P1 | 12 | 2025-05-07 | 2025-05-18 | 2025-09-02 | 2025-09-02 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | 1 | bar: 1900-07-24
CRP - Area | AC Installation In CRP room | P1 | 12 | 2025-05-07 | 2025-05-18 | 2025-09-01 | 2025-11-14 | M/s Hyosung | Nos | 8 | 8 | 8 | 0 | Completed | 1 | [8 empty] | 1900-09-22: 1; 1900-09-23: 1; 1900-09-25: 1; 1900-09-26: 1; 1900-10-05: 4
CRP - Area | Internal Cabling & termination | P1 | 12 | 2025-05-19 | 2025-05-30 | 2025-08-08 | 2025-11-02 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-06-29: 0.2; 1900-06-30: 0.2; 1900-07-01: 0.2; 1900-07-02: 0.1; 1900-08-11: 0.05; 1900-08-12: 0.05; 1900-08-13: 0.05; 1900-09-22: 5%; 1900-09-23: 10%
CRP - Area | LCC to CRP & System Integration | P1 | 11 | 2025-05-31 | 2025-06-10 | 2025-10-26 | 2025-11-05 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-09-16: 20%; 1900-09-17: 20%; 1900-09-18: 10%; 1900-09-24: 10%; 1900-09-25: 20%; 1900-09-26: 20%
MCR - Electrical | MCR | P1 | 30 | 2025-05-15 | 2025-06-13 | 2025-07-14 | bar: 1899-12-31 to 1900-07-22
MCR - Electrical | MSB | P1 | 10 | 2025-05-19 | 2025-05-28 | 2025-07-25 | 2025-07-25 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | bar: 1900-06-15
MCR - Electrical | ACDB | P1 | 10 | 2025-05-19 | 2025-05-28 | 2025-07-25 | 2025-07-25 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | bar: 1900-06-15
MCR - Electrical | MLDB | P1 | 10 | 2025-05-19 | 2025-05-28 | 2025-07-25 | 2025-07-25 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | bar: 1900-06-15
MCR - Electrical | 220V DCDB | P1 | 10 | 2025-05-19 | 2025-05-28 | 2025-07-25 | 2025-07-25 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | bar: 1900-06-15
MCR - Electrical | 48V DCDB | P1 | 10 | 2025-05-19 | 2025-05-28 | 2025-07-26 | 2025-07-26 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | bar: 1900-06-16
MCR - Electrical | DC-LDB | P1 | 10 | 2025-05-19 | 2025-05-28 | 2025-07-26 | 2025-07-26 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | bar: 1900-06-16
MCR - Electrical | Lightning DB | P1 | 10 | 2025-05-19 | 2025-05-28 | 2025-07-26 | 2025-07-26 | M/s Hyosung | Nos | 2 | 2 | 2 | 0 | Completed | [9 empty] | 1900-06-16: 2
MCR - Electrical | SUB ACDB | P1 | 10 | 2025-05-19 | 2025-05-28 | 2025-07-26 | 2025-07-26 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | bar: 1900-06-16
MCR - Electrical | UPS DB | P1 | 10 | 2025-05-19 | 2025-05-28 | 2025-07-27 | 2025-07-27 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | bar: 1900-06-16
MCR - Electrical | HVAC DB | P1 | 10 | 2025-05-19 | 2025-05-28 | 2025-07-27 | 2025-07-27 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | bar: 1900-06-17
MCR - Electrical | 48V DR Panel | P1 | 10 | 2025-05-19 | 2025-05-28 | 2025-07-28 | 2025-07-28 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | bar: 1900-06-18
MCR - Electrical | 220V DR Panel | P1 | 10 | 2025-05-19 | 2025-05-28 | 2025-07-28 | 2025-07-28 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | bar: 1900-06-18
MCR - Electrical | Receptacle Panel | P1 | 10 | 2025-05-19 | 2025-05-28 | 2025-07-27 | 2025-07-27 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | bar: 1900-06-19
MCR - Electrical | 220 V DC Battery charger Erection | P1 | 12 | 2025-05-15 | 2025-05-26 | 2025-07-27 | 2025-07-27 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-06-17
MCR - Electrical | 220 V DC Battery Erection | P1 | 12 | 2025-05-15 | 2025-05-26 | 2025-07-24 | 2025-07-26 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-06-14: 0.3; 1900-06-15: 0.3; 1900-06-16: 0.4
MCR - Electrical | 48 V DC Battery charger Erection | P1 | 12 | 2025-05-15 | 2025-05-26 | 2025-07-29 | 2025-07-29 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-06-19
MCR - Electrical | 48 V DC Battery Erection | P1 | 12 | 2025-05-15 | 2025-05-26 | 2025-07-26 | 2025-07-28 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-06-16: 0.3; 1900-06-17: 0.3; 1900-06-18: 0.4
MCR - Electrical | DG Erection and commissioning | P1 | 10 | 2025-05-19 | 2025-05-28 | 2025-12-19 | 2025-12-19 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-09: 100%
MCR - Electrical | Aux Trafo Erection | P1 | 16 | 2025-05-29 | 2025-06-13 | 2025-07-14 | 2025-07-15 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-06-05
MCR - Electrical | UPS Installation | P1 | 9 | 2025-05-22 | 2025-05-30 | 2025-07-23 | 2025-07-26 | M/s Hyosung | Lot | 1 | 1 | 0 | 1 | Completed
MCR - Electrical | AC Installation | P1 | 6 | 2025-05-31 | 2025-06-05 | 2025-09-03 | 2025-11-18 | M/s Hyosung | Nos | 19 | 19 | 19 | 0 | Completed | [9 empty] | 1900-10-09: 10; 1900-10-12: 9
MCR - Electrical | Illumination works | P1 | 11 | 2025-05-19 | 2025-05-29 | 2025-07-18 | 2025-11-30 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-06-08: 0.05; 1900-06-09: 0.05; 1900-06-11: 0.05; 1900-06-12: 0.05; 1900-06-15: 0.05; 1900-06-17: 0.025; 1900-06-19: 0.025; 1900-06-26: 0.05; 1900-06-27: 0.05; 1900-06-28: 0.1; 1900-06-29: 0.01; 1900-06-30: 0.05; 1900-07-01: 0.05; 1900-07-02: 0.05; 1900-07-05: 0.07; 1900-07-09: 0.02; 1900-07-10: 0.02; 1900-07-15: 0.05; 1900-07-16: 0.05; 1900-07-17: 0.03; 1900-10-17: 5%; 1900-10-21: 5%
MCR - Electrical | SCADA Room
MCR - Electrical | SAS Panel | P1 | 2 | 2025-05-15 | 2025-05-16 | 2025-08-01 | 2025-08-01 | M/s Hyosung | Nos | 2 | 2 | 2 | 0 | Completed | [9 empty] | 1900-06-22: 2
MCR - Electrical | SUX Panel | P1 | 2 | 2025-05-15 | 2025-05-16 | 2025-08-01 | 2025-08-01 | M/s Hyosung | Nos | 2 | 2 | 2 | 0 | Completed | [9 empty] | 1900-06-22: 2
MCR - Electrical | MCR Panel | P1 | 2 | 2025-05-15 | 2025-05-16 | 2025-08-01 | 2025-08-01 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | bar: 1900-06-22
MCR - Electrical | SCADA Server | P1 | 2 | 2025-05-15 | 2025-05-16 | 2025-08-09 | 2025-08-09 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | bar: 1900-06-30
MCR - Electrical | Network Rack | P1 | 2 | 2025-05-15 | 2025-05-16 | 2025-08-09 | 2025-08-09 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | bar: 1900-06-30
MCR - Electrical | Trackor Server | P1 | 2 | 2025-05-15 | 2025-05-16 | 2025-08-09 | 2025-08-09 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | bar: 1900-06-30
MCR - Electrical | PPC-M & S | P1 | 2 | 2025-05-15 | 2025-05-16 | 2025-08-09 | 2025-08-09 | M/s Hyosung | Nos | 2 | 2 | 2 | 0 | Completed | [9 empty] | 1900-07-01: 2
MCR - Electrical | Network Panel | P1 | 2 | 2025-05-15 | 2025-05-16 | 2025-08-09 | 2025-08-09 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | bar: 1900-07-01
MCR - Electrical | SCADA Internal Cabling | P1 | 4 | 2025-05-17 | 2025-05-20 | 2025-10-03 | 2025-11-06 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-08-24: 0.2; 1900-08-25: 0.3; 1900-08-26: 0.3; 1900-09-25: 10%; 1900-09-26: 5%; 1900-09-27: 5%
MCR - Electrical | SCADA Configuration & I/O Check | P1 | 10 | 2025-05-31 | 2025-06-09 | 2025-12-03 | 2025-12-03 | M/s Adaptive | Lot | 1 | 1 | 1 | 0 | Completed | 1 | [8 empty] | 1900-10-24: 100%
AIS | AIS | P1 | 27 | 2025-04-29 | 2025-05-25 | bar: 1899-12-31 to 1900-07-22
AIS | Line Side Structure Erection (LA-3, CVT-3, BPI-6, WT-2) | P1 | 8 | 2025-04-29 | 2025-05-06 | 2025-10-31 | 2025-11-23 | M/s Hyosung | Nos | 14 | 14 | 14 | 0 | Completed | [9 empty] | 1900-09-21: 2; 1900-09-22: 2; 1900-09-23: 2; 1900-09-24: 1; 1900-09-25: 2; 1900-10-14: 5
AIS | Line Equipment Erection | P1 | 5 | 2025-05-14 | 2025-05-18 | 2025-11-22 | 2025-11-25 | M/s Hyosung | Nos | 14 | 14 | 14 | 0 | Completed | [9 empty] | 1900-10-13: 3; 1900-10-14: 6; 1900-10-16: 5
AIS | Testing | P1 | 2 | 2025-05-19 | 2025-05-20 | 2025-12-01 | 2025-12-06 | M/s Hyosung | Nos | 14 | 14 | 14 | 0 | Completed | [9 empty] | 1900-10-22: 4; 1900-10-23: 4; 1900-10-26: 4; 1900-10-27: 2
AIS | Trafo Side Structure Erection (BPI-12 & LA-12) | P1 | 8 | 2025-05-06 | 2025-05-13 | 2025-11-01 | 2025-12-25 | M/s Hyosung | Nos | 24 | 24 | 24 | 0 | Completed | [9 empty] | 1900-09-22: 2; 1900-09-23: 1; 1900-09-24: 2; 1900-09-25: 1; 1900-10-10: 3; 1900-10-14: 3; 1900-10-15: 3; 1900-10-30: 3; 1900-11-01: 2; 1900-11-09: 3; 1900-11-15: 1
AIS | Trafo Equipment Erection | P1 | 5 | 2025-05-19 | 2025-05-23 | 2025-11-10 | 2025-12-25 | M/s Hyosung | Nos | 24 | 24 | 24 | 0 | Completed | [9 empty] | 1900-10-01: 6; 1900-10-10: 3; 1900-10-13: 5; 1900-10-16: 1; 1900-10-30: 3; 1900-11-15: 6
AIS | Testing | P1 | 2 | 2025-05-24 | 2025-05-25 | 2025-12-15 | 2025-12-28 | M/s Hyosung | Nos | 24 | 24 | 24 | 0 | Completed | [9 empty] | 1900-11-05: 12; 1900-11-12: 4; 1900-11-15: 5; 1900-11-18: 3
SVG - Electrical P1 | SVG - P1 ( 01 to 07 ) | P1 | 25 | 2025-06-01 | 2025-06-25 | 2025-07-11 |  |  |  | 7 | 7 | 7 | 0 |  | 7 | bar: 1899-12-31 to 1900-07-22
SVG - Electrical P1 | Container (TSVG -50/33- W-C ) - 1no/1SVG | P1 | 7 | 2025-06-01 | 2025-06-07 | 2025-11-08 | 2026-01-12 | M/s Akshar | Nos | 7 | 7 | 7 | 0 | Completed | 1 | [8 empty] | 1900-09-29: 1; 1900-09-30: 2; 1900-11-27: 1; 1900-11-28: 1; 1900-12-02: 1; 1900-12-03: 1
SVG - Electrical P1 | Reactor - 3nos/1SVG | P1 | 7 | 2025-06-02 | 2025-06-08 | 2025-11-13 | 2026-01-17 | M/s Akshar | Nos | 21 | 21 | 21 | 0 | Completed | 1 | [8 empty] | 1900-10-04: 3; 1900-10-05: 3; 1900-10-06: 3; 1900-12-04: 4; 1900-12-05: 3; 1900-12-06: 2; 1900-12-07: 2; 1900-12-08: 1
SVG - Electrical P1 | Resistor - 3nos/1SVG | P1 | 7 | 2025-06-04 | 2025-06-10 | 2025-11-15 | 2026-01-18 | M/s Akshar | Nos | 21 | 21 | 21 | 0 | Completed | 1 | [8 empty] | 1900-10-06: 3; 1900-10-10: 6; 1900-12-05: 3; 1900-12-06: 2; 1900-12-07: 2; 1900-12-08: 1; 1900-12-09: 4
SVG - Electrical P1 | VCB - 1no/1SVG | P1 | 5 | 2025-06-04 | 2025-06-08 | 2025-11-15 | 2026-01-19 | M/s Akshar | Nos | 7 | 7 | 7 | 0 | Completed | 1 | [8 empty] | 1900-10-06: 3; 1900-12-08: 3; 1900-12-09: 1
SVG - Electrical P1 | Arrestor - 3nos/1SVG | P1 | 5 | 2025-06-04 | 2025-06-08 | 2025-11-15 | 2026-01-20 | M/s Akshar | Nos | 21 | 21 | 21 | 0 | Completed | 1 | [8 empty] | 1900-10-06: 3; 1900-10-10: 6; 1900-12-07: 3; 1900-12-08: 1; 1900-12-09: 4; 1900-12-10: 2; 1900-12-11: 2
SVG - Electrical P1 | Heat Exchanger - 2nos/1SVG | P1 | 8 | 2025-06-09 | 2025-06-16 | 2025-11-19 | 2026-01-19 | M/s Akshar | Nos | 14 | 14 | 14 | 0 | Completed | 1 | [8 empty] | 1900-10-10: 6; 1900-12-06: 6; 1900-12-11: 2
SVG - Electrical P1 | H-Pole | P1 | 6 | 2025-06-10 | 2025-06-15 | 2025-11-19 | 2026-01-22 | M/s Akshar | Nos | 7 | 7 | 7 | 0 | Completed | 1 | [8 empty] | 1900-10-10: 3; 1900-12-09: 1; 1900-12-11: 1; 1900-12-12: 1; 1900-12-13: 1
SVG - Electrical P1 | Disconnect Switch & Cable Clamp 1set/ 1SVG | P1 | 7 | 2025-06-08 | 2025-06-14 | 2025-11-13 | 2026-01-21 | M/s Akshar | Set | 7 | 7 | 7 | 0 | Completed | [9 empty] | 1900-10-04: 2; 1900-10-09: 1; 1900-12-09: 1; 1900-12-10: 1; 1900-12-11: 1; 1900-12-12: 1
SVG - Electrical P1 | Fence with door (9.3x5x1.8) | P1 | 7 | 2025-06-11 | 2025-06-17 | 2025-12-18 | 2026-02-17 | M/s Akshar | Nos | 7 | 7 | 7 | 0 | Completed | bar: 1900-11-08; 1900-11-10; 1900-11-15; 1900-12-27; 1901-01-01; 1901-01-05; 1901-01-08
SVG - Electrical P1 | Street Light | P1 | 7 | 2025-06-11 | 2025-06-17 | 2025-12-02 | 2026-01-25 | M/s Akshar | Nos | 8 | 8 | 8 | 0 | Completed | [9 empty] | 1900-10-18: 2; 1900-10-30: 1; 1900-12-11: 100%; 1900-12-12: 1; 1900-12-13: 1; 1900-12-15: 1; 1900-12-16: 1
SVG - Electrical P1 | ACDB Panels | P1 | 1 | 2025-06-15 | 2025-06-15 | 2025-12-03 | 2026-01-27 | M/s Akshar | Nos | 3 | 3 | 3 | 0 | Completed | [9 empty] | 1900-10-18: 2; 1900-12-18: 1
SVG - Electrical P1 | Communication Panel | P1 | 1 | 2025-06-15 | 2025-06-15 | 2025-12-03 | 2025-12-03 | M/s Akshar | Nos | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-24: 100%
SVG - Electrical P1 | Cabling & Testing Works | P1
SVG - Electrical P1 | Tray support foundations | P1 | 5 | 2025-06-01 | 2025-06-05 | 2025-11-20 | 2026-01-18 | M/s Akshar | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-11: 15%; 1900-10-12: 15%; 1900-11-30: 10%; 1900-12-01: 10%; 1900-12-02: 10%; 1900-12-03: 10%; 1900-12-07: 10%; 1900-12-08: 10%; 1900-12-09: 10%
SVG - Electrical P1 | Tray Installation | P1 | 4 | 2025-06-05 | 2025-06-08 | 2025-11-22 | 2026-01-23 | M/s Akshar | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-13: 30%; 1900-11-30: 10%; 1900-12-01: 10%; 1900-12-02: 10%; 1900-12-03: 10%; 1900-12-07: 10%; 1900-12-13: 10%; 1900-12-14: 10%
SVG - Electrical P1 | 33KV Cable laying (H-Pole to SGR-01) | P1 | 6 | 2025-06-08 | 2025-06-13 | 2025-11-22 | 2026-02-04 | M/s Akshar | Run | 28 | 28 | 28 | 0 | Completed | [9 empty] | 1900-10-13: 4; 1900-10-19: 8; 1900-12-17: 2; 1900-12-18: 2; 1900-12-20: 2; 1900-12-21: 2; 1900-12-25: 4; 1900-12-26: 4
SVG - Electrical P1 | 33KV Cable End Termination | P1 | 5 | 2025-06-13 | 2025-06-17 | 2025-12-16 | 2026-02-11 | M/s Akshar | Nos | 56 | 56 | 56 | 0 | Completed | [9 empty] | 1900-11-06: 16; 1900-11-07: 8; 1900-11-30: 8; 1900-12-01: 8; 1900-12-02: 8; 1900-12-31: 4; 1901-01-01: 4
SVG - Electrical P1 | 33KV Cable VLF testing | P1 | 3 | 2025-06-17 | 2025-06-19 | 2025-11-24 | 2026-02-15 | M/s Akshar | Run | 28 | 28 | 28 | 0 | Completed | [9 empty] | 1900-10-15: 4; 1900-10-16: 4; 1900-10-17: 4; 1901-01-04: 4; 1901-01-05: 8; 1901-01-06: 4
SVG - Electrical P1 | ACDB (1,2,3) to MSB Panel - Power Cable Laying & Termination | P1 | 10 | 2025-06-09 | 2025-06-18 | 2025-12-21 | 2026-02-04 | M/s Akshar | Run | 8 | 8 | 8 | 0 | Completed | [9 empty] | 1900-11-11: 4; 1900-12-26: 4
SVG - Electrical P1 | ACDB (1,2,3) to MSB Panel - Cable IR Test | P1 | 10 | 2025-06-10 | 2025-06-19 | 2025-12-21 | 2026-02-04 | M/s Akshar | Each | 8 | 8 | 8 | 0 | Completed | [9 empty] | 1900-11-11: 4; 1900-12-26: 4
SVG - Electrical P1 | SVG to 400kv BUS PT -VR - Control Cable Laying & Termination | P1 | 10 | 2025-06-10 | 2025-06-19 | 2025-12-17 | 2026-01-31 | M/s Akshar | Run | 7 | 7 | 6 | 1 | Completed | [9 empty] | 1900-11-07: 3; 1900-12-20: 1; 1900-12-21: 1; 1900-12-22: 1
SVG - Electrical P1 | SVG to SGR I/D feeder CB interlock control cable laying and termination | P1 | 10 | 2025-06-11 | 2025-06-20 | 2025-12-18 | 2026-01-31 | M/s Akshar | Run | 7 | 7 | 6 | 1 | Completed | [9 empty] | 1900-11-08: 3; 1900-12-20: 1; 1900-12-21: 1; 1900-12-22: 1
SVG - Electrical P1 | Distilled water filling | P1 | 3 | 2025-06-23 | 2025-06-25 | 2025-12-26 |  | M/s Akshar | Each | 7 | 7 | 3 | 4 | [10 empty] | 1900-11-16: 3
SVG - Electrical P1 | Module Testing | P1 | 4 | 2025-06-21 | 2025-06-24 | 2025-12-25 |  | M/s Akshar | Each | 7 | 7 | 3 | 4 | [10 empty] | 1900-11-15: 3
SVG - Electrical P1 | 75*12 Sqmm Earthing Strip | P1 | 10 | 2025-06-08 | 2025-06-17 | 2025-07-11 | 2025-08-01 | M/s Varsa Solar | Rm | 1680 | 1680 | 1680 | 0 | Completed | [9 empty] | 1900-06-17: 50; 1900-06-18: 40; 1900-06-19: 80; 1900-06-20: 60; 1900-06-21: 120; 1900-06-22: 120; 1900-06-23: 100; 1900-06-24: 80; 1900-06-25: 120; 1900-06-26: 80; 1900-06-27: 90; 1900-06-28: 100; 1900-06-29: 220; 1900-06-30: 220; 1900-07-01: 200
SVG - Electrical P1 | 50*6 Sqmm Earthing Strip | P1 | 10 | 2025-06-08 | 2025-06-17 | 2025-11-21 | 2026-01-20 | M/s Akshar | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-12: 10%; 1900-10-21: 10%; 1900-10-26: 20%; 1900-12-07: 10%; 1900-12-08: 5%; 1900-12-09: 5%; 1900-12-10: 5%; 1900-12-11: 10%; 1900-12-16: 0.05; 1900-12-17: 0.05; 1900-12-18: 0.05; 1900-12-19: 0.05; 1900-12-20: 0.05
SVG - Electrical P1 | Earth Pit - 6 no's /SVG | P1 | 8 | 2025-06-13 | 2025-06-20 | 2025-11-19 | 2026-01-27 | M/s Akshar | Nos | 42 | 42 | 42 | 0 | Completed | [9 empty] | 1900-10-10: 3; 1900-10-11: 3; 1900-10-19: 3; 1900-10-20: 3; 1900-10-24: 3; 1900-10-25: 3; 1900-12-13: 5; 1900-12-14: 9; 1900-12-16: 6; 1900-12-18: 4
SVG - Electrical P1 | Charging | P1 | 1 | 2025-06-25 | 2025-06-25 | 2025-12-29 |  | M/s Akshar | Nos | 7 | 7 | 2 | 5 | bar: 1900-11-19; 1900-11-23
SVG - Electrical P2 | SVG -P2 (8 to 15) | P2 | 25 | 2025-06-01 | 2025-06-25 |  |  |  | Set | 8 | 8 | 0 | 8 | bar: 1899-12-31 to 1900-07-22
SVG - Electrical P2 | Container (TSVG -50/33- W-C ) - 1no/1SVG | P2 | 7 | 2025-06-01 | 2025-06-07 |  |  |  | Nos | 8 | 8 | 0 | 8
SVG - Electrical P2 | Reactor - 3nos/1SVG | P2 | 7 | 2025-06-02 | 2025-06-08 |  |  |  | Nos | 24 | 24 | 0 | 24
SVG - Electrical P2 | Resistor - 3nos/1SVG | P2 | 7 | 2025-06-04 | 2025-06-10 |  |  |  | Nos | 24 | 24 | 0 | 24
SVG - Electrical P2 | VCB - 1no/1SVG | P2 | 5 | 2025-06-04 | 2025-06-08 |  |  |  | Nos | 8 | 8 | 0 | 8
SVG - Electrical P2 | Arrestor - 3nos/1SVG | P2 | 5 | 2025-06-04 | 2025-06-08 |  |  |  | Nos | 24 | 24 | 0 | 24
SVG - Electrical P2 | Heat Exchanger - 2nos/1SVG | P2 | 8 | 2025-06-09 | 2025-06-16 |  |  |  | Nos | 16 | 16 | 0 | 16
SVG - Electrical P2 | H-Pole | P2 | 6 | 2025-06-10 | 2025-06-15 |  |  |  | Nos | 8 | 8 | 0 | 8
SVG - Electrical P2 | Disconnect Switch & Cable Clamp 1set/ 1SVG | P2 | 7 | 2025-06-08 | 2025-06-14 |  |  |  | Set | 8 | 8 | 0 | 8
SVG - Electrical P2 | Fence with door (9.3x5x1.8) | P2 | 7 | 2025-06-11 | 2025-06-17 |  |  |  | Nos | 8 | 8 | 0 | 8
SVG - Electrical P2 | Street Light | P2 | 7 | 2025-06-11 | 2025-06-17 |  |  |  | Nos | 9 | 9 | 0 | 9
SVG - Electrical P2 | ACDB Panels | P2 | 1 | 2025-06-15 | 2025-06-15 |  |  |  | Nos | 3 | 3 | 0 | 3
SVG - Electrical P2 | Communication Panel | P2 | 1 | 2025-06-15 | 2025-06-15 |  |  |  | Nos | 1 | 1 | 0 | 1
SVG - Electrical P2 | Cabling & Testing Works | P2
SVG - Electrical P2 | Tray support foundations | P2 | 5 | 2025-06-01 | 2025-06-05 |  |  |  | Lot | 1 | 1 | 0 | 1
SVG - Electrical P2 | Tray Installation | P2 | 4 | 2025-06-05 | 2025-06-08 |  |  |  | Lot | 1 | 1 | 0 | 1
SVG - Electrical P2 | 33KV Cable laying (H-Pole to SGR-02) | P2 | 6 | 2025-06-08 | 2025-06-13 |  |  |  | Runs | 32 | 32 | 0 | 32
SVG - Electrical P2 | 33KV Cable End Termination | P2 | 5 | 2025-06-13 | 2025-06-17 |  |  |  | Nos | 64 | 64 | 0 | 64
SVG - Electrical P2 | 33KV Cable VLF testing | P2 | 3 | 2025-06-17 | 2025-06-19 |  |  |  | Runs | 32 | 32 | 0 | 32
SVG - Electrical P2 | ACDB (4,5,6) to MSB Panel - Power Cable Laying & Termination | P2 | 10 | 2025-06-09 | 2025-06-18 |  |  |  | Each | 7 | 7 | 0 | 7
SVG - Electrical P2 | ACDB (4,5,6) to MSB Panel - Cable IR Test | P2 | 10 | 2025-06-10 | 2025-06-19 |  |  |  | Run | 7 | 7 | 0 | 7
SVG - Electrical P2 | SVG to 400kv BUS PT -VR - Control Cable Laying & Termination | P2 | 10 | 2025-06-10 | 2025-06-19 |  |  |  | Run | 8 | 8 | 0 | 8
SVG - Electrical P2 | SVG to SGR I/D feeder CB interlock control cable laying and termination | P2 | 10 | 2025-06-11 | 2025-06-20 |  |  |  | Run | 8 | 8 | 0 | 8
SVG - Electrical P2 | Distilled water filling | P2 | 3 | 2025-06-23 | 2025-06-25 |  |  |  | Each | 8 | 8 | 0 | 8
SVG - Electrical P2 | Module Testing | P2 | 4 | 2025-06-21 | 2025-06-24 |  |  |  | Each | 8 | 8 | 0 | 8
SVG - Electrical P2 | 75*12 Sqmm Earthing Strip | P2 | 10 | 2025-06-08 | 2025-06-17 |  |  |  | Rm | 1440 | 1440 | 0 | 1440
SVG - Electrical P2 | 50*6 Sqmm Earthing Strip | P2 | 10 | 2025-06-08 | 2025-06-17 |  |  |  | Rm |  | 0 | 0 | 0
SVG - Electrical P2 | Earth Pit - 6 no's /SVG | P2 | 8 | 2025-06-13 | 2025-06-20 |  |  |  | Nos | 48 | 48 | 0 | 48
SVG - Electrical P2 | Charging | P2 | 1 | 2025-06-25 | 2025-06-25 |  |  |  | Nos | 7 | 7 | 0 | 7
Harmonic Filter - Elec | Harmonic Filter -P1 | P1 | 25 | 2025-05-23 | 2025-06-16 | 2025-06-23 |  |  | Set | 4 | 4 | 4.0004 | -0.00035398 | bar: 1899-12-31 to 1900-07-22
Harmonic Filter - Elec | Support Structure Erection | P1 | 8 | 2025-05-23 | 2025-05-30 | 2025-06-23 | 2026-01-11 | M/s Hitachi | Set | 4 | 4 | 4.01 | -0.01 | Completed | [9 empty] | 1900-05-14: 0.1; 1900-05-15: 0.2; 1900-05-16: 0.4; 1900-05-17: 0.3; 1900-06-29: 0.3; 1900-06-30: 0.3; 1900-07-01: 0.4; 1900-07-20: 0.01; 1900-07-21: 0.3; 1900-07-22: 0.3; 1900-07-23: 0.4; 1900-11-28: 0.3; 1900-11-30: 0.3; 1900-12-01: 0.2; 1900-12-02: 0.2
Harmonic Filter - Elec | Capacitor Bank Erection | P1 | 15 | 2025-05-24 | 2025-06-07 | 2025-08-06 | 2026-01-16 | M/s Hitachi | Nos | 36 | 36 | 36 | 0 | Completed | [9 empty] | 1900-06-27: 3; 1900-07-02: 3; 1900-07-03: 3; 1900-07-04: 3; 1900-07-05: 3; 1900-07-08: 3; 1900-11-22: 3; 1900-11-23: 3; 1900-11-24: 3; 1900-12-05: 6; 1900-12-06: 3
Harmonic Filter - Elec | Reactor Erection | P1 | 15 | 2025-05-24 | 2025-06-07 | 2025-08-05 | 2026-01-15 | M/s Hitachi | Nos | 36 | 36 | 36 | 0 | Completed | [9 empty] | 1900-06-26: 1; 1900-06-27: 2; 1900-07-03: 3; 1900-07-04: 3; 1900-07-05: 3; 1900-07-15: 3; 1900-07-16: 3; 1900-07-25: 3; 1900-07-26: 3; 1900-07-27: 3; 1900-12-04: 6; 1900-12-05: 3
Harmonic Filter - Elec | Isolator With Cable Support & Surge Arrester With Monitor | P1 | 15 | 2025-05-24 | 2025-06-07 | 2025-08-05 | 2026-01-16 | M/s Hitachi | Nos | 36 | 36 | 36 | 0 | Completed | [9 empty] | 1900-07-02: 2; 1900-07-04: 2; 1900-07-05: 2; 1900-07-11: 2; 1900-07-12: 2; 1900-07-13: 2; 1900-07-16: 3; 1900-07-17: 3; 1900-10-11: 9; 1900-12-05: 7; 1900-12-06: 2
Harmonic Filter - Elec | Cable Laying & Termination | P1 | 15 | 2025-05-29 | 2025-06-12 | 2025-12-12 | 2025-12-12 | M/s Hitachi | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-02: 100%
Harmonic Filter - Elec | Earthing | P1 | 20 | 2025-05-24 | 2025-06-12 | 2025-07-04 | 2026-01-18 | M/s Hitachi | Rm | 2400 | 2400 | 2400 | 0 | Completed | [9 empty] | 1900-05-25: 100; 1900-05-27: 50; 1900-05-28: 50; 1900-06-20: 60; 1900-06-22: 60; 1900-07-01: 60; 1900-07-02: 80; 1900-07-07: 100; 1900-07-08: 100; 1900-07-10: 60; 1900-07-11: 100; 1900-11-09: 200; 1900-11-30: 120; 1900-12-01: 120; 1900-12-02: 100; 1900-12-03: 120; 1900-12-04: 100; 1900-12-05: 100; 1900-12-06: 120; 1900-12-07: 100; 1900-12-08: 200; 1900-12-09: 300
Harmonic Filter - Elec | Testing | P1 | 3 | 2025-06-13 | 2025-06-15 | 2025-12-21 | 2026-01-29 | M/s Hitachi | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-11: 30%; 1900-11-13: 20%; 1900-12-10: 5%; 1900-12-12: 5%; 1900-12-13: 5%; 1900-12-14: 5%; 1900-12-15: 5%; 1900-12-16: 5%; 1900-12-17: 5%; 1900-12-18: 5%; 1900-12-19: 5%; 1900-12-20: 5%
Harmonic Filter - Elec | Pre-commissioning & Charging | P1 | 1 | 2025-06-16 | 2025-06-16 | 2025-12-29 |  | M/s Hitachi | Nos | 4 | 4 | 3 | 1 | [10 empty] | 1900-11-19: 1; 1900-11-24: 2
Harmonic Filter - Elec | Harmonic Filter -P2 | P2 | 25 | 2025-05-22 | 2025-06-15 |  |  |  | Set | 4 | 4 | 0 | 4 | bar: 1899-12-31 to 1900-07-22
Harmonic Filter - Elec | Support Structure Erection | P2 | 8 | 2025-05-22 | 2025-05-29 |  |  |  | Set | 4 | 4 | 0 | 4
Harmonic Filter - Elec | Capacitor Bank Erection | P2 | 15 | 2025-05-23 | 2025-06-06 |  |  |  | Nos | 36 | 36 | 0 | 36
Harmonic Filter - Elec | Reactor Erection | P2 | 15 | 2025-05-23 | 2025-06-06 |  |  |  | Nos | 36 | 36 | 0 | 36
Harmonic Filter - Elec | Isolator With Cable Support & Surge Arrester With Monitor | P2 | 15 | 2025-05-23 | 2025-06-06 |  |  |  | Nos | 36 | 36 | 0 | 36
Harmonic Filter - Elec | Cable Laying & Termination | P2 | 15 | 2025-05-28 | 2025-06-11 |  |  |  | Lot | 1 | 1 | 0 | 1
Harmonic Filter - Elec | Earthing | P2 | 20 | 2025-05-23 | 2025-06-11 |  |  |  | Rm | 2400 | 2400 | 0 | 2400
Harmonic Filter - Elec | Testing | P2 | 3 | 2025-06-12 | 2025-06-14 |  |  |  | Lot | 1 | 1 | 0 | 1
Harmonic Filter - Elec | Pre-commissioning & Charging | P2 | 1 | 2025-06-15 | 2025-06-15 |  |  |  | lot | 1 | 1 | 0 | 1
PMU - Erection | PMU - Erection |  | 12 | 2025-05-30 | 2025-06-10 | bar: 1899-12-31 to 1900-07-22
PMU - Erection | PMU Installation | P1 & P2 | 3 | 2025-05-30 | 2025-06-01 | 2025-11-03 |  | M/s Hyosung | Nos | 3 | 3 | 2 | 1 | [10 empty] | 1900-09-24: 2
PMU - Erection | Cabling & Termination Works | P1 & P2 | 5 | 2025-06-02 | 2025-06-06 | 2025-11-04 |  | M/s Hyosung | Nos | 3 | 3 | 2 | 1 | [10 empty] | 1900-09-27: 0.5; 1900-09-29: 0.5; 1900-10-25: 1
PMU - Erection | Testing | P1 & P2 | 4 | 2025-06-07 | 2025-06-10 | 2025-12-15 |  | M/s Hyosung | Nos | 3 | 3 | 2 | 1 | bar: 1900-11-05
Gantry Erection | Gantry |  | 29 | 2025-05-15 | 2025-06-12 | bar: 1899-12-31 to 1900-07-22
Gantry Erection | Tower Erection | P1 | 15 | 2025-05-15 | 2025-05-29 | 2025-09-02 | 2025-11-16 | M/s Hyosung | Nos | 2 | 2 | 2 | 0 | completed | [9 empty] | 1900-10-05: 1; 1900-10-06: 0.5; 1900-10-07: 0.5
Gantry Erection | Beam Erection | P1 | 4 | 2025-05-30 | 2025-06-02 | 2025-11-16 | 2025-11-16 | M/s Hyosung | Nos | 1 | 1 | 1 | 0 | completed | bar: 1900-10-07
Gantry Erection | Stringing | P1 | 10 | 2025-06-03 | 2025-06-12 | 2025-11-16 | 2025-11-20 | M/s Hyosung | Lot | 1 | 1 | 0 | 1 | completed
Cable Tray Installation | Cable Tray Installation |  | 74 | 2025-04-23 | 2025-07-05 | 2025-07-02 | bar: 1899-12-31 to 1900-07-22
Cable Tray Installation | Below GIS & MCR Slab | P1 | 5 | 2025-05-20 | 2025-05-24 | 2025-07-02 | 2025-08-01 | M/s Hyosung | Lot | 1 | 1 | 0.95 | 0.05 | Completed | [9 empty] | 1900-05-24: 0.1; 1900-05-25: 0.2; 1900-05-28: 0.2; 1900-05-29: 0.1; 1900-05-31: 0.05; 1900-06-01: 0.1; 1900-06-05: 0.05; 1900-06-09: 0.05; 1900-06-22: 0.1
Cable Tray Installation | Below SGR-1 Slab | P1 | 14 | 2025-05-27 | 2025-06-09 | 2025-08-08 | 2025-08-14 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-06-29: 5%; 1900-06-30: 15%; 1900-07-01: 15%; 1900-07-02: 10%; 1900-07-03: 20%; 1900-07-04: 15%; 1900-07-05: 20%
Cable Tray Installation | Below SGR-2 Slab | P2 | 14 | 2025-06-22 | 2025-07-05 |  |  | M/s Hyosung | Lot | 1 | 1 | 0 | 1
Cable Tray Installation | From SGR-1a to Trafo 1 | P1 | 3 | 2025-04-23 | 2025-04-25 | 2025-12-04 | 2025-12-11 | M/s Hyosung | Lot | 1 | 1 | 0 | 1 | Completed
Cable Tray Installation | From SGR-1b to Trafo 2 | P1 | 3 | 2025-04-24 | 2025-04-26 | 2025-11-25 | 2025-11-25 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-16: 100%
Cable Tray Installation | From SGR-2a to Trafo 3 | P2 | 3 | 2025-05-06 | 2025-05-08 |  |  | M/s Hyosung | Lot | 1 | 1 | 0 | 1 | Completed
Cable Tray Installation | From SGR-2b To trafo 4 | P2 | 3 | 2025-05-08 | 2025-05-10 |  |  | M/s Hyosung | Lot | 1 | 1 | 0 | 1
Cable Tray Installation | GIS Hall to Trafo-1 & 2 | P1 | 7 | 2025-04-28 | 2025-05-04 | 2025-12-05 | 2025-12-10 | M/s Hyosung | Lot | 1 | 1 | 0 | 1 | Completed
Cable Tray Installation | GIS Hall to Trafo-3 & 4 | P2 | 7 | 2025-05-14 | 2025-05-20 | 2026-02-02 | 2026-02-10 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-12-24: 20%; 1900-12-25: 20%; 1900-12-26: 20%; 1900-12-27: 20%; 1901-01-01: 0.2
Cable Tray Installation | GIS Hall to SGR-1 | P1 | 4 | 2025-04-28 | 2025-05-01 | 2025-12-11 | 2025-12-15 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-01: 20%; 1900-11-03: 50%; 1900-11-05: 30%
Cable Tray Installation | GIS Hall to SGR-2 | P2 | 4 | 2025-05-18 | 2025-05-21 |  |  | M/s Hyosung | Lot | 1 | 1 | 0 | 1
Cable Tray Installation | GIS Hall to line side equipment's | P1 | 4 | 2025-04-28 | 2025-05-01 | 2025-12-05 | 2025-12-06 | M/s Hyosung | Lot | 1 | 1 | 0 | 1 | completed
Cabling Works & Termi. | Cabling Works & Terminations |  | 60 | 2025-05-17 | 2025-07-15 | 2025-07-14 | bar: 1900-04-25 to 1900-07-22
Cabling Works & Termi. | LCC to Equipment (Control Cable) | P1 | 21 | 2025-05-26 | 2025-06-15 | 2025-08-10 | 2025-09-04 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | completed | [9 empty] | 1900-07-01: 0.1; 1900-07-02: 0.05; 1900-07-03: 0.1; 1900-07-04: 0.1; 1900-07-05: 0.1; 1900-07-06: 0.15; 1900-07-07: 0.05; 1900-07-08: 0.05; 1900-07-11: 0.03; 1900-07-12: 0.03; 1900-07-14: 0.05; 1900-07-15: 0.05; 1900-07-25: 0.1; 1900-07-26: 0.04
Cabling Works & Termi. | LCC to CRP (Control Cable) | P1 | 21 | 2025-05-26 | 2025-06-15 | 2025-07-14 | 2025-09-04 | M/s Hyosung | Lot | 1 | 1 | 0.95 | 0.05 | Completed | [9 empty] | 1900-06-06: 0.2; 1900-06-07: 0.1; 1900-06-09: 0.1; 1900-06-11: 0.1; 1900-06-12: 0.3; 1900-06-13: 0.05; 1900-06-17: 0.1
Cabling Works & Termi. | CRP To PT-1 MB Box(Control Cables) | P1 | 8 | 2025-05-29 | 2025-06-05 | 2025-12-09 | 2025-12-11 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-30: 20%; 1900-10-31: 50%; 1900-11-01: 30%
Cabling Works & Termi. | CRP to PT-2 MB Box(Control Cables) | P1 | 8 | 2025-06-04 | 2025-06-11 | 2025-12-09 | 2025-12-11 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-10-30: 20%; 1900-10-31: 50%; 1900-11-01: 30%
Cabling Works & Termi. | CRP to PT-3 MB Box(Control Cables) | P2 | 8 | 2025-07-07 | 2025-07-14 | 2026-02-21 | 2026-02-21 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1901-01-12: 100%
Cabling Works & Termi. | CRP to PT-4 MB Box(Control Cables) | P2 | 8 | 2025-07-08 | 2025-07-15 |  |  | M/s Hyosung | Lot | 1 | 1 | 0 | 1
Cabling Works & Termi. | ACDB To CRP, LCC, PT MB Box, NIFPS, etc. (Power Cable) |  | 8 | 2025-06-03 | 2025-06-10 | 2025-08-01 |  | M/s Hyosung | Lot | 1 | 1 | 0.5 | 0.5 | [10 empty] | 1900-06-22: 0.01; 1900-06-23: 0.01; 1900-06-24: 0.02; 1900-06-25: 0.02; 1900-06-26: 0.01; 1900-06-27: 0.01; 1900-06-28: 0.05; 1900-06-29: 0.1; 1900-06-30: 0.05; 1900-07-01: 0.15; 1900-07-02: 0.05; 1900-07-03: 0.1; 1900-07-04: 0.05; 1900-07-05: 0.05; 1900-07-06: 0.05; 1900-07-07: 0.17; 1900-07-08: 0.1
Cabling Works & Termi. | DCDB to CRP, LCC, PT MB Box, RTCC etc. (Power Cables) |  | 8 | 2025-05-30 | 2025-06-06 | 2025-08-01 |  | M/s Hyosung | Lot | 1 | 1 | 0.5 | 0.5 | [10 empty] | 1900-06-22: 0.01; 1900-06-23: 0.01; 1900-06-24: 0.02; 1900-06-25: 0.02; 1900-06-26: 0.01; 1900-06-27: 0.01; 1900-06-28: 0.12; 1900-06-29: 0.1; 1900-06-30: 0.05; 1900-07-01: 0.15; 1900-07-02: 0.05; 1900-07-03: 0.1; 1900-07-04: 0.05; 1900-07-05: 0.05; 1900-07-06: 0.05; 1900-07-07: 0.1; 1900-07-08: 0.1
Cabling Works & Termi. | SCADA, CRP & FOTE Cabling | P1 | 30 | 2025-05-17 | 2025-06-15 | 2025-08-12 |  | M/s Hyosung | Lot | 1 | 1 | 0.5 | 0.5 | [10 empty] | 1900-07-03: 0.05; 1900-07-04: 0.1; 1900-07-05: 0.05; 1900-07-06: 0.1; 1900-07-07: 0.05; 1900-07-08: 0.05; 1900-07-09: 0.1
Cabling Works & Termi. | SGR-1 to Aux Trafo-1 | P1 | 3 | 2025-06-05 | 2025-06-07 | 2025-12-18 | 2025-12-18 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | [9 empty] | 1900-11-08: 100%
Cabling Works & Termi. | SGR-2 to Aux Trafo-2 | P2 | 3 | 2025-07-15 | 2025-07-17 |  |  | M/s Hyosung | Lot | 1 | 1 | 0 | 1
Cabling Works & Termi. | Cabling Works & Terminations - HV Cabling Works - SGR 01a | P1 |  |  |  | 2025-12-11 | 2025-12-12 | M/s Hyosung | run | 60 | 60 | 60 | 0 | Completed | [9 empty] | 1900-11-01: 3000%; 1900-11-02: 3000%
Cabling Works & Termi. | 33KV cable end termination |  |  |  |  | 2025-12-17 | 2025-12-17 | M/s Hyosung | run | 60 | 60 | 60 | 0 | Completed | [9 empty] | 1900-11-07: 60
Cabling Works & Termi. | Cabling Works & Terminations - HV Cabling Works - SGR 01b | P1 |  |  |  | 2025-11-26 | 2025-12-28 | M/s Hyosung | run | 60 | 60 | 60 | 0 | Completed | [9 empty] | 1900-10-17: 3000%; 1900-10-19: 30
Cabling Works & Termi. | 33KV cable end termination |  |  |  |  | 2025-12-17 | 2025-12-17 | M/s Hyosung | run | 60 | 60 | 60 | 0 | Completed | [9 empty] | 1900-11-07: 60
Cabling Works & Termi. | Cabling Works & Terminations - HV Cabling Works - SGR 02a | P2 | [5 empty] | M/s Hyosung
Cabling Works & Termi. | 33KV cable end termination | [6 empty] | M/s Hyosung
Cabling Works & Termi. | Cabling Works & Terminations - HV Cabling Works - SGR 02b | P2 | [5 empty] | M/s Hyosung
Cabling Works & Termi. | 33KV cable end termination | [6 empty] | M/s Hyosung
WMS Installation | WMS Installation | P1 | 5 | 2025-06-16
WMS Installation | WMS Structure Installation | P1 | 5 | 2025-04-13 | 2025-04-17 | 2025-12-23 | 2025-12-23 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-11-13
WMS Installation | WMS Equipment Installation & Cabling | P1 | 5 | 2025-04-18 | 2025-04-22 | 2025-12-23 | 2025-12-23 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-11-13
WMS Installation | Commissioning | P1 | 5 | 2025-06-16 | 2025-06-20 | 2025-12-23 | 2025-12-23 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | Completed | bar: 1900-11-13
P1 - CEA Inspection & Approval | P1 - CEA Inspection & Approval | P1 | 1 | 2025-06-26 |  | 2025-08-30
P1 - CEA Inspection & Approval | CEA Application ( 4 Set SGR, 2 PTR, GIS, P1 HF & P1 SVG) | P1 | 1 | 2025-06-11 | 2025-06-11 | 2025-08-30 |  | AGEL | Nos | 18 | 18 | 9 | 9 | Documents provided on 30-Aug-25 for SGR, PTR, 2HF) | [9 empty] | 1900-07-22: 9
P1 - CEA Inspection & Approval | CEA Inspection | P1 | 1 | 2025-06-25 | 2025-06-25 | 2025-10-09 |  | AGEL | Nos | 18 | 18 | 9 | 9
P1 - CEA Inspection & Approval | CEA Compliance & Approval | P1 | 7 | 2025-06-26 | 2025-07-02 | 2025-12-24 |  | AGEL | Nos | 18 | 18 | 9 | 9 | [10 empty] | 1900-11-14: 9
P1 - Pre Commissioning & Testing | P1 - Pre Commissioning & Testing | P1 | 1 | 2025-07-10
P1 - Pre Commissioning & Testing | 400kv Relay Testing | P1 | 7 | 2025-06-13 | 2025-06-19 | 2025-10-28 | 2025-11-13 | M/s Hyosung | Nos | 31 | 31 | 31 | 0 | completed | 1 | [8 empty] | 1900-09-18: 6; 1900-09-19: 5; 1900-09-20: 3; 1900-09-21: 6; 1900-09-22: 3; 1900-09-25: 2; 1900-09-26: 1; 1900-09-28: 1; 1900-10-03: 2; 1900-10-04: 2
P1 - Pre Commissioning & Testing | HV Test & PD (Partial Discharge) | P1 | 7 | 2025-07-01 | 2025-07-07 | 2025-11-25 | 2025-11-27 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | completed | 1 | [8 empty] | 1900-10-16: 0.2; 1900-10-17: 0.4; 1900-10-18: 0.4
P1 - Pre Commissioning & Testing | BB Stability Testing | P1 | 15 | 2025-06-11 | 2025-06-25 | 2025-12-11 | 2025-12-12 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | completed | 1 | [8 empty] | 1900-10-22: 0.25; 1900-11-13: 0.75
P1 - Pre Commissioning & Testing | Trafo Stability Test | P1 | 10 | 2025-06-25 | 2025-07-04 | 2025-12-21 | 2025-12-22 | M/s Hyosung | Nos | 2 | 2 | 2 | 0 | completed | 1 | bar: 1900-11-11 to 1900-11-12
P1 - Pre Commissioning & Testing | Preparation & Submission of pre commissioning Checklist | P1 | 1 | 2025-07-07 | 2025-07-07 | 2025-12-22 | 2025-12-22 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | completed | 1 | bar: 1900-11-12
P1 - Pre Commissioning & Testing | CFT- GIS, SGR & PTR | P1 | 3 | 2025-07-07 | 2025-07-09 | 2025-12-22 | 2025-12-23 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | completed | 1 | [8 empty] | 1900-11-12: 0.5; 1900-11-13: 0.5
P1 - Pre Commissioning & Testing | Form IV | P1 | 1 | 2025-07-09 | 2025-07-09 | 2025-12-24 | 2025-12-24 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | completed | 1 | bar: 1900-11-14
P1 - Pre Commissioning & Testing | CFT- SVG | P1 | 3 | 2025-07-07 | 2025-07-09 | 2025-12-22 |  | M/s Hyosung | Lot | 1 | 1 | 0.3 | 0.7 |  | 0.3 | [8 empty] | 1900-11-13: 0.3
P1 - Pre Commissioning & Testing | Form IV | P1 | 1 | 2025-07-09 | 2025-07-09 | 2025-12-28 |  | M/s Hyosung | Lot | 1 | 1 | 0 | 1 |  | 0
P1 - Pre Commissioning & Testing | CFT- Harmonic Fiter | P1 | 3 | 2025-07-07 | 2025-07-09 | 2025-12-22 |  | M/s Hyosung | Lot | 1 | 1 | 0.5 | 0.5 |  | 0.5 | [8 empty] | 1900-11-13: 0.5
P1 - Pre Commissioning & Testing | Form IV | P1 | 1 | 2025-07-09 | 2025-07-09 | 2025-12-28 |  | M/s Hyosung | Lot | 1 | 1 | 0.5 | 0.5 |  | 0.5 | [8 empty] | 1900-11-18: 0.5
P1 - Pre Commissioning & Testing | Final Checks & Ready for Charge | P1 | 1 | 2025-07-10 | 2025-07-10
P1 - Pre Commissioning & Testing | Final Checks & Ready for Charge -GIS | P1 | 1 | 2025-07-10 | 2025-07-10 | 2025-12-22 | 2025-12-22 | M/s Hyosung | Lot | 1 | 1 | 1 | 0 | completed | 1 | bar: 1900-11-13
P1 - Pre Commissioning & Testing | Final Checks & Ready for Charge -PTR | P1 | 1 | 2025-07-10 | 2025-07-10 | 2025-12-23 | 2025-12-23 | M/s Hyosung | Nos | 2 | 2 | 2 | 0 | completed | [9 empty] | 1900-11-13: 2
P1 - Pre Commissioning & Testing | Final Checks & Ready for Charge -SGR | P1 | 1 | 2025-07-10 | 2025-07-10 | 2025-12-27 | 2025-12-27 | M/s Hyosung | Set | 4 | 4 | 4 | 0 | completed | [9 empty] | 1900-11-17: 4
P1 - Pre Commissioning & Testing | Final Checks & Ready for Charge -SVG | P1 | 1 | 2025-07-10 | 2025-07-10 | 2025-12-27 |  |  | Nos | 7 | 7 | 3 | 4 | [10 empty] | 1900-11-17: 3
P1 - Pre Commissioning & Testing | Final Checks & Ready for Charge -HF | P1 | 1 | 2025-07-10 | 2025-07-10 | 2025-12-27 |  |  | Nos | 4 | 4 | 2 | 2 | [10 empty] | 1900-11-17: 2
P2 - CEA Inspection & Approval | P2 - CEA Inspection & Approval | P2 | 1 | 2025-07-20
P2 - CEA Inspection & Approval | CEA Application ( 4 Set SGR, 2 PTR, GIS, P2 HF & P2 SVG) | P2 | 1 | 2025-06-30 | 2025-06-30 |  |  |  | Nos | 19 | 19 | 0 | 19
P2 - CEA Inspection & Approval | CEA Inspection | P2 | 1 | 2024-07-14 | 2024-07-14 |  |  |  | Nos | 19 | 19 | 0 | 19
P2 - CEA Inspection & Approval | CEA Compliance & Approval | P2 | 6 | 2025-07-20 | 2025-07-25 |  |  |  | Nos | 19 | 19 | 0 | 19
P2 - Pre Commissioning & Testing | P2 - Pre Commissioning & Testing | P2 | 1 | 2025-07-30
P2 - Pre Commissioning & Testing | Trafo Stability Test | P2 | 4 | 2025-07-26 | 2025-07-29 |  |  |  | Nos | 2 | 2 | 0 | 2
P2 - Pre Commissioning & Testing | Preparation & Submission of pre commissioning Checklist | P2 | 1 | 2025-07-29 | 2025-07-29 |  |  |  | Lot | 1 | 1 | 0 | 1
P2 - Pre Commissioning & Testing | CFT- PTR, SGR (Inspection & Observation Closure as per SOP) | P2 | 2 | 2025-07-28 | 2025-07-29 |  |  |  | Lot | 1 | 1 | 0 | 1
P2 - Pre Commissioning & Testing | Form IV | P2 | 1 | 2025-07-29 | 2025-07-29 |  |  |  | Lot | 1 | 1 | 0 | 1
P2 - Pre Commissioning & Testing | CFT- SVG | P2 | 2 | 2025-07-28 | 2025-07-29 |  |  |  | Lot | 1 | 1 | 0 | 1
P2 - Pre Commissioning & Testing | Form IV | P2 | 1 | 2025-07-29 | 2025-07-29 |  |  |  | Lot | 1 | 1 | 0 | 1
P2 - Pre Commissioning & Testing | CFT- Harmonic Fiter | P2 | 2 | 2025-07-28 | 2025-07-29 |  |  |  | Lot | 1 | 1 | 0 | 1
P2 - Pre Commissioning & Testing | Form IV | P2 | 1 | 2025-07-29 | 2025-07-29 |  |  |  | Lot | 1 | 1 | 0 | 1
P2 - Pre Commissioning & Testing | Final Checks & Ready for Charge -PTR | P2 | 1 | 2025-07-30 | 2025-07-30 |  |  |  | Nos | 2 | 2 | 0 | 2
P2 - Pre Commissioning & Testing | Final Checks & Ready for Charge -SGR | P2 | 1 | 2025-07-30 | 2025-07-30 |  |  |  | Set | 4 | 4 | 0 | 4
P2 - Pre Commissioning & Testing | Final Checks & Ready for Charge -SVG | P2 | 1 | 2025-07-30 | 2025-07-30 |  |  |  | Nos | 8 | 8 | 0 | 8
P2 - Pre Commissioning & Testing | Final Checks & Ready for Charge -HF | P2 | 1 | 2025-07-30 | 2025-07-30 |  |  |  | Nos | 4 | 4 | 0 | 4

## PSS-6 Manpower & Machinery
Summary DPR'!A1
| Sr.No | Descriptions | Areas | Department | 2026-02-27 | 2025-02-15 | 2025-02-16 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-27 | 2025-12-28 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04
| A | PSS-06 Manpower |  |  | 154 | 5 | 8 | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 44 | 40 | 35 | 40 | 29 | 29 | 25 | 30 | 35 | 25 | 25 | 30 | 75 | 50 | 15 | 26 | 71 | 65 | 54 | 55 | 82 | 95 | 87 | 85 | 70 | 97 | 110 | 55 | 129 | 129 | 129 | 143 | 145 | 173 | 179 | 180 | 180 | 180 | 183 | 179 | 176 | 151 | 211 | 211 | 191 | 219 | 198 | 201 | 202 | 195 | 213 | 221 | 206 | 209 | 208 | 202 | 202 | 201 | 200 | 144 | 186 | 181 | 122 | 142 | 79 | 182 | 182 | 156 | 154 | 171 | 140 | 36 | 0 | 66 | 59 | 64 | 62 | 64 | 53 | 51 | 60 | 54 | 86 | 109 | 77 | 145 | 125 | 131 | 98 | 125 | 190 | 196 | 194 | 185 | 204 | 207 | 218 | 209 | 231 | 227 | 220 | 227 | 245 | 250 | 245 | 279 | 279 | 292 | 301 | 112 | 249 | 210 | 268 | 268 | 256 | 297 | 268 | 234 | 226 | 107 | 104 | 130 | 165 | 137 | 151 | 142 | 168 | 173 | 167 | 146 | 162 | 132 | 166 | 182 | 237 | 121 | 153 | 144 | 88 | 97 | 122 | 107 | 125 | 120 | 152 | 125 | 135 | 157 | 162 | 148 | 146 | 122 | 165 | 167 | 160 | 165 | 171 | 160 | 157 | 162 | 165 | 170 | 167 | 157 | 160 | 174 | 168 | 151 | 67 | 189 | 169 | 168 | 167 | 171 | 170 | 139 | 226 | 214 | 225 | 222 | 218 | 195 | 195 | 167 | 172 | 171 | 214 | 206 | 220 | 217 | 215 | 148 | 34 | 28 | 28 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 35 | 30 | 30 | 30 | 35 | 40 | 40 | 40 | 40 | 40 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 25 | 15 | 15 | 29 | 29 | 29 | 29 | 24 | 0 | 27 | 29 | 29 | 18 | 21 | 17 | 21 | 33 | 33 | 53 | 53 | 56 | 54 | 61 | 58 | 78 | 90 | 101 | 120 | 111 | 125 | 135 | 167 | 172 | 162 | 162 | 159 | 186 | 143 | 156 | 172 | 184 | 180 | 155 | 145 | 155 | 178 | 161 | 150 | 151 | 149 | 151 | 158 | 178 | 173 | 162 | 164 | 164 | 121 | 173 | 215 | 215 | 202 | 198 | 181 | 196 | 191 | 196 | 196 | 211 | 176 | 163 | 192 | 200 | 200 | 195 | 171 | 141 | 114 | 146 | 172 | 151 | 10 | 108 | 104 | 93 | 131 | 154 | 164 | 145 | 173 | 169 | 154 | 153 | 168 | 171 | 164 | 174 | 169 | 139 | 169 | 149 | 136 | 131 | 142 | 150 | 142 | 0 | 126 | 120 | 156 | 168 | 165 | 148 | 88 | 90 | 112 | 78 | 75 | 80 | 69 | 70 | 83 | 76 | 82 | 82 | 85 | 80 | 94 | 92 | 96 | 89 | 86 | 83 | 78 | 78 | 99 | 84 | 84 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | M/s DNC | PSS | Civil | 115 | 5 | 8 | 8 | 7 | [7 empty] | 45 | 45 | 44 | 40 | 35 | 40 | 29 | 29 | 25 | 30 | 35 | 25 | 25 | 30 | 60 | 35 | 0 | 11 | 56 | 50 | 39 | 40 | 67 | 80 | 72 | 70 | 55 | 82 | 95 | 40 | 114 | 114 | 114 | 128 | 130 | 145 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 130 | 160 | 160 | 130 | 170 | 150 | 150 | 150 | 150 | 150 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 100 | 140 | 140 | 90 | 110 | 40 | 150 | 150 | 120 | 120 | 120 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4 | 4 | 4 | 10 | 27 | 37 | 64 | 64 | 64 | 40 | 64 | 130 | 130 | 130 | 130 | 130 | 130 | 160 | 160 | 160 | 180 | 180 | 180 | 190 | 190 | 190 | 200 | 200 | 210 | 210 | 30 | 170 | 130 | 185 | 185 | 170 | 200 | 170 | 130 | 120 | 0 | 20 | 40 | 70 | 50 | 50 | 50 | 75 | 80 | 70 | 40 | 80 | 55 | 65 | 60 | 111 | 40 | 55 | 55 | 0 | 25 | 50 | 35 | 40 | 50 | 70 | 50 | 60 | 65 | 70 | 70 | 70 | 45 | 65 | 75 | 80 | 84 | 80 | 62 | 62 | 62 | 50 | 50 | 50 | 50 | 50 | 60 | 60 | 60 | 30 | 90 | 70 | 80 | 70 | 70 | 70 | 30 | 120 | 120 | 120 | 120 | 120 | 90 | 103 | 90 | 70 | 75 | 90 | 80 | 80 | 90 | 95 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 6 | 6 | 10 | 10 | 18 | 13 | 30 | 42 | 52 | 62 | 52 | 70 | 80 | 100 | 105 | 105 | 102 | 105 | 115 | 80 | 90 | 102 | 103 | 103 | 80 | 70 | 75 | 90 | 93 | 90 | 85 | 90 | 91 | 95 | 95 | 100 | 90 | 95 | 95 | 45 | 95 | 120 | 120 | 115 | 115 | 105 | 115 | 110 | 105 | 110 | 120 | 85 | 85 | 115 | 115 | 115 | 110 | 105 | 70 | 50 | 90 | 120 | 105 | 0 | 60 | 70 | 55 | 80 | 105 | 115 | 115 | 120 | 120 | 115 | 105 | 110 | 110 | 105 | 115 | 105 | 90 | 110 | 90 | 80 | 75 | 80 | 85 | 85 | 0 | 70 | 70 | 80 | 85 | 90 | 85 | 25 | 25 | 45 | 18 | 10 | 19 | 20 | 20 | 20 | 20 | 30 | 30 | 30 | 30 | 40 | 35 | 35 | 20 | 20 | 20 | 20 | 20 | 40 | 25 | 15 | 30
| 2 | M/s Bnal Prefabs Pvt Ltd. | GIS,MCR & SGR | PEB | 8 | [82 empty] | 15 | 14 | 14 | 0 | 11 | 10 | 15 | 13 | 15 | 16 | 15 | 15 | 15 | 32 | 32 | 0 | 37 | 34 | 35 | 20 | 17 | 24 | 24 | 22 | 17 | 32 | 32 | 27 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 27 | 33 | 28 | 28 | 25 | 27 | 27 | 27 | 28 | 20 | 20 | 20 | 26 | 18 | 40 | 38 | 32 | 46 | 36 | 34 | 34 | 38 | 38 | 34 | 32 | 32 | 32 | 32 | 21 | 25 | 24 | 15 | 14 | 14 | 14 | 22 | 7 | 14 | 12 | 5 | 20 | 20 | 6 | 0 | 0 | 15 | 12 | 11 | 12 | 15 | 15 | 15 | 12 | 14 | 22 | 18 | 17 | 11 | 12 | 15 | 6 | 0 | 8 | 12 | 8 | 10 | 10 | 10 | 18 | 18 | 18 | 18 | 10 | 10 | 0 | 4 | 4 | 4 | 8 | 8 | 10 | 10 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 5 | 0 | 0 | 5 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 6 | 10 | 12 | 10 | 12 | 10 | 12 | 12 | 10 | 10 | 8 | 8 | 8 | 10 | 10 | 10 | 10 | 10 | 3 | 10 | 10 | 10 | 10 | 12 | 12 | 10 | 0 | 10 | 8 | 10 | 12 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 11 | 11 | 12 | 12 | 12 | 10 | 12 | 10 | 10 | 0 | 0 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 12
| 3 | M/s Hyosung T&d India Pvt Ltd. | GIS,MCR & SGR | Electrical | 13 | [68 empty] | 3 | 3 | 5 | 5 | 8 | 8 | 8 | 10 | 10 | 14 | 10 | 10 | 13 | 11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 5 | 7 | 0 | 4 | 0 | 5 | 5 | 13 | 5 | 13 | 13 | 10 | 13 | 13 | 24 | 18 | 18 | 18 | 18 | 18 | 21 | 20 | 18 | 18 | 18 | 21 | 24 | 20 | 24 | 26 | 27 | 27 | 28 | 27 | 36 | 36 | 36 | 38 | 40 | 43 | 50 | 45 | 45 | 43 | 45 | 45 | 45 | 54 | 48 | 45 | 55 | 55 | 72 | 52 | 65 | 65 | 65 | 50 | 50 | 50 | 55 | 55 | 60 | 55 | 62 | 62 | 62 | 60 | 59 | 62 | 70 | 70 | 55 | 55 | 60 | 65 | 62 | 69 | 69 | 67 | 63 | 55 | 71 | 73 | 75 | 69 | 35 | 73 | 70 | 63 | 71 | 74 | 74 | 75 | 72 | 62 | 72 | 77 | 73 | 75 | 70 | 55 | 78 | 70 | 82 | 82 | 87 | 83 | 80 | 68 | 34 | 28 | 28 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 35 | 30 | 30 | 30 | 35 | 40 | 40 | 40 | 40 | 40 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 15 | 15 | 15 | 29 | 29 | 29 | 29 | 24 | 0 | 27 | 29 | 29 | 18 | 18 | 14 | 18 | 18 | 18 | 20 | 20 | 20 | 17 | 19 | 20 | 25 | 23 | 25 | 26 | 26 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 51 | 43 | 46 | 50 | 52 | 52 | 52 | 52 | 48 | 52 | 48 | 48 | 48 | 42 | 45 | 48 | 56 | 50 | 48 | 48 | 43 | 43 | 45 | 55 | 55 | 56 | 56 | 46 | 48 | 48 | 61 | 56 | 56 | 56 | 46 | 45 | 45 | 45 | 48 | 45 | 46 | 38 | 35 | 35 | 25 | 0 | 24 | 16 | 18 | 24 | 22 | 22 | 20 | 22 | 20 | 13 | 18 | 17 | 20 | 18 | 18 | 22 | 15 | 18 | 18 | 15 | 15 | 15 | 18 | 14 | 0 | 14 | 16 | 12 | 16 | 16 | 12 | 12 | 12 | 12 | 15 | 15 | 15 | 14 | 11 | 15 | 14 | 14 | 14 | 15 | 12 | 19 | 16 | 16 | 18 | 18 | 20 | 20 | 20 | 20 | 18 | 18 | 18
| 4 | M/s Hitachi Energy India Ltd | HF | Electrical | 12 | [128 empty] | 7 | 7 | 7 | 7 | 11 | 7 | 7 | 7 | 10 | 10 | 13 | 14 | 14 | 14 | 14 | 0 | 0 | 14 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 13 | 15 | 15 | 13 | 14 | 7 | 5 | 0 | 7 | 7 | 7 | 6 | 7 | 6 | 6 | 6 | 4 | 5 | 5 | 5 | 20 | 8 | 8 | 10 | 10 | 16 | 16 | 25 | 20 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 14 | 10 | 11 | 12 | 7 | 7 | 7 | 0 | 12 | 8 | 8 | 17 | 15 | 15 | 0 | 15 | 15 | 12 | 16 | 25 | 25 | 15 | 15 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12
| 5 | M/s TBEA | PTR | Electrical | 6 | [109 empty] | 7 | 7 | 7 | 7 | 0 | 0 | 8 | 12 | 12 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 10 | 10 | 12 | 12 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 11 | 11 | 11 | 14 | 15 | 15 | 15 | 11 | 11 | 2 | 11 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 18 | 18 | 18 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 4 | 4 | 4 | 4 | 6 | 5 | 7 | 7 | 7 | 7 | 2 | 2 | 6 | 3 | 3 | 3 | 12 | 8 | 6 | 3 | 3 | 3 | 3 | 15 | 15 | 10 | 10 | 10 | 12 | 12 | 10 | 10 | 12 | 12 | 9 | 9 | 12 | 12 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 6 | 6 | 6 | 6 | 6 | 10 | 10 | 8 | 0 | 7 | 6 | 9 | 10 | 4 | 6 | 6 | 6 | 8 | 8 | 8 | 9 | 0 | 8 | 8 | 10 | 6 | 8 | 10 | 9 | 8 | 8 | 9 | 10 | 10 | 9 | 9 | 9 | 9 | 9 | 9 | 9
| 6 | Rajiv Const(Departmental) |  |  | 0 | [55 empty] | 29 | 29 | 27 | 16 | 15 | 18 | 18 | 14 | 18 | 16 | 16 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 15 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 17 | 15 | 0 | 0 | 14 | 14 | 14 | 14 | 14 | 15 | 14 | 14 | 12 | 17 | 18 | 15 | 15 | 13 | 13 | 15 | 14 | 14 | 14 | 15 | 14 | 14 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | Shree Const(Departmental) |  |  | 0 | [57 empty] | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 14 | 14 | 11 | 11 | 11 | 13 | 12 | 14 | 14 | 17 | 14 | 14 | 15 | 15 | 13 | 13 | 22 | 0 | 41 | 35 | 35 | 35 | 33 | 20 | 18 | 25 | 23 | 22 | 25 | 25 | 25 | 14 | 14 | 18 | 17 | 17 | 15 | 14 | 14 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 | Mk Rajput(Departmental) |  |  | 0 | [111 empty] | 22 | 22 | 22 | 29 | 26 | 28 | 25 | 28 | 28 | 34 | 34 | 34 | 27 | 29 | 29 | 29 | 31 | 35 | 35 | 35 | 37 | 32 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | M/s Varsha Solar | SVG | Electrical | 0 | [146 empty] | 7 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 0 | 3 | 3 | 5 | 6 | 6 | 8 | 7 | 7 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | M/s Akshar Elec | SVG | Electrical | 0 | [252 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 6 | 8 | 8 | 20 | 20 | 10 | 13 | 11 | 16 | 16 | 16 | 16 | 15 | 15 | 16 | 16 | 20 | 25 | 18 | 10 | 12 | 10 | 12 | 12 | 12 | 12 | 15 | 15 | 23 | 20 | 20 | 15 | 15 | 14 | 14 | 17 | 18 | 18 | 8 | 8 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 0 | 6 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 0 | 20 | 20 | 45 | 45 | 45 | 35 | 35 | 35 | 35 | 25 | 30 | 25 | 24 | 20 | 28 | 20 | 20 | 20 | 18 | 19 | 17 | 18 | 21 | 19 | 16 | 12 | 12 | 12 | 12 | 8 | 8 | 8
| 11 | Departmental(SP Construction) |  | Electrical | 0 | [257 empty] | 24 | 24 | 23 | 21 | 18 | 23 | 21 | 23 | 22 | 30 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12 | HSB | HF | Civil | [260 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 12 | 12 | 10 | 5 | 5 | 6 | 0 | 10 | 10
| B | 400kv Transmission Line Manpower |  |  | 0
| 1 | M/s Usha Engineering | Erection |  | 0 | [25 empty] | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 22 | 22 | 22 | 22 | 22 | 17 | 17 | 14 | 14 | 14 | 14 | 14 | 13 | 13 | 13 | 13 | 13 | 19 | 19 | 14 | 13 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Stringing & OPGW |  | 0 | [46 empty] | 6 | 7 | 8 | 8 | 8 | 16 | 12 | 12 | 7 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 7 | 15 | 15 | 5 | 6 | 6 | 6 | 6 | 6 | 5 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| A | PSS-06 Machinery |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | AGEL Hired
|  | Crane |  |  | 0 | [274 empty] | 1
|  | Excavator |  |  | 0 | [274 empty] | 1
|  | Trailer |  |  | 0 | [212 empty] | 1
|  | DG Set |  |  | 0
|  | Farana |  |  | 0 | [274 empty] | 1
|  | Dumper |  |  | 0
|  | Roller |  |  | 0
|  | Manlifter |  |  | 0
|  | De-Watering Pump |  |  | 0
|  | MLT |  |  | 0 | [212 empty] | 3
| 2 | M/s DNC
|  | Crane |  |  | 0
|  | Excavator |  |  | 0
|  | Trailer |  |  | 0
|  | DG Set |  |  | 0
|  | Farana |  |  | 0
|  | Manlifter |  |  | 0
|  | De-Watering Pump |  |  | 0
|  | MLT |  |  | 0
| 3 | M/s Bnal Prefabs Pvt Ltd.
|  | Crane |  |  | 0
|  | Excavator |  |  | 0
|  | Trailer |  |  | 0
|  | DG Set |  |  | 0
|  | Farana |  |  | 0
|  | Manlifter |  |  | 0
|  | De-Watering Pump |  |  | 0
|  | MLT |  |  | 0
| 4 | M/s Hyosung T&d India Pvt Ltd.
|  | Crane |  |  | 0 | [274 empty] | 1
|  | Excavator |  |  | 0
|  | Trailer |  |  | 0
|  | DG Set |  |  | 0 | [274 empty] | 1
|  | Farana |  |  | 0 | [274 empty] | 1
|  | Manlifter |  |  | 0
|  | De-Watering Pump |  |  | 0
|  | MLT |  |  | 0
| 5 | M/s Hitachi Energy India Ltd
|  | Crane |  |  | 0
|  | Excavator |  |  | 0
|  | Trailer |  |  | 0
|  | DG Set |  |  | 0
|  | Farana |  |  | 0
|  | Manlifter |  |  | 0
|  | De-Watering Pump |  |  | 0
|  | MLT |  |  | 0
| 6 | M/s TBEA
|  | Crane |  |  | 0
|  | Excavator |  |  | 0
|  | Trailer |  |  | 0
|  | DG Set |  |  | 0
|  | Farana |  |  | 0
|  | Manlifter |  |  | 0
|  | De-Watering Pump |  |  | 0
|  | MLT |  |  | 0
| 7 | M/s Usha Eng | 400KV TL
|  | Crane |  |  | 0
|  | Excavator |  |  | 0
|  | Trailer |  |  | 0
|  | DG Set |  |  | 0
|  | Farana |  |  | 0
|  | Manlifter |  |  | 0
|  | De-Watering Pump |  |  | 0
|  | MLT |  |  | 0
| 8 | M/s Akshar Elec | SVG
Crane
Excavator
Trailer
|  | DG Set | [277 empty] | 1
|  | Farana | [277 empty] | 1
|  | JCB | [277 empty] | 1
Manlifter
De-Watering Pump
MLT

## 400kv TL Tower Erection
List of Completed Erection
Sl.No. | Month Sl.No. | AP-no | Location No. | Type of tower | Actual/ Forecast Start Date | Actual/ Forecast Finish Date | Weight of Tower (Kg) |  |  |  |  | Vendor's Name
[7 empty] | HT | MS | PW | B & N | Total
[5 empty] | 2024-10-04 | 2025-04-23
1 | April 25 | AP-14 | 14/0(SC) (90°) | DE+0(90°) | 2025-04-17 | 2025-04-23 | [5 empty] | M/s Usha Engineering
2 | April 25 | AP-13 | 13/0(SC) | FC+0 | 2025-04-09 | 2025-04-14 | [5 empty] | M/s Usha Engineering
3 | April 25 | AP-12 | 12/0(SC) | FC+0 | 2025-04-04 | 2025-04-07 | [5 empty] | M/s Usha Engineering
4 | April 25 | AP-11 | 11/0(SC) | FB+0 | 2025-03-31 | 2025-04-04 | [5 empty] | M/s Usha Engineering
5 | November 24 |  | 10/6(SC) | FA+0 | 2024-11-26 | 2024-11-27 | [5 empty] | M/s Usha Engineering
6 | November 24 |  | 10/5(SC) | FA+3 | 2024-11-23 | 2024-11-26 | [5 empty] | M/s Usha Engineering
7 | October 24 |  | 10/4(SC) | FA+3 | 2024-10-10 | 2024-10-13 | [5 empty] | M/s Usha Engineering
8 | October 24 |  | 10/3(SC) | FA+3 | 2024-10-14 | 2024-10-18 | [5 empty] | M/s Usha Engineering
9 | October 24 |  | 10/2(SC) | FA+0 | 2024-10-06 | 2024-10-08 | [5 empty] | M/s Usha Engineering
10 | October 24 |  | 10/1(SC) | FA+0 | 2024-10-04 | 2024-10-06 | [5 empty] | M/s Usha Engineering
11 | March 25 | AP-10 | 10/0(SC) | FB+0 | 2025-03-16 | 2025-03-20 | [5 empty] | M/s Usha Engineering
12 | March 25 |  | 9/1(SC) | FA+0 | 2025-03-10 | 2025-03-15 | [5 empty] | M/s Usha Engineering
13 | March 25 | AP-9 | 9/0(SC) | FD+6 | 2025-03-22 | 2025-03-29 | [5 empty] | M/s Usha Engineering
Formulas:
Actual/ Forecast Start Date = MIN([Actual/ Forecast Start Date, row below]:G32)
Actual/ Forecast Finish Date = MAX([Actual/ Forecast Finish Date, row below]:H18)

## 400kv TL Visual Chart
Line Name:- PSS-06 to KPS-01 Transmission line
Executing Agency:- Usha Engineering
[25 empty] | 400 kv Line Hgt=20.71 | [6 empty] | WIP | [5 empty] | Completed |  |  |  |  | Date- | 2026-02-27
| SL. NO. |  | Description |  |  |  | UOM |  | Total Qty |  | Completed |  |  | WIP |  | Balance |  | Remarks
| 1 |  | Foundation |  |  |  | Nos |  | 28 |  | 28 |  |  | 0 |  | 0 |  | 15 towers common for both PSS-02 & 06 Lines | [14 empty] | Tie Beam |  |  |  |  | Tie Beam
| 2 |  | Earthing |  |  |  | Nos |  | 28 |  | 28 |  |  | 0 |  | 0 | [16 empty] | Backfilling |  |  |  |  | Backfilling
| 3 |  | Tower Erection |  |  |  | Nos |  | 28 |  | 28 |  |  | 0 |  | 0 | [16 empty] | Chimney |  |  |  |  | Chimney
| 4 |  | Rough Sag |  |  |  | KM |  | 9.137 |  | 9.137 |  |  |  |  | 1.7764e-15 |  | Completed on 21-nov-25 | [14 empty] | Frustrum |  |  |  |  | Frustrum
| 5 |  | Final Sag |  |  |  | KM |  | 9.137 |  | 9.137 |  |  | - |  | 0 |  | Completed on 21-nov-25 | [14 empty] | PCC |  |  |  |  | PCC
[33 empty] | Blanketing |  |  |  |  | Blanketing
|  |  |  | 90 |  | 100.321 |  | 156.379 |  | 360.939 |  | 377.384 |  | 367.618 |  | 392.926 |  | 408.852 |  | 376.429 |  | 365.309 |  | 283.21 |  | 298.619 |  | 394.821 |  | 231 |  |  | Excavation |  |  |  |  | Excavation
[32 empty] | 231 |  | 368.493 |  | 351.354 |  | 374.106 |  | 393.023 |  | 374.978 |  | 259.659 |  | 345.438 |  | 408.635 |  | 421.375 | 453.004
Tie Beam |  | PSS-06 Gantry | [28 empty] | AP-8A
Backfilling | [30 empty] | 8A/0(SC)
Chimney | [30 empty] | DE+0(90 DEG) |  | AP-08 | [9 empty] | AP-07 |  | AP-06 |  |  |  |  | AP-05
Frustrum | [32 empty] | 8/0(DC)PSS2 |  | 7/4(DC)PSS2 |  | 7/3(DC)PSS2 | 7/3(DC)PSS2 | 7/2(DC)PSS2 | 7/2(DC)PSS2 | 7/1(DC)PSS2 | 7/1(DC)PSS2 | 7/0(DC)PSS2 | 7/0(DC)PSS2 | 6/0(DC)PSS2 | 6/0(DC)PSS2 | 5/2(DC)PSS2 | 5/2(DC)PSS2 | 5/1(DC)PSS2 | 5/0(DC)PSS2
PCC | [32 empty] | FC+9 |  | FA+3 |  | FA+0 | FA+0 | FA+3 | FA+3 | FA+3 | FA+3 | FB+0 | FB+0 | FB+0 | FB+0 | FA+3 | FA+3 | FA+3 | FB+6
Blanketing
Excavation
[5 empty] | AP-14 |  | AP-13 |  | AP-12 |  | AP-11 | [13 empty] | AP-10 |  |  |  | AP-9
[5 empty] | 14/0(SC) |  | 13/0(SC) |  | 12/0(SC) |  | 11/0(SC) |  | 10/6(SC) |  | 10/5(SC) |  | 10/4(SC) |  | 10/3(SC) |  | 10/2(SC) |  | 10/1(SC) |  | 10/0(SC) |  | 9/1(SC) |  | 9/0(SC)
[5 empty] | DE+0(90°) |  | FC+0 |  | FC+0 |  | FB+0 |  | FA+0 |  | FA+3 |  | FA+3 |  | FA+3 |  | FA+0 |  | FA+0 |  | FB+0 |  | FA+0 |  | FD+6
|  |  |  | 400 |  |  | 310.644 |  |  | 150.483 |  |  | 91.019
|  | AP-04 |  |  | AP-03 | AP-03 |  | AP-02 | AP-02 |  | AP-01 | AP-01 |  | KPS-1 Gantry
|  | 4/0(DC)PSS2 |  |  | 3/0(DC)PSS2 |  |  | 2/0(DC)PSS2 |  |  | 1/0(DC)PSS2
|  | FD+9 |  |  | FD+6 | FD+6 |  | FD+6 | FD+6 |  | FD+0 | FD+0

## 400kv TL Stringing
Line Name:- PSS-06 to KPS-01 Transmission line
STRINGING
SL. No. | Section |  | Vendor Name | Section Length | Completed | Section Reediness | Actual/Forecast |  | Insulator Hoisting |  | Paying Out |  |  | Rough Sag |  |  | Final Sag
| From | To |  |  |  |  | Start | Finish | Start | Finish | Start | Finish | Remarks | Start | Finish | Remarks | Start | Finish | Remarks
[7 empty] | 2025-03-31 |  | 2025-03-31 |  | 2025-04-02 |  |  | 2025-04-08 |  |  | 2025-04-08
1 | PSS6 GANTRY | AP-14 |  | 90 | 90 | Completed | 2025-11-20 | 2025-11-21 | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-20 | Completed | 2025-11-21 | 2025-11-21 | Completed | 2025-11-21 | 2025-11-21 | Completed
2 | AP-14 | AP-13 |  | 100.321 | 100.321 | Completed | 2025-04-27 | 2025-04-28 | 2025-04-27 | 2025-04-27 | 2025-04-27 | 2025-04-27 | Completed | 2025-04-28 | 2025-04-28 | Completed | 2025-04-28 | 2025-04-28 | Completed
3 | AP-13 | AP-12 |  | 156.379 | 156.379 | Completed | 2025-04-16 | 2025-04-17 | 2025-04-16 | 2025-04-16 | 2025-04-16 | 2025-04-16 | Completed | 2025-04-16 | 2025-04-16 | Completed | 2025-04-17 | 2025-04-17 | Completed
4 | AP-12 | AP-11 |  | 360.939 | 360.939 | Completed | 2025-04-09 | 2025-04-18 | 2025-04-09 | 2025-04-09 | 2025-04-10 | 2025-04-14 | Completed | 2025-04-14 | 2025-04-14 | Completed | 2025-04-18 | 2025-04-18 | Completed
5 | AP-11 | AP-10 |  | 2571.728 | 2571.728 | Completed | 2025-04-04 | 2025-04-12 | 2025-04-04 | 2025-04-07 | 2025-04-06 | 2025-04-08 | Completed | 2025-04-10 | 2025-04-10 | Completed | 2025-04-11 | 2025-04-12 | Completed
6 | AP-10 | AP-9 |  | 693.44 | 693.44 | Completed | 2025-03-31 | 2025-04-10 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-04 | Completed | 2025-04-09 | 2025-04-09 | Completed | 2025-04-10 | 2025-04-10 | Completed
7 | AP-9 | AP-8A |  | 231 | 231 | Completed | 2025-04-07 | 2025-04-08 | 2025-04-07 | 2025-04-07 | 2025-04-07 | 2025-04-07 | Completed | 2025-04-08 | 2025-04-08 | Completed | 2025-04-08 | 2025-04-08 | Completed
8 | AP-8A | AP-08 |  | 231 | 231 | Completed | completed | completed
9 | AP-08 | AP-07 |  | 1861.954 | 1861.954 | Completed | completed | completed
10 | AP-07 | AP-06 |  | 259.659 | 259.659 | Completed | completed | completed
11 | AP-06 | AP-05 |  | 1175.448 | 1175.448 | Completed | completed | completed
12 | AP-05 | AP-04 |  | 453.004 | 453.004 | Completed | completed | completed
13 | AP-04 | AP-03 |  | 400 | 400 | Completed | completed | completed
14 | AP-03 | AP-02 |  | 310.644 | 310.644 | Completed | completed | completed
15 | AP-02 | AP-01 |  | 150.483 | 150.483 | Completed | completed | completed
16 | AP-01 | KPS-1GANTRY |  | 91.019 | 91.019 | Completed | 2025-10-11 | 2025-10-12 | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-11 | Completed | 2025-10-12 | 2025-10-12 | Completed | 2025-10-12 | 2025-10-12 | Completed
|  |  |  | 9137.018 | 9137.018 | m
|  |  |  | 9.137 | 9.137 | Km
Formulas:
Actual/Forecast = MIN([Actual/Forecast, row below]:I14)
Actual/Forecast = MIN([Insulator Hoisting]:[Remarks])
Insulator Hoisting = MIN([Insulator Hoisting, row below]:K14)
Insulator Hoisting = [Actual/Forecast]
Paying Out = MIN([Paying Out, row below]:M14)
Paying Out = [Finish]
Rough Sag = MIN([Rough Sag, row below]:P14)
Rough Sag = [Finish]+1
Final Sag = MIN([Final Sag, row below]:S14)
Final Sag = [Finish]
Finish = [Actual/Forecast]+1
Finish = [Insulator Hoisting]

## Issues
PSS-06 ¦ Phase -II FY 25-26 ¦ Khavda ¦ |  |  |  |  | Open | 0
[5 empty] | Closed | 20
Sr.No | Area | Description | Start | Closure | Days Effected | Open / Closed | Scope | Responsible | Remarks/ Resolution | Impact On
1 | PSS | All works hampered due to rain | 2025-06-17 | 2025-06-20 | 4 | Closed | DNC | AGEL
2 | MCR,GIS,HF | Work Delayed due to Approach Road | 2025-06-16 | 2025-06-21 | 6 | Closed | DNC | AGEL
3 | MCR | Battery Room tiles not recived yet. | 2025-06-10 | 2025-06-27 | 18 | Closed | DNC | DNC |  | Handover to Electrical
4 | MCR | Partition wall Not recived. | 2025-06-14 | 2025-06-19 | 6 | Closed | Bnal | M/s Bnal |  | Handover to Electrical
5 | SVG | Bricks not recived | 2025-06-10 | 2025-06-23 | 14 | Closed | DNC | DNC |  | Reactor foundation works
6 | GIS - PEB | 1no Additional man Lifter required | 2025-06-11 | 2025-06-18 | 8 | Closed | Bnal | M/s Bnal |  | PEB erection
7 | P1- PTR- SGR | Supply of Box Culverts for cable trench work | 2025-06-18 | 2025-07-29 | 42 | Closed | AGEL | AGEL
8 | P1- HF & SVG | Sand required | 2025-06-10 | 2025-06-29 | 20 | Closed | DNC | DNC |  | HF- PCC & SVG - Foundation works
9 | Firewall -1 | Block material to be supplied for masonry works. | 2025-06-17 | 2025-06-29 | 13 | Closed | DNC | DNC |  | 2nd Lift Masonry works
10 | PSS | Waterlogged at site. | 2025-06-26 | 2025-07-30 | 35 | Closed | DNC | DNC |  | All works are delayed
11 | PSS | M/s DNC manpower to be increased. | 2025-06-27 | 2025-08-21 | 56 | Closed | DNC | DNC
12 | PSS | Engineering Drawings for AHU,Cable tray footing (Pullpitside to GIS) not recived. | 2025-07-14 | 2025-08-02 | 20 | Closed | AGEL | AGEL |  | Due to which work Delayed
13 | PSS | From Vendor Side No Engineers or Surveyors Are Available at Site including the PM of the DNC (Vendor Name:-DNC) | 2025-07-21 | 2025-07-30 | 10 | Closed | DNC | DNC |  | Entire work hampered on the PSS 6
14 | PSS | No materials including working tools for labour from DNC | 2025-07-21 | 2025-07-30 | 10 | Closed | DNC | DNC |  | Entire work hampered on the PSS 6
15 | PSS | Work Hampered due to rain | 2025-08-18 | 2025-08-19 | 2 | Closed
16 | PSS | PTR-01 & 02 Oil to be supplied | 2025-08-17 | 2025-08-28 | 12 | Closed | TBEA | TBEA | Recahed at khavda on 27-Aug-25. | Oil filling
17 | PSS | Work Hampered due to rain 4:PM -5:PM | 2025-08-20 | 2025-08-20 | 1 | Closed
18 | PSS | Work hamperd due to waterlogged. | 2025-08-21 | 2025-08-21 | 1 | Closed |  |  |  | GIB, Equipment & SGR foundation works, PEB works
19 | SVG | Electrical Erection Vendor to be mobilized | 2025-08-30 | 2025-10-30 | 62 | Closed |  | TC |  |  | Implementation Works
20 | PSS | Works Hampered due to Heavy Rain (from7:00pm 06sep) | 2025-09-06 | 2025-09-10 | 5 | Closed |  |  |  | All oudoor works
21 | PSS | Waterlogged at site | 2025-09-06 | 2025-10-16 | 41 | Closed |  |  |  | All oudoor works - Hampered
Formulas:
Closure = [Start]