## Slide 1
Battery Energy Storage Systems
Projects : FY 2026 – 27
22nd Sep 26

## Slide 2
Project Capacity
PSS | Power | Energy | Dispatchable Energy
PSS-11 | 1080 MW | 2436 MWh | 2210 MWh
PSS-12 | 960 MW | 2166 MWh | 1963 MWh
PSS-10(B) | 600 MW | 1204 MWh | 1078 MWh
PSS-09 | 1080 MW | 2436 MWh | 2209 MWh
PSS-05(B) | 1120 MW | 2527 MWh | 2284 MWh
PSS-08(B) | 420 MW | 843 MWh | 758 MWh
Total | 5260 MW | 11612 MWh | 10502 MWh

## Slide 3
Engineering Status
Package | Start | Finish | Total Drawings | Approved | Approval % | Remarks
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 

## Slide 4
Engineering Status (Cont.)
Package | Start | Finish | Total Drawings | Approved | Approval % | Remarks
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 
 |  |  | 0 | 0 | 0% | 

## Slide 5
Ordering Status
Package | Start | Finish | PR/Indent Date | PO Number | PO Date | Remarks
Battery Container - 384 nos |  |  |  |  |  | 
Structural material |  |  |  |  |  | 
Optic Fibre Cable (OFC) |  |  |  |  |  | 
Converter Transformer (CT) (Incl. NIFPS) - 48 nos |  |  |  |  |  | 
MV Switchgear - 16 nos |  |  |  |  |  | 
HT Cables |  |  |  |  |  | 
LT 1C X 400 Sqmm |  |  |  |  |  | 
Control Cables |  |  |  |  |  | 
CSS - 8 nos |  |  |  |  |  | 
Harmonic Filter |  |  |  |  |  | 
LT cable - 3.5X50 mm |  |  |  |  |  | 
PCS - 384 set |  |  |  |  |  | 
EMS |  |  |  |  |  | 
ACDB - 48 nos |  |  |  |  |  | 
Precast Structure ordering |  |  |  |  |  | 

## Slide 6
Ordering Status (Cont.)
Package | Start | Finish | PR/Indent Date | PO Number | PO Date | Remarks
SCADA Control Cable |  |  |  |  |  | 
Grid Compliance Study |  |  |  |  |  | 
Civil Works - Piling Works |  |  |  |  |  | 
Finalization of consultant |  |  |  |  |  | 
Structural/PEB works |  |  |  |  |  | 
Electrical work-ACDC |  |  |  |  |  | 
Civil works BOP( Equi. Foundation,HF) |  |  |  |  |  | 
REINFORCEMENT STEEL |  |  |  |  |  | 
ANCHOR BOLT |  |  |  |  |  | 
ANCHOR FLANGE |  |  |  |  |  | 
USS PRECAST |  |  |  |  |  | 
WTG (NHDT) |  |  |  |  |  | 
WTG (BLADE) |  |  |  |  |  | 
WTG (TOWER) |  |  |  |  |  | 
SCADA & PPC |  |  |  |  |  | 

## Slide 7
Ordering Status (Cont.)
Package | Start | Finish | PR/Indent Date | PO Number | PO Date | Remarks
USS TRANSFORMER |  |  |  |  |  | 
USS HT PANEL |  |  |  |  |  | 
33KV FO CABLE |  |  |  |  |  | 
33KV HT CABLE |  |  |  |  |  | 
STONE COLUMN |  |  |  |  |  | 
WTG & USS FOUNDATION |  |  |  |  |  | 
APPROACH ROAD FOR WTG FOUNDATION |  |  |  |  |  | 
WTG LOGISTICS |  |  |  |  |  | 
ROAD FOR ERECTION (INCL.TURNING RADIUS) |  |  |  |  |  | 
CRANE PAD |  |  |  |  |  | 
WTG ERECTION RELATED SERVICES |  |  |  |  |  | 
WTG ERECTION RELATED SERVICES |  |  |  |  |  | 
ELECTRICAL USS SERVICES |  |  |  |  |  | 
HT CABLE LAYING |  |  |  |  |  | 
Battery Container - 432 nos |  |  |  |  |  | 

## Slide 8
Ordering Status (Cont.)
Package | Start | Finish | PR/Indent Date | PO Number | PO Date | Remarks
Balance Supply Items To be deleted |  |  |  |  |  | 
Optic Fibre Cable (OFC) |  |  |  |  |  | 
Converter Transformer (CT) (Incl. NIFPS) - 54 nos |  |  |  |  |  | 
MV Switchgear - 18 nos |  |  |  |  |  | 
HT Cables |  |  |  |  |  | 
LT 1C X 400 Sqmm |  |  |  |  |  | 
Control Cables |  |  |  |  |  | 
CSS - 9 nos |  |  |  |  |  | 
Harmonic Filter |  |  |  |  |  | 
LT cable - 3.5X50 mm |  |  |  |  |  | 
PCS - 432 set |  |  |  |  |  | 
EMS |  |  |  |  |  | 
ACDB |  |  |  |  |  | 
Precast Structure ordering |  |  |  |  |  | 
SCADA Control Cable |  |  |  |  |  | 

## Slide 9
Ordering Status (Cont.)
Package | Start | Finish | PR/Indent Date | PO Number | PO Date | Remarks
Grid Compliance Study |  |  |  |  |  | 
Civil Works - Piling Works |  |  |  |  |  | 
Finalization of consultant |  |  |  |  |  | 
Structural/PEB works |  |  |  |  |  | 
Electrical work-ACDC |  |  |  |  |  | 
Civil works BOP( Equi. Foundation,HF) |  |  |  |  |  | 
Battery Container - 432 nos |  |  |  |  |  | 
Balance Supply Iteams To be deleted |  |  |  |  |  | 
Optic Fibre Cable (OFC) |  |  |  |  |  | 
Converter Transformer (CT) (Incl. NIFPS) - 54 nos |  |  |  |  |  | 
MV Switchgear - 18 nos |  |  |  |  |  | 
HT Cables |  |  |  |  |  | 
LT 1C X 400 Sqmm |  |  |  |  |  | 
Control Cables |  |  |  |  |  | 
CSS - 9 nos |  |  |  |  |  | 

## Slide 10
Ordering Status (Cont.)
Package | Start | Finish | PR/Indent Date | PO Number | PO Date | Remarks
Harmonic Filter |  |  |  |  |  | 
LT cable - 3.5X50 mm |  |  |  |  |  | 
PCS - 432 set |  |  |  |  |  | 
EMS |  |  |  |  |  | 
ACDB |  |  |  |  |  | 
Precast Structure ordering |  |  |  |  |  | 
SCADA Control Cable |  |  |  |  |  | 
Grid Compliance Study |  |  |  |  |  | 
Civil Works - Piling Works |  |  |  |  |  | 
Finalization of consultant |  |  |  |  |  | 
Structural/PEB works |  |  |  |  |  | 
Electrical work-ACDC |  |  |  |  |  | 
Civil works BOP( Equi. Foundation,HF) |  |  |  |  |  | 
Battery Container - 128 nos |  |  |  |  |  | 
Optic Fibre Cable (OFC) - Paramount - 7 Km |  |  |  |  |  | 

## Slide 11
Ordering Status (Cont.)
Package | Start | Finish | PR/Indent Date | PO Number | PO Date | Remarks
Converter Transformer (CT) (Incl. NIFPS) -24 nos |  |  |  |  |  | 
MV Switchgear - 8 nos |  |  |  |  |  | 
HT Cables - 19 kms - DIAMOND POWER |  |  |  |  |  | 
LT 3C X 300 SqmmDIAMOND POWER - 110 Kms |  |  |  |  |  | 
Control Cables - Paramount - 32 kms |  |  |  |  |  | 
CSS - 4 nos |  |  |  |  |  | 
Harmonic Filter |  |  |  |  |  | 
LT cable - 3.5X50 mm - Diamond Paramount- 35 Km |  |  |  |  |  | 
LT Panel (Type NNX) - 384 set |  |  |  |  |  | 
Staircase Precast |  |  |  |  |  | 
ACDB - Trisquare - 16 Nos |  |  |  |  |  | 
SCADA Control Cable - Delton - 37 Kms |  |  |  |  |  | 
Grid Compliance Study |  |  |  |  |  | 
Civil Works - Piling of Battery Container |  |  |  |  |  | 
Geo Technical Investigation |  |  |  |  |  | 

## Slide 12
Ordering Status (Cont.)
Package | Start | Finish | PR/Indent Date | PO Number | PO Date | Remarks
Roads & Drain |  |  |  |  |  | 
Control Room & SGR (PEB Building) |  |  |  |  |  | 
Electrical ETC work - Service Order |  |  |  |  |  | 
Integration of Battery container + PCS + EMS with PSS PPC |  |  |  |  |  | 
Civil Works - Cast in Situ |  |  |  |  |  | 
Civil Works - Precast CT, BOT, NIFPS etc |  |  |  |  |  | 
Civil Works - Harmonic Filter |  |  |  |  |  | 
Erection Works - Harmonic Filter |  |  |  |  |  | 
REINFORCEMENT STEEL |  |  |  |  |  | 
ANCHOR BOLT |  |  |  |  |  | 
ANCHOR FLANGE |  |  |  |  |  | 
USS PRECAST |  |  |  |  |  | 
WTG (NHDT) |  |  |  |  |  | 
WTG (BLADE) |  |  |  |  |  | 
WTG (TOWER) |  |  |  |  |  | 

## Slide 13
Ordering Status (Cont.)
Package | Start | Finish | PR/Indent Date | PO Number | PO Date | Remarks
SCADA & PPC |  |  |  |  |  | 
USS TRANSFORMER |  |  |  |  |  | 
USS HT PANEL |  |  |  |  |  | 
33KV FO CABLE |  |  |  |  |  | 
33KV HT CABLE |  |  |  |  |  | 
STONE COLUMN |  |  |  |  |  | 
WTG & USS FOUNDATION |  |  |  |  |  | 
APPROACH ROAD FOR WTG FOUNDATION |  |  |  |  |  | 
WTG LOGISTICS |  |  |  |  |  | 
ROAD FOR ERECTION (INCL.TURNING RADIUS) |  |  |  |  |  | 
CRANE PAD |  |  |  |  |  | 
WTG ERECTION RELATED SERVICES |  |  |  |  |  | 
WTG ERECTION RELATED SERVICES |  |  |  |  |  | 
ELECTRICAL USS SERVICES |  |  |  |  |  | 
HT CABLE LAYING |  |  |  |  |  | 

## Slide 14
Ordering Status (Cont.)
Package | Start | Finish | PR/Indent Date | PO Number | PO Date | Remarks
REINFORCEMENT STEEL |  |  |  |  |  | 
ANCHOR BOLT |  |  |  |  |  | 
ANCHOR FLANGE |  |  |  |  |  | 
USS PRECAST |  |  |  |  |  | 
WTG (NHDT) |  |  |  |  |  | 
WTG (BLADE) |  |  |  |  |  | 
WTG (TOWER) |  |  |  |  |  | 
SCADA & PPC |  |  |  |  |  | 
USS TRANSFORMER |  |  |  |  |  | 
USS HT PANEL |  |  |  |  |  | 
33KV FO CABLE |  |  |  |  |  | 
33KV HT CABLE |  |  |  |  |  | 
STONE COLUMN |  |  |  |  |  | 
WTG & USS FOUNDATION |  |  |  |  |  | 
APPROACH ROAD FOR WTG FOUNDATION |  |  |  |  |  | 

## Slide 15
Ordering Status (Cont.)
Package | Start | Finish | PR/Indent Date | PO Number | PO Date | Remarks
WTG LOGISTICS |  |  |  |  |  | 
ROAD FOR ERECTION (INCL.TURNING RADIUS) |  |  |  |  |  | 
CRANE PAD |  |  |  |  |  | 
WTG ERECTION RELATED SERVICES |  |  |  |  |  | 
WTG ERECTION RELATED SERVICES |  |  |  |  |  | 
ELECTRICAL USS SERVICES |  |  |  |  |  | 
HT CABLE LAYING |  |  |  |  |  | 
Battery Container - 384 nos |  |  |  |  |  | 
Balance Supply Iteams To be deleted |  |  |  |  |  | 
Optic Fibre Cable (OFC) |  |  |  |  |  | 
Converter Transformer (CT) (Incl. NIFPS) - 48 nos |  |  |  |  |  | 
MV Switchgear - 16 nos |  |  |  |  |  | 
HT Cables |  |  |  |  |  | 
LT 1C X 400 Sqmm |  |  |  |  |  | 
Control Cables |  |  |  |  |  | 

## Slide 16
Ordering Status (Cont.)
Package | Start | Finish | PR/Indent Date | PO Number | PO Date | Remarks
CSS - 8 nos |  |  |  |  |  | 
Harmonic Filter |  |  |  |  |  | 
LT cable - 3.5X50 mm |  |  |  |  |  | 
PCS - 384 set |  |  |  |  |  | 
EMS |  |  |  |  |  | 
ACDB |  |  |  |  |  | 
Precast Structure ordering |  |  |  |  |  | 
SCADA Control Cable |  |  |  |  |  | 
Grid Compliance Study |  |  |  |  |  | 
Civil Works - Piling Works |  |  |  |  |  | 
Finalization of consultant |  |  |  |  |  | 
Structural/PEB works |  |  |  |  |  | 
Electrical work-ACDC |  |  |  |  |  | 
Civil works BOP( Equi. Foundation,HF) |  |  |  |  |  | 
Battery Container - 432 nos |  |  |  |  |  | 

## Slide 17
Ordering Status (Cont.)
Package | Start | Finish | PR/Indent Date | PO Number | PO Date | Remarks
Balance Supply Iteams |  |  |  |  |  | 
Optic Fibre Cable (FO) |  |  |  |  |  | 
Converter Transformer (CT) (Incl. NIFPS) - 54 nos |  |  |  |  |  | 
MV Switchgear - 18 nos |  |  |  |  |  | 
HT Cable - 80 kms |  |  |  |  |  | 
LT 1C X 400 Sqmm |  |  |  |  |  | 
Control Cables |  |  |  |  |  | 
CSS - 9 nos |  |  |  |  |  | 
Harmonic Filter |  |  |  |  |  | 
LT cable - 3.5X50 mm |  |  |  |  |  | 
PCS - 432 set |  |  |  |  |  | 
EMS |  |  |  |  |  | 
ACDB |  |  |  |  |  | 
Precast Structure ordering |  |  |  |  |  | 
SCADA Control Cable |  |  |  |  |  | 

## Slide 18
Ordering Status (Cont.)
Package | Start | Finish | PR/Indent Date | PO Number | PO Date | Remarks
Grid Compliance Study |  |  |  |  |  | 
Civil Works - Piling Works |  |  |  |  |  | 
Finalization of consultant |  |  |  |  |  | 
Structural/PEB works |  |  |  |  |  | 
Electrical work-ACDC |  |  |  |  |  | 
Civil works BOP( Equi. Foundation,HF) |  |  |  |  |  | 
Battery Container - 168 nos |  |  |  |  |  | 
PEB Structure |  |  |  |  |  | 
Optic Fibre Cable (OFC) |  |  |  |  |  | 
Converter Transformer (CT) (Incl. NIFPS) - 21 nos |  |  |  |  |  | 
MV Switchgear - 4 nos |  |  |  |  |  | 
HT Cable |  |  |  |  |  | 
LT 1C X 400 Sqmm |  |  |  |  |  | 
Control Cables |  |  |  |  |  | 
CSS - 4 nos |  |  |  |  |  | 

## Slide 19
Ordering Status (Cont.)
Package | Start | Finish | PR/Indent Date | PO Number | PO Date | Remarks
Harmonic Filter |  |  |  |  |  | 
LT cable - 3.5X50 mm |  |  |  |  |  | 
PCS - 168 set |  |  |  |  |  | 
EMS |  |  |  |  |  | 
ACDB |  |  |  |  |  | 
Precast Structure ordering |  |  |  |  |  | 
SCADA Control Cable |  |  |  |  |  | 
Grid Compliance Study |  |  |  |  |  | 
Civil Works - Piling Works |  |  |  |  |  | 
Finalization of consultant |  |  |  |  |  | 
Structural/PEB works |  |  |  |  |  | 
Electrical work-ACDC |  |  |  |  |  | 
Civil works BOP( Equi. Foundation,HF) |  |  |  |  |  | 
Battery Container - 448 nos |  |  |  |  |  | 
Balance Supply Iteams |  |  |  |  |  | 

## Slide 20
Ordering Status (Cont.)
Package | Start | Finish | PR/Indent Date | PO Number | PO Date | Remarks
Optic Fibre Cable (OFC) |  |  |  |  |  | 
Converter Transformer (CT) (Incl. NIFPS) - 56 nos |  |  |  |  |  | 
MV Switchgear - 20 nos |  |  |  |  |  | 
HT Cable 171 km. |  |  |  |  |  | 
LT 1C X 400 Sqmm |  |  |  |  |  | 
Control Cables |  |  |  |  |  | 
CSS - 10 nos |  |  |  |  |  | 
Harmonic Filter |  |  |  |  |  | 
LT cable - 3.5X50 mm |  |  |  |  |  | 
PCS - 448 set |  |  |  |  |  | 
EMS |  |  |  |  |  | 
ACDB |  |  |  |  |  | 
Precast Structure ordering |  |  |  |  |  | 
SCADA Control Cable |  |  |  |  |  | 
Grid Compliance Study |  |  |  |  |  | 

## Slide 21
Ordering Status (Cont.)
Package | Start | Finish | PR/Indent Date | PO Number | PO Date | Remarks
Civil Works - Piling Works |  |  |  |  |  | 
Finalization of consultant |  |  |  |  |  | 
Structural/PEB works |  |  |  |  |  | 
Electrical work-ACDC |  |  |  |  |  | 
Civil works BOP( Equi. Foundation,HF) |  |  |  |  |  | 
Battery Container - 240 nos |  |  |  |  |  | 
Structure Material |  |  |  |  |  | 
Optic Fibre Cable (OFC) |  |  |  |  |  | 
Converter Transformer (CT) (Incl. NIFPS) - 30 nos |  |  |  |  |  | 
MV Switchgear - 10 nos |  |  |  |  |  | 
HT Cables |  |  |  |  |  | 
LT 1C X 400 Sqmm |  |  |  |  |  | 
Control Cables |  |  |  |  |  | 
CSS - 5 nos |  |  |  |  |  | 
Harmonic Filter |  |  |  |  |  | 

## Slide 22
Ordering Status (Cont.)
Package | Start | Finish | PR/Indent Date | PO Number | PO Date | Remarks
LT cable - 3.5X50 mm |  |  |  |  |  | 
PCS - 240 set |  |  |  |  |  | 
EMS |  |  |  |  |  | 
ACDB |  |  |  |  |  | 
Precast Structure ordering |  |  |  |  |  | 
SCADA Control Cable |  |  |  |  |  | 
Grid Compliance Study |  |  |  |  |  | 
Civil Works - Piling Works |  |  |  |  |  | 
Finalization of consultant |  |  |  |  |  | 
Structural/PEB works |  |  |  |  |  | 
Electrical work-ACDC |  |  |  |  |  | 
Civil works BOP( Equi. Foundation,HF) |  |  |  |  |  | 
Battery Container - 240 nos |  |  |  |  |  | 
Structure Material |  |  |  |  |  | 
Optic Fibre Cable (OFC) |  |  |  |  |  | 

## Slide 23
Ordering Status (Cont.)
Package | Start | Finish | PR/Indent Date | PO Number | PO Date | Remarks
Converter Transformer (CT) (Incl. NIFPS) - 30 nos |  |  |  |  |  | 
MV Switchgear - 10 nos |  |  |  |  |  | 
HT Cables |  |  |  |  |  | 
LT 1C X 400 Sqmm |  |  |  |  |  | 
Control Cables |  |  |  |  |  | 
CSS - 5 nos |  |  |  |  |  | 
Harmonic Filter |  |  |  |  |  | 
LT cable - 3.5X50 mm |  |  |  |  |  | 
PCS - 240 set |  |  |  |  |  | 
EMS |  |  |  |  |  | 
ACDB |  |  |  |  |  | 
Precast Structure ordering |  |  |  |  |  | 
SCADA Control Cable |  |  |  |  |  | 
Grid Compliance Study |  |  |  |  |  | 
Civil Works - Piling Works |  |  |  |  |  | 

## Slide 24
Ordering Status (Cont.)
Package | Start | Finish | PR/Indent Date | PO Number | PO Date | Remarks
Finalization of consultant |  |  |  |  |  | 
Structural/PEB works |  |  |  |  |  | 
Electrical work-ACDC |  |  |  |  |  | 
Civil works BOP( Equi. Foundation,HF) |  |  |  |  |  | 

## Slide 25
Delivery Status
Package | Start | Finish | CDD | MDCC Date | Delivered at Site | Remarks

## Slide 26
Delivery Status (Cont.)
Package | Start | Finish | CDD | MDCC Date | Delivered at Site | Remarks

## Slide 27
Delivery Status (Cont.)
Package | Start | Finish | CDD | MDCC Date | Delivered at Site | Remarks

## Slide 28
Physical Progress: PSS 11 S-Curve
Chart: 
| Mar-25 | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26
Monthly Plan | 1.96 | 4.18 | 14.59 | 21.13 | 0.87 | 0 | 0.41 | 13.12 | 20.79 | 17.66 | 5.26 | 0.03 | 0
Monthly Actual | 1.02 | 0.87 | 2.25 | 3.85 | 1.6 | 2.98 | 1.02 | 2.18 | 12.79 | 21.22 | 14.46 | 22.97 | 12.79
Planned | 1.96 | 6.14 | 20.73 | 41.86 | 42.73 | 42.73 | 43.14 | 56.26 | 77.05 | 94.71 | 99.97 | 100 | 100
Actual | 1.02 | 1.89 | 4.14 | 7.99 | 9.59 | 12.57 | 13.59 | 15.77 | 28.56 | 49.78 | 64.24 | 87.21 | 100

## Slide 29
Physical Progress: PSS 12 S-Curve
Chart: 
| Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26
Monthly Plan | 0 | 6.19 | 22.33 | 24.94 | 27.63 | 13.45 | 3.73 | 0 | 0 | 0.18 | 1.55
Monthly Actual | 0.04 | 4.15 | 4.04 | 9.06 | 8.96 | 4.87 | 7.47 | 12.02 | 11.66 | 4.21
Planned | 0 | 6.19 | 28.52 | 53.46 | 81.09 | 94.54 | 98.27 | 98.27 | 98.27 | 98.45 | 100
Actual | 0.04 | 4.19 | 8.23 | 17.29 | 26.25 | 31.12 | 38.59 | 50.61 | 62.27 | 66.48

## Slide 30
Physical Progress: PSS 10B S-Curve
Chart: 
| Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26
Monthly Plan | 0.01 | 0.97 | 28.86 | 34.56 | 23.49 | 10.17 | 0.22 | 0 | 0 | 1.66 | 0.06
Monthly Actual | 0 | 1.03 | 5.98 | 3.85 | 1.2 | 1.84 | 6.15 | 13.38 | 19.24 | 2.55
Planned | 0.01 | 0.98 | 29.84 | 64.4 | 87.89 | 98.06 | 98.28 | 98.28 | 98.28 | 99.94 | 100
Actual | 0 | 1.03 | 7.01 | 10.86 | 12.06 | 13.9 | 20.05 | 33.43 | 52.67 | 55.22

## Slide 31
Physical Progress: PSS 9 S-Curve
Chart: 
| Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26
Monthly Plan | 0.11 | 11.19 | 17.65 | 21.7 | 18.52 | 15.71 | 9.15 | 0 | 0 | 0.67 | 3.52 | 1.4 | 0.38
Monthly Actual | 0 | 0.13 | 3.22 | 7.32 | 7.71 | 2.93 | 3.7 | 7.8 | 5.65 | 2.45
Planned | 0.11 | 11.3 | 28.95 | 50.65 | 69.17 | 84.88 | 94.03 | 94.03 | 94.03 | 94.7 | 98.22 | 99.62 | 100
Actual | 0 | 0.13 | 3.35 | 10.67 | 18.38 | 21.31 | 25.01 | 32.81 | 38.46 | 40.91

## Slide 32
Physical Progress: PSS 5B S-Curve
Chart: 
| Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26
Monthly Plan | 0.68 | 9.58 | 23.26 | 16.4 | 15.86 | 1.67 | 5.04 | 12.37 | 9.82 | 2.3 | 1.91 | 1.11
Monthly Actual | 0.06 | 1.95 | 4.27 | 2.79 | 2.79 | 2.76 | 5.59 | 0.72
Planned | 0.68 | 10.26 | 33.52 | 49.92 | 65.78 | 67.45 | 72.49 | 84.86 | 94.68 | 96.98 | 98.89 | 100
Actual | 0.06 | 2.01 | 6.28 | 9.07 | 11.86 | 14.62 | 20.21 | 20.93

## Slide 33
Physical Progress: PSS 8B S-Curve
Chart: 
| Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27
Monthly Plan | 0.01 | 0.28 | 33.47 | 23.59 | 8.49 | 1.52 | 0.08 | 0.78 | 9.59 | 10.33 | 8.29 | 2.17 | 1.4
Monthly Actual | 0 | 1.32 | 5.73 | 2.17 | 9.93 | 8.37 | 6.59 | 0.7
Planned | 0.01 | 0.29 | 33.76 | 57.35 | 65.84 | 67.36 | 67.44 | 68.22 | 77.81 | 88.14 | 96.43 | 98.6 | 100
Actual | 0 | 1.32 | 7.05 | 9.22 | 19.15 | 27.52 | 34.11 | 34.81

## Slide 34
Civil Detailed Progress
Block | Activity | Scope | Completed | UOM
Block 01 - BCT 1 | BLK 1:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 01 - BCT 2 | BLK 1:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 01 - BCT 3 | BLK 1:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 01 - BCT 4 | BLK 1:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 01 - BCT 5 | BLK 1:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 01 - BCT 6 | BLK 1:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 02 - BCT 1 | BLK 2:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 02 - BCT 2 | BLK 2:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 02 - BCT 3 | BLK 2:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 02 - BCT 4 | BLK 2:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 02 - BCT 5 | BLK 2:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 02 - BCT 6 | BLK 2:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 03 - BCT 1 | BLK 3:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 03 - BCT 2 | BLK 3:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 03 - BCT 3 | BLK 3:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos

## Slide 35
Civil Detailed Progress (Cont.)
Block | Activity | Scope | Completed | UOM
Block 03 - BCT 4 | BLK 3:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 03 - BCT 5 | BLK 3:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 03 - BCT 6 | BLK 3:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 04 - BCT 1 | BLK 4:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 04 - BCT 2 | BLK 4:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 04 - BCT 3 | BLK 4:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 04 - BCT 4 | BLK 4:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 04 - BCT 5 | BLK 4:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 04 - BCT 6 | BLK 4:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 05 - BCT 1 | BLK 5:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 05 - BCT 2 | BLK 5:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 05 - BCT 3 | BLK 5:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 05 - BCT 4 | BLK 5:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 05 - BCT 5 | BLK 5:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 05 - BCT 6 | BLK 5:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos

## Slide 36
Civil Detailed Progress (Cont.)
Block | Activity | Scope | Completed | UOM
Block 06 - BCT 1 | BLK 6:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 06 - BCT 2 | BLK 6:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 06 - BCT 3 | BLK 6:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 06 - BCT 4 | BLK 6:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 06 - BCT 5 | BLK 6:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 06 - BCT 6 | BLK 6:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 07 - BCT 1 | BLK 7:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 07 - BCT 2 | BLK 7:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 07 - BCT 3 | BLK 7:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 07 - BCT 4 | BLK 7:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 07 - BCT 5 | BLK 7:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 07 - BCT 6 | BLK 7:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 08 - BCT 1 | BLK 8:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 08 - BCT 2 | BLK 8:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 08 - BCT 3 | BLK 8:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos

## Slide 37
Civil Detailed Progress (Cont.)
Block | Activity | Scope | Completed | UOM
Block 08 - BCT 4 | BLK 8:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 08 - BCT 5 | BLK 8:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 08 - BCT 6 | BLK 8:CIV:BC - BCF - Driven Cast in-situ Piling | 64 | 64 | Nos
Block 01 - BCT 1 | BLK 1:CIV:BC - BCF - PIT & Chipping of Pile | 64 | 64 | Nos
Block 01 - BCT 2 | BLK 1:CIV:BC - BCF - PIT & Chipping of Pile | 64 | 64 | Nos

## Slide 38
Electrical Progress
Block | Activity | Scope | Completed | UOM
Block 1 - BCT 1 | BLK 1:ERE:BC - Container Erection BCT-1 | 8 | 8 | Nos
Block 1 - BCT 2 | BLK 1:ERE:BC - Container Erection BCT-2 | 8 | 8 | Nos
Block 1 - BCT 3 | BLK 1:ERE:BC - Container Erection BCT-3 | 8 | 8 | Nos
Block 1 - BCT 4 | BLK 1:ERE:BC - Container Erection BCT-4 | 8 | 8 | Nos
Block 1 - BCT 5 | BLK 1:ERE:BC - Container Erection BCT-5 | 8 | 8 | Nos
Block 1 - BCT 6 | BLK 1:ERE:BC - Container Erection BCT-6 | 8 | 8 | Nos
Block 2 - BCT 1 | BLK 2:ERE:BC - Container Erection BCT-1 | 8 | 8 | Nos
Block 2 - BCT 2 | BLK 2:ERE:BC - Container Erection BCT-2 | 8 | 8 | Nos
Block 2 - BCT 3 | BLK 2:ERE:BC - Container Erection BCT-3 | 8 | 8 | Nos
Block 2 - BCT 4 | BLK 2:ERE:BC - Container Erection BCT-4 | 8 | 8 | Nos
Block 2 - BCT 5 | BLK 2:ERE:BC - Container Erection BCT-5 | 8 | 8 | Nos
Block 2 - BCT 6 | BLK 2:ERE:BC - Container Erection BCT-6 | 8 | 8 | Nos
Block 3 - BCT 1 | BLK 3:ERE:BC - Container Erection BCT-1 | 8 | 8 | Nos
Block 3 - BCT 2 | BLK 3:ERE:BC - Container Erection BCT-2 | 8 | 8 | Nos
Block 3 - BCT 3 | BLK 3:ERE:BC - Container Erection BCT-3 | 8 | 8 | Nos

## Slide 39
Electrical Progress (Cont.)
Block | Activity | Scope | Completed | UOM
Block 3 - BCT 4 | BLK 3:ERE:BC - Container Erection BCT-4 | 8 | 8 | Nos
Block 3 - BCT 5 | BLK 3:ERE:BC - Container Erection BCT-5 | 8 | 8 | Nos
Block 3 - BCT 6 | BLK 3:ERE:BC - Container Erection BCT-6 | 8 | 8 | Nos
Block 4 - BCT 1 | BLK 4:ERE:BC - Container Erection BCT-1 | 8 | 8 | Nos
Block 4 - BCT 2 | BLK 4:ERE:BC - Container Erection BCT-2 | 8 | 8 | Nos
Block 4 - BCT 3 | BLK 4:ERE:BC - Container Erection BCT-3 | 8 | 8 | Nos
Block 4 - BCT 4 | BLK 4:ERE:BC - Container Erection BCT-4 | 8 | 8 | Nos
Block 4 - BCT 5 | BLK 4:ERE:BC - Container Erection BCT-5 | 8 | 8 | Nos
Block 4 - BCT 6 | BLK 4:ERE:BC - Container Erection BCT-6 | 8 | 8 | Nos
Block 5 - BCT 1 | BLK 5:ERE:BC - Container Erection BCT-1 | 8 | 8 | Nos
Block 5 - BCT 2 | BLK 5:ERE:BC - Container Erection BCT-2 | 8 | 8 | Nos
Block 5 - BCT 3 | BLK 5:ERE:BC - Container Erection BCT-3 | 8 | 8 | Nos
Block 5 - BCT 4 | BLK 5:ERE:BC - Container Erection BCT-4 | 8 | 8 | Nos
Block 5 - BCT 5 | BLK 5:ERE:BC - Container Erection BCT-5 | 8 | 7 | Nos
Block 5 - BCT 6 | BLK 5:ERE:BC - Container Erection BCT-6 | 8 | 8 | Nos

## Slide 40
Electrical Progress (Cont.)
Block | Activity | Scope | Completed | UOM
Block 6 - BCT 1 | BLK 6:ERE:BC - Container Erection BCT-1 | 8 | 5 | Nos
Block 6 - BCT 2 | BLK 6:ERE:BC - Container Erection BCT-2 | 8 | 4 | Nos
Block 6 - BCT 3 | BLK 6:ERE:BC - Container Erection BCT-3 | 8 | 0 | Nos
Block 6 - BCT 4 | BLK 6:ERE:BC - Container Erection BCT-4 | 8 | 0 | Nos
Block 6 - BCT 5 | BLK 6:ERE:BC - Container Erection BCT-5 | 8 | 4 | Nos
Block 6 - BCT 6 | BLK 6:ERE:BC - Container Erection BCT-6 | 8 | 5 | Nos
Block 7 - BCT 1 | BLK 7:ERE:BC - Container Erection BCT-1 | 8 | 4 | Nos
Block 7 - BCT 2 | BLK 7:ERE:BC - Container Erection BCT-2 | 8 | 4 | Nos
Block 7 - BCT 3 | BLK 7:ERE:BC - Container Erection BCT-3 | 8 | 0 | Nos
Block 7 - BCT 4 | BLK 7:ERE:BC - Container Erection BCT-4 | 8 | 0 | Nos
Block 7 - BCT 5 | BLK 7:ERE:BC - Container Erection BCT-5 | 8 | 4 | Nos
Block 7 - BCT 6 | BLK 7:ERE:BC - Container Erection BCT-6 | 8 | 4 | Nos
Block 8 - BCT 1 | BLK 8:ERE:BC - Container Erection BCT-1 | 8 | 4 | Nos
Block 8 - BCT 2 | BLK 8:ERE:BC - Container Erectionr BCT-2 | 8 | 5 | Nos
Block 8 - BCT 3 | BLK 8:ERE:BC - Container Erection BCT-3 | 8 | 2 | Nos

## Slide 41
Electrical Progress (Cont.)
Block | Activity | Scope | Completed | UOM
Block 8 - BCT 4 | BLK 8:ERE:BC - Container Erection BCT-4 | 8 | 2 | Nos
Block 8 - BCT 5 | BLK 8:ERE:BC - Container Erection BCT-5 | 8 | 4 | Nos
Block 8 - BCT 6 | BLK 8:ERE:BC - Container Erection BCT-6 | 8 | 4 | Nos
Block 1 - BCT 1 | BLK 1:ERE:PCS - PCS Erection BCT-1 | 8 | 8 | Nos
Block 1 - BCT 2 | BLK 1:ERE:PCS - PCS Erection BCT-2 | 8 | 8 | Nos