## Slide 1
Battery Energy Storage Systems
Projects : FY 2026 – 27
10th Jun 26

## Slide 2
PSS | Power | Energy | Dispatchable Energy
PSS-11 | 1080 MW | 2436 MWh | 2210 MWh
PSS-12 | 960 MW | 2166 MWh | 1963 MWh
PSS-10(B) | 600 MW | 1204 MWh | 1078 MWh
PSS-09 | 1080 MW | 2436 MWh | 2209 MWh
PSS-05(B) | 1120 MW | 2527 MWh | 2284 MWh
PSS-08(B) | 420 MW | 843 MWh | 758 MWh
Total | 5260 MW | 11612 MWh | 10502 MWh

## Slide 3
Project Capacity : 5260 MW / 11619 MWh (Dispatchable Power : 10508 MWh)
Capex NFA : Capex NFA cost INR 14758 16358 Cr. Initial proposal approved by CMN on
08-Dec-25 for PSS-11, 12, 10(B) & 03-Jan-26 for PSS-09, 05(B) & 08(B).
Revised NFAs approved on 04-Apr-26.
PPA Effective Date : Not applicable
Tariff : Merchant Capacity only
Project Location : Khavda RE Park, Gujarat
As per approved NFA_R1 (04-Apr-26) | INR (Crores)
Total | 16358
Hard Cost (Supply, Services & PMC) | 14090
Soft Cost (Pre-Ops, Financials & IDC) | 647
Land Cost | 1190
Contingency | 431
SPV | AGE27BL | AGE27CL | ARE35L | AGE27AL | ARE44L | ARE35L
PSS | 11 | 12 | 10(B) | 09 | 05(B) | 08(B)
Connectivity | 1060 | 950 | 600 | 1060 | 1097 | 410
Land Lease (Years) | Lease: 40 Years Sub-lease: 29 Yr 11 Mo (SRPL) | Lease: 40 Years Sub-lease: 29 Yr 11 Mo (SRPL) | Lease: 40 Years Sub-lease: 29 Yr 11 Mo (SRPL) | Lease: 40 Years Sub-lease: 29 Yr 11 Mo (AGEL) | Lease: 40 Years Sub-lease: 29 Yr 11 Mo (AGEL/APL) | Lease: 40 Years Sub-lease: 29 Yr 11 Mo (AGEL)
Contractors | Cemindia / MSC / / Pratibha / Synergy | Cemindia / MSC / / Akshar / DP Consteel | Cemindia / Godhara / Green Revolution MSC/ Akshar / DP Consteel | Cemindia/ MSC / / Akshar / Synergy | Cemindia/ Rajnagnechi / Icecube / DP Consteel | Cemindia/ Shreeji / Sunelec / Synergy
Salient Features
3

## Slide 4
Overall Layout
BESS-12 | 
Plot No. | S5+S6
Capacity | 960 MW / 2166 MWh
Containers | 384 Nos
Land | 70.22 Acres (In 2 parcel)
BESS-10(B) | 
Plot No. | S13R
Capacity | 600 MW / 1204 MWh
Containers | 240 Nos
Land | 39.04 Acres
BESS-11 | 
Plot No. | S8+S9
Capacity | 1080 MW / 2436 MWh
Containers | 432 Nos
Land | 69.1 Acres (In 3 Parcel)
Air Strip
BESS-09 | 
Plot No. | A17
Capacity | 1080 MW / 2436 MWh
Containers | 432 Nos
Land | 70 Acres
BESS-08(B) | 
Plot No. | A18
Capacity | 420 MW / 843 MWh
Containers | 168 Nos
Land | 31.3 Acres
BESS-05(B) | 
Plot No. | A17
Capacity | 1120 MW / 2527 MWh
Containers | 448 Nos
Land | 68.81 Acres (In 2 Parcel)

## Slide 5
Commissioning Plan
COD | PSS-11 in MWh |  | PSS-12 in MWh |  | PSS-10(B) in MWh |  | PSS-09 in MWh |  | PSS-05(B) in MWh |  | PSS-08(B) in MWh |  | Total Capacity (MWh) | 
 | (CATL) |  | (CATL) |  | (Jinko) |  | (CATL) |  | (CATL) |  | (Greatpower) |  |  | 
 | MWh | Container | MWh | Container | MWh | Container | MWh | Container | MWh | Container | MWh | Container | MWh | Container
31-Jul-26 | 542 1264 1084 | 96 224 192 | 813 | 144 | 401 481 | 80 96 |  |  |  |  |  |  | 1756 1666 1264 1565 | 320 304 224 288
20-Aug-26 |  |  |  |  | 241 | 48 |  |  |  |  |  |  | 241 | 48
31-Aug-26 | 1355 | 240 | 813 | 144 | 401 241 | 80 48 |  |  |  |  |  |  | 1214 | 224
 |  |  | 948 542 | 168 96 |  |  |  |  |  |  |  |  | 1349 1896 | 248 336
10-Sep-26 |  |  |  |  | 481 | 96 |  |  |  |  |  |  | 481 | 96
15-Sep-26 |  |  | 226 542 | 40 96 |  |  |  |  |  |  |  |  | 226 542 | 40 96
20-Sep-26 |  |  | 542 | 96 |  |  |  |  |  |  |  |  | 542 | 96
30-Sep-26 |  |  | 768 452 542 | 136 80 96 | 401 | 80 |  |  |  |  | 241 | 48 | 401 1169 692 783 | 80 216 128 144
31-Oct-26 |  |  |  |  |  |  | 271 361 1084 | 48 64 192 | 271 361 | 48 64 | 241 | 48 | 542 722 1324 | 96 128 240
30-Nov-26 |  |  |  |  |  |  | 813 677 542 | 144 120 96 | 813 677 | 144 120 | 120 | 24 | 1626 1355 662 | 288 240 120
31-Dec-26 |  |  | 542 452 | 96 80 |  |  | 813 768 813 | 144 136 144 | 813 768 1355 | 144 136 240 | 281 241 | 56 48 | 2448 2268 2408 | 440 408 432
31-Jan-27 |  |  |  |  |  |  | 542 632 | 96 112 | 632 722 1174 | 112 128 208 | 281 | 56 | 1455 1635 1174 | 264 296 208
28-Feb-27 |  |  |  |  |  |  |  |  |  |  | 281 | 56 | 281 | 56
Total | 2438 | 432 | 2167 | 384 | 1204 | 240 | 2438 | 432 | 2529 | 448 | 843 | 168 | 11619 | 2104

## Slide 6
Physical Progress : PSS 11 S-Curve [updated till 31 May 26 as per R1]
Activity | Wtg. | FTM |  | Variance in Plan Vs Actual | Variance Remark & Mitigation/Action Plan
 |  | Plan | Actual |  | 
Statutory Approvals | 2% | 2.00% | 1.25% | 0.75% | Total approvals 18; 10 approvals are Completed, 6 In progress; 2 post commissioning.
Engineering | 5% | 5.00% | 3.85% | 1.15% | Refer Slide no. 12
Ordering, Manufacturing & Supply | 38% | 37.74% | 30.02% | 7.72% | All order placed, manufacturing started. The cable deliveries were originally planned from January, but they started in February. M/s Akshar (CSS) experienced delays due to late deliveries from their sub-vendors.
Construction (Civil), Electrical, Integration & Commissioning | 55% | 34.32% | 12.41% | 21.91% | The difference between ‘Plan’ and ‘Actual’ is mainly due to insufficient / delayed deployment of manpower & Container receipt at site.
Total | 100% | 79.06% | 47.53% | 31.52% | Mitigation Plan: Expedite the efforts of the BOP Civil and ACDC contractors to increase manpower in line with the commitments in the signed MOM.
Chart: 
| 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266
Monthly Plan | 0 | 0.1188 | 0.0211 | 0.0523 | 0.0531 | 0.1952 | 0.1955 | 0.1547 | 0.1324 | 0.0417 | 0.0171 | 0.0182
Monthly Actual | 0 | 0.0365 | 0.0997 | 0.0714 | 0.0434 | 0.0503 | 0.076607 | 0.067762
Planned | 0 | 0.1188 | 0.1399 | 0.1921 | 0.2452 | 0.4404 | 0.6359 | 0.7906 | 0.923 | 0.9647 | 0.9818 | 1
Actual | 0 | 0.0365 | 0.1362 | 0.2076 | 0.251 | 0.3013 | 0.39882 | 0.47535

## Slide 7
Physical Progress : PSS 12 S-Curve [updated till 31 May 26 as per R1]
Activity | Wtg. | FTM |  | Variance in Plan Vs Actual | Variance Remark & Mitigation/Action Plan
 |  | Plan | Actual |  | 
Statutory Approvals | 2% | 1.90% | 1.23% | 0.67% | Total approvals 18; 10 approvals are Completed, 6 In progress; 2 post commissioning.
Engineering | 5% | 5.00% | 3.20% | 1.80% | Refer Slide no. 12
Ordering, Manufacturing & Supply | 38% | 33.00% | 24.14% | 8.86% | All order placed, manufacturing started. The cable deliveries were originally planned from January to February, but they started in February and continued till April at the site. M/s Akshar (CSS) faced delays due to late deliveries from their sub-vendors.
Construction (Civil), Electrical, Integration & Commissioning | 55% | 26.63% | 11.18% | 15.45% | The difference between ‘Plan’ and ‘Actual’ is mainly due to insufficient manpower deployment by the M/s MSC (BOP) contractor, along with the late mobilization of the M/s Akshar (AC DC) contractor.
Total | 100% | 66.53% | 39.75% | 26.77% | Mitigation Plan: Expedite the efforts of the BOP Civil and ACDC contractors to increase manpower in line with the commitments in the signed MOM.
Chart: 
| 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296 | 46327 | 46357 | 46388 | 46419
Monthly Plan | 0 | 0.0667 | 0.0106 | 0.0477 | 0.0848 | 0.1653 | 0.1739 | 0.1164 | 0.0565 | 0.0934 | 0.0848 | 0.0006 | 0.0013 | 0.011 | 0.0523 | 0.0219 | 0.0129
Monthly Actual | 0 | 0.0422 | 0.0601 | 0.057 | 0.0562 | 0.041 | 0.051756 | 0.065152
Cumm. Planned | 0 | 0.0667 | 0.0772 | 0.1249 | 0.2096 | 0.3749 | 0.5488 | 0.6653 | 0.7218 | 0.8151 | 0.8999 | 0.9006 | 0.9019 | 0.9129 | 0.9652 | 0.9871 | 1
Cumm. Actual | 0 | 0.0422 | 0.1023 | 0.1592 | 0.2154 | 0.2564 | 0.31572 | 0.39755

## Slide 8
Physical Progress : PSS 10B S-Curve [updated till 31 May 26 as per R1]
Activity | Wtg. | FTM |  | Variance in Plan Vs Actual | Variance Remark & Mitigation/Action Plan
 |  | Plan | Actual |  | 
Statutory Approvals | 2% | 1.96% | 1.26% | 0.70% | Total approvals 18; 10 approvals are Completed, 6 In progress; 2 post commissioning.
Engineering | 5% | 5.00% | 3.10% | 1.90% | Refer Slide no. 12
Ordering, Manufacturing & Supply | 38% | 35.50% | 24.07% | 11.43% | All order placed, manufacturing started. The cable deliveries were originally planned from January to mid February, but they started in February and continued till March end at the site and delivery of Trafo also got delayed.
Construction (Civil), Electrical, Integration & Commissioning | 55% | 27.81% | 8.14% | 19.67% | The difference between ‘Plan’ and ‘Actual’ is mainly due to delayed mobilization and insufficient manpower from the M/s Godara (BOP) contractor and M/s Akshar did not have front availability around IDTs and manpower mobilization was late and inadequate.
Total | 100% | 70.27% | 36.57% | 33.70% | Mitigation Plan: Expedite the efforts of the BOP Civil and ACDC contractors to increase manpower in line with the commitments in the signed MOM.
Chart: 
| 45962 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296
Monthly Plan | 0 | 0.1262 | 0.0081 | 0.0335 | 0.0411 | 0.1602 | 0.2166 | 0.1169 | 0.0525 | 0.076 | 0.0924 | 0.0567 | 0.0198
Monthly Actual | 0 | 0.0304 | 0.0724 | 0.072 | 0.0375 | 0.039 | 0.035317 | 0.055018
Cumm. Planned | 0 | 0.1262 | 0.1344 | 0.1679 | 0.209 | 0.3692 | 0.5858 | 0.7027 | 0.7551 | 0.8311 | 0.9236 | 0.9802 | 1
Cumm. Actual | 0 | 0.0304 | 0.1028 | 0.1748 | 0.2123 | 0.2513 | 0.29781 | 0.36567

## Slide 9
Physical Progress : PSS 9 S-Curve [updated till 31 May 26]
Activity | Wtg. | FTM |  | Variance in Plan Vs Actual | Variance Remark & Mitigation/Action Plan
 |  | Plan | Actual |  | 
Statutory Approvals | 2% | 1.80% | 1.18% | 0.62% | Total approvals 18; 9 approvals are Completed, 7 In progress; 2 post commissioning.
Engineering | 5% | 5.00% | 2.87% | 2.13% | Refer Slide no. 12
Ordering, Manufacturing & Supply | 38% | 31.89% | 15.00% | 16.89% | All order placed, manufacturing started.The cable deliveries were originally planned from January to mid Mar, but they started in March and will continue to be delivered at the site until the end of June.
Construction (Civil), Electrical, Integration & Commissioning | 55% | 27.26% | 7.18% | 20.08% | The difference between ‘Plan’ and ‘Actual’ is primarily due to late release of engineering drawings which has led to delays in site execution and insufficient manpower deployment by the M/s MSC & M/s Akshar.
Total | 100% | 65.95% | 26.23% | 39.72% | Mitigation Plan: Expedite the efforts of the BOP Civil and ACDC contractors to increase manpower in line with the commitments in the signed MOM.
Chart: 
| 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296 | 46327 | 46357 | 46388 | 46419
Monthly Plan | 0.0196 | 0.0894 | 0.0736 | 0.0877 | 0.1275 | 0.1298 | 0.1319 | 0.0493 | 0.008 | 0.0084 | 0.0171 | 0.0704 | 0.0612 | 0.0561 | 0.0523 | 0.0177
Monthly Actual | 0.0155 | 0.0279 | 0.0435 | 0.0299 | 0.042 | 0.040896 | 0.044206
Planned | 0.0196 | 0.1089 | 0.1825 | 0.2702 | 0.3978 | 0.5275 | 0.6595 | 0.7088 | 0.7168 | 0.7252 | 0.7422 | 0.8126 | 0.8739 | 0.93 | 0.9823 | 1
Actual | 0.0155 | 0.0434 | 0.0869 | 0.1168 | 0.1588 | 0.20772 | 0.26231

## Slide 10
Physical Progress : PSS 5B S-Curve [updated till 31 May 26]
Activity | Wtg. | FTM |  | Variance in Plan Vs Actual | Variance Remark & Mitigation/Action Plan
 |  | Plan | Actual |  | 
Statutory Approvals | 2% | 1.80% | 1.17% | 0.63% | Total approvals 18; 9 approvals are Completed, 7 In progress; 2 post commissioning.
Engineering | 5% | 5.00% | 2.83% | 2.17% | Refer Slide no. 12
Ordering, Manufacturing & Supply | 38% | 23.28% | 13.44% | 9.83% | All order placed, manufacturing started. The cable deliveries were originally planned from January to mid Mar, but they started in March and will continue to be delivered at the site until the end of June and M/s Akshar (CSS) got delayed due to late delivery from their sub vendors.
Construction (Civil), Electrical, Integration & Commissioning | 55% | 23.60% | 4.05% | 19.55% | The difference between ‘Plan’ and ‘Actual’ is primarily due to late release of engineering drawings which has led to delays in site execution and insufficient manpower deployment by the M/s Shree Rajnagnechi & M/s ICE CUBE.
Total | 100% | 53.68% | 21.50% | 32.18% | Mitigation Plan: Expedite the efforts of the BOP Civil and ACDC contractors to increase manpower in line with the commitments in the signed MOM.
Chart: 
| 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296 | 46327 | 46357 | 46388 | 46419
Monthly Plan | 0.019 | 0.1002 | 0.0479 | 0.0818 | 0.1211 | 0.0781 | 0.0888 | 0.0352 | 0.0436 | 0.0851 | 0.0454 | 0.0652 | 0.0569 | 0.0605 | 0.0534 | 0.018
Monthly Actual | 0.0234 | 0.0143 | 0.0651 | 0.0291 | 0.0387 | 0.022363 | 0.019655
Planned | 0.019 | 0.1191 | 0.167 | 0.2488 | 0.3699 | 0.4479 | 0.5368 | 0.572 | 0.6156 | 0.7007 | 0.7461 | 0.8113 | 0.8681 | 0.9287 | 0.982 | 1
Actual | 0.0234 | 0.0377 | 0.1027 | 0.1318 | 0.1705 | 0.1905 | 0.21495

## Slide 11
Physical Progress : PSS 8B S-Curve [updated till 31 May 26]
Activity | Wtg. | FTM |  | Variance in Plan Vs Actual | Variance Remark & Mitigation/Action Plan
 |  | Plan | Actual |  | 
Statutory Approvals | 2% | 1.80% | 1.18% | 0.62% | Total approvals 18; 9 approvals are Completed, 7 In progress; 2 post commissioning.
Engineering | 5% | 5.00% | 2.00% | 3.00% | Refer Slide no. 12
Ordering, Manufacturing & Supply | 38% | 20.00% | 13.41% | 6.59% | All order placed (Except harmonic filter), manufacturing started. The cable deliveries were originally planned from January to mid Mar, but they started in May and will continue to be delivered at the site by mid June.
Construction (Civil), Electrical, Integration & Commissioning | 55% | 22.23% | 4.90% | 17.32% | The difference between ‘Plan’ and ‘Actual’ is primarily due to late release of engineering drawings which has led to delays in site execution and insufficient manpower deployment by the M/s Shreeji & M/s SUNELEC.
Total | 100% | 49.03% | 21.50% | 27.53% | Mitigation Plan: Expedite the efforts of the BOP Civil and ACDC contractors to increase manpower in line with the commitments in the signed MOM.
Chart: 
| 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296 | 46327 | 46357 | 46388 | 46419 | 46447 | 46478
Monthly Plan | 0.0181 | 0.1078 | 0.0284 | 0.0317 | 0.1273 | 0.1041 | 0.0728 | 0.0408 | 0.0346 | 0.0402 | 0.0592 | 0.0591 | 0.0365 | 0.0736 | 0.0909 | 0.0524 | 0.0224 | 0
Monthly Actual | 0.0134 | 0.0346 | 0.052 | 0.0268 | 0.0273 | 0.014324 | 0.032641
Planned | 0.0181 | 0.1259 | 0.1543 | 0.1861 | 0.3134 | 0.4175 | 0.4903 | 0.531 | 0.5656 | 0.6058 | 0.665 | 0.7241 | 0.7606 | 0.8343 | 0.9251 | 0.9776 | 1 | 1
Actual | 0.0134 | 0.0479 | 0.0999 | 0.1267 | 0.154 | 0.17231 | 0.21503

## Slide 12: Engineering Progress : PSS 11 / PSS 12 / PSS 10B/ PSS 09/ PSS08B/ PSS05B
Description | Overall Completion | Total Docs. | Overall Status up to Mar’26 |  |  |  |  |  |  |  |  | 
 |  |  | Docs. Cum. Received | Documents Approved |  |  |  |  | Documents Under Review | Cum. Total approved | Approved % | Remarks
 |  |  |  | Cat I | Cat II | Cat III | Cat IV | Cat IV* |  |  |  | 
A | Dates | B | C | D | E | F | G | H | I | J = D + E + F + G + H | k = j / b | 
PSS-11 | 13-Apr-26 | 232 | 145 | 82 | 24 | 0 | 39 | 0 | - | 145 | 63% | -
PSS-12 | 13-Apr-26 | 243 | 92 | 53 | 4 | 0 | 35 | 0 | - | 92 | 38% | -
PSS-10B | 13-Apr-26 | 245 | 141 | 94 | 4 | 0 | 43 | 0 | - | 141 | 56% | -
PSS-08B | 20-Apr-26 | 249 | 96 | 58 | 5 | 0 | 33 | 0 | - | 96 | 39% | -
PSS-09 | 20-Apr-26 | 240 | 123 | 80 | 4 | 0 | 39 | 0 | - | 123 | 51% | -
PSS-05B | 20-Apr-26 | 246 | 103 | 60 | 5 | 0 | 38 | 0 | - | 103 | 58% | -
Cat I: Approved, Cat II: Approved with minor comments, Cat III: Not approved, Cat IV: For Information, Cat IV*:Incorporate comments and resubmit for information

## Slide 13: Procurement Status: PSS 11, 12, 10B, 9, 05B & 08B

## Slide 14: Procurement & Monthly Rolling Plan for Supply of Equipment – PSS 11
Sr. No. | Packages | Manufacturer | UOM | Scope | Ordering Completed | Balance Ordering | PO Number | PO Date | Expected Delivery at Site |  | Manufacturing Status |  | Delivered At Site | Forecast Delivery Schedule (Qty) |  | Remarks
 |  |  |  |  |  |  |  |  | Start | Finish | QAP Acceptance Date | MC Date |  | Jun-26 | Jul-26 | 
1 | Battery Container | CATL | Nos. | 432 | 432 | 0 | 5310000957 | 16-Dec-25 | 10-May-26 25-Jun-26 | 01-Jul-26 15-Jul-26 | 26 Nov 25 | 11 Feb- 26 | - | 324 | 108 | FOB for battery container PSS-11:- FOB for 16 containers :19-May FOB for 54 containers :22-May FOB for 254 containers:25-May FOB for 108 containers :15-Jun
2 | PCS | Hopewind | Set | 54 | 54 | 0 | 5310000906 | 15-Dec-25 | 5-May-26 06-Jun-26 | 25-May-26 15-Jun-26 02-Jul-26 | 8-Jan-26 | 10-Jan-26 | - | 30 | 24 | 
3 | EMS | Emerson | Set | 1 | 1 | 0 | 4510020887 | 15-Dec-25 | 13-Mar-26 15-May-26 04-Jun-26 | 6-May-26 15-May-26 15-Jun-26 | same as of phase one (28/05/25) | - | - | 1 | - | 
4 | Converter Transformer | Ornet | Nos. | 54 | 54 | 0 | 4510020943 | 17-Dec-25 | 27-Mar-26 | 29-Apr-26 30-May-26 | 25-Feb-26 | 28-Feb-26 | 54 | - | - | 
5 | CSS | M/S Akshar | Nos. | 9 | 9 | 0 | 4510021229 | 16-Jan-26 | 26-Mar-26 20-May-26 | 10-Apr-26 15-May-26 10-Jun-26 | same as of phase one (27/05/25) | - | 4 | 5 | - | 
6 | MV Switchgear | Trisquare | Nos. | 18 | 18 | 0 | 4510021080 | 30-Dec-25 | 27-Mar-26 07-Apr-26 07-May-26 | 10-Apr-26 30-Apr-26 30-May-26 08-Jun-26 | 07-Feb-26 | - | 15 | 3 | - | 
7 | HT Cable | Diamond | Kms | 74 | 74 | 0 | 4510021080 | 18-Dec-25 | 11-Feb-26 | 9-Mar-26 30-Apr-26 | 12-Jan-26 | 15-Jan-26 | 74 | Completed |  | 
8 | DC & LT Cables* | Diamond | Kms | 822 | 822 | 0 | 4510021279 | 19-Jan-26 | 28-Feb-26 | 10-Mar-26 30-Apr-26 | 12-Jan-26 | 15-Jan-26 | 822 | Completed |  | 
9 | Control Cable | Gemscab | Kms | 140 | 140 | 0 | 4510021261 | 19-Jan-26 | 28-Feb-26 | 10-Mar-26 | 15-Jan-26 | 18-Jan-26 | 140 | Completed |  | 
10 | SCADA Cable | M/s Delton & M/s Suyog | Kms | 294 | 294 | 0 | 4510021157 & 4510021163 | 8-Jan-26 | 28-Feb-26 | 10-Mar-26 15-May-26 | 8-Jan-26 | 11-Jan-26 | 294 | Completed |  | 
11 | FO Cable | Paramount | Kms | 23 | 23 | 0 | 4510021089 | 2-Jan-26 | 15-Mar-26 | 30-Mar-26 | same as of phase one (14/05/25) | - | 23 | Completed |  | 

## Slide 15: Procurement & Monthly Rolling Plan for Supply of Equipment – PSS 12
Sr. No. | Packages | Manufacturer | UOM | Scope | Ordering Completed | Balance Ordering | PO Number | PO Date | Expected Delivery at Site |  | Manufacturing Status |  | Delivered At Site | Forecast Delivery Schedule (Qty) |  |  | Remarks
 |  |  |  |  |  |  |  |  | Start | Finish | QAP Acceptance Date | MC Date |  | Jun-26 | Jul-26 | Aug-26 | 
1 | Battery Container | CATL | Nos. | 384 | 384 | 0 | 5310000958 | 16-Dec-25 | 25-May-26 01-Jul-26 1-Aug-26 20-Jul-26 | 25-Dec-26 31-Aug-26 1-Dec-26 31-Aug-26 | 26 Nov 25 | 11 Feb 26 | - | - | 304 | 80 | FOB for 104 containers – 20-Jun FOB for 104 containers – 30-Jun FOB for 88 containers – 20-Jul FOB for 88 containers – 31-Jul
2 | PCS | Inova | Set | 48 | 48 | 0 | 5310000905 | 13-Dec-25 | 10-May-26 15-May-26 13-Jun-26 | 10-Jul-26 30-Jul-26 | 7-Feb-26 | - | - | 32 | 16 |  | 
3 | EMS | Honeywell | Set | 1 | 1 | 0 | 4510020955 | 17-Dec-25 | 13-Mar-26 31-May-26 30-Jun-26 | 6-Jul-26 30-Jun-26 | 29-Jan-26 | - | - | 1 | - | - | 
4 | Converter Transformer | Tesla | Nos. | 48 | 48 | 0 | 4510020942 | 17-Dec-25 | 27-Mar-26 15-Apr-26 03-Apr-26 | 29-Apr-26 15-May-26 20-Jun-26 | 7-Feb-26 | 9-Feb-26 | 41 | 7 | - |  | 
5 | CSS | M/S Akshar | Nos. | 8 | 8 | 0 | 4510021230 | 16-Jan-26 | 20-Apr-26 01-Jun-26 | 10-May-26 31-May-26 10-Jul-26 | same as of phase one (27/05/25) | - | 4 | 3 | 1 |  | 
6 | MV Switchgear | Trisquare | Nos. | 16 | 16 | 0 | 4510021081 | 30-Dec-25 | 27-Mar-26 08-Jun-26 | 30-Apr-26 30-May-26 20-Jun-26 | - | - | - | 16 | - |  | 
7 | HT Cable | Paramount | Kms | 62 | 62 | 0 | 4510020968 | 18-Dec-25 | 7-Feb-26 | 9-Mar-26 | 15-Jan-26 | 17-Jan-26 | 62 | Completed |  |  | 
8 | DC & LT Cables | APAR & DYNAMIC | Kms | 765 | 765 | 0 | 4510021281 & 4510021288 | 19-Jan-26 | 28-Feb-26 15-Apr-26 15-Jun-26 | 10-Mar-26 30-Apr-26 30-May-26 | 15-01-2026 & 23-01-26 | 15-Feb-26 | 765 |  | - |  | 
9 | Control Cable | Gemscab | Kms | 124 | 124 | 0 | 4510021262 | 19-Jan-26 | 28-Feb-26 | 10-Mar-26 | 15-Jan-26 | 17-Jan-26 | 124 | Completed |  |  | 
10 | SCADA Cable | M/s Delton & M/s Suyog | Kms | 262 | 262 | 0 | 4510021158 | 8-Jan-26 | 20-Mar-26 15-Apr-26 05-May-26 | 30-Apr-26 15-Jun-26 | 8-Jan-26 | 10-Jan-26 | 202 | 60 |  |  | 
11 | FO Cable | Paramount | Kms | 20 | 20 | 0 | 4510021094 | 2-Jan-26 | 15-Mar-26 | 30-Mar-26 | same as of phase one (14/05/25) | - | 20 | Completed |  |  | 

## Slide 16: Procurement & Monthly Rolling Plan for Supply of Equipment – PSS 10B
Sr. No. | Packages | Manufacturer | UOM | Scope | Ordering Completed | Balance Ordering | PO Number | PO Date | Expected Delivery at Site |  | Manufacturing Status |  | Delivered At Site | Forecast Delivery Schedule (Qty) |  |  |  | Remarks
 |  |  |  |  |  |  |  |  | Start | Finish | QAP Acceptance Date | MC Date |  | Jun-26 | Jul-26 | Aug-26 | Aug-26 | 
1 | Battery Container | Jinko | Nos. | 240 | 240 | 0 | 5310000955 | 15-Dec-25 | 25-May-26 31-May-26 20-Jun-26 | 25-Jul-26 31-Jul-26 01-Aug-26 | 24 Nov 25 | 11 Feb 26 | - | 40 | 120 | 80 | 80 | FOB for 38 containers – 20-May FOB for 46 containers – 25-May FOB for 29 containers - 15-Jun FOB for 90 containers – 20-Jun FOB for 37 containers – 30-Jun
2 | PCS | Inova | Set | 30 | 30 | 0 | 5310000904 | 13-Dec-25 | 10-May-26 01-Jun-26 13-Jun-26 | 10-Jun-26 15-Jun-26 10-Jul-26 | 7-Feb-26 | 9-Feb-26 | - | 15 | 15 |  |  | 
3 | EMS | Adaptive | Set | 1 | 1 | 0 | 4510020886 | 17-Dec-25 | 13-Mar-26 31-May-26 18-Jun-26 | 20-Jun-26 18-Jun-26 | 21-May-25 | - | - | 1 |  |  |  | 
4 | Converter Transformer | Tesla & Ornet | Nos. | 30 | 30 | 0 | 4510021010 & 4510021037 | 17-Dec-25 | 27-Mar-26 30-Apr-26 | 29-Apr-26 15-May-26 15-Jun-26 | 25-Feb-26 | 27-Feb-26 | 14 | 16 |  |  |  | 
5 | CSS | M/S Akshar | Nos. | 5 | 5 | 0 | 4510021228 | 16-Jan-26 | 5-May-26 10-Jun-26 | 20-May-26 15-Jun-26 20-Jun-26 | same as of phase one (27/05/25) | 27-Feb-26 | - | 5 | - |  |  | 
6 | MV Switchgear | Trisquare | Nos. | 10 | 10 | 0 | 4510021065 | 30-Dec-25 | 27-Mar-26 07-Apr-26 01-May-26 | 10-Apr-26 30-Apr-26 30-May-26 20-Jun-26 | Under approval (07-02-26) | 9-Feb-26 | 4 | 6 |  |  |  | 
7 | HT Cable | PARAMOUNT & DYNAMIC | Kms | 62 | 62 | 0 | 4510020976 & 4510020977 | 18-Dec-25 | 28-Feb-26 15-Mar-26 15-Apr-26 12-Jun-26 | 10-Mar-26 30-Mar-26 30-May-26 12-Jun-26 | 12-Jan-26 | 14-Jan-26 | 28 | 34 |  |  |  | 
8 | DC & LT Cables | PARAMOUNT & DYNAMIC | Kms | 480 | 480 | 0 | 4510021290 & 4510021287 | 19-Jan-26 | 28-Feb-26 | 10-Mar-26 | 07-02-26 & 23-01-26 | 9-Feb-26 | 480 | - | Completed |  |  | 
9 | Control Cable | Gemscab | Kms | 78 | 78 | 0 | 4510021246 | 19-Jan-26 | 20-Feb-26 | 10-Mar-26 | 15-Jan-26 | 17-Jan-26 | 78 | - | Completed |  |  | 
10 | SCADA Cable | M/s Delton & M/s Suyog | Kms | 166 | 166 | 0 | 4510021152 & 4510021150 | 8-Jan-26 | 20-Mar-26 | 30-Apr-26 31-May26 12-Jun-26 | 8-Jan-26 | 10-Jan-26 | 160 | 6 |  |  |  | 
11 | FO Cable | Paramount | Kms | 21 | 21 | 0 | 4510021085 | 2-Jan-26 | 15-Mar-26 | 30-Mar-26 | same as of phase one (14/05/25) | 10-Feb-26 | 21 | Completed |  |  |  | 

## Slide 17: Procurement & Monthly Rolling Plan for Supply of Equipment – PSS 09
Sr. No. | Packages | Manufacturer | UOM | Scope | Ordering Completed | Balance Ordering | PO Number | PO Date | Expected Delivery at Site |  | Manufacturing Status |  | Delivered At Site | Forecast Delivery Schedule |  |  |  | Remarks
 |  |  |  |  |  |  |  |  | Start | Finish | QAP Acceptance Date | MC Date |  | Jul-26 | Aug-26 | Sep-26 | Oct-26 | 
1 | Battery Container | CATL | Nos. | 432 | 432 | 0 | 5310000937 | 1-Jan-26 | 25-Sep-26 01-Oct-26 | 25-Mar-27 31-Oct-26 1-Jan-27 31-Oct-26 | 26 Nov 25 | 11 Feb 26 | - |  |  |  | 432 | 
2 | PCS | Inova | Set | 54 | 54 | 0 | 5310000934 | 3-Jan-26 | 25-Jun-26 01-Sep-26 | 25-Aug-26 31-Oct-26 17-Dec-26 04-Oct-26 | 7-Feb-26 | 10-Feb-26 | - |  |  | 37 | 17 | 
3 | EMS | Honeywell | Set | 1 | 1 | 0 | 4510021128 | 2-Jan-26 | 04-Jun-26 31-Aug-26 | 16-May-26 31-Aug-26 1-Oct-26 31-Aug-26 | 29-Jan-26 | 30-Jan-26 | - |  | 1 |  |  | 
4 | Converter Transformer | Ornet | Nos. | 54 | 54 | 0 | 4510021210 & 4510021241 | 13-Jan-26 | 25-Apr-26 01-May-26 01-Aug-26 | 27-May-26 30-May-26 31-Aug-26 | 25-Feb-26 | 26-Feb-26 | - |  | 54 |  |  | 
5 | CSS | M/S Akshar | Nos. | 9 | 9 | 0 | 4510021227 | 16-Jan-26 | 20-May-26 16-Aug-26 | 10-Jun-26 15-Sep-26 | same as of phase one (27/05/25) | - | - |  | 5 | 4 |  | 
6 | MV Switchgear | Popular | Nos. | 18 | 18 | 0 | 4510021111 | 1-Jan-26 | 25-Apr-26 01-May-26 01-Aug-26 | 30-Apr-26 30-Jun-26 30-Aug-26 | same as of phase one (03/06/25) | - | - |  | 18 |  |  | 
7 | HT Cable | Paramount | Kms | 80 | 80 | 0 | 4510021149 | 31-Dec-25 | 28-Feb-26 | 9-Mar-26 | 15-Jan-26 | 16-Jan-26 | 80 |  | Completed |  |  | 
8 | DC & LT Cables | Diamond | Kms | 962 | 822 | 0 | 4510021289 & 4510021286 | 19-Jan-26 | 28-Feb-26 | 7-Apr-26 15-Apr-26 | 12-Jan-26 | 15-Jan-26 | 962 |  | Completed |  |  | 
9 | Control Cable | Gemscab | Kms | 140 | 140 | 0 | 4510021265 | 19-Jan-26 | 10-Mar-26 05-Apr-26 | 31-Mar-26 15-Apr-26 | 15-Jan-26 | 16-Jan-26 | 140 |  | Completed |  |  | 
10 | SCADA Cable | M/s Delton & M/s Suyog | Kms | 295 | 295 | 0 | 4510021162 & 4510021167 | 8-Jan-26 | 15-Mar-26 | 25-Mar-26 20-May-26 15-Jun-26 | 15-Jan-26 | 16-Jan-26 | 295 |  |  |  |  | 
11 | FO Cable | Paramount WestCoast | Kms | 23 | 23 | 0 | 4510021124 4510022323 | 3-Jan-26 | 15-Mar-26 15-Apr-26 01-May-26 25-Jun-26 | 30-Mar-26 30-Apr-26 31-May-26 15-Jul-26 | same as of phase one (14/05/25) | - | - | 23 | 23 | - |  | 

## Slide 18: Procurement & Monthly Rolling Plan for Supply of Equipment – PSS 05B
Sr. No. | Packages | Manufacturer | UOM | Scope | Ordering Completed | Balance Ordering | PO Number | PO Date | Expected Delivery at Site |  | Manufacturing Status |  | Delivered At Site | Forecast Delivery Schedule |  |  |  |  |  |  |  | Remarks
 |  |  |  |  |  |  |  |  | Start | Finish | QAP Acceptance Date | MC Date |  | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | 
1 | Battery Container | CATL | Nos. | 448 | 448 | 0 | 5310000938 | 1-Jan-26 | 25-Oct-26 01-Aug-26 01-Oct-26 31-Oct-26 | 25-Feb-27 20-Nov-26 1-Jan-27 | 26 Nov 25 | 11 Feb 26 |  | - | - | - | - | 84 | 100 | 136 | 128 | FOB for 15 containers – 30-Sep FOB for 140 containers – 20-Oct FOB for 132 containers – 31-Oct FOB for 161 containers – 20-Nov
2 | PCS | Shenzen | Set | 56 | 56 | 0 | 5310000936 | 2-Jan-26 | 25-Sep-26 4-Oct-26 | 25-Nov-26 31-Dec-26 29-Nov-26 | 8-Jan-26 | - |  | - | - | - |  | 23 | 33 |  | - | 
3 | EMS | Emerson | Set | 1 | 1 | 0 | 4510021125 | 2-Jan-26 | 15-Aug-26 31-Aug-26 03-Sep-26 | 25-Sep-26 1-Oct-26 03-Sep-26 | same as of phase one (28/05/25) | - |  | - | - | - | 1 |  |  | - | - | 
4 | Converter Transformer | Tesla | Nos. | 57 | 57 | 0 | 4510021192 & 4510021248 | 13-Jan-26 | 30-May-26 01-Sep-26 | 30-Sep-26 | 7-Feb-26 | 9-Feb-26 | - |  |  |  | 57 |  |  | - | - | 
5 | CSS | M/S Akshar | Nos. | 10 | 10 | 0 | 4510021226 | 16-Jan-26 | 10-Jun-26 01-Sep-26 | 25-Jul-26 30-Sep-26 | same as of phase one (27/05/25) | - | - |  |  | - | 10 | - |  | - | - | 
6 | MV Switchgear | Symatic | Nos. | 20 | 20 | 0 | 4510021115 | 1-Jan-26 | 23-Jul-26 | 30-Sep-26 | same as of phase one (21/05/25) | - | - | - | 6 | 10 | 4 | - |  | - | - | 
7 | HT Cable | Paramount & Diamond | Kms | 40 | 40 | 0 | 4510021151 | 31-Dec-25 | 28-Feb-26 31-Mar-26 | 31-Mar-26 15-Apr-26 | 15-Jan-26 | 17-Jan-26 | 40 | Completed |  |  |  |  |  |  |  | 
8 | DC & LT Cables | APAR & DYNAMIC | Kms | 1001 | 1001 | 0 | 4510021283 & 4510021285 | 19-Jan-26 | 15-Mar-26 | 15-Apr-26 30-May-26 | 15-01-2026 & 23-01-26 | 25-Jan-26 | 1001 | Completed |  |  |  |  |  |  |  | 
9 | Control Cable | Gemscab | Kms | 146 | 146 | 0 | 4510021263 | 19-Jan-26 | 10-Mar-26 | 31-Mar-26 | 15-Jan-26 | 17-Jan-26 | 146 | Completed |  |  |  |  |  |  |  | 
10 | SCADA Cable | M/s Delton & M/s Suyog | Kms | 295 | 295 | 0 | 4510021159 & 4510021165 | 8-Jan-26 | 10-Apr-26 05-May-26 | 20-Jun-26 25-Jun-26 | 8-Jan-26 | 10-Jan-26 | 92 | 203 | - | - | - | - |  | - | - | 
11 | FO Cable | Paramount WestCoast | Kms | 23 | 23 | 0 | 4510021122 | 3-Jan-26 | 15-Mar-26 15-Apr-26 01-May-26 15-Jun-26 | 30-Mar-26 30-Apr-26 30-May-26 15-Jun-26 | same as of phase one (14/05/25) | - | - | 23 | - | - | - | - |  | - | - | 

## Slide 19: Procurement & Monthly Rolling Plan for Supply of Equipment – PSS 08B
Sr. No. | Packages | Manufacturer | UOM | Scope | Ordering Completed | Balance Ordering | PO Number | PO Date | Expected Delivery at Site |  | Manufacturing Status |  | Delivered At Site | Forecast Delivery Schedule |  |  |  |  | Remarks
 |  |  |  |  |  |  |  |  | Start | Finish | QAP Acceptance Date | MC Date |  | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | 
1 | Battery Container | GreatPower | Nos. | 168 | 168 | 0 | 5310000940 | 5-Jan-26 | 10-Sep-26 31-Oct-26 17-Dec-26 31-Aug-26 | 18-Nov-26 31-Dec-26 14-Jan-27 31-Oct-26 | 17 Nov 25 | 12 Mar 26 | - | - |  | 56 | 56 | 56 | Discussed with GP and the final dispatch date is 30-Sep which can reach at site by 31-Oct-26 with no implication of LD for 30 days.
2 | PCS | Shenzen | Set | 21 | 21 | 0 | 5310000935 | 2-Jan-26 | 25-Aug-26 15-Oct-26 Nov-26 24-Aug-26 | 25-Oct-26 15-Dec-26 Jan-27 04-Oct-26 | 8-Jan-26 | 10-Jan-26 | - | - |  | 7 | 10 | 4 | 
3 | EMS | Emerson | Set | 1 | 1 | 0 | 4510021126 | 2-Jan-26 | 5-Oct-26 1-Dec-26 31-Aug-26 | 25-Oct-26 1-Dec-26 31-Aug-26 | same as of phase one (28/05/25) | - | - | - |  | 1 | - | - | 
4 | Converter Transformer | Ornet | Nos. | 21 | 21 | 0 | 4510021222 | 13-Jan-26 | 22-Sep-26 01-Aug-26 | 30-Sep-26 24-Oct-26 31-Aug-26 | 25-Feb-26 | 27-Feb-26 | - | - |  | 21 | - |  | 
5 | CSS | M/S Akshar | Nos. | 4 | 4 | 0 | 4510021225 | 16-Jan-26 | 25-Jul-26 15-Jul-26 | 30-Aug-26 15-Aug-26 | same as of phase one (27/05/25) | - | - | 2 |  | 2 | - | - | 
6 | MV Switchgear | Symatic | Nos. | 8 | 8 | 0 | 4510021119 | 1-Jan-26 | 22-Sep-26 01-Jul-26 | 24-Oct-26 31-Jul-26 | same as of phase one (21/05/25) | - | - | - | 8 | - |  |  | 
7 | HT Cable | Diamond | Kms | 40 | 40 | 0 | 4510021119 | 31-Dec-25 | 1-Apr-26 30-May-26 20-Jun-26 | 30-Apr-26 30-May 20-Jun-26 | 12-Jan-26 | 14-Jan-26 | - | 40 |  | - | - | - | 
8 | DC & LT Cables | PARAMOUNT, Diamond | Kms | 480 | 480 | 0 | 4510021280 & 4510021284 | 19-Jan-26 | 1-Apr-26 01-May-26 18-May-26 | 30-Apr-26 31-May-26 31-Jul-26 | 07-02-26 & 23-01-26 | 9-Feb-26 | 37 | 221 | 221 | - | - | - | 
9 | Control Cable | Gemscab | Kms | 55 | 55 | 0 | 4510021264 | 19-Jan-26 | 15-Apr-26 01-May-26 | 30-Apr-26 31-May-26 | 15-Jan-26 | 17-Jan-26 | 55 | Completed |  |  |  |  | 
10 | SCADA Cable | M/s Delton & M/s Suyog | Kms | 150 114.5 | 150 114.5 | 0 | 4510021160 & 4510021166 | 8-Jan-26 | 01-Apr-26 01-May-26 18-May-26 | 20-Jun-26 30-Jun-26 | 8-Jan-26 | 10-Jan-26 | 34 | 81 |  | - | - | - | 
11 | FO Cable | Paramount WestCoast | Kms | 18 | 18 | 0 | 4510021123 | 3-Jan-26 | 15-Mar-26 15-Apr-26 01-May-26 08-Jun-26 | 30-Mar-26 30-Apr-26 31-May-26 08-Jun-26 | same as of phase one (14/05/25) | - | - | 18 |  | - | - | - | 

## Slide 20
PSS-11, 12 & 10B Progress

## Slide 21
Civil Construction Progress (Plan vs Actual) (PSS-11)
 | Plan |  |  | Actual (80% plan achieved)
 | Actual (between 40% to 80% plan achieved) |  |  | Actual (below 40% plan achieved)
Chart: BOP Civil Progress pss-11
| Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | PCS | SGR | MCR | CT | CSS | BOT | NIFPS | HF
Progress | 1 | 0.65185 | 1 | 0.47556 | 1 | 0.51333 | 1 | 0.84593 | 1 | 0.26222 | 1 | 0.95 | 1 | 0 | 1 | 0
Chart: BCF Progress pss-11
| Plan | Actual | BCF
Progress | 1 | 0.9637

## Slide 22
Construction Progress (Plan VS Actual) (PSS-12)
 | Plan |  |  | Actual (80% plan achieved)
 | Actual (between 40% to 80% plan achieved) |  |  | Actual (below 40% plan achieved)
Chart: BOP Civil Progress PSS-12
| Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | PCS | SGR | MCR | CT | CSS | BOT | NIFPS | HF
Progress | 1 | 0.715 | 1 | 0.63 | 1 | 0.525 | 1 | 0.78 | 1 | 0.16375 | 1 | 0.070833 | 1 | 0 | 1 | 0
Chart: BCF Progress pss-12
| Plan | Actual | 100% | 62% | BCF
Progress | 1 | 0.615

## Slide 23
Construction Progress (Plan VS Actual) (PSS-10(B))
 | Plan |  |  | Actual (80% plan achieved)
 | Actual (between 40% to 80% plan achieved) |  |  | Actual (below 40% plan achieved)
Chart: BOP Civil Progress- PSS-10(B)
| Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | PCS | SGR | MCR | CT | CSS | BOT | NIFPS | HF
Progress | 1 | 0.246 | 1 | 0.256 | 1 | 0.156 | 1 | 0.104 | 1 | 0.032 | 1 | 0 | 1 | 0 | 1 | 0
Chart: BCF Progress-PSS-10(B)
| Plan | Actual | BCF
Progress | 1 | 0.78767

## Slide 24
PSS-09, 5B & 8B Progress

## Slide 25
Construction Progress (Plan VS Actual) (PSS-09)
 | Plan |  |  | Actual (80% plan achieved)
 | Actual (between 40% to 80% plan achieved) |  |  | Actual (below 40% plan achieved)
Chart: BOP Civil Progress-PSS-09
| Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | PCS | SGR | MCR | CT | CSS | BOT | NIFPS | HF
Progress | 1 | 0.21185 | 1 | 0.29333 | 1 | 0.38667 | 1 | 0.3863 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0
Chart: BCF Progress-PSS-09
| Plan | Actual | 100% | 44% | BCF
Progress | 1 | 0.44

## Slide 26
Construction Progress (Plan VS Actual) (PSS-05(B))
 | Plan |  |  | Actual (80% plan achieved)
 | Actual (between 40% to 80% plan achieved) |  |  | Actual (below 40% plan achieved)
Chart: BOP Civil Progress-PSS-05(B)
| Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | PCS | SGR | MCR | CT | CSS | BOT | NIFPS | HF
Progress | 1 | 0.088571 | 1 | 0.08 | 0.996 | 0.08 | 1 | 0.10179 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0
Chart: BCF Progress-PSS-05(B)
| Plan | Actual | 100% | 43% | BCF
Progress | 1 | 0.42786

## Slide 27
Construction Progress (Plan VS Actual) (PSS-08(B))
 | Plan |  |  | Actual (80% plan achieved)
 | Actual (between 40% to 80% plan achieved) |  |  | Actual (below 40% plan achieved)
Chart: BOP Civil Progress-PSS-08(B)
| Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | PCS | SGR | MCR | CT | CSS | BOT | NIFPS | HF
Progress | 1 | 0.20952 | 1 | 0.08 | 1 | 0.08 | 1 | 0.35143 | 1 | 0.08 | 1 | 0 | 1 | 0 | 1 | 0
Chart: BCF Progress-PSS-08(B)
| Plan | Actual | 100% | 34% | BCF
Progress | 1 | 0.34286

## Slide 28: Manpower Status: PSS 11, 12, 10B, 9, 05B & 08B

## Slide 29
Manpower Deployment Plan vs Actual for Overall Project Execution- PSS 11, 12, 10B, 09, 08B & 05B
Note: Shortage of Contractor’s Manpower is impacting planned completion timelines. As a result, the work timelines will get extended.
Chart: 
| Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26
PSS-11 | 3720 | 3304.6 | 10981.75 | 3495.25 | 15113 | 3318 | 15028.8 | 4395.8 | 23790 | 4965 | 19111.5 | 6424.75
PSS-12 | 1860 | 527 | 11183.25 | 2092.5 | 17591 | 2821 | 13472.6 | 4321.4 | 17407.5 | 3195 | 20243 | 7261.75
PSS-05B | 5270 | 232.5 | 6160 | 700 | 15134.2 | 1333 | 17302.5 | 2175 | 6719.25 | 1581
PSS-08B | 1867.75 | 0 | 3864 | 357 | 8450.6 | 1357.8 | 12000 | 1162.5 | 8943.5 | 1751.5
PSS-09 | 4293.5 | 240.25 | 9051 | 1057 | 18110.2 | 3850.2 | 25320 | 3530 | 6665 | 2154.5
PSS-10B | 3554.6667 | 1787.6667 | 10555.5 | 1170.25 | 12047 | 980 | 6900.6 | 899 | 8895 | 780 | 8664.5 | 1131.5
Overall Plan | 9134.6667 | 44151.75 | 63826 | 77097 | 104715 | 70346.75
Overall Actual | 5619.2667 | 7230.75 | 9233 | 16157.2 | 15807.5 | 20305

## Slide 30
Contractor Manpower Status PSS-11

## Slide 31
Contractor Manpower Status (PSS-12)

## Slide 32
Contractor Manpower Status ( PSS-10(B) )

## Slide 33
Contractor Manpower Status (PSS-09)

## Slide 34
Contractor Manpower Status PSS-05(B)

## Slide 35
Contractor Manpower Status PSS-08(B)

## Slide 36: Major Milestones – Next 3 months (PSS – 11, 12, 10B, 9, 5B, 8B)
Jun-26 | Jul-26 | Aug-26
Civil: Completion of BOP for PSS 11. Progress of BOP work for 12, 10B, 09, 05B, & 08B. Monsoon Work Completion for PSS 11, 12, 10B, 09, 05B and 08B. Completion of Roads Work for PSS 11,12,10B. Electrical: Progress of Electrical work for 11, 12, & 10B Grid Study Completion of System Studies for PSS 11, 12, 10B Approvals : PSS 11,12 & 10B: Metering Scheme approval CON-IV Delivery at Site: PSS 11 : Battery Container – 324 (CATL) PSS 11 : PCS – 288 (Hopewind) PSS 10B : Battery Container – 84 (Jinko) | Civil: Completion of BOP for PSS 12, 10B & 08B. Progress of BOP work for 05B & 09 Electrical: Progress of Electrical work for 11, 12, 10B, 05B, 08B & 09. Grid Study Completion of System Studies for PSS 05B, 08B & 09. Delivery at Site: PSS 11 : Battery Container - 108 CATL PSS 11 : PCS – 144 (Hopewind) PSS 10B : PCS - 240 (Inovance) PSS 10B : Battery Container - 156 Jinko Integration, Pre-Commissioning & Commissioning: PSS 11 : 192 Containers (1084 MWh) PSS 10B : 96 Containers (481 MWh) Approvals : PSS 11,12 & 10B: CON-V Connectivity Agreement (CON VI) | Civil: Progress of BOP for PSS 05B & 09 Electrical: Progress of Electrical work for 11, 12, 10B, 05B, 08B & 09 Delivery at Site: PSS 12 : PCS – 384 (Inovance) PSS 12 : Battery Container – 384 (CATL) Integration, Pre-Commissioning & Commissioning: PSS 10B : 48 Containers (241 MWh)

## Slide 37: CRITICAL ISSUES FY 26-27
# | Issues | Potential Impact (Time & Cost) | Corrective Action(s) | Action By |  | Current Status | Support Required
 |  |  |  | Whom | Date |  | 
1 | Inadequate Manpower (Workmen) | Slow Progress of civil works | Regular coordination meetings are being conducted with the Contractors to closely monitor progress and ensure manpower mobilization is increased in line with the required levels. Warning letters have been issued to M/s MSC and M/s Shreeji, clearly stating that failure to complete the works as per contractual timelines will entitle the Adani team to execute the balance works at the Contractor’s Risk and Cost, in accordance with the contract provisions. In addition, alternate Vendors being identified. | Site Execution & Resource team | - | Following are the Manpower available for PSS: MSC for PSS-11 148/350, PSS-12 117/350, PSS-09 55/350 Godhara for PSS-10B 28/150 Shree Rajnagnechi for PSS-05B 36/350 Shreeji for PSS-08B 15/350 | -
2 | Monsoon Plan | Work delay | Work orders for Internal Roads, Earthen Drains, and Bund construction have been awarded to multiple contractors to ensure completion before the monsoon season. | Site Execution | - | Work for Roads, Drains and Bund is expected to be completed by 10-Jun | -
3 | Completion of Grid Study & Ordering of Harmonic Filter | Can delay Commissioning | Meeting held with Senior Management of M/s Hitachi to expedite progress & completion of Grid Studies. Ordering of Harmonic Filters (once specifications are received) being expedited. | Engineering & Project Team | - | PSS 10B – Steady State and Power Quality Analysis completed. Specifications for Harmonic Filters received. Ordering Placed on 26-Mar. | -

## Slide 38
Financial S Curve PSS – 11, 12, 10B, 9, 8B & 5B [updated till 31 May 26]
 | FY-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-27
Budgeted- cumulative | 1625 | 2110 | 2770 | 4474 | 5338 | 6080 | 7036 | 8780 | 11296 | 13404 | 14773 | 16132 | 16347 | 16358
Monthly Budgeted | - | 485 | 660 | 1,705 | 863 | 743 | 956 | 1,743 | 2,516 | 2,108 | 1,369 | 1,359 | 215 | 11
Actual Cumulative | 284.91 | 538.73 | 756.5 |  |  |  |  |  |  |  |  |  |  | 
Monthly Actual | - | 253.82 | 217.77 |  |  |  |  |  |  |  |  |  |  | 
Chart: 
| FY-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-27
Monthly Budgeted | 0 | 485.1726 | 660.066 | 1704.529 | 863.144 | 742.7321 | 955.8971 | 1743.4709 | 2516.0622 | 2108.4045 | 1368.6362 | 1359.4789 | 214.8811 | 10.7351
Monthly Actual | 0 | 253.8211 | 217.773
Budgeted- cumulative | 1624.6702 | 2109.8429 | 2769.9088 | 4474.4379 | 5337.5819 | 6080.314 | 7036.2111 | 8779.682 | 11295.7442 | 13404.1487 | 14772.7849 | 16132.2638 | 16347.1449 | 16357.88
Actual Cumulative | 284.91 | 538.7311 | 756.5041

## Slide 39
Thank You

## Slide 40: Ordering Status PSS-11, 12 & 10(B)
40

## Slide 41
SN | Equipment/ Package | Qty / Scope | Final / Revised Specifications Issue Date | Verified by Engineering consultant | TBER Date | Qualified Vendors | Receipt of Offer | Commercial NFA Submission | Release of PO / SO | Update
1 | Battery Container Package | 432 NOS 384 NOS 240 NOS | 30-Oct-25 | NA | 22 Nov 25 | Offers from Svolt, Jinko, Greatpower, Sunwoda, REPT, Narada Starcharge, Hyperstrong, Cospower Hithium, CATL Lishen, Saft, BYD | 11-Nov-25 | 11-Dec-25 | 16-Dec-25 | Order issued to CATL for PSS-11 & PSS-12 on 16-Dec-25 Order issued to Jinko for PSS-10(B) on 15-Dec-25
2 | PCS (Power Conversion System) | 432 NOS 384 NOS 240 NOS | 04-Nov 25 | NA | 18-Nov-25 | Offers from Sineng Hopewind, NR Electric Inovance, Soaring Sifang, Hoymiles | 14-Nov-25 | 06-Dec-25 | 15-Dec-25 | Order issued to Hopewind for PSS-11 on 15-Dec. Order issued to INOVA for PSS-12 & PSS-10(B) on 13-Dec-25
3 | EMS (Energy Management System) | 1 NOS 1 NOS 1 NOS | 01-Nov-25 | NA | 02-Dec-25 | Adaptive, Emerson, Schenider, Honeywell | 10-Nov-25 | 11-Dec-25 | 15-Dec-25 | Order issued to Emerson on 15-Dec. Order issued to Honeywell on 17-Dec. Order issued to Adaptive on 17-Dec
4 | Converter Transformer | 54 NOS 48 NOS 30 NOS | 21-Nov-25 | NA | 11-Dec-25 | Ornet, Silchar, Atlanta,Tesla, SSE | 06-Dec-25 | 15-Dec-25 | 17-Dec-25 | Order issued to Ornet on 17-Dec. Order issued to Tesla on 17-Dec. Order issued to Ornet on 17-Dec.
5 | CSS (Auxiliary Transformer) | 9 NOS 8 NOS 5 NOS | 21-Nov-25 | NA | 26-Dec-25 | ABB, Siemens, Schneider, Akshar, Trisquare, Voltamp, Sudhir, Rhine | 10-Dec-25 | 07-Jan-26 | 16-Jan-26 | Order released to M/s Akshar on 16-Jan-26.
6 | MV Switchgear | 18 NOS 16 NOS 10 NOS | 21-Nov-25 | NA | 20-Dec-25 | RFP: Trisquare, Symatic, Popular, Technocraft | Previous approved specs | 23-Dec-25 | 30-Dec-25 | Order issued to Trisquare on 30-Dec.
7 | LT Panel - ACDB | 54 NOS 48 NOS 30 NOS | 21-Nov-25 | NA | 20-Dec-25 | RFP: Akshar, Active, ECS, Swati, Prima, Trisquare, C&S, Narkhede | Received | 23-Dec-25 | 31-Dec-25 | Order issued to Prima Automation on 31-Dec-25 for PSS-11. Order issued to Active Engineers on 31-Dec-25 for PSS-12 & PSS-10(B).
Supply ordering Status (PSS-11, 12 & 10(B)) - Completed

## Slide 42
SN | Equipment/ Package | Qty / Scope | Final / Revised Specifications Issue Date | Verified by Engineering consultant | TBER Date | Qualified Vendors | Receipt of Offer | Commercial NFA Submission | Release of PO / SO | Update
8 | HT Cable | 73.5 km 62 km 62 Km | 21-Nov-25 | NA | Previous TBER is valid | Havells, Paramount, V Marc, DICAB, UCL, Polycab,TCL | NA | 15-Dec-25 | 18-Dec-25 | Order issued to Diamond for PSS-11 on 18-Dec-25. Order issued to Paramount for PSS-12 on 18-Dec-25. Order issued to Diamond for PSS-10(B) on 18-Dec-25
9 | DC & LT Cables | 822 km 765 km 480 km | 21-Nov-25 | NA | 19-Dec-25 | Offers: PARAMOUNT, KEI, DIAMOND, VMARC, FINOLEX, DYNAMIC, GEMSCAB | 08-Dec-25 | 02-Jan-26 | 19-Jan-26 | Order issued to DIAMOND (PSS-11), APAR & DYNAMIC (PSS-12), PARAMOUNT & DYNAMIC (PSS-10(B)) dated 19-Jan-26.
10 | Control Cables | 140.4 km 124.8 km 78 km | 21-Nov-25 | NA | 19-Dec-25 | Offers: Delton, Diamond, Havells, Ravin, Special, Suyog, Polycab, Paramount, Gemscab, Dynamic, Chandresh | 06-Dec-25 | 02-Jan-26 | 19-Jan-26 | Order issued to GEMSCAB dated 19-Jan-26.
11 | SCADA Cable | 294 km 262 km 166 km | 21-Nov-25 | NA | 19-Dec-25 | Special, Paramount, Gemscab, Suyog, Delton, KEI | 18-Dec-25 | 02-Jan-26 | 08-Jan-26 | Order releases to M/s Delton & M/s Suyog dated 08-Jan-26.
12 | FO Cable | 23 km 20 km 21 km | R0: 21-Nov-25 R1: 04-Dec-25 | NA | Previous TBER is valid | Repeat order confirmation received | NA | 27-Dec-25 | 02-Jan-26 | Order issued to Paramount on 02-Jan-26
13 | Precast Supply (Monolithic Beam, Staircase, BOT and NIFPS) | 1008 NOS 896 NOS 570 NOS | 26-Nov-25 | NA | 10-Dec-25 22-Dec-25 30-Dec-25 04-Jan-26 | RFP: Buildcast, Sachi Precast, Sachi Agency, Shreeji, VAB, Fuji | 06-Dec-25 | 16-Jan-26 | 28-Jan-26 | Vendors finalized. Orders for Monolithic Beam & BOT released dated 15-Jan-26. Orders for NIFPS and Staircase for BCF, PCS & SGR released on 28-Jan.
Supply ordering Status (PSS-11, 12 & 10(B)) - Completed

## Slide 43
SN | Equipment/ Package | Qty / Scope | Final / Revised Specifications Issue Date | Verified by Engineering consultant | TBER Date | Qualified Vendors | Receipt of Offer | Commercial NFA Submission | Release of PO / SO | Update
14 | Harmonic Filter | 8 SET 8 SET 8 SET | 24-Feb-26 13-Mar-26/ 12-Mar-26/ 07-Mar-26 | - | - |  | - | 03-Apr-26 | 07-Apr-26 | Order Released for PSS-10(B) on 26-Mar. HF sizing shared for PSS-11 on 13-Mar & PSS-12 on 12-Mar. Letter of award (LOA) released for PSS-11 & PSS-12 to Hitachi on 07-Apr.
15 | High Mast | 7 NOS 7 NOS 6 NOS | 20-Jan-26 | - | 30-Jan-26 | Pratibha, Akshar, Excel Infra, Sunlake, Ompech | 06-Feb-26 | 10-Feb-26 | 27-Feb-26 | Order issued to M/s Sunelec.
16 | Fire Protection, Detection & Alarm System Package incl of (Hooter, Fire extinguisher, Panel. ) | 1 LOT | 05-Mar-26 | - | 18-Apr-26 |  | - | - | 01-May-26 | TBER concluded on 18-Apr-26; LOA released to M/s APSNP on 01-May-26.
17 | Electrical Modification in existing PSS | 1 LOT | 07-Feb-26 16-Feb-26 | - | - |  | - | 01-Apr-26 | 06-Apr-26 | Letter of award (LOA) issued to M/s Trisquare for PSS-11 & PSS-10(B) on 06-Apr-26
18 | Structural modification works in existing PSS (Containerized solution) | 1 NOS 1 NOS - | 07-Feb-26 28-Feb-26 10-Mar-26 23-Mar-26 | - | 17-Apr-26 |  | - | 14-Feb-26 27-Feb-26 08-Mar-26 31-Mar-26 14-Apr-26 17-Apr-26 | 16-Feb-26 03-Mar-26 12-Mar-26 04-Apr-26 16-Apr-26 18-Apr-26 | LOA issued to M/s RV Enterprise dated 18-Apr-26
Supply ordering Status (PSS-11, 12 & 10(B)) - Completed

## Slide 44
SN | Equipment/ Package | Qty / Scope | Final / Revised Specifications Issue Date | Verified by Engineering consultant | TBER Date | Qualified Vendors | Receipt of Offer | Commercial NFA Submission | Release of PO / SO | Update
19 | Security Porta Cabin | 3 NOS 2 NOS 1 NOS | 23-Jan-26 | - | - | Meta Steel Prefab | - | 11-Feb-26 | 24-Feb-26 | Commercial NFA approved. Order placed to Meta Steel Prefab on 24-Feb-26.
20 | Supply for FIT Kit with Hardware & Software | 1 LOT | 15-Jan-26 | - |  | Emerson, Honeywell, Adaptive |  | NA | PSS-11 & 10(B): 08-Feb-26 21-Feb-26 PSS-12: 08-Feb-26 19-Feb-26 28-Feb-26 03-Mar-26 | Supply of Kit not required, instead logistics, travel & lodging-boarding required. Commercial NFA considered along with EMS Package. Order placed for PSS-11 to Emerson on 21-Feb; PSS-10(B) to Adaptive on 17-Feb; Order for PSS-12 placed on Honeywell on 28-Feb 03-Mar.
Supply ordering Status (PSS-11, 12 & 10(B)) - Completed

## Slide 45
SN | Equipment/ Package | Qty / Scope | Final / Revised Specifications Issue Date | Verified by Engineering consultant | TBER Date | Qualified Vendors | Receipt of Offer | Commercial NFA Submission | Release of PO / SO | Update
1 | Engineering Consultancy Services | 1 LOT 1 LOT 1 LOT | 11-Nov-25 | NA | 15-Nov-25 | Fictner, Worley, Tractebel & TCE | 17-Nov-25 | 18-Nov-25 | 26-Nov-25 | Order placed to Worley for PSS-11, 12 & 10(B).
2 | ACDC Electrical works | 1 LOT 1 LOT 1 LOT | 27-Nov-25 | NA | 01-Jan-26 | Akshar | - | 10-Jan-26 | 17-Jan-26 | Order issued to M/s Pratibha for PSS-11 and M/s Akshar for PSS-12 & 10(B) dated 17-Jan-26.
3 | Grid Modelling & System Study | 1 LOT 1 LOT 1 LOT | 06-Nov-25 | NA | 15-Nov-25 | Hitachi | - | - | 24-Nov-25 | Order placed to M/s Hitachi
4 | Piling works | 32,750 m 28,444 m 21,336 m | 18-Nov-25 | NA | NA | Cemindia | - | - | 25-Nov-25 | Order placed to Cemindia
5 | Civil Works – BOP (Equip. foundations, HF, Roads-drains-fencing, Security cabin, Exist. PSS modification) | 1 LOT 1 LOT 1 LOT | 26-Nov-25 | NA | 22-Dec-25 | Shreeji, Himalaya, Rajaram&Sons, Rokane, Rathore, Nageshwar Infra, Vinayaka, HSB, DEK & Mavericks, SMP, RAVJI MANJI, NRUPUR, GODARA, DNC, MEERA, M S CHOUHAN | 10-Dec-25 | 02-Jan-26 | 30-Dec-25 | Oder issued to MS Chauhan for PSS-11 & PSS-12 on 30-Dec-25. Order issued to Godhara Infratech for PSS-10(B) on 30-Dec-25. Order issued to GP Project for Roads-Drain on 03-Jan-26
6 | Structural/PEB works | 486 MT 431 MT 270 MT | 26-Nov-25 | NA | 22-Dec-25 | RFP sent to BNAL(regret), DP Consteel, Vats group, Synergy thirlling ton | 12-Dec-25 | 23-Dec-25 | 03-Jan-26 | Oder issued to DP Consteel on 03-Jan-26
7 | Consultancy for FSPA & Fire NOC |  |  |  |  |  |  |  | 05-Jan-26 | Order for FSPA & Fire NOC consultancy placed on 05-Jan-26
8 | BESS Cloud & Integration with ENOC | 1 LOT | 16-Jan-26 |  | 30-Jan-26 12-Feb-26 | Dell, HP | - | 16-Feb-26 | 18-Feb-26 | Order issued dated 18-Feb to Dell.
Service ordering Status (PSS-11, 12 & 10(B)) - Completed

## Slide 46
Service ordering Status (PSS-11, 12 & 10(B)) - Completed
SN | Equipment/ Package | Qty / Scope | Final / Revised Specifications Issue Date | Verified by Engineering consultant | TBER Date | Qualified Vendors | Receipt of Offer | Commercial NFA Submission | Release of PO / SO | Update
9 | Transportation of Precast items (from Buildcast) | 1 LOT | NA | NA | NA | Adani Logistics | NA | NA | 17-Feb-26 | Order issued to Adani Logistics dated 17-Feb-26.
10 | Hiring for Survey team | 1 NOS | As per old specification | As per old specification | As per old specification | Vital Infratech | As per old specification | 04-Feb-26 | 04-Feb-26 | Order placed to Vital Infratech on 04-Feb-26.
11 | Farana/Crane for Stores | 6 NOS 6 NOS 3 NOS | 14-Jan-26 | - | - | - | 05-Feb-26 | 26-Feb-26 | 16-Feb-26 25-Feb-26 05-Mar-26 12-Mar-26 | Order issued to M/s SAFAR Cranes on 12-Mar-26.
12 | Mobile Lighting towers (MLT) | 3 NOS 2 NOS 2 NOS | 19-Jan-26 | - | 29-Jan-26 | Accurate Power | - | 10-Feb-26 | 16-Feb-26 | Order issued to Accurate Power dated 16-Feb-26.

## Slide 47: Ordering Status PSS-09, 05(B) & 08(B)

## Slide 48
Supply ordering Status (PSS-09, 05(B) & 08(B)) - Completed
SN | Equipment/ Package | Qty / Scope | Final / Revised Specifications Issue Date | Verified by Engineering consultant | TBER Date | Qualified Vendors | Receipt of Offer | Commercial NFA Submission | Release of PO / SO | Update
1 | Battery Container Package | 432 NOS 448 NOS 168 NOS | 30-Oct-25 | NA | Previous TBER is valid | Offers from Svolt, Jinko, Greatpower, Sunwoda, REPT, Narada Starcharge, Hyperstrong, Cospower Hithium, CATL Lishen, Saft, BYD | - | 23-Dec-25 | 05-Jan-26 | Order issued to Xiamen Ampace Technology for PSS-09 & PSS-05(B) on 01-Jan-26. Order issued to GreatPower for PSS-08(B) on 05-Jan-26.
2 | PCS (Power Conversion System) | 432 NOS 448 NOS 168 NOS | 04-Nov 25 | NA | Previous TBER is valid | Offers from Sineng Hopewind, NR Electric Inovance, Soaring Sifang, Hoymiles | - | 16-Dec-25 | 02-Jan-26 | Order issued to INOVA Automation on 02-Jan-26 Order issued to SHENZEN Hope wind Energy for PSS-05(B) & PSS-08(B) on 02-Jan-26
3 | EMS (Energy Management System) | 1 NOS 1 NOS 1 NOS | 01-Nov-25 | NA | Previous TBER is valid | Adaptive, Emerson, Schenider, Honeywell | - | 17-Dec-25 | 02-Jan-26 | Order issued to Honeywell Automation for PSS-09 on 02-Jan-26 Order issued to Emerson for PSS-05(B) & PSS-08(B) on 02-Jan-26
4 | Converter Transformer | 54 NOS 56 NOS 21 NOS | 16-Dec-25 | NA | Previous TBER is valid | Ornet, Silchar, Atlanta,Tesla, SSE | - | 25-Dec-25 | 13-Jan-26 | Order for Convertor Transformer for PSS-09 & 05(B) released on 13-Jan-26. NFA approved for PSS-08(B), IMP Power based on type test approval, else Performance based to existing vendors.
5 | CSS (Auxiliary Transformer) | 9 NOS 10 NOS 4 NOS | 16-Dec-25 | NA | 26-Dec-25 | ABB, Siemens, Schneider, Akshar, Trisquare, Voltamp, Sudhir, Rhine | 10-Dec-25 | 07-Jan-26 | 16-Jan-26 | Order released to M/s Akshar on 16-Jan-26.
6 | MV Switchgear | 18 NOS 20 NOS 08 NOS | 16-Dec-25 | NA | 20-Dec-25 | RFP: Trisquare, Symatic, Popular, Technocraft | Previous approved specs | 23-Dec-25 | 01-Jan-26 | Order issued to Popular for PSS-09 on 01-Jan-26. Order issued to Symatic for PSS-05(B) and PSS-08(B) on 01-Jan-26
7 | LT Panel - ACDB | 54 NOS 56 NOS 21 NOS | 16-Dec-25 | NA | 20-Dec-25 | RFP: Akshar, Active, ECS, Swati, Prima, Trisquare, C&S, Narkhede | Received | 23-Dec-25 | 01-Jan-26 | Order issued to Prima Automation for PSS-09 & PSS-08(B). Order issued to Active Engineer for PSS-05(B) on 01-Jan-26

## Slide 49
SN | Equipment/ Package | Qty / Scope | Final / Revised Specifications Issue Date | Verified by Engineering consultant | TBER Date | Qualified Vendors | Receipt of Offer | Commercial NFA Submission | Release of PO / SO | Update
8 | HT Cable | 80 km 171 km 40 km | 16-Dec-25 | NA | Previous TBER is valid | Havells, Paramount, V Marc, DICAB, UCL, Polycab,TCL | - | 15-Dec-25 | 31-Dec-25 | Order issued to Paramount for PSS-09 on 31-Dec-25. Order issued to Paramount & Diamond on 31-Dec-25 Order issued to Diamond for PSS-08(B) on 31-Dec-26
9 | DC & LT Cables | 962 km 1001 km 382 km | 16-Dec-25 | NA | Previous TBER is valid | Offers: PARAMOUNT, KEI, DIAMOND, VMARC, FINOLEX, DYNAMIC, GEMSCAB | - | 29-Dec-25 | 19-Jan-26 | Order issued to APAR & DYNAMIC (PSS-09), PARAMOUNT & DYNAMIC (PSS-05(B)), DIAMOND & DYNAMIC (PSS-08(B)) dated 19-Jan-26.
10 | Control Cables | 140.4 km 145.6 km 54.6 km | 16-Dec-25 | NA | Previous TBER is valid | Offers: Delton, Diamond, Havells, Ravin, Special, Suyog, Polycab, Paramount, Gemscab, Dynamic, Chandresh | - | 29-Dec-25 | 19-Jan-26 | Order issued to GEMSCAB dated 19-Jan-26.
11 | SCADA Cables | 295 km 295 km 150 km | 16-Dec-25 | NA | Previous TBER is valid | Special, Paramount, Gemscab, Suyog, Delton, KEI | - | 02-Jan-26 | 08-Jan-26 | Order releases to M/s Delton & M/s Suyog dated 08-Jan-26.
12 | FO Cable | 23 km 22.5 km 18 km | 16-Dec-25 | NA | Previous TBER is valid | Repeat order confirmation received | - | 26-Dec-25 | 03-Jan-26 | Order issued to Paramount on 03-Jan-26
13 | Precast Supply (Monolithic Beam, Staircase, BOT and NIFPS) | 1008 NOS 1046 NOS 393 NOS | 14-Dec-25 | NA | 30-Dec-25 | RFP: Buildcast, Sachi Precast, Sachi Agency, Shreeji, VAB, Fuji | - | 16-Jan-26 | 28-Jan-26 | Vendors finalized. Orders for Monolithic Beam & BOT released dated 15-Jan-26. All orders for PSS-08(B) released. Orders for NIFPS and Staircase for BCF, PCS & SGR released on 28-Jan.
Supply ordering Status (PSS-09, 05(B) & 08(B)) - Completed

## Slide 50
Supply ordering Status (PSS-09, 05(B) & 08(B))
SN | Equipment/ Package | Qty / Scope | Final / Revised Specifications Issue Date | Verified by Engineering consultant | TBER Date | Qualified Vendors | Receipt of Offer | Commercial NFA Submission | Release of PO / SO | Update
14 | Harmonic Filter | 8 SET 12 SET 8 SET | 30-Mar-26 31-Mar-26 14-Apr-26 | - | - |  | - | 10-Apr-26 18-Apr-26 27-Apr-26 05-May-26 15-May-26 | 17-Apr-26 15-Apr-26 22-Apr-26 30-Apr-26 08-May-26 16-May-26 | Order confirmation issued to Clarient for PSS-09 on 17-Apr & PSS-05(B) on 15-Apr-26. Harmonic filter sizes for For PSS-08(B) received on 14-Apr. Final BOQ details will be concluded with Vendor by 09-May EOD.
15 | High Mast | 7 NOS 7 NOS 6 NOS | 20-Jan-26 | - | 30-Jan-26 | Pratibha, Akshar, Excel Infra, Sunlake, Ompech | 06-Feb-26 | 10-Feb-26 | 27-Feb-26 | Order issued to M/s Sunelec.
16 | Fire Protection, Detection & Alarm System Package incl of (Hooter, Fire extinguisher, Panel. ) | 1 LOT | 05-Mar-26 | - | 18-Apr-26 |  | - | - | 01-May-26 | TBER concluded on 18-Apr-26; LOA released to M/s APSNP on 01-May-26.
17 | Electrical Modification in existing PSS | 1 LOT | 07-Feb-26 09-Feb-26 | - | - |  | - | 01-Apr-26 | 06-Apr-26 | Letter of award (LOA) issued to M/s Trisquare for PSS-05(B),08(B) & M/s Symatic for PSS-09, PSS-05(B) & 08(B) on 06-Apr-26
18 | Structural modification works in existing PSS (Containerized solution) | 1 NOS - - | 07-Feb-26 28-Feb-26 10-Mar-26 23-Mar-26 | - | 17-Apr-26 |  | - | 14-Feb-26 27-Feb-26 08-Mar-26 31-Mar-26 14-Apr-26 17-Apr-26 | 16-Feb-26 03-Mar-26 12-Mar-26 04-Apr-26 16-Apr-26 18-Apr-26 | LOA issued to M/s RV Enterprise dated 18-Apr-26

## Slide 51
Supply ordering Status (PSS-09, 05(B) & 08(B)) - Completed
SN | Equipment/ Package | Qty / Scope | Final / Revised Specifications Issue Date | Verified by Engineering consultant | TBER Date | Qualified Vendors | Receipt of Offer | Commercial NFA Submission | Release of PO / SO | Update
19 | Security Porta Cabin | 1 NOS 2 NOS 1 NOS | 23-Jan-26 | - | - | Meta Steel Prefab | - | 11-Feb-26 | 24-Feb-26 | Commercial NFA approved. Order placed to Meta Steel Prefab on 24-Fb-26

## Slide 52
SN | Equipment/ Package | Qty / Scope | Final / Revised Specifications Issue Date | Verified by Engineering consultant | TBER Date | Qualified Vendors | Receipt of Offer | Commercial NFA Submission | Release of PO / SO | Update
1 | Engineering Consultancy Services | 1 LOT 1 LOT 1 LOT | 25-Dec-25 | NA | 31-Dec-25 | Fictner, Worley, Tractebel & TCE | 17-Nov-25 | 01-Jan-26 | 09-Jan-26 | Revised order according to itemized breakup released on 09-Jan-26 to Worley.
2 | ACDC Electrical works | 1 LOT 1 LOT 1 LOT | 27-Nov-25 | NA | 29-Nov-25 23-Dec-25 27-Dec-25 01-Jan-26 | Akshar | - | 10-Jan-26 | 07-Feb-26 | Order issued to M/s Ice Cube for PSS-05(B) dated 17-Jan-26. Order issued for PSS-09 & 08(B) dated 07-Feb-26.
3 | Grid Modelling & System Study | 1 LOT 1 LOT 1 LOT | 06-Nov-25 | NA | 15-Nov-25 | Hitachi | - | - | 24-Nov-25 | Order placed to M/s Hitachi
4 | Piling works | 41,447 m 47,321 m 17,786 m | 18-Nov-25 | NA | NA | Cemindia | - | - | 25-Nov-25 | Order placed to Cemindia
5 | Civil Works – BOP (Equip. foundations, HF, Roads-drains-fencing, Security cabin, Exist. PSS modification) | 1 LOT 1 LOT 1 LOT | 26-Nov-25 | NA | 22-Dec-25 | Shreeji, Himalaya, Rajaram&Sons, Rokane, Rathore, Nageshwar Infra, Vinayaka, HSB, DEK & Mavericks, SMP, RAVJI MANJI, NRUPUR, GODARA, DNC, MEERA, M S CHOUHAN | 10-Dec-25 | 02-Jan-26 | PSS-09 31-Dec-25 PSS-05(B) 31-Jan-26 PSS-08(B) 03-Jan-26 | Order issued to MS Chauhan for PSS 09 on 31-Dec-25. Order issued to Rajnagnechi for PSS-05(B) on 31-Dec-25. Order issued to Shreeji Construction for PSS-08(B) on 03-Jan-26. Order issued for Roads-Drains to Odhav Enterprise for PSS-09 & PSS-08(B on 03-Jan-26. Order issued for Roads-Drains to Vaibhav Enterprise on 03-Jan-26.
6 | Structural/PEB works | 489 MT 511 MT 194 MT | 26-Nov-25 | NA | 22-Dec-25 | RFP sent to BNAL(regret), DP Consteel, Vats group, Synergy thirlling ton | 12-Dec-25 | 23-Dec-25 | 06-Feb-26 | Order issued to M/s Synergy for PSS-09, 05(B) & 08(B) on 06-Feb.
7 | Consultancy for FSPA & Fire NOC |  |  |  |  |  |  |  | 05-Jan-26 | Order for FSPA & Fire NOC consultancy placed on 05-Jan-26
Service ordering Status (PSS-09, 05(B) & 08(B)) - Completed

## Slide 53
Service ordering Status (PSS-09, 05(B) & 08(B)) - Completed
SN | Equipment/ Package | Qty / Scope | Final / Revised Specifications Issue Date | Verified by Engineering consultant | TBER Date | Qualified Vendors | Receipt of Offer | Commercial NFA Submission | Release of PO / SO | Update
8 | Transportation of Precast items (from Buildcast) | 1 LOT | NA | NA | NA | Adani Logistics | NA | NA | 17-Feb-26 | Order issued to Adani Logistics dated 17-Feb-26.
9 | Hiring for Survey team | 1 NOS | As per old specification | As per old specification | As per old specification | Vital Infratech | As per old specification | 23-Feb-26 | 05-Mar-26 | Order issued to M/s Vital Infratech on 05-Mar.
10 | Farana/Crane for Stores | 6 NOS 6 NOS 3 NOS | 14-Jan-26 | - | - | - | 05-Feb-26 | 26-Feb-26 | 16-Feb-26 25-Feb-26 05-Mar-26 12-Mar-26 | Order issued to M/s SAFAR Cranes on 12-Mar-26.
11 | Mobile Lighting towers (MLT) | 2 NOS 2 NOS 2 NOS | 19-Jan-26 | - | 29-Jan-26 | Accurate Power | - | 10-Feb-26 | 16-Feb-26 | Order issued to Accurate Power dated 16-Feb-26.

## Slide 54
Statutory & Other approvals
PSS-11, 12 & 10(B)

## Slide 55
Statutory and Other Approvals (PSS-11, 12 & 10(B))
SN | Activity Name | Responsible | Approval Authority | Baseline Start | Baseline Finish | Actual/ Forecast Start | Actual/ Forecast Finish | Remarks
1 | CLRA - Contract Labor Regulation & Abolition Act | Site IR Team | Govt. of Gujrat (Dept of Labor) | 30-Nov-25 | 13-Jan-26 | 09-Dec-25 | 13-Jan-26 05-Feb-26 30-Apr-26 May-26 Jun-26 | On account of change of labour codes, online applications are on Hold. Intimation letter issued to govt. authority that application will be done once portal is working. Letter acknowledged by govt. office.
2 | Fire Safety Plan Approval (FSPA) | Project Team | Regional Fire Officer | 15-Dec-25 | 31-Jan-26 | 17-Dec-25 | 31-Jan-26 10-Feb-26 14-Feb-26 18-Feb-26 07-Mar-26 31-Mar-26 27-Apr-26 May-26 Jun-26 | As per CPO’s discussion with RFO, online FSPA application filed on 23-May for PSS-10(B). RFO will respond on applicability in online application response.
3 | Project Import Registration | TC Team | Commissioner of Customs, Kandla | 26-Nov-25 | 25-Dec-25 | 08-Dec-25 | 25-Dec 31-Jan 28-Feb 15-Mar 27-Mar 25-Apr 04-May 13-May 18-May 21-May-26 | Approval from Customs, Mundra received on 21-May.
4 | Project Insurance | Group Insurance Team | -N.A.- | - | - | 24-Feb-26 | 01-May-26 12-May-26 23-May-26 01-Jun-26 | Project Insurance policy issued on 01-Jun.

## Slide 56
Statutory and Other Approvals (PSS-11, 12 & 10(B))
SN | Activity Name | Responsible | Approval Authority | Baseline Start | Baseline Finish | Actual/ Forecast Start | Actual/ Forecast Finish | Remarks
5 | Approval of Grid Connectivity | Asset Commissioning + BD HO Team and Delhi Office | CTU | 20-Nov-25 | 30-Nov-25 | 05-Dec-25 | 28-Feb-26 31-Mar-26 30-Apr-26 15-May-26 27-May-26 30-May-26 05-Jun-26 10-Jun-26 | Application submitted on 05-Dec-25. WR CMETS meeting completed on 22-May.
6 | Metering Scheme approval | Engineering + Asset Commissioning Team | RLDC | 23-Feb-26 | 20-Mar-26 | 23-Feb-26 31-Mar-26 30-Apr-26 15-May-26 31-May-26 10-Jun-26 | 20-Mar-26 30-Apr-26 30-May-26 30-Jun-26 | Metering Scheme application can be submitted subsequent to in principle approval from CTU for connectivity.
7 | Connectivity Agreement (Con VI) | Asset Commissioning, Engineering and Delhi Office | CTU & WRLDC | 18-Feb-26 | 20-Mar-26 | 18-Feb-26 15-Mar-26 30-May-26 08-Jun-26 | 20-Mar-26 12-Apr-26 18-Jun-26 to 10-Jul-26 (*) | Priority wise: PSS-11 > PSS-12 ~ PSS-10(B)
8 | PTCC | Asset Commissioning & Projects | CEA, Department of Telecommunications & Indian Railways & Defense | 01-Feb-26 | 24-Mar-26 | 01-Feb-26 | 24-Mar-26 15~30 days before CoD | Application submitted on 16-Feb. NOC for BSNL & Railways received. Awaited from MoD. On account of validity of provisional PTCC approval for 60 days, approvals will be aligned with 15~30 days before CoD.
9 | Intimation to Labor Inspector | Site IR Team | Govt. of Gujrat (Dept of Labor) | Post Commissioning | Post Commissioning | Post Commissioning | Post Commissioning | Intimation to Labor Inspector needs to be sent post Commissioning.
10 | Fire NOC | O&M team | Regional Fire Officer | - | - | 01-Aug-26 21-Aug-26 01-Aug-26 | 31-Aug-26 30-Sep-26 10-Sep-26 | Fire NOC needs to be obtained before Commissioning.
* Dates are considered on a very aggressive completion path as PSS-11, 12 & 10(B) is on top priority.

## Slide 57
Statutory & Other approvals
PSS-09, 05(B) & 08(B)

## Slide 58
Statutory and Other Approvals (PSS-09, 05(B) & 08(B))
SN | Activity Name | Responsible | Approval Authority | Baseline Start | Baseline Finish | Actual/ Forecast Start | Actual/ Forecast Finish | Remarks
1 | CLRA - Contract Labor Regulation & Abolition Act | Site IR Team | Govt. of Gujrat (Dept of Labor) | 25-Dec-25 | 07-Feb-26 | 25-Dec-25 | 07-Feb-26 30-Apr-26 May-26 Jun-26 | On account of change of labour codes, online applications are on Hold. Intimation letter issued to govt. authority that application will be done once portal is working. Letter acknowledged by govt. office.
2 | Implementation Support Agreement (ISA) | BD Team | Internal | 26-Dec-25 | 24-Jan-26 | 26-Dec-25 | 24-Jan-26 07-Feb-26 12-Feb-26 31-Mar-26 18-May-26 30-May-26 15-Jun-26 | Way forward methodology for optimization of GST implications agreed in-principal, sign-off in process with Business, BD & Finance. Expected ISA sign-off by 15-Jun subsequent to RPT approval.
3 | Fire Safety Plan Approval (FSPA) | Project Team | Regional Fire Officer | 01-Jan-26 | 15-Feb-26 | 01-Jan-26 | 31-Jan-26 10-Feb-26 14-Feb-26 18-Feb-26 07-Mar-26 31-Mar-26 27-Apr-26 May-26 Jun-26 | As per CPO’s discussion with RFO, online FSPA application filed on 23-May for PSS-10(B). RFO will respond on applicability in online application response.
4 | Project Import Registration | TC Team | Commissioner of Customs, Kandla | 24-Jan-26 | 22-Feb-26 | 24-Jan-26 | 22-Feb 28-Feb 15-Mar 27-Mar 25-Apr 16-May 31-May 15-Jun 26-Jun-26 | Letter from Govt. of Gujarat received on 30-Mar-26. Application for 09, 05(B) & 08(B) will be submitted by 30-May.
5 | Project Insurance | Group Insurance Team | -N.A.- | - | - | 24-Feb-26 | 01-May-26 12-May-26 23-May-26 06-Jun-26 18-Jun-26 | Project Insurance finalization expected by 06-Jun. (Under final negotiation)

## Slide 59
SN | Activity Name | Responsible | Approval Authority | Baseline Start | Baseline Finish | Actual/ Forecast Start | Actual/ Forecast Finish | Remarks
6 | Approval of Grid Connectivity | Asset Commissioning + BD HO Team and Delhi Office | CTU | 30-Dec-25 | 09-Jan-26 | 05-Dec-25 | 28-Feb-26 31-Mar-26 30-Apr-26 30-May-26 05-Jun-26 10-Jun-26 | Application submitted on 05-Dec-25. WR CMETS meeting concluded on 22-May.
7 | Metering Scheme approval | Engineering + Asset Commissioning Team | RLDC | 26-Apr-26 | 25-May-26 | 30-Apr-26 30-May-26 10-Jun-26 | 25-May-26 30-Jun-26 | Metering Scheme application can be submitted subsequent to in principle approval from CTU for connectivity.
8 | Connectivity Agreement (Con VI) | Asset Commissioning, Engineering and Delhi Office | CTU & WRLDC | 09-Apr-26 | 18-May-26 | 09-Apr 20-Apr 08-Jun-26 | 18-May-26 25-Jul-26 to 26-Aug-26 | Priority wise: PSS-08(B) > PSS-09 > PSS-05(B)
9 | PTCC | Asset Commissioning & Projects | CEA, Department of Telecommunications & Indian Railways & Defense | 25-Mar-26 | 22-May-26 | 01-Feb-26 | 22-May-26 15~30 days before CoD | Application submitted on 16-Feb. NOC for BSNL & Railways received. Awaited from MoD. On account of validity of provisional PTCC approval for 60 days, approvals will be aligned with 15~30 days before CoD.
10 | Intimation to Labor Inspector | Site IR Team | Govt. of Gujrat (Dept of Labor) | Post Commissioning | Post Commissioning | Post Commissioning | Post Commissioning | Intimation to Labor Inspector needs to be send post Commissioning.
11 | Fire NOC | O&M team | Regional Fire Officer | - | - | 01-Nov-26 01-Dec-26 01-Oct-26 | 31-Dec-26 31-Jan-27 30-Nov-26 | Fire NOC needs to be obtained before Commissioning after installation of FDAS Package.
Statutory and Other Approvals (PSS-09, 05(B) & 08(B))

## Slide 60
Battery Energy Storage Systems
Projects : FY 2025 – 26
10th Jun 26

## Slide 61
Scope
  Executive Summary
  Khavda BESS
              Salient Features and Overall Layout
              Progress Update
              Major Milestones - Next 3 Months
                Major Critical Issues
                Financial Summary
                Financing Status

## Slide 62
Executive Summary
SNo | Location | Project Name (BESS Site) | Budgeted Initial Plan Rs; Cr | Actual till date Rs; Cr. | COD |  | Overall Progress % (As per R1 Schedule) |  | Remarks
 |  |  |  |  | Plan | Expected | Plan | Actual | 
1 | GJ/ Khavda | PSS 10 | 1926.7 | 1646 | 28 Feb 26 | 28 Feb 26 28-Mar-26 10 Apr 26 5 May 26 13-May-26 (*) | 100% | 94.41% | Initial deviation in ‘Plan’ and ‘Actual’ was attributable to prolonged delays in civil works caused by persistent and heavy rainfall (approximately 1,600 mm) experienced up to early November 2025. Presently, all containers have been commissioned, with 37 Greatpower containers pending for PSS 10. The existing gap is primarily attributable to downstream activities, including contract closure, gate fixing, and contribution board installation.
2 | GJ/ Khavda | PSS 05 | 1830.6 | 1616.4 | 21 Mar 26 | 31 Mar 26 27-Mar-26 27 Apr 26 8 May 26 | 100% | 96.93% | 
3 | GJ/ Khavda | PSS 08 | 992.8 | 802.3 | 21 Mar 26 | 31 Mar 26 28-Mar-26 15 Apr26 13 May 26 | 100% | 97.30% | 
Total (Cr.) |  |  | 4750.1 | 4064.7 |  |  |  |  | 
Project Capacity : 1126 MW / 3531MWh (Dispatchable Power : 3098 MWh)
Engineering Consultant : Fichtner
Capex NFA (Rs 4750.1 Cr) : Approved on 29 May 25
*37 GP Containers Pending

## Slide 63: Salient Project Features
Project | Khavda BESS (Overall) | PSS 10 | PSS 05 | PSS 08
Project Scope/ Capacity | 1126 MW / 3531 MWh | 422.4 MW / 1444.3 MWh | 422.4 MW / 1444.3 MWh | 281.6 MW / 641.9 MWh
Owner/ Developer | ARE43L / ARE37L / ARE36L | ARE43L | ARE37L | ARE36L
Location | Khavda, Bhuj, Kutch | S5 | A14 | A18
EPC, If applicable | - | - | - | -
Land Area (Acre) | 64.2 | 25.1 | 22.8 | 16.3
Project Start Date | May-2025 | May-2025 | May-2025 | May-2025
SCOD | 31 Mar 26 | 28 Feb 26 | 31 Mar 26 15-Mar-26 | 31 Mar 26 15-Mar-26
Expected COD | 31 Mar 26 | 28 Feb 26 28 Mar 26 20-Apr-26 5-May-26 31-May-26 (*) | 31 Mar 26 27-Mar-26 27-Apr-26 11-May-26 | 31 Mar 26 10-Apr-26 27-Apr-26 15-May-26
*37 GP Containers delayed

## Slide 64
BESS Site | Capacity (MW) | Capacity (MWh) | No of Containers | Land Area (Acre)
PSS-5 | 422.40 | 1444.32 | 288 | 22.76
PSS-8 | 281.6 | 641.92 | 128 | 16.26
PSS-10 | 422.40 | 1444.32 | 288 | 25.14
Total | 1126.4 | 3530.56 | 704 | 64.16
Overall Layout at Khavda
PSS 10
PSS 5
PSS 8
Airstrip

## Slide 65
Commissioning Plan
Commercial Operation Date (COD) | PSS-10 in MWh |  | PSS-05 in MWh |  | PSS-08 in MWh |  | Total Capacity(MWh) | 
 | MWh | Containers | MWh | Containers | MWh | Containers | MWh | Containers
09-Mar-26 | 240.72 | 48 |  |  |  |  | 240.72 | 48
18-Mar-26 | 240.72 | 48 |  |  |  |  | 240.72 | 48
26-Mar-26 | 180.54 | 36 |  |  |  |  | 180.54 | 36
30-Mar-26 | 361.08 | 72 | 481.44 | 96 |  |  | 842.52 | 168
31-Mar-26 | 60.18 | 12 |  |  |  |  | 60.18 | 12
09-Apr-26 | 60.18 | 12 | 240.72 | 48 |  |  | 300.90 | 60
15-Apr-26 | 60.18 | 12 | 180.54 | 36 |  |  | 240.72 | 48
17-Apr-26 |  |  | 60.18 | 12 |  |  | 60.18 | 12
24-Apr-26 |  |  |  |  | 280.84 | 56 | 280.84 | 56
25-Apr-26 |  |  | 180.54 | 36 |  |  | 180.54 | 36
28-Apr-26 |  |  |  |  | 40.12 | 8 | 40.12 | 8
30-Apr-26 |  |  | 180.54 | 36 |  |  | 180.54 | 36
05-May-26 |  |  | 60.18 | 12 | 160.48 | 32 | 220.66 | 44
08-May-26 | 55.17 | 11 | 60.18 | 12 |  |  | 115.35 | 23
13-May-26 |  |  |  |  | 120.36 | 24 | 120.36 | 24
13-May-26 |  |  |  |  | 120.36 | 24 | 120.36 | 24
13-May-26 |  |  |  |  | 40.12 | 8 | 40.12 | 8
Cumulative COD | 1258.77 | 251 | 1444.32 | 288 | 641.92 | 128 | 3345.01 | 667
28-Feb 28-Mar May-26 Jun-26 (*) | 185.55 | 37 |  |  |  |  | 185.55 | 37
Total | 1444.32 | 288 | 1444.32 | 288 | 641.92 | 128 | 3530.56 | 704
* 37 GP containers delayed

## Slide 66
Physical Progress : PSS 10A S-Curve [updated till 31 May 26]
Activity | Wtg. | FTM |  | Variance in Plan Vs Actual | Variance Remark & Mitigation/Action Plan
 |  | Plan | Actual |  | 
Statutory Approvals | 2% | 2% | 1.94% | 0.06% | Balance approvals (Fire NOC, Intimation to Labor Inspector) after Commissioning.
Engineering | 5% | 5% | 5.00% | 0.00% | Completed
Ordering, Manufacturing & Supply | 38% | 38% | 37.34% | 0.66% | All ordering completed. Shortfall is due to deliveries of Battery Containers extended to Jun-26.
Construction (Civil), Electrical, Integration & Commissioning | 55% | 55% | 50.13% | 4.87% | The difference between ‘Plan’ and ‘Actual’ in view of the following:- Delay in Pre-Commissioning and Commissioning activities for Phase 3 Container erection, Integration, Cable laying & Cable Termination pending (in view of delay in receipt of Battery Containers). Gate fixing, Contract Closure & Project close out report are pending.
Total | 100% | 100% | 94.41% | 5.59% | Mitigation Plan: Expedite the pending delivery of battery containers and accelerate associated activities, including cable termination, integration for remaining containers.
Chart: 
| 45689 | 45717 | 45748 | 45778 | 45809 | 45839 | 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143
Monthly Plan | 0.0001 | 0.0267 | 0.0411 | 0.1131 | 0.0832 | 0.1263 | 0.024 | 0.1306 | 0.1124 | 0.1258 | 0.1044 | 0.0715 | 0.0243 | 0.0157 | 0.0008 | 0
Monthly Actual | 0.0078 | 0.0182 | 0.0406 | 0.0804 | 0.027 | 0.0365 | 0.0445 | 0.0649 | 0.0689 | 0.0657 | 0.1463 | 0.0927 | 0.079 | 0.1285 | 0.033173 | 0.011332
Month | 0.0001 | 0.0268 | 0.0679 | 0.181 | 0.2642 | 0.3905 | 0.4145 | 0.5451 | 0.6575 | 0.7833 | 0.8877 | 0.9592 | 0.9835 | 0.9992 | 1 | 1
Actual | 0.0078 | 0.0261 | 0.0667 | 0.1471 | 0.174 | 0.2106 | 0.255 | 0.3199 | 0.3888 | 0.4545 | 0.6008 | 0.6935 | 0.7725 | 0.901 | 0.93449 | 0.94407

## Slide 67
Physical Progress : PSS 5A S-Curve [updated till 31 May 26]
Activity | Wtg. | FTM |  | Variance in Plan Vs Actual | Variance Remark & Mitigation/Action Plan
 |  | Plan | Actual |  | 
Statutory Approvals | 2% | 2% | 1.94% | 0.06% | Balance approvals (Fire NOC, Intimation to Labor Inspector) after Commissioning.
Engineering | 5% | 5% | 5.00% | 0.00% | Completed
Ordering, Manufacturing & Supply | 38% | 38.00% | 38.00% | 0.00% | Completed
Construction (Civil), Electrical, Integration & Commissioning | 55% | 55% | 51.99% | 3.01% | The difference between ‘Plan’ and ‘Actual’ view following:- Gate fixing, Roads and Drains, Contract Closure & Project close out report are pending by 3.01%
Total | 100% | 100% | 96.93% | 3.07% | 
Chart: 
| 45689 | 45717 | 45748 | 45778 | 45809 | 45839 | 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143
Monthly Plan | 0.0078 | 0.019 | 0.0386 | 0.1189 | 0.1084 | 0.0687 | 0.0331 | 0.0996 | 0.0898 | 0.091 | 0.1261 | 0.0901 | 0.0678 | 0.0255 | 0.0156 | 0.0156
Monthly Actual | 0.0078 | 0.019 | 0.0435 | 0.0812 | 0.02 | 0.0178 | 0.0298 | 0.08 | 0.0401 | 0.0887 | 0.1382 | 0.0876 | 0.0569 | 0.1189 | 0.10094 | 0.020165
Planned | 0.0078 | 0.0268 | 0.0654 | 0.1843 | 0.2927 | 0.3614 | 0.3945 | 0.4941 | 0.5839 | 0.6749 | 0.801 | 0.8911 | 0.9589 | 0.9844 | 1 | 1
Actual | 0.0078 | 0.0268 | 0.0703 | 0.1515 | 0.1715 | 0.1893 | 0.2191 | 0.2991 | 0.3392 | 0.4278 | 0.566 | 0.6536 | 0.7105 | 0.8294 | 0.9494 | 0.96926

## Slide 68
Physical Progress : PSS 8A S-Curve [updated till 31 May 26]
Activity | Wtg. | FTM |  | Variance in Plan Vs Actual | Variance Remark & Mitigation/Action Plan
 |  | Plan | Actual |  | 
Statutory Approvals | 2% | 2% | 1.94% | 0.06% | Balance approvals (Fire NOC, Intimation to Labor Inspector) after Commissioning.
Engineering | 5% | 5% | 5.00% | 0.00% | Completed
Ordering, Manufacturing & Supply | 38% | 38% | 38.00% | 0.00% | Completed
Construction (Civil), Electrical, Integration & Commissioning | 55% | 55% | 52.36% | 2.64% | The difference between ‘Plan’ and ‘Actual’ view following:- Contract Closure & Project close out report are pending
Total | 100% | 100% | 97.30% | 2.70% | 
Chart: 
| 45717 | 45748 | 45778 | 45809 | 45839 | 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143
Monthly Plan | 0 | 0.02 | 0.03 | 0.05 | 0.078 | 0.0716 | 0.103 | 0.1513 | 0.1132 | 0.1005 | 0.1311 | 0.082 | 0.0693 | 0.0008 | 0.0008
Monthly Actual | 0 | 0.005 | 0.02 | 0.04 | 0.0473 | 0.0332 | 0.0045 | 0.0504 | 0.0848 | 0.1848 | 0.1301 | 0.1067 | 0.0473 | 0.10459 | 0.10786
Cumm. Planned | 0 | 0.02 | 0.05 | 0.1 | 0.178 | 0.2496 | 0.3526 | 0.5039 | 0.6171 | 0.7176 | 0.8487 | 0.9307 | 1 | 1 | 1
Cumm. Actual | 0 | 0.005 | 0.025 | 0.065 | 0.1123 | 0.1455 | 0.15 | 0.2004 | 0.2852 | 0.47 | 0.6001 | 0.7068 | 0.7541 | 0.86509 | 0.97295

## Slide 69: Engineering Progress : PSS 10 / PSS 05 / PSS 08
Description | Overall Completion | Total Docs. | Overall Status up to Feb’26 |  |  |  |  |  |  |  |  |  | 
 |  |  | Total Cum. Planned | Docs. Cum. Received | Documents Approved |  |  |  |  | Documents Under Review | Cum. Total approved | Approved % | Remarks
 |  |  |  |  | Cat I | Cat II | Cat III | Cat IV | Cat IV* |  |  |  | 
A | Dates | B | C | D | E | F | G | H | I | J | K = E + F + H + I | l = k / b | 
PSS-10 | 17-Jan-26 | 209 | 209 | 209 | 165 | - | - | 44 | - | - | 209 | 100% | -
PSS-05 | 17-Jan-26 | 223 | 223 | 223 | 183 | - | - | 40 | - | - | 223 | 100% | -
PSS-08 | 31-Jan-26 | 209 | 209 | 209 | 192 | - | - | 17 | - | - | 209 | 100% | -
Cat I: Approved, Cat II: Approved with minor comments, Cat III: Not approved, Cat IV: For Information, Cat IV*:Incorporate comments and resubmit for information

## Slide 70
Civil Plan Vs Actual Summary PSS 10 - Completed
BOP Plan Vs Actual :
BCF Plan Vs Actual :
 | Plan |  |  | Actual (80% plan achieved)
 | Actual (between 40% to 80% plan achieved) |  |  | Actual (below 40% plan achieved)
 |  | Total | Marking & Excavation | Plum concrete & PCC | Footing & column casting | Backfilling | Slab Casting | Progress
PCS | Plan | 24 | 24 | 24 | 24 | 24 | 24 | 100%
 | Actual | 24 | 24 | 24 | 24 | 24 | 24 | 100%
SGR | Plan | 4 | 4 | 4 | 4 | 4 | 4 | 100%
 | Actual | 4 | 4 | 4 | 4 | 4 | 4 | 100%
MCR | Plan | 4 | 4 | 4 | 4 | 4 | 4 | 100%
 | Actual | 4 | 4 | 4 | 4 | 4 | 4 | 100%
CT | Plan | 24 | 24 | 24 | 24 | 24 | 24 | 100%
 | Actual | 24 | 24 | 24 | 24 | 24 | 24 | 100%
CSS | Plan | 4 | 4 | 4 | 4 | 4 | 4 | 100%
 | Actual | 4 | 4 | 4 | 4 | 4 | 4 | 100%
BOT | Plan | 12 | 12 | 12 | 12 | 12 |  | 100%
 | Actual | 12 | 12 | 12 | 12 | 12 |  | 100%
NIFPS | Plan | 24 | 24 | 24 | 24 |  |  | 100%
 | Actual | 24 | 24 | 24 | 24 |  |  | 100%
 |  | Total | Marking & Excavation | Plum concrete & PCC | Column & Beam erection | Backfilling | Wet concrete | Progress
BCF Total | Plan | Plan | 288 | 288 | 288 | 288 | 288 | 288
 | Actual | Actual | 288 | 288 | 288 | 288 | 288 | 288
BCF Shreeji | Plan | Plan | 144 | 144 | 144 | 144 | 144 | 144
 | Actual | Actual | 144 | 144 | 144 | 144 | 144 | 144
BCF Radhe Radhe | Plan | Plan | 144 | 144 | 144 | 144 | 144 | 144
 | Actual | Actual | 144 | 144 | 144 | 144 | 144 | 144
Chart: BOP Civil Progress PSS-10
| Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | PCS | SGR | MCR | CT | CSS | BOT | NIFPS
Progress | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Chart: BCF Progress PSS-10
| Plan | Actual | Plan | Actual | Plan | Actual | BCF Total | BCF Shreeji | BCF Radhe Radhe/Ankit/VAB
Progress | 1 | 1 | 1 | 1 | 1 | 1

## Slide 71
Electrical Plan Vs Actual Summary PSS 10 [updated till 30 Apr 26]
 | UoM | Scope | Plan | Actual | Plan % | Actual %
HT Cable | RM | 18268 | 18268 | 18268 | 100% | 100%
Aux Cable | RM | 32500 | 32500 | 32500 | 100% | 100%
LT Cable | RM | 113360 | 113360 | 113225 | 100% | 100%
FO Cable | RM | 3546 | 3546 | 3546 | 100% | 100%
DC Cable | RM | 71558 | 71558 | 71558 | 100% | 100%
Communication Cable | RM | 24826 | 24826 | 24392 | 100% | 98%
EMS Control Cable | RM | 28306 | 28306 | 27855 | 100% | 98%
CT Control Cable | RM | 19229 | 19229 | 19229 | 100% | 100%
Chart: Electrical Progress PSS - 10
| HT Cable | Aux Cable | LT Cable | FO Cable | DC Cable | Communication Cable | EMS Control Cable | CT Control Cable
Plan % | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Actual % | 1 | 1 | 0.99881 | 1 | 1 | 0.98252 | 0.98407 | 1

## Slide 72
Civil Plan Vs Actual PSS-05 - Completed
BOP Plan Vs Actual :
BCF Plan Vs Actual :
 | Plan |  |  | Actual (80% plan achieved)
 | Actual (between 40% to 80% plan achieved) |  |  | Actual (below 40% plan achieved)
 |  | Total | Marking & Excavation | Plum concrete & PCC | Footing & column casting | Backfilling | Slab Casting | Progress
PCS | Plan | 24 | 24 | 24 | 24 | 24 | 24 | 100%
 | Actual | 24 | 24 | 24 | 24 | 24 | 24 | 100%
SGR | Plan | 6 | 4 | 4 | 4 | 4 | 6 | 100%
 | Actual | 6 | 4 | 4 | 4 | 4 | 6 | 100%
MCR | Plan | 6 | 4 | 4 | 4 | 4 | 6 | 100%
 | Actual | 6 | 4 | 4 | 4 | 4 | 6 | 100%
CT | Plan | 24 | 24 | 24 | 24 | 24 | 24 | 100%
 | Actual | 24 | 24 | 24 | 24 | 24 | 24 | 100%
CSS | Plan | 6 | 6 | 6 | 6 | 6 | 6 | 100%
 | Actual | 6 | 6 | 6 | 6 | 6 | 6 | 100%
BOT | Plan | 12 | 12 | 12 | 12 | 12 |  | 100%
 | Actual | 12 | 12 | 12 | 12 | 12 |  | 100%
NIFPS | Plan | 24 | 24 | 24 | 24 |  |  | 100%
 | Actual | 24 | 24 | 24 | 24 |  |  | 100%
 |  | Total | Marking & Excavation | Plum concrete & PCC | Column & Beam erection | Backfilling/ Welding with Pile | Wet concrete | Progress
BCF Total | Plan | 288 | 288 | 288 | 288 | 288 | 246 | 100%
 | Actual | 288 | 288 | 288 | 288 | 288 | 246 | 100%
BCF Shreeji | Plan | 120 | 120 | 120 | 120 | 120 | 120 | 100%
 | Actual | 120 | 120 | 120 | 120 | 120 | 120 | 100%
BCF RR/VAB | Plan | 126 | 126 | 126 | 126 | 126 | 126 | 100%
 | Actual | 126 | 126 | 126 | 126 | 126 | 126 | 100%
BCF Cemindia/ Ankit | Plan | 42 | 42 | 42 | 42 | 42 |  | 100%
 | Actual | 42 | 42 | 42 | 42 | 42 |  | 100%
Chart: BCF Progress PSS-05
| Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | BCF Total | BCF Shreeji | BCF RR/VAB | BCF Cemindia/Ankit
Progress | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Chart: BOP Civil Progress PSS-05
| Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | PCS | SGR | MCR | CT | CSS | BOT | NIFPS
Progress | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Slide 73
Electrical Plan Vs Actual Summary PSS 05 [updated till 30 Apr 26]
 | UoM | Scope | Plan | Actual | Plan % | Actual %
HT Cable | RM | 19572 | 19572 | 19572 | 100% | 100%
Aux Cable | RM | 33679 | 33679 | 33679 | 100% | 100%
LT Cable | RM | 102432 | 102432 | 102432 | 100% | 100%
FO Cable | RM | 5268 | 5268 | 5268 | 100% | 100%
DC Cable | RM | 77870 | 77870 | 76946 | 100% | 99%
Communication Cable | RM | 33284 | 33284 | 32889 | 100% | 99%
EMS Control Cable | RM | 31117 | 31117 | 30084 | 100% | 97%
CT Control Cable | RM | 18148 | 18148 | 17819 | 100% | 98%
Chart: Electrical Progress PSS 05
| HT Cable | Aux Cable | LT Cable | FO Cable | DC Cable | Communication Cable | EMS Control Cable | CT Control Cable
 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
 | 1 | 0.99763 | 1 | 1 | 0.98813 | 0.98813 | 0.9668 | 0.98187

## Slide 74
Civil Plan Vs Actual PSS 08 - Completed
BOP Plan Vs Actual :
BCF Plan Vs Actual :
 | Plan |  |  | Actual (80% plan achieved)
 | Actual (between 40% to 80% plan achieved) |  |  | Actual (below 40% plan achieved)
 |  | Total Scope | DCIS Piling | PIT & Pile Chipping | Footing & Column Casting | Slab Casting |  | Progress
LT Panel Found. | Plan | 16 | 16 | 16 | 16 | 16 |  | 100%
 | Actual | 16 | 16 | 16 | 16 | 16 |  | 100%
SGR | Plan | 4 | 4 | 4 | 4 | 4 |  | 100%
 | Actual | 4 | 4 | 4 | 4 | 4 |  | 100%
MCR | Plan | 4 | 4 | 4 | 4 | 4 |  | 100%
 | Actual | 4 | 4 | 4 | 4 | 4 |  | 100%
 |  | Total Scope | Excavation & PCC | Footing & Wall Casting/ Precast Installation | Backfilling | Final Lift & Rail fixing | Slab work | Progress
CT | Plan | 16 | 16 | 16 | 16 | 16 | 16 | 100%
 | Actual | 16 | 16 | 16 | 16 | 16 | 16 | 100%
CSS | Plan | 4 | 4 | 4 | 4 | - | 4 | 100%
 | Actual | 4 | 4 | 4 | 4 | - | 4 | 100%
BOT | Plan | 8 | 8 | 8 | 8 | - | - | 100%
 | Actual | 8 | 8 | 8 | 8 | - | - | 100%
NIFPS | Plan | 16 | 16 | 16 | - | - | - | 100%
 | Actual | 16 | 16 | 16 | - | - | - | 100%
 |  | Total Scope | DCIS Piling | PIT & Pile Chipping | Pile Built up | Precast erection | Progress
BCF | Plan | 128 | 128 | 128 | 128 | 128 | 100%
 | Actual | 128 | 128 | 128 | 128 | 128 | 100%
Chart: BCF Progress PSS-08
| Plan | Actual | BCF
Progress | 1 | 1
Chart: BOP Civil Progress
| Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | LT Panel Found. | SGR | MCR | CT | CSS | BOT | NIFPS
Progress | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Slide 75
Electrical Plan Vs Actual Summary PSS 08 [updated till 30 Apr 26]
 | UoM | Scope | Plan | Actual | Plan % | Actual %
HT Cable | RM | 15824 | 15824 | 15824 | 100% | 100%
Aux Cable | Nos. | 16949 | 16949 | 16949 | 100% | 100%
LT Cable | RM | 88024 | 88024 | 88024 | 100% | 100%
FO Cable | RM | 4164 | 4164 | 4164 | 100% | 100%
Communication Cable | RM | 14994 | 14994 | 14994 | 100% | 100%
EMS Control Cable | RM | 44031 | 44031 | 44031 | 100% | 100%
CT Control Cable | RM | 15824 | 15824 | 15824 | 100% | 100%
Chart: Electrical Progress PSS 08
| HT Cable | Aux Cable | LT Cable | FO Cable | Communication Cable | EMS Control Cable | CT Control Cable
Plan % | 1 | 1 | 1 | 1 | 1 | 1 | 1
Actual % | 1 | 0.9564 | 1 | 1 | 0.97499 | 0.9898 | 0.98947

## Slide 76: Major Milestones – Next 3 months (PSS – 10A, 5A & 8A)
Jun-26 | Jul-26
Civil: Completion of Roads & Gate fixing works for PSS 10, 5 & 8. Completion of Gravel filling PSS 5 & 8 Delivery at Site: Battery Container - Great Power Jinko (37). Contract Closure: Continuation of contract closure activities. Obtaining Fire NOC for PSS 10, 5 & 8. Intimation to Labour Inspector for PSS 10, 5 & 8 Completion of FAP for BESS 10,5 & 8. HOTO for PSS 10, 5 & 8. | Electrical: Completion of all Electrical works for 10. Completion of all Integration work for PSS 10. Pre-Commissioning and Commissioning activities at PSS 10 (37 Container). Commissioning: PSS 10: Commissioning of 37 Containers. Contract Closure: Completion of contract closure activities. HOTO for PSS 10 (37 Container).

## Slide 77: CRITICAL ISSUES FY 25-26
# | Issues | Potential Impact (Time & Cost) | Corrective Action(s) | Action By |  | Current Status | Support Required
 |  |  |  | Whom | Date |  | 
1 | Timely Integration and Commissioning | Commissioning Delay | M/s Geon contracted for Integration and Commissioning activities. A multi-disciplinary team consisting of members from O&M, Asset Commissioning, Project, Technology Teams formed for supervising Integration, Commissioning activities. A Commissioning App has also been created so that all activities are correctly undertaken and in the right sequence. Separate DG set installed to meet requirement of auxiliary supply. | O&M, Asset Commissioning, Project, Technology | Contracted | Manpower from M/s Geon available wef 24 Dec 2025 | -
2 | Delivery of Battery Containers has been delayed due to geopolitical tensions arising from the Iran–Israel–US conflict, resulting in disruption to international logistics and shipping movements. | Commissioning Delay for PSS-10 | Active engagement with logistics partners for expedited container release, | Logistic Team, TC Team | - | A total of 37 numbers of Great Power Battery Containers are presently held up at Jebel Ali Port (UAE), awaiting further instructions for dispatch. | -
3 | Lack of Skilled Civil & ACDC manpower led to delays in project execution. | Commissioning Delay | Specific skill set such as power engineering, control engineering, SCADA should be included in partners team. | Project | - | It will be mitigated in the next project adding skilled manpower on need basis to obviate delays to project timeline. | 

## Slide 78
Financial Progress: S Curve [updated till 31 May 26]
* Considering 667 Nos of Container & all PCS reached at site
 | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr 26 | May-26
Budgeted- cumulative | 0 | 365 | 558 | 1129 | 2391 | 3202 | 3723 | 3834 | 4185 | 4480 | 4621 | 4744 | 4750 | 4750
Actual Cash-Cumulative | 0 | 0 | 2 | 132 | 200.8 | 242.48 | 276.00 | 310 | 435 | 3084 | 3513.5 | 3744* |  | 
Actual- LC-Cumulative |  |  |  | 134.49 | 154.59 | 336.84 | 376.00 | 425 | 340.00 |  |  |  |  | 
Actual Cumulative | - | - | 2.00 | 266.49 | 355.39 | 579.32 | 651 | 735 | 775 | 3,084 | 3,514 | 3,800 | 3,843 | 4,064
Chart: 
| 45777 | 45808 | 45838 | 45869 | 45900 | 45930 | 45961 | 45991 | 46022 | 46053 | 46081 | 46112 | 46142 | 46173
Budgeted- cummulative | 0 | 365 | 558 | 1129 | 2391 | 3202 | 3723 | 3834 | 4185 | 4480 | 4621 | 4744 | 4750 | 4750
Actal Cummulative | 0 | 0 | 2 | 266.4859 | 355.3867 | 579.32 | 651.32 | 735 | 775 | 3084 | 3513.5 | 3744 | 3843 | 4064

## Slide 79
BESS Project Financing Status - Completed
Project Cost (INR Cr.) |  | Debt Equity Ratio | Lenders | Project Debt (INR Cr.) | Amount Disbursed (INR Cr.) | Balance to be disbursed (INR Cr.)
5,067 |  | 65:35 | SBI | 3,294 | 2385 | 909
Sr. | FC Aspects | Status and Remarks |  |  |  | 
1 | Financial Closure Status | Sanction letter from SBI received on 16-Jan-26. SBI has appointed M/s IRCLASS as LIE for Technical Due Diligence (“DD”) & Kaithan for Legal DD. Financing Document signed off on 19-Feb-26. |  |  |  | 
2 | Key Timelines | Data submitted to IRCLASS on 04-Feb-2026. LIE report submitted to lender. Financing Document signed off on 19-Feb-26. First Disbursement of 2385 Cr received. Further disbursement based on Project progress and expenses. |  |  |  | 
3 | Critical Points | No Pending Points |  |  |  | 

## Slide 80
Manpower Deployment Plan vs Actual PSS 10, 5 & 8 [updated till 27 Apr 26]
Note: Shortage of Contractor’s Manpower has impacted planned completion timelines. As a result, the work timelines have gotten extended.
Chart: 
| Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26
PSS10 | 4612.8 | 2802.4 | 9354.25 | 8385.5 | 12439 | 10038 | 13903.5 | 7564 | 5250 | 1282.5
PSS05 | 7111.4 | 3019.4 | 8168.5 | 5223.5 | 12600 | 6111 | 13950 | 7176.5 | 13500 | 7620
PSS08 | 6789 | 4191.2 | 9935.5 | 4758.5 | 13636 | 6237 | 11222 | 5184.75 | 10185 | 7432.5
Overall Plan | 18513.2 | 27458.25 | 38675 | 39075.5 | 28935
Overall Actual | 10013 | 18367.5 | 22386 | 19925.25 | 16335

## Slide 81
Manpower Deployment Plan vs Actual - PSS 10
Sr. No. | Description | Contractor | Forecast & Actual | Oct-25 |  |  | Nov-25 |  |  |  | Dec-25 |  |  |  |  | Jan-26 |  |  |  | Feb-26 |  |  |  | Mar-26 |  |  |  | Apr-26 |  |  |  | 
 |  |  |  | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | 27-Apr | W4
1 | ACDC | Akshar | Forecast | 23 | 33 | 44 | 74 | 123 | 130 | 65 | 67 | 138 | 140 | 125 | 171 | 171 | 260 | 298 | 298 | 390 | 390 | 390 | 390 | 390 | 390 | 390 | 390 | 200 | 100 | 100 | 100 | 50
 |  |  | Actual | 14 | 11 | 17 | 10 | 15 | 24 | 41 | 61 | 98 | 101 | 109 | 72 | 159 | 238 | 282 | 304 | 295 | 330 | 341 | 343 | 274 | 208 | 192 | 271 | 88 | 63 | 10 | 4 | 
 |  |  | Shortfall | 9 | 22 | 27 | 64 | 108 | 106 | 24 | 6 | 40 | 39 | 16 | 99 | 12 | 22 | 16 | -6 | 95 | 60 | 49 | 47 | 116 | 182 | 198 | 119 | 112 | 37 | 90 | 96 | 
2 | Structural Shed / PEB | DP Consteel / Carsfab Laxcon | Forecast |  |  |  |  |  |  |  | 20 | 20 | 25 | 30 | 8 | 30 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
 |  |  | Actual |  |  |  |  |  |  |  | 0 | 0 | 8 | 3 |  | 11 | 27 | 38 | 23 | 26 | 20 | 37 | 42 | 11 | 5 | 3 | 12 | 0 | 0 | 0 | 0 | 
 |  |  | Shortfall |  |  |  |  |  |  |  | 20 | 20 | 17 | 27 | 8 | 19 | 23 | 12 | 27 | 24 | 30 | 13 | 8 | 39 | 45 | 47 | 38 | 50 | 50 | 50 | 50 | 
Total |  |  | Forecast | 23 | 33 | 44 | 74 | 123 | 130 | 65 | 87 | 158 | 165 | 155 | 179 | 201 | 310 | 348 | 348 | 440 | 440 | 440 | 457 | 457 | 457 | 440 | 440 | 250 | 150 | 150 | 150 | 100
 |  |  | Actual | 14 | 11 | 17 | 10 | 15 | 24 | 41 | 61 | 98 | 109 | 112 | 72 | 170 | 265 | 320 | 327 | 321 | 350 | 378 | 385 | 285 | 213 | 195 | 283 | 88 | 63 | 10 | 4 | 
 |  |  | Shortfall | 9 | 22 | 27 | 64 | 108 | 106 | 24 | 26 | 60 | 56 | 43 | 107 | 31 | 45 | 28 | 21 | 119 | 90 | 62 | 55 | 155 | 227 | 245 | 157 | 162 | 87 | 140 | 146 | 
Others (Potaliya, MSC, Jay Vijay, Geon) |  |  | Actual | 180 | 158 | 180 | 163 | 205 | 210 | 288 | 302 | 261 | 311 | 255 | 186 | 162 | 137 | 109 | 74 | 77 | 75 | 47 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 
 |  |  | Total Actual | 194 | 169 | 197 | 173 | 220 | 234 | 329 | 363 | 359 | 420 | 367 | 258 | 332 | 402 | 429 | 401 | 398 | 425 | 425 | 429 | 285 | 213 | 195 | 283 | 88 | 63 | 10 | 4 | 

## Slide 82
Manpower Deployment Plan vs Actual - PSS 05
Sr. No. | Description | Contractor | Forecast & Actual | Oct-25 |  |  | Nov-25 |  |  |  | Dec-25 |  |  |  |  | Jan-26 |  |  |  | Feb-26 |  |  |  | Mar-26 |  |  |  | Apr-26 |  |  |  | 
 |  |  |  | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | 27-Apr | W4
1 | ACDC | Akshar | Forecast |  | 10 | 10 | 65 | 65 | 94 | 61 | 59 | 88 | 123 | 123 | 123 | 135 | 135 | 177 | 177 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400
 |  |  | Actual |  | 0 | 2 | 9 | 13 | 16 | 27 | 52 | 69 | 74 | 60 | 42 | 68 | 78 | 155 | 160 | 158 | 210 | 219 | 210 | 183 | 246 | 243 | 202 | 228 | 240 | 233 | 20 | 
 |  |  | Shortfall |  | 10 | 8 | 56 | 52 | 78 | 34 | 7 | 19 | 49 | 63 | 81 | 67 | 57 | 22 | 17 | 242 | 190 | 181 | 190 | 217 | 154 | 157 | 198 | 172 | 160 | 167 | 180 | 
2 | Structural Shed / PEB | DP Consteel / Carsfab Laxcon | Forecast |  |  |  |  |  |  |  | 20 | 20 | 25 | 30 | 30 | 30 | 30 | 30 | 30 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
 |  |  | Actual |  |  |  |  |  |  |  | 5 | 5 | 2 | 1 | 0 | 11 | 15 | 13 | 7 | 17 | 18 | 20 | 21 | 13 | 7 | 6 | 10 | 21 | 24 | 17 | 10 | 
 |  |  | Shortfall |  |  |  |  |  |  |  | 15 | 15 | 23 | 29 | 30 | 19 | 15 | 17 | 23 | 33 | 32 | 30 | 29 | 37 | 43 | 44 | 40 | 29 | 26 | 33 | 34 | 
Total |  |  | Forecast | 0 | 10 | 10 | 65 | 65 | 94 | 61 | 79 | 108 | 148 | 153 | 153 | 165 | 165 | 207 | 207 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450
 |  |  | Actual | 0 | 0 | 2 | 9 | 13 | 16 | 27 | 57 | 74 | 76 | 61 | 42 | 79 | 93 | 168 | 167 | 175 | 228 | 239 | 231 | 196 | 253 | 249 | 212 | 249 | 264 | 250 | 236 | 
 |  |  | Shortfall | 0 | 10 | 8 | 56 | 52 | 78 | 34 | 22 | 34 | 72 | 92 | 111 | 86 | 72 | 39 | 40 | 275 | 222 | 211 | 219 | 254 | 197 | 201 | 238 | 201 | 186 | 200 | 214 | 
Others (Sachi, Potaliya, MSC, Hitachi, Geon, JayVijay) |  |  | Actual | 121 | 107 | 125 | 92 | 115 | 143 | 194 | 145 | 145 | 170 | 150 | 136 | 112 | 90 | 78 | 56 | 61 | 78 | 71 | 53 | 24 | 21 | 19 | 16 | 0 | 0 | 0 | 0 | 
 |  |  | Total Actual | 121 | 107 | 127 | 101 | 128 | 159 | 221 | 202 | 219 | 246 | 211 | 178 | 191 | 183 | 246 | 223 | 236 | 306 | 310 | 284 | 220 | 274 | 268 | 228 | 249 | 264 | 250 | 236 | 

## Slide 83
Manpower Deployment Plan vs Actual - PSS 08
Sr. No. | Description | Contractor | Forecast & Actual | Nov-25 |  |  |  | Dec-25 |  |  |  |  | Jan-26 |  |  |  | Feb-26 |  |  |  | Mar-26 |  |  |  | Apr-26 |  |  |  | 
 |  |  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | 27-Apr | W4
1 | ACDC | Akshar | Forecast |  | 15 | 25 | 25 | 25 | 35 | 52 | 52 | 52 | 76 | 89 | 89 | 89 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300
 |  |  | Actual |  | 3 | 7 | 16 | 21 | 25 | 29 | 22 | 21 | 59 | 72 | 77 | 82 | 89 | 120 | 161 | 161 | 142 | 165 | 162 | 63 | 202 | 200 | 143 | 297 | 
 |  |  | Shortfall |  | 12 | 18 | 9 | 4 | 10 | 23 | 30 | 31 | 17 | 17 | 12 | 7 | 211 | 180 | 139 | 139 | 158 | 135 | 138 | 237 | 98 | 100 | 157 | 167 | 
2 | Harmonic Filter | Hitachi | Forecast |  |  |  |  |  |  |  |  |  | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 |  |  |  | 
 |  |  | Actual |  |  |  |  |  |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 2 | 9 | 15 | 25 | 25 | 10 |  |  |  | 
 |  |  | Shortfall |  |  |  |  |  |  |  |  |  | 30 | 30 | 30 | 30 | 30 | 30 | 18 | 28 | 21 | 15 | 5 | 5 | 20 |  |  |  | 
3 | Structural Shed / PEB | Carsfab DP Consteel / Laxcon | Forecast |  |  |  |  |  |  |  |  |  |  | 20 | 25 | 30 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
 |  |  | Actual |  |  |  |  |  |  |  |  |  |  | 0 | 0 | 4 | 0 | 0 | 0 | 3 | 10 | 16 | 19 | 7 | 16 | 26 | 25 | 28 | 
 |  |  | Shortfall |  |  |  |  |  |  |  |  |  |  | 20 | 25 | 26 | 32 | 32 | 32 | 29 | 22 | 16 | 13 | 25 | 16 | 6 | 7 | 10 | 
Total |  |  | Forecast | 0 | 15 | 25 | 25 | 25 | 35 | 52 | 52 | 52 | 106 | 139 | 144 | 149 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 332 | 332 | 332 | 332
 |  |  | Actual | 0 | 3 | 7 | 16 | 21 | 25 | 29 | 22 | 21 | 59 | 72 | 77 | 86 | 89 | 120 | 173 | 166 | 161 | 196 | 206 | 95 | 228 | 226 | 168 | 155 | 
 |  |  | Shortfall | 0 | 12 | 18 | 9 | 4 | 10 | 23 | 30 | 31 | 47 | 67 | 67 | 63 | 273 | 242 | 189 | 196 | 201 | 166 | 156 | 267 | 134 | 106 | 164 | 177 | 
Others (MSC, Jay Vijay) |  |  | Actual | 21 | 43 | 46 | 49 | 78 | 112 | 123 | 78 | 72 | 65 | 75 | 70 | 110 | 127 | 132 | 84 | 39 | 33 | 18 | 18 | 11 | 0 | 0 | 0 | 0 | 
 |  |  | Total Actual | 21 | 46 | 53 | 65 | 99 | 137 | 152 | 100 | 93 | 124 | 147 | 147 | 196 | 216 | 252 | 257 | 205 | 194 | 214 | 224 | 106 | 228 | 226 | 168 | 155 |