## Bess 11 Part Wise (hidden)
2026-05-02
Container Make | Block No. | Containers | MWH | IDT Charging / Commissioning Start | Trial-Run Start Date | COD | Status | [6 empty] | Remarks
[7 empty] | Sr. | Activity | Progress |  |  | EDC | vendor
[9 empty] | S | C | B
CATL | 1, 2, 3 & 4 | 192 | 962.88 |  |  |  | 1.1 | BCF Precast Erection & Welding | 192 | 192 | 0 |  | MSC
[7 empty] | 1.2 | Battery Container Erection | #REF! | #REF! | #REF! |  | HEFT & Pratibha
[7 empty] | 1.3 | CT Rail Fixing | 24 | 24 | 0 |  | MSC
[7 empty] | 1.4 | CT Erection | 24 | 24 | 0 |  | Pratibha
[7 empty] | 1.5 | PCS Slab casting | 24 | 24 | 0 |  | MSC
[7 empty] | 1.6 | PCS Erection | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 1.7 | ACDB Erection | 24 | 24 | 0 |  | Pratibha
[7 empty] | 1.8 | ECP Panel Erection (Communication Panel) | 24 | 12 | 12 |  | Pratibha
[7 empty] | 1.9 | PCS PEB | 24 | 24 | 0 |  | Synergy
[7 empty] | 1.1 | SGR Slab Casting | 4 | 4 | 0 |  | MSC
[7 empty] | 1.11 | HT Panel Erection | 8 | 8 | 0 |  | Pratibha
[7 empty] | 1.12 | SGR PEB | 4 | 4 | 0 |  | Synergy
[7 empty] | 1.13 | MCR Slab Casting | 4 | 4 | 0 |  | MSC
[7 empty] | 1.14 | EMS Panel Erection | 4 | 2 | 2 |  | Pratibha
[7 empty] | 1.15 | MCR PEB | 4 | 4 | 0 |  | Synergy
[7 empty] | 1.16 | CSS Slab Casting | 4 | 4 | 0 |  | MSC
[7 empty] | 1.17 | CSS Erection | 4 | 4 | 0 |  | Pratibha
[7 empty] | 1.18 | NIFPS Precast Erection | 17 | 15 | 2 |  | MSC
[7 empty] | 1.19 | NIFPS Panel Erection | 24 | 12 | 12 |  | Ornet
[7 empty] | 1.2 | NIFPS Fabrication | 24 | 12 | 12 |  | Ornet
[7 empty] | 1.21 | BOT Precast Erection | #REF! | #REF! | #REF! |  | Sachi
[7 empty] | 1.22 | BOT Slab casting | 16 | 16 | 0 |  | MSC
[7 empty] | 1.23 | HT cable laying | 31595 | 31595 | 0 |  | Pratibha
[7 empty] | 1.24 | HT cable termination | 112 | 112 | 0 |  | Pratibha
[7 empty] | 1.25 | DC & LT cable laying | 53748 | 53748 | 0 |  | Pratibha
[7 empty] | 1.26 | DC & LT cable termination | 6144 | 3072 | 3072 |  | Pratibha
[7 empty] | 1.27 | Aux, Control & communication cable laying | 32729 | 23132 | 9597 |  | Pratibha
[7 empty] | 1.28 | CT Testing | 24 | 24 | 0 |  | Pratibha
[7 empty] | 1.29 | HTP testing | 48 | 12 | 36 |  | Pratibha
[7 empty] | 1.3 | Earthing | 17921.8 | 8507.7 | 9414.1 |  | Pratibha
[7 empty] | 1.31 | LA | 40 | 10 | 30 |  | Pratibha
CATL | 5, 6, 7 & 8 | 48 | 240.72 |  |  |  | 2.1 | BCF Precast Erection & Welding | 192 | 192 | 0 |  | MSC
[7 empty] | 2.2 | Battery Container Erection | #REF! | #REF! | #REF! |  | HEFT & Pratibha
[7 empty] | 2.3 | CT Rail Fixing | 24 | 24 | 0 |  | MSC
[7 empty] | 2.4 | CT Erection | 24 | 12 | 12 |  | Pratibha
[7 empty] | 2.5 | PCS Slab casting | 24 | 24 | 0 |  | MSC
[7 empty] | 2.6 | PCS Erection | 192 | 0 | 192 |  | Pratibha
[7 empty] | 2.7 | ACDB Erection | 24 | 0 | 24 |  | Pratibha
[7 empty] | 2.8 | ECP Panel Erection (Communication Panel) | 24 | 0 | 24 |  | Pratibha
[7 empty] | 2.9 | PCS PEB | 24 | 18 | 6 |  | Synergy
[7 empty] | 2.1 | SGR Slab Casting | 4 | 4 | 0 |  | MSC
[7 empty] | 2.11 | HT Panel Erection | 8 | 0 | 8 |  | Pratibha
[7 empty] | 2.12 | SGR PEB | 4 | 0 | 4 |  | Synergy
[7 empty] | 2.13 | MCR Slab Casting | 4 | 4 | 0 |  | MSC
[7 empty] | 2.14 | EMS Panel Erection | 4 | 0 | 4 |  | Pratibha
[7 empty] | 2.15 | MCR PEB | 4 | 0 | 4 |  | Synergy
[7 empty] | 2.16 | CSS Slab Casting | 4 | 4 | 0 |  | MSC
[7 empty] | 2.17 | CSS Erection | 4 | 0 | 4 |  | Pratibha
[7 empty] | 2.18 | NIFPS Precast Erection | 12 | 12 | 0 |  | MSC
[7 empty] | 2.19 | NIFPS Panel Erection | 24 | 0 | 24 |  | Ornet
[7 empty] | 2.2 | NIFPS Fabrication | 24 | 0 | 24 |  | Ornet
[7 empty] | 2.21 | BOT Precast Erection | 24 | 24 | 0 |  | Sachi
[7 empty] | 2.22 | HT cable laying | 18554.05 | 603 | 17951.05 |  | Pratibha
[7 empty] | 2.23 | HT cable termination | 112 | 0 | 112 |  | Pratibha
[7 empty] | 2.24 | DC & LT cable laying | 57154 | 0 | 57154 |  | Pratibha
[7 empty] | 2.25 | DC & LT cable termination | 6144 | 0 | 6144 |  | Pratibha
[7 empty] | 2.26 | Aux, Control & communication cable laying | 32928 | 0 | 32928 |  | Pratibha
[7 empty] | 2.27 | CT Testing | 24 | 0 | 24 |  | Pratibha
[7 empty] | 2.28 | HTP testing | 48 | 0 | 48 |  | Pratibha
[7 empty] | 2.29 | Earthing | 17136 | 0 | 17136 |  | Pratibha
[7 empty] | 2.3 | LA | 40 | 0 | 40 |  | Pratibha
CATL | 9 | 48 | 240.72 |  |  |  | 3.1 | BCF Precast Erection & Welding | 48 | 48 | 0 |  | MSC
[7 empty] | 3.2 | Battery Container Erection | #REF! | #REF! | #REF! |  | HEFT & Pratibha
[7 empty] | 3.3 | CT Rail Fixing | 6 | 0 | 6 |  | MSC
[7 empty] | 3.4 | CT Erection | 6 | 0 | 6 |  | Pratibha
[7 empty] | 3.5 | PCS Slab casting | 6 | 3 | 3 |  | MSC
[7 empty] | 3.6 | PCS Erection | 48 | 0 | 48 |  | Pratibha
[7 empty] | 3.7 | ACDB Erection | 6 | 0 | 6 |  | Pratibha
[7 empty] | 3.8 | ECP Panel Erection (Communication Panel) | 6 | 0 | 6 |  | Pratibha
[7 empty] | 3.9 | PCS PEB | 6 | 0 | 6 |  | Synergy
[7 empty] | 3.1 | SGR Slab Casting | 1 | 0 | 1 |  | MSC
[7 empty] | 3.11 | HT Panel Erection | 2 | 0 | 2 |  | Pratibha
[7 empty] | 3.12 | SGR PEB | 1 | 0 | 1 |  | Synergy
[7 empty] | 3.13 | MCR Slab Casting | 1 | 0 | 1 |  | MSC
[7 empty] | 3.14 | EMS Panel Erection | 1 | 0 | 1 |  | Pratibha
[7 empty] | 3.15 | MCR PEB | 1 | 0 | 1 |  | Synergy
[7 empty] | 3.16 | CSS Slab Casting | 3 | 3 | 0 |  | MSC
[7 empty] | 3.17 | CSS Erection | 1 | 0 | 1 |  | Pratibha
[7 empty] | 3.18 | NIFPS Precast Erection | 1 | 0 | 1 |  | MSC
[7 empty] | 3.19 | NIFPS Panel Erection | 6 | 0 | 6 |  | Ornet
[7 empty] | 3.2 | NIFPS Fabrication | 6 | 0 | 6 |  | Ornet
[7 empty] | 3.21 | BOT Precast Erection | 6 | 0 | 6 |  | Sachi
[7 empty] | 3.22 | HT cable laying | 4518.48 | 0 | 4518.48 |  | Pratibha
[7 empty] | 3.23 | HT cable termination | 28 | 0 | 28 |  | Pratibha
[7 empty] | 3.24 | DC & LT cable laying | 14288 | 0 | 14288 |  | Pratibha
[7 empty] | 3.25 | DC & LT cable termination | 1536 | 0 | 1536 |  | Pratibha
[7 empty] | 3.26 | Aux, Control & communication cable laying | 8232 | 0 | 8232 |  | Pratibha
[7 empty] | 3.27 | CT Testing | 6 | 0 | 6 |  | Pratibha
[7 empty] | 3.28 | HTP testing | 12 | 0 | 12 |  | Pratibha
[7 empty] | 3.29 | Earthing | 4284 | 0 | 4284 |  | Pratibha
[7 empty] | 3.3 | LA | 10 | 0 | 10 |  | Pratibha

## 12 - Daily requirement (2) (hidden)
| IDT Charging / Commissioning Start | Trial-Run End Date | COD | Activity | Mandays | Days | Min. Date | 2026-06-22 | 2026-06-23 | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07 | 1900-02-08 | 1900-02-09 | 1900-02-10 | 1900-02-11 | 1900-02-12 | 1900-02-13 | 1900-02-14 | 1900-02-15 | 1900-02-16 | 1900-02-17 | 1900-02-18 | 1900-02-19 | 1900-02-20 | 1900-02-21 | 1900-02-22 | 1900-02-23 | 1900-02-24 | 1900-02-25 | 1900-02-26 | 1900-02-27 | 1900-02-28 | 1900-03-01 | 1900-03-02 | 1900-03-03 | 1900-03-04 | 1900-03-05 | 1900-03-06 | 1900-03-07 | 1900-03-08 | 1900-03-09 | 1900-03-10 | 1900-03-11 | 1900-03-12 | 1900-03-13 | 1900-03-14 | 1900-03-15 | 1900-03-16 | 1900-03-17 | 1900-03-18 | 1900-03-19 | 1900-03-20 | 1900-03-21 | 1900-03-22 | 1900-03-23 | Average Manpower | Peak Manpower | #VALUE! | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 | 2026-11-29 | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 2026-12-06 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-12 | 2026-12-13 | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-19 | 2026-12-20 | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-26 | 2026-12-27 | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31
Block 1 | 2026-07-28 | 2026-08-02 | 2026-08-05 | Erection | #VALUE! | 1 | 0 | - | - | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | #VALUE! | 1 | 0 | - | - | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | #VALUE! | 1 | 2026-07-30 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 1 | 2026-07-30 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 | 30 | 2026-07-25 | [11 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5
[7 empty] | Total | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | [45 empty] | #VALUE! | #VALUE!
Block 2 | 31 Jul 02 Aug | 05 Aug 07 Aug |  | Activity | Mandays | Days | Min. Date | 2026-06-22 | 2026-06-23 | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07 | 1900-02-08 | 1900-02-09 | 1900-02-10 | 1900-02-11 | 1900-02-12 | 1900-02-13 | 1900-02-14 | 1900-02-15 | 1900-02-16 | 1900-02-17 | 1900-02-18 | 1900-02-19 | 1900-02-20 | 1900-02-21 | 1900-02-22 | 1900-02-23 | 1900-02-24 | 1900-02-25 | 1900-02-26 | 1900-02-27 | 1900-02-28 | 1900-03-01 | 1900-03-02 | 1900-03-03 | 1900-03-04 | 1900-03-05 | 1900-03-06 | 1900-03-07 | 1900-03-08 | 1900-03-09 | 1900-03-10 | 1900-03-11 | 1900-03-12 | 1900-03-13 | 1900-03-14 | 1900-03-15 | 1900-03-16 | 1900-03-17 | 1900-03-18 | 1900-03-19 | 1900-03-20 | 1900-03-21 | 1900-03-22 | 1900-03-23
|  |  | 08 Aug 10 Aug | Erection | #VALUE! | 1 | 2026-07-26 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | #VALUE! | 1 | 2026-07-30 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | #VALUE! | 32 | 2026-07-31 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 5 | 2026-08-01 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 | 30 | #VALUE! | [13 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5
[7 empty] | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | [43 empty] | 5.814 | 30
Block 4 | 24 Jul 28 Jul | 29 Jul 02 Aug |  | Activity | Mandays | Days | Min. Date | time axis 2026-06-22 to 2026-09-15
|  |  | 01 Aug 05 Aug | Erection | #VALUE! | 1 | 0 | - | - | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | #VALUE! | 1 | 0 | - | - | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | #VALUE! | 1 | 0 | - | - | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 1 | 0 | - | - | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 | 30 | #VALUE! | 2026-07-08: 5; 2026-07-09: 5; 2026-07-10: 5; 2026-07-11: 5; 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 30; 2026-08-02: 30; 2026-08-03: 30; 2026-08-04: 30; 2026-08-05: 5; 2026-08-06: 5
[7 empty] | Total | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [27 empty] | #VALUE! | #VALUE!
Block 3 | 2026-08-06 | 2026-08-11 |  | Activity | Mandays | Days | Min. Date | time axis 2026-06-22 to 2026-09-15
|  |  | 2026-08-14 | Erection | #VALUE! | 10 | 2026-07-26 | bar: 2026-06-22 to 2026-09-15
|  |  |  | Cable Laying | #VALUE! | 1 | 2026-07-29 | bar: 2026-06-22 to 2026-09-15
|  |  |  | Termination | #VALUE! | 1 | 2026-07-29 | bar: 2026-06-22 to 2026-09-15
|  |  |  | Testing | #VALUE! | 11 | 2026-07-27 | bar: 2026-06-22 to 2026-09-15
|  |  |  | CFT | 250 | 30 | 2026-08-03 | 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 5; 2026-08-04: 5; 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 5; 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 30; 2026-08-13: 30; 2026-08-14: 30; 2026-08-15: 30; 2026-08-16: 5; 2026-08-17: 5
[7 empty] | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | [25 empty] | 4.6296 | 5
Block 5 | 2026-08-07 | 2026-08-12 |  | Activity | Mandays | Days | Min. Date | [88 empty] | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | time axis 2026-06-22 to 2026-09-15
|  |  | 2026-08-15 | Erection | #VALUE! | 6 | 2026-07-25 | [88 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Cable Laying | #VALUE! | 1 | 2026-07-30 | [88 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Termination | #VALUE! | 4 | 2026-07-30 | [88 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Testing | #VALUE! | 8 | 2026-07-28 | [88 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | CFT | 250 | 30 | 2026-08-04 | 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 5; 2026-08-04: 5; 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 5; 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 5; 2026-08-15: 30; 2026-08-16: 30; 2026-08-17: 30; 2026-08-18: 30; 2026-08-19: 5; 2026-08-20: 5
[7 empty] | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block 6 | 2026-08-24 | 2026-08-28 |  | Activity | Mandays | Days | Min. Date | [88 empty] | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | time axis 2026-06-22 to 2026-09-15
|  |  | 2026-08-31 | Erection | #VALUE! | 7 | 2026-08-02 | [88 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Cable Laying | #VALUE! | 4 | 2026-08-09 | [88 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Termination | #VALUE! | 5 | 2026-08-12 | [88 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Testing | #VALUE! | 17 | 2026-08-10 | [88 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | CFT | 250 | 30 | 2026-08-21 | 2026-08-04: 5; 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 5; 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 5; 2026-08-15: 5; 2026-08-16: 5; 2026-08-17: 5; 2026-08-18: 5; 2026-08-19: 5; 2026-08-20: 5; 2026-08-21: 5; 2026-08-22: 5; 2026-08-23: 5; 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 30; 2026-08-29: 30; 2026-08-30: 30; 2026-08-31: 30; 2026-09-01: 5; 2026-09-02: 5
[7 empty] | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block 7 | 31 Aug 17 Sep | 05 Sep 22 Sep |  | Activity | Mandays | Days | Min. Date | [88 empty] | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | time axis 2026-06-22 to 2026-09-15
|  |  | 08 Sep 25 Sep | Erection | #VALUE! | 29 | 2026-08-03 | [88 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Cable Laying | #VALUE! | 6 | 2026-08-04 | [88 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Termination | #VALUE! | 27 | 2026-08-14 | [88 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Testing | #VALUE! | 35 | 2026-08-11 | [88 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | CFT | 250 | 30 | #VALUE! | 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 5; 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 5; 2026-08-15: 5; 2026-08-16: 5; 2026-08-17: 5; 2026-08-18: 5; 2026-08-19: 5; 2026-08-20: 5; 2026-08-21: 5; 2026-08-22: 5; 2026-08-23: 5; 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 5; 2026-08-29: 5; 2026-08-30: 5; 2026-08-31: 30; 2026-09-01: 30; 2026-09-02: 30; 2026-09-03: 30; 2026-09-04: 5; 2026-09-05: 5
[7 empty] | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block 8 | 11 Sep 17 Sep | 16 Sep 22 Sep |  | Activity | Mandays | Days | Min. Date | [88 empty] | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | time axis 2026-06-22 to 2026-09-15
|  |  | 19 Sep 25 Sep | Erection | #VALUE! | 37 | 2026-08-05 | [88 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Cable Laying | #VALUE! | 11 | 2026-08-12 | [88 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Termination | #VALUE! | 18 | 2026-08-28 | [88 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Testing | #VALUE! | 32 | 2026-08-14 | [88 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | CFT | 250 | 30 | #VALUE! | 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 5; 2026-08-15: 5; 2026-08-16: 5; 2026-08-17: 5; 2026-08-18: 5; 2026-08-19: 5; 2026-08-20: 5; 2026-08-21: 5; 2026-08-22: 5; 2026-08-23: 5; 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 5; 2026-08-29: 5; 2026-08-30: 5; 2026-08-31: 5; 2026-09-01: 5; 2026-09-02: 5; 2026-09-03: 30; 2026-09-04: 30; 2026-09-05: 30; 2026-09-06: 30; 2026-09-07: 5; 2026-09-08: 5
[7 empty] | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 10B - Daily requirement (2) (hidden)
| IDT Charging / Commissioning Start | Trial-Run End Date | COD | Activity | Mandays | Days | Min. Date | time axis 2026-06-22 to 2026-12-31
Block 1 | 2026-08-05 | 2026-08-10 | 2026-08-13 | Erection | #VALUE! | 1 | 2026-07-31 | 2026-06-22: -; 2026-06-23: -; 2026-06-24: -; 2026-06-25: -; 2026-06-26: -; 2026-06-27: -; 2026-06-28: -; 2026-06-29: -; 2026-06-30: -; 2026-07-01: -; 2026-07-02: -; 2026-07-03: -; 2026-07-04: -; 2026-07-05: -; 2026-07-06: -; 2026-07-07: -; 2026-07-08: -; 2026-07-09: -; 2026-07-10: -; 2026-07-11: -; 2026-07-12: -; 2026-07-13: -; 2026-07-14: -; 2026-07-15: -; 2026-07-16: -; 2026-07-17: -; 2026-07-18: -; 2026-07-19: -; 2026-07-20: -; 2026-07-21: -; 2026-07-22: -; 2026-07-23: -; 2026-07-24: -; 2026-07-25: -; 2026-07-26: -; 2026-07-27: -; 2026-07-28: -; 2026-07-29: -; 2026-07-30: -; 2026-07-31: #VALUE!; 2026-08-01: -; 2026-08-02: -; 2026-08-03: -; 2026-08-04: -; 2026-08-05: -; 2026-08-06: -; 2026-08-07: -; 2026-08-08: -; 2026-08-09: -; 2026-08-10: -; 2026-08-11: -; 2026-08-12: -; 2026-08-13: -; 2026-08-14: -; 2026-08-15: -; 2026-08-16: -; 2026-08-17: -; 2026-08-18: -; 2026-08-19: -; 2026-08-20: -; 2026-08-21: -; 2026-08-22: -; 2026-08-23: -; 2026-08-24: -; 2026-08-25: -; 2026-08-26: -; 2026-08-27: -; 2026-08-28: -; 2026-08-29: -; 2026-08-30: -; 2026-08-31: -; 2026-09-01: -; 2026-09-02: -; 2026-09-03: -; 2026-09-04: -; 2026-09-05: -; 2026-09-06: -; 2026-09-07: -; 2026-09-08: -; 2026-09-09: -; 2026-09-10: -; 2026-09-11: -; 2026-09-12: -; 2026-09-13: -; 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -
|  |  |  | Cable Laying | #VALUE! | 1 | 2026-07-30 | 2026-06-22: -; 2026-06-23: -; 2026-06-24: -; 2026-06-25: -; 2026-06-26: -; 2026-06-27: -; 2026-06-28: -; 2026-06-29: -; 2026-06-30: -; 2026-07-01: -; 2026-07-02: -; 2026-07-03: -; 2026-07-04: -; 2026-07-05: -; 2026-07-06: -; 2026-07-07: -; 2026-07-08: -; 2026-07-09: -; 2026-07-10: -; 2026-07-11: -; 2026-07-12: -; 2026-07-13: -; 2026-07-14: -; 2026-07-15: -; 2026-07-16: -; 2026-07-17: -; 2026-07-18: -; 2026-07-19: -; 2026-07-20: -; 2026-07-21: -; 2026-07-22: -; 2026-07-23: -; 2026-07-24: -; 2026-07-25: -; 2026-07-26: -; 2026-07-27: -; 2026-07-28: -; 2026-07-29: -; 2026-07-30: #VALUE!; 2026-07-31: -; 2026-08-01: -; 2026-08-02: -; 2026-08-03: -; 2026-08-04: -; 2026-08-05: -; 2026-08-06: -; 2026-08-07: -; 2026-08-08: -; 2026-08-09: -; 2026-08-10: -; 2026-08-11: -; 2026-08-12: -; 2026-08-13: -; 2026-08-14: -; 2026-08-15: -; 2026-08-16: -; 2026-08-17: -; 2026-08-18: -; 2026-08-19: -; 2026-08-20: -; 2026-08-21: -; 2026-08-22: -; 2026-08-23: -; 2026-08-24: -; 2026-08-25: -; 2026-08-26: -; 2026-08-27: -; 2026-08-28: -; 2026-08-29: -; 2026-08-30: -; 2026-08-31: -; 2026-09-01: -; 2026-09-02: -; 2026-09-03: -; 2026-09-04: -; 2026-09-05: -; 2026-09-06: -; 2026-09-07: -; 2026-09-08: -; 2026-09-09: -; 2026-09-10: -; 2026-09-11: -; 2026-09-12: -; 2026-09-13: -; 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -
|  |  |  | Termination | #VALUE! | 1 | 2026-08-01 | 2026-06-22: -; 2026-06-23: -; 2026-06-24: -; 2026-06-25: -; 2026-06-26: -; 2026-06-27: -; 2026-06-28: -; 2026-06-29: -; 2026-06-30: -; 2026-07-01: -; 2026-07-02: -; 2026-07-03: -; 2026-07-04: -; 2026-07-05: -; 2026-07-06: -; 2026-07-07: -; 2026-07-08: -; 2026-07-09: -; 2026-07-10: -; 2026-07-11: -; 2026-07-12: -; 2026-07-13: -; 2026-07-14: -; 2026-07-15: -; 2026-07-16: -; 2026-07-17: -; 2026-07-18: -; 2026-07-19: -; 2026-07-20: -; 2026-07-21: -; 2026-07-22: -; 2026-07-23: -; 2026-07-24: -; 2026-07-25: -; 2026-07-26: -; 2026-07-27: -; 2026-07-28: -; 2026-07-29: -; 2026-07-30: -; 2026-07-31: -; 2026-08-01: #VALUE!; 2026-08-02: -; 2026-08-03: -; 2026-08-04: -; 2026-08-05: -; 2026-08-06: -; 2026-08-07: -; 2026-08-08: -; 2026-08-09: -; 2026-08-10: -; 2026-08-11: -; 2026-08-12: -; 2026-08-13: -; 2026-08-14: -; 2026-08-15: -; 2026-08-16: -; 2026-08-17: -; 2026-08-18: -; 2026-08-19: -; 2026-08-20: -; 2026-08-21: -; 2026-08-22: -; 2026-08-23: -; 2026-08-24: -; 2026-08-25: -; 2026-08-26: -; 2026-08-27: -; 2026-08-28: -; 2026-08-29: -; 2026-08-30: -; 2026-08-31: -; 2026-09-01: -; 2026-09-02: -; 2026-09-03: -; 2026-09-04: -; 2026-09-05: -; 2026-09-06: -; 2026-09-07: -; 2026-09-08: -; 2026-09-09: -; 2026-09-10: -; 2026-09-11: -; 2026-09-12: -; 2026-09-13: -; 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -
|  |  |  | Testing | #VALUE! | 6 | 2026-07-30 | 2026-06-22: -; 2026-06-23: -; 2026-06-24: -; 2026-06-25: -; 2026-06-26: -; 2026-06-27: -; 2026-06-28: -; 2026-06-29: -; 2026-06-30: -; 2026-07-01: -; 2026-07-02: -; 2026-07-03: -; 2026-07-04: -; 2026-07-05: -; 2026-07-06: -; 2026-07-07: -; 2026-07-08: -; 2026-07-09: -; 2026-07-10: -; 2026-07-11: -; 2026-07-12: -; 2026-07-13: -; 2026-07-14: -; 2026-07-15: -; 2026-07-16: -; 2026-07-17: -; 2026-07-18: -; 2026-07-19: -; 2026-07-20: -; 2026-07-21: -; 2026-07-22: -; 2026-07-23: -; 2026-07-24: -; 2026-07-25: -; 2026-07-26: -; 2026-07-27: -; 2026-07-28: -; 2026-07-29: -; 2026-07-30: #VALUE!; 2026-07-31: #VALUE!; 2026-08-01: #VALUE!; 2026-08-02: #VALUE!; 2026-08-03: #VALUE!; 2026-08-04: #VALUE!; 2026-08-05: -; 2026-08-06: -; 2026-08-07: -; 2026-08-08: -; 2026-08-09: -; 2026-08-10: -; 2026-08-11: -; 2026-08-12: -; 2026-08-13: -; 2026-08-14: -; 2026-08-15: -; 2026-08-16: -; 2026-08-17: -; 2026-08-18: -; 2026-08-19: -; 2026-08-20: -; 2026-08-21: -; 2026-08-22: -; 2026-08-23: -; 2026-08-24: -; 2026-08-25: -; 2026-08-26: -; 2026-08-27: -; 2026-08-28: -; 2026-08-29: -; 2026-08-30: -; 2026-08-31: -; 2026-09-01: -; 2026-09-02: -; 2026-09-03: -; 2026-09-04: -; 2026-09-05: -; 2026-09-06: -; 2026-09-07: -; 2026-09-08: -; 2026-09-09: -; 2026-09-10: -; 2026-09-11: -; 2026-09-12: -; 2026-09-13: -; 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -
|  |  |  | CFT | 250 | 30 | 2026-08-02 | 2026-07-09: 5; 2026-07-10: 5; 2026-07-11: 5; 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 30; 2026-08-03: 30; 2026-08-04: 30; 2026-08-05: 30; 2026-08-06: 5; 2026-08-07: 5
[7 empty] | Total | 2026-06-24: 0; 2026-06-25: 0; 2026-06-26: 0; 2026-06-27: 0; 2026-06-28: 0; 2026-06-29: 0; 2026-06-30: 0; 2026-07-01: 0; 2026-07-02: 0; 2026-07-03: 0; 2026-07-04: 0; 2026-07-05: 0; 2026-07-06: 0; 2026-07-07: 0; 2026-07-08: 0; 2026-07-09: 5; 2026-07-10: 5; 2026-07-11: 5; 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: #VALUE!; 2026-07-31: #VALUE!; 2026-08-01: #VALUE!; 2026-08-02: #VALUE!; 2026-08-03: #VALUE!; 2026-08-04: #VALUE!; 2026-08-05: 30; 2026-08-06: 5; 2026-08-07: 5; 2026-08-08: 0; 2026-08-09: 0; 2026-08-10: 0; 2026-08-11: 0; 2026-08-12: 0; 2026-08-13: 0; 2026-08-14: 0; 2026-08-15: 0; 2026-08-16: 0; 2026-08-17: 0; 2026-08-18: 0; 2026-08-19: 0; 2026-08-20: 0; 2026-08-21: 0; 2026-08-22: 0; 2026-08-23: 0; 2026-08-24: 0; 2026-08-25: 0; 2026-08-26: 0; 2026-08-27: 0; 2026-08-28: 0; 2026-08-29: 0; 2026-08-30: 0; 2026-08-31: 0; 2026-09-01: 0; 2026-09-02: 0; 2026-09-03: 0; 2026-09-04: 0; 2026-09-05: 0; 2026-09-06: 0; 2026-09-07: 0; 2026-09-08: 0; 2026-09-09: 0; 2026-09-10: 0; 2026-09-11: 0; 2026-09-12: 0; 2026-09-13: 0; 2026-09-14: 0; 2026-09-15: 0; 2026-09-16: 0; 2026-09-17: 0; 2026-09-18: 0; 2026-09-19: 0
Block 2 | 2026-08-11 | 2026-08-16 |  | Activity | Mandays | Days | Min. Date | 2026-06-22: 2026-06-22; 2026-06-23: 2026-06-23; 2026-06-24: 0; 2026-06-25: 1899-12-31; 2026-06-26: 1900-01-01; 2026-06-27: 1900-01-02; 2026-06-28: 1900-01-03; 2026-06-29: 1900-01-04; 2026-06-30: 1900-01-05; 2026-07-01: 1900-01-06; 2026-07-02: 1900-01-07; 2026-07-03: 1900-01-08; 2026-07-04: 1900-01-09; 2026-07-05: 1900-01-10; 2026-07-06: 1900-01-11; 2026-07-07: 1900-01-12; 2026-07-08: 1900-01-13; 2026-07-09: 1900-01-14; 2026-07-10: 1900-01-15; 2026-07-11: 1900-01-16; 2026-07-12: 1900-01-17; 2026-07-13: 1900-01-18; 2026-07-14: 1900-01-19; 2026-07-15: 1900-01-20; 2026-07-16: 1900-01-21; 2026-07-17: 1900-01-22; 2026-07-18: 1900-01-23; 2026-07-19: 1900-01-24; 2026-07-20: 1900-01-25; 2026-07-21: 1900-01-26; 2026-07-22: 1900-01-27; 2026-07-23: 1900-01-28; 2026-07-24: 1900-01-29; 2026-07-25: 1900-01-30; 2026-07-26: 1900-01-31; 2026-07-27: 1900-02-01; 2026-07-28: 1900-02-02; 2026-07-29: 1900-02-03; 2026-07-30: 1900-02-04; 2026-07-31: 1900-02-05; 2026-08-01: 1900-02-06; 2026-08-02: 1900-02-07; 2026-08-03: 1900-02-08; 2026-08-04: 1900-02-09; 2026-08-05: 1900-02-10; 2026-08-06: 1900-02-11; 2026-08-07: 1900-02-12; 2026-08-08: 1900-02-13; 2026-08-09: 1900-02-14; 2026-08-10: 1900-02-15; 2026-08-11: 1900-02-16; 2026-08-12: 1900-02-17; 2026-08-13: 1900-02-18; 2026-08-14: 1900-02-19; 2026-08-15: 1900-02-20; 2026-08-16: 1900-02-21; 2026-08-17: 1900-02-22; 2026-08-18: 1900-02-23; 2026-08-19: 1900-02-24; 2026-08-20: 1900-02-25; 2026-08-21: 1900-02-26; 2026-08-22: 1900-02-27; 2026-08-23: 1900-02-28; 2026-08-24: 1900-03-01; 2026-08-25: 1900-03-02; 2026-08-26: 1900-03-03; 2026-08-27: 1900-03-04; 2026-08-28: 1900-03-05; 2026-08-29: 1900-03-06; 2026-08-30: 1900-03-07; 2026-08-31: 1900-03-08; 2026-09-01: 1900-03-09; 2026-09-02: 1900-03-10; 2026-09-03: 1900-03-11; 2026-09-04: 1900-03-12; 2026-09-05: 1900-03-13; 2026-09-06: 1900-03-14; 2026-09-07: 1900-03-15; 2026-09-08: 1900-03-16; 2026-09-09: 1900-03-17; 2026-09-10: 1900-03-18; 2026-09-11: 1900-03-19; 2026-09-12: 1900-03-20; 2026-09-13: 1900-03-21; 2026-09-14: 1900-03-22; 2026-09-15: 1900-03-23; 2026-09-16: 1900-03-24; 2026-09-17: 1900-03-25; 2026-09-18: 1900-03-26; 2026-09-19: 1900-03-27
|  |  | 2026-08-19 | Erection | #VALUE! | 9 | 2026-07-25 | 2026-06-22: -; 2026-06-23: -; 2026-06-24: -; 2026-06-25: -; 2026-06-26: -; 2026-06-27: -; 2026-06-28: -; 2026-06-29: -; 2026-06-30: -; 2026-07-01: -; 2026-07-02: -; 2026-07-03: -; 2026-07-04: -; 2026-07-05: -; 2026-07-06: -; 2026-07-07: -; 2026-07-08: -; 2026-07-09: -; 2026-07-10: -; 2026-07-11: -; 2026-07-12: -; 2026-07-13: -; 2026-07-14: -; 2026-07-15: -; 2026-07-16: -; 2026-07-17: -; 2026-07-18: -; 2026-07-19: -; 2026-07-20: -; 2026-07-21: -; 2026-07-22: -; 2026-07-23: -; 2026-07-24: -; 2026-07-25: #VALUE!; 2026-07-26: #VALUE!; 2026-07-27: #VALUE!; 2026-07-28: #VALUE!; 2026-07-29: #VALUE!; 2026-07-30: #VALUE!; 2026-07-31: #VALUE!; 2026-08-01: #VALUE!; 2026-08-02: #VALUE!; 2026-08-03: -; 2026-08-04: -; 2026-08-05: -; 2026-08-06: -; 2026-08-07: -; 2026-08-08: -; 2026-08-09: -; 2026-08-10: -; 2026-08-11: -; 2026-08-12: -; 2026-08-13: -; 2026-08-14: -; 2026-08-15: -; 2026-08-16: -; 2026-08-17: -; 2026-08-18: -; 2026-08-19: -; 2026-08-20: -; 2026-08-21: -; 2026-08-22: -; 2026-08-23: -; 2026-08-24: -; 2026-08-25: -; 2026-08-26: -; 2026-08-27: -; 2026-08-28: -; 2026-08-29: -; 2026-08-30: -; 2026-08-31: -; 2026-09-01: -; 2026-09-02: -; 2026-09-03: -; 2026-09-04: -; 2026-09-05: -; 2026-09-06: -; 2026-09-07: -; 2026-09-08: -; 2026-09-09: -; 2026-09-10: -; 2026-09-11: -; 2026-09-12: -; 2026-09-13: -; 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -
|  |  |  | Cable Laying | #VALUE! | 3 | 2026-07-29 | 2026-06-22: -; 2026-06-23: -; 2026-06-24: -; 2026-06-25: -; 2026-06-26: -; 2026-06-27: -; 2026-06-28: -; 2026-06-29: -; 2026-06-30: -; 2026-07-01: -; 2026-07-02: -; 2026-07-03: -; 2026-07-04: -; 2026-07-05: -; 2026-07-06: -; 2026-07-07: -; 2026-07-08: -; 2026-07-09: -; 2026-07-10: -; 2026-07-11: -; 2026-07-12: -; 2026-07-13: -; 2026-07-14: -; 2026-07-15: -; 2026-07-16: -; 2026-07-17: -; 2026-07-18: -; 2026-07-19: -; 2026-07-20: -; 2026-07-21: -; 2026-07-22: -; 2026-07-23: -; 2026-07-24: -; 2026-07-25: -; 2026-07-26: -; 2026-07-27: -; 2026-07-28: -; 2026-07-29: #VALUE!; 2026-07-30: #VALUE!; 2026-07-31: #VALUE!; 2026-08-01: -; 2026-08-02: -; 2026-08-03: -; 2026-08-04: -; 2026-08-05: -; 2026-08-06: -; 2026-08-07: -; 2026-08-08: -; 2026-08-09: -; 2026-08-10: -; 2026-08-11: -; 2026-08-12: -; 2026-08-13: -; 2026-08-14: -; 2026-08-15: -; 2026-08-16: -; 2026-08-17: -; 2026-08-18: -; 2026-08-19: -; 2026-08-20: -; 2026-08-21: -; 2026-08-22: -; 2026-08-23: -; 2026-08-24: -; 2026-08-25: -; 2026-08-26: -; 2026-08-27: -; 2026-08-28: -; 2026-08-29: -; 2026-08-30: -; 2026-08-31: -; 2026-09-01: -; 2026-09-02: -; 2026-09-03: -; 2026-09-04: -; 2026-09-05: -; 2026-09-06: -; 2026-09-07: -; 2026-09-08: -; 2026-09-09: -; 2026-09-10: -; 2026-09-11: -; 2026-09-12: -; 2026-09-13: -; 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -
|  |  |  | Termination | #VALUE! | 6 | 2026-07-31 | 2026-06-22: -; 2026-06-23: -; 2026-06-24: -; 2026-06-25: -; 2026-06-26: -; 2026-06-27: -; 2026-06-28: -; 2026-06-29: -; 2026-06-30: -; 2026-07-01: -; 2026-07-02: -; 2026-07-03: -; 2026-07-04: -; 2026-07-05: -; 2026-07-06: -; 2026-07-07: -; 2026-07-08: -; 2026-07-09: -; 2026-07-10: -; 2026-07-11: -; 2026-07-12: -; 2026-07-13: -; 2026-07-14: -; 2026-07-15: -; 2026-07-16: -; 2026-07-17: -; 2026-07-18: -; 2026-07-19: -; 2026-07-20: -; 2026-07-21: -; 2026-07-22: -; 2026-07-23: -; 2026-07-24: -; 2026-07-25: -; 2026-07-26: -; 2026-07-27: -; 2026-07-28: -; 2026-07-29: -; 2026-07-30: -; 2026-07-31: #VALUE!; 2026-08-01: #VALUE!; 2026-08-02: #VALUE!; 2026-08-03: #VALUE!; 2026-08-04: #VALUE!; 2026-08-05: #VALUE!; 2026-08-06: -; 2026-08-07: -; 2026-08-08: -; 2026-08-09: -; 2026-08-10: -; 2026-08-11: -; 2026-08-12: -; 2026-08-13: -; 2026-08-14: -; 2026-08-15: -; 2026-08-16: -; 2026-08-17: -; 2026-08-18: -; 2026-08-19: -; 2026-08-20: -; 2026-08-21: -; 2026-08-22: -; 2026-08-23: -; 2026-08-24: -; 2026-08-25: -; 2026-08-26: -; 2026-08-27: -; 2026-08-28: -; 2026-08-29: -; 2026-08-30: -; 2026-08-31: -; 2026-09-01: -; 2026-09-02: -; 2026-09-03: -; 2026-09-04: -; 2026-09-05: -; 2026-09-06: -; 2026-09-07: -; 2026-09-08: -; 2026-09-09: -; 2026-09-10: -; 2026-09-11: -; 2026-09-12: -; 2026-09-13: -; 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -
|  |  |  | Testing | #VALUE! | 12 | 2026-07-28 | 2026-06-22: -; 2026-06-23: -; 2026-06-24: -; 2026-06-25: -; 2026-06-26: -; 2026-06-27: -; 2026-06-28: -; 2026-06-29: -; 2026-06-30: -; 2026-07-01: -; 2026-07-02: -; 2026-07-03: -; 2026-07-04: -; 2026-07-05: -; 2026-07-06: -; 2026-07-07: -; 2026-07-08: -; 2026-07-09: -; 2026-07-10: -; 2026-07-11: -; 2026-07-12: -; 2026-07-13: -; 2026-07-14: -; 2026-07-15: -; 2026-07-16: -; 2026-07-17: -; 2026-07-18: -; 2026-07-19: -; 2026-07-20: -; 2026-07-21: -; 2026-07-22: -; 2026-07-23: -; 2026-07-24: -; 2026-07-25: -; 2026-07-26: -; 2026-07-27: -; 2026-07-28: #VALUE!; 2026-07-29: #VALUE!; 2026-07-30: #VALUE!; 2026-07-31: #VALUE!; 2026-08-01: #VALUE!; 2026-08-02: #VALUE!; 2026-08-03: #VALUE!; 2026-08-04: #VALUE!; 2026-08-05: #VALUE!; 2026-08-06: #VALUE!; 2026-08-07: #VALUE!; 2026-08-08: #VALUE!; 2026-08-09: -; 2026-08-10: -; 2026-08-11: -; 2026-08-12: -; 2026-08-13: -; 2026-08-14: -; 2026-08-15: -; 2026-08-16: -; 2026-08-17: -; 2026-08-18: -; 2026-08-19: -; 2026-08-20: -; 2026-08-21: -; 2026-08-22: -; 2026-08-23: -; 2026-08-24: -; 2026-08-25: -; 2026-08-26: -; 2026-08-27: -; 2026-08-28: -; 2026-08-29: -; 2026-08-30: -; 2026-08-31: -; 2026-09-01: -; 2026-09-02: -; 2026-09-03: -; 2026-09-04: -; 2026-09-05: -; 2026-09-06: -; 2026-09-07: -; 2026-09-08: -; 2026-09-09: -; 2026-09-10: -; 2026-09-11: -; 2026-09-12: -; 2026-09-13: -; 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -
|  |  |  | CFT | 250 | 30 | 2026-08-08 | 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 5; 2026-08-04: 5; 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 5; 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 30; 2026-08-15: 30; 2026-08-16: 30; 2026-08-17: 30; 2026-08-18: 5; 2026-08-19: 5
[7 empty] | Total | 2026-06-24: 0; 2026-06-25: 0; 2026-06-26: 0; 2026-06-27: 0; 2026-06-28: 0; 2026-06-29: 0; 2026-06-30: 0; 2026-07-01: 0; 2026-07-02: 0; 2026-07-03: 0; 2026-07-04: 0; 2026-07-05: 0; 2026-07-06: 0; 2026-07-07: 0; 2026-07-08: 0; 2026-07-09: 0; 2026-07-10: 0; 2026-07-11: 0; 2026-07-12: 0; 2026-07-13: 0; 2026-07-14: 0; 2026-07-15: 0; 2026-07-16: 0; 2026-07-17: 0; 2026-07-18: 0; 2026-07-19: 0; 2026-07-20: 0; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: #VALUE!; 2026-07-26: #VALUE!; 2026-07-27: #VALUE!; 2026-07-28: #VALUE!; 2026-07-29: #VALUE!; 2026-07-30: #VALUE!; 2026-07-31: #VALUE!; 2026-08-01: #VALUE!; 2026-08-02: #VALUE!; 2026-08-03: #VALUE!; 2026-08-04: #VALUE!; 2026-08-05: #VALUE!; 2026-08-06: #VALUE!; 2026-08-07: #VALUE!; 2026-08-08: #VALUE!; 2026-08-09: 5; 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 30; 2026-08-15: 30; 2026-08-16: 30; 2026-08-17: 30; 2026-08-18: 5; 2026-08-19: 5; 2026-08-20: 0; 2026-08-21: 0; 2026-08-22: 0; 2026-08-23: 0; 2026-08-24: 0; 2026-08-25: 0; 2026-08-26: 0; 2026-08-27: 0; 2026-08-28: 0; 2026-08-29: 0; 2026-08-30: 0; 2026-08-31: 0; 2026-09-01: 0; 2026-09-02: 0; 2026-09-03: 0; 2026-09-04: 0; 2026-09-05: 0; 2026-09-06: 0; 2026-09-07: 0; 2026-09-08: 0; 2026-09-09: 0; 2026-09-10: 0; 2026-09-11: 0; 2026-09-12: 0; 2026-09-13: 0; 2026-09-14: 0; 2026-09-15: 0; 2026-09-16: 0; 2026-09-17: 0; 2026-09-18: 0; 2026-09-19: 0
Block 3 | 08 Aug 23 Aug | 13 Aug 28 Aug |  | Activity | Mandays | Days | Min. Date | time axis 2026-06-22 to 2026-09-19
|  |  | 16 Aug 31 Aug | Erection | #VALUE! | 5 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  |  | Cable Laying | #VALUE! | 5 | 2026-08-08 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | #VALUE! | 8 | 2026-08-10 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 10 | 2026-08-12 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 | 30 | #VALUE! | 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 5; 2026-08-04: 5; 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 5; 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 5; 2026-08-15: 5; 2026-08-16: 30; 2026-08-17: 30; 2026-08-18: 30; 2026-08-19: 30; 2026-08-20: 5; 2026-08-21: 5
[7 empty] | Total |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Block 4 | 30 Aug 21 Sep | 04 Sep 26 Sep |  | Activity | Mandays | Days | Min. Date | time axis 2026-06-22 to 2026-09-19
|  |  | 07 Sep 29 Sep | Erection | #VALUE! | #VALUE! | 2026-08-10 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  |  | Cable Laying | #VALUE! | 13 | 2026-08-08 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | #VALUE! | 21 | 2026-08-23 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 24 | 2026-08-26 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | -
|  |  |  | CFT | 250 | 30 | #VALUE! | 2026-08-14: 5; 2026-08-15: 5; 2026-08-16: 5; 2026-08-17: 5; 2026-08-18: 5; 2026-08-19: 5; 2026-08-20: 5; 2026-08-21: 5; 2026-08-22: 5; 2026-08-23: 5; 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 5; 2026-08-29: 5; 2026-08-30: 5; 2026-08-31: 5; 2026-09-01: 5; 2026-09-02: 5; 2026-09-03: 5; 2026-09-04: 5; 2026-09-05: 5; 2026-09-06: 5; 2026-09-07: 30; 2026-09-08: 30; 2026-09-09: 30; 2026-09-10: 30; 2026-09-11: 5; 2026-09-12: 5
[7 empty] | Total |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Block 5 | 04 Sep 30 Sep | 09 Sep 05 Oct |  | Activity | Mandays | Days | Min. Date | time axis 2026-06-22 to 2026-09-19
|  |  | 12 Sep 08 Oct | Erection | #VALUE! | 30 | 2026-08-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | -
|  |  |  | Cable Laying | #VALUE! | 9 | 2026-08-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | #VALUE! | 24 | 2026-08-28 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  |  | Testing | #VALUE! | 28 | 2026-08-31 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  |  | CFT | 250 | 30 | #VALUE! | 2026-08-16: 5; 2026-08-17: 5; 2026-08-18: 5; 2026-08-19: 5; 2026-08-20: 5; 2026-08-21: 5; 2026-08-22: 5; 2026-08-23: 5; 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 5; 2026-08-29: 5; 2026-08-30: 5; 2026-08-31: 5; 2026-09-01: 5; 2026-09-02: 5; 2026-09-03: 5; 2026-09-04: 5; 2026-09-05: 5; 2026-09-06: 5; 2026-09-07: 5; 2026-09-08: 5; 2026-09-09: 30; 2026-09-10: 30; 2026-09-11: 30; 2026-09-12: 30; 2026-09-13: 5; 2026-09-14: 5
[7 empty] | Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!

## BC Arrival Productivity (hidden)
BESS 11
| Battery Container | Scope | Actual | Balance | Start date | End Date | Days | Productivity | Manpower | Total Manpower | Avg Manpower | time axis 2026-06-28 to 2026-09-24
| Battery Container Erection | 48 | 0 | 48 | 28 Jun, 05 Jul | #VALUE! | #VALUE! | 10 | 1 | 4.8 | #DIV/0! | 2026-06-28: #VALUE!; 2026-06-29: #VALUE!; 2026-06-30: #VALUE!; 2026-07-01: #VALUE!; 2026-07-02: #VALUE!; 2026-07-03: #VALUE!; 2026-07-04: #VALUE!; 2026-07-05: #VALUE!; 2026-07-06: #VALUE!; 2026-07-07: #VALUE!; 2026-07-08: #VALUE!; 2026-07-09: #VALUE!; 2026-07-10: #VALUE!; 2026-07-11: #VALUE!; 2026-07-12: #VALUE!; 2026-07-13: #VALUE!; 2026-07-14: #VALUE!; 2026-07-15: #VALUE!; 2026-07-16: #VALUE!; 2026-07-17: #VALUE!; 2026-07-18: #VALUE!; 2026-07-19: #VALUE!; 2026-07-20: #VALUE!; 2026-07-21: #VALUE!; 2026-07-22: #VALUE!; 2026-07-23: #VALUE!; 2026-07-24: #VALUE!; 2026-07-25: #VALUE!; 2026-07-26: #VALUE!; 2026-07-27: #VALUE!; 2026-07-28: #VALUE!; 2026-07-29: #VALUE!; 2026-07-30: #VALUE!; 2026-07-31: #VALUE!; 2026-08-01: #VALUE!; 2026-08-02: #VALUE!; 2026-08-03: #VALUE!; 2026-08-04: #VALUE!; 2026-08-05: #VALUE!; 2026-08-06: #VALUE!; 2026-08-07: #VALUE!
B4 | DC termination | 768 | 810 | -42 | 28 Jun, 05 Jul | #VALUE! | #VALUE! | 40 | 18 | -18.9 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Control & Communication termination | 1344 | 0 | 1344 | 28 Jun, 05 Jul | #VALUE! | #VALUE! | 40 | 6 | 201.6 |  | 2026-06-28: #VALUE!; 2026-06-29: #VALUE!; 2026-06-30: #VALUE!; 2026-07-01: #VALUE!; 2026-07-02: #VALUE!; 2026-07-03: #VALUE!; 2026-07-04: #VALUE!; 2026-07-05: #VALUE!; 2026-07-06: #VALUE!; 2026-07-07: #VALUE!; 2026-07-08: #VALUE!; 2026-07-09: #VALUE!; 2026-07-10: #VALUE!; 2026-07-11: #VALUE!; 2026-07-12: #VALUE!
| Battery Container | Scope | Actual | Balance | Start date | End Date | Days | Productivity | Manpower | Total Manpower | Avg Manpower | time axis 2026-06-28 to 2026-09-24
B3 | Battery Container Erection | 48 | 0 | 48 | 04 Jul, 08 Jul, 13 Jul | #VALUE! | #VALUE! | 10 | 1 | 4.8 | #DIV/0! | 2026-06-28: #VALUE!; 2026-06-29: #VALUE!; 2026-06-30: #VALUE!; 2026-07-01: #VALUE!; 2026-07-02: #VALUE!; 2026-07-03: #VALUE!; 2026-07-04: #VALUE!; 2026-07-05: #VALUE!; 2026-07-06: #VALUE!; 2026-07-07: #VALUE!; 2026-07-08: #VALUE!; 2026-07-09: #VALUE!; 2026-07-10: #VALUE!; 2026-07-11: #VALUE!; 2026-07-12: #VALUE!; 2026-07-13: #VALUE!; 2026-07-14: #VALUE!; 2026-07-15: #VALUE!; 2026-07-16: #VALUE!; 2026-07-17: #VALUE!; 2026-07-18: #VALUE!; 2026-07-19: #VALUE!; 2026-07-20: #VALUE!; 2026-07-21: #VALUE!; 2026-07-22: #VALUE!; 2026-07-23: #VALUE!; 2026-07-24: #VALUE!; 2026-07-25: #VALUE!; 2026-07-26: #VALUE!; 2026-07-27: #VALUE!; 2026-07-28: #VALUE!; 2026-07-29: #VALUE!; 2026-07-30: #VALUE!; 2026-07-31: #VALUE!; 2026-08-01: #VALUE!; 2026-08-02: #VALUE!; 2026-08-03: #VALUE!; 2026-08-04: #VALUE!; 2026-08-05: #VALUE!; 2026-08-06: #VALUE!; 2026-08-07: #VALUE!
| DC termination | 768 | 810 | -42 | 04 Jul, 08 Jul, 13 Jul | #VALUE! | #VALUE! | 30 | 18 | -25.2 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Control & Communication termination | 1344 | 0 | 1344 | 04 Jul, 08 Jul, 13 Jul | #VALUE! | #VALUE! | 30 | 6 | 268.8 |  | 2026-06-28: #VALUE!; 2026-06-29: #VALUE!; 2026-06-30: #VALUE!; 2026-07-01: #VALUE!; 2026-07-02: #VALUE!; 2026-07-03: #VALUE!; 2026-07-04: #VALUE!; 2026-07-05: #VALUE!; 2026-07-06: #VALUE!; 2026-07-07: #VALUE!; 2026-07-08: #VALUE!; 2026-07-09: #VALUE!; 2026-07-10: #VALUE!; 2026-07-11: #VALUE!; 2026-07-12: #VALUE!
| Battery Container | Scope | Actual | Balance | Start date | End Date | Days | Productivity | Manpower | Total Manpower | Avg Manpower | time axis 2026-06-28 to 2026-09-24
B2 | Battery Container Erection | 48 | 0 | 48 | 13 Jul, 20 Jul 21 Jul | #VALUE! | #VALUE! | 10 | 1 | 4.8 | #DIV/0! | 2026-06-28: #VALUE!; 2026-06-29: #VALUE!; 2026-06-30: #VALUE!; 2026-07-01: #VALUE!; 2026-07-02: #VALUE!; 2026-07-03: #VALUE!; 2026-07-04: #VALUE!; 2026-07-05: #VALUE!; 2026-07-06: #VALUE!; 2026-07-07: #VALUE!; 2026-07-08: #VALUE!; 2026-07-09: #VALUE!; 2026-07-10: #VALUE!; 2026-07-11: #VALUE!; 2026-07-12: #VALUE!; 2026-07-13: #VALUE!; 2026-07-14: #VALUE!; 2026-07-15: #VALUE!; 2026-07-16: #VALUE!; 2026-07-17: #VALUE!; 2026-07-18: #VALUE!; 2026-07-19: #VALUE!; 2026-07-20: #VALUE!; 2026-07-21: #VALUE!; 2026-07-22: #VALUE!; 2026-07-23: #VALUE!; 2026-07-24: #VALUE!; 2026-07-25: #VALUE!; 2026-07-26: #VALUE!; 2026-07-27: #VALUE!; 2026-07-28: #VALUE!; 2026-07-29: #VALUE!; 2026-07-30: #VALUE!; 2026-07-31: #VALUE!; 2026-08-01: #VALUE!; 2026-08-02: #VALUE!; 2026-08-03: #VALUE!; 2026-08-04: #VALUE!; 2026-08-05: #VALUE!; 2026-08-06: #VALUE!; 2026-08-07: #VALUE!
| DC termination | 768 | 810 | -42 | 13 Jul, 20 Jul 21 Jul | #VALUE! | #VALUE! | 30 | 18 | -25.2 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Control & Communication termination | 1344 | 0 | 1344 | 13 Jul, 20 Jul 21 Jul | #VALUE! | #VALUE! | 30 | 6 | 268.8 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Battery Container | Scope | Actual | Balance | Start date | End Date | Days | Productivity | Manpower | Total Manpower | Avg Manpower | time axis 2026-06-28 to 2026-09-24
B1 | Battery Container Erection | 48 | 0 | 48 | 16 Jul, 23 Jul 24 Jul | #VALUE! | #VALUE! | 10 | 1 | 4.8 | #DIV/0! | 2026-06-28: #VALUE!; 2026-06-29: #VALUE!; 2026-06-30: #VALUE!; 2026-07-01: #VALUE!; 2026-07-02: #VALUE!; 2026-07-03: #VALUE!; 2026-07-04: #VALUE!; 2026-07-05: #VALUE!; 2026-07-06: #VALUE!; 2026-07-07: #VALUE!; 2026-07-08: #VALUE!; 2026-07-09: #VALUE!; 2026-07-10: #VALUE!; 2026-07-11: #VALUE!; 2026-07-12: #VALUE!; 2026-07-13: #VALUE!; 2026-07-14: #VALUE!; 2026-07-15: #VALUE!; 2026-07-16: #VALUE!; 2026-07-17: #VALUE!; 2026-07-18: #VALUE!; 2026-07-19: #VALUE!; 2026-07-20: #VALUE!; 2026-07-21: #VALUE!; 2026-07-22: #VALUE!; 2026-07-23: #VALUE!; 2026-07-24: #VALUE!; 2026-07-25: #VALUE!; 2026-07-26: #VALUE!; 2026-07-27: #VALUE!; 2026-07-28: #VALUE!; 2026-07-29: #VALUE!; 2026-07-30: #VALUE!; 2026-07-31: #VALUE!; 2026-08-01: #VALUE!; 2026-08-02: #VALUE!; 2026-08-03: #VALUE!; 2026-08-04: #VALUE!; 2026-08-05: #VALUE!; 2026-08-06: #VALUE!; 2026-08-07: #VALUE!
| DC termination | 768 | 810 | -42 | 16 Jul, 23 Jul 24 Jul | #VALUE! | #VALUE! | 30 | 18 | -25.2 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Control & Communication termination | 1344 | 0 | 1344 | 16 Jul, 23 Jul 24 Jul | #VALUE! | #VALUE! | 30 | 6 | 268.8 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Battery Container | Scope | Actual | Balance | Start date | End Date | Days | Productivity | Manpower | Total Manpower | Avg Manpower | time axis 2026-06-28 to 2026-09-24
B5 | Battery Container Erection | 48 | 0 | 48 | 04 Aug, 15 Aug 24 Aug 31 Aug | #VALUE! | #VALUE! | 10 | 1 | 4.8 | #DIV/0! | 2026-06-28: #VALUE!; 2026-06-29: #VALUE!; 2026-06-30: #VALUE!; 2026-07-01: #VALUE!; 2026-07-02: #VALUE!; 2026-07-03: #VALUE!; 2026-07-04: #VALUE!; 2026-07-05: #VALUE!; 2026-07-06: #VALUE!; 2026-07-07: #VALUE!; 2026-07-08: #VALUE!; 2026-07-09: #VALUE!; 2026-07-10: #VALUE!; 2026-07-11: #VALUE!; 2026-07-12: #VALUE!; 2026-07-13: #VALUE!; 2026-07-14: #VALUE!; 2026-07-15: #VALUE!; 2026-07-16: #VALUE!; 2026-07-17: #VALUE!; 2026-07-18: #VALUE!; 2026-07-19: #VALUE!; 2026-07-20: #VALUE!; 2026-07-21: #VALUE!; 2026-07-22: #VALUE!; 2026-07-23: #VALUE!; 2026-07-24: #VALUE!; 2026-07-25: #VALUE!; 2026-07-26: #VALUE!; 2026-07-27: #VALUE!; 2026-07-28: #VALUE!; 2026-07-29: #VALUE!; 2026-07-30: #VALUE!; 2026-07-31: #VALUE!; 2026-08-01: #VALUE!; 2026-08-02: #VALUE!; 2026-08-03: #VALUE!; 2026-08-04: #VALUE!; 2026-08-05: #VALUE!; 2026-08-06: #VALUE!; 2026-08-07: #VALUE!
| DC termination | 768 | 810 | -42 | 04 Aug, 15 Aug 24 Aug 31 Aug | #VALUE! | #VALUE! | 30 | 18 | -25.2 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Control & Communication termination | 1344 | 0 | 1344 | 04 Aug, 15 Aug 24 Aug 31 Aug | #VALUE! | #VALUE! | 30 | 6 | 268.8 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Battery Container | Scope | Actual | Balance | Start date | End Date | Days | Productivity | Manpower | Total Manpower | Avg Manpower | time axis 2026-06-28 to 2026-09-24
B6 | Battery Container Erection | 48 | 0 | 48 | 09 Aug, 16 Aug 05 Sep 31 Aug | #VALUE! | #VALUE! | 10 | 1 | 4.8 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| DC termination | 768 | 810 | -42 | 09 Aug, 16 Aug 05 Sep 31 Aug | #VALUE! | #VALUE! | 30 | 18 | -25.2 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Control & Communication termination | 1344 | 0 | 1344 | 09 Aug, 16 Aug 05 Sep 31 Aug | #VALUE! | #VALUE! | 30 | 6 | 268.8 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Battery Container | Scope | Actual | Balance | Start date | End Date | Days | Productivity | Manpower | Total Manpower | Avg Manpower | time axis 2026-06-28 to 2026-09-24
B7 | Battery Container Erection | 48 | 0 | 48 | 19 Aug, 22 Aug 05 Sep 08 Sep | #VALUE! | #VALUE! | 10 | 1 | 4.8 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| DC termination | 768 | 810 | -42 | 19 Aug, 22 Aug 05 Sep 08 Sep | #VALUE! | #VALUE! | 30 | 18 | -25.2 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Control & Communication termination | 1344 | 0 | 1344 | 19 Aug, 22 Aug 05 Sep 08 Sep | #VALUE! | #VALUE! | 30 | 6 | 268.8 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Battery Container | Scope | Actual | Balance | Start date | End Date | Days | Productivity | Manpower | Total Manpower | Avg Manpower | time axis 2026-06-28 to 2026-09-24
B8 | Battery Container Erection | 48 | 0 | 48 | 21 Aug, 24 Aug 05 Sep 08 Sep | #VALUE! | #VALUE! | 10 | 1 | 4.8 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| DC termination | 768 | 810 | -42 | 21 Aug, 24 Aug 05 Sep 08 Sep | #VALUE! | #VALUE! | 30 | 18 | -25.2 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Control & Communication termination | 1344 | 0 | 1344 | 21 Aug, 24 Aug 05 Sep 08 Sep | #VALUE! | #VALUE! | 30 | 6 | 268.8 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Battery Container | Scope | Actual | Balance | Start date | End Date | Days | Productivity | Manpower | Total Manpower | Avg Manpower | time axis 2026-06-28 to 2026-09-24
B9 | Battery Container Erection | 48 | 0 | 48 | 22 Aug, 26 Aug 05 Sep 08 Sep | #VALUE! | #VALUE! | 10 | 1 | 4.8 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| DC termination | 768 | 810 | -42 | 22 Aug, 26 Aug 05 Sep 08 Sep | #VALUE! | #VALUE! | 30 | 18 | -25.2 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Control & Communication termination | 1344 | 0 | 1344 | 22 Aug, 26 Aug 05 Sep 08 Sep | #VALUE! | #VALUE! | 30 | 6 | 268.8 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
BESS 12
| Battery Container | Scope | Actual | Balance | Start date | End Date | Days | Productivity | Manpower | Total Manpower | Avg Manpower | time axis 2026-06-28 to 2026-09-24
B1 | Battery Container Erection | 48 | 0 | 48 | 30 Jun 04 Jul 09 Jul | #VALUE! | #VALUE! | 10 | 1 | 4.8 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| DC termination | 768 | 810 | -42 | 30 Jun 04 Jul 09 Jul | #VALUE! | #VALUE! | 30 | 18 | -25.2 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Control & Communication termination | 1344 | 0 | 1344 | 30 Jun 04 Jul 09 Jul | #VALUE! | #VALUE! | 30 | 6 | 268.8 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Battery Container | Scope | Actual | Balance | Start date | End Date | Days | Productivity | Manpower | Total Manpower | Avg Manpower | time axis 2026-06-28 to 2026-09-24
B2 | Battery Container Erection | 48 | 0 | 48 | 04 Jul, 07 Jul 10 Jul 14 Jul | #VALUE! | #VALUE! | 10 | 1 | 4.8 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| DC termination | 768 | 810 | -42 | 04 Jul, 07 Jul 10 Jul 14 Jul | #VALUE! | #VALUE! | 30 | 18 | -25.2 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Control & Communication termination | 1344 | 0 | 1344 | 04 Jul, 07 Jul 10 Jul 14 Jul | #VALUE! | #VALUE! | 30 | 6 | 268.8 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Battery Container | Scope | Actual | Balance | Start date | End Date | Days | Productivity | Manpower | Total Manpower | Avg Manpower | time axis 2026-06-28 to 2026-09-24
B4 | Battery Container Erection | 48 | 0 | 48 | 07 Jul 09 Jul | #VALUE! | #VALUE! | 10 | 1 | 4.8 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| DC termination | 768 | 810 | -42 | 07 Jul 09 Jul | #VALUE! | #VALUE! | 30 | 18 | -25.2 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Control & Communication termination | 1344 | 0 | 1344 | 07 Jul 09 Jul | #VALUE! | #VALUE! | 30 | 6 | 268.8 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Battery Container | Scope | Actual | Balance | Start date | End Date | Days | Productivity | Manpower | Total Manpower | Avg Manpower | time axis 2026-06-28 to 2026-09-24
B3 | Battery Container Erection | 48 | 0 | 48 | 13 Jul 20 Jul 22 Jul | #VALUE! | #VALUE! | 10 | 1 | 4.8 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| DC termination | 768 | 810 | -42 | 13 Jul 20 Jul 22 Jul | #VALUE! | #VALUE! | 30 | 18 | -25.2 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Control & Communication termination | 1344 | 0 | 1344 | 13 Jul 20 Jul 22 Jul | #VALUE! | #VALUE! | 30 | 6 | 268.8 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Battery Container | Scope | Actual | Balance | Start date | End Date | Days | Productivity | Manpower | Total Manpower | Avg Manpower | time axis 2026-06-28 to 2026-09-24
B5 | Battery Container Erection | 48 | 0 | 48 | 14 Jul 21 Jul 24 Jul | #VALUE! | #VALUE! | 10 | 1 | 4.8 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| DC termination | 768 | 810 | -42 | 14 Jul 21 Jul 24 Jul | #VALUE! | #VALUE! | 30 | 18 | -25.2 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Control & Communication termination | 1344 | 0 | 1344 | 14 Jul 21 Jul 24 Jul | #VALUE! | #VALUE! | 30 | 6 | 268.8 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Battery Container | Scope | Actual | Balance | Start date | End Date | Days | Productivity | Manpower | Total Manpower | Avg Manpower | time axis 2026-06-28 to 2026-09-24
B6 | Battery Container Erection | 48 | 0 | 48 | 03 Aug 17 Aug 02 Aug 04 Aug | #VALUE! | #VALUE! | 10 | 1 | 4.8 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| DC termination | 768 | 810 | -42 | 03 Aug 17 Aug 02 Aug 04 Aug | #VALUE! | #VALUE! | 30 | 18 | -25.2 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Control & Communication termination | 1344 | 0 | 1344 | 03 Aug 17 Aug 02 Aug 04 Aug | #VALUE! | #VALUE! | 30 | 6 | 268.8 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Battery Container | Scope | Actual | Balance | Start date | End Date | Days | Productivity | Manpower | Total Manpower | Avg Manpower | time axis 2026-06-28 to 2026-09-24
B7 | Battery Container Erection | 48 | 0 | 48 | 07 Aug 19 Aug 27 Aug 29 Aug | #VALUE! | #VALUE! | 10 | 1 | 4.8 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| DC termination | 768 | 810 | -42 | 07 Aug 19 Aug 27 Aug 29 Aug | #VALUE! | #VALUE! | 30 | 18 | -25.2 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Control & Communication termination | 1344 | 0 | 1344 | 07 Aug 19 Aug 27 Aug 29 Aug | #VALUE! | #VALUE! | 30 | 6 | 268.8 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Battery Container | Scope | Actual | Balance | Start date | End Date | Days | Productivity | Manpower | Total Manpower | Avg Manpower | time axis 2026-06-28 to 2026-09-24
B8 | Battery Container Erection | 48 | 0 | 48 | 18 Aug 23 Aug 27 Aug 29 Aug | #VALUE! | #VALUE! | 10 | 1 | 4.8 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| DC termination | 768 | 810 | -42 | 18 Aug 23 Aug 27 Aug 29 Aug | #VALUE! | #VALUE! | 30 | 18 | -25.2 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Control & Communication termination | 1344 | 0 | 1344 | 18 Aug 23 Aug 27 Aug 29 Aug | #VALUE! | #VALUE! | 30 | 6 | 268.8 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!

## 11 - Daily requirement (2) (hidden)
| IDT Charging / Commissioning Start | Trial-Run End Date | COD | Activity | Mandays | Days |  | Min. Date | [133 empty] | Average Manpower | Peak Manpower | 2026-12-26 | 2026-12-27 | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31 | time axis 2026-06-22 to 2026-11-01
Block 4 | 22 Jul 28 Jul | 27 Jul 02 Aug | 30 Jul 05 Aug | Erection | 0 | 1 | 0 | 0 | bar: 2026-06-22 to 2026-11-01
|  |  |  | Cable Laying | 0 | 1 | 0 | 0 | bar: 2026-06-22 to 2026-11-01
|  |  |  | Termination | 0 | 1 | 0 | 0 | bar: 2026-06-22 to 2026-11-01
|  |  |  | Testing | 0.004 | 1 |  | 0 | bar: 2026-06-22 to 2026-11-01
|  |  |  | CFT | 250 | 30 |  | #VALUE! | 2026-06-28: 5; 2026-06-29: 5; 2026-06-30: 5; 2026-07-01: 5; 2026-07-02: 5; 2026-07-03: 5; 2026-07-04: 5; 2026-07-05: 5; 2026-07-06: 5; 2026-07-07: 5; 2026-07-08: 5; 2026-07-09: 5; 2026-07-10: 5; 2026-07-11: 5; 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 30; 2026-07-23: 30; 2026-07-24: 30; 2026-07-25: 30; 2026-07-26: 5; 2026-07-27: 5
[8 empty] | Total |  |  | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.9444 | 30
Block 3 | 28 Jul 06 Aug | 02 Aug 10 Aug |  | Activity | Mandays | Days |  | Min. Date | 2026-06-22 | 2026-06-23 | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07 | 1900-02-08 | 1900-02-09 | 1900-02-10 | 1900-02-11 | 1900-02-12 | 1900-02-13 | 1900-02-14 | 1900-02-15 | 1900-02-16 | 1900-02-17 | 1900-02-18 | 1900-02-19 | 1900-02-20 | 1900-02-21 | 1900-02-22 | 1900-02-23 | 1900-02-24 | 1900-02-25 | 1900-02-26 | 1900-02-27 | 1900-02-28 | 1900-03-01 | 1900-03-02 | 1900-03-03 | 1900-03-04 | 1900-03-05 | 1900-03-06 | 1900-03-07 | 1900-03-08 | 1900-03-09 | 1900-03-10 | 1900-03-11 | 1900-03-12 | 1900-03-13 | 1900-03-14 | 1900-03-15 | 1900-03-16 | 1900-03-17 | 1900-03-18 | 1900-03-19 | 1900-03-20 | 1900-03-21 | 1900-03-22 | 1900-03-23 | 1900-03-24 | 1900-03-25 | 1900-03-26 | 1900-03-27 | 1900-03-28 | 1900-03-29 | 1900-03-30 | 1900-03-31 | 1900-04-01 | 1900-04-02 | 1900-04-03 | 1900-04-04 | 1900-04-05 | 1900-04-06 | 1900-04-07 | 1900-04-08 | 1900-04-09 | 1900-04-10 | 1900-04-11 | 1900-04-12 | 1900-04-13 | 1900-04-14 | 1900-04-15 | 1900-04-16 | 1900-04-17 | 1900-04-18 | 1900-04-19 | 1900-04-20 | 1900-04-21 | 1900-04-22 | 1900-04-23 | 1900-04-24 | 1900-04-25 | 1900-04-26 | 1900-04-27 | 1900-04-28 | 1900-04-29 | 1900-04-30 | 1900-05-01 | 1900-05-02 | 1900-05-03 | 1900-05-04 | 1900-05-05 | 1900-05-06 | 1900-05-07 | 1900-05-08 | 1900-05-09
|  |  | 05 Aug 13 Aug | Erection | 4 | 1 |  | 2026-07-30 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 4 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | 155.21 | 1 |  | 2026-07-30 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 155 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | 127.0667 | 4 |  | 2026-08-01 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 32 | 32 | 32 | 32 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 221.6667 | 5 |  | 2026-07-31 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 44 | 44 | 44 | 44 | 44 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 | 30 |  | #VALUE! | 2026-06-30: 5; 2026-07-01: 5; 2026-07-02: 5; 2026-07-03: 5; 2026-07-04: 5; 2026-07-05: 5; 2026-07-06: 5; 2026-07-07: 5; 2026-07-08: 5; 2026-07-09: 5; 2026-07-10: 5; 2026-07-11: 5; 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 30; 2026-07-25: 30; 2026-07-26: 30; 2026-07-27: 30; 2026-07-28: 5; 2026-07-29: 5
[8 empty] | Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 159 | 44 | 76 | 76 | 76 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.9211 | 159
Block 2 | 2026-08-06 | 2026-08-11 |  | Activity | Mandays | Days |  | Min. Date | time axis 2026-06-22 to 2026-11-01
|  |  | 2026-08-14 | Erection | 4 | 9 |  | 2026-07-20 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | 251.3 | 1 |  | 2026-07-30 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 251 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | 2431.0667 | 4 |  | 2026-07-31 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 608 | 608 | 608 | 608 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 317.8133 | 13 |  | 2026-07-25 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 | 30 |  | 2026-08-03 | 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 5; 2026-08-04: 5; 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 30; 2026-08-10: 30; 2026-08-11: 30; 2026-08-12: 30; 2026-08-13: 5; 2026-08-14: 5
[8 empty] | Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 29 | 29 | 29 | 29 | 29 | 280 | 637 | 637 | 637 | 637 | 29 | 29 | 29 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60.0926 | 637
Block 1 | 2026-08-09 | 2026-08-14 |  | Activity | Mandays | Days |  | Min. Date | time axis 2026-06-22 to 2026-11-01
|  |  | 2026-08-17 | Erection | 4 | 10 |  | 2026-07-22 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | 277.83 | 1 |  | 2026-08-03 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 278 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | 2432.6667 | 1 |  | 2026-08-05 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 2433 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 323.4133 | 11 |  | 2026-07-30 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 | 30 |  | 2026-08-06 | 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 5; 2026-08-04: 5; 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 5; 2026-08-10: 5; 2026-08-11: 30; 2026-08-12: 30; 2026-08-13: 30; 2026-08-14: 30; 2026-08-15: 5; 2026-08-16: 5
[8 empty] | Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 34 | 34 | 34 | 34 | 312 | 34 | 2467 | 34 | 34 | 34 | 34 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.5714 | 2467
Block 5 | 28 Aug 14 Sep | 02 Sep 19 Sep |  | Activity | Mandays | Days |  | Min. Date | time axis 2026-06-22 to 2026-11-01
|  |  | 05 Sep 22 Sep | Erection | 47.2 | 36 |  | 2026-07-25 | bar: 2026-06-22 to 2026-11-01
|  |  |  | Cable Laying | 1513.278 | 10 |  | 2026-08-01 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | 2453.6667 | 27 |  | 2026-08-11 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 340.6933 | 38 |  | 2026-08-05 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 | 30 |  | #VALUE! | 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 5; 2026-08-15: 5; 2026-08-16: 5; 2026-08-17: 5; 2026-08-18: 5; 2026-08-19: 5; 2026-08-20: 5; 2026-08-21: 5; 2026-08-22: 5; 2026-08-23: 5; 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 5; 2026-08-29: 5; 2026-08-30: 5; 2026-08-31: 5; 2026-09-01: 5; 2026-09-02: 5; 2026-09-03: 5; 2026-09-04: 5; 2026-09-05: 30; 2026-09-06: 30; 2026-09-07: 30; 2026-09-08: 30; 2026-09-09: 5; 2026-09-10: 5
[8 empty] | Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 152 | 152 | 152 | 152 | 161 | 161 | 161 | 161 | 161 | 161 | 101 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 105 | 105 | 105 | 105 | 105 | 105 | 130 | 130 | 39 | 39 | 14 | 14 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59.4605 | 161
Block 6 | 02 Sep 23 Sep | 07 Sep 27 Sep |  | Activity | Mandays | Days |  | Min. Date | time axis 2026-06-22 to 2026-11-01
|  |  | 10 Sep 30 Sep | Erection | 47.2 | 43 |  | 2026-07-30 | bar: 2026-06-22 to 2026-11-01
|  |  |  | Cable Laying | 1506.8875 | 10 |  | 2026-08-05 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | 2453.6667 | 28 |  | 2026-08-16 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 340.6933 | 44 |  | 2026-08-09 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 | 30 |  | #VALUE! | 2026-09-02: 5; 2026-09-03: 5; 2026-09-04: 5; 2026-09-05: 5; 2026-09-06: 5; 2026-09-07: 5; 2026-09-08: 5; 2026-09-09: 5; 2026-09-10: 5; 2026-09-11: 5; 2026-09-12: 5; 2026-09-13: 5; 2026-09-14: 5; 2026-09-15: 5; 2026-09-16: 5; 2026-09-17: 5; 2026-09-18: 5; 2026-09-19: 5; 2026-09-20: 5; 2026-09-21: 5; 2026-09-22: 5; 2026-09-23: 5; 2026-09-24: 5; 2026-09-25: 5; 2026-09-26: 5; 2026-09-27: 5; 2026-09-28: 5; 2026-09-29: 5; 2026-09-30: 30; 2026-10-01: 30; 2026-10-02: 30; 2026-10-03: 30; 2026-10-04: 5; 2026-10-05: 5
[8 empty] | Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 152 | 152 | 152 | 152 | 160 | 160 | 160 | 160 | 160 | 160 | 9 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 101 | 101 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45.8485 | 160
Block 7 | 12 Sep 23 Sep | 17 Sep 27 Sep |  | Activity | Mandays | Days |  | Min. Date | time axis 2026-06-22 to 2026-11-01
|  |  | 20 Sep 30 Sep | Erection | 59.2 | 40 |  | 2026-08-02 | bar: 2026-06-22 to 2026-11-01
|  |  |  | Cable Laying | 1492.9995 | 7 |  | 2026-08-14 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 213 | 213 | 213 | 213 | 213 | 213 | 213 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | 2453.6667 | 20 |  | 2026-08-26 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 340.6933 | 34 |  | 2026-08-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 | 30 |  | #VALUE! | 2026-09-05: 5; 2026-09-06: 5; 2026-09-07: 5; 2026-09-08: 5; 2026-09-09: 5; 2026-09-10: 5; 2026-09-11: 5; 2026-09-12: 5; 2026-09-13: 5; 2026-09-14: 5; 2026-09-15: 5; 2026-09-16: 5; 2026-09-17: 5; 2026-09-18: 5; 2026-09-19: 5; 2026-09-20: 5; 2026-09-21: 5; 2026-09-22: 5; 2026-09-23: 5; 2026-09-24: 5; 2026-09-25: 5; 2026-09-26: 5; 2026-09-27: 5; 2026-09-28: 5; 2026-09-29: 5; 2026-09-30: 5; 2026-10-01: 5; 2026-10-02: 5; 2026-10-03: 30; 2026-10-04: 30; 2026-10-05: 30; 2026-10-06: 30; 2026-10-07: 5; 2026-10-08: 5
[8 empty] | Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 214 | 214 | 214 | 214 | 214 | 224 | 224 | 11 | 11 | 11 | 11 | 11 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 139 | 139 | 139 | 139 | 139 | 139 | 138 | 138 | 138 | 138 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.1275 | 224
Block 8 | 14 Sep 23 Sep | 19 Sep 27 Sep |  | Activity | Mandays | Days |  | Min. Date | time axis 2026-06-22 to 2026-11-01
|  |  | 22 Sep 30 Sep | Erection | 59.2 | 37 |  | 2026-08-05 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | 1464.3285 | 11 |  | 2026-08-12 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | 2453.6667 | 18 |  | 2026-08-28 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 340.6933 | 32 |  | 2026-08-21 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 | 30 |  | #VALUE! | 2026-09-08: 5; 2026-09-09: 5; 2026-09-10: 5; 2026-09-11: 5; 2026-09-12: 5; 2026-09-13: 5; 2026-09-14: 5; 2026-09-15: 5; 2026-09-16: 5; 2026-09-17: 5; 2026-09-18: 5; 2026-09-19: 5; 2026-09-20: 5; 2026-09-21: 5; 2026-09-22: 5; 2026-09-23: 5; 2026-09-24: 5; 2026-09-25: 5; 2026-09-26: 5; 2026-09-27: 5; 2026-09-28: 5; 2026-09-29: 5; 2026-09-30: 5; 2026-10-01: 5; 2026-10-02: 5; 2026-10-03: 30; 2026-10-04: 30; 2026-10-05: 30; 2026-10-06: 30; 2026-10-07: 5; 2026-10-08: 5
[8 empty] | Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 146 | 146 | 13 | 13 | 13 | 13 | 13 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 154 | 154 | 154 | 152 | 152 | 152 | 152 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.7692 | 154
Block 9 | 15 Sep 23 Sep | 20 Sep 27 Sep |  | Activity | Mandays | Days |  | Min. Date | time axis 2026-06-22 to 2026-11-01
|  |  | 23 Sep 30 Sep | Erection | 90.4 | 27 |  | 2026-08-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | 1517.478 | 11 |  | 2026-08-13 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | 2453.6667 | 17 |  | 2026-08-29 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 340.6933 | 35 |  | 2026-08-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 | 39 |  | #VALUE! | 2026-09-12: 5; 2026-09-13: 5; 2026-09-14: 5; 2026-09-15: 5; 2026-09-16: 5; 2026-09-17: 5; 2026-09-18: 5; 2026-09-19: 5; 2026-09-20: 5; 2026-09-21: 5; 2026-09-22: 5; 2026-09-23: 5; 2026-09-24: 5; 2026-09-25: 5; 2026-09-26: 5; 2026-09-27: 5; 2026-09-28: 5; 2026-09-29: 5; 2026-09-30: 5; 2026-10-01: 5; 2026-10-02: 5; 2026-10-03: 5; 2026-10-04: 5; 2026-10-05: 5; 2026-10-06: 30; 2026-10-07: 30; 2026-10-08: 30; 2026-10-09: 30; 2026-10-10: 5; 2026-10-11: 5
[8 empty] | Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 138 | 141 | 141 | 141 | 151 | 151 | 151 | 151 | 151 | 151 | 13 | 13 | 13 | 13 | 13 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 154 | 159 | 159 | 159 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.0561 | 159

## 12 - Daily requirement (hidden)
PSS-12 | IDT Charging / Commissioning Start | Trial-Run End Date | COD | Activity | Mandays | Max dates | Start date | Days | Avg Manpower | Peak Manpower | 2026-06-22 | 2026-06-23 | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07 | 1900-02-08 | 1900-02-09 | 1900-02-10 | 1900-02-11 | 1900-02-12 | 1900-02-13 | 1900-02-14 | 1900-02-15 | 1900-02-16 | 1900-02-17 | 1900-02-18 | 1900-02-19 | 1900-02-20 | 1900-02-21 | 1900-02-22 | 1900-02-23 | 1900-02-24 | 1900-02-25 | 1900-02-26 | 1900-02-27 | 1900-02-28 | 1900-03-01 | 1900-03-02 | 1900-03-03 | 1900-03-04 | 1900-03-05 | 1900-03-06 | 1900-03-07 | 1900-03-08 | 1900-03-09 | 1900-03-10 | 1900-03-11 | 1900-03-12 | 1900-03-13 | 1900-03-14 | 1900-03-15 | 1900-03-16 | 1900-03-17 | 1900-03-18 | 1900-03-19 | 1900-03-20 | 1900-03-21 | 1900-03-22 | 1900-03-23 | Average Manpower | Peak Manpower | #VALUE! | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 | 2026-11-29 | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 2026-12-06 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-12 | 2026-12-13 | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-19 | 2026-12-20 | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-26 | 2026-12-27 | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31
Block 1 | 2026-07-28 | 2026-08-02 | 2026-08-05 | Erection | #VALUE! | 0 | 2026-07-30 | -46233 | 8.3333 | 30 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | #VALUE! | 0 | 2026-07-30 | -46233 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | #VALUE! | 2026-07-30 | 2026-08-06 | -7 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 2026-07-30 | 2026-07-16 | 14 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 | 2026-07-25 |  | 30 | [13 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | [45 empty] | 6.0976 | 30
Block 2 | 31 Jul 02 Aug | 05 Aug 07 Aug |  | Activity | Mandays | Max dates | Start date | Days |  |  | 2026-06-22 | 2026-06-23 | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07 | 1900-02-08 | 1900-02-09 | 1900-02-10 | 1900-02-11 | 1900-02-12 | 1900-02-13 | 1900-02-14 | 1900-02-15 | 1900-02-16 | 1900-02-17 | 1900-02-18 | 1900-02-19 | 1900-02-20 | 1900-02-21 | 1900-02-22 | 1900-02-23 | 1900-02-24 | 1900-02-25 | 1900-02-26 | 1900-02-27 | 1900-02-28 | 1900-03-01 | 1900-03-02 | 1900-03-03 | 1900-03-04 | 1900-03-05 | 1900-03-06 | 1900-03-07 | 1900-03-08 | 1900-03-09 | 1900-03-10 | 1900-03-11 | 1900-03-12 | 1900-03-13 | 1900-03-14 | 1900-03-15 | 1900-03-16 | 1900-03-17 | 1900-03-18 | 1900-03-19 | 1900-03-20 | 1900-03-21 | 1900-03-22 | 1900-03-23
|  |  | 08 Aug 10 Aug | Erection | #VALUE! | 2026-07-30 | 2026-07-30 | 0 | 8.3333 | 30 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | #VALUE! | 2026-07-30 | 2026-07-30 | 0 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | #VALUE! | 2026-08-31 | 2026-08-06 | 25 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 2026-08-04 | 2026-07-21 | 14 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 | #VALUE! |  | 30 | [15 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | [43 empty] | 5.814 | 30
Block 4 | 24 Jul 28 Jul | 29 Jul 02 Aug |  | Activity | Mandays | Max dates | Start date | Days | time axis 2026-06-22 to 2026-09-15
|  |  | 01 Aug 05 Aug | Erection | #VALUE! | 0 | 2026-07-30 | -46233 | 8.3333 | 30 | bar: 2026-06-22 to 2026-09-15
|  |  |  | Cable Laying | #VALUE! | 0 | 2026-07-30 | -46233 | bar: 2026-06-22 to 2026-09-15
|  |  |  | Termination | #VALUE! | 0 | 2026-08-06 | -46240 | bar: 2026-06-22 to 2026-09-15
|  |  |  | Testing | #VALUE! | 0 | -14 | 14 | bar: 2026-06-22 to 2026-09-15
|  |  |  | CFT | 250 | #VALUE! |  | 30 |  |  | 2026-07-08: 5; 2026-07-09: 5; 2026-07-10: 5; 2026-07-11: 5; 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 30; 2026-08-02: 30; 2026-08-03: 30; 2026-08-04: 30; 2026-08-05: 5; 2026-08-06: 5
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [27 empty] | 5.2083 | 30
Block 3 | 2026-08-06 | 2026-08-11 |  | Activity | Mandays | Max dates | Start date | Days | time axis 2026-06-22 to 2026-09-15
|  |  | 2026-08-14 | Erection | #VALUE! | 2026-08-04 | 2026-07-25 | 10 | 8.3333 | 30 | bar: 2026-06-22 to 2026-09-15
|  |  |  | Cable Laying | #VALUE! | 2026-08-04 | 2026-07-30 | 5 | bar: 2026-06-22 to 2026-09-15
|  |  |  | Termination | #VALUE! | 2026-08-01 | 2026-08-06 | -5 | bar: 2026-06-22 to 2026-09-15
|  |  |  | Testing | #VALUE! | 2026-08-03 | 2026-07-20 | 14 | bar: 2026-06-22 to 2026-09-15
|  |  |  | CFT | 250 | 2026-08-03 |  | 30 |  |  | 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 5; 2026-08-04: 5; 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 5; 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 30; 2026-08-13: 30; 2026-08-14: 30; 2026-08-15: 30; 2026-08-16: 5; 2026-08-17: 5
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | [25 empty] | 4.6296 | 5
Block 5 | 2026-08-07 | 2026-08-12 |  | Activity | Mandays | Max dates | Start date | Days | [90 empty] | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | time axis 2026-06-22 to 2026-09-15
|  |  | 2026-08-15 | Erection | #VALUE! | 2026-08-02 | 2026-07-21 | 12 | 8.3333 | 30 | [88 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Cable Laying | #VALUE! | 2026-08-07 | 2026-07-18 | 20 | [90 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Termination | #VALUE! | 2026-08-14 | 2026-07-25 | 20 | [90 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Testing | #VALUE! | 2026-08-04 | 2026-07-21 | 14 | [90 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | CFT | 250 | 2026-08-04 |  | 30 |  |  | 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 5; 2026-08-04: 5; 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 5; 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 5; 2026-08-15: 30; 2026-08-16: 30; 2026-08-17: 30; 2026-08-18: 30; 2026-08-19: 5; 2026-08-20: 5
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block 6 | 2026-08-24 | 2026-08-28 |  | Activity | Mandays | Max dates | Start date | Days | [90 empty] | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | time axis 2026-06-22 to 2026-09-15
|  |  | 2026-08-31 | Erection | #VALUE! | 2026-08-12 | 2026-08-02 | 10 | 8.3333 | 30 | [88 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Cable Laying | #VALUE! | 2026-08-22 | 2026-08-02 | 20 | [90 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Termination | #VALUE! | 2026-08-29 | 2026-08-09 | 20 | [90 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Testing | #VALUE! | 2026-08-21 | 2026-08-07 | 14 | [90 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | CFT | 250 | 2026-08-21 |  | 30 |  |  | 2026-08-04: 5; 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 5; 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 5; 2026-08-15: 5; 2026-08-16: 5; 2026-08-17: 5; 2026-08-18: 5; 2026-08-19: 5; 2026-08-20: 5; 2026-08-21: 5; 2026-08-22: 5; 2026-08-23: 5; 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 30; 2026-08-29: 30; 2026-08-30: 30; 2026-08-31: 30; 2026-09-01: 5; 2026-09-02: 5
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block 7 | 31 Aug 17 Sep | 05 Sep 22 Sep |  | Activity | Mandays | Max dates | Start date | Days | [90 empty] | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | time axis 2026-06-22 to 2026-09-15
|  |  | 08 Sep 25 Sep | Erection | #VALUE! | 2026-08-12 | 2026-08-02 | 10 | #DIV/0! | #VALUE! | [88 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Cable Laying | #VALUE! | 2026-08-22 | 2026-08-02 | 20 | [90 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Termination | #VALUE! | 2026-08-29 | 2026-08-09 | 20 | [90 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Testing | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  |  | CFT | 250 | #VALUE! |  | 30 |  |  | 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 5; 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 5; 2026-08-15: 5; 2026-08-16: 5; 2026-08-17: 5; 2026-08-18: 5; 2026-08-19: 5; 2026-08-20: 5; 2026-08-21: 5; 2026-08-22: 5; 2026-08-23: 5; 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 5; 2026-08-29: 5; 2026-08-30: 5; 2026-08-31: 30; 2026-09-01: 30; 2026-09-02: 30; 2026-09-03: 30; 2026-09-04: 5; 2026-09-05: 5
[7 empty] | Total |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Block 8 | 11 Sep 17 Sep | 16 Sep 22 Sep |  | Activity | Mandays | Max dates | Start date | Days | [90 empty] | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | time axis 2026-06-22 to 2026-09-15
|  |  | 19 Sep 25 Sep | Erection | #VALUE! | 2026-08-12 | 2026-08-02 | 10 | #DIV/0! | #VALUE! | [88 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Cable Laying | #VALUE! | 2026-08-22 | 2026-08-02 | 20 | [90 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Termination | #VALUE! | 2026-08-29 | 2026-08-09 | 20 | [90 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Testing | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  |  | CFT | 250 | #VALUE! |  | 30 |  |  | 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 5; 2026-08-15: 5; 2026-08-16: 5; 2026-08-17: 5; 2026-08-18: 5; 2026-08-19: 5; 2026-08-20: 5; 2026-08-21: 5; 2026-08-22: 5; 2026-08-23: 5; 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 5; 2026-08-29: 5; 2026-08-30: 5; 2026-08-31: 5; 2026-09-01: 5; 2026-09-02: 5; 2026-09-03: 30; 2026-09-04: 30; 2026-09-05: 30; 2026-09-06: 30; 2026-09-07: 5; 2026-09-08: 5
[7 empty] | Total |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[42 empty] | termination | 22 | LD-22
[42 empty] | testing | 16 | LD - 16
5
6
7
8
9
Note on H25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Toay sebdays xzyada aarha tha

## 12 - Daily requirement working (hidden)
PSS-12 | [8 empty] | 2026-06-23
| IDT Charging / Commissioning Start | Trial-Run End Date | COD | Activity | Mandays | Start Date | End Date | Days | Avg Manpower | Peak Manpower | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | Average Manpower | Peak Manpower | #VALUE! | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 | 2026-11-29 | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 2026-12-06 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-12 | 2026-12-13 | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-19 | 2026-12-20 | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-26 | 2026-12-27 | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31
Block 1 | 2026-07-28 | 2026-08-02 | 2026-08-05 | Erection | #VALUE! | 2026-07-30 | 2026-08-09 | 10 | 5 | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | #VALUE! | 2026-07-30 | 0 | -46233 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | #VALUE! | 2026-07-30 | 2026-07-30 | 0 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 2026-07-16 | 2026-07-30 | 14 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | 2026-07-25 | 30 | [13 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5
[6 empty] | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [45 empty] | #VALUE! | #VALUE!
Block 2 | 31 Jul 02 Aug | 05 Aug 07 Aug |  | Activity | Mandays | Start date | Max dates | Days | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-09-15
|  |  | 08 Aug 10 Aug | Erection | #VALUE! | 2026-07-30 | 2026-07-30 | 0 | 5 | #VALUE! | bar: 2026-06-22 to 2026-09-15
|  |  |  | Cable Laying | #VALUE! | 2026-07-30 | 2026-07-30 | 0 | bar: 2026-06-22 to 2026-09-15
|  |  |  | Termination | #VALUE! | 2026-07-30 | 2026-08-31 | 32 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 2026-07-21 | 2026-08-04 | 14 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | #VALUE! | 30 |  |  | 2026-07-05: 5; 2026-07-06: 5; 2026-07-07: 5; 2026-07-08: 5; 2026-07-09: 5; 2026-07-10: 5; 2026-07-11: 5; 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 30; 2026-07-30: 30; 2026-07-31: 30; 2026-08-01: 30; 2026-08-02: 5; 2026-08-03: 5
[6 empty] | Total |  |  |  |  | 2026-06-22: 0; 2026-06-23: 0; 2026-06-24: 0; 2026-06-25: 0; 2026-06-26: 0; 2026-06-27: 0; 2026-06-28: 0; 2026-06-29: 0; 2026-06-30: 0; 2026-07-01: 0; 2026-07-02: 0; 2026-07-03: 0; 2026-07-04: 0; 2026-07-05: 5; 2026-07-06: 5; 2026-07-07: 5; 2026-07-08: 5; 2026-07-09: 5; 2026-07-10: 5; 2026-07-11: 5; 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: #VALUE!; 2026-07-22: #VALUE!; 2026-07-23: #VALUE!; 2026-07-24: #VALUE!; 2026-07-25: #VALUE!; 2026-07-26: #VALUE!; 2026-07-27: #VALUE!; 2026-07-28: #VALUE!; 2026-07-29: #VALUE!; 2026-07-30: #VALUE!; 2026-07-31: #VALUE!; 2026-08-01: #VALUE!; 2026-08-02: #VALUE!; 2026-08-03: #VALUE! | #VALUE! | #VALUE!
Block 4 | 24 Jul 28 Jul | 29 Jul 02 Aug |  | Activity | Mandays | Start date | Max dates | Days | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-09-15
|  |  | 01 Aug 05 Aug | Erection | #VALUE! | 2026-07-30 | 0 | -46233 | 8.3333 | 30 | bar: 2026-06-22 to 2026-09-15
|  |  |  | Cable Laying | #VALUE! | 2026-07-30 | 0 | -46233 | bar: 2026-06-22 to 2026-09-15
|  |  |  | Termination | #VALUE! | 2026-07-30 | 0 | -46233 | bar: 2026-06-22 to 2026-09-15
|  |  |  | Testing | #VALUE! | -14 | 0 | 14 | bar: 2026-06-22 to 2026-09-15
|  |  |  | CFT | 250 |  | #VALUE! | 30 |  |  | 2026-07-08: 5; 2026-07-09: 5; 2026-07-10: 5; 2026-07-11: 5; 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 30; 2026-08-02: 30; 2026-08-03: 30; 2026-08-04: 30; 2026-08-05: 5; 2026-08-06: 5
[6 empty] | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [27 empty] | 5.2083 | 30
Block 3 | 2026-08-06 | 2026-08-11 |  | Activity | Mandays | Start date | Max dates | Days | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-09-15
|  |  | 2026-08-14 | Erection | #VALUE! | 2026-07-30 | 2026-08-09 | 10 | 15 | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | #VALUE! | 2026-07-30 | 2026-07-29 | -1 | bar: 2026-06-22 to 2026-09-15
|  |  |  | Termination | #VALUE! | 2026-07-30 | 2026-08-01 | 2 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 2026-07-20 | 2026-08-03 | 14 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | 2026-08-03 | 30 |  |  | 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 5; 2026-08-04: 5; 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 5; 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 30; 2026-08-13: 30; 2026-08-14: 30; 2026-08-15: 30; 2026-08-16: 5; 2026-08-17: 5
[6 empty] | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | [25 empty] | #VALUE! | #VALUE!
Block 5 | 2026-08-07 | 2026-08-12 |  | Activity | Mandays | Start date | Max dates | Days | Avg Manpower | Peak Manpower | [88 empty] | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | time axis 2026-06-22 to 2026-09-15
|  |  | 2026-08-15 | Erection | #VALUE! | 2026-07-30 | 2026-08-09 | 10 | 13.3333 | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | #VALUE! | 2026-07-30 | 2026-07-30 | 0 | [90 empty] | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 2026-06-22 to 2026-09-15
|  |  |  | Termination | #VALUE! | 2026-07-30 | 2026-08-02 | 3 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 2026-07-21 | 2026-08-04 | 14 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | 2026-08-04 | 30 |  |  | 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 5; 2026-08-04: 5; 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 5; 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 5; 2026-08-15: 30; 2026-08-16: 30; 2026-08-17: 30; 2026-08-18: 30; 2026-08-19: 5; 2026-08-20: 5
[6 empty] | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block 6 | 2026-08-24 | 2026-08-28 |  | Activity | Mandays | Start date | Max dates | Days | Avg Manpower | Peak Manpower | [88 empty] | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | time axis 2026-06-22 to 2026-09-15
|  |  | 2026-08-31 | Erection | #VALUE! | 2026-07-30 | 2026-08-09 | 10 | #DIV/0! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 1 | 1 | 1 | 1 | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | #VALUE! | 2026-07-30 | 2026-08-24 | 25 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | #VALUE! | 2026-08-04 | 2026-08-29 | 25 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 182 | 182 | 182 | 182 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 2026-08-24 | 2026-09-07 | 14 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - |  |  | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | 2026-08-21 | 30 |  |  | 2026-08-04: 5; 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 5; 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 5; 2026-08-15: 5; 2026-08-16: 5; 2026-08-17: 5; 2026-08-18: 5; 2026-08-19: 5; 2026-08-20: 5; 2026-08-21: 5; 2026-08-22: 5; 2026-08-23: 5; 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 30; 2026-08-29: 30; 2026-08-30: 30; 2026-08-31: 30; 2026-09-01: 5; 2026-09-02: 5
[6 empty] | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block 7 | 31 Aug 17 Sep | 05 Sep 22 Sep |  | Activity | Mandays | Start date | Max dates | Days | Avg Manpower | Peak Manpower | [88 empty] | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | time axis 2026-06-22 to 2026-09-15
|  |  | 08 Sep 25 Sep | Erection | #VALUE! | 2026-07-30 | 2026-08-09 | 10 | #DIV/0! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 1 | 1 | 1 | 1 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | #VALUE! | 2026-07-30 | 2026-08-24 | 25 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | #VALUE! | 2026-08-04 | 2026-08-29 | 25 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | 136 | 136 | 136 | 136 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 2026-08-24 | 2026-09-07 | 14 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - |  |  | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | #VALUE! | 30 |  |  | 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 5; 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 5; 2026-08-15: 5; 2026-08-16: 5; 2026-08-17: 5; 2026-08-18: 5; 2026-08-19: 5; 2026-08-20: 5; 2026-08-21: 5; 2026-08-22: 5; 2026-08-23: 5; 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 5; 2026-08-29: 5; 2026-08-30: 5; 2026-08-31: 30; 2026-09-01: 30; 2026-09-02: 30; 2026-09-03: 30; 2026-09-04: 5; 2026-09-05: 5
[6 empty] | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block 8 | 11 Sep 17 Sep | 16 Sep 22 Sep |  | Activity | Mandays | Start date | Max dates | Days | Avg Manpower | Peak Manpower | [88 empty] | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | time axis 2026-06-22 to 2026-09-15
|  |  | 19 Sep 25 Sep | Erection | #VALUE! | 2026-07-30 | 2026-08-18 | 19 | 5 | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 1 | 1 | 1 | 1 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | #VALUE! | 2026-07-30 | 2026-08-24 | 25 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | #VALUE! | 2026-08-04 | 2026-08-29 | 25 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 136 | 136 | 136 | 136 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 2026-08-24 | 2026-09-07 | 14 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - |  |  | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | #VALUE! | 30 |  |  | 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 5; 2026-08-15: 5; 2026-08-16: 5; 2026-08-17: 5; 2026-08-18: 5; 2026-08-19: 5; 2026-08-20: 5; 2026-08-21: 5; 2026-08-22: 5; 2026-08-23: 5; 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 5; 2026-08-29: 5; 2026-08-30: 5; 2026-08-31: 5; 2026-09-01: 5; 2026-09-02: 5; 2026-09-03: 30; 2026-09-04: 30; 2026-09-05: 30; 2026-09-06: 30; 2026-09-07: 5; 2026-09-08: 5
[6 empty] | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Total of all blocks |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 10 | 10 | 10 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Avg. |  |  | 2026-06-22: #VALUE!; 2026-06-23: #VALUE!
[8 empty] | Peak |  |  | 2026-06-22: #VALUE!; 2026-06-23: #VALUE!

## 11 - Daily requirement (hidden)
PSS-11 | [8 empty] | 2026-06-23
| IDT Charging / Commissioning Start | Trial-Run End Date | COD | Activity | Mandays | Start date | End Date | Days | Avg Manpower | Peak Manpower | [135 empty] | 2026-12-26 | 2026-12-27 | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31 | time axis 2026-06-22 to 2026-11-01
Block 4 | 22 Jul 28 Jul | 27 Jul 02 Aug | 30 Jul 05 Aug | Erection | 0 | 2026-07-30 | 0 | -46233 | 8.4667 | 30 | bar: 2026-06-22 to 2026-11-01
|  |  |  | Cable Laying | 0 | 2026-07-30 | 0 | -46233 | bar: 2026-06-22 to 2026-11-01
|  |  |  | Termination | 0 | 2026-07-30 | 0 | -46233 | bar: 2026-06-22 to 2026-11-01
|  |  |  | Testing | 0.004 | -14 | 0 | 14 | bar: 2026-06-22 to 2026-11-01
|  |  |  | CFT | 250 |  | #VALUE! | 30 |  |  | 2026-06-26: 5; 2026-06-27: 5; 2026-06-28: 5; 2026-06-29: 5; 2026-06-30: 5; 2026-07-01: 5; 2026-07-02: 5; 2026-07-03: 5; 2026-07-04: 5; 2026-07-05: 5; 2026-07-06: 5; 2026-07-07: 5; 2026-07-08: 5; 2026-07-09: 5; 2026-07-10: 5; 2026-07-11: 5; 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 30; 2026-07-21: 30; 2026-07-22: 30; 2026-07-23: 30; 2026-07-24: 5; 2026-07-25: 5
[6 empty] | Total |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 5 | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.0556 | 30
Block 3 | 28 Jul 06 Aug | 02 Aug 10 Aug |  | Activity | Mandays | Start date | End Date | Days | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-11-01
|  |  | 05 Aug 13 Aug | Erection | 4 | 2026-07-30 | 2026-07-30 | 0 | #DIV/0! | #VALUE! | bar: 2026-06-22 to 2026-11-01
|  |  |  | Cable Laying | 155.21 | 2026-07-30 | 2026-07-30 | 0 | bar: 2026-06-22 to 2026-11-01
|  |  |  | Termination | 127.0667 | 2026-07-30 | 2026-08-19 | 20 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 221.6667 | #VALUE! | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  |  | CFT | 250 |  | #VALUE! | 30 |  |  | 2026-07-02: 5; 2026-07-03: 5; 2026-07-04: 5; 2026-07-05: 5; 2026-07-06: 5; 2026-07-07: 5; 2026-07-08: 5; 2026-07-09: 5; 2026-07-10: 5; 2026-07-11: 5; 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 30; 2026-07-27: 30; 2026-07-28: 30; 2026-07-29: 30; 2026-07-30: 5; 2026-07-31: 5
[6 empty] | Total |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Block 2 | 2026-08-06 | 2026-08-11 |  | Activity | Mandays | Start date | End Date | Days | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-11-01
|  |  | 2026-08-14 | Erection | 4 | 2026-07-30 | 2026-08-09 | 10 | 61.2653 | 134 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | 251.3 | 2026-07-30 | 2026-07-30 | 0 | bar: 2026-06-22 to 2026-11-01
|  |  |  | Termination | 2431.0667 | 2026-07-30 | 2026-08-29 | 30 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 317.8133 | 2026-07-23 | 2026-08-06 | 14 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | 2026-08-03 | 30 |  |  | 2026-07-11: 5; 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 5; 2026-08-04: 30; 2026-08-05: 30; 2026-08-06: 30; 2026-08-07: 30; 2026-08-08: 5; 2026-08-09: 5
[6 empty] | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 109 | 109 | 109 | 109 | 109 | 134 | 134 | 111 | 111 | 86 | 86 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.8627 | 134
Block 1 | 2026-08-09 | 2026-08-14 |  | Activity | Mandays | Start date | End Date | Days | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-11-01
|  |  | 2026-08-17 | Erection | 4 | 2026-07-30 | 2026-08-09 | 10 | 64.6667 | 167 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | 277.83 | 2026-07-30 | 2026-08-03 | 4 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 69 | 69 | 69 | 69 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | 2432.6667 | 2026-07-30 | 2026-09-03 | 35 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 323.4133 | 2026-07-26 | 2026-08-09 | 14 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | 2026-08-06 | 30 |  |  | 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 5; 2026-08-04: 5; 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 30; 2026-08-08: 30; 2026-08-09: 30; 2026-08-10: 30; 2026-08-11: 5; 2026-08-12: 5
[6 empty] | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 28 | 28 | 28 | 28 | 167 | 167 | 167 | 167 | 98 | 98 | 98 | 98 | 123 | 123 | 100 | 100 | 75 | 75 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.4444 | 167
Block 5 | 28 Aug 14 Sep | 02 Sep 19 Sep |  | Activity | Mandays | Start date | End Date | Days | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-11-01
|  |  | 05 Sep 22 Sep | Erection | 47.2 | 2026-07-30 | 2026-08-09 | 10 | 128.5 | 203 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 5 | 5 | 5 | 5 | 5 | 1 | 1 | 1 | 1 | 5 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | 1513.278 | 2026-07-30 | 2026-08-24 | 25 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | 1993.0667 | 2026-08-04 | 2026-08-29 | 25 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 136 | 136 | 136 | 136 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 340.6933 | 2026-08-19 | 2026-09-02 | 14 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | #VALUE! | 30 |  |  | 2026-08-02: 5; 2026-08-03: 5; 2026-08-04: 5; 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 5; 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 5; 2026-08-15: 5; 2026-08-16: 5; 2026-08-17: 5; 2026-08-18: 5; 2026-08-19: 5; 2026-08-20: 5; 2026-08-21: 5; 2026-08-22: 5; 2026-08-23: 5; 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 30; 2026-08-27: 30; 2026-08-28: 30; 2026-08-29: 30; 2026-08-30: 5; 2026-08-31: 5
[6 empty] | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 66 | 66 | 71 | 71 | 203 | 203 | 203 | 203 | 151 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 170 | 170 | 170 | 170 | 170 | 109 | 109 | 134 | 134 | 134 | 54 | 29 | 29 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71.623 | 203
Block 6 | 02 Sep 23 Sep | 07 Sep 27 Sep |  | Activity | Mandays | Start date | End Date | Days | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-11-01
|  |  | 10 Sep 30 Sep | Erection | 47.2 | 2026-07-30 | 2026-08-09 | 10 | 114.8421 | 202 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 1 | 1 | 1 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | 1506.8875 | 2026-07-30 | 2026-08-24 | 25 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | 1993.0667 | 2026-08-04 | 2026-08-29 | 25 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 80 | 80 | 80 | 80 | 80 | 136 | 136 | 136 | 136 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 340.6933 | 2026-08-19 | 2026-09-02 | 14 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | #VALUE! | 30 |  |  | 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 5; 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 5; 2026-08-15: 5; 2026-08-16: 5; 2026-08-17: 5; 2026-08-18: 5; 2026-08-19: 5; 2026-08-20: 5; 2026-08-21: 5; 2026-08-22: 5; 2026-08-23: 5; 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 5; 2026-08-29: 5; 2026-08-30: 5; 2026-08-31: 30; 2026-09-01: 30; 2026-09-02: 30; 2026-09-03: 30; 2026-09-04: 5; 2026-09-05: 5
[6 empty] | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 65 | 65 | 65 | 65 | 145 | 145 | 145 | 150 | 150 | 202 | 202 | 202 | 202 | 145 | 145 | 145 | 145 | 145 | 145 | 169 | 169 | 169 | 169 | 169 | 109 | 109 | 109 | 109 | 109 | 29 | 29 | 54 | 54 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67.1385 | 202
Block 7 | 12 Sep 23 Sep | 17 Sep 27 Sep |  | Activity | Mandays | Start date | End Date | Days | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-11-01
|  |  | 20 Sep 30 Sep | Erection | 59.2 | 2026-07-30 | 2026-08-09 | 10 | 91.125 | 226 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | - | - | - | - | - | - | - | - | - | - | 1 | 1 | 1 | 1 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | 1492.9995 | 2026-07-30 | 2026-08-24 | 25 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | 1993.0667 | 2026-08-04 | 2026-08-29 | 25 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 136 | 136 | 136 | 136 | 80 | 80 | 80 | 80 | 80 | 80 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 340.6933 | 2026-08-19 | 2026-09-02 | 14 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | #VALUE! | 30 |  |  | 2026-08-17: 5; 2026-08-18: 5; 2026-08-19: 5; 2026-08-20: 5; 2026-08-21: 5; 2026-08-22: 5; 2026-08-23: 5; 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 5; 2026-08-29: 5; 2026-08-30: 5; 2026-08-31: 5; 2026-09-01: 5; 2026-09-02: 5; 2026-09-03: 5; 2026-09-04: 5; 2026-09-05: 5; 2026-09-06: 5; 2026-09-07: 5; 2026-09-08: 5; 2026-09-09: 5; 2026-09-10: 30; 2026-09-11: 30; 2026-09-12: 30; 2026-09-13: 30; 2026-09-14: 5; 2026-09-15: 5
[6 empty] | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 66 | 66 | 66 | 66 | 146 | 146 | 146 | 146 | 146 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 145 | 145 | 226 | 226 | 226 | 226 | 169 | 109 | 109 | 109 | 109 | 109 | 29 | 29 | 29 | 29 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64.3235 | 226
Block 8 | 14 Sep 23 Sep | 19 Sep 27 Sep |  | Activity | Mandays | Start date | End Date | Days | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-11-01
|  |  | 22 Sep 30 Sep | Erection | 59.2 | 2026-07-30 | 2026-08-09 | 10 | 86.98 | 225 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | - | - | - | - | - | - | - | - | - | - | - | - | 1 | 1 | 1 | 1 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | 1464.3285 | 2026-07-30 | 2026-08-24 | 25 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | 1993.0667 | 2026-08-04 | 2026-08-29 | 25 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 136 | 136 | 136 | 136 | 80 | 80 | 80 | 80 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 340.6933 | 2026-08-19 | 2026-09-02 | 14 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | #VALUE! | 30 |  |  | 2026-08-19: 5; 2026-08-20: 5; 2026-08-21: 5; 2026-08-22: 5; 2026-08-23: 5; 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 5; 2026-08-29: 5; 2026-08-30: 5; 2026-08-31: 5; 2026-09-01: 5; 2026-09-02: 5; 2026-09-03: 5; 2026-09-04: 5; 2026-09-05: 5; 2026-09-06: 5; 2026-09-07: 5; 2026-09-08: 5; 2026-09-09: 5; 2026-09-10: 5; 2026-09-11: 5; 2026-09-12: 30; 2026-09-13: 30; 2026-09-14: 30; 2026-09-15: 30; 2026-09-16: 5; 2026-09-17: 5
[6 empty] | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 65 | 65 | 65 | 65 | 145 | 145 | 145 | 145 | 145 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 168 | 168 | 225 | 225 | 225 | 166 | 109 | 109 | 109 | 109 | 29 | 29 | 29 | 29 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62.1286 | 225
Block 9 | 15 Sep 23 Sep | 20 Sep 27 Sep |  | Activity | Mandays | Start date | End Date | Days | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-11-01
|  |  | 23 Sep 30 Sep | Erection | 90.4 | 2026-07-30 | 2026-08-09 | 10 | 86.8431 | 227 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | - | - | - | - | - | - | - | - | - | - | - | - | - | 1 | 1 | 1 | 1 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | 1517.478 | 2026-07-30 | 2026-08-24 | 25 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | 1993.0667 | 2026-08-04 | 2026-08-29 | 25 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 136 | 136 | 136 | 136 | 80 | 80 | 80 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 340.6933 | 2026-08-19 | 2026-09-02 | 14 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | #VALUE! | 30 |  |  | 2026-08-20: 5; 2026-08-21: 5; 2026-08-22: 5; 2026-08-23: 5; 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 5; 2026-08-29: 5; 2026-08-30: 5; 2026-08-31: 5; 2026-09-01: 5; 2026-09-02: 5; 2026-09-03: 5; 2026-09-04: 5; 2026-09-05: 5; 2026-09-06: 5; 2026-09-07: 5; 2026-09-08: 5; 2026-09-09: 5; 2026-09-10: 5; 2026-09-11: 5; 2026-09-12: 5; 2026-09-13: 30; 2026-09-14: 30; 2026-09-15: 30; 2026-09-16: 30; 2026-09-17: 5; 2026-09-18: 5
[6 empty] | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 70 | 70 | 70 | 70 | 150 | 150 | 150 | 150 | 150 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 165 | 170 | 170 | 227 | 227 | 166 | 166 | 109 | 109 | 109 | 29 | 29 | 29 | 29 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Total of all blocks |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | Avg. |  |  | 2026-06-22: #VALUE!; 2026-06-23: #VALUE!
[8 empty] | Peak |  |  | 2026-06-22: #VALUE!; 2026-06-23: #VALUE!

## BESS 11
BESS 11 Charging Schedule | [17 empty] | 2026-07-30 |  |  | Common for PSS
Container Make | Block No. | Containers at Site | MWh | IDT Charging / Commissioning Start | Trial-Run End Date | COD | Status | [7 empty] | Productivity | Manpower | Total Mandays | Remarks |  |  | Tools & tackles | Required At site | Available At site
[7 empty] | Sr. | Activity | Progress |  |  | EDC | New EDC | vendor
[9 empty] | S | C | B
CATL | 4 | 28 Jun, 05 Jul | 271 MWh (48 Containers) | 22 Jul 28 Jul | 27 Jul 02 Aug | 30 Jul 05 Aug |  |  |  | Civil | [10 empty] | Machinery
[7 empty] | 4.1 | BCF Precast Erection & Welding | 48 | 48 | 0 | Completed |  | MSC | 1 | 2 | 0 |  |  |  | Cable jack | 6
[7 empty] | 4.2 | CT Rail Fixing | 6 | 6 | 0 | Completed |  | MSC | 1 | 16 | 0 |  |  |  | JCB | 6
[7 empty] | 4.3 | PCS Slab casting | 6 | 6 | 0 | Completed |  | MSC | 1 | 39 | 0 |  |  |  | Excavator | 1
[7 empty] | 4.4 | SGR Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 37 | 0 |  |  |  | farana | 6
[7 empty] | 4.5 | MCR Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 34 | 0 |  |  |  | DG with Sablizer | 8
[7 empty] | 4.6 | CSS Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 54 | 0 |  |  |  | Welding Machine | 10
[7 empty] | 4.7 | BOT Slab casting | 3 | 3 | 0 | Completed |  | MSC | 1 | 5 | 0 |  |  |  | HOT Gun | 20
[7 empty] | 4.8 | NIFPS Precast Erection | 6 | 6 | 0 | Completed |  | MSC | 1 | 5 | 0 |  |  |  | Blower | 10
[7 empty] | 4.9 | PCS PEB | 6 | 6 | 0 | Completed |  | Synergy | 1 | 27 | 0 |  |  |  | Drilling Machine | 5
[7 empty] | 4.1 | SGR PEB | 1 | 1 | 0 | Completed |  | Synergy | 1 | 25 | 0 |  |  |  | Drilling Machine [Hammering] | 2
[7 empty] | 4.11 | MCR PEB | 1 | 1 | 0 | Completed |  | RV Enterprise | [6 empty] | Auger Machine | 1
[10 empty] | Electrical | [10 empty] | Tractor | 2
[7 empty] | 4.12 | CT Erection | 6 | 6 | 0 | Completed |  | Pratibha | 2 | 8 | 0 |  |  |  | Cable Puller | 2
[7 empty] | 4.13 | PCS Erection | 48 | 48 | 0 | Completed |  | Pratibha | 10 | 8 | 0 |  |  |  | Testing Kits
[7 empty] | 4.14 | ACDB Erection | 6 | 6 | 0 | Completed |  | Pratibha | 5 | 4 | 0 |  |  |  | Megar | 5
[7 empty] | 4.15 | ECP Panel Erection (Communication Panel) | 6 | 6 | 0 | Completed |  | Pratibha | 6 | 8 | 0 |  |  |  | Filtration Machine | 1
[7 empty] | 4.16 | HT Panel Erection | 2 | 2 | 0 | Completed |  | Pratibha | 1 | [5 empty] | Online PPM Meter | 1
[7 empty] | 4.17 | EMS Panel Erection | 1 | 1 | 0 | Completed |  | Pratibha | 1 | [5 empty] | SFRA Test kit | 1
[7 empty] | 4.18 | CSS Erection | 1 | 1 | 0 | Completed |  | Pratibha | 1 | [5 empty] | Tan delta kit | 1
* Min. 60 termination teams required for DC & LT Cable termination with crimping tool (Each team required at least 01 skilled technician with 01 helper) Common for PSS Available - 26 teams (52 Technician) of DC & LT Cable Termination & 2 HT Cable Termination Teams Machinery - Crimping tool: 60, Cable jack: 06, JCB: 06, Excavator: 01, Farana: 06, DG: 08, Welding machine: 10 (Common For PSS) Testing To be Completed by 19 Jul, 22 july, 26 July. Required Testing Team (6 Skilled & 12 Unskilled) (Common For PSS) Testing kits : Oil Filteration, Online PPM Meter, SFRA & Tan Delta, DC Winding Resistance, Turn Ratio meter, routine test kit (common for 1 PSS) ERT, DC High POT, (common for 1 PSS) VLF kit (1 nos), IR Tester, Multimeter & Clamp Meter (atleast 3 per PSS) Breaker CRM & Timing, Vaccum Bottle Integrity (common for 1 PSS), CT Analyzer (2 nos), Relay Testing Kit, CT Primary Injection (3-Phase), PT Stability (3-Phase), Impedence meter (Common for 1 PSS) | [6 empty] | 4.19 | NIFPS Panel Erection | 6 | 6 | 0 | Completed |  | Ornet / EMR | 6 | - | - |  |  |  | Routine test kit | 1
[7 empty] | 4.2 | NIFPS Fabrication | 6 | 6 | 0 | Completed |  | Ornet / EMR | 0.66667 | 0 | 0 |  |  |  | CT Analyzer | 2
[7 empty] | 4.21 | Battery Container Erection | 48 | 48 | 0 | Completed |  | HEFT & Pratibha | 10 | 4 | 0 |  |  |  | ERT Meter | 1
[7 empty] | 4.22 | HT cable laying | 6909 | 6909 | 0 | Completed |  | Pratibha | 1500 | 48 | 0 |  |  |  | Primary injection kit | 1
[7 empty] | 4.23 | HT cable termination | 28 | 28 | 0 | Completed |  | Pratibha | 8 | 6 | 0 |  |  |  | PT test kit | 1
[7 empty] | 4.24 | DC Cable laying | 13556 | 13556 | 0 | Completed |  | Pratibha | 600 | 10 | 0 |  |  |  | 3 Phase Primary injection kit | 1
[7 empty] | 4.25 | LT Cable laying | 44160 | 44160 | 0 | Completed |  | Pratibha | 600 | 10 | 0 |  |  |  | Breaker, CRM, Timming & vacuum Bottle test kits | 1 | 1
[7 empty] | 4.26 | DC Cable termination | 1536 | 1536 | 0 | Completed |  | Pratibha | 30 | 18 | 0 |  |  |  | DC high Pot kit | 1
[7 empty] | 4.27 | LT Cable termination | 2304 | 2304 | 0 | Completed |  | Pratibha | 30 | 18 | 0 |  |  |  | VLF Kit | 1
[7 empty] | 4.28 | Aux Cable laying | 7701 | 7701 | 0 | Completed |  | Pratibha | 800 | 10 | 0 |  |  |  | Relay Secondary injection kit | 2
[7 empty] | 4.29 | Control Cable laying | 13198 | 13198 | 0 | Completed |  | Pratibha | 1000 | 10 | 0 |  |  |  | Multimeter, IR Tester & Clamp meter | 3 | 2
[7 empty] | 4.3 | Communication Cable laying | 5175 | 5175 | 0 | Completed |  | Pratibha | 600 | 10 | 0 |  |  |  | Impedance Meter | 2
[7 empty] | 4.31 | Aux Cable termination | 284 | 284 | 0 | Completed |  | Pratibha | 30 | 6 | 0
[7 empty] | 4.32 | Control Cable termination | 504 | 504 | 0 | Completed |  | Akshar & Emerson | 30 | 4 | 0 |  |  |  | Tools
[7 empty] | 4.33 | Communication Cable termination | 380 | 380 | 0 | Completed |  | Akshar & Emerson | - | - | - |  | #VALUE! | 0.004 | Crimping tool | 60
[7 empty] | 4.34 | CT SFRA & Tan delta Test | 6 | 6 | 0 | Completed |  | Canbay | - | - | - |  |  |  | Torque Wrench | 10
[7 empty] | 4.35 | CT Routine Test | 6 | 6 | 0 | Completed |  | Pratibha | 2 | 8 | 0 |  |  |  | Tool Set | 10
[7 empty] | 4.36 | CT Control scheme & Stability Test | 6 | 6 | 0 | Completed |  | Akshar | 2 | 4 | 0 |  | #VALUE! | 0.004 | Cable Cutter | 10
[7 empty] | 4.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | 12 | 12 | 0 | Completed |  | Pratibha | 0.5 | 4 | 0
[7 empty] | 4.38 | HT Panel relay test | 16 | 16 | 0 | Completed |  | Pratibha | 6 | 4 | 0
[7 empty] | 4.39 | HT Cable VLF Test | 14 | 14 | 0 | Completed |  | Pratibha | 6 | 5 | 0
[7 empty] | 4.4 | CSS routine test | 1 | 1 | 0 | Completed |  | Pratibha | 1 | 5 | 0
[7 empty] | 4.41 | ACDB routine test | 6 | 6 | 0 | Completed |  | Pratibha | 3 | 5 | 0
[7 empty] | 4.42 | Earthing | 5069.8 | 5069.7 | 0.1 | Completed |  | Pratibha | 150 | 6 | 0.004
[7 empty] | 4.43 | LA | 10 | 10 | 0 | Completed |  | Pratibha | 5 | 6 | 0 | CFT to be completed by 30 Jul.
CATL | 3 | 04 Jul, 08 Jul, 13 Jul | 271 MWh (48 Containers) | 28 Jul 06 Aug | 02 Aug 10 Aug | 05 Aug 13 Aug |  |  |  | Civil
[7 empty] | 3.1 | BCF Precast Erection & Welding | 48 | 48 | 0 | Completed |  | MSC | 1 | 2 | 0
[7 empty] | 3.2 | CT Rail Fixing | 6 | 6 | 0 | Completed |  | MSC | 1 | 16 | 0
[7 empty] | 3.3 | PCS Slab casting | 6 | 6 | 0 | Completed |  | MSC | 1 | 39 | 0
[7 empty] | 3.4 | SGR Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 37 | 0
[7 empty] | 3.5 | MCR Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 34 | 0
[7 empty] | 3.6 | CSS Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 54 | 0
[7 empty] | 3.7 | BOT Slab casting | 2 | 2 | 0 | Completed |  | MSC | 1 | 5 | 0
[7 empty] | 3.8 | BOT Precast Erection | 1 | 1 | 0 | Completed |  | Sachi | 3 | 5 | 0
[7 empty] | 3.9 | NIFPS Precast Erection | 6 | 6 | 0 | Completed |  | MSC | 1 | 5 | 0
[7 empty] | 3.1 | PCS PEB | 6 | 6 | 0 | Completed |  | Synergy | 1 | 27 | 0
[7 empty] | 3.11 | SGR PEB | 1 | 1 | 0 | Completed |  | Synergy | 1 | 25 | 0
[7 empty] | 3.12 | MCR PEB | 1 | 1 | 0 | Completed |  | RV Enterprise | - | - | -
Electrical
[7 empty] | 3.13 | CT Erection | 6 | 6 | 0 | Completed |  | Pratibha | 2 | 4 | 0
[7 empty] | 3.14 | PCS Erection | 48 | 48 | 0 | Completed |  | Pratibha | 10 | 4 | 0
[7 empty] | 3.15 | ACDB Erection | 6 | 6 | 0 | Completed |  | Pratibha | 5 | 4 | 0
[7 empty] | 3.16 | ECP Panel Erection (Communication Panel) | 6 | 6 | 0 | Completed |  | Pratibha/ Akshar | 20 | 4 | 4
[7 empty] | 3.17 | HT Panel Erection | 2 | 2 | 0 | Completed |  | Pratibha/ Akshar | 10
[7 empty] | 3.18 | EMS Panel Erection | 1 | 0 | 1 | 04 Jul, 07 Jul, 25 Jul, 30 Jul | 2026-07-30 | Akshar | 10 |  |  | Placed on slab, welding WIP
[7 empty] | 3.19 | CSS Erection | 1 | 1 | 0 | Completed |  | Pratibha/ Akshar | 10
[7 empty] | 3.2 | NIFPS Panel Erection | 6 | 6 | 0 | Completed |  | Ornet / EMR | 20
[7 empty] | 3.21 | NIFPS Fabrication | 6 | 6 | 0 | Completed |  | Ornet / EMR | 0.66667 | 0 | 0
[7 empty] | 3.22 | Battery Container Erection | 48 | 48 | 0 | Completed |  | HEFT & Pratibha | 10 | 4 | 0
[7 empty] | 3.23 | HT cable laying | 7650 | 7650 | 0 | Completed |  | Pratibha | 1500 | 48 | 0
[7 empty] | 3.24 | HT cable termination | 28 | 28 | 0 | 11 Jul, 12 Jul, 26 Jul, 04 Aug | 2026-08-04 | Pratibha/ Akshar | 8 | 6 | 0 | Lugging complete, Torquing pending.
[7 empty] | 3.25 | DC Cable laying | 13780 | 13780 | 0 | Completed |  | Pratibha | 600 | 10 | 0
[7 empty] | 3.26 | LT Cable laying | 45596 | 45596 | 0 | Completed |  | Pratibha | 600 | 10 | 0
[7 empty] | 3.27 | DC Cable termination | 1536 | 1536 | 0 | 15 Jul, 18 Jul, 25 Jul, 01 Aug | 2026-08-01 | Akshar | 30 | 18 | 0 | Only Lugging WIP, Torquing YTS.
[7 empty] | 3.28 | LT Cable termination | 2304 | 2304 | 0 | 15 Jul, 18 Jul, 25 Jul, 02 Aug | 2026-08-02 | Akshar | 30 | 18 | 0 | Only Lugging WIP, Torquing YTS.
[7 empty] | 3.29 | Aux Cable laying | 8355 | 6186 | 2169 | 05 Jul, 10 Jul, 25 Jul, 30 Jul | 2026-07-30 | Akshar | 1000 | 10 | 21.69
[7 empty] | 3.3 | Control Cable laying | 13076 | 9308 | 3768 | 05 Jul, 10 Jul, 25 Jul, 30 Jul | 2026-07-30 | Akshar | 1000 | 10 | 37.68
[7 empty] | 3.31 | Communication Cable laying | 4792 | 0 | 4792 | 05 Jul, 10 Jul, 25 Jul, 30 Jul | 2026-07-30 | Akshar | 500 | 10 | 95.84
[7 empty] | 3.32 | Aux Cable termination | 286 | 0 | 286 | 15 Jul, 25 Jul, 27 Jul, 02 Aug | 2026-08-02 | Akshar | 30 | 6 | 57.2
[7 empty] | 3.33 | Control Cable termination | 524 | 0 | 524 | 15 Jul, 25 Jul, 27 Jul, 01 Aug | 2026-08-01 | Akshar & Emerson | 30 | 4 | 69.8667
[7 empty] | 3.34 | Communication Cable termination | 384 | 0 | 384 | 15 Jul, 25 Jul, 27 Jul, 02 Aug | 2026-08-02 | Akshar & Emerson | - | - | - |  | 3 | 507.9433
[7 empty] | 3.35 | CT SFRA & Tan delta Test | 6 | 6 | 0 | Completed |  | Canbay | 2 | 8 | -
[7 empty] | 3.36 | CT Routine Test | 6 | 6 | 0 | Completed |  | Pratibha |  |  | 12
[7 empty] | 3.37 | CT Control scheme & Stability Test | 6 | 0 | 6 | 25 Jul, 28 Jul, 04 Aug | 2026-08-04 | Akshar | 2 | 4 | 12 |  | 5 | 507.9433
[7 empty] | 3.38 | HT Panel Routine (CT & PT, Breaker & Meter) Test | 12 | 0 | 12 | 11 Jul, 19 Jul, 25 Jul, 31 Jul | 2026-07-31 | Akshar | 0.5 | 4 | 96 | HT Panel - breaker test completed
[7 empty] | 3.39 | HT Panel relay test | 16 | 0 | 16 | 23 Jul, 27 Jul, 03 Aug | 2026-08-03 | Akshar | 6 | 4 | 10.6667
[7 empty] | 3.4 | HT Cable VLF Test | 14 | 14 | 0 | Completed |  | Pratibha/ Akshar | 6 | 5 | 0
[7 empty] | 3.41 | CSS routine test | 1 | 0 | 1 | 11 Jul, 20 Jul, 25 Jul, 31 Jul | 2026-07-31 | Akshar | 1 | 5 | 5
[7 empty] | 3.42 | ACDB routine test | 6 | 6 | 0 | Completed |  | Akshar | 3 | 5 | 0
[7 empty] | 3.43 | Earthing | 4284 | 2434 | 1850 | 13 Jul, 19 Jul, 26 Jul, 02 Aug | 2026-08-02 | Akshar | 150 | 6 | 74
[7 empty] | 3.44 | LA | 10 | 0 | 10 | 15 Jul, 25 Jul, 02 Aug | 2026-08-02 | Akshar | 5 | 6 | 12
CATL | 2 | 13 Jul, 20 Jul 21 Jul | 271 MWh (48 Containers) | 2026-08-06 | 2026-08-11 | 2026-08-14 |  |  |  | Civil
[7 empty] | 2.1 | BCF Precast Erection & Welding | 48 | 48 | 0 | Completed |  | MSC | 1 | 2 | 0
[7 empty] | 2.2 | CT Rail Fixing | 6 | 6 | 0 | Completed |  | MSC | 1 | 16 | 0
[7 empty] | 2.3 | PCS Slab casting | 6 | 6 | 0 | Completed |  | MSC | 1 | 39 | 0
[7 empty] | 2.4 | SGR Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 37 | 0
[7 empty] | 2.5 | MCR Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 34 | 0
[7 empty] | 2.6 | CSS Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 54 | 0
[7 empty] | 2.7 | BOT Slab casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 5 | 0
[7 empty] | 2.8 | BOT Precast Erection | 2 | 2 | 0 | Completed |  | Sachi | 3 | 5 | 0
[7 empty] | 2.9 | NIFPS Precast Erection | 6 | 5 | 1 | 22 Jun, 02 Jul, 20 Jul, 28 Jul | 2026-07-28 | MSC | 1 | 5 | 5 | Cable trench excavated, will be done post trench backfilling
[7 empty] | 2.1 | PCS PEB | 6 | 6 | 0 | Completed |  | Synergy | 1 | 27 | 0
[7 empty] | 2.11 | SGR PEB | 1 | 1 | 0 | Completed |  | Synergy | 1 | 25 | 0
[7 empty] | 2.12 | MCR PEB | 1 | 1 | 0 | Completed |  | RV Enterprise | - | - | -
Electrical
[7 empty] | 2.13 | CT Erection | 6 | 6 | 0 | Completed |  | Pratibha | 2 | 4 | 0
[7 empty] | 2.14 | PCS Erection | 48 | 48 | 0 | Completed |  | Pratibha | 10 | 4 | 0
[7 empty] | 2.15 | ACDB Erection | 6 | 6 | 0 | Completed |  | Pratibha | 5 | 4 | 0
[7 empty] | 2.16 | ECP Panel Erection (Communication Panel) | 6 | 0 | 6 | 06 Jul, 10 Jul, 25 Jul | 2026-07-25 | Akshar | 20 | 4 | 4
[7 empty] | 2.17 | HT Panel Erection | 2 | 2 | 0 | Completed |  | Pratibha | 10
[7 empty] | 2.18 | EMS Panel Erection | 1 | 1 | 0 | 05 Jul, 11 Jul, 20 Jul | 2026-07-20 | Pratibha | 10
[7 empty] | 2.19 | CSS Erection | 1 | 1 | 0 | Completed |  | Pratibha | 10
[7 empty] | 2.2 | NIFPS Panel Erection | 6 | 0 | 6 | 11 Jul, 16 Jul, 23 Jul | 2026-07-23 | Ornet / EMR | 20
[7 empty] | 2.21 | NIFPS Fabrication | 6 | 0 | 6 | 15 Jul, 18 Jul, 25 Jul | 2026-07-25 | Ornet / EMR | 0.66667 | 0 | 0
[7 empty] | 2.22 | Battery Container Erection | 48 | 48 | 0 | 18-Jul, 25 Jul, 28 Jul | 2026-07-28 | HEFT & Akshar | 10 | 4 | 0 | Welding with foundation WIP
[7 empty] | 2.23 | HT cable laying | 8171 | 8171 | 0 | Completed |  | Pratibha | 1500 | 48 | 0
[7 empty] | 2.24 | HT cable termination | 28 | 28 | 0 | 20 Jul, 26 Jul, 31 Jul | 2026-07-31 | Akshar | 8 | 6 | 0 | Lugging completed, toquing will be done post VLF testing.
[7 empty] | 2.25 | DC Cable laying | 13292 | 13292 | 0 | Completed |  | Pratibha | 600 | 10 | 0
[7 empty] | 2.26 | LT Cable laying | 46080 | 46080 | 0 | Completed |  | Pratibha | 600 | 10 | 0
[7 empty] | 2.27 | DC Cable termination | 1536 | 0 | 1536 | 24-Jul, 03 Aug | 2026-08-03 | Akshar | 30 | 18 | 921.6
[7 empty] | 2.28 | LT Cable termination | 2304 | 0 | 2304 | 24-Jul, 03 Aug | 2026-08-03 | Akshar | 30 | 18 | 1382.4
[7 empty] | 2.29 | Aux Cable laying | 8391 | 4672 | 3719 | 02 Jul, 07 Jul, 12 Jul, 30 Jul | 2026-07-30 | Akshar | 1000 | 10 | 37.19
[7 empty] | 2.3 | Control Cable laying | 14355 | 2528 | 11827 | 14-Jul, 30 Jul | 2026-07-30 | Akshar | 1000 | 10 | 118.27
[7 empty] | 2.31 | Communication Cable laying | 4792 | 0 | 4792 | 14-Jul, 30 Jul | 2026-07-30 | Akshar | 500 | 10 | 95.84
[7 empty] | 2.32 | Aux Cable termination | 286 | 0 | 286 | 24-Jul, 03 Aug | 2026-08-03 | Akshar | 30 | 6 | 57.2
[7 empty] | 2.33 | Control Cable termination | 524 | 0 | 524 | 24-Jul, 03 Aug | 2026-08-03 | Akshar & Emerson | 30 | 4 | 69.8667
[7 empty] | 2.34 | Communication Cable termination | 384 | 0 | 384 | 24-Jul, 03 Aug | 2026-08-03 | Akshar & Emerson | - | - | - |  | 4 | 3004.18
[7 empty] | 2.35 | CT SFRA & Tan delta Test | 6 | 6 | 0 | Completed |  | Canbay | 2 | 8 | -
[7 empty] | 2.36 | CT Routine Test | 6 | 0 | 6 | 13 Jul, 30 Jul | 2026-07-30 | Akshar |  |  | 12
[7 empty] | 2.37 | CT Control scheme & Stability Test | 6 | 0 | 6 | 03 Aug, 06 Aug | 2026-08-06 | Akshar | 2 | 4 | 12 |  | 7 | 3004.18
[7 empty] | 2.38 | HT Panel Routine (CT & PT, Breaker & Meter) Test | 12 | 0 | 12 | 20 Jul, 29 Jul | 2026-07-29 | Akshar | 0.5 | 4 | 96
[7 empty] | 2.39 | HT Panel relay test | 16 | 0 | 16 | 01 Aug, 05 Aug | 2026-08-05 | Akshar | 6 | 4 | 10.6667
[7 empty] | 2.4 | HT Cable VLF Test | 14 | 0 | 14 | 20 Jul, 25 Jul | 2026-07-25 | Akshar | 6 | 5 | 11.6667
[7 empty] | 2.41 | CSS routine test | 1 | 0 | 1 | 20 Jul, 30 Jul | 2026-07-30 | Akshar | 1 | 5 | 5
[7 empty] | 2.42 | ACDB routine test | 6 | 0 | 6 | 20 Jul, 29 Jul | 2026-07-29 | Akshar | 3 | 5 | 10
[7 empty] | 2.43 | Earthing | 4284 | 572 | 3712 | 22 Jul, 01 Aug | 2026-08-01 | Akshar | 150 | 6 | 148.48
[7 empty] | 2.44 | LA | 10 | 0 | 10 | 22 Jul, 01 Aug | 2026-08-01 | Akshar | 5 | 6 | 12
CATL | 1 | 16 Jul, 23 Jul 24 Jul | 271 MWh (48 Containers) | 2026-08-09 | 2026-08-14 | 2026-08-17 |  |  |  | Civil
[7 empty] | 1.1 | BCF Precast Erection & Welding | 48 | 48 | 0 | Completed |  | MSC | 1 | 2 | 0
[7 empty] | 1.2 | CT Rail Fixing | 6 | 6 | 0 | Completed |  | MSC | 1 | 16 | 0
[7 empty] | 1.3 | PCS Slab casting | 6 | 6 | 0 | Completed |  | MSC | 1 | 39 | 0
[7 empty] | 1.4 | SGR Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 37 | 0
[7 empty] | 1.5 | MCR Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 34 | 0
[7 empty] | 1.6 | CSS Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 54 | 0
[7 empty] | 1.7 | BOT Slab casting | 3 | 3 | 0 | Completed |  | MSC | 1 | 5 | 0
[7 empty] | 1.8 | NIFPS Precast Erection | 6 | 5 | 1 | 24 Jun, 30 Jun, 22 Jul, 28 Jul | 2026-07-28 | MSC | 1 | 5 | 5 | Cable trench excavated, will be done post trench backfilling
[7 empty] | 1.9 | PCS PEB | 6 | 6 | 0 | Completed |  | Synergy | 1 | 27 | 0
[7 empty] | 1.1 | SGR PEB | 1 | 1 | 0 | Completed |  | Synergy | 1 | 25 | 0
[7 empty] | 1.11 | MCR PEB | 1 | 1 | 0 | 01 Jul, 12 Jul, 22 Jul | 2026-07-22 | RV Enterprise | - | - | -
Electrical
[7 empty] | 1.12 | CT Erection | 6 | 6 | 0 | Completed |  | Pratibha | 2 | 4 | 0
[7 empty] | 1.13 | PCS Erection | 48 | 48 | 0 | Completed |  | Pratibha | 10 | 4 | 0
[7 empty] | 1.14 | ACDB Erection | 6 | 6 | 0 | Completed |  | Pratibha | 5 | 4 | 0
[7 empty] | 1.15 | ECP Panel Erection (Communication Panel) | 6 | 0 | 6 | 05 Jul, 13 Jul, 31 Jul | 2026-07-31 | Akshar | 20 | 4 | 4 | Placed on slab, anchoring WIP
[7 empty] | 1.16 | HT Panel Erection | 2 | 2 | 0 | Completed |  | Pratibha | 10
[7 empty] | 1.17 | EMS Panel Erection | 1 | 0 | 1 | 05 Jul, 13 Jul, 22 Jul | 2026-07-22 | Akshar | 10
[7 empty] | 1.18 | CSS Erection | 1 | 1 | 0 | Completed |  | Pratibha | 10
[7 empty] | 1.19 | NIFPS Panel Erection | 6 | 0 | 6 | 15 Jul, 17 Jul, 25 Jul | 2026-07-25 | Ornet / EMR | 20
[7 empty] | 1.2 | NIFPS Fabrication | 6 | 0 | 6 | 20 Jul, 27 Jul, 02 Aug | 2026-08-02 | Ornet / EMR | 0.66667 | 0 | 0
[7 empty] | 1.21 | Battery Container Erection | 48 | 48 | 0 | 21-Jul, 28-Jul | 2026-07-28 | HEFT & Akshar | 10 | 4 | 0
[7 empty] | 1.22 | HT cable laying | 8865 | 8865 | 0 | Completed |  | Pratibha | 1500 | 48 | 0
[7 empty] | 1.23 | HT cable termination | 28 | 28 | 0 | 12 Jul, 20 Jul, 05 Aug | 2026-08-05 | Akshar | 8 | 6 | 0
[7 empty] | 1.24 | DC Cable laying | 13120 | 13120 | 0 | Completed |  | Pratibha | 600 | 10 | 0
[7 empty] | 1.25 | LT Cable laying | 44784 | 44784 | 0 | Completed |  | Pratibha | 600 | 10 | 0
[7 empty] | 1.26 | DC Cable termination | 1536 | 0 | 1536 | 27 Jul, 05 Aug | 2026-08-05 | Akshar | 30 | 18 | 921.6
[7 empty] | 1.27 | LT Cable termination | 2304 | 0 | 2304 | 27 Jul, 05 Aug | 2026-08-05 | Akshar | 30 | 18 | 1382.4
[7 empty] | 1.28 | Aux Cable laying | 8282 | 4573 | 3709 | 17 Jul, 03 Aug | 2026-08-03 | Akshar | 1000 | 10 | 37.09
[7 empty] | 1.29 | Control Cable laying | 14490 | 0 | 14490 | 17 Jul, 03 Aug | 2026-08-03 | Akshar | 1000 | 10 | 144.9
[7 empty] | 1.3 | Communication Cable laying | 4792 | 0 | 4792 | 17 Jul, 03 Aug | 2026-08-03 | Akshar | 500 | 10 | 95.84
[7 empty] | 1.31 | Aux Cable termination | 286 | 0 | 286 | 27 Jul, 05 Aug | 2026-08-05 | Akshar | 30 | 6 | 57.2
[7 empty] | 1.32 | Control Cable termination | 536 | 0 | 536 | 20-Jul, 05 Aug | 2026-08-05 | Akshar & Emerson | 30 | 4 | 71.4667
[7 empty] | 1.33 | Communication Cable termination | 384 | 0 | 384 | 20-Jul, 05 Aug | 2026-08-05 | Akshar & Emerson | - | - | - |  | 6 | 3037.91
[7 empty] | 1.34 | CT SFRA & Tan delta Test | 6 | 6 | 0 | Completed |  | Canbay | 2 | 8 | -
[7 empty] | 1.35 | CT Routine Test | 6 | 0 | 6 | 16-Jul, 03 Aug | 2026-08-03 | Akshar |  |  | 12
[7 empty] | 1.36 | CT Control scheme & Stability Test | 6 | 0 | 6 | 06 Aug, 09 Aug | 2026-08-09 | Akshar | 2 | 4 | 12 |  | 10 | 3037.91
[7 empty] | 1.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | 12 | 0 | 12 | 23- Jul, 03 Aug | 2026-08-03 | Akshar | 0.5 | 4 | 96
[7 empty] | 1.38 | HT Panel relay test | 16 | 0 | 16 | 04 Aug, 08 Aug | 2026-08-08 | Akshar | 6 | 4 | 10.6667
[7 empty] | 1.39 | HT Cable VLF Test | 14 | 0 | 14 | 23 Jul, 30 Jul | 2026-07-30 | Akshar | 6 | 5 | 11.6667
[7 empty] | 1.4 | CSS routine test | 1 | 0 | 1 | 23 Jul, 03 Aug | 2026-08-03 | Akshar | 1 | 5 | 5
[7 empty] | 1.41 | ACDB routine test | 6 | 0 | 6 | 23 Jul, 04 Aug | 2026-08-04 | Akshar | 3 | 5 | 10
[7 empty] | 1.42 | Earthing | 4284 | 432 | 3852 | 25-Jul, 07 Aug | 2026-08-07 | Akshar | 150 | 6 | 154.08
[7 empty] | 1.43 | LA | 10 | 0 | 10 | 27- Jul, 07 Aug | 2026-08-07 | Akshar | 5 | 6 | 12
CATL | 5 | 04 Aug, 15 Aug 24 Aug 31 Aug | 271 MWh (48 Containers) | 28 Aug 14 Sep | 02 Sep 19 Sep | 05 Sep 22 Sep |  |  |  | Civil
[7 empty] | 5.1 | BCF Precast Erection & Welding | 48 | 48 | 0 | Completed |  | MSC | 1 | 2 | 0
[7 empty] | 5.2 | CT Rail Fixing | 6 | 6 | 0 | Completed |  | MSC | 1 | 16 | 0
[7 empty] | 5.3 | PCS Slab casting | 6 | 6 | 0 | Completed |  | MSC | 1 | 39 | 0
[7 empty] | 5.4 | SGR Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 37 | 0
[7 empty] | 5.5 | MCR Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 34 | 0
[7 empty] | 5.6 | CSS Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 54 | 0
[7 empty] | 5.7 | BOT Precast Erection | 3 | 3 | 0 | Completed |  | Sachi | 3 | 5 | 0
[7 empty] | 5.8 | NIFPS Precast Erection | 6 | 6 | 0 | Completed |  | MSC | 1 | 5 | 0
[7 empty] | 5.9 | PCS PEB | 6 | 6 | 0 | Completed |  | Synergy | 1 | 27 | 0
[7 empty] | 5.1 | SGR PEB | 1 | 0 | 1 | 05 Jul, 20 Jul, 30 Jul | 2026-07-30 | Synergy | 1 | 25 | 25
[7 empty] | 5.11 | MCR PEB | 1 | 0 | 1 | 06 Jul, 14 Jul, 26 Jul, 30 Jul | 2026-07-30 | RV Enterprise | - | - | -
Electrical
[7 empty] | 5.12 | CT Erection | 6 | 6 | 0 | Completed |  | Pratibha | 2 | 4 | 0
[7 empty] | 5.13 | PCS Erection | 48 | 0 | 48 | 20 Jul, 25 Jul, 05 Aug | 2026-08-05 | Akshar | 10 | 4 | 19.2 | 48 PCS placed on slab, anchoring WIP
[7 empty] | 5.14 | ACDB Erection | 6 | 0 | 6 | 22 Jul, 25 Jul, 05 Aug | 2026-08-05 | Akshar | 5 | 4 | 4.8
[7 empty] | 5.15 | ECP Panel Erection (Communication Panel) | 6 | 0 | 6 | 22 Jul, 25 Jul, 05 Aug | 2026-08-05 | Akshar | 20 | 4 | 4
[7 empty] | 5.16 | HT Panel Erection | 2 | 0 | 2 | 07 Jul, 17 Jul, 28 Jul | 2026-07-28 | Akshar | 10
[7 empty] | 5.17 | EMS Panel Erection | 1 | 0 | 1 | 10 Jul, 16 Jul, 01 Aug, 05 Aug | 2026-08-05 | Akshar | 10
[7 empty] | 5.18 | CSS Erection | 1 | 0 | 1 | 10 Jul, 15 Jul, 25 Jul | 2026-07-25 | Akshar | 10
[7 empty] | 5.19 | NIFPS Panel Erection | 6 | 0 | 6 | 19 Jul, 27 Jul, 06 Aug | 2026-08-06 | Ornet / EMR | 20
[7 empty] | 5.2 | NIFPS Fabrication | 6 | 0 | 6 | 24 Jul, 30 Jul, 10 Aug | 2026-08-10 | Ornet / EMR | 0.66667 | 0 | 0
[7 empty] | 5.21 | Battery Container Erection | 48 | 0 | 48 | 09 Aug, 20 Aug, 29 Aug | 2026-08-29 | HEFT & Akshar | 10 | 4 | 19.2
[7 empty] | 5.22 | HT cable laying | 5680.75 | 603 | 5077.75 | 26 Jul, 01 Aug | 2026-08-01 | Akshar | 1500 | 48 | 162.488
[7 empty] | 5.23 | HT cable termination | 28 | 0 | 28 | 2026-08-11 | 2026-08-11 | Akshar | 8 | 6 | 21
[7 empty] | 5.24 | DC Cable laying | 14290 | 0 | 14290 | 01 Aug, 05 Aug | 2026-08-05 | Akshar | 600 | 10 | 238.1667
[7 empty] | 5.25 | LT Cable laying | 47399 | 0 | 47399 | 26 Jul, 05 Aug | 2026-08-05 | Akshar | 600 | 10 | 789.9833
[7 empty] | 5.26 | DC Cable termination | 1536 | 0 | 1536 | 15 Aug, 20 Aug, 06 Sep | 2026-09-06 | Akshar | 30 | 18 | 921.6
[7 empty] | 5.27 | LT Cable termination | 2304 | 0 | 2304 | 15 Aug, 25 Aug | 2026-08-25 | Akshar | 30 | 18 | 1382.4
[7 empty] | 5.28 | Aux Cable laying | 8232 | 0 | 8232 | 05 Aug, 10 Aug | 2026-08-10 | Akshar | 1000 | 10 | 82.32
[7 empty] | 5.29 | Control Cable laying | 14448 | 0 | 14448 | 05 Aug, 10 Aug | 2026-08-10 | Akshar | 1000 | 10 | 144.48
[7 empty] | 5.3 | Communication Cable laying | 4792 | 0 | 4792 | 05 Aug, 10 Aug | 2026-08-10 | Akshar | 500 | 10 | 95.84
[7 empty] | 5.31 | Aux Cable termination | 286 | 0 | 286 | 15 Aug, 20 Aug, 06 Sep | 2026-09-06 | Akshar | 30 | 6 | 57.2
[7 empty] | 5.32 | Control Cable termination | 536 | 0 | 536 | 15 Aug, 20 Aug, 06 Sep | 2026-09-06 | Akshar & Emerson | 30 | 4 | 71.4667
[7 empty] | 5.33 | Communication Cable termination | 384 | 0 | 384 | 15 Aug, 20 Aug, 06 Sep | 2026-09-06 | Akshar & Emerson | - | - | - |  | 38 | 4354.838
[7 empty] | 5.34 | CT SFRA & Tan delta Test | 6 | 0 | 6 | 31 Jul, 05 Aug | 2026-08-05 | Canbay | 2 | 8 | -
[7 empty] | 5.35 | CT Routine Test | 6 | 0 | 6 | 04 Aug, 10 Aug | 2026-08-10 | Akshar |  |  | 12
[7 empty] | 5.36 | CT Control scheme & Stability Test | 6 | 0 | 6 | 25 Aug, 11 Sep | 2026-09-11 | Akshar | 2 | 4 | 12 |  | 43 | 4354.838
[7 empty] | 5.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | 12 | 0 | 12 | 11 Aug, 20 Aug |  | Akshar | 0.5 | 4 | 96
[7 empty] | 5.38 | HT Panel relay test | 16 | 0 | 16 | 23 Aug, 09 Sep | 2026-09-09 | Akshar | 6 | 4 | 10.6667
[7 empty] | 5.39 | HT Cable VLF Test | 14 | 0 | 14 | 11 Aug, 20 Aug | 2026-08-20 | Akshar | 6 | 5 | 11.6667
[7 empty] | 5.4 | CSS routine test | 1 | 0 | 1 | 11 Aug, 20 Aug | 2026-08-20 | Akshar | 1 | 5 | 5
[7 empty] | 5.41 | ACDB routine test | 6 | 0 | 6 | 11 Aug, 20 Aug | 2026-08-20 | Akshar | 3 | 5 | 10
[7 empty] | 5.42 | Earthing | 4284 | 0 | 4284 | 13 Aug, 31 Aug | 2026-08-31 | Akshar | 150 | 6 | 171.36
[7 empty] | 5.43 | LA | 10 | 0 | 10 | 15 Aug, 31 Aug | 2026-08-31 | Akshar | 5 | 6 | 12
CATL | 6 | 09 Aug, 16 Aug 05 Sep 31 Aug | 271 MWh (48 Containers) | 02 Sep 23 Sep | 07 Sep 27 Sep | 10 Sep 30 Sep |  |  |  | Civil
[7 empty] | 6.1 | BCF Precast Erection & Welding | 48 | 48 | 0 | Completed |  | MSC | 1 | 2 | 0
[7 empty] | 6.2 | CT Rail Fixing | 6 | 6 | 0 | Completed |  | MSC | 1 | 16 | 0
[7 empty] | 6.3 | PCS Slab casting | 6 | 6 | 0 | Completed |  | MSC | 1 | 39 | 0
[7 empty] | 6.4 | SGR Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 37 | 0
[7 empty] | 6.5 | MCR Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 34 | 0
[7 empty] | 6.6 | CSS Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 54 | 0
[7 empty] | 6.7 | BOT Precast Erection | 3 | 3 | 0 | Completed |  | Sachi | 3 | 5 | 0
[7 empty] | 6.8 | NIFPS Precast Erection | 6 | 6 | 0 | Completed |  | MSC | 1 | 5 | 0
[7 empty] | 6.9 | PCS PEB | 6 | 6 | 0 | Completed |  | Synergy | 1 | 27 | 0
[7 empty] | 6.1 | SGR PEB | 1 | 0 | 1 | 05 Jul, 20 Jul, 30 Jul | 2026-07-30 | Synergy | 1 | 25 | 25
[7 empty] | 6.11 | MCR PEB | 1 | 0 | 1 | 05 Jul, 15 Jul, 29 Jul | 2026-07-29 | RV Enterprise | - | - | -
Electrical
[7 empty] | 6.12 | CT Erection | 6 | 6 | 0 | Completed |  | Pratibha | 2 | 4 | 0
[7 empty] | 6.13 | PCS Erection | 48 | 0 | 48 | 2026-08-02 | 2026-08-02 | Akshar | 10 | 4 | 19.2 | 48 PCS placed on slab, anchoring WIP | [5 empty] | 5
[7 empty] | 6.14 | ACDB Erection | 6 | 0 | 6 | 2026-08-05 | 2026-08-05 | Akshar | 5 | 4 | 4.8
[7 empty] | 6.15 | ECP Panel Erection (Communication Panel) | 6 | 0 | 6 | 2026-08-02 | 2026-08-02 | Akshar | 20 | 4 | 4
[7 empty] | 6.16 | HT Panel Erection | 2 | 0 | 2 | 02 Jul, 06 Jul, 27 Jul, 07 Aug | 2026-08-07 | Akshar | 10
[7 empty] | 6.17 | EMS Panel Erection | 1 | 0 | 1 | 09 Jul, 18 Jul, 30 Jul | 2026-07-30 | Akshar | 10
[7 empty] | 6.18 | CSS Erection | 1 | 0 | 1 | 15 Jul, 30 Jul, 0 5 Aug | 2026-08-05 | Akshar | 10
[7 empty] | 6.19 | NIFPS Panel Erection | 6 | 0 | 6 | 23 Jul, 30 Jul | 2026-07-30 | Ornet / EMR | 20
[7 empty] | 6.2 | NIFPS Fabrication | 6 | 0 | 6 | 28 Jul, 05 Aug | 2026-08-05 | Ornet / EMR | 0.66667 | 0 | 0
[7 empty] | 6.21 | Battery Container Erection | 48 | 0 | 48 | 14 Aug, 21 Aug, 10 Sep | 2026-09-10 | HEFT & Akshar | 10 | 4 | 19.2
[7 empty] | 6.22 | HT cable laying | 4879.09 | 0 | 4879.09 | 31 Jul, 05 Aug | 2026-08-05 | Akshar | 1500 | 48 | 156.1309
[7 empty] | 6.23 | HT cable termination | 28 | 0 | 28 | 2026-08-16 | 2026-08-16 | Akshar | 8 | 6 | 21
[7 empty] | 6.24 | DC Cable laying | 14288 | 0 | 14288 | 06 Aug, 10 Aug | 2026-08-10 | Akshar | 600 | 10 | 238.1333
[7 empty] | 6.25 | LT Cable laying | 47399 | 0 | 47399 | 31 Jul, 10 Aug | 2026-08-10 | Akshar | 600 | 10 | 789.9833
[7 empty] | 6.26 | DC Cable termination | 1536 | 0 | 1536 | 20 Aug, 12 Sep | 2026-09-12 | Akshar | 30 | 18 | 921.6
[7 empty] | 6.27 | LT Cable termination | 2304 | 0 | 2304 | 20 Aug, 12 Sep | 2026-09-12 | Akshar | 30 | 18 | 1382.4
[7 empty] | 6.28 | Aux Cable laying | 8232 | 0 | 8232 | 10 Aug, 14 Aug | 2026-08-14 | Akshar | 1000 | 10 | 82.32
[7 empty] | 6.29 | Control Cable laying | 14448 | 0 | 14448 | 10 Aug, 14 Aug | 2026-08-14 | Akshar | 1000 | 10 | 144.48
[7 empty] | 6.3 | Communication Cable laying | 4792 | 0 | 4792 | 10 Aug, 14 Aug | 2026-08-14 | Akshar | 500 | 10 | 95.84
[7 empty] | 6.31 | Aux Cable termination | 286 | 0 | 286 | 20 Aug, 12 Sep | 2026-09-12 | Akshar | 30 | 6 | 57.2
[7 empty] | 6.32 | Control Cable termination | 536 | 0 | 536 | 20 Aug, 12 Sep | 2026-09-12 | Akshar & Emerson | 30 | 4 | 71.4667
[7 empty] | 6.33 | Communication Cable termination | 384 | 0 | 384 | 20 Aug, 12 Sep | 2026-09-12 | Akshar & Emerson | - | - | - |  | 44 | 4348.4475
[7 empty] | 6.34 | CT SFRA & Tan delta Test | 6 | 0 | 6 | 2026-08-05 | 2026-08-05 | Canbay | 2 | 8 | -
[7 empty] | 6.35 | CT Routine Test | 6 | 0 | 6 | 2026-08-09 | 2026-08-09 | Akshar |  |  | 12
[7 empty] | 6.36 | CT Control scheme & Stability Test | 6 | 0 | 6 | 30 Aug, 21 Sep | 2026-09-21 | Akshar | 2 | 4 | 12 |  | 53 | 4348.4475
[7 empty] | 6.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | 12 | 0 | 12 | 2026-08-16 | 2026-08-16 | Akshar | 0.5 | 4 | 96
[7 empty] | 6.38 | HT Panel relay test | 16 | 0 | 16 | 28 Aug, 19 Sep | 2026-09-19 | Akshar | 6 | 4 | 10.6667
[7 empty] | 6.39 | HT Cable VLF Test | 14 | 0 | 14 | 16 Aug, 25Aug | 2026-08-25 | Akshar | 6 | 5 | 11.6667
[7 empty] | 6.4 | CSS routine test | 1 | 0 | 1 | 16 Aug, 25Aug | 2026-08-25 | Akshar | 1 | 5 | 5
[7 empty] | 6.41 | ACDB routine test | 6 | 0 | 6 | 16 Aug, 25Aug | 2026-08-25 | Akshar | 3 | 5 | 10
[7 empty] | 6.42 | Earthing | 4284 | 0 | 4284 | 18 Aug, 12 Sep | 2026-09-12 | Akshar | 150 | 6 | 171.36
[7 empty] | 6.43 | LA | 10 | 0 | 10 | 20 Aug, 11 Sep | 2026-09-11 | Akshar | 5 | 6 | 12
CATL | 7 | 19 Aug, 22 Aug 05 Sep 08 Sep | 271 MWh (48 Containers) | 12 Sep 23 Sep | 17 Sep 27 Sep | 20 Sep 30 Sep |  |  |  | Civil
[7 empty] | 7.1 | BCF Precast Erection & Welding | 48 | 48 | 0 | Completed |  | MSC | 1 | 2 | 0
[7 empty] | 7.2 | CT Rail Fixing | 6 | 6 | 0 | Completed |  | MSC | 1 | 16 | 0
[7 empty] | 7.3 | PCS Slab casting | 6 | 6 | 0 | Completed |  | MSC | 1 | 39 | 0
[7 empty] | 7.4 | SGR Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 37 | 0
[7 empty] | 7.5 | MCR Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 34 | 0
[7 empty] | 7.6 | CSS Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 54 | 0
[7 empty] | 7.7 | BOT Precast Erection | 3 | 3 | 0 | Completed |  | Sachi | 3 | 5 | 0
[7 empty] | 7.8 | NIFPS Precast Erection | 6 | 6 | 0 | Completed |  | MSC | 1 | 5 | 0
[7 empty] | 7.9 | PCS PEB | 6 | 6 | 0 | Completed |  | Synergy | 1 | 27 | 0
[7 empty] | 7.1 | SGR PEB | 1 | 0 | 1 | 10 Jul, 20 Jul, 07 Aug | 2026-08-07 | Synergy | 1 | 25 | 25
[7 empty] | 7.11 | MCR PEB | 1 | 0 | 1 | 11 Jul, 15 Jul, 01 Aug | 2026-08-01 | RV Enterprise | - | - | -
Electrical
[7 empty] | 7.12 | CT Erection | 6 | 0 | 6 | 25 Jul, 05 Aug | 2026-08-05 | Akshar | 2 | 4 | 12
[7 empty] | 7.13 | PCS Erection | 48 | 0 | 48 | 25 Jul, 05 Aug | 2026-08-05 | Akshar | 10 | 4 | 19.2
[7 empty] | 7.14 | ACDB Erection | 6 | 0 | 6 | 30 Jul, 05 Aug | 2026-08-05 | Akshar | 5 | 4 | 4.8
[7 empty] | 7.15 | ECP Panel Erection (Communication Panel) | 6 | 0 | 6 | 30 Jul, 05 Aug | 2026-08-05 | Akshar | 20 | 4 | 4
[7 empty] | 7.16 | HT Panel Erection | 2 | 0 | 2 | 2026-08-05 | 2026-08-05 | Akshar | 10
[7 empty] | 7.17 | EMS Panel Erection | 1 | 0 | 1 | 30 Jul, 05 Aug | 2026-08-05 | Akshar | 10
[7 empty] | 7.18 | CSS Erection | 1 | 0 | 1 | 20 Jul, 02 Aug | 2026-08-02 | Akshar | 10
[7 empty] | 7.19 | NIFPS Panel Erection | 6 | 0 | 6 | 27 Jul, 07 Aug | 2026-08-07 | Ornet / EMR | 20
[7 empty] | 7.2 | NIFPS Fabrication | 6 | 0 | 6 | 01 Aug, 12 Aug | 2026-08-12 | Ornet / EMR | 0.66667 | 0 | 0
[7 empty] | 7.21 | Battery Container Erection | 48 | 0 | 48 | 24 Aug, 27 Aug, 10 Sep | 2026-09-10 | HEFT & Akshar | 10 | 4 | 19.2
[7 empty] | 7.22 | HT cable laying | 4445.09 | 0 | 4445.09 | 10 Aug, 14 Aug | 2026-08-14 | Akshar | 1500 | 48 | 142.2429
[7 empty] | 7.23 | HT cable termination | 28 | 0 | 28 | 2026-08-26 | 2026-08-26 | Akshar | 8 | 6 | 21
[7 empty] | 7.24 | DC Cable laying | 14288 | 0 | 14288 | 2026-08-16 | 2026-08-16 | Akshar | 600 | 10 | 238.1333
[7 empty] | 7.25 | LT Cable laying | 47399 | 0 | 47399 | 10 Aug, 16 Aug | 2026-08-16 | Akshar | 600 | 10 | 789.9833
[7 empty] | 7.26 | DC Cable termination | 1536 | 0 | 1536 | 30 Aug, 14 Sep | 2026-09-14 | Akshar | 30 | 18 | 921.6
[7 empty] | 7.27 | LT Cable termination | 2304 | 0 | 2304 | 30 Aug, 14 Sep | 2026-09-14 | Akshar | 30 | 18 | 1382.4
[7 empty] | 7.28 | Aux Cable laying | 8232 | 0 | 8232 | 2026-08-20 | 2026-08-20 | Akshar | 1000 | 10 | 82.32
[7 empty] | 7.29 | Control Cable laying | 14448 | 0 | 14448 | 2026-08-20 | 2026-08-20 | Akshar | 1000 | 10 | 144.48
[7 empty] | 7.3 | Communication Cable laying | 4792 | 0 | 4792 | 2026-08-20 | 2026-08-20 | Akshar | 500 | 10 | 95.84
[7 empty] | 7.31 | Aux Cable termination | 286 | 0 | 286 | 30 Aug, 14 Sep | 2026-09-14 | Akshar | 30 | 6 | 57.2
[7 empty] | 7.32 | Control Cable termination | 536 | 0 | 536 | 30 Aug, 14 Sep | 2026-09-14 | Akshar & Emerson | 30 | 4 | 71.4667
[7 empty] | 7.33 | Communication Cable termination | 384 | 0 | 384 | 30 Aug, 14 Sep | 2026-09-14 | Akshar & Emerson | - | - | - |  | 46 | 4346.5595
[7 empty] | 7.34 | CT SFRA & Tan delta Test | 6 | 0 | 6 | 2026-08-15 | 2026-08-15 | Canbay | 2 | 8 | -
[7 empty] | 7.35 | CT Routine Test | 6 | 0 | 6 | 2026-08-19 | 2026-08-19 | Akshar |  |  | 12
[7 empty] | 7.36 | CT Control scheme & Stability Test | 6 | 0 | 6 | 09 Sep, 21 Sep | 2026-09-21 | Akshar | 2 | 4 | 12 |  | 53 | 4346.5595
[7 empty] | 7.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | 12 | 0 | 12 | 26 Aug, 06 Sep | 2026-09-06 | Akshar | 0.5 | 4 | 96
[7 empty] | 7.38 | HT Panel relay test | 16 | 0 | 16 | 07 Sep, 19 Sep | 2026-09-19 | Akshar | 6 | 4 | 10.6667
[7 empty] | 7.39 | HT Cable VLF Test | 14 | 0 | 14 | 26 Aug, 06 Sep | 2026-09-06 | Akshar | 6 | 5 | 11.6667
[7 empty] | 7.4 | CSS routine test | 1 | 0 | 1 | 26 Aug, 06 Sep | 2026-09-06 | Akshar | 1 | 5 | 5
[7 empty] | 7.41 | ACDB routine test | 6 | 0 | 6 | 26 Aug, 06 Sep | 2026-09-06 | Akshar | 3 | 5 | 10
[7 empty] | 7.42 | Earthing | 4284 | 0 | 4284 | 28 Aug, 10 Sep | 2026-09-10 | Akshar | 150 | 6 | 171.36
[7 empty] | 7.43 | LA | 10 | 0 | 10 | 30 Aug, 10 Sep | 2026-09-10 | Akshar | 5 | 6 | 12
CATL | 8 | 21 Aug, 24 Aug 05 Sep 08 Sep | 271 MWh (48 Containers) | 14 Sep 23 Sep | 19 Sep 27 Sep | 22 Sep 30 Sep |  |  |  | Civil
[7 empty] | 8.1 | BCF Precast Erection & Welding | 48 | 48 | 0 | Completed |  | MSC | 1 | 2 | 0
[7 empty] | 8.2 | CT Rail Fixing | 6 | 6 | 0 | Completed |  | MSC | 1 | 16 | 0
[7 empty] | 8.3 | PCS Slab casting | 6 | 6 | 0 | Completed |  | MSC | 1 | 39 | 0
[7 empty] | 8.4 | SGR Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 37 | 0
[7 empty] | 8.5 | MCR Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 34 | 0
[7 empty] | 8.6 | CSS Slab Casting | 1 | 1 | 0 | Completed |  | MSC | 1 | 54 | 0
[7 empty] | 8.7 | BOT Precast Erection | 3 | 3 | 0 | Completed |  | Sachi | 3 | 5 | 0
[7 empty] | 8.8 | NIFPS Precast Erection | 6 | 6 | 0 | Completed |  | MSC | 1 | 5 | 0
[7 empty] | 8.9 | PCS PEB | 6 | 0 | 6 | 15 Jul, 31 Jul | 2026-07-31 | Synergy | 1 | 27 | 162
[7 empty] | 8.1 | SGR PEB | 1 | 0 | 1 | 15 Jul, 07 Aug | 2026-08-07 | Synergy | 1 | 25 | 25
[7 empty] | 8.11 | MCR PEB | 1 | 0 | 1 | 15 Jul, 04 Aug | 2026-08-04 | RV Enterprise | - | - | -
Electrical
[7 empty] | 8.12 | CT Erection | 6 | 0 | 6 | 30 Jul, 10 Aug | 2026-08-10 | Akshar | 2 | 4 | 12
[7 empty] | 8.13 | PCS Erection | 48 | 0 | 48 | 2026-08-05 | 2026-08-05 | Akshar | 10 | 4 | 19.2
[7 empty] | 8.14 | ACDB Erection | 6 | 0 | 6 | 2026-08-06 | 2026-08-06 | Akshar | 5 | 4 | 4.8
[7 empty] | 8.15 | ECP Panel Erection (Communication Panel) | 6 | 0 | 6 | 2026-08-06 | 2026-08-06 | Akshar | 20 | 4 | 4
[7 empty] | 8.16 | HT Panel Erection | 2 | 0 | 2 | 2026-08-05 | 2026-08-05 | Akshar | 10
[7 empty] | 8.17 | EMS Panel Erection | 1 | 0 | 1 | 31 Jul, 06 Aug | 2026-08-06 | Akshar | 10
[7 empty] | 8.18 | CSS Erection | 1 | 0 | 1 | 2026-08-10 | 2026-08-10 | Akshar | 10
[7 empty] | 8.19 | NIFPS Panel Erection | 6 | 0 | 6 | 31 Jul, 15 Aug | 2026-08-15 | Ornet / EMR | 20
[7 empty] | 8.2 | NIFPS Fabrication | 6 | 0 | 6 | 05 Aug, 20 Aug | 2026-08-20 | Ornet / EMR | 0.66667 | 0 | 0
[7 empty] | 8.21 | Battery Container Erection | 48 | 0 | 48 | 26 Aug, 29 Aug, 10 Sep | 2026-09-10 | HEFT & Akshar | 10 | 4 | 19.2
[7 empty] | 8.22 | HT cable laying | 3549.12 | 0 | 3549.12 | 2026-08-12 | 2026-08-12 | Akshar | 1500 | 48 | 113.5718
[7 empty] | 8.23 | HT cable termination | 28 | 0 | 28 | 2026-08-28 | 2026-08-28 | Akshar | 8 | 6 | 21
[7 empty] | 8.24 | DC Cable laying | 14288 | 0 | 14288 | 2026-08-18 | 2026-08-18 | Akshar | 600 | 10 | 238.1333
[7 empty] | 8.25 | LT Cable laying | 47399 | 0 | 47399 | 1 2Aug, 18 Aug | 2026-08-18 | Akshar | 600 | 10 | 789.9833
[7 empty] | 8.26 | DC Cable termination | 1536 | 0 | 1536 | 01 Sep, 14 Sep | 2026-09-14 | Akshar | 30 | 18 | 921.6
[7 empty] | 8.27 | LT Cable termination | 2304 | 0 | 2304 | 01 Sep, 14 Sep | 2026-09-14 | Akshar | 30 | 18 | 1382.4
[7 empty] | 8.28 | Aux Cable laying | 8232 | 0 | 8232 | 2026-08-22 | 2026-08-22 | Akshar | 1000 | 10 | 82.32
[7 empty] | 8.29 | Control Cable laying | 14448 | 0 | 14448 | 2026-08-22 | 2026-08-22 | Akshar | 1000 | 10 | 144.48
[7 empty] | 8.3 | Communication Cable laying | 4792 | 0 | 4792 | 2026-08-22 | 2026-08-22 | Akshar | 500 | 10 | 95.84
[7 empty] | 8.31 | Aux Cable termination | 286 | 0 | 286 | 01 Sep, 14 Sep | 2026-09-14 | Akshar | 30 | 6 | 57.2
[7 empty] | 8.32 | Control Cable termination | 536 | 0 | 536 | 01 Sep, 14 Sep | 2026-09-14 | Akshar & Emerson | 30 | 4 | 71.4667
[7 empty] | 8.33 | Communication Cable termination | 384 | 0 | 384 | 01 Sep, 14 Sep | 2026-09-14 | Akshar & Emerson | - | - | - |  | 46 | 4317.8885
[7 empty] | 8.34 | CT SFRA & Tan delta Test | 6 | 0 | 6 | 2026-08-17 | 2026-08-17 | Canbay | 2 | 8 | -
[7 empty] | 8.35 | CT Routine Test | 6 | 0 | 6 | 2026-08-21 | 2026-08-21 | Akshar |  |  | 12
[7 empty] | 8.36 | CT Control scheme & Stability Test | 6 | 0 | 6 | 11 Sep, 21 Sep | 2026-09-21 | Akshar | 2 | 4 | 12 |  | 53 | 4317.8885
[7 empty] | 8.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | 12 | 0 | 12 | 28 Aug, 08 Sep | 2026-09-08 | Akshar | 0.5 | 4 | 96
[7 empty] | 8.38 | HT Panel relay test | 16 | 0 | 16 | 09 Sep, 19 Sep | 2026-09-19 | Akshar | 6 | 4 | 10.6667
[7 empty] | 8.39 | HT Cable VLF Test | 14 | 0 | 14 | 28 Aug, 08 Sep | 2026-09-08 | Akshar | 6 | 5 | 11.6667
[7 empty] | 8.4 | CSS routine test | 1 | 0 | 1 | 28 Aug, 08 Sep | 2026-09-08 | Akshar | 1 | 5 | 5
[7 empty] | 8.41 | ACDB routine test | 6 | 0 | 6 | 28 Aug, 08 Sep | 2026-09-08 | Akshar | 3 | 5 | 10
[7 empty] | 8.42 | Earthing | 4284 | 0 | 4284 | 30 Aug, 11 Sep | 2026-09-11 | Akshar | 150 | 6 | 171.36
[7 empty] | 8.43 | LA | 10 | 0 | 10 | 01 Sep, 12 Sep | 2026-09-12 | Akshar | 5 | 6 | 12
CATL | 9 | 22 Aug, 26 Aug 05 Sep 08 Sep | 271 MWh (48 Containers) | 15 Sep 23 Sep | 20 Sep 27 Sep | 23 Sep 30 Sep |  |  |  | Civil
[7 empty] | 9.1 | BCF Precast Erection & Welding | 48 | 48 | 0 | Completed |  | MSC | 1 | 2 | 0
[7 empty] | 9.2 | CT Rail Fixing | 6 | 0 | 6 | 30-Jun, 06 Jul, 15 Jul, 28 Jul | 2026-07-28 | MSC | 1 | 16 | 96
[7 empty] | 9.3 | PCS Slab casting | 6 | 3 | 3 | 05 Jul, 08 Jul, 20 Jul, 28 Jul | 2026-07-28 | MSC | 1 | 39 | 117
[7 empty] | 9.4 | SGR Slab Casting | 1 | 0 | 1 | 03 Jul, 10 Jul, 18 Jul, 28 Jul | 2026-07-28 | MSC | 1 | 37 | 37
[7 empty] | 9.5 | MCR Slab Casting | 1 | 0 | 1 | 07 Jul, 18 Jul, 28 Jul | 2026-07-28 | MSC | 1 | 34 | 34
[7 empty] | 9.6 | CSS Slab Casting | 1 | 0 | 1 | 10 Jul, 20 Jul, 28 Jul | 2026-07-28 | MSC | 1 | 54 | 54
[7 empty] | 9.7 | BOT Precast Erection | 3 | 3 | 0 | Completed |  | Sachi | 3 | 5 | 0
[7 empty] | 9.8 | NIFPS Precast Erection | 6 | 0 | 6 | 30 Jun, 03 Jul, 15 Jul, 28 Jul | 2026-07-28 | MSC | 1 | 5 | 30
[7 empty] | 9.9 | PCS PEB | 6 | 0 | 6 | 16 Jul, 08 Aug | 2026-08-08 | Synergy | 1 | 27 | 162
[7 empty] | 9.1 | SGR PEB | 1 | 0 | 1 | 16 Jul, 17 Aug | 2026-08-17 | Synergy | 1 | 25 | 25
[7 empty] | 9.11 | MCR PEB | 1 | 0 | 1 | 21 Jul, 07 Aug | 2026-08-07 | RV Enterprise | - | - | -
Electrical
[7 empty] | 9.12 | CT Erection | 6 | 0 | 6 | 2026-08-15 | 2026-08-15 | Akshar | 2 | 8 | 24
[7 empty] | 9.13 | PCS Erection | 48 | 0 | 48 | 2026-08-15 | 2026-08-15 | Akshar | 10 | 8 | 38.4
[7 empty] | 9.14 | ACDB Erection | 6 | 0 | 6 | 2026-08-18 | 2026-08-18 | Akshar | 5 | 4 | 4.8
[7 empty] | 9.15 | ECP Panel Erection (Communication Panel) | 6 | 0 | 6 | 2026-08-15 | 2026-08-15 | Akshar | 20 | 8 | 4
[7 empty] | 9.16 | HT Panel Erection | 2 | 0 | 2 | 2026-08-15 | 2026-08-15 | Akshar | 10
[7 empty] | 9.17 | EMS Panel Erection | 1 | 0 | 1 | 2026-08-22 | 2026-08-22 | Akshar | 10
[7 empty] | 9.18 | CSS Erection | 1 | 0 | 1 | 2026-08-22 | 2026-08-22 | Akshar | 10
[7 empty] | 9.19 | NIFPS Panel Erection | 6 | 0 | 6 | 04 Jul, 20 Aug | 2026-08-20 | Ornet / EMR | 20
[7 empty] | 9.2 | NIFPS Fabrication | 6 | 0 | 6 | 09 Aug, 25 Aug | 2026-08-25 | Ornet / EMR | 0.66667 | 0 | 0
[7 empty] | 9.21 | Battery Container Erection | 48 | 0 | 48 | 27 Aug, 31 Aug, 10 Sep | 2026-09-10 | HEFT & Akshar | 10 | 4 | 19.2
[7 empty] | 9.22 | HT cable laying | 4518.48 | 0 | 4518.48 | 2026-08-13 | 2026-08-13 | Akshar | 1500 | 48 | 144.5914
[7 empty] | 9.23 | HT cable termination | 28 | 0 | 28 | 2026-08-29 | 2026-08-29 | Akshar | 8 | 6 | 21
[7 empty] | 9.24 | DC Cable laying | 14288 | 0 | 14288 | 2026-08-19 | 2026-08-19 | Akshar | 600 | 10 | 238.1333
[7 empty] | 9.25 | LT Cable laying | 47492 | 0 | 47492 | 2026-08-13 | 2026-08-13 | Akshar | 600 | 10 | 791.5333
[7 empty] | 9.26 | DC Cable termination | 1536 | 0 | 1536 | 02 Sep, 14 Sep | 2026-09-14 | Akshar | 30 | 18 | 921.6
[7 empty] | 9.27 | LT Cable termination | 2304 | 0 | 2304 | 02 Sep, 14 Sep | 2026-09-14 | Akshar | 30 | 18 | 1382.4
[7 empty] | 9.28 | Aux Cable laying | 8232 | 0 | 8232 | 2026-08-23 | 2026-08-23 | Akshar | 800 | 10 | 102.9
[7 empty] | 9.29 | Control Cable laying | 14448 | 0 | 14448 | 2026-08-23 | 2026-08-23 | Akshar | 1000 | 10 | 144.48
[7 empty] | 9.3 | Communication Cable laying | 4792 | 0 | 4792 | 2026-08-23 | 2026-08-23 | Akshar | 500 | 10 | 95.84
[7 empty] | 9.31 | Aux Cable termination | 286 | 0 | 286 | 02 Sep, 14 Sep | 2026-09-14 | Akshar | 30 | 6 | 57.2
[7 empty] | 9.32 | Control Cable termination | 536 | 0 | 536 | 02 Sep, 14 Sep | 2026-09-14 | Akshar & Emerson | 30 | 4 | 71.4667
[7 empty] | 9.33 | Communication Cable termination | 384 | 0 | 384 | 02 Sep, 14 Sep | 2026-09-14 | Akshar & Emerson | - | - | - |  | 46 | 4402.238
[7 empty] | 9.34 | CT SFRA & Tan delta Test | 6 | 0 | 6 | 2026-08-18 | 2026-08-18 | Canbay | 2 | 8 | -
[7 empty] | 9.35 | CT Routine Test | 6 | 0 | 6 | 2026-08-22 | 2026-08-22 | Akshar |  |  | 12
[7 empty] | 9.36 | CT Control scheme & Stability Test | 6 | 0 | 6 | 12 Sep, 21 Sep | 2026-09-21 | Akshar | 2 | 4 | 12 |  | 53 | 4402.238
[7 empty] | 9.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | 12 | 0 | 12 | 29 Aug, 10 Sep | 2026-09-10 | Akshar | 0.5 | 4 | 96
[7 empty] | 9.38 | HT Panel relay test | 16 | 0 | 16 | 10 Sep, 19 Sep | 2026-09-19 | Akshar | 6 | 4 | 10.6667
[7 empty] | 9.39 | HT Cable VLF Test | 14 | 0 | 14 | 29 Aug, 10 Sep | 2026-09-10 | Akshar | 6 | 5 | 11.6667
[7 empty] | 9.4 | CSS routine test | 1 | 0 | 1 | 29 Aug, 10 Sep | 2026-09-10 | Akshar | 1 | 5 | 5
[7 empty] | 9.41 | ACDB routine test | 6 | 0 | 6 | 29 Aug, 10 Sep | 2026-09-10 | Akshar | 3 | 5 | 10
[7 empty] | 9.42 | Earthing | 4284 | 0 | 4284 | 31 Aug, 12 Sep | 2026-09-12 | Akshar | 150 | 6 | 171.36
[7 empty] | 9.43 | LA | 10 | 0 | 10 | 02 Sep, 14 Sep | 2026-09-14 | Akshar | 5 | 6 | 12
Assumptions:-
1. Ship berthing + 72 hrs - clearing of 30 containers per day for site
2. 30 containers erected on site on 4th day
3. IDT charging = 24 days from erection of last container in the block
4. Trial run start date = IDT charging + 3 days
5. Trial run end date = Trial run start date + 2 days
6. COD = Trial run end date + 2 days
Formulas:
New EDC = IF(LEN([EDC])=5,[EDC],(IF([EDC]="Completed"," ",DATEVALUE(RIGHT([EDC],6)))))

## BESS 12
| BESS 12 Charging Schedule | [17 empty] | 2026-07-30 |  |  |  | Common for PSS
| Container Make | Block No. | Containers at Site | MWh | IDT Charging / Commissioning Start | Trial-Run End Date | COD | Status | [7 empty] | Productivity | Manpower | Total Mandays | Remarks |  |  |  | Tools & tackles | Required At site | Available At site
[8 empty] | Sr. | Activity | Progress |  |  | EDC | New EDC | vendor
[10 empty] | S | C | B
4 | CATL | 4 | 07 Jul 09 Jul | 271 MWh (48 Containers) | 24 Jul 28 Jul | 29 Jul 02 Aug | 01 Aug 05 Aug |  |  |  | Civil | [11 empty] | Machinery
4 | [7 empty] | 4.1 | BCF Precast Erection & Welding | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 2 | #VALUE! |  |  |  |  | Cable jack | 6
4 | [7 empty] | 4.2 | CT Rail Fixing | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 16 | #VALUE! |  |  |  |  | JCB | 6
4 | [7 empty] | 4.3 | PCS Slab casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 39 | #VALUE! |  |  |  |  | Excavator | 1
4 | [7 empty] | 4.4 | SGR Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 37 | #VALUE! |  |  |  |  | farana | 6
4 | [7 empty] | 4.5 | MCR Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 34 | #VALUE! |  |  |  |  | DG with Sablizer | 8
4 | [7 empty] | 4.6 | CSS Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 54 | #VALUE! |  |  |  |  | Welding Machine | 10
4 | [7 empty] | 4.7 | BOT Slab casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | [7 empty] | HOT Gun | 20
4 | [7 empty] | 4.8 | BOT Precast Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Sachi | 3 | 5 | #VALUE! |  |  |  |  | Blower | 10
4 | [7 empty] | 4.9 | NIFPS Precast Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 5 | #VALUE! |  |  |  |  | Drilling Machine | 5
4 | [7 empty] | 4.1 | PCS PEB | #VALUE! | #VALUE! | #VALUE! | Completed | - | DP Consteel | 1 | 27 | #VALUE! |  |  |  |  | Drilling Machine [Hammering] | 2
4 | [7 empty] | 4.11 | SGR PEB | #VALUE! | #VALUE! | #VALUE! | Completed | - | Synergy | 1 | 25 | #VALUE! |  |  |  |  | Auger Machine | 1
4 | [7 empty] | 4.12 | MCR PEB | #VALUE! | #VALUE! | #VALUE! | Completed | - | Metastar | - | - | - |  |  |  |  | Tractor | 2
4 | [10 empty] | Electrical | [11 empty] | Cable Puller | 2
4 | [7 empty] | 4.13 | CT Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 2 | 4 | #VALUE! |  |  |  |  | Testing Kits
4 | [7 empty] | 4.14 | PCS Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 10 | 4 | #VALUE! |  |  |  |  | Megar | 5 | 3
4 | [7 empty] | 4.15 | ACDB Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 5 | 4 | #VALUE! |  |  |  |  | Filtration Machine | 1 | 0
4 | [7 empty] | 4.16 | ECP Panel Erection (Communication Panel) | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 20 | 4 | 4 |  |  |  |  | Online PPM Meter | 1 | 1
4 | [7 empty] | 4.17 | HT Panel Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 10 | [6 empty] | SFRA Test kit | 1 | 1
4 | [7 empty] | 4.18 | EMS Panel Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 10 | [6 empty] | Tan delta kit | 1 | 1
4 | [7 empty] | 4.19 | CSS Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 10 | [6 empty] | Routine test kit | 1 | 1
4 | * Min. 80 termination team required for DC & LT Cable termination with crimping tool (Each team required at least 01 skilled technician with 01 helper) - (Common For PSS) Available - 4 Teams (4 Skilled & 8 Helpers) for HT Cable Termination, 10 (10 Skilled & 15 Helpers) Teams for Aux. Cable termination & 35 Teams (75 Technician) for DC & LT Cable termination at site. (Spread Across 4 Blocks) Total Machinery - crimping tool: 50, cable jack: 07, welding machine: 10, Farana: 04, JCB: 07 available at site (Common for PSS) Testing to be completed by 21 Jul, 24 Jul . Required Testing Team (6 Skilled & 12 Unskilled) (Common for PSS) Testing kits : Oil Filteration, Online PPM Meter, SFRA & Tan Delta, DC Winding Resistance, Turn Ratio meter, routine test kit (common for 1 PSS) ERT, DC High POT, (common for 1 PSS) VLF kit (1 nos), IR Tester, Multimeter & Clamp Meter (atleast 3 per PSS) Breaker CRM & Timing, Vaccum Bottle Integrity (common for 1 PSS), CT Analyzer (2 nos), Relay Testing Kit, CT Primary Injection (3-Phase), PT Stability (3-Phase), Impedence meter (Common for 1 PSS) | [6 empty] | 4.2 | NIFPS Panel Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Tesla / CTR | 20 | [6 empty] | CT Analyzer | 2 | 2
4 | [7 empty] | 4.21 | NIFPS Fabrication | #VALUE! | #VALUE! | #VALUE! | Completed | - | Tesla / CTR | 0.66667 | 0 | #VALUE! |  |  |  |  | ERT Meter | 1 | 1
4 | [7 empty] | 4.22 | Battery Container Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 10 | 4 | #VALUE! |  |  |  |  | Primary injection kit | 1 | 3
4 | [7 empty] | 4.23 | HT cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 1500 | 48 | #VALUE! |  |  |  |  | PT test kit | 1 | 2
4 | [7 empty] | 4.24 | HT cable termination | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 8 | 6 | #VALUE! |  |  |  |  | 3 Phase Primary injection kit | 1 | 1
4 | [7 empty] | 4.25 | DC Cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 600 | 10 | #VALUE! |  |  |  |  | Breaker, CRM, Timming & vacuum Bottle test kits | 1 | 3
4 | [7 empty] | 4.26 | LT Cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 600 | 10 | #VALUE! |  |  |  |  | DC high Pot kit | 1 | 1
4 | [7 empty] | 4.27 | DC Cable termination | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 30 | 18 | #VALUE! |  |  |  |  | VLF Kit | 1 | 1
4 | [7 empty] | 4.28 | LT Cable termination | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 30 | 18 | #VALUE! |  |  |  |  | Relay Secondary injection kit | 2 | 2
4 | [7 empty] | 4.29 | Aux Cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 1000 | 10 | #VALUE! |  |  |  |  | Multimeter, IR Tester & Clamp meter | 3 | 4
4 | [7 empty] | 4.3 | Control Cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 1000 | 10 | #VALUE! |  |  |  |  | Impedance Meter | 2 | 1
4 | [7 empty] | 4.31 | Communication Cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 500 | 10 | #VALUE!
4 | [7 empty] | 4.32 | Aux Cable termination | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 30 | 6 | #VALUE! |  |  |  |  | Tools
4 | [7 empty] | 4.33 | Control Cable termination | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar & Honeywell | 30 | 4 | #VALUE! |  |  |  |  | Crimping tool | 60 | 40
4 | [7 empty] | 4.34 | Communication Cable termination | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar & Honeywell | - | - | - |  | #VALUE! | #VALUE! | #VALUE! | Torque Wrench | 10
4 | [7 empty] | 4.35 | CT SFRA & Tan delta Test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 2 | 8 | - |  |  |  |  | Tool Set | 10
4 | [7 empty] | 4.36 | CT Routine Test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar |  |  | - |  |  |  |  | Cable Cutter | 10
4 | [7 empty] | 4.37 | CT Control scheme & Stability Test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 2 | 4 | #VALUE! |  | #VALUE! | #VALUE! | #VALUE!
4 | [7 empty] | 4.38 | HT Panel Routine (CT & PT, Breaker & Meter) Test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 0.5 | 4 | #VALUE!
4 | [7 empty] | 4.39 | HT Panel relay test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 6 | 4 | #VALUE!
4 | [7 empty] | 4.4 | HT Cable VLF Test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 6 | 5 | #VALUE!
4 | [7 empty] | 4.41 | CSS routine test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 1 | 5 | #VALUE!
4 | [7 empty] | 4.42 | ACDB routine test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 3 | 5 | #VALUE!
4 | [7 empty] | 4.43 | Earthing | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 150 | 6 | #VALUE!
4 | [7 empty] | 4.44 | LA | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 5 | 6 | #VALUE!
1 | CATL | 1 | 30 Jun 04 Jul 09 Jul | 271 MWh (48 Containers) | 2026-07-28 | 2026-08-02 | 2026-08-05 |  |  |  | Civil
1 | [7 empty] | 1.1 | BCF Precast Erection & Welding | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 2 | #VALUE!
1 | [7 empty] | 1.2 | CT Rail Fixing | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 16 | #VALUE!
1 | [7 empty] | 1.3 | PCS Slab casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 39 | #VALUE!
1 | [7 empty] | 1.4 | SGR Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 37 | #VALUE!
1 | [7 empty] | 1.5 | MCR Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 34 | #VALUE!
1 | [7 empty] | 1.6 | CSS Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 54 | #VALUE!
1 | [7 empty] | 1.7 | BOT Precast Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Sachi | 3 | 5 | #VALUE!
1 | [7 empty] | 1.8 | NIFPS Precast Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 5 | #VALUE!
1 | [7 empty] | 1.9 | PCS PEB | #VALUE! | #VALUE! | #VALUE! | Completed | - | DP Consteel | 1 | 27 | #VALUE!
1 | [7 empty] | 1.1 | SGR PEB | #VALUE! | #VALUE! | #VALUE! | Completed | - | Synergy | 1 | 25 | #VALUE!
1 | [7 empty] | 1.11 | MCR PEB | #VALUE! | #VALUE! | #VALUE! | Completed | - | Metastar | - | - | -
1 | [10 empty] | Electrical
1 | [7 empty] | 1.12 | CT Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 2 | 4 | #VALUE!
1 | [7 empty] | 1.13 | PCS Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 10 | 4 | #VALUE!
1 | [7 empty] | 1.14 | ACDB Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 5 | 4 | #VALUE!
1 | [7 empty] | 1.15 | ECP Panel Erection (Communication Panel) | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 20 | 4 | 4
1 | [7 empty] | 1.16 | HT Panel Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 10
1 | [7 empty] | 1.17 | EMS Panel Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 10
1 | [7 empty] | 1.18 | CSS Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 10
1 | [7 empty] | 1.19 | NIFPS Panel Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Tesla / CTR | 20
1 | [7 empty] | 1.2 | NIFPS Fabrication | #VALUE! | #VALUE! | #VALUE! | Completed | - | Tesla / CTR | 1 | 0 | #VALUE!
1 | [7 empty] | 1.21 | Battery Container Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 10 | 4 | #VALUE!
1 | [7 empty] | 1.22 | HT cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 1500 | 48 | #VALUE!
1 | [7 empty] | 1.23 | HT cable termination | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 8 | 6 | #VALUE! | Torquing WIP
1 | [7 empty] | 1.24 | DC Cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 600 | 10 | #VALUE!
1 | [7 empty] | 1.25 | LT Cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 600 | 10 | #VALUE!
1 | [7 empty] | 1.26 | DC Cable termination | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 30 | 18 | #VALUE!
1 | [7 empty] | 1.27 | LT Cable termination | #VALUE! | #VALUE! | #VALUE! | 11 Jul, 15 Jul, 25 Jul, 30 Jul | 2026-07-30 | Akshar | 30 | 18 | #VALUE! | Lugging completed, Torquing WIP (2160 completed) traffo CT replacement WIP.
1 | [7 empty] | 1.28 | Aux Cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 1000 | 10 | #VALUE!
1 | [7 empty] | 1.29 | Control Cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 1000 | 10 | #VALUE!
1 | [7 empty] | 1.3 | Communication Cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 500 | 10 | #VALUE!
1 | [7 empty] | 1.31 | Aux Cable termination | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 30 | 6 | #VALUE!
1 | [7 empty] | 1.32 | Control Cable termination | #VALUE! | #VALUE! | #VALUE! | 11 Jul, 15 Jul, 26 Jul, 30 Jul | 2026-07-30 | Akshar & Honeywell | 30 | 4 | #VALUE!
1 | [7 empty] | 1.33 | Communication Cable termination | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar & Honeywell | - | - | - |  | #VALUE! | #VALUE! | #VALUE!
1 | [7 empty] | 1.34 | CT SFRA & Tan delta Test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 2 | 8 | -
1 | [7 empty] | 1.35 | CT Routine Test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar |  |  | -
1 | [7 empty] | 1.36 | CT Control scheme & Stability Test | #VALUE! | #VALUE! | #VALUE! | 21 Jul, 25 Jul, 28 Jul, 30 Jul | 2026-07-30 | Akshar | 2 | 4 | #VALUE! |  | 0 | #VALUE! | #VALUE!
1 | [7 empty] | 1.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 0.5 | 4 | #VALUE!
1 | [7 empty] | 1.38 | HT Panel relay test | #VALUE! | #VALUE! | #VALUE! | 19 Jul, 23 Jul, 27 Jul, 30 Jul | 2026-07-30 | Akshar | 6 | 4 | #VALUE!
1 | [7 empty] | 1.39 | HT Cable VLF Test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 6 | 5 | #VALUE!
1 | [7 empty] | 1.4 | CSS routine test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 1 | 5 | #VALUE!
1 | [7 empty] | 1.41 | ACDB routine test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 3 | 5 | #VALUE!
1 | [7 empty] | 1.42 | Earthing | #VALUE! | #VALUE! | #VALUE! | 09 Jul, 13 Jul, 26 Jul, 30 Jul | 2026-07-30 | Akshar | 150 | 6 | #VALUE!
1 | [7 empty] | 1.43 | LA | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 5 | 6 | #VALUE! | CFT to be completed by 30 Jul.
2 | CATL | 2 | 04 Jul, 07 Jul 10 Jul 14 Jul | 271 MWh (48 Containers) | 31 Jul 02 Aug | 05 Aug 07 Aug | 08 Aug 10 Aug |  |  |  | Civil
2 | [7 empty] | 2.1 | BCF Precast Erection & Welding | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 2 | #VALUE!
2 | [7 empty] | 2.2 | CT Rail Fixing | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 16 | #VALUE!
2 | [7 empty] | 2.3 | PCS Slab casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 39 | #VALUE!
2 | [7 empty] | 2.4 | SGR Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 37 | #VALUE!
2 | [7 empty] | 2.5 | MCR Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 34 | #VALUE!
2 | [7 empty] | 2.6 | CSS Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 54 | #VALUE!
2 | [7 empty] | 2.7 | BOT Precast Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Sachi | 3 | 5 | #VALUE!
2 | [7 empty] | 2.8 | NIFPS Precast Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 5 | #VALUE!
2 | [7 empty] | 2.9 | PCS PEB | #VALUE! | 6 | #VALUE! | Completed | - | DP Consteel | 1 | 27 | #VALUE!
2 | [7 empty] | 2.1 | SGR PEB | #VALUE! | #VALUE! | #VALUE! | Completed | - | Synergy | 1 | 25 | #VALUE!
2 | [7 empty] | 2.11 | MCR PEB | #VALUE! | #VALUE! | #VALUE! | Completed | - | Metastar | - | - | -
2 | [10 empty] | Electrical
2 | [7 empty] | 2.12 | CT Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 2 | 4 | #VALUE!
2 | [7 empty] | 2.13 | PCS Erection | #VALUE! | #VALUE! | #VALUE! | 27 Jun, 14 Jul, 25 Jul, 30 Jul | 2026-07-30 | Akshar | 10 | 4 | #VALUE! | PCS Placed on slab, Anchoring WIP
2 | [7 empty] | 2.14 | ACDB Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 5 | 4 | #VALUE!
2 | [7 empty] | 2.15 | ECP Panel Erection (Communication Panel) | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 20 | 4 | 4
2 | [7 empty] | 2.16 | HT Panel Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 10
2 | [7 empty] | 2.17 | EMS Panel Erection | #VALUE! | #VALUE! | #VALUE! | 04 Jul, 15 Jul, 26 Jul, 30 Jul | 2026-07-30 | Akshar | 10 |  |  | Placed on slab, Anchoring WIP
2 | [7 empty] | 2.18 | CSS Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 10
2 | [7 empty] | 2.19 | NIFPS Panel Erection | #VALUE! | #VALUE! | #VALUE! | 09 Jul, 15 Jul, 22 Jul, 26 Jul | 2026-07-26 | Tesla / CTR | 20
2 | [7 empty] | 2.2 | NIFPS Fabrication | #VALUE! | #VALUE! | #VALUE! | 14 Jul, 20 Jul, 25 Jul, 28 Jul | 2026-07-28 | Tesla / CTR | 0.66667 | 0 | #VALUE!
2 | [7 empty] | 2.21 | Battery Container Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 10 | 4 | #VALUE!
2 | [7 empty] | 2.22 | HT cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 1500 | 48 | #VALUE!
2 | [7 empty] | 2.23 | HT cable termination | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 8 | 6 | #VALUE! | Lugging completed, Torquing WIP
2 | [7 empty] | 2.24 | DC Cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 600 | 10 | #VALUE!
2 | [7 empty] | 2.25 | LT Cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 600 | 10 | #VALUE!
2 | [7 empty] | 2.26 | DC Cable termination | #VALUE! | #VALUE! | #VALUE! | 15 Jul, 23 Jul, 28 Jul, 31 Aug | 2026-08-31 | Akshar | 30 | 18 | #VALUE! | Lugging - 1248, toquing - 512
2 | [7 empty] | 2.27 | LT Cable termination | #VALUE! | #VALUE! | #VALUE! | 15 Jul, 23 Jul, 28 Jul, 31 Aug | 2026-08-31 | Akshar | 30 | 18 | #VALUE! | Lugging - 2112, toquing - 384
2 | [7 empty] | 2.28 | Aux Cable laying | #VALUE! | #VALUE! | #VALUE! | 05 Jul, 10 Jul, 25 Jul, 30 Jul | 2026-07-30 | Akshar | 1000 | 10 | #VALUE!
2 | [7 empty] | 2.29 | Control Cable laying | #VALUE! | #VALUE! | #VALUE! | 05 Jul, 10 Jul, 25 Jul, 30 Jul | 2026-07-30 | Akshar | 1000 | 10 | #VALUE!
2 | [7 empty] | 2.3 | Communication Cable laying | #VALUE! | #VALUE! | #VALUE! | 05 Jul, 10 Jul, 25 Jul, 30 Jul | 2026-07-30 | Akshar | 500 | 10 | #VALUE!
2 | [7 empty] | 2.31 | Aux Cable termination | #VALUE! | #VALUE! | #VALUE! | 15 Jul, 24 Jul, 28 Jul, 31 Jul | 2026-07-31 | Akshar | 30 | 6 | #VALUE!
2 | [7 empty] | 2.32 | Control Cable termination | #VALUE! | #VALUE! | #VALUE! | 15 Jul, 24 Jul, 28 Jul, 31 Jul | 2026-07-31 | Akshar & Honeywell | 30 | 4 | #VALUE!
2 | [7 empty] | 2.33 | Communication Cable termination | #VALUE! | #VALUE! | #VALUE! | 15 Jul, 24 Jul, 28 Jul, 31 Jul | 2026-07-31 | Akshar & Honeywell | - | - | - |  | 1 | #VALUE! | #VALUE!
2 | [7 empty] | 2.34 | CT SFRA & Tan delta Test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 2 | 8 | -
2 | [7 empty] | 2.35 | CT Routine Test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar |  |  | -
2 | [7 empty] | 2.36 | CT Control scheme & Stability Test | #VALUE! | #VALUE! | #VALUE! | 28 Jul, 31 Jul, 02 Aug | 2026-08-02 | Akshar | 2 | 4 | #VALUE! |  | 3 | #VALUE! | #VALUE!
2 | [7 empty] | 2.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 0.5 | 4 | #VALUE!
2 | [7 empty] | 2.38 | HT Panel relay test | #VALUE! | #VALUE! | #VALUE! | 26 Jul, 29 Jul, 01 Aug | 2026-08-01 | Akshar | 6 | 4 | #VALUE!
2 | [7 empty] | 2.39 | HT Cable VLF Test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 6 | 5 | #VALUE!
2 | [7 empty] | 2.4 | CSS routine test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 1 | 5 | #VALUE!
2 | [7 empty] | 2.41 | ACDB routine test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 3 | 5 | #VALUE!
2 | [7 empty] | 2.42 | Earthing | #VALUE! | #VALUE! | #VALUE! | 13 Jul, 25 Jul, 28 Jul, 01 Aug | 2026-08-01 | Akshar | 150 | 6 | #VALUE!
2 | [7 empty] | 2.43 | LA | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 5 | 6 | #VALUE!
3 | CATL | 3 | 13 Jul 20 Jul 22 Jul | 271MWh (48 Containers) | 2026-08-06 | 2026-08-11 | 2026-08-14 |  |  |  | Civil
3 | [7 empty] | 3.1 | BCF Precast Erection & Welding | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 2 | #VALUE!
3 | [7 empty] | 3.2 | CT Rail Fixing | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 16 | #VALUE!
3 | [7 empty] | 3.3 | PCS Slab casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 39 | #VALUE!
3 | [7 empty] | 3.4 | SGR Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 37 | #VALUE!
3 | [7 empty] | 3.5 | MCR Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 34 | #VALUE!
3 | [7 empty] | 3.6 | CSS Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 54 | #VALUE!
3 | [7 empty] | 3.7 | BOT Precast Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Sachi | 3 | 5 | #VALUE!
3 | [7 empty] | 3.8 | NIFPS Precast Erection | #VALUE! | #VALUE! | #VALUE! | 24 Jun, 08 Jul, 20 Jul, 28 Jul | 2026-07-28 | MSC | 1 | 5 | #VALUE! | Cable trench excavated, will be done post trench backfilling
3 | [7 empty] | 3.9 | PCS PEB | #VALUE! | #VALUE! | #VALUE! | Completed | - | DP Consteel | 1 | 27 | #VALUE!
3 | [7 empty] | 3.1 | SGR PEB | #VALUE! | #VALUE! | #VALUE! | 05 Jul, 20 Jul, 25 Jul, 28 Jul | 2026-07-28 | Synergy | 1 | 25 | #VALUE!
3 | [7 empty] | 3.11 | MCR PEB | #VALUE! | #VALUE! | #VALUE! | 06 Jul, 10 Jul, 24 Jul, 29 Jul | 2026-07-29 | Metastar | - | - | -
3 | [10 empty] | Electrical
3 | [7 empty] | 3.12 | CT Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 2 | 4 | #VALUE!
3 | [7 empty] | 3.13 | PCS Erection | #VALUE! | #VALUE! | #VALUE! | 06 Jul, 16 Jul, 24 Jul, 29 Jul | 2026-07-29 | Akshar | 10 | 4 | #VALUE!
3 | [7 empty] | 3.14 | ACDB Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 5 | 4 | #VALUE!
3 | [7 empty] | 3.15 | ECP Panel Erection (Communication Panel) | #VALUE! | #VALUE! | #VALUE! | 06 Jul, 15 Jul, 19 Jul, 29 Jul | 2026-07-29 | Akshar | 20 | 4 | 4
3 | [7 empty] | 3.16 | HT Panel Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 10 |  |  | Placed on slab, anchoring WIP
3 | [7 empty] | 3.17 | EMS Panel Erection | #VALUE! | #VALUE! | #VALUE! | 13 Jul, 17 Jul, 20 Jul, 26 Jul | 2026-07-26 | Akshar | 10
3 | [7 empty] | 3.18 | CSS Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 10
3 | [7 empty] | 3.19 | NIFPS Panel Erection | #VALUE! | #VALUE! | #VALUE! | 17 Jul, 23 Jul, 27 Jul | 2026-07-27 | Tesla / CTR | 20
3 | [7 empty] | 3.2 | NIFPS Fabrication | #VALUE! | #VALUE! | #VALUE! | 22 Jul, 26 Jul, 31 Jul | 2026-07-31 | Tesla / CTR | 0.66667 | 0 | #VALUE!
3 | [7 empty] | 3.21 | Battery Container Erection | #VALUE! | #VALUE! | #VALUE! | 18 Jul, 24 Jul, 28 Jul | 2026-07-28 | Akshar | 10 | 4 | #VALUE! | Welding with foundation WIP
3 | [7 empty] | 3.22 | HT cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 1500 | 48 | #VALUE!
3 | [7 empty] | 3.23 | HT cable termination | #VALUE! | #VALUE! | #VALUE! | 20 Jul, 29 Jul | 2026-07-29 | Akshar | 8 | 6 | #VALUE!
3 | [7 empty] | 3.24 | DC Cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 600 | 10 | #VALUE!
3 | [7 empty] | 3.25 | LT Cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 600 | 10 | #VALUE!
3 | [7 empty] | 3.26 | DC Cable termination | #VALUE! | #VALUE! | #VALUE! | 24 Jul, 01 Aug | 2026-08-01 | Akshar | 30 | 18 | #VALUE!
3 | [7 empty] | 3.27 | LT Cable termination | #VALUE! | #VALUE! | #VALUE! | 24 Jul, 01 Aug | 2026-08-01 | Akshar | 30 | 18 | #VALUE!
3 | [7 empty] | 3.28 | Aux Cable laying | #VALUE! | #VALUE! | #VALUE! | 14 Jul, 23 Jul, 29 Jul | 2026-07-29 | Akshar | 1000 | 10 | #VALUE!
3 | [7 empty] | 3.29 | Control Cable laying | #VALUE! | #VALUE! | #VALUE! | 14 Jul, 23 Jul, 29 Jul | 2026-07-29 | Akshar | 1000 | 10 | #VALUE!
3 | [7 empty] | 3.3 | Communication Cable laying | #VALUE! | #VALUE! | #VALUE! | 14 Jul, 23 Jul, 29 Jul | 2026-07-29 | Akshar | 500 | 10 | #VALUE!
3 | [7 empty] | 3.31 | Aux Cable termination | #VALUE! | #VALUE! | #VALUE! | 24 Jul, 26 Jul, 01 Aug | 2026-08-01 | Akshar | 30 | 6 | #VALUE!
3 | [7 empty] | 3.32 | Control Cable termination | #VALUE! | #VALUE! | #VALUE! | 24 Jul, 26 Jul, 01 Aug | 2026-08-01 | Akshar & Honeywell | 30 | 4 | #VALUE!
3 | [7 empty] | 3.33 | Communication Cable termination | #VALUE! | #VALUE! | #VALUE! | 24 Jul, 26 Jul, 01 Aug | 2026-08-01 | Akshar & Honeywell | - | - | - |  | 2 | #VALUE! | #VALUE!
3 | [7 empty] | 3.34 | CT SFRA & Tan delta Test | #VALUE! | #VALUE! | #VALUE! | 09 Jul, 20 Jul, 27 Jul | 2026-07-27 | Akshar | 2 | 8 | 12
3 | [7 empty] | 3.35 | CT Routine Test | #VALUE! | #VALUE! | #VALUE! | 13 Jul, 21 Jul, 29 Jul | 2026-07-29 | Akshar
3 | [7 empty] | 3.36 | CT Control scheme & Stability Test | #VALUE! | #VALUE! | #VALUE! | 2026-08-03 | 2026-08-03 | Akshar | 2 | 4 | #VALUE! |  | 4 | #VALUE! | #VALUE!
3 | [7 empty] | 3.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | #VALUE! | #VALUE! | #VALUE! | 20 Jul, 29 Jul | 2026-07-29 | Akshar | 0.5 | 4 | #VALUE!
3 | [7 empty] | 3.38 | HT Panel relay test | #VALUE! | #VALUE! | #VALUE! | 2026-08-01 | 2026-08-01 | Akshar | 6 | 4 | #VALUE!
3 | [7 empty] | 3.39 | HT Cable VLF Test | #VALUE! | #VALUE! | #VALUE! | 20 Jul, 31 Jul | 2026-07-31 | Akshar | 6 | 5 | #VALUE!
3 | [7 empty] | 3.4 | CSS routine test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 1 | 5 | #VALUE!
3 | [7 empty] | 3.41 | ACDB routine test | #VALUE! | #VALUE! | #VALUE! | 20 Jul, 30 Jul | 2026-07-30 | Akshar | 3 | 5 | #VALUE!
3 | [7 empty] | 3.42 | Earthing | #VALUE! | #VALUE! | #VALUE! | 22 Jul, 03 Aug | 2026-08-03 | Akshar | 150 | 6 | #VALUE!
3 | [7 empty] | 3.43 | LA | #VALUE! | #VALUE! | #VALUE! | 24 Jul, 31 Jul | 2026-07-31 | Akshar | 5 | 6 | #VALUE!
5 | CATL | 5 | 14 Jul 21 Jul 24 Jul | 271 MWh (48 Containers) | 2026-08-07 | 2026-08-12 | 2026-08-15 |  |  |  | Civil
5 | [7 empty] | 5.1 | BCF Precast Erection & Welding | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 2 | #VALUE!
5 | [7 empty] | 5.2 | CT Rail Fixing | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 16 | #VALUE!
5 | [7 empty] | 5.3 | PCS Slab casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 39 | #VALUE!
5 | [7 empty] | 5.4 | SGR Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 37 | #VALUE!
5 | [7 empty] | 5.5 | MCR Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 34 | #VALUE!
5 | [7 empty] | 5.6 | CSS Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 54 | #VALUE!
5 | [7 empty] | 5.7 | BOT Precast Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Sachi | 3 | 5 | #VALUE!
5 | [7 empty] | 5.8 | NIFPS Precast Erection | #VALUE! | #VALUE! | #VALUE! | 26 Jun, 08 Jul, 21 Jul, 28 Jul | 2026-07-28 | MSC | 1 | 5 | #VALUE! | Cable trench excavated, will be done post trench backfilling
5 | [7 empty] | 5.9 | PCS PEB | #VALUE! | #VALUE! | #VALUE! | Completed | - | DP Consteel | 1 | 27 | #VALUE!
5 | [7 empty] | 5.1 | SGR PEB | #VALUE! | #VALUE! | #VALUE! | 10 Jul, 18 Jul, 28 Jul | 2026-07-28 | Synergy | 1 | 25 | #VALUE!
5 | [7 empty] | 5.11 | MCR PEB | #VALUE! | #VALUE! | #VALUE! | Completed | - | Metastar | - | - | -
5 | [10 empty] | Electrical
5 | [7 empty] | 5.12 | CT Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 2 | 4 | #VALUE!
5 | [7 empty] | 5.13 | PCS Erection | #VALUE! | #VALUE! | #VALUE! | 07 Jul, 18 Jul, 27 Jul, 30 Jul | 2026-07-30 | Akshar | 10 | 4 | #VALUE!
5 | [7 empty] | 5.14 | ACDB Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 5 | 4 | #VALUE!
5 | [7 empty] | 5.15 | ECP Panel Erection (Communication Panel) | #VALUE! | #VALUE! | #VALUE! | 07 Jul, 15 Jul, 25 Jul, 30 Jul | 2026-07-30 | Akshar | 20 | 4 | 4
5 | [7 empty] | 5.16 | HT Panel Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 10
5 | [7 empty] | 5.17 | EMS Panel Erection | #VALUE! | #VALUE! | #VALUE! | 14 Jul, 19 Jul, 27 Jul | 2026-07-27 | Akshar | 10
5 | [7 empty] | 5.18 | CSS Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 10
5 | [7 empty] | 5.19 | NIFPS Panel Erection | #VALUE! | #VALUE! | #VALUE! | 21 Jul, 26 Jul | 2026-07-26 | Tesla / CTR | 20
5 | [7 empty] | 5.2 | NIFPS Fabrication | #VALUE! | #VALUE! | #VALUE! | 26 Jul, 29 Jul | 2026-07-29 | Tesla / CTR | 0.66667 | 0 | #VALUE!
5 | [7 empty] | 5.21 | Battery Container Erection | #VALUE! | #VALUE! | #VALUE! | 19 Jul, 25 Jul | 2026-07-25 | Akshar | 10 | 4 | #VALUE!
5 | [7 empty] | 5.22 | HT cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 1500 | 48 | #VALUE!
5 | [7 empty] | 5.23 | HT cable termination | #VALUE! | #VALUE! | #VALUE! | 21 Jul, 30 Jul | 2026-07-30 | Akshar | 8 | 6 | #VALUE!
5 | [7 empty] | 5.24 | DC Cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 600 | 10 | #VALUE!
5 | [7 empty] | 5.25 | LT Cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 600 | 10 | #VALUE!
5 | [7 empty] | 5.26 | DC Cable termination | #VALUE! | #VALUE! | #VALUE! | 25 Jul, 02 Aug | 2026-08-02 | Akshar | 30 | 18 | #VALUE!
5 | [7 empty] | 5.27 | LT Cable termination | #VALUE! | #VALUE! | #VALUE! | 25 Jul, 02 Aug | 2026-08-02 | Akshar | 30 | 18 | #VALUE!
5 | [7 empty] | 5.28 | Aux Cable laying | #VALUE! | #VALUE! | #VALUE! | 15 Jul, 25 Jul, 30 Jul | 2026-07-30 | Akshar | 1000 | 10 | #VALUE!
5 | [7 empty] | 5.29 | Control Cable laying | #VALUE! | #VALUE! | #VALUE! | 15 Jul, 25 Jul, 30 Jul | 2026-07-30 | Akshar | 1000 | 10 | #VALUE!
5 | [7 empty] | 5.3 | Communication Cable laying | #VALUE! | #VALUE! | #VALUE! | 15 Jul, 25 Jul, 30 Jul | 2026-07-30 | Akshar | 500 | 10 | #VALUE!
5 | [7 empty] | 5.31 | Aux Cable termination | #VALUE! | #VALUE! | #VALUE! | 25 Jul, 27 Jul, 02 Aug | 2026-08-02 | Akshar | 30 | 6 | #VALUE!
5 | [7 empty] | 5.32 | Control Cable termination | #VALUE! | #VALUE! | #VALUE! | 25 Jul, 27 Jul, 02 Aug | 2026-08-02 | Akshar & Honeywell | 30 | 4 | #VALUE!
5 | [7 empty] | 5.33 | Communication Cable termination | #VALUE! | #VALUE! | #VALUE! | 25 Jul, 27 Jul, 02 Aug | 2026-08-02 | Akshar & Honeywell | - | - | - |  | 3 | #VALUE! | #VALUE!
5 | [7 empty] | 5.34 | CT SFRA & Tan delta Test | #VALUE! | #VALUE! | #VALUE! | 10 Jul, 23 Jul, 28 Jul | 2026-07-28 | Akshar | 2 | 8 | 12
5 | [7 empty] | 5.35 | CT Routine Test | #VALUE! | #VALUE! | #VALUE! | 14 Jul, 24 Jul, 30 Jul | 2026-07-30 | Akshar
5 | [7 empty] | 5.36 | CT Control scheme & Stability Test | #VALUE! | #VALUE! | #VALUE! | 2026-08-04 | 2026-08-04 | Akshar | 2 | 4 | #VALUE! |  | 5 | #VALUE! | #VALUE!
5 | [7 empty] | 5.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | #VALUE! | #VALUE! | #VALUE! | 21 Jul, 30 Jul | 2026-07-30 | Akshar | 0.5 | 4 | #VALUE!
5 | [7 empty] | 5.38 | HT Panel relay test | #VALUE! | #VALUE! | #VALUE! | 2026-08-02 | 2026-08-02 | Akshar | 6 | 4 | #VALUE!
5 | [7 empty] | 5.39 | HT Cable VLF Test | #VALUE! | #VALUE! | #VALUE! | 21 Jul, 01 Aug | 2026-08-01 | Akshar | 6 | 5 | #VALUE!
5 | [7 empty] | 5.4 | CSS routine test | #VALUE! | #VALUE! | #VALUE! | 21 Jul, 31 Jul | 2026-07-31 | Akshar | 1 | 5 | #VALUE!
5 | [7 empty] | 5.41 | ACDB routine test | #VALUE! | #VALUE! | #VALUE! | 21 Jul, 31 Jul | 2026-07-31 | Akshar | 3 | 5 | #VALUE!
5 | [7 empty] | 5.42 | Earthing | #VALUE! | #VALUE! | #VALUE! | 23 Jul, 04 Aug | 2026-08-04 | Akshar | 150 | 6 | #VALUE!
5 | [7 empty] | 5.43 | LA | #VALUE! | #VALUE! | #VALUE! | 25 Jul, 01 Aug | 2026-08-01 | Akshar | 5 | 6 | #VALUE!
6 | CATL | 6 | 03 Aug 17 Aug 02 Aug 04 Aug | 271 MWh (48 Containers) | 2026-08-24 | 2026-08-28 | 2026-08-31 |  |  |  | Civil
6 | [7 empty] | 6.1 | BCF Precast Erection & Welding | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 2 | #VALUE! | Container welding with foundation WIP
6 | [7 empty] | 6.2 | CT Rail Fixing | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 16 | #VALUE!
6 | [7 empty] | 6.3 | PCS Slab casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 39 | #VALUE!
6 | [7 empty] | 6.4 | SGR Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 37 | #VALUE!
6 | [7 empty] | 6.5 | MCR Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 34 | #VALUE!
6 | [7 empty] | 6.6 | CSS Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 54 | #VALUE!
6 | [7 empty] | 6.7 | BOT Precast Erection | #VALUE! | #VALUE! | #VALUE! | 30 Jun, 10 Jul, 21 Jul, 27 Jul | 2026-07-27 | Sachi | 3 | 5 | #VALUE!
6 | [7 empty] | 6.8 | NIFPS Precast Erection | #VALUE! | #VALUE! | #VALUE! | 30 Jun, 10 Jul, 22 Jul, 29 Jul | 2026-07-29 | MSC | 1 | 5 | #VALUE!
6 | [7 empty] | 6.9 | PCS PEB | #VALUE! | #VALUE! | #VALUE! | Completed | - | DP Consteel | 1 | 27 | #VALUE!
6 | [7 empty] | 6.1 | SGR PEB | #VALUE! | #VALUE! | #VALUE! | 20 Jul, 30 Jul | 2026-07-30 | Synergy | 1 | 25 | #VALUE!
6 | [7 empty] | 6.11 | MCR PEB | #VALUE! | #VALUE! | #VALUE! | 10 Jul, 20 Jul, 31 Jul | 2026-07-31 | Metastar | - | - | -
6 | [10 empty] | Electrical
6 | [7 empty] | 6.12 | CT Erection | #VALUE! | #VALUE! | #VALUE! | 27 Jul, 07 Aug | 2026-08-07 | Akshar | 2 | 4 | ,
6 | [7 empty] | 6.13 | PCS Erection | #VALUE! | #VALUE! | #VALUE! | 27 Jul, 02 Aug | 2026-08-02 | Akshar | 10 | 4 | #VALUE!
6 | [7 empty] | 6.14 | ACDB Erection | #VALUE! | #VALUE! | #VALUE! | 30 Jul, 04 Aug | 2026-08-04 | Akshar | 5 | 4 | #VALUE!
6 | [7 empty] | 6.15 | ECP Panel Erection (Communication Panel) | #VALUE! | #VALUE! | #VALUE! | 27 Jul, 04 Aug | 2026-08-04 | Akshar | 20 | 4 | 4
6 | [7 empty] | 6.16 | HT Panel Erection | #VALUE! | #VALUE! | #VALUE! | 27 Jul, 04 Aug | 2026-08-04 | Akshar | 10
6 | [7 empty] | 6.17 | EMS Panel Erection | #VALUE! | #VALUE! | #VALUE! | 2026-08-03 | 2026-08-03 | Akshar | 10
6 | [7 empty] | 6.18 | CSS Erection | #VALUE! | #VALUE! | #VALUE! | 2026-08-03 | 2026-08-03 | Akshar | 10
6 | [7 empty] | 6.19 | NIFPS Panel Erection | #VALUE! | #VALUE! | #VALUE! | 25 Jul, 05 Aug | 2026-08-05 | Tesla / CTR | 20
6 | [7 empty] | 6.2 | NIFPS Fabrication | #VALUE! | #VALUE! | #VALUE! | 30 Jul, 08 Aug | 2026-08-08 | Tesla / CTR | 0.66667 | 0 | #VALUE!
6 | [7 empty] | 6.21 | Battery Container Erection | #VALUE! | #VALUE! | #VALUE! | 2026-08-08 | 2026-08-08 | Akshar | 10 | 4 | #VALUE!
6 | [7 empty] | 6.22 | HT cable laying | #VALUE! | #VALUE! | #VALUE! | 25 Jul, 09 Aug | 2026-08-09 | Akshar | 1500 | 48 | #VALUE!
6 | [7 empty] | 6.23 | HT cable termination | #VALUE! | #VALUE! | #VALUE! | 10 Aug, 12 Aug | 2026-08-12 | Akshar | 8 | 6 | #VALUE!
6 | [7 empty] | 6.24 | DC Cable laying | #VALUE! | #VALUE! | #VALUE! | 31 Jul, 10 Aug | 2026-08-10 | Akshar | 600 | 10 | #VALUE!
6 | [7 empty] | 6.25 | LT Cable laying | #VALUE! | #VALUE! | #VALUE! | 25 Jul, 10 Aug | 2026-08-10 | Akshar | 600 | 10 | #VALUE!
6 | [7 empty] | 6.26 | DC Cable termination | #VALUE! | #VALUE! | #VALUE! | 2026-08-14 | 2026-08-14 | Akshar | 30 | 18 | #VALUE!
6 | [7 empty] | 6.27 | LT Cable termination | #VALUE! | #VALUE! | #VALUE! | 2026-08-14 | 2026-08-14 | Akshar | 30 | 18 | #VALUE!
6 | [7 empty] | 6.28 | Aux Cable laying | #VALUE! | #VALUE! | #VALUE! | 04 Aug, 12 Aug | 2026-08-12 | Akshar | 1000 | 10 | #VALUE!
6 | [7 empty] | 6.29 | Control Cable laying | #VALUE! | #VALUE! | #VALUE! | 04 Aug, 12 Aug | 2026-08-12 | Akshar | 1000 | 10 | #VALUE!
6 | [7 empty] | 6.3 | Communication Cable laying | #VALUE! | #VALUE! | #VALUE! | 04 Aug, 12 Aug | 2026-08-12 | Akshar | 500 | 10 | #VALUE!
6 | [7 empty] | 6.31 | Aux Cable termination | #VALUE! | #VALUE! | #VALUE! | 14 Aug, 16 Aug | 2026-08-16 | Akshar | 30 | 6 | #VALUE!
6 | [7 empty] | 6.32 | Control Cable termination | #VALUE! | #VALUE! | #VALUE! | 14 Aug, 16 Aug | 2026-08-16 | Akshar & Honeywell | 30 | 4 | #VALUE!
6 | [7 empty] | 6.33 | Communication Cable termination | #VALUE! | #VALUE! | #VALUE! | 14 Aug, 16 Aug | 2026-08-16 | Akshar & Honeywell | - | - | - |  | 17 | #VALUE! | #VALUE!
6 | [7 empty] | 6.34 | CT SFRA & Tan delta Test | #VALUE! | #VALUE! | #VALUE! | 30 Jul, 12 Aug | 2026-08-12 | Akshar | 2 | 8 | 12
6 | [7 empty] | 6.35 | CT Routine Test | #VALUE! | #VALUE! | #VALUE! | 03 Aug, 15 Aug | 2026-08-15 | Akshar
6 | [7 empty] | 6.36 | CT Control scheme & Stability Test | #VALUE! | #VALUE! | #VALUE! | 24 Aug, 26 Aug | 2026-08-26 | Akshar | 2 | 4 | #VALUE! |  | 27 | #VALUE! | #VALUE!
6 | [7 empty] | 6.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | #VALUE! | #VALUE! | #VALUE! | 2026-08-10 | 2026-08-10 | Akshar | 0.5 | 4 | #VALUE!
6 | [7 empty] | 6.38 | HT Panel relay test | #VALUE! | #VALUE! | #VALUE! | 22 Aug, 24 Aug | 2026-08-24 | Akshar | 6 | 4 | #VALUE!
6 | [7 empty] | 6.39 | HT Cable VLF Test | #VALUE! | #VALUE! | #VALUE! | 10 Aug, 14 Aug | 2026-08-14 | Akshar | 6 | 5 | #VALUE!
6 | [7 empty] | 6.4 | CSS routine test | #VALUE! | #VALUE! | #VALUE! | 2026-08-10 | 2026-08-10 | Akshar | 1 | 5 | #VALUE!
6 | [7 empty] | 6.41 | ACDB routine test | #VALUE! | #VALUE! | #VALUE! | 2026-08-10 | 2026-08-10 | Akshar | 3 | 5 | #VALUE!
6 | [7 empty] | 6.42 | Earthing | #VALUE! | #VALUE! | #VALUE! | 12 Aug, 21 Aug | 2026-08-21 | Akshar | 150 | 6 | #VALUE!
6 | [7 empty] | 6.43 | LA | #VALUE! | #VALUE! | #VALUE! | 14 Aug, 21 Aug | 2026-08-21 | Akshar | 5 | 6 | #VALUE!
7 | CATL | 7 | 07 Aug 19 Aug 27 Aug 29 Aug | 271 MWh (48 Containers) | 31 Aug 17 Sep | 05 Sep 22 Sep | 08 Sep 25 Sep |  |  |  | Civil
7 | [7 empty] | 7.1 | BCF Precast Erection & Welding | #VALUE! | #VALUE! | #VALUE! | 10 Jul, 12 Jul, 22 Jul, 26 Jul | 2026-07-26 | MSC | 1 | 2 | #VALUE!
7 | [7 empty] | 7.2 | CT Rail Fixing | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 16 | #VALUE!
7 | [7 empty] | 7.3 | PCS Slab casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 39 | #VALUE!
7 | [7 empty] | 7.4 | SGR Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 37 | #VALUE!
7 | [7 empty] | 7.5 | MCR Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 34 | #VALUE!
7 | [7 empty] | 7.6 | CSS Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 54 | #VALUE!
7 | [7 empty] | 7.7 | BOT Precast Erection | #VALUE! | #VALUE! | #VALUE! | 30 Jun, 10 Jul, 21 Jul, 27 Jul | 2026-07-27 | Sachi | 3 | 5 | #VALUE!
7 | [7 empty] | 7.8 | NIFPS Precast Erection | #VALUE! | #VALUE! | #VALUE! | 30 Jun, 10 Jul, 23 Jul, 29 Jul | 2026-07-29 | MSC | 1 | 5 | #VALUE!
7 | [7 empty] | 7.9 | PCS PEB | #VALUE! | #VALUE! | #VALUE! | Completed | - | DP Consteel | 1 | 27 | #VALUE!
7 | [7 empty] | 7.1 | SGR PEB | #VALUE! | #VALUE! | #VALUE! | 25 Jul, 03 Aug | 2026-08-03 | Synergy | 1 | 25 | #VALUE!
7 | [7 empty] | 7.11 | MCR PEB | #VALUE! | #VALUE! | #VALUE! | 20 Jul, 03 Aug | 2026-08-03 | Metastar | - | - | -
7 | [10 empty] | Electrical
7 | [7 empty] | 7.12 | CT Erection | #VALUE! | #VALUE! | #VALUE! | 31 Jul, 05 Aug | 2026-08-05 | Akshar | 2 | 4 | #VALUE!
7 | [7 empty] | 7.13 | PCS Erection | #VALUE! | #VALUE! | #VALUE! | 31 Jul, 05 Aug | 2026-08-05 | Akshar | 10 | 4 | #VALUE!
7 | [7 empty] | 7.14 | ACDB Erection | #VALUE! | #VALUE! | #VALUE! | 2026-08-03 | 2026-08-03 | Akshar | 5 | 4 | #VALUE!
7 | [7 empty] | 7.15 | ECP Panel Erection (Communication Panel) | #VALUE! | #VALUE! | #VALUE! | 31 Jul, 05 Aug | 2026-08-05 | Akshar | 20 | 4 | 4
7 | [7 empty] | 7.16 | HT Panel Erection | #VALUE! | #VALUE! | #VALUE! | 31 Jul, 05 Aug | 2026-08-05 | Akshar | 10
7 | [7 empty] | 7.17 | EMS Panel Erection | #VALUE! | #VALUE! | #VALUE! | 2026-08-07 | 2026-08-07 | Akshar | 10
7 | [7 empty] | 7.18 | CSS Erection | #VALUE! | #VALUE! | #VALUE! | 2026-08-07 | 2026-08-07 | Akshar | 10
7 | [7 empty] | 7.19 | NIFPS Panel Erection | #VALUE! | #VALUE! | #VALUE! | 29 Jul, 08 Aug | 2026-08-08 | Tesla / CTR | 20
7 | [7 empty] | 7.2 | NIFPS Fabrication | #VALUE! | #VALUE! | #VALUE! | 03 Aug, 11 Aug | 2026-08-11 | Tesla / CTR | 0.66667 | 0 | #VALUE!
7 | [7 empty] | 7.21 | Battery Container Erection | #VALUE! | #VALUE! | #VALUE! | 12 Aug, 23 Aug, 31 Aug | 2026-08-31 | Akshar | 10 | 4 | #VALUE!
7 | [7 empty] | 7.22 | HT cable laying | #VALUE! | #VALUE! | #VALUE! | 29 Jul, 09 Aug | 2026-08-09 | Akshar | 1500 | 48 | #VALUE!
7 | [7 empty] | 7.23 | HT cable termination | #VALUE! | #VALUE! | #VALUE! | 2026-08-14 | 2026-08-14 | Akshar | 8 | 6 | #VALUE!
7 | [7 empty] | 7.24 | DC Cable laying | #VALUE! | #VALUE! | #VALUE! | 2026-08-04 | 2026-08-04 | Akshar | 600 | 10 | #VALUE!
7 | [7 empty] | 7.25 | LT Cable laying | #VALUE! | #VALUE! | #VALUE! | 29 Jul, 04 Aug | 2026-08-04 | Akshar | 600 | 10 | #VALUE!
7 | [7 empty] | 7.26 | DC Cable termination | #VALUE! | #VALUE! | #VALUE! | 18 Aug, 24 Aug, 09 Sep | 2026-09-09 | Akshar | 30 | 18 | #VALUE!
7 | [7 empty] | 7.27 | LT Cable termination | #VALUE! | #VALUE! | #VALUE! | 18 Aug, 30 Aug | 2026-08-30 | Akshar | 30 | 18 | #VALUE!
7 | [7 empty] | 7.28 | Aux Cable laying | #VALUE! | #VALUE! | #VALUE! | 2026-08-08 | 2026-08-08 | Akshar | 1000 | 10 | #VALUE!
7 | [7 empty] | 7.29 | Control Cable laying | #VALUE! | #VALUE! | #VALUE! | 2026-08-08 | 2026-08-08 | Akshar | 1000 | 10 | #VALUE!
7 | [7 empty] | 7.3 | Communication Cable laying | #VALUE! | #VALUE! | #VALUE! | 2026-08-08 | 2026-08-08 | Akshar | 500 | 10 | #VALUE!
7 | [7 empty] | 7.31 | Aux Cable termination | #VALUE! | #VALUE! | #VALUE! | 18 Aug, 24 Aug, 09 Sep | 2026-09-09 | Akshar | 30 | 6 | #VALUE!
7 | [7 empty] | 7.32 | Control Cable termination | #VALUE! | #VALUE! | #VALUE! | 18 Aug, 24 Aug, 09 Sep | 2026-09-09 | Akshar & Honeywell | 30 | 4 | #VALUE!
7 | [7 empty] | 7.33 | Communication Cable termination | #VALUE! | #VALUE! | #VALUE! | 18 Aug, 24 Aug, 09 Sep | 2026-09-09 | Akshar & Honeywell | - | - | - |  | 41 | #VALUE! | #VALUE!
7 | [7 empty] | 7.34 | CT SFRA & Tan delta Test | #VALUE! | #VALUE! | #VALUE! | 03 Aug, 11 Aug | 2026-08-11 | Akshar | 2 | 8 | 12
7 | [7 empty] | 7.35 | CT Routine Test | #VALUE! | #VALUE! | #VALUE! | 07 Aug, 15 Aug | 2026-08-15 | Akshar
7 | [7 empty] | 7.36 | CT Control scheme & Stability Test | #VALUE! | #VALUE! | #VALUE! | 28 Aug, 14 Sep | 2026-09-14 | Akshar | 2 | 4 | #VALUE! |  | 46 | #VALUE! | #VALUE!
7 | [7 empty] | 7.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | #VALUE! | #VALUE! | #VALUE! | 14 Aug, 24 Aug | 2026-08-24 | Akshar | 0.5 | 4 | #VALUE!
7 | [7 empty] | 7.38 | HT Panel relay test | #VALUE! | #VALUE! | #VALUE! | 26 Aug, 12 Sep | 2026-09-12 | Akshar | 6 | 4 | #VALUE!
7 | [7 empty] | 7.39 | HT Cable VLF Test | #VALUE! | #VALUE! | #VALUE! | 14 Aug, 24 Aug | 2026-08-24 | Akshar | 6 | 5 | #VALUE!
7 | [7 empty] | 7.4 | CSS routine test | #VALUE! | #VALUE! | #VALUE! | 14 Aug, 24 Aug | 2026-08-24 | Akshar | 1 | 5 | #VALUE!
7 | [7 empty] | 7.41 | ACDB routine test | #VALUE! | #VALUE! | #VALUE! | 14 Aug, 24 Aug | 2026-08-24 | Akshar | 3 | 5 | #VALUE!
7 | [7 empty] | 7.42 | Earthing | #VALUE! | #VALUE! | #VALUE! | 16 Aug, 02 Sep | 2026-09-02 | Akshar | 150 | 6 | #VALUE!
7 | [7 empty] | 7.43 | LA | #VALUE! | #VALUE! | #VALUE! | 18 Aug, 04 Sep | 2026-09-04 | Akshar | 5 | 6 | #VALUE!
8 | CATL | 8 | 18 Aug 23 Aug 27 Aug 29 Aug | 271 MWh (48 Containers) | 11 Sep 17 Sep | 16 Sep 22 Sep | 19 Sep 25 Sep |  |  |  | Civil
8 | [7 empty] | 8.1 | BCF Precast Erection & Welding | #VALUE! | #VALUE! | #VALUE! | 14 Jul, 25 Jul | 2026-07-25 | MSC | 1 | 2 | #VALUE!
8 | [7 empty] | 8.2 | CT Rail Fixing | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 16 | #VALUE!
8 | [7 empty] | 8.3 | PCS Slab casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 39 | #VALUE!
8 | [7 empty] | 8.4 | SGR Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 37 | #VALUE!
8 | [7 empty] | 8.5 | MCR Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 34 | #VALUE!
8 | [7 empty] | 8.6 | CSS Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 54 | #VALUE!
8 | [7 empty] | 8.7 | BOT Precast Erection | #VALUE! | #VALUE! | #VALUE! | 05 Jul, 10 Jul, 22 Jul, 27 Jul | 2026-07-27 | Sachi | 3 | 5 | #VALUE!
8 | [7 empty] | 8.8 | NIFPS Precast Erection | #VALUE! | #VALUE! | #VALUE! | 05 Jul, 10 Jul, 23 Jul, 29 Jul | 2026-07-29 | MSC | 1 | 5 | #VALUE!
8 | [7 empty] | 8.9 | PCS PEB | #VALUE! | #VALUE! | #VALUE! | Completed | - | DP Consteel | 1 | 27 | #VALUE!
8 | [7 empty] | 8.1 | SGR PEB | #VALUE! | #VALUE! | #VALUE! | 25 Jul, 06 Aug | 2026-08-06 | Synergy | 1 | 25 | #VALUE!
8 | [7 empty] | 8.11 | MCR PEB | #VALUE! | #VALUE! | #VALUE! | 20 Jul, 06 Aug | 2026-08-06 | Metastar | - | - | -
8 | [10 empty] | Electrical
8 | [7 empty] | 8.12 | CT Erection | #VALUE! | #VALUE! | #VALUE! | 2026-08-11 | 2026-08-11 | Akshar | 2 | 4 | #VALUE!
8 | [7 empty] | 8.13 | PCS Erection | #VALUE! | #VALUE! | #VALUE! | 2026-08-11 | 2026-08-11 | Akshar | 10 | 4 | #VALUE!
8 | [7 empty] | 8.14 | ACDB Erection | #VALUE! | #VALUE! | #VALUE! | 2026-08-14 | 2026-08-14 | Akshar | 5 | 4 | #VALUE!
8 | [7 empty] | 8.15 | ECP Panel Erection (Communication Panel) | #VALUE! | #VALUE! | #VALUE! | 2026-08-11 | 2026-08-11 | Akshar | 20 | 4 | 4
8 | [7 empty] | 8.16 | HT Panel Erection | #VALUE! | #VALUE! | #VALUE! | 2026-08-11 | 2026-08-11 | Akshar | 10
8 | [7 empty] | 8.17 | EMS Panel Erection | #VALUE! | #VALUE! | #VALUE! | 2026-08-18 | 2026-08-18 | Akshar | 10
8 | [7 empty] | 8.18 | CSS Erection | #VALUE! | #VALUE! | #VALUE! | 2026-08-18 | 2026-08-18 | Akshar | 10
8 | [7 empty] | 8.19 | NIFPS Panel Erection | #VALUE! | #VALUE! | #VALUE! | 02 Aug, 11 Aug | 2026-08-11 | Tesla / CTR | 20
8 | [7 empty] | 8.2 | NIFPS Fabrication | #VALUE! | #VALUE! | #VALUE! | 07 Aug, 15Aug | 2026-08-15 | Tesla / CTR | 0.66667 | 0 | #VALUE!
8 | [7 empty] | 8.21 | Battery Container Erection | #VALUE! | #VALUE! | #VALUE! | 23 Aug, 27 Aug, 01 Sep | 2026-09-01 | Akshar | 10 | 4 | #VALUE!
8 | [7 empty] | 8.22 | HT cable laying | #VALUE! | #VALUE! | #VALUE! | 2026-08-09 | 2026-08-09 | Akshar | 1500 | 48 | #VALUE!
8 | [7 empty] | 8.23 | HT cable termination | #VALUE! | #VALUE! | #VALUE! | 2026-08-25 | 2026-08-25 | Akshar | 8 | 6 | #VALUE!
8 | [7 empty] | 8.24 | DC Cable laying | #VALUE! | #VALUE! | #VALUE! | 2026-08-15 | 2026-08-15 | Akshar | 600 | 10 | #VALUE!
8 | [7 empty] | 8.25 | LT Cable laying | #VALUE! | #VALUE! | #VALUE! | 2026-08-09 | 2026-08-09 | Akshar | 600 | 10 | #VALUE!
8 | [7 empty] | 8.26 | DC Cable termination | #VALUE! | #VALUE! | #VALUE! | 29 Aug, 09 Sep | 2026-09-09 | Akshar | 30 | 18 | #VALUE!
8 | [7 empty] | 8.27 | LT Cable termination | #VALUE! | #VALUE! | #VALUE! | 29 Aug, 09 Sep | 2026-09-09 | Akshar | 30 | 18 | #VALUE!
8 | [7 empty] | 8.28 | Aux Cable laying | #VALUE! | #VALUE! | #VALUE! | 2026-08-19 | 2026-08-19 | Akshar | 1000 | 10 | #VALUE!
8 | [7 empty] | 8.29 | Control Cable laying | #VALUE! | #VALUE! | #VALUE! | 2026-08-19 | 2026-08-19 | Akshar | 1000 | 10 | #VALUE!
8 | [7 empty] | 8.3 | Communication Cable laying | #VALUE! | #VALUE! | #VALUE! | 2026-08-19 | 2026-08-19 | Akshar | 500 | 10 | #VALUE!
8 | [7 empty] | 8.31 | Aux Cable termination | #VALUE! | #VALUE! | #VALUE! | 29 Aug, 09 Sep | 2026-09-09 | Akshar | 30 | 6 | #VALUE!
8 | [7 empty] | 8.32 | Control Cable termination | #VALUE! | #VALUE! | #VALUE! | 29 Aug, 09 Sep | 2026-09-09 | Akshar & Honeywell | 30 | 4 | #VALUE!
8 | [7 empty] | 8.33 | Communication Cable termination | #VALUE! | #VALUE! | #VALUE! | 29 Aug, 09 Sep | 2026-09-09 | Akshar & Honeywell | - | - | - |  | 41 | #VALUE! | #VALUE!
8 | [7 empty] | 8.34 | CT SFRA & Tan delta Test | #VALUE! | #VALUE! | #VALUE! | 2026-08-14 | 2026-08-14 | Akshar | 2 | 8 | -
8 | [7 empty] | 8.35 | CT Routine Test | #VALUE! | #VALUE! | #VALUE! | 2026-08-18 | 2026-08-18 | Akshar |  |  | 12
8 | [7 empty] | 8.36 | CT Control scheme & Stability Test | #VALUE! | #VALUE! | #VALUE! | 08 Sep, 14 Sep | 2026-09-14 | Akshar | 2 | 4 | #VALUE! |  | 46 | #VALUE! | #VALUE!
8 | [7 empty] | 8.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | #VALUE! | #VALUE! | #VALUE! | 2026-08-25 | 2026-08-25 | Akshar | 0.5 | 4 | #VALUE!
8 | [7 empty] | 8.38 | HT Panel relay test | #VALUE! | #VALUE! | #VALUE! | 06 Sep, 12 Sep | 2026-09-12 | Akshar | 6 | 4 | #VALUE!
8 | [7 empty] | 8.39 | HT Cable VLF Test | #VALUE! | #VALUE! | #VALUE! | 2026-08-25 | 2026-08-25 | Akshar | 6 | 5 | #VALUE!
8 | [7 empty] | 8.4 | CSS routine test | #VALUE! | #VALUE! | #VALUE! | 2026-08-25 | 2026-08-25 | Akshar | 1 | 5 | #VALUE!
8 | [7 empty] | 8.41 | ACDB routine test | #VALUE! | #VALUE! | #VALUE! | 2026-08-25 | 2026-08-25 | Akshar | 3 | 5 | #VALUE!
8 | [7 empty] | 8.42 | Earthing | #VALUE! | #VALUE! | #VALUE! | 27 Aug, 03 Sep | 2026-09-03 | Akshar | 150 | 6 | #VALUE!
8 | [7 empty] | 8.43 | LA | #VALUE! | #VALUE! | #VALUE! | 29 Aug, 05 Sep | 2026-09-05 | Akshar | 5 | 6 | #VALUE!
8 | Assumptions:-
8 | 1. Ship berthing + 72 hrs - clearing of 30 containers per day for site
8 | 2. 30 containers erected on site on 4th day
8 | 3. IDT charging = 24 days from erection of last container in the block
8 | 4. Trial run start date = IDT charging + 3 days
8 | 5. Trial run end date = Trial run start date + 2 days
8 | 6. COD = Trial run end date + 2 days
Formulas:
New EDC = IF(LEN([EDC])=5,[EDC],(IF([EDC]="Completed","-",DATEVALUE(RIGHT([EDC],6)))))

## BESS 10B
BESS 10B Charging Schedule | [17 empty] | 2026-07-30 |  |  |  | Common for PSS
Container Make | Block No. | Containers at Site | MWh | IDT Charging / Commissioning Start | Trial-Run End Date | COD | Status | [7 empty] | Productivity | Manpower | Total Mandays | Remarks |  |  |  | Tools & tackles | Required At site | Available At site
[7 empty] | Sr. | Activity | Progress |  |  | EDC | New EDC | vendor
[9 empty] | S | C | B
Jinko | 1 | 12 Jul 19 Jul 21 Jul | 240 MWh (48 containers) | 2026-08-05 | 2026-08-10 | 2026-08-13 |  |  |  | Civil | [11 empty] | Machinery
[7 empty] | 1.1 | BCF Precast Erection & Welding | #VALUE! | #VALUE! | #VALUE! | Completed | - | GODARA | 1 | 2 | #VALUE! |  |  |  |  | Cable jack | 6
[7 empty] | 1.2 | CT Rail Fixing | #VALUE! | #VALUE! | #VALUE! | Completed | - | Godara/ MSC | 1 | 16 | #VALUE! |  |  |  |  | JCB | 6
[7 empty] | 1.3 | PCS Slab casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | GODARA | 1 | 39 | #VALUE! |  |  |  |  | Excavator | 1
[7 empty] | 1.4 | SGR Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | GODARA | 1 | 37 | #VALUE! |  |  |  |  | farana | 6
[7 empty] | 1.5 | MCR Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | GODARA | 1 | 34 | #VALUE! |  |  |  |  | DG with Sablizer | 8
[7 empty] | 1.6 | CSS Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | Godara/ MSC | 1 | 54 | #VALUE! |  |  |  |  | Welding Machine | 10
[7 empty] | 1.7 | BOT Precast Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Sachi | 3 | 5 | #VALUE! |  |  |  |  | HOT Gun | 20
[7 empty] | 1.8 | NIFPS Precast Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 5 | #VALUE! |  |  |  |  | Blower | 10
[7 empty] | 1.9 | PCS PEB | #VALUE! | #VALUE! | #VALUE! | Completed | - | DP Consteel | 1 | 27 | #VALUE! |  |  |  |  | Drilling Machine | 5
[7 empty] | 1.1 | SGR PEB | #VALUE! | #VALUE! | #VALUE! | Completed | - | Synergy | 1 | 25 | #VALUE! |  |  |  |  | Drilling Machine [Hammering] | 2
[7 empty] | 1.11 | MCR PEB | #VALUE! | #VALUE! | #VALUE! | Completed | - | Metastar | - | - | - |  |  |  |  | Auger Machine | 1
[10 empty] | Electrical | [11 empty] | Tractor | 2
[7 empty] | 1.12 | CT Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 2 | 4 | #VALUE! |  |  |  |  | Cable Puller | 2
[7 empty] | 1.13 | PCS Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 10 | 4 | #VALUE! |  |  |  |  | Testing Kits
[7 empty] | 1.14 | ACDB Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 5 | 4 | #VALUE! |  |  |  |  | Megar | 5
[7 empty] | 1.15 | ECP Panel Erection (Communication Panel) | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 20 | 4 | 4 |  |  |  |  | Filtration Machine | 1
[7 empty] | 1.16 | HT Panel Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 10 | [6 empty] | Online PPM Meter | 1
[7 empty] | 1.17 | EMS Panel Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 10 | [6 empty] | SFRA Test kit | 1
[7 empty] | 1.18 | CSS Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 10 | [6 empty] | Tan delta kit | 1
* Min. 40 termination teams required for DC & LT Cable termination with crimping tool (Each team required at least 01 skilled technician with 01 helper) Common for PSS Total Machinery - crimping tool: 18, welding machine: 07, cable jack: 05, Farana: 01, JCB: 07 available at site (Common for PSS) Testing To be Completed by 02 Aug. Required Testing Team (6 Skilled & 12 Unskilled) (Common for PSS) Testing kits : Oil Filteration, Online PPM Meter, SFRA & Tan Delta, DC Winding Resistance, Turn Ratio meter, routine test kit (common for 1 PSS) ERT, DC High POT, (common for 1 PSS) VLF kit (1 nos), IR Tester, Multimeter & Clamp Meter (atleast 3 per PSS) Breaker CRM & Timing, Vaccum Bottle Integrity (common for 1 PSS), CT Analyzer (2 nos), Relay Testing Kit, CT Primary Injection (3-Phase), PT Stability (3-Phase), Impedence meter (Common for 1 PSS) | [6 empty] | 1.19 | NIFPS Panel Erection | #VALUE! | #VALUE! | #VALUE! | 02 Jul, 15 Jul, 28 Jul, 31 Jul | 2026-07-31 | Ornet/ EMR | 20 | [6 empty] | Routine test kit | 1
[7 empty] | 1.2 | NIFPS Fabrication | #VALUE! | #VALUE! | #VALUE! | 07 Jul, 18 Jul, 31 Jul, 01 Aug | 2026-08-01 | Ornet/ EMR | 0.66667 | 0 | #VALUE! |  |  |  |  | CT Analyzer | 2
[7 empty] | 1.21 | Battery Container Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 10 | 4 | #VALUE! |  |  |  |  | ERT Meter | 1
[7 empty] | 1.22 | HT cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 1500 | 48 | #VALUE! |  |  |  |  | Primary injection kit | 1
[7 empty] | 1.23 | HT cable termination | #VALUE! | #VALUE! | #VALUE! | 19 Jul, 22 Jul, 01 Aug | 2026-08-01 | Akshar | 8 | 6 | #VALUE! | Torquing will be done post VLF test |  |  |  | PT test kit | 1
[7 empty] | 1.24 | DC Cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 600 | 10 | #VALUE! |  |  |  |  | 3 Phase Primary injection kit | 1
[7 empty] | 1.25 | LT Cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 600 | 10 | #VALUE! |  |  |  |  | Breaker, CRM, Timming & vacuum Bottle test kits | 1 | 1
[7 empty] | 1.26 | DC Cable termination | #VALUE! | #VALUE! | #VALUE! | 23 Jul, 30 Jul, 01 Aug | 2026-08-01 | Akshar | 30 | 18 | #VALUE! | Lugging completed, torquing WIP (1280 completed) |  |  |  | DC high Pot kit | 1
[7 empty] | 1.27 | LT Cable termination | #VALUE! | #VALUE! | #VALUE! | 23 Jul, 30 Jul, 01 Aug | 2026-08-01 | Akshar | 30 | 18 | #VALUE! | Lugigng -1824, Torquing - 960 completed |  |  |  | VLF Kit | 1
[7 empty] | 1.28 | Aux Cable laying | #VALUE! | #VALUE! | #VALUE! | 13-Jul, 26 Jul, 30 Jul | 2026-07-30 | Akshar | 1000 | 10 | #VALUE! |  |  |  |  | Relay Secondary injection kit | 2
[7 empty] | 1.29 | Control Cable laying | #VALUE! | #VALUE! | #VALUE! | 13-Jul, 26 Jul, 30-Jul | 2026-07-30 | Akshar | 1000 | 10 | #VALUE! |  |  |  |  | Multimeter, IR Tester & Clamp meter | 3 | 2
[7 empty] | 1.3 | Communication Cable laying | #VALUE! | #VALUE! | #VALUE! | 13-Jul, 26 Jul, 30-Jul | 2026-07-30 | Akshar | 500 | 10 | #VALUE! |  |  |  |  | Impedance Meter | 2
[7 empty] | 1.31 | Aux Cable termination | #VALUE! | #VALUE! | #VALUE! | 23-Jul, 28 Jul, 1- Aug | 2026-08-01 | Akshar | 30 | 6 | #VALUE!
[7 empty] | 1.32 | Control Cable termination | #VALUE! | #VALUE! | #VALUE! | 23-Jul, 29 Jul, 01-Aug | 2026-08-01 | Akshar & Adaptive | 30 | 4 | #VALUE! |  |  |  |  | Tools
[7 empty] | 1.33 | Communication Cable termination | #VALUE! | #VALUE! | #VALUE! | 23-Jul, 29 Jul, 01-Aug | 2026-08-01 | Akshar & Adaptive | - | - | - |  | 2 | #VALUE! | #VALUE! | Crimping tool | 60
[7 empty] | 1.34 | CT SFRA & Tan delta Test | #VALUE! | #VALUE! | #VALUE! | 08 Jul, 15 Jul, 22 Jul, 27 Jul, 30 Jul | 2026-07-30 | Akshar | 2 | 8 | 12 |  |  |  |  | Torque Wrench | 10
[7 empty] | 1.35 | CT Routine Test | #VALUE! | #VALUE! | #VALUE! | 12 Jul, 17 Jul, 28 Jul, 30 Jul | 2026-07-30 | Akshar | [7 empty] | Tool Set | 10
[7 empty] | 1.36 | CT Control scheme & Stability Test | #VALUE! | #VALUE! | #VALUE! | 02 Aug, 04 Aug | 2026-08-04 | Akshar | 2 | 4 | #VALUE! |  | 5 | #VALUE! | #VALUE! | Cable Cutter | 10
[7 empty] | 1.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 0.5 | 4 | #VALUE!
[7 empty] | 1.38 | HT Panel relay test | #VALUE! | #VALUE! | #VALUE! | 02 Aug, 03 Aug | 2026-08-03 | Akshar | 6 | 4 | #VALUE!
[7 empty] | 1.39 | HT Cable VLF Test | #VALUE! | #VALUE! | #VALUE! | 19-Jul, 28 Jul, 02 Aug | 2026-08-02 | Akshar | 6 | 5 | #VALUE!
[7 empty] | 1.4 | CSS routine test | #VALUE! | #VALUE! | #VALUE! | 19-Jul, 28 Jul, 31 Jul | 2026-07-31 | Akshar | 1 | 5 | #VALUE!
[7 empty] | 1.41 | ACDB routine test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 3 | 5 | #VALUE!
[7 empty] | 1.42 | Earthing | #VALUE! | #VALUE! | #VALUE! | 21-Jul, 30 Jul, 02 Aug | 2026-08-02 | Akshar | 150 | 6 | #VALUE!
[7 empty] | 1.43 | LA | #VALUE! | #VALUE! | #VALUE! | 23- Jul, 28 Jul, 30 Jul. 31 Jul | 2026-07-31 | Akshar | 5 | 6 | #VALUE!
Jinko | 2 | 18 Jul 25 Jul 27 Jul | 240 MWh (48 containers) | 2026-08-11 | 2026-08-16 | 2026-08-19 |  |  |  | Civil
[7 empty] | 2.1 | BCF Precast Erection & Welding | #VALUE! | #VALUE! | #VALUE! | Completed | - | GODARA | 1 | 2 | #VALUE!
[7 empty] | 2.2 | CT Rail Fixing | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 16 | #VALUE!
[7 empty] | 2.3 | PCS Slab casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | Godara/ MSC | 1 | 39 | #VALUE!
[7 empty] | 2.4 | SGR Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 37 | #VALUE!
[7 empty] | 2.5 | MCR Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 34 | #VALUE!
[7 empty] | 2.6 | CSS Slab Casting | #VALUE! | #VALUE! | #VALUE! | 2026-07-30 | 2026-07-30 | MSC | 1 | 54 | #VALUE! | [7 empty] | Backfilling Done
[7 empty] | 2.7 | BOT Precast Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Sachi | 3 | 5 | #VALUE!
[7 empty] | 2.8 | NIFPS Precast Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 5 | #VALUE!
[7 empty] | 2.9 | PCS PEB | #VALUE! | #VALUE! | #VALUE! | Completed | - | DP Consteel | 1 | 27 | #VALUE!
[7 empty] | 2.1 | SGR PEB | #VALUE! | #VALUE! | #VALUE! | 05 Jul, 12 Jul, 25 Jul, 30 Jul | 2026-07-30 | Synergy | 1 | 25 | #VALUE!
[7 empty] | 2.11 | MCR PEB | #VALUE! | #VALUE! | #VALUE! | Completed | - | Metastar | - | - | -
Electrical
[7 empty] | 2.12 | CT Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 2 | 4 | #VALUE!
[7 empty] | 2.13 | PCS Erection | #VALUE! | #VALUE! | #VALUE! | 11 Jul, 17 Jul, 25 Jul | 2026-07-25 | Akshar | 10 | 4 | #VALUE! | Placed on slab, anchoring WIP
[7 empty] | 2.14 | ACDB Erection | #VALUE! | #VALUE! | #VALUE! | 14-Jul, 25 Jul | 2026-07-25 | Akshar | 5 | 4 | #VALUE! | 04 ACDB placed on slab, anchoring WIP |  |  |  | 2026-07-17
[7 empty] | 2.15 | ECP Panel Erection (Communication Panel) | #VALUE! | #VALUE! | #VALUE! | 11-Jul, 25 Jul | 2026-07-25 | Akshar | 20 | 4 | 4 |  |  |  |  | 2026-07-17
[7 empty] | 2.16 | HT Panel Erection | #VALUE! | #VALUE! | #VALUE! | 11-Jul, 25 Jul | 2026-07-25 | Akshar | 10 |  |  | Placed on slab, anchoring WIP
[7 empty] | 2.17 | EMS Panel Erection | #VALUE! | #VALUE! | #VALUE! | 18-Jul, 24 Jul, 02 Aug | 2026-08-02 | Akshar | 10
[7 empty] | 2.18 | CSS Erection | #VALUE! | #VALUE! | #VALUE! | 19-Jul, 30 Jul | 2026-07-30 | Akshar | 10
[7 empty] | 2.19 | NIFPS Panel Erection | #VALUE! | #VALUE! | #VALUE! | 06 Jul, 17 Jul, 31 Jul | 2026-07-31 | Ornet/ EMR | 20
[7 empty] | 2.2 | NIFPS Fabrication | #VALUE! | #VALUE! | #VALUE! | 11 Jul, 22 Jul, 03 Aug | 2026-08-03 | Ornet/ EMR | 0.66667 | 0 | #VALUE!
[7 empty] | 2.21 | Battery Container Erection | #VALUE! | #VALUE! | #VALUE! | 23-Jul, 30 Jul | 2026-07-30 | Akshar | 10 | 4 | #VALUE!
[7 empty] | 2.22 | HT cable laying | #VALUE! | #VALUE! | #VALUE! | 09 Jul, 22 Jul, 30 Jul | 2026-07-30 | Akshar | 1500 | 48 | #VALUE!
[7 empty] | 2.23 | HT cable termination | #VALUE! | #VALUE! | #VALUE! | 25-Jul, 31 Jul | 2026-07-31 | Akshar | 8 | 6 | #VALUE!
[7 empty] | 2.24 | DC Cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 600 | 10 | #VALUE!
[7 empty] | 2.25 | LT Cable laying | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 600 | 10 | #VALUE!
[7 empty] | 2.26 | DC Cable termination | #VALUE! | #VALUE! | #VALUE! | 29 Jul, 05 Aug | 2026-08-05 | Akshar | 30 | 18 | #VALUE!
[7 empty] | 2.27 | LT Cable termination | #VALUE! | #VALUE! | #VALUE! | 29 Jul, 05 Aug | 2026-08-05 | Akshar | 30 | 18 | #VALUE!
[7 empty] | 2.28 | Aux Cable laying | #VALUE! | #VALUE! | #VALUE! | 19-Jul, 29 Jul | 2026-07-29 | Akshar | 1000 | 10 | #VALUE!
[7 empty] | 2.29 | Control Cable laying | #VALUE! | #VALUE! | #VALUE! | 19-Jul, 31 Jul | 2026-07-31 | Akshar | 1000 | 10 | #VALUE!
[7 empty] | 2.3 | Communication Cable laying | #VALUE! | #VALUE! | #VALUE! | 19-Jul, 31 Jul | 2026-07-31 | Akshar | 500 | 10 | #VALUE!
[7 empty] | 2.31 | Aux Cable termination | #VALUE! | #VALUE! | #VALUE! | 29-Jul, 01 Aug | 2026-08-01 | Akshar | 30 | 6 | #VALUE!
[7 empty] | 2.32 | Control Cable termination | #VALUE! | #VALUE! | #VALUE! | 29-Jul, 03 Aug | 2026-08-03 | Akshar & Adaptive | 30 | 4 | #VALUE!
[7 empty] | 2.33 | Communication Cable termination | #VALUE! | #VALUE! | #VALUE! | 29-Jul, 03 Aug | 2026-08-03 | Akshar & Adaptive | - | - | - |  | 4 | #VALUE! | #VALUE!
[7 empty] | 2.34 | CT SFRA & Tan delta Test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar | 2 | 8 | 12
[7 empty] | 2.35 | CT Routine Test | #VALUE! | #VALUE! | #VALUE! | Completed | - | Akshar
[7 empty] | 2.36 | CT Control scheme & Stability Test | #VALUE! | #VALUE! | #VALUE! | 2026-08-08 | 2026-08-08 | Akshar | 2 | 4 | #VALUE! |  | 9 | #VALUE! | #VALUE!
[7 empty] | 2.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | #VALUE! | #VALUE! | #VALUE! | 25 Jul, 01 Aug | 2026-08-01 | Akshar | 0.5 | 4 | #VALUE!
[7 empty] | 2.38 | HT Panel relay test | #VALUE! | #VALUE! | #VALUE! | 2026-08-08 | 2026-08-08 | Akshar | 6 | 4 | #VALUE!
[7 empty] | 2.39 | HT Cable VLF Test | #VALUE! | #VALUE! | #VALUE! | 25-Jul, 01 Aug, 04 Aug | 2026-08-04 | Akshar | 6 | 5 | #VALUE!
[7 empty] | 2.4 | CSS routine test | #VALUE! | #VALUE! | #VALUE! | 25-Jul, 02 Aug | 2026-08-02 | Akshar | 1 | 5 | #VALUE!
[7 empty] | 2.41 | ACDB routine test | #VALUE! | #VALUE! | #VALUE! | 25-Jul, 28 Jul | 2026-07-28 | Akshar | 3 | 5 | #VALUE!
[7 empty] | 2.42 | Earthing | #VALUE! | #VALUE! | #VALUE! | 27-Jul, 05 Aug | 2026-08-05 | Akshar | 150 | 6 | #VALUE!
[7 empty] | 2.43 | LA | #VALUE! | #VALUE! | #VALUE! | 29-Jul, 31 Jul | 2026-07-31 | Akshar | 5 | 6 | #VALUE!
Jinko | 5 | 15 Jul 28 Jul 03 Aug | 240 MWh (48 containers) | 08 Aug 23 Aug | 13 Aug 28 Aug | 16 Aug 31 Aug |  |  |  | Civil
[7 empty] | 5.1 | BCF Precast Erection & Welding | #VALUE! | #VALUE! | #VALUE! | Completed | - | GODARA | 1 | 2 | #VALUE!
[7 empty] | 5.2 | CT Rail Fixing | #VALUE! | #VALUE! | #VALUE! | 02 Jul, 06 Jul, 22 Jul, 29 Jul | 2026-07-29 | MSC | 1 | 16 | #VALUE! | [7 empty] | erection pendig /8 aug
[7 empty] | 5.3 | PCS Slab casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 39 | #VALUE! |  |  |  |  | 1 casted
[7 empty] | 5.4 | SGR Slab Casting | #VALUE! | #VALUE! | #VALUE! | 18 Jul, 28 Jul | 2026-07-28 | MSC | 1 | 37 | #VALUE! | [7 empty] | F Done /4Aug
[7 empty] | 5.5 | MCR Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 34 | #VALUE!
[7 empty] | 5.6 | CSS Slab Casting | #VALUE! | #VALUE! | #VALUE! | 10 Jul, 20 Jul, 26 Jul, 02 Aug | 2026-08-02 | MSC | 1 | 54 | #VALUE! | [7 empty] | F Done/08 aug
[7 empty] | 5.7 | BOT Precast Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Sachi | 3 | 5 | #VALUE!
[7 empty] | 5.8 | NIFPS Precast Erection | #VALUE! | #VALUE! | #VALUE! | 05 Jul, 09 Jul, 15 Jul, 28 Jul | 2026-07-28 | MSC | 1 | 5 | #VALUE! | [7 empty] | EX Pending/08 aug
[7 empty] | 5.9 | PCS PEB | #VALUE! | #VALUE! | #VALUE! | 20 Jul, 25 Jul, 08 Aug | 2026-08-08 | DP Consteel | 1 | 27 | #VALUE!
[7 empty] | 5.1 | SGR PEB | #VALUE! | #VALUE! | #VALUE! | 15 Jul, 25 Jul, 31 Jul | 2026-07-31 | Synergy | 1 | 25 | #VALUE!
[7 empty] | 5.11 | MCR PEB | #VALUE! | #VALUE! | #VALUE! | 11 Jul, 18 Jul, 31 Jul | 2026-07-31 | Metastar | - | - | -
Electrical
[7 empty] | 5.12 | CT Erection | #VALUE! | #VALUE! | #VALUE! | 08 Jul, 19 Jul, 26 Jul, 08 Aug | 2026-08-08 | Akshar | 2 | 4 | #VALUE!
[7 empty] | 5.13 | PCS Erection | #VALUE! | #VALUE! | #VALUE! | 08 Jul, 24 Jul, 02 Aug, 08 Aug | 2026-08-08 | Akshar | 10 | 4 | #VALUE!
[7 empty] | 5.14 | ACDB Erection | #VALUE! | #VALUE! | #VALUE! | 11 Jul, 24 Jul, 02 Aug, 08 Aug | 2026-08-08 | Akshar | 5 | 4 | #VALUE! |  |  |  |  | 2026-07-24
[7 empty] | 5.15 | ECP Panel Erection (Communication Panel) | #VALUE! | #VALUE! | #VALUE! | 08 Jul, 24 Jul, 02 Aug, 08 Aug | 2026-08-08 | Akshar | 20 | 4 | 4 |  |  |  |  | 2026-07-24
[7 empty] | 5.16 | HT Panel Erection | #VALUE! | #VALUE! | #VALUE! | 08 Jul, 24 Jul, 01 Aug, 04 Aug | 2026-08-04 | Akshar | 10 | [6 empty] | 2026-07-24
[7 empty] | 5.17 | EMS Panel Erection | #VALUE! | #VALUE! | #VALUE! | 15 Jul, 24 Jul, 01 Aug, 04 Aug | 2026-08-04 | Akshar | 10 | [6 empty] | 2026-07-24
[7 empty] | 5.18 | CSS Erection | #VALUE! | #VALUE! | #VALUE! | 15 Jul, 25 Jul, 02 Aug, 08 Aug | 2026-08-08 | Akshar | 10 | [6 empty] | 2026-07-25
[7 empty] | 5.19 | NIFPS Panel Erection | #VALUE! | #VALUE! | #VALUE! | 10 Jul, 19 Jul, 04 Aug | 2026-08-04 | Tesla/ CTR | 20
[7 empty] | 5.2 | NIFPS Fabrication | #VALUE! | #VALUE! | #VALUE! | 15 Jul, 26 Jul, 08 Aug | 2026-08-08 | Tesla/ CTR | 0.66667 | 0 | #VALUE!
[7 empty] | 5.21 | Battery Container Erection | #VALUE! | #VALUE! | #VALUE! | 20-Jul, 02 Aug, 08 Aug | 2026-08-08 | Akshar | 10 | 4 | #VALUE!
[7 empty] | 5.22 | HT cable laying | #VALUE! | #VALUE! | #VALUE! | 06 Jul, 25 Jul, 01 Aug, 08 Aug | 2026-08-08 | Akshar | 1500 | 48 | #VALUE!
[7 empty] | 5.23 | HT cable termination | #VALUE! | #VALUE! | #VALUE! | 22 Jul, 27 Jul, 03 Aug, 15 Aug | 2026-08-15 | Akshar | 8 | 6 | #VALUE!
[7 empty] | 5.24 | DC Cable laying | #VALUE! | #VALUE! | #VALUE! | 12 Jul, 28 Jul, 02 Aug, 10 Aug | 2026-08-10 | Akshar | 600 | 10 | #VALUE!
[7 empty] | 5.25 | LT Cable laying | #VALUE! | #VALUE! | #VALUE! | 06 Jul, 28 Jul, 02 Aug, 10 Aug | 2026-08-10 | Akshar | 600 | 10 | #VALUE!
[7 empty] | 5.26 | DC Cable termination | #VALUE! | #VALUE! | #VALUE! | 26 Jul, 02 Aug, 04 Aug, 16 Aug | 2026-08-16 | Akshar | 30 | 18 | #VALUE!
[7 empty] | 5.27 | LT Cable termination | #VALUE! | #VALUE! | #VALUE! | 26 Jul, 02 Aug, 05 Aug | 2026-08-05 | Akshar | 30 | 18 | #VALUE!
[7 empty] | 5.28 | Aux Cable laying | #VALUE! | #VALUE! | #VALUE! | 16-Jul, 08 Aug, 12 Aug | 2026-08-12 | Akshar | 1000 | 10 | #VALUE!
[7 empty] | 5.29 | Control Cable laying | #VALUE! | #VALUE! | #VALUE! | 16-Jul, 08 Aug, 12 Aug | 2026-08-12 | Akshar | 1000 | 10 | #VALUE!
[7 empty] | 5.3 | Communication Cable laying | #VALUE! | #VALUE! | #VALUE! | 16-Jul, 08 Aug, 12 Aug | 2026-08-12 | Akshar | 500 | 10 | #VALUE!
[7 empty] | 5.31 | Aux Cable termination | #VALUE! | #VALUE! | #VALUE! | 26-Jul, 05 Aug, 17 Aug | 2026-08-17 | Akshar | 30 | 6 | #VALUE!
[7 empty] | 5.32 | Control Cable termination | #VALUE! | #VALUE! | #VALUE! | 26-Jul, 05 Aug, 17 Aug | 2026-08-17 | Akshar & Adaptive | 30 | 4 | #VALUE!
[7 empty] | 5.33 | Communication Cable termination | #VALUE! | #VALUE! | #VALUE! | 26-Jul, 05 Aug, 17 Aug | 2026-08-17 | Akshar & Adaptive | - | - | - |  | 18 | #VALUE! | #VALUE!
[7 empty] | 5.34 | CT SFRA & Tan delta Test | #VALUE! | #VALUE! | #VALUE! | 11-Jul, 04 Aug, 12 Aug | 2026-08-12 | Akshar | 2 | 8 | 12
[7 empty] | 5.35 | CT Routine Test | #VALUE! | #VALUE! | #VALUE! | 15-Jul, 05 Aug, 16 Aug | 2026-08-16 | Akshar
[7 empty] | 5.36 | CT Control scheme & Stability Test | #VALUE! | #VALUE! | #VALUE! | 05-Aug, 07 Aug, 21 Aug | 2026-08-21 | Akshar | 2 | 4 | #VALUE! |  | 22 | #VALUE! | #VALUE!
[7 empty] | 5.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | #VALUE! | #VALUE! | #VALUE! | 22-Jul, 03 Aug, 12 Aug | 2026-08-12 | Akshar | 0.5 | 4 | #VALUE!
[7 empty] | 5.38 | HT Panel relay test | #VALUE! | #VALUE! | #VALUE! | 05-Aug, 06 Aug, 19 Aug | 2026-08-19 | Akshar | 6 | 4 | #VALUE!
[7 empty] | 5.39 | HT Cable VLF Test | #VALUE! | #VALUE! | #VALUE! | 22-Jul, 04 Aug, 17 Aug | 2026-08-17 | Akshar | 6 | 5 | #VALUE!
[7 empty] | 5.4 | CSS routine test | #VALUE! | #VALUE! | #VALUE! | 22-Jul, 05 Aug, 15 Aug | 2026-08-15 | Akshar | 1 | 5 | #VALUE!
[7 empty] | 5.41 | ACDB routine test | #VALUE! | #VALUE! | #VALUE! | 22-Jul, 04 Aug, 15 Aug | 2026-08-15 | Akshar | 3 | 5 | #VALUE!
[7 empty] | 5.42 | Earthing | #VALUE! | #VALUE! | #VALUE! | 24-Jul, 04 Aug, 16 Aug | 2026-08-16 | Akshar | 150 | 6 | #VALUE!
[7 empty] | 5.43 | LA | #VALUE! | #VALUE! | #VALUE! | 26-Jul, 05 Aug, 17 Aug | 2026-08-17 | Akshar | 5 | 6 | #VALUE!
Jinko | 3 | 06 Aug 20 Aug 31 Aug | 240 MWh (48 containers) | 30 Aug 21 Sep | 04 Sep 26 Sep | 07 Sep 29 Sep |  |  |  | Civil
[7 empty] | 3.1 | BCF Precast Erection & Welding | #VALUE! | #VALUE! | #VALUE! | Completed | - | GODARA | 1 | 2 | #VALUE!
[7 empty] | 3.2 | CT Rail Fixing | #VALUE! | #VALUE! | #VALUE! | 10 Jul, 20 Jul, 26 Jul, 06 Aug | 2026-08-06 | MSC | 1 | 16 | #VALUE!
[7 empty] | 3.3 | PCS Slab casting | #VALUE! | #VALUE! | #VALUE! | 09 Jul, 15 Jul, 24 Jul, 28 Jul | 2026-07-28 | MSC | 1 | 39 | #VALUE! | [7 empty] | F done / 8 Aug
[7 empty] | 3.4 | SGR Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 37 | #VALUE!
[7 empty] | 3.5 | MCR Slab Casting | #VALUE! | #VALUE! | #VALUE! | Completed | - | MSC | 1 | 34 | #VALUE!
[7 empty] | 3.6 | CSS Slab Casting | #VALUE! | #VALUE! | #VALUE! | 16 Jul, 26 Jul, 06 Aug | 2026-08-06 | MSC | 1 | 54 | #VALUE! | [7 empty] | PCC done / 17 aug
[7 empty] | 3.7 | BOT Precast Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Sachi | 3 | 5 | #VALUE!
[7 empty] | 3.8 | NIFPS Precast Erection | #VALUE! | #VALUE! | #VALUE! | 10 Jul, 22 Jul, 06 Aug | 2026-08-06 | MSC | 1 | 5 | #VALUE! | [7 empty] | 2 ex pending
[7 empty] | 3.9 | PCS PEB | #VALUE! | #VALUE! | #VALUE! | 28 Jul, 15 Aug | 2026-08-15 | DP Consteel | 1 | 27 | #VALUE!
[7 empty] | 3.1 | SGR PEB | #VALUE! | #VALUE! | #VALUE! | 04 Aug, 15 Aug | 2026-08-15 | Synergy | 1 | 25 | #VALUE!
[7 empty] | 3.11 | MCR PEB | #VALUE! | #VALUE! | #VALUE! | 05 Aug, 15 Aug | 2026-08-15 | Metastar | - | - | -
Electrical
[7 empty] | 3.12 | CT Erection | #VALUE! | #VALUE! | #VALUE! | 30-Jul, 05 Aug, 16 Aug | 2026-08-16 | Akshar | 2 | 4 | #VALUE!
[7 empty] | 3.13 | PCS Erection | #VALUE! | #VALUE! | #VALUE! | 30-Jul, 06 Aug, 17 Aug | 2026-08-17 | Akshar | 10 | 4 | #VALUE!
[7 empty] | 3.14 | ACDB Erection | #VALUE! | #VALUE! | #VALUE! | 02-Aug, 06 Aug, 17 Aug | 2026-08-17 | Akshar | 5 | 4 | #VALUE!
[7 empty] | 3.15 | ECP Panel Erection (Communication Panel) | #VALUE! | #VALUE! | #VALUE! | 30-Jul, 07 Aug, 17 Aug | 2026-08-17 | Akshar | 20 | 4 | 4
[7 empty] | 3.16 | HT Panel Erection | #VALUE! | #VALUE! | #VALUE! | 30-Jul, 05 Aug, 16Aug |  | Akshar | 10
[7 empty] | 3.17 | EMS Panel Erection | #VALUE! | #VALUE! | #VALUE! | 06 Aug, 17Aug | 2026-08-17 | Akshar | 10
[7 empty] | 3.18 | CSS Erection | #VALUE! | #VALUE! | #VALUE! | 06 Aug, 17Aug | 2026-08-17 | Akshar | 10
[7 empty] | 3.19 | NIFPS Panel Erection | #VALUE! | #VALUE! | #VALUE! | 14 Jul, 25 Jul, 10 Aug | 2026-08-10 | Tesla/ CTR | 20
[7 empty] | 3.2 | NIFPS Fabrication | #VALUE! | #VALUE! | #VALUE! | 19 Jul, 30 Jul, 16 Aug | 2026-08-16 | Tesla/ CTR | 0.66667 | 0 | #VALUE!
[7 empty] | 3.21 | Battery Container Erection | #VALUE! | #VALUE! | #VALUE! | 11-Aug, 23 Aug, 04 Sep | 2026-09-04 | Akshar | 10 | 4 | #VALUE!
[7 empty] | 3.22 | HT cable laying | #VALUE! | #VALUE! | #VALUE! | 28-Jul, 08 Aug | 2026-08-08 | Akshar | 1500 | 48 | #VALUE!
[7 empty] | 3.23 | HT cable termination | #VALUE! | #VALUE! | #VALUE! | 13 Aug, 23 Aug | 2026-08-23 | Akshar | 8 | 6 | #VALUE!
[7 empty] | 3.24 | DC Cable laying | #VALUE! | #VALUE! | #VALUE! | 03-Aug, 12 Aug | 2026-08-12 | Akshar | 600 | 10 | #VALUE!
[7 empty] | 3.25 | LT Cable laying | #VALUE! | #VALUE! | #VALUE! | 28-Jul, 13 Aug | 2026-08-13 | Akshar | 600 | 10 | #VALUE!
[7 empty] | 3.26 | DC Cable termination | #VALUE! | #VALUE! | #VALUE! | 17-Aug, 24 Aug, 12 Sep | 2026-09-12 | Akshar | 30 | 18 | #VALUE!
[7 empty] | 3.27 | LT Cable termination | #VALUE! | #VALUE! | #VALUE! | 17 Aug, 10 Sep | 2026-09-10 | Akshar | 30 | 18 | #VALUE!
[7 empty] | 3.28 | Aux Cable laying | #VALUE! | #VALUE! | #VALUE! | 07-Aug, 20 Aug | 2026-08-20 | Akshar | 1000 | 10 | #VALUE!
[7 empty] | 3.29 | Control Cable laying | #VALUE! | #VALUE! | #VALUE! | 07-Aug, 20 Aug | 2026-08-20 | Akshar | 1000 | 10 | #VALUE!
[7 empty] | 3.3 | Communication Cable laying | #VALUE! | #VALUE! | #VALUE! | 07-Aug, 20 Aug | 2026-08-20 | Akshar | 500 | 10 | #VALUE!
[7 empty] | 3.31 | Aux Cable termination | #VALUE! | #VALUE! | #VALUE! | 17-Aug, 24 Aug, 12 Sep | 2026-09-12 | Akshar | 30 | 6 | #VALUE!
[7 empty] | 3.32 | Control Cable termination | #VALUE! | #VALUE! | #VALUE! | 17-Aug, 24 Aug, 12 Sep | 2026-09-12 | Akshar & Adaptive | 30 | 4 | #VALUE!
[7 empty] | 3.33 | Communication Cable termination | #VALUE! | #VALUE! | #VALUE! | 17-Aug, 24 Aug, 12 Sep | 2026-09-12 | Akshar & Adaptive | - | - | - |  | 44 | #VALUE! | #VALUE!
[7 empty] | 3.34 | CT SFRA & Tan delta Test | #VALUE! | #VALUE! | #VALUE! | 02-Aug, 10 Aug, 26 Aug | 2026-08-26 | Akshar | 2 | 8 | 12
[7 empty] | 3.35 | CT Routine Test | #VALUE! | #VALUE! | #VALUE! | 06-Aug, 12 Aug, 01 Sep | 2026-09-01 | Akshar
[7 empty] | 3.36 | CT Control scheme & Stability Test | #VALUE! | #VALUE! | #VALUE! | 27 Aug, 18 Sep | 2026-09-18 | Akshar | 2 | 4 | #VALUE! |  | 50 | #VALUE! | #VALUE!
[7 empty] | 3.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | #VALUE! | #VALUE! | #VALUE! | 13 Aug, 26 Aug | 2026-08-26 | Akshar | 0.5 | 4 | #VALUE!
[7 empty] | 3.38 | HT Panel relay test | #VALUE! | #VALUE! | #VALUE! | 27 Aug, 16 Sep | 2026-09-16 | Akshar | 6 | 4 | #VALUE!
[7 empty] | 3.39 | HT Cable VLF Test | #VALUE! | #VALUE! | #VALUE! | 13-Aug, 15 Aug, 2 5Aug |  | Akshar | 6 | 5 | #VALUE!
[7 empty] | 3.4 | CSS routine test | #VALUE! | #VALUE! | #VALUE! | 13 Aug, 27 Aug | 2026-08-27 | Akshar | 1 | 5 | #VALUE!
[7 empty] | 3.41 | ACDB routine test | #VALUE! | #VALUE! | #VALUE! | 13 Aug, 27 Aug | 2026-08-27 | Akshar | 3 | 5 | #VALUE!
[7 empty] | 3.42 | Earthing | #VALUE! | #VALUE! | #VALUE! | 15-Aug, 26 Aug, 06 Sep | 2026-09-06 | Akshar | 150 | 6 | #VALUE!
[7 empty] | 3.43 | LA | #VALUE! | #VALUE! | #VALUE! | 17-Aug, 25 Aug, 07 Sep | 2026-09-07 | Akshar | 5 | 6 | #VALUE!
Jinko | 4 | 11 Aug 30 Aug 09 Sep | 240 MWh (48 containers) | 04 Sep 30 Sep | 09 Sep 05 Oct | 12 Sep 08 Oct |  |  |  | Civil
[7 empty] | 4.1 | BCF Precast Erection & Welding | #VALUE! | #VALUE! | #VALUE! | Completed | - | GODARA | 1 | 2 | #VALUE!
[7 empty] | 4.2 | CT Rail Fixing | #VALUE! | #VALUE! | #VALUE! | 22 Jul, 28 Jul, 06 Aug | 2026-08-06 | MSC | 1 | 16 | #VALUE! | [7 empty] | final lift pending
[7 empty] | 4.3 | PCS Slab casting | #VALUE! | #VALUE! | #VALUE! | 17 Jul, 26 Jul, 08 Aug | 2026-08-08 | MSC | 1 | 39 | #VALUE! | [7 empty] | F done/ 25 Aug
[7 empty] | 4.4 | SGR Slab Casting | #VALUE! | #VALUE! | #VALUE! | 09 Jul, 28 Jul, 08 Aug | 2026-08-08 | MSC | 1 | 37 | #VALUE! | [7 empty] | F done/ 24 Aug
[7 empty] | 4.5 | MCR Slab Casting | #VALUE! | #VALUE! | #VALUE! | 13 Jul, 28 Jul, 08 Aug | 2026-08-08 | MSC | 1 | 34 | #VALUE! | [7 empty] | F done
[7 empty] | 4.6 | CSS Slab Casting | #VALUE! | #VALUE! | #VALUE! | 28 Jul, 03 Aug | 2026-08-03 | MSC | 1 | 54 | #VALUE! | [7 empty] | pcc Done
[7 empty] | 4.7 | BOT Precast Erection | #VALUE! | #VALUE! | #VALUE! | Completed | - | Sachi | 3 | 5 | #VALUE!
[7 empty] | 4.8 | NIFPS Precast Erection | #VALUE! | #VALUE! | #VALUE! | 22 Jul, 28 Jul | 2026-07-28 | MSC | 1 | 5 | #VALUE! | [7 empty] | Ex Pending
[7 empty] | 4.9 | PCS PEB | #VALUE! | #VALUE! | #VALUE! | 2026-08-10 | 2026-08-10 | DP Consteel | 1 | 27 | #VALUE!
[7 empty] | 4.1 | SGR PEB | #VALUE! | #VALUE! | #VALUE! | 2026-08-04 | 2026-08-04 | Synergy | 1 | 25 | #VALUE!
[7 empty] | 4.11 | MCR PEB | #VALUE! | #VALUE! | #VALUE! | 2026-08-05 | 2026-08-05 | Metastar | - | - | -
Electrical
[7 empty] | 4.12 | CT Erection | #VALUE! | #VALUE! | #VALUE! | 04-Aug, 10 Aug, 21 Aug | 2026-08-21 | Akshar | 2 | 4 | #VALUE!
[7 empty] | 4.13 | PCS Erection | #VALUE! | #VALUE! | #VALUE! | 04-Aug, 08 Aug, 25 Aug | 2026-08-25 | Akshar | 10 | 4 | #VALUE!
[7 empty] | 4.14 | ACDB Erection | #VALUE! | #VALUE! | #VALUE! | 07-Aug, 08 Aug, 25 Aug | 2026-08-25 | Akshar | 5 | 4 | #VALUE!
[7 empty] | 4.15 | ECP Panel Erection (Communication Panel) | #VALUE! | #VALUE! | #VALUE! | 04-Aug, 09 Aug, 24 Aug | 2026-08-24 | Akshar | 20 | 4 | 4
[7 empty] | 4.16 | HT Panel Erection | #VALUE! | #VALUE! | #VALUE! | 04-Aug, 07 Aug, 24 Aug | 2026-08-24 | Akshar | 10
[7 empty] | 4.17 | EMS Panel Erection | #VALUE! | #VALUE! | #VALUE! | 11 Aug, 22 Aug | 2026-08-22 | Akshar | 10
[7 empty] | 4.18 | CSS Erection | #VALUE! | #VALUE! | #VALUE! | 11 Aug, 23 Aug | 2026-08-23 | Akshar | 10
[7 empty] | 4.19 | NIFPS Panel Erection | #VALUE! | #VALUE! | #VALUE! | 25 Jul, 15 Aug | 2026-08-15 | Ornet/ EMR | 20
[7 empty] | 4.2 | NIFPS Fabrication | #VALUE! | #VALUE! | #VALUE! | 30 Jul, 23 Aug | 2026-08-23 | Ornet/ EMR | 0.66667 | 0 | #VALUE!
[7 empty] | 4.21 | Battery Container Erection | #VALUE! | #VALUE! | #VALUE! | 16-Aug, 02 Sep, 13 Sep | 2026-09-13 | Akshar | 10 | 4 | #VALUE!
[7 empty] | 4.22 | HT cable laying | #VALUE! | #VALUE! | #VALUE! | 02-Aug, 15 Aug | 2026-08-15 | Akshar | 1500 | 48 | #VALUE!
[7 empty] | 4.23 | HT cable termination | #VALUE! | #VALUE! | #VALUE! | 18 Aug, 28 Aug | 2026-08-28 | Akshar | 8 | 6 | #VALUE!
[7 empty] | 4.24 | DC Cable laying | #VALUE! | #VALUE! | #VALUE! | 08-Aug, 20 Aug | 2026-08-20 | Akshar | 600 | 10 | #VALUE!
[7 empty] | 4.25 | LT Cable laying | #VALUE! | #VALUE! | #VALUE! | 02-Aug, 20 Aug | 2026-08-20 | Akshar | 600 | 10 | #VALUE!
[7 empty] | 4.26 | DC Cable termination | #VALUE! | #VALUE! | #VALUE! | 22-Aug, 02 Sep, 20 Sep | 2026-09-20 | Akshar | 30 | 18 | #VALUE!
[7 empty] | 4.27 | LT Cable termination | #VALUE! | #VALUE! | #VALUE! | 22 Aug, 15 Sep | 2026-09-15 | Akshar | 30 | 18 | #VALUE!
[7 empty] | 4.28 | Aux Cable laying | #VALUE! | #VALUE! | #VALUE! | 12-Aug, 23 Aug | 2026-08-23 | Akshar | 1000 | 10 | #VALUE!
[7 empty] | 4.29 | Control Cable laying | #VALUE! | #VALUE! | #VALUE! | 12-Aug, 23 Aug | 2026-08-23 | Akshar | 1000 | 10 | #VALUE!
[7 empty] | 4.3 | Communication Cable laying | #VALUE! | #VALUE! | #VALUE! | 12-Aug, 23 Aug | 2026-08-23 | Akshar | 500 | 10 | #VALUE!
[7 empty] | 4.31 | Aux Cable termination | #VALUE! | #VALUE! | #VALUE! | 22-Aug, 02 Sep, 20 Sep | 2026-09-20 | Akshar | 30 | 6 | #VALUE!
[7 empty] | 4.32 | Control Cable termination | #VALUE! | #VALUE! | #VALUE! | 22-Aug, 02 Sep, 20 Sep | 2026-09-20 | Akshar & Adaptive | 30 | 4 | #VALUE!
[7 empty] | 4.33 | Communication Cable termination | #VALUE! | #VALUE! | #VALUE! | 22-Aug, 02 Sep, 20 Sep | 2026-09-20 | Akshar & Adaptive | - | - | - |  | 52 | #VALUE! | #VALUE!
[7 empty] | 4.34 | CT SFRA & Tan delta Test | #VALUE! | #VALUE! | #VALUE! | 07-Aug, 15 Aug, 31 Aug | 2026-08-31 | Akshar | 2 | 8 | 12
[7 empty] | 4.35 | CT Routine Test | #VALUE! | #VALUE! | #VALUE! | 11-Aug, 20 Aug, 05 Sep | 2026-09-05 | Akshar
[7 empty] | 4.36 | CT Control scheme & Stability Test | #VALUE! | #VALUE! | #VALUE! | 01-Sep, 03 Sep, 27 Sep | 2026-09-27 | Akshar | 2 | 4 | #VALUE!
[7 empty] | 4.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | #VALUE! | #VALUE! | #VALUE! | 18 Aug, 04 Sep | 2026-09-04 | Akshar | 0.5 | 4 | #VALUE!
[7 empty] | 4.38 | HT Panel relay test | #VALUE! | #VALUE! | #VALUE! | 01-Sep, 02 Sep, 25 Sep | 2026-09-25 | Akshar | 6 | 4 | #VALUE!
[7 empty] | 4.39 | HT Cable VLF Test | #VALUE! | #VALUE! | #VALUE! | 18-Aug, 20 Aug, 03 Sep | 2026-09-03 | Akshar | 6 | 5 | #VALUE!
[7 empty] | 4.4 | CSS routine test | #VALUE! | #VALUE! | #VALUE! | 18 Aug, 02 Sep | 2026-09-02 | Akshar | 1 | 5 | #VALUE!
[7 empty] | 4.41 | ACDB routine test | #VALUE! | #VALUE! | #VALUE! | 18 Aug, 02 Sep | 2026-09-02 | Akshar | 3 | 5 | #VALUE!
[7 empty] | 4.42 | Earthing | #VALUE! | #VALUE! | #VALUE! | 20-Aug, 02 Sep, 13 Sep | 2026-09-13 | Akshar | 150 | 6 | #VALUE!
[7 empty] | 4.43 | LA | #VALUE! | #VALUE! | #VALUE! | 22-Aug, 02 Sep, 14 Sep | 2026-09-14 | Akshar | 5 | 6 | #VALUE!
Assumptions:-
1. Ship berthing + 72 hrs - clearing of 30 containers per day for site
2. 30 containers erected on site on 4th day
3. IDT charging = 24 days from erection of last container in the block
4. Trial run start date = IDT charging + 3 days
5. Trial run end date = Trial run start date + 2 days
6. COD = Trial run end date + 2 days
Formulas:
New EDC = IF(LEN([EDC])=5,[EDC],(IF([EDC]="Completed","-",DATEVALUE(RIGHT([EDC],6)))))

## 11 Working (hidden)
BESS 11 Charging Schedule | [17 empty] | 2026-07-30 |  |  | Common for PSS
Container Make | Block No. | Containers at Site | MWh | IDT Charging / Commissioning Start | Trial-Run End Date | COD | Status | [7 empty] | Productivity | Manpower | Total Mandays | Remarks |  |  | Tools & tackles | Required At site | Available At site | 2026-07-30
[7 empty] | Sr. | Activity | Progress |  |  | EDC | New EDC | vendor
[9 empty] | S | C | B
CATL | 4 | 28 Jun, 05 Jul | 271 MWh (48 Containers) | 2026-07-22 | 2026-07-27 | 2026-07-30 |  |  |  | Civil | [10 empty] | Machinery
[7 empty] | 4.1 | BCF Precast Erection & Welding | 48 | 48 | 0 | Completed | - | MSC | 1 | 2 | 0 |  |  |  | Cable jack | 6
[7 empty] | 4.2 | CT Rail Fixing | 6 | 6 | 0 | Completed | - | MSC | 1 | 16 | 0 |  |  |  | JCB | 6
[7 empty] | 4.3 | PCS Slab casting | 6 | 6 | 0 | Completed | - | MSC | 1 | 39 | 0 |  |  |  | Excavator | 1
[7 empty] | 4.4 | SGR Slab Casting | 1 | 1 | 0 | Completed | - | MSC | 1 | 37 | 0 |  |  |  | farana | 6
[7 empty] | 4.5 | MCR Slab Casting | 1 | 1 | 0 | Completed | - | MSC | 1 | 34 | 0 |  |  |  | DG with Sablizer | 8
[7 empty] | 4.6 | CSS Slab Casting | 1 | 1 | 0 | Completed | - | MSC | 1 | 54 | 0 |  |  |  | Welding Machine | 10
[7 empty] | 4.7 | BOT Slab casting | 3 | 3 | 0 | Completed | - | MSC | 1 | 5 | 0 |  |  |  | HOT Gun | 20
[7 empty] | 4.8 | NIFPS Precast Erection | 6 | 6 | 0 | Completed | - | MSC | 1 | 5 | 0 |  |  |  | Blower | 10
[7 empty] | 4.9 | PCS PEB | 6 | 6 | 0 | Completed | - | Synergy | 1 | 27 | 0 |  |  |  | Drilling Machine | 5
[7 empty] | 4.1 | SGR PEB | 1 | 1 | 0 | Completed | - | Synergy | 1 | 25 | 0 |  |  |  | Drilling Machine [Hammering] | 2
[7 empty] | 4.11 | MCR PEB | 1 | 1 | 0 | Completed | - | RV Enterprise | [6 empty] | Auger Machine | 1
[10 empty] | Electrical | [10 empty] | Tractor | 2
[7 empty] | 4.12 | CT Erection | 6 | 6 | 0 | Completed | - | Pratibha | 2 | 8 | 0 |  |  |  | Cable Puller | 2
[7 empty] | 4.13 | PCS Erection | 48 | 48 | 0 | Completed | - | Pratibha | 10 | 8 | 0 |  |  |  | Testing Kits
[7 empty] | 4.14 | ACDB Erection | 6 | 6 | 0 | Completed | - | Pratibha | 5 | 4 | 0 |  |  |  | Megar | 5
[7 empty] | 4.15 | ECP Panel Erection (Communication Panel) | 6 | 6 | 0 | Completed | - | Pratibha | 6 | 8 | 4 |  |  |  | Filtration Machine | 1
[7 empty] | 4.16 | HT Panel Erection | 2 | 2 | 0 | Completed | - | Pratibha | 1 | [5 empty] | Online PPM Meter | 1
[7 empty] | 4.17 | EMS Panel Erection | 1 | 1 | 0 | Completed | - | Pratibha | 1 | [5 empty] | SFRA Test kit | 1
[7 empty] | 4.18 | CSS Erection | 1 | 1 | 0 | Completed | - | Pratibha | 1 | [5 empty] | Tan delta kit | 1
* Min. 60 termination teams required for DC & LT Cable termination with crimping tool (Each team required at least 01 skilled technician with 01 helper) Common for PSS Available - 26 teams (52 Technician) of DC & LT Cable Termination & 2 HT Cable Termination Teams Machinery - Crimping tool: 60, Cable jack: 06, JCB: 06, Excavator: 01, Farana: 06, DG: 08, Welding machine: 10 (Common For PSS) Testing To be Completed by 19 Jul, 22 july. Required Testing Team (6 Skilled & 12 Unskilled) (Common For PSS) Testing kits : Oil Filteration, Online PPM Meter, SFRA & Tan Delta, DC Winding Resistance, Turn Ratio meter, routine test kit (common for 1 PSS) ERT, DC High POT, (common for 1 PSS) VLF kit (1 nos), IR Tester, Multimeter & Clamp Meter (atleast 3 per PSS) Breaker CRM & Timing, Vaccum Bottle Integrity (common for 1 PSS), CT Analyzer (2 nos), Relay Testing Kit, CT Primary Injection (3-Phase), PT Stability (3-Phase), Impedence meter (Common for 1 PSS) | [6 empty] | 4.19 | NIFPS Panel Erection | 6 | 6 | 0 | Completed | - | Ornet / EMR | 6 | - | - |  |  |  | Routine test kit | 1
[7 empty] | 4.2 | NIFPS Fabrication | 6 | 6 | 0 | Completed | - | Ornet / EMR | 0.66667 | 0 | 0 |  |  |  | CT Analyzer | 2
[7 empty] | 4.21 | Battery Container Erection | 48 | 48 | 0 | Completed | - | HEFT & Pratibha | 10 | 4 | 0 |  |  |  | ERT Meter | 1
[7 empty] | 4.22 | HT cable laying | 6909 | 6909 | 0 | Completed | - | Pratibha | 1500 | 48 | 0 |  |  |  | Primary injection kit | 1
[7 empty] | 4.23 | HT cable termination | 28 | 28 | 0 | 05 Jul, 09 Jul, 18 Jul | 05 Jul, 09 Jul, 18 Jul | Pratibha | 8 | 6 | 0 | Torquing WIP |  |  | PT test kit | 1
[7 empty] | 4.24 | DC Cable laying | 13556 | 13556 | 0 | Completed | - | Pratibha | 600 | 10 | 0 |  |  |  | 3 Phase Primary injection kit | 1
[7 empty] | 4.25 | LT Cable laying | 44160 | 44160 | 0 | Completed | - | Pratibha | 600 | 10 | 0 |  |  |  | Breaker, CRM, Timming & vacuum Bottle test kits | 1 | 1
[7 empty] | 4.26 | DC Cable termination | 1536 | 1536 | 0 | 18 Jul | 18 Jul | Pratibha | 30 | 18 | 0 | Lugging WIP, Sleev & Torquing WIP (512 nos torquing completed) |  |  | DC high Pot kit | 1 |  | #VALUE!
[7 empty] | 4.27 | LT Cable termination | 2304 | 2304 | 0 | 20 Jul | 20 Jul | Pratibha | 30 | 18 | 0 | Lugging completed, Sleev & Torquing WIP (384 nos torquing completed) |  |  | VLF Kit | 1
[7 empty] | 4.28 | Aux Cable laying | 7701 | 7701 | 0 | 2026-07-16 | 2026-07-09 | Pratibha | 800 | 10 | 0 |  |  |  | Relay Secondary injection kit | 2
[7 empty] | 4.29 | Control Cable laying | 13198 | 13198 | 0 | 2026-07-17 | 2026-07-09 | Pratibha | 1000 | 10 | 0 |  |  |  | Multimeter, IR Tester & Clamp meter | 3 | 2
[7 empty] | 4.3 | Communication Cable laying | 5175 | 5175 | 0 | 2026-07-16 | 2026-07-09 | Pratibha | 600 | 10 | 0 |  |  |  | Impedance Meter | 2
[7 empty] | 4.31 | Aux Cable termination | 284 | 284 | 0 | 20 Jul | 20 Jul | Pratibha | 30 | 6 | 0
[7 empty] | 4.32 | Control Cable termination | 504 | 504 | 0 | 20 Jul | 20 Jul | Pratibha & Emerson | 30 | 4 | 0 | Glanding WIP. |  |  | Tools
[7 empty] | 4.33 | Communication Cable termination | 380 | 380 | 0 | 09 Jul, 15 Jul, 20 Jul | 09 Jul, 15 Jul, 20 Jul | Pratibha & Emerson | - | - | - | Glanding WIP. | #VALUE! | 4.004 | Crimping tool | 60
[7 empty] | 4.34 | CT SFRA & Tan delta Test | 6 | 6 | 0 | Completed | - | Canbay | - | - | - |  |  |  | Torque Wrench | 10
[7 empty] | 4.35 | CT Routine Test | 6 | 6 | 0 | Completed | - | Pratibha | 2 | 8 | 0 |  |  |  | Tool Set | 10
[7 empty] | 4.36 | CT Control scheme & Stability Test | 6 | 6 | 0 | 19 Jul, 22 Jul | 2026-07-22 | Pratibha | 2 | 4 | 0 |  | -8 | 4.004 | Cable Cutter | 10
[7 empty] | 4.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | 12 | 12 | 0 | 05 Jul, 09 Jul, 16 Jul | 05 Jul, 09 Jul, 16 Jul | Pratibha | 0.5 | 4 | 0 | Breaker test completed, reamining CT, PT & meter test WIP
[7 empty] | 4.38 | HT Panel relay test | 16 | 16 | 0 | 17 Jul, 21 Jul | 2026-07-21 | Pratibha | 6 | 4 | 0
[7 empty] | 4.39 | HT Cable VLF Test | 14 | 14 | 0 | Completed | Completed | Pratibha | 6 | 5 | 0
[7 empty] | 4.4 | CSS routine test | 1 | 1 | 0 | 05 Jul, 09 Jul, 17 Jul | 05 Jul, 09 Jul, 17 Jul | Pratibha | 1 | 5 | 0 | 01 Testing team available at site
Pratibha: Available manpower - 95 nos Avg. required manpower - 115 nos | [6 empty] | 4.41 | ACDB routine test | 6 | 6 | 0 | Completed | Completed | Pratibha | 3 | 5 | 0 | Required 06 Testing teams at site
[7 empty] | 4.42 | Earthing | 5069.8 | 5069.7 | 0.1 | 07 Jul, 09 Jul, 18 Jul | 07 Jul, 09 Jul, 18 Jul | Pratibha | 150 | 6 | 0.004
[7 empty] | 4.43 | LA | 10 | 10 | 0 | 09 Jul, 12 Jul, 20 Jul | 09 Jul, 12 Jul, 20 Jul | Pratibha | 5 | 6 | 0
CATL | 3 | 04 Jul, 08 Jul, 13 Jul | 271 MWh (48 Containers) | 2026-07-28 | 2026-08-02 | 2026-08-05 |  |  |  | Civil
[7 empty] | 3.1 | BCF Precast Erection & Welding | 48 | 48 | 0 | Completed | - | MSC | 1 | 2 | 0
[7 empty] | 3.2 | CT Rail Fixing | 6 | 6 | 0 | Completed | - | MSC | 1 | 16 | 0
[7 empty] | 3.3 | PCS Slab casting | 6 | 6 | 0 | Completed | - | MSC | 1 | 39 | 0
[7 empty] | 3.4 | SGR Slab Casting | 1 | 1 | 0 | Completed | - | MSC | 1 | 37 | 0
[7 empty] | 3.5 | MCR Slab Casting | 1 | 1 | 0 | Completed | - | MSC | 1 | 34 | 0
[7 empty] | 3.6 | CSS Slab Casting | 1 | 1 | 0 | Completed | - | MSC | 1 | 54 | 0
[7 empty] | 3.7 | BOT Slab casting | 2 | 2 | 0 | Completed | - | MSC | 1 | 5 | 0
[7 empty] | 3.8 | BOT Precast Erection | 1 | 1 | 0 | Completed | - | Sachi | 3 | 5 | 0
[7 empty] | 3.9 | NIFPS Precast Erection | 6 | 6 | 0 | Completed | - | MSC | 1 | 5 | 0
[7 empty] | 3.1 | PCS PEB | 6 | 6 | 0 | Completed | - | Synergy | 1 | 27 | 0
[7 empty] | 3.11 | SGR PEB | 1 | 1 | 0 | Completed | - | Synergy | 1 | 25 | 0
[7 empty] | 3.12 | MCR PEB | 1 | 1 | 0 | 01 Jul, 06 Jul, 11 Jul, 20 Jul | 2026-07-11 | RV Enterprise | - | - | - | PEB Container installation WIP.
Electrical
[7 empty] | 3.13 | CT Erection | 6 | 6 | 0 | Completed | - | Pratibha | 2 | 4 | 0
[7 empty] | 3.14 | PCS Erection | 48 | 48 | 0 | Completed | - | Pratibha | 10 | 4 | 0
[7 empty] | 3.15 | ACDB Erection | 6 | 6 | 0 | Completed | - | Pratibha | 5 | 4 | 0
[7 empty] | 3.16 | ECP Panel Erection (Communication Panel) | 6 | 6 | 0 | 27 Jun, 30 Jun, 10 Jul, 17 Jul | 2026-07-17 | Pratibha | 20 | 4 | 4 | Placed on slab, anchoring WIP
[7 empty] | 3.17 | HT Panel Erection | 2 | 2 | 0 | Completed | - | Pratibha | 10
[7 empty] | 3.18 | EMS Panel Erection | 1 | 0 | 1 | 04 Jul, 07 Jul, 11 Jul, 17 Jul | 2026-07-11 | Pratibha | 10
Testing to be completed by 28 july. | [6 empty] | 3.19 | CSS Erection | 1 | 1 | 0 | Completed | - | Pratibha | 10
[7 empty] | 3.2 | NIFPS Panel Erection | 6 | 6 | 0 | Completed | - | Ornet / EMR | 20
[7 empty] | 3.21 | NIFPS Fabrication | 6 | 6 | 0 | 10 Jul, 18 Jul | 2026-07-18 | Ornet / EMR | 0.66667 | 0 | 0
[7 empty] | 3.22 | Battery Container Erection | 48 | 48 | 0 | 09 Jul, 13 Jul, 19 Jul | 09 Jul, 13 Jul, 19 Jul | HEFT & Pratibha | 10 | 4 | 0 | Welding with foundation WIP
[7 empty] | 3.23 | HT cable laying | 7650 | 7650 | 0 | Completed | - | Pratibha | 1500 | 48 | 0
[7 empty] | 3.24 | HT cable termination | 28 | 28 | 0 | 11 Jul, 12 Jul, 22 Jul | 11 Jul, 12 Jul, 22 Jul | Pratibha | 8 | 6 | 0 | Lugging complete, Torquing will be done post VLT test.
[7 empty] | 3.25 | DC Cable laying | 13780 | 13780 | 0 | Completed | - | Pratibha | 600 | 10 | 0
[7 empty] | 3.26 | LT Cable laying | 45596 | 45596 | 0 | Completed | - | Pratibha | 600 | 10 | 0
[7 empty] | 3.27 | DC Cable termination | 1536 | 1536 | 0 | 15 Jul, 18 Jul, 25 Jul | 15 Jul, 18 Jul, 25 Jul | Pratibha | 30 | 18 | 0
[7 empty] | 3.28 | LT Cable termination | 2304 | 2304 | 0 | 15 Jul, 18 Jul, 25 Jul | 15 Jul, 18 Jul, 25 Jul | Pratibha | 30 | 18 | 0 | Lugging WIP, Torquing YTS.
[7 empty] | 3.29 | Aux Cable laying | 8355 | 6186 | 2169 | 05 Jul, 10 Jul, 20 Jul | 05 Jul, 10 Jul, 20 Jul | Pratibha | 1000 | 10 | 21.69
[7 empty] | 3.3 | Control Cable laying | 13076 | 9308 | 3768 | 05 Jul, 11 Jul, 22 Jul | 05 Jul, 11 Jul, 22 Jul | Pratibha | 1000 | 10 | 37.68
[7 empty] | 3.31 | Communication Cable laying | 4792 | 0 | 4792 | 05 Jul, 12 Jul, 22 Jul | 05 Jul, 12 Jul, 22 Jul | Pratibha | 500 | 10 | 95.84
[7 empty] | 3.32 | Aux Cable termination | 286 | 0 | 286 | 15 Jul, 25 Jul | 2026-07-25 | Pratibha | 30 | 6 | 57.2
[7 empty] | 3.33 | Control Cable termination | 524 | 0 | 524 | 15 Jul, 25 Jul | 2026-07-25 | Pratibha & Emerson | 30 | 4 | 69.8667
[7 empty] | 3.34 | Communication Cable termination | 384 | 0 | 384 | 15 Jul, 25 Jul | 2026-07-25 | Pratibha & Emerson | - | - | - |  | -5 | 507.9433
[7 empty] | 3.35 | CT SFRA & Tan delta Test | 6 | 6 | 0 | Completed | - | Canbay | 2 | 8 | -
[7 empty] | 3.36 | CT Routine Test | 6 | 6 | 0 | Completed | - | Pratibha |  |  | 12
[7 empty] | 3.37 | CT Control scheme & Stability Test | 6 | 0 | 6 | 25 Jul, 28 Jul | 2026-07-28 | Pratibha | 2 | 4 | 12 |  | -2 | 507.9433
[7 empty] | 3.38 | HT Panel Routine (CT & PT, Breaker & Meter) Test | 12 | 0 | 12 | 11 Jul, 19 Jul | 2026-07-19 | Pratibha | 0.5 | 4 | 96 | HT Panel - breaker test completed
[7 empty] | 3.39 | HT Panel relay test | 16 | 0 | 16 | 23 Jul, 27 Jul | 2026-07-27 | Pratibha | 6 | 4 | 10.6667
[7 empty] | 3.4 | HT Cable VLF Test | 14 | 14 | 0 | 11 Jul, 18 Jul | 2026-07-18 | Pratibha | 6 | 5 | 0
Pratibha: Available manpower - 70 nos Avg. required manpower - 122 nos | [6 empty] | 3.41 | CSS routine test | 1 | 0 | 1 | 11 Jul, 20 Jul | 2026-07-20 | Pratibha | 1 | 5 | 5 | 01 Testing team available at site
[7 empty] | 3.42 | ACDB routine test | 6 | 6 | 0 | 11 Jul, 21 Jul | 2026-07-21 | Pratibha | 3 | 5 | 0 | Required 06 Testing teams at site
[7 empty] | 3.43 | Earthing | 4284 | 2434 | 1850 | 13 Jul, 19Jul | 2026-07-19 | Pratibha | 150 | 6 | 74
[7 empty] | 3.44 | LA | 10 | 0 | 10 | 15 Jul, 25 Jul | 2026-07-25 | Pratibha | 5 | 6 | 12
CATL | 2 | 13 Jul, 20 Jul | 271 MWh (48 Containers) | 2026-08-06 | 2026-08-11 | 2026-08-14 |  |  |  | Civil
[7 empty] | 2.1 | BCF Precast Erection & Welding | 48 | 48 | 0 | Completed | - | MSC | 1 | 2 | 0
[7 empty] | 2.2 | CT Rail Fixing | 6 | 6 | 0 | Completed | - | MSC | 1 | 16 | 0
[7 empty] | 2.3 | PCS Slab casting | 6 | 6 | 0 | Completed | - | MSC | 1 | 39 | 0
[7 empty] | 2.4 | SGR Slab Casting | 1 | 1 | 0 | Completed | - | MSC | 1 | 37 | 0
[7 empty] | 2.5 | MCR Slab Casting | 1 | 1 | 0 | Completed | - | MSC | 1 | 34 | 0
[7 empty] | 2.6 | CSS Slab Casting | 1 | 1 | 0 | Completed | - | MSC | 1 | 54 | 0
[7 empty] | 2.7 | BOT Slab casting | 1 | 1 | 0 | Completed | - | MSC | 1 | 5 | 0
[7 empty] | 2.8 | BOT Precast Erection | 2 | 2 | 0 | Completed | - | Sachi | 3 | 5 | 0
[7 empty] | 2.9 | NIFPS Precast Erection | 6 | 5 | 1 | 22 Jun, 02 Jul, 14 Jul, 20 Jul | 2026-07-20 | MSC | 1 | 5 | 5 | Cable trench excavated, will be done post trench backfilling
[7 empty] | 2.1 | PCS PEB | 6 | 6 | 0 | Completed | - | Synergy | 1 | 27 | 0
[7 empty] | 2.11 | SGR PEB | 1 | 1 | 0 | Completed | - | Synergy | 1 | 25 | 0
[7 empty] | 2.12 | MCR PEB | 1 | 1 | 0 | 01 Jul, 10 Jul, 14 Jul, 21 Jul | 2026-07-14 | RV Enterprise | - | - | -
Electrical
[7 empty] | 2.13 | CT Erection | 6 | 6 | 0 | Completed | - | Pratibha | 2 | 4 | 0
[7 empty] | 2.14 | PCS Erection | 48 | 48 | 0 | Completed | Completed | Pratibha | 10 | 4 | 0
[7 empty] | 2.15 | ACDB Erection | 6 | 6 | 0 | Completed | - | Pratibha | 5 | 4 | 0 | Welding with foundation WIP
[7 empty] | 2.16 | ECP Panel Erection (Communication Panel) | 6 | 0 | 6 | 06 Jul, 10 Jul, 25 Jul | 06 Jul, 10 Jul, 25 Jul | Pratibha | 20 | 4 | 4 | Placed on slab, anchoring WIP
[7 empty] | 2.17 | HT Panel Erection | 2 | 2 | 0 | Completed | - | Pratibha | 10
[7 empty] | 2.18 | EMS Panel Erection | 1 | 1 | 0 | 05 Jul, 11 Jul, 20 Jul | 05 Jul, 11 Jul, 20 Jul | Pratibha | 10
Testing to be completed by 06 Aug. | [6 empty] | 2.19 | CSS Erection | 1 | 1 | 0 | Completed | - | Pratibha | 10
[7 empty] | 2.2 | NIFPS Panel Erection | 6 | 0 | 6 | 11 Jul, 16 Jul, 23 Jul | 11 Jul, 16 Jul, 23 Jul | Ornet / EMR | 20
[7 empty] | 2.21 | NIFPS Fabrication | 6 | 0 | 6 | 15 Jul, 18 Jul, 25 Jul | 15 Jul, 18 Jul, 25 Jul | Ornet / EMR | 0.66667 | 0 | 0
[7 empty] | 2.22 | Battery Container Erection | 48 | 48 | 0 | 18-Jul, 25 Jul | 2026-07-25 | HEFT & Pratibha | 10 | 4 | 0
[7 empty] | 2.23 | HT cable laying | 8171 | 8171 | 0 | Completed | - | Pratibha | 1500 | 48 | 0
[7 empty] | 2.24 | HT cable termination | 28 | 28 | 0 | 20 Jul, 26 Jul | 2026-07-26 | Pratibha | 8 | 6 | 0 | Lugging completed, toquing will be done post VLF testing.
[7 empty] | 2.25 | DC Cable laying | 13292 | 13292 | 0 | Completed | Completed | Pratibha | 600 | 10 | 0
[7 empty] | 2.26 | LT Cable laying | 46080 | 46080 | 0 | Completed | - | Pratibha | 600 | 10 | 0
[7 empty] | 2.27 | DC Cable termination | 1536 | 0 | 1536 | 24-Jul, 03 Aug | 2026-08-03 | Pratibha | 30 | 18 | 921.6
[7 empty] | 2.28 | LT Cable termination | 2304 | 0 | 2304 | 24-Jul, 03 Aug | 2026-08-03 | Pratibha | 30 | 18 | 1382.4
[7 empty] | 2.29 | Aux Cable laying | 8391 | 4672 | 3719 | 02 Jul, 07 Jul, 12 Jul, 30 Jul | 2026-07-12 | Pratibha | 1000 | 10 | 37.19
[7 empty] | 2.3 | Control Cable laying | 14355 | 2528 | 11827 | 14-Jul, 30 Jul | 2026-07-30 | Pratibha | 1000 | 10 | 118.27
[7 empty] | 2.31 | Communication Cable laying | 4792 | 0 | 4792 | 14-Jul, 30 Jul | 2026-07-30 | Pratibha | 500 | 10 | 95.84
[7 empty] | 2.32 | Aux Cable termination | 286 | 0 | 286 | 24-Jul, 03 Aug | 2026-08-03 | Pratibha | 30 | 6 | 57.2
[7 empty] | 2.33 | Control Cable termination | 524 | 0 | 524 | 24-Jul, 03 Aug | 2026-08-03 | Pratibha & Emerson | 30 | 4 | 69.8667
[7 empty] | 2.34 | Communication Cable termination | 384 | 0 | 384 | 24-Jul, 03 Aug | 2026-08-03 | Pratibha & Emerson | - | - | - |  | 4 | 3004.18
[7 empty] | 2.35 | CT SFRA & Tan delta Test | 6 | 6 | 0 | Completed | - | Canbay | 2 | 8 | -
[7 empty] | 2.36 | CT Routine Test | 6 | 0 | 6 | 13 Jul, 30 Jul | 2026-07-30 | Pratibha |  |  | 12
[7 empty] | 2.37 | CT Control scheme & Stability Test | 6 | 0 | 6 | 03 Aug, 06 Aug | 2026-08-06 | Pratibha | 2 | 4 | 12 | 01 Testing team available at site | 7 | 3004.18
[7 empty] | 2.38 | HT Panel Routine (CT & PT, Breaker & Meter) Test | 12 | 0 | 12 | 20 Jul, 29 Jul | 2026-07-29 | Pratibha | 0.5 | 4 | 96 | Required 06 Testing teams at site
[7 empty] | 2.39 | HT Panel relay test | 16 | 0 | 16 | 01 Aug, 05 Aug | 2026-08-05 | Pratibha | 6 | 4 | 10.6667
[7 empty] | 2.4 | HT Cable VLF Test | 14 | 0 | 14 | 20 Jul, 25 Jul | 2026-07-25 | Pratibha | 6 | 5 | 11.6667
Pratibha: Available manpower - 52 nos Avg. required manpower - 121 nos | [6 empty] | 2.41 | CSS routine test | 1 | 0 | 1 | 20 Jul, 30 Jul | 2026-07-30 | Pratibha | 1 | 5 | 5
[7 empty] | 2.42 | ACDB routine test | 6 | 0 | 6 | 20 Jul, 29 Jul | 2026-07-29 | Pratibha | 3 | 5 | 10
[7 empty] | 2.43 | Earthing | 4284 | 572 | 3712 | 22 Jul, 01 Aug | 2026-08-01 | Pratibha | 150 | 6 | 148.48
[7 empty] | 2.44 | LA | 10 | 0 | 10 | 22 Jul, 01 Aug | 2026-08-01 | Pratibha | 5 | 6 | 12
CATL | 1 | 16 Jul, 23 Jul | 271 MWh (48 Containers) | 2026-08-09 | 2026-08-14 | 2026-08-17 |  |  |  | Civil
[7 empty] | 1.1 | BCF Precast Erection & Welding | 48 | 48 | 0 | Completed | - | MSC | 1 | 2 | 0
[7 empty] | 1.2 | CT Rail Fixing | 6 | 6 | 0 | Completed | - | MSC | 1 | 16 | 0
[7 empty] | 1.3 | PCS Slab casting | 6 | 6 | 0 | Completed | - | MSC | 1 | 39 | 0
[7 empty] | 1.4 | SGR Slab Casting | 1 | 1 | 0 | Completed | - | MSC | 1 | 37 | 0
[7 empty] | 1.5 | MCR Slab Casting | 1 | 1 | 0 | Completed | - | MSC | 1 | 34 | 0
[7 empty] | 1.6 | CSS Slab Casting | 1 | 1 | 0 | Completed | - | MSC | 1 | 54 | 0
[7 empty] | 1.7 | BOT Slab casting | 3 | 3 | 0 | Completed | - | MSC | 1 | 5 | 0
[7 empty] | 1.8 | NIFPS Precast Erection | 6 | 5 | 1 | 24 Jun, 30 Jun, 15 Jul, 22 Jul | 2026-07-15 | MSC | 1 | 5 | 5 | Cable trench excavated, will be done post trench backfilling
[7 empty] | 1.9 | PCS PEB | 6 | 6 | 0 | Completed | - | Synergy | 1 | 27 | 0
[7 empty] | 1.1 | SGR PEB | 1 | 1 | 0 | Completed | - | Synergy | 1 | 25 | 0
[7 empty] | 1.11 | MCR PEB | 1 | 1 | 0 | 01 Jul, 12 Jul, 22 Jul | 01 Jul, 12 Jul, 22 Jul | RV Enterprise | - | - | -
Electrical
[7 empty] | 1.12 | CT Erection | 6 | 6 | 0 | Completed | - | Pratibha | 2 | 4 | 0
[7 empty] | 1.13 | PCS Erection | 48 | 48 | 0 | Completed | Completed | Pratibha | 10 | 4 | 0
[7 empty] | 1.14 | ACDB Erection | 6 | 6 | 0 | Completed | - | Pratibha | 5 | 4 | 0
[7 empty] | 1.15 | ECP Panel Erection (Communication Panel) | 6 | 0 | 6 | Completed | Completed | Pratibha | 20 | 4 | 4 | Placed on slab, anchoring WIP
[7 empty] | 1.16 | HT Panel Erection | 2 | 2 | 0 | Completed | - | Pratibha | 10
[7 empty] | 1.17 | EMS Panel Erection | 1 | 0 | 1 | 05 Jul, 13 Jul, 22 Jul | 05 Jul, 13 Jul, 22 Jul | Pratibha | 10
[7 empty] | 1.18 | CSS Erection | 1 | 1 | 0 | Completed | - | Pratibha | 10
Testing to be completed by 09 Aug. | [6 empty] | 1.19 | NIFPS Panel Erection | 6 | 0 | 6 | 15 Jul, 17 Jul, 25 Jul | 15 Jul, 17 Jul, 25 Jul | Ornet / EMR | 20
[7 empty] | 1.2 | NIFPS Fabrication | 6 | 0 | 6 | 20 Jul, 27 Jul | 2026-07-27 | Ornet / EMR | 0.66667 | 0 | 0
[7 empty] | 1.21 | Battery Container Erection | 48 | 48 | 0 | 21-Jul, 28-Jul | 2026-07-28 | HEFT & Pratibha | 10 | 4 | 0
[7 empty] | 1.22 | HT cable laying | 8865 | 8865 | 0 | Completed | - | Pratibha | 1500 | 48 | 0
[7 empty] | 1.23 | HT cable termination | 28 | 28 | 0 | 12 Jul, 20 Jul, 05 Aug | 12 Jul, 20 Jul, 05 Aug | Pratibha | 8 | 6 | 0
[7 empty] | 1.24 | DC Cable laying | 13120 | 13120 | 0 | Completed | Completed | Pratibha | 600 | 10 | 0
[7 empty] | 1.25 | LT Cable laying | 44784 | 44784 | 0 | Completed | Completed | Pratibha | 600 | 10 | 0
[7 empty] | 1.26 | DC Cable termination | 1536 | 0 | 1536 | 27 Jul, 05 Aug | 2026-08-05 | Pratibha | 30 | 18 | 921.6
[7 empty] | 1.27 | LT Cable termination | 2304 | 0 | 2304 | 27 Jul, 05 Aug | 2026-08-05 | Pratibha | 30 | 18 | 1382.4
[7 empty] | 1.28 | Aux Cable laying | 8282 | 4573 | 3709 | 17 Jul, 03 Aug | 2026-08-03 | Pratibha | 1000 | 10 | 37.09
[7 empty] | 1.29 | Control Cable laying | 14490 | 0 | 14490 | 17 Jul, 03 Aug | 2026-08-03 | Pratibha | 1000 | 10 | 144.9
[7 empty] | 1.3 | Communication Cable laying | 4792 | 0 | 4792 | 17 Jul, 03 Aug | 2026-08-03 | Pratibha | 500 | 10 | 95.84
[7 empty] | 1.31 | Aux Cable termination | 286 | 0 | 286 | 27 Jul, 05 Aug | 2026-08-05 | Pratibha | 30 | 6 | 57.2
[7 empty] | 1.32 | Control Cable termination | 536 | 0 | 536 | 20-Jul, 05 Aug | 2026-08-05 | Pratibha & Emerson | 30 | 4 | 71.4667
[7 empty] | 1.33 | Communication Cable termination | 384 | 0 | 384 | 20-Jul, 05 Aug | 2026-08-05 | Pratibha & Emerson | - | - | - |  | 6 | 3037.91
[7 empty] | 1.34 | CT SFRA & Tan delta Test | 6 | 6 | 0 | Completed | - | Canbay | 2 | 8 | -
[7 empty] | 1.35 | CT Routine Test | 6 | 0 | 6 | 16-Jul, 03 Aug | 2026-08-03 | Pratibha |  |  | 12
[7 empty] | 1.36 | CT Control scheme & Stability Test | 6 | 0 | 6 | 06 Aug, 09 Aug | 2026-08-09 | Pratibha | 2 | 4 | 12 |  | 10 | 3037.91
[7 empty] | 1.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | 12 | 0 | 12 | 23- Jul, 03 Aug | 2026-08-03 | Pratibha | 0.5 | 4 | 96
[7 empty] | 1.38 | HT Panel relay test | 16 | 0 | 16 | 04 Aug, 08 Aug | 2026-08-08 | Pratibha | 6 | 4 | 10.6667
[7 empty] | 1.39 | HT Cable VLF Test | 14 | 0 | 14 | 23 Jul, 30 Jul | 2026-07-30 | Pratibha | 6 | 5 | 11.6667
[7 empty] | 1.4 | CSS routine test | 1 | 0 | 1 | 23 Jul, 03 Aug | 2026-08-03 | Pratibha | 1 | 5 | 5 | 01 Testing team available at site
Pratibha: Available manpower - 36 nos Avg. required manpower - 122 nos | [6 empty] | 1.41 | ACDB routine test | 6 | 0 | 6 | 23 Jul, 04 Aug | 2026-08-04 | Pratibha | 3 | 5 | 10 | Required 06 Testing teams at site
[7 empty] | 1.42 | Earthing | 4284 | 432 | 3852 | 25-Jul, 07 Aug | 2026-08-07 | Pratibha | 150 | 6 | 154.08
[7 empty] | 1.43 | LA | 10 | 0 | 10 | 27- Jul, 07 Aug | 2026-08-07 | Pratibha | 5 | 6 | 12
CATL | 5 | 04 Aug, 15 Aug | 271 MWh (48 Containers) | 2026-08-28 | 2026-09-02 | 2026-09-05 |  |  |  | Civil
[7 empty] | 5.1 | BCF Precast Erection & Welding | 48 | 48 | 0 | Completed | - | MSC | 1 | 2 | 0
[7 empty] | 5.2 | CT Rail Fixing | 6 | 6 | 0 | Completed | - | MSC | 1 | 16 | 0
[7 empty] | 5.3 | PCS Slab casting | 6 | 6 | 0 | Completed | - | MSC | 1 | 39 | 0
[7 empty] | 5.4 | SGR Slab Casting | 1 | 1 | 0 | 25 Jun, 30 Jun, 13 Jul, 17 Jul | 2026-07-13 | MSC | 1 | 37 | 0
[7 empty] | 5.5 | MCR Slab Casting | 1 | 1 | 0 | Completed | 2026-07-13 | MSC | 1 | 34 | 0
[7 empty] | 5.6 | CSS Slab Casting | 1 | 1 | 0 | Completed | - | MSC | 1 | 54 | 0
[7 empty] | 5.7 | BOT Precast Erection | 3 | 3 | 0 | Completed | - | Sachi | 3 | 5 | 0
[7 empty] | 5.8 | NIFPS Precast Erection | 6 | 6 | 0 | Completed | - | MSC | 1 | 5 | 0
[7 empty] | 5.9 | PCS PEB | 6 | 6 | 0 | Completed | - | Synergy | 1 | 27 | 0
[7 empty] | 5.1 | SGR PEB | 1 | 0 | 1 | 05 Jul, 20 Jul, 30 Jul | 05 Jul, 20 Jul, 30 Jul | Synergy | 1 | 25 | 25
[7 empty] | 5.11 | MCR PEB | 1 | 0 | 1 | 06 Jul, 14 Jul, 17 Jul, 26 Jul | 2026-07-26 | RV Enterprise | - | - | -
Electrical
[7 empty] | 5.12 | CT Erection | 6 | 6 | 0 | Completed | - | Pratibha | 2 | 4 | 0
[7 empty] | 5.13 | PCS Erection | 48 | 0 | 48 | 20 Jul, 25Jul | 2026-07-25 | Pratibha | 10 | 4 | 19.2 | 48 PCS placed on slab, anchoring WIP
[7 empty] | 5.14 | ACDB Erection | 6 | 0 | 6 | 22 Jul, 25Jul | 2026-07-25 | Pratibha | 5 | 4 | 4.8
[7 empty] | 5.15 | ECP Panel Erection (Communication Panel) | 6 | 0 | 6 | 22 Jul, 25Jul | 2026-07-25 | Pratibha | 20 | 4 | 4
[7 empty] | 5.16 | HT Panel Erection | 2 | 0 | 2 | 07 Jul, 17 Jul, 28 Jul | 07 Jul, 17 Jul, 28 Jul | Pratibha | 10
[7 empty] | 5.17 | EMS Panel Erection | 1 | 0 | 1 | 10 Jul, 16 Jul, 18 Jul, 01 Aug | 2026-08-01 | Pratibha | 10
[7 empty] | 5.18 | CSS Erection | 1 | 0 | 1 | 10 Jul, 15 Jul, 25 Jul | 10 Jul, 15 Jul, 25 Jul | Pratibha | 10
Testing to be completed by 25 Aug. | [6 empty] | 5.19 | NIFPS Panel Erection | 6 | 0 | 6 | 19 Jul, 27 Jul | 2026-07-27 | Ornet / EMR | 20
[7 empty] | 5.2 | NIFPS Fabrication | 6 | 0 | 6 | 24 Jul, 30 Jul | 2026-07-30 | Ornet / EMR | 0.66667 | 0 | 0
[7 empty] | 5.21 | Battery Container Erection | 48 | 0 | 48 | 09 Aug, 20 Aug | 2026-08-20 | HEFT & Pratibha | 10 | 4 | 19.2
[7 empty] | 5.22 | HT cable laying | 5680.75 | 603 | 5077.75 | 2026-07-26 | 2026-07-26 | Pratibha | 1500 | 48 | 162.488
[7 empty] | 5.23 | HT cable termination | 28 | 0 | 28 | 2026-08-11 | 2026-08-11 | Pratibha | 8 | 6 | 21
[7 empty] | 5.24 | DC Cable laying | 14290 | 0 | 14290 | 2026-08-01 | 2026-08-01 | Pratibha | 600 | 10 | 238.1667
[7 empty] | 5.25 | LT Cable laying | 47399 | 0 | 47399 | 2026-07-26 | 2026-07-26 | Pratibha | 600 | 10 | 789.9833
[7 empty] | 5.26 | DC Cable termination | 1536 | 0 | 1536 | 15 Aug, 20 Aug | 2026-08-20 | Pratibha | 30 | 18 | 921.6
[7 empty] | 5.27 | LT Cable termination | 2304 | 0 | 2304 | 2026-08-15 | 2026-08-15 | Pratibha | 30 | 18 | 1382.4
[7 empty] | 5.28 | Aux Cable laying | 8232 | 0 | 8232 | 2026-08-05 | 2026-08-05 | Pratibha | 1000 | 10 | 82.32
[7 empty] | 5.29 | Control Cable laying | 14448 | 0 | 14448 | 2026-08-05 | 2026-08-05 | Pratibha | 1000 | 10 | 144.48
[7 empty] | 5.3 | Communication Cable laying | 4792 | 0 | 4792 | 2026-08-05 | 2026-08-05 | Pratibha | 500 | 10 | 95.84
[7 empty] | 5.31 | Aux Cable termination | 286 | 0 | 286 | 15 Aug, 20 Aug | 2026-08-20 | Pratibha | 30 | 6 | 57.2
[7 empty] | 5.32 | Control Cable termination | 536 | 0 | 536 | 15 Aug, 20 Aug | 2026-08-20 | Pratibha & Emerson | 30 | 4 | 71.4667
[7 empty] | 5.33 | Communication Cable termination | 384 | 0 | 384 | 15 Aug, 20 Aug | 2026-08-20 | Pratibha & Emerson | - | - | - |  | 21 | 4354.838
[7 empty] | 5.34 | CT SFRA & Tan delta Test | 6 | 0 | 6 | 2026-07-31 | 2026-07-31 | Canbay | 2 | 8 | -
[7 empty] | 5.35 | CT Routine Test | 6 | 0 | 6 | 2026-08-04 | 2026-08-04 | Pratibha |  |  | 12
[7 empty] | 5.36 | CT Control scheme & Stability Test | 6 | 0 | 6 | 2026-08-25 | 2026-08-25 | Pratibha | 2 | 4 | 12 |  | 26 | 4354.838
[7 empty] | 5.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | 12 | 0 | 12 | 2026-08-11 | 2026-08-11 | Pratibha | 0.5 | 4 | 96
[7 empty] | 5.38 | HT Panel relay test | 16 | 0 | 16 | 2026-08-23 | 2026-08-23 | Pratibha | 6 | 4 | 10.6667
[7 empty] | 5.39 | HT Cable VLF Test | 14 | 0 | 14 | 2026-08-11 | 2026-08-11 | Pratibha | 6 | 5 | 11.6667
[7 empty] | 5.4 | CSS routine test | 1 | 0 | 1 | 2026-08-11 | 2026-08-11 | Pratibha | 1 | 5 | 5
Pratibha: Avg. required manpower - 118 nos | [6 empty] | 5.41 | ACDB routine test | 6 | 0 | 6 | 2026-08-11 | 2026-08-11 | Pratibha | 3 | 5 | 10
[7 empty] | 5.42 | Earthing | 4284 | 0 | 4284 | 2026-08-13 | 2026-08-13 | Pratibha | 150 | 6 | 171.36
[7 empty] | 5.43 | LA | 10 | 0 | 10 | 2026-08-15 | 2026-08-15 | Pratibha | 5 | 6 | 12
CATL | 6 | 09 Aug, 16 Aug | 271 MWh (48 Containers) | 2026-09-02 | 2026-09-07 | 2026-09-10 |  |  |  | Civil
[7 empty] | 6.1 | BCF Precast Erection & Welding | 48 | 48 | 0 | Completed | - | MSC | 1 | 2 | 0
[7 empty] | 6.2 | CT Rail Fixing | 6 | 6 | 0 | Completed | - | MSC | 1 | 16 | 0
[7 empty] | 6.3 | PCS Slab casting | 6 | 6 | 0 | Completed | - | MSC | 1 | 39 | 0
[7 empty] | 6.4 | SGR Slab Casting | 1 | 1 | 0 | Completed | - | MSC | 1 | 37 | 0
[7 empty] | 6.5 | MCR Slab Casting | 1 | 1 | 0 | Completed | - | MSC | 1 | 34 | 0
[7 empty] | 6.6 | CSS Slab Casting | 1 | 1 | 0 | 28 Jun, 02 Jul, 09 Jul, 22 Jul | 2026-07-09 | MSC | 1 | 54 | 0
[7 empty] | 6.7 | BOT Precast Erection | 3 | 3 | 0 | Completed | - | Sachi | 3 | 5 | 0
[7 empty] | 6.8 | NIFPS Precast Erection | 6 | 6 | 0 | Completed | - | MSC | 1 | 5 | 0
[7 empty] | 6.9 | PCS PEB | 6 | 6 | 0 | Completed | - | Synergy | 1 | 27 | 0
[7 empty] | 6.1 | SGR PEB | 1 | 0 | 1 | 05 Jul, 20 Jul, 30 Jul | 05 Jul, 20 Jul, 30 Jul | Synergy | 1 | 25 | 25
[7 empty] | 6.11 | MCR PEB | 1 | 0 | 1 | 05 Jul, 15 Jul, 29 Jul | 05 Jul, 15 Jul, 29 Jul | RV Enterprise | - | - | -
Electrical
[7 empty] | 6.12 | CT Erection | 6 | 6 | 0 | Completed | - | Pratibha | 2 | 4 | 0
[7 empty] | 6.13 | PCS Erection | 48 | 0 | 48 | 2026-08-02 | 2026-08-02 | Pratibha | 10 | 4 | 19.2 | 48 PCS placed on slab, anchoring WIP
[7 empty] | 6.14 | ACDB Erection | 6 | 0 | 6 | 2026-08-05 | 2026-08-05 | Pratibha | 5 | 4 | 4.8
[7 empty] | 6.15 | ECP Panel Erection (Communication Panel) | 6 | 0 | 6 | 2026-08-02 | 2026-08-02 | Pratibha | 20 | 4 | 4
[7 empty] | 6.16 | HT Panel Erection | 2 | 0 | 2 | 02 Jul, 06 Jul, 15 Jul, 27 jul | 2026-07-15 | Pratibha | 10
[7 empty] | 6.17 | EMS Panel Erection | 1 | 0 | 1 | 09 Jul, 18 Jul, 30 Jul | 09 Jul, 18 Jul, 30 Jul | Pratibha | 10
[7 empty] | 6.18 | CSS Erection | 1 | 0 | 1 | 15 Jul, 30 Jul | 2026-07-30 | Pratibha | 10
Testing to be completed by 30 Aug. | [6 empty] | 6.19 | NIFPS Panel Erection | 6 | 0 | 6 | 23 Jul, 30 Jul | 2026-07-30 | Ornet / EMR | 20
[7 empty] | 6.2 | NIFPS Fabrication | 6 | 0 | 6 | 28 Jul, 05 Aug | 2026-08-05 | Ornet / EMR | 0.66667 | 0 | 0
[7 empty] | 6.21 | Battery Container Erection | 48 | 0 | 48 | 14 Aug, 21 Aug | 2026-08-21 | HEFT & Pratibha | 10 | 4 | 19.2
[7 empty] | 6.22 | HT cable laying | 4879.09 | 0 | 4879.09 | 2026-07-31 | 2026-07-31 | Pratibha | 1500 | 48 | 156.1309
[7 empty] | 6.23 | HT cable termination | 28 | 0 | 28 | 2026-08-16 | 2026-08-16 | Pratibha | 8 | 6 | 21
[7 empty] | 6.24 | DC Cable laying | 14288 | 0 | 14288 | 2026-08-06 | 2026-08-06 | Pratibha | 600 | 10 | 238.1333
[7 empty] | 6.25 | LT Cable laying | 47399 | 0 | 47399 | 2026-07-31 | 2026-07-31 | Pratibha | 600 | 10 | 789.9833
[7 empty] | 6.26 | DC Cable termination | 1536 | 0 | 1536 | 2026-08-20 | 2026-08-20 | Pratibha | 30 | 18 | 921.6
[7 empty] | 6.27 | LT Cable termination | 2304 | 0 | 2304 | 2026-08-20 | 2026-08-20 | Pratibha | 30 | 18 | 1382.4
[7 empty] | 6.28 | Aux Cable laying | 8232 | 0 | 8232 | 2026-08-10 | 2026-08-10 | Pratibha | 1000 | 10 | 82.32
[7 empty] | 6.29 | Control Cable laying | 14448 | 0 | 14448 | 2026-08-10 | 2026-08-10 | Pratibha | 1000 | 10 | 144.48
[7 empty] | 6.3 | Communication Cable laying | 4792 | 0 | 4792 | 2026-08-10 | 2026-08-10 | Pratibha | 500 | 10 | 95.84
[7 empty] | 6.31 | Aux Cable termination | 286 | 0 | 286 | 2026-08-20 | 2026-08-20 | Pratibha | 30 | 6 | 57.2
[7 empty] | 6.32 | Control Cable termination | 536 | 0 | 536 | 2026-08-20 | 2026-08-20 | Pratibha & Emerson | 30 | 4 | 71.4667
[7 empty] | 6.33 | Communication Cable termination | 384 | 0 | 384 | 2026-08-20 | 2026-08-20 | Pratibha & Emerson | - | - | - |  | 21 | 4348.4475
[7 empty] | 6.34 | CT SFRA & Tan delta Test | 6 | 0 | 6 | 2026-08-05 | 2026-08-05 | Canbay | 2 | 8 | -
[7 empty] | 6.35 | CT Routine Test | 6 | 0 | 6 | 2026-08-09 | 2026-08-09 | Pratibha |  |  | 12
[7 empty] | 6.36 | CT Control scheme & Stability Test | 6 | 0 | 6 | 2026-08-30 | 2026-08-30 | Pratibha | 2 | 4 | 12 |  | 31 | 4348.4475
[7 empty] | 6.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | 12 | 0 | 12 | 2026-08-16 | 2026-08-16 | Pratibha | 0.5 | 4 | 96
[7 empty] | 6.38 | HT Panel relay test | 16 | 0 | 16 | 2026-08-28 | 2026-08-28 | Pratibha | 6 | 4 | 10.6667
[7 empty] | 6.39 | HT Cable VLF Test | 14 | 0 | 14 | 2026-08-16 | 2026-08-16 | Pratibha | 6 | 5 | 11.6667
[7 empty] | 6.4 | CSS routine test | 1 | 0 | 1 | 2026-08-16 | 2026-08-16 | Pratibha | 1 | 5 | 5
Pratibha: Avg. required manpower - 106 nos | [6 empty] | 6.41 | ACDB routine test | 6 | 0 | 6 | 2026-08-16 | 2026-08-16 | Pratibha | 3 | 5 | 10
[7 empty] | 6.42 | Earthing | 4284 | 0 | 4284 | 2026-08-18 | 2026-08-18 | Pratibha | 150 | 6 | 171.36
[7 empty] | 6.43 | LA | 10 | 0 | 10 | 2026-08-20 | 2026-08-20 | Pratibha | 5 | 6 | 12
CATL | 7 | 19 Aug, 22 Aug | 271 MWh (48 Containers) | 2026-09-12 | 2026-09-17 | 2026-09-20 |  |  |  | Civil
[7 empty] | 7.1 | BCF Precast Erection & Welding | 48 | 48 | 0 | Completed | - | MSC | 1 | 2 | 0
[7 empty] | 7.2 | CT Rail Fixing | 6 | 6 | 0 | Completed | - | MSC | 1 | 16 | 0
[7 empty] | 7.3 | PCS Slab casting | 6 | 6 | 0 | Completed | - | MSC | 1 | 39 | 0
[7 empty] | 7.4 | SGR Slab Casting | 1 | 1 | 0 | Completed | - | MSC | 1 | 37 | 0
[7 empty] | 7.5 | MCR Slab Casting | 1 | 1 | 0 | Completed | - | MSC | 1 | 34 | 0
[7 empty] | 7.6 | CSS Slab Casting | 1 | 1 | 0 | Completed | 2026-07-13 | MSC | 1 | 54 | 0
[7 empty] | 7.7 | BOT Precast Erection | 3 | 3 | 0 | Completed | - | Sachi | 3 | 5 | 0
[7 empty] | 7.8 | NIFPS Precast Erection | 6 | 6 | 0 | Completed | - | MSC | 1 | 5 | 0
[7 empty] | 7.9 | PCS PEB | 6 | 6 | 0 | Completed | - | Synergy | 1 | 27 | 0
[7 empty] | 7.1 | SGR PEB | 1 | 0 | 1 | 10 Jul, 20 Jul, 07 Aug | 10 Jul, 20 Jul, 07 Aug | Synergy | 1 | 25 | 25
[7 empty] | 7.11 | MCR PEB | 1 | 0 | 1 | 11 Jul, 15 Jul, 01 Aug | 11 Jul, 15 Jul, 01 Aug | RV Enterprise | - | - | -
Electrical
[7 empty] | 7.12 | CT Erection | 6 | 0 | 6 | 2026-07-25 | 2026-07-25 | Pratibha | 2 | 4 | 12
[7 empty] | 7.13 | PCS Erection | 48 | 0 | 48 | 2026-07-25 | 2026-07-25 | Pratibha | 10 | 4 | 19.2
[7 empty] | 7.14 | ACDB Erection | 6 | 0 | 6 | 2026-07-30 | 2026-07-30 | Pratibha | 5 | 4 | 4.8
[7 empty] | 7.15 | ECP Panel Erection (Communication Panel) | 6 | 0 | 6 | 2026-07-30 | 2026-07-30 | Pratibha | 20 | 4 | 4
[7 empty] | 7.16 | HT Panel Erection | 2 | 0 | 2 | 2026-08-05 | 2026-08-05 | Pratibha | 10
[7 empty] | 7.17 | EMS Panel Erection | 1 | 0 | 1 | 2026-07-30 | 2026-07-30 | Pratibha | 10
[7 empty] | 7.18 | CSS Erection | 1 | 0 | 1 | 2026-07-20 | 2026-07-20 | Pratibha | 10
Testing to be completed by 9 Sep. | [6 empty] | 7.19 | NIFPS Panel Erection | 6 | 0 | 6 | 27 Jul, 07 Aug | 2026-08-07 | Ornet / EMR | 20
[7 empty] | 7.2 | NIFPS Fabrication | 6 | 0 | 6 | 01 Aug, 12 Aug | 2026-08-12 | Ornet / EMR | 0.66667 | 0 | 0
[7 empty] | 7.21 | Battery Container Erection | 48 | 0 | 48 | 24 Aug, 27 Aug | 2026-08-27 | HEFT & Pratibha | 10 | 4 | 19.2
[7 empty] | 7.22 | HT cable laying | 4445.09 | 0 | 4445.09 | 2026-08-10 | 2026-08-10 | Pratibha | 1500 | 48 | 142.2429
[7 empty] | 7.23 | HT cable termination | 28 | 0 | 28 | 2026-08-26 | 2026-08-26 | Pratibha | 8 | 6 | 21
[7 empty] | 7.24 | DC Cable laying | 14288 | 0 | 14288 | 2026-08-16 | 2026-08-16 | Pratibha | 600 | 10 | 238.1333
[7 empty] | 7.25 | LT Cable laying | 47399 | 0 | 47399 | 2026-08-10 | 2026-08-10 | Pratibha | 600 | 10 | 789.9833
[7 empty] | 7.26 | DC Cable termination | 1536 | 0 | 1536 | 2026-08-30 | 2026-08-30 | Pratibha | 30 | 18 | 921.6
[7 empty] | 7.27 | LT Cable termination | 2304 | 0 | 2304 | 2026-08-30 | 2026-08-30 | Pratibha | 30 | 18 | 1382.4
[7 empty] | 7.28 | Aux Cable laying | 8232 | 0 | 8232 | 2026-08-20 | 2026-08-20 | Pratibha | 1000 | 10 | 82.32
[7 empty] | 7.29 | Control Cable laying | 14448 | 0 | 14448 | 2026-08-20 | 2026-08-20 | Pratibha | 1000 | 10 | 144.48
[7 empty] | 7.3 | Communication Cable laying | 4792 | 0 | 4792 | 2026-08-20 | 2026-08-20 | Pratibha | 500 | 10 | 95.84
[7 empty] | 7.31 | Aux Cable termination | 286 | 0 | 286 | 2026-08-30 | 2026-08-30 | Pratibha | 30 | 6 | 57.2
[7 empty] | 7.32 | Control Cable termination | 536 | 0 | 536 | 2026-08-30 | 2026-08-30 | Pratibha & Emerson | 30 | 4 | 71.4667
[7 empty] | 7.33 | Communication Cable termination | 384 | 0 | 384 | 2026-08-30 | 2026-08-30 | Pratibha & Emerson | - | - | - |  | 31 | 4346.5595
[7 empty] | 7.34 | CT SFRA & Tan delta Test | 6 | 0 | 6 | 2026-08-15 | 2026-08-15 | Canbay | 2 | 8 | -
[7 empty] | 7.35 | CT Routine Test | 6 | 0 | 6 | 2026-08-19 | 2026-08-19 | Pratibha |  |  | 12
[7 empty] | 7.36 | CT Control scheme & Stability Test | 6 | 0 | 6 | 2026-09-09 | 2026-09-09 | Pratibha | 2 | 4 | 12 |  | 41 | 4346.5595
[7 empty] | 7.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | 12 | 0 | 12 | 2026-08-26 | 2026-08-26 | Pratibha | 0.5 | 4 | 96
[7 empty] | 7.38 | HT Panel relay test | 16 | 0 | 16 | 2026-09-07 | 2026-09-07 | Pratibha | 6 | 4 | 10.6667
[7 empty] | 7.39 | HT Cable VLF Test | 14 | 0 | 14 | 2026-08-26 | 2026-08-26 | Pratibha | 6 | 5 | 11.6667
[7 empty] | 7.4 | CSS routine test | 1 | 0 | 1 | 2026-08-26 | 2026-08-26 | Pratibha | 1 | 5 | 5
Pratibha: Avg. required manpower - 117 nos | [6 empty] | 7.41 | ACDB routine test | 6 | 0 | 6 | 2026-08-26 | 2026-08-26 | Pratibha | 3 | 5 | 10
[7 empty] | 7.42 | Earthing | 4284 | 0 | 4284 | 2026-08-28 | 2026-08-28 | Pratibha | 150 | 6 | 171.36
[7 empty] | 7.43 | LA | 10 | 0 | 10 | 2026-08-30 | 2026-08-30 | Pratibha | 5 | 6 | 12
CATL | 8 | 21 Aug, 24 Aug | 271 MWh (48 Containers) | 2026-09-14 | 2026-09-19 | 2026-09-22 |  |  |  | Civil
[7 empty] | 8.1 | BCF Precast Erection & Welding | 48 | 48 | 0 | Completed | - | MSC | 1 | 2 | 0
[7 empty] | 8.2 | CT Rail Fixing | 6 | 6 | 0 | Completed | - | MSC | 1 | 16 | 0
[7 empty] | 8.3 | PCS Slab casting | 6 | 6 | 0 | Completed | 2026-07-09 | MSC | 1 | 39 | 0
[7 empty] | 8.4 | SGR Slab Casting | 1 | 1 | 0 | Completed | 2026-07-09 | MSC | 1 | 37 | 0
[7 empty] | 8.5 | MCR Slab Casting | 1 | 1 | 0 | Completed | - | MSC | 1 | 34 | 0
[7 empty] | 8.6 | CSS Slab Casting | 1 | 1 | 0 | 25-Jun, 04 Jul, 11 Jul, 22 Jul | 2026-07-11 | MSC | 1 | 54 | 0
[7 empty] | 8.7 | BOT Precast Erection | 3 | 3 | 0 | Completed | - | Sachi | 3 | 5 | 0
[7 empty] | 8.8 | NIFPS Precast Erection | 6 | 6 | 0 | Completed | - | MSC | 1 | 5 | 0
[7 empty] | 8.9 | PCS PEB | 6 | 0 | 6 | 15 Jul, 31 Jul | 2026-07-31 | Synergy | 1 | 27 | 162
[7 empty] | 8.1 | SGR PEB | 1 | 0 | 1 | 15 Jul, 07 Aug | 2026-08-07 | Synergy | 1 | 25 | 25
[7 empty] | 8.11 | MCR PEB | 1 | 0 | 1 | 15 Jul, 04 Aug | 2026-08-04 | RV Enterprise | - | - | -
Electrical
[7 empty] | 8.12 | CT Erection | 6 | 0 | 6 | 2026-07-30 | 2026-07-30 | Pratibha | 2 | 4 | 12
[7 empty] | 8.13 | PCS Erection | 48 | 0 | 48 | 2026-08-05 | 2026-08-05 | Pratibha | 10 | 4 | 19.2
[7 empty] | 8.14 | ACDB Erection | 6 | 0 | 6 | 2026-08-06 | 2026-08-06 | Pratibha | 5 | 4 | 4.8
[7 empty] | 8.15 | ECP Panel Erection (Communication Panel) | 6 | 0 | 6 | 2026-08-06 | 2026-08-06 | Pratibha | 20 | 4 | 4
[7 empty] | 8.16 | HT Panel Erection | 2 | 0 | 2 | 2026-08-05 | 2026-08-05 | Pratibha | 10
[7 empty] | 8.17 | EMS Panel Erection | 1 | 0 | 1 | 2026-07-31 | 2026-07-31 | Pratibha | 10
[7 empty] | 8.18 | CSS Erection | 1 | 0 | 1 | 2026-08-10 | 2026-08-10 | Pratibha | 10
Testing to be completed by 11 Sep. | [6 empty] | 8.19 | NIFPS Panel Erection | 6 | 0 | 6 | 31 Jul, 15 Aug | 2026-08-15 | Ornet / EMR | 20
[7 empty] | 8.2 | NIFPS Fabrication | 6 | 0 | 6 | 05 Aug, 20 Aug | 2026-08-20 | Ornet / EMR | 0.66667 | 0 | 0
[7 empty] | 8.21 | Battery Container Erection | 48 | 0 | 48 | 26 Aug, 29 Aug | 2026-08-29 | HEFT & Pratibha | 10 | 4 | 19.2
[7 empty] | 8.22 | HT cable laying | 3549.12 | 0 | 3549.12 | 2026-08-12 | 2026-08-12 | Pratibha | 1500 | 48 | 113.5718
[7 empty] | 8.23 | HT cable termination | 28 | 0 | 28 | 2026-08-28 | 2026-08-28 | Pratibha | 8 | 6 | 21
[7 empty] | 8.24 | DC Cable laying | 14288 | 0 | 14288 | 2026-08-18 | 2026-08-18 | Pratibha | 600 | 10 | 238.1333
[7 empty] | 8.25 | LT Cable laying | 47399 | 0 | 47399 | 2026-08-12 | 2026-08-12 | Pratibha | 600 | 10 | 789.9833
[7 empty] | 8.26 | DC Cable termination | 1536 | 0 | 1536 | 2026-09-01 | 2026-09-01 | Pratibha | 30 | 18 | 921.6
[7 empty] | 8.27 | LT Cable termination | 2304 | 0 | 2304 | 2026-09-01 | 2026-09-01 | Pratibha | 30 | 18 | 1382.4
[7 empty] | 8.28 | Aux Cable laying | 8232 | 0 | 8232 | 2026-08-22 | 2026-08-22 | Pratibha | 1000 | 10 | 82.32
[7 empty] | 8.29 | Control Cable laying | 14448 | 0 | 14448 | 2026-08-22 | 2026-08-22 | Pratibha | 1000 | 10 | 144.48
[7 empty] | 8.3 | Communication Cable laying | 4792 | 0 | 4792 | 2026-08-22 | 2026-08-22 | Pratibha | 500 | 10 | 95.84
[7 empty] | 8.31 | Aux Cable termination | 286 | 0 | 286 | 2026-09-01 | 2026-09-01 | Pratibha | 30 | 6 | 57.2
[7 empty] | 8.32 | Control Cable termination | 536 | 0 | 536 | 2026-09-01 | 2026-09-01 | Pratibha & Emerson | 30 | 4 | 71.4667
[7 empty] | 8.33 | Communication Cable termination | 384 | 0 | 384 | 2026-09-01 | 2026-09-01 | Pratibha & Emerson | - | - | - |  | 33 | 4317.8885
[7 empty] | 8.34 | CT SFRA & Tan delta Test | 6 | 0 | 6 | 2026-08-17 | 2026-08-17 | Canbay | 2 | 8 | -
[7 empty] | 8.35 | CT Routine Test | 6 | 0 | 6 | 2026-08-21 | 2026-08-21 | Pratibha |  |  | 12
[7 empty] | 8.36 | CT Control scheme & Stability Test | 6 | 0 | 6 | 2026-09-11 | 2026-09-11 | Pratibha | 2 | 4 | 12 |  | 43 | 4317.8885
[7 empty] | 8.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | 12 | 0 | 12 | 2026-08-28 | 2026-08-28 | Pratibha | 0.5 | 4 | 96
[7 empty] | 8.38 | HT Panel relay test | 16 | 0 | 16 | 2026-09-09 | 2026-09-09 | Pratibha | 6 | 4 | 10.6667
[7 empty] | 8.39 | HT Cable VLF Test | 14 | 0 | 14 | 2026-08-28 | 2026-08-28 | Pratibha | 6 | 5 | 11.6667
[7 empty] | 8.4 | CSS routine test | 1 | 0 | 1 | 2026-08-28 | 2026-08-28 | Pratibha | 1 | 5 | 5
Pratibha: Avg. required manpower - 111 nos | [6 empty] | 8.41 | ACDB routine test | 6 | 0 | 6 | 2026-08-28 | 2026-08-28 | Pratibha | 3 | 5 | 10
[7 empty] | 8.42 | Earthing | 4284 | 0 | 4284 | 2026-08-30 | 2026-08-30 | Pratibha | 150 | 6 | 171.36
[7 empty] | 8.43 | LA | 10 | 0 | 10 | 2026-09-01 | 2026-09-01 | Pratibha | 5 | 6 | 12
CATL | 9 | 22 Aug, 26 Aug | 271 MWh (48 Containers) | 2026-09-15 | 2026-09-20 | 2026-09-23 |  |  |  | Civil
[7 empty] | 9.1 | BCF Precast Erection & Welding | 48 | 48 | 0 | Completed | - | MSC | 1 | 2 | 0
[7 empty] | 9.2 | CT Rail Fixing | 6 | 0 | 6 | 30-Jun, 06 Jul, 15 Jul, 28 Jul | 2026-07-15 | MSC | 1 | 16 | 96
[7 empty] | 9.3 | PCS Slab casting | 6 | 3 | 3 | 05 Jul, 08 Jul, 20 Jul, 28 Jul | 2026-07-20 | MSC | 1 | 39 | 117
[7 empty] | 9.4 | SGR Slab Casting | 1 | 0 | 1 | 03 Jul, 10 Jul, 18 Jul, 28 Jul | 2026-07-18 | MSC | 1 | 37 | 37
[7 empty] | 9.5 | MCR Slab Casting | 1 | 0 | 1 | 07 Jul, 18 Jul, 28 Jul | 07 Jul, 18 Jul, 28 Jul | MSC | 1 | 34 | 34
[7 empty] | 9.6 | CSS Slab Casting | 1 | 0 | 1 | 10 Jul, 20 Jul, 28 Jul | 10 Jul, 20 Jul, 28 Jul | MSC | 1 | 54 | 54
[7 empty] | 9.7 | BOT Precast Erection | 3 | 3 | 0 | Completed | - | Sachi | 3 | 5 | 0
[7 empty] | 9.8 | NIFPS Precast Erection | 6 | 0 | 6 | 30 Jun, 03 Jul, 15 Jul, 28 Jul | 2026-07-15 | MSC | 1 | 5 | 30
[7 empty] | 9.9 | PCS PEB | 6 | 0 | 6 | 16 Jul, 08 Aug | 2026-08-08 | Synergy | 1 | 27 | 162
[7 empty] | 9.1 | SGR PEB | 1 | 0 | 1 | 16 Jul, 17 Aug | 2026-08-17 | Synergy | 1 | 25 | 25
[7 empty] | 9.11 | MCR PEB | 1 | 0 | 1 | 21 Jul, 07 Aug | 2026-08-07 | RV Enterprise | - | - | -
Electrical
[7 empty] | 9.12 | CT Erection | 6 | 0 | 6 | 2026-08-15 | 2026-08-15 | Pratibha | 2 | 8 | 24
[7 empty] | 9.13 | PCS Erection | 48 | 0 | 48 | 2026-08-15 | 2026-08-15 | Pratibha | 10 | 8 | 38.4
[7 empty] | 9.14 | ACDB Erection | 6 | 0 | 6 | 2026-08-18 | 2026-08-18 | Pratibha | 5 | 4 | 4.8
[7 empty] | 9.15 | ECP Panel Erection (Communication Panel) | 6 | 0 | 6 | 2026-08-15 | 2026-08-15 | Pratibha | 20 | 8 | 4
[7 empty] | 9.16 | HT Panel Erection | 2 | 0 | 2 | 2026-08-15 | 2026-08-15 | Pratibha | 10
[7 empty] | 9.17 | EMS Panel Erection | 1 | 0 | 1 | 2026-08-22 | 2026-08-22 | Pratibha | 10
[7 empty] | 9.18 | CSS Erection | 1 | 0 | 1 | 2026-08-22 | 2026-08-22 | Pratibha | 10
Testing to be completed by 12 Sep. | [6 empty] | 9.19 | NIFPS Panel Erection | 6 | 0 | 6 | 04 Jul, 20 Aug | 2026-08-20 | Ornet / EMR | 20
[7 empty] | 9.2 | NIFPS Fabrication | 6 | 0 | 6 | 09 Aug, 25 Aug | 2026-08-25 | Ornet / EMR | 0.66667 | 0 | 0
[7 empty] | 9.21 | Battery Container Erection | 48 | 0 | 48 | 27 Aug, 31 Aug | 2026-08-31 | HEFT & Pratibha | 10 | 4 | 19.2
[7 empty] | 9.22 | HT cable laying | 4518.48 | 0 | 4518.48 | 2026-08-13 | 2026-08-13 | Pratibha | 1500 | 48 | 144.5914
[7 empty] | 9.23 | HT cable termination | 28 | 0 | 28 | 2026-08-29 | 2026-08-29 | Pratibha | 8 | 6 | 21
[7 empty] | 9.24 | DC Cable laying | 14288 | 0 | 14288 | 2026-08-19 | 2026-08-19 | Pratibha | 600 | 10 | 238.1333
[7 empty] | 9.25 | LT Cable laying | 47492 | 0 | 47492 | 2026-08-13 | 2026-08-13 | Pratibha | 600 | 10 | 791.5333
[7 empty] | 9.26 | DC Cable termination | 1536 | 0 | 1536 | 2026-09-02 | 2026-09-02 | Pratibha | 30 | 18 | 921.6
[7 empty] | 9.27 | LT Cable termination | 2304 | 0 | 2304 | 2026-09-02 | 2026-09-02 | Pratibha | 30 | 18 | 1382.4
[7 empty] | 9.28 | Aux Cable laying | 8232 | 0 | 8232 | 2026-08-23 | 2026-08-23 | Pratibha | 800 | 10 | 102.9
[7 empty] | 9.29 | Control Cable laying | 14448 | 0 | 14448 | 2026-08-23 | 2026-08-23 | Pratibha | 1000 | 10 | 144.48
[7 empty] | 9.3 | Communication Cable laying | 4792 | 0 | 4792 | 2026-08-23 | 2026-08-23 | Pratibha | 500 | 10 | 95.84
[7 empty] | 9.31 | Aux Cable termination | 286 | 0 | 286 | 2026-09-02 | 2026-09-02 | Pratibha | 30 | 6 | 57.2
[7 empty] | 9.32 | Control Cable termination | 536 | 0 | 536 | 2026-09-02 | 2026-09-02 | Pratibha & Emerson | 30 | 4 | 71.4667
[7 empty] | 9.33 | Communication Cable termination | 384 | 0 | 384 | 2026-09-02 | 2026-09-02 | Pratibha & Emerson | - | - | - |  | 34 | 4402.238
[7 empty] | 9.34 | CT SFRA & Tan delta Test | 6 | 0 | 6 | 2026-08-18 | 2026-08-18 | Canbay | 2 | 8 | -
[7 empty] | 9.35 | CT Routine Test | 6 | 0 | 6 | 2026-08-22 | 2026-08-22 | Pratibha |  |  | 12
[7 empty] | 9.36 | CT Control scheme & Stability Test | 6 | 0 | 6 | 2026-09-12 | 2026-09-12 | Pratibha | 2 | 4 | 12 |  | 44 | 4402.238
[7 empty] | 9.37 | HT Panel Routine (CT & PT, Breaker & Meter) Test | 12 | 0 | 12 | 2026-08-29 | 2026-08-29 | Pratibha | 0.5 | 4 | 96
[7 empty] | 9.38 | HT Panel relay test | 16 | 0 | 16 | 2026-09-10 | 2026-09-10 | Pratibha | 6 | 4 | 10.6667
[7 empty] | 9.39 | HT Cable VLF Test | 14 | 0 | 14 | 2026-08-29 | 2026-08-29 | Pratibha | 6 | 5 | 11.6667
[7 empty] | 9.4 | CSS routine test | 1 | 0 | 1 | 2026-08-29 | 2026-08-29 | Pratibha | 1 | 5 | 5
Pratibha: Avg. required manpower - 112 nos | [6 empty] | 9.41 | ACDB routine test | 6 | 0 | 6 | 2026-08-29 | 2026-08-29 | Pratibha | 3 | 5 | 10
[7 empty] | 9.42 | Earthing | 4284 | 0 | 4284 | 2026-08-31 | 2026-08-31 | Pratibha | 150 | 6 | 171.36
[7 empty] | 9.43 | LA | 10 | 0 | 10 | 2026-09-02 | 2026-09-02 | Pratibha | 5 | 6 | 12
Assumptions:-
1. Ship berthing + 72 hrs - clearing of 30 containers per day for site
2. 30 containers erected on site on 4th day
3. IDT charging = 24 days from erection of last container in the block
4. Trial run start date = IDT charging + 3 days
5. Trial run end date = Trial run start date + 2 days
6. COD = Trial run end date + 2 days
Formulas:
New EDC = IFERROR(DATEVALUE(TRIM(TEXTAFTER([EDC],",",-1))&"-"&YEAR(TODAY())),[EDC])

## 11 - Daily requirement (3)
PSS-11 | [9 empty] | 2026-06-23
| IDT Charging / Commissioning Start | Trial-Run End Date | COD | Activity | Mandays | Start date | End Date | Days | Avg Manpower + 20% Buffer | Avg Manpower | Peak Manpower | [135 empty] | 2026-12-26 | 2026-12-27 | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31 | time axis 2026-06-22 to 2026-11-01
Block 4 | 2026-07-28 | 2026-08-02 | 2026-08-05 | Erection | 0 | 2026-07-30 | 2026-07-30 | 0 | 10 | 8.3333 | 30 | bar: 2026-06-22 to 2026-11-01
|  |  |  | Cable Laying | 0 | 2026-07-30 | 2026-07-30 | 0 | bar: 2026-06-22 to 2026-11-01
|  |  |  | Termination | 0 | 2026-07-31 | 2026-07-31 | 0 | bar: 2026-06-22 to 2026-11-01
|  |  |  | Testing | 0.004 | 2026-07-30 | 2026-07-30 | 0 | bar: 2026-06-22 to 2026-11-01
|  |  |  | CFT | 250 |  | 2026-07-25 | 30 |  |  |  | 2026-07-02: 5; 2026-07-03: 5; 2026-07-04: 5; 2026-07-05: 5; 2026-07-06: 5; 2026-07-07: 5; 2026-07-08: 5; 2026-07-09: 5; 2026-07-10: 5; 2026-07-11: 5; 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 30; 2026-07-27: 30; 2026-07-28: 30; 2026-07-29: 30; 2026-07-30: 5; 2026-07-31: 5
[6 empty] | Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 30
Block 3 | 2026-08-06 | 2026-08-10 | 2026-08-13 | Activity | Mandays | Start date | End Date | Days |  | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-11-01
|  |  |  | Erection | 4 | 2026-07-30 | 2026-07-30 | 0 | 17.7 | 14.75 | 66 | bar: 2026-06-22 to 2026-11-01
|  |  |  | Cable Laying | 155.21 | 2026-07-30 | 2026-07-30 | 0 | bar: 2026-06-22 to 2026-11-01
|  |  |  | Termination | 127.0667 | 2026-07-31 | 2026-08-20 | 20 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 221.6667 | 2026-07-30 | 2026-08-03 | 4 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 55 | 55 | 55 | 55 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | 2026-08-03 | 30 |  |  |  | 2026-07-11: 5; 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 5; 2026-08-04: 30; 2026-08-05: 30; 2026-08-06: 30; 2026-08-07: 30; 2026-08-08: 5; 2026-08-09: 5
[6 empty] | Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 60 | 66 | 66 | 66 | 11 | 36 | 36 | 36 | 36 | 11 | 11 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4048 | 66
Block 2 | 2026-08-06 | 2026-08-11 | 2026-08-14 | Activity | Mandays | Start date | End Date | Days |  | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-11-01
|  |  |  | Erection | 4 | 2026-07-30 | 2026-07-25 | -5 | 119.88 | 99.9 | 658 | bar: 2026-06-22 to 2026-11-01
|  |  |  | Cable Laying | 251.3 | 2026-07-30 | 2026-07-30 | 0 | bar: 2026-06-22 to 2026-11-01
|  |  |  | Termination | 2431.0667 | 2026-07-30 | 2026-08-03 | 4 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 608 | 608 | 608 | 608 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 317.8133 | 2026-07-30 | 2026-08-06 | 7 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 45 | 45 | 45 | 45 | 45 | 45 | 45 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | 2026-08-03 | 30 |  |  |  | 2026-07-11: 5; 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 5; 2026-08-04: 30; 2026-08-05: 30; 2026-08-06: 30; 2026-08-07: 30; 2026-08-08: 5; 2026-08-09: 5
[6 empty] | Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 658 | 658 | 658 | 658 | 50 | 75 | 75 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.7647 | 658
Block 1 | 2026-08-09 | 2026-08-14 | 2026-08-17 | Activity | Mandays | Start date | End Date | Days |  | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-11-01
|  |  |  | Erection | 4 | 2026-07-30 | 2026-07-31 | 1 | 109.6667 | 91.3889 | 232 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 4 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | 277.83 | 2026-07-30 | 2026-08-03 | 4 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 69 | 69 | 69 | 69 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | 2432.6667 | 2026-07-30 | 2026-08-19 | 20 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 323.4133 | 2026-07-30 | 2026-08-09 | 10 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | 2026-08-06 | 30 |  |  |  | 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 5; 2026-08-04: 5; 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 30; 2026-08-08: 30; 2026-08-09: 30; 2026-08-10: 30; 2026-08-11: 5; 2026-08-12: 5
[6 empty] | Total | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 232 | 228 | 228 | 228 | 159 | 159 | 159 | 159 | 184 | 184 | 152 | 152 | 127 | 127 | 122 | 122 | 122 | 122 | 122 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.8679 | 232
Block 5 | 2026-09-14 | 2026-09-19 | 2026-09-22 | Activity | Mandays | Start date | End Date | Days |  | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-11-01
|  |  |  | Erection | 47.2 | 2026-08-19 | 2026-08-29 | 10 | 135.0439 | 112.5366 | 157 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | 1513.278 | 2026-07-30 | 2026-08-10 | 11 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | 2453.6667 | 2026-08-20 | 2026-09-09 | 20 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 340.6933 | 2026-08-28 | 2026-09-11 | 14 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | 2026-09-11 | 30 |  |  |  | 2026-08-19: 5; 2026-08-20: 5; 2026-08-21: 5; 2026-08-22: 5; 2026-08-23: 5; 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 5; 2026-08-29: 5; 2026-08-30: 5; 2026-08-31: 5; 2026-09-01: 5; 2026-09-02: 5; 2026-09-03: 5; 2026-09-04: 5; 2026-09-05: 5; 2026-09-06: 5; 2026-09-07: 5; 2026-09-08: 5; 2026-09-09: 5; 2026-09-10: 5; 2026-09-11: 5; 2026-09-12: 30; 2026-09-13: 30; 2026-09-14: 30; 2026-09-15: 30; 2026-09-16: 5; 2026-09-17: 5
[6 empty] | Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 157 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 29 | 29 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.5246 | 157
Block 6 | 2026-09-23 | 2026-09-27 | 2026-09-30 | Activity | Mandays | Start date | End Date | Days |  | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-11-01
|  |  |  | Erection | 47.2 | 2026-08-05 | 2026-09-10 | 36 | 93.1932 | 77.661 | 224 | bar: 2026-06-22 to 2026-11-01
|  |  |  | Cable Laying | 1506.8875 | 2026-07-30 | 2026-08-14 | 15 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | 2453.6667 | 2026-08-06 | 2026-08-26 | 20 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 340.6933 | 2026-09-07 | 2026-09-21 | 14 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | 2026-09-20 | 30 |  |  |  | 2026-08-28: 5; 2026-08-29: 5; 2026-08-30: 5; 2026-08-31: 5; 2026-09-01: 5; 2026-09-02: 5; 2026-09-03: 5; 2026-09-04: 5; 2026-09-05: 5; 2026-09-06: 5; 2026-09-07: 5; 2026-09-08: 5; 2026-09-09: 5; 2026-09-10: 5; 2026-09-11: 5; 2026-09-12: 5; 2026-09-13: 5; 2026-09-14: 5; 2026-09-15: 5; 2026-09-16: 5; 2026-09-17: 5; 2026-09-18: 5; 2026-09-19: 5; 2026-09-20: 5; 2026-09-21: 30; 2026-09-22: 30; 2026-09-23: 30; 2026-09-24: 30; 2026-09-25: 5; 2026-09-26: 5
[6 empty] | Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 101 | 224 | 224 | 224 | 224 | 224 | 224 | 224 | 224 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 1 | 1 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 30 | 30 | 30 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block 7 | 2026-09-23 | 2026-09-27 | 2026-09-30 | Activity | Mandays | Start date | End Date | Days |  | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-11-01
|  |  |  | Erection | 59.2 | 2026-08-31 | 2026-09-10 | 10 | 110.544 | 92.12 | 158 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | 1492.9995 | 2026-07-31 | 2026-08-20 | 20 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | 2453.6667 | 2026-09-01 | 2026-09-21 | 20 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 340.6933 | 2026-09-07 | 2026-09-21 | 14 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | 2026-09-20 | 30 |  |  |  | 2026-08-28: 5; 2026-08-29: 5; 2026-08-30: 5; 2026-08-31: 5; 2026-09-01: 5; 2026-09-02: 5; 2026-09-03: 5; 2026-09-04: 5; 2026-09-05: 5; 2026-09-06: 5; 2026-09-07: 5; 2026-09-08: 5; 2026-09-09: 5; 2026-09-10: 5; 2026-09-11: 5; 2026-09-12: 5; 2026-09-13: 5; 2026-09-14: 5; 2026-09-15: 5; 2026-09-16: 5; 2026-09-17: 5; 2026-09-18: 5; 2026-09-19: 5; 2026-09-20: 5; 2026-09-21: 30; 2026-09-22: 30; 2026-09-23: 30; 2026-09-24: 30; 2026-09-25: 5; 2026-09-26: 5
[6 empty] | Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 11 | 134 | 134 | 134 | 134 | 134 | 134 | 158 | 158 | 158 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block 8 | 2026-09-23 | 2026-09-27 | 2026-09-30 | Activity | Mandays | Start date | End Date | Days |  | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-11-01
|  |  |  | Erection | 59.2 | 2026-09-03 | 2026-09-10 | 7 | 105.6 | 88 | 160 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 8 | 8 | 8 | 8 | 8 | 8 | 8 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | 1464.3285 | 2026-07-31 | 2026-08-22 | 22 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | 2453.6667 | 2026-09-04 | 2026-09-24 | 20 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 340.6933 | 2026-09-07 | 2026-09-21 | 14 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | 2026-09-20 | 30 |  |  |  | 2026-08-28: 5; 2026-08-29: 5; 2026-08-30: 5; 2026-08-31: 5; 2026-09-01: 5; 2026-09-02: 5; 2026-09-03: 5; 2026-09-04: 5; 2026-09-05: 5; 2026-09-06: 5; 2026-09-07: 5; 2026-09-08: 5; 2026-09-09: 5; 2026-09-10: 5; 2026-09-11: 5; 2026-09-12: 5; 2026-09-13: 5; 2026-09-14: 5; 2026-09-15: 5; 2026-09-16: 5; 2026-09-17: 5; 2026-09-18: 5; 2026-09-19: 5; 2026-09-20: 5; 2026-09-21: 30; 2026-09-22: 30; 2026-09-23: 30; 2026-09-24: 30; 2026-09-25: 5; 2026-09-26: 5
[6 empty] | Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 13 | 136 | 136 | 136 | 160 | 160 | 160 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 153 | 153 | 153 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block 9 | 2026-09-23 | 2026-09-27 | 2026-09-30 | Activity | Mandays | Start date | End Date | Days |  | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-11-01
|  |  |  | Erection | 90.4 | 2026-09-03 | 2026-09-10 | 7 | 105.3962 | 87.8302 | 165 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 13 | 13 | 13 | 13 | 13 | 13 | 13 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | 1517.478 | 2026-07-31 | 2026-08-23 | 23 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | 2453.6667 | 2026-09-04 | 2026-09-24 | 20 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | 340.6933 | 2026-09-07 | 2026-09-21 | 14 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | 2026-09-20 | 30 |  |  |  | 2026-08-28: 5; 2026-08-29: 5; 2026-08-30: 5; 2026-08-31: 5; 2026-09-01: 5; 2026-09-02: 5; 2026-09-03: 5; 2026-09-04: 5; 2026-09-05: 5; 2026-09-06: 5; 2026-09-07: 5; 2026-09-08: 5; 2026-09-09: 5; 2026-09-10: 5; 2026-09-11: 5; 2026-09-12: 5; 2026-09-13: 5; 2026-09-14: 5; 2026-09-15: 5; 2026-09-16: 5; 2026-09-17: 5; 2026-09-18: 5; 2026-09-19: 5; 2026-09-20: 5; 2026-09-21: 30; 2026-09-22: 30; 2026-09-23: 30; 2026-09-24: 30; 2026-09-25: 5; 2026-09-26: 5
[6 empty] | Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 18 | 141 | 141 | 141 | 165 | 165 | 165 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 153 | 153 | 153 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Total of all blocks |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 15 | 15 | 15 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 45 | 45 | 45 | 45 | 1193 | 1403 | 1398 | 1398 | 666 | 716 | 717 | 795 | 820 | 770 | 738 | 590 | 565 | 565 | 560 | 460 | 460 | 460 | 460 | 460 | 348 | 390 | 390 | 323 | 257 | 257 | 257 | 134 | 134 | 178 | 173 | 173 | 179 | 302 | 302 | 323 | 569 | 569 | 569 | 665 | 665 | 542 | 514 | 490 | 515 | 515 | 515 | 515 | 490 | 490 | 485 | 485 | 485 | 366 | 366 | 366 | 120 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Avg. |  |  |  | 2026-06-22: 226.7669; 2026-06-23: 272.1203
[8 empty] | Peak |  |  |  | 2026-06-22: 1403; 2026-06-23: 1683.6

## 12 - Daily requirement work (2)
PSS-12 | [9 empty] | 2026-06-23
| IDT Charging / Commissioning Start | Trial-Run End Date | COD | Activity | Mandays | Start Date | End Date | Days | Avg Manpower + 20% Buffer | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-12-31
Block 1 | 2026-07-28 | 2026-08-02 | 2026-08-05 | Erection | #VALUE! | 2026-07-30 | 2026-07-30 | 0 | 10 | 8.3333 | 30 | bar: 2026-06-22 to 2026-10-13
|  |  |  | Cable Laying | #VALUE! | 2026-07-30 | 2026-07-30 | 0 | bar: 2026-06-22 to 2026-10-13
|  |  |  | Termination | #VALUE! | 2026-07-30 | 2026-07-30 | 0 | bar: 2026-06-22 to 2026-10-13
|  |  |  | Testing | #VALUE! | 2026-07-30 | 2026-07-30 | 0 | bar: 2026-06-22 to 2026-10-13
|  |  |  | CFT | 250 |  | 2026-07-25 | 30 |  |  |  | 2026-07-02: 5; 2026-07-03: 5; 2026-07-04: 5; 2026-07-05: 5; 2026-07-06: 5; 2026-07-07: 5; 2026-07-08: 5; 2026-07-09: 5; 2026-07-10: 5; 2026-07-11: 5; 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 30; 2026-07-27: 30; 2026-07-28: 30; 2026-07-29: 30; 2026-07-30: 5; 2026-07-31: 5
[6 empty] | Total | [5 empty] | 2026-06-22: 0; 2026-06-23: 0; 2026-06-24: 0; 2026-06-25: 0; 2026-06-26: 0; 2026-06-27: 0; 2026-06-28: 0; 2026-06-29: 0; 2026-06-30: 0; 2026-07-01: 0; 2026-07-02: 5; 2026-07-03: 5; 2026-07-04: 5; 2026-07-05: 5; 2026-07-06: 5; 2026-07-07: 5; 2026-07-08: 5; 2026-07-09: 5; 2026-07-10: 5; 2026-07-11: 5; 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 30; 2026-07-27: 30; 2026-07-28: 30; 2026-07-29: 30; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 0; 2026-08-02: 0; 2026-08-03: 0; 2026-08-04: 0; 2026-08-05: 0; 2026-08-06: 0; 2026-08-07: 0; 2026-08-08: 0; 2026-08-09: 0; 2026-08-10: 0; 2026-08-11: 0; 2026-08-12: 0; 2026-08-13: 0; 2026-08-14: 0; 2026-08-15: 0; 2026-08-16: 0; 2026-08-17: 0; 2026-08-18: 0; 2026-08-19: 0; 2026-08-20: 0; 2026-08-21: 0; 2026-08-22: 0; 2026-08-23: 0; 2026-08-24: 0; 2026-08-25: 0; 2026-08-26: 0; 2026-08-27: 0; 2026-08-28: 0; 2026-08-29: 0; 2026-08-30: 0; 2026-08-31: 0; 2026-09-01: 0; 2026-09-02: 0; 2026-09-03: 0; 2026-09-04: 0; 2026-09-05: 0; 2026-09-06: 0; 2026-09-07: 0; 2026-09-08: 0; 2026-09-09: 0; 2026-09-10: 0; 2026-09-11: 0; 2026-09-12: 0; 2026-09-13: 0; 2026-09-14: 0; 2026-09-15: 0; 2026-09-16: 0; 2026-09-17: 0; 2026-09-18: 0; 2026-09-19: 0; 2026-09-20: 0; 2026-09-21: 0; 2026-09-22: 0; 2026-09-23: 0; 2026-09-24: 0; 2026-09-25: 0; 2026-09-26: 0; 2026-09-27: 0; 2026-09-28: 0; 2026-09-29: 0; 2026-09-30: 0; 2026-10-01: 0; 2026-10-02: 0; 2026-10-03: 0; 2026-10-04: 0; 2026-10-05: 0; 2026-10-06: 0; 2026-10-07: 0; 2026-10-08: 0; 2026-10-09: 0; 2026-10-10: 0; 2026-10-11: 0; 2026-10-12: 0; 2026-10-13: 0
Block 2 | 2026-08-02 | 2026-08-07 | 2026-08-10 | Activity | Mandays | Start date | Max dates | Days |  | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-10-13
|  |  |  | Erection | #VALUE! | 2026-07-30 | 2026-07-30 | 0 | 6 | 5 | #VALUE! | bar: 2026-06-22 to 2026-10-13
|  |  |  | Cable Laying | #VALUE! | 2026-07-30 | 2026-07-30 | 0 | bar: 2026-06-22 to 2026-10-13
|  |  |  | Termination | #VALUE! | 2026-07-30 | 2026-08-31 | 32 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 2026-07-30 | 2026-08-02 | 3 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | 2026-07-30 | 30 |  |  |  | 2026-07-07: 5; 2026-07-08: 5; 2026-07-09: 5; 2026-07-10: 5; 2026-07-11: 5; 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 30; 2026-08-01: 30; 2026-08-02: 30; 2026-08-03: 30; 2026-08-04: 5; 2026-08-05: 5
[6 empty] | Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block 4 | 2026-07-28 | 2026-08-02 | 2026-08-05 | Activity | Mandays | Start date | Max dates | Days |  | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-10-13
|  |  |  | Erection | #VALUE! | 2026-07-30 | 2026-07-30 | 0 | 10 | 8.3333 | 30 | bar: 2026-06-22 to 2026-10-13
|  |  |  | Cable Laying | #VALUE! | 2026-07-30 | 2026-07-30 | 0 | bar: 2026-06-22 to 2026-10-13
|  |  |  | Termination | #VALUE! | 2026-07-30 | 2026-07-30 | 0 | bar: 2026-06-22 to 2026-10-13
|  |  |  | Testing | #VALUE! | 2026-07-30 | 2026-07-30 | 0 | bar: 2026-06-22 to 2026-10-13
|  |  |  | CFT | 250 |  | 2026-07-25 | 30 |  |  |  | 2026-07-02: 5; 2026-07-03: 5; 2026-07-04: 5; 2026-07-05: 5; 2026-07-06: 5; 2026-07-07: 5; 2026-07-08: 5; 2026-07-09: 5; 2026-07-10: 5; 2026-07-11: 5; 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 30; 2026-07-27: 30; 2026-07-28: 30; 2026-07-29: 30; 2026-07-30: 5; 2026-07-31: 5
[6 empty] | Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block 3 | 2026-08-06 | 2026-08-11 | 2026-08-14 | Activity | Mandays | Start date | Max dates | Days |  | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-10-13
|  |  |  | Erection | #VALUE! | 2026-07-30 | 2026-07-29 | -1 | 10.6154 | 8.8462 | #VALUE! | bar: 2026-06-22 to 2026-10-13
|  |  |  | Cable Laying | #VALUE! | 2026-07-30 | 2026-07-29 | -1 | bar: 2026-06-22 to 2026-10-13
|  |  |  | Termination | #VALUE! | 2026-07-30 | 2026-08-01 | 2 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 2026-07-30 | 2026-08-03 | 4 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | 2026-08-03 | 30 |  |  |  | 2026-07-11: 5; 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 5; 2026-08-04: 30; 2026-08-05: 30; 2026-08-06: 30; 2026-08-07: 30; 2026-08-08: 5; 2026-08-09: 5
[6 empty] | Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block 5 | 2026-08-07 | 2026-08-12 | 2026-08-15 | Activity | Mandays | Start date | Max dates | Days |  | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-10-13
|  |  |  | Erection | #VALUE! | 2026-07-30 | 2026-07-30 | 0 | 10.8 | 9 | #VALUE! | bar: 2026-06-22 to 2026-10-13
|  |  |  | Cable Laying | #VALUE! | 2026-07-30 | 2026-07-30 | 0 | bar: 2026-06-22 to 2026-10-13
|  |  |  | Termination | #VALUE! | 2026-07-30 | 2026-08-02 | 3 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 2026-07-30 | 2026-08-04 | 5 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | 2026-08-04 | 30 |  |  |  | 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 5; 2026-08-04: 5; 2026-08-05: 30; 2026-08-06: 30; 2026-08-07: 30; 2026-08-08: 30; 2026-08-09: 5; 2026-08-10: 5
[6 empty] | Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block 6 | 2026-08-24 | 2026-08-28 | 2026-08-31 | Activity | Mandays | Start date | Max dates | Days |  | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-10-13
|  |  |  | Erection | #VALUE! | 2026-07-30 | 2026-08-07 | 8 | 21 | 17.5 | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | #VALUE! | 2026-07-30 | 2026-08-12 | 13 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | #VALUE! | 2026-07-30 | 2026-08-16 | 17 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 2026-08-07 | 2026-08-21 | 14 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | 2026-08-21 | 30 |  |  |  | 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 5; 2026-08-04: 5; 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 5; 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 5; 2026-08-15: 5; 2026-08-16: 5; 2026-08-17: 5; 2026-08-18: 5; 2026-08-19: 5; 2026-08-20: 5; 2026-08-21: 5; 2026-08-22: 30; 2026-08-23: 30; 2026-08-24: 30; 2026-08-25: 30; 2026-08-26: 5; 2026-08-27: 5
[6 empty] | Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block 7 | 2026-09-17 | 2026-09-22 | 2026-09-25 | Activity | Mandays | Start date | Max dates | Days |  | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-10-13
|  |  |  | Erection | #VALUE! | 2026-07-30 | 2026-08-07 | 8 | 21 | 17.5 | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | #VALUE! | 2026-07-30 | 2026-08-09 | 10 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | #VALUE! | 2026-08-20 | 2026-09-09 | 20 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 2026-08-31 | 2026-09-14 | 14 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | 2026-09-14 | 30 |  |  |  | 2026-08-22: 5; 2026-08-23: 5; 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 5; 2026-08-29: 5; 2026-08-30: 5; 2026-08-31: 5; 2026-09-01: 5; 2026-09-02: 5; 2026-09-03: 5; 2026-09-04: 5; 2026-09-05: 5; 2026-09-06: 5; 2026-09-07: 5; 2026-09-08: 5; 2026-09-09: 5; 2026-09-10: 5; 2026-09-11: 5; 2026-09-12: 5; 2026-09-13: 5; 2026-09-14: 5; 2026-09-15: 30; 2026-09-16: 30; 2026-09-17: 30; 2026-09-18: 30; 2026-09-19: 5; 2026-09-20: 5
[6 empty] | Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block 8 | 2026-09-17 | 2026-09-22 | 2026-09-25 | Activity | Mandays | Start date | Max dates | Days |  | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-10-13
|  |  |  | Erection | #VALUE! | 2026-08-08 | 2026-08-18 | 10 | 21 | 17.5 | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | #VALUE! | 2026-07-30 | 2026-08-19 | 20 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | #VALUE! | 2026-08-20 | 2026-09-09 | 20 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 2026-08-31 | 2026-09-14 | 14 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 |  | 2026-09-14 | 30 |  |  |  | 2026-08-22: 5; 2026-08-23: 5; 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 5; 2026-08-29: 5; 2026-08-30: 5; 2026-08-31: 5; 2026-09-01: 5; 2026-09-02: 5; 2026-09-03: 5; 2026-09-04: 5; 2026-09-05: 5; 2026-09-06: 5; 2026-09-07: 5; 2026-09-08: 5; 2026-09-09: 5; 2026-09-10: 5; 2026-09-11: 5; 2026-09-12: 5; 2026-09-13: 5; 2026-09-14: 5; 2026-09-15: 30; 2026-09-16: 30; 2026-09-17: 30; 2026-09-18: 30; 2026-09-19: 5; 2026-09-20: 5
[6 empty] | Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Total of all blocks |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 15 | 15 | 15 | 15 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 75 | 75 | 75 | 80 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 10 | 60
[8 empty] | Avg. |  |  |  | 2026-06-22: #VALUE!; 2026-06-23: #VALUE!
[8 empty] | Peak |  |  |  | 2026-06-22: #VALUE!; 2026-06-23: #VALUE!

## 10B - Daily requirement (3)
PSS-10(B) | [9 empty] | 2026-06-23
| IDT Charging / Commissioning Start | Trial-Run End Date | COD | Activity | Mandays | Start Date | End Date | Days | Avg Manpower + 20% Buffer | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-12-31
Block 1 | 2026-08-05 | 2026-08-10 | 2026-08-13 | Erection | #VALUE! | 2026-07-25 | 2026-07-25 | 0 | 9.6 | 8 | #VALUE! | bar: 2026-06-22 to 2026-11-30
|  |  |  | Cable Laying | #VALUE! | 2026-07-30 | 2026-07-30 | 0 | bar: 2026-06-22 to 2026-11-30
|  |  |  | Termination | #VALUE! | 2026-07-30 | 2026-08-01 | 2 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 2026-07-30 | 2026-08-04 | 5 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 | 2026-08-02 |  | 30 |  |  |  | 2026-07-10: 5; 2026-07-11: 5; 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 30; 2026-08-04: 30; 2026-08-05: 30; 2026-08-06: 30; 2026-08-07: 5; 2026-08-08: 5
[6 empty] | Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block 2 | 2026-08-11 | 2026-08-16 | 2026-08-19 | Activity | Mandays | Start Date | End Date | Days |  | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-11-30
|  |  |  | Erection | #VALUE! | 2026-07-30 | 2026-08-02 | 3 | 11.7143 | 9.7619 | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | #VALUE! | 2026-07-30 | 2026-07-31 | 1 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | #VALUE! | 2026-07-30 | 2026-08-05 | 6 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 2026-07-30 | 2026-08-08 | 9 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 | 2026-08-08 |  | 30 |  |  |  | 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 5; 2026-08-04: 5; 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 30; 2026-08-10: 30; 2026-08-11: 30; 2026-08-12: 30; 2026-08-13: 5; 2026-08-14: 5
[6 empty] | Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block 3 | 2026-09-21 | 2026-09-26 | 2026-09-29 | Activity | Mandays | Start Date | End Date | Days |  | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-11-30
|  |  |  | Erection | #VALUE! | 2026-07-30 | 2026-08-08 | 9 | 7.2 | 6 | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | #VALUE! | 2026-07-30 | 2026-08-12 | 13 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | #VALUE! | 2026-07-30 | 2026-08-17 | 18 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 2026-08-07 | 2026-08-21 | 14 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 | 2026-09-18 |  | 30 |  |  |  | 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 5; 2026-08-29: 5; 2026-08-30: 5; 2026-08-31: 5; 2026-09-01: 5; 2026-09-02: 5; 2026-09-03: 5; 2026-09-04: 5; 2026-09-05: 5; 2026-09-06: 5; 2026-09-07: 5; 2026-09-08: 5; 2026-09-09: 5; 2026-09-10: 5; 2026-09-11: 5; 2026-09-12: 5; 2026-09-13: 5; 2026-09-14: 5; 2026-09-15: 5; 2026-09-16: 5; 2026-09-17: 5; 2026-09-18: 5; 2026-09-19: 30; 2026-09-20: 30; 2026-09-21: 30; 2026-09-22: 30; 2026-09-23: 5; 2026-09-24: 5
[6 empty] | Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block 4 | 2026-09-30 | 2026-10-05 | 2026-10-08 | Activity | Mandays | Start Date | End Date | Days |  | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-11-30
|  |  |  | Erection | #VALUE! | 2026-08-07 | 2026-08-17 | 10 | 6 | 5 | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | #VALUE! | 2026-07-31 | 2026-08-20 | 20 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | #VALUE! | 2026-08-23 | 2026-09-12 | 20 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 2026-09-04 | 2026-09-18 | 14 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 | 2026-09-27 |  | 30 |  |  |  | 2026-09-04: 5; 2026-09-05: 5; 2026-09-06: 5; 2026-09-07: 5; 2026-09-08: 5; 2026-09-09: 5; 2026-09-10: 5; 2026-09-11: 5; 2026-09-12: 5; 2026-09-13: 5; 2026-09-14: 5; 2026-09-15: 5; 2026-09-16: 5; 2026-09-17: 5; 2026-09-18: 5; 2026-09-19: 5; 2026-09-20: 5; 2026-09-21: 5; 2026-09-22: 5; 2026-09-23: 5; 2026-09-24: 5; 2026-09-25: 5; 2026-09-26: 5; 2026-09-27: 5; 2026-09-28: 30; 2026-09-29: 30; 2026-09-30: 30; 2026-10-01: 30; 2026-10-02: 5; 2026-10-03: 5
[6 empty] | Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block 5 | 2026-08-23 | 2026-08-28 | 2026-08-31 | Activity | Mandays | Start Date | End Date | Days |  | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-11-30
|  |  |  | Erection | #VALUE! | 2026-08-15 | 2026-08-25 | 10 | 6 | 5 | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | #VALUE! | 2026-08-03 | 2026-08-23 | 20 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | #VALUE! | 2026-08-31 | 2026-09-20 | 20 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 2026-09-13 | 2026-09-27 | 14 |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 | 2026-08-20 |  | 30 |  |  |  | 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 5; 2026-08-04: 5; 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 5; 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 5; 2026-08-15: 5; 2026-08-16: 5; 2026-08-17: 5; 2026-08-18: 5; 2026-08-19: 5; 2026-08-20: 5; 2026-08-21: 30; 2026-08-22: 30; 2026-08-23: 30; 2026-08-24: 30; 2026-08-25: 5; 2026-08-26: 5
[6 empty] | Total | [5 empty] | 2026-06-22: 0; 2026-06-23: 0; 2026-06-24: 0; 2026-06-25: 0; 2026-06-26: 0; 2026-06-27: 0; 2026-06-28: 0; 2026-06-29: 0; 2026-06-30: 0; 2026-07-01: 0; 2026-07-02: 0; 2026-07-03: 0; 2026-07-04: 0; 2026-07-05: 0; 2026-07-06: 0; 2026-07-07: 0; 2026-07-08: 0; 2026-07-09: 0; 2026-07-10: 0; 2026-07-11: 0; 2026-07-12: 0; 2026-07-13: 0; 2026-07-14: 0; 2026-07-15: 0; 2026-07-16: 0; 2026-07-17: 0; 2026-07-18: 0; 2026-07-19: 0; 2026-07-20: 0; 2026-07-21: 0; 2026-07-22: 0; 2026-07-23: 0; 2026-07-24: 0; 2026-07-25: 0; 2026-07-26: 0; 2026-07-27: 0; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: #VALUE!; 2026-08-04: #VALUE!; 2026-08-05: #VALUE!; 2026-08-06: #VALUE!; 2026-08-07: #VALUE!; 2026-08-08: #VALUE!; 2026-08-09: #VALUE!; 2026-08-10: #VALUE!; 2026-08-11: #VALUE!; 2026-08-12: #VALUE!; 2026-08-13: #VALUE!; 2026-08-14: #VALUE!; 2026-08-15: #VALUE!; 2026-08-16: #VALUE!; 2026-08-17: #VALUE!; 2026-08-18: #VALUE!; 2026-08-19: #VALUE!; 2026-08-20: #VALUE!; 2026-08-21: #VALUE!; 2026-08-22: #VALUE!; 2026-08-23: #VALUE!; 2026-08-24: #VALUE!; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 0; 2026-08-28: 0; 2026-08-29: 0; 2026-08-30: 0; 2026-08-31: #VALUE!; 2026-09-01: #VALUE!; 2026-09-02: #VALUE!; 2026-09-03: #VALUE!; 2026-09-04: #VALUE!; 2026-09-05: #VALUE!; 2026-09-06: #VALUE!; 2026-09-07: #VALUE!; 2026-09-08: #VALUE!; 2026-09-09: #VALUE!; 2026-09-10: #VALUE!; 2026-09-11: #VALUE!; 2026-09-12: #VALUE!; 2026-09-13: #VALUE!; 2026-09-14: #VALUE!; 2026-09-15: #VALUE!; 2026-09-16: #VALUE!; 2026-09-17: #VALUE!; 2026-09-18: #VALUE!; 2026-09-19: #VALUE!
[7 empty] | Total of all blocks |  |  |  |  | 2026-06-22: 0; 2026-06-23: 0; 2026-06-24: 0; 2026-06-25: 0; 2026-06-26: 0; 2026-06-27: 0; 2026-06-28: 0; 2026-06-29: 0; 2026-06-30: 0; 2026-07-01: 0; 2026-07-02: 0; 2026-07-03: 0; 2026-07-04: 0; 2026-07-05: 0; 2026-07-06: 0; 2026-07-07: 0; 2026-07-08: 0; 2026-07-09: 0; 2026-07-10: 5; 2026-07-11: 5; 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 10; 2026-07-17: 10; 2026-07-18: 10; 2026-07-19: 10; 2026-07-20: 10; 2026-07-21: 10; 2026-07-22: 10; 2026-07-23: 10; 2026-07-24: 10; 2026-07-25: 10; 2026-07-26: 10; 2026-07-27: 10; 2026-07-28: 15; 2026-07-29: 15; 2026-07-30: #VALUE!; 2026-07-31: #VALUE!; 2026-08-01: #VALUE!; 2026-08-02: #VALUE!; 2026-08-03: #VALUE!; 2026-08-04: #VALUE!; 2026-08-05: #VALUE!; 2026-08-06: #VALUE!; 2026-08-07: #VALUE!; 2026-08-08: #VALUE!; 2026-08-09: #VALUE!; 2026-08-10: #VALUE!; 2026-08-11: #VALUE!; 2026-08-12: #VALUE!; 2026-08-13: #VALUE!; 2026-08-14: #VALUE!; 2026-08-15: #VALUE!; 2026-08-16: #VALUE!; 2026-08-17: #VALUE!; 2026-08-18: #VALUE!; 2026-08-19: #VALUE!; 2026-08-20: #VALUE!; 2026-08-21: #VALUE!; 2026-08-22: #VALUE!; 2026-08-23: #VALUE!; 2026-08-24: #VALUE!; 2026-08-25: #VALUE!; 2026-08-26: #VALUE!; 2026-08-27: #VALUE!; 2026-08-28: #VALUE!; 2026-08-29: #VALUE!; 2026-08-30: #VALUE!; 2026-08-31: #VALUE!; 2026-09-01: #VALUE!; 2026-09-02: #VALUE!; 2026-09-03: #VALUE!; 2026-09-04: #VALUE!; 2026-09-05: #VALUE!; 2026-09-06: #VALUE!; 2026-09-07: #VALUE!; 2026-09-08: #VALUE!; 2026-09-09: #VALUE!; 2026-09-10: #VALUE!; 2026-09-11: #VALUE!; 2026-09-12: #VALUE!; 2026-09-13: #VALUE!; 2026-09-14: #VALUE!; 2026-09-15: #VALUE!; 2026-09-16: #VALUE!; 2026-09-17: #VALUE!; 2026-09-18: #VALUE!; 2026-09-19: #VALUE!
[7 empty] | Avg. |  |  |  |  | 2026-06-22: #VALUE!; 2026-06-23: #VALUE!
[7 empty] | Peak |  |  |  |  | 2026-06-22: #VALUE!; 2026-06-23: #VALUE!

## 10B - Daily requirement (hidden)
PSS-10(B) | [8 empty] | 2026-06-23
| IDT Charging / Commissioning Start | Trial-Run End Date | COD | Activity | Mandays | Start Date | End Date | Days | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-12-31
Block 1 | 2026-08-05 | 2026-08-10 | 2026-08-13 | Erection | #VALUE! | 2026-07-02 | 2026-07-12 | 10 | 16.1111 | #VALUE! | 2026-06-22: -; 2026-06-23: -; 2026-06-24: -; 2026-06-25: -; 2026-06-26: -; 2026-06-27: -; 2026-06-28: -; 2026-06-29: -; 2026-06-30: -; 2026-07-01: -; 2026-07-02: #VALUE!; 2026-07-03: #VALUE!; 2026-07-04: #VALUE!; 2026-07-05: #VALUE!; 2026-07-06: #VALUE!; 2026-07-07: #VALUE!; 2026-07-08: #VALUE!; 2026-07-09: #VALUE!; 2026-07-10: #VALUE!; 2026-07-11: #VALUE!; 2026-07-12: -; 2026-07-13: -; 2026-07-14: -; 2026-07-15: -; 2026-07-16: -; 2026-07-17: -; 2026-07-18: -; 2026-07-19: -; 2026-07-20: -; 2026-07-21: -; 2026-07-22: -; 2026-07-23: -; 2026-07-24: -; 2026-07-25: -; 2026-07-26: -; 2026-07-27: -; 2026-07-28: -; 2026-07-29: -; 2026-07-30: -; 2026-07-31: -; 2026-08-01: -; 2026-08-02: -; 2026-08-03: -; 2026-08-04: -; 2026-08-05: -; 2026-08-06: -; 2026-08-07: -; 2026-08-08: -; 2026-08-09: -; 2026-08-10: -; 2026-08-11: -; 2026-08-12: -; 2026-08-13: -; 2026-08-14: -; 2026-08-15: -; 2026-08-16: -; 2026-08-17: -; 2026-08-18: -; 2026-08-19: -; 2026-08-20: -; 2026-08-21: -; 2026-08-22: -; 2026-08-23: -; 2026-08-24: -; 2026-08-25: -; 2026-08-26: -; 2026-08-27: -; 2026-08-28: -; 2026-08-29: -; 2026-08-30: -; 2026-08-31: -; 2026-09-01: -; 2026-09-02: -; 2026-09-03: -; 2026-09-04: -; 2026-09-05: -; 2026-09-06: -; 2026-09-07: -; 2026-09-08: -; 2026-09-09: -; 2026-09-10: -; 2026-09-11: -; 2026-09-12: -; 2026-09-13: -; 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -
|  |  |  | Cable Laying | #VALUE! | 2026-07-30 | 2026-07-30 | 0 | bar: 2026-06-22 to 2026-09-19
|  |  |  | Termination | #VALUE! | 2026-07-12 | 2026-08-01 | 20 |  |  | 2026-06-22: -; 2026-06-23: -; 2026-06-24: -; 2026-06-25: -; 2026-06-26: -; 2026-06-27: -; 2026-06-28: -; 2026-06-29: -; 2026-06-30: -; 2026-07-01: -; 2026-07-02: -; 2026-07-03: -; 2026-07-04: -; 2026-07-05: -; 2026-07-06: -; 2026-07-07: -; 2026-07-08: -; 2026-07-09: -; 2026-07-10: -; 2026-07-11: -; 2026-07-12: #VALUE!; 2026-07-13: #VALUE!; 2026-07-14: #VALUE!; 2026-07-15: #VALUE!; 2026-07-16: #VALUE!; 2026-07-17: #VALUE!; 2026-07-18: #VALUE!; 2026-07-19: #VALUE!; 2026-07-20: #VALUE!; 2026-07-21: #VALUE!; 2026-07-22: #VALUE!; 2026-07-23: #VALUE!; 2026-07-24: #VALUE!; 2026-07-25: #VALUE!; 2026-07-26: #VALUE!; 2026-07-27: #VALUE!; 2026-07-28: #VALUE!; 2026-07-29: #VALUE!; 2026-07-30: #VALUE!; 2026-07-31: #VALUE!; 2026-08-01: -; 2026-08-02: -; 2026-08-03: -; 2026-08-04: -; 2026-08-05: -; 2026-08-06: -; 2026-08-07: -; 2026-08-08: -; 2026-08-09: -; 2026-08-10: -; 2026-08-11: -; 2026-08-12: -; 2026-08-13: -; 2026-08-14: -; 2026-08-15: -; 2026-08-16: -; 2026-08-17: -; 2026-08-18: -; 2026-08-19: -; 2026-08-20: -; 2026-08-21: -; 2026-08-22: -; 2026-08-23: -; 2026-08-24: -; 2026-08-25: -; 2026-08-26: -; 2026-08-27: -; 2026-08-28: -; 2026-08-29: -; 2026-08-30: -; 2026-08-31: -; 2026-09-01: -; 2026-09-02: -; 2026-09-03: -; 2026-09-04: -; 2026-09-05: -; 2026-09-06: -; 2026-09-07: -; 2026-09-08: -; 2026-09-09: -; 2026-09-10: -; 2026-09-11: -; 2026-09-12: -; 2026-09-13: -; 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -
|  |  |  | Testing | #VALUE! | 2026-07-19 | 2026-08-02 | 14 |  |  | 2026-06-22: -; 2026-06-23: -; 2026-06-24: -; 2026-06-25: -; 2026-06-26: -; 2026-06-27: -; 2026-06-28: -; 2026-06-29: -; 2026-06-30: -; 2026-07-01: -; 2026-07-02: -; 2026-07-03: -; 2026-07-04: -; 2026-07-05: -; 2026-07-06: -; 2026-07-07: -; 2026-07-08: -; 2026-07-09: -; 2026-07-10: -; 2026-07-11: -; 2026-07-12: -; 2026-07-13: -; 2026-07-14: -; 2026-07-15: -; 2026-07-16: -; 2026-07-17: -; 2026-07-18: -; 2026-07-19: #VALUE!; 2026-07-20: #VALUE!; 2026-07-21: #VALUE!; 2026-07-22: #VALUE!; 2026-07-23: #VALUE!; 2026-07-24: #VALUE!; 2026-07-25: #VALUE!; 2026-07-26: #VALUE!; 2026-07-27: #VALUE!; 2026-07-28: #VALUE!; 2026-07-29: #VALUE!; 2026-07-30: #VALUE!; 2026-07-31: #VALUE!; 2026-08-01: #VALUE!; 2026-08-02: -; 2026-08-03: -; 2026-08-04: -; 2026-08-05: -; 2026-08-06: -; 2026-08-07: -; 2026-08-08: -; 2026-08-09: -; 2026-08-10: -; 2026-08-11: -; 2026-08-12: -; 2026-08-13: -; 2026-08-14: -; 2026-08-15: -; 2026-08-16: -; 2026-08-17: -; 2026-08-18: -; 2026-08-19: -; 2026-08-20: -; 2026-08-21: -; 2026-08-22: -; 2026-08-23: -; 2026-08-24: -; 2026-08-25: -; 2026-08-26: -; 2026-08-27: -; 2026-08-28: -; 2026-08-29: -; 2026-08-30: -; 2026-08-31: -; 2026-09-01: -; 2026-09-02: -; 2026-09-03: -; 2026-09-04: -; 2026-09-05: -; 2026-09-06: -; 2026-09-07: -; 2026-09-08: -; 2026-09-09: -; 2026-09-10: -; 2026-09-11: -; 2026-09-12: -; 2026-09-13: -; 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -
|  |  |  | CFT | 250 | 2026-08-02 |  | 30 |  |  | 2026-06-22: -; 2026-06-23: -; 2026-06-24: -; 2026-06-25: -; 2026-06-26: -; 2026-06-27: -; 2026-06-28: -; 2026-06-29: -; 2026-06-30: -; 2026-07-01: -; 2026-07-02: -; 2026-07-03: -; 2026-07-04: -; 2026-07-05: -; 2026-07-06: -; 2026-07-07: -; 2026-07-08: -; 2026-07-09: -; 2026-07-10: -; 2026-07-12: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 30; 2026-08-04: 30; 2026-08-05: 30; 2026-08-06: 30; 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 5; 2026-08-10: 5; 2026-08-11: -; 2026-08-12: -; 2026-08-13: -; 2026-08-14: -; 2026-08-15: -; 2026-08-16: -; 2026-08-17: -; 2026-08-18: -; 2026-08-19: -; 2026-08-20: -; 2026-08-21: -; 2026-08-22: -; 2026-08-23: -; 2026-08-24: -; 2026-08-25: -; 2026-08-26: -; 2026-08-27: -; 2026-08-28: -; 2026-08-29: -; 2026-08-30: -; 2026-08-31: -; 2026-09-01: -; 2026-09-02: -; 2026-09-03: -; 2026-09-04: -; 2026-09-05: -; 2026-09-06: -; 2026-09-07: -; 2026-09-08: -; 2026-09-09: -; 2026-09-10: -; 2026-09-11: -; 2026-09-12: -; 2026-09-13: -; 2026-09-14: -; 2026-09-15: -; 2026-09-16: -; 2026-09-17: -; 2026-09-18: -; 2026-09-19: -
[6 empty] | Total |  |  |  |  | 2026-06-22: 0; 2026-06-23: 0; 2026-06-24: 0; 2026-06-25: 0; 2026-06-26: 0; 2026-06-27: 0; 2026-06-28: 0; 2026-06-29: 0; 2026-06-30: 0; 2026-07-01: 0; 2026-07-02: #VALUE!; 2026-07-03: #VALUE!; 2026-07-04: #VALUE!; 2026-07-05: #VALUE!; 2026-07-06: #VALUE!; 2026-07-07: #VALUE!; 2026-07-08: #VALUE!; 2026-07-09: #VALUE!; 2026-07-10: #VALUE!; 2026-07-11: #VALUE!; 2026-07-12: #VALUE!; 2026-07-13: #VALUE!; 2026-07-14: #VALUE!; 2026-07-15: #VALUE!; 2026-07-16: #VALUE!; 2026-07-17: #VALUE!; 2026-07-18: #VALUE!; 2026-07-19: #VALUE!; 2026-07-20: #VALUE!; 2026-07-21: #VALUE!; 2026-07-22: #VALUE!; 2026-07-23: #VALUE!; 2026-07-24: #VALUE!; 2026-07-25: #VALUE!; 2026-07-26: #VALUE!; 2026-07-27: #VALUE!; 2026-07-28: #VALUE!; 2026-07-29: #VALUE!; 2026-07-30: #VALUE!; 2026-07-31: #VALUE!; 2026-08-01: #VALUE!; 2026-08-02: 5; 2026-08-03: 30; 2026-08-04: 30; 2026-08-05: 30; 2026-08-06: 30; 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 5; 2026-08-10: 5; 2026-08-11: 0; 2026-08-12: 0; 2026-08-13: 0; 2026-08-14: 0; 2026-08-15: 0; 2026-08-16: 0; 2026-08-17: 0; 2026-08-18: 0; 2026-08-19: 0; 2026-08-20: 0; 2026-08-21: 0; 2026-08-22: 0; 2026-08-23: 0; 2026-08-24: 0; 2026-08-25: 0; 2026-08-26: 0; 2026-08-27: 0; 2026-08-28: 0; 2026-08-29: 0; 2026-08-30: 0; 2026-08-31: 0; 2026-09-01: 0; 2026-09-02: 0; 2026-09-03: 0; 2026-09-04: 0; 2026-09-05: 0; 2026-09-06: 0; 2026-09-07: 0; 2026-09-08: 0; 2026-09-09: 0; 2026-09-10: 0; 2026-09-11: 0; 2026-09-12: 0; 2026-09-13: 0; 2026-09-14: 0; 2026-09-15: 0; 2026-09-16: 0; 2026-09-17: 0; 2026-09-18: 0; 2026-09-19: 0
Block 2 | 2026-08-11 | 2026-08-16 |  | Activity | Mandays | Start Date | End Date | Days | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-09-19
|  |  | 2026-08-19 | Erection | #VALUE! | -10 | 0 | 10 | 16.1111 | #VALUE! | bar: 2026-06-22 to 2026-09-19
|  |  |  | Cable Laying | #VALUE! | 2026-07-11 | 2026-07-31 | 20 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | #VALUE! | 2026-07-16 | 2026-08-05 | 20 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 2026-07-25 | 2026-08-08 | 14 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 | 2026-08-08 |  | 30 |  |  | 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 5; 2026-08-04: 5; 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 30; 2026-08-10: 30; 2026-08-11: 30; 2026-08-12: 30; 2026-08-13: 5; 2026-08-14: 5; 2026-08-15: 5; 2026-08-16: 5
[6 empty] | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 5 | 30 | 30 | 30 | 30 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block 3 | 08 Aug 23 Aug | 13 Aug 28 Aug |  | Activity | Mandays | Start Date | End Date | Days | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-09-19
|  |  | 16 Aug 31 Aug | Erection | #VALUE! | 2026-07-29 | 2026-08-08 | 10 | 5 | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | #VALUE! | 2026-07-23 | 2026-08-12 | 20 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | #VALUE! | 2026-07-28 | 2026-08-17 | 20 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 2026-08-07 | 2026-08-21 | 14 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | CFT | 250 | #VALUE! |  | 30 |  |  | 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-18: 5; 2026-07-19: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-25: 5; 2026-07-26: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5; 2026-08-01: 5; 2026-08-02: 5; 2026-08-03: 5; 2026-08-04: 5; 2026-08-05: 5; 2026-08-06: 30; 2026-08-07: 30; 2026-08-08: 30; 2026-08-09: 30; 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5
[6 empty] | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block 4 | 30 Aug 21 Sep | 04 Sep 26 Sep |  | Activity | Mandays | Start Date | End Date | Days | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-09-19
|  |  | 07 Sep 29 Sep | Erection | #VALUE! | 2026-08-07 | 2026-08-17 | 10 | 5 | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | #VALUE! | 2026-07-31 | 2026-08-20 | 20 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | #VALUE! | 2026-08-23 | 2026-09-12 | 20 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | -
|  |  |  | Testing | #VALUE! | 2026-09-04 | 2026-09-18 | 14 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | -
|  |  |  | CFT | 250 | #VALUE! |  | 30 |  |  | 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 5; 2026-08-08: 5; 2026-08-09: 5; 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 5; 2026-08-15: 5; 2026-08-16: 5; 2026-08-17: 5; 2026-08-18: 5; 2026-08-19: 5; 2026-08-20: 5; 2026-08-21: 5; 2026-08-22: 5; 2026-08-23: 5; 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 30; 2026-08-29: 30; 2026-08-30: 30; 2026-08-31: 30; 2026-09-01: 5; 2026-09-02: 5; 2026-09-03: 5; 2026-09-04: 5
[6 empty] | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 5 | 5 | 5 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0
Block 5 | 04 Sep 30 Sep | 09 Sep 05 Oct |  | Activity | Mandays | Start Date | End Date | Days | Avg Manpower | Peak Manpower | time axis 2026-06-22 to 2026-09-19
|  |  | 12 Sep 08 Oct | Erection | #VALUE! | 2026-08-15 | 2026-08-25 | 10 | 5 | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Cable Laying | #VALUE! | 2026-08-03 | 2026-08-23 | 20 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Termination | #VALUE! | 2026-08-31 | 2026-09-20 | 20 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  |  | Testing | #VALUE! | 2026-09-13 | 2026-09-27 | 14 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  |  | CFT | 250 | #VALUE! |  | 30 |  |  | 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 5; 2026-08-15: 5; 2026-08-16: 5; 2026-08-17: 5; 2026-08-18: 5; 2026-08-19: 5; 2026-08-20: 5; 2026-08-21: 5; 2026-08-22: 5; 2026-08-23: 5; 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 5; 2026-08-29: 5; 2026-08-30: 5; 2026-08-31: 5; 2026-09-01: 5; 2026-09-02: 30; 2026-09-03: 30; 2026-09-04: 30; 2026-09-05: 30; 2026-09-06: 5; 2026-09-07: 5; 2026-09-08: 5; 2026-09-09: 5
[6 empty] | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 5 | 5 | 5 | 5 | 5 | 5 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | Total of all blocks |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | Avg. |  |  |  | 2026-06-22: #VALUE!; 2026-06-23: #VALUE!
[7 empty] | Peak |  |  |  | 2026-06-22: #VALUE!; 2026-06-23: #VALUE!