## Bess 11 Part Wise (hidden)
2026-05-02
Container Make | Block No. | Containers | MWH | IDT Charging / Commissioning Start | Trial-Run Start Date | COD | Status | [6 empty] | Remarks
[7 empty] | Sr. | Activity | Progress |  |  | EDC | vendor
[9 empty] | S | C | B
CATL | 1, 2, 3 & 4 | 192 | 962.88 |  |  |  | 1.1 | BCF Precast Erection & Welding | #REF! | #REF! | #REF! |  | MSC
[7 empty] | 1.2 | Battery Container Erection | #REF! | #REF! | #REF! |  | HEFT & Pratibha
[7 empty] | 1.3 | CT Rail Fixing | #REF! | #REF! | #REF! |  | MSC
[7 empty] | 1.4 | CT Erection | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 1.5 | PCS Slab casting | #REF! | #REF! | #REF! |  | MSC
[7 empty] | 1.6 | PCS Erection | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 1.7 | ACDB Erection | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 1.8 | ECP Panel Erection (Communication Panel) | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 1.9 | PCS PEB | #REF! | #REF! | #REF! |  | Synergy
[7 empty] | 1.1 | SGR Slab Casting | #REF! | #REF! | #REF! |  | MSC
[7 empty] | 1.11 | HT Panel Erection | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 1.12 | SGR PEB | #REF! | #REF! | #REF! |  | Synergy
[7 empty] | 1.13 | MCR Slab Casting | #REF! | #REF! | #REF! |  | MSC
[7 empty] | 1.14 | EMS Panel Erection | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 1.15 | MCR PEB | #REF! | #REF! | #REF! |  | Synergy
[7 empty] | 1.16 | CSS Slab Casting | #REF! | #REF! | #REF! |  | MSC
[7 empty] | 1.17 | CSS Erection | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 1.18 | NIFPS Precast Erection | #REF! | #REF! | #REF! |  | MSC
[7 empty] | 1.19 | NIFPS Panel Erection | #REF! | #REF! | #REF! |  | Ornet
[7 empty] | 1.2 | NIFPS Fabrication | #REF! | #REF! | #REF! |  | Ornet
[7 empty] | 1.21 | BOT Precast Erection | #REF! | #REF! | #REF! |  | Sachi
[7 empty] | 1.22 | BOT Slab casting | #REF! | #REF! | #REF! |  | MSC
[7 empty] | 1.23 | HT cable laying | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 1.24 | HT cable termination | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 1.25 | DC & LT cable laying | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 1.26 | DC & LT cable termination | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 1.27 | Aux, Control & communication cable laying | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 1.28 | CT Testing | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 1.29 | HTP testing | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 1.3 | Earthing | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 1.31 | LA | #REF! | #REF! | #REF! |  | Pratibha
CATL | 5, 6, 7 & 8 | 48 | 240.72 |  |  |  | 2.1 | BCF Precast Erection & Welding | #REF! | #REF! | #REF! |  | MSC
[7 empty] | 2.2 | Battery Container Erection | #REF! | #REF! | #REF! |  | HEFT & Pratibha
[7 empty] | 2.3 | CT Rail Fixing | #REF! | #REF! | #REF! |  | MSC
[7 empty] | 2.4 | CT Erection | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 2.5 | PCS Slab casting | #REF! | #REF! | #REF! |  | MSC
[7 empty] | 2.6 | PCS Erection | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 2.7 | ACDB Erection | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 2.8 | ECP Panel Erection (Communication Panel) | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 2.9 | PCS PEB | #REF! | #REF! | #REF! |  | Synergy
[7 empty] | 2.1 | SGR Slab Casting | #REF! | #REF! | #REF! |  | MSC
[7 empty] | 2.11 | HT Panel Erection | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 2.12 | SGR PEB | #REF! | #REF! | #REF! |  | Synergy
[7 empty] | 2.13 | MCR Slab Casting | #REF! | #REF! | #REF! |  | MSC
[7 empty] | 2.14 | EMS Panel Erection | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 2.15 | MCR PEB | #REF! | #REF! | #REF! |  | Synergy
[7 empty] | 2.16 | CSS Slab Casting | #REF! | #REF! | #REF! |  | MSC
[7 empty] | 2.17 | CSS Erection | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 2.18 | NIFPS Precast Erection | #REF! | #REF! | #REF! |  | MSC
[7 empty] | 2.19 | NIFPS Panel Erection | #REF! | #REF! | #REF! |  | Ornet
[7 empty] | 2.2 | NIFPS Fabrication | #REF! | #REF! | #REF! |  | Ornet
[7 empty] | 2.21 | BOT Precast Erection | #REF! | #REF! | #REF! |  | Sachi
[7 empty] | 2.22 | HT cable laying | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 2.23 | HT cable termination | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 2.24 | DC & LT cable laying | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 2.25 | DC & LT cable termination | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 2.26 | Aux, Control & communication cable laying | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 2.27 | CT Testing | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 2.28 | HTP testing | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 2.29 | Earthing | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 2.3 | LA | #REF! | #REF! | #REF! |  | Pratibha
CATL | 9 | 48 | 240.72 |  |  |  | 3.1 | BCF Precast Erection & Welding | #REF! | #REF! | #REF! |  | MSC
[7 empty] | 3.2 | Battery Container Erection | #REF! | #REF! | #REF! |  | HEFT & Pratibha
[7 empty] | 3.3 | CT Rail Fixing | #REF! | #REF! | #REF! |  | MSC
[7 empty] | 3.4 | CT Erection | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 3.5 | PCS Slab casting | #REF! | #REF! | #REF! |  | MSC
[7 empty] | 3.6 | PCS Erection | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 3.7 | ACDB Erection | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 3.8 | ECP Panel Erection (Communication Panel) | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 3.9 | PCS PEB | #REF! | #REF! | #REF! |  | Synergy
[7 empty] | 3.1 | SGR Slab Casting | #REF! | #REF! | #REF! |  | MSC
[7 empty] | 3.11 | HT Panel Erection | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 3.12 | SGR PEB | #REF! | #REF! | #REF! |  | Synergy
[7 empty] | 3.13 | MCR Slab Casting | #REF! | #REF! | #REF! |  | MSC
[7 empty] | 3.14 | EMS Panel Erection | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 3.15 | MCR PEB | #REF! | #REF! | #REF! |  | Synergy
[7 empty] | 3.16 | CSS Slab Casting | #REF! | #REF! | #REF! |  | MSC
[7 empty] | 3.17 | CSS Erection | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 3.18 | NIFPS Precast Erection | #REF! | #REF! | #REF! |  | MSC
[7 empty] | 3.19 | NIFPS Panel Erection | #REF! | #REF! | #REF! |  | Ornet
[7 empty] | 3.2 | NIFPS Fabrication | #REF! | #REF! | #REF! |  | Ornet
[7 empty] | 3.21 | BOT Precast Erection | #REF! | #REF! | #REF! |  | Sachi
[7 empty] | 3.22 | HT cable laying | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 3.23 | HT cable termination | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 3.24 | DC & LT cable laying | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 3.25 | DC & LT cable termination | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 3.26 | Aux, Control & communication cable laying | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 3.27 | CT Testing | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 3.28 | HTP testing | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 3.29 | Earthing | #REF! | #REF! | #REF! |  | Pratibha
[7 empty] | 3.3 | LA | #REF! | #REF! | #REF! |  | Pratibha

## BESS 11_Updated
BESS 11 Charging Schedule | [23 empty] | 2026-07-30
Container Make | Block No. | Containers at Site | MWh | IDT Charging / Commissioning Start | Trial-Run End Date | COD | Status | [8 empty] | Standard Productivity Per Team | Weekly Productivity Rate | Target 30-Jul-2026 | Progress As Of 29-Jul-2026 | Forcasted Date |  | Total Team Required to acieve the Target | Schedule Status | Remark - 29-Jul-2026
[7 empty] | Sr. | Activity | Progress |  |  |  | EDC | New EDC | Vendor | [5 empty] | Forcasted Date
[9 empty] | S | C | B | Status
CATL | 4 | 2026-06-28 | 271 MWh (48 Containers) | 2026-07-22 | 2026-07-27 | 2026-07-30 |  |  |  | Civil
[7 empty] | 4.01 | BCF Precast Erection & Welding | 48 | 48 | 0 | 100% | Completed | Completed | MSC | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.02 | CT Rail Fixing | 6 | 6 | 0 | 100% | Completed | Completed | MSC | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.03 | PCS Slab casting | 6 | 6 | 0 | 100% | Completed | Completed | MSC | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.04 | SGR Slab Casting | 1 | 1 | 0 | 100% | Completed | Completed | MSC | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.05 | MCR Slab Casting | 1 | 1 | 0 | 100% | Completed | Completed | MSC | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.06 | CSS Slab Casting | 1 | 1 | 0 | 100% | Completed | Completed | MSC | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.07 | BOT Slab casting | 3 | 3 | 0 | 100% | Completed | Completed | MSC | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.08 | NIFPS Precast Erection | 6 | 6 | 0 | 100% | Completed | Completed | MSC | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.09 | PCS PEB | 6 | 6 | 0 | 100% | Completed | Completed | Synergy | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.1 | SGR PEB | 1 | 1 | 0 | 100% | Completed | Completed | Synergy | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.11 | MCR PEB | 1 | 0 | 1 | 0% | 2026-07-01 | 2026-07-01 | RV Enterprise | 1 | 0 | 1 | 0 | NO PROGRESS | 2026-07-31 | 1 | DELAYED | Door work is pending. Expected to be completed by 20 July.
[10 empty] | Electrical | [10 empty] | Completed
[7 empty] | 4.12 | CT Erection | 6 | 6 | 0 | 100% | Completed | Completed | Pratibha | 2 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.13 | PCS Erection | 48 | 48 | 0 | 100% | Completed | Completed | Pratibha | 10 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.14 | ACDB Erection | 6 | 6 | 0 | 100% | Completed | Completed | Pratibha | 5 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.15 | ECP Panel Erection (Communication Panel) | 6 | 6 | 0 | 100% | 21 Jun, 28 Jun, 03 Jul, 8-Jul | Completed | Pratibha | 6 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.16 | HT Panel Erection | 2 | 2 | 0 | 100% | Completed | Completed | Pratibha | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.17 | EMS Panel Erection | 1 | 1 | 0 | 100% | 28 Jun, 02 Jul, 06 Jul, 08 Jul | Completed | Pratibha | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.18 | CSS Erection | 1 | 1 | 0 | 100% | Completed | Completed | Pratibha | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.19 | NIFPS Panel Erection | 6 | 6 | 0 | 100% | Completed | Completed | Ornet / EMR | 6 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.2 | NIFPS Fabrication | 6 | 6 | 0 | 100% | Completed | Completed | Ornet | 0.66667 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED | Completed
[7 empty] | 4.21 | Battery Container Erection | 48 | 48 | 0 | 100% | 2026-07-03 | Completed | HEFT & Pratibha | 10 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.22 | HT cable laying | 6909 | 6909 | 0 | 100% | 25 Jun, 28 Jun | Completed | Pratibha | 1500 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.23 | HT cable termination | 28 | 28 | 0 | 100% | 05 Jul, 09 Jul | Completed | Pratibha | 8 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.24 | HT Cable Torquing & Marking | 28 | 0 | 28 | 0% | 05 Jul, 12 Jul,18 Jul | 2026-07-18 | Pratibha | 15 | 0 | 28 | 0 | NO PROGRESS | 2026-07-31 20:48 | 2 | DELAYED
[7 empty] | 4.25 | FO Cable Internal Ring | 1021 | 812 | 209 | 79.53% |  |  | Pratibha | 600 | 0 | 209 | 0 | NO PROGRESS | 2026-07-30 08:22 | 1 | NO EDC
[7 empty] | 4.26 | DC Cable laying | 13556 | 13556 | 0 | 100% | Completed | Completed | Pratibha | 600 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.27 | LT Cable laying | 44160 | 44160 | 0 | 100% | Completed | Completed | Pratibha | 600 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.28 | DC Cable termination | 1536 | 1126 | 410 | 73.31% | 09 Jul, 13 Jul,18 Jul | 2026-07-18 | Pratibha | 15 | 0 | 410 | 0 | NO PROGRESS | 2026-08-26 08:00 | 28 | DELAYED | Work in Progress. 10 teams (4 M.P each) deployed. Need more team for timely completion of work.
[7 empty] | 4.29 | DC Cable Torquing & Marking | 1536 | 1520 | 16 | 98.96% | 09 Jul, 13 Jul,18 Jul | 2026-07-18 | Pratibha | 150 | 0 | 16 | 0 | NO PROGRESS | 2026-07-30 02:34 | 1 | DELAYED
[7 empty] | 4.3 | LT Cable termination | 2304 | 2304 | 0 | 100% | 09 Jul, 13 Jul | Completed | Pratibha | 15 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.31 | LT Cable Torquing & Marking | 2304 | 1488 | 816 | 64.58% | 09 Jul, 13 Jul,20 july | 2026-07-20 | Pratibha | 150 | 0 | 816 | 0 | NO PROGRESS | 2026-08-04 10:34 | 6 | DELAYED
[7 empty] | 4.32 | Aux Cable laying | 7701 | 7676 | 25 | 99.68% | 29 Jun, 05 Jul, 09 Jul,16Jul | 2026-07-16 | Pratibha | 800 | 0 | 25 | 0 | NO PROGRESS | 2026-07-30 00:45 | 1 | DELAYED | work in progress.2 teams (6 M.P. each) deplolyed. Completion of work is expected by EOD.
[7 empty] | 4.33 | Control Cable laying | 14190 | 13178 | 1012 | 92.87% | 29 Jun, 05 Jul, 09 Jul,17 Jul | 2026-07-17 | Pratibha | 1000 | 0 | 1012 | 0 | NO PROGRESS | 2026-07-31 00:17 | 2 | DELAYED
[7 empty] | 4.34 | Communication Cable laying | 5195 | 5023 | 172 | 96.69% | 29 Jun, 05 Jul, 09 Jul, 16 Jul | 2026-07-16 | Pratibha | 600 | 0 | 172 | 0 | NO PROGRESS | 2026-07-30 06:53 | 1 | DELAYED
[7 empty] | 4.35 | Aux Cable termination | 286 | 139 | 147 | 48.6% | 09 Jul, 13 Jul, 20 Jul | 2026-07-20 | Pratibha | 30 | 0 | 147 | 0 | NO PROGRESS | 2026-08-03 21:36 | 5 | DELAYED | Only 1 team (4M.P) currently deployed. Need more team to complete activity on time.
[7 empty] | 4.36 | Control Cable termination | 536 | 102 | 434 | 19.03% | 09 Jul, 15 Jul, 20 Jul | 2026-07-20 | Pratibha & Emerson | 30 | 51 | 434 | 0 | 2026-09-27 13:39 | 2026-08-13 11:12 | 15 | DELAYED | Only 3 teams (15 MP is deployed) for control termination.Need more team for timely completion of work.
[7 empty] | 4.37 | Communication Cable termination | 384 | 32 | 352 | 8.333% | 09 Jul, 15 Jul, 20 Jul | 2026-07-20 | Pratibha & Emerson | 50 | 32 | 352 | 0 | 2026-10-15 | 2026-08-06 00:58 | 8 | DELAYED | Work in progress.5 team (3 MP each) deployed. Pratibha to provide full front to emerson
[7 empty] | 4.38 | CT SFRA & Tan delta Test | 12 | 12 | 0 | 100% | Completed | Completed | Canbay |  | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.39 | CT Routine Test | 6 | 6 | 0 | 100% | Completed | Completed | Pratibha | 2 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.4 | CT Control scheme & Stability Test | 12 | 11 | 1 | 91.67% | 7/19/2026, 22 Jul | 2026-07-22 | Pratibha | 2 | 4 | 1 | 0 | 2026-07-31 18:00 | 2026-07-30 12:00 | 1 | DELAYED
[7 empty] | 4.41 | HT Panel Routine (CT & PT, Breaker & Meter) Test | 36 | 24 | 12 | 66.67% | 05 Jul, 09 Jul, 16 jul | 2026-07-16 | Pratibha | 0.5 | 0 | 12 | 0 | NO PROGRESS | 2026-08-23 | 24 | DELAYED
[7 empty] | 4.42 | HT Panel relay test | 28 | 16 | 12 | 57.14% | 7/17/2026, 21 Jul | 2026-07-21 | Pratibha | 6 | 8 | 12 | 0 | 2026-08-09 12:00 | 2026-08-01 | 2 | DELAYED
[7 empty] | 4.43 | HT Cable VLF Test | 14 | 14 | 0 | 100% | 05 Jul, 12 Jul | 2026-07-12 | Pratibha | 6 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.44 | CSS routine test | 1 | 0 | 1 | 0% | 05 Jul, 09 Jul, 17 jul | 2026-07-17 | Pratibha | 1 | 0 | 1 | 0 | NO PROGRESS | 2026-07-31 | 1 | DELAYED
[7 empty] | 4.45 | ACDB routine test | 6 | 6 | 0 | 100% | 05 Jul, 09 Jul | 2026-07-09 | Pratibha | 3 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 4.46 | Earthing - Earthing Strip | 5069.8 | 5069.7 | 0.1 | 100% | 07 Jul, 09 Jul, 18 jul | 2026-07-18 | Pratibha | 150 | 0 | 0.1 | 0 | NO PROGRESS | 2026-07-30 00:01 | 1 | DELAYED
[7 empty] | 4.47 | Earthing - Earth Pit | 54 | 9 | 45 | 16.67% |  | 2026-07-18 | Pratibha | 10 | 0 | 45 | 0 | NO PROGRESS | 2026-08-03 12:00 | 5 | DELAYED | 3 teams (4.MP each) deployed . Need more teams to complete activity on time.
[7 empty] | 4.48 | LA | 10 | 0 | 10 | 0% | 09 Jul, 12 Jul, 20 Jul | 2026-07-20 | Pratibha | 5 | 0 | 10 | 0 | NO PROGRESS | 2026-08-01 | 2 | DELAYED | Foundation Casting work is in progress. 1 team deployed.
CATL | 3 | 2026-07-04 | 271 MWh (48 Containers) | 2026-07-28 | 2026-08-02 | 2026-08-05 |  |  |  | Civil | [10 empty] | Completed
[7 empty] | 3.01 | BCF Precast Erection & Welding | 48 | 48 | 0 | 100% | Completed | Completed | MSC | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.02 | CT Rail Fixing | 6 | 6 | 0 | 100% | Completed | Completed | MSC | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.03 | PCS Slab casting | 6 | 6 | 0 | 100% | Completed | Completed | MSC | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.04 | SGR Slab Casting | 1 | 1 | 0 | 100% | Completed | Completed | MSC | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.05 | MCR Slab Casting | 1 | 1 | 0 | 100% | Completed | Completed | MSC | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.06 | CSS Slab Casting | 1 | 1 | 0 | 100% | Completed | Completed | MSC | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.07 | BOT Slab casting | 2 | 2 | 0 | 100% | Completed | Completed | MSC | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.08 | BOT Precast Erection | 1 | 1 | 0 | 100% | Completed | Completed | Sachi | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.09 | NIFPS Precast Erection | 6 | 6 | 0 | 100% | Completed | Completed | MSC | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.1 | PCS PEB | 6 | 6 | 0 | 100% | Completed | Completed | Synergy | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.11 | SGR PEB | 1 | 1 | 0 | 100% | Completed | Completed | Synergy | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.12 | MCR PEB | 1 | 1 | 0 | 100% | 01 Jul, 06 Jul, 11 Jul, 20 Jul | 2026-07-20 | RV Enterprise | 1 | 1 | 0 | 0 | Completed | Completed | 0 | COMPLETED | No manpower deployed
[10 empty] | Electrical | [10 empty] | Completed
[7 empty] | 3.13 | CT Erection | 6 | 6 | 0 | 100% | Completed | Completed | Pratibha | 2 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.14 | PCS Erection | 48 | 48 | 0 | 100% | 27 Jun, 30 Jun | Completed | Pratibha | 10 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.15 | ACDB Erection | 6 | 6 | 0 | 100% | Completed | Completed | Pratibha | 5 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.16 | ECP Panel Erection (Communication Panel) | 6 | 0 | 6 | 0% | 27 Jun, 30 Jun, 03 Jul, 10 Jul,17 Jul | 2026-07-17 | Pratibha | 6 | 0 | 6 | 0 | NO PROGRESS | 2026-07-31 | 1 | DELAYED
[7 empty] | 3.17 | HT Panel Erection | 2 | 2 | 0 | 100% | Completed | Completed | Pratibha | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.18 | EMS Panel Erection | 1 | 0 | 1 | 0% | 04 Jul, 07 Jul, 11 Jul, 17 Jul | 2026-07-17 | Pratibha | 1 | 0 | 1 | 0 | NO PROGRESS | 2026-07-31 | 1 | DELAYED
[7 empty] | 3.19 | CSS Erection | 1 | 1 | 0 | 100% | Completed | Completed | Pratibha | 1 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.2 | NIFPS Panel Erection | 6 | 6 | 0 | 100% | 04 Jul, 09 Jul | 2026-07-09 | Ornet / EMR | 6 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.21 | NIFPS Fabrication | 6 | 6 | 0 | 100% | 7/10/2026,18 Jul | 2026-07-18 | Ornet | 0.66667 | 1 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.22 | Battery Container Erection | 48 | 48 | 0 | 100% | 09 Jul, 13 Jul | 2026-07-13 | HEFT & Pratibha | 10 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.23 | HT cable laying | 7650 | 7650 | 0 | 100% | Completed | Completed | Pratibha | 1500 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.24 | HT cable termination | 28 | 22 | 6 | 78.57% | 11 Jul, 12 Jul, 22 Jul | 2026-07-22 | Pratibha | 8 | 0 | 6 | 0 | NO PROGRESS | 2026-07-30 18:00 | 1 | DELAYED | No team Deployed
[7 empty] | 3.25 | HT Cable Torquing & Marking | 28 | 0 | 28 | 0% | 11 Jul, 12 Jul, 22 Jul | 2026-07-20 | Pratibha | 15 | 0 | 28 | 0 | NO PROGRESS | 2026-07-31 20:48 | 2 | DELAYED
[7 empty] | 3.26 | FO Cable Internal Ring | 1021 | 877 | 144 | 85.9% | 2026-07-27 | 2026-07-20 | Pratibha | 600 | 0 | 144 | 0 | NO PROGRESS | 2026-07-30 05:46 | 1 | DELAYED
[7 empty] | 3.27 | DC Cable laying | 13780 | 13780 | 0 | 100% | 25 Jun, 1 Jul | 2026-07-01 | Pratibha | 600 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.28 | LT Cable laying | 45596 | 45596 | 0 | 100% | Completed | Completed | Pratibha | 600 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.29 | DC Cable termination | 1536 | 0 | 1536 | 0% | 15 Jul, 18 Jul, 25 Jul | 2026-07-25 | Pratibha | 30 | 0 | 1536 | 0 | NO PROGRESS | 2026-09-19 04:48 | 52 | DELAYED
[7 empty] | 3.3 | DC Cable Torquing & Marking | 1536 | 0 | 1536 | 0% | 15 Jul, 18 Jul, 25 Jul | 2026-07-25 | Pratibha | 150 | 0 | 1536 | 0 | NO PROGRESS | 2026-08-09 05:46 | 11 | DELAYED
[7 empty] | 3.31 | LT Cable termination | 2304 | 120 | 2184 | 5.208% | 15 Jul, 18 Jul, 25 Jul | 2026-07-27 | Pratibha | 30 | 0 | 2184 | 0 | NO PROGRESS | 2026-10-10 19:12 | 73 | DELAYED
[7 empty] | 3.32 | LT Cable Torquing & Marking | 2304 | 0 | 2304 | 0% | 15 Jul, 18 Jul, 25 Jul | 2026-07-25 | Pratibha | 150 | 0 | 2304 | 0 | NO PROGRESS | 2026-08-14 08:38 | 16 | DELAYED
[7 empty] | 3.33 | Aux Cable laying | 8413 | 6642 | 1771 | 78.95% | 05 Jul, 10 Jul, 20 Jul | 2026-07-20 | Pratibha | 800 | 0 | 1771 | 0 | NO PROGRESS | 2026-08-01 05:08 | 3 | DELAYED
[7 empty] | 3.34 | Control Cable laying | 14204 | 8437 | 5767 | 59.4% | 05 Jul, 11 Jul, 22 Jul | 2026-07-22 | Pratibha | 1000 | 0 | 5767 | 0 | NO PROGRESS | 2026-08-04 18:24 | 6 | DELAYED | No team deployed
[7 empty] | 3.35 | Communication Cable laying | 4792 | 0 | 4792 | 0% | 05 Jul, 12 Jul, 25 Jul | 2026-07-25 | Pratibha | 600 | 0 | 4792 | 0 | NO PROGRESS | 2026-08-06 23:41 | 8 | DELAYED | No team deployed
[7 empty] | 3.36 | Aux Cable termination | 286 | 0 | 286 | 0% | 7/15/2026, 25 Jul | 2026-07-25 | Pratibha | 30 | 0 | 286 | 0 | NO PROGRESS | 2026-08-08 12:48 | 10 | DELAYED | No team deployed
[7 empty] | 3.37 | Control Cable termination | 536 | 0 | 536 | 0% | 7/15/2026, 25 Jul | 2026-07-25 | Pratibha & Emerson | 30 | 0 | 536 | 0 | NO PROGRESS | 2026-08-16 20:48 | 18 | DELAYED | No front available. Pratibha to provide front
[7 empty] | 3.38 | Communication Cable termination | 384 | 0 | 384 | 0% | 7/15/2026, 25 Jul | 2026-07-25 | Pratibha & Emerson | 50 | 0 | 384 | 0 | NO PROGRESS | 2026-08-06 16:19 | 8 | DELAYED | No front available. Pratibha to provide front
[7 empty] | 3.39 | CT SFRA & Tan delta Test | 12 | 12 | 0 | 100% | Completed | Completed | Canbay |  | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.4 | CT Routine Test | 6 | 6 | 0 | 100% | 2026-07-04 | Completed | Pratibha | 2 | Completed | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 3.41 | CT Control scheme & Stability Test | 12 | 0 | 12 | 0% | 7/25/2026, 28 Jul | 2026-07-28 | Pratibha | 2 | 0 | 12 | 0 | NO PROGRESS | 2026-08-05 | 6 | DELAYED
[7 empty] | 3.42 | HT Panel Routine (CT & PT, Breaker & Meter) Test | 36 | 9 | 27 | 25% | 7/11/2026, 19 Jul | 2026-07-19 | Pratibha | 0.5 | 0 | 27 | 0 | NO PROGRESS | 2026-09-22 | 54 | DELAYED
[7 empty] | 3.43 | HT Panel relay test | 28 | 0 | 28 | 0% | 7/23/2026, 27 jul | 2026-07-27 | Pratibha | 6 | 0 | 28 | 0 | NO PROGRESS | 2026-08-03 16:00 | 5 | DELAYED
[7 empty] | 3.44 | HT Cable VLF Test | 14 | 7 | 7 | 50% | 7/11/2026, 18 jul | 2026-07-18 | Pratibha | 6 | 0 | 7 | 0 | NO PROGRESS | 2026-07-31 04:00 | 2 | DELAYED
[7 empty] | 3.45 | CSS routine test | 1 | 0 | 1 | 0% | 7/11/2026, 20 jul | 2026-07-20 | Pratibha | 1 | 0 | 1 | 0 | NO PROGRESS | 2026-07-31 | 1 | DELAYED
[7 empty] | 3.46 | ACDB routine test | 6 | 0 | 6 | 0% | 7/11/2026, 21 jul | 2026-07-21 | Pratibha | 3 | 0 | 6 | 0 | NO PROGRESS | 2026-08-01 | 2 | DELAYED
[7 empty] | 3.47 | Earthing - Earthing Strip | 4284 | 2344 | 1940 | 54.72% | 7/13/2026, 19 Jul | 2026-07-19 | Pratibha | 150 | 0 | 1940 | 0 | NO PROGRESS | 2026-08-11 22:24 | 13 | DELAYED
[7 empty] | 3.48 | Earthing - Earth Pit | 54 | 0 | 54 | 0% | 2026-07-26 | 2026-07-26 | Pratibha | 10 | 0 | 54 | 0 | NO PROGRESS | 2026-08-04 09:36 | 6 | DELAYED
[7 empty] | 3.49 | LA | 10 | 0 | 10 | 0% | 7/15/2026, 25 jul | 2026-07-25 | Pratibha | 5 | 0 | 10 | 0 | NO PROGRESS | 2026-08-01 | 2 | DELAYED | No team Deployed.
CATL | 2 | 2026-07-13 | 271 MWh (48 Containers) | 2026-08-06 | 2026-08-11 | 2026-08-14 |  |  |  | Civil | [10 empty] | Completed
[7 empty] | 2.01 | BCF Precast Erection & Welding |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed | #VALUE! | #VALUE! | COMPLETED
[7 empty] | 2.02 | CT Rail Fixing |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed | #VALUE! | #VALUE! | COMPLETED
[7 empty] | 2.03 | PCS Slab casting |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed | #VALUE! | #VALUE! | COMPLETED
[7 empty] | 2.04 | SGR Slab Casting |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed | #VALUE! | #VALUE! | COMPLETED
[7 empty] | 2.05 | MCR Slab Casting |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed | #VALUE! | #VALUE! | COMPLETED
[7 empty] | 2.06 | CSS Slab Casting |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed | #VALUE! | #VALUE! | COMPLETED
[7 empty] | 2.07 | BOT Slab casting |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed | #VALUE! | #VALUE! | COMPLETED
[7 empty] | 2.08 | BOT Precast Erection |  |  | 0 |  | Completed | - | Sachi | 1 | 0 | #VALUE! | 0 | Completed | #VALUE! | #VALUE! | COMPLETED
[7 empty] | 2.09 | NIFPS Precast Erection |  |  | 0 |  | 22 Jun, 02 Jul | 2026-07-02 | MSC | 1 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED | Cable trench excavated for cable laying, will be done post trench backfilling
[7 empty] | 2.1 | PCS PEB |  |  | 0 |  | Completed | - | Synergy | 1 | 0 | #VALUE! | 0 | Completed | #VALUE! | #VALUE! | COMPLETED
[7 empty] | 2.11 | SGR PEB |  |  | 0 |  | Completed | - | Synergy | 1 | 0 | #VALUE! | 0 | Completed | #VALUE! | #VALUE! | COMPLETED
[7 empty] | 2.12 | MCR PEB |  |  | 0 |  | 2026-07-01 | 2026-07-01 | RV Enterprise | 1 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[10 empty] | Electrical | [10 empty] | Completed
[7 empty] | 2.13 | CT Erection |  |  | 0 |  | Completed | - | Pratibha | 2 | 0 | #VALUE! | 0 | Completed | #VALUE! | #VALUE! | COMPLETED
[7 empty] | 2.14 | PCS Erection |  |  | 0 |  | 2026-07-06 | 2026-07-06 | Pratibha | 10 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED | 38 PCS placed on slab. Anchoring WIP
[7 empty] | 2.15 | ACDB Erection |  |  | 0 |  | 2026-07-09 | 2026-07-09 | Pratibha | 5 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.16 | ECP Panel Erection (Communication Panel) |  |  | 0 |  | 2026-07-06 | 2026-07-06 | Pratibha | 6 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.17 | HT Panel Erection |  |  | 0 |  | Completed | - | Pratibha | 1 | 0 | #VALUE! | 0 | Completed | #VALUE! | #VALUE! | COMPLETED
[7 empty] | 2.18 | EMS Panel Erection |  |  | 0 |  | 2026-07-05 | 2026-07-05 | Pratibha | 1 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.19 | CSS Erection |  |  | 0 |  | Completed | - | Pratibha | 1 | 0 | #VALUE! | 0 | Completed | #VALUE! | #VALUE! | COMPLETED
[7 empty] | 2.2 | NIFPS Panel Erection |  |  | 0 |  | 2026-07-11 | 2026-07-11 | Ornet / EMR | 6 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.21 | NIFPS Fabrication |  |  | 0 |  | 2026-07-15 | 2026-07-15 | Ornet | 0.66667 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.22 | Battery Container Erection |  |  | 0 |  | 2026-07-18 | 2026-07-18 | HEFT & Pratibha | 10 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.23 | HT cable laying |  |  | 0 |  | Completed | - | Pratibha | 1500 | 0 | #VALUE! | 0 | Completed | #VALUE! | #VALUE! | COMPLETED
[7 empty] | 2.24 | HT cable termination |  |  | 0 |  | 2026-07-20 | 2026-07-20 | Pratibha | 8 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED | 2 Termination Teams At site
[7 empty] | 2.25 | HT Cable Torquing & Marking | [7 empty] | 15 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.26 | FO Cable Internal Ring | [7 empty] | 600 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.27 | DC Cable laying |  |  | 0 |  | 2026-07-10 | 2026-07-10 | Pratibha | 600 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED | Required 60 Termination Teams with crimping
[7 empty] | 2.28 | LT Cable laying |  |  | 0 |  | Completed | - | Pratibha | 600 | 0 | #VALUE! | 0 | Completed | #VALUE! | #VALUE! | COMPLETED | Tools And 300 Termination per day
[7 empty] | 2.29 | DC Cable termination |  |  | 0 |  | 2026-07-24 | 2026-07-24 | Pratibha | 30 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.3 | DC Cable Torquing & Marking | [7 empty] | 150 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.31 | LT Cable termination |  |  | 0 |  | 2026-07-24 | 2026-07-24 | Pratibha | 30 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.32 | LT Cable Torquing & Marking | [7 empty] | 150 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.33 | Aux Cable laying |  |  | 0 |  | 2026-07-02 | 2026-07-02 | Pratibha | 800 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.34 | Control Cable laying |  |  | 0 |  | 2026-07-14 | 2026-07-14 | Pratibha | 1000 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.35 | Communication Cable laying |  |  | 0 |  | 2026-07-14 | 2026-07-14 | Pratibha | 600 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.36 | Aux Cable termination |  |  | 0 |  | 2026-07-24 | 2026-07-24 | Pratibha | 30 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.37 | Control Cable termination |  |  | 0 |  | 2026-07-24 | 2026-07-24 | Pratibha & Emerson | 30 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.38 | Communication Cable termination |  |  | 0 |  | 2026-07-24 | 2026-07-24 | Pratibha & Emerson | 50 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.39 | CT SFRA & Tan delta Test |  |  | 0 |  | Completed | - | Canbay |  | 0 | #VALUE! | 0 | Completed | #VALUE! | #VALUE! | COMPLETED
[7 empty] | 2.4 | CT Routine Test |  |  | 0 |  | 2026-07-13 | 2026-07-13 | Pratibha | 2 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.41 | CT Control scheme & Stability Test |  |  | 0 |  | 2026-08-03 | 2026-08-03 | Pratibha | 2 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.42 | HT Panel Routine (CT & PT, Breaker & Meter) Test |  |  | 0 |  | 2026-07-20 | 2026-07-20 | Pratibha | 0.5 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED | Pratibha: Available manpower - 30 nos Avg. required manpower - 95 nos
[7 empty] | 2.43 | HT Panel relay test |  |  | 0 |  | 2026-08-01 | 2026-08-01 | Pratibha | 6 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.44 | HT Cable VLF Test |  |  | 0 |  | 2026-07-20 | 2026-07-20 | Pratibha | 6 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.45 | CSS routine test |  |  | 0 |  | 2026-07-20 | 2026-07-20 | Pratibha | 1 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED | Machinery - Crimping tool: 10, Cable jack: 06, JCB: 06, Excavator: 01, Farana: 06, DG: 08, Welding machine: 10
[7 empty] | 2.46 | ACDB routine test |  |  | 0 |  | 2026-07-20 | 2026-07-20 | Pratibha | 3 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.47 | Earthing - Earthing Strip |  |  | 0 |  | 2026-07-22 | 2026-07-22 | Pratibha | 150 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
[7 empty] | 2.48 | Earthing - Earth Pit | 64 | 0 | 64 | 0% |  |  | Pratibha | 10 | 0 | 64 | 0 | NO PROGRESS | 2026-08-05 09:36 | 7 | NO EDC
[7 empty] | 2.49 | LA |  |  | 0 |  | 2026-07-24 | 2026-07-24 | Pratibha | 5 | 0 | 0 | 0 | Completed | Completed | 0 | COMPLETED
CATL | 1 | 2026-07-16 | 271 MWh (48 Containers) | 2026-08-09 | 2026-08-14 | 2026-08-17 |  |  |  | Civil
[7 empty] | 1.01 | BCF Precast Erection & Welding |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 1.02 | CT Rail Fixing |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 1.03 | PCS Slab casting |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 1.04 | SGR Slab Casting |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 1.05 | MCR Slab Casting |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 1.06 | CSS Slab Casting |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 1.07 | BOT Slab casting |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 1.08 | NIFPS Precast Erection |  |  | 0 |  | 24 Jun, 30 Jun | 2026-06-30 | MSC | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.09 | PCS PEB |  |  | 0 |  | Completed | - | Synergy | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 1.1 | SGR PEB |  |  | 0 |  | Completed | - | Synergy | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 1.11 | MCR PEB |  |  | 0 |  | 2026-07-01 | 2026-07-01 | RV Enterprise | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[10 empty] | Electrical | [6 empty] | 0 | 0 | 0 | Completed |  | #DIV/0! | COMPLETED
[7 empty] | 1.12 | CT Erection |  |  | 0 |  | Completed | - | Pratibha | 2 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 1.13 | PCS Erection |  |  | 0 |  | 2026-07-09 | 2026-07-09 | Pratibha | 10 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED | 24 PCS placed on slab, anchoring WIP
[7 empty] | 1.14 | ACDB Erection |  |  | 0 |  | Completed | - | Pratibha | 5 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 1.15 | ECP Panel Erection (Communication Panel) |  |  | 0 |  | 2026-07-09 | 2026-07-09 | Pratibha | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.16 | HT Panel Erection |  |  | 0 |  | Completed | - | Pratibha | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 1.17 | EMS Panel Erection |  |  | 0 |  | 2026-07-05 | 2026-07-05 | Pratibha | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.18 | CSS Erection |  |  | 0 |  | 2026-07-16 | 2026-07-16 | Pratibha | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.19 | NIFPS Panel Erection |  |  | 0 |  | 2026-07-15 | 2026-07-15 | Ornet / EMR | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.2 | NIFPS Fabrication |  |  | 0 |  | 2026-07-20 | 2026-07-20 | Ornet | 0.66667 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.21 | Battery Container Erection |  |  | 0 |  | 2026-07-21 | 2026-07-21 | HEFT & Pratibha | 10 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.22 | HT cable laying |  |  | 0 |  | 2026-07-07 | 2026-07-07 | Pratibha | 1500 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.23 | HT cable termination |  |  | 0 |  | 2026-07-12 | 2026-07-12 | Pratibha | 8 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED | 2 Termination Teams At site
[7 empty] | 1.24 | HT Cable Torquing & Marking | [7 empty] | 15 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.25 | FO Cable Internal Ring | [7 empty] | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.26 | DC Cable laying |  |  | 0 |  | 2026-07-13 | 2026-07-13 | Pratibha | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED | Required 60 Termination Teams with crimping
[7 empty] | 1.27 | LT Cable laying |  |  | 0 |  | 2026-07-07 | 2026-07-07 | Pratibha | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED | Tools And 350 Termination per day
[7 empty] | 1.28 | DC Cable termination |  |  | 0 |  | 2026-07-27 | 2026-07-27 | Pratibha | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.29 | DC Cable Torquing & Marking | [7 empty] | 150 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.3 | LT Cable termination |  |  | 0 |  | 2026-07-27 | 2026-07-27 | Pratibha | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.31 | LT Cable Torquing & Marking | [7 empty] | 150 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.32 | Aux Cable laying |  |  | 0 |  | 2026-07-17 | 2026-07-17 | Pratibha | 800 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.33 | Control Cable laying |  |  | 0 |  | 2026-07-17 | 2026-07-10 | Pratibha | 1000 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.34 | Communication Cable laying |  |  | 0 |  | 2026-07-17 | 2026-07-10 | Pratibha | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.35 | Aux Cable termination |  |  | 0 |  | 2026-07-27 | 2026-07-27 | Pratibha | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.36 | Control Cable termination |  |  | 0 |  | 2026-07-20 | 2026-07-20 | Pratibha & Emerson | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.37 | Communication Cable termination |  |  | 0 |  | 2026-07-20 | 2026-07-20 | Pratibha & Emerson | 50 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.38 | CT SFRA & Tan delta Test |  |  | 0 |  | Completed | - | Canbay |  | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 1.39 | CT Routine Test |  |  | 0 |  | 2026-07-16 | 2026-07-16 | Pratibha | 2 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.4 | CT Control scheme & Stability Test |  |  | 0 |  | 2026-08-06 | 2026-08-06 | Pratibha | 2 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.41 | HT Panel Routine (CT & PT, Breaker & Meter) Test |  |  | 0 |  | 2026-07-23 | 2026-07-23 | Pratibha | 0.5 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED | Pratibha: Available manpower - 41 nos Avg. required manpower - 98 nos
[7 empty] | 1.42 | HT Panel relay test |  |  | 0 |  | 2026-08-04 | 2026-08-04 | Pratibha | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.43 | HT Cable VLF Test |  |  | 0 |  | 2026-07-23 | 2026-07-23 | Pratibha | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.44 | CSS routine test |  |  | 0 |  | 2026-07-23 | 2026-07-23 | Pratibha | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED | Machinery - Crimping tool: 10, Cable jack: 06, JCB: 06, Excavator: 01, Farana: 06, DG: 08, Welding machine: 10
[7 empty] | 1.45 | ACDB routine test |  |  | 0 |  | 2026-07-23 | 2026-07-23 | Pratibha | 3 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.46 | Earthing - Earthing Strip |  |  | 0 |  | 2026-07-25 | 2026-07-25 | Pratibha | 150 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 1.47 | Earthing - Earth Pit | 73 | 0 | 73 | 0% |  |  | Pratibha | 10 | 0 | 73 | 0 | NO PROGRESS |  | 8 | NO EDC
[7 empty] | 1.48 | LA |  |  | 0 |  | 2026-07-27 | 2026-07-27 | Pratibha | 5 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
CATL | 5 | 2026-08-04 | 271 MWh (48 Containers) | 2026-08-28 | 2026-09-02 | 2026-09-05 |  |  |  | Civil
[7 empty] | 5.01 | BCF Precast Erection & Welding |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 5.02 | CT Rail Fixing |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 5.03 | PCS Slab casting |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 5.04 | SGR Slab Casting |  |  | 0 |  | 25 Jun, 30 Jun | 2026-06-30 | MSC | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.05 | MCR Slab Casting |  |  | 0 |  | 26 Jun, 30 Jun | 2026-06-30 | MSC | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.06 | CSS Slab Casting |  |  | 0 |  | 25 Jun, 28 Jun | 2026-06-28 | MSC | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.07 | BOT Precast Erection |  |  | 0 |  | Completed | - | Sachi | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 5.08 | NIFPS Precast Erection |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 5.09 | PCS PEB |  |  | 0 |  | 2026-07-07 | 2026-07-07 | Synergy | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.1 | SGR PEB |  |  | 0 |  | 2026-07-05 | 2026-07-05 | Synergy | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.11 | MCR PEB |  |  | 0 |  | 2026-07-06 | 2026-07-06 | RV Enterprise | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
Electrical
[7 empty] | 5.12 | CT Erection |  |  | 0 |  | Completed | - | Pratibha | 2 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 5.13 | PCS Erection |  |  | 0 |  | 2026-07-20 | 2026-07-20 | Pratibha | 10 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.14 | ACDB Erection |  |  | 0 |  | 2026-07-22 | 2026-07-22 | Pratibha | 5 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.15 | ECP Panel Erection (Communication Panel) |  |  | 0 |  | 2026-07-22 | 2026-07-22 | Pratibha | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.16 | HT Panel Erection |  |  | 0 |  | 2026-07-07 | 2026-07-07 | Pratibha | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.17 | EMS Panel Erection |  |  | 0 |  | 2026-07-10 | 2026-07-10 | Pratibha | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.18 | CSS Erection |  |  | 0 |  | 2026-07-10 | 2026-07-10 | Pratibha | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.19 | NIFPS Panel Erection |  |  | 0 |  | 2026-07-19 | 2026-07-19 | Ornet / EMR | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.2 | NIFPS Fabrication |  |  | 0 |  | 2026-07-24 | 2026-07-24 | Ornet | 0.66667 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.21 | Battery Container Erection |  |  | 0 |  | 2026-08-09 | 2026-08-09 | HEFT & Pratibha | 10 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.22 | HT cable laying |  |  | 0 |  | 2026-07-26 | 2026-07-26 | Pratibha | 1500 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.23 | HT cable termination |  |  | 0 |  | 2026-08-11 | 2026-08-11 | Pratibha | 8 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.24 | HT Cable Torquing & Marking | [7 empty] | 15 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.25 | FO Cable Internal Ring | [7 empty] | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.26 | DC Cable laying |  |  | 0 |  | 2026-08-01 | 2026-08-01 | Pratibha | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.27 | LT Cable laying |  |  | 0 |  | 2026-07-26 | 2026-07-26 | Pratibha | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.28 | DC Cable termination |  |  | 0 |  | 2026-08-15 | 2026-08-15 | Pratibha | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.29 | DC Cable Torquing & Marking | [7 empty] | 150 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.3 | LT Cable termination |  |  | 0 |  | 2026-08-15 | 2026-08-15 | Pratibha | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.31 | LT Cable Torquing & Marking | [7 empty] | 150 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.32 | Aux Cable laying |  |  | 0 |  | 2026-08-05 | 2026-08-05 | Pratibha | 800 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.33 | Control Cable laying |  |  | 0 |  | 2026-08-05 | 2026-08-05 | Pratibha | 1000 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.34 | Communication Cable laying |  |  | 0 |  | 2026-08-05 | 2026-08-05 | Pratibha | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.35 | Aux Cable termination |  |  | 0 |  | 2026-08-15 | 2026-08-15 | Pratibha | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.36 | Control Cable termination |  |  | 0 |  | 2026-08-15 | 2026-08-15 | Pratibha & Emerson | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.37 | Communication Cable termination |  |  | 0 |  | 2026-08-15 | 2026-08-15 | Pratibha & Emerson | 50 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.38 | CT SFRA & Tan delta Test |  |  | 0 |  | 2026-07-31 | 2026-07-31 | Canbay |  | 0 | 0 | 0 | Completed |  | #DIV/0! | COMPLETED
[7 empty] | 5.39 | CT Routine Test |  |  | 0 |  | 2026-08-04 | 2026-08-04 | Pratibha | 2 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.4 | CT Control scheme & Stability Test |  |  | 0 |  | 2026-08-25 | 2026-08-25 | Pratibha | 2 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.41 | HT Panel Routine (CT & PT, Breaker & Meter) Test |  |  | 0 |  | 2026-08-11 | 2026-08-11 | Pratibha | 0.5 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED | Pratibha: Avg. required manpower - 118 nos
[7 empty] | 5.42 | HT Panel relay test |  |  | 0 |  | 2026-08-23 | 2026-08-23 | Pratibha | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.43 | HT Cable VLF Test |  |  | 0 |  | 2026-08-11 | 2026-08-11 | Pratibha | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.44 | CSS routine test |  |  | 0 |  | 2026-08-11 | 2026-08-11 | Pratibha | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.45 | ACDB routine test |  |  | 0 |  | 2026-08-11 | 2026-08-11 | Pratibha | 3 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.46 | Earthing - Earthing Strip |  |  | 0 |  | 2026-08-13 | 2026-08-13 | Pratibha | 150 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 5.47 | Earthing - Earth Pit | 1 | 0 | 1 | 0% |  |  | Pratibha | 10 | 0 | 1 | 0 | NO PROGRESS |  | 1 | NO EDC
[7 empty] | 5.48 | LA |  |  | 0 |  | 2026-08-15 | 2026-08-15 | Pratibha | 5 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
CATL | 6 | 2026-08-09 | 271 MWh (48 Containers) | 2026-09-02 | 2026-09-07 | 2026-09-10 |  |  |  | Civil
[7 empty] | 6.01 | BCF Precast Erection & Welding |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 6.02 | CT Rail Fixing |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 6.03 | PCS Slab casting |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 6.04 | SGR Slab Casting |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 6.05 | MCR Slab Casting |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 6.06 | CSS Slab Casting |  |  | 0 |  | 28 Jun, 02 Jul | 2026-07-02 | MSC | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.07 | BOT Precast Erection |  |  | 0 |  | Completed | - | Sachi | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 6.08 | NIFPS Precast Erection |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 6.09 | PCS PEB |  |  | 0 |  | 2026-07-07 | 2026-07-07 | Synergy | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.1 | SGR PEB |  |  | 0 |  | 2026-07-05 | 2026-07-05 | Synergy | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.11 | MCR PEB |  |  | 0 |  | 2026-07-05 | 2026-07-05 | RV Enterprise | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
Electrical
[7 empty] | 6.12 | CT Erection |  |  | 0 |  | Completed | - | Pratibha | 2 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 6.13 | PCS Erection |  |  | 0 |  | 2026-08-02 | 2026-08-02 | Pratibha | 10 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.14 | ACDB Erection |  |  | 0 |  | 2026-08-05 | 2026-08-05 | Pratibha | 5 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.15 | ECP Panel Erection (Communication Panel) |  |  | 0 |  | 2026-08-02 | 2026-08-02 | Pratibha | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.16 | HT Panel Erection |  |  | 0 |  | 2026-07-02 | 2026-07-02 | Pratibha | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.17 | EMS Panel Erection |  |  | 0 |  | 2026-07-09 | 2026-08-09 | Pratibha | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.18 | CSS Erection |  |  | 0 |  | 2026-07-15 | 2026-07-15 | Pratibha | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.19 | NIFPS Panel Erection |  |  | 0 |  | 2026-07-23 | 2026-07-23 | Ornet / EMR | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.2 | NIFPS Fabrication |  |  | 0 |  | 2026-07-28 | 2026-07-28 | Ornet | 0.66667 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.21 | Battery Container Erection |  |  | 0 |  | 2026-08-14 | 2026-08-14 | HEFT & Pratibha | 10 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.22 | HT cable laying |  |  | 0 |  | 2026-07-31 | 2026-07-31 | Pratibha | 1500 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.23 | HT cable termination |  |  | 0 |  | 2026-08-16 | 2026-08-16 | Pratibha | 8 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.24 | HT Cable Torquing & Marking | [7 empty] | 15 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.25 | FO Cable Internal Ring | [7 empty] | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.26 | DC Cable laying |  |  | 0 |  | 2026-08-06 | 2026-08-06 | Pratibha | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.27 | LT Cable laying |  |  | 0 |  | 2026-07-31 | 2026-07-31 | Pratibha | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.28 | DC Cable termination |  |  | 0 |  | 2026-08-20 | 2026-08-20 | Pratibha | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.29 | DC Cable Torquing & Marking | [7 empty] | 150 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.3 | LT Cable termination |  |  | 0 |  | 2026-08-20 | 2026-08-20 | Pratibha | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.31 | LT Cable Torquing & Marking | [7 empty] | 150 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.32 | Aux Cable laying |  |  | 0 |  | 2026-08-10 | 2026-08-10 | Pratibha | 800 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.33 | Control Cable laying |  |  | 0 |  | 2026-08-10 | 2026-08-10 | Pratibha | 1000 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.34 | Communication Cable laying |  |  | 0 |  | 2026-08-10 | 2026-08-10 | Pratibha | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.35 | Aux Cable termination |  |  | 0 |  | 2026-08-20 | 2026-08-20 | Pratibha | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.36 | Control Cable termination |  |  | 0 |  | 2026-08-20 | 2026-08-20 | Pratibha & Emerson | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.37 | Communication Cable termination |  |  | 0 |  | 2026-08-20 | 2026-08-20 | Pratibha & Emerson | 50 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.38 | CT SFRA & Tan delta Test |  |  | 0 |  | 2026-08-05 | 2026-08-05 | Canbay |  | 0 | 0 | 0 | Completed |  | #DIV/0! | COMPLETED
[7 empty] | 6.39 | CT Routine Test |  |  | 0 |  | 2026-08-09 | 2026-08-09 | Pratibha | 2 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.4 | CT Control scheme & Stability Test |  |  | 0 |  | 2026-08-30 | 2026-08-30 | Pratibha | 2 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.41 | HT Panel Routine (CT & PT, Breaker & Meter) Test |  |  | 0 |  | 2026-08-16 | 2026-08-16 | Pratibha | 0.5 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED | Pratibha: Avg. required manpower - 106 nos
[7 empty] | 6.42 | HT Panel relay test |  |  | 0 |  | 2026-08-28 | 2026-08-28 | Pratibha | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.43 | HT Cable VLF Test |  |  | 0 |  | 2026-08-16 | 2026-08-16 | Pratibha | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.44 | CSS routine test |  |  | 0 |  | 2026-08-16 | 2026-08-16 | Pratibha | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.45 | ACDB routine test |  |  | 0 |  | 2026-08-16 | 2026-08-16 | Pratibha | 3 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.46 | Earthing - Earthing Strip |  |  | 0 |  | 2026-08-18 | 2026-08-18 | Pratibha | 150 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 6.47 | Earthing - Earth Pit | 1 | 0 | 1 | 0% |  |  | Pratibha | 10 | 0 | 1 | 0 | NO PROGRESS |  | 1 | NO EDC
[7 empty] | 6.48 | LA |  |  | 0 |  | 2026-08-20 | 2026-08-20 | Pratibha | 5 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
CATL | 7 | 2026-08-19 | 271 MWh (48 Containers) | 2026-09-12 | 2026-09-17 | 2026-09-20 |  |  |  | Civil
[7 empty] | 7.01 | BCF Precast Erection & Welding |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 7.02 | CT Rail Fixing |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 7.03 | PCS Slab casting |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 7.04 | SGR Slab Casting |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 7.05 | MCR Slab Casting |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 7.06 | CSS Slab Casting |  |  | 0 |  | 2026-06-29 | 2026-06-29 | MSC | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.07 | BOT Precast Erection |  |  | 0 |  | Completed | - | Sachi | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 7.08 | NIFPS Precast Erection |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 7.09 | PCS PEB |  |  | 0 |  | 2026-07-10 | 2026-07-10 | Synergy | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.1 | SGR PEB |  |  | 0 |  | 2026-07-10 | 2026-07-10 | Synergy | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.11 | MCR PEB |  |  | 0 |  | 2026-07-11 | 2026-07-11 | RV Enterprise | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
Electrical
[7 empty] | 7.12 | CT Erection |  |  | 0 |  | 2026-07-25 | 2026-07-25 | Pratibha | 2 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.13 | PCS Erection |  |  | 0 |  | 2026-07-25 | 2026-07-25 | Pratibha | 10 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.14 | ACDB Erection |  |  | 0 |  | 2026-07-30 | 2026-07-30 | Pratibha | 5 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.15 | ECP Panel Erection (Communication Panel) |  |  | 0 |  | 2026-07-30 | 2026-07-30 | Pratibha | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.16 | HT Panel Erection |  |  | 0 |  | 2026-08-05 | 2026-08-05 | Pratibha | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.17 | EMS Panel Erection |  |  | 0 |  | 2026-07-30 | 2026-07-30 | Pratibha | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.18 | CSS Erection |  |  | 0 |  | 2026-07-20 | 2026-07-20 | Pratibha | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.19 | NIFPS Panel Erection |  |  | 0 |  | 2026-07-27 | 2026-07-27 | Ornet / EMR | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.2 | NIFPS Fabrication |  |  | 0 |  | 2026-08-01 | 2026-08-01 | Ornet | 0.66667 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.21 | Battery Container Erection |  |  | 0 |  | 2026-08-24 | 2026-08-24 | HEFT & Pratibha | 10 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.22 | HT cable laying |  |  | 0 |  | 2026-08-10 | 2026-08-10 | Pratibha | 1500 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.23 | HT cable termination |  |  | 0 |  | 2026-08-26 | 2026-08-26 | Pratibha | 8 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.24 | HT Cable Torquing & Marking | [7 empty] | 15 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.25 | FO Cable Internal Ring | [7 empty] | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.26 | DC Cable laying |  |  | 0 |  | 2026-08-16 | 2026-08-16 | Pratibha | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.27 | LT Cable laying |  |  | 0 |  | 2026-08-10 | 2026-08-10 | Pratibha | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.28 | DC Cable termination |  |  | 0 |  | 2026-08-30 | 2026-08-30 | Pratibha | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.29 | DC Cable Torquing & Marking | [7 empty] | 150 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.3 | LT Cable termination |  |  | 0 |  | 2026-08-30 | 2026-08-30 | Pratibha | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.31 | LT Cable Torquing & Marking | [7 empty] | 150 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.32 | Aux Cable laying |  |  | 0 |  | 2026-08-20 | 2026-08-20 | Pratibha | 800 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.33 | Control Cable laying |  |  | 0 |  | 2026-08-20 | 2026-08-20 | Pratibha | 1000 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.34 | Communication Cable laying |  |  | 0 |  | 2026-08-20 | 2026-08-20 | Pratibha | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.35 | Aux Cable termination |  |  | 0 |  | 2026-08-30 | 2026-08-30 | Pratibha | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.36 | Control Cable termination |  |  | 0 |  | 2026-08-30 | 2026-08-30 | Pratibha & Emerson | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.37 | Communication Cable termination |  |  | 0 |  | 2026-08-30 | 2026-08-30 | Pratibha & Emerson | 50 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.38 | CT SFRA & Tan delta Test |  |  | 0 |  | 2026-08-15 | 2026-08-15 | Canbay |  | 0 | 0 | 0 | Completed |  | #DIV/0! | COMPLETED
[7 empty] | 7.39 | CT Routine Test |  |  | 0 |  | 2026-08-19 | 2026-08-19 | Pratibha | 2 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.4 | CT Control scheme & Stability Test |  |  | 0 |  | 2026-09-09 | 2026-09-09 | Pratibha | 2 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.41 | HT Panel Routine (CT & PT, Breaker & Meter) Test |  |  | 0 |  | 2026-08-26 | 2026-08-26 | Pratibha | 0.5 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED | Pratibha: Avg. required manpower - 117 nos
[7 empty] | 7.42 | HT Panel relay test |  |  | 0 |  | 2026-09-07 | 2026-09-07 | Pratibha | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.43 | HT Cable VLF Test |  |  | 0 |  | 2026-08-26 | 2026-08-26 | Pratibha | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.44 | CSS routine test |  |  | 0 |  | 2026-08-26 | 2026-08-26 | Pratibha | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.45 | ACDB routine test |  |  | 0 |  | 2026-08-26 | 2026-08-26 | Pratibha | 3 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.46 | Earthing - Earthing Strip |  |  | 0 |  | 2026-08-28 | 2026-08-28 | Pratibha | 150 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 7.47 | Earthing - Earth Pit | 1 | 0 | 1 | 0% |  |  | Pratibha | 10 | 0 | 1 | 0 | NO PROGRESS |  | 1 | NO EDC
[7 empty] | 7.48 | LA |  |  | 0 |  | 2026-08-30 | 2026-08-30 | Pratibha | 5 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
CATL | 8 | 2026-08-21 | 271 MWh (48 Containers) | 2026-09-14 | 2026-09-19 | 2026-09-22 |  |  |  | Civil
[7 empty] | 8.01 | BCF Precast Erection & Welding |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 8.02 | CT Rail Fixing |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 8.03 | PCS Slab casting |  |  | 0 |  | 2026-06-30 | 2026-06-30 | MSC | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.04 | SGR Slab Casting |  |  | 0 |  | 2026-06-27 | 2026-06-27 | MSC | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.05 | MCR Slab Casting |  |  | 0 |  | 2026-06-29 | 2026-06-29 | MSC | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.06 | CSS Slab Casting |  |  | 0 |  | 25-Jun, 04 Jul | 2026-07-04 | MSC | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.07 | BOT Precast Erection |  |  | 0 |  | Completed | - | Sachi | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 8.08 | NIFPS Precast Erection |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 8.09 | PCS PEB |  |  | 0 |  | 2026-07-15 | 2026-07-15 | Synergy | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.1 | SGR PEB |  |  | 0 |  | 2026-07-15 | 2026-07-15 | Synergy | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.11 | MCR PEB |  |  | 0 |  | 2026-07-15 | 2026-07-15 | RV Enterprise | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
Electrical
[7 empty] | 8.12 | CT Erection |  |  | 0 |  | 2026-07-30 | 2026-07-30 | Pratibha | 2 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.13 | PCS Erection |  |  | 0 |  | 2026-08-05 | 2026-08-05 | Pratibha | 10 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.14 | ACDB Erection |  |  | 0 |  | 2026-08-06 | 2026-08-06 | Pratibha | 5 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.15 | ECP Panel Erection (Communication Panel) |  |  | 0 |  | 2026-08-06 | 2026-08-06 | Pratibha | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.16 | HT Panel Erection |  |  | 0 |  | 2026-08-05 | 2026-08-05 | Pratibha | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.17 | EMS Panel Erection |  |  | 0 |  | 2026-07-31 | 2026-07-31 | Pratibha | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.18 | CSS Erection |  |  | 0 |  | 2026-08-10 | 2026-08-10 | Pratibha | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.19 | NIFPS Panel Erection |  |  | 0 |  | 2026-07-31 | 2026-07-31 | Ornet / EMR | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.2 | NIFPS Fabrication |  |  | 0 |  | 2026-08-05 | 2026-08-05 | Ornet | 0.66667 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.21 | Battery Container Erection |  |  | 0 |  | 2026-08-26 | 2026-08-26 | HEFT & Pratibha | 10 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.22 | HT cable laying |  |  | 0 |  | 2026-08-12 | 2026-08-12 | Pratibha | 1500 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.23 | HT cable termination |  |  | 0 |  | 2026-08-28 | 2026-08-28 | Pratibha | 8 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.24 | HT Cable Torquing & Marking | [7 empty] | 15 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.25 | FO Cable Internal Ring | [7 empty] | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.26 | DC Cable laying |  |  | 0 |  | 2026-08-18 | 2026-08-18 | Pratibha | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.27 | LT Cable laying |  |  | 0 |  | 2026-08-12 | 2026-08-12 | Pratibha | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.28 | DC Cable termination |  |  | 0 |  | 2026-09-01 | 2026-09-01 | Pratibha | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.29 | DC Cable Torquing & Marking | [7 empty] | 150 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.3 | LT Cable termination |  |  | 0 |  | 2026-09-01 | 2026-09-01 | Pratibha | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.31 | LT Cable Torquing & Marking | [7 empty] | 150 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.32 | Aux Cable laying |  |  | 0 |  | 2026-08-22 | 2026-08-22 | Pratibha | 800 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.33 | Control Cable laying |  |  | 0 |  | 2026-08-22 | 2026-08-22 | Pratibha | 1000 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.34 | Communication Cable laying |  |  | 0 |  | 2026-08-22 | 2026-08-22 | Pratibha | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.35 | Aux Cable termination |  |  | 0 |  | 2026-09-01 | 2026-09-01 | Pratibha | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.36 | Control Cable termination |  |  | 0 |  | 2026-09-01 | 2026-09-01 | Pratibha & Emerson | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.37 | Communication Cable termination |  |  | 0 |  | 2026-09-01 | 2026-09-01 | Pratibha & Emerson | 50 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.38 | CT SFRA & Tan delta Test |  |  | 0 |  | 2026-08-17 | 2026-08-17 | Canbay |  | 0 | 0 | 0 | Completed |  | #DIV/0! | COMPLETED
[7 empty] | 8.39 | CT Routine Test |  |  | 0 |  | 2026-08-21 | 2026-08-21 | Pratibha | 2 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.4 | CT Control scheme & Stability Test |  |  | 0 |  | 2026-09-11 | 2026-09-11 | Pratibha | 2 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.41 | HT Panel Routine (CT & PT, Breaker & Meter) Test |  |  | 0 |  | 2026-08-28 | 2026-08-28 | Pratibha | 0.5 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED | Pratibha: Avg. required manpower - 111 nos
[7 empty] | 8.42 | HT Panel relay test |  |  | 0 |  | 2026-09-09 | 2026-09-09 | Pratibha | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.43 | HT Cable VLF Test |  |  | 0 |  | 2026-08-28 | 2026-08-28 | Pratibha | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.44 | CSS routine test |  |  | 0 |  | 2026-08-28 | 2026-08-28 | Pratibha | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.45 | ACDB routine test |  |  | 0 |  | 2026-08-28 | 2026-08-28 | Pratibha | 3 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.46 | Earthing - Earthing Strip |  |  | 0 |  | 2026-08-30 | 2026-08-30 | Pratibha | 150 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 8.47 | Earthing - Earth Pit | 1021 | 0 | 1021 | 0% |  |  | Pratibha | 10 | 0 | 1021 | 0 | NO PROGRESS |  | 103 | NO EDC
[7 empty] | 8.48 | LA |  |  | 0 |  | 2026-09-01 | 2026-09-01 | Pratibha | 5 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
CATL | 9 | 2026-08-22 | 271 MWh (48 Containers) | 2026-09-15 | 2026-09-20 | 2026-09-23 |  |  |  | Civil
[7 empty] | 9.01 | BCF Precast Erection & Welding |  |  | 0 |  | Completed | - | MSC | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 9.02 | CT Rail Fixing |  |  | 0 |  | 30-Jun, 06 Jul | 2026-07-06 | MSC | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.03 | PCS Slab casting |  |  | 0 |  | 2026-07-05 | 2026-07-05 | MSC | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.04 | SGR Slab Casting |  |  | 0 |  | 2026-07-03 | 2026-07-03 | MSC | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.05 | MCR Slab Casting |  |  | 0 |  | 2026-07-07 | 2026-07-07 | MSC | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.06 | CSS Slab Casting |  |  | 0 |  | 2026-07-10 | 2026-07-10 | MSC | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.07 | BOT Precast Erection |  |  | 0 |  | Completed | - | Sachi | 1 | 0 | #VALUE! | 0 | Completed |  | #VALUE! | COMPLETED
[7 empty] | 9.08 | NIFPS Precast Erection |  |  | 0 |  | 2026-06-30 | 2026-06-30 | MSC | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.09 | PCS PEB |  |  | 0 |  | 2026-07-16 | 2026-07-16 | Synergy | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.1 | SGR PEB |  |  | 0 |  | 2026-07-16 | 2026-07-16 | Synergy | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.11 | MCR PEB |  |  | 0 |  | 2026-07-21 | 2026-07-21 | RV Enterprise | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
Electrical
[7 empty] | 9.12 | CT Erection |  |  | 0 |  | 2026-08-15 | 2026-08-15 | Pratibha | 2 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.13 | PCS Erection |  |  | 0 |  | 2026-08-15 | 2026-08-15 | Pratibha | 10 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.14 | ACDB Erection |  |  | 0 |  | 2026-08-18 | 2026-08-18 | Pratibha | 5 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.15 | ECP Panel Erection (Communication Panel) |  |  | 0 |  | 2026-08-15 | 2026-08-15 | Pratibha | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.16 | HT Panel Erection |  |  | 0 |  | 2026-08-15 | 2026-08-15 | Pratibha | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.17 | EMS Panel Erection |  |  | 0 |  | 2026-08-22 | 2026-08-22 | Pratibha | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.18 | CSS Erection |  |  | 0 |  | 2026-08-22 | 2026-08-22 | Pratibha | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.19 | NIFPS Panel Erection |  |  | 0 |  | 2026-08-04 | 2026-08-04 | Ornet / EMR | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.2 | NIFPS Fabrication |  |  | 0 |  | 2026-08-09 | 2026-08-09 | Ornet | 0.66667 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.21 | Battery Container Erection |  |  | 0 |  | 2026-08-27 | 2026-08-27 | HEFT & Pratibha | 10 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.22 | HT cable laying |  |  | 0 |  | 2026-08-13 | 2026-08-13 | Pratibha | 1500 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.23 | HT cable termination |  |  | 0 |  | 2026-08-29 | 2026-08-29 | Pratibha | 8 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.24 | HT Cable Torquing & Marking | [7 empty] | 15 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.25 | FO Cable Internal Ring | [7 empty] | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.26 | DC Cable laying |  |  | 0 |  | 2026-08-19 | 2026-08-19 | Pratibha | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.27 | LT Cable laying |  |  | 0 |  | 2026-08-13 | 2026-08-13 | Pratibha | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.28 | DC Cable termination |  |  | 0 |  | 2026-09-02 | 2026-09-02 | Pratibha | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.29 | DC Cable Torquing & Marking | [7 empty] | 150 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.3 | LT Cable termination |  |  | 0 |  | 2026-09-02 | 2026-09-02 | Pratibha | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.31 | LT Cable Torquing & Marking | [7 empty] | 150 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.32 | Aux Cable laying |  |  | 0 |  | 2026-08-23 | 2026-08-23 | Pratibha | 800 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.33 | Control Cable laying |  |  | 0 |  | 2026-08-23 | 2026-08-23 | Pratibha | 1000 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.34 | Communication Cable laying |  |  | 0 |  | 2026-08-23 | 2026-08-23 | Pratibha | 600 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.35 | Aux Cable termination |  |  | 0 |  | 2026-09-02 | 2026-09-02 | Pratibha | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.36 | Control Cable termination |  |  | 0 |  | 2026-09-02 | 2026-09-02 | Pratibha & Emerson | 30 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.37 | Communication Cable termination |  |  | 0 |  | 2026-09-02 | 2026-09-02 | Pratibha & Emerson | 50 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.38 | CT SFRA & Tan delta Test |  |  | 0 |  | 2026-08-18 | 2026-08-18 | Canbay |  | 0 | 0 | 0 | Completed |  | #DIV/0! | COMPLETED
[7 empty] | 9.39 | CT Routine Test |  |  | 0 |  | 2026-08-22 | 2026-08-22 | Pratibha | 2 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.4 | CT Control scheme & Stability Test |  |  | 0 |  | 2026-09-12 | 2026-09-12 | Pratibha | 2 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.41 | HT Panel Routine (CT & PT, Breaker & Meter) Test |  |  | 0 |  | 2026-08-29 | 2026-08-29 | Pratibha | 0.5 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED | Pratibha: Avg. required manpower - 112 nos
[7 empty] | 9.42 | HT Panel relay test |  |  | 0 |  | 2026-09-10 | 2026-09-10 | Pratibha | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.43 | HT Cable VLF Test |  |  | 0 |  | 2026-08-29 | 2026-08-29 | Pratibha | 6 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.44 | CSS routine test |  |  | 0 |  | 2026-08-29 | 2026-08-29 | Pratibha | 1 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.45 | ACDB routine test |  |  | 0 |  | 2026-08-29 | 2026-08-29 | Pratibha | 3 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.46 | Earthing - Earthing Strip |  |  | 0 |  | 2026-08-31 | 2026-08-31 | Pratibha | 150 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
[7 empty] | 9.47 | Earthing - Earth Pit | 140 | 0 | 140 | 0% |  |  | Pratibha | 10 | 0 | 140 | 0 | NO PROGRESS |  | 14 | NO EDC
[7 empty] | 9.48 | LA |  |  | 0 |  | 2026-09-02 | 2026-09-02 | Pratibha | 5 | 0 | 0 | 0 | Completed |  | 0 | COMPLETED
Assumptions:-
1. Ship berthing + 72 hrs - clearing of 30 containers per day for site
2. 30 containers erected on site on 4th day
3. IDT charging = 24 days from erection of last container in the block
4. Trial run start date = IDT charging + 3 days
5. Trial run end date = Trial run start date + 2 days
6. COD = Trial run end date + 2 days
Formulas:
Forcasted Date = IF(T6=0,"Completed",TODAY()+[B]/R6)
EDC = [EDC, row above]+4
New EDC = IFERROR(DATEVALUE(TRIM(TEXTAFTER([EDC],",",-1))&"-"&YEAR(TODAY())),[EDC])
New EDC = [New EDC, row below]-21

## Sheet1
Forecasted IDT Charging Date
Activity | Block-4 | Block-3
SCADA Readiness | 2026-07-24 | 2026-07-26
Relay, Control scheme, Stability Test | 2026-07-26 | 2026-07-28
SFQP signoff & CFT | 2026-07-28 | 2026-07-30
IDT Charging | 2026-07-28 | 2026-08-01
sn
Formulas:
Block-4 = [Block-4, row above]+2
Block-4 = [Block-4, row above]
Block-3 = [Block-3, row above]+2

## Productivity Tracking
Productivity Tracker |  |  | Date
2026-07-30
Container Make | Block No. | Sr. | Activity | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-27 | 2025-12-28 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 | 2026-11-29 | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 2026-12-06 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-12 | 2026-12-13 | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-19 | 2026-12-20 | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-26 | 2026-12-27 | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31 | 2027-01-01 | 2027-01-02 | 2027-01-03 | 2027-01-04 | 2027-01-05 | 2027-01-06 | 2027-01-07 | 2027-01-08 | 2027-01-09 | 2027-01-10 | 2027-01-11 | 2027-01-12 | 2027-01-13 | 2027-01-14 | 2027-01-15 | 2027-01-16 | 2027-01-17 | 2027-01-18 | 2027-01-19 | 2027-01-20 | 2027-01-21 | 2027-01-22 | 2027-01-23 | 2027-01-24 | 2027-01-25 | 2027-01-26 | 2027-01-27 | 2027-01-28 | 2027-01-29 | 2027-01-30 | 2027-01-31 | 2027-02-01 | 2027-02-02 | 2027-02-03 | 2027-02-04 | 2027-02-05 | 2027-02-06 | 2027-02-07 | 2027-02-08 | 2027-02-09 | 2027-02-10 | 2027-02-11 | 2027-02-12 | 2027-02-13 | 2027-02-14 | 2027-02-15 | 2027-02-16 | 2027-02-17 | 2027-02-18 | 2027-02-19 | 2027-02-20 | 2027-02-21 | 2027-02-22 | 2027-02-23 | 2027-02-24 | 2027-02-25 | 2027-02-26 | 2027-02-27 | 2027-02-28 | 2027-03-01 | 2027-03-02 | 2027-03-03 | 2027-03-04 | 2027-03-05 | 2027-03-06 | 2027-03-07 | 2027-03-08 | 2027-03-09 | 2027-03-10 | 2027-03-11 | 2027-03-12 | 2027-03-13 | 2027-03-14 | 2027-03-15 | 2027-03-16 | 2027-03-17 | 2027-03-18 | 2027-03-19 | 2027-03-20 | 2027-03-21 | 2027-03-22 | 2027-03-23 | 2027-03-24 | 2027-03-25 | 2027-03-26 | 2027-03-27 | 2027-03-28 | 2027-03-29 | 2027-03-30 | 2027-03-31
|  |  |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed
CATL | 4 | Civil
|  | 4.1 | BCF Precast Erection & Welding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.2 | CT Rail Fixing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.3 | PCS Slab casting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.4 | SGR Slab Casting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.5 | MCR Slab Casting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.6 | CSS Slab Casting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.7 | BOT Slab casting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.8 | NIFPS Precast Erection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.9 | PCS PEB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.1 | SGR PEB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.11 | MCR PEB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Electrical
|  | 4.12 | CT Erection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.13 | PCS Erection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.14 | ACDB Erection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.15 | ECP Panel Erection (Communication Panel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.16 | HT Panel Erection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.17 | EMS Panel Erection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.18 | CSS Erection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.19 | NIFPS Panel Erection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.2 | NIFPS Fabrication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.21 | Battery Container Erection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 18 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.22 | HT cable laying | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 173 | 0 | 351 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.23 | HT cable termination | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 3 | 4 | 1 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.24 | HT Cable Torquing & Marking | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.25 | FO Cable Internal Ring | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.26 | DC Cable laying | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2224 | 0 | 950 | 0 | 0 | 0 | 6624 | 3520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.27 | LT Cable laying | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2712 | 0 | 0 | 2800 | 2871 | 2753 | 0 | 0 | 0 | 0 | 2928 | 2784 | 0 | 1776 | 5052 | 0 | 0 | 1776 | 6180 | 4856 | 4744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.28 | DC Cable termination | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 528 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 0 | 128 | 64 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.29 | DC Cable Torquing & Marking | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384 | 0 | 0 | 0 | 1136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.3 | LT Cable termination | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 432 | 168 | 40 | 280 | 400 | 384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.31 | LT Cable Torquing & Marking | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192 | 0 | 384 | 720 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.32 | Aux Cable laying | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1040 | 0 | 232 | 1408 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223 | 0 | 0 | 0 | 0 | 671 | 447 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 14 | 0 | 0 | 0 | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.33 | Control Cable laying | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2779 | 4330 | 1006 | 0 | 996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1011 | 285 | 0 | 0 | 705 | 246 | 225 | 0 | 0 | 0 | 0 | 0 | 1595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.34 | Communication Cable laying | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 545 | 0 | 3646 | 238 | 520 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.35 | Aux Cable Termination | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 24 | 40 | 56 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.36 | Control Cable Termination | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.37 | Communication Cable Termination | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.38 | CT SFRA & Tan delta Test | Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 2; Fri: 4; Sat: 0; Sun: 0; Mon: 0; Tue: 2; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 2; Tue: 0; Wed: 2; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0
|  | 4.39 | CT Routine Test | Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 2; Wed: 2; Thu: 2; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0
|  | 4.4 | CT Control scheme & Stability Test | Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 6; Fri: 0; Sat: 0; Sun: 2; Mon: 3; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0
|  | 4.41 | HT Panel Routine (CT & PT, Breaker & Meter) Test | Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 12; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 12; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0
|  | 4.42 | HT Panel relay test | Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 15; Fri: 1; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0
|  | 4.43 | HT Cable VLF Test | Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 4; Mon: 4; Tue: 6; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0
|  | 4.44 | CSS routine test | Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0
|  | 4.45 | ACDB routine test | Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 2; Mon: 0; Tue: 4; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0
|  | 4.46 | Earthing - Earthing Strip | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 217 | 0 | 0 | 113 | 0 | 270 | 100 | 0 | 0 | 0 | 71 | 288 | 400 | 0 | 0 | 71 | 0 | 35 | 187 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2514 | 0 | 0 | 0 | 0 | 0 | 0 | 436.7 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.47 | Earthing - Earth Pit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.48 | LA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CATL | 3 | Civil
|  | 3.1 | BCF Precast Erection & Welding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 2 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.2 | CT Rail Fixing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.3 | PCS Slab casting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.4 | SGR Slab Casting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.5 | MCR Slab Casting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.6 | CSS Slab Casting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.7 | BOT Slab casting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.8 | BOT Precast Erection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.9 | NIFPS Precast Erection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.1 | PCS PEB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.11 | SGR PEB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.12 | MCR PEB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Electrical
|  | 3.13 | CT Erection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.14 | PCS Erection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.15 | ACDB Erection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.16 | ECP Panel Erection (Communication Panel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.17 | HT Panel Erection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.18 | EMS Panel Erection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.19 | CSS Erection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.2 | NIFPS Panel Erection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.21 | NIFPS Fabrication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.22 | Battery Container Erection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 11 | 11 | 4 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.23 | HT cable laying | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 331 | 310 | 450 | 500 | 500 | 654 | 450 | 600 | 350 | 240 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 470 | 540 | 0 | 0 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.24 | HT cable termination | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 3 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.25 | HT Cable Torquing & Marking | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.26 | FO Cable Internal Ring | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.27 | DC Cable laying | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2272 | 0 | 2400 | 3408 | 2320 | 2160 | 0 | 0 | 1172 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.28 | LT Cable laying | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3744 | 3836 | 0 | 0 | 0 | 0 | 1824 | 4524 | 7296 | 3552 | 0 | 0 | 4500 | 5376 | 5568 | 5376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.29 | DC Cable termination | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.3 | DC Cable Torquing & Marking | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.31 | LT Cable termination | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.32 | LT Cable Torquing & Marking | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.33 | Aux Cable laying | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 861 | 0 | 0 | 579 | 0 | 835 | 0 | 508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 832 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290 | 0 | 0 | 0 | 495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.34 | Control Cable laying | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4227 | 1040 | 973 | 2197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.35 | Communication Cable laying | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.36 | Aux Cable Termination | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.37 | Control Cable Termination | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.38 | Communication Cable Termination | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.39 | CT SFRA & Tan delta Test | Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 2; Tue: 4; Wed: 2; Thu: 0; Fri: 0; Sat: 2; Sun: 0; Mon: 0; Tue: 0; Wed: 2; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0
|  | 3.4 | CT Routine Test | Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 2; Sat: 3; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 1; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0
|  | 3.41 | CT Control scheme & Stability Test | Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0
|  | 3.42 | HT Panel Routine (CT & PT, Breaker & Meter) Test | Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 9; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0
|  | 3.43 | HT Panel relay test | Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0
|  | 3.44 | HT Cable VLF Test | Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 7; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0
|  | 3.45 | CSS routine test | Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0
|  | 3.46 | ACDB routine test | Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0; Thu: 0; Fri: 0; Sat: 0; Sun: 0
|  | 3.47 | Earthing - Earthing Strip | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 60 | 0 | 189 | 0 | 0 | 0 | 0 | 0 | 350 | 71 | 0 | 0 | 0 | 0 | 71 | 0 | 35 | 96 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.48 | Earthing - Earth Pit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.49 | LA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CATL | 2 | Civil
|  | 2.1 | BCF Precast Erection & Welding
|  | 2.2 | CT Rail Fixing
|  | 2.3 | PCS Slab casting
|  | 2.4 | SGR Slab Casting
|  | 2.5 | MCR Slab Casting
|  | 2.6 | CSS Slab Casting
|  | 2.7 | BOT Slab casting
|  | 2.8 | BOT Precast Erection
|  | 2.9 | NIFPS Precast Erection
|  | 2.1 | PCS PEB
|  | 2.11 | SGR PEB
|  | 2.12 | MCR PEB
Electrical
|  | 2.13 | CT Erection
|  | 2.14 | PCS Erection
|  | 2.15 | ACDB Erection
|  | 2.16 | ECP Panel Erection (Communication Panel)
|  | 2.17 | HT Panel Erection
|  | 2.18 | EMS Panel Erection
|  | 2.19 | CSS Erection
|  | 2.2 | NIFPS Panel Erection
|  | 2.21 | NIFPS Fabrication
|  | 2.22 | Battery Container Erection
|  | 2.23 | HT cable laying
|  | 2.24 | HT cable termination
|  | 2.25 | HT Cable Torquing & Marking
|  | 2.26 | FO Cable Internal Ring
|  | 2.27 | DC Cable laying
|  | 2.28 | LT Cable laying
|  | 2.29 | DC Cable termination
|  | 2.3 | DC Cable Torquing & Marking
|  | 2.31 | LT Cable termination
|  | 2.32 | LT Cable Torquing & Marking
|  | 2.33 | Aux Cable laying
|  | 2.34 | Control Cable laying
|  | 2.35 | Communication Cable laying
|  | 2.36 | Aux Cable Termination
|  | 2.37 | Control Cable Termination
|  | 2.38 | Communication Cable Termination
|  | 2.39 | CT SFRA & Tan delta Test
|  | 2.4 | CT Routine Test
|  | 2.41 | CT Control scheme & Stability Test
|  | 2.42 | HT Panel Routine (CT & PT, Breaker & Meter) Test
|  | 2.43 | HT Panel relay test
|  | 2.44 | HT Cable VLF Test
|  | 2.45 | CSS routine test
|  | 2.46 | ACDB routine test
|  | 2.47 | Earthing
|  | 2.48 | LA
CATL | 1 | Civil
|  | 1.1 | BCF Precast Erection & Welding
|  | 1.2 | CT Rail Fixing
|  | 1.3 | PCS Slab casting
|  | 1.4 | SGR Slab Casting
|  | 1.5 | MCR Slab Casting
|  | 1.6 | CSS Slab Casting
|  | 1.7 | BOT Slab casting
|  | 1.8 | NIFPS Precast Erection
|  | 1.9 | PCS PEB
|  | 1.1 | SGR PEB
|  | 1.11 | MCR PEB
Electrical
|  | 1.12 | CT Erection
|  | 1.13 | PCS Erection
|  | 1.14 | ACDB Erection
|  | 1.15 | ECP Panel Erection (Communication Panel)
|  | 1.16 | HT Panel Erection
|  | 1.17 | EMS Panel Erection
|  | 1.18 | CSS Erection
|  | 1.19 | NIFPS Panel Erection
|  | 1.2 | NIFPS Fabrication
|  | 1.21 | Battery Container Erection
|  | 1.22 | HT cable laying
|  | 1.23 | HT cable termination
|  | 1.24 | HT Cable Torquing & Marking
|  | 1.25 | FO Cable Internal Ring
|  | 1.26 | DC Cable laying
|  | 1.27 | LT Cable laying
|  | 1.28 | DC Cable termination
|  | 1.29 | DC Cable Torquing & Marking
|  | 1.3 | LT Cable termination
|  | 1.31 | LT Cable Torquing & Marking
|  | 1.32 | Aux Cable laying
|  | 1.33 | Control Cable laying
|  | 1.34 | Communication Cable laying
|  | 1.35 | Aux Cable Termination
|  | 1.36 | Control Cable Termination
|  | 1.37 | Communication Cable Termination
|  | 1.38 | CT SFRA & Tan delta Test
|  | 1.39 | CT Routine Test
|  | 1.4 | CT Control scheme & Stability Test
|  | 1.41 | HT Panel Routine (CT & PT, Breaker & Meter) Test
|  | 1.42 | HT Panel relay test
|  | 1.43 | HT Cable VLF Test
|  | 1.44 | CSS routine test
|  | 1.45 | ACDB routine test
|  | 1.46 | Earthing
|  | 1.47 | LA
CATL | 5 | Civil
|  | 5.1 | BCF Precast Erection & Welding
|  | 5.2 | CT Rail Fixing
|  | 5.3 | PCS Slab casting
|  | 5.4 | SGR Slab Casting
|  | 5.5 | MCR Slab Casting
|  | 5.6 | CSS Slab Casting
|  | 5.7 | BOT Precast Erection
|  | 5.8 | NIFPS Precast Erection
|  | 5.9 | PCS PEB
|  | 5.1 | SGR PEB
|  | 5.11 | MCR PEB
Electrical
|  | 5.12 | CT Erection
|  | 5.13 | PCS Erection
|  | 5.14 | ACDB Erection
|  | 5.15 | ECP Panel Erection (Communication Panel)
|  | 5.16 | HT Panel Erection
|  | 5.17 | EMS Panel Erection
|  | 5.18 | CSS Erection
|  | 5.19 | NIFPS Panel Erection
|  | 5.2 | NIFPS Fabrication
|  | 5.21 | Battery Container Erection
|  | 5.22 | HT cable laying
|  | 5.23 | HT cable termination
|  | 5.24 | HT Cable Torquing & Marking
|  | 5.25 | FO Cable Internal Ring
|  | 5.26 | DC Cable laying
|  | 5.27 | LT Cable laying
|  | 5.28 | DC Cable termination
|  | 5.29 | DC Cable Torquing & Marking
|  | 5.3 | LT Cable termination
|  | 5.31 | LT Cable Torquing & Marking
|  | 5.32 | Aux Cable laying
|  | 5.33 | Control Cable laying
|  | 5.34 | Communication Cable laying
|  | 5.35 | Aux Cable Termination
|  | 5.36 | Control Cable Termination
|  | 5.37 | Communication Cable Termination
|  | 5.38 | CT SFRA & Tan delta Test
|  | 5.39 | CT Routine Test
|  | 5.4 | CT Control scheme & Stability Test
|  | 5.41 | HT Panel Routine (CT & PT, Breaker & Meter) Test
|  | 5.42 | HT Panel relay test
|  | 5.43 | HT Cable VLF Test
|  | 5.44 | CSS routine test
|  | 5.45 | ACDB routine test
|  | 5.46 | Earthing
|  | 5.47 | LA
CATL | 6 | Civil
|  | 6.1 | BCF Precast Erection & Welding
|  | 6.2 | CT Rail Fixing
|  | 6.3 | PCS Slab casting
|  | 6.4 | SGR Slab Casting
|  | 6.5 | MCR Slab Casting
|  | 6.6 | CSS Slab Casting
|  | 6.7 | BOT Precast Erection
|  | 6.8 | NIFPS Precast Erection
|  | 6.9 | PCS PEB
|  | 6.1 | SGR PEB
|  | 6.11 | MCR PEB
Electrical
|  | 6.12 | CT Erection
|  | 6.13 | PCS Erection
|  | 6.14 | ACDB Erection
|  | 6.15 | ECP Panel Erection (Communication Panel)
|  | 6.16 | HT Panel Erection
|  | 6.17 | EMS Panel Erection
|  | 6.18 | CSS Erection
|  | 6.19 | NIFPS Panel Erection
|  | 6.2 | NIFPS Fabrication
|  | 6.21 | Battery Container Erection
|  | 6.22 | HT cable laying
|  | 6.23 | HT cable termination
|  | 6.24 | HT Cable Torquing & Marking
|  | 6.25 | FO Cable Internal Ring
|  | 6.26 | DC Cable laying
|  | 6.27 | LT Cable laying
|  | 6.28 | DC Cable termination
|  | 6.29 | DC Cable Torquing & Marking
|  | 6.3 | LT Cable termination
|  | 6.31 | LT Cable Torquing & Marking
|  | 6.32 | Aux Cable laying
|  | 6.33 | Control Cable laying
|  | 6.34 | Communication Cable laying
|  | 6.35 | Aux Cable Termination
|  | 6.36 | Control Cable Termination
|  | 6.37 | Communication Cable Termination
|  | 6.38 | CT SFRA & Tan delta Test
|  | 6.39 | CT Routine Test
|  | 6.4 | CT Control scheme & Stability Test
|  | 6.41 | HT Panel Routine (CT & PT, Breaker & Meter) Test
|  | 6.42 | HT Panel relay test
|  | 6.43 | HT Cable VLF Test
|  | 6.44 | CSS routine test
|  | 6.45 | ACDB routine test
|  | 6.46 | Earthing
|  | 6.47 | LA
CATL | 7 | Civil
|  | 7.1 | BCF Precast Erection & Welding
|  | 7.2 | CT Rail Fixing
|  | 7.3 | PCS Slab casting
|  | 7.4 | SGR Slab Casting
|  | 7.5 | MCR Slab Casting
|  | 7.6 | CSS Slab Casting
|  | 7.7 | BOT Precast Erection
|  | 7.8 | NIFPS Precast Erection
|  | 7.9 | PCS PEB
|  | 7.1 | SGR PEB
|  | 7.11 | MCR PEB
Electrical
|  | 7.12 | CT Erection
|  | 7.13 | PCS Erection
|  | 7.14 | ACDB Erection
|  | 7.15 | ECP Panel Erection (Communication Panel)
|  | 7.16 | HT Panel Erection
|  | 7.17 | EMS Panel Erection
|  | 7.18 | CSS Erection
|  | 7.19 | NIFPS Panel Erection
|  | 7.2 | NIFPS Fabrication
|  | 7.21 | Battery Container Erection
|  | 7.22 | HT cable laying
|  | 7.23 | HT cable termination
|  | 7.24 | HT Cable Torquing & Marking
|  | 7.25 | FO Cable Internal Ring
|  | 7.26 | DC Cable laying
|  | 7.27 | LT Cable laying
|  | 7.28 | DC Cable termination
|  | 7.29 | DC Cable Torquing & Marking
|  | 7.3 | LT Cable termination
|  | 7.31 | LT Cable Torquing & Marking
|  | 7.32 | Aux Cable laying
|  | 7.33 | Control Cable laying
|  | 7.34 | Communication Cable laying
|  | 7.35 | Aux Cable Termination
|  | 7.36 | Control Cable Termination
|  | 7.37 | Communication Cable Termination
|  | 7.38 | CT SFRA & Tan delta Test
|  | 7.39 | CT Routine Test
|  | 7.4 | CT Control scheme & Stability Test
|  | 7.41 | HT Panel Routine (CT & PT, Breaker & Meter) Test
|  | 7.42 | HT Panel relay test
|  | 7.43 | HT Cable VLF Test
|  | 7.44 | CSS routine test
|  | 7.45 | ACDB routine test
|  | 7.46 | Earthing
|  | 7.47 | LA
CATL | 8 | Civil
|  | 8.1 | BCF Precast Erection & Welding
|  | 8.2 | CT Rail Fixing
|  | 8.3 | PCS Slab casting
|  | 8.4 | SGR Slab Casting
|  | 8.5 | MCR Slab Casting
|  | 8.6 | CSS Slab Casting
|  | 8.7 | BOT Precast Erection
|  | 8.8 | NIFPS Precast Erection
|  | 8.9 | PCS PEB
|  | 8.1 | SGR PEB
|  | 8.11 | MCR PEB
Electrical
|  | 8.12 | CT Erection
|  | 8.13 | PCS Erection
|  | 8.14 | ACDB Erection
|  | 8.15 | ECP Panel Erection (Communication Panel)
|  | 8.16 | HT Panel Erection
|  | 8.17 | EMS Panel Erection
|  | 8.18 | CSS Erection
|  | 8.19 | NIFPS Panel Erection
|  | 8.2 | NIFPS Fabrication
|  | 8.21 | Battery Container Erection
|  | 8.22 | HT cable laying
|  | 8.23 | HT cable termination
|  | 8.24 | HT Cable Torquing & Marking
|  | 8.25 | FO Cable Internal Ring
|  | 8.26 | DC Cable laying
|  | 8.27 | LT Cable laying
|  | 8.28 | DC Cable termination
|  | 8.29 | DC Cable Torquing & Marking
|  | 8.3 | LT Cable termination
|  | 8.31 | LT Cable Torquing & Marking
|  | 8.32 | Aux Cable laying
|  | 8.33 | Control Cable laying
|  | 8.34 | Communication Cable laying
|  | 8.35 | Aux Cable Termination
|  | 8.36 | Control Cable Termination
|  | 8.37 | Communication Cable Termination
|  | 8.38 | CT SFRA & Tan delta Test
|  | 8.39 | CT Routine Test
|  | 8.4 | CT Control scheme & Stability Test
|  | 8.41 | HT Panel Routine (CT & PT, Breaker & Meter) Test
|  | 8.42 | HT Panel relay test
|  | 8.43 | HT Cable VLF Test
|  | 8.44 | CSS routine test
|  | 8.45 | ACDB routine test
|  | 8.46 | Earthing
|  | 8.47 | LA
CATL | 9 | Civil
|  | 9.1 | BCF Precast Erection & Welding
|  | 9.2 | CT Rail Fixing
|  | 9.3 | PCS Slab casting
|  | 9.4 | SGR Slab Casting
|  | 9.5 | MCR Slab Casting
|  | 9.6 | CSS Slab Casting
|  | 9.7 | BOT Precast Erection
|  | 9.8 | NIFPS Precast Erection
|  | 9.9 | PCS PEB
|  | 9.1 | SGR PEB
|  | 9.11 | MCR PEB
Electrical
|  | 9.12 | CT Erection
|  | 9.13 | PCS Erection
|  | 9.14 | ACDB Erection
|  | 9.15 | ECP Panel Erection (Communication Panel)
|  | 9.16 | HT Panel Erection
|  | 9.17 | EMS Panel Erection
|  | 9.18 | CSS Erection
|  | 9.19 | NIFPS Panel Erection
|  | 9.2 | NIFPS Fabrication
|  | 9.21 | Battery Container Erection
|  | 9.22 | HT cable laying
|  | 9.23 | HT cable termination
|  | 9.24 | HT Cable Torquing & Marking
|  | 9.25 | FO Cable Internal Ring
|  | 9.26 | DC Cable laying
|  | 9.27 | LT Cable laying
|  | 9.28 | DC Cable termination
|  | 9.29 | DC Cable Torquing & Marking
|  | 9.3 | LT Cable termination
|  | 9.31 | LT Cable Torquing & Marking
|  | 9.32 | Aux Cable laying
|  | 9.33 | Control Cable laying
|  | 9.34 | Communication Cable laying
|  | 9.35 | Aux Cable Termination
|  | 9.36 | Control Cable Termination
|  | 9.37 | Communication Cable Termination
|  | 9.38 | CT SFRA & Tan delta Test
|  | 9.39 | CT Routine Test
|  | 9.4 | CT Control scheme & Stability Test
|  | 9.41 | HT Panel Routine (CT & PT, Breaker & Meter) Test
|  | 9.42 | HT Panel relay test
|  | 9.43 | HT Cable VLF Test
|  | 9.44 | CSS routine test
|  | 9.45 | ACDB routine test
|  | 9.46 | Earthing
|  | 9.47 | LA

## Timeline
Start Date |  |  |  | 2026-07-01
|  |  |  | SGR 4 | SGR 3 | SGR 2 | SGR 1 | SGR 5 | SGR 6 | SGR 7 | SGR 8 | SGR 9
Sr. No. | Category | Sr. No. | Activities | Task Target Completion Date | Task Target Completion Date | Task Target Completion Date | Task Target Completion Date | Task Target Completion Date | Task Target Completion Date | Task Target Completion Date | Task Target Completion Date | Task Target Completion Date
1 | Structure | 1.01 | MCR Room | 2026-07-08
|  | 1.02 | SGR PEB Sheet | 2026-07-08
|  | 1.03 | PCS PEB Sheet | 2026-07-17
2 | Safety | 2.01 | Handrail/Guard Railing - SGR | 2026-07-09
|  | 2.02 | Handrail/Guard Railing - PCS | 2026-07-19
|  | 2.03 | Ladder Handrail - MCR | 2026-07-09
|  | 2.04 | Ladder Handrail - SGR | 2026-07-09
|  | 2.05 | Ladder Handrail - PCS | 2026-07-18
|  | 2.06 | Rubber Mat - MCR | 2026-07-22
|  | 2.07 | Rubber Mat - SGR | 2026-07-22
|  | 2.08 | Rubber Mat - PCS | 2026-07-22
|  | 2.09 | HT Cable Route Marking | 2026-07-18
3 | Earthing | 3.01 | Strip Laying | 2026-07-17
|  | 3.02 | Equipments Body Earthing | 2026-07-18
|  | 3.03 | LA Earth Pit Installation and Connection | 2026-07-10
|  | 3.04 | CAN Cable Shield Earthing -PCS Side | 2026-07-19
|  | 3.05 | DC Cable - PCS Side | 2026-07-18
|  | 3.06 | Earth Pit Chamber Installation | 2026-07-19
4 | Nomenclature | 4.01 | MCR Room Nomenclature | 2026-07-08
|  | 4.02 | PCS Shed Nomenclature | 2026-07-17
|  | 4.03 | SGR Shed Nomenclature | 2026-07-08
|  | 4.04 | Equipment Nomenclature | 2026-07-12
|  | 4.05 | Earth Pit Chamber Nomenclature | 2026-07-20
5 | Erection | 5.01 | Battery Containers | 2026-07-08
|  | 5.02 | CT | 2026-07-02
|  | 5.03 | CT Accessories Installation | 2026-07-03
|  | 5.04 | PCS | 2026-07-05
|  | 5.05 | ACDB | 2026-07-04
|  | 5.06 | ECP | 2026-07-01
|  | 5.07 | HT Panel | 2026-07-05
|  | 5.08 | CSS | 2026-07-03
|  | 5.09 | EMS | 2026-07-05
|  | 5.1 | Sub - ACDB | 2026-07-05
|  | 5.11 | UPS | 2026-07-05
|  | 5.12 | UPS DB - Battery Rack | 2026-07-05
|  | 5.13 | LA Erection | 2026-07-09
|  | 5.14 | NIFPS Panel | 2026-07-06
|  | 5.15 | FAP Installation
6 | Trench Excavation | 6.01 | HT Cable | 2026-07-09
|  | 6.02 | DC Cable | 2026-07-04
|  | 6.03 | LT Cable | 2026-07-06
|  | 6.04 | Earthing | 2026-07-13
6 | Laying | 6.01 | HT Cable | 2026-07-12
|  | 6.02 | DC Cable | 2026-07-11
|  | 6.03 | LT Cable | 2026-07-14
|  | 6.04 | AUX Cable | 2026-07-15
|  | 6.05 | Control Cable | 2026-07-17
|  | 6.06 | Communication Cable | 2026-07-16
|  | 6.07 | FO Cable | 2026-07-16
7 | Conduit Placement | 7.01 | CAT 6 Communication Cable - PVC Conduit | 2026-07-16
|  | 7.02 | CAN Cable - Metallic Conduit | 2026-07-16
8 | Glanding & Termination | 8.01 | HT Cable | 2026-07-15
|  | 8.02 | DC Cable | 2026-07-13
|  | 8.03 | LT Cable | 2026-07-16
|  | 8.04 | AUX Cable | 2026-07-17
|  | 8.05 | Control Cable | 2026-07-19
|  | 8.06 | Communication Cable | 2026-07-18
9 | IR & Continuity Test | 9.01 | HT Cable | 2026-07-15
|  | 9.02 | DC Cable | 2026-07-16
|  | 9.03 | LT Cable | 2026-07-19
|  | 9.04 | AUX Cable | 2026-07-18
|  | 9.05 | Control Cable | 2026-07-20
|  | 9.06 | Communication Cable | 2026-07-19
10 | Torquing & Marking | 10.01 | HT Cable | 2026-07-20
|  | 10.02 | DC Cable | 2026-07-18
|  | 10.03 | LT Cable | 2026-07-21
|  | 10.04 | AUX Cable | 2026-07-19
|  | 10.05 | Control Cable | 2026-07-21
|  | 10.06 | Communication Cable | 2026-07-20
11 | Miscellaneous | 11.01 | PCS Fixation | 2026-07-06
|  | 11.02 | Equipments Fixation | 2026-07-08
|  | 11.03 | Battery Container Welding & Painting | 2026-07-10
|  | 11.04 | AC Installation -MCR Room | 2026-07-08
|  | 11.05 | NIFPS Panel Fabrication | 2026-07-18
|  | 11.06 | DC Cable U Clamp Support -Battery Side | 2026-07-19
|  | 11.07 | LT Cable U Clamp Support -PCS Side | 2026-07-22
|  | 11.08 | AUX Cable Support - Battery Side | 2026-07-19
|  | 11.09 | PCS Hole Sealing | 2026-07-22
|  | 11.1 | Battery Hole Sealing | 2026-07-19
|  | 11.11 | ACDB Hole Sealing | 2026-07-22
|  | 11.12 | ECP Hole Sealing | 2026-07-19
|  | 11.13 | Cable Tag | 2026-07-21
|  | 11.14 | Earthing Strip Painting | 2026-07-19
|  | 11.15 | Chequere Plate Installation | 2026-07-09
|  | 11.16 | Gravel Filling - in CT Block | 2026-07-04
|  | 11.17 | Gravel Filling | 2026-07-26
|  | 11.18 | FRP Ladder for Battery Containers
12 | Harmonic | 12.01 | Support Structure Erection
|  | 12.02 | Capacitor Bank Erection
|  | 12.03 | Reactor Erection
|  | 12.04 | Isolator With Cable Support & Surge Arrester With Monitor
|  | 12.05 | Earthing Strip Laying [75 X 12]
|  | 12.06 | Earthing Strip Laying [50 X 6]
|  | 12.07 | Earth pit
|  | 12.08 | HT Cable Laying
|  | 12.09 | HT Cable Termination
|  | 12.1 | HT Cable Torquing
13 | Pre-Commissiong | 13.01 | UPS Power Up | 2026-07-19
|  | 13.02 | Battery Configuration | 2026-07-22
|  | 13.03 | PCS Configuration | 2026-07-22
|  | 13.04 | EMS Configuration | 2026-07-23
14 | Test | 14.01 | CT - Oil Filteration & BDV Test | 2026-07-05
|  | 14.02 | CT - Online PPM Test | 2026-07-05
|  | 14.03 | CT - SFRA | 2026-07-05
|  | 14.04 | CT - TAN DELTA | 2026-07-06
|  | 14.05 | CT - TRF ROUTINE TEST | 2026-07-06
|  | 14.06 | CT - Current Transformer Testing - CT Analyzer | 2026-07-08
|  | 14.07 | Earthing Check | 2026-07-19
|  | 14.08 | HT Panel - Current Transformer Testing - CT Analyzer - BESS Panel | 2026-07-07
|  | 14.09 | HT Panel - Current Transformer Testing - Primary Injection - BESS Panel | 2026-07-07
|  | 14.1 | HT Panel - PT Test_BESS SIDE | 2026-07-07
|  | 14.11 | HT Panel - Current Transformer Testing - CT Analyzer - PSS Panel | 2026-07-08
|  | 14.12 | HT Panel - Current Transformer Testing - Primary Injection -- PSS Panel | 2026-07-08
|  | 14.13 | HT Panel - Meter Check_BESS SIDE - 3 Phase Primary injection | 2026-07-07
|  | 14.14 | HT Panel - Meter Check_PSS SIDE (Including HF) | 2026-07-08
|  | 14.15 | HT Panel - Breaker, CRM, Timming & vacuum Bottle Test BESS Side | 2026-07-07
|  | 14.16 | HT Panel - Breaker, CRM, Timming & vacuum Bottle Test PSS Side (Including HF) | 2026-07-09
|  | 14.17 | HT Panel - Busbar, CRM & Highpot Test | 2026-07-09
|  | 14.18 | HT Cable VLF test (Including HF) | 2026-07-19
|  | 14.19 | HT Panel - Control wiring & Relay BI/BO Test - BESS Side | 2026-07-15
|  | 14.2 | HT Panel - Control wiring & Relay BI/BO Test - PSS Side | 2026-07-07
|  | 14.21 | HT Panel - Protection Relay Test_PSS SIDE | 2026-07-08
|  | 14.22 | CSS - Dry Type Transformer Test | 2026-07-04
|  | 14.23 | CSS - Routine Test | 2026-07-04
|  | 14.24 | CSS - Control Scheme Test | 2026-07-21
|  | 14.25 | HF - Isolator, Capacitor, Damping Resistor, Reactor, Main Busbar/NCT Test | 1900-01-05
|  | 14.26 | HF Stability Test | 1899-12-31
|  | 14.27 | ACDB - Routine Test | 2026-07-06
|  | 14.28 | HT Panel - Protection Relay Test_BESS SIDE | 2026-07-23
|  | 14.29 | HT Panel - Control Scheme Test_BESS side | 2026-07-23
|  | 14.3 | HT Panel - Control Scheme Test_PSS side | 2026-07-09
|  | 14.31 | CT - Pre commisioning test - OTI, WTI, PRV, MOG etc Simulation tests | 2026-07-13
|  | 14.32 | NIFPS Pre commisioning test | 2026-07-19
|  | 14.33 | CT-Stability test | 2026-07-25
15 | SFQP Sign Off | 15.01 | SFQP Sign Off | 2026-07-23
16 | Cross Function Team Audit | 16.01 | Cross Function Team Audit | 2026-07-24
17 | CFT Punch Point Closure | 17.01 | CFT Punch Point Closure | 2026-07-26
18 | CFT Sign OFF | 18.01 | CFT Sign OFF | 2026-07-26
19 | BOXUP | 19.01 | Battery Containers | 2026-07-26
|  | 19.02 | CT | 2026-07-26
|  | 19.03 | PCS | 2026-07-26
|  | 19.04 | ACDB | 2026-07-26
|  | 19.05 | ECP | 2026-07-26
|  | 19.06 | HT Panel | 2026-07-26
|  | 19.07 | CSS | 2026-07-26
|  | 19.08 | EMS | 2026-07-26
|  | 19.09 | Sub - ACDB | 2026-07-26
|  | 19.1 | UPS | 2026-07-26
|  | 19.11 | NIFPS Panel | 2026-07-26
20 | FTC | 20.01 | FTC | 2026-07-27
21 | IDT Charging | 21.01 | IDT Charging | 2026-07-27
22 | Trial Run | 22.01 | Trial Run | 2026-07-31
23 | COD | 23.01 | COD | 2026-08-02
Formulas:
SGR 4 = [SGR 4, row above]
SGR 4 = [SGR 4, row above]+1

## Package Owner Detail
SR. No. | Activity | OFF Role Package Owner | Contact No
1 | Erection | Manohar Singh Jadega | 9166641579
2 | Cable Laying | Amit Kumar | 9507126241
3 | HT, LT, AUX, Control, Communication Cable Termination | Amit Kumar | 9507126241
4 | HT, LT Cable Torquing | Amit Kumar | 9507126241
5 | DC Cable Torquing | Manohar Singh Jadega | 9166641579
6 | Earthing and LA | Bahadur Singh
7 | Testing | Durgesh Pal and Neeral Dalvade