## DC Side
Green cell = value recorded on that date. Blank = no entry made.
Activity ID | Description | Block | Status | Priority | Contractor Name | UOM | Scope | Completed as on 29-Sep-26 | Balance | Physical Progress % | Baseline Start | Baseline Finish | Actual Start | Actual Finish | Forecast Start | Forecast Finish | Resource | 24-Sep-26 | 25-Sep-26 | 26-Sep-26 | 27-Sep-26 | 28-Sep-26 | 29-Sep-26 | 30-Sep-26 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01
| Piling - MMS (Marking, Auguring & Concreting) (Σ of 28) |  |  |  |  | Number | 86632 | 86632 | 0 |  | 16-Aug-24 | 25-Apr-26 | 16-Aug-24 | 23-Jun-26
51R1-CC-1000 | Block-06 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-06 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 25-Jan-25 | 22-Feb-25 | 25-Jan-25 | 22-Feb-25 |  |  | Solar-MT01-B |  |  |  | 6 | 4
51R1-CC-1130 | Block-07 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-07 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 15-Jan-25 | 12-Feb-25 | 15-Jan-25 | 12-Feb-25 |  |  | Solar-MT01-B
51R1-CC-1260 | Block-11 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-11 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 14-Jan-25 | 05-Feb-25 | 14-Jan-25 | 05-Feb-25 |  |  | Solar-MT01-B
51R1-CC-1390 | Block-12 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-12 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 20-Jan-25 | 28-Jan-25 | 20-Jan-25 | 28-Jan-25 |  |  | Solar-MT01-B
51R1-CC-1520 | Block-13 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-13 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 17-Jan-25 | 05-Feb-25 | 17-Jan-25 | 05-Feb-25 |  |  | Solar-MT01-B
51R1-CC-1650 | Block-14 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-14 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 29-Dec-24 | 27-Jan-25 | 29-Dec-24 | 27-Jan-25 |  |  | Solar-MT01-B
51R1-CC-1780 | Block-35 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-35 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 14-Dec-24 | 15-Jan-25 | 14-Dec-24 | 15-Jan-25 |  |  | Solar-MT01-B
51R1-CC-1910 | Block-36 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-36 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 02-Jan-25 | 03-Feb-25 | 02-Jan-25 | 03-Feb-25 |  |  | Solar-MT01-B
51R1-CC-2040 | Block-37 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-37 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 27-Dec-24 | 25-Jan-25 | 27-Dec-24 | 25-Jan-25 |  |  | Solar-MT01-B
51R1-CC-2170 | Block-38 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-38 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 21-Jan-25 | 03-Feb-25 | 21-Jan-25 | 03-Feb-25 |  |  | Solar-MT01-B
51R1-CC-2300 | Block-39 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-39 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 14-Dec-24 | 16-Jan-25 | 14-Dec-24 | 16-Jan-25 |  |  | Solar-MT01-B
51R1-CC-2430 | Block-40 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-40 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 25-Jan-25 | 18-Feb-25 | 25-Jan-25 | 18-Feb-25 |  |  | Solar-MT01-B
51R1-CC-2560 | Block-41 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-41 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 14-Jan-25 | 21-Mar-26 | 14-Jan-25 | 30-May-26 |  |  | Solar-MT01-B
51R1-CC-2690 | Block-42 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-42 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 15-Jan-25 | 07-Feb-25 | 15-Jan-25 | 07-Feb-25 |  |  | Solar-MT01-B
51R1-CC-2820 | Block-43 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-43 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 21-Dec-24 | 25-Apr-26 | 21-Dec-24 | 12-Jun-26 |  |  | Solar-MT01-B
51R1-CC-2950 | Block-44 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-44 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 27-Dec-24 | 22-Jan-25 | 27-Dec-24 | 22-Jan-25 |  |  | Solar-MT01-B
51R1-CC-3080 | Block-45 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-45 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 16-Jan-25 | 09-Feb-25 | 16-Jan-25 | 09-Feb-25 |  |  | Solar-MT01-B
51R1-CC-3210 | Block-46 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-46 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 09-Jan-25 | 04-Apr-25 | 09-Jan-25 | 04-Apr-25 |  |  | Solar-MT01-B
51R1-CC-3340 | Block-47 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-47 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 11-Jan-25 | 27-Mar-25 | 11-Jan-25 | 27-Mar-25 |  |  | Solar-MT01-B
51R1-CC-3470 | Block-48 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-48 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 19-Jan-25 | 27-Mar-25 | 19-Jan-25 | 27-Mar-25 |  |  | Solar-MT01-B
51R1-CC-3600 | Block-49 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-49 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 25-Jan-25 | 12-Feb-25 | 25-Jan-25 | 12-Feb-25 |  |  | Solar-MT01-B
51R1-CC-3730 | Block-50 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-50 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 22-Jan-25 | 18-Feb-25 | 22-Jan-25 | 18-Feb-25 |  |  | Solar-MT01-B
51R1-CC-3860 | Block-51 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-51 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 17-Jan-25 | 21-Mar-26 | 17-Jan-25 | 23-Jun-26 |  |  | Solar-MT01-B
51R1-CC-3990 | Block-52 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-52 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 25-Jan-25 | 03-Mar-25 | 25-Jan-25 | 03-Mar-25 |  |  | Solar-MT01-B
51R1-CC-4120 | Block-53 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-53 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 27-Jan-25 | 09-Mar-25 | 27-Jan-25 | 09-Mar-25 |  |  | Solar-MT01-B
51R1-CC-4250 | Block-54 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-54 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 13-Dec-24 | 21-Mar-26 | 13-Dec-24 | 23-May-26 |  |  | Solar-MT01-B
51R1-CC-4380 | Block-55 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-55 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 22-Jan-25 | 21-Mar-26 | 22-Jan-25 | 13-May-26 |  |  | Solar-MT01-B
51R1-CC-4510 | Block-56 -Piling - MMS (Marking, Auguring & Concreting) | BLOCK-56 | Completed |  |  | Number | 3094 | 3094 | 0 | 100 | 16-Aug-24 | 24-Mar-26 | 16-Aug-24 | 24-May-26 |  |  | Solar-MT01-B
| Pile Capping (Σ of 28) |  |  |  |  | Days | 559629 | 14643 | 544986 |  | 17-Aug-24 | 04-May-26 | 17-Aug-24 | 16-Aug-26
51R1-CC-1002 | Block-06 -Pile Capping | BLOCK-06 | Completed |  |  | Days | 474540 | 540 | 474000 | 100 | 28-Jan-25 | 27-Feb-25 | 28-Jan-25 | 27-Feb-25
51R1-CC-1132 | Block-07 -Pile Capping | BLOCK-07 | Completed |  |  | Days | 3102 | 751 | 2351 | 100 | 03-Feb-25 | 26-Feb-25 | 03-Feb-25 | 26-Feb-25
51R1-CC-1262 | Block-11 -Pile Capping | BLOCK-11 | Completed |  |  | Days | 5665 | 1582 | 4083 | 100 | 29-Jan-25 | 05-Feb-25 | 29-Jan-25 | 05-Feb-25
51R1-CC-1392 | Block-12 -Pile Capping | BLOCK-12 | Completed |  |  | Days | 5064 | 320 | 4744 | 100 | 28-Jan-25 | 21-Mar-26 | 28-Jan-25 | 16-Aug-26
51R1-CC-1522 | Block-13 -Pile Capping | BLOCK-13 | Completed |  |  | Days | 56 | 608 | -552 | 100 | 21-Jan-25 | 13-Feb-25 | 21-Jan-25 | 13-Feb-25
51R1-CC-1652 | Block-14 -Pile Capping | BLOCK-14 | Completed |  |  | Days | 3074 | 350 | 2724 | 100 | 17-Jan-25 | 29-Jan-25 | 17-Jan-25 | 29-Jan-25
51R1-CC-1782 | Block-35 -Pile Capping | BLOCK-35 | Completed |  |  | Days | 3062 | 252 | 2810 | 100 | 30-Dec-24 | 10-Jan-25 | 30-Dec-24 | 10-Jan-25
51R1-CC-1912 | Block-36 -Pile Capping | BLOCK-36 | Completed |  |  | Days | 3119 | 200 | 2919 | 100 | 22-Jan-25 | 20-Feb-25 | 22-Jan-25 | 20-Feb-25
51R1-CC-2042 | Block-37 -Pile Capping | BLOCK-37 | Completed |  |  | Days | 3132 | 153 | 2979 | 100 | 30-Dec-24 | 20-Feb-25 | 30-Dec-24 | 20-Feb-25
51R1-CC-2172 | Block-38 -Pile Capping | BLOCK-38 | Completed |  |  | Days | 3096 | 468 | 2628 | 100 | 17-Jan-25 | 20-Feb-25 | 17-Jan-25 | 20-Feb-25
51R1-CC-2302 | Block-39 -Pile Capping | BLOCK-39 | Completed |  |  | Days | 3090 | 180 | 2910 | 100 | 31-Dec-24 | 27-Jan-25 | 31-Dec-24 | 27-Jan-25
51R1-CC-2432 | Block-40 -Pile Capping | BLOCK-40 | Completed |  |  | Days | 3090 | 1100 | 1990 | 100 | 27-Jan-25 | 20-Feb-25 | 27-Jan-25 | 20-Feb-25
51R1-CC-2562 | Block-41 -Pile Capping | BLOCK-41 | Completed |  |  | Days | 3116 | 502 | 2614 | 100 | 15-Jan-25 | 28-Mar-26 | 15-Jan-25 | 23-Jun-26
51R1-CC-2692 | Block-42 -Pile Capping | BLOCK-42 | Completed |  |  | Days | 3102 | 316 | 2786 | 100 | 22-Jan-25 | 10-Feb-25 | 22-Jan-25 | 10-Feb-25
51R1-CC-2822 | Block-43 -Pile Capping | BLOCK-43 | Completed |  |  | Days | 3066 | 451 | 2615 | 100 | 25-Dec-24 | 04-May-26 | 25-Dec-24 | 23-Jun-26
51R1-CC-2952 | Block-44 -Pile Capping | BLOCK-44 | Completed |  |  | Days | 3095 | 243 | 2852 | 100 | 29-Dec-24 | 27-Jan-25 | 29-Dec-24 | 27-Jan-25
51R1-CC-3082 | Block-45 -Pile Capping | BLOCK-45 | Completed |  |  | Days | 3101 | 500 | 2601 | 100 | 22-Jan-25 | 19-Feb-25 | 22-Jan-25 | 19-Feb-25
51R1-CC-3212 | Block-46 -Pile Capping | BLOCK-46 | Completed |  |  | Days | 3102 | 230 | 2872 | 100 | 11-Jan-25 | 04-Apr-25 | 11-Jan-25 | 04-Apr-25
51R1-CC-3342 | Block-47 -Pile Capping | BLOCK-47 | Completed |  |  | Days | 3090 | 215 | 2875 | 100 | 19-Jan-25 | 28-Mar-25 | 19-Jan-25 | 28-Mar-25
51R1-CC-3472 | Block-48 -Pile Capping | BLOCK-48 | Completed |  |  | Days | 3094 | 248 | 2846 | 100 | 22-Jan-25 | 28-Mar-25 | 22-Jan-25 | 28-Mar-25
51R1-CC-3602 | Block-49 -Pile Capping | BLOCK-49 | Completed |  |  | Days | 3136 | 356 | 2780 | 100 | 31-Jan-25 | 03-Mar-25 | 31-Jan-25 | 03-Mar-25
51R1-CC-3732 | Block-50 -Pile Capping | BLOCK-50 | Completed |  |  | Days | 3090 | 544 | 2546 | 100 | 04-Feb-25 | 21-Feb-25 | 04-Feb-25 | 21-Feb-25
51R1-CC-3862 | Block-51 -Pile Capping | BLOCK-51 | Completed |  |  | Days | 3102 | 538 | 2564 | 100 | 27-Jan-25 | 28-Mar-26 | 27-Jan-25 | 23-Jun-26
51R1-CC-3992 | Block-52 -Pile Capping | BLOCK-52 | Completed |  |  | Days | 3090 | 550 | 2540 | 100 | 04-Feb-25 | 03-Mar-25 | 04-Feb-25 | 03-Mar-25
51R1-CC-4122 | Block-53 -Pile Capping | BLOCK-53 | Completed |  |  | Days | 3138 | 950 | 2188 | 100 | 05-Feb-25 | 10-Mar-25 | 05-Feb-25 | 10-Mar-25
51R1-CC-4252 | Block-54 -Pile Capping | BLOCK-54 | Completed |  |  | Days | 3109 | 320 | 2789 | 100 | 20-Dec-24 | 31-Mar-26 | 20-Dec-24 | 23-Jun-26
51R1-CC-4382 | Block-55 -Pile Capping | BLOCK-55 | Completed |  |  | Days | 3078 | 700 | 2378 | 100 | 04-Feb-25 | 28-Mar-26 | 04-Feb-25 | 26-May-26
51R1-CC-4512 | Block-56 -Pile Capping | BLOCK-56 | Completed |  |  | Days | 3030 | 1476 | 1554 | 100 | 17-Aug-24 | 31-Mar-26 | 17-Aug-24 | 25-May-26
| Piling - LT Cable Hanger System (Σ of 28) |  |  |  |  | Number | 1092 | 1105 | -13 |  | 16-Jan-25 | 25-Apr-26 | 16-Jan-25 | 23-Jun-26
51R1-CC-1004 | Block-06 -Piling - LT Cable Hanger System | BLOCK-06 | Completed |  |  | Number | 39 | 39 | 0 | 100 | 22-Feb-25 | 24-Feb-25 | 22-Feb-25 | 24-Feb-25 |  |  | Solar-MT02-B
51R1-CC-1134 | Block-07 -Piling - LT Cable Hanger System | BLOCK-07 | Completed |  |  | Number | 39 | 39 | 0 | 100 | 24-Feb-25 | 27-Feb-25 | 24-Feb-25 | 27-Feb-25 |  |  | Solar-MT02-B
51R1-CC-1264 | Block-11 -Piling - LT Cable Hanger System | BLOCK-11 | Completed |  |  | Number | 39 | 39 | 0 | 100 | 11-Feb-25 | 11-Feb-25 | 11-Feb-25 | 11-Feb-25 |  |  | Solar-MT02-B
51R1-CC-1394 | Block-12 -Piling - LT Cable Hanger System | BLOCK-12 | Completed |  |  | Number | 39 | 39 | 0 | 100 | 11-Feb-25 | 13-Feb-25 | 11-Feb-25 | 13-Feb-25 |  |  | Solar-MT02-B
51R1-CC-1524 | Block-13 -Piling - LT Cable Hanger System | BLOCK-13 | Completed |  |  | Number | 39 | 39 | 0 | 100 | 11-Feb-25 | 11-Feb-25 | 11-Feb-25 | 11-Feb-25 |  |  | Solar-MT02-B
51R1-CC-1654 | Block-14 -Piling - LT Cable Hanger System | BLOCK-14 | Completed |  |  | Number | 39 | 39 | 0 | 100 | 25-Feb-25 | 27-Feb-25 | 25-Feb-25 | 27-Feb-25 |  |  | Solar-MT02-B
51R1-CC-1784 | Block-35 -Piling - LT Cable Hanger System | BLOCK-35 | Completed |  |  | Number | 39 | 39 | 0 | 100 | 22-Jan-25 | 04-Feb-25 | 22-Jan-25 | 04-Feb-25 |  |  | Solar-MT02-B
51R1-CC-1914 | Block-36 -Piling - LT Cable Hanger System | BLOCK-36 | Completed |  |  | Number | 39 | 39 | 0 | 100 | 01-Feb-25 | 03-Feb-25 | 01-Feb-25 | 03-Feb-25 |  |  | Solar-MT02-B
51R1-CC-2044 | Block-37 -Piling - LT Cable Hanger System | BLOCK-37 | Completed |  |  | Number | 39 | 39 | 0 | 100 | 16-Jan-25 | 04-Feb-25 | 16-Jan-25 | 04-Feb-25 |  |  | Solar-MT02-B
51R1-CC-2174 | Block-38 -Piling - LT Cable Hanger System | BLOCK-38 | Completed |  |  | Number | 39 | 39 | 0 | 100 | 01-Feb-25 | 04-Feb-25 | 01-Feb-25 | 04-Feb-25 |  |  | Solar-MT02-B
51R1-CC-2304 | Block-39 -Piling - LT Cable Hanger System | BLOCK-39 | Completed |  |  | Number | 39 | 39 | 0 | 100 | 16-Jan-25 | 22-Mar-26 | 16-Jan-25 | 23-Jun-26 |  |  | Solar-MT02-B
51R1-CC-2434 | Block-40 -Piling - LT Cable Hanger System | BLOCK-40 | Completed |  |  | Number | 39 | 39 | 0 | 100 | 19-Feb-25 | 22-Mar-26 | 19-Feb-25 | 23-Jun-26 |  |  | Solar-MT02-B
51R1-CC-2564 | Block-41 -Piling - LT Cable Hanger System | BLOCK-41 | Completed |  |  | Number | 39 | 39 | 0 | 100 | 25-Jan-25 | 30-Jan-25 | 25-Jan-25 | 30-Jan-25 |  |  | Solar-MT02-B
51R1-CC-2694 | Block-42 -Piling - LT Cable Hanger System | BLOCK-42 | Completed |  |  | Number | 39 | 39 | 0 | 100 | 06-Feb-25 | 08-Feb-25 | 06-Feb-25 | 08-Feb-25 |  |  | Solar-MT02-B
51R1-CC-2824 | Block-43 -Piling - LT Cable Hanger System | BLOCK-43 | Completed |  |  | Number | 39 | 39 | 0 | 100 | 31-Mar-26 | 25-Apr-26 | 07-Jun-26 | 07-Jun-26 |  |  | Solar-MT02-B
51R1-CC-2954 | Block-44 -Piling - LT Cable Hanger System | BLOCK-44 | Completed |  |  | Number | 39 | 39 | 0 | 100 | 16-Jan-25 | 28-Jan-25 | 16-Jan-25 | 28-Jan-25 |  |  | Solar-MT02-B
51R1-CC-3084 | Block-45 -Piling - LT Cable Hanger System | BLOCK-45 | Completed |  |  | Number | 39 | 39 | 0 | 100 | 17-Feb-25 | 27-Feb-25 | 17-Feb-25 | 27-Feb-25 |  |  | Solar-MT02-B
51R1-CC-3214 | Block-46 -Piling - LT Cable Hanger System | BLOCK-46 | Completed |  |  | Number | 39 | 40 | -1 | 100 | 05-Apr-25 | 07-Apr-25 | 05-Apr-25 | 07-Apr-25 |  |  | Solar-MT02-B
51R1-CC-3344 | Block-47 -Piling - LT Cable Hanger System | BLOCK-47 | Completed |  |  | Number | 39 | 39 | 0 | 100 | 21-Mar-26 | 12-Apr-26 | 31-May-26 | 01-Jun-26 |  |  | Solar-MT02-B
51R1-CC-3474 | Block-48 -Piling - LT Cable Hanger System | BLOCK-48 | Completed |  |  | Number | 39 | 39 | 0 | 100 | 21-Mar-26 | 12-Apr-26 | 30-May-26 | 31-May-26 |  |  | Solar-MT02-B
51R1-CC-3604 | Block-49 -Piling - LT Cable Hanger System | BLOCK-49 | Completed |  |  | Number | 39 | 40 | -1 | 100 | 20-Feb-25 | 22-Feb-25 | 20-Feb-25 | 22-Feb-25 |  |  | Solar-MT02-B
51R1-CC-3734 | Block-50 -Piling - LT Cable Hanger System | BLOCK-50 | Completed |  |  | Number | 39 | 39 | 0 | 100 | 22-Feb-25 | 27-Feb-25 | 22-Feb-25 | 27-Feb-25 |  |  | Solar-MT02-B
51R1-CC-3864 | Block-51 -Piling - LT Cable Hanger System | BLOCK-51 | Completed |  |  | Number | 39 | 39 | 0 | 100 | 27-Feb-25 | 23-Mar-26 | 27-Feb-25 | 23-Jun-26 |  |  | Solar-MT02-B
51R1-CC-3994 | Block-52 -Piling - LT Cable Hanger System | BLOCK-52 | Completed |  |  | Number | 39 | 39 | 0 | 100 | 27-Feb-25 | 01-Mar-25 | 27-Feb-25 | 01-Mar-25 |  |  | Solar-MT02-B
51R1-CC-4124 | Block-53 -Piling - LT Cable Hanger System | BLOCK-53 | Completed |  |  | Number | 39 | 42 | -3 | 100 | 05-Mar-25 | 09-Mar-25 | 05-Mar-25 | 09-Mar-25 |  |  | Solar-MT02-B
51R1-CC-4254 | Block-54 -Piling - LT Cable Hanger System | BLOCK-54 | Completed |  |  | Number | 39 | 39 | 0 | 100 | 27-Jan-25 | 02-Apr-26 | 27-Jan-25 | 23-Jun-26 |  |  | Solar-MT02-B
51R1-CC-4384 | Block-55 -Piling - LT Cable Hanger System | BLOCK-55 | Completed |  |  | Number | 39 | 43 | -4 | 100 | 01-Mar-25 | 05-Mar-25 | 01-Mar-25 | 05-Mar-25 |  |  | Solar-MT02-B
51R1-CC-4514 | Block-56 -Piling - LT Cable Hanger System | BLOCK-56 | Completed |  |  | Number | 39 | 43 | -4 | 100 | 21-Mar-26 | 12-Apr-26 | 25-May-26 | 25-May-26 |  |  | Solar-MT02-B
| Piling - Inverters (Σ of 28) |  |  |  |  | Number | 2632 | 2632 | 0 |  | 06-Jan-25 | 07-Apr-26 | 06-Jan-25 | 01-Jun-26
51R1-CC-1006 | Block-06 -Piling - Inverters | BLOCK-06 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 24-Feb-25 | 28-Feb-25 | 24-Feb-25 | 28-Feb-25 |  |  | Solar-MT03-B
51R1-CC-1136 | Block-07 -Piling - Inverters | BLOCK-07 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 25-Feb-25 | 25-Feb-25 | 25-Feb-25 | 25-Feb-25 |  |  | Solar-MT03-B
51R1-CC-1266 | Block-11 -Piling - Inverters | BLOCK-11 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 11-Feb-25 | 15-Feb-25 | 11-Feb-25 | 15-Feb-25 |  |  | Solar-MT03-B
51R1-CC-1396 | Block-12 -Piling - Inverters | BLOCK-12 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 15-Feb-25 | 18-Feb-25 | 15-Feb-25 | 18-Feb-25 |  |  | Solar-MT03-B
51R1-CC-1526 | Block-13 -Piling - Inverters | BLOCK-13 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 08-Feb-25 | 09-Feb-25 | 08-Feb-25 | 09-Feb-25 |  |  | Solar-MT03-B
51R1-CC-1656 | Block-14 -Piling - Inverters | BLOCK-14 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 25-Mar-25 | 28-Mar-25 | 25-Mar-25 | 28-Mar-25 |  |  | Solar-MT03-B
51R1-CC-1786 | Block-35 -Piling - Inverters | BLOCK-35 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 06-Jan-25 | 07-Jan-25 | 06-Jan-25 | 07-Jan-25 |  |  | Solar-MT03-B
51R1-CC-1916 | Block-36 -Piling - Inverters | BLOCK-36 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 01-Feb-25 | 03-Feb-25 | 01-Feb-25 | 03-Feb-25 |  |  | Solar-MT03-B
51R1-CC-2046 | Block-37 -Piling - Inverters | BLOCK-37 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 08-Feb-25 | 11-Feb-25 | 08-Feb-25 | 11-Feb-25 |  |  | Solar-MT03-B
51R1-CC-2176 | Block-38 -Piling - Inverters | BLOCK-38 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 01-Feb-25 | 05-Feb-25 | 01-Feb-25 | 05-Feb-25 |  |  | Solar-MT03-B
51R1-CC-2306 | Block-39 -Piling - Inverters | BLOCK-39 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 11-Jan-25 | 16-Jan-25 | 11-Jan-25 | 16-Jan-25 |  |  | Solar-MT03-B
51R1-CC-2436 | Block-40 -Piling - Inverters | BLOCK-40 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 18-Feb-25 | 19-Feb-25 | 18-Feb-25 | 19-Feb-25 |  |  | Solar-MT03-B
51R1-CC-2566 | Block-41 -Piling - Inverters | BLOCK-41 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 31-Jan-25 | 24-Apr-25 | 31-Jan-25 | 24-Apr-25 |  |  | Solar-MT03-B
51R1-CC-2696 | Block-42 -Piling - Inverters | BLOCK-42 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 07-Feb-25 | 09-Feb-25 | 07-Feb-25 | 09-Feb-25 |  |  | Solar-MT03-B
51R1-CC-2826 | Block-43 -Piling - Inverters | BLOCK-43 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 09-Apr-25 | 11-Apr-25 | 09-Apr-25 | 11-Apr-25 |  |  | Solar-MT03-B
51R1-CC-2956 | Block-44 -Piling - Inverters | BLOCK-44 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 08-Jan-25 | 11-Jan-25 | 08-Jan-25 | 11-Jan-25 |  |  | Solar-MT03-B
51R1-CC-3086 | Block-45 -Piling - Inverters | BLOCK-45 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 17-Feb-25 | 17-Feb-25 | 17-Feb-25 | 17-Feb-25 |  |  | Solar-MT03-B
51R1-CC-3216 | Block-46 -Piling - Inverters | BLOCK-46 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 09-Feb-25 | 04-Apr-25 | 09-Feb-25 | 04-Apr-25 |  |  | Solar-MT03-B
51R1-CC-3346 | Block-47 -Piling - Inverters | BLOCK-47 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 21-Mar-26 | 07-Apr-26 | 31-May-26 | 01-Jun-26 |  |  | Solar-MT03-B
51R1-CC-3476 | Block-48 -Piling - Inverters | BLOCK-48 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 21-Mar-26 | 07-Apr-26 | 30-May-26 | 31-May-26 |  |  | Solar-MT03-B
51R1-CC-3606 | Block-49 -Piling - Inverters | BLOCK-49 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 11-Feb-25 | 12-Feb-25 | 11-Feb-25 | 12-Feb-25 |  |  | Solar-MT03-B
51R1-CC-3736 | Block-50 -Piling - Inverters | BLOCK-50 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 21-Mar-26 | 07-Apr-26 | 31-May-26 | 01-Jun-26 |  |  | Solar-MT03-B
51R1-CC-3866 | Block-51 -Piling - Inverters | BLOCK-51 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 31-Jan-25 | 03-Feb-25 | 31-Jan-25 | 03-Feb-25 |  |  | Solar-MT03-B
51R1-CC-3996 | Block-52 -Piling - Inverters | BLOCK-52 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 21-Mar-26 | 07-Apr-26 | 31-May-26 | 01-Jun-26 |  |  | Solar-MT03-B
51R1-CC-4126 | Block-53 -Piling - Inverters | BLOCK-53 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 07-Mar-25 | 10-Mar-25 | 07-Mar-25 | 10-Mar-25 |  |  | Solar-MT03-B
51R1-CC-4256 | Block-54 -Piling - Inverters | BLOCK-54 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 12-Jan-25 | 27-Mar-26 | 12-Jan-25 | 27-May-26 |  |  | Solar-MT03-B
51R1-CC-4386 | Block-55 -Piling - Inverters | BLOCK-55 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 21-Mar-26 | 07-Apr-26 | 24-May-26 | 26-May-26 |  |  | Solar-MT03-B
51R1-CC-4516 | Block-56 -Piling - Inverters | BLOCK-56 | Completed |  |  | Number | 94 | 94 | 0 | 100 | 21-Mar-26 | 07-Apr-26 | 25-May-26 | 25-May-26 |  |  | Solar-MT03-B
| Piling - Robotic Docking System (Σ of 28) |  |  |  |  | Number | 1288 | 1427 | -139 |  | 19-Feb-25 | 25-Apr-26 | 19-Feb-25 | 23-Jun-26
51R1-CC-1008 | Block-06 -Piling - Robotic Docking System | BLOCK-06 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 20-Feb-25 | 28-Mar-26 | 20-Feb-25 | 28-May-26 |  |  | Solar-MT04-B
51R1-CC-1138 | Block-07 -Piling - Robotic Docking System | BLOCK-07 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 21-Feb-25 | 24-Mar-26 | 21-Feb-25 | 28-May-26 |  |  | Solar-MT04-B
51R1-CC-1268 | Block-11 -Piling - Robotic Docking System | BLOCK-11 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 21-Mar-26 | 30-Mar-26 | 29-May-26 | 23-Jun-26 |  |  | Solar-MT04-B
51R1-CC-1398 | Block-12 -Piling - Robotic Docking System | BLOCK-12 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 22-Feb-25 | 22-Feb-25 | 22-Feb-25 | 22-Feb-25 |  |  | Solar-MT04-B
51R1-CC-1528 | Block-13 -Piling - Robotic Docking System | BLOCK-13 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 01-Apr-25 | 11-May-25 | 01-Apr-25 | 11-May-25 |  |  | Solar-MT04-B
51R1-CC-1658 | Block-14 -Piling - Robotic Docking System | BLOCK-14 | Completed |  |  | Number | 46 | 60 | -14 | 100 | 21-Mar-26 | 30-Mar-26 | 21-Jun-26 | 23-Jun-26 |  |  | Solar-MT04-B
51R1-CC-1788 | Block-35 -Piling - Robotic Docking System | BLOCK-35 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 09-Mar-25 | 13-Mar-25 | 09-Mar-25 | 13-Mar-25 |  |  | Solar-MT04-B
51R1-CC-1918 | Block-36 -Piling - Robotic Docking System | BLOCK-36 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 21-Mar-26 | 30-Mar-26 | 13-Jun-26 | 14-Jun-26 |  |  | Solar-MT04-B
51R1-CC-2048 | Block-37 -Piling - Robotic Docking System | BLOCK-37 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 20-May-25 | 23-May-25 | 20-May-25 | 23-May-25 |  |  | Solar-MT04-B
51R1-CC-2178 | Block-38 -Piling - Robotic Docking System | BLOCK-38 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 21-Mar-26 | 30-Mar-26 | 13-Jun-26 | 14-Jun-26 |  |  | Solar-MT04-B
51R1-CC-2308 | Block-39 -Piling - Robotic Docking System | BLOCK-39 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 21-Mar-26 | 30-Mar-26 | 18-Jun-26 | 23-Jun-26 |  |  | Solar-MT04-B
51R1-CC-2438 | Block-40 -Piling - Robotic Docking System | BLOCK-40 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 19-Feb-25 | 20-Feb-25 | 19-Feb-25 | 20-Feb-25 |  |  | Solar-MT04-B
51R1-CC-2568 | Block-41 -Piling - Robotic Docking System | BLOCK-41 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 23-Apr-25 | 24-Apr-25 | 23-Apr-25 | 24-Apr-25 |  |  | Solar-MT04-B
51R1-CC-2698 | Block-42 -Piling - Robotic Docking System | BLOCK-42 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 22-Apr-25 | 24-Apr-25 | 22-Apr-25 | 24-Apr-25 |  |  | Solar-MT04-B
51R1-CC-2828 | Block-43 -Piling - Robotic Docking System | BLOCK-43 | Completed |  |  | Number | 46 | 75 | -29 | 100 | 12-Apr-26 | 25-Apr-26 | 09-Jun-26 | 15-Jun-26 |  |  | Solar-MT04-B
51R1-CC-2958 | Block-44 -Piling - Robotic Docking System | BLOCK-44 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 21-Mar-26 | 30-Mar-26 | 07-Jun-26 | 11-Jun-26 |  |  | Solar-MT04-B
51R1-CC-3088 | Block-45 -Piling - Robotic Docking System | BLOCK-45 | Completed |  |  | Number | 46 | 56 | -10 | 100 | 04-Apr-25 | 09-Apr-25 | 04-Apr-25 | 09-Apr-25 |  |  | Solar-MT04-B
51R1-CC-3218 | Block-46 -Piling - Robotic Docking System | BLOCK-46 | Completed |  |  | Number | 46 | 60 | -14 | 100 | 01-Apr-25 | 02-Apr-25 | 01-Apr-25 | 02-Apr-25 |  |  | Solar-MT04-B
51R1-CC-3348 | Block-47 -Piling - Robotic Docking System | BLOCK-47 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 21-Mar-26 | 30-Mar-26 | 01-Jun-26 | 05-Jun-26 |  |  | Solar-MT04-B
51R1-CC-3478 | Block-48 -Piling - Robotic Docking System | BLOCK-48 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 21-Mar-26 | 30-Mar-26 | 15-Jun-26 | 18-Jun-26 |  |  | Solar-MT04-B
51R1-CC-3608 | Block-49 -Piling - Robotic Docking System | BLOCK-49 | Completed |  |  | Number | 46 | 84 | -38 | 100 | 20-Feb-25 | 22-Feb-25 | 20-Feb-25 | 22-Feb-25 |  |  | Solar-MT04-B
51R1-CC-3738 | Block-50 -Piling - Robotic Docking System | BLOCK-50 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 21-Mar-26 | 30-Mar-26 | 21-Jun-26 | 23-Jun-26 |  |  | Solar-MT04-B
51R1-CC-3868 | Block-51 -Piling - Robotic Docking System | BLOCK-51 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 21-Mar-26 | 30-Mar-26 | 19-Jun-26 | 23-Jun-26 |  |  | Solar-MT04-B
51R1-CC-3998 | Block-52 -Piling - Robotic Docking System | BLOCK-52 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 21-Mar-26 | 30-Mar-26 | 21-Jun-26 | 23-Jun-26 |  |  | Solar-MT04-B
51R1-CC-4128 | Block-53 -Piling - Robotic Docking System | BLOCK-53 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 21-Mar-26 | 30-Mar-26 | 21-Jun-26 | 23-Jun-26 |  |  | Solar-MT04-B
51R1-CC-4258 | Block-54 -Piling - Robotic Docking System | BLOCK-54 | Completed |  |  | Number | 46 | 80 | -34 | 100 | 21-Mar-26 | 30-Mar-26 | 10-Jun-26 | 16-Jun-26 |  |  | Solar-MT04-B
51R1-CC-4388 | Block-55 -Piling - Robotic Docking System | BLOCK-55 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 21-Mar-26 | 30-Mar-26 | 09-Jun-26 | 23-Jun-26 |  |  | Solar-MT04-B
51R1-CC-4518 | Block-56 -Piling - Robotic Docking System | BLOCK-56 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 21-Mar-26 | 30-Mar-26 | 14-Jun-26 | 18-Jun-26 |  |  | Solar-MT04-B
| Array Earthing (Σ of 28) |  |  |  |  | Kilometer | 168 | 53316 | -53148 |  | 21-Jan-25 | 26-Apr-26 | 21-Jan-25 | 30-Aug-26 | 27-Sep-26 | 26-Oct-26
51R1-CC-1010 | Block-06 -Array Earthing | BLOCK-06 | Completed |  |  | Kilometer | 6 | 440 | -434 | 100 | 08-Jan-26 | 23-Mar-26 | 08-Jan-26 | 20-Apr-26 |  |  | Solar-MT05-B
51R1-CC-1140 | Block-07 -Array Earthing | BLOCK-07 | Completed |  |  | Kilometer | 6 | 550 | -544 | 100 | 07-Jan-26 | 22-Mar-26 | 07-Jan-26 | 03-Feb-26 |  |  | Solar-MT05-B
51R1-CC-1270 | Block-11 -Array Earthing | BLOCK-11 | Completed |  |  | Kilometer | 6 | 500 | -494 | 100 | 08-Jan-26 | 22-Mar-26 | 08-Jan-26 | 17-Mar-26 |  |  | Solar-MT05-B
51R1-CC-1400 | Block-12 -Array Earthing | BLOCK-12 | Completed |  |  | Kilometer | 6 | 1000 | -994 | 100 | 06-Jan-26 | 22-Mar-26 | 06-Jan-26 | 23-Jan-26 |  |  | Solar-MT05-B
51R1-CC-1530 | Block-13 -Array Earthing | BLOCK-13 | Completed |  |  | Kilometer | 6 | 700 | -694 | 100 | 03-Jan-26 | 22-Mar-26 | 03-Jan-26 | 11-Feb-26 |  |  | Solar-MT05-B
51R1-CC-1660 | Block-14 -Array Earthing | BLOCK-14 | Completed |  |  | Kilometer | 6 | 600 | -594 | 100 | 03-Jan-26 | 22-Mar-26 | 03-Jan-26 | 13-Jan-26 |  |  | Solar-MT05-B
51R1-CC-1790 | Block-35 -Array Earthing | BLOCK-35 | Completed |  |  | Kilometer | 6 | 5800 | -5794 | 100 | 05-Feb-25 | 25-Mar-26 | 05-Feb-25 | 08-Jul-26 |  |  | Solar-MT05-B
51R1-CC-1920 | Block-36 -Array Earthing | BLOCK-36 | Completed |  |  | Kilometer | 6 | 1500 | -1494 | 100 | 02-Feb-25 | 27-Mar-26 | 02-Feb-25 | 08-Jul-26 |  |  | Solar-MT05-B
51R1-CC-2050 | Block-37 -Array Earthing | BLOCK-37 | Completed |  |  | Kilometer | 6 | 1750 | -1744 | 100 | 14-Feb-25 | 03-Apr-26 | 14-Feb-25 | 08-Jul-26 |  |  | Solar-MT05-B
51R1-CC-2180 | Block-38 -Array Earthing | BLOCK-38 | Completed |  |  | Kilometer | 6 | 4000 | -3994 | 100 | 21-Mar-26 | 18-Apr-26 | 09-Jun-26 | 08-Jul-26 |  |  | Solar-MT05-B
51R1-CC-2310 | Block-39 -Array Earthing | BLOCK-39 | Completed |  |  | Kilometer | 6 | 2000 | -1994 | 100 | 14-Feb-25 | 09-Apr-26 | 14-Feb-25 | 09-May-26 |  |  | Solar-MT05-B
51R1-CC-2440 | Block-40 -Array Earthing | BLOCK-40 | Completed |  |  | Kilometer | 6 | 700 | -694 | 100 | 20-Jan-26 | 22-Mar-26 | 20-Jan-26 | 19-Mar-26 |  |  | Solar-MT05-B
51R1-CC-2570 | Block-41 -Array Earthing | BLOCK-41 | Completed |  |  | Kilometer | 6 | 1000 | -994 | 100 | 29-Jan-26 | 22-Mar-26 | 29-Jan-26 | 08-Jul-26 |  |  | Solar-MT05-B
51R1-CC-2700 | Block-42 -Array Earthing | BLOCK-42 | Completed |  |  | Kilometer | 6 | 900 | -894 | 100 | 07-Feb-26 | 23-Mar-26 | 07-Feb-26 | 23-Mar-26 |  |  | Solar-MT05-B
51R1-CC-2830 | Block-43 -Array Earthing | BLOCK-43 | Completed |  |  | Kilometer | 6 | 1000 | -994 | 100 | 20-Jan-26 | 26-Apr-26 | 20-Jan-26 | 08-Jul-26 |  |  | Solar-MT05-B
51R1-CC-2960 | Block-44 -Array Earthing | BLOCK-44 | Completed |  |  | Kilometer | 6 | 4962 | -4956 | 100 | 14-Feb-25 | 26-Mar-26 | 14-Feb-25 | 10-May-26 |  |  | Solar-MT05-B
51R1-CC-3090 | Block-45 -Array Earthing | BLOCK-45 | Completed |  |  | Kilometer | 6 | 1000 | -994 | 100 | 14-Feb-26 | 22-Mar-26 | 14-Feb-26 | 08-Jul-26 |  |  | Solar-MT05-B
51R1-CC-3220 | Block-46 -Array Earthing | BLOCK-46 | Completed |  |  | Kilometer | 6 | 1800 | -1794 | 100 | 21-Mar-26 | 18-Apr-26 | 22-Jun-26 | 08-Jul-26 |  |  | Solar-MT05-B
51R1-CC-3350 | Block-47 -Array Earthing | BLOCK-47 | Completed |  |  | Kilometer | 6 | 1511 | -1505 | 100 | 21-Mar-26 | 18-Apr-26 | 27-Mar-26 | 19-Jun-26 |  |  | Solar-MT05-B
51R1-CC-3480 | Block-48 -Array Earthing | BLOCK-48 | Completed |  |  | Kilometer | 6 | 4900 | -4894 | 100 | 21-Mar-26 | 18-Apr-26 | 11-Aug-26 | 30-Aug-26 |  |  | Solar-MT05-B
51R1-CC-3610 | Block-49 -Array Earthing | BLOCK-49 | Completed |  |  | Kilometer | 6 | 1000 | -994 | 100 | 20-Mar-26 | 22-Mar-26 | 20-Mar-26 | 08-Jul-26 |  |  | Solar-MT05-B
51R1-CC-3740 | Block-50 -Array Earthing | BLOCK-50 | Completed |  |  | Kilometer | 6 | 2500 | -2494 | 100 | 21-Mar-26 | 18-Apr-26 | 19-Jun-26 | 24-Jun-26 |  |  | Solar-MT05-B
51R1-CC-3870 | Block-51 -Array Earthing | BLOCK-51 | In Progress |  |  | Kilometer | 6 | 4500 | -4494 | 84 | 21-Mar-26 | 18-Apr-26 | 02-Jul-26 |  |  | 29-Sep-26 | Solar-MT05-B
51R1-CC-4000 | Block-52 -Array Earthing | BLOCK-52 | Not Started |  |  | Kilometer | 6 | 0 | 6 | 0 | 21-Mar-26 | 18-Apr-26 |  |  | 27-Sep-26 | 20-Oct-26 | Solar-MT05-B
51R1-CC-4130 | Block-53 -Array Earthing | BLOCK-53 | In Progress |  |  | Kilometer | 6 | 3 | 3 | 49 | 21-Mar-26 | 18-Apr-26 | 21-Sep-26 |  |  | 12-Oct-26 | Solar-MT05-B
51R1-CC-4260 | Block-54 -Array Earthing | BLOCK-54 | Completed |  |  | Kilometer | 6 | 3200 | -3194 | 100 | 21-Jan-25 | 03-Apr-26 | 21-Jan-25 | 13-Jul-26 |  |  | Solar-MT05-B
51R1-CC-4390 | Block-55 -Array Earthing | BLOCK-55 | Not Started |  |  | Kilometer | 6 | 0 | 6 | 0 | 21-Mar-26 | 18-Apr-26 |  |  | 27-Sep-26 | 26-Oct-26 | Solar-MT05-B
51R1-CC-4520 | Block-56 -Array Earthing | BLOCK-56 | Completed |  |  | Kilometer | 6 | 5500 | -5494 | 100 | 21-Mar-26 | 18-Apr-26 | 08-Jun-26 | 09-Jun-26 |  |  | Solar-MT05-B
| MMS Erection - Torque Tube/Raftar (Σ of 28) |  |  |  |  | Tables | 7476 | 7383 | 93 |  | 15-Jan-25 | 14-May-26 | 15-Jan-25 | 02-Sep-26 |  | 20-Oct-26
51R1-CC-1012 | Block-06 -MMS Erection - Torque Tube/Raftar | BLOCK-06 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 12-Mar-26 | 16-Apr-26 | 12-Mar-26 | 19-May-26 |  |  | Solar-MT09-B
51R1-CC-1142 | Block-07 -MMS Erection - Torque Tube/Raftar | BLOCK-07 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 21-Mar-26 | 22-Apr-26 | 14-Mar-26 | 19-May-26 |  |  | Solar-MT09-B
51R1-CC-1272 | Block-11 -MMS Erection - Torque Tube/Raftar | BLOCK-11 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 21-Mar-26 | 22-Apr-26 | 01-Apr-26 | 10-May-26 |  |  | Solar-MT09-B
51R1-CC-1402 | Block-12 -MMS Erection - Torque Tube/Raftar | BLOCK-12 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 21-Mar-26 | 22-Apr-26 | 26-Mar-26 | 01-Apr-26 |  |  | Solar-MT09-B
51R1-CC-1532 | Block-13 -MMS Erection - Torque Tube/Raftar | BLOCK-13 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 21-Mar-26 | 22-Apr-26 | 29-Mar-26 | 19-May-26 |  |  | Solar-MT09-B
51R1-CC-1662 | Block-14 -MMS Erection - Torque Tube/Raftar | BLOCK-14 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 21-Mar-26 | 22-Apr-26 | 26-Mar-26 | 01-Apr-26 |  |  | Solar-MT09-B
51R1-CC-1792 | Block-35 -MMS Erection - Torque Tube/Raftar | BLOCK-35 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 05-Feb-25 | 04-Apr-26 | 05-Feb-25 | 31-Mar-26 |  |  | Solar-MT09-B
51R1-CC-1922 | Block-36 -MMS Erection - Torque Tube/Raftar | BLOCK-36 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 20-Mar-26 | 04-Apr-26 | 20-Mar-26 | 19-May-26 |  |  | Solar-MT09-B
51R1-CC-2052 | Block-37 -MMS Erection - Torque Tube/Raftar | BLOCK-37 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 21-Mar-26 | 22-Apr-26 | 13-Jul-26 | 20-Jul-26 |  |  | Solar-MT09-B
51R1-CC-2182 | Block-38 -MMS Erection - Torque Tube/Raftar | BLOCK-38 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 21-Mar-26 | 22-Apr-26 | 12-Jun-26 | 01-Jul-26 |  |  | Solar-MT09-B
51R1-CC-2312 | Block-39 -MMS Erection - Torque Tube/Raftar | BLOCK-39 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 20-Jan-26 | 22-Mar-26 | 20-Jan-26 | 22-Mar-26 |  |  | Solar-MT09-B
51R1-CC-2442 | Block-40 -MMS Erection - Torque Tube/Raftar | BLOCK-40 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 21-Mar-26 | 22-Apr-26 | 08-May-26 | 10-May-26 |  |  | Solar-MT09-B
51R1-CC-2572 | Block-41 -MMS Erection - Torque Tube/Raftar | BLOCK-41 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 21-Mar-26 | 22-Apr-26 | 03-Apr-26 | 12-Aug-26 |  |  | Solar-MT09-B
51R1-CC-2702 | Block-42 -MMS Erection - Torque Tube/Raftar | BLOCK-42 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 21-Mar-26 | 22-Apr-26 | 05-Apr-26 | 19-May-26 |  |  | Solar-MT09-B
51R1-CC-2832 | Block-43 -MMS Erection - Torque Tube/Raftar | BLOCK-43 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 08-Apr-26 | 14-May-26 | 16-May-26 | 29-Jul-26 |  |  | Solar-MT09-B
51R1-CC-2962 | Block-44 -MMS Erection - Torque Tube/Raftar | BLOCK-44 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 23-Jan-26 | 29-Mar-26 | 23-Jan-26 | 13-Aug-26 |  |  | Solar-MT09-B
51R1-CC-3092 | Block-45 -MMS Erection - Torque Tube/Raftar | BLOCK-45 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 21-Mar-26 | 22-Apr-26 | 20-Apr-26 | 15-Jul-26 |  |  | Solar-MT09-B
51R1-CC-3222 | Block-46 -MMS Erection - Torque Tube/Raftar | BLOCK-46 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 21-Mar-26 | 22-Apr-26 | 12-Jul-26 | 18-Aug-26 |  |  | Solar-MT09-B
51R1-CC-3352 | Block-47 -MMS Erection - Torque Tube/Raftar | BLOCK-47 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 21-Mar-26 | 22-Apr-26 | 15-Aug-26 | 28-Aug-26 |  |  | Solar-MT09-B
51R1-CC-3482 | Block-48 -MMS Erection - Torque Tube/Raftar | BLOCK-48 | Completed |  |  | Tables | 267 | 252 | 15 | 100 | 21-Mar-26 | 22-Apr-26 | 12-Jun-26 | 22-Jun-26 |  |  | Solar-MT09-B
51R1-CC-3612 | Block-49 -MMS Erection - Torque Tube/Raftar | BLOCK-49 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 21-Mar-26 | 22-Apr-26 | 29-Apr-26 | 19-May-26 |  |  | Solar-MT09-B
51R1-CC-3742 | Block-50 -MMS Erection - Torque Tube/Raftar | BLOCK-50 | In Progress |  |  | Tables | 267 | 256 | 11 | 96 | 21-Mar-26 | 22-Apr-26 | 15-Jun-26 |  |  | 28-Sep-26 | Solar-MT09-B
51R1-CC-3872 | Block-51 -MMS Erection - Torque Tube/Raftar | BLOCK-51 | In Progress |  |  | Tables | 267 | 259 | 8 | 97 | 21-Mar-26 | 22-Apr-26 | 29-Jun-26 |  |  | 29-Sep-26 | Solar-MT09-B
51R1-CC-4002 | Block-52 -MMS Erection - Torque Tube/Raftar | BLOCK-52 | In Progress |  |  | Tables | 267 | 259 | 8 | 97 | 21-Mar-26 | 22-Apr-26 | 05-Sep-26 |  |  | 20-Oct-26 | Solar-MT09-B
51R1-CC-4132 | Block-53 -MMS Erection - Torque Tube/Raftar | BLOCK-53 | In Progress |  |  | Tables | 267 | 216 | 51 | 81 | 21-Mar-26 | 22-Apr-26 | 09-Sep-26 |  |  | 12-Oct-26 | Solar-MT09-B
51R1-CC-4262 | Block-54 -MMS Erection - Torque Tube/Raftar | BLOCK-54 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 15-Jan-25 | 06-Apr-26 | 15-Jan-25 | 22-Aug-26 |  |  | Solar-MT09-B
51R1-CC-4392 | Block-55 -MMS Erection - Torque Tube/Raftar | BLOCK-55 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 21-Mar-26 | 22-Apr-26 | 12-Jun-26 | 02-Sep-26 |  |  | Solar-MT09-B
51R1-CC-4522 | Block-56 -MMS Erection - Torque Tube/Raftar | BLOCK-56 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 21-Mar-26 | 22-Apr-26 | 11-Jun-26 | 31-Aug-26 |  |  | Solar-MT09-B
| MMS Erection - Transmission Shaft/Bracing (Σ of 28) |  |  |  |  | Tables | 7476 | 6750 | 726 |  | 14-Feb-25 | 20-May-26 | 14-Feb-25 | 12-Sep-26 | 27-Sep-26 | 25-Oct-26
51R1-CC-1014 | Block-06 -MMS Erection - Transmission Shaft/Bracing | BLOCK-06 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 21-Mar-26 | 22-Apr-26 | 29-Mar-26 | 19-May-26 |  |  | Solar-MT10-B
51R1-CC-1144 | Block-07 -MMS Erection - Transmission Shaft/Bracing | BLOCK-07 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 27-Apr-26 | 28-Mar-26 | 19-May-26 |  |  | Solar-MT10-B
51R1-CC-1274 | Block-11 -MMS Erection - Transmission Shaft/Bracing | BLOCK-11 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 27-Apr-26 | 04-Apr-26 | 10-May-26 |  |  | Solar-MT10-B
51R1-CC-1404 | Block-12 -MMS Erection - Transmission Shaft/Bracing | BLOCK-12 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 27-Apr-26 | 11-Apr-26 | 02-Jun-26 |  |  | Solar-MT10-B
51R1-CC-1534 | Block-13 -MMS Erection - Transmission Shaft/Bracing | BLOCK-13 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 27-Apr-26 | 01-Apr-26 | 19-May-26 |  |  | Solar-MT10-B
51R1-CC-1664 | Block-14 -MMS Erection - Transmission Shaft/Bracing | BLOCK-14 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 27-Apr-26 | 29-Mar-26 | 02-Apr-26 |  |  | Solar-MT10-B
51R1-CC-1794 | Block-35 -MMS Erection - Transmission Shaft/Bracing | BLOCK-35 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 21-Mar-26 | 22-Apr-26 | 19-May-26 | 29-May-26 |  |  | Solar-MT10-B
51R1-CC-1924 | Block-36 -MMS Erection - Transmission Shaft/Bracing | BLOCK-36 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 24-Mar-26 | 26-Apr-26 | 25-Jun-26 | 05-Jul-26 |  |  | Solar-MT10-B
51R1-CC-2054 | Block-37 -MMS Erection - Transmission Shaft/Bracing | BLOCK-37 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 27-Apr-26 | 11-Aug-26 | 17-Aug-26 |  |  | Solar-MT10-B
51R1-CC-2184 | Block-38 -MMS Erection - Transmission Shaft/Bracing | BLOCK-38 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 27-Apr-26 | 27-Jun-26 | 07-Jul-26 |  |  | Solar-MT10-B
51R1-CC-2314 | Block-39 -MMS Erection - Transmission Shaft/Bracing | BLOCK-39 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 08-Feb-26 | 23-Mar-26 | 08-Feb-26 | 23-Mar-26 |  |  | Solar-MT10-B
51R1-CC-2444 | Block-40 -MMS Erection - Transmission Shaft/Bracing | BLOCK-40 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 27-Apr-26 | 10-May-26 | 17-Jul-26 |  |  | Solar-MT10-B
51R1-CC-2574 | Block-41 -MMS Erection - Transmission Shaft/Bracing | BLOCK-41 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 28-Apr-26 | 09-Apr-26 | 12-Aug-26 |  |  | Solar-MT10-B
51R1-CC-2704 | Block-42 -MMS Erection - Transmission Shaft/Bracing | BLOCK-42 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 28-Apr-26 | 29-Apr-26 | 19-May-26 |  |  | Solar-MT10-B
51R1-CC-2834 | Block-43 -MMS Erection - Transmission Shaft/Bracing | BLOCK-43 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 14-Apr-26 | 20-May-26 | 30-Jul-26 | 12-Aug-26 |  |  | Solar-MT10-B
51R1-CC-2964 | Block-44 -MMS Erection - Transmission Shaft/Bracing | BLOCK-44 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 18-Mar-26 | 08-Apr-26 | 18-Mar-26 | 29-Aug-26 |  |  | Solar-MT10-B
51R1-CC-3094 | Block-45 -MMS Erection - Transmission Shaft/Bracing | BLOCK-45 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 28-Apr-26 | 13-Jul-26 | 17-Jul-26 |  |  | Solar-MT10-B
51R1-CC-3224 | Block-46 -MMS Erection - Transmission Shaft/Bracing | BLOCK-46 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 28-Apr-26 | 10-Aug-26 | 25-Aug-26 |  |  | Solar-MT10-B
51R1-CC-3354 | Block-47 -MMS Erection - Transmission Shaft/Bracing | BLOCK-47 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 28-Apr-26 | 21-Aug-26 | 04-Sep-26 |  |  | Solar-MT10-B
51R1-CC-3484 | Block-48 -MMS Erection - Transmission Shaft/Bracing | BLOCK-48 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 28-Apr-26 | 23-Jun-26 | 10-Jul-26 |  |  | Solar-MT10-B
51R1-CC-3614 | Block-49 -MMS Erection - Transmission Shaft/Bracing | BLOCK-49 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 28-Apr-26 | 05-May-26 | 03-Aug-26 |  |  | Solar-MT10-B
51R1-CC-3744 | Block-50 -MMS Erection - Transmission Shaft/Bracing | BLOCK-50 | In Progress |  |  | Tables | 267 | 238 | 29 | 90 | 25-Mar-26 | 28-Apr-26 | 25-Jun-26 |  |  | 04-Oct-26 | Solar-MT10-B
51R1-CC-3874 | Block-51 -MMS Erection - Transmission Shaft/Bracing | BLOCK-51 | In Progress |  |  | Tables | 267 | 238 | 29 | 90 | 25-Mar-26 | 28-Apr-26 | 29-Jun-26 |  |  | 05-Oct-26 | Solar-MT10-B
51R1-CC-4004 | Block-52 -MMS Erection - Transmission Shaft/Bracing | BLOCK-52 | Not Started |  |  | Tables | 267 | 0 | 267 | 0 | 25-Mar-26 | 28-Apr-26 |  |  | 03-Oct-26 | 25-Oct-26 | Solar-MT10-B
51R1-CC-4134 | Block-53 -MMS Erection - Transmission Shaft/Bracing | BLOCK-53 | Not Started |  |  | Tables | 267 | 0 | 267 | 0 | 25-Mar-26 | 28-Apr-26 |  |  | 27-Sep-26 | 20-Oct-26 | Solar-MT10-B
51R1-CC-4264 | Block-54 -MMS Erection - Transmission Shaft/Bracing | BLOCK-54 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 14-Feb-25 | 11-Apr-26 | 14-Feb-25 | 12-Sep-26 |  |  | Solar-MT10-B
51R1-CC-4394 | Block-55 -MMS Erection - Transmission Shaft/Bracing | BLOCK-55 | In Progress |  |  | Tables | 267 | 160 | 107 | 60 | 25-Mar-26 | 28-Apr-26 | 26-Aug-26 |  |  | 06-Oct-26 | Solar-MT10-B
51R1-CC-4524 | Block-56 -MMS Erection - Transmission Shaft/Bracing | BLOCK-56 | In Progress |  |  | Tables | 267 | 240 | 27 | 90 | 25-Mar-26 | 28-Apr-26 | 20-Aug-26 |  |  | 29-Sep-26 | Solar-MT10-B
| MMS Erection - Purlin (Σ of 28) |  |  |  |  | Tables | 7476 | 6119 | 1357 |  | 07-Feb-25 | 20-May-26 | 07-Feb-25 | 25-Sep-26 | 08-Oct-26 | 30-Oct-26
51R1-CC-1016 | Block-06 -MMS Erection - Purlin | BLOCK-06 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 21-Mar-26 | 22-Apr-26 | 20-Apr-26 | 19-May-26 |  |  | Solar-MT11-B
51R1-CC-1146 | Block-07 -MMS Erection - Purlin | BLOCK-07 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 27-Apr-26 | 30-Mar-26 | 19-May-26 |  |  | Solar-MT11-B
51R1-CC-1276 | Block-11 -MMS Erection - Purlin | BLOCK-11 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 27-Apr-26 | 07-May-26 | 14-May-26 |  |  | Solar-MT11-B
51R1-CC-1406 | Block-12 -MMS Erection - Purlin | BLOCK-12 | Completed |  |  | Tables | 267 | 280 | -13 | 100 | 25-Mar-26 | 27-Apr-26 | 20-May-26 | 02-Jul-26 |  |  | Solar-MT11-B
51R1-CC-1536 | Block-13 -MMS Erection - Purlin | BLOCK-13 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 27-Apr-26 | 04-May-26 | 19-May-26 |  |  | Solar-MT11-B
51R1-CC-1666 | Block-14 -MMS Erection - Purlin | BLOCK-14 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 27-Apr-26 | 29-Mar-26 | 19-Apr-26 |  |  | Solar-MT11-B
51R1-CC-1796 | Block-35 -MMS Erection - Purlin | BLOCK-35 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 21-Mar-26 | 22-Apr-26 | 21-May-26 | 26-May-26 |  |  | Solar-MT11-B
51R1-CC-1926 | Block-36 -MMS Erection - Purlin | BLOCK-36 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 24-Mar-26 | 26-Apr-26 | 13-Jun-26 | 24-Jun-26 |  |  | Solar-MT11-B
51R1-CC-2056 | Block-37 -MMS Erection - Purlin | BLOCK-37 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 27-Apr-26 | 24-Jul-26 | 16-Aug-26 |  |  | Solar-MT11-B
51R1-CC-2186 | Block-38 -MMS Erection - Purlin | BLOCK-38 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 27-Apr-26 | 04-Jul-26 | 17-Jul-26 |  |  | Solar-MT11-B
51R1-CC-2316 | Block-39 -MMS Erection - Purlin | BLOCK-39 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 16-Mar-26 | 24-Mar-26 | 16-Mar-26 | 30-Mar-26 |  |  | Solar-MT11-B
51R1-CC-2446 | Block-40 -MMS Erection - Purlin | BLOCK-40 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 27-Apr-26 | 16-May-26 | 17-Jul-26 |  |  | Solar-MT11-B
51R1-CC-2576 | Block-41 -MMS Erection - Purlin | BLOCK-41 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 28-Apr-26 | 19-May-26 | 12-Aug-26 |  |  | Solar-MT11-B
51R1-CC-2706 | Block-42 -MMS Erection - Purlin | BLOCK-42 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 28-Apr-26 | 22-May-26 | 18-Aug-26 |  |  | Solar-MT11-B
51R1-CC-2836 | Block-43 -MMS Erection - Purlin | BLOCK-43 | In Progress |  |  | Tables | 267 | 187 | 80 | 70 | 14-Apr-26 | 20-May-26 | 11-Aug-26 |  |  | 07-Oct-26 | Solar-MT11-B
51R1-CC-2966 | Block-44 -MMS Erection - Purlin | BLOCK-44 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 21-Mar-26 | 15-Apr-26 | 21-Mar-26 | 29-Aug-26 |  |  | Solar-MT11-B
51R1-CC-3096 | Block-45 -MMS Erection - Purlin | BLOCK-45 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 28-Apr-26 | 13-Jul-26 | 17-Jul-26 |  |  | Solar-MT11-B
51R1-CC-3226 | Block-46 -MMS Erection - Purlin | BLOCK-46 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 28-Apr-26 | 13-Aug-26 | 31-Aug-26 |  |  | Solar-MT11-B
51R1-CC-3356 | Block-47 -MMS Erection - Purlin | BLOCK-47 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 28-Apr-26 | 24-Aug-26 | 04-Sep-26 |  |  | Solar-MT11-B
51R1-CC-3486 | Block-48 -MMS Erection - Purlin | BLOCK-48 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 28-Apr-26 | 30-Jun-26 | 08-Jul-26 |  |  | Solar-MT11-B
51R1-CC-3616 | Block-49 -MMS Erection - Purlin | BLOCK-49 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 25-Mar-26 | 28-Apr-26 | 05-Jun-26 | 17-Aug-26 |  |  | Solar-MT11-B
51R1-CC-3746 | Block-50 -MMS Erection - Purlin | BLOCK-50 | Not Started |  |  | Tables | 267 | 0 | 267 | 0 | 25-Mar-26 | 28-Apr-26 |  |  | 08-Oct-26 | 30-Oct-26 | Solar-MT11-B
51R1-CC-3876 | Block-51 -MMS Erection - Purlin | BLOCK-51 | Not Started |  |  | Tables | 267 | 0 | 267 | 0 | 25-Mar-26 | 28-Apr-26 |  |  | 08-Oct-26 | 30-Oct-26 | Solar-MT11-B
51R1-CC-4006 | Block-52 -MMS Erection - Purlin | BLOCK-52 | Not Started |  |  | Tables | 267 | 0 | 267 | 0 | 25-Mar-26 | 28-Apr-26 |  |  | 08-Oct-26 | 30-Oct-26 | Solar-MT11-B
51R1-CC-4136 | Block-53 -MMS Erection - Purlin | BLOCK-53 | Not Started |  |  | Tables | 267 | 0 | 267 | 0 | 25-Mar-26 | 28-Apr-26 |  |  | 08-Oct-26 | 30-Oct-26 | Solar-MT11-B
51R1-CC-4266 | Block-54 -MMS Erection - Purlin | BLOCK-54 | Completed |  |  | Tables | 267 | 267 | 0 | 100 | 07-Feb-25 | 11-Apr-26 | 07-Feb-25 | 25-Sep-26 |  |  | Solar-MT11-B
51R1-CC-4396 | Block-55 -MMS Erection - Purlin | BLOCK-55 | In Progress |  |  | Tables | 267 | 72 | 195 | 27 | 25-Mar-26 | 28-Apr-26 | 28-Aug-26 |  |  | 14-Oct-26 | Solar-MT11-B
51R1-CC-4526 | Block-56 -MMS Erection - Purlin | BLOCK-56 | In Progress |  |  | Tables | 267 | 240 | 27 | 90 | 25-Mar-26 | 28-Apr-26 | 01-Sep-26 |  |  | 07-Oct-26 | Solar-MT11-B
| MMS - RFI Completion (Σ of 28) |  |  |  |  | Days | 0 | 0 | 0 |  | 21-Mar-26 | 25-May-26 | 01-Jul-26 | 01-Sep-26 | 27-Sep-26 | 03-Nov-26
51R1-CC-1018 | Block-06 -MMS - RFI Completion | BLOCK-06 | Completed |  |  | Days |  | 0 | 0 | 100 | 25-Mar-26 | 27-Apr-26 | 12-Jul-26 | 13-Jul-26
51R1-CC-1148 | Block-07 -MMS - RFI Completion | BLOCK-07 | Completed |  |  | Days |  | 0 | 0 | 100 | 29-Mar-26 | 03-May-26 | 12-Jul-26 | 13-Jul-26
51R1-CC-1278 | Block-11 -MMS - RFI Completion | BLOCK-11 | Completed |  |  | Days |  | 0 | 0 | 100 | 29-Mar-26 | 03-May-26 | 16-Aug-26 | 20-Aug-26
51R1-CC-1408 | Block-12 -MMS - RFI Completion | BLOCK-12 | Completed |  |  | Days |  | 0 | 0 | 100 | 29-Mar-26 | 03-May-26 | 16-Aug-26 | 19-Aug-26
51R1-CC-1538 | Block-13 -MMS - RFI Completion | BLOCK-13 | Completed |  |  | Days |  | 0 | 0 | 100 | 29-Mar-26 | 03-May-26 | 01-Jul-26 | 03-Jul-26
51R1-CC-1668 | Block-14 -MMS - RFI Completion | BLOCK-14 | Completed |  |  | Days |  | 0 | 0 | 100 | 29-Mar-26 | 03-May-26 | 01-Jul-26 | 03-Jul-26
51R1-CC-1798 | Block-35 -MMS - RFI Completion | BLOCK-35 | Completed |  |  | Days |  | 0 | 0 | 100 | 25-Mar-26 | 27-Apr-26 | 16-Aug-26 | 20-Aug-26
51R1-CC-1928 | Block-36 -MMS - RFI Completion | BLOCK-36 | Completed |  |  | Days |  | 0 | 0 | 100 | 28-Mar-26 | 01-May-26 | 18-Aug-26 | 21-Aug-26
51R1-CC-2058 | Block-37 -MMS - RFI Completion | BLOCK-37 | Completed |  |  | Days |  | 0 | 0 | 100 | 29-Mar-26 | 03-May-26 | 17-Aug-26 | 21-Aug-26
51R1-CC-2188 | Block-38 -MMS - RFI Completion | BLOCK-38 | Completed |  |  | Days |  | 0 | 0 | 100 | 29-Mar-26 | 03-May-26 | 17-Aug-26 | 21-Aug-26
51R1-CC-2318 | Block-39 -MMS - RFI Completion | BLOCK-39 | Completed |  |  | Days |  | 0 | 0 | 100 | 21-Mar-26 | 22-Apr-26 | 16-Aug-26 | 17-Aug-26
51R1-CC-2448 | Block-40 -MMS - RFI Completion | BLOCK-40 | Completed |  |  | Days |  | 0 | 0 | 100 | 29-Mar-26 | 03-May-26 | 17-Aug-26 | 21-Aug-26
51R1-CC-2578 | Block-41 -MMS - RFI Completion | BLOCK-41 | Completed |  |  | Days |  | 0 | 0 | 100 | 29-Mar-26 | 03-May-26 | 17-Aug-26 | 21-Aug-26
51R1-CC-2708 | Block-42 -MMS - RFI Completion | BLOCK-42 | Completed |  |  | Days |  | 0 | 0 | 100 | 29-Mar-26 | 03-May-26 | 17-Aug-26 | 21-Aug-26
51R1-CC-2838 | Block-43 -MMS - RFI Completion | BLOCK-43 | Not Started |  |  | Days |  | 0 | 0 | 0 | 19-Apr-26 | 25-May-26 |  |  | 27-Sep-26 | 21-Oct-26
51R1-CC-2968 | Block-44 -MMS - RFI Completion | BLOCK-44 | In Progress |  |  | Days |  | 0 | 0 | 90 | 25-Mar-26 | 27-Apr-26 | 17-Aug-26 |  |  | 30-Sep-26
51R1-CC-3098 | Block-45 -MMS - RFI Completion | BLOCK-45 | Completed |  |  | Days |  | 0 | 0 | 100 | 29-Mar-26 | 03-May-26 | 17-Aug-26 | 21-Aug-26
51R1-CC-3228 | Block-46 -MMS - RFI Completion | BLOCK-46 | Completed |  |  | Days |  | 0 | 0 | 100 | 29-Mar-26 | 03-May-26 | 17-Aug-26 | 01-Sep-26
51R1-CC-3358 | Block-47 -MMS - RFI Completion | BLOCK-47 | In Progress |  |  | Days |  | 0 | 0 | 20 | 29-Mar-26 | 03-May-26 | 25-Aug-26 |  |  | 15-Oct-26
51R1-CC-3488 | Block-48 -MMS - RFI Completion | BLOCK-48 | Completed |  |  | Days |  | 0 | 0 | 100 | 29-Mar-26 | 03-May-26 | 17-Aug-26 | 21-Aug-26
51R1-CC-3618 | Block-49 -MMS - RFI Completion | BLOCK-49 | Completed |  |  | Days |  | 0 | 0 | 100 | 29-Mar-26 | 03-May-26 | 17-Aug-26 | 20-Aug-26
51R1-CC-3748 | Block-50 -MMS - RFI Completion | BLOCK-50 | In Progress |  |  | Days |  | 0 | 0 | 80 | 29-Mar-26 | 03-May-26 | 21-Sep-26 |  |  | 03-Nov-26
51R1-CC-3878 | Block-51 -MMS - RFI Completion | BLOCK-51 | Not Started |  |  | Days |  | 0 | 0 | 0 | 29-Mar-26 | 03-May-26 |  |  | 12-Oct-26 | 03-Nov-26
51R1-CC-4008 | Block-52 -MMS - RFI Completion | BLOCK-52 | In Progress |  |  | Days |  | 0 | 0 | 50 | 29-Mar-26 | 03-May-26 | 20-Sep-26 |  |  | 03-Nov-26
51R1-CC-4138 | Block-53 -MMS - RFI Completion | BLOCK-53 | Not Started |  |  | Days |  | 0 | 0 | 0 | 29-Mar-26 | 03-May-26 |  |  | 12-Oct-26 | 03-Nov-26
51R1-CC-4268 | Block-54 -MMS - RFI Completion | BLOCK-54 | In Progress |  |  | Days |  | 0 | 0 | 50 | 21-Mar-26 | 22-Apr-26 | 17-Aug-26 |  |  | 09-Oct-26
51R1-CC-4398 | Block-55 -MMS - RFI Completion | BLOCK-55 | In Progress |  |  | Days |  | 0 | 0 | 20 | 29-Mar-26 | 03-May-26 | 26-Aug-26 |  |  | 19-Oct-26
51R1-CC-4528 | Block-56 -MMS - RFI Completion | BLOCK-56 | In Progress |  |  | Days |  | 0 | 0 | 60 | 29-Mar-26 | 03-May-26 | 03-Sep-26 |  |  | 12-Oct-26
| Module Installation (Σ of 28) |  |  |  |  | MegaWatt DC | 477 | 968 | -491 |  | 03-Apr-26 | 11-Jun-26 | 21-Apr-26 | 13-Sep-26 | 05-Oct-26 | 29-Nov-26
51R1-CC-1020 | Block-06 -Module Installation | BLOCK-06 | Completed |  |  | MegaWatt DC | 17 | 20 | -3 | 100 | 12-Apr-26 | 08-May-26 | 21-Apr-26 | 19-May-26 |  |  | Solar-MT12-B
51R1-CC-1150 | Block-07 -Module Installation | BLOCK-07 | Completed |  |  | MegaWatt DC | 17 | 149 | -132 | 100 | 17-Apr-26 | 13-May-26 | 05-May-26 | 19-May-26 |  |  | Solar-MT12-B
51R1-CC-1280 | Block-11 -Module Installation | BLOCK-11 | Completed |  |  | MegaWatt DC | 17 | 27 | -10 | 100 | 17-Apr-26 | 13-May-26 | 31-May-26 | 28-Jun-26 |  |  | Solar-MT12-B
51R1-CC-1410 | Block-12 -Module Installation | BLOCK-12 | Completed |  |  | MegaWatt DC | 17 | 17 | 0 | 100 | 17-Apr-26 | 13-May-26 | 19-Jun-26 | 05-Jul-26 |  |  | Solar-MT12-B
51R1-CC-1540 | Block-13 -Module Installation | BLOCK-13 | Completed |  |  | MegaWatt DC | 17 | 175 | -158 | 100 | 17-Apr-26 | 13-May-26 | 19-May-26 | 22-Jun-26 |  |  | Solar-MT12-B
51R1-CC-1670 | Block-14 -Module Installation | BLOCK-14 | Completed |  |  | MegaWatt DC | 17 | 20 | -3 | 100 | 17-Apr-26 | 13-May-26 | 19-May-26 | 11-Jun-26 |  |  | Solar-MT12-B
51R1-CC-1800 | Block-35 -Module Installation | BLOCK-35 | Completed |  |  | MegaWatt DC | 17 | 20 | -3 | 100 | 12-Apr-26 | 08-May-26 | 24-Jun-26 | 07-Jul-26 |  |  | Solar-MT12-B
51R1-CC-1930 | Block-36 -Module Installation | BLOCK-36 | Completed |  |  | MegaWatt DC | 17 | 39 | -22 | 100 | 16-Apr-26 | 12-May-26 | 12-Jul-26 | 19-Aug-26 |  |  | Solar-MT12-B
51R1-CC-2060 | Block-37 -Module Installation | BLOCK-37 | Completed |  |  | MegaWatt DC | 17 | 95 | -78 | 100 | 17-Apr-26 | 13-May-26 | 26-Aug-26 | 07-Sep-26 |  |  | Solar-MT12-B
51R1-CC-2190 | Block-38 -Module Installation | BLOCK-38 | Completed |  |  | MegaWatt DC | 17 | 32 | -15 | 100 | 17-Apr-26 | 13-May-26 | 02-Aug-26 | 26-Aug-26 |  |  | Solar-MT12-B
51R1-CC-2320 | Block-39 -Module Installation | BLOCK-39 | Completed |  |  | MegaWatt DC | 17 | 24 | -7 | 100 | 07-Apr-26 | 03-May-26 | 06-Jun-26 | 08-Jul-26 |  |  | Solar-MT12-B
51R1-CC-2450 | Block-40 -Module Installation | BLOCK-40 | Completed |  |  | MegaWatt DC | 17 | 38 | -21 | 100 | 17-Apr-26 | 13-May-26 | 04-Jul-26 | 19-Jul-26 |  |  | Solar-MT12-B
51R1-CC-2580 | Block-41 -Module Installation | BLOCK-41 | Completed |  |  | MegaWatt DC | 17 | 25 | -8 | 100 | 03-Apr-26 | 01-Jun-26 | 12-Aug-26 | 11-Sep-26 |  |  | Solar-MT12-B
51R1-CC-2710 | Block-42 -Module Installation | BLOCK-42 | Completed |  |  | MegaWatt DC | 17 | 24 | -7 | 100 | 25-Apr-26 | 20-May-26 | 27-Jul-26 | 26-Aug-26 |  |  | Solar-MT12-B
51R1-CC-2840 | Block-43 -Module Installation | BLOCK-43 | Not Started |  |  | MegaWatt DC | 17 | 0 | 17 | 0 | 17-May-26 | 11-Jun-26 |  |  | 05-Oct-26 | 29-Oct-26 | Solar-MT12-B
51R1-CC-2970 | Block-44 -Module Installation | BLOCK-44 | In Progress |  |  | MegaWatt DC | 17 | 27 | -10 | 98 | 19-Apr-26 | 15-May-26 | 10-Jul-26 |  |  | 28-Sep-26 | Solar-MT12-B
51R1-CC-3100 | Block-45 -Module Installation | BLOCK-45 | In Progress |  |  | MegaWatt DC | 17 | 41 | -24 | 98 | 25-Apr-26 | 20-May-26 | 21-Aug-26 |  |  | 28-Sep-26 | Solar-MT12-B
51R1-CC-3230 | Block-46 -Module Installation | BLOCK-46 | Completed |  |  | MegaWatt DC | 17 | 47 | -30 | 100 | 25-Apr-26 | 20-May-26 | 29-Aug-26 | 12-Sep-26 |  |  | Solar-MT12-B
51R1-CC-3360 | Block-47 -Module Installation | BLOCK-47 | Completed |  |  | MegaWatt DC | 17 | 36 | -19 | 100 | 25-Apr-26 | 20-May-26 | 02-Sep-26 | 13-Sep-26 |  |  | Solar-MT12-B
51R1-CC-3490 | Block-48 -Module Installation | BLOCK-48 | Completed |  |  | MegaWatt DC | 17 | 60 | -43 | 100 | 25-Apr-26 | 20-May-26 | 20-Jul-26 | 23-Aug-26 |  |  | Solar-MT12-B
51R1-CC-3620 | Block-49 -Module Installation | BLOCK-49 | In Progress |  |  | MegaWatt DC | 17 | 50 | -33 | 98 | 25-Apr-26 | 20-May-26 | 18-Aug-26 |  |  | 28-Sep-26 | Solar-MT12-B
51R1-CC-3750 | Block-50 -Module Installation | BLOCK-50 | Not Started |  |  | MegaWatt DC | 17 | 0 | 17 | 0 | 25-Apr-26 | 20-May-26 |  |  | 27-Oct-26 | 18-Nov-26 | Solar-MT12-B
51R1-CC-3880 | Block-51 -Module Installation | BLOCK-51 | Not Started |  |  | MegaWatt DC | 17 | 0 | 17 | 0 | 25-Apr-26 | 20-May-26 |  |  | 27-Oct-26 | 18-Nov-26 | Solar-MT12-B
51R1-CC-4010 | Block-52 -Module Installation | BLOCK-52 | Not Started |  |  | MegaWatt DC | 17 | 0 | 17 | 0 | 25-Apr-26 | 20-May-26 |  |  | 30-Oct-26 | 21-Nov-26 | Solar-MT12-B
51R1-CC-4140 | Block-53 -Module Installation | BLOCK-53 | Not Started |  |  | MegaWatt DC | 17 | 0 | 17 | 0 | 25-Apr-26 | 20-May-26 |  |  | 07-Nov-26 | 29-Nov-26 | Solar-MT12-B
51R1-CC-4270 | Block-54 -Module Installation | BLOCK-54 | In Progress |  |  | MegaWatt DC | 17 | 2 | 15 | 11 | 14-Apr-26 | 09-May-26 | 21-Sep-26 |  |  | 24-Oct-26 | Solar-MT12-B
51R1-CC-4400 | Block-55 -Module Installation | BLOCK-55 | Not Started |  |  | MegaWatt DC | 17 | 0 | 17 | 0 | 25-Apr-26 | 20-May-26 |  |  | 07-Nov-26 | 29-Nov-26 | Solar-MT12-B
51R1-CC-4530 | Block-56 -Module Installation | BLOCK-56 | Not Started |  |  | MegaWatt DC | 18 | 0 | 18 | 0 | 25-Apr-26 | 20-May-26 |  |  | 07-Nov-26 | 29-Nov-26 | Solar-MT12-B
| Module - RFI Completion (Σ of 28) |  |  |  |  | Days | 0 | 0 | 0 |  | 12-Apr-26 | 16-Jun-26 | 02-Jul-26 | 15-Sep-26 | 06-Oct-26 | 03-Dec-26
51R1-CC-1022 | Block-06 -Module - RFI Completion | BLOCK-06 | Completed |  |  | Days |  | 0 | 0 | 100 | 17-Apr-26 | 13-May-26 | 14-Jul-26 | 15-Jul-26
51R1-CC-1152 | Block-07 -Module - RFI Completion | BLOCK-07 | Completed |  |  | Days |  | 0 | 0 | 100 | 22-Apr-26 | 18-May-26 | 12-Jul-26 | 15-Jul-26
51R1-CC-1282 | Block-11 -Module - RFI Completion | BLOCK-11 | Completed |  |  | Days |  | 0 | 0 | 100 | 22-Apr-26 | 18-May-26 | 16-Aug-26 | 21-Aug-26
51R1-CC-1412 | Block-12 -Module - RFI Completion | BLOCK-12 | Completed |  |  | Days |  | 0 | 0 | 100 | 22-Apr-26 | 18-May-26 | 16-Aug-26 | 19-Aug-26
51R1-CC-1542 | Block-13 -Module - RFI Completion | BLOCK-13 | Completed |  |  | Days |  | 0 | 0 | 100 | 22-Apr-26 | 18-May-26 | 02-Jul-26 | 04-Jul-26
51R1-CC-1672 | Block-14 -Module - RFI Completion | BLOCK-14 | Completed |  |  | Days |  | 0 | 0 | 100 | 22-Apr-26 | 18-May-26 | 02-Jul-26 | 04-Jul-26
51R1-CC-1802 | Block-35 -Module - RFI Completion | BLOCK-35 | Completed |  |  | Days |  | 0 | 0 | 100 | 17-Apr-26 | 13-May-26 | 15-Aug-26 | 18-Aug-26
51R1-CC-1932 | Block-36 -Module - RFI Completion | BLOCK-36 | Completed |  |  | Days |  | 0 | 0 | 100 | 21-Apr-26 | 17-May-26 | 17-Aug-26 | 20-Aug-26
51R1-CC-2062 | Block-37 -Module - RFI Completion | BLOCK-37 | Completed |  |  | Days |  | 0 | 0 | 100 | 22-Apr-26 | 18-May-26 | 27-Aug-26 | 09-Sep-26
51R1-CC-2192 | Block-38 -Module - RFI Completion | BLOCK-38 | Completed |  |  | Days |  | 0 | 0 | 100 | 22-Apr-26 | 18-May-26 | 21-Aug-26 | 01-Sep-26
51R1-CC-2322 | Block-39 -Module - RFI Completion | BLOCK-39 | Completed |  |  | Days |  | 0 | 0 | 100 | 12-Apr-26 | 08-May-26 | 16-Aug-26 | 18-Aug-26
51R1-CC-2452 | Block-40 -Module - RFI Completion | BLOCK-40 | Completed |  |  | Days |  | 0 | 0 | 100 | 22-Apr-26 | 18-May-26 | 18-Aug-26 | 22-Aug-26
51R1-CC-2582 | Block-41 -Module - RFI Completion | BLOCK-41 | Completed |  |  | Days |  | 0 | 0 | 100 | 12-May-26 | 06-Jun-26 | 18-Aug-26 | 15-Sep-26
51R1-CC-2712 | Block-42 -Module - RFI Completion | BLOCK-42 | Completed |  |  | Days |  | 0 | 0 | 100 | 30-Apr-26 | 25-May-26 | 17-Aug-26 | 03-Sep-26
51R1-CC-2842 | Block-43 -Module - RFI Completion | BLOCK-43 | Not Started |  |  | Days |  | 0 | 0 | 0 | 22-May-26 | 16-Jun-26 |  |  | 11-Oct-26 | 02-Nov-26
51R1-CC-2972 | Block-44 -Module - RFI Completion | BLOCK-44 | In Progress |  |  | Days |  | 0 | 0 | 90 | 24-Apr-26 | 20-May-26 | 18-Aug-26 |  |  | 03-Oct-26
51R1-CC-3102 | Block-45 -Module - RFI Completion | BLOCK-45 | In Progress |  |  | Days |  | 0 | 0 | 60 | 30-Apr-26 | 25-May-26 | 18-Aug-26 |  |  | 03-Oct-26
51R1-CC-3232 | Block-46 -Module - RFI Completion | BLOCK-46 | In Progress |  |  | Days |  | 0 | 0 | 90 | 30-Apr-26 | 25-May-26 | 29-Aug-26 |  |  | 01-Oct-26
51R1-CC-3362 | Block-47 -Module - RFI Completion | BLOCK-47 | In Progress |  |  | Days |  | 0 | 0 | 30 | 30-Apr-26 | 25-May-26 | 31-Aug-26 |  |  | 14-Oct-26
51R1-CC-3492 | Block-48 -Module - RFI Completion | BLOCK-48 | Completed |  |  | Days |  | 0 | 0 | 100 | 30-Apr-26 | 25-May-26 | 17-Aug-26 | 21-Aug-26
51R1-CC-3622 | Block-49 -Module - RFI Completion | BLOCK-49 | In Progress |  |  | Days |  | 0 | 0 | 90 | 30-Apr-26 | 25-May-26 | 18-Aug-26 |  |  | 03-Oct-26
51R1-CC-3752 | Block-50 -Module - RFI Completion | BLOCK-50 | Not Started |  |  | Days |  | 0 | 0 | 0 | 30-Apr-26 | 25-May-26 |  |  | 01-Nov-26 | 23-Nov-26
51R1-CC-3882 | Block-51 -Module - RFI Completion | BLOCK-51 | Not Started |  |  | Days |  | 0 | 0 | 0 | 30-Apr-26 | 25-May-26 |  |  | 29-Oct-26 | 21-Nov-26
51R1-CC-4012 | Block-52 -Module - RFI Completion | BLOCK-52 | Not Started |  |  | Days |  | 0 | 0 | 0 | 30-Apr-26 | 25-May-26 |  |  | 01-Nov-26 | 23-Nov-26
51R1-CC-4142 | Block-53 -Module - RFI Completion | BLOCK-53 | Not Started |  |  | Days |  | 0 | 0 | 0 | 30-Apr-26 | 25-May-26 |  |  | 11-Nov-26 | 03-Dec-26
51R1-CC-4272 | Block-54 -Module - RFI Completion | BLOCK-54 | Not Started |  |  | Days |  | 0 | 0 | 0 | 19-Apr-26 | 15-May-26 |  |  | 06-Oct-26 | 28-Oct-26
51R1-CC-4402 | Block-55 -Module - RFI Completion | BLOCK-55 | Not Started |  |  | Days |  | 0 | 0 | 0 | 30-Apr-26 | 25-May-26 |  |  | 11-Nov-26 | 03-Dec-26
51R1-CC-4532 | Block-56 -Module - RFI Completion | BLOCK-56 | Not Started |  |  | Days |  | 0 | 0 | 0 | 30-Apr-26 | 25-May-26 |  |  | 11-Nov-26 | 03-Dec-26
| DC Cable Laying (Σ of 28) |  |  |  |  | Kilometer | 3388 | 2466 | 922 |  | 07-Feb-25 | 06-Jun-26 | 07-Feb-25 | 24-Sep-26 | 07-Oct-26 | 24-Nov-26
51R1-CC-1024 | Block-06 -DC Cable Laying | BLOCK-06 | Completed |  |  | Kilometer | 121 | 121 | 0 | 100 | 13-Apr-26 | 03-May-26 | 12-Apr-26 | 08-Jul-26 |  |  | Solar-MT13-B
51R1-CC-1154 | Block-07 -DC Cable Laying | BLOCK-07 | Completed |  |  | Kilometer | 121 | 121 | 0 | 100 | 19-Apr-26 | 08-May-26 | 03-Apr-26 | 19-Apr-26 |  |  | Solar-MT13-B
51R1-CC-1284 | Block-11 -DC Cable Laying | BLOCK-11 | Completed |  |  | Kilometer | 121 | 121 | 0 | 100 | 19-Apr-26 | 08-May-26 | 09-Apr-26 | 02-May-26 |  |  | Solar-MT13-B
51R1-CC-1414 | Block-12 -DC Cable Laying | BLOCK-12 | Completed |  |  | Kilometer | 121 | 121 | 0 | 100 | 19-Apr-26 | 08-May-26 | 06-Apr-26 | 28-Apr-26 |  |  | Solar-MT13-B
51R1-CC-1544 | Block-13 -DC Cable Laying | BLOCK-13 | Completed |  |  | Kilometer | 121 | 121 | 0 | 100 | 19-Apr-26 | 08-May-26 | 09-Apr-26 | 05-May-26 |  |  | Solar-MT13-B
51R1-CC-1674 | Block-14 -DC Cable Laying | BLOCK-14 | Completed |  |  | Kilometer | 121 | 121 | 0 | 100 | 19-Apr-26 | 08-May-26 | 27-Mar-26 | 05-May-26 |  |  | Solar-MT13-B
51R1-CC-1804 | Block-35 -DC Cable Laying | BLOCK-35 | Completed |  |  | Kilometer | 121 | 121 | 0 | 100 | 10-Feb-25 | 23-Mar-26 | 10-Feb-25 | 11-Aug-26 |  |  | Solar-MT13-B
51R1-CC-1934 | Block-36 -DC Cable Laying | BLOCK-36 | Completed |  |  | Kilometer | 121 | 121 | 0 | 100 | 17-Apr-26 | 06-May-26 | 18-Jul-26 | 21-Aug-26 |  |  | Solar-MT13-B
51R1-CC-2064 | Block-37 -DC Cable Laying | BLOCK-37 | Completed |  |  | Kilometer | 121 | 121 | 0 | 100 | 19-Dec-25 | 03-Apr-26 | 19-Dec-25 | 15-Sep-26 |  |  | Solar-MT13-B
51R1-CC-2194 | Block-38 -DC Cable Laying | BLOCK-38 | Completed |  |  | Kilometer | 121 | 121 | 0 | 100 | 19-Apr-26 | 08-May-26 | 21-Aug-26 | 24-Aug-26 |  |  | Solar-MT13-B
51R1-CC-2324 | Block-39 -DC Cable Laying | BLOCK-39 | Completed |  |  | Kilometer | 121 | 121 | 0 | 100 | 08-Apr-26 | 27-Apr-26 | 23-Jul-26 | 11-Aug-26 |  |  | Solar-MT13-B
51R1-CC-2454 | Block-40 -DC Cable Laying | BLOCK-40 | Completed |  |  | Kilometer | 121 | 121 | 0 | 100 | 19-Apr-26 | 08-May-26 | 26-Aug-26 | 30-Aug-26 |  |  | Solar-MT13-B
51R1-CC-2584 | Block-41 -DC Cable Laying | BLOCK-41 | Completed |  |  | Kilometer | 121 | 121 | 0 | 100 | 09-Apr-26 | 28-Apr-26 | 23-Apr-26 | 13-Sep-26 |  |  | Solar-MT13-B
51R1-CC-2714 | Block-42 -DC Cable Laying | BLOCK-42 | Completed |  |  | Kilometer | 121 | 121 | 0 | 100 | 26-Apr-26 | 15-May-26 | 26-Aug-26 | 31-Aug-26 |  |  | Solar-MT13-B
51R1-CC-2844 | Block-43 -DC Cable Laying | BLOCK-43 | Not Started |  |  | Kilometer | 121 | 0 | 121 | 0 | 18-May-26 | 06-Jun-26 |  |  | 07-Oct-26 | 23-Oct-26 | Solar-MT13-B
51R1-CC-2974 | Block-44 -DC Cable Laying | BLOCK-44 | Completed |  |  | Kilometer | 121 | 121 | 0 | 100 | 20-Apr-26 | 09-May-26 | 13-Sep-26 | 17-Sep-26 |  |  | Solar-MT13-B
51R1-CC-3104 | Block-45 -DC Cable Laying | BLOCK-45 | In Progress |  |  | Kilometer | 121 | 46 | 75 | 38 | 26-Apr-26 | 15-May-26 | 21-Sep-26 |  |  | 08-Oct-26 | Solar-MT13-B
51R1-CC-3234 | Block-46 -DC Cable Laying | BLOCK-46 | Completed |  |  | Kilometer | 121 | 121 | 0 | 100 | 26-Apr-26 | 15-May-26 | 12-Sep-26 | 15-Sep-26 |  |  | Solar-MT13-B
51R1-CC-3364 | Block-47 -DC Cable Laying | BLOCK-47 | Completed |  |  | Kilometer | 121 | 121 | 0 | 100 | 26-Apr-26 | 15-May-26 | 08-Sep-26 | 15-Sep-26 |  |  | Solar-MT13-B
51R1-CC-3494 | Block-48 -DC Cable Laying | BLOCK-48 | Completed |  |  | Kilometer | 121 | 121 | 0 | 100 | 26-Apr-26 | 15-May-26 | 29-Aug-26 | 06-Sep-26 |  |  | Solar-MT13-B
51R1-CC-3624 | Block-49 -DC Cable Laying | BLOCK-49 | Completed |  |  | Kilometer | 121 | 121 | 0 | 100 | 26-Apr-26 | 15-May-26 | 12-Sep-26 | 24-Sep-26 |  |  | Solar-MT13-B
51R1-CC-3754 | Block-50 -DC Cable Laying | BLOCK-50 | Not Started |  |  | Kilometer | 121 | 0 | 121 | 0 | 26-Apr-26 | 15-May-26 |  |  | 28-Oct-26 | 14-Nov-26 | Solar-MT13-B
51R1-CC-3884 | Block-51 -DC Cable Laying | BLOCK-51 | In Progress |  |  | Kilometer | 121 | 58 | 63 | 48 | 26-Apr-26 | 15-May-26 | 02-Jul-26 |  |  | 06-Oct-26 | Solar-MT13-B
51R1-CC-4014 | Block-52 -DC Cable Laying | BLOCK-52 | Not Started |  |  | Kilometer | 121 | 0 | 121 | 0 | 26-Apr-26 | 15-May-26 |  |  | 31-Oct-26 | 16-Nov-26 | Solar-MT13-B
51R1-CC-4144 | Block-53 -DC Cable Laying | BLOCK-53 | Not Started |  |  | Kilometer | 121 | 0 | 121 | 0 | 26-Apr-26 | 15-May-26 |  |  | 08-Nov-26 | 24-Nov-26 | Solar-MT13-B
51R1-CC-4274 | Block-54 -DC Cable Laying | BLOCK-54 | In Progress |  |  | Kilometer | 121 | 63 | 58 | 52 | 07-Feb-25 | 28-Mar-26 | 07-Feb-25 |  |  | 06-Oct-26 | Solar-MT13-B
51R1-CC-4404 | Block-55 -DC Cable Laying | BLOCK-55 | Not Started |  |  | Kilometer | 121 | 0 | 121 | 0 | 26-Apr-26 | 15-May-26 |  |  | 08-Nov-26 | 24-Nov-26 | Solar-MT13-B
51R1-CC-4534 | Block-56 -DC Cable Laying | BLOCK-56 | Not Started |  |  | Kilometer | 121 | 0 | 121 | 0 | 26-Apr-26 | 15-May-26 |  |  | 08-Nov-26 | 24-Nov-26 | Solar-MT13-B
| Module Interconnection & MC4 Termination (Σ of 28) |  |  |  |  | Number | 1316 | 829 | 487 |  | 11-Apr-26 | 12-Jun-26 | 27-May-26 | 25-Sep-26 | 27-Sep-26 | 30-Nov-26
51R1-CC-1026 | Block-06 -Module Interconnection & MC4 Termination | BLOCK-06 | Completed |  |  | Number | 47 | 47 | 0 | 100 | 16-Apr-26 | 12-May-26 | 15-Jul-26 | 17-Jul-26 |  |  | Solar-MT14-B
51R1-CC-1156 | Block-07 -Module Interconnection & MC4 Termination | BLOCK-07 | Completed |  |  | Number | 47 | 47 | 0 | 100 | 21-Apr-26 | 17-May-26 | 08-Jun-26 | 15-Jul-26 |  |  | Solar-MT14-B
51R1-CC-1286 | Block-11 -Module Interconnection & MC4 Termination | BLOCK-11 | Completed |  |  | Number | 47 | 47 | 0 | 100 | 21-Apr-26 | 17-May-26 | 12-Aug-26 | 18-Aug-26 |  |  | Solar-MT14-B
51R1-CC-1416 | Block-12 -Module Interconnection & MC4 Termination | BLOCK-12 | Completed |  |  | Number | 47 | 47 | 0 | 100 | 21-Apr-26 | 17-May-26 | 08-Aug-26 | 11-Aug-26 |  |  | Solar-MT14-B
51R1-CC-1546 | Block-13 -Module Interconnection & MC4 Termination | BLOCK-13 | Completed |  |  | Number | 47 | 47 | 0 | 100 | 21-Apr-26 | 17-May-26 | 05-Jul-26 | 06-Jul-26 |  |  | Solar-MT14-B
51R1-CC-1676 | Block-14 -Module Interconnection & MC4 Termination | BLOCK-14 | Completed |  |  | Number | 47 | 47 | 0 | 100 | 21-Apr-26 | 17-May-26 | 05-Jul-26 | 06-Jul-26 |  |  | Solar-MT14-B
51R1-CC-1806 | Block-35 -Module Interconnection & MC4 Termination | BLOCK-35 | Completed |  |  | Number | 47 | 30 | 17 | 100 | 13-Apr-26 | 09-May-26 | 14-Aug-26 | 19-Aug-26 |  |  | Solar-MT14-B
51R1-CC-1936 | Block-36 -Module Interconnection & MC4 Termination | BLOCK-36 | Completed |  |  | Number | 47 | 47 | 0 | 100 | 20-Apr-26 | 15-May-26 | 19-Jul-26 | 20-Aug-26 |  |  | Solar-MT14-B
51R1-CC-2066 | Block-37 -Module Interconnection & MC4 Termination | BLOCK-37 | Completed |  |  | Number | 47 | 47 | 0 | 100 | 19-Apr-26 | 14-May-26 | 18-Sep-26 | 22-Sep-26 |  |  | Solar-MT14-B
51R1-CC-2196 | Block-38 -Module Interconnection & MC4 Termination | BLOCK-38 | Completed |  |  | Number | 47 | 47 | 0 | 100 | 21-Apr-26 | 17-May-26 | 21-Aug-26 | 24-Aug-26 |  |  | Solar-MT14-B
51R1-CC-2326 | Block-39 -Module Interconnection & MC4 Termination | BLOCK-39 | Completed |  |  | Number | 47 | 47 | 0 | 100 | 11-Apr-26 | 06-May-26 | 12-Aug-26 | 17-Aug-26 |  |  | Solar-MT14-B
51R1-CC-2456 | Block-40 -Module Interconnection & MC4 Termination | BLOCK-40 | Completed |  |  | Number | 47 | 47 | 0 | 100 | 21-Apr-26 | 17-May-26 | 27-May-26 | 03-Jun-26 |  |  | Solar-MT14-B
51R1-CC-2586 | Block-41 -Module Interconnection & MC4 Termination | BLOCK-41 | Completed |  |  | Number | 47 | 47 | 0 | 100 | 14-May-26 | 02-Jun-26 | 01-Jun-26 | 15-Sep-26 |  |  | Solar-MT14-B
51R1-CC-2716 | Block-42 -Module Interconnection & MC4 Termination | BLOCK-42 | Completed |  |  | Number | 47 | 47 | 0 | 100 | 02-May-26 | 22-May-26 | 31-Aug-26 | 01-Sep-26 |  |  | Solar-MT14-B
51R1-CC-2846 | Block-43 -Module Interconnection & MC4 Termination | BLOCK-43 | Not Started |  |  | Number | 47 | 0 | 47 | 0 | 24-May-26 | 12-Jun-26 |  |  | 13-Oct-26 | 30-Oct-26 | Solar-MT14-B
51R1-CC-2976 | Block-44 -Module Interconnection & MC4 Termination | BLOCK-44 | Completed |  |  | Number | 47 | 47 | 0 | 100 | 27-Apr-26 | 16-May-26 | 17-Sep-26 | 25-Sep-26 |  |  | Solar-MT14-B
51R1-CC-3106 | Block-45 -Module Interconnection & MC4 Termination | BLOCK-45 | Not Started |  |  | Number | 47 | 0 | 47 | 0 | 02-May-26 | 22-May-26 |  |  | 27-Sep-26 | 14-Oct-26 | Solar-MT14-B
51R1-CC-3236 | Block-46 -Module Interconnection & MC4 Termination | BLOCK-46 | Completed |  |  | Number | 47 | 47 | 0 | 100 | 02-May-26 | 22-May-26 | 18-Sep-26 | 25-Sep-26 |  |  | Solar-MT14-B
51R1-CC-3366 | Block-47 -Module Interconnection & MC4 Termination | BLOCK-47 | Completed |  |  | Number | 47 | 47 | 0 | 100 | 02-May-26 | 22-May-26 | 13-Sep-26 | 25-Sep-26 |  |  | Solar-MT14-B
51R1-CC-3496 | Block-48 -Module Interconnection & MC4 Termination | BLOCK-48 | Completed |  |  | Number | 47 | 47 | 0 | 100 | 02-May-26 | 22-May-26 | 05-Sep-26 | 06-Sep-26 |  |  | Solar-MT14-B
51R1-CC-3626 | Block-49 -Module Interconnection & MC4 Termination | BLOCK-49 | Not Started |  |  | Number | 47 | 0 | 47 | 0 | 02-May-26 | 22-May-26 |  |  | 27-Sep-26 | 14-Oct-26 | Solar-MT14-B
51R1-CC-3756 | Block-50 -Module Interconnection & MC4 Termination | BLOCK-50 | Not Started |  |  | Number | 47 | 0 | 47 | 0 | 02-May-26 | 22-May-26 |  |  | 03-Nov-26 | 20-Nov-26 | Solar-MT14-B
51R1-CC-3886 | Block-51 -Module Interconnection & MC4 Termination | BLOCK-51 | Not Started |  |  | Number | 47 | 0 | 47 | 0 | 02-May-26 | 22-May-26 |  |  | 03-Nov-26 | 20-Nov-26 | Solar-MT14-B
51R1-CC-4016 | Block-52 -Module Interconnection & MC4 Termination | BLOCK-52 | Not Started |  |  | Number | 47 | 0 | 47 | 0 | 02-May-26 | 22-May-26 |  |  | 05-Nov-26 | 22-Nov-26 | Solar-MT14-B
51R1-CC-4146 | Block-53 -Module Interconnection & MC4 Termination | BLOCK-53 | Not Started |  |  | Number | 47 | 0 | 47 | 0 | 02-May-26 | 22-May-26 |  |  | 13-Nov-26 | 30-Nov-26 | Solar-MT14-B
51R1-CC-4276 | Block-54 -Module Interconnection & MC4 Termination | BLOCK-54 | Not Started |  |  | Number | 47 | 0 | 47 | 0 | 22-Apr-26 | 11-May-26 |  |  | 08-Oct-26 | 25-Oct-26 | Solar-MT14-B
51R1-CC-4406 | Block-55 -Module Interconnection & MC4 Termination | BLOCK-55 | Not Started |  |  | Number | 47 | 0 | 47 | 0 | 02-May-26 | 22-May-26 |  |  | 13-Nov-26 | 30-Nov-26 | Solar-MT14-B
51R1-CC-4536 | Block-56 -Module Interconnection & MC4 Termination | BLOCK-56 | Not Started |  |  | Number | 47 | 0 | 47 | 0 | 02-May-26 | 22-May-26 |  |  | 13-Nov-26 | 30-Nov-26 | Solar-MT14-B
| VOC Testing (Σ of 28) |  |  |  |  | Days | 1315 | 351 | 964 |  | 20-Apr-26 | 15-Jun-26 | 02-Jun-26 | 25-Sep-26 | 27-Sep-26 | 02-Dec-26
51R1-CC-1028 | Block-06 -VOC Testing | BLOCK-06 | Completed |  |  | Days | 47 | 100 | -53 | 100 | 25-Apr-26 | 14-May-26 | 12-Jul-26 | 17-Jul-26
51R1-CC-1158 | Block-07 -VOC Testing | BLOCK-07 | Completed |  |  | Days | 47 | 50 | -3 | 100 | 30-Apr-26 | 19-May-26 | 08-Jul-26 | 12-Jul-26
51R1-CC-1288 | Block-11 -VOC Testing | BLOCK-11 | Completed |  |  | Days | 47 | 20 | 27 | 100 | 30-Apr-26 | 19-May-26 | 16-Aug-26 | 19-Aug-26
51R1-CC-1418 | Block-12 -VOC Testing | BLOCK-12 | Completed |  |  | Days | 47 | 10 | 37 | 100 | 30-Apr-26 | 19-May-26 | 05-Aug-26 | 12-Aug-26
51R1-CC-1548 | Block-13 -VOC Testing | BLOCK-13 | Completed |  |  | Days | 47 | 9 | 38 | 100 | 30-Apr-26 | 19-May-26 | 04-Jun-26 | 11-Jun-26
51R1-CC-1678 | Block-14 -VOC Testing | BLOCK-14 | Completed |  |  | Days | 47 | 10 | 37 | 100 | 30-Apr-26 | 19-May-26 | 02-Jun-26 | 11-Jun-26
51R1-CC-1808 | Block-35 -VOC Testing | BLOCK-35 | Completed |  |  | Days | 47 | 10 | 37 | 100 | 22-Apr-26 | 12-May-26 | 14-Aug-26 | 19-Aug-26
51R1-CC-1938 | Block-36 -VOC Testing | BLOCK-36 | Completed |  |  | Days | 47 | 20 | 27 | 100 | 29-Apr-26 | 18-May-26 | 21-Aug-26 | 26-Aug-26
51R1-CC-2068 | Block-37 -VOC Testing | BLOCK-37 | Completed |  |  | Days | 47 | 10 | 37 | 100 | 28-Apr-26 | 17-May-26 | 19-Sep-26 | 25-Sep-26
51R1-CC-2198 | Block-38 -VOC Testing | BLOCK-38 | Completed |  |  | Days | 47 | 10 | 37 | 100 | 30-Apr-26 | 19-May-26 | 21-Aug-26 | 02-Sep-26
51R1-CC-2328 | Block-39 -VOC Testing | BLOCK-39 | Completed |  |  | Days | 47 | 19 | 28 | 100 | 20-Apr-26 | 09-May-26 | 12-Aug-26 | 17-Aug-26
51R1-CC-2458 | Block-40 -VOC Testing | BLOCK-40 | Completed |  |  | Days | 47 | 5 | 42 | 100 | 30-Apr-26 | 19-May-26 | 02-Sep-26 | 06-Sep-26
51R1-CC-2588 | Block-41 -VOC Testing | BLOCK-41 | Completed |  |  | Days | 47 | 5 | 42 | 100 | 17-May-26 | 05-Jun-26 | 17-Sep-26 | 25-Sep-26
51R1-CC-2718 | Block-42 -VOC Testing | BLOCK-42 | Completed |  |  | Days | 47 | 23 | 24 | 100 | 05-May-26 | 24-May-26 | 21-Aug-26 | 04-Sep-26
51R1-CC-2848 | Block-43 -VOC Testing | BLOCK-43 | Not Started |  |  | Days | 47 | 0 | 47 | 0 | 27-May-26 | 15-Jun-26 |  |  | 26-Oct-26 | 12-Nov-26
51R1-CC-2978 | Block-44 -VOC Testing | BLOCK-44 | Not Started |  |  | Days | 47 | 0 | 47 | 0 | 29-Apr-26 | 18-May-26 |  |  | 27-Sep-26 | 14-Oct-26
51R1-CC-3108 | Block-45 -VOC Testing | BLOCK-45 | Not Started |  |  | Days | 47 | 0 | 47 | 0 | 05-May-26 | 24-May-26 |  |  | 01-Oct-26 | 19-Oct-26
51R1-CC-3238 | Block-46 -VOC Testing | BLOCK-46 | Completed |  |  | Days | 47 | 12 | 35 | 100 | 05-May-26 | 24-May-26 | 18-Sep-26 | 25-Sep-26
51R1-CC-3368 | Block-47 -VOC Testing | BLOCK-47 | Completed |  |  | Days | 47 | 15 | 32 | 100 | 05-May-26 | 24-May-26 | 17-Sep-26 | 25-Sep-26
51R1-CC-3498 | Block-48 -VOC Testing | BLOCK-48 | Completed |  |  | Days | 47 | 23 | 24 | 100 | 05-May-26 | 24-May-26 | 09-Sep-26 | 10-Sep-26
51R1-CC-3628 | Block-49 -VOC Testing | BLOCK-49 | Not Started |  |  | Days | 47 | 0 | 47 | 0 | 05-May-26 | 24-May-26 |  |  | 03-Oct-26 | 20-Oct-26
51R1-CC-3758 | Block-50 -VOC Testing | BLOCK-50 | Not Started |  |  | Days | 47 | 0 | 47 | 0 | 05-May-26 | 24-May-26 |  |  | 05-Nov-26 | 22-Nov-26
51R1-CC-3888 | Block-51 -VOC Testing | BLOCK-51 | Not Started |  |  | Days | 47 | 0 | 47 | 0 | 05-May-26 | 24-May-26 |  |  | 05-Nov-26 | 22-Nov-26
51R1-CC-4018 | Block-52 -VOC Testing | BLOCK-52 | Not Started |  |  | Days | 47 | 0 | 47 | 0 | 05-May-26 | 24-May-26 |  |  | 08-Nov-26 | 24-Nov-26
51R1-CC-4148 | Block-53 -VOC Testing | BLOCK-53 | Not Started |  |  | Days | 47 | 0 | 47 | 0 | 05-May-26 | 24-May-26 |  |  | 16-Nov-26 | 02-Dec-26
51R1-CC-4278 | Block-54 -VOC Testing | BLOCK-54 | Not Started |  |  | Days | 47 | 0 | 47 | 0 | 24-Apr-26 | 13-May-26 |  |  | 10-Oct-26 | 27-Oct-26
51R1-CC-4408 | Block-55 -VOC Testing | BLOCK-55 | Not Started |  |  | Days | 47 | 0 | 47 | 0 | 05-May-26 | 24-May-26 |  |  | 16-Nov-26 | 02-Dec-26
51R1-CC-4538 | Block-56 -VOC Testing | BLOCK-56 | Not Started |  |  | Days | 46 | 0 | 46 | 0 | 05-May-26 | 24-May-26 |  |  | 16-Nov-26 | 02-Dec-26
| Robotic Structure - Docking Station Installation (Σ of 28) |  |  |  |  | Number | 1302 | 718 | 584 |  | 27-Mar-26 | 16-May-26 | 24-Jun-26 | 25-Sep-26 | 27-Sep-26 | 22-Oct-26
51R1-CC-1030 | Block-06 -Robotic Structure - Docking Station Installation | BLOCK-06 | Completed |  |  | Number | 46 | 57 | -11 | 100 | 06-Apr-26 | 18-Apr-26 | 12-Jul-26 | 14-Jul-26 |  |  | Solar-MT15-B
51R1-CC-1160 | Block-07 -Robotic Structure - Docking Station Installation | BLOCK-07 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 12-Apr-26 | 25-Apr-26 | 12-Jul-26 | 15-Jul-26 |  |  | Solar-MT15-B
51R1-CC-1290 | Block-11 -Robotic Structure - Docking Station Installation | BLOCK-11 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 12-Apr-26 | 25-Apr-26 | 09-Aug-26 | 11-Aug-26 |  |  | Solar-MT15-B
51R1-CC-1420 | Block-12 -Robotic Structure - Docking Station Installation | BLOCK-12 | Completed |  |  | Number | 46 | 47 | -1 | 100 | 12-Apr-26 | 25-Apr-26 | 09-Aug-26 | 11-Aug-26 |  |  | Solar-MT15-B
51R1-CC-1550 | Block-13 -Robotic Structure - Docking Station Installation | BLOCK-13 | Completed |  |  | Number | 46 | 48 | -2 | 100 | 12-Apr-26 | 25-Apr-26 | 28-Jun-26 | 29-Jun-26 |  |  | Solar-MT15-B
51R1-CC-1680 | Block-14 -Robotic Structure - Docking Station Installation | BLOCK-14 | Completed |  |  | Number | 60 | 60 | 0 | 100 | 12-Apr-26 | 25-Apr-26 | 24-Jun-26 | 28-Jun-26 |  |  | Solar-MT15-B
51R1-CC-1810 | Block-35 -Robotic Structure - Docking Station Installation | BLOCK-35 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 27-Mar-26 | 07-Apr-26 | 16-Aug-26 | 19-Aug-26 |  |  | Solar-MT15-B
51R1-CC-1940 | Block-36 -Robotic Structure - Docking Station Installation | BLOCK-36 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 31-Mar-26 | 12-Apr-26 | 02-Sep-26 | 04-Sep-26 |  |  | Solar-MT15-B
51R1-CC-2070 | Block-37 -Robotic Structure - Docking Station Installation | BLOCK-37 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 12-Apr-26 | 25-Apr-26 | 16-Sep-26 | 17-Sep-26 |  |  | Solar-MT15-B
51R1-CC-2200 | Block-38 -Robotic Structure - Docking Station Installation | BLOCK-38 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 12-Apr-26 | 25-Apr-26 | 05-Sep-26 | 07-Sep-26 |  |  | Solar-MT15-B
51R1-CC-2330 | Block-39 -Robotic Structure - Docking Station Installation | BLOCK-39 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 31-Mar-26 | 12-Apr-26 | 16-Aug-26 | 17-Aug-26 |  |  | Solar-MT15-B
51R1-CC-2460 | Block-40 -Robotic Structure - Docking Station Installation | BLOCK-40 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 12-Apr-26 | 25-Apr-26 | 08-Sep-26 | 09-Sep-26 |  |  | Solar-MT15-B
51R1-CC-2590 | Block-41 -Robotic Structure - Docking Station Installation | BLOCK-41 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 12-Apr-26 | 25-Apr-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT15-B
51R1-CC-2720 | Block-42 -Robotic Structure - Docking Station Installation | BLOCK-42 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 12-Apr-26 | 25-Apr-26 | 07-Sep-26 | 08-Sep-26 |  |  | Solar-MT15-B
51R1-CC-2850 | Block-43 -Robotic Structure - Docking Station Installation | BLOCK-43 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 04-May-26 | 16-May-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT15-B
51R1-CC-2980 | Block-44 -Robotic Structure - Docking Station Installation | BLOCK-44 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 31-Mar-26 | 12-Apr-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT15-B
51R1-CC-3110 | Block-45 -Robotic Structure - Docking Station Installation | BLOCK-45 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 12-Apr-26 | 25-Apr-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT15-B
51R1-CC-3240 | Block-46 -Robotic Structure - Docking Station Installation | BLOCK-46 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 12-Apr-26 | 25-Apr-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT15-B
51R1-CC-3370 | Block-47 -Robotic Structure - Docking Station Installation | BLOCK-47 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 12-Apr-26 | 25-Apr-26 | 18-Sep-26 | 25-Sep-26 |  |  | Solar-MT15-B
51R1-CC-3500 | Block-48 -Robotic Structure - Docking Station Installation | BLOCK-48 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 12-Apr-26 | 25-Apr-26 | 19-Sep-26 | 24-Sep-26 |  |  | Solar-MT15-B
51R1-CC-3630 | Block-49 -Robotic Structure - Docking Station Installation | BLOCK-49 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 12-Apr-26 | 25-Apr-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT15-B
51R1-CC-3760 | Block-50 -Robotic Structure - Docking Station Installation | BLOCK-50 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 12-Apr-26 | 25-Apr-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT15-B
51R1-CC-3890 | Block-51 -Robotic Structure - Docking Station Installation | BLOCK-51 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 12-Apr-26 | 25-Apr-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT15-B
51R1-CC-4020 | Block-52 -Robotic Structure - Docking Station Installation | BLOCK-52 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 12-Apr-26 | 25-Apr-26 |  |  | 11-Oct-26 | 22-Oct-26 | Solar-MT15-B
51R1-CC-4150 | Block-53 -Robotic Structure - Docking Station Installation | BLOCK-53 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 12-Apr-26 | 25-Apr-26 |  |  | 03-Oct-26 | 14-Oct-26 | Solar-MT15-B
51R1-CC-4280 | Block-54 -Robotic Structure - Docking Station Installation | BLOCK-54 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 31-Mar-26 | 12-Apr-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT15-B
51R1-CC-4410 | Block-55 -Robotic Structure - Docking Station Installation | BLOCK-55 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 12-Apr-26 | 25-Apr-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT15-B
51R1-CC-4540 | Block-56 -Robotic Structure - Docking Station Installation | BLOCK-56 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 12-Apr-26 | 25-Apr-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT15-B
| Robotic Structure - Reverse Station Installation (Σ of 28) |  |  |  |  | Number | 1288 | 552 | 736 |  | 27-Mar-26 | 16-May-26 | 25-Jun-26 | 09-Sep-26 | 27-Sep-26 | 22-Oct-26
51R1-CC-1032 | Block-06 -Robotic Structure - Reverse Station Installation | BLOCK-06 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 06-Apr-26 | 18-Apr-26 | 12-Jul-26 | 13-Jul-26 |  |  | Solar-MT16-B
51R1-CC-1162 | Block-07 -Robotic Structure - Reverse Station Installation | BLOCK-07 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 12-Apr-26 | 25-Apr-26 | 12-Jul-26 | 15-Jul-26 |  |  | Solar-MT16-B
51R1-CC-1292 | Block-11 -Robotic Structure - Reverse Station Installation | BLOCK-11 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 12-Apr-26 | 25-Apr-26 | 11-Aug-26 | 13-Aug-26 |  |  | Solar-MT16-B
51R1-CC-1422 | Block-12 -Robotic Structure - Reverse Station Installation | BLOCK-12 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 12-Apr-26 | 25-Apr-26 | 10-Aug-26 | 14-Aug-26 |  |  | Solar-MT16-B
51R1-CC-1552 | Block-13 -Robotic Structure - Reverse Station Installation | BLOCK-13 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 12-Apr-26 | 25-Apr-26 | 28-Jun-26 | 02-Jul-26 |  |  | Solar-MT16-B
51R1-CC-1682 | Block-14 -Robotic Structure - Reverse Station Installation | BLOCK-14 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 12-Apr-26 | 25-Apr-26 | 25-Jun-26 | 28-Jun-26 |  |  | Solar-MT16-B
51R1-CC-1812 | Block-35 -Robotic Structure - Reverse Station Installation | BLOCK-35 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 27-Mar-26 | 07-Apr-26 | 16-Aug-26 | 18-Aug-26 |  |  | Solar-MT16-B
51R1-CC-1942 | Block-36 -Robotic Structure - Reverse Station Installation | BLOCK-36 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 31-Mar-26 | 12-Apr-26 | 02-Sep-26 | 04-Sep-26 |  |  | Solar-MT16-B
51R1-CC-2072 | Block-37 -Robotic Structure - Reverse Station Installation | BLOCK-37 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 12-Apr-26 | 25-Apr-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT16-B
51R1-CC-2202 | Block-38 -Robotic Structure - Reverse Station Installation | BLOCK-38 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 12-Apr-26 | 25-Apr-26 | 05-Sep-26 | 07-Sep-26 |  |  | Solar-MT16-B
51R1-CC-2332 | Block-39 -Robotic Structure - Reverse Station Installation | BLOCK-39 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 31-Mar-26 | 12-Apr-26 | 16-Aug-26 | 18-Aug-26 |  |  | Solar-MT16-B
51R1-CC-2462 | Block-40 -Robotic Structure - Reverse Station Installation | BLOCK-40 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 12-Apr-26 | 25-Apr-26 | 08-Sep-26 | 09-Sep-26 |  |  | Solar-MT16-B
51R1-CC-2592 | Block-41 -Robotic Structure - Reverse Station Installation | BLOCK-41 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 12-Apr-26 | 25-Apr-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT16-B
51R1-CC-2722 | Block-42 -Robotic Structure - Reverse Station Installation | BLOCK-42 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 12-Apr-26 | 25-Apr-26 | 07-Sep-26 | 08-Sep-26 |  |  | Solar-MT16-B
51R1-CC-2852 | Block-43 -Robotic Structure - Reverse Station Installation | BLOCK-43 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 04-May-26 | 16-May-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT16-B
51R1-CC-2982 | Block-44 -Robotic Structure - Reverse Station Installation | BLOCK-44 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 31-Mar-26 | 12-Apr-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT16-B
51R1-CC-3112 | Block-45 -Robotic Structure - Reverse Station Installation | BLOCK-45 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 12-Apr-26 | 25-Apr-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT16-B
51R1-CC-3242 | Block-46 -Robotic Structure - Reverse Station Installation | BLOCK-46 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 12-Apr-26 | 25-Apr-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT16-B
51R1-CC-3372 | Block-47 -Robotic Structure - Reverse Station Installation | BLOCK-47 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 12-Apr-26 | 25-Apr-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT16-B
51R1-CC-3502 | Block-48 -Robotic Structure - Reverse Station Installation | BLOCK-48 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 12-Apr-26 | 25-Apr-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT16-B
51R1-CC-3632 | Block-49 -Robotic Structure - Reverse Station Installation | BLOCK-49 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 12-Apr-26 | 25-Apr-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT16-B
51R1-CC-3762 | Block-50 -Robotic Structure - Reverse Station Installation | BLOCK-50 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 12-Apr-26 | 25-Apr-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT16-B
51R1-CC-3892 | Block-51 -Robotic Structure - Reverse Station Installation | BLOCK-51 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 12-Apr-26 | 25-Apr-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT16-B
51R1-CC-4022 | Block-52 -Robotic Structure - Reverse Station Installation | BLOCK-52 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 12-Apr-26 | 25-Apr-26 |  |  | 11-Oct-26 | 22-Oct-26 | Solar-MT16-B
51R1-CC-4152 | Block-53 -Robotic Structure - Reverse Station Installation | BLOCK-53 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 12-Apr-26 | 25-Apr-26 |  |  | 03-Oct-26 | 14-Oct-26 | Solar-MT16-B
51R1-CC-4282 | Block-54 -Robotic Structure - Reverse Station Installation | BLOCK-54 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 31-Mar-26 | 12-Apr-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT16-B
51R1-CC-4412 | Block-55 -Robotic Structure - Reverse Station Installation | BLOCK-55 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 12-Apr-26 | 25-Apr-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT16-B
51R1-CC-4542 | Block-56 -Robotic Structure - Reverse Station Installation | BLOCK-56 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 12-Apr-26 | 25-Apr-26 |  |  | 27-Sep-26 | 09-Oct-26 | Solar-MT16-B
| Robotic Structure - Bridges Installation (Σ of 28) |  |  |  |  | Number | 1288 | 552 | 736 |  | 10-Apr-26 | 14-Jun-26 | 25-Jun-26 | 09-Sep-26 | 27-Sep-26 | 01-Dec-26
51R1-CC-1034 | Block-06 -Robotic Structure - Bridges Installation | BLOCK-06 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 15-Apr-26 | 10-May-26 | 12-Jul-26 | 13-Jul-26 |  |  | Solar-MT17-B
51R1-CC-1164 | Block-07 -Robotic Structure - Bridges Installation | BLOCK-07 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 20-Apr-26 | 15-May-26 | 12-Jul-26 | 14-Jul-26 |  |  | Solar-MT17-B
51R1-CC-1294 | Block-11 -Robotic Structure - Bridges Installation | BLOCK-11 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 20-Apr-26 | 15-May-26 | 16-Aug-26 | 19-Aug-26 |  |  | Solar-MT17-B
51R1-CC-1424 | Block-12 -Robotic Structure - Bridges Installation | BLOCK-12 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 20-Apr-26 | 15-May-26 | 16-Aug-26 | 18-Aug-26 |  |  | Solar-MT17-B
51R1-CC-1554 | Block-13 -Robotic Structure - Bridges Installation | BLOCK-13 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 20-Apr-26 | 15-May-26 | 28-Jun-26 | 02-Jul-26 |  |  | Solar-MT17-B
51R1-CC-1684 | Block-14 -Robotic Structure - Bridges Installation | BLOCK-14 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 20-Apr-26 | 15-May-26 | 25-Jun-26 | 28-Jun-26 |  |  | Solar-MT17-B
51R1-CC-1814 | Block-35 -Robotic Structure - Bridges Installation | BLOCK-35 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 15-Apr-26 | 10-May-26 | 16-Aug-26 | 19-Aug-26 |  |  | Solar-MT17-B
51R1-CC-1944 | Block-36 -Robotic Structure - Bridges Installation | BLOCK-36 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 19-Apr-26 | 14-May-26 | 30-Aug-26 | 03-Sep-26 |  |  | Solar-MT17-B
51R1-CC-2074 | Block-37 -Robotic Structure - Bridges Installation | BLOCK-37 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 20-Apr-26 | 15-May-26 |  |  | 27-Sep-26 | 20-Oct-26 | Solar-MT17-B
51R1-CC-2204 | Block-38 -Robotic Structure - Bridges Installation | BLOCK-38 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 20-Apr-26 | 15-May-26 | 05-Sep-26 | 07-Sep-26 |  |  | Solar-MT17-B
51R1-CC-2334 | Block-39 -Robotic Structure - Bridges Installation | BLOCK-39 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 10-Apr-26 | 05-May-26 | 16-Aug-26 | 18-Aug-26 |  |  | Solar-MT17-B
51R1-CC-2464 | Block-40 -Robotic Structure - Bridges Installation | BLOCK-40 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 20-Apr-26 | 15-May-26 | 07-Sep-26 | 09-Sep-26 |  |  | Solar-MT17-B
51R1-CC-2594 | Block-41 -Robotic Structure - Bridges Installation | BLOCK-41 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 08-May-26 | 02-Jun-26 |  |  | 27-Sep-26 | 20-Oct-26 | Solar-MT17-B
51R1-CC-2724 | Block-42 -Robotic Structure - Bridges Installation | BLOCK-42 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 27-Apr-26 | 23-May-26 | 07-Sep-26 | 08-Sep-26 |  |  | Solar-MT17-B
51R1-CC-2854 | Block-43 -Robotic Structure - Bridges Installation | BLOCK-43 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 19-May-26 | 14-Jun-26 |  |  | 08-Oct-26 | 30-Oct-26 | Solar-MT17-B
51R1-CC-2984 | Block-44 -Robotic Structure - Bridges Installation | BLOCK-44 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 22-Apr-26 | 17-May-26 |  |  | 27-Sep-26 | 20-Oct-26 | Solar-MT17-B
51R1-CC-3114 | Block-45 -Robotic Structure - Bridges Installation | BLOCK-45 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 27-Apr-26 | 23-May-26 |  |  | 27-Sep-26 | 20-Oct-26 | Solar-MT17-B
51R1-CC-3244 | Block-46 -Robotic Structure - Bridges Installation | BLOCK-46 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 27-Apr-26 | 23-May-26 |  |  | 27-Sep-26 | 20-Oct-26 | Solar-MT17-B
51R1-CC-3374 | Block-47 -Robotic Structure - Bridges Installation | BLOCK-47 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 27-Apr-26 | 23-May-26 |  |  | 27-Sep-26 | 20-Oct-26 | Solar-MT17-B
51R1-CC-3504 | Block-48 -Robotic Structure - Bridges Installation | BLOCK-48 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 27-Apr-26 | 23-May-26 |  |  | 27-Sep-26 | 20-Oct-26 | Solar-MT17-B
51R1-CC-3634 | Block-49 -Robotic Structure - Bridges Installation | BLOCK-49 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 27-Apr-26 | 23-May-26 |  |  | 27-Sep-26 | 20-Oct-26 | Solar-MT17-B
51R1-CC-3764 | Block-50 -Robotic Structure - Bridges Installation | BLOCK-50 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 27-Apr-26 | 23-May-26 |  |  | 29-Oct-26 | 21-Nov-26 | Solar-MT17-B
51R1-CC-3894 | Block-51 -Robotic Structure - Bridges Installation | BLOCK-51 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 27-Apr-26 | 23-May-26 |  |  | 29-Oct-26 | 21-Nov-26 | Solar-MT17-B
51R1-CC-4024 | Block-52 -Robotic Structure - Bridges Installation | BLOCK-52 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 27-Apr-26 | 23-May-26 |  |  | 01-Nov-26 | 23-Nov-26 | Solar-MT17-B
51R1-CC-4154 | Block-53 -Robotic Structure - Bridges Installation | BLOCK-53 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 27-Apr-26 | 23-May-26 |  |  | 09-Nov-26 | 01-Dec-26 | Solar-MT17-B
51R1-CC-4284 | Block-54 -Robotic Structure - Bridges Installation | BLOCK-54 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 16-Apr-26 | 12-May-26 |  |  | 01-Oct-26 | 25-Oct-26 | Solar-MT17-B
51R1-CC-4414 | Block-55 -Robotic Structure - Bridges Installation | BLOCK-55 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 27-Apr-26 | 23-May-26 |  |  | 09-Nov-26 | 01-Dec-26 | Solar-MT17-B
51R1-CC-4544 | Block-56 -Robotic Structure - Bridges Installation | BLOCK-56 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 27-Apr-26 | 23-May-26 |  |  | 09-Nov-26 | 01-Dec-26 | Solar-MT17-B
| Robot Installation (Σ of 28) |  |  |  |  | Number | 1288 | 553 | 735 |  | 20-Apr-26 | 14-Jun-26 | 28-Jun-26 | 09-Sep-26 | 27-Sep-26 | 01-Dec-26
51R1-CC-1036 | Block-06 -Robot Installation | BLOCK-06 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 25-Apr-26 | 10-May-26 | 13-Jul-26 | 15-Jul-26 |  |  | Solar-MT18-B
51R1-CC-1166 | Block-07 -Robot Installation | BLOCK-07 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 30-Apr-26 | 15-May-26 | 14-Jul-26 | 16-Jul-26 |  |  | Solar-MT18-B
51R1-CC-1296 | Block-11 -Robot Installation | BLOCK-11 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 30-Apr-26 | 15-May-26 | 10-Aug-26 | 12-Aug-26 |  |  | Solar-MT18-B
51R1-CC-1426 | Block-12 -Robot Installation | BLOCK-12 | Completed |  |  | Number | 46 | 47 | -1 | 100 | 30-Apr-26 | 15-May-26 | 10-Aug-26 | 12-Aug-26 |  |  | Solar-MT18-B
51R1-CC-1556 | Block-13 -Robot Installation | BLOCK-13 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 30-Apr-26 | 15-May-26 | 28-Jun-26 | 29-Jun-26 |  |  | Solar-MT18-B
51R1-CC-1686 | Block-14 -Robot Installation | BLOCK-14 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 30-Apr-26 | 15-May-26 | 29-Jun-26 | 05-Jul-26 |  |  | Solar-MT18-B
51R1-CC-1816 | Block-35 -Robot Installation | BLOCK-35 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 25-Apr-26 | 10-May-26 | 20-Aug-26 | 20-Aug-26 |  |  | Solar-MT18-B
51R1-CC-1946 | Block-36 -Robot Installation | BLOCK-36 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 29-Apr-26 | 14-May-26 | 03-Sep-26 | 04-Sep-26 |  |  | Solar-MT18-B
51R1-CC-2076 | Block-37 -Robot Installation | BLOCK-37 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 30-Apr-26 | 15-May-26 |  |  | 27-Sep-26 | 11-Oct-26 | Solar-MT18-B
51R1-CC-2206 | Block-38 -Robot Installation | BLOCK-38 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 30-Apr-26 | 15-May-26 | 05-Sep-26 | 07-Sep-26 |  |  | Solar-MT18-B
51R1-CC-2336 | Block-39 -Robot Installation | BLOCK-39 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 20-Apr-26 | 05-May-26 | 19-Aug-26 | 19-Aug-26 |  |  | Solar-MT18-B
51R1-CC-2466 | Block-40 -Robot Installation | BLOCK-40 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 30-Apr-26 | 15-May-26 | 08-Sep-26 | 09-Sep-26 |  |  | Solar-MT18-B
51R1-CC-2596 | Block-41 -Robot Installation | BLOCK-41 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 19-May-26 | 04-Jun-26 |  |  | 01-Oct-26 | 15-Oct-26 | Solar-MT18-B
51R1-CC-2726 | Block-42 -Robot Installation | BLOCK-42 | Completed |  |  | Number | 46 | 46 | 0 | 100 | 08-May-26 | 23-May-26 | 07-Sep-26 | 08-Sep-26 |  |  | Solar-MT18-B
51R1-CC-2856 | Block-43 -Robot Installation | BLOCK-43 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 29-May-26 | 14-Jun-26 |  |  | 18-Oct-26 | 31-Oct-26 | Solar-MT18-B
51R1-CC-2986 | Block-44 -Robot Installation | BLOCK-44 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 02-May-26 | 17-May-26 |  |  | 01-Oct-26 | 15-Oct-26 | Solar-MT18-B
51R1-CC-3116 | Block-45 -Robot Installation | BLOCK-45 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 08-May-26 | 23-May-26 |  |  | 01-Oct-26 | 15-Oct-26 | Solar-MT18-B
51R1-CC-3246 | Block-46 -Robot Installation | BLOCK-46 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 08-May-26 | 23-May-26 |  |  | 01-Oct-26 | 15-Oct-26 | Solar-MT18-B
51R1-CC-3376 | Block-47 -Robot Installation | BLOCK-47 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 08-May-26 | 23-May-26 |  |  | 27-Sep-26 | 11-Oct-26 | Solar-MT18-B
51R1-CC-3506 | Block-48 -Robot Installation | BLOCK-48 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 08-May-26 | 23-May-26 |  |  | 27-Sep-26 | 11-Oct-26 | Solar-MT18-B
51R1-CC-3636 | Block-49 -Robot Installation | BLOCK-49 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 08-May-26 | 23-May-26 |  |  | 01-Oct-26 | 15-Oct-26 | Solar-MT18-B
51R1-CC-3766 | Block-50 -Robot Installation | BLOCK-50 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 08-May-26 | 23-May-26 |  |  | 07-Nov-26 | 21-Nov-26 | Solar-MT18-B
51R1-CC-3896 | Block-51 -Robot Installation | BLOCK-51 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 08-May-26 | 23-May-26 |  |  | 07-Nov-26 | 21-Nov-26 | Solar-MT18-B
51R1-CC-4026 | Block-52 -Robot Installation | BLOCK-52 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 08-May-26 | 23-May-26 |  |  | 10-Nov-26 | 23-Nov-26 | Solar-MT18-B
51R1-CC-4156 | Block-53 -Robot Installation | BLOCK-53 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 08-May-26 | 23-May-26 |  |  | 18-Nov-26 | 01-Dec-26 | Solar-MT18-B
51R1-CC-4286 | Block-54 -Robot Installation | BLOCK-54 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 27-Apr-26 | 12-May-26 |  |  | 13-Oct-26 | 26-Oct-26 | Solar-MT18-B
51R1-CC-4416 | Block-55 -Robot Installation | BLOCK-55 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 08-May-26 | 23-May-26 |  |  | 18-Nov-26 | 01-Dec-26 | Solar-MT18-B
51R1-CC-4546 | Block-56 -Robot Installation | BLOCK-56 | Not Started |  |  | Number | 46 | 0 | 46 | 0 | 08-May-26 | 23-May-26 |  |  | 18-Nov-26 | 01-Dec-26 | Solar-MT18-B
| 📝 DPR Level Activities | [5 empty] | 0 | 0 | 0
| New DPR Activity |  | Not Started |  |  | Nos | 0 | 0 | 0
| New DPR Activity |  | Not Started |  |  | Nos | 0 | 0 | 0