## Activities
WBS Name | Activity ID | Activity Name | Status | Activity Type | Planned Start Date | Planned Finish Date | Actual Start Date | Actual Finish Date | % Complete | Total Quantity | UOM | Actual Quantity | Gap (Balance)
ARRAY EARTHING LAYOUT | 603F-EN-1910 | Array Earthing Layout For Block-02 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-1950 | Array Earthing Layout For Block-06 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-1920 | Array Earthing Layout For Block-03 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-1900 | Array Earthing Layout For Block-01 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-2140 | Array Earthing Layout For Block-25 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-1940 | Array Earthing Layout For Block-05 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-2010 | Array Earthing Layout For Block-12 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-2000 | Array Earthing Layout For Block-11 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-2050 | Array Earthing Layout For Block-16 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-1980 | Array Earthing Layout For Block-09 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-2130 | Array Earthing Layout For Block-24 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-2070 | Array Earthing Layout For Block-18 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-2150 | Array Earthing Layout For Block-26 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-2060 | Array Earthing Layout For Block-17 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-2080 | Array Earthing Layout For Block-19 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-2090 | Array Earthing Layout For Block-20 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-2030 | Array Earthing Layout For Block-14 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-2100 | Array Earthing Layout For Block-21 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-2110 | Array Earthing Layout For Block-22 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-2020 | Array Earthing Layout For Block-13 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-2040 | Array Earthing Layout For Block-15 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-1930 | Array Earthing Layout For Block-04 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-1990 | Array Earthing Layout For Block-10 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-2160 | Array Earthing Layout For Block-27 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-2120 | Array Earthing Layout For Block-23 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-1970 | Array Earthing Layout For Block-08 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
ARRAY EARTHING LAYOUT | 603F-EN-1960 | Array Earthing Layout For Block-07 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-14 17:00 | 2025-05-03 | 2025-05-03 | 1 | 0 |  | 0 | 0
BLOCK-01 | 603F-HT-1000 | Block-01 -Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-01 | 603F-HT-1010 | Block-01 -Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-01 | 603F-HT-1020 | Block-01 -Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-01 | 603F-HT-1050 | Block-01 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-01 | 603F-HT-1060 | Block-01 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-01 | 603F-HT-1040 | Block-01 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-01 | 603F-HT-1030 | Block-01 -Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-01 | 603F-HT-1070 | Block-01 -HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-02 | 603F-HT-1100 | Block-02 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-02 | 603F-HT-1110 | Block-02 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-02 | 603F-HT-1120 | Block-02 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-02 | 603F-HT-1150 | Block-02 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-02 | 603F-HT-1160 | Block-02 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-02 | 603F-HT-1140 | Block-02 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-02 | 603F-HT-1130 | Block-02 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-02 | 603F-HT-1170 | Block-02 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-03 | 603F-HT-1200 | Block-03 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-03 | 603F-HT-1210 | Block-03 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-03 | 603F-HT-1220 | Block-03 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-03 | 603F-HT-1250 | Block-03 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-03 | 603F-HT-1260 | Block-03 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-03 | 603F-HT-1240 | Block-03 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-03 | 603F-HT-1230 | Block-03 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-03 | 603F-HT-1270 | Block-03 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-04 | 603F-HT-1300 | Block-04 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-04 | 603F-HT-1310 | Block-04 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-04 | 603F-HT-1320 | Block-04 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-04 | 603F-HT-1350 | Block-04 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-04 | 603F-HT-1360 | Block-04 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-04 | 603F-HT-1340 | Block-04 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-04 | 603F-HT-1330 | Block-04 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-04 | 603F-HT-1370 | Block-04 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-05 | 603F-HT-1400 | Block-05 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-05 | 603F-HT-1410 | Block-05 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-05 | 603F-HT-1420 | Block-05 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-05 | 603F-HT-1450 | Block-05 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-05 | 603F-HT-1460 | Block-05 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-05 | 603F-HT-1440 | Block-05 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-05 | 603F-HT-1430 | Block-05 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-05 | 603F-HT-1470 | Block-05 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-06 | 603F-HT-1500 | Block-06 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-06 | 603F-HT-1510 | Block-06 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-06 | 603F-HT-1520 | Block-06 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-06 | 603F-HT-1550 | Block-06 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-06 | 603F-HT-1560 | Block-06 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-06 | 603F-HT-1540 | Block-06 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-06 | 603F-HT-1530 | Block-06 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-06 | 603F-HT-1570 | Block-06 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-07 | 603F-HT-1600 | Block-07 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-07 | 603F-HT-1610 | Block-07 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-07 | 603F-HT-1620 | Block-07 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-07 | 603F-HT-1650 | Block-07 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-07 | 603F-HT-1660 | Block-07 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-07 | 603F-HT-1640 | Block-07 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-07 | 603F-HT-1630 | Block-07 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-07 | 603F-HT-1670 | Block-07 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-08 | 603F-HT-1700 | Block-08 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-08 | 603F-HT-1710 | Block-08 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-08 | 603F-HT-1720 | Block-08 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-08 | 603F-HT-1760 | Block-08 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-08 | 603F-HT-1770 | Block-08 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-08 | 603F-HT-1750 | Block-08 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-08 | 603F-HT-1730 | Block-08 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-08 | 603F-HT-1740 | Block-08 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-09 | 603F-HT-1800 | Block-09 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-09 | 603F-HT-1810 | Block-09 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-09 | 603F-HT-1820 | Block-09 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-09 | 603F-HT-1860 | Block-09 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-09 | 603F-HT-1870 | Block-09 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-09 | 603F-HT-1850 | Block-09 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-09 | 603F-HT-1830 | Block-09 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-09 | 603F-HT-1840 | Block-09 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-10 | 603F-HT-1900 | Block-10 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-10 | 603F-HT-1910 | Block-10 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-10 | 603F-HT-1920 | Block-10 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-10 | 603F-HT-1950 | Block-10 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-10 | 603F-HT-1960 | Block-10 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-10 | 603F-HT-1940 | Block-10 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-10 | 603F-HT-1930 | Block-10 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-10 | 603F-HT-1970 | Block-10 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-11 | 603F-HT-2000 | Block-11 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-11 | 603F-HT-2010 | Block-11 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-11 | 603F-HT-2020 | Block-11 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-11 | 603F-HT-2050 | Block-11 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-11 | 603F-HT-2060 | Block-11 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-11 | 603F-HT-2040 | Block-11 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-11 | 603F-HT-2030 | Block-11 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-11 | 603F-HT-2070 | Block-11 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-12 | 603F-HT-2100 | Block-12 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-12 | 603F-HT-2110 | Block-12 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-12 | 603F-HT-2120 | Block-12 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-12 | 603F-HT-2150 | Block-12 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-12 | 603F-HT-2160 | Block-12 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-12 | 603F-HT-2140 | Block-12 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-12 | 603F-HT-2130 | Block-12 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-12 | 603F-HT-2170 | Block-12 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-13 | 603F-HT-2200 | Block-13 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-13 | 603F-HT-2210 | Block-13 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-13 | 603F-HT-2220 | Block-13 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-13 | 603F-HT-2250 | Block-13 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-13 | 603F-HT-2260 | Block-13 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-13 | 603F-HT-2240 | Block-13 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-13 | 603F-HT-2230 | Block-13 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-13 | 603F-HT-2270 | Block-13 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-14 | 603F-HT-2300 | Block-14 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-14 | 603F-HT-2310 | Block-14 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-14 | 603F-HT-2320 | Block-14 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-14 | 603F-HT-2350 | Block-14 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-14 | 603F-HT-2360 | Block-14 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-14 | 603F-HT-2340 | Block-14 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-14 | 603F-HT-2330 | Block-14 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-14 | 603F-HT-2370 | Block-14 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-15 | 603F-HT-2400 | Block-15 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-15 | 603F-HT-2410 | Block-15 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-15 | 603F-HT-2420 | Block-15 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-15 | 603F-HT-2450 | Block-15 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-15 | 603F-HT-2460 | Block-15 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-15 | 603F-HT-2440 | Block-15 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-15 | 603F-HT-2430 | Block-15 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-15 | 603F-HT-2470 | Block-15 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-16 | 603F-HT-2500 | Block-16 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-16 | 603F-HT-2510 | Block-16 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-16 | 603F-HT-2520 | Block-16 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-16 | 603F-HT-2550 | Block-16 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-16 | 603F-HT-2560 | Block-16 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-16 | 603F-HT-2540 | Block-16 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-16 | 603F-HT-2530 | Block-16 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-16 | 603F-HT-2570 | Block-16 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-17 | 603F-HT-2600 | Block-17 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-17 | 603F-HT-2610 | Block-17 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-17 | 603F-HT-2620 | Block-17 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-17 | 603F-HT-2650 | Block-17 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-17 | 603F-HT-2660 | Block-17 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-17 | 603F-HT-2640 | Block-17 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-17 | 603F-HT-2630 | Block-17 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-17 | 603F-HT-2670 | Block-17 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-18 | 603F-HT-2700 | Block-18 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-18 | 603F-HT-2710 | Block-18 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-18 | 603F-HT-2720 | Block-18 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-18 | 603F-HT-2750 | Block-18 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-18 | 603F-HT-2760 | Block-18 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-18 | 603F-HT-2740 | Block-18 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-18 | 603F-HT-2730 | Block-18 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-18 | 603F-HT-2770 | Block-18 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-19 | 603F-HT-2800 | Block-19 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-19 | 603F-HT-2810 | Block-19 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-19 | 603F-HT-2820 | Block-19 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-19 | 603F-HT-2850 | Block-19 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-19 | 603F-HT-2860 | Block-19 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-19 | 603F-HT-2840 | Block-19 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-19 | 603F-HT-2830 | Block-19 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-19 | 603F-HT-2870 | Block-19 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-20 | 603F-HT-2900 | Block-20 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-20 | 603F-HT-2910 | Block-20 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-20 | 603F-HT-2920 | Block-20 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-20 | 603F-HT-2950 | Block-20 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-20 | 603F-HT-2960 | Block-20 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-20 | 603F-HT-2940 | Block-20 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-20 | 603F-HT-2930 | Block-20 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-20 | 603F-HT-2970 | Block-20 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-21 | 603F-HT-3000 | Block-21 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-21 | 603F-HT-3010 | Block-21 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-21 | 603F-HT-3020 | Block-21 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-21 | 603F-HT-3050 | Block-21 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-21 | 603F-HT-3060 | Block-21 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-21 | 603F-HT-3040 | Block-21 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-21 | 603F-HT-3030 | Block-21 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-21 | 603F-HT-3070 | Block-21 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-22 | 603F-HT-3100 | Block-22 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-22 | 603F-HT-3110 | Block-22 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-22 | 603F-HT-3120 | Block-22 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-22 | 603F-HT-3150 | Block-22 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-22 | 603F-HT-3160 | Block-22 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-22 | 603F-HT-3140 | Block-22 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-22 | 603F-HT-3130 | Block-22 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-22 | 603F-HT-3170 | Block-22 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-23 | 603F-HT-3200 | Block-23 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-23 | 603F-HT-3210 | Block-23 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-23 | 603F-HT-3220 | Block-23 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-23 | 603F-HT-3250 | Block-23 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-23 | 603F-HT-3260 | Block-23 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-23 | 603F-HT-3240 | Block-23 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-23 | 603F-HT-3230 | Block-23 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-23 | 603F-HT-3270 | Block-23 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-24 | 603F-HT-3300 | Block-24 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-24 | 603F-HT-3310 | Block-24 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-24 | 603F-HT-3320 | Block-24 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-24 | 603F-HT-3350 | Block-24 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-24 | 603F-HT-3360 | Block-24 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-24 | 603F-HT-3340 | Block-24 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-24 | 603F-HT-3330 | Block-24 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-24 | 603F-HT-3370 | Block-24 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-25 | 603F-HT-3400 | Block-25 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-25 | 603F-HT-3410 | Block-25 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-25 | 603F-HT-3420 | Block-25 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-25 | 603F-HT-3450 | Block-25 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-25 | 603F-HT-3460 | Block-25 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-25 | 603F-HT-3440 | Block-25 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-25 | 603F-HT-3430 | Block-25 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-25 | 603F-HT-3470 | Block-25 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-26 | 603F-HT-3500 | Block-26 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-26 | 603F-HT-3510 | Block-26 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-26 | 603F-HT-3520 | Block-26 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-26 | 603F-HT-3550 | Block-26 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-26 | 603F-HT-3560 | Block-26 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-26 | 603F-HT-3540 | Block-26 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-26 | 603F-HT-3530 | Block-26 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-26 | 603F-HT-3570 | Block-26 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-27 | 603F-HT-3600 | Block-27 - Final Inspection Offer To O&M Team | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-05-27 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-27 | 603F-HT-3610 | Block-27 - Punch Point Identification By O&M Team | Not Started | Task Dependent | 2026-05-27 14:00 | 2026-05-31 13:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-27 | 603F-HT-3620 | Block-27 - Punch Point Rectification By Project Team | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-23 14:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-27 | 603F-HT-3650 | Block-27 -House Keeping & Removal of Scraps | Not Started | Task Dependent | 2026-06-02 08:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-27 | 603F-HT-3660 | Block-27 -Handing Over of Mandatory Spares | Not Started | Task Dependent | 2026-06-13 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-27 | 603F-HT-3640 | Block-27 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Not Started | Task Dependent | 2026-06-18 15:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-27 | 603F-HT-3630 | Block-27 - Punch Point Closure Validation By O&M Team | Not Started | Task Dependent | 2026-06-23 14:00 | 2026-06-28 15:00 |  |  | 0 | 0 |  | 0 | 0
BLOCK-27 | 603F-HT-3670 | Block-27 - HOTO Sign Off | Not Started | Task Dependent | 2026-06-29 08:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
CIVIL | 603F-EN-1040 | Fix Tilt Typical Pile Details | Completed | Task Dependent | 2025-02-21 07:00 | 2025-02-22 17:00 | 2025-03-24 | 2025-03-25 | 1 | 0 |  | 0 | 0
CIVIL | 603F-EN-1010 | Array Layout Overall Plant Layout | Completed | Task Dependent | 2025-02-24 07:00 | 2025-02-27 17:00 | 2025-04-03 | 2025-04-03 | 1 | 0 |  | 0 | 0
CIVIL | 603F-EN-1120 | Typical Array Earthing Details | Completed | Task Dependent | 2025-02-28 07:00 | 2025-03-01 17:00 | 2025-04-08 | 2025-04-08 | 1 | 0 |  | 0 | 0
CIVIL | 603F-EN-1070 | Road Layout | Completed | Task Dependent | 2025-02-28 07:00 | 2025-03-05 17:00 | 2025-04-10 | 2025-04-10 | 1 | 0 |  | 0 | 0
CIVIL | 603F-EN-1080 | IDT Station HT Panel Platfrom Foundation Layout And Details | Completed | Task Dependent | 2025-03-06 07:00 | 2025-03-11 17:00 | 2025-03-26 | 2025-03-27 | 1 | 0 |  | 0 | 0
CIVIL | 603F-EN-1100 | IDT Station Layout Plan And Details | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-13 17:00 | 2025-03-26 | 2025-03-27 | 1 | 0 |  | 0 | 0
CIVIL | 603F-EN-1020 | Distribution Transformer Foundation (Precast Type) Layout And RC Details (Ornet) | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-13 17:00 | 2025-03-27 | 2025-03-28 | 1 | 0 |  | 0 | 0
CIVIL | 603F-EN-1150 | Earthing Layout Of IDT Station -Type-BB (33Kv Switchgear) | Completed | Task Dependent | 2025-03-12 07:00 | 2025-03-13 17:00 | 2025-04-01 | 2025-04-01 | 1 | 0 |  | 0 | 0
CIVIL | 603F-EN-1090 | IDT Station HT Panel Platfrom R.C.C Details Slab AndBeam Layout | Completed | Task Dependent | 2025-03-12 07:00 | 2025-03-17 17:00 | 2025-03-27 | 2025-03-28 | 1 | 0 |  | 0 | 0
CIVIL | 603F-EN-1030 | GA & RC Details Of Burnt Oil Pit For DT | Completed | Task Dependent | 2025-03-14 07:00 | 2025-03-15 17:00 | 2025-03-26 | 2025-03-27 | 1 | 0 |  | 0 | 0
CIVIL | 603F-EN-1130 | Typical Array LigHTning Protection Details | Completed | Task Dependent | 2025-03-14 07:00 | 2025-03-15 17:00 | 2025-04-08 | 2025-04-08 | 1 | 0 |  | 0 | 0
CIVIL | 603F-EN-1110 | IDT Station Fencing Layout And Details | Completed | Task Dependent | 2025-03-14 07:00 | 2025-03-15 17:00 | 2025-03-26 | 2025-03-27 | 1 | 0 |  | 0 | 0
CIVIL | 603F-EN-1050 | Typical Pile Details For Docking Station | Completed | Task Dependent | 2025-03-16 07:00 | 2025-03-17 17:00 | 2025-04-30 | 2025-04-30 | 1 | 0 |  | 0 | 0
CIVIL | 603F-EN-1160 | Robotic Docking Station Pile Layout | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-17 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
CIVIL | 603F-EN-1060 | Inverter Typical Pile Details | Completed | Task Dependent | 2025-07-12 07:00 | 2025-07-13 17:00 | 2025-07-02 07:00 | 2025-07-03 17:00 | 1 | 0 |  | 0 | 0
CIVIL | 603F-EN-1140 | LT Cable Trench Section Typical Details Drawing | Completed | Task Dependent | 2025-08-16 07:00 | 2025-08-18 17:00 | 2025-08-05 07:00 | 2025-08-07 17:00 | 1 | 0 |  | 0 | 0
CIVIL, MMS & MODULE INSTALLATION WORKS | 603F-PR-6000 | Civil, MMS & Module Installation Works-Boq & Tech Specs Release | Completed | Task Dependent | 2025-03-06 07:00 | 2025-03-09 17:00 | 2025-03-06 07:00 | 2025-03-09 17:00 | 1 | 0 |  | 0 | 0
CIVIL, MMS & MODULE INSTALLATION WORKS | 603F-PR-6010 | Civil, Mms & Module Installation Works-TBER | Completed | Task Dependent | 2025-03-06 07:00 | 2025-03-17 17:00 | 2025-03-06 07:00 | 2025-03-17 17:00 | 1 | 0 |  | 0 | 0
CIVIL, MMS & MODULE INSTALLATION WORKS | 603F-PR-6020 | Civil, MMS & Module Installation Works-Purchase Requistion | Completed | Task Dependent | 2025-03-18 07:00 | 2025-03-18 17:00 | 2025-03-18 07:00 | 2025-03-18 17:00 | 1 | 0 |  | 0 | 0
CIVIL, MMS & MODULE INSTALLATION WORKS | 603F-PR-6030 | Civil, MMS & Module Installation Works-Note For Approval | Completed | Task Dependent | 2025-03-18 07:00 | 2025-03-19 17:00 | 2025-03-18 07:00 | 2025-03-19 17:00 | 1 | 0 |  | 0 | 0
CIVIL, MMS & MODULE INSTALLATION WORKS | 603F-PR-6040 | Civil, Mms & Module Installation Works-LOI / PO Release | Completed | Task Dependent | 2025-03-20 07:00 | 2025-03-21 17:00 | 2025-03-20 07:00 | 2025-03-21 17:00 | 1 | 0 |  | 0 | 0
COMMON INFRA | PR-CI-A-050 | Site & Admin Office | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
COMMON INFRA | PR-CI-A-090 | Fire Station | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
COMMON INFRA | PR-CI-A-130 | Mobile/Internet Communication Infra Set Up | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
COMMON INFRA | PR-CI-A-020 | Construction Water Infrastructure | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
COMMON INFRA | PR-CI-A-060 | Store ( Covered / Open) | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
COMMON INFRA | PR-CI-A-100 | Operational Health & Safety ( OHS) Set up | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
COMMON INFRA | PR-CI-A-030 | Raw Water pump House & Water Pipeline upto Project site | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
COMMON INFRA | PR-CI-A-150 | Air strip | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
COMMON INFRA | PR-CI-A-070 | Weigh Bridge | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
COMMON INFRA | PR-CI-A-040 | Construction & Start Up Power Infra | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
COMMON INFRA | PR-CI-A-110 | Parking Area | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
COMMON INFRA | PR-CI-A-080 | Diversion of any Existing Infra- Nala/Drain/Stream/Transmission Line/Road etc | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
COMMON INFRA | PR-CI-A-120 | Bank Facilities | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
COMMON INFRA | PR-CI-A-010 | Boundary Wall or Fencing at Project initiation | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
Consent to Establish (CTE) — SPCB | PR-CA-04-010 | Consent To Establish (CTE) Pollution Board (Under Intimation Of State PCB) | Completed | Task Dependent | 2025-03-06 08:00 | 2025-03-19 12:00 | 2025-03-11 08:00 | 2025-03-11 16:00 | 1 | 0 |  | 0 | 0
Consent to Operate (CTO) — SPCB/CPCB | PR-CA-16-010 | Submission of Application | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 08:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
Consent to Operate (CTO) — SPCB/CPCB | PR-CA-16-020 | Grant of Clearance | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 08:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
Construction Commencement Certificate | PR-CA-18-010 | Submission of Application | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-14 08:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
Construction Commencement Certificate | PR-CA-18-020 | Grant of Clearance | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-14 08:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4790 | Block-12 -CEA Application | Completed | Task Dependent | 2026-01-20 07:00 | 2026-01-20 17:00 | 2026-01-01 07:00 | 2026-01-01 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4795 | Block-12 -CEA Inspection | Completed | Task Dependent | 2026-01-25 07:00 | 2026-01-25 17:00 | 2026-01-12 07:00 | 2026-01-12 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1270 | Block-01 -CEA Application | Completed | Task Dependent | 2026-02-03 07:00 | 2026-02-03 17:00 | 2026-01-01 07:00 | 2026-01-01 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6390 | Block-17 -CEA Application | Completed | Task Dependent | 2026-02-06 07:00 | 2026-02-06 17:00 | 2026-01-01 07:00 | 2026-01-01 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5130 | Block-13 -CEA Application | Completed | Task Dependent | 2026-02-07 07:00 | 2026-02-07 17:00 | 2026-01-01 07:00 | 2026-01-01 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5430 | Block-14 -CEA Application | Completed | Task Dependent | 2026-02-07 07:00 | 2026-02-07 17:00 | 2026-01-01 07:00 | 2026-01-01 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1275 | Block-01 -CEA Inspection | Completed | Task Dependent | 2026-02-10 07:00 | 2026-02-10 17:00 | 2026-01-12 07:00 | 2026-01-12 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6395 | Block-17 -CEA Inspection | Completed | Task Dependent | 2026-02-11 07:00 | 2026-02-11 17:00 | 2026-01-13 07:00 | 2026-01-13 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5750 | Block-15 -CEA Application | Completed | Task Dependent | 2026-02-11 07:00 | 2026-02-11 17:00 | 2026-01-01 07:00 | 2026-01-01 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6080 | Block-16 -CEA Compliance & Approval | Completed | Task Dependent | 2026-02-14 07:00 | 2026-02-18 17:00 | 2026-01-20 07:00 | 2026-01-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5760 | Block-15 -CEA Compliance & Approval | Completed | Task Dependent | 2026-02-14 07:00 | 2026-02-18 17:00 | 2026-01-20 07:00 | 2026-01-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5440 | Block-14 -CEA Compliance & Approval | Completed | Task Dependent | 2026-02-14 07:00 | 2026-02-18 17:00 | 2026-01-20 07:00 | 2026-01-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5140 | Block-13 -CEA Compliance & Approval | Completed | Task Dependent | 2026-02-14 07:00 | 2026-02-18 17:00 | 2026-01-20 07:00 | 2026-01-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6400 | Block-17 -CEA Compliance & Approval | Completed | Task Dependent | 2026-02-14 07:00 | 2026-02-18 17:00 | 2026-01-20 07:00 | 2026-01-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6720 | Block-18 -CEA Compliance & Approval | Completed | Task Dependent | 2026-02-14 07:00 | 2026-02-18 17:00 | 2026-01-20 07:00 | 2026-01-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4800 | Block-12 -CEA Compliance & Approval | Completed | Task Dependent | 2026-02-14 07:00 | 2026-02-18 17:00 | 2026-01-20 07:00 | 2026-01-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1600 | Block-02 -CEA Compliance & Approval | Completed | Task Dependent | 2026-02-14 07:00 | 2026-02-18 17:00 | 2026-01-20 07:00 | 2026-01-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1920 | Block-03 -CEA Compliance & Approval | Completed | Task Dependent | 2026-02-14 07:00 | 2026-02-18 17:00 | 2026-01-20 07:00 | 2026-01-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1280 | Block-01 -CEA Compliance & Approval | Completed | Task Dependent | 2026-02-14 07:00 | 2026-02-18 17:00 | 2026-01-20 07:00 | 2026-01-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5135 | Block-13 -CEA Inspection | Completed | Task Dependent | 2026-02-15 07:00 | 2026-02-15 17:00 | 2026-01-12 07:00 | 2026-01-12 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6710 | Block-18 -CEA Application | Completed | Task Dependent | 2026-02-18 07:00 | 2026-02-18 17:00 | 2026-01-01 07:00 | 2026-01-01 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4470 | Block-11 -CEA Application | Completed | Task Dependent | 2026-02-19 07:00 | 2026-02-19 17:00 | 2026-02-14 07:00 | 2026-02-14 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4805 | Block-12 -First Time Charging - Application | Completed | Task Dependent | 2026-02-21 07:00 | 2026-02-21 17:00 | 2026-02-11 07:00 | 2026-02-11 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1285 | Block-01 -First Time Charging - Application | Completed | Task Dependent | 2026-02-21 07:00 | 2026-02-21 17:00 | 2026-02-11 07:00 | 2026-02-11 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5755 | Block-15 -CEA Inspection | Completed | Task Dependent | 2026-02-21 07:00 | 2026-02-21 17:00 | 2026-01-12 07:00 | 2026-01-12 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5145 | Block-13 -First Time Charging - Application | Completed | Task Dependent | 2026-02-21 07:00 | 2026-02-21 17:00 | 2026-02-11 07:00 | 2026-02-11 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6715 | Block-18 -CEA Inspection | Completed | Task Dependent | 2026-02-21 07:00 | 2026-02-21 17:00 | 2026-01-13 07:00 | 2026-01-13 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5435 | Block-14 -CEA Inspection | Completed | Task Dependent | 2026-02-21 07:00 | 2026-02-21 17:00 | 2026-01-12 07:00 | 2026-01-12 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1290 | Block-01 -First Time Charging - Approval | Completed | Task Dependent | 2026-02-22 07:00 | 2026-02-23 17:00 | 2026-02-16 07:00 | 2026-02-16 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4495 | Block-11 -First Time Charging | Completed | Task Dependent | 2026-02-22 07:00 | 2026-02-22 17:00 | 2026-02-26 07:00 | 2026-02-26 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1910 | Block-03 -CEA Application | Completed | Task Dependent | 2026-02-22 07:00 | 2026-02-22 17:00 | 2026-01-01 07:00 | 2026-01-01 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1295 | Block-01 -First Time Charging | Completed | Task Dependent | 2026-02-22 07:00 | 2026-02-22 17:00 | 2026-02-26 07:00 | 2026-02-26 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5150 | Block-13 -First Time Charging - Approval | Completed | Task Dependent | 2026-02-22 07:00 | 2026-02-23 17:00 | 2026-02-16 07:00 | 2026-02-16 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6070 | Block-16 -CEA Application | Completed | Task Dependent | 2026-02-22 07:00 | 2026-02-22 17:00 | 2026-01-01 07:00 | 2026-01-01 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1590 | Block-02 -CEA Application | Completed | Task Dependent | 2026-02-22 07:00 | 2026-02-22 17:00 | 2026-01-01 07:00 | 2026-01-01 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4810 | Block-12 -First Time Charging - Approval | Completed | Task Dependent | 2026-02-22 07:00 | 2026-02-23 17:00 | 2026-02-16 07:00 | 2026-02-16 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1595 | Block-02 -CEA Inspection | Completed | Task Dependent | 2026-02-25 07:00 | 2026-02-25 17:00 | 2026-01-12 07:00 | 2026-01-12 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4485 | Block-11 -First Time Charging - Application | Completed | Task Dependent | 2026-02-26 07:00 | 2026-02-26 17:00 | 2026-02-11 07:00 | 2026-02-11 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1915 | Block-03 -CEA Inspection | Completed | Task Dependent | 2026-02-27 07:00 | 2026-02-27 17:00 | 2026-01-12 07:00 | 2026-01-12 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4490 | Block-11 -First Time Charging - Approval | Completed | Task Dependent | 2026-02-27 07:00 | 2026-02-28 17:00 | 2026-02-16 07:00 | 2026-02-16 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-9610 | Block-27 -First Time Charging - Approval | Completed | Task Dependent | 2026-02-28 07:00 | 2026-03-01 17:00 | 2026-03-07 07:00 | 2026-03-07 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5770 | Block-15 -First Time Charging - Approval | Completed | Task Dependent | 2026-02-28 07:00 | 2026-03-01 17:00 | 2026-03-07 07:00 | 2026-03-07 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4475 | Block-11 -CEA Inspection | Completed | Task Dependent | 2026-02-28 07:00 | 2026-02-28 17:00 | 2026-02-25 07:00 | 2026-02-25 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4825 | Block-12 -Trial Operation | Completed | Task Dependent | 2026-02-28 07:00 | 2026-02-28 17:00 | 2026-02-28 07:00 | 2026-02-28 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6405 | Block-17 -First Time Charging - Application | Completed | Task Dependent | 2026-02-28 07:00 | 2026-02-28 17:00 | 2026-04-03 07:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6410 | Block-17 -First Time Charging - Approval | Completed | Task Dependent | 2026-03-01 07:00 | 2026-03-02 17:00 | 2026-04-14 07:00 | 2026-04-14 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8000 | Block-22 -CEA Compliance & Approval | Completed | Task Dependent | 2026-03-01 07:00 | 2026-03-05 17:00 | 2026-02-28 07:00 | 2026-02-28 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5775 | Block-15 -First Time Charging | Completed | Task Dependent | 2026-03-02 07:00 | 2026-03-02 17:00 | 2026-03-08 07:00 | 2026-03-08 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4480 | Block-11 -CEA Compliance & Approval | Completed | Task Dependent | 2026-03-02 07:00 | 2026-03-06 17:00 | 2026-02-28 07:00 | 2026-02-28 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-9615 | Block-27 -First Time Charging | Completed | Task Dependent | 2026-03-02 07:00 | 2026-03-02 17:00 | 2026-03-08 07:00 | 2026-03-08 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4815 | Block-12 -First Time Charging | Completed | Task Dependent | 2026-03-03 07:00 | 2026-03-03 17:00 | 2026-02-26 07:00 | 2026-02-26 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6415 | Block-17 -First Time Charging | Completed | Task Dependent | 2026-03-03 07:00 | 2026-03-03 17:00 | 2026-03-08 07:00 | 2026-03-08 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5765 | Block-15 -First Time Charging - Application | Completed | Task Dependent | 2026-03-03 07:00 | 2026-03-03 17:00 | 2026-02-28 07:00 | 2026-02-28 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5155 | Block-13 -First Time Charging | Completed | Task Dependent | 2026-03-03 07:00 | 2026-03-03 17:00 | 2026-02-26 07:00 | 2026-02-26 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6075 | Block-16 -CEA Inspection | Completed | Task Dependent | 2026-03-04 07:00 | 2026-03-04 17:00 | 2026-01-12 07:00 | 2026-01-12 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8005 | Block-22 -First Time Charging - Application | Completed | Task Dependent | 2026-03-06 07:00 | 2026-03-06 17:00 | 2026-02-28 07:00 | 2026-02-28 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8010 | Block-22 -First Time Charging - Approval | Completed | Task Dependent | 2026-03-07 07:00 | 2026-03-08 17:00 | 2026-03-07 07:00 | 2026-03-07 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8015 | Block-22 -First Time Charging | Completed | Task Dependent | 2026-03-09 07:00 | 2026-03-09 17:00 | 2026-03-08 07:00 | 2026-03-08 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1305 | Block-01 -Trial Operation | Completed | Task Dependent | 2026-03-13 07:00 | 2026-03-13 17:00 | 2026-02-28 07:00 | 2026-02-28 11:30 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4845 | Block-13 -Trial Operation | Completed | Task Dependent | 2026-03-13 07:00 | 2026-03-13 17:00 | 2026-02-28 07:00 | 2026-02-28 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6430 | Block-17 -Trial Run Certificate | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-14 17:00 | 2026-03-06 07:00 | 2026-03-06 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-9630 | Block-27 -Trial Run Certificate | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-14 17:00 | 2026-03-11 07:00 | 2026-03-11 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4850 | Block-13 -Trial Run Certificate | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-14 17:00 | 2026-03-06 07:00 | 2026-03-06 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4830 | Block-12 -Trial Run Certificate | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-14 17:00 | 2026-03-06 07:00 | 2026-03-06 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1310 | Block-01 -Trial Run Certificate | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-14 17:00 | 2026-03-06 07:00 | 2026-03-06 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5790 | Block-15 -Trial Run Certificate | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-14 17:00 | 2026-03-11 07:00 | 2026-03-11 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8030 | Block-22 -Trial Run Certificate | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-14 17:00 | 2026-03-11 07:00 | 2026-03-11 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4510 | Block-11 -Trial Run Certificate | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-14 17:00 | 2026-03-11 07:00 | 2026-03-11 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7030 | Block-19 -CEA Application | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-14 17:00 | 2026-02-28 07:00 | 2026-02-28 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-9590 | Block-27 -CEA Application | Completed | Task Dependent | 2026-03-14 16:00 | 2026-03-15 16:00 | 2026-02-15 16:00 | 2026-02-15 16:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7990 | Block-22 -CEA Application | Completed | Task Dependent | 2026-03-15 07:00 | 2026-03-15 17:00 | 2026-02-15 07:00 | 2026-02-15 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7350 | Block-20 -CEA Application | Completed | Task Dependent | 2026-03-15 07:00 | 2026-03-15 17:00 | 2026-02-28 07:00 | 2026-02-28 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3830 | Block-09 -CEA Application | Completed | Task Dependent | 2026-03-16 07:00 | 2026-03-16 17:00 | 2026-02-28 07:00 | 2026-02-28 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7355 | Block-20 -CEA Inspection | Completed | Task Dependent | 2026-03-16 07:00 | 2026-03-16 17:00 | 2026-03-09 07:00 | 2026-03-09 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4505 | Block-11 -Trial Operation | Completed | Task Dependent | 2026-03-16 07:00 | 2026-03-16 17:00 | 2026-02-28 07:00 | 2026-02-28 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4150 | Block-10 -CEA Application | Completed | Task Dependent | 2026-03-16 07:00 | 2026-03-16 17:00 | 2026-02-28 07:00 | 2026-02-28 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1605 | Block-02 -First Time Charging - Application | Completed | Task Dependent | 2026-03-17 07:00 | 2026-03-17 17:00 | 2026-03-14 07:00 | 2026-03-14 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2550 | Block-05 -CEA Application | Completed | Task Dependent | 2026-03-17 07:00 | 2026-03-17 17:00 | 2026-03-15 07:00 | 2026-03-15 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7360 | Block-20 -CEA Compliance & Approval | Completed | Task Dependent | 2026-03-18 07:00 | 2026-03-22 17:00 | 2026-03-18 07:00 | 2026-03-18 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8025 | Block-22 -Trial Operation | Completed | Task Dependent | 2026-03-18 07:00 | 2026-03-18 17:00 | 2026-03-09 07:00 | 2026-03-09 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-9595 | Block-27 -CEA Inspection | Completed | Task Dependent | 2026-03-18 16:00 | 2026-03-19 16:00 | 2026-02-26 16:00 | 2026-02-26 16:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7995 | Block-22 -CEA Inspection | Completed | Task Dependent | 2026-03-19 07:00 | 2026-03-19 17:00 | 2026-02-26 07:00 | 2026-02-26 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6425 | Block-17 -Trial Operation | Completed | Task Dependent | 2026-03-20 07:00 | 2026-03-20 17:00 | 2026-03-09 07:00 | 2026-03-09 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5785 | Block-15 -Trial Operation | Completed | Task Dependent | 2026-03-20 07:00 | 2026-03-20 17:00 | 2026-03-08 07:00 | 2026-03-08 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-9625 | Block-27 -Trial Operation | Completed | Task Dependent | 2026-03-20 07:00 | 2026-03-20 17:00 | 2026-03-09 07:00 | 2026-03-09 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-9600 | Block-27 -CEA Compliance & Approval | Completed | Task Dependent | 2026-03-20 16:00 | 2026-03-25 16:00 | 2026-02-28 16:00 | 2026-02-28 16:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2890 | Block-06 -First Time Charging - Approval | Completed | Task Dependent | 2026-03-21 07:00 | 2026-03-22 17:00 | 2026-03-21 07:00 | 2026-03-21 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1610 | Block-02 -First Time Charging - Approval | Completed | Task Dependent | 2026-03-21 07:00 | 2026-03-22 17:00 | 2026-03-21 07:00 | 2026-03-21 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2570 | Block-05 -First Time Charging - Approval | Completed | Task Dependent | 2026-03-21 07:00 | 2026-03-22 17:00 | 2026-03-24 07:00 | 2026-03-24 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2555 | Block-05 -CEA Inspection | Completed | Task Dependent | 2026-03-22 07:00 | 2026-03-22 17:00 | 2026-03-21 07:00 | 2026-03-21 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7035 | Block-19 -CEA Inspection | Completed | Task Dependent | 2026-03-23 07:00 | 2026-03-23 17:00 | 2026-03-08 07:00 | 2026-03-08 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8985 | Block-25 -Trial Operation | Completed | Task Dependent | 2026-03-23 07:00 | 2026-03-23 17:00 | 2026-03-27 07:00 | 2026-03-27 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2585 | Block-05 -Trial Operation | Completed | Task Dependent | 2026-03-24 07:00 | 2026-03-24 17:00 | 2026-03-27 07:00 | 2026-03-27 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-9305 | Block-26 -Trial Operation | Completed | Task Dependent | 2026-03-24 07:00 | 2026-03-24 17:00 | 2026-03-27 07:00 | 2026-03-27 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2560 | Block-05 -CEA Compliance & Approval | Completed | Task Dependent | 2026-03-24 07:00 | 2026-03-28 17:00 | 2026-03-22 07:00 | 2026-03-22 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2905 | Block-06 -Trial Operation | Completed | Task Dependent | 2026-03-24 07:00 | 2026-03-24 17:00 | 2026-03-27 07:00 | 2026-03-27 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2870 | Block-06 -CEA Application | Completed | Task Dependent | 2026-03-25 07:00 | 2026-03-25 17:00 | 2026-03-15 07:00 | 2026-03-15 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3835 | Block-09 -CEA Inspection | Completed | Task Dependent | 2026-03-25 07:00 | 2026-03-25 17:00 | 2026-03-09 07:00 | 2026-03-09 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7040 | Block-19 -CEA Compliance & Approval | Completed | Task Dependent | 2026-03-25 07:00 | 2026-03-29 17:00 | 2026-03-12 07:00 | 2026-03-12 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-9605 | Block-27 -First Time Charging - Application | Completed | Task Dependent | 2026-03-25 16:00 | 2026-03-26 16:00 | 2026-02-28 16:00 | 2026-02-28 16:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3840 | Block-09 -CEA Compliance & Approval | Completed | Task Dependent | 2026-03-27 07:00 | 2026-03-31 17:00 | 2026-03-18 07:00 | 2026-03-18 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1625 | Block-02 -Trial Operation | Completed | Task Dependent | 2026-03-27 07:00 | 2026-03-27 17:00 | 2026-03-27 07:00 | 2026-03-27 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1615 | Block-02 -First Time Charging | Completed | Task Dependent | 2026-03-28 07:00 | 2026-03-28 17:00 | 2026-03-25 07:00 | 2026-03-25 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5445 | Block-14 -First Time Charging - Application | Completed | Task Dependent | 2026-03-28 07:00 | 2026-03-28 17:00 | 2026-02-28 07:00 | 2026-02-28 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3190 | Block-07 -CEA Application | Completed | Task Dependent | 2026-03-28 07:00 | 2026-03-28 17:00 | 2026-02-28 07:00 | 2026-02-28 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2575 | Block-05 -First Time Charging | Completed | Task Dependent | 2026-03-28 07:00 | 2026-03-28 17:00 | 2026-03-25 07:00 | 2026-03-25 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2895 | Block-06 -First Time Charging | Completed | Task Dependent | 2026-03-28 07:00 | 2026-03-28 17:00 | 2026-03-25 07:00 | 2026-03-25 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2875 | Block-06 -CEA Inspection | Completed | Task Dependent | 2026-03-31 07:00 | 2026-03-31 17:00 | 2026-03-21 07:00 | 2026-03-21 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1315 | Block-01 -COD | Completed | Task Dependent | 2026-04-01 07:00 | 2026-04-01 17:00 | 2026-03-13 07:00 | 2026-03-13 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4155 | Block-10 -CEA Inspection | Completed | Task Dependent | 2026-04-01 07:00 | 2026-04-01 17:00 | 2026-03-09 07:00 | 2026-03-09 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4835 | Block-12 -COD | Completed | Task Dependent | 2026-04-01 07:00 | 2026-04-01 17:00 | 2026-03-13 07:00 | 2026-03-13 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5795 | Block-15 -COD | Completed | Task Dependent | 2026-04-01 07:00 | 2026-04-01 17:00 | 2026-03-13 07:00 | 2026-03-13 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4515 | Block-11 -COD | Completed | Task Dependent | 2026-04-01 07:00 | 2026-04-01 17:00 | 2026-03-13 07:00 | 2026-03-13 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-9635 | Block-27 -COD | Completed | Task Dependent | 2026-04-01 07:00 | 2026-04-01 17:00 | 2026-03-13 07:00 | 2026-03-13 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8035 | Block-22 -COD | Completed | Task Dependent | 2026-04-01 07:00 | 2026-04-01 17:00 | 2026-03-13 07:00 | 2026-03-13 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2565 | Block-05 -First Time Charging - Application | Completed | Task Dependent | 2026-04-02 07:00 | 2026-04-02 17:00 | 2026-03-13 07:00 | 2026-03-14 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2880 | Block-06 -CEA Compliance & Approval | Completed | Task Dependent | 2026-04-02 07:00 | 2026-04-06 17:00 | 2026-03-22 07:00 | 2026-03-22 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4160 | Block-10 -CEA Compliance & Approval | Completed | Task Dependent | 2026-04-03 07:00 | 2026-04-07 17:00 | 2026-03-18 07:00 | 2026-03-18 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4855 | Block-13 -COD | Completed | Task Dependent | 2026-04-03 07:00 | 2026-04-03 17:00 | 2026-03-13 07:00 | 2026-03-13 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8975 | Block-25 -First Time Charging | Completed | Task Dependent | 2026-04-05 16:00 | 2026-04-06 16:00 | 2026-03-24 16:00 | 2026-03-24 16:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7055 | Block-19 -First Time Charging | Completed | Task Dependent | 2026-04-06 07:00 | 2026-04-06 17:00 | 2026-04-03 07:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4175 | Block-10 -First Time Charging | Completed | Task Dependent | 2026-04-06 07:00 | 2026-04-06 17:00 | 2026-04-03 07:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3855 | Block-09 -First Time Charging | Completed | Task Dependent | 2026-04-06 07:00 | 2026-04-06 17:00 | 2026-04-03 07:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2885 | Block-06 -First Time Charging - Application | Completed | Task Dependent | 2026-04-07 14:00 | 2026-04-08 14:00 | 2026-03-13 14:00 | 2026-03-14 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-9295 | Block-26 -First Time Charging | Completed | Task Dependent | 2026-04-07 16:00 | 2026-04-08 16:00 | 2026-03-23 16:00 | 2026-03-23 16:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4185 | Block-10 -Trial Operation | Completed | Task Dependent | 2026-04-10 13:00 | 2026-04-11 12:00 | 2026-04-09 13:00 | 2026-04-10 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5450 | Block-14 -First Time Charging - Approval | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-12 17:00 | 2026-03-07 07:00 | 2026-03-07 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3210 | Block-07 -First Time Charging - Approval | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-12 17:00 | 2026-03-20 07:00 | 2026-03-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3530 | Block-08 -First Time Charging - Approval | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-12 17:00 | 2026-03-23 07:00 | 2026-03-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6090 | Block-16 -First Time Charging - Approval | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-12 17:00 | 2026-03-07 07:00 | 2026-03-07 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4170 | Block-10 -First Time Charging - Approval | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-12 17:00 | 2026-03-20 07:00 | 2026-03-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8950 | Block-25 -CEA Application | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-11 17:00 | 2026-03-31 07:00 | 2026-03-31 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-9270 | Block-26 -CEA Application | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-11 17:00 | 2026-03-31 07:00 | 2026-03-31 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6435 | Block-17 -COD | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-11 17:00 | 2026-03-13 07:00 | 2026-03-13 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7370 | Block-20 -First Time Charging - Approval | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-12 17:00 | 2026-03-20 07:00 | 2026-03-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3850 | Block-09 -First Time Charging - Approval | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-12 17:00 | 2026-03-20 07:00 | 2026-03-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2250 | Block-04 -First Time Charging - Approval | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-12 17:00 | 2026-03-23 07:00 | 2026-03-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8310 | Block-23 -CEA Application | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-11 17:00 | 2026-03-31 07:00 | 2026-03-31 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7065 | Block-19 -Trial Operation | Completed | Task Dependent | 2026-04-11 15:00 | 2026-04-12 15:00 | 2026-04-10 15:00 | 2026-04-10 15:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7670 | Block-21 -CEA Application | Completed | Task Dependent | 2026-04-12 07:00 | 2026-04-12 17:00 | 2026-03-31 07:00 | 2026-03-31 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2230 | Block-04 -CEA Application | Completed | Task Dependent | 2026-04-12 11:00 | 2026-04-13 11:00 | 2026-03-15 11:00 | 2026-03-15 11:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3510 | Block-08 -CEA Application | Completed | Task Dependent | 2026-04-12 11:00 | 2026-04-13 11:00 | 2026-03-15 11:00 | 2026-03-15 11:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8345 | Block-23 -Trial Operation | Completed | Task Dependent | 2026-04-13 10:00 | 2026-04-14 10:00 | 2026-04-10 10:00 | 2026-04-10 10:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-9275 | Block-26 -CEA Inspection | Completed | Task Dependent | 2026-04-14 07:00 | 2026-04-14 17:00 | 2026-04-09 07:00 | 2026-04-09 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8630 | Block-24 -CEA Application | Completed | Task Dependent | 2026-04-14 13:00 | 2026-04-15 12:00 | 2026-03-31 09:00 | 2026-03-31 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3865 | Block-09 -Trial Operation | Completed | Task Dependent | 2026-04-14 13:00 | 2026-04-15 12:00 | 2026-04-09 13:00 | 2026-04-10 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7045 | Block-19 -First Time Charging - Application | Completed | Task Dependent | 2026-04-14 14:00 | 2026-04-15 14:00 | 2026-04-03 14:00 | 2026-04-03 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8955 | Block-25 -CEA Inspection | Completed | Task Dependent | 2026-04-15 07:00 | 2026-04-15 17:00 | 2026-04-09 07:00 | 2026-04-09 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8315 | Block-23 -CEA Inspection | Completed | Task Dependent | 2026-04-15 07:00 | 2026-04-15 17:00 | 2026-04-09 07:00 | 2026-04-09 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7050 | Block-19 -First Time Charging - Approval | Completed | Task Dependent | 2026-04-15 14:00 | 2026-04-17 14:00 | 2026-04-14 14:00 | 2026-04-14 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-9280 | Block-26 -CEA Compliance & Approval | Completed | Task Dependent | 2026-04-16 07:00 | 2026-04-20 17:00 | 2026-04-14 07:00 | 2026-04-14 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8335 | Block-23 -First Time Charging | Completed | Task Dependent | 2026-04-16 09:00 | 2026-04-17 09:00 | 2026-04-03 09:00 | 2026-04-03 09:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3195 | Block-07 -CEA Inspection | Completed | Task Dependent | 2026-04-16 11:00 | 2026-04-17 11:00 | 2026-03-09 11:00 | 2026-03-09 11:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2235 | Block-04 -CEA Inspection | Completed | Task Dependent | 2026-04-16 11:00 | 2026-04-17 11:00 | 2026-03-21 11:00 | 2026-03-21 11:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8960 | Block-25 -CEA Compliance & Approval | Completed | Task Dependent | 2026-04-17 07:00 | 2026-04-18 17:00 | 2026-04-14 07:00 | 2026-04-14 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8320 | Block-23 -CEA Compliance & Approval | Completed | Task Dependent | 2026-04-17 07:00 | 2026-04-21 17:00 | 2026-04-14 07:00 | 2026-04-14 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6085 | Block-16 -First Time Charging - Application | Completed | Task Dependent | 2026-04-17 11:00 | 2026-04-18 11:00 | 2026-02-28 11:00 | 2026-02-28 11:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3515 | Block-08 -CEA Inspection | Completed | Task Dependent | 2026-04-17 13:00 | 2026-04-18 12:00 | 2026-03-20 13:00 | 2026-03-21 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3845 | Block-09 -First Time Charging - Application | Completed | Task Dependent | 2026-04-17 13:00 | 2026-04-18 12:00 | 2026-03-13 13:00 | 2026-03-14 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2240 | Block-04 -CEA Compliance & Approval | Completed | Task Dependent | 2026-04-18 11:00 | 2026-04-23 11:00 | 2026-03-22 11:00 | 2026-03-22 11:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3200 | Block-07 -CEA Compliance & Approval | Completed | Task Dependent | 2026-04-18 11:00 | 2026-04-23 11:00 | 2026-03-18 11:00 | 2026-03-18 11:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8965 | Block-25 -First Time Charging - Application | Completed | Task Dependent | 2026-04-19 07:00 | 2026-04-19 17:00 | 2026-04-03 07:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3520 | Block-08 -CEA Compliance & Approval | Completed | Task Dependent | 2026-04-19 13:00 | 2026-04-24 12:00 | 2026-03-21 13:00 | 2026-03-22 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8970 | Block-25 -First Time Charging - Approval | Completed | Task Dependent | 2026-04-20 07:00 | 2026-04-21 17:00 | 2026-04-14 07:00 | 2026-04-14 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-9285 | Block-26 -First Time Charging - Application | Completed | Task Dependent | 2026-04-21 07:00 | 2026-04-21 17:00 | 2026-04-03 07:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7675 | Block-21 -CEA Inspection | Completed | Task Dependent | 2026-04-21 10:00 | 2026-04-22 10:00 | 2026-04-09 10:00 | 2026-04-09 10:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7375 | Block-20 -First Time Charging | Completed | Task Dependent | 2026-04-21 14:00 | 2026-04-22 14:00 | 2026-04-17 14:00 | 2026-04-17 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3535 | Block-08 -First Time Charging | Completed | Task Dependent | 2026-04-21 14:00 | 2026-04-22 14:00 | 2026-04-17 14:00 | 2026-04-17 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8325 | Block-23 -First Time Charging - Application | Completed | Task Dependent | 2026-04-22 07:00 | 2026-04-22 17:00 | 2026-04-03 07:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-9290 | Block-26 -First Time Charging - Approval | Completed | Task Dependent | 2026-04-22 07:00 | 2026-04-23 17:00 | 2026-04-14 07:00 | 2026-04-14 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8330 | Block-23 -First Time Charging - Approval | Completed | Task Dependent | 2026-04-23 07:00 | 2026-04-24 17:00 | 2026-04-14 07:00 | 2026-04-14 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5455 | Block-14 -First Time Charging | Completed | Task Dependent | 2026-04-23 09:00 | 2026-04-24 09:00 | 2026-04-17 09:00 | 2026-04-17 09:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6095 | Block-16 -First Time Charging | Completed | Task Dependent | 2026-04-23 09:00 | 2026-04-24 09:00 | 2026-04-17 09:00 | 2026-04-17 09:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1925 | Block-03 -First Time Charging - Application | Completed | Task Dependent | 2026-04-23 10:00 | 2026-04-24 10:00 | 2026-02-11 10:00 | 2026-02-11 10:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7680 | Block-21 -CEA Compliance & Approval | Completed | Task Dependent | 2026-04-23 10:00 | 2026-04-28 10:00 | 2026-04-14 10:00 | 2026-04-14 10:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8635 | Block-24 -CEA Inspection | Completed | Task Dependent | 2026-04-23 14:00 | 2026-04-24 14:00 | 2026-04-09 10:00 | 2026-04-09 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1930 | Block-03 -First Time Charging - Approval | Completed | Task Dependent | 2026-04-24 10:00 | 2026-04-26 10:00 | 2026-02-16 10:00 | 2026-02-16 10:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7365 | Block-20 -First Time Charging - Application | Completed | Task Dependent | 2026-04-25 09:00 | 2026-04-26 09:00 | 2026-03-13 09:00 | 2026-03-14 09:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8640 | Block-24 -CEA Compliance & Approval | Completed | Task Dependent | 2026-04-25 14:00 | 2026-04-30 14:00 | 2026-04-14 14:00 | 2026-04-14 15:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4165 | Block-10 -First Time Charging - Application | Completed | Task Dependent | 2026-04-25 14:00 | 2026-04-26 14:00 | 2026-03-13 14:00 | 2026-03-14 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1935 | Block-03 -First Time Charging | Completed | Task Dependent | 2026-04-26 15:00 | 2026-04-27 15:00 | 2026-04-17 15:00 | 2026-04-17 15:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6725 | Block-18 -First Time Charging - Application | Completed | Task Dependent | 2026-04-26 15:00 | 2026-04-27 15:00 | 2026-04-03 15:00 | 2026-04-03 15:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3215 | Block-07 -First Time Charging | Completed | Task Dependent | 2026-04-26 15:00 | 2026-04-27 15:00 | 2026-04-17 15:00 | 2026-04-17 15:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6730 | Block-18 -First Time Charging - Approval | Completed | Task Dependent | 2026-04-27 15:00 | 2026-04-29 15:00 | 2026-04-14 15:00 | 2026-04-14 15:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6105 | Block-16 -Trial Operation | Completed | Task Dependent | 2026-04-29 14:00 | 2026-04-30 14:00 | 2026-04-17 14:00 | 2026-04-17 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6735 | Block-18 -First Time Charging | Completed | Task Dependent | 2026-04-29 15:00 | 2026-04-30 15:00 | 2026-04-17 15:00 | 2026-04-17 15:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3205 | Block-07 -First Time Charging - Application | Completed | Task Dependent | 2026-04-30 13:00 | 2026-05-01 12:00 | 2026-03-13 13:00 | 2026-03-14 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3525 | Block-08 -First Time Charging - Application | Completed | Task Dependent | 2026-05-01 14:00 | 2026-05-02 14:00 | 2026-03-13 14:00 | 2026-03-14 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2255 | Block-04 -First Time Charging | Completed | Task Dependent | 2026-05-04 13:00 | 2026-05-05 12:00 | 2026-04-16 13:00 | 2026-04-17 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-9315 | Block-26 -COD | Completed | Task Dependent | 2026-05-04 14:00 | 2026-05-05 14:00 | 2026-03-29 14:00 | 2026-03-30 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8995 | Block-25 -COD | Completed | Task Dependent | 2026-05-04 14:00 | 2026-05-05 14:00 | 2026-03-29 14:00 | 2026-03-30 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2595 | Block-05 -COD | Completed | Task Dependent | 2026-05-04 14:00 | 2026-05-05 14:00 | 2026-03-29 14:00 | 2026-03-30 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7685 | Block-21 -First Time Charging - Application | Completed | Task Dependent | 2026-05-05 15:00 | 2026-05-06 15:00 | 2026-04-03 15:00 | 2026-04-03 15:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6745 | Block-18 -Trial Operation | Completed | Task Dependent | 2026-05-06 15:00 | 2026-05-07 15:00 | 2026-04-17 15:00 | 2026-04-17 15:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7690 | Block-21 -First Time Charging - Approval | Completed | Task Dependent | 2026-05-06 15:00 | 2026-05-08 15:00 | 2026-04-14 15:00 | 2026-04-14 15:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2245 | Block-04 -First Time Charging - Application | Completed | Task Dependent | 2026-05-07 11:00 | 2026-05-08 11:00 | 2026-03-13 11:00 | 2026-03-14 11:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8645 | Block-24 -First Time Charging - Application | Completed | Task Dependent | 2026-05-08 13:00 | 2026-05-09 12:00 | 2026-04-03 07:00 | 2026-04-03 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7695 | Block-21 -First Time Charging | Completed | Task Dependent | 2026-05-08 15:00 | 2026-05-09 15:00 | 2026-04-17 15:00 | 2026-04-17 15:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5465 | Block-14 -Trial Operation | Completed | Task Dependent | 2026-05-09 13:00 | 2026-05-10 12:00 | 2026-04-17 13:00 | 2026-04-18 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8650 | Block-24 -First Time Charging - Approval | Completed | Task Dependent | 2026-05-09 13:00 | 2026-05-11 12:00 | 2026-04-14 08:00 | 2026-04-14 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3225 | Block-07 -Trial Operation | Completed | Task Dependent | 2026-05-10 14:00 | 2026-05-11 14:00 | 2026-04-17 14:00 | 2026-04-17 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8655 | Block-24 -First Time Charging | Completed | Task Dependent | 2026-05-11 13:00 | 2026-05-12 12:00 | 2026-04-16 13:00 | 2026-04-17 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1945 | Block-03 -Trial Operation | Completed | Task Dependent | 2026-05-12 09:00 | 2026-05-13 09:00 | 2026-04-17 09:00 | 2026-04-17 09:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8665 | Block-24 -Trial Operation | Completed | Task Dependent | 2026-05-13 13:00 | 2026-05-14 12:00 | 2026-04-17 13:00 | 2026-04-18 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7705 | Block-21 -Trial Operation | Completed | Task Dependent | 2026-05-15 15:00 | 2026-05-16 15:00 | 2026-04-17 15:00 | 2026-04-17 15:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2915 | Block-06 -COD | Completed | Task Dependent | 2026-05-17 13:00 | 2026-05-18 12:00 | 2026-03-29 13:00 | 2026-03-30 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7390 | Block-20 -Trial Run Certificate | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8990 | Block-25 -Trial Run Certificate | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5780 | Block-15 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-06-03 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5470 | Block-14 -Trial Run Certificate | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2270 | Block-04 -Trial Run Certificate | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1950 | Block-03 -Trial Run Certificate | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-9310 | Block-26 -Trial Run Certificate | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4190 | Block-10 -Trial Run Certificate | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3550 | Block-08 -Trial Run Certificate | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2910 | Block-06 -Trial Run Certificate | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7710 | Block-21 -Trial Run Certificate | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1300 | Block-01 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-06-03 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6110 | Block-16 -Trial Run Certificate | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4820 | Block-12 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-06-03 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3230 | Block-07 -Trial Run Certificate | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8020 | Block-22 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-06-03 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2590 | Block-05 -Trial Run Certificate | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1630 | Block-02 -Trial Run Certificate | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6750 | Block-18 -Trial Run Certificate | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8350 | Block-23 -Trial Run Certificate | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7070 | Block-19 -Trial Run Certificate | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8670 | Block-24 -Trial Run Certificate | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-9620 | Block-27 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-06-03 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4500 | Block-11 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-06-03 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3870 | Block-09 -Trial Run Certificate | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4840 | Block-13 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-05-26 13:00 | 2026-06-06 12:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2265 | Block-04 -Trial Operation | Completed | Task Dependent | 2026-05-30 09:00 | 2026-05-31 09:00 | 2026-04-17 09:00 | 2026-04-17 09:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7385 | Block-20 -Trial Operation | Completed | Task Dependent | 2026-05-31 09:00 | 2026-06-01 09:00 | 2026-04-17 09:00 | 2026-04-17 09:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3545 | Block-08 -Trial Operation | Completed | Task Dependent | 2026-05-31 11:00 | 2026-06-01 11:00 | 2026-04-17 11:00 | 2026-04-17 11:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3860 | Block-09 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-06-05 09:00 | 2026-06-16 09:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6740 | Block-18 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-06-05 14:00 | 2026-06-16 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2580 | Block-05 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-06-05 14:00 | 2026-06-16 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7060 | Block-19 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-06-05 14:00 | 2026-06-16 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6420 | Block-17 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-06-05 14:00 | 2026-06-16 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5460 | Block-14 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-06-05 14:00 | 2026-06-16 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3540 | Block-08 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-06-05 14:00 | 2026-06-16 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8340 | Block-23 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-06-05 14:00 | 2026-06-16 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4180 | Block-10 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-06-05 14:00 | 2026-06-16 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8980 | Block-25 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-06-05 14:00 | 2026-06-16 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2900 | Block-06 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-06-05 14:00 | 2026-06-16 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1940 | Block-03 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-06-05 14:00 | 2026-06-16 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8660 | Block-24 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-06-05 14:00 | 2026-06-16 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6100 | Block-16 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-06-05 14:00 | 2026-06-16 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-9300 | Block-26 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-06-05 14:00 | 2026-06-16 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1620 | Block-02 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-06-05 14:00 | 2026-06-16 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7700 | Block-21 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-06-07 13:00 | 2026-06-18 13:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2260 | Block-04 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-06-10 10:00 | 2026-06-21 10:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3875 | Block-09 -COD | Not Started | Task Dependent | 2026-06-16 09:00 | 2026-06-17 09:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6115 | Block-16 -COD | Not Started | Task Dependent | 2026-06-16 14:00 | 2026-06-17 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7075 | Block-19 -COD | Not Started | Task Dependent | 2026-06-16 14:00 | 2026-06-17 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1635 | Block-02 -COD | Not Started | Task Dependent | 2026-06-16 14:00 | 2026-06-17 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8675 | Block-24 -COD | Not Started | Task Dependent | 2026-06-16 14:00 | 2026-06-17 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-5475 | Block-14 -COD | Not Started | Task Dependent | 2026-06-16 14:00 | 2026-06-17 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-8355 | Block-23 -COD | Not Started | Task Dependent | 2026-06-16 14:00 | 2026-06-17 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-1955 | Block-03 -COD | Not Started | Task Dependent | 2026-06-16 14:00 | 2026-06-17 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-6755 | Block-18 -COD | Not Started | Task Dependent | 2026-06-16 14:00 | 2026-06-17 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-4195 | Block-10 -COD | Not Started | Task Dependent | 2026-06-16 14:00 | 2026-06-17 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3555 | Block-08 -COD | Not Started | Task Dependent | 2026-06-16 14:00 | 2026-06-17 14:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7715 | Block-21 -COD | Not Started | Task Dependent | 2026-06-18 13:00 | 2026-06-19 12:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3220 | Block-07 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-06-18 13:00 | 2026-06-29 12:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-2275 | Block-04 -COD | Not Started | Task Dependent | 2026-06-21 10:00 | 2026-06-22 10:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7380 | Block-20 -Robot Commissioning - SCADA | Not Started | Task Dependent | 2026-06-28 13:00 | 2026-07-09 12:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-3235 | Block-07 -COD | Not Started | Task Dependent | 2026-06-29 13:00 | 2026-06-30 12:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-COMMISSIONING | 603F-CC-7395 | Block-20 -COD | Not Started | Task Dependent | 2026-07-09 13:00 | 2026-07-10 12:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4955 | Block-13 -IDT Foundation Up To Rail | Completed | Task Dependent | 2025-06-28 07:00 | 2025-08-03 10:00 | 2025-07-02 07:00 | 2026-02-02 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5575 | Block-15 -IDT Foundation Up To Rail | Completed | Task Dependent | 2025-07-19 07:00 | 2025-08-26 11:00 | 2025-07-25 07:00 | 2026-02-12 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6220 | Block-17 -HT & LT Station - Slab | Completed | Task Dependent | 2025-11-29 08:00 | 2025-12-13 17:00 | 2025-11-26 08:00 | 2025-12-29 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9420 | Block-27 -HT & LT Station - Slab | Completed | Task Dependent | 2025-11-29 08:00 | 2025-12-13 17:00 | 2025-11-25 08:00 | 2025-12-10 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4620 | Block-12 -HT & LT Station - Slab | Completed | Task Dependent | 2025-11-29 08:00 | 2025-12-13 17:00 | 2025-11-22 08:00 | 2025-12-15 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9415 | Block-27 -IDT Foundation Up To Rail | Completed | Task Dependent | 2025-11-29 08:00 | 2025-12-19 17:00 | 2025-11-25 08:00 | 2025-12-10 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4615 | Block-12 -IDT Foundation Up To Rail | Completed | Task Dependent | 2025-11-29 08:00 | 2025-12-19 17:00 | 2025-11-21 08:00 | 2025-12-11 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5255 | Block-14 -IDT Foundation Up To Rail | Completed | Task Dependent | 2025-11-29 08:00 | 2025-12-19 17:00 | 2025-08-27 08:00 | 2026-02-05 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6285 | Block-17 -HT Cable Laying | Completed | Task Dependent | 2025-12-06 08:00 | 2025-12-12 17:00 | 2025-12-03 08:00 | 2026-02-26 17:00 | 1 | 4 | Kilometer | 4 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5645 | Block-15 -HT Cable Laying | Completed | Task Dependent | 2025-12-06 08:00 | 2025-12-12 17:00 | 2025-12-05 08:00 | 2026-02-25 17:00 | 1 | 4 | Kilometer | 4 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6215 | Block-17 -IDT Foundation Up To Rail | Completed | Task Dependent | 2025-12-06 08:00 | 2025-12-26 17:00 | 2025-11-29 08:00 | 2025-12-16 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5025 | Block-13 -HT Cable Laying | Completed | Task Dependent | 2025-12-06 08:00 | 2025-12-12 17:00 | 2025-12-03 08:00 | 2026-02-23 17:00 | 1 | 4 | Kilometer | 4 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6605 | Block-18 -HT Cable Laying | Completed | Task Dependent | 2025-12-06 08:00 | 2025-12-12 17:00 | 2025-12-04 08:00 | 2026-04-07 12:00 | 1 | 4 | Kilometer | 4 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6925 | Block-19 -HT Cable Laying | Completed | Task Dependent | 2025-12-06 08:00 | 2025-12-12 17:00 | 2025-12-05 08:00 | 2026-03-27 17:00 | 1 | 4 | Kilometer | 4 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7885 | Block-22 -HT Cable Laying | Completed | Task Dependent | 2025-12-06 08:00 | 2025-12-12 17:00 | 2025-12-04 08:00 | 2026-02-25 17:00 | 1 | 4 | Kilometer | 4 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7180 | Block-20 -HT & LT Station - Slab | Completed | Task Dependent | 2025-12-06 08:00 | 2025-12-20 17:00 | 2025-11-25 08:00 | 2025-12-22 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7175 | Block-20 -IDT Foundation Up To Rail | Completed | Task Dependent | 2025-12-06 08:00 | 2025-12-26 17:00 | 2025-11-30 08:00 | 2025-12-13 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5325 | Block-14 -HT Cable Laying | Completed | Task Dependent | 2025-12-06 08:00 | 2025-12-12 17:00 | 2025-12-04 08:00 | 2026-04-07 10:00 | 1 | 4 | Kilometer | 4 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5015 | Block-13 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2025-12-08 08:00 | 2025-12-12 17:00 | 2025-11-24 08:00 | 2026-02-19 17:00 | 1 | 8 | Lot | 7.7 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5020 | Block-13 -LT Cable Laying | Completed | Task Dependent | 2025-12-10 08:00 | 2025-12-29 17:00 | 2025-11-22 08:00 | 2025-11-24 17:00 | 1 | 12 | Kilometer | 9.625 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7565 | Block-21 -HT Cable Laying | Completed | Task Dependent | 2025-12-13 08:00 | 2025-12-19 17:00 | 2025-12-06 08:00 | 2026-04-12 10:00 | 1 | 4 | Kilometer | 4 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2445 | Block-05 -HT Cable Laying | Completed | Task Dependent | 2025-12-13 08:00 | 2025-12-19 17:00 | 2025-12-11 08:00 | 2026-03-20 17:00 | 1 | 4 | Kilometer | 4 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8525 | Block-24 -HT Cable Laying | Completed | Task Dependent | 2025-12-13 08:00 | 2025-12-19 17:00 | 2025-12-07 08:00 | 2026-04-12 10:00 | 1 | 4 | Kilometer | 4 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2125 | Block-04 -HT Cable Laying | Completed | Task Dependent | 2025-12-13 08:00 | 2025-12-19 17:00 | 2025-12-11 08:00 | 2026-04-20 12:00 | 1 | 4 | Kilometer | 4 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8845 | Block-25 -HT Cable Laying | Completed | Task Dependent | 2025-12-13 08:00 | 2025-12-19 17:00 | 2025-12-06 08:00 | 2026-03-13 17:00 | 1 | 4 | Kilometer | 4 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4045 | Block-10 -HT Cable Laying | Completed | Task Dependent | 2025-12-13 08:00 | 2025-12-19 17:00 | 2025-12-12 08:00 | 2026-03-28 17:00 | 1 | 4 | Kilometer | 4 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9165 | Block-26 -HT Cable Laying | Completed | Task Dependent | 2025-12-13 08:00 | 2025-12-19 17:00 | 2025-12-06 08:00 | 2026-02-24 17:00 | 1 | 4 | Kilometer | 4 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5965 | Block-16 -HT Cable Laying | Completed | Task Dependent | 2025-12-13 08:00 | 2025-12-19 17:00 | 2025-12-07 08:00 | 2026-04-07 10:00 | 1 | 4 | Kilometer | 4 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1805 | Block-03 -HT Cable Laying | Completed | Task Dependent | 2025-12-13 08:00 | 2025-12-19 17:00 | 2025-12-11 08:00 | 2026-04-20 10:00 | 1 | 4 | Kilometer | 4 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7245 | Block-20 -HT Cable Laying | Completed | Task Dependent | 2025-12-13 08:00 | 2025-12-19 17:00 | 2025-12-08 08:00 | 2026-04-12 10:00 | 1 | 4 | Kilometer | 4 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1485 | Block-02 -HT Cable Laying | Completed | Task Dependent | 2025-12-13 08:00 | 2025-12-19 17:00 | 2025-12-10 08:00 | 2026-03-22 17:00 | 1 | 4 | Kilometer | 4 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3725 | Block-09 -HT Cable Laying | Completed | Task Dependent | 2025-12-13 08:00 | 2025-12-19 17:00 | 2025-12-11 08:00 | 2026-03-28 17:00 | 1 | 4 | Kilometer | 4 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8205 | Block-23 -HT Cable Laying | Completed | Task Dependent | 2025-12-13 08:00 | 2025-12-19 17:00 | 2025-12-08 08:00 | 2026-03-27 17:00 | 1 | 4 | Kilometer | 4 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9485 | Block-27 -HT Cable Laying | Completed | Task Dependent | 2025-12-13 08:00 | 2025-12-19 17:00 | 2025-12-06 08:00 | 2026-03-04 17:00 | 1 | 4 | Kilometer | 4 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5055 | Block-13 -Inverter Installation | Completed | Task Dependent | 2025-12-17 08:00 | 2025-12-23 17:00 | 2025-11-25 08:00 | 2026-02-18 17:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1100 | Block-01 -HT & LT Station - Slab | Completed | Task Dependent | 2025-12-20 08:00 | 2026-01-03 17:00 | 2025-12-20 08:00 | 2026-01-06 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4300 | Block-11 -HT & LT Station - Slab | Completed | Task Dependent | 2025-12-20 08:00 | 2026-01-03 17:00 | 2025-12-21 08:00 | 2026-01-02 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6540 | Block-18 -HT & LT Station - Slab | Completed | Task Dependent | 2025-12-20 08:00 | 2026-01-03 17:00 | 2025-12-08 08:00 | 2026-02-07 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4295 | Block-11 -IDT Foundation Up To Rail | Completed | Task Dependent | 2025-12-20 08:00 | 2026-01-09 17:00 | 2025-12-13 08:00 | 2026-01-02 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7500 | Block-21 -HT & LT Station - Slab | Completed | Task Dependent | 2025-12-20 08:00 | 2026-01-03 17:00 | 2025-12-16 08:00 | 2026-01-19 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7495 | Block-21 -IDT Foundation Up To Rail | Completed | Task Dependent | 2025-12-20 08:00 | 2026-01-09 17:00 | 2025-12-15 08:00 | 2026-01-15 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3020 | Block-07 -HT & LT Station - Slab | Completed | Task Dependent | 2025-12-20 08:00 | 2026-01-03 17:00 | 2025-12-10 08:00 | 2026-01-20 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1095 | Block-01 -IDT Foundation Up To Rail | Completed | Task Dependent | 2025-12-20 08:00 | 2026-01-09 17:00 | 2025-12-15 08:00 | 2026-01-03 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8135 | Block-23 -IDT Foundation Up To Rail | Completed | Task Dependent | 2025-12-20 08:00 | 2026-01-09 17:00 | 2025-12-22 08:00 | 2026-01-18 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9445 | Block-27 -BOT Foundation | Completed | Task Dependent | 2025-12-24 08:00 | 2026-01-02 17:00 | 2025-12-09 08:00 | 2025-12-15 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9450 | Block-27 -Aux Transformer Foundation | Completed | Task Dependent | 2025-12-24 08:00 | 2025-12-28 17:00 | 2025-12-15 08:00 | 2025-12-16 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9435 | Block-27 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2025-12-24 08:00 | 2026-01-01 17:00 | 2025-12-11 08:00 | 2025-12-17 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4645 | Block-12 -BOT Foundation | Completed | Task Dependent | 2025-12-24 08:00 | 2026-01-02 17:00 | 2025-12-16 08:00 | 2025-12-26 11:36 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4635 | Block-12 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2025-12-24 08:00 | 2026-01-01 17:00 | 2025-12-11 08:00 | 2025-12-18 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7205 | Block-20 -BOT Foundation | Completed | Task Dependent | 2025-12-24 08:00 | 2026-01-02 17:00 | 2025-12-15 08:00 | 2025-12-27 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9440 | Block-27 -NIFPS Foundation | Completed | Task Dependent | 2025-12-24 08:00 | 2026-01-02 17:00 | 2025-12-15 08:00 | 2025-12-16 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6310 | Block-17 -IDT Erection | Completed | Task Dependent | 2025-12-27 08:00 | 2025-12-31 17:00 | 2025-12-28 08:00 | 2025-12-28 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9530 | Block-27 -Aux Transformer - Installation | Completed | Task Dependent | 2025-12-27 08:00 | 2025-12-30 17:00 | 2025-12-16 08:00 | 2025-12-16 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4640 | Block-12 -NIFPS Foundation | Completed | Task Dependent | 2025-12-27 08:00 | 2026-01-05 17:00 | 2025-12-25 08:00 | 2025-12-26 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4650 | Block-12 -Aux Transformer Foundation | Completed | Task Dependent | 2025-12-27 08:00 | 2025-12-31 17:00 | 2025-12-25 08:00 | 2025-12-26 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7270 | Block-20 -IDT Erection | Completed | Task Dependent | 2025-12-27 08:00 | 2025-12-31 17:00 | 2025-12-27 08:00 | 2025-12-27 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6535 | Block-18 -IDT Foundation Up To Rail | Completed | Task Dependent | 2025-12-27 08:00 | 2026-01-16 17:00 | 2025-12-31 08:00 | 2026-01-26 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9510 | Block-27 -IDT Erection | Completed | Task Dependent | 2025-12-27 08:00 | 2025-12-31 17:00 | 2025-12-25 08:00 | 2025-12-25 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7820 | Block-22 -HT & LT Station - Slab | Completed | Task Dependent | 2025-12-27 08:00 | 2026-01-10 17:00 | 2026-01-01 08:00 | 2026-01-26 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7815 | Block-22 -IDT Foundation Up To Rail | Completed | Task Dependent | 2025-12-27 08:00 | 2026-01-16 17:00 | 2025-12-31 08:00 | 2026-01-14 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9480 | Block-27 -LT Cable Laying | Completed | Task Dependent | 2025-12-27 08:00 | 2026-01-15 17:00 | 2025-12-24 08:00 | 2025-12-26 17:00 | 1 | 10.7 | Kilometer | 11 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4710 | Block-12 -IDT Erection | Completed | Task Dependent | 2025-12-27 08:00 | 2025-12-31 17:00 | 2025-12-23 08:00 | 2025-12-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4675 | Block-12 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2025-12-30 08:00 | 2026-01-03 17:00 | 2025-12-23 08:00 | 2026-02-18 17:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4315 | Block-11 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2025-12-31 08:00 | 2026-01-08 17:00 | 2025-12-31 08:00 | 2026-01-03 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9515 | Block-27 -Inverter Installation | Completed | Task Dependent | 2025-12-31 08:00 | 2026-01-06 17:00 | 2025-12-15 08:00 | 2026-01-03 17:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4715 | Block-12 -Inverter Installation | Completed | Task Dependent | 2025-12-31 08:00 | 2026-01-06 17:00 | 2025-12-25 08:00 | 2026-01-04 17:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5315 | Block-14 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-01-01 08:00 | 2026-01-05 17:00 | 2025-12-11 08:00 | 2026-03-27 17:00 | 1 | 8 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8235 | Block-23 -Inverter Installation | Completed | Task Dependent | 2026-01-01 08:00 | 2026-01-07 17:00 | 2026-01-02 08:00 | 2026-03-23 17:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7595 | Block-21 -Inverter Installation | Completed | Task Dependent | 2026-01-01 08:00 | 2026-01-07 17:00 | 2026-01-02 08:00 | 2026-01-09 17:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9475 | Block-27 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-01-01 08:00 | 2026-01-05 17:00 | 2025-12-11 08:00 | 2026-02-19 17:00 | 1 | 8 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9500 | Block-27 -HT Panel Erection | Completed | Task Dependent | 2026-01-02 08:00 | 2026-01-02 17:00 | 2025-12-15 08:00 | 2025-12-15 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7915 | Block-22 -Inverter Installation | Completed | Task Dependent | 2026-01-02 12:19 | 2026-01-09 12:19 | 2025-12-30 12:19 | 2026-01-09 17:00 | 1 | 94 | Number | 94 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4365 | Block-11 -HT Cable Laying | Completed | Task Dependent | 2026-01-03 08:00 | 2026-01-09 17:00 | 2026-01-08 08:00 | 2026-02-23 17:00 | 1 | 6.6 | Kilometer | 7 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1420 | Block-02 -HT & LT Station - Slab | Completed | Task Dependent | 2026-01-03 08:00 | 2026-01-17 17:00 | 2026-01-05 08:00 | 2026-02-02 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7185 | Block-20 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-01-03 08:00 | 2026-01-07 17:00 | 2026-01-09 08:00 | 2026-01-16 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3975 | Block-10 -IDT Foundation Up To Rail | Completed | Task Dependent | 2026-01-03 08:00 | 2026-01-23 17:00 | 2026-01-04 08:00 | 2026-01-10 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2695 | Block-06 -IDT Foundation Up To Rail | Completed | Task Dependent | 2026-01-03 08:00 | 2026-01-23 17:00 | 2026-01-02 08:00 | 2026-02-04 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7875 | Block-22 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-01-03 08:00 | 2026-01-07 17:00 | 2026-01-02 08:00 | 2026-02-19 17:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8455 | Block-24 -IDT Foundation Up To Rail | Completed | Task Dependent | 2026-01-03 08:00 | 2026-01-23 17:00 | 2026-01-05 08:00 | 2026-02-14 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8140 | Block-23 -HT & LT Station - Slab | Completed | Task Dependent | 2026-01-03 08:00 | 2026-01-17 17:00 | 2026-01-04 08:00 | 2026-01-29 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6235 | Block-17 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-01-03 08:00 | 2026-01-11 17:00 | 2026-01-03 08:00 | 2026-01-10 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3085 | Block-07 -HT Cable Laying | Completed | Task Dependent | 2026-01-03 08:00 | 2026-01-09 17:00 | 2026-01-04 08:00 | 2026-02-23 17:00 | 1 | 5.9 | Kilometer | 6 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9490 | Block-27 -FO Cable Laying | Completed | Task Dependent | 2026-01-03 08:00 | 2026-01-09 17:00 | 2026-01-10 08:00 | 2026-03-04 17:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9425 | Block-27 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-01-03 08:00 | 2026-01-07 17:00 | 2026-01-05 08:00 | 2026-01-09 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1735 | Block-03 -IDT Foundation Up To Rail | Completed | Task Dependent | 2026-01-03 08:00 | 2026-01-23 17:00 | 2026-01-05 08:00 | 2026-02-02 08:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5320 | Block-14 -LT Cable Laying | Completed | Task Dependent | 2026-01-03 08:00 | 2026-01-22 17:00 | 2025-12-10 08:00 | 2026-03-10 17:00 | 1 | 12 | Kilometer | 12 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5355 | Block-14 -Inverter Installation | Completed | Task Dependent | 2026-01-03 08:00 | 2026-01-09 17:00 | 2026-01-03 08:00 | 2026-03-10 17:00 | 1 | 94 | Number | 94 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3405 | Block-08 -HT Cable Laying | Completed | Task Dependent | 2026-01-03 08:00 | 2026-01-09 17:00 | 2026-01-09 08:00 | 2026-04-07 10:00 | 1 | 6.2 | Kilometer | 6 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4960 | Block-13 -HT & LT Station - Slab | Completed | Task Dependent | 2026-01-03 08:00 | 2026-01-17 17:00 | 2026-01-02 08:00 | 2026-02-02 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4625 | Block-12 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-01-03 08:00 | 2026-01-07 17:00 | 2026-01-05 08:00 | 2026-01-09 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7560 | Block-21 -LT Cable Laying | Completed | Task Dependent | 2026-01-04 08:00 | 2026-01-23 17:00 | 2025-12-30 08:00 | 2026-01-05 17:00 | 1 | 9.3 | Kilometer | 9 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4700 | Block-12 -HT Panel Erection | Completed | Task Dependent | 2026-01-04 08:00 | 2026-01-04 17:00 | 2025-12-29 08:00 | 2025-12-29 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1190 | Block-01 -IDT Erection | Completed | Task Dependent | 2026-01-05 08:00 | 2026-01-09 17:00 | 2026-01-09 08:00 | 2026-01-09 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7880 | Block-22 -LT Cable Laying | Completed | Task Dependent | 2026-01-05 08:00 | 2026-01-24 17:00 | 2026-01-02 08:00 | 2026-01-06 17:00 | 1 | 9.3 | Kilometer | 9 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8200 | Block-23 -LT Cable Laying | Completed | Task Dependent | 2026-01-06 08:00 | 2026-01-25 17:00 | 2026-01-09 08:00 | 2026-02-01 17:00 | 1 | 9.3 | Kilometer | 9 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4320 | Block-11 -NIFPS Foundation | Completed | Task Dependent | 2026-01-07 08:00 | 2026-01-16 17:00 | 2026-01-03 08:00 | 2026-01-04 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4330 | Block-11 -Aux Transformer Foundation | Completed | Task Dependent | 2026-01-07 08:00 | 2026-01-11 17:00 | 2026-01-03 08:00 | 2026-01-04 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7515 | Block-21 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-01-07 08:00 | 2026-01-15 17:00 | 2026-01-06 08:00 | 2026-01-15 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4325 | Block-11 -BOT Foundation | Completed | Task Dependent | 2026-01-07 08:00 | 2026-01-16 17:00 | 2026-01-02 08:00 | 2026-01-07 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7240 | Block-20 -LT Cable Laying | Completed | Task Dependent | 2026-01-09 08:00 | 2026-01-29 17:00 | 2026-01-09 08:00 | 2026-02-06 17:00 | 1 | 10.8 | Kilometer | 11 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7555 | Block-21 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-01-09 08:00 | 2026-01-13 17:00 | 2026-01-02 08:00 | 2026-03-02 17:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4305 | Block-11 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-01-09 08:00 | 2026-01-13 17:00 | 2026-01-07 08:00 | 2026-01-09 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1130 | Block-01 -BOT Foundation | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-19 17:00 | 2026-01-14 08:00 | 2026-01-20 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9430 | Block-27 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-11 17:00 | 2026-01-11 08:00 | 2026-01-11 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1740 | Block-03 -HT & LT Station - Slab | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-24 17:00 | 2026-01-10 08:00 | 2026-03-11 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7890 | Block-22 -FO Cable Laying | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-16 17:00 | 2026-01-13 08:00 | 2026-03-02 17:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4680 | Block-12 -LT Cable Laying | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-30 17:00 | 2025-12-20 08:00 | 2026-02-18 17:00 | 1 | 10.9 | Kilometer | 11 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7275 | Block-20 -Inverter Installation | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-16 17:00 | 2026-01-06 08:00 | 2026-04-06 10:00 | 1 | 96 | Number | 96 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7200 | Block-20 -NIFPS Foundation | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-19 17:00 | 2026-01-16 08:00 | 2026-01-16 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6275 | Block-17 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-14 17:00 | 2026-01-09 08:00 | 2026-02-19 17:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6860 | Block-19 -HT & LT Station - Slab | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-24 17:00 | 2026-01-11 08:00 | 2026-02-05 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6855 | Block-19 -IDT Foundation Up To Rail | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-31 17:00 | 2026-01-10 08:00 | 2026-01-30 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3655 | Block-09 -IDT Foundation Up To Rail | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-31 17:00 | 2026-01-10 08:00 | 2026-01-27 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7195 | Block-20 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-18 17:00 | 2026-01-02 08:00 | 2026-02-20 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5900 | Block-16 -HT & LT Station - Slab | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-24 17:00 | 2026-01-13 08:00 | 2026-02-26 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6300 | Block-17 -HT Panel Erection | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-10 17:00 | 2026-01-06 08:00 | 2026-01-06 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4630 | Block-12 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-11 17:00 | 2026-01-10 08:00 | 2026-01-10 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7210 | Block-20 -Aux Transformer Foundation | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-14 17:00 | 2026-01-16 08:00 | 2026-01-16 08:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4685 | Block-12 -HT Cable Laying | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-16 17:00 | 2026-01-12 08:00 | 2026-02-23 17:00 | 1 | 5.9 | Kilometer | 6 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3015 | Block-07 -IDT Foundation Up To Rail | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-31 17:00 | 2026-01-15 08:00 | 2026-02-13 17:00 | 1 | 3 | Number | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1120 | Block-01 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-18 17:00 | 2026-01-09 08:00 | 2026-01-13 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7260 | Block-20 -HT Panel Erection | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-10 17:00 | 2026-01-06 08:00 | 2026-01-06 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3335 | Block-08 -IDT Foundation Up To Rail | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-31 17:00 | 2026-01-13 08:00 | 2026-02-12 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9170 | Block-26 -FO Cable Laying | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-16 17:00 | 2026-01-10 08:00 | 2026-03-02 17:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4390 | Block-11 -IDT Erection | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-14 17:00 | 2026-01-10 08:00 | 2026-01-10 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1415 | Block-02 -IDT Foundation Up To Rail | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-31 17:00 | 2026-01-10 08:00 | 2026-02-03 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4310 | Block-11 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-11 17:00 | 2026-01-10 08:00 | 2026-01-10 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2765 | Block-06 -HT Cable Laying | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-16 17:00 | 2026-01-12 08:00 | 2026-03-18 17:00 | 1 | 5.9 | Kilometer | 6 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1165 | Block-01 -HT Cable Laying | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-16 17:00 | 2026-01-15 08:00 | 2026-02-23 17:00 | 1 | 5.6 | Kilometer | 6 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8195 | Block-23 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-01-11 08:00 | 2026-01-15 17:00 | 2026-01-12 08:00 | 2026-02-02 17:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4725 | Block-12 -ACDB Installation | Completed | Task Dependent | 2026-01-12 08:00 | 2026-01-13 17:00 | 2026-01-10 08:00 | 2026-01-10 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6315 | Block-17 -Inverter Installation | Completed | Task Dependent | 2026-01-12 08:00 | 2026-01-18 17:00 | 2026-01-05 08:00 | 2026-01-17 17:00 | 1 | 96 | Number | 96 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9525 | Block-27 -ACDB Installation | Completed | Task Dependent | 2026-01-12 08:00 | 2026-01-13 17:00 | 2026-01-12 08:00 | 2026-01-12 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6280 | Block-17 -LT Cable Laying | Completed | Task Dependent | 2026-01-12 08:00 | 2026-02-01 17:00 | 2026-01-03 08:00 | 2026-01-20 17:00 | 1 | 10.8 | Kilometer | 11 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4720 | Block-12 -SCADA & SACU Installation | Completed | Task Dependent | 2026-01-12 08:00 | 2026-01-13 17:00 | 2026-01-10 08:00 | 2026-01-10 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4705 | Block-12 -LT Panel Erection | Completed | Task Dependent | 2026-01-12 08:00 | 2026-01-17 17:00 | 2026-01-05 08:00 | 2026-01-12 17:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9505 | Block-27 -LT Panel Erection | Completed | Task Dependent | 2026-01-12 08:00 | 2026-01-17 17:00 | 2026-01-06 08:00 | 2026-01-24 17:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4395 | Block-11 -Inverter Installation | Completed | Task Dependent | 2026-01-14 08:00 | 2026-01-20 17:00 | 2026-01-14 08:00 | 2026-01-31 17:00 | 1 | 94 | Number | 94 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4380 | Block-11 -HT Panel Erection | Completed | Task Dependent | 2026-01-16 08:00 | 2026-01-16 17:00 | 2026-01-05 08:00 | 2026-01-05 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7835 | Block-22 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-01-17 08:00 | 2026-01-25 17:00 | 2026-01-23 08:00 | 2026-01-25 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1125 | Block-01 -NIFPS Foundation | Completed | Task Dependent | 2026-01-17 08:00 | 2026-01-27 17:00 | 2026-01-19 08:00 | 2026-01-19 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2375 | Block-05 -IDT Foundation Up To Rail | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-07 17:00 | 2026-01-23 08:00 | 2026-02-06 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5895 | Block-16 -IDT Foundation Up To Rail | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-07 17:00 | 2026-01-18 08:00 | 2026-02-08 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7530 | Block-21 -Aux Transformer Foundation | Completed | Task Dependent | 2026-01-17 08:00 | 2026-01-21 17:00 | 2026-01-21 08:00 | 2026-01-21 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1170 | Block-01 -FO Cable Laying | Completed | Task Dependent | 2026-01-17 08:00 | 2026-01-23 17:00 | 2026-01-17 08:00 | 2026-02-22 17:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4415 | Block-11 -NIFPS - Installation | Completed | Task Dependent | 2026-01-17 08:00 | 2026-01-23 17:00 | 2026-01-22 08:00 | 2026-01-22 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5030 | Block-13 -FO Cable Laying | Completed | Task Dependent | 2026-01-17 08:00 | 2026-01-23 17:00 | 2026-01-17 08:00 | 2026-02-23 17:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4070 | Block-10 -IDT Erection | Completed | Task Dependent | 2026-01-17 08:00 | 2026-01-21 17:00 | 2026-01-24 08:00 | 2026-01-24 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7520 | Block-21 -NIFPS Foundation | Completed | Task Dependent | 2026-01-17 08:00 | 2026-01-27 17:00 | 2026-01-21 08:00 | 2026-01-21 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3660 | Block-09 -HT & LT Station - Slab | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-01 17:00 | 2026-01-17 08:00 | 2026-01-26 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3995 | Block-10 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-01-17 08:00 | 2026-01-25 17:00 | 2026-01-15 08:00 | 2026-01-15 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5640 | Block-15 -LT Cable Laying | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-06 17:00 | 2026-01-01 08:00 | 2026-01-06 17:00 | 1 | 9.5 | Kilometer | 10 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1135 | Block-01 -Aux Transformer Foundation | Completed | Task Dependent | 2026-01-17 08:00 | 2026-01-21 17:00 | 2026-01-19 08:00 | 2026-01-19 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6225 | Block-17 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-01-17 08:00 | 2026-01-21 17:00 | 2026-01-19 08:00 | 2026-01-20 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4355 | Block-11 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-01-18 08:00 | 2026-01-22 17:00 | 2026-01-17 08:00 | 2026-02-19 17:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4360 | Block-11 -LT Cable Laying | Completed | Task Dependent | 2026-01-19 08:00 | 2026-02-08 17:00 | 2026-01-13 08:00 | 2026-01-27 17:00 | 1 | 9.2 | Kilometer | 9 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8155 | Block-23 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-01-20 08:00 | 2026-01-29 17:00 | 2026-01-13 08:00 | 2026-01-20 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4040 | Block-10 -LT Cable Laying | Completed | Task Dependent | 2026-01-24 08:00 | 2026-02-13 17:00 | 2026-01-26 08:00 | 2026-02-09 17:00 | 1 | 9.2 | Kilometer | 9 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9535 | Block-27 -NIFPS - Installation | Completed | Task Dependent | 2026-01-24 08:00 | 2026-01-31 17:00 | 2026-01-17 08:00 | 2026-01-17 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3090 | Block-07 -FO Cable Laying | Completed | Task Dependent | 2026-01-24 08:00 | 2026-01-31 17:00 | 2026-01-26 08:00 | 2026-01-27 17:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9520 | Block-27 -SCADA & SACU Installation | Completed | Task Dependent | 2026-01-24 08:00 | 2026-01-25 17:00 | 2026-01-25 08:00 | 2026-01-25 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4690 | Block-12 -FO Cable Laying | Completed | Task Dependent | 2026-01-24 08:00 | 2026-01-31 17:00 | 2026-01-27 08:00 | 2026-02-23 17:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1195 | Block-01 -Inverter Installation | Completed | Task Dependent | 2026-01-24 08:00 | 2026-01-31 17:00 | 2026-01-17 08:00 | 2026-02-02 17:00 | 1 | 94 | Number | 94 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4730 | Block-12 -Aux Transformer - Installation | Completed | Task Dependent | 2026-01-24 08:00 | 2026-01-28 17:00 | 2026-01-28 08:00 | 2026-01-28 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1180 | Block-01 -HT Panel Erection | Completed | Task Dependent | 2026-01-24 08:00 | 2026-01-24 17:00 | 2026-01-21 08:00 | 2026-01-21 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4385 | Block-11 -LT Panel Erection | Completed | Task Dependent | 2026-01-24 08:00 | 2026-01-30 17:00 | 2026-01-30 08:00 | 2026-01-30 17:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7590 | Block-21 -IDT Erection | Completed | Task Dependent | 2026-01-24 08:00 | 2026-01-29 17:00 | 2026-01-26 08:00 | 2026-01-26 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4400 | Block-11 -SCADA & SACU Installation | Completed | Task Dependent | 2026-01-24 08:00 | 2026-01-25 17:00 | 2026-01-30 08:00 | 2026-01-31 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7910 | Block-22 -IDT Erection | Completed | Task Dependent | 2026-01-24 08:00 | 2026-01-29 17:00 | 2026-01-26 08:00 | 2026-01-26 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7190 | Block-20 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-01-24 08:00 | 2026-01-25 17:00 | 2026-01-30 08:00 | 2026-01-30 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7840 | Block-22 -NIFPS Foundation | Completed | Task Dependent | 2026-01-24 08:00 | 2026-02-03 17:00 | 2026-01-29 08:00 | 2026-01-29 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4075 | Block-10 -Inverter Installation | Completed | Task Dependent | 2026-01-25 08:00 | 2026-02-01 17:00 | 2026-01-08 08:00 | 2026-03-23 17:00 | 1 | 94 | Number | 94 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6325 | Block-17 -ACDB Installation | Completed | Task Dependent | 2026-01-27 08:00 | 2026-01-28 17:00 | 2026-01-25 08:00 | 2026-01-25 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1215 | Block-01 -NIFPS - Installation | Completed | Task Dependent | 2026-01-27 08:00 | 2026-02-02 17:00 | 2026-01-25 08:00 | 2026-01-25 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6320 | Block-17 -SCADA & SACU Installation | Completed | Task Dependent | 2026-01-27 08:00 | 2026-01-28 17:00 | 2026-01-25 08:00 | 2026-01-25 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8230 | Block-23 -IDT Erection | Completed | Task Dependent | 2026-01-28 08:00 | 2026-02-01 17:00 | 2026-01-24 08:00 | 2026-01-24 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1155 | Block-01 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-01-28 08:00 | 2026-02-01 17:00 | 2026-01-28 08:00 | 2026-02-18 17:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1160 | Block-01 -LT Cable Laying | Completed | Task Dependent | 2026-01-28 08:00 | 2026-02-16 17:00 | 2026-01-20 08:00 | 2026-02-18 17:00 | 1 | 9.5 | Kilometer | 10 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4035 | Block-10 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-01-28 08:00 | 2026-02-01 17:00 | 2026-01-12 08:00 | 2026-03-27 17:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3675 | Block-09 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-01-29 08:00 | 2026-02-06 17:00 | 2026-01-21 08:00 | 2026-01-28 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6305 | Block-17 -LT Panel Erection | Completed | Task Dependent | 2026-01-29 08:00 | 2026-02-03 17:00 | 2026-01-25 08:00 | 2026-02-22 17:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6920 | Block-19 -LT Cable Laying | Completed | Task Dependent | 2026-01-29 08:00 | 2026-02-17 17:00 | 2026-01-19 08:00 | 2026-03-01 17:00 | 1 | 10.8 | Kilometer | 11 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6630 | Block-18 -IDT Erection | Completed | Task Dependent | 2026-01-30 08:00 | 2026-02-03 17:00 | 2026-01-30 08:00 | 2026-01-30 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3750 | Block-09 -IDT Erection | Completed | Task Dependent | 2026-01-30 08:00 | 2026-02-03 17:00 | 2026-01-29 08:00 | 2026-01-29 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3690 | Block-09 -Aux Transformer Foundation | Completed | Task Dependent | 2026-01-30 08:00 | 2026-02-03 17:00 | 2026-01-30 08:00 | 2026-01-30 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3680 | Block-09 -NIFPS Foundation | Completed | Task Dependent | 2026-01-30 08:00 | 2026-02-08 17:00 | 2026-01-29 08:00 | 2026-01-30 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6245 | Block-17 -BOT Foundation | Completed | Task Dependent | 2026-01-31 08:00 | 2026-02-09 17:00 | 2026-01-30 08:00 | 2026-02-05 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7580 | Block-21 -HT Panel Erection | Completed | Task Dependent | 2026-01-31 08:00 | 2026-01-31 17:00 | 2026-01-22 08:00 | 2026-01-22 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2380 | Block-05 -HT & LT Station - Slab | Completed | Task Dependent | 2026-01-31 08:00 | 2026-02-14 17:00 | 2026-01-24 08:00 | 2026-02-04 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3685 | Block-09 -BOT Foundation | Completed | Task Dependent | 2026-01-31 08:00 | 2026-02-09 17:00 | 2026-02-01 08:00 | 2026-02-05 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6950 | Block-19 -IDT Erection | Completed | Task Dependent | 2026-01-31 08:00 | 2026-02-04 17:00 | 2026-02-04 08:00 | 2026-02-05 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3980 | Block-10 -HT & LT Station - Slab | Completed | Task Dependent | 2026-01-31 08:00 | 2026-02-14 17:00 | 2026-02-04 08:00 | 2026-02-08 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7235 | Block-20 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-01-31 08:00 | 2026-02-04 17:00 | 2026-02-06 08:00 | 2026-03-23 17:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6915 | Block-19 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-02-01 08:00 | 2026-02-05 17:00 | 2026-01-27 08:00 | 2026-03-01 17:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6955 | Block-19 -Inverter Installation | Completed | Task Dependent | 2026-02-01 08:00 | 2026-02-07 17:00 | 2026-01-17 08:00 | 2026-04-07 10:00 | 1 | 96 | Number | 96 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5635 | Block-15 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-02-02 08:00 | 2026-02-06 17:00 | 2026-02-04 08:00 | 2026-03-04 17:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3395 | Block-08 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-02-03 08:00 | 2026-02-07 17:00 | 2026-01-30 08:00 | 2026-04-28 10:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5050 | Block-13 -IDT Erection | Completed | Task Dependent | 2026-02-04 08:00 | 2026-02-08 17:00 | 2026-02-04 08:00 | 2026-02-05 08:00 | 1 | 1 | Number | 270 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4990 | Block-13 -Aux Transformer Foundation | Completed | Task Dependent | 2026-02-04 08:00 | 2026-02-08 17:00 | 2026-02-03 08:00 | 2026-02-05 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4980 | Block-13 -NIFPS Foundation | Completed | Task Dependent | 2026-02-04 08:00 | 2026-02-13 17:00 | 2026-02-01 08:00 | 2026-02-05 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2795 | Block-06 -Inverter Installation | Completed | Task Dependent | 2026-02-05 08:00 | 2026-02-11 17:00 | 2026-01-22 08:00 | 2026-02-11 17:00 | 1 | 94 | Number | 94 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3355 | Block-08 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-02-05 08:00 | 2026-02-13 17:00 | 2026-01-28 08:00 | 2026-01-31 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3400 | Block-08 -LT Cable Laying | Completed | Task Dependent | 2026-02-05 08:00 | 2026-02-24 17:00 | 2026-01-28 08:00 | 2026-03-27 17:00 | 1 | 9.2 | Kilometer | 9 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3435 | Block-08 -Inverter Installation | Completed | Task Dependent | 2026-02-06 08:00 | 2026-02-12 17:00 | 2026-01-29 08:00 | 2026-04-07 12:00 | 1 | 94 | Number | 94 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2755 | Block-06 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-02-06 08:00 | 2026-02-10 17:00 | 2026-01-22 08:00 | 2026-03-20 17:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4745 | Block-12 -LT Cable Terminations - LT Panel to IDT | Completed | Task Dependent | 2026-02-06 08:00 | 2026-02-09 17:00 | 2026-02-04 08:00 | 2026-02-19 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2470 | Block-05 -IDT Erection | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-11 17:00 | 2026-02-09 08:00 | 2026-02-09 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1110 | Block-01 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-11 17:00 | 2026-02-12 08:00 | 2026-02-12 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6250 | Block-17 -Aux Transformer Foundation | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-11 17:00 | 2026-01-26 08:00 | 2026-01-26 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7845 | Block-22 -BOT Foundation | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-16 17:00 | 2026-02-01 08:00 | 2026-02-19 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6230 | Block-17 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-08 17:00 | 2026-02-13 08:00 | 2026-02-13 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2060 | Block-04 -HT & LT Station - Slab | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-21 17:00 | 2026-01-26 08:00 | 2026-02-11 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6240 | Block-17 -NIFPS Foundation | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-16 17:00 | 2026-01-25 08:00 | 2026-02-07 08:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9095 | Block-26 -IDT Foundation Up To Rail | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-27 17:00 | 2026-01-28 08:00 | 2026-02-15 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6600 | Block-18 -LT Cable Laying | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-26 17:00 | 2026-01-29 08:00 | 2026-03-27 17:00 | 1 | 10.8 | Kilometer | 11 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1510 | Block-02 -IDT Erection | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-11 17:00 | 2026-02-07 08:00 | 2026-02-07 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7615 | Block-21 -NIFPS - Installation | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-13 17:00 | 2026-02-11 08:00 | 2026-02-11 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4975 | Block-13 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-15 17:00 | 2026-02-07 08:00 | 2026-02-07 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7850 | Block-22 -Aux Transformer Foundation | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-11 17:00 | 2026-01-29 08:00 | 2026-02-11 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6570 | Block-18 -Aux Transformer Foundation | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-11 17:00 | 2026-02-09 08:00 | 2026-02-09 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5580 | Block-15 -HT & LT Station - Slab | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-21 17:00 | 2026-01-26 08:00 | 2026-02-18 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1435 | Block-02 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-15 17:00 | 2026-01-29 08:00 | 2026-01-29 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6565 | Block-18 -BOT Foundation | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-16 17:00 | 2026-02-15 08:00 | 2026-02-15 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3340 | Block-08 -HT & LT Station - Slab | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-21 17:00 | 2026-02-07 08:00 | 2026-02-15 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4670 | Block-12 -HT LT Station - Staircase | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-08 17:00 | 2026-02-16 08:00 | 2026-02-16 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6560 | Block-18 -NIFPS Foundation | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-16 17:00 | 2026-02-09 08:00 | 2026-02-11 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6875 | Block-19 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-15 17:00 | 2026-02-07 08:00 | 2026-02-18 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7525 | Block-21 -BOT Foundation | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-16 17:00 | 2026-01-28 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2055 | Block-04 -IDT Foundation Up To Rail | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-27 17:00 | 2026-01-30 08:00 | 2026-03-11 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9155 | Block-26 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-11 17:00 | 2026-02-11 08:00 | 2026-03-20 17:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4985 | Block-13 -BOT Foundation | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-16 17:00 | 2026-02-06 08:00 | 2026-02-18 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2700 | Block-06 -HT & LT Station - Slab | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-21 17:00 | 2026-01-24 08:00 | 2026-02-28 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8460 | Block-24 -HT & LT Station - Slab | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-21 17:00 | 2026-02-24 08:00 | 2026-03-05 17:00 | 1 | 2 | Number | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1475 | Block-02 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-11 17:00 | 2026-02-08 08:00 | 2026-03-15 17:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4405 | Block-11 -ACDB Installation | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-08 17:00 | 2026-01-30 08:00 | 2026-01-30 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6555 | Block-18 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-15 17:00 | 2026-02-09 08:00 | 2026-02-11 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2395 | Block-05 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-15 17:00 | 2026-02-08 08:00 | 2026-02-09 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8530 | Block-24 -FO Cable Laying | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-13 17:00 | 2026-02-13 08:00 | 2026-04-12 10:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2790 | Block-06 -IDT Erection | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-11 17:00 | 2026-02-07 08:00 | 2026-02-07 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4410 | Block-11 -Aux Transformer - Installation | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-10 17:00 | 2026-02-11 08:00 | 2026-02-11 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8220 | Block-23 -HT Panel Erection | Completed | Task Dependent | 2026-02-09 08:00 | 2026-02-09 17:00 | 2026-02-01 08:00 | 2026-02-01 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6865 | Block-19 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-02-09 08:00 | 2026-02-13 17:00 | 2026-03-11 08:00 | 2026-03-11 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2760 | Block-06 -LT Cable Laying | Completed | Task Dependent | 2026-02-10 08:00 | 2026-03-01 17:00 | 2026-01-20 08:00 | 2026-02-11 17:00 | 1 | 9.2 | Kilometer | 9 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6595 | Block-18 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-02-11 08:00 | 2026-02-15 17:00 | 2026-01-31 08:00 | 2026-04-28 11:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1830 | Block-03 -IDT Erection | Completed | Task Dependent | 2026-02-11 08:00 | 2026-02-15 17:00 | 2026-02-06 08:00 | 2026-02-06 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1480 | Block-02 -LT Cable Laying | Completed | Task Dependent | 2026-02-11 08:00 | 2026-03-02 17:00 | 2026-02-07 08:00 | 2026-02-07 17:00 | 1 | 5.3 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1115 | Block-01 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-02-12 08:00 | 2026-02-13 17:00 | 2026-02-13 08:00 | 2026-02-13 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5670 | Block-15 -IDT Erection | Completed | Task Dependent | 2026-02-12 08:00 | 2026-02-16 17:00 | 2026-02-15 08:00 | 2026-02-15 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8520 | Block-24 -LT Cable Laying | Completed | Task Dependent | 2026-02-13 08:00 | 2026-03-04 17:00 | 2026-02-11 08:00 | 2026-03-01 17:00 | 1 | 10.6 | Kilometer | 11 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6335 | Block-17 -NIFPS - Installation | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-20 17:00 | 2026-02-18 08:00 | 2026-02-18 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4695 | Block-12 -Control Cable Laying | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-16 17:00 | 2026-02-18 08:00 | 2026-02-19 17:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9195 | Block-26 -Inverter Installation | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-20 17:00 | 2026-02-11 08:00 | 2026-02-13 17:00 | 1 | 94 | Number | 94 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5595 | Block-15 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-22 17:00 | 2026-02-20 08:00 | 2026-02-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5600 | Block-15 -NIFPS Foundation | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-23 17:00 | 2026-02-19 08:00 | 2026-02-20 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5605 | Block-15 -BOT Foundation | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-23 17:00 | 2026-02-19 08:00 | 2026-02-20 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5350 | Block-14 -IDT Erection | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-18 17:00 | 2026-02-13 08:00 | 2026-02-13 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5610 | Block-15 -Aux Transformer Foundation | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-18 17:00 | 2026-02-19 08:00 | 2026-02-20 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5075 | Block-13 -NIFPS - Installation | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-20 17:00 | 2026-02-18 08:00 | 2026-02-18 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5070 | Block-13 -Aux Transformer - Installation | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-17 17:00 | 2026-02-18 08:00 | 2026-02-18 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5010 | Block-13 -HT LT Station - Staircase | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-15 17:00 | 2026-02-18 08:00 | 2026-02-18 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6590 | Block-18 -HT LT Station - Staircase | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-15 17:00 | 2026-02-18 08:00 | 2026-02-18 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8475 | Block-24 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-22 17:00 | 2026-02-14 08:00 | 2026-02-18 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1500 | Block-02 -HT Panel Erection | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-14 17:00 | 2026-02-09 08:00 | 2026-02-09 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6890 | Block-19 -Aux Transformer Foundation | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-18 17:00 | 2026-02-16 08:00 | 2026-02-16 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4965 | Block-13 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-18 17:00 | 2026-02-17 08:00 | 2026-02-17 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7935 | Block-22 -NIFPS - Installation | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-20 17:00 | 2026-02-19 08:00 | 2026-02-19 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1200 | Block-01 -SCADA & SACU Installation | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-15 17:00 | 2026-02-13 08:00 | 2026-02-13 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1105 | Block-01 -HT LT Station - Staircase | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-15 17:00 | 2026-02-18 08:00 | 2026-02-18 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3110 | Block-07 -IDT Erection | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-18 17:00 | 2026-02-17 08:00 | 2026-02-17 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9100 | Block-26 -HT & LT Station - Slab | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-28 17:00 | 2026-02-13 08:00 | 2026-02-18 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6880 | Block-19 -NIFPS Foundation | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-23 17:00 | 2026-02-16 08:00 | 2026-02-16 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1210 | Block-01 -Aux Transformer - Installation | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-17 17:00 | 2026-02-18 08:00 | 2026-02-18 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1205 | Block-01 -ACDB Installation | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-15 17:00 | 2026-02-13 08:00 | 2026-02-13 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1175 | Block-01 -Control Cable Laying | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-16 17:00 | 2026-02-18 08:00 | 2026-02-18 17:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4425 | Block-11 -LT Cable Terminations - LT Panel to IDT | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-17 17:00 | 2026-02-19 08:00 | 2026-02-19 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8515 | Block-24 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-18 17:00 | 2026-02-16 08:00 | 2026-03-30 10:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8555 | Block-24 -Inverter Installation | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-20 17:00 | 2026-02-07 08:00 | 2026-03-01 17:00 | 1 | 94 | Number | 94 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4375 | Block-11 -Control Cable Laying | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-16 17:00 | 2026-02-19 08:00 | 2026-02-19 17:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4350 | Block-11 -HT LT Station - Staircase | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-15 17:00 | 2026-02-19 08:00 | 2026-02-19 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3430 | Block-08 -IDT Erection | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-18 17:00 | 2026-02-16 08:00 | 2026-02-16 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9545 | Block-27 -LT Cable Terminations - LT Panel to IDT | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-17 17:00 | 2026-02-19 08:00 | 2026-03-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6345 | Block-17 -LT Cable Terminations - LT Panel to IDT | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-17 17:00 | 2026-02-19 08:00 | 2026-02-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6330 | Block-17 -Aux Transformer - Installation | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-17 17:00 | 2026-02-19 08:00 | 2026-02-19 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4430 | Block-11 -LT Cable Terminations - Inverter to LT Panel | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-17 17:00 | 2026-02-19 08:00 | 2026-02-19 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4735 | Block-12 -NIFPS - Installation | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-20 17:00 | 2026-02-18 08:00 | 2026-02-18 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5990 | Block-16 -IDT Erection | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-18 17:00 | 2026-02-14 08:00 | 2026-02-14 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7570 | Block-21 -FO Cable Laying | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-20 17:00 | 2026-02-13 08:00 | 2026-04-12 10:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6270 | Block-17 -HT LT Station - Staircase | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-15 17:00 | 2026-02-18 08:00 | 2026-02-18 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4655 | Block-12 -IDT Area - Fencing | Completed | Task Dependent | 2026-02-15 08:00 | 2026-02-19 17:00 | 2026-02-16 08:00 | 2026-02-16 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9160 | Block-26 -LT Cable Laying | Completed | Task Dependent | 2026-02-15 08:00 | 2026-03-06 17:00 | 2026-01-30 08:00 | 2026-03-01 17:00 | 1 | 9.1 | Kilometer | 9 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7930 | Block-22 -Aux Transformer - Installation | Completed | Task Dependent | 2026-02-15 08:00 | 2026-02-18 17:00 | 2026-02-19 08:00 | 2026-02-19 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7825 | Block-22 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-02-15 08:00 | 2026-02-19 17:00 | 2026-02-05 08:00 | 2026-02-19 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1185 | Block-01 -LT Panel Erection | Completed | Task Dependent | 2026-02-16 08:00 | 2026-02-21 17:00 | 2026-02-13 08:00 | 2026-02-13 17:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6940 | Block-19 -HT Panel Erection | Completed | Task Dependent | 2026-02-16 08:00 | 2026-02-16 17:00 | 2026-02-16 08:00 | 2026-02-16 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1230 | Block-01 -LT Cable Terminations - Inverter To LT Panel | Completed | Task Dependent | 2026-02-17 08:00 | 2026-02-23 17:00 | 2026-02-19 08:00 | 2026-02-19 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1225 | Block-01 -LT Cable Terminations - LT Panel To IDT | Completed | Task Dependent | 2026-02-17 08:00 | 2026-02-23 17:00 | 2026-02-19 08:00 | 2026-02-19 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1140 | Block-01 -IDT Area - Fencing | Completed | Task Dependent | 2026-02-18 08:00 | 2026-02-22 17:00 | 2026-02-19 08:00 | 2026-02-19 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7905 | Block-22 -LT Panel Erection | Completed | Task Dependent | 2026-02-18 08:00 | 2026-02-23 17:00 | 2026-02-20 08:00 | 2026-02-20 17:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5915 | Block-16 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-02-18 08:00 | 2026-02-26 17:00 | 2026-02-14 08:00 | 2026-02-18 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5675 | Block-15 -Inverter Installation | Completed | Task Dependent | 2026-02-18 08:00 | 2026-02-24 17:00 | 2026-02-02 08:00 | 2026-02-07 17:00 | 1 | 94 | Number | 94 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4970 | Block-13 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-02-19 08:00 | 2026-02-20 17:00 | 2026-02-17 08:00 | 2026-02-18 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4750 | Block-12 -LT Cable Terminations - Inverter to LT Panel | Completed | Task Dependent | 2026-02-20 08:00 | 2026-02-23 17:00 | 2026-02-19 08:00 | 2026-02-19 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4660 | Block-12 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-02-20 08:00 | 2026-02-21 17:00 | 2026-02-16 08:00 | 2026-02-16 08:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5060 | Block-13 -SCADA & SACU Installation | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-22 17:00 | 2026-02-18 08:00 | 2026-02-19 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1440 | Block-02 -NIFPS Foundation | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-02 17:00 | 2026-02-24 08:00 | 2026-02-24 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2715 | Block-06 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-01 17:00 | 2026-02-20 08:00 | 2026-02-26 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4370 | Block-11 -FO Cable Laying | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-27 17:00 | 2026-02-21 08:00 | 2026-02-22 17:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6610 | Block-18 -FO Cable Laying | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-27 17:00 | 2026-02-21 08:00 | 2026-04-12 10:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2400 | Block-05 -NIFPS Foundation | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-02 17:00 | 2026-02-24 08:00 | 2026-02-24 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5925 | Block-16 -BOT Foundation | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-02 17:00 | 2026-02-22 08:00 | 2026-02-26 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5920 | Block-16 -NIFPS Foundation | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-02 17:00 | 2026-02-27 08:00 | 2026-02-27 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5005 | Block-13 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-23 17:00 | 2026-02-24 08:00 | 2026-02-25 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4050 | Block-10 -FO Cable Laying | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-27 17:00 | 2026-02-21 08:00 | 2026-03-23 17:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5930 | Block-16 -Aux Transformer Foundation | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-25 17:00 | 2026-02-27 08:00 | 2026-02-27 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2460 | Block-05 -HT Panel Erection | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-21 17:00 | 2026-02-18 08:00 | 2026-02-18 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6290 | Block-17 -FO Cable Laying | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-27 17:00 | 2026-02-21 08:00 | 2026-03-02 17:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4665 | Block-12 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-23 17:00 | 2026-02-16 08:00 | 2026-02-16 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8775 | Block-25 -IDT Foundation Up To Rail | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-13 17:00 | 2026-02-22 08:00 | 2026-02-26 17:00 | 1 | 3 | Number | 3 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1450 | Block-02 -Aux Transformer Foundation | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-25 17:00 | 2026-02-24 08:00 | 2026-02-24 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8480 | Block-24 -NIFPS Foundation | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-02 17:00 | 2026-02-26 08:00 | 2026-02-26 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4010 | Block-10 -Aux Transformer Foundation | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-25 17:00 | 2026-02-24 08:00 | 2026-02-24 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1490 | Block-02 -FO Cable Laying | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-27 17:00 | 2026-02-26 08:00 | 2026-03-20 17:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3755 | Block-09 -Inverter Installation | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-27 17:00 | 2026-02-26 08:00 | 2026-03-08 17:00 | 1 | 94 | Number | 94 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8780 | Block-25 -HT & LT Station - Slab | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-07 17:00 | 2026-02-22 08:00 | 2026-02-27 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2410 | Block-05 -Aux Transformer Foundation | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-25 17:00 | 2026-02-24 08:00 | 2026-02-24 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5650 | Block-15 -FO Cable Laying | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-27 17:00 | 2026-02-21 08:00 | 2026-03-02 17:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8490 | Block-24 -Aux Transformer Foundation | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-25 17:00 | 2026-02-26 08:00 | 2026-02-26 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1810 | Block-03 -FO Cable Laying | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-27 17:00 | 2026-02-26 08:00 | 2026-04-20 12:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4000 | Block-10 -NIFPS Foundation | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-02 17:00 | 2026-02-24 08:00 | 2026-02-24 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6295 | Block-17 -Control Cable Laying | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-23 17:00 | 2026-02-23 08:00 | 2026-02-23 17:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5065 | Block-13 -ACDB Installation | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-22 17:00 | 2026-02-19 08:00 | 2026-02-19 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5035 | Block-13 -Control Cable Laying | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-23 17:00 | 2026-02-18 08:00 | 2026-02-19 17:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9130 | Block-26 -Aux Transformer Foundation | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-25 17:00 | 2026-02-26 08:00 | 2026-02-26 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4345 | Block-11 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-23 17:00 | 2026-02-24 08:00 | 2026-02-25 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3715 | Block-09 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-25 17:00 | 2026-02-26 08:00 | 2026-02-27 17:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7830 | Block-22 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-22 17:00 | 2026-02-24 08:00 | 2026-02-24 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1150 | Block-01 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-23 17:00 | 2026-02-24 08:00 | 2026-02-25 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5040 | Block-13 -HT Panel Erection | Completed | Task Dependent | 2026-02-21 08:00 | 2026-02-21 17:00 | 2026-02-17 08:00 | 2026-02-17 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9120 | Block-26 -NIFPS Foundation | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-02 17:00 | 2026-02-26 08:00 | 2026-02-26 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4335 | Block-11 -IDT Area - Fencing | Completed | Task Dependent | 2026-02-22 08:00 | 2026-02-26 17:00 | 2026-02-24 08:00 | 2026-02-25 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7215 | Block-20 -IDT Area - Fencing | Completed | Task Dependent | 2026-02-22 08:00 | 2026-02-26 17:00 | 2026-04-12 08:00 | 2026-04-12 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4740 | Block-12 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-02-22 08:00 | 2026-02-23 17:00 | 2026-02-21 08:00 | 2026-02-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5080 | Block-13 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-02-22 08:00 | 2026-02-23 17:00 | 2026-02-21 08:00 | 2026-02-22 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7900 | Block-22 -HT Panel Erection | Completed | Task Dependent | 2026-02-22 08:00 | 2026-02-22 17:00 | 2026-02-04 08:00 | 2026-02-04 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5585 | Block-15 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-02-22 08:00 | 2026-02-26 17:00 | 2026-02-24 08:00 | 2026-02-24 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4995 | Block-13 -IDT Area - Fencing | Completed | Task Dependent | 2026-02-22 08:00 | 2026-02-26 17:00 | 2026-02-24 08:00 | 2026-02-24 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5630 | Block-15 -HT LT Station - Staircase | Completed | Task Dependent | 2026-02-22 08:00 | 2026-02-23 17:00 | 2026-02-23 08:00 | 2026-02-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3720 | Block-09 -LT Cable Laying | Completed | Task Dependent | 2026-02-23 08:00 | 2026-03-14 17:00 | 2026-02-26 08:00 | 2026-02-27 17:00 | 1 | 12.5 | Kilometer | 13 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1145 | Block-01 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-02-23 08:00 | 2026-02-23 17:00 | 2026-02-19 08:00 | 2026-02-19 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7920 | Block-22 -SCADA & SACU Installation | Completed | Task Dependent | 2026-02-23 08:00 | 2026-02-24 17:00 | 2026-02-21 08:00 | 2026-02-21 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5045 | Block-13 -LT Panel Erection | Completed | Task Dependent | 2026-02-23 08:00 | 2026-02-28 17:00 | 2026-02-18 08:00 | 2026-02-18 17:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7925 | Block-22 -ACDB Installation | Completed | Task Dependent | 2026-02-23 08:00 | 2026-02-24 17:00 | 2026-02-22 08:00 | 2026-02-22 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9540 | Block-27 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-02-24 08:00 | 2026-02-25 17:00 | 2026-02-21 08:00 | 2026-02-26 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1220 | Block-01 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-02-24 08:00 | 2026-02-25 17:00 | 2026-02-21 08:00 | 2026-02-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5690 | Block-15 -Aux Transformer - Installation | Completed | Task Dependent | 2026-02-24 08:00 | 2026-02-27 17:00 | 2026-02-25 08:00 | 2026-02-25 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6255 | Block-17 -IDT Area - Fencing | Completed | Task Dependent | 2026-02-25 08:00 | 2026-03-01 17:00 | 2026-02-23 08:00 | 2026-02-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7940 | Block-22 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-02-25 08:00 | 2026-02-26 17:00 | 2026-02-21 08:00 | 2026-02-26 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5085 | Block-13 -LT Cable Terminations - LT Panel to IDT | Completed | Task Dependent | 2026-02-26 08:00 | 2026-03-01 17:00 | 2026-02-19 08:00 | 2026-02-19 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5090 | Block-13 -LT Cable Terminations - Inverter to LT Panel | Completed | Task Dependent | 2026-02-26 08:00 | 2026-03-01 17:00 | 2026-02-19 08:00 | 2026-02-19 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5695 | Block-15 -NIFPS - Installation | Completed | Task Dependent | 2026-02-27 08:00 | 2026-03-05 17:00 | 2026-02-22 08:00 | 2026-02-22 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5590 | Block-15 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-02-27 08:00 | 2026-02-28 17:00 | 2026-02-24 08:00 | 2026-02-24 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4340 | Block-11 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-02-27 08:00 | 2026-02-28 17:00 | 2026-02-24 08:00 | 2026-02-24 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2450 | Block-05 -FO Cable Laying | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-06 17:00 | 2026-03-02 08:00 | 2026-03-20 17:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5970 | Block-16 -FO Cable Laying | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-06 17:00 | 2026-03-02 08:00 | 2026-04-12 12:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3365 | Block-08 -BOT Foundation | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-09 17:00 | 2026-02-27 08:00 | 2026-02-28 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1425 | Block-02 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-04 17:00 | 2026-03-02 08:00 | 2026-03-02 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4420 | Block-11 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-01 17:00 | 2026-02-21 08:00 | 2026-02-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5620 | Block-15 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-01 17:00 | 2026-03-06 08:00 | 2026-03-06 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5685 | Block-15 -ACDB Installation | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-01 17:00 | 2026-03-03 08:00 | 2026-03-03 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5655 | Block-15 -Control Cable Laying | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-02 17:00 | 2026-03-03 08:00 | 2026-03-03 17:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9550 | Block-27 -LT Cable Terminations - Inverter to LT Panel | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-03 17:00 | 2026-03-01 08:00 | 2026-03-01 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8145 | Block-23 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-04 17:00 | 2026-03-03 08:00 | 2026-03-03 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8850 | Block-25 -FO Cable Laying | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-06 17:00 | 2026-03-02 08:00 | 2026-03-20 17:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1445 | Block-02 -BOT Foundation | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-09 17:00 | 2026-03-05 08:00 | 2026-03-05 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6350 | Block-17 -LT Cable Terminations - Inverter to LT Panel | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-03 17:00 | 2026-03-01 08:00 | 2026-03-01 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9470 | Block-27 -HT LT Station - Staircase | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-01 17:00 | 2026-03-03 08:00 | 2026-03-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9495 | Block-27 -Control Cable Laying | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-02 17:00 | 2026-03-02 08:00 | 2026-03-04 08:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7870 | Block-22 -HT LT Station - Staircase | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-01 17:00 | 2026-02-28 08:00 | 2026-02-28 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8550 | Block-24 -IDT Erection | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-04 17:00 | 2026-03-02 08:00 | 2026-03-02 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3410 | Block-08 -FO Cable Laying | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-06 17:00 | 2026-03-02 08:00 | 2026-04-12 10:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1755 | Block-03 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-08 17:00 | 2026-02-27 08:00 | 2026-03-02 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7945 | Block-22 -LT Cable Terminations - LT Panel to IDT | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-03 17:00 | 2026-03-03 08:00 | 2026-03-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7860 | Block-22 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-01 17:00 | 2026-03-06 08:00 | 2026-03-06 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7895 | Block-22 -Control Cable Laying | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-02 17:00 | 2026-03-03 08:00 | 2026-03-03 17:00 | 1 | 0.74 | Kilometer | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7250 | Block-20 -FO Cable Laying | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-06 17:00 | 2026-03-02 08:00 | 2026-04-12 10:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2770 | Block-06 -FO Cable Laying | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-06 17:00 | 2026-03-02 08:00 | 2026-03-20 17:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5330 | Block-14 -FO Cable Laying | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-06 17:00 | 2026-03-02 08:00 | 2026-04-12 12:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6340 | Block-17 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-01 17:00 | 2026-02-21 08:00 | 2026-02-21 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8805 | Block-25 -BOT Foundation | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-09 17:00 | 2026-02-24 08:00 | 2026-02-28 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3730 | Block-09 -FO Cable Laying | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-06 17:00 | 2026-03-02 08:00 | 2026-03-23 17:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8210 | Block-23 -FO Cable Laying | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-06 17:00 | 2026-03-02 08:00 | 2026-03-23 17:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7950 | Block-22 -LT Cable Terminations - Inverter to LT Panel | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-03 17:00 | 2026-03-04 08:00 | 2026-03-04 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7505 | Block-21 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-04 17:00 | 2026-03-02 08:00 | 2026-03-02 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6265 | Block-17 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-02 17:00 | 2026-03-04 08:00 | 2026-03-04 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3740 | Block-09 -HT Panel Erection | Completed | Task Dependent | 2026-02-28 08:00 | 2026-02-28 17:00 | 2026-02-26 08:00 | 2026-02-26 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5705 | Block-15 -LT Cable Terminations - LT Panel to IDT | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-03 17:00 | 2026-03-03 08:00 | 2026-03-04 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6930 | Block-19 -FO Cable Laying | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-06 17:00 | 2026-03-02 08:00 | 2026-03-23 17:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2130 | Block-04 -FO Cable Laying | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-06 17:00 | 2026-03-02 08:00 | 2026-04-20 12:00 | 1 | 1.1 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3985 | Block-10 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-04 17:00 | 2026-03-06 08:00 | 2026-03-06 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9455 | Block-27 -IDT Area - Fencing | Completed | Task Dependent | 2026-03-01 08:00 | 2026-03-05 17:00 | 2026-03-06 08:00 | 2026-03-06 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5660 | Block-15 -HT Panel Erection | Completed | Task Dependent | 2026-03-01 08:00 | 2026-03-01 17:00 | 2026-02-25 08:00 | 2026-02-25 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2705 | Block-06 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-03-01 08:00 | 2026-03-05 17:00 | 2026-03-06 08:00 | 2026-03-06 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5680 | Block-15 -SCADA & SACU Installation | Completed | Task Dependent | 2026-03-01 08:00 | 2026-03-02 17:00 | 2026-02-26 08:00 | 2026-02-26 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6260 | Block-17 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-03-02 08:00 | 2026-03-03 17:00 | 2026-02-23 08:00 | 2026-02-23 08:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5700 | Block-15 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-03-02 08:00 | 2026-03-03 17:00 | 2026-02-21 08:00 | 2026-03-04 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9465 | Block-27 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-03-02 08:00 | 2026-03-04 17:00 | 2026-03-04 08:00 | 2026-03-04 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7865 | Block-22 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-03-03 08:00 | 2026-03-05 17:00 | 2026-03-03 08:00 | 2026-03-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5665 | Block-15 -LT Panel Erection | Completed | Task Dependent | 2026-03-03 08:00 | 2026-03-08 17:00 | 2026-02-25 08:00 | 2026-02-25 17:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9190 | Block-26 -IDT Erection | Completed | Task Dependent | 2026-03-03 08:00 | 2026-03-07 17:00 | 2026-02-17 08:00 | 2026-02-17 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5625 | Block-15 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-03-03 08:00 | 2026-03-05 17:00 | 2026-03-03 08:00 | 2026-03-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7855 | Block-22 -IDT Area - Fencing | Completed | Task Dependent | 2026-03-04 08:00 | 2026-03-08 17:00 | 2026-03-03 08:00 | 2026-03-03 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5615 | Block-15 -IDT Area - Fencing | Completed | Task Dependent | 2026-03-04 08:00 | 2026-03-08 17:00 | 2026-03-03 08:00 | 2026-03-03 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7585 | Block-21 -LT Panel Erection | Completed | Task Dependent | 2026-03-04 08:00 | 2026-03-09 17:00 | 2026-03-05 08:00 | 2026-03-05 17:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5710 | Block-15 -LT Cable Terminations - Inverter to LT Panel | Completed | Task Dependent | 2026-03-06 08:00 | 2026-03-09 17:00 | 2026-02-26 08:00 | 2026-03-02 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9460 | Block-27 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-03-06 08:00 | 2026-03-07 17:00 | 2026-03-06 08:00 | 2026-03-06 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5000 | Block-13 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-08 17:00 | 2026-02-18 08:00 | 2026-02-18 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9115 | Block-26 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-15 17:00 | 2026-03-12 08:00 | 2026-03-12 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1470 | Block-02 -HT LT Station - Staircase | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-08 17:00 | 2026-03-12 08:00 | 2026-03-12 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3775 | Block-09 -NIFPS - Installation | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-13 17:00 | 2026-03-13 08:00 | 2026-03-13 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3045 | Block-07 -BOT Foundation | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-16 17:00 | 2026-02-22 08:00 | 2026-03-09 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1535 | Block-02 -NIFPS - Installation | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-13 17:00 | 2026-03-12 08:00 | 2026-03-12 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3100 | Block-07 -HT Panel Erection | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-07 17:00 | 2026-03-02 08:00 | 2026-03-02 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1430 | Block-02 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-08 17:00 | 2026-03-07 08:00 | 2026-03-07 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2720 | Block-06 -NIFPS Foundation | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-11 17:00 | 2026-03-11 08:00 | 2026-03-11 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2385 | Block-05 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-11 17:00 | 2026-03-11 08:00 | 2026-03-11 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9215 | Block-26 -NIFPS - Installation | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-13 17:00 | 2026-03-12 08:00 | 2026-03-12 17:00 | 1 | 1 | Number | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7600 | Block-21 -SCADA & SACU Installation | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-08 17:00 | 2026-03-02 08:00 | 2026-03-02 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9105 | Block-26 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-11 17:00 | 2026-03-12 08:00 | 2026-03-12 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3025 | Block-07 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-11 17:00 | 2026-03-12 08:00 | 2026-03-12 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2750 | Block-06 -HT LT Station - Staircase | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-08 17:00 | 2026-03-13 08:00 | 2026-03-13 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9150 | Block-26 -HT LT Station - Staircase | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-08 17:00 | 2026-03-13 08:00 | 2026-03-13 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3665 | Block-09 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-11 17:00 | 2026-02-25 08:00 | 2026-03-13 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3345 | Block-08 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-11 17:00 | 2026-03-12 08:00 | 2026-03-12 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7605 | Block-21 -ACDB Installation | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-08 17:00 | 2026-03-02 08:00 | 2026-03-02 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9210 | Block-26 -Aux Transformer - Installation | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-10 17:00 | 2026-03-12 08:00 | 2026-03-12 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8830 | Block-25 -HT LT Station - Staircase | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-08 17:00 | 2026-03-13 08:00 | 2026-03-13 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2435 | Block-05 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-11 17:00 | 2026-03-10 08:00 | 2026-03-10 17:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6620 | Block-18 -HT Panel Erection | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-07 17:00 | 2026-03-02 08:00 | 2026-03-02 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2475 | Block-05 -Inverter Installation | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-13 17:00 | 2026-03-09 08:00 | 2026-03-09 17:00 | 1 | 94 | Number | 94 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5260 | Block-14 -HT & LT Station - Slab | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-21 17:00 | 2026-03-02 08:00 | 2026-03-12 17:00 | 1 | 2 | Number | 2 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3990 | Block-10 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-08 17:00 | 2026-03-12 08:00 | 2026-03-12 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4060 | Block-10 -HT Panel Erection | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-07 17:00 | 2026-03-02 08:00 | 2026-03-02 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3420 | Block-08 -HT Panel Erection | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-07 17:00 | 2026-03-02 08:00 | 2026-03-02 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2730 | Block-06 -Aux Transformer Foundation | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-11 17:00 | 2026-03-11 08:00 | 2026-03-11 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8785 | Block-25 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-11 17:00 | 2026-03-11 08:00 | 2026-03-11 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1515 | Block-02 -Inverter Installation | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-13 17:00 | 2026-03-10 08:00 | 2026-03-15 17:00 | 1 | 60 | Number | 60 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2155 | Block-04 -Inverter Installation | Completed | Task Dependent | 2026-03-09 08:00 | 2026-03-15 17:00 | 2026-02-26 08:00 | 2026-04-17 10:00 | 1 | 94 | Number | 94 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5980 | Block-16 -HT Panel Erection | Completed | Task Dependent | 2026-03-09 08:00 | 2026-03-09 17:00 | 2026-03-02 08:00 | 2026-03-02 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2495 | Block-05 -NIFPS - Installation | Completed | Task Dependent | 2026-03-09 08:00 | 2026-03-15 17:00 | 2026-02-27 08:00 | 2026-02-27 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8860 | Block-25 -HT Panel Erection | Completed | Task Dependent | 2026-03-10 08:00 | 2026-03-10 17:00 | 2026-03-06 08:00 | 2026-03-06 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6885 | Block-19 -BOT Foundation | Completed | Task Dependent | 2026-03-10 08:00 | 2026-03-19 17:00 | 2026-03-10 08:00 | 2026-03-10 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1505 | Block-02 -LT Panel Erection | Completed | Task Dependent | 2026-03-11 08:00 | 2026-03-16 17:00 | 2026-03-12 08:00 | 2026-03-17 17:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2780 | Block-06 -HT Panel Erection | Completed | Task Dependent | 2026-03-11 08:00 | 2026-03-11 17:00 | 2026-03-02 08:00 | 2026-03-02 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9180 | Block-26 -HT Panel Erection | Completed | Task Dependent | 2026-03-11 08:00 | 2026-03-11 17:00 | 2026-02-19 08:00 | 2026-02-19 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2440 | Block-05 -LT Cable Laying | Completed | Task Dependent | 2026-03-11 08:00 | 2026-03-30 17:00 | 2026-03-10 08:00 | 2026-03-11 17:00 | 1 | 10 | Kilometer | 10 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2115 | Block-04 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-03-12 08:00 | 2026-03-16 17:00 | 2026-02-26 08:00 | 2026-04-28 15:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7625 | Block-21 -LT Cable Terminations - LT Panel to IDT | Completed | Task Dependent | 2026-03-12 08:00 | 2026-03-15 17:00 | 2026-03-02 08:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7630 | Block-21 -LT Cable Terminations - Inverter to LT Panel | Completed | Task Dependent | 2026-03-12 08:00 | 2026-03-15 17:00 | 2026-03-02 08:00 | 2026-03-04 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8835 | Block-25 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-03-12 08:00 | 2026-03-16 17:00 | 2026-03-12 08:00 | 2026-03-20 17:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3350 | Block-08 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-03-12 08:00 | 2026-03-13 17:00 | 2026-03-12 08:00 | 2026-03-12 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9225 | Block-26 -LT Cable Terminations - LT Panel to IDT | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-17 17:00 | 2026-03-15 08:00 | 2026-03-16 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8905 | Block-25 -LT Cable Terminations - LT Panel to IDT | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-17 17:00 | 2026-03-20 08:00 | 2026-03-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1550 | Block-02 -LT Cable Terminations - Inverter To LT Panel | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-20 17:00 | 2026-03-15 08:00 | 2026-03-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1520 | Block-02 -SCADA & SACU Installation | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-15 17:00 | 2026-03-15 08:00 | 2026-03-15 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9205 | Block-26 -ACDB Installation | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-15 17:00 | 2026-03-09 08:00 | 2026-03-09 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2405 | Block-05 -BOT Foundation | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-23 17:00 | 2026-03-15 08:00 | 2026-03-15 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8840 | Block-25 -LT Cable Laying | Completed | Task Dependent | 2026-03-14 08:00 | 2026-04-03 12:00 | 2026-03-10 08:00 | 2026-03-14 17:00 | 1 | 12.2 | Kilometer | 12 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5285 | Block-14 -BOT Foundation | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-23 17:00 | 2026-03-15 08:00 | 2026-03-16 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9230 | Block-26 -LT Cable Terminations - Inverter to LT Panel | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-17 17:00 | 2026-03-16 08:00 | 2026-03-17 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3760 | Block-09 -SCADA & SACU Installation | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-15 17:00 | 2026-03-13 08:00 | 2026-03-13 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9200 | Block-26 -SCADA & SACU Installation | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-15 17:00 | 2026-03-09 08:00 | 2026-03-09 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8870 | Block-25 -IDT Erection | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-18 17:00 | 2026-02-27 08:00 | 2026-02-27 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2485 | Block-05 -ACDB Installation | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-15 17:00 | 2026-03-12 08:00 | 2026-03-12 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2490 | Block-05 -Aux Transformer - Installation | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-17 17:00 | 2026-03-18 08:00 | 2026-03-18 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1525 | Block-02 -ACDB Installation | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-15 17:00 | 2026-03-15 08:00 | 2026-03-15 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3765 | Block-09 -ACDB Installation | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-15 17:00 | 2026-03-13 08:00 | 2026-03-13 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2150 | Block-04 -IDT Erection | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-18 17:00 | 2026-03-14 08:00 | 2026-03-14 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1495 | Block-02 -Control Cable Laying | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-16 17:00 | 2026-03-15 08:00 | 2026-03-20 08:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8795 | Block-25 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-22 17:00 | 2026-03-12 08:00 | 2026-03-15 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8790 | Block-25 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-15 17:00 | 2026-03-14 08:00 | 2026-03-18 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2390 | Block-05 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-15 17:00 | 2026-03-17 08:00 | 2026-03-18 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9175 | Block-26 -Control Cable Laying | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-16 17:00 | 2026-03-20 08:00 | 2026-03-20 17:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9220 | Block-26 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-15 17:00 | 2026-03-20 08:00 | 2026-03-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8800 | Block-25 -NIFPS Foundation | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-23 17:00 | 2026-02-25 08:00 | 2026-02-25 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9125 | Block-26 -BOT Foundation | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-23 17:00 | 2026-03-15 08:00 | 2026-03-20 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2505 | Block-05 -LT Cable Terminations - LT Panel To IDT | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-20 17:00 | 2026-03-15 08:00 | 2026-03-18 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8890 | Block-25 -Aux Transformer - Installation | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-17 17:00 | 2026-03-16 08:00 | 2026-03-16 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2480 | Block-05 -SCADA & SACU Installation | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-15 17:00 | 2026-03-12 08:00 | 2026-03-12 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8810 | Block-25 -Aux Transformer Foundation | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-18 17:00 | 2026-02-25 08:00 | 2026-02-25 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2455 | Block-05 -Control Cable Laying | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-16 17:00 | 2026-03-20 08:00 | 2026-03-20 17:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1530 | Block-02 -Aux Transformer - Installation | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-17 17:00 | 2026-03-20 08:00 | 2026-03-20 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8895 | Block-25 -NIFPS - Installation | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-20 17:00 | 2026-03-16 08:00 | 2026-03-16 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2430 | Block-05 -HT LT Station - Staircase | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-15 17:00 | 2026-03-20 08:00 | 2026-03-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1545 | Block-02 -LT Cable Terminations - LT Panel To IDT | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-20 17:00 | 2026-03-15 08:00 | 2026-03-17 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1465 | Block-02 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-03-15 08:00 | 2026-03-17 17:00 | 2026-03-20 08:00 | 2026-03-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8885 | Block-25 -ACDB Installation | Completed | Task Dependent | 2026-03-15 08:00 | 2026-03-16 17:00 | 2026-03-17 08:00 | 2026-03-17 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8880 | Block-25 -SCADA & SACU Installation | Completed | Task Dependent | 2026-03-15 08:00 | 2026-03-16 17:00 | 2026-03-20 08:00 | 2026-03-20 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8855 | Block-25 -Control Cable Laying | Completed | Task Dependent | 2026-03-15 08:00 | 2026-03-17 17:00 | 2026-03-20 08:00 | 2026-03-20 17:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8910 | Block-25 -LT Cable Terminations - Inverter to LT Panel | Completed | Task Dependent | 2026-03-15 08:00 | 2026-03-18 17:00 | 2026-03-20 08:00 | 2026-03-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2810 | Block-06 -Aux Transformer - Installation | Completed | Task Dependent | 2026-03-15 08:00 | 2026-03-18 17:00 | 2026-03-18 08:00 | 2026-03-18 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2805 | Block-06 -ACDB Installation | Completed | Task Dependent | 2026-03-16 08:00 | 2026-03-17 17:00 | 2026-03-18 08:00 | 2026-03-18 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2120 | Block-04 -LT Cable Laying | Completed | Task Dependent | 2026-03-16 08:00 | 2026-04-06 09:00 | 2026-02-26 08:00 | 2026-04-17 09:00 | 1 | 9.8 | Kilometer | 10 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2775 | Block-06 -Control Cable Laying | Completed | Task Dependent | 2026-03-16 08:00 | 2026-03-18 17:00 | 2026-03-20 08:00 | 2026-03-20 17:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2800 | Block-06 -SCADA & SACU Installation | Completed | Task Dependent | 2026-03-16 08:00 | 2026-03-17 17:00 | 2026-03-20 08:00 | 2026-03-20 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3745 | Block-09 -LT Panel Erection | Completed | Task Dependent | 2026-03-16 08:00 | 2026-03-21 17:00 | 2026-03-13 08:00 | 2026-03-13 17:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9185 | Block-26 -LT Panel Erection | Completed | Task Dependent | 2026-03-16 08:00 | 2026-03-21 17:00 | 2026-03-11 08:00 | 2026-03-11 17:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2465 | Block-05 -LT Panel Erection | Completed | Task Dependent | 2026-03-16 08:00 | 2026-03-21 17:00 | 2026-03-11 08:00 | 2026-03-12 17:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2425 | Block-05 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-03-17 08:00 | 2026-03-19 17:00 | 2026-03-20 08:00 | 2026-03-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2815 | Block-06 -NIFPS - Installation | Completed | Task Dependent | 2026-03-18 08:00 | 2026-03-24 17:00 | 2026-03-12 08:00 | 2026-03-12 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1455 | Block-02 -IDT Area - Fencing | Completed | Task Dependent | 2026-03-18 08:00 | 2026-03-22 17:00 | 2026-03-20 08:00 | 2026-03-20 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8875 | Block-25 -Inverter Installation | Completed | Task Dependent | 2026-03-18 08:00 | 2026-03-24 17:00 | 2026-03-10 08:00 | 2026-03-22 17:00 | 1 | 94 | Number | 94 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2785 | Block-06 -LT Panel Erection | Completed | Task Dependent | 2026-03-18 08:00 | 2026-03-23 17:00 | 2026-03-18 08:00 | 2026-03-18 17:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8865 | Block-25 -LT Panel Erection | Completed | Task Dependent | 2026-03-18 08:00 | 2026-03-23 17:00 | 2026-03-16 08:00 | 2026-03-18 08:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2830 | Block-06 -LT Cable Terminations - Inverter To LT Panel | Completed | Task Dependent | 2026-03-18 08:00 | 2026-03-24 17:00 | 2026-03-20 08:00 | 2026-03-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2825 | Block-06 -LT Cable Terminations - LT Panel To IDT | Completed | Task Dependent | 2026-03-18 08:00 | 2026-03-24 17:00 | 2026-03-20 08:00 | 2026-03-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1540 | Block-02 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-03-18 08:00 | 2026-03-19 17:00 | 2026-03-20 08:00 | 2026-03-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2415 | Block-05 -IDT Area - Fencing | Completed | Task Dependent | 2026-03-18 08:00 | 2026-03-22 17:00 | 2026-03-20 08:00 | 2026-03-20 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1795 | Block-03 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-03-19 08:00 | 2026-03-23 17:00 | 2026-03-16 08:00 | 2026-04-08 14:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2500 | Block-05 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-22 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3735 | Block-09 -Control Cable Laying | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-23 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3785 | Block-09 -LT Cable Terminations - LT Panel to IDT | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-24 17:00 | 2026-03-27 08:00 | 2026-03-29 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3790 | Block-09 -LT Cable Terminations - Inverter to LT Panel | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-24 17:00 | 2026-03-23 08:00 | 2026-03-26 08:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4105 | Block-10 -LT Cable Terminations - LT Panel to IDT | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-24 17:00 | 2026-03-21 08:00 | 2026-03-29 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3770 | Block-09 -Aux Transformer - Installation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-24 17:00 | 2026-03-24 08:00 | 2026-03-24 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3670 | Block-09 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-22 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8170 | Block-23 -Aux Transformer Foundation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-25 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6545 | Block-18 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-25 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4005 | Block-10 -BOT Foundation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-30 17:00 | 2026-02-20 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4030 | Block-10 -HT LT Station - Staircase | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-22 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4085 | Block-10 -ACDB Installation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-22 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4065 | Block-10 -LT Panel Erection | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-26 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4080 | Block-10 -SCADA & SACU Installation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-22 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4090 | Block-10 -Aux Transformer - Installation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-24 17:00 | 2026-03-27 08:00 | 2026-03-27 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8190 | Block-23 -HT LT Station - Staircase | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-22 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4055 | Block-10 -Control Cable Laying | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-23 17:00 | 2026-03-27 08:00 | 2026-03-29 17:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4095 | Block-10 -NIFPS - Installation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-27 17:00 | 2026-03-27 08:00 | 2026-03-27 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8160 | Block-23 -NIFPS Foundation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-24 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9145 | Block-26 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-23 17:00 | 2026-03-22 08:00 | 2026-03-22 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2140 | Block-04 -HT Panel Erection | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-21 17:00 | 2026-03-18 08:00 | 2026-03-18 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8165 | Block-23 -BOT Foundation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-30 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9110 | Block-26 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-22 17:00 | 2026-03-22 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7610 | Block-21 -Aux Transformer - Installation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-24 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7550 | Block-21 -HT LT Station - Staircase | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-22 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3360 | Block-08 -NIFPS Foundation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-30 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3370 | Block-08 -Aux Transformer Foundation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-25 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2725 | Block-06 -BOT Foundation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-30 17:00 | 2026-03-12 08:00 | 2026-03-22 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2820 | Block-06 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-22 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7310 | Block-20 -LT Cable Terminations - Inverter to LT Panel | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-24 17:00 | 2026-03-23 08:00 | 2026-03-26 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7305 | Block-20 -LT Cable Terminations - LT Panel to IDT | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-24 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7280 | Block-20 -SCADA & SACU Installation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-22 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7265 | Block-20 -LT Panel Erection | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-26 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7295 | Block-20 -NIFPS - Installation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-27 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7285 | Block-20 -ACDB Installation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-22 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8825 | Block-25 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-23 17:00 | 2026-03-22 08:00 | 2026-03-22 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6910 | Block-19 -HT LT Station - Staircase | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-22 17:00 | 2026-03-22 08:00 | 2026-03-22 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7255 | Block-20 -Control Cable Laying | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-23 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8465 | Block-24 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-25 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8540 | Block-24 -HT Panel Erection | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-21 17:00 | 2026-03-06 08:00 | 2026-03-06 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8485 | Block-24 -BOT Foundation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-30 17:00 | 2026-03-15 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8570 | Block-24 -Aux Transformer - Installation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-24 17:00 | 2026-03-27 08:00 | 2026-03-27 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7290 | Block-20 -Aux Transformer - Installation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-24 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6970 | Block-19 -Aux Transformer - Installation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-24 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8575 | Block-24 -NIFPS - Installation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-27 17:00 | 2026-03-27 08:00 | 2026-03-27 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6975 | Block-19 -NIFPS - Installation | Completed | Task Dependent | 2026-03-21 08:00 | 2026-03-27 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8815 | Block-25 -IDT Area - Fencing | Completed | Task Dependent | 2026-03-22 08:00 | 2026-03-26 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8900 | Block-25 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-03-22 08:00 | 2026-03-23 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9135 | Block-26 -IDT Area - Fencing | Completed | Task Dependent | 2026-03-22 08:00 | 2026-03-26 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3075 | Block-07 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-03-22 08:00 | 2026-03-26 17:00 | 2026-03-23 08:00 | 2026-03-30 12:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1820 | Block-03 -HT Panel Erection | Completed | Task Dependent | 2026-03-22 08:00 | 2026-03-22 17:00 | 2026-03-18 08:00 | 2026-03-18 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1460 | Block-02 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-03-23 08:00 | 2026-03-23 17:00 | 2026-03-20 08:00 | 2026-03-20 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6965 | Block-19 -ACDB Installation | Completed | Task Dependent | 2026-03-23 08:00 | 2026-03-24 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8560 | Block-24 -SCADA & SACU Installation | Completed | Task Dependent | 2026-03-23 08:00 | 2026-03-24 17:00 | 2026-03-27 08:00 | 2026-03-30 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1800 | Block-03 -LT Cable Laying | Completed | Task Dependent | 2026-03-23 08:00 | 2026-04-15 09:00 | 2026-03-16 08:00 | 2026-03-16 09:00 | 1 | 9.2 | Kilometer | 9 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8565 | Block-24 -ACDB Installation | Completed | Task Dependent | 2026-03-23 08:00 | 2026-03-24 17:00 | 2026-03-24 08:00 | 2026-03-24 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8240 | Block-23 -SCADA & SACU Installation | Completed | Task Dependent | 2026-03-23 08:00 | 2026-03-24 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6935 | Block-19 -Control Cable Laying | Completed | Task Dependent | 2026-03-23 08:00 | 2026-03-25 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2420 | Block-05 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-03-23 08:00 | 2026-03-23 17:00 | 2026-03-20 08:00 | 2026-03-20 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8215 | Block-23 -Control Cable Laying | Completed | Task Dependent | 2026-03-23 08:00 | 2026-03-25 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8245 | Block-23 -ACDB Installation | Completed | Task Dependent | 2026-03-23 08:00 | 2026-03-24 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6960 | Block-19 -SCADA & SACU Installation | Completed | Task Dependent | 2026-03-23 08:00 | 2026-03-24 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5955 | Block-16 -Cable Hanger - Structure & Messenger Wire Erection | Completed | Task Dependent | 2026-03-24 08:00 | 2026-03-28 17:00 | 2026-03-23 08:00 | 2026-04-28 10:00 | 1 | 8.08 | Lot | 8 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4110 | Block-10 -LT Cable Terminations - Inverter to LT Panel | Completed | Task Dependent | 2026-03-24 08:00 | 2026-03-27 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8225 | Block-23 -LT Panel Erection | Completed | Task Dependent | 2026-03-25 08:00 | 2026-03-30 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6945 | Block-19 -LT Panel Erection | Completed | Task Dependent | 2026-03-25 08:00 | 2026-03-30 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3115 | Block-07 -Inverter Installation | Completed | Task Dependent | 2026-03-25 08:00 | 2026-03-31 17:00 | 2026-03-23 08:00 | 2026-03-27 17:00 | 1 | 94 | Number | 94 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2510 | Block-05 -LT Cable Terminations - Inverter To LT Panel | Completed | Task Dependent | 2026-03-26 08:00 | 2026-04-02 10:00 | 2026-03-12 08:00 | 2026-03-14 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3080 | Block-07 -LT Cable Laying | Completed | Task Dependent | 2026-03-26 08:00 | 2026-04-18 15:00 | 2026-03-23 08:00 | 2026-03-23 15:00 | 1 | 10.9 | Kilometer | 11 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5960 | Block-16 -LT Cable Laying | Completed | Task Dependent | 2026-03-26 08:00 | 2026-04-18 15:00 | 2026-03-23 08:00 | 2026-03-27 17:00 | 1 | 12.9 | Kilometer | 13 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8820 | Block-25 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-03-27 08:00 | 2026-03-28 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-9140 | Block-26 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-03-27 08:00 | 2026-03-28 17:00 | 2026-03-22 08:00 | 2026-03-22 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8585 | Block-24 -LT Cable Terminations - LT Panel to IDT | Completed | Task Dependent | 2026-03-28 08:00 | 2026-03-31 17:00 | 2026-03-30 08:00 | 2026-04-09 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6980 | Block-19 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-03-28 08:00 | 2026-03-29 17:00 | 2026-04-03 08:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6985 | Block-19 -LT Cable Terminations - LT Panel to IDT | Completed | Task Dependent | 2026-03-28 08:00 | 2026-03-31 17:00 | 2026-03-23 08:00 | 2026-03-27 08:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6990 | Block-19 -LT Cable Terminations - Inverter to LT Panel | Completed | Task Dependent | 2026-03-28 08:00 | 2026-03-31 17:00 | 2026-03-23 08:00 | 2026-03-27 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5385 | Block-14 -LT Cable Terminations - LT Panel to IDT | Completed | Task Dependent | 2026-03-28 08:00 | 2026-03-31 17:00 | 2026-04-03 08:00 | 2026-04-15 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8265 | Block-23 -LT Cable Terminations - LT Panel to IDT | Completed | Task Dependent | 2026-03-28 08:00 | 2026-03-31 17:00 | 2026-03-23 08:00 | 2026-03-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8185 | Block-23 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-03-28 08:00 | 2026-03-28 17:00 | 2026-04-03 08:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8270 | Block-23 -LT Cable Terminations - Inverter to LT Panel | Completed | Task Dependent | 2026-03-28 08:00 | 2026-03-31 17:00 | 2026-03-23 08:00 | 2026-03-26 08:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2085 | Block-04 -BOT Foundation | Completed | Task Dependent | 2026-03-28 08:00 | 2026-04-08 13:00 | 2026-03-28 08:00 | 2026-04-01 13:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4100 | Block-10 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-03-28 08:00 | 2026-03-29 17:00 | 2026-04-03 08:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4025 | Block-10 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-03-28 08:00 | 2026-03-30 17:00 | 2026-04-03 08:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6650 | Block-18 -Aux Transformer - Installation | Completed | Task Dependent | 2026-03-28 08:00 | 2026-03-31 17:00 | 2026-03-31 08:00 | 2026-03-31 14:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7575 | Block-21 -Control Cable Laying | Completed | Task Dependent | 2026-03-28 08:00 | 2026-03-30 17:00 | 2026-03-30 08:00 | 2026-04-07 12:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2075 | Block-04 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-03-28 08:00 | 2026-04-07 11:00 | 2026-03-25 08:00 | 2026-03-31 11:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8150 | Block-23 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-03-28 08:00 | 2026-03-29 17:00 | 2026-04-03 08:00 | 2026-04-03 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8260 | Block-23 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-03-28 08:00 | 2026-03-29 17:00 | 2026-04-03 08:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6870 | Block-19 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-03-28 08:00 | 2026-03-29 17:00 | 2026-04-02 08:00 | 2026-04-03 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6905 | Block-19 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-03-28 08:00 | 2026-03-30 17:00 | 2026-04-03 08:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1760 | Block-03 -NIFPS Foundation | Completed | Task Dependent | 2026-03-28 08:00 | 2026-04-08 13:00 | 2026-04-02 08:00 | 2026-04-02 13:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3780 | Block-09 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-03-28 08:00 | 2026-03-29 17:00 | 2026-04-03 08:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1770 | Block-03 -Aux Transformer Foundation | Completed | Task Dependent | 2026-03-28 08:00 | 2026-04-02 10:00 | 2026-04-02 08:00 | 2026-04-02 10:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3705 | Block-09 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-03-28 08:00 | 2026-03-30 17:00 | 2026-04-03 08:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3710 | Block-09 -HT LT Station - Staircase | Completed | Task Dependent | 2026-03-28 08:00 | 2026-03-29 17:00 | 2026-03-29 08:00 | 2026-03-29 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8535 | Block-24 -Control Cable Laying | Completed | Task Dependent | 2026-03-28 08:00 | 2026-03-30 17:00 | 2026-03-31 08:00 | 2026-04-08 12:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4015 | Block-10 -IDT Area - Fencing | Completed | Task Dependent | 2026-03-29 08:00 | 2026-04-03 12:00 | 2026-04-03 08:00 | 2026-04-03 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8175 | Block-23 -IDT Area - Fencing | Completed | Task Dependent | 2026-03-29 08:00 | 2026-04-03 12:00 | 2026-04-03 08:00 | 2026-04-03 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8250 | Block-23 -Aux Transformer - Installation | Completed | Task Dependent | 2026-03-29 08:00 | 2026-04-02 10:00 | 2026-03-23 08:00 | 2026-04-23 10:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6895 | Block-19 -IDT Area - Fencing | Completed | Task Dependent | 2026-03-29 08:00 | 2026-04-03 12:00 | 2026-04-03 08:00 | 2026-04-03 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3695 | Block-09 -IDT Area - Fencing | Completed | Task Dependent | 2026-03-29 08:00 | 2026-04-03 12:00 | 2026-04-03 08:00 | 2026-04-03 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8545 | Block-24 -LT Panel Erection | Completed | Task Dependent | 2026-03-30 08:00 | 2026-04-06 09:00 | 2026-03-23 08:00 | 2026-03-30 12:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6645 | Block-18 -ACDB Installation | Completed | Task Dependent | 2026-03-30 08:00 | 2026-03-31 17:00 | 2026-03-31 08:00 | 2026-03-31 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6640 | Block-18 -SCADA & SACU Installation | Completed | Task Dependent | 2026-03-30 08:00 | 2026-03-31 17:00 | 2026-03-31 08:00 | 2026-03-31 17:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6625 | Block-18 -LT Panel Erection | Completed | Task Dependent | 2026-03-30 08:00 | 2026-04-06 09:00 | 2026-03-23 08:00 | 2026-03-31 17:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2745 | Block-06 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-03-31 08:00 | 2026-04-03 12:00 | 2026-03-22 08:00 | 2026-03-22 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5995 | Block-16 -Inverter Installation | Completed | Task Dependent | 2026-03-31 08:00 | 2026-04-08 13:00 | 2026-03-23 08:00 | 2026-04-21 10:00 | 1 | 94 | Number | 94 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8255 | Block-23 -NIFPS - Installation | Completed | Task Dependent | 2026-03-31 08:00 | 2026-04-08 13:00 | 2026-03-23 08:00 | 2026-04-23 13:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3150 | Block-07 -LT Cable Terminations - Inverter To LT Panel | Completed | Task Dependent | 2026-04-01 08:00 | 2026-04-09 15:00 | 2026-04-03 08:00 | 2026-04-12 13:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8590 | Block-24 -LT Cable Terminations - Inverter to LT Panel | Completed | Task Dependent | 2026-04-02 10:00 | 2026-04-07 11:00 | 2026-03-23 10:00 | 2026-03-24 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6030 | Block-16 -LT Cable Terminations - Inverter to LT Panel | Completed | Task Dependent | 2026-04-03 10:00 | 2026-04-08 11:00 | 2026-04-03 10:00 | 2026-04-28 10:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6900 | Block-19 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-04-03 12:00 | 2026-04-06 09:00 | 2026-04-02 12:00 | 2026-04-03 09:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-4020 | Block-10 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-04-03 12:00 | 2026-04-06 09:00 | 2026-04-02 12:00 | 2026-04-03 09:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3700 | Block-09 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-04-03 12:00 | 2026-04-06 09:00 | 2026-04-02 12:00 | 2026-04-03 09:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5345 | Block-14 -LT Panel Erection | Completed | Task Dependent | 2026-04-03 12:00 | 2026-04-11 10:00 | 2026-03-09 12:00 | 2026-03-10 10:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8180 | Block-23 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-04-03 12:00 | 2026-04-06 09:00 | 2026-04-02 12:00 | 2026-04-03 09:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5280 | Block-14 -NIFPS Foundation | Completed | Task Dependent | 2026-04-04 08:00 | 2026-04-16 14:00 | 2026-04-04 08:00 | 2026-04-04 14:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5275 | Block-14 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-04-04 08:00 | 2026-04-15 12:00 | 2026-04-02 08:00 | 2026-04-04 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5905 | Block-16 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-04-04 08:00 | 2026-04-10 11:00 | 2026-04-09 08:00 | 2026-04-09 11:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3450 | Block-08 -Aux Transformer - Installation | Completed | Task Dependent | 2026-04-04 08:00 | 2026-04-09 09:00 | 2026-04-10 08:00 | 2026-04-10 09:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3390 | Block-08 -HT LT Station - Staircase | Completed | Task Dependent | 2026-04-04 08:00 | 2026-04-06 12:00 | 2026-04-04 08:00 | 2026-04-04 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3445 | Block-08 -ACDB Installation | Completed | Task Dependent | 2026-04-04 08:00 | 2026-04-06 12:00 | 2026-04-08 08:00 | 2026-04-08 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3425 | Block-08 -LT Panel Erection | Completed | Task Dependent | 2026-04-04 08:00 | 2026-04-11 13:00 | 2026-04-06 08:00 | 2026-04-08 13:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8510 | Block-24 -HT LT Station - Staircase | Completed | Task Dependent | 2026-04-04 08:00 | 2026-04-06 12:00 | 2026-04-09 08:00 | 2026-04-09 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5390 | Block-14 -LT Cable Terminations - Inverter to LT Panel | Completed | Task Dependent | 2026-04-04 08:00 | 2026-04-09 09:00 | 2026-04-03 08:00 | 2026-04-17 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5290 | Block-14 -Aux Transformer Foundation | Completed | Task Dependent | 2026-04-04 08:00 | 2026-04-10 11:00 | 2026-04-04 08:00 | 2026-04-04 11:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2065 | Block-04 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-04-04 08:00 | 2026-04-10 11:00 | 2026-04-07 08:00 | 2026-04-07 11:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2110 | Block-04 -HT LT Station - Staircase | Completed | Task Dependent | 2026-04-04 08:00 | 2026-04-06 12:00 | 2026-04-06 08:00 | 2026-04-06 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2080 | Block-04 -NIFPS Foundation | Completed | Task Dependent | 2026-04-04 08:00 | 2026-04-16 14:00 | 2026-04-04 08:00 | 2026-04-04 14:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2090 | Block-04 -Aux Transformer Foundation | Completed | Task Dependent | 2026-04-04 08:00 | 2026-04-10 11:00 | 2026-04-04 08:00 | 2026-04-04 11:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5265 | Block-14 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-04-04 08:00 | 2026-04-10 11:00 | 2026-04-07 08:00 | 2026-04-07 11:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6635 | Block-18 -Inverter Installation | Completed | Task Dependent | 2026-04-04 08:00 | 2026-04-12 15:00 | 2026-04-09 08:00 | 2026-04-18 11:00 | 1 | 96 | Number | 96 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5310 | Block-14 -HT LT Station - Staircase | Completed | Task Dependent | 2026-04-04 08:00 | 2026-04-06 12:00 | 2026-04-06 08:00 | 2026-04-06 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5340 | Block-14 -HT Panel Erection | Completed | Task Dependent | 2026-04-04 14:00 | 2026-04-06 09:00 | 2026-03-27 14:00 | 2026-03-28 09:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1850 | Block-03 -Aux Transformer - Installation | Completed | Task Dependent | 2026-04-06 09:00 | 2026-04-11 10:00 | 2026-04-03 09:00 | 2026-04-03 10:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2740 | Block-06 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-04-07 11:00 | 2026-04-08 13:00 | 2026-03-22 08:00 | 2026-03-22 13:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3465 | Block-08 -LT Cable Terminations - LT Panel to IDT | Completed | Task Dependent | 2026-04-07 14:00 | 2026-04-12 15:00 | 2026-04-09 14:00 | 2026-04-15 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3470 | Block-08 -LT Cable Terminations - Inverter to LT Panel | Completed | Task Dependent | 2026-04-07 14:00 | 2026-04-12 15:00 | 2026-04-06 14:00 | 2026-04-11 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3105 | Block-07 -LT Panel Erection | Completed | Task Dependent | 2026-04-09 09:00 | 2026-04-16 14:00 | 2026-04-09 09:00 | 2026-04-11 12:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2165 | Block-04 -ACDB Installation | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-13 12:00 | 2026-04-15 08:00 | 2026-04-15 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2160 | Block-04 -SCADA & SACU Installation | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-13 12:00 | 2026-04-15 08:00 | 2026-04-15 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3040 | Block-07 -NIFPS Foundation | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-23 14:00 | 2026-04-10 08:00 | 2026-04-10 14:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2135 | Block-04 -Control Cable Laying | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-14 14:00 | 2026-04-15 08:00 | 2026-04-20 12:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5370 | Block-14 -Aux Transformer - Installation | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-16 09:00 | 2026-04-11 08:00 | 2026-04-11 09:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3455 | Block-08 -NIFPS - Installation | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-19 15:00 | 2026-04-12 08:00 | 2026-04-12 15:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3050 | Block-07 -Aux Transformer Foundation | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-17 11:00 | 2026-04-10 08:00 | 2026-04-10 11:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1815 | Block-03 -Control Cable Laying | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-14 14:00 | 2026-04-15 08:00 | 2026-04-20 12:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3030 | Block-07 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-13 12:00 | 2026-04-17 08:00 | 2026-04-17 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2170 | Block-04 -Aux Transformer - Installation | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-16 09:00 | 2026-04-11 08:00 | 2026-04-11 09:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6010 | Block-16 -Aux Transformer - Installation | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-16 09:00 | 2026-04-11 08:00 | 2026-04-11 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1855 | Block-03 -NIFPS - Installation | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-19 15:00 | 2026-04-14 08:00 | 2026-04-14 15:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1845 | Block-03 -ACDB Installation | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-13 12:00 | 2026-04-15 08:00 | 2026-04-15 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2070 | Block-04 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-13 12:00 | 2026-04-14 08:00 | 2026-04-14 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7220 | Block-20 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-13 12:00 | 2026-04-12 08:00 | 2026-04-12 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1790 | Block-03 -HT LT Station - Staircase | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-13 12:00 | 2026-04-14 08:00 | 2026-04-14 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3145 | Block-07 -LT Cable Terminations - LT Panel To IDT | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-19 15:00 | 2026-04-15 08:00 | 2026-04-15 15:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3440 | Block-08 -SCADA & SACU Installation | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-13 12:00 | 2026-04-11 08:00 | 2026-04-11 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3035 | Block-07 -IDT Foundation - Grade Slab Casting & Dyke Wall | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-22 12:00 | 2026-02-02 08:00 | 2026-04-11 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7230 | Block-20 -HT LT Station - Staircase | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-13 12:00 | 2026-02-20 08:00 | 2026-02-20 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6665 | Block-18 -LT Cable Terminations - LT Panel to IDT | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-16 09:00 | 2026-04-13 08:00 | 2026-04-15 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1765 | Block-03 -BOT Foundation | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-23 14:00 | 2026-04-11 08:00 | 2026-04-12 14:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6550 | Block-18 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-13 12:00 | 2026-04-17 08:00 | 2026-04-17 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1745 | Block-03 -HT & LT Station - Shed Installation | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-17 11:00 | 2026-04-13 08:00 | 2026-04-14 11:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5950 | Block-16 -HT LT Station - Staircase | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-13 12:00 | 2026-04-13 08:00 | 2026-04-13 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3415 | Block-08 -Control Cable Laying | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-14 14:00 | 2026-04-12 08:00 | 2026-04-20 10:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8470 | Block-24 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-13 12:00 | 2026-04-13 08:00 | 2026-04-14 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3070 | Block-07 -HT LT Station - Staircase | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-13 12:00 | 2026-04-14 08:00 | 2026-04-14 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1750 | Block-03 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-13 12:00 | 2026-04-15 08:00 | 2026-04-15 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7545 | Block-21 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-14 14:00 | 2026-04-13 08:00 | 2026-04-13 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5270 | Block-14 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-13 12:00 | 2026-04-11 08:00 | 2026-04-11 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3380 | Block-08 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-13 12:00 | 2026-04-17 08:00 | 2026-04-17 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7225 | Block-20 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-14 14:00 | 2026-04-13 08:00 | 2026-04-13 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6615 | Block-18 -Control Cable Laying | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-14 14:00 | 2026-04-14 08:00 | 2026-04-20 14:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6025 | Block-16 -LT Cable Terminations - LT Panel to IDT | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-16 09:00 | 2026-04-15 08:00 | 2026-04-15 09:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1865 | Block-03 -LT Cable Terminations - LT Panel To IDT | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-19 15:00 | 2026-04-17 08:00 | 2026-04-17 15:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7510 | Block-21 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-04-11 08:00 | 2026-04-13 12:00 | 2026-04-14 08:00 | 2026-04-14 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8580 | Block-24 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-04-12 10:00 | 2026-04-14 14:00 | 2026-04-12 10:00 | 2026-04-14 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7620 | Block-21 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-04-12 10:00 | 2026-04-14 14:00 | 2026-04-12 10:00 | 2026-04-14 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6660 | Block-18 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-04-12 10:00 | 2026-04-14 14:00 | 2026-04-12 10:00 | 2026-04-22 10:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7300 | Block-20 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-04-12 10:00 | 2026-04-14 14:00 | 2026-04-12 10:00 | 2026-04-14 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3460 | Block-08 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-04-12 10:00 | 2026-04-14 14:00 | 2026-04-14 10:00 | 2026-04-22 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7535 | Block-21 -IDT Area - Fencing | Completed | Task Dependent | 2026-04-12 10:00 | 2026-04-18 13:00 | 2026-04-12 10:00 | 2026-04-12 13:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6000 | Block-16 -SCADA & SACU Installation | Completed | Task Dependent | 2026-04-13 12:00 | 2026-04-16 09:00 | 2026-04-12 12:00 | 2026-04-12 14:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3095 | Block-07 -Control Cable Laying | Completed | Task Dependent | 2026-04-13 12:00 | 2026-04-17 11:00 | 2026-04-12 12:00 | 2026-04-15 09:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8505 | Block-24 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-04-13 12:00 | 2026-04-17 11:00 | 2026-04-13 12:00 | 2026-04-13 15:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6020 | Block-16 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-04-13 12:00 | 2026-04-16 09:00 | 2026-04-12 12:00 | 2026-04-22 10:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3125 | Block-07 -ACDB Installation | Completed | Task Dependent | 2026-04-13 12:00 | 2026-04-16 09:00 | 2026-04-10 12:00 | 2026-04-11 09:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3120 | Block-07 -SCADA & SACU Installation | Completed | Task Dependent | 2026-04-13 12:00 | 2026-04-16 09:00 | 2026-04-10 12:00 | 2026-04-11 09:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5335 | Block-14 -Control Cable Laying | Completed | Task Dependent | 2026-04-13 12:00 | 2026-04-17 11:00 | 2026-04-15 12:00 | 2026-04-17 12:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6005 | Block-16 -ACDB Installation | Completed | Task Dependent | 2026-04-13 12:00 | 2026-04-16 09:00 | 2026-04-11 12:00 | 2026-04-11 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5360 | Block-14 -SCADA & SACU Installation | Completed | Task Dependent | 2026-04-13 12:00 | 2026-04-16 09:00 | 2026-04-14 12:00 | 2026-04-15 09:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5975 | Block-16 -Control Cable Laying | Completed | Task Dependent | 2026-04-13 12:00 | 2026-04-17 11:00 | 2026-04-14 12:00 | 2026-04-20 12:00 | 1 | 0.74 | Kilometer | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5365 | Block-14 -ACDB Installation | Completed | Task Dependent | 2026-04-13 12:00 | 2026-04-16 09:00 | 2026-04-15 12:00 | 2026-04-15 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3375 | Block-08 -IDT Area - Fencing | Completed | Task Dependent | 2026-04-14 10:00 | 2026-04-20 13:00 | 2026-04-04 10:00 | 2026-04-04 13:00 | 1 | 1 | Number | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8495 | Block-24 -IDT Area - Fencing | Completed | Task Dependent | 2026-04-14 14:00 | 2026-04-21 10:00 | 2026-04-12 08:00 | 2026-04-12 10:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2145 | Block-04 -LT Panel Erection | Completed | Task Dependent | 2026-04-15 12:00 | 2026-04-23 10:00 | 2026-04-10 12:00 | 2026-04-15 14:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5985 | Block-16 -LT Panel Erection | Completed | Task Dependent | 2026-04-15 12:00 | 2026-04-23 10:00 | 2026-04-09 12:00 | 2026-04-11 12:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2190 | Block-04 -LT Cable Terminations - Inverter To LT Panel | Completed | Task Dependent | 2026-04-15 12:00 | 2026-04-24 12:00 | 2026-04-08 12:00 | 2026-04-28 10:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6670 | Block-18 -LT Cable Terminations - Inverter to LT Panel | Completed | Task Dependent | 2026-04-16 09:00 | 2026-04-21 10:00 | 2026-04-12 09:00 | 2026-04-28 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1775 | Block-03 -IDT Area - Fencing | Completed | Task Dependent | 2026-04-16 09:00 | 2026-04-22 12:00 | 2026-04-16 09:00 | 2026-04-17 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1835 | Block-03 -Inverter Installation | Completed | Task Dependent | 2026-04-16 14:00 | 2026-04-25 14:00 | 2026-04-08 14:00 | 2026-04-17 10:00 | 1 | 94 | Number | 94 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5305 | Block-14 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-04-18 08:00 | 2026-04-21 14:00 | 2026-04-18 08:00 | 2026-04-19 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6655 | Block-18 -NIFPS - Installation | Completed | Task Dependent | 2026-04-18 08:00 | 2026-04-26 15:00 | 2026-04-20 08:00 | 2026-04-20 15:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5910 | Block-16 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-04-18 08:00 | 2026-04-20 12:00 | 2026-04-09 08:00 | 2026-04-10 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6015 | Block-16 -NIFPS - Installation | Completed | Task Dependent | 2026-04-18 08:00 | 2026-04-26 15:00 | 2026-04-20 08:00 | 2026-04-20 15:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5380 | Block-14 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-04-18 08:00 | 2026-04-20 12:00 | 2026-04-20 08:00 | 2026-04-22 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3140 | Block-07 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-04-18 08:00 | 2026-04-20 12:00 | 2026-04-20 08:00 | 2026-04-22 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3135 | Block-07 -NIFPS - Installation | Completed | Task Dependent | 2026-04-18 12:00 | 2026-04-27 12:00 | 2026-04-20 12:00 | 2026-04-20 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2185 | Block-04 -LT Cable Terminations - LT Panel To IDT | Completed | Task Dependent | 2026-04-18 13:00 | 2026-04-27 13:00 | 2026-04-15 13:00 | 2026-04-15 13:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5295 | Block-14 -IDT Area - Fencing | Completed | Task Dependent | 2026-04-18 13:00 | 2026-04-25 09:00 | 2026-04-11 13:00 | 2026-04-12 09:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-7540 | Block-21 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-04-18 13:00 | 2026-04-21 10:00 | 2026-04-12 10:00 | 2026-04-12 14:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3385 | Block-08 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-04-19 10:00 | 2026-04-23 09:00 | 2026-04-18 10:00 | 2026-04-19 09:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1870 | Block-03 -LT Cable Terminations - Inverter To LT Panel | Completed | Task Dependent | 2026-04-19 11:00 | 2026-04-28 11:00 | 2026-04-08 11:00 | 2026-04-28 10:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1840 | Block-03 -SCADA & SACU Installation | Completed | Task Dependent | 2026-04-20 08:00 | 2026-04-22 12:00 | 2026-04-14 08:00 | 2026-04-14 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1860 | Block-03 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-04-20 12:00 | 2026-04-23 09:00 | 2026-04-20 12:00 | 2026-04-22 09:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2180 | Block-04 -HT Cable Terminations - IDT Side | Completed | Task Dependent | 2026-04-20 12:00 | 2026-04-23 09:00 | 2026-04-20 12:00 | 2026-04-22 09:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5935 | Block-16 -IDT Area - Fencing | Completed | Task Dependent | 2026-04-21 10:00 | 2026-04-27 13:00 | 2026-04-16 10:00 | 2026-04-16 13:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3130 | Block-07 -Aux Transformer - Installation | Completed | Task Dependent | 2026-04-21 10:00 | 2026-04-26 11:00 | 2026-04-14 10:00 | 2026-04-14 11:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-8500 | Block-24 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-04-21 10:00 | 2026-04-23 14:00 | 2026-04-12 08:00 | 2026-04-12 14:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6575 | Block-18 -IDT Area - Fencing | Completed | Task Dependent | 2026-04-21 10:00 | 2026-04-27 13:00 | 2026-04-14 10:00 | 2026-04-14 13:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1780 | Block-03 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-04-22 12:00 | 2026-04-23 14:00 | 2026-04-17 12:00 | 2026-04-17 14:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1825 | Block-03 -LT Panel Erection | Completed | Task Dependent | 2026-04-22 12:00 | 2026-04-30 10:00 | 2026-04-12 12:00 | 2026-04-13 10:00 | 1 | 16 | Number | 16 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2095 | Block-04 -IDT Area - Fencing | Completed | Task Dependent | 2026-04-22 14:00 | 2026-04-29 10:00 | 2026-04-16 14:00 | 2026-04-17 10:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5375 | Block-14 -NIFPS - Installation | Completed | Task Dependent | 2026-04-24 12:00 | 2026-05-03 12:00 | 2026-04-09 12:00 | 2026-04-09 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2175 | Block-04 -NIFPS - Installation | Completed | Task Dependent | 2026-04-25 08:00 | 2026-05-03 15:00 | 2026-04-28 08:00 | 2026-04-28 15:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5300 | Block-14 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-04-25 09:00 | 2026-04-27 13:00 | 2026-04-11 09:00 | 2026-04-12 13:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6585 | Block-18 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-04-27 08:00 | 2026-04-30 14:00 | 2026-04-23 08:00 | 2026-04-23 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5945 | Block-16 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-04-27 08:00 | 2026-04-30 14:00 | 2026-04-22 08:00 | 2026-04-23 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2105 | Block-04 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-04-27 08:00 | 2026-04-30 14:00 | 2026-04-23 08:00 | 2026-04-23 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3065 | Block-07 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-04-27 12:00 | 2026-05-01 11:00 | 2026-04-18 12:00 | 2026-04-19 11:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-5940 | Block-16 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-04-27 13:00 | 2026-04-30 10:00 | 2026-04-17 12:00 | 2026-04-17 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-6580 | Block-18 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-04-27 13:00 | 2026-04-30 10:00 | 2026-04-13 13:00 | 2026-04-14 10:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2100 | Block-04 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-04-29 10:00 | 2026-04-30 12:00 | 2026-04-17 10:00 | 2026-04-17 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-1785 | Block-03 -IDT Area - Gravel Filling | Completed | Task Dependent | 2026-05-02 08:00 | 2026-05-05 14:00 | 2026-05-06 08:00 | 2026-05-06 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3055 | Block-07 -IDT Area - Fencing | Completed | Task Dependent | 2026-05-11 14:00 | 2026-05-18 10:00 | 2026-04-16 14:00 | 2026-04-17 10:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2710 | Block-06 -HT & LT Station - Sheeting Installation | Completed | Task Dependent | 2026-05-17 08:00 | 2026-05-19 12:00 | 2026-03-24 08:00 | 2026-03-26 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-2735 | Block-06 -IDT Area - Fencing | Completed | Task Dependent | 2026-05-17 08:00 | 2026-05-23 11:00 | 2026-03-24 08:00 | 2026-03-26 11:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-AC SIDE | 603F-CC-3060 | Block-07 -IDT Area - Gate Installation | Completed | Task Dependent | 2026-05-18 10:00 | 2026-05-19 12:00 | 2026-04-17 10:00 | 2026-04-17 12:00 | 1 | 1 | Number | 1 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4860 | Block-13 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2025-05-31 07:00 | 2025-07-11 10:00 | 2025-04-18 07:00 | 2026-01-04 17:00 | 1 | 5928 | Number | 5928 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5480 | Block-15 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2025-05-31 07:00 | 2025-07-11 10:00 | 2025-04-19 07:00 | 2026-02-16 17:00 | 1 | 5916 | Number | 5916 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5160 | Block-14 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2025-05-31 07:00 | 2025-07-11 10:00 | 2025-05-03 07:00 | 2026-03-13 17:00 | 1 | 5916 | Number | 5916 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4865 | Block-13 -Pile Capping | Completed | Task Dependent | 2025-06-09 07:00 | 2025-07-24 08:00 | 2025-05-05 07:00 | 2026-01-10 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9000 | Block-26 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2025-06-29 07:00 | 2025-08-22 08:00 | 2025-06-13 07:00 | 2026-03-09 17:00 | 1 | 5844 | Number | 5844 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1000 | Block-01 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2025-07-05 07:00 | 2025-08-28 12:00 | 2025-12-21 07:00 | 2026-01-18 17:00 | 1 | 5928 | Number | 5928 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9320 | Block-27 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2025-07-05 07:03 | 2025-08-29 07:03 | 2025-11-21 07:03 | 2025-12-19 17:00 | 1 | 5916 | Number | 5916 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8680 | Block-25 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2025-07-05 07:03 | 2025-08-29 07:03 | 2025-05-27 07:03 | 2026-03-14 17:00 | 1 | 5928 | Number | 5928 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4885 | Block-13 -Array Earthing | Completed | Task Dependent | 2025-11-15 08:00 | 2025-12-09 17:00 | 2025-11-15 08:00 | 2026-02-19 17:00 | 1 | 5 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4870 | Block-13 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2025-11-22 08:00 | 2025-12-11 17:00 | 2025-11-20 08:00 | 2026-01-12 17:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4520 | Block-12 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2025-11-22 08:00 | 2025-12-21 17:00 | 2025-11-21 08:00 | 2025-12-22 17:00 | 1 | 5844 | Number | 5844 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5485 | Block-15 -Pile Capping | Completed | Task Dependent | 2025-11-24 08:00 | 2025-12-23 17:00 | 2025-11-20 08:00 | 2026-02-22 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9005 | Block-26 -Pile Capping | Completed | Task Dependent | 2025-11-29 08:00 | 2025-12-28 17:00 | 2025-11-24 08:00 | 2026-03-14 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5165 | Block-14 -Pile Capping | Completed | Task Dependent | 2025-11-29 08:00 | 2025-12-28 17:00 | 2025-11-22 08:00 | 2026-03-14 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2920 | Block-07 -Piling - MMS (Marking, Auguring & Concreting) | In Progress | Task Dependent | 2025-11-29 08:00 | 2025-12-28 17:00 | 2025-11-25 08:00 |  | 0.99 | 5844 | Number | 5785 | 143
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7080 | Block-20 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2025-11-29 08:00 | 2025-12-28 17:00 | 2025-11-25 08:00 | 2026-01-13 17:00 | 1 | 5844 | Number | 5844 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8685 | Block-25 -Pile Capping | Completed | Task Dependent | 2025-11-29 08:00 | 2025-12-28 17:00 | 2025-11-27 08:00 | 2026-03-16 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7400 | Block-21 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2025-11-29 08:00 | 2025-12-28 17:00 | 2025-11-24 08:00 | 2026-01-26 17:00 | 1 | 5844 | Number | 5844 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7720 | Block-22 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2025-11-29 08:00 | 2025-12-28 17:00 | 2025-11-25 08:00 | 2026-01-03 17:00 | 1 | 5844 | Number | 5844 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8040 | Block-23 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2025-11-29 08:00 | 2025-12-28 17:00 | 2025-11-26 08:00 | 2026-01-24 17:00 | 1 | 5844 | Number | 5844 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8360 | Block-24 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2025-11-29 08:00 | 2025-12-28 17:00 | 2025-11-28 08:00 | 2026-03-31 17:00 | 1 | 5844 | Number | 5844 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4525 | Block-12 -Pile Capping | Completed | Task Dependent | 2025-12-04 08:00 | 2026-01-02 17:00 | 2025-11-23 08:00 | 2025-12-27 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9325 | Block-27 -Pile Capping | Completed | Task Dependent | 2025-12-05 08:00 | 2026-01-03 17:00 | 2025-11-23 08:00 | 2025-12-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6760 | Block-19 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2025-12-06 08:00 | 2026-01-04 17:00 | 2025-11-30 08:00 | 2026-04-10 14:00 | 1 | 5844 | Number | 5844 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4875 | Block-13 -Piling - Inverters | Completed | Task Dependent | 2025-12-06 08:00 | 2025-12-21 17:00 | 2025-11-28 08:00 | 2026-02-18 17:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6120 | Block-17 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2025-12-06 08:00 | 2026-01-04 17:00 | 2025-11-29 08:00 | 2026-01-13 17:00 | 1 | 5844 | Number | 5844 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7405 | Block-21 -Pile Capping | Completed | Task Dependent | 2025-12-09 08:00 | 2026-01-07 17:00 | 2025-12-02 08:00 | 2026-01-28 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7725 | Block-22 -Pile Capping | Completed | Task Dependent | 2025-12-11 08:00 | 2026-01-09 17:00 | 2025-12-03 08:00 | 2026-01-05 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2925 | Block-07 -Pile Capping | In Progress | Task Dependent | 2025-12-11 08:00 | 2026-01-09 17:00 | 2025-12-04 08:00 |  | 0.94 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7085 | Block-20 -Pile Capping | Completed | Task Dependent | 2025-12-12 08:00 | 2026-01-10 17:00 | 2025-11-29 08:00 | 2026-01-18 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4545 | Block-12 -Array Earthing | Completed | Task Dependent | 2025-12-13 08:00 | 2026-01-06 17:00 | 2025-12-07 08:00 | 2026-02-19 17:00 | 1 | 5 | Kilometer | 5.435 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4535 | Block-12 -Piling - Inverters | Completed | Task Dependent | 2025-12-13 08:00 | 2025-12-28 17:00 | 2025-12-07 08:00 | 2025-12-25 17:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4550 | Block-12 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2025-12-13 08:00 | 2026-01-09 17:00 | 2025-12-09 08:00 | 2026-01-10 17:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9330 | Block-27 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2025-12-13 08:00 | 2026-01-01 17:00 | 2025-12-07 08:00 | 2025-12-20 17:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9345 | Block-27 -Array Earthing | Completed | Task Dependent | 2025-12-13 08:00 | 2026-01-06 17:00 | 2025-12-06 08:00 | 2026-02-19 17:00 | 1 | 4.1 | Kilometer | 4 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6765 | Block-19 -Pile Capping | Completed | Task Dependent | 2025-12-13 08:00 | 2026-01-11 17:00 | 2025-12-05 08:00 | 2026-05-06 10:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6440 | Block-18 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Resource Dependent | 2025-12-13 08:00 | 2026-02-27 10:03 | 2025-12-14 08:00 | 2026-03-30 12:22 | 1 | 5416 | Number | 5416 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4530 | Block-12 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2025-12-13 08:00 | 2026-01-01 17:00 | 2025-12-07 08:00 | 2026-02-18 17:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4200 | Block-11 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2025-12-13 08:00 | 2026-01-11 17:00 | 2025-12-12 08:00 | 2026-01-10 17:00 | 1 | 5844 | Number | 5844 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5185 | Block-14 -Array Earthing | Completed | Task Dependent | 2025-12-13 08:00 | 2026-01-06 17:00 | 2025-12-06 08:00 | 2026-03-27 17:00 | 1 | 5 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5170 | Block-14 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2025-12-13 08:00 | 2026-01-01 17:00 | 2025-12-08 08:00 | 2026-01-21 17:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9335 | Block-27 -Piling - Inverters | Completed | Task Dependent | 2025-12-13 08:00 | 2025-12-28 17:00 | 2025-12-07 08:00 | 2025-12-19 17:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8050 | Block-23 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2025-12-13 08:00 | 2026-01-01 17:00 | 2025-12-07 08:00 | 2026-01-17 17:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7410 | Block-21 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2025-12-13 08:00 | 2026-01-01 17:00 | 2025-12-07 08:00 | 2026-01-27 17:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7415 | Block-21 -Piling - Inverters | Completed | Task Dependent | 2025-12-14 08:00 | 2025-12-29 17:00 | 2025-12-11 08:00 | 2026-01-05 17:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8055 | Block-23 -Piling - Inverters | Completed | Task Dependent | 2025-12-14 08:00 | 2025-12-29 17:00 | 2025-12-11 08:00 | 2026-01-17 17:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7730 | Block-22 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2025-12-16 08:00 | 2026-01-04 17:00 | 2025-12-11 08:00 | 2025-12-27 17:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4555 | Block-12 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2025-12-17 12:00 | 2026-01-14 12:00 | 2025-12-09 | 2026-01-10 12:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2930 | Block-07 -Piling - LT Cable Hanger System | In Progress | Task Dependent | 2025-12-19 08:00 | 2026-01-07 17:00 | 2025-12-12 08:00 |  | 0.94 | 660 | Number | 621 | 15
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6770 | Block-19 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2025-12-19 08:00 | 2026-01-07 17:00 | 2025-12-11 08:00 | 2026-02-05 17:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3240 | Block-08 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2025-12-20 08:00 | 2026-01-18 17:00 | 2025-12-15 08:00 | 2026-02-19 17:00 | 1 | 5928 | Number | 5928 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5175 | Block-14 -Piling - Inverters | Completed | Task Dependent | 2025-12-20 08:00 | 2026-01-04 17:00 | 2025-12-20 08:00 | 2026-03-10 17:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6125 | Block-17 -Pile Capping | Completed | Task Dependent | 2025-12-20 08:00 | 2026-03-07 10:03 | 2025-12-09 08:00 | 2026-01-18 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5800 | Block-16 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2025-12-20 08:00 | 2026-01-18 17:00 | 2025-12-20 08:00 | 2026-04-13 10:00 | 1 | 5928 | Number | 5928 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3880 | Block-10 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2025-12-20 08:00 | 2026-01-18 17:00 | 2025-12-16 08:00 | 2026-03-17 17:00 | 1 | 5916 | Number | 5916 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8045 | Block-23 -Pile Capping | Completed | Task Dependent | 2025-12-20 08:00 | 2026-01-18 17:00 | 2025-12-06 08:00 | 2026-01-24 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6130 | Block-17 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2025-12-21 08:00 | 2026-01-09 17:00 | 2025-12-20 08:00 | 2026-02-18 17:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8365 | Block-24 -Pile Capping | Completed | Task Dependent | 2025-12-24 08:00 | 2026-01-22 17:00 | 2025-12-16 08:00 | 2026-03-31 09:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7090 | Block-20 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2025-12-25 08:00 | 2026-01-13 17:00 | 2025-12-22 08:00 | 2026-01-18 17:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6145 | Block-17 -Array Earthing | Completed | Task Dependent | 2025-12-27 08:00 | 2026-01-20 17:00 | 2025-12-26 08:00 | 2026-02-18 17:00 | 1 | 4.861 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4210 | Block-11 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2025-12-27 08:00 | 2026-01-15 17:00 | 2025-12-29 08:00 | 2026-01-20 17:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4205 | Block-11 -Pile Capping | Completed | Task Dependent | 2025-12-27 08:00 | 2026-01-25 17:00 | 2025-12-23 08:00 | 2026-01-16 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4560 | Block-12 -MMS Erection - Purlin | Completed | Task Dependent | 2025-12-27 08:00 | 2026-01-23 17:00 | 2025-12-16 08:00 | 2026-01-22 17:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5505 | Block-15 -Array Earthing | Completed | Task Dependent | 2025-12-27 08:00 | 2026-01-20 17:00 | 2025-12-23 08:00 | 2026-02-19 17:00 | 1 | 4.859 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7745 | Block-22 -Array Earthing | Completed | Task Dependent | 2025-12-27 08:00 | 2026-01-20 17:00 | 2025-12-30 08:00 | 2026-02-19 17:00 | 1 | 4.866 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6135 | Block-17 -Piling - Inverters | Completed | Task Dependent | 2025-12-27 08:00 | 2026-01-11 17:00 | 2025-12-30 08:00 | 2026-01-18 17:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4225 | Block-11 -Array Earthing | Completed | Task Dependent | 2025-12-27 08:00 | 2026-01-20 17:00 | 2025-12-29 | 2026-02-19 17:00 | 1 | 5.032 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4890 | Block-13 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2025-12-27 08:00 | 2026-01-23 17:00 | 2025-12-29 08:00 | 2026-02-09 08:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1005 | Block-01 -Pile Capping | Completed | Task Dependent | 2025-12-27 08:00 | 2026-01-25 17:00 | 2025-12-22 08:00 | 2026-01-18 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7095 | Block-20 -Piling - Inverters | Completed | Task Dependent | 2025-12-27 08:00 | 2026-01-11 17:00 | 2025-12-24 08:00 | 2026-01-13 17:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8370 | Block-24 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2025-12-27 08:00 | 2026-01-15 17:00 | 2025-12-15 08:00 | 2026-02-07 17:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2600 | Block-06 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2025-12-27 08:00 | 2026-01-25 17:00 | 2025-12-27 08:00 | 2026-02-21 17:00 | 1 | 5792 | Number | 5792 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7735 | Block-22 -Piling - Inverters | Completed | Task Dependent | 2025-12-27 08:00 | 2026-01-11 17:00 | 2025-12-16 08:00 | 2025-12-27 12:19 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7425 | Block-21 -Array Earthing | Completed | Task Dependent | 2025-12-27 08:00 | 2026-01-20 17:00 | 2025-12-26 08:00 | 2026-01-28 17:00 | 1 | 4.865 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6775 | Block-19 -Piling - Inverters | Completed | Task Dependent | 2025-12-28 08:00 | 2026-01-12 17:00 | 2026-01-01 08:00 | 2026-03-23 17:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4215 | Block-11 -Piling - Inverters | Completed | Task Dependent | 2025-12-29 08:00 | 2026-01-13 17:00 | 2025-12-30 08:00 | 2026-01-13 17:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8375 | Block-24 -Piling - Inverters | Completed | Task Dependent | 2025-12-30 08:00 | 2026-01-14 17:00 | 2025-12-31 08:00 | 2026-02-07 17:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3245 | Block-08 -Pile Capping | Completed | Task Dependent | 2025-12-30 08:00 | 2026-01-29 17:00 | 2025-12-26 08:00 | 2026-02-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3885 | Block-10 -Pile Capping | Completed | Task Dependent | 2025-12-31 08:00 | 2026-01-30 17:00 | 2025-12-23 08:00 | 2026-03-24 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4895 | Block-13 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2025-12-31 12:00 | 2026-01-29 12:00 | 2025-12-29 12:00 | 2026-02-09 17:00 | 1 | 493 | Tables | 493 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4920 | Block-13 -DC Cable Laying | Completed | Task Dependent | 2026-01-01 11:00 | 2026-01-16 11:00 | 2025-11-26 11:00 | 2026-02-18 17:00 | 1 | 122 | Kilometer | 81 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3250 | Block-08 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2026-01-02 08:00 | 2026-01-21 17:00 | 2025-12-31 08:00 | 2026-02-17 17:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1320 | Block-02 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2026-01-03 08:00 | 2026-02-02 17:00 | 2026-01-03 08:00 | 2026-02-18 17:00 | 1 | 3780 | Number | 3780 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7105 | Block-20 -Array Earthing | Completed | Task Dependent | 2026-01-03 08:00 | 2026-01-28 17:00 | 2026-01-05 08:00 | 2026-04-08 14:00 | 1 | 4.864 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3560 | Block-09 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2026-01-03 08:00 | 2026-02-02 17:00 | 2026-01-09 08:00 | 2026-04-02 17:00 | 1 | 5928 | Number | 5928 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2605 | Block-06 -Pile Capping | Completed | Task Dependent | 2026-01-03 08:00 | 2026-02-02 17:00 | 2025-12-30 08:00 | 2026-02-22 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1640 | Block-03 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2026-01-03 08:00 | 2026-02-02 17:00 | 2026-01-07 08:00 | 2026-04-23 10:00 | 1 | 5928 | Number | 5928 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3890 | Block-10 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2026-01-03 08:00 | 2026-01-22 17:00 | 2026-01-07 08:00 | 2026-02-02 17:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5805 | Block-16 -Pile Capping | Completed | Task Dependent | 2026-01-03 08:00 | 2026-02-02 17:00 | 2026-01-07 08:00 | 2026-04-15 10:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7110 | Block-20 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2026-01-03 08:00 | 2026-01-31 17:00 | 2026-01-03 08:00 | 2026-05-18 11:00 | 1 | 493 | Tables | 493 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8065 | Block-23 -Array Earthing | Completed | Task Dependent | 2026-01-03 08:00 | 2026-01-28 17:00 | 2026-01-02 08:00 | 2026-03-23 17:00 | 1 | 4.867 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4900 | Block-13 -MMS Erection - Purlin | Completed | Task Dependent | 2026-01-03 08:00 | 2026-01-31 17:00 | 2025-12-30 08:00 | 2026-02-09 17:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3255 | Block-08 -Piling - Inverters | Completed | Task Dependent | 2026-01-05 08:00 | 2026-01-20 17:00 | 2026-01-03 08:00 | 2026-02-18 17:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7115 | Block-20 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2026-01-07 12:00 | 2026-02-05 12:00 | 2026-01-03 12:00 | 2026-05-18 09:00 | 1 | 493 | Tables | 493 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7120 | Block-20 -MMS Erection - Purlin | In Progress | Task Dependent | 2026-01-07 12:00 | 2026-02-05 12:00 | 2026-01-07 12:00 |  | 0.94 | 487 | Tables | 458 | 29
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3895 | Block-10 -Piling - Inverters | Completed | Task Dependent | 2026-01-08 08:00 | 2026-01-23 17:00 | 2026-01-07 08:00 | 2026-02-02 17:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1030 | Block-01 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2026-01-09 08:00 | 2026-02-06 17:00 | 2026-01-06 08:00 | 2026-02-13 17:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5190 | Block-14 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2026-01-10 08:00 | 2026-02-07 17:00 | 2026-01-16 08:00 | 2026-05-19 09:00 | 1 | 493 | Tables | 493 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1325 | Block-02 -Pile Capping | Completed | Task Dependent | 2026-01-10 08:00 | 2026-02-09 17:00 | 2026-01-05 08:00 | 2026-02-19 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6450 | Block-18 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-30 17:00 | 2026-01-11 08:00 | 2026-03-30 10:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4230 | Block-11 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2026-01-10 08:00 | 2026-02-07 17:00 | 2026-01-14 08:00 | 2026-02-09 17:00 | 1 | 493 | Tables | 493 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8070 | Block-23 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2026-01-10 08:00 | 2026-02-07 17:00 | 2026-01-10 08:00 | 2026-05-07 14:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7430 | Block-21 -MMS Erection - Torque Tube/Raftar | In Progress | Task Dependent | 2026-01-10 08:00 | 2026-02-07 17:00 | 2026-01-12 08:00 |  | 0.99 | 493 | Tables | 486 | 7
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2280 | Block-05 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2026-01-10 08:00 | 2026-02-09 17:00 | 2026-01-12 08:00 | 2026-02-07 17:00 | 1 | 5928 | Number | 5928 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1025 | Block-01 -Array Earthing | Completed | Task Dependent | 2026-01-10 08:00 | 2026-02-04 17:00 | 2026-01-14 08:00 | 2026-02-19 17:00 | 1 | 5.059 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2935 | Block-07 -Piling - Inverters | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-25 17:00 | 2026-01-12 08:00 | 2026-03-27 17:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1960 | Block-04 -Piling - MMS (Marking, Auguring & Concreting) | Completed | Task Dependent | 2026-01-10 08:00 | 2026-02-09 17:00 | 2026-01-12 08:00 | 2026-04-16 10:00 | 1 | 5928 | Number | 5928 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3905 | Block-10 -Array Earthing | Completed | Task Dependent | 2026-01-10 08:00 | 2026-02-04 17:00 | 2026-01-12 08:00 | 2026-04-17 12:00 | 1 | 5.13 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1010 | Block-01 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-30 17:00 | 2026-01-12 08:00 | 2026-01-18 08:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6785 | Block-19 -Array Earthing | Completed | Task Dependent | 2026-01-10 08:00 | 2026-02-04 17:00 | 2026-01-15 08:00 | 2026-04-18 12:00 | 1 | 4.863 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3910 | Block-10 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2026-01-10 08:00 | 2026-02-07 17:00 | 2026-01-14 08:00 | 2026-04-22 10:00 | 1 | 493 | Tables | 493 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1015 | Block-01 -Piling - Inverters | Completed | Task Dependent | 2026-01-10 08:00 | 2026-01-25 17:00 | 2026-01-12 08:00 | 2026-01-18 17:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7750 | Block-22 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2026-01-11 08:00 | 2026-02-08 17:00 | 2026-01-01 08:00 | 2026-01-30 | 1 | 493 | Tables | 493 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1040 | Block-01 -MMS Erection - Purlin | Completed | Task Dependent | 2026-01-13 08:00 | 2026-02-10 17:00 | 2026-01-06 08:00 | 2026-02-14 17:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1035 | Block-01 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2026-01-13 08:00 | 2026-02-10 17:00 | 2026-01-06 08:00 | 2026-02-13 17:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8075 | Block-23 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2026-01-14 12:00 | 2026-02-12 12:00 | 2026-01-10 12:00 | 2026-05-07 12:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3915 | Block-10 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2026-01-14 12:00 | 2026-02-12 12:00 | 2026-01-14 12:00 | 2026-04-22 15:00 | 1 | 493 | Tables | 493 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5195 | Block-14 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2026-01-14 12:00 | 2026-02-12 12:00 | 2026-01-16 12:00 | 2026-05-19 14:00 | 1 | 493 | Tables | 493 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4235 | Block-11 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2026-01-14 12:00 | 2026-02-12 12:00 | 2026-01-14 12:00 | 2026-02-09 12:00 | 1 | 493 | Tables | 493 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7435 | Block-21 -MMS Erection - Transmission Shaft/Bracing | In Progress | Task Dependent | 2026-01-14 12:00 | 2026-02-12 12:00 | 2026-01-12 12:00 |  | 0.99 | 493 | Tables | 486 | 7
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4580 | Block-12 -DC Cable Laying | Completed | Task Dependent | 2026-01-15 11:00 | 2026-01-31 11:00 | 2025-12-12 11:00 | 2026-02-18 17:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7760 | Block-22 -MMS Erection - Purlin | Completed | Task Dependent | 2026-01-15 12:00 | 2026-02-13 12:00 | 2026-01-01 12:00 | 2026-02-18 17:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7755 | Block-22 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2026-01-15 12:00 | 2026-02-13 12:00 | 2026-01-01 12:00 | 2026-02-24 12:00 | 1 | 493 | Tables | 493 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2950 | Block-07 -MMS Erection - Torque Tube/Raftar | In Progress | Task Dependent | 2026-01-17 08:00 | 2026-02-14 17:00 | 2026-01-22 08:00 |  | 0.87 | 494 | Tables | 432 | 62
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3920 | Block-10 -MMS Erection - Purlin | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-14 17:00 | 2026-01-14 08:00 | 2026-04-23 10:00 | 1 | 487 | Tables | 470 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3570 | Block-09 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-06 17:00 | 2026-01-22 08:00 | 2026-02-02 17:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1645 | Block-03 -Pile Capping | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-16 17:00 | 2026-01-17 08:00 | 2026-05-14 10:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6150 | Block-17 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-14 17:00 | 2026-01-21 08:00 | 2026-02-25 17:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5490 | Block-15 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-06 17:00 | 2026-01-22 08:00 | 2026-02-14 17:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1965 | Block-04 -Pile Capping | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-16 17:00 | 2026-01-12 08:00 | 2026-04-16 10:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1335 | Block-02 -Piling - Inverters | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-02 17:00 | 2026-01-17 08:00 | 2026-02-18 17:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2610 | Block-06 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-06 17:00 | 2026-01-17 08:00 | 2026-02-02 17:00 | 1 | 621 | Number | 621 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5510 | Block-15 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-14 17:00 | 2026-01-21 08:00 | 2026-02-24 17:00 | 1 | 493 | Tables | 493 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2625 | Block-06 -Array Earthing | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-11 17:00 | 2026-01-17 08:00 | 2026-03-18 17:00 | 1 | 5 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3565 | Block-09 -Pile Capping | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-16 17:00 | 2026-01-20 08:00 | 2026-04-02 09:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7100 | Block-20 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-01-17 08:00 | 2026-01-27 17:00 | 2026-01-18 08:00 | 2026-05-14 11:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5815 | Block-16 -Piling - Inverters | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-02 17:00 | 2026-01-16 08:00 | 2026-04-15 12:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1330 | Block-02 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-06 17:00 | 2026-01-16 08:00 | 2026-02-18 17:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2615 | Block-06 -Piling - Inverters | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-02 17:00 | 2026-01-17 08:00 | 2026-02-02 17:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2630 | Block-06 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-14 17:00 | 2026-01-22 08:00 | 2026-03-22 17:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8080 | Block-23 -MMS Erection - Purlin | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-14 17:00 | 2026-01-19 08:00 | 2026-05-15 12:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6455 | Block-18 -Piling - Inverters | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-02 17:00 | 2026-01-21 08:00 | 2026-02-18 17:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6465 | Block-18 -Array Earthing | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-11 17:00 | 2026-01-17 08:00 | 2026-04-27 11:00 | 1 | 4.862 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4240 | Block-11 -MMS Erection - Purlin | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-14 17:00 | 2026-01-14 08:00 | 2026-02-09 17:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5810 | Block-16 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-06 17:00 | 2026-01-17 08:00 | 2026-04-14 09:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2285 | Block-05 -Pile Capping | Completed | Task Dependent | 2026-01-17 08:00 | 2026-02-16 17:00 | 2026-01-12 08:00 | 2026-03-13 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4570 | Block-12 -Module Installation | Completed | Task Dependent | 2026-01-17 11:00 | 2026-02-07 11:00 | 2025-12-30 11:00 | 2026-01-24 11:00 | 1 | 16.5 | MegaWatt DC | 17 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7440 | Block-21 -MMS Erection - Purlin | In Progress | Task Dependent | 2026-01-17 12:00 | 2026-02-15 12:00 | 2026-01-17 12:00 |  | 0.92 | 487 | Tables | 451 | 36
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3270 | Block-08 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2026-01-18 08:00 | 2026-02-15 17:00 | 2026-01-20 08:00 | 2026-05-20 09:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3575 | Block-09 -Piling - Inverters | Completed | Task Dependent | 2026-01-21 08:00 | 2026-02-06 17:00 | 2026-01-23 08:00 | 2026-02-02 17:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2635 | Block-06 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2026-01-21 08:00 | 2026-02-18 17:00 | 2026-01-22 08:00 | 2026-03-22 17:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2955 | Block-07 -MMS Erection - Transmission Shaft/Bracing | In Progress | Task Dependent | 2026-01-21 08:00 | 2026-02-18 17:00 | 2026-01-22 08:00 |  | 0.87 | 494 | Tables | 432 | 62
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6155 | Block-17 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2026-01-21 12:00 | 2026-02-19 12:00 | 2026-01-21 12:00 | 2026-02-25 12:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5515 | Block-15 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2026-01-21 12:00 | 2026-02-19 12:00 | 2026-01-21 12:00 | 2026-02-24 12:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6160 | Block-17 -MMS Erection - Purlin | Completed | Task Dependent | 2026-01-21 12:00 | 2026-02-19 12:00 | 2026-01-23 12:00 | 2026-02-25 12:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9350 | Block-27 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2026-01-22 08:00 | 2026-02-19 17:00 | 2025-12-09 08:00 | 2026-01-10 17:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3275 | Block-08 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2026-01-22 12:00 | 2026-02-20 12:00 | 2026-01-20 12:00 | 2026-05-20 14:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5200 | Block-14 -MMS Erection - Purlin | Completed | Task Dependent | 2026-01-23 08:00 | 2026-02-20 17:00 | 2026-01-21 08:00 | 2026-05-22 09:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3265 | Block-08 -Array Earthing | Completed | Task Dependent | 2026-01-24 08:00 | 2026-02-18 17:00 | 2026-01-28 08:00 | 2026-05-10 11:00 | 1 | 5.263 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1975 | Block-04 -Piling - Inverters | Completed | Task Dependent | 2026-01-24 08:00 | 2026-02-09 17:00 | 2026-01-25 08:00 | 2026-04-08 14:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8690 | Block-25 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2026-01-24 08:00 | 2026-02-13 17:00 | 2026-01-30 08:00 | 2026-03-14 17:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8385 | Block-24 -Array Earthing | Completed | Task Dependent | 2026-01-24 08:00 | 2026-02-18 17:00 | 2026-01-29 08:00 | 2026-04-05 10:00 | 1 | 4.868 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2290 | Block-05 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2026-01-24 08:00 | 2026-02-13 17:00 | 2026-01-29 08:00 | 2026-02-07 17:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2295 | Block-05 -Piling - Inverters | Completed | Task Dependent | 2026-01-24 08:00 | 2026-02-09 17:00 | 2026-01-23 08:00 | 2026-02-02 17:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9015 | Block-26 -Piling - Inverters | Completed | Task Dependent | 2026-01-24 08:00 | 2026-02-09 17:00 | 2026-01-30 08:00 | 2026-02-10 17:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9010 | Block-26 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2026-01-24 08:00 | 2026-02-13 17:00 | 2026-01-30 08:00 | 2026-02-10 17:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8695 | Block-25 -Piling - Inverters | Completed | Task Dependent | 2026-01-24 08:00 | 2026-02-09 17:00 | 2026-01-30 08:00 | 2026-03-14 17:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7785 | Block-22 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-01-27 08:00 | 2026-02-10 17:00 | 2026-01-26 08:00 | 2026-01-26 17:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2640 | Block-06 -MMS Erection - Purlin | Completed | Task Dependent | 2026-01-27 08:00 | 2026-02-23 17:00 | 2026-01-24 08:00 | 2026-03-22 17:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9355 | Block-27 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2026-01-27 12:00 | 2026-02-24 12:00 | 2025-12-09 12:00 | 2026-01-10 12:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2960 | Block-07 -MMS Erection - Purlin | In Progress | Task Dependent | 2026-01-28 08:00 | 2026-02-24 17:00 | 2026-01-29 08:00 |  | 0.7 | 487 | Tables | 341 | 146
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3280 | Block-08 -MMS Erection - Purlin | In Progress | Task Dependent | 2026-01-29 08:00 | 2026-02-25 17:00 | 2026-01-24 08:00 |  | 0.86 | 487 | Tables | 421 | 66
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9360 | Block-27 -MMS Erection - Purlin | Completed | Task Dependent | 2026-01-30 08:00 | 2026-02-26 17:00 | 2025-12-16 08:00 | 2026-01-14 12:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6470 | Block-18 -MMS Erection - Torque Tube/Raftar | In Progress | Task Dependent | 2026-01-31 08:00 | 2026-02-27 17:00 | 2026-02-05 08:00 |  | 0.97 | 494 | Tables | 478 | 16
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9025 | Block-26 -Array Earthing | Completed | Task Dependent | 2026-01-31 08:00 | 2026-02-24 17:00 | 2026-01-30 08:00 | 2026-03-18 17:00 | 1 | 4.87 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3590 | Block-09 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2026-01-31 08:00 | 2026-02-27 17:00 | 2026-02-02 08:00 | 2026-04-25 10:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1350 | Block-02 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2026-01-31 08:00 | 2026-02-27 17:00 | 2026-02-06 08:00 | 2026-03-12 17:00 | 1 | 315 | Tables | 315 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7140 | Block-20 -DC Cable Laying | Completed | Task Dependent | 2026-02-03 08:00 | 2026-02-17 17:00 | 2026-01-08 08:00 | 2026-03-26 17:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1360 | Block-02 -MMS Erection - Purlin | Completed | Task Dependent | 2026-02-04 08:00 | 2026-03-03 17:00 | 2026-02-06 08:00 | 2026-03-12 17:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5520 | Block-15 -MMS Erection - Purlin | Completed | Task Dependent | 2026-02-04 08:00 | 2026-03-03 17:00 | 2026-02-02 08:00 | 2026-02-24 17:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1355 | Block-02 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2026-02-04 08:00 | 2026-03-03 17:00 | 2026-02-06 08:00 | 2026-03-12 17:00 | 1 | 315 | Tables | 315 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4260 | Block-11 -DC Cable Laying | Completed | Task Dependent | 2026-02-04 11:00 | 2026-02-19 11:00 | 2026-01-01 11:00 | 2026-02-19 17:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6475 | Block-18 -MMS Erection - Transmission Shaft/Bracing | In Progress | Task Dependent | 2026-02-04 12:00 | 2026-03-04 12:00 | 2026-02-05 12:00 |  | 0.97 | 494 | Tables | 478 | 16
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3595 | Block-09 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2026-02-04 12:00 | 2026-03-04 12:00 | 2026-02-02 12:00 | 2026-04-25 15:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5220 | Block-14 -DC Cable Laying | Completed | Task Dependent | 2026-02-05 08:00 | 2026-02-19 17:00 | 2025-12-12 08:00 | 2026-03-27 17:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2310 | Block-05 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2026-02-07 08:00 | 2026-03-06 17:00 | 2026-02-12 08:00 | 2026-03-20 17:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4540 | Block-12 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-16 17:00 | 2026-02-12 08:00 | 2026-02-12 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5830 | Block-16 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2026-02-07 08:00 | 2026-03-06 17:00 | 2026-02-14 08:00 | 2026-05-11 10:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1990 | Block-04 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2026-02-07 08:00 | 2026-03-06 17:00 | 2026-02-14 08:00 | 2026-05-19 10:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6790 | Block-19 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2026-02-07 08:00 | 2026-03-06 17:00 | 2026-02-14 08:00 | 2026-05-06 12:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9030 | Block-26 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2026-02-07 08:00 | 2026-03-06 17:00 | 2026-02-10 08:00 | 2026-03-14 17:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1650 | Block-03 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-26 17:00 | 2026-02-13 08:00 | 2026-04-23 14:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3600 | Block-09 -MMS Erection - Purlin | Completed | Task Dependent | 2026-02-07 08:00 | 2026-03-06 17:00 | 2026-02-06 08:00 | 2026-04-25 13:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5495 | Block-15 -Piling - Inverters | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-22 17:00 | 2026-02-05 08:00 | 2026-02-05 17:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1655 | Block-03 -Piling - Inverters | Completed | Task Dependent | 2026-02-07 08:00 | 2026-02-22 17:00 | 2026-02-13 08:00 | 2026-04-17 10:00 | 1 | 93 | Number | 93 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8390 | Block-24 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2026-02-07 08:00 | 2026-03-06 17:00 | 2026-02-15 08:00 | 2026-05-09 10:00 | 1 | 493 | Tables | 493 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4910 | Block-13 -Module Installation | Completed | Task Dependent | 2026-02-08 11:00 | 2026-02-28 11:00 | 2026-01-21 11:00 | 2026-02-15 17:00 | 1 | 16.5 | MegaWatt DC | 17 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6820 | Block-19 -DC Cable Laying | Completed | Task Dependent | 2026-02-08 15:00 | 2026-02-23 15:00 | 2026-01-15 15:00 | 2026-03-26 17:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5540 | Block-15 -DC Cable Laying | Completed | Task Dependent | 2026-02-08 15:00 | 2026-02-23 15:00 | 2026-02-08 15:00 | 2026-02-19 17:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6480 | Block-18 -MMS Erection - Purlin | In Progress | Task Dependent | 2026-02-09 12:00 | 2026-03-09 12:00 | 2026-02-08 12:00 |  | 0.92 | 487 | Tables | 449 | 38
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7780 | Block-22 -DC Cable Laying | Completed | Task Dependent | 2026-02-09 15:00 | 2026-02-24 15:00 | 2025-12-30 15:00 | 2026-02-19 17:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6180 | Block-17 -DC Cable Laying | Completed | Task Dependent | 2026-02-09 15:00 | 2026-02-24 15:00 | 2025-12-26 15:00 | 2026-02-18 17:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7460 | Block-21 -DC Cable Laying | Completed | Task Dependent | 2026-02-09 15:00 | 2026-02-24 15:00 | 2025-12-29 15:00 | 2026-03-05 17:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9035 | Block-26 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2026-02-11 08:00 | 2026-03-10 17:00 | 2026-02-10 12:00 | 2026-03-14 12:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1995 | Block-04 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2026-02-11 08:00 | 2026-03-10 17:00 | 2026-02-14 08:00 | 2026-05-19 11:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2315 | Block-05 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2026-02-11 08:00 | 2026-03-10 17:00 | 2026-02-12 08:00 | 2026-03-20 17:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1050 | Block-01 -Module Installation | Completed | Task Dependent | 2026-02-11 11:00 | 2026-03-03 11:00 | 2026-01-19 11:00 | 2026-02-15 17:00 | 1 | 16.5 | MegaWatt DC | 17 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6800 | Block-19 -MMS Erection - Purlin | Completed | Task Dependent | 2026-02-11 12:00 | 2026-03-11 12:00 | 2026-02-14 12:00 | 2026-05-06 10:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6795 | Block-19 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2026-02-11 12:00 | 2026-03-11 12:00 | 2026-02-14 12:00 | 2026-05-06 10:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5835 | Block-16 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2026-02-11 12:00 | 2026-03-11 12:00 | 2026-02-14 12:00 | 2026-05-11 15:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8395 | Block-24 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2026-02-11 12:00 | 2026-03-11 12:00 | 2026-02-15 12:00 | 2026-05-09 15:00 | 1 | 493 | Tables | 493 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1060 | Block-01 -DC Cable Laying | Completed | Task Dependent | 2026-02-12 11:00 | 2026-02-27 11:00 | 2026-01-17 11:00 | 2026-02-18 17:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3940 | Block-10 -DC Cable Laying | Completed | Task Dependent | 2026-02-13 11:00 | 2026-02-28 11:00 | 2026-01-12 11:00 | 2026-03-27 17:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6165 | Block-17 -MMS - RFI Completion | Completed | Task Dependent | 2026-02-14 08:00 | 2026-03-13 17:00 | 2026-01-23 08:00 | 2026-01-26 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4270 | Block-11 -VOC Testing | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-28 17:00 | 2026-02-17 08:00 | 2026-02-24 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7765 | Block-22 -MMS - RFI Completion | Completed | Task Dependent | 2026-02-14 08:00 | 2026-03-13 17:00 | 2026-01-03 08:00 | 2026-01-30 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4905 | Block-13 -MMS - RFI Completion | Completed | Task Dependent | 2026-02-14 08:00 | 2026-03-13 17:00 | 2026-01-05 08:00 | 2026-02-11 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9365 | Block-27 -MMS - RFI Completion | Completed | Task Dependent | 2026-02-14 08:00 | 2026-03-13 17:00 | 2026-01-07 08:00 | 2026-01-25 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4605 | Block-12 -Robotic Structure - Bridges Installation | Completed | Task Dependent | 2026-02-14 08:00 | 2026-03-05 17:00 | 2026-02-14 08:00 | 2026-02-16 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4600 | Block-12 -Robotic Structure - Reverse Station Installation | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-23 17:00 | 2026-02-16 08:00 | 2026-02-18 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4565 | Block-12 -MMS - RFI Completion | Completed | Task Dependent | 2026-02-14 08:00 | 2026-03-13 17:00 | 2026-02-01 08:00 | 2026-02-17 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1020 | Block-01 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-23 17:00 | 2026-02-18 08:00 | 2026-02-18 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1045 | Block-01 -MMS - RFI Completion | Completed | Task Dependent | 2026-02-14 08:00 | 2026-03-13 17:00 | 2026-01-10 08:00 | 2026-02-14 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4220 | Block-11 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-23 17:00 | 2026-02-19 08:00 | 2026-02-19 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1345 | Block-02 -Array Earthing | Completed | Task Dependent | 2026-02-14 08:00 | 2026-03-10 17:00 | 2026-02-07 08:00 | 2026-03-15 17:00 | 1 | 4.934 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4880 | Block-13 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-23 17:00 | 2026-02-18 08:00 | 2026-05-20 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4285 | Block-11 -Robotic Structure - Bridges Installation | In Progress | Task Dependent | 2026-02-14 08:00 | 2026-03-05 17:00 | 2026-02-16 08:00 |  | 0.96 | 39 | Number | 38 | 1
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1070 | Block-01 -VOC Testing | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-28 17:00 | 2026-02-17 08:00 | 2026-02-26 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4575 | Block-12 -Module - RFI Completion | Completed | Task Dependent | 2026-02-14 08:00 | 2026-03-05 17:00 | 2026-02-12 08:00 | 2026-03-08 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4245 | Block-11 -MMS - RFI Completion | Completed | Task Dependent | 2026-02-14 08:00 | 2026-03-13 17:00 | 2026-01-19 08:00 | 2026-02-19 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6140 | Block-17 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-23 17:00 | 2026-02-19 08:00 | 2026-02-19 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4925 | Block-13 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-02-14 08:00 | 2026-02-28 17:00 | 2026-02-18 08:00 | 2026-02-18 17:00 | 1 | 48 | Number | 48 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9040 | Block-26 -MMS Erection - Purlin | Completed | Task Dependent | 2026-02-14 12:00 | 2026-03-14 12:00 | 2026-02-16 12:00 | 2026-03-15 12:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6500 | Block-18 -DC Cable Laying | Completed | Task Dependent | 2026-02-15 15:00 | 2026-03-02 15:00 | 2026-01-22 15:00 | 2026-04-12 14:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4930 | Block-13 -VOC Testing | Completed | Task Dependent | 2026-02-16 08:00 | 2026-03-02 17:00 | 2026-02-18 08:00 | 2026-02-19 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2320 | Block-05 -MMS Erection - Purlin | Completed | Task Dependent | 2026-02-16 08:00 | 2026-03-15 17:00 | 2026-02-19 08:00 | 2026-03-22 17:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6445 | Block-18 -Pile Capping | Completed | Task Dependent | 2026-02-16 10:10 | 2026-03-18 10:10 | 2025-12-17 10:10 | 2026-04-06 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4590 | Block-12 -VOC Testing | Completed | Task Dependent | 2026-02-16 11:00 | 2026-03-03 11:00 | 2026-01-21 11:00 | 2026-02-04 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1065 | Block-01 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-02-16 11:00 | 2026-03-08 11:00 | 2026-01-30 11:00 | 2026-02-19 17:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4250 | Block-11 -Module Installation | Completed | Task Dependent | 2026-02-16 11:00 | 2026-03-08 11:00 | 2026-01-25 11:00 | 2026-02-21 17:00 | 1 | 16.5 | MegaWatt DC | 17 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4595 | Block-12 -Robotic Structure - Docking Station Installation | Completed | Task Dependent | 2026-02-17 08:00 | 2026-02-26 17:00 | 2026-02-13 08:00 | 2026-02-13 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2660 | Block-06 -DC Cable Laying | Completed | Task Dependent | 2026-02-17 11:00 | 2026-03-04 11:00 | 2026-01-19 11:00 | 2026-03-09 17:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6170 | Block-17 -Module Installation | Completed | Task Dependent | 2026-02-17 15:00 | 2026-03-09 15:00 | 2026-01-27 15:00 | 2026-03-03 17:00 | 1 | 16.5 | MegaWatt DC | 17 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9370 | Block-27 -Module Installation | Completed | Task Dependent | 2026-02-18 16:00 | 2026-02-28 16:00 | 2026-01-20 16:00 | 2026-03-01 17:00 | 1 | 16.5 | MegaWatt DC | 17 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9380 | Block-27 -DC Cable Laying | Completed | Task Dependent | 2026-02-20 15:00 | 2026-03-07 15:00 | 2025-12-13 15:00 | 2026-02-19 17:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3585 | Block-09 -Array Earthing | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-17 17:00 | 2026-02-26 08:00 | 2026-03-30 10:00 | 1 | 5.262 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4610 | Block-12 -Robot Installation | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-04 17:00 | 2026-02-21 08:00 | 2026-02-22 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1085 | Block-01 -Robotic Structure - Bridges Installation | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-12 17:00 | 2026-02-23 08:00 | 2026-04-24 15:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8400 | Block-24 -MMS Erection - Purlin | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-20 17:00 | 2026-02-23 08:00 | 2026-05-09 12:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8710 | Block-25 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-20 17:00 | 2026-02-24 08:00 | 2026-03-16 17:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3925 | Block-10 -MMS - RFI Completion | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-20 17:00 | 2026-01-15 08:00 | 2026-04-25 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8085 | Block-23 -MMS - RFI Completion | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-20 17:00 | 2026-01-21 08:00 | 2026-05-15 15:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6805 | Block-19 -MMS - RFI Completion | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-20 17:00 | 2026-02-16 08:00 | 2026-05-06 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6485 | Block-18 -MMS - RFI Completion | In Progress | Task Dependent | 2026-02-21 08:00 | 2026-03-20 17:00 | 2026-02-09 08:00 |  | 0.65 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7445 | Block-21 -MMS - RFI Completion | In Progress | Task Dependent | 2026-02-21 08:00 | 2026-03-20 17:00 | 2026-01-19 08:00 |  | 0.67 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7125 | Block-20 -MMS - RFI Completion | In Progress | Task Dependent | 2026-02-21 08:00 | 2026-03-20 17:00 | 2026-01-09 08:00 |  | 0.42 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4940 | Block-13 -Robotic Structure - Reverse Station Installation | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-02 17:00 | 2026-02-23 08:00 | 2026-02-23 17:00 | 1 | 39 | Number | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1365 | Block-02 -MMS - RFI Completion | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-20 17:00 | 2026-02-09 08:00 | 2026-03-13 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2645 | Block-06 -MMS - RFI Completion | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-20 17:00 | 2026-01-26 08:00 | 2026-03-22 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9045 | Block-26 -MMS - RFI Completion | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-20 17:00 | 2026-02-18 08:00 | 2026-03-15 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4275 | Block-11 -Robotic Structure - Docking Station Installation | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-02 17:00 | 2026-02-22 08:00 | 2026-02-22 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1985 | Block-04 -Array Earthing | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-17 17:00 | 2026-02-26 08:00 | 2026-04-28 14:00 | 1 | 5 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5205 | Block-14 -MMS - RFI Completion | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-20 17:00 | 2026-01-23 08:00 | 2026-05-23 10:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5545 | Block-15 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-02-21 08:00 | 2026-03-07 17:00 | 2026-02-22 08:00 | 2026-03-04 17:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7770 | Block-22 -Module Installation | Completed | Task Dependent | 2026-02-21 11:00 | 2026-03-13 11:00 | 2026-02-02 11:00 | 2026-02-19 17:00 | 1 | 16.5 | MegaWatt DC | 17 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9385 | Block-27 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-02-21 11:00 | 2026-03-08 11:00 | 2026-01-25 11:00 | 2026-03-06 17:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4585 | Block-12 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-02-21 11:00 | 2026-03-08 11:00 | 2026-01-26 11:00 | 2026-01-26 11:00 | 1 | 48 | Number | 48 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3285 | Block-08 -MMS - RFI Completion | In Progress | Task Dependent | 2026-02-22 08:00 | 2026-03-21 17:00 | 2026-01-25 08:00 |  | 0.34 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2665 | Block-06 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-02-22 11:00 | 2026-03-14 11:00 | 2026-01-26 11:00 | 2026-03-16 13:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4265 | Block-11 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-02-22 11:00 | 2026-03-09 11:00 | 2026-01-27 11:00 | 2026-02-18 17:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7465 | Block-21 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-02-22 15:00 | 2026-03-09 15:00 | 2026-01-26 15:00 | 2026-01-27 15:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8405 | Block-24 -MMS - RFI Completion | Completed | Task Dependent | 2026-02-23 08:00 | 2026-03-22 17:00 | 2026-02-24 08:00 | 2026-05-12 11:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4950 | Block-13 -Robot Installation | Completed | Task Dependent | 2026-02-23 08:00 | 2026-03-06 17:00 | 2026-02-21 08:00 | 2026-02-21 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1090 | Block-01 -Robot Installation | Completed | Task Dependent | 2026-02-23 08:00 | 2026-03-06 17:00 | 2026-02-23 08:00 | 2026-02-23 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4280 | Block-11 -Robotic Structure - Reverse Station Installation | Completed | Task Dependent | 2026-02-24 08:00 | 2026-03-05 17:00 | 2026-02-18 08:00 | 2026-02-20 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3300 | Block-08 -DC Cable Laying | Completed | Task Dependent | 2026-02-24 08:00 | 2026-03-10 17:00 | 2026-01-28 08:00 | 2026-04-12 14:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4935 | Block-13 -Robotic Structure - Docking Station Installation | Completed | Task Dependent | 2026-02-24 08:00 | 2026-03-05 17:00 | 2026-02-19 08:00 | 2026-02-19 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1080 | Block-01 -Robotic Structure - Reverse Station Installation | Completed | Task Dependent | 2026-02-24 08:00 | 2026-03-05 17:00 | 2026-02-19 08:00 | 2026-02-27 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1075 | Block-01 -Robotic Structure - Docking Station Installation | Completed | Task Dependent | 2026-02-24 08:00 | 2026-03-05 17:00 | 2026-02-19 08:00 | 2026-02-19 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3930 | Block-10 -Module Installation | Completed | Task Dependent | 2026-02-24 11:00 | 2026-03-16 11:00 | 2026-02-04 11:00 | 2026-05-22 10:00 | 1 | 16.5 | MegaWatt DC | 17 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8420 | Block-24 -DC Cable Laying | Completed | Task Dependent | 2026-02-24 12:00 | 2026-03-11 12:00 | 2026-01-29 12:00 | 2026-03-02 17:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4290 | Block-11 -Robot Installation | Completed | Task Dependent | 2026-02-25 08:00 | 2026-03-08 17:00 | 2026-02-22 08:00 | 2026-02-22 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6490 | Block-18 -Module Installation | In Progress | Task Dependent | 2026-02-25 12:00 | 2026-03-17 12:00 | 2026-02-15 12:00 |  | 0.87 | 16.5 | MegaWatt DC | 15 | 2
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8715 | Block-25 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2026-02-25 12:00 | 2026-03-25 12:00 | 2026-02-24 12:00 | 2026-03-16 12:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8720 | Block-25 -MMS Erection - Purlin | Completed | Task Dependent | 2026-02-25 12:00 | 2026-03-25 12:00 | 2026-02-27 12:00 | 2026-03-17 12:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2965 | Block-07 -MMS - RFI Completion | In Progress | Task Dependent | 2026-02-26 08:00 | 2026-03-25 17:00 | 2026-01-30 08:00 |  | 0.45 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2325 | Block-05 -MMS - RFI Completion | Completed | Task Dependent | 2026-02-26 08:00 | 2026-03-25 17:00 | 2026-02-20 08:00 | 2026-03-22 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5525 | Block-15 -MMS - RFI Completion | Completed | Task Dependent | 2026-02-26 08:00 | 2026-03-25 17:00 | 2026-01-25 08:00 | 2026-02-05 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5840 | Block-16 -MMS Erection - Purlin | Completed | Task Dependent | 2026-02-26 12:00 | 2026-03-26 12:00 | 2026-02-22 12:00 | 2026-05-12 15:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8725 | Block-25 -MMS - RFI Completion | Completed | Task Dependent | 2026-02-27 12:00 | 2026-03-27 12:00 | 2026-02-28 12:00 | 2026-03-16 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6825 | Block-19 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-02-27 15:00 | 2026-03-14 15:00 | 2026-01-27 15:00 | 2026-03-26 17:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8100 | Block-23 -DC Cable Laying | Completed | Task Dependent | 2026-02-27 16:00 | 2026-03-14 16:00 | 2026-01-02 16:00 | 2026-03-23 17:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9390 | Block-27 -VOC Testing | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-14 17:00 | 2026-02-03 08:00 | 2026-03-06 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9340 | Block-27 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-09 17:00 | 2026-03-01 08:00 | 2026-03-01 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7800 | Block-22 -Robotic Structure - Reverse Station Installation | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-09 17:00 | 2026-02-28 08:00 | 2026-03-06 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7795 | Block-22 -Robotic Structure - Docking Station Installation | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-09 17:00 | 2026-03-03 08:00 | 2026-03-03 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1370 | Block-02 -Module Installation | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-19 17:00 | 2026-02-13 08:00 | 2026-03-15 17:00 | 1 | 10.88 | MegaWatt DC | 11 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5565 | Block-15 -Robotic Structure - Bridges Installation | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-19 17:00 | 2026-03-03 08:00 | 2026-03-04 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7450 | Block-21 -Module Installation | In Progress | Task Dependent | 2026-02-28 08:00 | 2026-03-19 17:00 | 2026-02-19 08:00 |  | 0.82 | 16.5 | MegaWatt DC | 14 | 2.5
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5500 | Block-15 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-09 17:00 | 2026-03-02 08:00 | 2026-03-02 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5560 | Block-15 -Robotic Structure - Reverse Station Installation | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-09 17:00 | 2026-03-04 08:00 | 2026-03-04 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7805 | Block-22 -Robotic Structure - Bridges Installation | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-19 17:00 | 2026-03-03 08:00 | 2026-03-04 17:00 | 1 | 39 | Number | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7740 | Block-22 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-09 17:00 | 2026-03-02 08:00 | 2026-03-02 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9400 | Block-27 -Robotic Structure - Reverse Station Installation | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-09 17:00 | 2026-03-04 08:00 | 2026-03-06 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9405 | Block-27 -Robotic Structure - Bridges Installation | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-19 17:00 | 2026-03-03 08:00 | 2026-03-04 17:00 | 1 | 39 | Number | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5555 | Block-15 -Robotic Structure - Docking Station Installation | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-09 17:00 | 2026-03-03 08:00 | 2026-03-03 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7775 | Block-22 -Module - RFI Completion | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-19 17:00 | 2026-03-06 08:00 | 2026-05-13 09:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5550 | Block-15 -VOC Testing | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-14 17:00 | 2026-03-03 08:00 | 2026-03-04 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6195 | Block-17 -Robotic Structure - Docking Station Installation | Completed | Task Dependent | 2026-02-28 08:00 | 2026-03-09 17:00 | 2026-03-03 08:00 | 2026-03-03 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5845 | Block-16 -MMS - RFI Completion | Completed | Task Dependent | 2026-02-28 12:00 | 2026-03-28 12:00 | 2026-02-24 12:00 | 2026-05-13 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9060 | Block-26 -DC Cable Laying | Completed | Task Dependent | 2026-02-28 15:00 | 2026-03-15 15:00 | 2026-01-30 15:00 | 2026-03-11 17:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8105 | Block-23 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-02-28 15:00 | 2026-03-15 15:00 | 2026-02-03 15:00 | 2026-04-23 14:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1380 | Block-02 -DC Cable Laying | Completed | Task Dependent | 2026-03-01 08:00 | 2026-03-15 17:00 | 2026-02-09 | 2026-03-15 17:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3605 | Block-09 -MMS - RFI Completion | Completed | Task Dependent | 2026-03-01 08:00 | 2026-03-28 17:00 | 2026-02-07 08:00 | 2026-04-28 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5530 | Block-15 -Module Installation | Completed | Task Dependent | 2026-03-01 11:00 | 2026-03-21 11:00 | 2026-02-06 11:00 | 2026-02-25 17:00 | 1 | 16.5 | MegaWatt DC | 17 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5570 | Block-15 -Robot Installation | Completed | Task Dependent | 2026-03-04 08:00 | 2026-03-15 17:00 | 2026-03-04 08:00 | 2026-03-04 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6210 | Block-17 -Robot Installation | In Progress | Task Dependent | 2026-03-04 08:00 | 2026-03-15 17:00 | 2026-03-04 08:00 |  | 0.36 | 39 | Number | 15 | 24
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7810 | Block-22 -Robot Installation | Completed | Task Dependent | 2026-03-04 08:00 | 2026-03-15 17:00 | 2026-03-04 08:00 | 2026-03-04 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4255 | Block-11 -Module - RFI Completion | In Progress | Task Dependent | 2026-03-04 08:00 | 2026-03-23 17:00 | 2026-02-12 08:00 |  | 0.73 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9410 | Block-27 -Robot Installation | Completed | Task Dependent | 2026-03-04 08:00 | 2026-03-15 17:00 | 2026-03-03 08:00 | 2026-03-03 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6185 | Block-17 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-03-05 08:00 | 2026-03-19 17:00 | 2026-02-19 08:00 | 2026-03-02 17:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6190 | Block-17 -VOC Testing | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-21 17:00 | 2026-02-19 08:00 | 2026-03-02 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8705 | Block-25 -Array Earthing | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-24 17:00 | 2026-03-10 08:00 | 2026-03-22 17:00 | 1 | 4.869 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7790 | Block-22 -VOC Testing | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-21 17:00 | 2026-02-18 08:00 | 2026-02-26 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2305 | Block-05 -Array Earthing | Completed | Task Dependent | 2026-03-07 08:00 | 2026-03-26 17:00 | 2026-03-10 08:00 | 2026-03-18 17:00 | 1 | 5.011 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6810 | Block-19 -Module Installation | Completed | Task Dependent | 2026-03-09 11:00 | 2026-03-29 11:00 | 2026-02-18 11:00 | 2026-05-07 12:00 | 1 | 16.5 | MegaWatt DC | 17 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9050 | Block-26 -Module Installation | Completed | Task Dependent | 2026-03-09 15:00 | 2026-03-29 15:00 | 2026-02-20 15:00 | 2026-03-18 11:00 | 1 | 16.5 | MegaWatt DC | 17 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9395 | Block-27 -Robotic Structure - Docking Station Installation | Completed | Task Dependent | 2026-03-10 08:00 | 2026-03-19 17:00 | 2026-03-01 08:00 | 2026-03-01 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8740 | Block-25 -DC Cable Laying | Completed | Task Dependent | 2026-03-13 15:00 | 2026-03-28 15:00 | 2026-03-13 15:00 | 2026-03-22 17:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1385 | Block-02 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-03-14 08:00 | 2026-04-03 12:00 | 2026-03-15 08:00 | 2026-03-20 17:00 | 1 | 30 | Number | 30 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8425 | Block-24 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-28 17:00 | 2026-03-01 08:00 | 2026-04-08 14:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1665 | Block-03 -Array Earthing | Completed | Task Dependent | 2026-03-14 08:00 | 2026-04-09 15:00 | 2026-03-16 08:00 | 2026-03-16 15:00 | 1 | 5.258 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9020 | Block-26 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-23 17:00 | 2026-03-18 08:00 | 2026-03-18 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2300 | Block-05 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-23 17:00 | 2026-03-18 08:00 | 2026-03-18 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1340 | Block-02 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-23 17:00 | 2026-03-18 08:00 | 2026-03-18 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8700 | Block-25 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-03-14 08:00 | 2026-03-23 17:00 | 2026-03-18 08:00 | 2026-03-18 17:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2650 | Block-06 -Module Installation | Completed | Task Dependent | 2026-03-14 11:00 | 2026-04-03 15:00 | 2026-02-22 11:00 | 2026-03-22 12:00 | 1 | 16.5 | MegaWatt DC | 17 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9065 | Block-26 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-03-15 15:00 | 2026-03-30 15:00 | 2026-02-19 15:00 | 2026-03-20 11:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8090 | Block-23 -Module Installation | Completed | Task Dependent | 2026-03-16 08:00 | 2026-03-25 17:00 | 2026-02-23 08:00 | 2026-05-21 10:00 | 1 | 16.5 | MegaWatt DC | 17 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8410 | Block-24 -Module Installation | Completed | Task Dependent | 2026-03-18 08:00 | 2026-03-27 17:00 | 2026-02-26 08:00 | 2026-05-16 10:00 | 1 | 16.5 | MegaWatt DC | 17 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2330 | Block-05 -Module Installation | Completed | Task Dependent | 2026-03-19 08:00 | 2026-04-09 15:00 | 2026-03-07 08:00 | 2026-03-23 17:00 | 1 | 16.5 | MegaWatt DC | 17 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2340 | Block-05 -DC Cable Laying | Completed | Task Dependent | 2026-03-20 08:00 | 2026-04-04 14:00 | 2026-03-10 08:00 | 2026-03-18 17:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8745 | Block-25 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-03-21 08:00 | 2026-04-06 09:00 | 2026-03-22 15:00 | 2026-03-23 17:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1390 | Block-02 -VOC Testing | Completed | Task Dependent | 2026-03-21 08:00 | 2026-04-06 09:00 | 2026-03-15 08:00 | 2026-03-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5860 | Block-16 -DC Cable Laying | Completed | Task Dependent | 2026-03-21 08:00 | 2026-04-06 09:00 | 2026-03-23 08:00 | 2026-05-06 12:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8110 | Block-23 -VOC Testing | In Progress | Task Dependent | 2026-03-21 08:00 | 2026-04-06 09:00 | 2026-03-24 08:00 |  | 0.98 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2945 | Block-07 -Array Earthing | Completed | Task Dependent | 2026-03-21 08:00 | 2026-04-18 15:00 | 2026-03-23 08:00 | 2026-04-20 12:00 | 1 | 4.92 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5825 | Block-16 -Array Earthing | Completed | Task Dependent | 2026-03-21 08:00 | 2026-04-18 15:00 | 2026-03-23 08:00 | 2026-04-27 12:00 | 1 | 4.86 | Kilometer | 5 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5225 | Block-14 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-03-21 08:00 | 2026-04-06 09:00 | 2026-03-10 08:00 | 2026-03-30 09:00 | 1 | 48 | Number | 48 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3945 | Block-10 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-03-21 08:00 | 2026-04-06 09:00 | 2026-03-26 08:00 | 2026-04-07 09:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5850 | Block-16 -Module Installation | Completed | Task Dependent | 2026-03-21 15:00 | 2026-04-13 12:00 | 2026-02-27 15:00 | 2026-05-15 09:00 | 1 | 16.5 | MegaWatt DC | 17 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6830 | Block-19 -VOC Testing | Completed | Task Dependent | 2026-03-22 08:00 | 2026-04-07 11:00 | 2026-03-24 08:00 | 2026-05-15 10:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2345 | Block-05 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-03-22 08:00 | 2026-04-13 14:00 | 2026-02-16 08:00 | 2026-03-20 17:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3610 | Block-09 -Module Installation | Completed | Task Dependent | 2026-03-22 11:00 | 2026-04-14 10:00 | 2026-02-22 11:00 | 2026-04-26 12:00 | 1 | 16.5 | MegaWatt DC | 17 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3620 | Block-09 -DC Cable Laying | Completed | Task Dependent | 2026-03-23 11:00 | 2026-04-09 09:00 | 2026-02-26 11:00 | 2026-03-23 17:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2020 | Block-04 -DC Cable Laying | Completed | Task Dependent | 2026-03-23 11:00 | 2026-04-09 09:00 | 2026-02-26 11:00 | 2026-04-20 10:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8750 | Block-25 -VOC Testing | Completed | Task Dependent | 2026-03-24 08:00 | 2026-04-09 15:00 | 2026-03-22 15:00 | 2026-03-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9070 | Block-26 -VOC Testing | Completed | Task Dependent | 2026-03-24 15:00 | 2026-04-10 15:00 | 2026-03-14 15:00 | 2026-03-20 11:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3625 | Block-09 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-03-26 08:00 | 2026-04-12 12:00 | 2026-03-13 08:00 | 2026-03-27 17:00 | 1 | 48 | Number | 48 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2985 | Block-07 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-03-26 08:00 | 2026-04-18 15:00 | 2026-03-26 08:00 | 2026-04-11 15:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2670 | Block-06 -VOC Testing | In Progress | Task Dependent | 2026-03-27 11:00 | 2026-04-14 10:00 | 2026-03-14 11:00 |  | 0.72 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3950 | Block-10 -VOC Testing | In Progress | Task Dependent | 2026-03-28 08:00 | 2026-04-15 09:00 | 2026-03-29 08:00 |  | 0.97 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1970 | Block-04 -Piling - LT Cable Hanger System | Completed | Task Dependent | 2026-03-28 08:00 | 2026-04-21 12:00 | 2026-03-28 08:00 | 2026-04-23 14:00 | 1 | 660 | Number | 660 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1670 | Block-03 -MMS Erection - Torque Tube/Raftar | Completed | Task Dependent | 2026-03-28 08:00 | 2026-05-01 14:00 | 2026-04-01 08:00 | 2026-05-12 10:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3580 | Block-09 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-03-28 08:00 | 2026-04-08 13:00 | 2026-04-02 08:00 | 2026-04-02 13:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2350 | Block-05 -VOC Testing | Completed | Task Dependent | 2026-03-29 08:00 | 2026-04-16 11:00 | 2026-03-13 08:00 | 2026-03-22 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5210 | Block-14 -Module Installation | Completed | Task Dependent | 2026-03-29 08:00 | 2026-04-22 14:00 | 2026-04-01 08:00 | 2026-05-23 14:00 | 1 | 16.5 | MegaWatt DC | 17 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2000 | Block-04 -MMS Erection - Purlin | Completed | Task Dependent | 2026-03-29 08:00 | 2026-05-03 09:00 | 2026-02-20 08:00 | 2026-05-19 11:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1680 | Block-03 -MMS Erection - Purlin | Completed | Task Dependent | 2026-04-01 08:00 | 2026-05-06 15:00 | 2026-04-02 08:00 | 2026-05-13 11:00 | 1 | 487 | Tables | 487 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1675 | Block-03 -MMS Erection - Transmission Shaft/Bracing | Completed | Task Dependent | 2026-04-01 08:00 | 2026-05-06 15:00 | 2026-04-01 08:00 | 2026-05-12 11:00 | 1 | 494 | Tables | 494 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5865 | Block-16 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-04-01 12:00 | 2026-04-20 14:00 | 2026-04-01 12:00 | 2026-05-06 13:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3630 | Block-09 -VOC Testing | Completed | Task Dependent | 2026-04-02 10:00 | 2026-04-21 12:00 | 2026-03-16 10:00 | 2026-05-16 10:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5870 | Block-16 -VOC Testing | Completed | Task Dependent | 2026-04-02 14:00 | 2026-04-22 09:00 | 2026-03-30 14:00 | 2026-05-16 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9375 | Block-27 -Module - RFI Completion | Completed | Task Dependent | 2026-04-04 08:00 | 2026-04-29 13:00 | 2026-04-09 08:00 | 2026-05-13 11:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9055 | Block-26 -Module - RFI Completion | Completed | Task Dependent | 2026-04-04 08:00 | 2026-04-29 13:00 | 2026-04-09 08:00 | 2026-05-13 13:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5535 | Block-15 -Module - RFI Completion | In Progress | Task Dependent | 2026-04-04 08:00 | 2026-04-29 13:00 | 2026-04-09 08:00 |  | 0.99 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1375 | Block-02 -Module - RFI Completion | In Progress | Task Dependent | 2026-04-04 08:00 | 2026-04-29 13:00 | 2026-04-07 08:00 |  | 0.66 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1980 | Block-04 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-04-04 08:00 | 2026-04-16 14:00 | 2026-04-09 08:00 | 2026-04-09 14:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1055 | Block-01 -Module - RFI Completion | In Progress | Task Dependent | 2026-04-04 08:00 | 2026-04-29 13:00 | 2026-04-07 08:00 |  | 0.6 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6505 | Block-18 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-04-04 12:00 | 2026-04-23 14:00 | 2026-04-09 12:00 | 2026-04-28 10:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8730 | Block-25 -Module Installation | Completed | Task Dependent | 2026-04-04 12:00 | 2026-04-17 11:00 | 2026-03-01 12:00 | 2026-03-17 17:00 | 1 | 16.5 | MegaWatt DC | 17 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2970 | Block-07 -Module Installation | In Progress | Task Dependent | 2026-04-05 10:00 | 2026-04-30 15:00 | 2026-04-04 10:00 |  | 0.69 | 16.5 | MegaWatt DC | 12 | 4.5
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2980 | Block-07 -DC Cable Laying | Completed | Task Dependent | 2026-04-06 09:00 | 2026-04-25 11:00 | 2026-03-23 09:00 | 2026-04-07 10:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1685 | Block-03 -MMS - RFI Completion | Completed | Task Dependent | 2026-04-11 08:00 | 2026-05-16 15:00 | 2026-04-03 08:00 | 2026-05-14 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2005 | Block-04 -MMS - RFI Completion | In Progress | Task Dependent | 2026-04-11 08:00 | 2026-05-16 15:00 | 2026-02-23 08:00 |  | 0.72 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7470 | Block-21 -VOC Testing | In Progress | Task Dependent | 2026-04-12 10:00 | 2026-05-01 12:00 | 2026-04-09 10:00 |  | 0.75 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5230 | Block-14 -VOC Testing | In Progress | Task Dependent | 2026-04-14 10:00 | 2026-05-03 12:00 | 2026-04-10 10:00 |  | 0.94 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1700 | Block-03 -DC Cable Laying | Completed | Task Dependent | 2026-04-15 09:00 | 2026-05-04 11:00 | 2026-03-24 09:00 | 2026-04-11 12:00 | 1 | 122 | Kilometer | 122 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7145 | Block-20 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-04-16 09:00 | 2026-05-05 11:00 | 2026-03-26 09:00 | 2026-04-11 11:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6510 | Block-18 -VOC Testing | In Progress | Task Dependent | 2026-04-17 11:00 | 2026-05-06 13:00 | 2026-04-17 11:00 |  | 0.79 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8430 | Block-24 -VOC Testing | Completed | Task Dependent | 2026-04-18 08:00 | 2026-05-07 10:00 | 2026-04-17 08:00 | 2026-05-18 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8765 | Block-25 -Robotic Structure - Bridges Installation | Completed | Task Dependent | 2026-04-18 08:00 | 2026-04-30 14:00 | 2026-04-24 08:00 | 2026-04-24 14:00 | 1 | 39 | Number | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9075 | Block-26 -Robotic Structure - Docking Station Installation | Completed | Task Dependent | 2026-04-18 08:00 | 2026-04-30 14:00 | 2026-04-24 08:00 | 2026-04-24 14:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9085 | Block-26 -Robotic Structure - Bridges Installation | Completed | Task Dependent | 2026-04-18 08:00 | 2026-05-13 13:00 | 2026-04-24 08:00 | 2026-04-24 13:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2365 | Block-05 -Robotic Structure - Bridges Installation | Completed | Task Dependent | 2026-04-18 08:00 | 2026-05-13 13:00 | 2026-04-24 08:00 | 2026-04-24 13:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2990 | Block-07 -VOC Testing | In Progress | Task Dependent | 2026-04-21 10:00 | 2026-05-10 12:00 | 2026-04-12 10:00 |  | 0.7 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2010 | Block-04 -Module Installation | In Progress | Task Dependent | 2026-04-22 14:00 | 2026-05-18 12:00 | 2026-03-28 14:00 |  | 0.98 | 16.5 | MegaWatt DC | 16 | 0.5
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2370 | Block-05 -Robot Installation | Completed | Task Dependent | 2026-04-23 09:00 | 2026-05-08 12:00 | 2026-04-24 09:00 | 2026-04-24 12:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1690 | Block-03 -Module Installation | In Progress | Task Dependent | 2026-04-23 14:00 | 2026-05-19 12:00 | 2026-04-05 14:00 |  | 0.94 | 16.5 | MegaWatt DC | 16 | 0.5
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1710 | Block-03 -VOC Testing | In Progress | Task Dependent | 2026-04-23 14:00 | 2026-05-13 09:00 | 2026-04-15 14:00 |  | 0.93 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7130 | Block-20 -Module Installation | In Progress | Task Dependent | 2026-04-25 12:00 | 2026-05-21 10:00 | 2026-04-05 12:00 |  | 0.79 | 16.5 | MegaWatt DC | 14 | 2.5
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1705 | Block-03 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-04-29 08:00 | 2026-05-24 13:00 | 2026-04-14 08:00 | 2026-04-17 12:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6780 | Block-19 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-05-02 08:00 | 2026-05-14 14:00 | 2026-05-10 08:00 | 2026-05-10 14:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3290 | Block-08 -Module Installation | In Progress | Task Dependent | 2026-05-02 10:00 | 2026-05-27 15:00 | 2026-04-06 10:00 |  | 0.83 | 16.5 | MegaWatt DC | 15 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2025 | Block-04 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-05-02 14:00 | 2026-05-28 12:00 | 2026-04-11 14:00 | 2026-04-28 09:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2690 | Block-06 -Robot Installation | In Progress | Task Dependent | 2026-05-06 08:00 | 2026-05-21 11:00 | 2026-04-24 08:00 |  | 0.49 | 39 | Number | 20 | 19
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7150 | Block-20 -VOC Testing | In Progress | Task Dependent | 2026-05-07 13:00 | 2026-05-26 15:00 | 2026-04-12 13:00 |  | 0.74 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4915 | Block-13 -Module - RFI Completion | In Progress | Task Dependent | 2026-05-10 08:00 | 2026-06-04 13:00 | 2026-05-13 08:00 |  | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8060 | Block-23 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-05-10 08:00 | 2026-05-22 14:00 | 2026-05-13 08:00 | 2026-05-13 14:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3615 | Block-09 -Module - RFI Completion | In Progress | Task Dependent | 2026-05-10 08:00 | 2026-06-04 13:00 | 2026-05-13 08:00 |  | 0.23 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2335 | Block-05 -Module - RFI Completion | In Progress | Task Dependent | 2026-05-10 08:00 | 2026-06-04 13:00 | 2026-05-13 08:00 |  | 0.78 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8380 | Block-24 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-05-10 08:00 | 2026-05-22 14:00 | 2026-05-13 08:00 | 2026-05-20 11:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6460 | Block-18 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-05-10 08:00 | 2026-05-22 14:00 | 2026-05-14 08:00 | 2026-05-14 14:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3305 | Block-08 -Module Interconnection & MC4 Termination | Completed | Task Dependent | 2026-05-10 08:00 | 2026-05-29 10:00 | 2026-04-10 08:00 | 2026-04-28 11:00 | 1 | 47 | Number | 47 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2655 | Block-06 -Module - RFI Completion | Completed | Task Dependent | 2026-05-10 08:00 | 2026-06-04 13:00 | 2026-05-13 08:00 | 2026-05-13 13:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5820 | Block-16 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-05-10 08:00 | 2026-05-22 14:00 | 2026-05-14 08:00 | 2026-05-14 14:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7420 | Block-21 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-05-10 08:00 | 2026-05-22 14:00 | 2026-05-11 08:00 | 2026-05-11 14:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8735 | Block-25 -Module - RFI Completion | In Progress | Task Dependent | 2026-05-10 08:00 | 2026-05-22 14:00 | 2026-05-13 08:00 |  | 0.65 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2030 | Block-04 -VOC Testing | In Progress | Task Dependent | 2026-05-11 14:00 | 2026-05-31 09:00 | 2026-04-15 14:00 |  | 0.98 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2015 | Block-04 -Module - RFI Completion | In Progress | Task Dependent | 2026-05-12 12:00 | 2026-06-07 10:00 | 2026-05-13 12:00 |  | 0.36 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3310 | Block-08 -VOC Testing | In Progress | Task Dependent | 2026-05-20 13:00 | 2026-06-08 15:00 | 2026-04-28 13:00 |  | 0.28 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7485 | Block-21 -Robotic Structure - Bridges Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3645 | Block-09 -Robotic Structure - Bridges Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3635 | Block-09 -Robotic Structure - Docking Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3640 | Block-09 -Robotic Structure - Reverse Station Installation | Completed | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 | 2026-05-22 08:00 | 2026-05-22 14:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2940 | Block-07 -Piling - Robotic Docking System | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1695 | Block-03 -Module - RFI Completion | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1660 | Block-03 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 | 2026-05-20 08:00 | 2026-06-20 14:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3005 | Block-07 -Robotic Structure - Bridges Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1720 | Block-03 -Robotic Structure - Reverse Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1715 | Block-03 -Robotic Structure - Docking Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1725 | Block-03 -Robotic Structure - Bridges Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-4945 | Block-13 -Robotic Structure - Bridges Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3900 | Block-10 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 | 2026-05-20 08:00 | 2026-05-20 14:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3935 | Block-10 -Module - RFI Completion | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3960 | Block-10 -Robotic Structure - Reverse Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2040 | Block-04 -Robotic Structure - Reverse Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3955 | Block-10 -Robotic Structure - Docking Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2045 | Block-04 -Robotic Structure - Bridges Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3965 | Block-10 -Robotic Structure - Bridges Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2035 | Block-04 -Robotic Structure - Docking Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2360 | Block-05 -Robotic Structure - Reverse Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5855 | Block-16 -Module - RFI Completion | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5875 | Block-16 -Robotic Structure - Docking Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2355 | Block-05 -Robotic Structure - Docking Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5885 | Block-16 -Robotic Structure - Bridges Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5880 | Block-16 -Robotic Structure - Reverse Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2620 | Block-06 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 | 2026-05-20 08:00 | 2026-06-20 14:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1395 | Block-02 -Robotic Structure - Docking Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1400 | Block-02 -Robotic Structure - Reverse Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1405 | Block-02 -Robotic Structure - Bridges Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2675 | Block-06 -Robotic Structure - Docking Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2680 | Block-06 -Robotic Structure - Reverse Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2685 | Block-06 -Robotic Structure - Bridges Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5180 | Block-14 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 | 2026-05-16 08:00 | 2026-05-16 14:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5245 | Block-14 -Robotic Structure - Bridges Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5215 | Block-14 -Module - RFI Completion | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5240 | Block-14 -Robotic Structure - Reverse Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5235 | Block-14 -Robotic Structure - Docking Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8415 | Block-24 -Module - RFI Completion | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6845 | Block-19 -Robotic Structure - Bridges Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8435 | Block-24 -Robotic Structure - Docking Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8445 | Block-24 -Robotic Structure - Bridges Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6815 | Block-19 -Module - RFI Completion | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6835 | Block-19 -Robotic Structure - Docking Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6840 | Block-19 -Robotic Structure - Reverse Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8440 | Block-24 -Robotic Structure - Reverse Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7155 | Block-20 -Robotic Structure - Docking Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8755 | Block-25 -Robotic Structure - Docking Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8760 | Block-25 -Robotic Structure - Reverse Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7160 | Block-20 -Robotic Structure - Reverse Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3260 | Block-08 -Piling - Robotic Docking System | Completed | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 | 2026-05-22 08:00 | 2026-05-22 14:00 | 1 | 39 | Number | 39 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3295 | Block-08 -Module - RFI Completion | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3320 | Block-08 -Robotic Structure - Reverse Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3325 | Block-08 -Robotic Structure - Bridges Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7480 | Block-21 -Robotic Structure - Reverse Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6175 | Block-17 -Module - RFI Completion | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3315 | Block-08 -Robotic Structure - Docking Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7455 | Block-21 -Module - RFI Completion | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7475 | Block-21 -Robotic Structure - Docking Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6200 | Block-17 -Robotic Structure - Reverse Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6205 | Block-17 -Robotic Structure - Bridges Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8095 | Block-23 -Module - RFI Completion | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9080 | Block-26 -Robotic Structure - Reverse Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-9090 | Block-26 -Robot Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-08 11:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8115 | Block-23 -Robotic Structure - Docking Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8120 | Block-23 -Robotic Structure - Reverse Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6495 | Block-18 -Module - RFI Completion | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8125 | Block-23 -Robotic Structure - Bridges Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6515 | Block-18 -Robotic Structure - Docking Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6520 | Block-18 -Robotic Structure - Reverse Station Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6525 | Block-18 -Robotic Structure - Bridges Installation | Not Started | Task Dependent | 2026-05-24 08:00 | 2026-06-18 13:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2975 | Block-07 -Module - RFI Completion | Not Started | Task Dependent | 2026-05-25 10:00 | 2026-06-19 15:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8450 | Block-24 -Robot Installation | Not Started | Task Dependent | 2026-05-29 09:00 | 2026-06-13 12:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6530 | Block-18 -Robot Installation | Not Started | Task Dependent | 2026-05-29 09:00 | 2026-06-13 12:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3330 | Block-08 -Robot Installation | Not Started | Task Dependent | 2026-05-29 09:00 | 2026-06-13 12:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5890 | Block-16 -Robot Installation | Not Started | Task Dependent | 2026-05-29 09:00 | 2026-06-13 12:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1730 | Block-03 -Robot Installation | Not Started | Task Dependent | 2026-05-29 09:00 | 2026-06-13 12:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-6850 | Block-19 -Robot Installation | Not Started | Task Dependent | 2026-05-29 09:00 | 2026-06-13 12:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8770 | Block-25 -Robot Installation | Not Started | Task Dependent | 2026-05-29 09:00 | 2026-06-13 12:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-8130 | Block-23 -Robot Installation | Not Started | Task Dependent | 2026-05-29 09:00 | 2026-06-13 12:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3970 | Block-10 -Robot Installation | Not Started | Task Dependent | 2026-05-29 09:00 | 2026-06-13 12:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-5250 | Block-14 -Robot Installation | Not Started | Task Dependent | 2026-05-29 09:00 | 2026-06-13 12:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3650 | Block-09 -Robot Installation | Not Started | Task Dependent | 2026-05-29 09:00 | 2026-06-13 12:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-1410 | Block-02 -Robot Installation | Not Started | Task Dependent | 2026-05-29 09:00 | 2026-06-13 12:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7490 | Block-21 -Robot Installation | Not Started | Task Dependent | 2026-05-31 13:00 | 2026-06-16 09:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2050 | Block-04 -Robot Installation | Not Started | Task Dependent | 2026-06-03 10:00 | 2026-06-18 13:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3000 | Block-07 -Robotic Structure - Reverse Station Installation | Not Started | Task Dependent | 2026-06-05 14:00 | 2026-06-18 13:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-2995 | Block-07 -Robotic Structure - Docking Station Installation | Not Started | Task Dependent | 2026-06-05 14:00 | 2026-06-18 13:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7165 | Block-20 -Robotic Structure - Bridges Installation | Not Started | Task Dependent | 2026-06-07 12:00 | 2026-07-04 10:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-3010 | Block-07 -Robot Installation | Not Started | Task Dependent | 2026-06-11 08:00 | 2026-06-26 11:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7135 | Block-20 -Module - RFI Completion | Not Started | Task Dependent | 2026-06-11 11:00 | 2026-07-09 12:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-DC SIDE | 603F-CC-7170 | Block-20 -Robot Installation | Not Started | Task Dependent | 2026-06-19 09:00 | 2026-07-05 14:00 |  |  | 0 | 39 | Number | 0 | 39
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-1235 | Block-01 -IDT Filtration | Completed | Task Dependent | 2026-02-07 07:00 | 2026-02-09 17:00 | 2026-02-07 07:00 | 2026-02-07 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-1240 | Block-01 -IDT Testing | Completed | Task Dependent | 2026-02-10 07:00 | 2026-02-11 17:00 | 2026-02-09 07:00 | 2026-02-09 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-4445 | Block-11 -HT Panel Testing | Completed | Task Dependent | 2026-02-14 07:00 | 2026-02-14 17:00 | 2026-02-19 07:00 | 2026-02-19 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-4450 | Block-11 -LT Panel Testing | Completed | Task Dependent | 2026-02-14 07:00 | 2026-02-14 17:00 | 2026-02-19 07:00 | 2026-02-19 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-4765 | Block-12 -HT Panel Testing | Completed | Task Dependent | 2026-02-14 07:00 | 2026-02-14 17:00 | 2026-02-19 07:00 | 2026-02-19 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-5100 | Block-13 -IDT Testing | Completed | Task Dependent | 2026-02-14 07:00 | 2026-02-15 17:00 | 2026-02-19 07:00 | 2026-02-19 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-4755 | Block-12 -IDT Filtration | Completed | Task Dependent | 2026-02-14 07:00 | 2026-02-16 17:00 | 2026-02-09 07:00 | 2026-02-09 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7635 | Block-21 -IDT Filtration | Completed | Task Dependent | 2026-02-14 07:00 | 2026-02-16 17:00 | 2026-02-19 07:00 | 2026-02-19 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-4435 | Block-11 -IDT Filtration | Completed | Task Dependent | 2026-02-14 07:00 | 2026-02-16 17:00 | 2026-02-12 07:00 | 2026-02-12 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-4770 | Block-12 -LT Panel Testing | Completed | Task Dependent | 2026-02-14 07:00 | 2026-02-14 17:00 | 2026-02-19 07:00 | 2026-02-19 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-9555 | Block-27 -IDT Filtration | Completed | Task Dependent | 2026-02-14 07:00 | 2026-02-16 17:00 | 2026-02-18 07:00 | 2026-02-18 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7315 | Block-20 -IDT Filtration | Completed | Task Dependent | 2026-02-14 07:00 | 2026-02-16 17:00 | 2026-02-08 07:00 | 2026-02-08 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-4760 | Block-12 -IDT Testing | Completed | Task Dependent | 2026-02-17 07:00 | 2026-02-18 17:00 | 2026-02-11 07:00 | 2026-02-11 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-4440 | Block-11 -IDT Testing | Completed | Task Dependent | 2026-02-17 07:00 | 2026-02-18 17:00 | 2026-02-19 07:00 | 2026-02-19 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-5095 | Block-13 -IDT Filtration | Completed | Task Dependent | 2026-02-19 07:00 | 2026-02-21 17:00 | 2026-02-07 07:00 | 2026-02-07 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-1250 | Block-01 -LT Panel Testing | Completed | Task Dependent | 2026-02-21 07:00 | 2026-02-21 17:00 | 2026-02-23 07:00 | 2026-02-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7955 | Block-22 -IDT Filtration | Completed | Task Dependent | 2026-02-21 07:00 | 2026-02-23 17:00 | 2026-02-16 07:00 | 2026-02-16 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-1245 | Block-01 -HT Panel Testing | Completed | Task Dependent | 2026-02-21 07:00 | 2026-02-21 17:00 | 2026-02-23 07:00 | 2026-02-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-5105 | Block-13 -HT Panel Testing | Completed | Task Dependent | 2026-02-22 07:00 | 2026-02-22 17:00 | 2026-02-19 07:00 | 2026-02-19 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-4775 | Block-12 -Inspection Offer To Asset Commissioning Team | Completed | Task Dependent | 2026-02-24 07:00 | 2026-02-24 17:00 | 2026-02-23 07:00 | 2026-02-24 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-5115 | Block-13 -Inspection Offer To Asset Commissioning Team | Completed | Task Dependent | 2026-02-24 07:00 | 2026-02-24 17:00 | 2026-02-23 07:00 | 2026-02-24 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-5120 | Block-13 -Punch Point Identification By Asset Commissioning Team | Completed | Task Dependent | 2026-02-25 07:00 | 2026-02-27 17:00 | 2026-02-24 07:00 | 2026-02-25 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-4780 | Block-12 -Punch Point Identification By Asset Commissioning Team | Completed | Task Dependent | 2026-02-25 07:00 | 2026-02-27 17:00 | 2026-02-24 07:00 | 2026-02-25 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-1255 | Block-01 -Inspection Offer To Asset Commissioning Team | Completed | Task Dependent | 2026-02-26 07:00 | 2026-02-26 17:00 | 2026-02-23 07:00 | 2026-02-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-1260 | Block-01 -Punch Point Identification By Asset Commissioning Team | Completed | Task Dependent | 2026-02-27 07:00 | 2026-03-01 17:00 | 2026-02-24 07:00 | 2026-02-25 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7960 | Block-22 -IDT Testing | Completed | Task Dependent | 2026-02-28 07:00 | 2026-03-01 17:00 | 2026-03-03 07:00 | 2026-03-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-6370 | Block-17 -LT Panel Testing | Completed | Task Dependent | 2026-02-28 07:00 | 2026-02-28 17:00 | 2026-03-03 07:00 | 2026-03-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-6375 | Block-17 -Inspection Offer To Asset Commissioning Team | Completed | Task Dependent | 2026-02-28 07:00 | 2026-02-28 17:00 | 2026-03-06 07:00 | 2026-03-06 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-6365 | Block-17 -HT Panel Testing | Completed | Task Dependent | 2026-02-28 07:00 | 2026-02-28 17:00 | 2026-03-04 07:00 | 2026-03-04 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-9565 | Block-27 -HT Panel Testing | Completed | Task Dependent | 2026-02-28 07:00 | 2026-02-28 17:00 | 2026-03-03 07:00 | 2026-03-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7975 | Block-22 -Inspection Offer To Asset Commissioning Team | Completed | Task Dependent | 2026-02-28 07:00 | 2026-02-28 17:00 | 2026-03-06 07:00 | 2026-03-06 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-5730 | Block-15 -LT Panel Testing | Completed | Task Dependent | 2026-02-28 07:00 | 2026-02-28 17:00 | 2026-03-03 07:00 | 2026-03-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7970 | Block-22 -LT Panel Testing | Completed | Task Dependent | 2026-02-28 07:00 | 2026-02-28 17:00 | 2026-03-04 07:00 | 2026-03-04 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-9560 | Block-27 -IDT Testing | Completed | Task Dependent | 2026-02-28 07:00 | 2026-03-01 17:00 | 2026-03-04 07:00 | 2026-03-04 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-9570 | Block-27 -LT Panel Testing | Completed | Task Dependent | 2026-02-28 07:00 | 2026-02-28 17:00 | 2026-03-04 07:00 | 2026-03-04 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-5725 | Block-15 -HT Panel Testing | Completed | Task Dependent | 2026-02-28 07:00 | 2026-02-28 17:00 | 2026-03-03 07:00 | 2026-03-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-5125 | Block-13 -Punch Point Rectification And Pre Charging Sign Off | Completed | Task Dependent | 2026-02-28 07:00 | 2026-03-02 17:00 | 2026-02-24 07:00 | 2026-02-25 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7965 | Block-22 -HT Panel Testing | Completed | Task Dependent | 2026-02-28 07:00 | 2026-02-28 17:00 | 2026-03-04 07:00 | 2026-03-04 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-9575 | Block-27 -Inspection Offer To Asset Commissioning Team | Completed | Task Dependent | 2026-02-28 07:00 | 2026-02-28 17:00 | 2026-03-06 07:00 | 2026-03-06 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-5735 | Block-15 -Inspection Offer To Asset Commissioning Team | Completed | Task Dependent | 2026-02-28 07:00 | 2026-02-28 17:00 | 2026-03-06 07:00 | 2026-03-06 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-5715 | Block-15 -IDT Filtration | Completed | Task Dependent | 2026-02-28 07:00 | 2026-03-02 17:00 | 2026-03-03 07:00 | 2026-03-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-4785 | Block-12 -Punch Point Rectification And Pre Charging Sign Off | Completed | Task Dependent | 2026-02-28 07:00 | 2026-03-02 17:00 | 2026-02-24 07:00 | 2026-02-25 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-9580 | Block-27 -Punch Point Identification By Asset Commissioning Team | Completed | Task Dependent | 2026-03-01 07:00 | 2026-03-03 17:00 | 2026-03-06 07:00 | 2026-03-06 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-5740 | Block-15 -Punch Point Identification By Asset Commissioning Team | Completed | Task Dependent | 2026-03-01 07:00 | 2026-03-03 17:00 | 2026-03-06 07:00 | 2026-03-06 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7980 | Block-22 -Punch Point Identification By Asset Commissioning Team | Completed | Task Dependent | 2026-03-01 07:00 | 2026-03-03 17:00 | 2026-03-06 07:00 | 2026-03-06 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-6380 | Block-17 -Punch Point Identification By Asset Commissioning Team | Completed | Task Dependent | 2026-03-01 07:00 | 2026-03-03 17:00 | 2026-03-06 07:00 | 2026-03-06 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-5110 | Block-13 -LT Panel Testing | Completed | Task Dependent | 2026-03-01 07:00 | 2026-03-01 17:00 | 2026-02-19 07:00 | 2026-02-19 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-1265 | Block-01 -Punch Point Rectification And Pre Charging Sign Off | Completed | Task Dependent | 2026-03-02 07:00 | 2026-03-04 17:00 | 2026-02-24 07:00 | 2026-02-26 07:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-4455 | Block-11 -Inspection Offer To Asset Commissioning Team | Completed | Task Dependent | 2026-03-02 07:00 | 2026-03-02 17:00 | 2026-02-23 07:00 | 2026-02-24 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-6995 | Block-19 -IDT Filtration | Completed | Task Dependent | 2026-03-02 07:00 | 2026-03-04 17:00 | 2026-02-21 07:00 | 2026-02-21 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-6355 | Block-17 -IDT Filtration | Completed | Task Dependent | 2026-03-02 07:00 | 2026-03-04 17:00 | 2026-02-14 07:00 | 2026-03-14 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-5720 | Block-15 -IDT Testing | Completed | Task Dependent | 2026-03-03 07:00 | 2026-03-04 17:00 | 2026-03-03 07:00 | 2026-03-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-4460 | Block-11 -Punch Point Identification By Asset Commissioning Team | Completed | Task Dependent | 2026-03-03 07:00 | 2026-03-05 17:00 | 2026-02-24 07:00 | 2026-02-25 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-5745 | Block-15 -Punch Point Rectification And Pre Charging Sign Off | Completed | Task Dependent | 2026-03-04 07:00 | 2026-03-06 17:00 | 2026-03-06 07:00 | 2026-03-08 07:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-9585 | Block-27 -Punch Point Rectification And Pre Charging Sign Off | Completed | Task Dependent | 2026-03-04 07:00 | 2026-03-06 17:00 | 2026-03-06 07:00 | 2026-03-08 07:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-6385 | Block-17 -Punch Point Rectification And Pre Charging Sign Off | Completed | Task Dependent | 2026-03-04 07:00 | 2026-03-06 17:00 | 2026-03-06 07:00 | 2026-03-08 07:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7985 | Block-22 -Punch Point Rectification And Pre Charging Sign Off | Completed | Task Dependent | 2026-03-04 07:00 | 2026-03-06 17:00 | 2026-03-06 07:00 | 2026-03-08 07:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-6360 | Block-17 -IDT Testing | Completed | Task Dependent | 2026-03-05 07:00 | 2026-03-06 17:00 | 2026-02-14 07:00 | 2026-02-14 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-4465 | Block-11 -Punch Point Rectification And Pre Charging Sign Off | Completed | Task Dependent | 2026-03-06 07:00 | 2026-03-08 17:00 | 2026-02-24 07:00 | 2026-02-26 07:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-1560 | Block-02 -IDT Testing | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-15 17:00 | 2026-03-18 07:00 | 2026-03-18 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-9250 | Block-26 -LT Panel Testing | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-14 17:00 | 2026-03-20 07:00 | 2026-03-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-9245 | Block-26 -HT Panel Testing | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-14 17:00 | 2026-03-20 07:00 | 2026-03-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-9235 | Block-26 -IDT Filtration | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-16 17:00 | 2026-03-13 07:00 | 2026-03-13 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-3795 | Block-09 -IDT Filtration | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-16 17:00 | 2026-03-18 07:00 | 2026-03-18 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-9240 | Block-26 -IDT Testing | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-15 17:00 | 2026-03-18 07:00 | 2026-03-18 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-8915 | Block-25 -IDT Filtration | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-16 17:00 | 2026-03-18 07:00 | 2026-03-18 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-8925 | Block-25 -HT Panel Testing | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-14 17:00 | 2026-03-20 07:00 | 2026-03-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-2835 | Block-06 -IDT Filtration | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-16 17:00 | 2026-03-15 07:00 | 2026-03-15 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-2840 | Block-06 -IDT Testing | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-15 17:00 | 2026-03-18 07:00 | 2026-03-18 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-1570 | Block-02 -LT Panel Testing | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-14 17:00 | 2026-03-20 07:00 | 2026-03-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-1565 | Block-02 -HT Panel Testing | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-14 17:00 | 2026-03-20 07:00 | 2026-03-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-2515 | Block-05 -IDT Filtration | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-16 17:00 | 2026-03-14 07:00 | 2026-03-14 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-2530 | Block-05 -LT Panel Testing | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-14 17:00 | 2026-03-20 07:00 | 2026-03-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-2520 | Block-05 -IDT Testing | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-15 17:00 | 2026-03-18 07:00 | 2026-03-18 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-1555 | Block-02 -IDT Filtration | Completed | Task Dependent | 2026-03-14 07:00 | 2026-03-16 17:00 | 2026-03-13 07:00 | 2026-03-13 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-2845 | Block-06 -HT Panel Testing | Completed | Task Dependent | 2026-03-16 07:00 | 2026-03-16 17:00 | 2026-03-20 07:00 | 2026-03-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-8930 | Block-25 -LT Panel Testing | Completed | Task Dependent | 2026-03-16 07:00 | 2026-03-16 17:00 | 2026-03-20 07:00 | 2026-03-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-2525 | Block-05 -HT Panel Testing | Completed | Task Dependent | 2026-03-16 07:00 | 2026-03-16 17:00 | 2026-03-20 07:00 | 2026-03-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-8920 | Block-25 -IDT Testing | Completed | Task Dependent | 2026-03-17 07:00 | 2026-03-18 17:00 | 2026-03-20 07:00 | 2026-03-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-8290 | Block-23 -LT Panel Testing | Completed | Task Dependent | 2026-03-21 07:00 | 2026-03-21 17:00 | 2026-03-27 07:00 | 2026-03-27 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-1575 | Block-02 -Inspection Offer To Asset Commissioning Team | Completed | Task Dependent | 2026-03-21 07:00 | 2026-03-21 17:00 | 2026-03-23 07:00 | 2026-03-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-3810 | Block-09 -LT Panel Testing | Completed | Task Dependent | 2026-03-21 07:00 | 2026-03-21 17:00 | 2026-03-27 07:00 | 2026-03-27 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-3805 | Block-09 -HT Panel Testing | Completed | Task Dependent | 2026-03-21 07:00 | 2026-03-21 17:00 | 2026-03-26 07:00 | 2026-03-26 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-8280 | Block-23 -IDT Testing | Completed | Task Dependent | 2026-03-21 07:00 | 2026-03-22 17:00 | 2026-03-24 07:00 | 2026-03-24 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-8595 | Block-24 -IDT Filtration | Completed | Task Dependent | 2026-03-21 07:00 | 2026-03-23 17:00 | 2026-03-18 07:00 | 2026-03-18 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-2535 | Block-05 -Inspection Offer To Asset Commissioning Team | Completed | Task Dependent | 2026-03-21 07:00 | 2026-03-21 17:00 | 2026-03-23 07:00 | 2026-03-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7005 | Block-19 -HT Panel Testing | Completed | Task Dependent | 2026-03-21 07:00 | 2026-03-21 17:00 | 2026-03-26 07:00 | 2026-03-26 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-4130 | Block-10 -LT Panel Testing | Completed | Task Dependent | 2026-03-21 07:00 | 2026-03-21 17:00 | 2026-03-27 07:00 | 2026-03-27 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7000 | Block-19 -IDT Testing | Completed | Task Dependent | 2026-03-21 07:00 | 2026-03-22 17:00 | 2026-03-23 07:00 | 2026-03-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7010 | Block-19 -LT Panel Testing | Completed | Task Dependent | 2026-03-21 07:00 | 2026-03-21 17:00 | 2026-03-27 07:00 | 2026-03-27 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-2855 | Block-06 -Inspection Offer To Asset Commissioning Team | Completed | Task Dependent | 2026-03-21 07:00 | 2026-03-21 17:00 | 2026-03-24 07:00 | 2026-03-24 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-8285 | Block-23 -HT Panel Testing | Completed | Task Dependent | 2026-03-21 07:00 | 2026-03-21 17:00 | 2026-03-26 07:00 | 2026-03-26 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-9255 | Block-26 -Inspection Offer To Asset Commissioning Team | Completed | Task Dependent | 2026-03-21 07:00 | 2026-03-21 17:00 | 2026-03-23 07:00 | 2026-03-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-9260 | Block-26 -Punch Point Identification By Asset Commissioning Team | Completed | Task Dependent | 2026-03-22 07:00 | 2026-03-24 17:00 | 2026-03-23 07:00 | 2026-03-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-1580 | Block-02 -Punch Point Identification By Asset Commissioning Team | Completed | Task Dependent | 2026-03-22 07:00 | 2026-03-24 17:00 | 2026-03-24 07:00 | 2026-03-24 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-2860 | Block-06 -Punch Point Identification By Asset Commissioning Team | Completed | Task Dependent | 2026-03-22 07:00 | 2026-03-24 17:00 | 2026-03-24 07:00 | 2026-03-24 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-2540 | Block-05 -Punch Point Identification By Asset Commissioning Team | Completed | Task Dependent | 2026-03-22 07:00 | 2026-03-24 17:00 | 2026-03-24 07:00 | 2026-03-24 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-8935 | Block-25 -Inspection Offer To Asset Commissioning Team | Completed | Task Dependent | 2026-03-24 07:00 | 2026-03-24 17:00 | 2026-03-23 07:00 | 2026-03-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-2850 | Block-06 -LT Panel Testing | Completed | Task Dependent | 2026-03-24 07:00 | 2026-03-24 17:00 | 2026-03-20 07:00 | 2026-03-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-9265 | Block-26 -Punch Point Rectification And Pre Charging Sign Off | Completed | Task Dependent | 2026-03-25 07:00 | 2026-03-27 17:00 | 2026-03-23 07:00 | 2026-03-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-1585 | Block-02 -Punch Point Rectification And Pre Charging Sign Off | Completed | Task Dependent | 2026-03-25 07:00 | 2026-03-27 17:00 | 2026-03-24 07:00 | 2026-03-24 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-8940 | Block-25 -Punch Point Identification By Asset Commissioning Team | Completed | Task Dependent | 2026-03-25 07:00 | 2026-03-27 17:00 | 2026-03-24 07:00 | 2026-03-24 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-2865 | Block-06 -Punch Point Rectification And Pre Charging Sign Off | Completed | Task Dependent | 2026-03-25 07:00 | 2026-03-27 17:00 | 2026-03-24 07:00 | 2026-03-25 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-2545 | Block-05 -Punch Point Rectification And Pre Charging Sign Off | Completed | Task Dependent | 2026-03-25 07:00 | 2026-03-27 17:00 | 2026-03-24 07:00 | 2026-03-24 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-4120 | Block-10 -IDT Testing | Completed | Task Dependent | 2026-03-28 07:00 | 2026-03-29 17:00 | 2026-03-29 07:00 | 2026-03-29 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-4125 | Block-10 -HT Panel Testing | Completed | Task Dependent | 2026-03-28 07:00 | 2026-03-28 17:00 | 2026-03-30 07:00 | 2026-03-30 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-4115 | Block-10 -IDT Filtration | Completed | Task Dependent | 2026-03-28 07:00 | 2026-03-30 17:00 | 2026-03-23 07:00 | 2026-03-23 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-8945 | Block-25 -Punch Point Rectification And Pre Charging Sign Off | Completed | Task Dependent | 2026-03-28 07:00 | 2026-03-30 17:00 | 2026-03-24 07:00 | 2026-03-24 07:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-3800 | Block-09 -IDT Testing | Completed | Task Dependent | 2026-03-28 07:00 | 2026-03-29 17:00 | 2026-03-29 07:00 | 2026-03-29 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-3815 | Block-09 -Inspection Offer To Asset Commissioning Team | Completed | Task Dependent | 2026-03-30 07:00 | 2026-03-30 17:00 | 2026-04-02 07:00 | 2026-04-02 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7015 | Block-19 -Inspection Offer To Asset Commissioning Team | Completed | Task Dependent | 2026-03-30 07:00 | 2026-03-30 17:00 | 2026-04-02 07:00 | 2026-04-02 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-4135 | Block-10 -Inspection Offer To Asset Commissioning Team | Completed | Task Dependent | 2026-03-30 07:00 | 2026-03-30 17:00 | 2026-04-02 07:00 | 2026-04-02 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-8295 | Block-23 -Inspection Offer To Asset Commissioning Team | Completed | Task Dependent | 2026-03-30 07:00 | 2026-03-30 17:00 | 2026-04-02 07:00 | 2026-04-02 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7020 | Block-19 -Punch Point Identification By Asset Commissioning Team | Completed | Task Dependent | 2026-03-31 07:00 | 2026-04-02 17:00 | 2026-04-03 07:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-3820 | Block-09 -Punch Point Identification By Asset Commissioning Team | Completed | Task Dependent | 2026-03-31 07:00 | 2026-04-02 17:00 | 2026-04-03 07:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-8300 | Block-23 -Punch Point Identification By Asset Commissioning Team | Completed | Task Dependent | 2026-03-31 07:00 | 2026-04-02 17:00 | 2026-04-03 07:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-4140 | Block-10 -Punch Point Identification By Asset Commissioning Team | Completed | Task Dependent | 2026-03-31 07:00 | 2026-04-02 17:00 | 2026-04-03 07:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-4145 | Block-10 -Punch Point Rectification And Pre Charging Sign Off | Completed | Task Dependent | 2026-04-03 07:00 | 2026-04-05 17:00 | 2026-04-03 07:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-3825 | Block-09 -Punch Point Rectification And Pre Charging Sign Off | Completed | Task Dependent | 2026-04-03 07:00 | 2026-04-05 17:00 | 2026-04-03 07:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7025 | Block-19 -Punch Point Rectification And Pre Charging Sign Off | Completed | Task Dependent | 2026-04-03 07:00 | 2026-04-05 17:00 | 2026-04-03 07:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-8305 | Block-23 -Punch Point Rectification And Pre Charging Sign Off | Completed | Task Dependent | 2026-04-03 07:00 | 2026-04-05 17:00 | 2026-04-03 07:00 | 2026-04-03 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-8600 | Block-24 -IDT Testing | Completed | Task Dependent | 2026-04-04 07:00 | 2026-04-05 17:00 | 2026-04-06 07:00 | 2026-04-06 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7645 | Block-21 -HT Panel Testing | Completed | Task Dependent | 2026-04-04 07:00 | 2026-04-04 17:00 | 2026-04-06 07:00 | 2026-04-06 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-3160 | Block-07 -IDT Testing | Completed | Task Dependent | 2026-04-04 07:00 | 2026-04-05 17:00 | 2026-04-10 07:00 | 2026-04-10 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7320 | Block-20 -IDT Testing | Completed | Task Dependent | 2026-04-04 07:00 | 2026-04-05 17:00 | 2026-04-10 07:00 | 2026-04-10 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7640 | Block-21 -IDT Testing | Completed | Task Dependent | 2026-04-04 07:00 | 2026-04-05 17:00 | 2026-04-06 07:00 | 2026-04-06 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-8605 | Block-24 -HT Panel Testing | Completed | Task Dependent | 2026-04-04 07:00 | 2026-04-04 17:00 | 2026-04-06 07:00 | 2026-04-06 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-6040 | Block-16 -IDT Testing | Completed | Task Dependent | 2026-04-04 07:00 | 2026-04-05 17:00 | 2026-04-10 07:00 | 2026-04-10 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-6035 | Block-16 -IDT Filtration | Completed | Task Dependent | 2026-04-04 14:00 | 2026-04-07 14:00 | 2026-04-03 14:00 | 2026-04-03 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-8275 | Block-23 -IDT Filtration | Completed | Task Dependent | 2026-04-08 13:00 | 2026-04-11 12:00 | 2026-03-22 13:00 | 2026-03-23 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-5400 | Block-14 -IDT Testing | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-12 17:00 | 2026-04-12 07:00 | 2026-04-12 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7650 | Block-21 -LT Panel Testing | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-11 17:00 | 2026-04-11 07:00 | 2026-04-11 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-6690 | Block-18 -LT Panel Testing | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-11 17:00 | 2026-04-13 07:00 | 2026-04-13 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-6685 | Block-18 -HT Panel Testing | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-11 17:00 | 2026-04-13 07:00 | 2026-04-13 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-5405 | Block-14 -HT Panel Testing | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-11 17:00 | 2026-04-11 07:00 | 2026-04-11 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-1885 | Block-03 -HT Panel Testing | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-11 17:00 | 2026-04-15 07:00 | 2026-04-15 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-3485 | Block-08 -HT Panel Testing | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-11 17:00 | 2026-04-12 07:00 | 2026-04-12 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7325 | Block-20 -HT Panel Testing | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-11 17:00 | 2026-04-11 07:00 | 2026-04-11 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-3490 | Block-08 -LT Panel Testing | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-11 17:00 | 2026-04-12 07:00 | 2026-04-12 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-1880 | Block-03 -IDT Testing | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-12 17:00 | 2026-04-17 07:00 | 2026-04-17 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-5410 | Block-14 -LT Panel Testing | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-11 17:00 | 2026-04-15 07:00 | 2026-04-15 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7330 | Block-20 -LT Panel Testing | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-11 17:00 | 2026-04-11 07:00 | 2026-04-11 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-6045 | Block-16 -HT Panel Testing | Completed | Task Dependent | 2026-04-11 07:00 | 2026-04-11 17:00 | 2026-04-13 07:00 | 2026-04-13 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-2205 | Block-04 -HT Panel Testing | Completed | Task Dependent | 2026-04-12 15:00 | 2026-04-13 15:00 | 2026-04-09 15:00 | 2026-04-09 15:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-3475 | Block-08 -IDT Filtration | Completed | Task Dependent | 2026-04-12 15:00 | 2026-04-15 15:00 | 2026-04-10 15:00 | 2026-04-10 15:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-8610 | Block-24 -LT Panel Testing | Completed | Task Dependent | 2026-04-13 13:00 | 2026-04-14 12:00 | 2026-04-11 09:00 | 2026-04-11 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-6050 | Block-16 -LT Panel Testing | Completed | Task Dependent | 2026-04-13 13:00 | 2026-04-14 12:00 | 2026-04-13 13:00 | 2026-04-13 14:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-3170 | Block-07 -LT Panel Testing | Completed | Task Dependent | 2026-04-13 13:00 | 2026-04-14 12:00 | 2026-04-14 13:00 | 2026-04-15 13:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-3165 | Block-07 -HT Panel Testing | Completed | Task Dependent | 2026-04-13 13:00 | 2026-04-14 12:00 | 2026-04-11 13:00 | 2026-04-12 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-3480 | Block-08 -IDT Testing | Completed | Task Dependent | 2026-04-15 15:00 | 2026-04-17 15:00 | 2026-04-10 15:00 | 2026-04-10 15:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-1890 | Block-03 -LT Panel Testing | Completed | Task Dependent | 2026-04-18 07:00 | 2026-04-18 17:00 | 2026-04-20 07:00 | 2026-04-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-2210 | Block-04 -LT Panel Testing | Completed | Task Dependent | 2026-04-18 07:00 | 2026-04-18 17:00 | 2026-04-20 07:00 | 2026-04-20 17:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-6675 | Block-18 -IDT Filtration | Completed | Task Dependent | 2026-04-19 15:00 | 2026-04-22 15:00 | 2026-04-13 15:00 | 2026-04-13 15:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-1875 | Block-03 -IDT Filtration | Completed | Task Dependent | 2026-04-19 15:00 | 2026-04-22 15:00 | 2026-04-12 15:00 | 2026-04-12 15:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-6680 | Block-18 -IDT Testing | Completed | Task Dependent | 2026-04-22 15:00 | 2026-04-24 15:00 | 2026-04-14 15:00 | 2026-04-14 15:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-3155 | Block-07 -IDT Filtration | Completed | Task Dependent | 2026-04-25 11:00 | 2026-04-28 11:00 | 2026-04-01 11:00 | 2026-04-01 11:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-2195 | Block-04 -IDT Filtration | Completed | Task Dependent | 2026-05-03 13:00 | 2026-05-06 12:00 | 2026-04-05 13:00 | 2026-04-06 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-5395 | Block-14 -IDT Filtration | Completed | Task Dependent | 2026-05-03 13:00 | 2026-05-06 12:00 | 2026-04-05 13:00 | 2026-04-06 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-2200 | Block-04 -IDT Testing | Completed | Task Dependent | 2026-05-06 13:00 | 2026-05-08 12:00 | 2026-04-08 13:00 | 2026-04-09 12:00 | 1 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-6055 | Block-16 -Inspection Offer To Asset Commissioning Team | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-2215 | Block-04 -Inspection Offer To Asset Commissioning Team | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-1895 | Block-03 -Inspection Offer To Asset Commissioning Team | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7335 | Block-20 -Inspection Offer To Asset Commissioning Team | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-8615 | Block-24 -Inspection Offer To Asset Commissioning Team | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-3495 | Block-08 -Inspection Offer To Asset Commissioning Team | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7655 | Block-21 -Inspection Offer To Asset Commissioning Team | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-6695 | Block-18 -Inspection Offer To Asset Commissioning Team | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-5415 | Block-14 -Inspection Offer To Asset Commissioning Team | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-3175 | Block-07 -Inspection Offer To Asset Commissioning Team | Not Started | Task Dependent | 2026-05-24 07:00 | 2026-05-24 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-2220 | Block-04 -Punch Point Identification By Asset Commissioning Team | Not Started | Task Dependent | 2026-05-25 07:00 | 2026-05-27 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-3180 | Block-07 -Punch Point Identification By Asset Commissioning Team | Not Started | Task Dependent | 2026-05-25 07:00 | 2026-05-27 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-3500 | Block-08 -Punch Point Identification By Asset Commissioning Team | Not Started | Task Dependent | 2026-05-25 07:00 | 2026-05-27 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7340 | Block-20 -Punch Point Identification By Asset Commissioning Team | Not Started | Task Dependent | 2026-05-25 07:00 | 2026-05-27 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-1900 | Block-03 -Punch Point Identification By Asset Commissioning Team | Not Started | Task Dependent | 2026-05-25 07:00 | 2026-05-27 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-8620 | Block-24 -Punch Point Identification By Asset Commissioning Team | Not Started | Task Dependent | 2026-05-25 07:00 | 2026-05-27 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-5420 | Block-14 -Punch Point Identification By Asset Commissioning Team | Not Started | Task Dependent | 2026-05-25 07:00 | 2026-05-27 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-6700 | Block-18 -Punch Point Identification By Asset Commissioning Team | Not Started | Task Dependent | 2026-05-25 07:00 | 2026-05-27 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7660 | Block-21 -Punch Point Identification By Asset Commissioning Team | Not Started | Task Dependent | 2026-05-25 07:00 | 2026-05-27 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-6060 | Block-16 -Punch Point Identification By Asset Commissioning Team | Not Started | Task Dependent | 2026-05-25 07:00 | 2026-05-27 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7345 | Block-20 -Punch Point Rectification And Pre Charging Sign Off | Not Started | Task Dependent | 2026-05-28 07:00 | 2026-05-30 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-2225 | Block-04 -Punch Point Rectification And Pre Charging Sign Off | Not Started | Task Dependent | 2026-05-28 07:00 | 2026-05-30 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-1905 | Block-03 -Punch Point Rectification And Pre Charging Sign Off | Not Started | Task Dependent | 2026-05-28 07:00 | 2026-05-30 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-6705 | Block-18 -Punch Point Rectification And Pre Charging Sign Off | Not Started | Task Dependent | 2026-05-28 07:00 | 2026-05-30 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-5425 | Block-14 -Punch Point Rectification And Pre Charging Sign Off | Not Started | Task Dependent | 2026-05-28 07:00 | 2026-05-30 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-3505 | Block-08 -Punch Point Rectification And Pre Charging Sign Off | Not Started | Task Dependent | 2026-05-28 07:00 | 2026-05-30 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-8625 | Block-24 -Punch Point Rectification And Pre Charging Sign Off | Not Started | Task Dependent | 2026-05-28 07:00 | 2026-05-30 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-7665 | Block-21 -Punch Point Rectification And Pre Charging Sign Off | Not Started | Task Dependent | 2026-05-28 07:00 | 2026-05-30 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-3185 | Block-07 -Punch Point Rectification And Pre Charging Sign Off | Not Started | Task Dependent | 2026-05-28 07:00 | 2026-05-30 17:00 |  |  | 0 | 0 |  | 0 | 0
CONSTRUCTION-PV AREA-PRE COMMISSIONING | 603F-CC-6065 | Block-16 -Punch Point Rectification And Pre Charging Sign Off | Not Started | Task Dependent | 2026-05-28 07:00 | 2026-05-30 17:00 |  |  | 0 | 0 |  | 0 | 0
CONTROL CABLES | 603F-PR-3020 | Control Cables-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-23 07:00 | 2025-02-26 17:00 | 2025-02-23 07:00 | 2025-02-26 17:00 | 1 | 0 |  | 0 | 0
CONTROL CABLES | 603F-PR-3030 | Control Cables-TBER | Completed | Task Dependent | 2025-02-23 07:00 | 2025-03-06 17:00 | 2025-02-23 07:00 | 2025-03-06 17:00 | 1 | 0 |  | 0 | 0
CONTROL CABLES | 603F-PR-3040 | Control Cables-Purchase Requistion | Completed | Task Dependent | 2025-03-07 07:00 | 2025-03-07 17:00 | 2025-03-07 07:00 | 2025-03-07 17:00 | 1 | 0 |  | 0 | 0
CONTROL CABLES | 603F-PR-3050 | Control Cables-Note For Approval | Completed | Task Dependent | 2025-03-07 07:00 | 2025-03-08 17:00 | 2025-03-07 07:00 | 2025-03-08 17:00 | 1 | 0 |  | 0 | 0
CONTROL CABLES | 603F-PR-3060 | Control Cables-LOI / PO Release | Completed | Task Dependent | 2025-03-09 07:00 | 2025-03-10 17:00 | 2025-03-09 07:00 | 2025-03-10 17:00 | 1 | 0 |  | 0 | 0
CONTROL CABLES | 603F-PR-3070 | Control Cables-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-10 07:00 | 2025-06-08 17:00 | 2025-03-20 07:00 | 2025-04-05 07:00 | 1 | 0 |  | 0 | 0
CONTROL CABLES | 603F-PR-4940 | Control Cables-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-07-12 07:00 | 2025-07-21 17:00 | 2025-05-30 07:00 | 2025-06-08 17:00 | 1 | 0 |  | 0 | 0
CONTROL CABLES | 603F-PR-3100 | Control Cables-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-07-12 07:00 | 2025-07-21 17:00 | 2025-05-30 07:00 | 2025-06-08 17:00 | 1 | 0 |  | 0 | 0
CONTROL CABLES | 603F-PR-3080 | Control Cables-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-07-12 07:00 | 2025-07-21 17:00 | 2025-04-24 07:00 | 2025-05-03 17:00 | 1 | 0 |  | 0 | 0
CONTROL CABLES | 603F-PR-3090 | Control Cables-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-07-15 07:00 | 2025-07-24 17:00 | 2025-05-05 07:00 | 2025-05-14 17:00 | 1 | 9 | Kilometer | 0 | 0
CONTROL CABLES | 603F-PR-3110 | Control Cables-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-07-16 07:00 | 2025-07-25 17:00 | 2025-06-06 07:00 | 2025-06-15 17:00 | 1 | 9 | Kilometer | 0 | 0
CONTROL CABLES | 603F-PR-4950 | Control Cables-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-07-17 07:00 | 2025-07-26 17:00 | 2025-06-06 07:00 | 2025-06-15 17:00 | 1 | 9 | Kilometer | 0 | 0
DC CABLE | 603F-PR-3950 | DC Cable-TBER | Completed | Task Dependent | 2025-02-23 07:00 | 2025-03-06 17:00 | 2025-02-23 07:00 | 2025-03-06 17:00 | 1 | 0 |  | 0 | 0
DC CABLE | 603F-PR-3940 | DC Cable-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-23 07:00 | 2025-02-26 17:00 | 2025-02-23 07:00 | 2025-02-26 17:00 | 1 | 0 |  | 0 | 0
DC CABLE | 603F-PR-3970 | DC Cable-Note For Approval | Completed | Task Dependent | 2025-03-07 07:00 | 2025-03-08 17:00 | 2025-03-07 07:00 | 2025-03-08 17:00 | 1 | 0 |  | 0 | 0
DC CABLE | 603F-PR-3960 | DC Cable-Purchase Requistion | Completed | Task Dependent | 2025-03-07 07:00 | 2025-03-07 17:00 | 2025-03-07 07:00 | 2025-03-07 17:00 | 1 | 0 |  | 0 | 0
DC CABLE | 603F-PR-3980 | DC Cable-LOI / PO Release | Completed | Task Dependent | 2025-03-09 07:00 | 2025-03-10 17:00 | 2025-03-09 07:00 | 2025-03-10 17:00 | 1 | 0 |  | 0 | 0
DC CABLE | 603F-PR-3990 | DC Cable-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-10 07:00 | 2025-06-30 17:00 | 2025-03-20 07:00 | 2025-04-20 07:00 | 1 | 0 |  | 0 | 0
DC CABLE | 603F-PR-4000 | DC Cable-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-10-04 07:00 | 2025-10-28 17:00 | 2025-05-30 07:00 | 2025-06-12 17:00 | 1 | 0 |  | 0 | 0
DC CABLE | 603F-PR-5130 | DC Cable-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-10-11 07:00 | 2025-10-21 17:00 | 2025-09-03 07:00 | 2025-11-24 17:00 | 1 | 0 |  | 0 | 0
DC CABLE | 603F-PR-5140 | DC Cable-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-10-14 07:00 | 2025-10-24 17:00 | 2025-10-06 07:00 | 2025-11-27 17:00 | 1 | 1098 | Kilometer | 0 | 0
DC CABLE | 603F-PR-4010 | DC Cable-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-10-21 07:00 | 2025-10-31 17:00 | 2025-06-09 07:00 | 2025-06-24 17:00 | 1 | 1098 | Kilometer | 0 | 0
DC CABLE | 603F-PR-4020 | DC Cable-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-11-07 07:00 | 2025-11-17 17:00 | 2025-06-23 07:00 | 2025-07-01 17:00 | 1 | 0 |  | 0 | 0
DC CABLE | 603F-PR-4030 | DC Cable-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-11-10 07:00 | 2025-11-20 17:00 | 2025-06-27 07:00 | 2025-10-31 17:00 | 1 | 1098 | Kilometer | 0 | 0
EARTHING FLAT | 603F-PR-1920 | Earthing Flat-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-21 07:00 | 2025-02-24 17:00 | 2025-02-21 07:00 | 2025-02-24 17:00 | 1 | 0 |  | 0 | 0
EARTHING FLAT | 603F-PR-1930 | Earthing Flat-TBER | Completed | Task Dependent | 2025-02-21 07:00 | 2025-03-04 17:00 | 2025-02-21 07:00 | 2025-03-04 17:00 | 1 | 0 |  | 0 | 0
EARTHING FLAT | 603F-PR-1940 | Earthing Flat-Purchase Requistion | Completed | Task Dependent | 2025-03-05 07:00 | 2025-03-05 17:00 | 2025-03-05 07:00 | 2025-03-05 17:00 | 1 | 0 |  | 0 | 0
EARTHING FLAT | 603F-PR-1950 | Earthing Flat-Note For Approval | Completed | Task Dependent | 2025-03-05 07:00 | 2025-03-06 17:00 | 2025-03-05 07:00 | 2025-03-06 17:00 | 1 | 0 |  | 0 | 0
EARTHING FLAT | 603F-PR-1960 | Earthing Flat-LOI / PO Release | Completed | Task Dependent | 2025-03-07 07:00 | 2025-03-08 17:00 | 2025-03-07 07:00 | 2025-03-08 17:00 | 1 | 0 |  | 0 | 0
EARTHING FLAT | 603F-PR-1970 | Earthing Flat-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-08 07:00 | 2025-05-08 17:00 | 2025-04-08 07:00 | 2025-05-08 17:00 | 1 | 0 |  | 0 | 0
EARTHING FLAT | 603F-PR-1980 | Earthing Flat-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-04-23 07:00 | 2025-04-28 17:00 | 2025-04-23 07:00 | 2025-04-28 07:00 | 1 | 0 |  | 0 | 0
EARTHING FLAT | 603F-PR-2000 | Earthing Flat-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-05-24 07:00 | 2025-05-29 17:00 | 2025-04-29 07:00 | 2025-05-04 17:00 | 1 | 0 |  | 0 | 0
EARTHING FLAT | 603F-PR-1990 | Earthing Flat-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-05-24 07:00 | 2025-05-29 17:00 | 2025-04-26 07:00 | 2025-05-01 17:00 | 1 | 46 | Kilometer | 0 | 0
EARTHING FLAT | 603F-PR-2010 | Earthing Flat-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-05-24 07:00 | 2025-05-29 17:00 | 2025-05-22 07:00 | 2025-05-26 17:00 | 1 | 46 | Kilometer | 0 | 0
EARTHING FLAT | 603F-PR-4720 | Earthing Flat-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-06-21 07:00 | 2025-06-26 17:00 | 2025-05-23 07:00 | 2025-05-27 17:00 | 1 | 0 |  | 0 | 0
EARTHING FLAT | 603F-PR-4730 | Earthing Flat-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-06-25 07:00 | 2025-06-30 17:00 | 2025-05-25 07:00 | 2025-05-31 17:00 | 1 | 46 | Kilometer | 0 | 0
ELECTRICAL AC DC WORKS | 603F-PR-6050 | Electrical AC DC Works-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-03-06 07:00 | 2025-03-09 17:00 | 2025-03-06 07:00 | 2025-03-09 17:00 | 1 | 0 |  | 0 | 0
ELECTRICAL AC DC WORKS | 603F-PR-6060 | Electrical AC DC Works-TBER | Completed | Task Dependent | 2025-03-06 07:00 | 2025-03-17 17:00 | 2025-03-06 07:00 | 2025-03-17 17:00 | 1 | 0 |  | 0 | 0
ELECTRICAL AC DC WORKS | 603F-PR-6080 | Electrical AC DC Works-Note For Approval | Completed | Task Dependent | 2025-03-18 07:00 | 2025-03-19 17:00 | 2025-03-18 07:00 | 2025-03-19 17:00 | 1 | 0 |  | 0 | 0
ELECTRICAL AC DC WORKS | 603F-PR-6070 | Electrical AC DC Works-Purchase Requistion | Completed | Task Dependent | 2025-03-18 07:00 | 2025-03-18 17:00 | 2025-03-18 07:00 | 2025-03-18 17:00 | 1 | 0 |  | 0 | 0
ELECTRICAL AC DC WORKS | 603F-PR-6090 | Electrical AC DC Works-LOI / PO Release | Completed | Task Dependent | 2025-03-20 07:00 | 2025-03-21 17:00 | 2025-03-20 07:00 | 2025-03-21 17:00 | 1 | 0 |  | 0 | 0
ELECTRICAL AC/DC WORKS | 603F-PR-4460 | Electrical AC/DC Works-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-21 07:00 | 2025-02-24 17:00 | 2025-02-21 07:00 | 2025-02-24 17:00 | 1 | 0 |  | 0 | 0
ELECTRICAL AC/DC WORKS | 603F-PR-4470 | Electrical AC/DC Works-TBER | Completed | Task Dependent | 2025-02-21 07:00 | 2025-03-04 17:00 | 2025-02-21 07:00 | 2025-03-04 17:00 | 1 | 0 |  | 0 | 0
ELECTRICAL AC/DC WORKS | 603F-PR-4480 | Electrical AC/DC Works-Purchase Requistion | Completed | Task Dependent | 2025-03-05 07:00 | 2025-03-05 17:00 | 2025-03-05 07:00 | 2025-03-05 17:00 | 1 | 0 |  | 0 | 0
ELECTRICAL AC/DC WORKS | 603F-PR-4490 | Electrical AC/DC Works-Note For Approval | Completed | Task Dependent | 2025-03-05 07:00 | 2025-03-06 17:00 | 2025-03-05 07:00 | 2025-03-06 17:00 | 1 | 0 |  | 0 | 0
ELECTRICAL AC/DC WORKS | 603F-PR-4500 | Electrical AC/DC Works-LOI / PO Release | Completed | Task Dependent | 2025-03-07 07:00 | 2025-03-08 17:00 | 2025-03-07 07:00 | 2025-03-08 17:00 | 1 | 0 |  | 0 | 0
ELECTRICAL AC/DC WORKS | 603F-PR-4510 | Electrical AC/DC Works-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-08 07:00 | 2025-06-18 17:00 | 2025-03-26 07:00 | 2025-05-23 17:00 | 1 | 0 |  | 0 | 0
ELECTRICAL AC/DC WORKS | 603F-PR-4520 | Electrical AC/DC Works-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-06-21 07:00 | 2025-07-02 17:00 | 2025-03-26 07:00 | 2025-05-31 17:00 | 1 | 0 |  | 0 | 0
ELECTRICAL AC/DC WORKS | 603F-PR-4530 | Electrical AC/DC Works-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-06-24 07:00 | 2025-07-05 17:00 | 2025-03-26 07:00 | 2025-06-06 17:00 | 1 | 9 | Lot | 9 | 0
ELECTRICAL AC/DC WORKS | 603F-PR-4540 | Electrical AC/DC Works-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-07-03 07:00 | 2025-07-10 17:00 | 2025-06-02 07:00 | 2025-06-19 17:00 | 1 | 0 |  | 0 | 0
ELECTRICAL AC/DC WORKS | 603F-PR-4550 | Electrical AC/DC Works-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-07-06 07:00 | 2025-07-13 17:00 | 2025-06-25 07:00 | 2025-06-28 17:00 | 1 | 9 | Lot | 9 | 0
ELECTRICAL AC/DC WORKS | 603F-PR-5230 | Electrical AC/DC Works-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-07-11 07:00 | 2025-07-18 17:00 | 2025-07-01 07:00 | 2025-07-10 17:00 | 1 | 0 |  | 0 | 0
ELECTRICAL AC/DC WORKS | 603F-PR-5240 | Electrical AC/DC Works-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-07-16 07:00 | 2025-07-23 17:00 | 2025-07-18 07:00 | 2025-07-19 17:00 | 1 | 9 | Lot | 9 | 0
Electricity Connection Sanction; HT/LT Connection; Transformer & Captive Substation Approvals | PR-CA-14-020 | Grant of Clearance | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 08:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
Electricity Connection Sanction; HT/LT Connection; Transformer & Captive Substation Approvals | PR-CA-14-010 | Submission of Application | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 08:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1200 | GA of 2Px28 MMS Exterior Table (MMS Fix Tilt GA) | Completed | Task Dependent | 2025-02-19 07:00 | 2025-02-20 17:00 | 2025-03-18 | 2025-03-18 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1210 | GA of 2Px28 MMS Interior Table (MMS Fix Tilt GA) | Completed | Task Dependent | 2025-02-19 07:00 | 2025-02-20 17:00 | 2025-03-18 | 2025-03-18 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1230 | MMS Fix Tilt Fabrication Drawings (Interior) | Completed | Task Dependent | 2025-02-21 07:00 | 2025-02-24 17:00 | 2025-03-18 | 2025-03-18 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1220 | MMS Fix Tilt Fabrication Drawings (Exterior) | Completed | Task Dependent | 2025-02-21 07:00 | 2025-02-24 17:00 | 2025-03-18 | 2025-03-18 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1380 | Equipment Layout Of IDT Station-Type-BB (33Kv Switchgear) | Completed | Task Dependent | 2025-03-06 07:00 | 2025-03-11 17:00 | 2025-03-28 | 2025-03-28 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1360 | Cable Hanger Arrangement- GA | Completed | Task Dependent | 2025-03-07 07:00 | 2025-03-08 17:00 | 2025-03-28 | 2025-03-28 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1450 | GTP Of IDT | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-13 17:00 | 2025-04-26 | 2025-04-28 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1420 | GA Drawings With List Of Fittings For IDT | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-11 17:00 | 2025-04-26 | 2025-04-28 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1460 | O&M Manual Of IDT | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-31 17:00 | 2025-04-26 | 2025-04-28 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1440 | NIFPS (Nitrogen Injection & Fire Protection System) Drawings | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-13 17:00 | 2025-04-26 | 2025-04-28 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1430 | GA Of Marshalling Box & Wiring Diagram And Schematic Diagram Of Cooling System | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-11 17:00 | 2025-04-26 | 2025-04-28 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1590 | GA & GTP of Equipment Outline TDS1GL3XS_Trolly Mount | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-16 16:00 | 2025-03-08 | 2025-03-08 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1270 | Inverter Mounting Structure GA | Completed | Task Dependent | 2025-03-10 07:00 | 2025-03-11 17:00 | 2025-03-22 | 2025-03-22 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1510 | GTP Of HT Cable 3C X 300Sq.Mm | Completed | Task Dependent | 2025-03-11 07:00 | 2025-03-12 17:00 | 2025-03-19 | 2025-03-20 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1390 | Illumination Layout Of IDT Station Type-BB (33Kv Switchgear) | Completed | Task Dependent | 2025-03-12 07:00 | 2025-03-13 17:00 | 2025-04-01 | 2025-04-01 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1400 | Cable Route Layout Of IDT Station -Type-BB (33Kv Switchgear) | Completed | Task Dependent | 2025-03-12 07:00 | 2025-03-13 17:00 | 2025-04-01 | 2025-04-01 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1290 | IDT Station - HT - LT Panel Supporting Platformlayout And Details Of Structural Steel Shed | Completed | Task Dependent | 2025-03-12 07:00 | 2025-03-14 17:00 | 2025-03-26 | 2025-03-27 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1280 | Inverter Mounting Structure Fabrication | Completed | Task Dependent | 2025-03-12 07:00 | 2025-03-13 17:00 | 2025-03-22 | 2025-03-22 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1300 | IDT Station-HT-LT Panel Platfrom LT Panel Supporting Arragement | Completed | Task Dependent | 2025-03-14 07:00 | 2025-03-15 17:00 | 2025-03-27 | 2025-03-28 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1410 | Control & Auxiliary Cable Schedule Of IDT Station | Completed | Task Dependent | 2025-03-14 07:00 | 2025-03-15 17:00 | 2025-04-01 | 2025-04-01 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1580 | GA,GTP, SLD & Schematics for Outdoor Switchgear- TYPE BB | Completed | Task Dependent | 2025-03-22 07:00 | 2025-03-30 16:00 | 2025-04-28 | 2025-04-28 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1530 | GTP Of FO Cable For Armord Cable | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-15 17:00 | 2025-05-16 | 2025-05-16 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1520 | GTP Of DC Cable | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-15 17:00 | 2025-05-20 | 2025-05-20 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1320 | HT Cable Typical Section Details Drawing | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-19 17:00 | 2025-06-03 | 2025-06-03 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1570 | Robot Installation Manual (Civil) | Completed | Task Dependent | 2025-06-14 07:00 | 2025-07-03 17:00 | 2025-05-20 | 2025-05-21 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1240 | Robotic Cleaning System Docking Station Structure GA Details | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-15 17:00 | 2025-05-12 | 2025-05-12 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1550 | GTP Of LT Cable | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-15 17:00 | 2025-05-20 | 2025-05-21 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1310 | HT & FO Cable Routing Layout | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-19 17:00 | 2025-06-03 | 2025-06-03 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1470 | Inverter Datasheet | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-15 17:00 | 2025-05-20 | 2025-05-20 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1480 | Inverter Installation Manual | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-29 17:00 | 2025-05-20 | 2025-05-20 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1560 | Robot Communication Box GA And Foundation | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-17 17:00 | 2025-05-20 | 2025-05-21 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1370 | Cable Hanger Arrangement- Fabrication | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-15 17:00 | 2025-05-16 | 2025-05-16 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1260 | Robotic Cleaning System Docking Station Structure Fabrication Details (Leapting) | Completed | Task Dependent | 2025-06-16 07:00 | 2025-06-17 17:00 | 2025-05-20 | 2025-05-20 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1250 | Robotic Cleaning System Docking Station Structure Fabrication Details (Common) | Completed | Task Dependent | 2025-06-16 07:00 | 2025-06-17 17:00 | 2025-05-12 | 2025-05-12 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1330 | HT Cable Schedule | Completed | Task Dependent | 2025-06-20 07:00 | 2025-06-23 17:00 | 2025-06-03 | 2025-06-03 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1340 | FO Cable Schedule | Completed | Task Dependent | 2025-06-24 07:00 | 2025-06-27 17:00 | 2025-06-03 | 2025-06-03 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1500 | PV Module Installation Manual | Completed | Task Dependent | 2025-07-05 07:00 | 2025-07-08 17:00 | 2025-06-30 07:00 | 2025-06-30 17:00 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1490 | PV Module Data Sheet | Completed | Task Dependent | 2025-07-05 07:00 | 2025-07-08 17:00 | 2025-06-30 07:00 | 2025-06-30 17:00 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1350 | Typical DC String Cable Arrangement | Completed | Task Dependent | 2025-08-16 07:00 | 2025-08-18 17:00 | 2025-08-02 07:00 | 2025-08-04 17:00 | 1 | 0 |  | 0 | 0
ELECTRO-MECHANICAL | 603F-EN-1540 | Module Allocation Schedule | Completed | Task Dependent | 2025-11-01 07:00 | 2025-11-24 17:00 | 2025-10-27 07:00 | 2025-10-31 17:00 | 1 | 0 |  | 0 | 0
FIBER OPTIC CABLE | 603F-PR-3230 | Fiber Optic Cable-TBER | Completed | Task Dependent | 2025-02-24 07:00 | 2025-03-07 17:00 | 2025-02-24 07:00 | 2025-03-07 17:00 | 1 | 0 |  | 0 | 0
FIBER OPTIC CABLE | 603F-PR-3220 | Fiber Optic Cable-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-24 07:00 | 2025-02-27 17:00 | 2025-02-24 07:00 | 2025-02-27 17:00 | 1 | 0 |  | 0 | 0
FIBER OPTIC CABLE | 603F-PR-3240 | Fiber Optic Cable-Purchase Requistion | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-08 17:00 | 2025-03-08 07:00 | 2025-03-08 17:00 | 1 | 0 |  | 0 | 0
FIBER OPTIC CABLE | 603F-PR-3250 | Fiber Optic Cable-Note For Approval | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-09 17:00 | 2025-03-08 07:00 | 2025-03-09 17:00 | 1 | 0 |  | 0 | 0
FIBER OPTIC CABLE | 603F-PR-3260 | Fiber Optic Cable-LOI / PO Release | Completed | Task Dependent | 2025-03-10 07:00 | 2025-03-11 17:00 | 2025-03-10 07:00 | 2025-03-11 17:00 | 1 | 0 |  | 0 | 0
FIBER OPTIC CABLE | 603F-PR-3270 | Fiber Optic Cable-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-06-16 07:00 | 2025-08-02 17:00 | 2025-03-20 07:00 | 2025-04-10 17:00 | 1 | 0 |  | 0 | 0
FIBER OPTIC CABLE | 603F-PR-3280 | Fiber Optic Cable-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-11-22 07:00 | 2025-12-19 17:00 | 2025-11-17 07:00 | 2025-11-20 17:00 | 1 | 0 |  | 0 | 0
FIBER OPTIC CABLE | 603F-PR-4980 | Fiber Optic Cable-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-11-22 07:00 | 2025-12-19 17:00 | 2025-11-17 07:00 | 2025-11-20 17:00 | 1 | 0 |  | 0 | 0
FIBER OPTIC CABLE | 603F-PR-3300 | Fiber Optic Cable-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-11-22 07:00 | 2025-12-19 17:00 | 2025-11-17 07:00 | 2025-11-20 17:00 | 1 | 0 |  | 0 | 0
FIBER OPTIC CABLE | 603F-PR-4990 | Fiber Optic Cable-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-11-25 07:00 | 2025-12-22 17:00 | 2025-11-21 07:00 | 2025-11-22 17:00 | 1 | 10 | Kilometer | 0 | 0
FIBER OPTIC CABLE | 603F-PR-3290 | Fiber Optic Cable-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-11-25 07:00 | 2025-12-22 17:00 | 2025-11-21 07:00 | 2025-11-22 17:00 | 1 | 10 | Kilometer | 0 | 0
FIBER OPTIC CABLE | 603F-PR-3310 | Fiber Optic Cable-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-11-25 07:00 | 2025-12-22 17:00 | 2025-11-21 07:00 | 2025-11-22 17:00 | 1 | 10 | Kilometer | 0 | 0
Fire NOC / Fire Safety Certificate (State Fire Services) | PR-CA-23-020 | Grant of Clearance | Completed | Task Dependent | 2025-01-01 08:00 | 2025-01-01 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
Fire NOC / Fire Safety Certificate (State Fire Services) | PR-CA-23-010 | Submission of Application | Completed | Task Dependent | 2025-01-01 08:00 | 2025-01-01 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
Government Land | PR-LA-G-020 | Administrative Approval | Completed | Task Dependent | 2025-01-01 08:00 | 2026-03-10 16:00 | 2025-05-03 08:00 | 2025-07-30 16:00 | 1 | 0 |  | 0 | 0
Government Land | PR-LA-G-010 | Application to Nodal department | Completed | Task Dependent | 2025-01-01 08:00 | 2026-03-10 16:00 | 2025-05-03 08:00 | 2025-07-30 16:00 | 1 | 0 |  | 0 | 0
Government Land | PR-LA-G-030 | Lease Agreement | Completed | Task Dependent | 2025-01-01 08:00 | 2026-03-10 16:00 | 2025-05-03 08:00 | 2025-07-30 16:00 | 1 | 0 |  | 0 | 0
Government Land | PR-LA-G-040 | Transfer order | Completed | Task Dependent | 2025-01-01 08:00 | 2026-03-10 16:00 | 2025-05-03 08:00 | 2025-07-30 16:00 | 1 | 0 |  | 0 | 0
Government Land | PR-LA-G-050 | Possession handover | Completed | Task Dependent | 2025-01-01 08:00 | 2025-03-10 16:00 | 2025-05-03 08:00 | 2025-07-30 16:00 | 1 | 0 |  | 0 | 0
HT CABLE | 603F-PR-3120 | Ht Cable-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-23 07:00 | 2025-02-26 17:00 | 2025-02-23 07:00 | 2025-02-26 17:00 | 1 | 0 |  | 0 | 0
HT CABLE | 603F-PR-3130 | Ht Cable-TBER | Completed | Task Dependent | 2025-02-23 07:00 | 2025-03-06 17:00 | 2025-02-23 07:00 | 2025-03-06 17:00 | 1 | 0 |  | 0 | 0
HT CABLE | 603F-PR-3150 | HT Cable-Note For Approval | Completed | Task Dependent | 2025-03-07 07:00 | 2025-03-08 17:00 | 2025-03-07 07:00 | 2025-03-08 17:00 | 1 | 0 |  | 0 | 0
HT CABLE | 603F-PR-3140 | HT Cable-Purchase Requistion | Completed | Task Dependent | 2025-03-07 07:00 | 2025-03-07 17:00 | 2025-03-07 07:00 | 2025-03-07 17:00 | 1 | 0 |  | 0 | 0
HT CABLE | 603F-PR-3160 | Ht Cable-LOI / PO Release | Completed | Task Dependent | 2025-03-09 07:00 | 2025-03-10 17:00 | 2025-03-09 07:00 | 2025-03-10 17:00 | 1 | 0 |  | 0 | 0
HT CABLE | 603F-PR-3170 | HT Cable-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-10 07:00 | 2025-06-18 17:00 | 2025-03-31 07:00 | 2025-04-20 17:00 | 1 | 0 |  | 0 | 0
HT CABLE | 603F-PR-3180 | HT Cable-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-07-12 07:00 | 2025-07-31 17:00 | 2025-07-12 07:00 | 2025-07-31 17:00 | 1 | 0 |  | 0 | 0
HT CABLE | 603F-PR-3200 | HT Cable-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-10-11 07:00 | 2025-11-09 17:00 | 2025-07-20 07:00 | 2025-11-14 17:00 | 1 | 0 |  | 0 | 0
HT CABLE | 603F-PR-3190 | HT Cable-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-10-11 07:00 | 2025-11-03 17:00 | 2025-07-29 07:00 | 2025-08-20 17:00 | 1 | 36 | Kilometer | 0 | 0
HT CABLE | 603F-PR-3210 | HT Cable-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-10-13 07:00 | 2025-11-15 17:00 | 2025-08-18 07:00 | 2025-11-18 07:00 | 1 | 36 | Kilometer | 0 | 0
HT CABLE | 603F-PR-4960 | HT Cable-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-11-08 07:00 | 2025-11-19 17:00 | 2025-09-17 07:00 | 2025-11-18 17:00 | 1 | 0 |  | 0 | 0
HT CABLE | 603F-PR-4970 | HT Cable-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-11-16 07:00 | 2025-12-05 17:00 | 2025-11-16 07:00 | 2025-11-27 17:00 | 1 | 36 | Kilometer | 0 | 0
HT PANEL | 603F-PR-1720 | HT Panel-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-20 07:00 | 2025-02-23 17:00 | 2025-02-20 07:00 | 2025-02-23 17:00 | 1 | 0 |  | 0 | 0
HT PANEL | 603F-PR-1730 | HT Panel-TBER | Completed | Task Dependent | 2025-02-20 07:00 | 2025-03-03 17:00 | 2025-02-20 07:00 | 2025-03-03 17:00 | 1 | 0 |  | 0 | 0
HT PANEL | 603F-PR-1750 | HT Panel-Note For Approval | Completed | Task Dependent | 2025-03-04 07:00 | 2025-03-05 17:00 | 2025-03-04 07:00 | 2025-03-05 17:00 | 1 | 0 |  | 0 | 0
HT PANEL | 603F-PR-1740 | HT Panel-Purchase Requistion | Completed | Task Dependent | 2025-03-04 07:00 | 2025-03-04 17:00 | 2025-03-04 07:00 | 2025-03-04 17:00 | 1 | 0 |  | 0 | 0
HT PANEL | 603F-PR-1760 | HT Panel-LOI / PO Release | Completed | Task Dependent | 2025-03-06 07:00 | 2025-03-07 17:00 | 2025-03-06 07:00 | 2025-03-07 17:00 | 1 | 0 |  | 0 | 0
HT PANEL | 603F-PR-1770 | HT Panel-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-07 07:00 | 2025-06-21 17:00 | 2025-03-20 07:00 | 2025-04-10 07:59 | 1 | 0 |  | 0 | 0
HT PANEL | 603F-PR-1780 | HT Panel-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-07-12 07:00 | 2025-07-17 17:00 | 2025-06-03 07:00 | 2025-06-08 17:00 | 1 | 0 |  | 0 | 0
HT PANEL | 603F-PR-1800 | HT Panel-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-07-12 07:00 | 2025-07-17 17:00 | 2025-06-15 07:00 | 2025-06-20 17:00 | 1 | 0 |  | 0 | 0
HT PANEL | 603F-PR-1790 | HT Panel-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-07-15 07:00 | 2025-07-20 17:00 | 2025-06-09 07:00 | 2025-06-14 17:00 | 1 | 9 | Number | 0 | 0
HT PANEL | 603F-PR-1810 | HT Panel-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-07-15 07:00 | 2025-07-20 17:00 | 2025-06-21 07:00 | 2025-06-26 17:00 | 1 | 9 | Number | 0 | 0
HT PANEL | 603F-PR-4690 | HT Panel-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-09-20 07:00 | 2025-09-25 17:00 | 2025-09-07 07:00 | 2025-09-12 17:00 | 1 | 9 | Number | 0 | 0
HT PANEL | 603F-PR-4680 | HT Panel-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-09-20 07:00 | 2025-09-25 17:00 | 2025-09-01 07:00 | 2025-09-06 17:00 | 1 | 0 |  | 0 | 0
IDT FENCING & GATE | 603F-PR-4370 | IDT Fencing & Gate-TBER | Completed | Task Dependent | 2025-02-25 07:00 | 2025-03-08 17:00 | 2025-02-25 07:00 | 2025-03-08 17:00 | 1 | 0 |  | 0 | 0
IDT FENCING & GATE | 603F-PR-4360 | IDT Fencing & Gate-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-25 07:00 | 2025-02-28 17:00 | 2025-02-25 07:00 | 2025-02-28 17:00 | 1 | 0 |  | 0 | 0
IDT FENCING & GATE | 603F-PR-4390 | IDT Fencing & Gate-Note For Approval | Completed | Task Dependent | 2025-03-09 07:00 | 2025-03-10 17:00 | 2025-03-09 07:00 | 2025-03-10 17:00 | 1 | 0 |  | 0 | 0
IDT FENCING & GATE | 603F-PR-4380 | IDT Fencing & Gate-Purchase Requistion | Completed | Task Dependent | 2025-03-09 07:00 | 2025-03-09 17:00 | 2025-03-09 07:00 | 2025-03-09 17:00 | 1 | 0 |  | 0 | 0
IDT FENCING & GATE | 603F-PR-4400 | IDT Fencing & Gate-LOI / PO Release | Completed | Task Dependent | 2025-03-11 07:00 | 2025-03-12 17:00 | 2025-03-11 07:00 | 2025-03-12 17:00 | 1 | 0 |  | 0 | 0
IDT FENCING & GATE | 603F-PR-4410 | IDT Fencing & Gate-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-12 07:00 | 2025-06-22 17:00 | 2025-04-12 07:00 | 2025-06-10 17:00 | 1 | 0 |  | 0 | 0
IDT FENCING & GATE | 603F-PR-4420 | IDT Fencing & Gate-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-07-12 07:00 | 2025-07-15 17:00 | 2025-06-14 07:00 | 2025-06-18 17:00 | 1 | 0 |  | 0 | 0
IDT FENCING & GATE | 603F-PR-4430 | IDT Fencing & Gate-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-07-15 07:00 | 2025-07-18 17:00 | 2025-06-20 07:00 | 2025-06-23 17:00 | 1 | 18 | Number | 0 | 0
IDT FENCING & GATE | 603F-PR-4440 | IDT Fencing & Gate-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-07-16 07:00 | 2025-07-19 17:00 | 2025-06-14 07:00 | 2025-06-18 17:00 | 1 | 0 |  | 0 | 0
IDT FENCING & GATE | 603F-PR-4450 | IDT Fencing & Gate-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-07-19 07:00 | 2025-07-22 17:00 | 2025-07-20 07:00 | 2025-07-23 17:00 | 1 | 18 | Number | 0 | 0
IDT FENCING & GATE | 603F-PR-5210 | IDT Fencing & Gate-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-07-25 07:00 | 2025-07-28 17:00 | 2025-06-14 07:00 | 2025-06-18 17:00 | 1 | 0 |  | 0 | 0
IDT FENCING & GATE | 603F-PR-5220 | IDT Fencing & Gate-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-07-26 07:00 | 2025-07-29 17:00 | 2025-06-20 07:00 | 2025-06-23 17:00 | 1 | 18 | Number | 0 | 0
IDT (INCL. NIFPS) | 603F-PR-1620 | IDT (Incl. NIFPS)-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-20 07:00 | 2025-02-23 17:00 | 2025-02-20 07:00 | 2025-02-23 17:00 | 1 | 0 |  | 0 | 0
IDT (INCL. NIFPS) | 603F-PR-1630 | IDT (Incl. NIFPS)-TBER | Completed | Task Dependent | 2025-02-20 07:00 | 2025-03-03 17:00 | 2025-02-20 07:00 | 2025-03-03 17:00 | 1 | 0 |  | 0 | 0
IDT (INCL. NIFPS) | 603F-PR-1640 | IDT (Incl. NIFPS)-Purchase Requistion | Completed | Task Dependent | 2025-03-04 07:00 | 2025-03-04 17:00 | 2025-03-04 07:00 | 2025-03-04 17:00 | 1 | 0 |  | 0 | 0
IDT (INCL. NIFPS) | 603F-PR-1650 | IDT (Incl. NIFPS)-Note For Approval | Completed | Task Dependent | 2025-03-04 07:00 | 2025-03-05 17:00 | 2025-03-04 07:00 | 2025-03-05 17:00 | 1 | 0 |  | 0 | 0
IDT (INCL. NIFPS) | 603F-PR-1660 | IDT (Incl. NIFPS)-LOI / PO Release | Completed | Task Dependent | 2025-03-06 07:00 | 2025-03-07 17:00 | 2025-03-06 07:00 | 2025-03-07 17:00 | 1 | 0 |  | 0 | 0
IDT (INCL. NIFPS) | 603F-PR-1670 | IDT (Incl. NIFPS)-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-07 07:00 | 2025-06-13 17:00 | 2025-04-01 07:00 | 2025-11-23 17:00 | 1 | 0 |  | 0 | 0
IDT (INCL. NIFPS) | 603F-PR-1680 | IDT (Incl. NIFPS)-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-11-15 07:00 | 2025-12-24 17:00 | 2025-11-09 07:00 | 2025-11-13 17:00 | 1 | 0 |  | 0 | 0
IDT (INCL. NIFPS) | 603F-PR-1690 | IDT (Incl. NIFPS)-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-11-23 07:00 | 2025-12-24 17:00 | 2025-11-13 07:00 | 2025-11-15 17:00 | 1 | 9 | Number | 0 | 0
IDT (INCL. NIFPS) | 603F-PR-4660 | IDT (Incl. NIFPS)-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-12-07 07:00 | 2025-12-10 17:00 | 2025-11-23 07:00 | 2025-11-25 17:00 | 1 | 0 |  | 0 | 0
IDT (INCL. NIFPS) | 603F-PR-4670 | IDT (Incl. NIFPS)-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-12-11 07:00 | 2025-12-17 17:00 | 2025-11-26 07:00 | 2025-11-26 17:00 | 1 | 9 | Number | 0 | 0
IDT (INCL. NIFPS) | 603F-PR-1700 | IDT (Incl. NIFPS)-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-12-28 07:00 | 2025-12-31 17:00 | 2025-11-09 07:00 | 2025-11-24 17:00 | 1 | 0 |  | 0 | 0
IDT (INCL. NIFPS) | 603F-PR-1710 | IDT (Incl. NIFPS)-Receipt At Site-Lot-02 | Completed | Task Dependent | 2026-01-01 07:00 | 2026-01-04 17:00 | 2025-11-18 07:00 | 2025-11-27 17:00 | 1 | 9 | Number | 0 | 0
IDT STATION - FOUNDATION BOLT & INSERTS | 603F-PR-2120 | IDT Station - Foundation Bolt & Inserts-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-21 07:00 | 2025-02-24 17:00 | 2025-02-21 07:00 | 2025-02-24 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - FOUNDATION BOLT & INSERTS | 603F-PR-2130 | IDT Station - Foundation Bolt & Inserts-TBER | Completed | Task Dependent | 2025-02-24 07:00 | 2025-02-24 17:00 | 2025-02-24 07:00 | 2025-02-24 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - FOUNDATION BOLT & INSERTS | 603F-PR-2140 | IDT Station - Foundation Bolt & Inserts-Purchase Requistion | Completed | Task Dependent | 2025-02-25 07:00 | 2025-02-25 17:00 | 2025-02-25 07:00 | 2025-02-25 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - FOUNDATION BOLT & INSERTS | 603F-PR-2150 | IDT Station - Foundation Bolt & Inserts-Note For Approval | Completed | Task Dependent | 2025-02-25 07:00 | 2025-02-26 17:00 | 2025-02-25 07:00 | 2025-02-26 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - FOUNDATION BOLT & INSERTS | 603F-PR-2160 | IDT Station - Foundation Bolt & Inserts-LOI / PO Release | Completed | Task Dependent | 2025-02-27 07:00 | 2025-02-28 17:00 | 2025-02-27 07:00 | 2025-02-28 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - FOUNDATION BOLT & INSERTS | 603F-PR-2170 | IDT Station - Foundation Bolt & Inserts-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-03-31 07:00 | 2025-05-17 17:00 | 2025-03-31 07:00 | 2025-05-17 16:46 | 1 | 0 |  | 0 | 0
IDT STATION - FOUNDATION BOLT & INSERTS | 603F-PR-2180 | IDT Station - Foundation Bolt & Inserts-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-26 17:00 | 2025-04-12 07:00 | 2025-04-24 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - FOUNDATION BOLT & INSERTS | 603F-PR-2190 | IDT Station - Foundation Bolt & Inserts-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-06-17 07:00 | 2025-06-29 17:00 | 2025-04-15 07:00 | 2025-04-27 17:00 | 1 | 9 | Number | 0 | 0
IDT STATION - FOUNDATION BOLT & INSERTS | 603F-PR-2200 | IDT Station - Foundation Bolt & Inserts-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-06-27 07:00 | 2025-07-09 17:00 | 2025-04-25 07:00 | 2025-05-07 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - FOUNDATION BOLT & INSERTS | 603F-PR-2210 | IDT Station - Foundation Bolt & Inserts-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-07-01 07:00 | 2025-07-13 17:00 | 2025-04-29 07:00 | 2025-05-11 17:00 | 1 | 9 | Number | 0 | 0
IDT STATION - FOUNDATION BOLT & INSERTS | 603F-PR-4760 | IDT Station - Foundation Bolt & Inserts-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-08-03 16:46 | 2025-08-17 16:46 | 2025-05-15 16:46 | 2025-05-30 16:46 | 1 | 0 |  | 0 | 0
IDT STATION - FOUNDATION BOLT & INSERTS | 603F-PR-4770 | IDT Station - Foundation Bolt & Inserts-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-08-04 16:46 | 2025-08-18 16:46 | 2025-05-22 16:46 | 2025-05-30 16:46 | 1 | 9 | Number | 0 | 0
IDT STATION - RAIL | 603F-PR-2220 | IDT Station - Rail-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-21 07:00 | 2025-02-24 17:00 | 2025-02-21 07:00 | 2025-02-24 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - RAIL | 603F-PR-2230 | IDT Station - Rail-TBER | Completed | Task Dependent | 2025-02-24 07:00 | 2025-02-24 17:00 | 2025-02-24 07:00 | 2025-02-24 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - RAIL | 603F-PR-2240 | IDT Station - Rail-Purchase Requistion | Completed | Task Dependent | 2025-02-25 07:00 | 2025-02-25 17:00 | 2025-02-25 07:00 | 2025-02-25 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - RAIL | 603F-PR-2250 | IDT Station - Rail-Note For Approval | Completed | Task Dependent | 2025-02-25 07:00 | 2025-02-26 17:00 | 2025-02-25 07:00 | 2025-02-26 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - RAIL | 603F-PR-2260 | IDT Station - Rail-LOI / PO Release | Completed | Task Dependent | 2025-02-27 07:00 | 2025-02-28 17:00 | 2025-02-27 07:00 | 2025-02-28 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - RAIL | 603F-PR-2270 | IDT Station - Rail-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-03-31 07:00 | 2025-05-17 17:00 | 2025-03-31 07:00 | 2025-05-17 08:47 | 1 | 0 |  | 0 | 0
IDT STATION - RAIL | 603F-PR-2280 | IDT Station - Rail-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-26 17:00 | 2025-04-12 07:00 | 2025-04-24 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - RAIL | 603F-PR-2300 | IDT Station - Rail-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-06-27 07:00 | 2025-07-09 17:00 | 2025-04-25 07:00 | 2025-05-07 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - RAIL | 603F-PR-2290 | IDT Station - Rail-Receipt For Site-Lot-01 | Completed | Task Dependent | 2025-06-27 07:00 | 2025-07-09 17:00 | 2025-04-25 07:00 | 2025-05-07 17:00 | 1 | 9 | Number | 0 | 0
IDT STATION - RAIL | 603F-PR-2310 | IDT Station - Rail-Receipt For Site-Lot-02 | Completed | Task Dependent | 2025-07-01 07:00 | 2025-07-13 17:00 | 2025-04-29 07:00 | 2025-05-11 17:00 | 1 | 9 | Number | 0 | 0
IDT STATION - RAIL | 603F-PR-4780 | IDT Station - Rail-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-07-31 08:47 | 2025-08-13 08:47 | 2025-05-18 08:47 | 2025-05-28 08:47 | 1 | 0 |  | 0 | 0
IDT STATION - RAIL | 603F-PR-4790 | IDT Station - Rail-Receipt For Site-Lot-03 | Completed | Task Dependent | 2025-08-04 08:47 | 2025-08-18 08:47 | 2025-05-22 08:47 | 2025-05-30 08:47 | 1 | 9 | Number | 0 | 0
IDT STATION - REBAR | 603F-PR-2020 | IDT Station - Rebar-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-21 07:00 | 2025-02-24 17:00 | 2025-02-21 07:00 | 2025-02-24 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - REBAR | 603F-PR-2030 | IDT Station - Rebar-TBER | Completed | Task Dependent | 2025-02-24 07:00 | 2025-02-24 17:00 | 2025-02-24 07:00 | 2025-02-24 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - REBAR | 603F-PR-2050 | IDT Station - Rebar-Note For Approval | Completed | Task Dependent | 2025-02-25 07:00 | 2025-02-26 17:00 | 2025-02-25 07:00 | 2025-02-26 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - REBAR | 603F-PR-2040 | IDT Station - Rebar-Purchase Requistion | Completed | Task Dependent | 2025-02-25 07:00 | 2025-02-25 17:00 | 2025-02-25 07:00 | 2025-02-25 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - REBAR | 603F-PR-2060 | IDT Station - Rebar-LOI / PO Release | Completed | Task Dependent | 2025-02-27 07:00 | 2025-02-28 17:00 | 2025-02-27 07:00 | 2025-02-28 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - REBAR | 603F-PR-2070 | IDT Station - Rebar-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-03-01 07:00 | 2025-04-22 17:00 | 2025-03-01 07:00 | 2025-03-20 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - REBAR | 603F-PR-2080 | IDT Station - Rebar-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-03-13 07:00 | 2025-03-25 17:00 | 2025-03-13 07:00 | 2025-03-16 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - REBAR | 603F-PR-2090 | IDT Station - Rebar-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-03-16 07:00 | 2025-03-28 17:00 | 2025-03-15 07:00 | 2025-03-18 17:00 | 1 | 9 | Number | 0 | 0
IDT STATION - REBAR | 603F-PR-2100 | IDT Station - Rebar-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-03-26 07:00 | 2025-04-07 17:00 | 2025-03-16 07:00 | 2025-03-20 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - REBAR | 603F-PR-2110 | IDT Station - Rebar-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-03-30 07:00 | 2025-04-11 17:00 | 2025-03-18 07:00 | 2025-03-22 17:00 | 1 | 9 | Number | 0 | 0
IDT STATION - REBAR | 603F-PR-4740 | IDT Station - Rebar-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-04-23 07:00 | 2025-05-05 17:00 | 2025-03-20 07:00 | 2025-03-26 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - REBAR | 603F-PR-4750 | IDT Station - Rebar-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-04-27 07:00 | 2025-05-09 17:00 | 2025-03-22 07:00 | 2025-03-31 17:00 | 1 | 9 | Number | 0 | 0
IDT STATION - STRUCTURE, SHEETING & FASTENERS | 603F-PR-2320 | IDT Station - Structure, Sheeting & Fasteners-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-22 07:00 | 2025-02-25 17:00 | 2025-02-22 07:00 | 2025-02-25 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - STRUCTURE, SHEETING & FASTENERS | 603F-PR-2330 | IDT Station - Structure, Sheeting & Fasteners-TBER | Completed | Task Dependent | 2025-02-24 07:00 | 2025-02-25 17:00 | 2025-02-24 07:00 | 2025-02-25 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - STRUCTURE, SHEETING & FASTENERS | 603F-PR-2350 | IDT Station - Structure, Sheeting & Fasteners-Note For Approval | Completed | Task Dependent | 2025-02-26 07:00 | 2025-02-27 17:00 | 2025-02-26 07:00 | 2025-02-27 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - STRUCTURE, SHEETING & FASTENERS | 603F-PR-2340 | IDT Station - Structure, Sheeting & Fasteners-Purchase Requistion | Completed | Task Dependent | 2025-02-26 07:00 | 2025-02-26 17:00 | 2025-02-26 07:00 | 2025-02-26 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - STRUCTURE, SHEETING & FASTENERS | 603F-PR-2360 | IDT Station - Structure, Sheeting & Fasteners-LOI / PO Release | Completed | Task Dependent | 2025-02-28 07:00 | 2025-03-01 17:00 | 2025-02-28 07:00 | 2025-03-01 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - STRUCTURE, SHEETING & FASTENERS | 603F-PR-2380 | IDT Station - Structure, Sheeting & Fasteners-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-19 17:00 | 2025-05-15 07:00 | 2025-06-13 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - STRUCTURE, SHEETING & FASTENERS | 603F-PR-2370 | IDT Station - Structure, Sheeting & Fasteners-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-06-14 07:00 | 2025-07-13 17:00 | 2025-05-14 07:00 | 2025-07-04 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - STRUCTURE, SHEETING & FASTENERS | 603F-PR-2390 | IDT Station - Structure, Sheeting & Fasteners-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-19 17:00 | 2025-05-20 07:00 | 2025-05-27 17:00 | 1 | 18 | Number | 18 | 0
IDT STATION - STRUCTURE, SHEETING & FASTENERS | 603F-PR-2400 | IDT Station - Structure, Sheeting & Fasteners-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2026-01-03 07:00 | 2026-01-05 17:00 | 2025-12-28 07:00 | 2025-12-28 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - STRUCTURE, SHEETING & FASTENERS | 603F-PR-2410 | IDT Station - Structure, Sheeting & Fasteners-Receipt At Site-Lot-02 | Completed | Task Dependent | 2026-01-04 07:00 | 2026-01-06 17:00 | 2026-01-01 07:00 | 2026-01-02 17:00 | 1 | 18 | Number | 18 | 0
IDT STATION - STRUCTURE, SHEETING & FASTENERS | 603F-PR-4800 | IDT Station - Structure, Sheeting & Fasteners-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2026-01-06 07:00 | 2026-01-11 17:00 | 2025-12-28 07:00 | 2025-12-29 17:00 | 1 | 0 |  | 0 | 0
IDT STATION - STRUCTURE, SHEETING & FASTENERS | 603F-PR-4810 | IDT Station - Structure, Sheeting & Fasteners-Receipt At Site-Lot-03 | Completed | Task Dependent | 2026-01-07 07:00 | 2026-01-12 17:00 | 2026-01-02 07:00 | 2026-01-03 17:00 | 1 | 18 | Number | 18 | 0
INVERTER | 603F-PR-1530 | Inverter-TBER | Completed | Task Dependent | 2025-02-20 07:00 | 2025-03-03 17:00 | 2025-02-20 07:00 | 2025-03-03 17:00 | 1 | 0 |  | 0 | 0
INVERTER | 603F-PR-1520 | Inverter-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-20 07:00 | 2025-02-23 17:00 | 2025-02-20 07:00 | 2025-02-23 17:00 | 1 | 0 |  | 0 | 0
INVERTER | 603F-PR-1550 | Inverter-Note For Approval | Completed | Task Dependent | 2025-03-04 07:00 | 2025-03-05 17:00 | 2025-03-04 07:00 | 2025-03-05 17:00 | 1 | 0 |  | 0 | 0
INVERTER | 603F-PR-1540 | Inverter-Purchase Requistion | Completed | Task Dependent | 2025-03-04 07:00 | 2025-03-04 17:00 | 2025-03-04 07:00 | 2025-03-04 17:00 | 1 | 0 |  | 0 | 0
INVERTER | 603F-PR-1560 | Inverter-LOI / PO Release | Completed | Task Dependent | 2025-03-06 07:00 | 2025-03-07 17:00 | 2025-03-06 07:00 | 2025-03-07 17:00 | 1 | 0 |  | 0 | 0
INVERTER | 603F-PR-1570 | Inverter-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-07 07:00 | 2025-06-25 17:00 | 2025-02-25 07:00 | 2025-03-15 07:09 | 1 | 0 |  | 0 | 0
INVERTER | 603F-PR-1590 | Inverter-Receipt At Site--Lot-01 | Completed | Task Dependent | 2025-07-12 07:00 | 2025-08-04 17:00 | 2025-07-08 07:00 | 2025-07-30 17:00 | 1 | 419 | Number | 0 | 0
INVERTER | 603F-PR-1580 | Inverter-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-07-12 07:00 | 2025-08-04 17:00 | 2025-07-04 07:00 | 2025-07-05 17:00 | 1 | 0 |  | 0 | 0
INVERTER | 603F-PR-1600 | Inverter-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-12-05 07:00 | 2025-12-19 17:00 | 2025-10-08 07:00 | 2025-10-20 17:00 | 1 | 0 |  | 0 | 0
INVERTER | 603F-PR-1610 | Inverter-Receipt At Site--Lot-02 | Completed | Task Dependent | 2025-12-07 07:00 | 2025-12-23 17:00 | 2025-10-22 07:00 | 2025-10-30 17:00 | 1 | 419 | Number | 0 | 0
INVERTER | 603F-PR-4640 | Inverter-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-12-20 07:00 | 2026-01-05 17:00 | 2025-10-08 07:00 | 2025-10-20 17:00 | 1 | 0 |  | 0 | 0
INVERTER | 603F-PR-4650 | Inverter-Receipt At Site--Lot-03 | Completed | Task Dependent | 2025-12-21 07:00 | 2026-01-06 17:00 | 2025-10-22 07:00 | 2025-10-30 17:00 | 1 | 419 | Number | 0 | 0
INVERTER STRUCTURE - CANOPY | 603F-PR-3520 | Inverter Structure - Canopy-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-24 07:00 | 2025-02-27 17:00 | 2025-02-24 07:00 | 2025-02-27 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - CANOPY | 603F-PR-3530 | Inverter Structure - Canopy-TBER | Completed | Task Dependent | 2025-02-24 07:00 | 2025-03-07 17:00 | 2025-02-24 07:00 | 2025-03-07 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - CANOPY | 603F-PR-3550 | Inverter Structure - Canopy-Note For Approval | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-09 17:00 | 2025-03-08 07:00 | 2025-03-09 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - CANOPY | 603F-PR-3540 | Inverter Structure - Canopy-Purchase Requistion | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-08 17:00 | 2025-03-08 07:00 | 2025-03-08 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - CANOPY | 603F-PR-3560 | Inverter Structure - Canopy-LOI / PO Release | Completed | Task Dependent | 2025-03-10 07:00 | 2025-03-11 17:00 | 2025-03-10 07:00 | 2025-03-11 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - CANOPY | 603F-PR-3570 | Inverter Structure - Canopy-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-11 07:00 | 2025-06-09 17:00 | 2025-05-16 07:00 | 2025-06-30 07:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - CANOPY | 603F-PR-3580 | Inverter Structure - Canopy-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-04-26 07:00 | 2025-05-07 17:00 | 2025-05-19 07:00 | 2025-05-31 07:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - CANOPY | 603F-PR-3590 | Inverter Structure - Canopy-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-04-29 07:00 | 2025-05-10 17:00 | 2025-05-22 07:00 | 2025-06-03 07:00 | 1 | 419 | Number | 0 | 0
INVERTER STRUCTURE - CANOPY | 603F-PR-3600 | Inverter Structure - Canopy-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-05-08 07:00 | 2025-05-19 17:00 | 2025-06-01 07:00 | 2025-06-15 07:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - CANOPY | 603F-PR-3610 | Inverter Structure - Canopy-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-05-12 07:00 | 2025-05-23 17:00 | 2025-06-04 07:00 | 2025-06-18 17:00 | 1 | 419 | Number | 0 | 0
INVERTER STRUCTURE - CANOPY | 603F-PR-5040 | Inverter Structure - Canopy-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-25 17:00 | 2025-07-01 07:00 | 2025-07-10 07:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - CANOPY | 603F-PR-5050 | Inverter Structure - Canopy-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-06-18 07:00 | 2025-06-29 17:00 | 2025-07-04 07:00 | 2025-07-14 17:00 | 1 | 419 | Number | 0 | 0
INVERTER STRUCTURE - FASTENERS | 603F-PR-3430 | Inverter Structure - Fasteners-TBER | Completed | Task Dependent | 2025-02-24 07:00 | 2025-03-07 17:00 | 2025-02-24 07:00 | 2025-03-07 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - FASTENERS | 603F-PR-3420 | Inverter Structure - Fasteners-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-24 07:00 | 2025-02-27 17:00 | 2025-02-24 07:00 | 2025-02-27 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - FASTENERS | 603F-PR-3440 | Inverter Structure - Fasteners-Purchase Requistion | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-08 17:00 | 2025-03-08 07:00 | 2025-03-08 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - FASTENERS | 603F-PR-3450 | Inverter Structure - Fasteners-Note For Approval | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-09 17:00 | 2025-03-08 07:00 | 2025-03-09 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - FASTENERS | 603F-PR-3460 | Inverter Structure - Fasteners-LOI / PO Release | Completed | Task Dependent | 2025-03-10 07:00 | 2025-03-11 17:00 | 2025-03-10 07:00 | 2025-03-11 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - FASTENERS | 603F-PR-3470 | Inverter Structure - Fasteners-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-11 07:00 | 2025-06-09 17:00 | 2025-05-23 07:00 | 2025-05-25 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - FASTENERS | 603F-PR-3480 | Inverter Structure - Fasteners-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-04-26 07:00 | 2025-05-07 17:00 | 2025-05-30 07:00 | 2025-05-30 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - FASTENERS | 603F-PR-3490 | Inverter Structure - Fasteners-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-04-29 07:00 | 2025-05-10 17:00 | 2025-06-04 07:00 | 2025-06-04 17:00 | 1 | 419 | Number | 0 | 0
INVERTER STRUCTURE - FASTENERS | 603F-PR-3500 | Inverter Structure - Fasteners-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-05-08 07:00 | 2025-05-19 17:00 | 2025-05-30 07:00 | 2025-05-30 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - FASTENERS | 603F-PR-3510 | Inverter Structure - Fasteners-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-05-12 07:00 | 2025-05-23 17:00 | 2025-06-04 07:00 | 2025-06-04 07:05 | 1 | 419 | Number | 0 | 0
INVERTER STRUCTURE - FASTENERS | 603F-PR-5020 | Inverter Structure - Fasteners-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-25 17:00 | 2025-05-30 07:00 | 2025-05-30 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - FASTENERS | 603F-PR-5030 | Inverter Structure - Fasteners-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-06-18 07:00 | 2025-06-29 17:00 | 2025-06-04 07:00 | 2025-06-04 17:00 | 1 | 419 | Number | 0 | 0
INVERTER STRUCTURE - SELF TAPPING SCREW | 603F-PR-3630 | Inverter Structure - Self Tapping Screw-TBER | Completed | Task Dependent | 2025-02-24 07:00 | 2025-03-07 17:00 | 2025-02-24 07:00 | 2025-03-07 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - SELF TAPPING SCREW | 603F-PR-3620 | Inverter Structure - Self Tapping Screw-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-24 07:00 | 2025-02-27 17:00 | 2025-02-24 07:00 | 2025-02-27 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - SELF TAPPING SCREW | 603F-PR-3650 | Inverter Structure - Self Tapping Screw-Note For Approval | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-09 17:00 | 2025-03-08 07:00 | 2025-03-09 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - SELF TAPPING SCREW | 603F-PR-3640 | Inverter Structure - Self Tapping Screw-Purchase Requistion | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-08 17:00 | 2025-03-08 07:00 | 2025-03-08 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - SELF TAPPING SCREW | 603F-PR-3660 | Inverter Structure - Self Tapping Screw-LOI / PO Release | Completed | Task Dependent | 2025-03-10 07:00 | 2025-03-11 17:00 | 2025-03-10 07:00 | 2025-03-11 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - SELF TAPPING SCREW | 603F-PR-3670 | Inverter Structure - Self Tapping Screw-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-11 07:00 | 2025-06-09 17:00 | 2025-03-12 07:00 | 2025-03-20 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - SELF TAPPING SCREW | 603F-PR-3680 | Inverter Structure - Self Tapping Screw-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-04-26 07:00 | 2025-05-07 17:00 | 2025-03-21 07:00 | 2025-03-23 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - SELF TAPPING SCREW | 603F-PR-3690 | Inverter Structure - Self Tapping Screw-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-04-29 07:00 | 2025-05-10 17:00 | 2025-03-25 07:00 | 2025-03-26 17:00 | 1 | 419 | Number | 0 | 0
INVERTER STRUCTURE - SELF TAPPING SCREW | 603F-PR-3700 | Inverter Structure - Self Tapping Screw-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-05-08 07:00 | 2025-05-19 17:00 | 2025-03-26 07:00 | 2025-03-27 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - SELF TAPPING SCREW | 603F-PR-3710 | Inverter Structure - Self Tapping Screw-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-05-12 07:00 | 2025-05-23 17:00 | 2025-03-28 07:00 | 2025-03-29 17:00 | 1 | 419 | Number | 0 | 0
INVERTER STRUCTURE - SELF TAPPING SCREW | 603F-PR-5060 | Inverter Structure - Self Tapping Screw-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-06-10 07:00 | 2025-06-21 17:00 | 2025-03-30 07:00 | 2025-03-31 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - SELF TAPPING SCREW | 603F-PR-5070 | Inverter Structure - Self Tapping Screw-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-25 17:00 | 2025-04-01 07:00 | 2025-04-02 17:00 | 1 | 419 | Number | 0 | 0
INVERTER STRUCTURE - SUPPORT BEAM & COLUMN | 603F-PR-3320 | Inverter Structure - Support Beam & Column-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-23 07:00 | 2025-02-26 17:00 | 2025-02-23 07:00 | 2025-02-26 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - SUPPORT BEAM & COLUMN | 603F-PR-3330 | Inverter Structure - Support Beam & Column-TBER | Completed | Task Dependent | 2025-02-23 07:00 | 2025-03-06 17:00 | 2025-02-23 07:00 | 2025-03-06 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - SUPPORT BEAM & COLUMN | 603F-PR-3340 | Inverter Structure - Support Beam & Column-Purchase Requistion | Completed | Task Dependent | 2025-03-07 07:00 | 2025-03-07 17:00 | 2025-03-07 07:00 | 2025-03-07 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - SUPPORT BEAM & COLUMN | 603F-PR-3350 | Inverter Structure - Support Beam & Column-Note For Approval | Completed | Task Dependent | 2025-03-07 07:00 | 2025-03-08 17:00 | 2025-03-07 07:00 | 2025-03-08 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - SUPPORT BEAM & COLUMN | 603F-PR-3360 | Inverter Structure - Support Beam & Column-LOI / PO Release | Completed | Task Dependent | 2025-03-09 07:00 | 2025-03-10 17:00 | 2025-03-09 07:00 | 2025-03-10 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - SUPPORT BEAM & COLUMN | 603F-PR-3370 | Inverter Structure - Support Beam & Column-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-10 07:00 | 2025-06-08 17:00 | 2025-05-04 07:00 | 2025-05-30 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - SUPPORT BEAM & COLUMN | 603F-PR-3410 | Inverter Structure - Support Beam & Column-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-05-24 07:00 | 2025-06-04 17:00 | 2025-05-23 07:00 | 2025-06-04 17:00 | 1 | 419 | Number | 419 | 0
INVERTER STRUCTURE - SUPPORT BEAM & COLUMN | 603F-PR-3380 | Inverter Structure - Support Beam & Column-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-05-24 07:00 | 2025-06-04 17:00 | 2025-05-07 07:00 | 2025-05-21 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - SUPPORT BEAM & COLUMN | 603F-PR-3390 | Inverter Structure - Support Beam & Column-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-05-27 07:00 | 2025-06-07 17:00 | 2025-05-08 07:00 | 2025-05-29 17:00 | 1 | 419 | Number | 419 | 0
INVERTER STRUCTURE - SUPPORT BEAM & COLUMN | 603F-PR-3400 | Inverter Structure - Support Beam & Column-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-06-05 07:00 | 2025-06-16 17:00 | 2025-05-18 07:00 | 2025-05-23 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - SUPPORT BEAM & COLUMN | 603F-PR-5000 | Inverter Structure - Support Beam & Column-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2026-01-07 07:00 | 2026-01-10 17:00 | 2025-11-26 07:00 | 2025-11-29 17:00 | 1 | 0 |  | 0 | 0
INVERTER STRUCTURE - SUPPORT BEAM & COLUMN | 603F-PR-5010 | Inverter Structure - Support Beam & Column-Receipt At Site-Lot-03 | Completed | Task Dependent | 2026-01-08 07:00 | 2026-01-11 17:00 | 2025-12-28 07:00 | 2026-01-03 17:00 | 1 | 419 | Number | 419 | 0
LAND ACQUISITION | 51R1-LD-1000 | Land Sub Lease agreement with SPV | Completed | Task Dependent | 2025-02-15 08:00 | 2025-03-20 14:00 | 2025-05-03 | 2025-07-30 17:00 | 1 | 0 |  | 0 | 0
LOGISTICS & MATERIAL HANDLING INFRASTRUCTURE | PR-LM-A-010 | Construction / Strengthening of external roads for movment of Manpower/Equipment/Machinery to site | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
LT CABLE | 603F-PR-2930 | LT Cable-TBER | Completed | Task Dependent | 2025-02-23 07:00 | 2025-03-06 17:00 | 2025-02-23 07:00 | 2025-03-06 17:00 | 1 | 0 |  | 0 | 0
LT CABLE | 603F-PR-2920 | LT Cable-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-23 07:00 | 2025-02-26 17:00 | 2025-02-23 07:00 | 2025-02-26 17:00 | 1 | 0 |  | 0 | 0
LT CABLE | 603F-PR-2940 | LT Cable-Purchase Requistion | Completed | Task Dependent | 2025-03-07 07:00 | 2025-03-07 17:00 | 2025-03-07 07:00 | 2025-03-07 17:00 | 1 | 0 |  | 0 | 0
LT CABLE | 603F-PR-2950 | LT Cable-Note For Approval | Completed | Task Dependent | 2025-03-07 07:00 | 2025-03-08 17:00 | 2025-03-07 07:00 | 2025-03-08 17:00 | 1 | 0 |  | 0 | 0
LT CABLE | 603F-PR-2960 | LT Cable-LOI / PO Release | Completed | Task Dependent | 2025-03-09 07:00 | 2025-03-10 15:00 | 2025-03-09 07:00 | 2025-03-10 15:00 | 1 | 0 |  | 0 | 0
LT CABLE | 603F-PR-2970 | LT Cable-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-09 15:00 | 2025-06-25 15:00 | 2025-03-31 15:00 | 2025-05-20 07:01 | 1 | 0 |  | 0 | 0
LT CABLE | 603F-PR-2980 | LT Cable-Dispatch For Site-Lot-01 (To be used from surplus available from Phase I and Phase II.) | Completed | Task Dependent | 2025-10-11 07:00 | 2025-11-04 17:00 | 2025-06-18 07:00 | 2025-07-16 17:00 | 1 | 0 |  | 0 | 0
LT CABLE | 603F-PR-2990 | LT Cable-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-10-19 07:00 | 2025-11-07 17:00 | 2025-07-17 07:00 | 2025-08-07 17:00 | 1 | 111 | Kilometer | 0 | 0
LT CABLE | 603F-PR-4920 | LT Cable-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-11-01 07:00 | 2025-11-25 17:00 | 2025-10-13 07:00 | 2025-10-27 17:00 | 1 | 0 |  | 0 | 0
LT CABLE | 603F-PR-3000 | LT Cable-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-11-05 07:00 | 2025-11-29 17:00 | 2025-08-08 07:00 | 2025-09-30 17:00 | 1 | 0 |  | 0 | 0
LT CABLE | 603F-PR-4930 | LT Cable-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-11-06 07:00 | 2025-12-15 17:00 | 2025-10-28 07:00 | 2025-11-01 17:00 | 1 | 111 | Kilometer | 0 | 0
LT CABLE | 603F-PR-3010 | LT Cable-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-11-07 07:00 | 2025-12-16 17:00 | 2025-09-27 07:00 | 2025-10-10 17:00 | 1 | 111 | Kilometer | 0 | 0
LT CABLE - CLAMPS | 603F-PR-2720 | LT Cable - Clamps-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-22 07:00 | 2025-02-25 17:00 | 2025-02-22 07:00 | 2025-02-25 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - CLAMPS | 603F-PR-2730 | LT Cable - Clamps-TBER | Completed | Task Dependent | 2025-02-22 07:00 | 2025-03-05 17:00 | 2025-02-22 07:00 | 2025-03-05 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - CLAMPS | 603F-PR-2750 | LT Cable - Clamps-Note For Approval | Completed | Task Dependent | 2025-03-06 07:00 | 2025-03-07 17:00 | 2025-03-06 07:00 | 2025-03-07 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - CLAMPS | 603F-PR-2740 | LT Cable - Clamps-Purchase Requistion | Completed | Task Dependent | 2025-03-06 07:00 | 2025-03-06 17:00 | 2025-03-06 07:00 | 2025-03-06 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - CLAMPS | 603F-PR-2760 | LT Cable - Clamps-LOI / PO Release | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-09 17:00 | 2025-03-08 07:00 | 2025-03-09 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - CLAMPS | 603F-PR-2770 | LT Cable - Clamps-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-09 07:00 | 2025-06-11 17:00 | 2025-04-01 07:00 | 2025-04-30 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - CLAMPS | 603F-PR-2780 | LT Cable - Clamps-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-05-11 07:00 | 2025-05-22 17:00 | 2025-05-11 07:00 | 2025-05-30 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - CLAMPS | 603F-PR-2790 | LT Cable - Clamps-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-05-14 07:00 | 2025-05-25 17:00 | 2025-04-04 07:00 | 2025-05-03 17:00 | 1 | 9 | Lot | 0 | 0
LT CABLE - CLAMPS | 603F-PR-2800 | LT Cable - Clamps-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-05-23 07:00 | 2025-06-03 17:00 | 2025-04-06 07:00 | 2025-05-20 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - CLAMPS | 603F-PR-4880 | LT Cable - Clamps-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-05-24 07:00 | 2025-06-04 17:00 | 2025-05-23 07:00 | 2025-05-27 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - CLAMPS | 603F-PR-2810 | LT Cable - Clamps-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-05-27 07:00 | 2025-06-07 17:00 | 2025-04-06 07:00 | 2025-05-23 17:00 | 1 | 9 | Lot | 0 | 0
LT CABLE - CLAMPS | 603F-PR-4890 | LT Cable - Clamps-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-25 17:00 | 2025-04-10 07:00 | 2025-05-31 17:00 | 1 | 9 | Lot | 0 | 0
LT CABLE - FASTENERS | 603F-PR-2520 | LT Cable - Fasteners-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-22 07:00 | 2025-02-25 17:00 | 2025-02-22 07:00 | 2025-02-25 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - FASTENERS | 603F-PR-2530 | LT Cable - Fasteners-TBER | Completed | Task Dependent | 2025-02-22 07:00 | 2025-03-05 17:00 | 2025-02-22 07:00 | 2025-03-05 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - FASTENERS | 603F-PR-2540 | LT Cable - Fasteners-Purchase Requistion | Completed | Task Dependent | 2025-03-06 07:00 | 2025-03-06 17:00 | 2025-03-06 07:00 | 2025-03-06 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - FASTENERS | 603F-PR-2550 | LT Cable - Fasteners-Note For Approval | Completed | Task Dependent | 2025-03-06 07:00 | 2025-03-07 17:00 | 2025-03-06 07:00 | 2025-03-07 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - FASTENERS | 603F-PR-2560 | LT Cable - Fasteners-LOI / PO Release | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-09 17:00 | 2025-03-08 07:00 | 2025-03-09 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - FASTENERS | 603F-PR-2570 | LT Cable - Fasteners-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-09 07:00 | 2025-06-11 17:00 | 2025-05-23 07:00 | 2025-05-25 16:42 | 1 | 0 |  | 0 | 0
LT CABLE - FASTENERS | 603F-PR-2580 | LT Cable - Fasteners-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-05-24 07:00 | 2025-06-04 17:00 | 2025-05-30 07:00 | 2025-05-30 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - FASTENERS | 603F-PR-2590 | LT Cable - Fasteners-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-25 17:00 | 2025-06-04 07:00 | 2025-06-04 17:00 | 1 | 9 | Lot | 0 | 0
LT CABLE - FASTENERS | 603F-PR-2600 | LT Cable - Fasteners-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-06-18 07:00 | 2025-06-29 17:00 | 2025-05-30 07:00 | 2025-05-30 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - FASTENERS | 603F-PR-2610 | LT Cable - Fasteners-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-06-22 07:00 | 2025-07-03 17:00 | 2025-06-04 07:00 | 2025-06-04 17:00 | 1 | 9 | Lot | 0 | 0
LT CABLE - FASTENERS | 603F-PR-4840 | LT Cable - Fasteners-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-08-21 16:42 | 2025-09-02 16:42 | 2025-05-30 16:42 | 2025-05-30 16:42 | 1 | 0 |  | 0 | 0
LT CABLE - FASTENERS | 603F-PR-4850 | LT Cable - Fasteners-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-08-22 16:42 | 2025-09-03 16:42 | 2025-05-04 16:42 | 2025-05-04 16:42 | 1 | 9 | Lot | 0 | 0
LT CABLE - HANGERS | 603F-PR-2830 | LT Cable - Hangers-TBER | Completed | Task Dependent | 2025-02-22 07:00 | 2025-03-05 17:00 | 2025-02-22 07:00 | 2025-03-05 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - HANGERS | 603F-PR-2820 | LT Cable - Hangers-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-22 07:00 | 2025-02-25 17:00 | 2025-02-22 07:00 | 2025-02-25 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - HANGERS | 603F-PR-2840 | LT Cable - Hangers-Purchase Requistion | Completed | Task Dependent | 2025-03-06 07:00 | 2025-03-06 17:00 | 2025-03-06 07:00 | 2025-03-06 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - HANGERS | 603F-PR-2850 | LT Cable - Hangers-Note For Approval | Completed | Task Dependent | 2025-03-06 07:00 | 2025-03-07 17:00 | 2025-03-06 07:00 | 2025-03-07 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - HANGERS | 603F-PR-2860 | LT Cable - Hangers-LOI / PO Release | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-09 17:00 | 2025-03-08 07:00 | 2025-03-09 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - HANGERS | 603F-PR-2870 | LT Cable - Hangers-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-09 07:00 | 2025-06-11 17:00 | 2025-04-01 | 2026-01-12 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - HANGERS | 603F-PR-2880 | LT Cable - Hangers-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-05-24 07:00 | 2025-06-04 17:00 | 2025-04-04 | 2025-05-13 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - HANGERS | 603F-PR-2890 | LT Cable - Hangers-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-05-27 07:00 | 2025-06-07 17:00 | 2025-04-04 | 2025-05-23 17:00 | 1 | 9 | Lot | 0 | 0
LT CABLE - HANGERS | 603F-PR-2900 | LT Cable - Hangers-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-06-05 07:00 | 2025-06-16 17:00 | 2025-04-06 | 2025-12-21 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - HANGERS | 603F-PR-2910 | LT Cable - Hangers-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-06-09 07:00 | 2025-06-20 17:00 | 2025-04-06 | 2025-12-22 17:00 | 1 | 9 | Lot | 9 | 0
LT CABLE - HANGERS | 603F-PR-4910 | LT Cable - Hangers-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-25 17:00 | 2025-04-10 | 2025-12-26 17:00 | 1 | 9 | Lot | 9 | 0
LT CABLE - HANGERS | 603F-PR-4900 | LT Cable - Hangers-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-06-17 07:00 | 2025-06-28 17:00 | 2025-05-23 07:00 | 2025-12-23 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - MESSENGER WIRE | 603F-PR-2630 | LT Cable - Messenger Wire-TBER | Completed | Task Dependent | 2025-02-22 07:00 | 2025-03-05 17:00 | 2025-02-22 07:00 | 2025-03-05 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - MESSENGER WIRE | 603F-PR-2620 | LT Cable - Messenger Wire-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-22 07:00 | 2025-02-25 17:00 | 2025-02-22 07:00 | 2025-02-25 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - MESSENGER WIRE | 603F-PR-2640 | LT Cable - Messenger Wire-Purchase Requistion | Completed | Task Dependent | 2025-03-06 07:00 | 2025-03-06 17:00 | 2025-03-06 07:00 | 2025-03-06 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - MESSENGER WIRE | 603F-PR-2650 | LT Cable - Messenger Wire-Note For Approval | Completed | Task Dependent | 2025-03-06 07:00 | 2025-03-07 17:00 | 2025-03-06 07:00 | 2025-03-07 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - MESSENGER WIRE | 603F-PR-2660 | LT Cable - Messenger Wire-LOI / PO Release | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-09 17:00 | 2025-03-08 07:00 | 2025-03-09 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - MESSENGER WIRE | 603F-PR-2670 | LT Cable - Messenger Wire-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-09 07:00 | 2025-06-11 17:00 | 2025-04-01 07:00 | 2025-04-30 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - MESSENGER WIRE | 603F-PR-2680 | LT Cable - Messenger Wire-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-05-11 07:00 | 2025-05-22 17:00 | 2025-04-04 07:00 | 2025-04-23 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - MESSENGER WIRE | 603F-PR-2690 | LT Cable - Messenger Wire-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-05-14 07:00 | 2025-05-25 17:00 | 2025-04-04 07:00 | 2025-05-03 17:00 | 1 | 37 | Kilometer | 0 | 0
LT CABLE - MESSENGER WIRE | 603F-PR-2700 | LT Cable - Messenger Wire-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-05-23 07:00 | 2025-06-03 17:00 | 2025-04-06 07:00 | 2025-05-20 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - MESSENGER WIRE | 603F-PR-2710 | LT Cable - Messenger Wire-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-05-27 07:00 | 2025-06-07 17:00 | 2025-04-06 07:00 | 2025-05-23 17:00 | 1 | 37 | Kilometer | 0 | 0
LT CABLE - MESSENGER WIRE | 603F-PR-4860 | LT Cable - Messenger Wire-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-25 17:00 | 2025-04-10 07:00 | 2025-05-25 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - MESSENGER WIRE | 603F-PR-4870 | LT Cable - Messenger Wire-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-06-15 07:00 | 2025-06-26 17:00 | 2025-04-10 07:00 | 2025-05-31 17:00 | 1 | 37 | Kilometer | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2210 | LT Cable Routing Layout For Block-02 | Completed | Task Dependent | 2025-06-16 07:00 | 2025-06-16 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2200 | LT Cable Routing Layout For Block-01 | Completed | Task Dependent | 2025-06-16 07:00 | 2025-06-16 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2220 | LT Cable Routing Layout For Block-03 | Completed | Task Dependent | 2025-06-17 07:00 | 2025-06-17 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2230 | LT Cable Routing Layout For Block-04 | Completed | Task Dependent | 2025-06-17 07:00 | 2025-06-17 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2290 | LT Cable Routing Layout For Block-10 | Completed | Task Dependent | 2025-06-18 07:00 | 2025-06-18 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2260 | LT Cable Routing Layout For Block-07 | Completed | Task Dependent | 2025-06-18 07:00 | 2025-06-18 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2280 | LT Cable Routing Layout For Block-09 | Completed | Task Dependent | 2025-06-18 07:00 | 2025-06-18 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2270 | LT Cable Routing Layout For Block-08 | Completed | Task Dependent | 2025-06-18 07:00 | 2025-06-18 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2250 | LT Cable Routing Layout For Block-06 | Completed | Task Dependent | 2025-06-18 07:00 | 2025-06-18 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2240 | LT Cable Routing Layout For Block-05 | Completed | Task Dependent | 2025-06-18 07:00 | 2025-06-18 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2300 | LT Cable Routing Layout For Block-11 | Completed | Task Dependent | 2025-06-19 07:00 | 2025-06-19 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2310 | LT Cable Routing Layout For Block-12 | Completed | Task Dependent | 2025-06-19 07:00 | 2025-06-19 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2330 | LT Cable Routing Layout For Block-14 | Completed | Task Dependent | 2025-06-20 07:00 | 2025-06-20 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2320 | LT Cable Routing Layout For Block-13 | Completed | Task Dependent | 2025-06-20 07:00 | 2025-06-20 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2340 | LT Cable Routing Layout For Block-15 | Completed | Task Dependent | 2025-06-21 07:00 | 2025-06-21 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2350 | LT Cable Routing Layout For Block-16 | Completed | Task Dependent | 2025-06-21 07:00 | 2025-06-21 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2360 | LT Cable Routing Layout For Block-17 | Completed | Task Dependent | 2025-06-22 07:00 | 2025-06-22 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2370 | LT Cable Routing Layout For Block-18 | Completed | Task Dependent | 2025-06-22 07:00 | 2025-06-22 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2380 | LT Cable Routing Layout For Block-19 | Completed | Task Dependent | 2025-06-23 07:00 | 2025-06-23 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2390 | LT Cable Routing Layout For Block-20 | Completed | Task Dependent | 2025-06-23 07:00 | 2025-06-23 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2400 | LT Cable Routing Layout For Block-21 | Completed | Task Dependent | 2025-06-24 07:00 | 2025-06-24 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2410 | LT Cable Routing Layout For Block-22 | Completed | Task Dependent | 2025-06-24 07:00 | 2025-06-24 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2430 | LT Cable Routing Layout For Block-24 | Completed | Task Dependent | 2025-06-25 07:00 | 2025-06-25 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2420 | LT Cable Routing Layout For Block-23 | Completed | Task Dependent | 2025-06-25 07:00 | 2025-06-25 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2450 | LT Cable Routing Layout For Block-26 | Completed | Task Dependent | 2025-06-26 07:00 | 2025-06-26 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2440 | LT Cable Routing Layout For Block-25 | Completed | Task Dependent | 2025-06-26 07:00 | 2025-06-26 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE ROUTING LAYOUT | 603F-EN-2460 | LT Cable Routing Layout For Block-27 | Completed | Task Dependent | 2025-06-27 07:00 | 2025-06-27 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2500 | LT Cable Schedule For Block-01 | Completed | Task Dependent | 2025-06-17 07:00 | 2025-06-17 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2510 | LT Cable Schedule For Block-02 | Completed | Task Dependent | 2025-06-18 07:00 | 2025-06-18 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2520 | LT Cable Schedule For Block-03 | Completed | Task Dependent | 2025-06-20 07:00 | 2025-06-20 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2530 | LT Cable Schedule For Block-04 | Completed | Task Dependent | 2025-06-20 07:00 | 2025-06-20 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2540 | LT Cable Schedule For Block-05 | Completed | Task Dependent | 2025-06-22 07:00 | 2025-06-22 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2550 | LT Cable Schedule For Block-06 | Completed | Task Dependent | 2025-06-23 07:00 | 2025-06-23 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2560 | LT Cable Schedule For Block-07 | Completed | Task Dependent | 2025-06-24 07:00 | 2025-06-24 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2580 | LT Cable Schedule For Block-09 | Completed | Task Dependent | 2025-06-25 07:00 | 2025-06-25 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2570 | LT Cable Schedule For Block-08 | Completed | Task Dependent | 2025-06-25 07:00 | 2025-06-25 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2590 | LT Cable Schedule For Block-10 | Completed | Task Dependent | 2025-06-26 07:00 | 2025-06-26 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2600 | LT Cable Schedule For Block-11 | Completed | Task Dependent | 2025-06-28 07:00 | 2025-06-28 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2610 | LT Cable Schedule For Block-12 | Completed | Task Dependent | 2025-06-29 07:00 | 2025-06-29 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2620 | LT Cable Schedule For Block-13 | Completed | Task Dependent | 2025-07-01 07:00 | 2025-07-01 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2630 | LT Cable Schedule For Block-14 | Completed | Task Dependent | 2025-07-01 07:00 | 2025-07-01 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2640 | LT Cable Schedule For Block-15 | Completed | Task Dependent | 2025-07-03 07:00 | 2025-07-03 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2650 | LT Cable Schedule For Block-16 | Completed | Task Dependent | 2025-07-04 07:00 | 2025-07-04 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2660 | LT Cable Schedule For Block-17 | Completed | Task Dependent | 2025-07-06 07:00 | 2025-07-06 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2670 | LT Cable Schedule For Block-18 | Completed | Task Dependent | 2025-07-07 07:00 | 2025-07-07 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2680 | LT Cable Schedule For Block-19 | Completed | Task Dependent | 2025-07-08 07:00 | 2025-07-08 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2690 | LT Cable Schedule For Block-20 | Completed | Task Dependent | 2025-07-09 07:00 | 2025-07-09 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2700 | LT Cable Schedule For Block-21 | Completed | Task Dependent | 2025-07-11 07:00 | 2025-07-11 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2710 | LT Cable Schedule For Block-22 | Completed | Task Dependent | 2025-07-12 07:00 | 2025-07-12 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2730 | LT Cable Schedule For Block-24 | Completed | Task Dependent | 2025-07-14 07:00 | 2025-07-14 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2720 | LT Cable Schedule For Block-23 | Completed | Task Dependent | 2025-07-14 07:00 | 2025-07-14 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2740 | LT Cable Schedule For Block-25 | Completed | Task Dependent | 2025-07-16 07:00 | 2025-07-16 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2750 | LT Cable Schedule For Block-26 | Completed | Task Dependent | 2025-07-17 07:00 | 2025-07-17 17:00 | 2025-05-02 | 2025-05-02 | 1 | 0 |  | 0 | 0
LT CABLE SCHEDULE | 603F-EN-2760 | LT Cable Schedule For Block-27 | Completed | Task Dependent | 2025-07-19 07:00 | 2025-07-19 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
LT CABLE - SUPPORT STRUCTURE | 603F-PR-2430 | LT Cable - Support Structure-TBER | Completed | Task Dependent | 2025-02-22 07:00 | 2025-03-05 17:00 | 2025-02-22 07:00 | 2025-03-05 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - SUPPORT STRUCTURE | 603F-PR-2420 | LT Cable - Support Structure-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-22 07:00 | 2025-02-25 17:00 | 2025-02-22 07:00 | 2025-02-25 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - SUPPORT STRUCTURE | 603F-PR-2450 | LT Cable - Support Structure-Note For Approval | Completed | Task Dependent | 2025-03-06 07:00 | 2025-03-07 17:00 | 2025-03-06 07:00 | 2025-03-07 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - SUPPORT STRUCTURE | 603F-PR-2440 | LT Cable - Support Structure-Purchase Requistion | Completed | Task Dependent | 2025-03-06 07:00 | 2025-03-06 17:00 | 2025-03-06 07:00 | 2025-03-06 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - SUPPORT STRUCTURE | 603F-PR-2460 | LT Cable - Support Structure-LOI / PO Release | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-09 17:00 | 2025-03-08 07:00 | 2025-03-09 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - SUPPORT STRUCTURE | 603F-PR-2470 | LT Cable - Support Structure-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-09 07:00 | 2025-06-11 17:00 | 2025-04-09 07:00 | 2025-05-23 07:00 | 1 | 0 |  | 0 | 0
LT CABLE - SUPPORT STRUCTURE | 603F-PR-2480 | LT Cable - Support Structure-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-05-24 07:00 | 2025-06-04 17:00 | 2025-05-11 07:00 | 2025-05-22 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - SUPPORT STRUCTURE | 603F-PR-2490 | LT Cable - Support Structure-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-25 17:00 | 2025-05-14 07:00 | 2025-05-23 17:00 | 1 | 9 | Lot | 0 | 0
LT CABLE - SUPPORT STRUCTURE | 603F-PR-2500 | LT Cable - Support Structure-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-06-18 07:00 | 2025-06-29 17:00 | 2025-05-23 07:00 | 2025-05-28 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - SUPPORT STRUCTURE | 603F-PR-2510 | LT Cable - Support Structure-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-06-22 07:00 | 2025-07-03 17:00 | 2025-05-27 07:00 | 2025-06-03 17:00 | 1 | 9 | Lot | 0 | 0
LT CABLE - SUPPORT STRUCTURE | 603F-PR-4820 | LT Cable - Support Structure-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-06-30 07:00 | 2025-07-11 17:00 | 2025-05-30 07:00 | 2025-06-02 17:00 | 1 | 0 |  | 0 | 0
LT CABLE - SUPPORT STRUCTURE | 603F-PR-4830 | LT Cable - Support Structure-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-07-01 07:00 | 2025-07-12 17:00 | 2025-06-01 07:00 | 2025-06-12 17:00 | 1 | 9 | Lot | 0 | 0
LT PANEL | 603F-PR-1820 | LT Panel-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-20 07:00 | 2025-02-23 17:00 | 2025-02-20 07:00 | 2025-02-23 17:00 | 1 | 0 |  | 0 | 0
LT PANEL | 603F-PR-1830 | LT Panel-TBER | Completed | Task Dependent | 2025-02-20 07:00 | 2025-03-03 17:00 | 2025-02-20 07:00 | 2025-03-03 17:00 | 1 | 0 |  | 0 | 0
LT PANEL | 603F-PR-1850 | LT Panel-Note For Approval | Completed | Task Dependent | 2025-03-04 07:00 | 2025-03-05 17:00 | 2025-03-04 07:00 | 2025-03-05 17:00 | 1 | 0 |  | 0 | 0
LT PANEL | 603F-PR-1840 | LT Panel-Purchase Requistion | Completed | Task Dependent | 2025-03-04 07:00 | 2025-03-04 17:00 | 2025-03-04 07:00 | 2025-03-04 17:00 | 1 | 0 |  | 0 | 0
LT PANEL | 603F-PR-1860 | LT Panel-LOI / PO Release | Completed | Task Dependent | 2025-03-06 07:00 | 2025-03-07 17:00 | 2025-03-06 07:00 | 2025-03-07 17:00 | 1 | 0 |  | 0 | 0
LT PANEL | 603F-PR-1870 | LT Panel-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-11-15 07:00 | 2025-12-14 17:00 | 2025-11-09 07:00 | 2025-11-15 17:00 | 1 | 0 |  | 0 | 0
LT PANEL | 603F-PR-1880 | LT Panel-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-11-30 07:00 | 2025-12-09 17:00 | 2025-11-09 07:00 | 2025-11-12 07:00 | 1 | 0 |  | 0 | 0
LT PANEL | 603F-PR-1890 | LT Panel-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-12-03 07:00 | 2025-12-12 17:00 | 2025-11-13 07:00 | 2025-11-15 17:00 | 1 | 144 | Number | 0 | 0
LT PANEL | 603F-PR-1900 | LT Panel-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-12-10 07:00 | 2025-12-19 17:00 | 2025-11-09 07:00 | 2025-11-12 17:00 | 1 | 0 |  | 0 | 0
LT PANEL | 603F-PR-1910 | LT Panel-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-12-13 07:00 | 2025-12-22 17:00 | 2025-11-13 07:00 | 2025-11-15 17:00 | 1 | 144 | Number | 0 | 0
LT PANEL | 603F-PR-4700 | LT Panel-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-12-20 07:00 | 2025-12-29 17:00 | 2025-11-09 07:00 | 2025-11-12 17:00 | 1 | 0 |  | 0 | 0
LT PANEL | 603F-PR-4710 | LT Panel-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-12-22 07:00 | 2025-12-31 17:00 | 2025-11-13 07:00 | 2025-11-15 17:00 | 1 | 144 | Number | 0 | 0
MC4 CONNECTOR | 603F-PR-4040 | Mc4 Connector-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-26 07:00 | 2025-03-01 17:00 | 2025-02-26 07:00 | 2025-03-01 17:00 | 1 | 0 |  | 0 | 0
MC4 CONNECTOR | 603F-PR-4050 | Mc4 Connector-TBER | Completed | Task Dependent | 2025-02-26 07:00 | 2025-03-09 17:00 | 2025-02-26 07:00 | 2025-03-09 17:00 | 1 | 0 |  | 0 | 0
MC4 CONNECTOR | 603F-PR-4070 | Mc4 Connector-Note For Approval | Completed | Task Dependent | 2025-03-10 07:00 | 2025-03-11 17:00 | 2025-03-10 07:00 | 2025-03-11 17:00 | 1 | 0 |  | 0 | 0
MC4 CONNECTOR | 603F-PR-4060 | Mc4 Connector-Purchase Requistion | Completed | Task Dependent | 2025-03-10 07:00 | 2025-03-10 17:00 | 2025-03-10 07:00 | 2025-03-10 17:00 | 1 | 0 |  | 0 | 0
MC4 CONNECTOR | 603F-PR-4080 | Mc4 Connector-LOI / PO Release | Completed | Task Dependent | 2025-03-12 07:00 | 2025-03-13 17:00 | 2025-03-12 07:00 | 2025-03-13 17:00 | 1 | 0 |  | 0 | 0
MC4 CONNECTOR | 603F-PR-4090 | Mc4 Connector-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-13 07:00 | 2025-07-03 17:00 | 2025-05-05 07:00 | 2025-05-20 07:44 | 1 | 0 |  | 0 | 0
MC4 CONNECTOR | 603F-PR-4100 | Mc4 Connector-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-25 17:00 | 2025-05-11 07:00 | 2025-06-19 17:00 | 1 | 0 |  | 0 | 0
MC4 CONNECTOR | 603F-PR-4110 | Mc4 Connector-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-06-17 07:00 | 2025-06-28 17:00 | 2025-05-14 07:00 | 2025-06-30 17:00 | 1 | 419 | Number | 0 | 0
MC4 CONNECTOR | 603F-PR-4120 | Mc4 Connector-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-06-26 07:00 | 2025-07-07 17:00 | 2025-05-18 07:00 | 2025-06-19 17:00 | 1 | 0 |  | 0 | 0
MC4 CONNECTOR | 603F-PR-4130 | Mc4 Connector-Receipt For Site-Lot-02 | Completed | Task Dependent | 2025-06-29 07:00 | 2025-07-10 17:00 | 2025-05-21 07:00 | 2025-06-30 17:00 | 1 | 419 | Number | 0 | 0
MC4 CONNECTOR | 603F-PR-5150 | Mc4 Connector-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-09-01 07:44 | 2025-09-13 07:44 | 2025-06-01 07:00 | 2025-06-19 17:00 | 1 | 0 |  | 0 | 0
MC4 CONNECTOR | 603F-PR-5160 | Mc4 Connector-Receipt For Site-Lot-03 | Completed | Task Dependent | 2025-09-04 07:44 | 2025-09-16 07:44 | 2025-06-01 07:00 | 2025-06-30 17:00 | 1 | 419 | Number | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-2800 | Messenger Wire And Cable Hanger Arrangement Layout For Block-01 | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-08 17:00 | 2025-04-30 | 2025-04-30 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-2810 | Messenger Wire And Cable Hanger Arrangement Layout For Block-02 | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-08 17:00 | 2025-04-30 | 2025-04-30 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-2830 | Messenger Wire And Cable Hanger Arrangement Layout For Block-04 | Completed | Task Dependent | 2025-03-10 07:00 | 2025-03-10 17:00 | 2025-04-30 | 2025-04-30 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-2820 | Messenger Wire And Cable Hanger Arrangement Layout For Block-03 | Completed | Task Dependent | 2025-03-10 07:00 | 2025-03-10 17:00 | 2025-04-30 | 2025-04-30 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-2840 | Messenger Wire And Cable Hanger Arrangement Layout For Block-05 | Completed | Task Dependent | 2025-03-12 07:00 | 2025-03-12 17:00 | 2025-04-30 | 2025-04-30 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-2870 | Messenger Wire And Cable Hanger Arrangement Layout For Block-08 | Completed | Task Dependent | 2025-03-12 07:00 | 2025-03-12 17:00 | 2025-04-30 | 2025-04-30 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-2850 | Messenger Wire And Cable Hanger Arrangement Layout For Block-06 | Completed | Task Dependent | 2025-03-12 07:00 | 2025-03-12 17:00 | 2025-04-30 | 2025-04-30 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-2860 | Messenger Wire And Cable Hanger Arrangement Layout For Block-07 | Completed | Task Dependent | 2025-03-12 07:00 | 2025-03-12 17:00 | 2025-04-30 | 2025-04-30 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-2880 | Messenger Wire And Cable Hanger Arrangement Layout For Block-09 | Completed | Task Dependent | 2025-06-22 07:00 | 2025-06-22 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-2890 | Messenger Wire And Cable Hanger Arrangement Layout For Block-10 | Completed | Task Dependent | 2025-06-22 07:00 | 2025-06-22 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-2910 | Messenger Wire And Cable Hanger Arrangement Layout For Block-12 | Completed | Task Dependent | 2025-06-24 07:00 | 2025-06-24 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-2900 | Messenger Wire And Cable Hanger Arrangement Layout For Block-11 | Completed | Task Dependent | 2025-06-24 07:00 | 2025-06-24 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-2930 | Messenger Wire And Cable Hanger Arrangement Layout For Block-14 | Completed | Task Dependent | 2025-06-26 07:00 | 2025-06-26 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-2920 | Messenger Wire And Cable Hanger Arrangement Layout For Block-13 | Completed | Task Dependent | 2025-06-26 07:00 | 2025-06-26 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-2950 | Messenger Wire And Cable Hanger Arrangement Layout For Block-16 | Completed | Task Dependent | 2025-06-28 07:00 | 2025-06-28 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-2940 | Messenger Wire And Cable Hanger Arrangement Layout For Block-15 | Completed | Task Dependent | 2025-06-28 07:00 | 2025-06-28 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-2970 | Messenger Wire And Cable Hanger Arrangement Layout For Block-18 | Completed | Task Dependent | 2025-06-30 07:00 | 2025-06-30 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-2960 | Messenger Wire And Cable Hanger Arrangement Layout For Block-17 | Completed | Task Dependent | 2025-06-30 07:00 | 2025-06-30 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-2980 | Messenger Wire And Cable Hanger Arrangement Layout For Block-19 | Completed | Task Dependent | 2025-07-02 07:00 | 2025-07-02 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-2990 | Messenger Wire And Cable Hanger Arrangement Layout For Block-20 | Completed | Task Dependent | 2025-07-02 07:00 | 2025-07-02 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-3000 | Messenger Wire And Cable Hanger Arrangement Layout For Block-21 | Completed | Task Dependent | 2025-07-04 07:00 | 2025-07-04 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-3010 | Messenger Wire And Cable Hanger Arrangement Layout For Block-22 | Completed | Task Dependent | 2025-07-04 07:00 | 2025-07-04 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-3020 | Messenger Wire And Cable Hanger Arrangement Layout For Block-23 | Completed | Task Dependent | 2025-07-06 07:00 | 2025-07-06 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-3030 | Messenger Wire And Cable Hanger Arrangement Layout For Block-24 | Completed | Task Dependent | 2025-07-06 07:00 | 2025-07-06 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-3040 | Messenger Wire And Cable Hanger Arrangement Layout For Block-25 | Completed | Task Dependent | 2025-07-08 07:00 | 2025-07-08 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-3050 | Messenger Wire And Cable Hanger Arrangement Layout For Block-26 | Completed | Task Dependent | 2025-07-08 07:00 | 2025-07-08 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
MESSENGER WIRE AND CABLE HANGER ARRANGEMENT LAYOUT | 603F-EN-3060 | Messenger Wire And Cable Hanger Arrangement Layout For Block-27 | Completed | Task Dependent | 2025-07-10 07:00 | 2025-07-10 17:00 | 2025-05-05 | 2025-05-05 | 1 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1030 | MMS Piling Stubs Delivery Start | Completed | Start Milestone | 2025-04-03 07:00 | 2025-04-03 07:00 | 2025-04-03 07:00 | 2025-04-03 07:00 | 1 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1020 | Project Technology Finalization | Completed | Finish Milestone | 2025-05-24 07:00 | 2025-05-24 07:00 | 2025-02-18 07:00 | 2025-02-18 07:00 | 1 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1070 | Construction (MMS Piling) Start | Completed | Start Milestone | 2025-06-21 07:00 | 2025-06-21 07:00 | 2025-04-18 07:00 | 2025-04-18 07:00 | 1 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1010 | PSS-06 Charging (Interface from PSS-06 project) | Completed | Task Dependent | 2025-06-21 07:00 | 2025-08-07 17:00 | 2025-02-15 07:00 | 2025-02-15 17:00 | 1 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1040 | MMS Superstructure Delivery at site Start | Completed | Start Milestone | 2025-06-21 07:00 | 2025-06-21 07:00 | 2025-04-17 07:00 | 2025-04-17 07:00 | 1 | 0 |  | 0 | 0
MILESTONES | 51R1-MS-1000 | Project Start | Completed | Start Milestone | 2025-08-02 07:00 | 2025-08-02 07:00 | 2025-02-15 07:00 | 2025-02-15 07:00 | 1 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1050 | Module Dispatch from China Start | Completed | Start Milestone | 2026-03-07 07:00 | 2026-03-07 07:00 | 2025-10-09 07:00 | 2025-10-09 07:00 | 1 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1060 | Module Installation Start | Completed | Start Milestone | 2026-03-07 07:00 | 2026-03-07 07:00 | 2025-12-30 07:00 | 2025-12-30 07:00 | 1 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1230 | P1-50MW (Block No.1,11,12,13) | Completed | Finish Milestone | 2026-03-16 17:00 | 2026-03-16 17:00 | 2026-02-28 17:00 | 2026-02-28 17:00 | 1 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1240 | P2-50MW (Block No.15,17,22,27) | Completed | Finish Milestone | 2026-03-20 17:00 | 2026-03-20 17:00 | 2026-03-09 17:00 | 2026-03-09 17:00 | 1 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1300 | P2-50MW COD (Block No.15,17,22,27) | Completed | Finish Milestone | 2026-03-21 16:00 | 2026-03-21 16:00 | 2026-03-13 16:00 | 2026-03-13 16:00 | 1 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1290 | P1-50MW COD (Block No.1,11,12,13) | Completed | Finish Milestone | 2026-03-21 16:00 | 2026-03-21 16:00 | 2026-03-13 16:00 | 2026-03-13 16:00 | 1 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1250 | P3-58MW (Block No.2,5,6,25,26) | Completed | Finish Milestone | 2026-03-27 17:00 | 2026-03-27 17:00 | 2026-03-27 17:00 | 2026-03-27 17:00 | 1 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1170 | First Time Charging - Phase-III (150 MW) | Completed | Finish Milestone | 2026-04-11 07:00 | 2026-04-11 07:00 | 2026-04-17 07:00 | 2026-04-17 07:00 | 1 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1190 | Trial Run Finish - Phase-III (150 MW) | Completed | Finish Milestone | 2026-04-11 07:00 | 2026-04-11 07:00 | 2026-04-18 07:00 | 2026-04-18 07:00 | 1 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1260 | P4-50MW (Block No.9,10,19,23) | Completed | Finish Milestone | 2026-04-15 12:00 | 2026-04-15 12:00 | 2026-04-10 12:00 | 2026-04-10 12:00 | 1 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1130 | First Time Charging - Phase-II (100 MW) | Completed | Finish Milestone | 2026-04-26 14:00 | 2026-04-26 14:00 | 2026-03-08 14:00 | 2026-03-08 14:00 | 1 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1150 | Trial Run Finish - Phase-II (100 MW) | Completed | Finish Milestone | 2026-05-03 14:00 | 2026-05-03 14:00 | 2026-03-09 14:00 | 2026-03-09 14:00 | 1 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1270 | P5-75MW (Block No.7,21,14,16,18,24) | Completed | Finish Milestone | 2026-05-16 15:00 | 2026-05-16 15:00 | 2026-04-17 15:00 | 2026-04-17 15:00 | 1 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1120 | Module Delivery at Site Finish | Not Started | Finish Milestone | 2026-05-24 07:00 | 2026-05-24 07:00 |  |  | 0 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1100 | Trial Run Finish - Phase-I (83 MW) | Not Started | Finish Milestone | 2026-05-24 07:00 | 2026-05-24 07:00 |  |  | 0 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1080 | First Time Charging - Phase-I (83 MW) | Not Started | Finish Milestone | 2026-05-24 07:00 | 2026-05-24 07:00 |  |  | 0 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1280 | P6-50MW (Block No.3,4,8,20) | Completed | Finish Milestone | 2026-06-01 11:00 | 2026-06-01 11:00 | 2026-04-17 11:00 | 2026-04-17 11:00 | 1 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1140 | Robot Commissioing Finish - Phase-II (100 MW) | Not Started | Finish Milestone | 2026-06-16 14:00 | 2026-06-16 14:00 |  |  | 0 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1320 | P4-50MW COD (Block No.9,10,19,23) | Not Started | Finish Milestone | 2026-06-17 14:00 | 2026-06-17 14:00 |  |  | 0 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1160 | COD - Phase-II (100 MW) | Not Started | Finish Milestone | 2026-06-17 14:00 | 2026-06-17 14:00 |  |  | 0 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1310 | P3-58MW COD (Block No.2,5,6,25,26) | Not Started | Finish Milestone | 2026-06-17 14:00 | 2026-06-17 14:00 |  |  | 0 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1090 | Robot Commissioing Finish - Phase-I (83 MW) | Not Started | Finish Milestone | 2026-06-29 12:00 | 2026-06-29 12:00 |  |  | 0 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1210 | HOTO | Not Started | Finish Milestone | 2026-06-30 10:00 | 2026-06-30 10:00 |  |  | 0 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1330 | P5-75MW COD (Block No.7,21,14,16,18,24) | Not Started | Finish Milestone | 2026-06-30 12:00 | 2026-06-30 12:00 |  |  | 0 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1110 | COD - Phase-I (83 MW) | Not Started | Finish Milestone | 2026-06-30 12:00 | 2026-06-30 12:00 |  |  | 0 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1180 | Robot Commissioing Finish - Phase-III (150 MW) | Not Started | Finish Milestone | 2026-07-09 12:00 | 2026-07-09 12:00 |  |  | 0 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1200 | COD - Phase-III (150 MW) | Not Started | Finish Milestone | 2026-07-10 12:00 | 2026-07-10 12:00 |  |  | 0 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1340 | P6-50MW COD (Block No.3,4,8,20) | Not Started | Finish Milestone | 2026-07-10 12:00 | 2026-07-10 12:00 |  |  | 0 | 0 |  | 0 | 0
MILESTONES | 603F-MS-1220 | Contract Closure | Not Started | Finish Milestone | 2026-08-09 10:00 | 2026-08-09 10:00 |  |  | 0 | 0 |  | 0 | 0
MMS - FT | 603F-PR-1430 | MMS - FT-TBER | Completed | Task Dependent | 2025-02-19 07:00 | 2025-03-02 17:00 | 2025-02-19 07:00 | 2025-03-02 17:00 | 1 | 0 |  | 0 | 0
MMS - FT | 603F-PR-1420 | MMS - FT-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-19 07:00 | 2025-02-22 17:00 | 2025-02-19 07:00 | 2025-02-22 17:00 | 1 | 0 |  | 0 | 0
MMS - FT | 603F-PR-1450 | MMS - FT-Note For Approval | Completed | Task Dependent | 2025-03-03 07:00 | 2025-03-04 17:00 | 2025-03-03 07:00 | 2025-03-04 17:00 | 1 | 0 |  | 0 | 0
MMS - FT | 603F-PR-1440 | MMS - FT-Purchase Requistion | Completed | Task Dependent | 2025-03-03 07:00 | 2025-03-03 17:00 | 2025-03-03 07:00 | 2025-03-03 17:00 | 1 | 0 |  | 0 | 0
MMS - FT | 603F-PR-1460 | Mms - FT-LOI / PO Release | Completed | Task Dependent | 2025-03-05 07:00 | 2025-03-06 17:00 | 2025-03-05 07:00 | 2025-03-06 17:00 | 1 | 0 |  | 0 | 0
MMS - FT | 603F-PR-1470 | MMS - FT-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-01 07:00 | 2025-06-04 17:00 | 2025-04-10 07:00 | 2025-12-22 17:00 | 1 | 0 |  | 0 | 0
MMS - FT | 603F-PR-1480 | MMS - FT-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-04-30 07:00 | 2025-05-11 17:00 | 2025-04-15 07:00 | 2025-07-03 17:00 | 1 | 0 |  | 0 | 0
MMS - FT | 603F-PR-1490 | MMS - FT-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-06-17 07:00 | 2025-06-26 17:00 | 2025-04-17 07:00 | 2025-07-16 17:00 | 1 | 13149 | Tables | 13149 | 0
MMS - FT | 603F-PR-1500 | MMS - FT-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-12-07 07:00 | 2025-12-18 17:00 | 2025-07-16 07:00 | 2025-07-31 17:00 | 1 | 0 |  | 0 | 0
MMS - FT | 603F-PR-1510 | MMS - FT-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-12-12 07:00 | 2025-12-21 17:00 | 2025-07-30 07:00 | 2025-08-07 17:00 | 1 | 13149 | Tables | 13149 | 0
MMS - FT | 603F-PR-4620 | MMS - FT-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2026-01-15 07:00 | 2026-01-20 17:00 | 2025-12-28 07:00 | 2025-12-28 17:00 | 1 | 0 |  | 0 | 0
MMS - FT | 603F-PR-4630 | MMS - FT-Receipt At Site-Lot-03 | Completed | Task Dependent | 2026-01-18 07:00 | 2026-01-22 17:00 | 2026-01-01 07:00 | 2026-01-03 17:00 | 1 | 13149 | Tables | 13149 | 0
MODULE (IMPORTED FROM CHINA) | 603F-PR-4150 | Module-TBER | Completed | Task Dependent | 2025-02-23 07:00 | 2025-03-06 17:00 | 2025-02-23 07:00 | 2025-03-06 17:00 | 1 | 0 |  | 0 | 0
MODULE (IMPORTED FROM CHINA) | 603F-PR-4140 | Module-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-23 07:00 | 2025-02-26 17:00 | 2025-02-23 07:00 | 2025-02-26 17:00 | 1 | 0 |  | 0 | 0
MODULE (IMPORTED FROM CHINA) | 603F-PR-4160 | Module-Purchase Requistion | Completed | Task Dependent | 2025-03-07 07:00 | 2025-03-07 17:00 | 2025-03-07 07:00 | 2025-03-07 17:00 | 1 | 0 |  | 0 | 0
MODULE (IMPORTED FROM CHINA) | 603F-PR-4170 | Module-Note For Approval | Completed | Task Dependent | 2025-03-07 07:00 | 2025-03-08 17:00 | 2025-03-07 07:00 | 2025-03-08 17:00 | 1 | 0 |  | 0 | 0
MODULE (IMPORTED FROM CHINA) | 603F-PR-4180 | Module-LOI / PO Release | Completed | Task Dependent | 2025-03-09 07:00 | 2025-03-10 17:00 | 2025-03-09 07:00 | 2025-03-10 17:00 | 1 | 0 |  | 0 | 0
MODULE (IMPORTED FROM CHINA) | 603F-PR-4190 | Module-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-10-25 07:00 | 2025-12-11 17:00 | 2025-10-12 07:00 | 2025-11-25 17:00 | 1 | 0 |  | 0 | 0
MODULE (IMPORTED FROM CHINA) | 603F-PR-4200 | Module-Dispatch From China-Lot-01 | Completed | Task Dependent | 2025-10-25 07:00 | 2025-10-26 17:00 | 2025-10-25 07:00 | 2026-01-01 08:02 | 1 | 0 |  | 0 | 0
MODULE (IMPORTED FROM CHINA) | 603F-PR-4210 | Module-Transportation & Custom Clearance-Lot-01 | Completed | Task Dependent | 2025-12-06 08:02 | 2025-12-26 08:02 | 2025-12-06 08:02 | 2026-02-14 17:00 | 1 | 0 |  | 0 | 0
MODULE (IMPORTED FROM CHINA) | 603F-PR-4230 | Module-Dispatch From China-Lot-02 | Completed | Task Dependent | 2025-12-16 07:00 | 2025-12-17 17:00 | 2025-10-25 07:00 | 2026-01-19 17:00 | 1 | 0 |  | 0 | 0
MODULE (IMPORTED FROM CHINA) | 603F-PR-4240 | Module-Transportation & Custom Clearance-Lot-02 | Completed | Task Dependent | 2025-12-24 07:00 | 2026-01-12 17:00 | 2025-10-25 07:00 | 2026-03-06 17:00 | 1 | 0 |  | 0 | 0
MODULE (IMPORTED FROM CHINA) | 603F-PR-4220 | Module-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-12-28 08:02 | 2026-01-01 08:02 | 2025-12-28 08:02 | 2026-02-16 17:00 | 1 | 220 | MegaWatt DC | 220 | 0
MODULE (IMPORTED FROM CHINA) | 603F-PR-4252 | Module-Dispatch From China-Lot-03 | Completed | Task Dependent | 2026-01-25 08:00 | 2026-02-13 16:00 | 2026-01-03 08:00 | 2026-01-26 16:00 | 1 | 0 |  | 0 | 0
MODULE (IMPORTED FROM CHINA) | 603F-PR-4250 | Module-Receipt Site At-Lot-02 | Completed | Task Dependent | 2026-02-02 07:00 | 2026-02-05 17:00 | 2026-01-02 07:00 | 2026-03-10 17:00 | 1 | 141 | MegaWatt DC | 141 | 0
MODULE (IMPORTED FROM CHINA) | 603F-PR-4254 | Module-Transportation & Custom Clearance-Lot-03 | Completed | Task Dependent | 2026-02-08 16:00 | 2026-02-15 16:00 | 2026-01-20 16:00 | 2026-03-14 17:00 | 1 | 0 |  | 0 | 0
MODULE (IMPORTED FROM CHINA) | 603F-PR-4256 | Module-Receipt Site At-Lot-03 | Completed | Task Dependent | 2026-03-17 07:00 | 2026-03-21 16:00 | 2026-03-12 07:00 | 2026-03-24 16:00 | 1 | 80 | MegaWatt DC | 80 | 0
OTHERS IF ANY | PR-CA-27-011 | WRLDC Registration | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-24 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
OTHERS IF ANY | PR-CA-27-010 | Implementation Service Agreement (ISA, applicable for Solar parks) | Completed | Task Dependent | 2025-01-20 08:00 | 2025-02-18 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
OTHERS IF ANY | PR-CA-27-017 | GST No. Certificate | Completed | Task Dependent | 2025-03-06 08:00 | 2025-03-25 09:00 | 2025-02-15 08:00 | 2025-02-15 16:00 | 1 | 0 |  | 0 | 0
OTHERS IF ANY | PR-CA-27-018 | Contract Labour Registration (CLRA) Liscense | Completed | Task Dependent | 2025-03-23 08:00 | 2025-03-30 15:00 | 2025-02-15 08:00 | 2025-02-15 16:00 | 1 | 0 |  | 0 | 0
OTHERS IF ANY | PR-CA-27-019 | Registration Under Buildings And Other Construction Works (BOCW) | Completed | Task Dependent | 2025-03-23 08:00 | 2025-03-30 15:00 | 2025-02-15 08:00 | 2025-02-15 16:00 | 1 | 0 |  | 0 | 0
OTHERS IF ANY | PR-CA-27-015 | EAR Policy | Completed | Task Dependent | 2025-05-24 08:00 | 2025-05-31 15:00 | 2025-03-23 08:00 | 2025-03-29 16:00 | 1 | 0 |  | 0 | 0
OTHERS IF ANY | PR-CA-27-020 | SPV Name Finalization | Completed | Task Dependent | 2025-06-06 08:00 | 2025-06-12 14:00 | 2025-02-28 08:00 | 2025-03-05 16:00 | 1 | 0 |  | 0 | 0
OTHERS IF ANY | PR-CA-27-016 | Marine Policy | Completed | Task Dependent | 2026-04-04 08:00 | 2026-04-08 16:00 | 2025-03-23 08:00 | 2025-03-29 16:00 | 1 | 0 |  | 0 | 0
OTHERS IF ANY | PR-CA-27-013 | PTCC | Completed | Task Dependent | 2026-04-11 08:00 | 2026-07-09 16:00 | 2025-11-29 08:00 | 2026-02-09 08:00 | 1 | 0 |  | 0 | 0
OTHERS IF ANY | PR-CA-27-012 | First Time Charging Approval of Line & Bay from RLDC | Completed | Task Dependent | 2026-05-18 08:00 | 2026-05-19 16:00 | 2026-02-11 08:00 | 2026-04-14 08:00 | 1 | 0 |  | 0 | 0
PHASE-1 | 603F-CL-1020 | Block-03 - Contract Closure | Not Started | Task Dependent | 2026-06-16 14:00 | 2026-07-26 14:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-1 | 603F-CL-1060 | Block-07 - Contract Closure | Not Started | Task Dependent | 2026-06-16 14:00 | 2026-07-26 14:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-1 | 603F-CL-1050 | Block-06 - Contract Closure | Not Started | Task Dependent | 2026-06-16 14:00 | 2026-07-26 14:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-1 | 603F-CL-1010 | Block-02 - Contract Closure | Not Started | Task Dependent | 2026-06-16 14:00 | 2026-07-26 14:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-1 | 603F-CL-1040 | Block-05 - Contract Closure | Not Started | Task Dependent | 2026-06-16 14:00 | 2026-07-26 14:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-1 | 603F-CL-1030 | Block-04 - Contract Closure | Not Started | Task Dependent | 2026-06-16 14:00 | 2026-07-26 14:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-1 | 603F-CL-1000 | Block-01 -Contract Closure | Not Started | Task Dependent | 2026-06-16 14:00 | 2026-07-26 14:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-2 | 603F-CL-1150 | Block-13 - Contract Closure | Not Started | Task Dependent | 2026-06-30 10:00 | 2026-08-09 10:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-2 | 603F-CL-1160 | Block-14 - Contract Closure | Not Started | Task Dependent | 2026-06-30 10:00 | 2026-08-09 10:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-2 | 603F-CL-1130 | Block-11 - Contract Closure | Not Started | Task Dependent | 2026-06-30 10:00 | 2026-08-09 10:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-2 | 603F-CL-1170 | Block-15 - Contract Closure | Not Started | Task Dependent | 2026-06-30 10:00 | 2026-08-09 10:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-2 | 603F-CL-1110 | Block-09 - Contract Closure | Not Started | Task Dependent | 2026-06-30 10:00 | 2026-08-09 10:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-2 | 603F-CL-1120 | Block-10 - Contract Closure | Not Started | Task Dependent | 2026-06-30 10:00 | 2026-08-09 10:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-2 | 603F-CL-1100 | Block-08 - Contract Closure | Not Started | Task Dependent | 2026-06-30 10:00 | 2026-08-09 10:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-2 | 603F-CL-1140 | Block-12 - Contract Closure | Not Started | Task Dependent | 2026-06-30 10:00 | 2026-08-09 10:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-3 | 603F-CL-1270 | Block-23 - Contract Closure | Not Started | Task Dependent | 2026-06-30 10:00 | 2026-08-09 10:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-3 | 603F-CL-1260 | Block-22 - Contract Closure | Not Started | Task Dependent | 2026-06-30 10:00 | 2026-08-09 10:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-3 | 603F-CL-1240 | Block-20 - Contract Closure | Not Started | Task Dependent | 2026-06-30 10:00 | 2026-08-09 10:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-3 | 603F-CL-1300 | Block-26 - Contract Closure | Not Started | Task Dependent | 2026-06-30 10:00 | 2026-08-09 10:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-3 | 603F-CL-1220 | Block-18 - Contract Closure | Not Started | Task Dependent | 2026-06-30 10:00 | 2026-08-09 10:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-3 | 603F-CL-1290 | Block-25 - Contract Closure | Not Started | Task Dependent | 2026-06-30 10:00 | 2026-08-09 10:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-3 | 603F-CL-1310 | Block-27 - Contract Closure | Not Started | Task Dependent | 2026-06-30 10:00 | 2026-08-09 10:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-3 | 603F-CL-1280 | Block-24 - Contract Closure | Not Started | Task Dependent | 2026-06-30 10:00 | 2026-08-09 10:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-3 | 603F-CL-1250 | Block-21 - Contract Closure | Not Started | Task Dependent | 2026-06-30 10:00 | 2026-08-09 10:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-3 | 603F-CL-1230 | Block-19 - Contract Closure | Not Started | Task Dependent | 2026-06-30 10:00 | 2026-08-09 10:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-3 | 603F-CL-1210 | Block-17 - Contract Closure | Not Started | Task Dependent | 2026-06-30 10:00 | 2026-08-09 10:00 |  |  | 0 | 0 |  | 0 | 0
PHASE-3 | 603F-CL-1200 | Block-16 - Contract Closure | Not Started | Task Dependent | 2026-06-30 10:00 | 2026-08-09 10:00 |  |  | 0 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1600 | Pile Foundation Layout For Block-01 | Completed | Task Dependent | 2025-02-28 07:00 | 2025-02-28 17:00 | 2025-04-08 | 2025-04-08 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1610 | Pile Foundation Layout For Block-02 | Completed | Task Dependent | 2025-02-28 07:00 | 2025-02-28 17:00 | 2025-04-08 | 2025-04-08 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1620 | Pile Foundation Layout For Block-03 | Completed | Task Dependent | 2025-03-01 07:00 | 2025-03-01 17:00 | 2025-04-08 | 2025-04-08 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1630 | Pile Foundation Layout For Block-04 | Completed | Task Dependent | 2025-03-01 07:00 | 2025-03-01 17:00 | 2025-04-08 | 2025-04-08 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1640 | Pile Foundation Layout For Block-05 | Completed | Task Dependent | 2025-03-02 07:00 | 2025-03-02 17:00 | 2025-04-08 | 2025-04-08 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1670 | Pile Foundation Layout For Block-08 | Completed | Task Dependent | 2025-03-02 07:00 | 2025-03-02 17:00 | 2025-04-08 | 2025-04-08 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1660 | Pile Foundation Layout For Block-07 | Completed | Task Dependent | 2025-03-02 07:00 | 2025-03-02 17:00 | 2025-04-08 | 2025-04-08 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1690 | Pile Foundation Layout For Block-10 | Completed | Task Dependent | 2025-03-03 07:00 | 2025-03-03 17:00 | 2025-04-08 | 2025-04-08 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1680 | Pile Foundation Layout For Block-09 | Completed | Task Dependent | 2025-03-03 07:00 | 2025-03-03 17:00 | 2025-04-08 | 2025-04-08 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1710 | Pile Foundation Layout For Block-12 | Completed | Task Dependent | 2025-03-04 07:00 | 2025-03-04 17:00 | 2025-04-08 | 2025-04-08 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1700 | Pile Foundation Layout For Block-11 | Completed | Task Dependent | 2025-03-04 07:00 | 2025-03-04 17:00 | 2025-04-08 | 2025-04-08 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1720 | Pile Foundation Layout For Block-13 | Completed | Task Dependent | 2025-03-05 07:00 | 2025-03-05 17:00 | 2025-04-08 | 2025-04-08 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1730 | Pile Foundation Layout For Block-14 | Completed | Task Dependent | 2025-03-05 07:00 | 2025-03-05 17:00 | 2025-04-08 | 2025-04-08 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1750 | Pile Foundation Layout For Block-16 | Completed | Task Dependent | 2025-03-06 07:00 | 2025-03-06 17:00 | 2025-04-08 | 2025-04-08 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1740 | Pile Foundation Layout For Block-15 | Completed | Task Dependent | 2025-03-06 07:00 | 2025-03-06 17:00 | 2025-04-08 | 2025-04-08 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1770 | Pile Foundation Layout For Block-18 | Completed | Task Dependent | 2025-03-07 07:00 | 2025-03-07 17:00 | 2025-04-10 | 2025-04-10 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1760 | Pile Foundation Layout For Block-17 | Completed | Task Dependent | 2025-03-07 07:00 | 2025-03-07 17:00 | 2025-04-08 | 2025-04-08 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1780 | Pile Foundation Layout For Block-19 | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-08 17:00 | 2025-04-10 | 2025-04-10 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1790 | Pile Foundation Layout For Block-20 | Completed | Task Dependent | 2025-03-08 07:00 | 2025-03-08 17:00 | 2025-04-10 | 2025-04-10 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1800 | Pile Foundation Layout For Block-21 | Completed | Task Dependent | 2025-03-09 07:00 | 2025-03-09 17:00 | 2025-04-10 | 2025-04-10 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1810 | Pile Foundation Layout For Block-22 | Completed | Task Dependent | 2025-03-09 07:00 | 2025-03-09 17:00 | 2025-04-10 | 2025-04-10 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1820 | Pile Foundation Layout For Block-23 | Completed | Task Dependent | 2025-03-10 07:00 | 2025-03-10 17:00 | 2025-04-14 | 2025-04-14 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1830 | Pile Foundation Layout For Block-24 | Completed | Task Dependent | 2025-03-10 07:00 | 2025-03-10 17:00 | 2025-04-14 | 2025-04-14 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1840 | Pile Foundation Layout For Block-25 | Completed | Task Dependent | 2025-03-11 07:00 | 2025-03-11 17:00 | 2025-04-14 | 2025-04-14 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1850 | Pile Foundation Layout For Block-26 | Completed | Task Dependent | 2025-03-11 07:00 | 2025-03-11 17:00 | 2025-04-14 | 2025-04-14 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1860 | Pile Foundation Layout For Block-27 | Completed | Task Dependent | 2025-03-12 07:00 | 2025-03-12 17:00 | 2025-04-14 | 2025-04-14 | 1 | 0 |  | 0 | 0
PILE FOUNDATION LAYOUT | 603F-EN-1650 | Pile Foundation Layout For Block-06 | Completed | Task Dependent | 2025-03-16 07:00 | 2025-03-16 17:00 | 2025-04-08 | 2025-04-08 | 1 | 0 |  | 0 | 0
PILING STUB - INVERTER | 603F-PR-1120 | Piling Stub Inverter-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-03-06 07:00 | 2025-03-09 17:00 | 2025-03-06 07:00 | 2025-03-09 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - INVERTER | 603F-PR-1130 | Piling Stub Inverter-TBER | Completed | Task Dependent | 2025-03-10 07:00 | 2025-03-21 17:00 | 2025-03-10 07:00 | 2025-03-21 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - INVERTER | 603F-PR-1140 | Piling Stub Inverter-Purchase Requistion | Completed | Task Dependent | 2025-03-22 07:00 | 2025-03-22 17:00 | 2025-03-22 07:00 | 2025-03-22 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - INVERTER | 603F-PR-1150 | Piling Stub Inverter-Note For Approval | Completed | Task Dependent | 2025-03-22 07:00 | 2025-03-23 17:00 | 2025-03-22 07:00 | 2025-03-23 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - INVERTER | 603F-PR-1160 | Piling Stub Inverter-LOI / PO Release | Completed | Task Dependent | 2025-03-24 07:00 | 2025-03-25 17:00 | 2025-03-24 07:00 | 2025-03-25 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - INVERTER | 603F-PR-1170 | Piling Stub Inverter-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-25 07:00 | 2025-05-26 17:00 | 2025-04-04 07:00 | 2025-05-04 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - INVERTER | 603F-PR-1180 | Piling Stub Inverter-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-05-10 07:00 | 2025-05-17 17:00 | 2025-05-05 07:00 | 2025-05-12 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - INVERTER | 603F-PR-1190 | Piling Stub Inverter-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-05-13 07:00 | 2025-05-20 17:00 | 2025-05-06 07:00 | 2025-05-10 07:34 | 1 | 837 | Number | 0 | 0
PILING STUB - INVERTER | 603F-PR-1200 | Piling Stub Inverter-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-21 17:00 | 2025-05-08 07:00 | 2025-05-12 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - INVERTER | 603F-PR-1210 | Piling Stub Inverter-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-06-17 07:00 | 2025-06-24 17:00 | 2025-05-10 07:00 | 2025-05-14 17:00 | 1 | 837 | Number | 0 | 0
PILING STUB - INVERTER | 603F-PR-4560 | Piling Stub Inverter-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-06-22 07:00 | 2025-06-29 17:00 | 2025-05-13 07:00 | 2025-05-17 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - INVERTER | 603F-PR-4570 | Piling Stub Inverter-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-06-25 07:00 | 2025-07-02 17:00 | 2025-05-14 07:00 | 2025-07-18 17:00 | 1 | 837 | Number | 0 | 0
PILING STUB - LT CABLE SUPPORT STRUCTURE | 603F-PR-1220 | Piling Stub-LT Cable Support Structure-Boq & Tech Specs Release | Completed | Task Dependent | 2025-02-19 07:00 | 2025-02-22 17:00 | 2025-02-19 07:00 | 2025-02-22 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - LT CABLE SUPPORT STRUCTURE | 603F-PR-1230 | Piling Stub-LT Cable Support Structure-TBER | Completed | Task Dependent | 2025-02-23 07:00 | 2025-03-06 17:00 | 2025-02-23 07:00 | 2025-03-06 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - LT CABLE SUPPORT STRUCTURE | 603F-PR-1240 | Piling Stub-LT Cable Support Structure-Purchase Requistion | Completed | Task Dependent | 2025-03-07 07:00 | 2025-03-07 17:00 | 2025-03-07 07:00 | 2025-03-07 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - LT CABLE SUPPORT STRUCTURE | 603F-PR-1250 | Piling Stub-LT Cable Support Structure-Note For Approval | Completed | Task Dependent | 2025-03-07 07:00 | 2025-03-08 17:00 | 2025-03-07 07:00 | 2025-03-08 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - LT CABLE SUPPORT STRUCTURE | 603F-PR-1260 | Piling Stub-Lt Cable Support Structure-LOI / PO Release | Completed | Task Dependent | 2025-03-09 07:00 | 2025-03-10 17:00 | 2025-03-09 07:00 | 2025-03-10 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - LT CABLE SUPPORT STRUCTURE | 603F-PR-1270 | Piling Stub-LT Cable Support Structure-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-10 07:00 | 2025-05-11 17:00 | 2025-04-16 07:00 | 2025-05-17 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - LT CABLE SUPPORT STRUCTURE | 603F-PR-1280 | Piling Stub-LT Cable Support Structure-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-04-25 07:00 | 2025-05-02 17:00 | 2025-05-18 07:00 | 2025-05-21 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - LT CABLE SUPPORT STRUCTURE | 603F-PR-1290 | Piling Stub-LT Cable Support Structure-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-04-28 07:00 | 2025-05-05 17:00 | 2025-05-11 07:00 | 2025-05-24 17:00 | 1 | 5940 | Number | 0 | 0
PILING STUB - LT CABLE SUPPORT STRUCTURE | 603F-PR-1300 | Piling Stub-LT Cable Support Structure-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-07-12 07:00 | 2025-07-19 17:00 | 2025-05-25 07:00 | 2025-06-01 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - LT CABLE SUPPORT STRUCTURE | 603F-PR-1310 | Piling Stub-LT Cable Support Structure-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-07-15 07:00 | 2025-07-22 17:00 | 2025-05-30 07:00 | 2025-06-06 17:00 | 1 | 5940 | Number | 0 | 0
PILING STUB - LT CABLE SUPPORT STRUCTURE | 603F-PR-4580 | Piling Stub-LT Cable Support Structure-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-07-21 07:00 | 2025-07-24 17:00 | 2025-06-07 07:00 | 2025-06-10 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - LT CABLE SUPPORT STRUCTURE | 603F-PR-4590 | Piling Stub-LT Cable Support Structure-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-07-22 07:00 | 2025-07-25 17:00 | 2025-06-12 07:00 | 2025-06-14 17:00 | 1 | 5940 | Number | 0 | 0
PILING STUB - MMS | 603F-PR-1000 | Piling Stub MMS-Boq & Tech Specs Release | Completed | Task Dependent | 2025-02-19 07:00 | 2025-02-22 17:00 | 2025-02-19 07:00 | 2025-02-22 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - MMS | 603F-PR-1010 | Piling Stub MMS-TBER | Completed | Task Dependent | 2025-02-23 07:00 | 2025-03-06 17:00 | 2025-02-23 07:00 | 2025-03-06 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - MMS | 603F-PR-1020 | Piling Stub MMS-Purchase Requistion | Completed | Task Dependent | 2025-03-07 07:00 | 2025-03-07 17:00 | 2025-03-07 07:00 | 2025-03-07 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - MMS | 603F-PR-1030 | Piling Stub MMS-Note For Approval | Completed | Task Dependent | 2025-03-07 07:00 | 2025-03-08 17:00 | 2025-03-07 07:00 | 2025-03-08 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - MMS | 603F-PR-1040 | Piling Stub MMS-LOI / PO Release | Completed | Task Dependent | 2025-03-09 07:00 | 2025-03-10 17:00 | 2025-03-09 07:00 | 2025-03-10 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - MMS | 603F-PR-1050 | Piling Stub MMS-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-10 07:00 | 2025-05-11 17:00 | 2025-03-24 07:00 | 2025-07-11 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - MMS | 603F-PR-1060 | Piling Stub MMS-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-04-25 07:00 | 2025-05-02 17:00 | 2025-03-31 07:00 | 2025-05-28 07:03 | 1 | 0 |  | 0 | 0
PILING STUB - MMS | 603F-PR-1070 | Piling Stub MMS-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-06-17 07:03 | 2025-06-25 07:03 | 2025-04-03 07:03 | 2025-05-31 07:03 | 1 | 52596 | Number | 0 | 0
PILING STUB - MMS | 603F-PR-1080 | Piling Stub MMS-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-06-22 07:03 | 2025-06-30 07:03 | 2025-04-02 07:03 | 2025-05-30 07:00 | 1 | 0 |  | 0 | 0
PILING STUB - MMS | 603F-PR-1090 | Piling Stub MMS-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-06-25 07:03 | 2025-07-03 07:03 | 2025-04-04 07:03 | 2025-06-01 07:03 | 1 | 52596 | Number | 0 | 0
PILING STUB - MMS | 603F-PR-1100 | Piling Stub MMS-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-07-11 07:00 | 2025-07-14 17:00 | 2025-07-11 07:00 | 2025-07-19 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - MMS | 603F-PR-1110 | Piling Stub MMS-Receipt At Site-Lot-03 | Completed | Resource Dependent | 2025-11-23 08:00 | 2025-12-02 15:27 | 2025-07-22 08:00 | 2025-07-30 10:33 | 1 | 52596 | Number | 0 | 0
PILING STUB - ROBOTIC DOCKING STATION | 603F-PR-1320 | Piling Stub-Robotic Docking Station-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-03-14 07:00 | 2025-03-17 17:00 | 2025-03-14 07:00 | 2025-03-17 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - ROBOTIC DOCKING STATION | 603F-PR-1330 | Piling Stub-Robotic Docking Station-TBER | Completed | Task Dependent | 2025-03-18 07:00 | 2025-03-29 17:00 | 2025-03-18 07:00 | 2025-03-29 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - ROBOTIC DOCKING STATION | 603F-PR-1340 | Piling Stub-Robotic Docking Station-Purchase Requistion | Completed | Task Dependent | 2025-03-30 07:00 | 2025-03-30 17:00 | 2025-03-30 07:00 | 2025-03-30 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - ROBOTIC DOCKING STATION | 603F-PR-1350 | Piling Stub-Robotic Docking Station-Note For Approval | Completed | Task Dependent | 2025-03-30 07:00 | 2025-03-31 17:00 | 2025-03-30 07:00 | 2025-03-31 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - ROBOTIC DOCKING STATION | 603F-PR-1360 | Piling Stub-Robotic Docking Station-LOI / PO Release | Completed | Task Dependent | 2025-04-01 07:00 | 2025-04-02 17:00 | 2025-04-01 07:00 | 2025-04-02 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - ROBOTIC DOCKING STATION | 603F-PR-1370 | Piling Stub-Robotic Docking Station-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-05-03 07:00 | 2025-06-03 17:00 | 2025-05-03 07:00 | 2025-09-01 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - ROBOTIC DOCKING STATION | 603F-PR-1380 | Piling Stub-Robotic Docking Station-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-09-01 07:00 | 2025-09-07 17:00 | 2025-09-01 07:00 | 2025-09-07 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - ROBOTIC DOCKING STATION | 603F-PR-1400 | Piling Stub-Robotic Docking Station-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-09-13 07:00 | 2025-09-20 17:00 | 2025-09-01 07:00 | 2025-09-07 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - ROBOTIC DOCKING STATION | 603F-PR-1410 | Piling Stub-Robotic Docking Station-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-09-16 07:00 | 2025-09-23 17:00 | 2025-09-05 07:00 | 2025-09-10 07:00 | 1 | 351 | Number | 0 | 0
PILING STUB - ROBOTIC DOCKING STATION | 603F-PR-1390 | Piling Stub-Robotic Docking Station-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-09-16 07:00 | 2025-09-23 17:00 | 2025-09-05 07:00 | 2025-09-09 17:00 | 1 | 351 | Number | 0 | 0
PILING STUB - ROBOTIC DOCKING STATION | 603F-PR-4600 | Piling Stub-Robotic Docking Station-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-11-22 07:00 | 2025-11-29 17:00 | 2025-09-02 07:00 | 2025-09-06 17:00 | 1 | 0 |  | 0 | 0
PILING STUB - ROBOTIC DOCKING STATION | 603F-PR-4610 | Piling Stub-Robotic Docking Station-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-11-25 07:00 | 2025-12-02 17:00 | 2025-09-08 07:00 | 2025-09-10 17:00 | 1 | 351 | Number | 0 | 0
PLANT LEVEL | 603F-EN-1000 | Project Technology Finalization | Completed | Task Dependent | 2025-02-15 07:00 | 2025-02-18 17:00 | 2025-02-15 07:00 | 2025-02-18 17:00 | 1 | 0 |  | 0 | 0
Power Purchase Agreement (PPA) / Grid Interconnection | PR-CA-11-020 | Regulatory Approval | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 08:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
Power Purchase Agreement (PPA) / Grid Interconnection | PR-CA-11-030 | Grid Connectivity | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 08:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
PRE-CONSTRUCTION STUDIES/PLANNING | PR-ST-A-010 | Geo Tech Investigation | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
PRE-CONSTRUCTION STUDIES/PLANNING | PR-ST-A-030 | Topography Survey | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
PRE-CONSTRUCTION STUDIES/PLANNING | PR-ST-A-060 | Signing of Security Management Plant ( SMP) for Construction & Operation phase ( Including Accomodations) | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
PRE-CONSTRUCTION STUDIES/PLANNING | PR-ST-A-070 | Onboarding of Project Engineering Consultant | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
PRE-CONSTRUCTION STUDIES/PLANNING | PR-ST-A-040 | Route Survey for movement of Manpower/Equipment/Over Dimension Consignment to site | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
PRE-CONSTRUCTION STUDIES/PLANNING | PR-ST-A-020 | Flood & Catchment Area Studies | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
PRE-CONSTRUCTION STUDIES/PLANNING | PR-ST-A-050 | Concept Approval of Accomodation & Township | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTIC STRUCTURE (EXTENDED MMS STRUCTURE) | 603F-PR-3720 | Robotic Cleaning System - Robotic Structure-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-26 07:00 | 2025-03-01 17:00 | 2025-02-26 07:00 | 2025-03-01 17:00 | 1 | 0 |  | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTIC STRUCTURE (EXTENDED MMS STRUCTURE) | 603F-PR-3730 | Robotic Cleaning System - Robotic Structure-TBER | Completed | Task Dependent | 2025-02-26 07:00 | 2025-03-09 17:00 | 2025-02-26 07:00 | 2025-03-09 17:00 | 1 | 0 |  | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTIC STRUCTURE (EXTENDED MMS STRUCTURE) | 603F-PR-3740 | Robotic Cleaning System - Robotic Structure-Purchase Requistion | Completed | Task Dependent | 2025-03-10 07:00 | 2025-03-10 17:00 | 2025-03-10 07:00 | 2025-03-10 17:00 | 1 | 0 |  | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTIC STRUCTURE (EXTENDED MMS STRUCTURE) | 603F-PR-3750 | Robotic Cleaning System - Robotic Structure-Note For Approval | Completed | Task Dependent | 2025-03-10 07:00 | 2025-03-11 17:00 | 2025-03-10 07:00 | 2025-03-11 17:00 | 1 | 0 |  | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTIC STRUCTURE (EXTENDED MMS STRUCTURE) | 603F-PR-3760 | Robotic Cleaning System - Robotic Structure-LOI / PO Release | Completed | Task Dependent | 2025-03-12 07:00 | 2025-03-13 17:00 | 2025-03-12 07:00 | 2025-03-13 17:00 | 1 | 0 |  | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTIC STRUCTURE (EXTENDED MMS STRUCTURE) | 603F-PR-3770 | Robotic Cleaning System - Robotic Structure-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-13 07:00 | 2025-06-18 17:00 | 2025-05-16 07:00 | 2025-06-05 07:22 | 1 | 0 |  | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTIC STRUCTURE (EXTENDED MMS STRUCTURE) | 603F-PR-5110 | Robotic Cleaning System - Robotic Structure-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-09-01 07:00 | 2025-09-07 17:00 | 2025-09-01 07:00 | 2025-09-07 17:00 | 1 | 0 |  | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTIC STRUCTURE (EXTENDED MMS STRUCTURE) | 603F-PR-3810 | Robotic Cleaning System - Robotic Structure-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-09-06 07:00 | 2025-09-12 17:00 | 2025-09-06 07:00 | 2025-09-12 17:00 | 1 | 1053 | Number | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTIC STRUCTURE (EXTENDED MMS STRUCTURE) | 603F-PR-3800 | Robotic Cleaning System - Robotic Structure-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-09-13 07:00 | 2025-09-19 17:00 | 2025-09-01 07:00 | 2025-09-07 17:00 | 1 | 0 |  | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTIC STRUCTURE (EXTENDED MMS STRUCTURE) | 603F-PR-3780 | Robotic Cleaning System - Robotic Structure-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-09-13 07:00 | 2025-09-19 17:00 | 2025-09-01 07:00 | 2025-09-07 17:00 | 1 | 0 |  | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTIC STRUCTURE (EXTENDED MMS STRUCTURE) | 603F-PR-3790 | Robotic Cleaning System - Robotic Structure-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-09-18 07:00 | 2025-09-24 17:00 | 2025-09-06 07:00 | 2025-09-12 17:00 | 1 | 1053 | Number | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTIC STRUCTURE (EXTENDED MMS STRUCTURE) | 603F-PR-5120 | Robotic Cleaning System - Robotic Structure-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-09-18 07:00 | 2025-09-24 17:00 | 2025-09-06 07:00 | 2025-09-12 17:00 | 1 | 1053 | Number | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTS (INCL DOCKING & RETURN STATION) (IMPORTED FROM CHINA) | 603F-PR-3830 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-TBER | Completed | Task Dependent | 2025-02-26 07:00 | 2025-03-09 17:00 | 2025-02-26 07:00 | 2025-03-09 17:00 | 1 | 0 |  | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTS (INCL DOCKING & RETURN STATION) (IMPORTED FROM CHINA) | 603F-PR-3820 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-26 07:00 | 2025-03-01 17:00 | 2025-02-26 07:00 | 2025-03-01 17:00 | 1 | 0 |  | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTS (INCL DOCKING & RETURN STATION) (IMPORTED FROM CHINA) | 603F-PR-3850 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Note For Approval | Completed | Task Dependent | 2025-03-10 07:00 | 2025-03-11 17:00 | 2025-03-10 07:00 | 2025-03-11 17:00 | 1 | 0 |  | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTS (INCL DOCKING & RETURN STATION) (IMPORTED FROM CHINA) | 603F-PR-3840 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Purchase Requistion | Completed | Task Dependent | 2025-03-10 07:00 | 2025-03-10 17:00 | 2025-03-10 07:00 | 2025-03-10 17:00 | 1 | 0 |  | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTS (INCL DOCKING & RETURN STATION) (IMPORTED FROM CHINA) | 603F-PR-3860 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-LOI / PO Release | Completed | Task Dependent | 2025-03-12 07:00 | 2025-03-13 17:00 | 2025-03-12 07:00 | 2025-03-13 17:00 | 1 | 0 |  | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTS (INCL DOCKING & RETURN STATION) (IMPORTED FROM CHINA) | 603F-PR-3870 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-13 07:00 | 2025-06-01 17:00 | 2025-05-16 07:00 | 2025-06-05 07:01 | 1 | 0 |  | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTS (INCL DOCKING & RETURN STATION) (IMPORTED FROM CHINA) | 603F-PR-3880 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Dispatch From China-Lot-01 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-15 17:00 | 2025-06-12 07:00 | 2025-06-12 17:00 | 1 | 0 |  | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTS (INCL DOCKING & RETURN STATION) (IMPORTED FROM CHINA) | 603F-PR-3910 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Dispatch From China-Lot-02 | Completed | Task Dependent | 2025-06-14 07:00 | 2025-06-15 17:00 | 2025-06-12 07:00 | 2025-06-12 17:00 | 1 | 0 |  | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTS (INCL DOCKING & RETURN STATION) (IMPORTED FROM CHINA) | 603F-PR-3890 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Transportation & Custom Clearance-Lot-01 | Completed | Task Dependent | 2025-06-16 07:00 | 2025-07-07 17:00 | 2025-06-13 07:00 | 2025-09-09 17:00 | 1 | 0 |  | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTS (INCL DOCKING & RETURN STATION) (IMPORTED FROM CHINA) | 603F-PR-5080 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Dispatch From China-Lot-03 | Completed | Task Dependent | 2025-06-16 07:00 | 2025-06-17 17:00 | 2025-06-12 07:00 | 2025-06-12 17:00 | 1 | 0 |  | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTS (INCL DOCKING & RETURN STATION) (IMPORTED FROM CHINA) | 603F-PR-3920 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Transportation & Custom Clearance-Lot-02 | Completed | Task Dependent | 2025-06-16 07:00 | 2025-07-07 17:00 | 2025-06-13 07:00 | 2025-09-09 17:00 | 1 | 0 |  | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTS (INCL DOCKING & RETURN STATION) (IMPORTED FROM CHINA) | 603F-PR-5090 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Transportation & Custom Clearance-Lot-03 | Completed | Task Dependent | 2025-06-18 07:00 | 2025-07-09 17:00 | 2025-06-08 07:00 | 2025-09-09 17:00 | 1 | 0 |  | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTS (INCL DOCKING & RETURN STATION) (IMPORTED FROM CHINA) | 603F-PR-3900 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-09-21 07:00 | 2025-09-24 17:00 | 2025-09-08 07:00 | 2025-09-11 17:00 | 1 | 351 | Number | 0 | 0
ROBOTIC CLEANING SYSTEM - ROBOTS (INCL DOCKING & RETURN STATION) (IMPORTED FROM CHINA) | 603F-PR-3930 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-09-23 07:00 | 2025-09-24 17:00 | 2025-09-08 07:00 | 2025-09-11 17:00 | 1 | 351 | Number | 0 | 0
SCADA | 603F-PR-4270 | SCADA-TBER | Completed | Task Dependent | 2025-02-23 07:00 | 2025-03-06 17:00 | 2025-02-23 07:00 | 2025-03-06 17:00 | 1 | 0 |  | 0 | 0
SCADA | 603F-PR-4260 | SCADA-BOQ & Tech Specs Release | Completed | Task Dependent | 2025-02-23 07:00 | 2025-02-26 17:00 | 2025-02-23 07:00 | 2025-02-26 17:00 | 1 | 0 |  | 0 | 0
SCADA | 603F-PR-4290 | SCADA-Note For Approval | Completed | Task Dependent | 2025-03-07 07:00 | 2025-03-08 17:00 | 2025-03-07 07:00 | 2025-03-08 17:00 | 1 | 0 |  | 0 | 0
SCADA | 603F-PR-4280 | SCADA-Purchase Requistion | Completed | Task Dependent | 2025-03-07 07:00 | 2025-03-07 17:00 | 2025-03-07 07:00 | 2025-03-07 17:00 | 1 | 0 |  | 0 | 0
SCADA | 603F-PR-4300 | SCADA-LOI / PO Release | Completed | Task Dependent | 2025-03-09 07:00 | 2025-03-10 17:00 | 2025-03-09 07:00 | 2025-03-10 17:00 | 1 | 0 |  | 0 | 0
SCADA | 603F-PR-4310 | SCADA-Manufacturing Clearance & Manufacturing | Completed | Task Dependent | 2025-04-10 07:00 | 2025-07-10 17:00 | 2025-05-05 07:00 | 2025-05-20 07:00 | 1 | 0 |  | 0 | 0
SCADA | 603F-PR-4330 | SCADA-Receipt At Site-Lot-01 | Completed | Task Dependent | 2025-05-24 07:00 | 2025-06-04 17:00 | 2025-05-14 | 2025-05-31 17:00 | 1 | 9 | Number | 0 | 0
SCADA | 603F-PR-4340 | SCADA-Dispatch For Site-Lot-02 | Completed | Task Dependent | 2025-05-24 07:00 | 2025-06-04 17:00 | 2025-05-18 | 2025-05-25 07:00 | 1 | 0 |  | 0 | 0
SCADA | 603F-PR-4350 | SCADA-Receipt At Site-Lot-02 | Completed | Task Dependent | 2025-05-27 07:00 | 2025-06-07 17:00 | 2025-05-21 | 2025-05-31 17:00 | 1 | 9 | Number | 0 | 0
SCADA | 603F-PR-4320 | SCADA-Dispatch For Site-Lot-01 | Completed | Task Dependent | 2025-06-05 07:00 | 2025-06-16 17:00 | 2025-05-11 | 2025-05-25 17:00 | 1 | 0 |  | 0 | 0
SCADA | 603F-PR-5190 | SCADA-Dispatch For Site-Lot-03 | Completed | Task Dependent | 2025-06-05 07:00 | 2025-06-16 17:00 | 2025-05-18 07:00 | 2025-05-25 07:00 | 1 | 0 |  | 0 | 0
SCADA | 603F-PR-5200 | SCADA-Receipt At Site-Lot-03 | Completed | Task Dependent | 2025-06-17 07:00 | 2025-06-22 17:00 | 2025-05-21 07:00 | 2025-05-31 17:00 | 1 | 9 | Number | 0 | 0
STAFF INFRASTRUCTURE DURING CONSTRUCTION & OPERATION PHASE | PR-SI-A-040 | Contractor Mobilisaton | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
STAFF INFRASTRUCTURE DURING CONSTRUCTION & OPERATION PHASE | PR-SI-A-010 | Township ( Incl Bachelor Hostels, Operator Colony , Common Utilities, Visitor Guest House ) | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
STAFF INFRASTRUCTURE DURING CONSTRUCTION & OPERATION PHASE | PR-SI-A-030 | Order Placement ( End Date ) | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
STAFF INFRASTRUCTURE DURING CONSTRUCTION & OPERATION PHASE | PR-SI-A-050 | Township Possession | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
STAFF INFRASTRUCTURE DURING CONSTRUCTION & OPERATION PHASE | PR-SI-A-020 | Architech/Consultant Onboarding for Township | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
Water Allocation & Groundwater Extraction NOC (CGWA / State) | PR-CA-10-020 | Compliance Documentation | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 08:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
Water Allocation & Groundwater Extraction NOC (CGWA / State) | PR-CA-10-010 | Hydrology Report & Application Submission | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 08:00 | 2025-02-15 08:00 | 2025-03-09 16:00 | 1 | 0 |  | 0 | 0
Water Allocation & Groundwater Extraction NOC (CGWA / State) | PR-CA-10-030 | Review & Inspection | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 08:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
Water Allocation & Groundwater Extraction NOC (CGWA / State) | PR-CA-10-040 | Grant of NOC | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 08:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
WORKER INFRASTRUCTURE DURING CONSTRUCTION & OPERATION PHASE | PR-WI-A-060 | Portable Toilets at construction areas | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
WORKER INFRASTRUCTURE DURING CONSTRUCTION & OPERATION PHASE | PR-WI-A-010 | Worker Colony | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
WORKER INFRASTRUCTURE DURING CONSTRUCTION & OPERATION PHASE | PR-WI-A-050 | Worker Rest shelter at construction areas | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
WORKER INFRASTRUCTURE DURING CONSTRUCTION & OPERATION PHASE | PR-WI-A-070 | Canteen Kitchen & Dining | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
WORKER INFRASTRUCTURE DURING CONSTRUCTION & OPERATION PHASE | PR-WI-A-030 | Order Placement ( End Date ) | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
WORKER INFRASTRUCTURE DURING CONSTRUCTION & OPERATION PHASE | PR-WI-A-080 | Effluent / Sewage/Potable Water | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
WORKER INFRASTRUCTURE DURING CONSTRUCTION & OPERATION PHASE | PR-WI-A-040 | Contractor Mobilisaton | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0
WORKER INFRASTRUCTURE DURING CONSTRUCTION & OPERATION PHASE | PR-WI-A-020 | Architech/Consultant Onboarding for Worker Colony | Completed | Task Dependent | 2025-01-20 08:00 | 2025-01-20 16:00 | 2025-02-15 08:00 | 2026-03-10 16:00 | 1 | 0 |  | 0 | 0

## Resources & Manpower
Activity ID | Activity Name | Resource ID | Resource Name | Resource Type | Planned Units | Actual Units | Gap (Remaining Units) | Budget at Completion | % Complete | Actual Start Date | Actual Finish Date
51R1-LD-1000 | Land Sub Lease agreement with SPV | Solar-MP15 | Land Resource | Labor | 60534 | 60534 | 0 | 0 | 1 | 2025-05-03 | 2025-07-30 17:00
603F-CC-1000 | Block-01 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2025-12-21 07:00 | 2026-01-18 17:00
603F-CC-1000 | Block-01 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5928 | 5928 | 0 | 0 | 1 | 2025-12-21 07:00 | 2026-01-18 17:00
603F-CC-1005 | Block-01 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2025-12-22 08:00 | 2026-01-18 17:00
603F-CC-1010 | Block-01 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-01-18 08:00
603F-CC-1010 | Block-01 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-01-18 08:00
603F-CC-1015 | Block-01 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-01-18 17:00
603F-CC-1015 | Block-01 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-01-18 17:00
603F-CC-1020 | Block-01 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-1020 | Block-01 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-1025 | Block-01 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2026-01-14 08:00 | 2026-02-19 17:00
603F-CC-1025 | Block-01 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 5.06 | 5 | 0 | 0 | 1 | 2026-01-14 08:00 | 2026-02-19 17:00
603F-CC-1030 | Block-01 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2026-01-06 08:00 | 2026-02-13 17:00
603F-CC-1030 | Block-01 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-01-06 08:00 | 2026-02-13 17:00
603F-CC-1035 | Block-01 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-01-06 08:00 | 2026-02-13 17:00
603F-CC-1035 | Block-01 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-01-06 08:00 | 2026-02-13 17:00
603F-CC-1040 | Block-01 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-01-06 08:00 | 2026-02-14 17:00
603F-CC-1040 | Block-01 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2026-01-06 08:00 | 2026-02-14 17:00
603F-CC-1045 | Block-01 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 1125 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-02-14 17:00
603F-CC-1050 | Block-01 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 17 | 0 | 0 | 1 | 2026-01-19 11:00 | 2026-02-15 17:00
603F-CC-1050 | Block-01 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 9882 | 0 | 0 | 1 | 2026-01-19 11:00 | 2026-02-15 17:00
603F-CC-1055 | Block-01 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 468 | 306 | 0 | 0.60465 | 2026-04-07 08:00
603F-CC-1060 | Block-01 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2026-01-17 11:00 | 2026-02-18 17:00
603F-CC-1060 | Block-01 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2026-01-17 11:00 | 2026-02-18 17:00
603F-CC-1065 | Block-01 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-01-30 11:00 | 2026-02-19 17:00
603F-CC-1065 | Block-01 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-01-30 11:00 | 2026-02-19 17:00
603F-CC-1070 | Block-01 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 52 | 0 | 0 | 1 | 2026-02-17 08:00 | 2026-02-26 17:00
603F-CC-1075 | Block-01 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-1075 | Block-01 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-1080 | Block-01 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-27 17:00
603F-CC-1080 | Block-01 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-27 17:00
603F-CC-1085 | Block-01 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 1845 | 0 | 0 | 1 | 2026-02-23 08:00 | 2026-04-24 15:00
603F-CC-1085 | Block-01 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-02-23 08:00 | 2026-04-24 15:00
603F-CC-1090 | Block-01 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 495 | 0 | 0 | 1 | 2026-02-23 08:00 | 2026-02-23 17:00
603F-CC-1090 | Block-01 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-02-23 08:00 | 2026-02-23 17:00
603F-CC-1095 | Block-01 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2025-12-15 08:00 | 2026-01-03 17:00
603F-CC-1095 | Block-01 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-15 08:00 | 2026-01-03 17:00
603F-CC-1095 | Block-01 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-15 08:00 | 2026-01-03 17:00
603F-CC-1095 | Block-01 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-15 08:00 | 2026-01-03 17:00
603F-CC-1100 | Block-01 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2025-12-20 08:00 | 2026-01-06 17:00
603F-CC-1100 | Block-01 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-20 08:00 | 2026-01-06 17:00
603F-CC-1100 | Block-01 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-20 08:00 | 2026-01-06 17:00
603F-CC-1105 | Block-01 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-1110 | Block-01 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-12 08:00 | 2026-02-12 17:00
603F-CC-1110 | Block-01 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-12 08:00 | 2026-02-12 17:00
603F-CC-1115 | Block-01 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-02-13 17:00
603F-CC-1115 | Block-01 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-02-13 17:00
603F-CC-1120 | Block-01 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-01-09 08:00 | 2026-01-13 17:00
603F-CC-1120 | Block-01 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-09 08:00 | 2026-01-13 17:00
603F-CC-1125 | Block-01 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-01-19 08:00 | 2026-01-19 17:00
603F-CC-1125 | Block-01 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-19 08:00 | 2026-01-19 17:00
603F-CC-1130 | Block-01 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-01-14 08:00 | 2026-01-20 17:00
603F-CC-1130 | Block-01 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-14 08:00 | 2026-01-20 17:00
603F-CC-1135 | Block-01 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-01-19 08:00 | 2026-01-19 17:00
603F-CC-1135 | Block-01 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-19 08:00 | 2026-01-19 17:00
603F-CC-1140 | Block-01 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-1140 | Block-01 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-1145 | Block-01 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-1145 | Block-01 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-1150 | Block-01 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-25 17:00
603F-CC-1155 | Block-01 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-01-28 08:00 | 2026-02-18 17:00
603F-CC-1155 | Block-01 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-28 08:00 | 2026-02-18 17:00
603F-CC-1155 | Block-01 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-28 08:00 | 2026-02-18 17:00
603F-CC-1155 | Block-01 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-28 08:00 | 2026-02-18 17:00
603F-CC-1155 | Block-01 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2026-01-28 08:00 | 2026-02-18 17:00
603F-CC-1155 | Block-01 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-28 08:00 | 2026-02-18 17:00
603F-CC-1160 | Block-01 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2026-01-20 08:00 | 2026-02-18 17:00
603F-CC-1160 | Block-01 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 9.5 | 10 | 0 | 0 | 1 | 2026-01-20 08:00 | 2026-02-18 17:00
603F-CC-1165 | Block-01 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2026-01-15 08:00 | 2026-02-23 17:00
603F-CC-1165 | Block-01 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 5.6 | 6 | 0 | 0 | 1 | 2026-01-15 08:00 | 2026-02-23 17:00
603F-CC-1170 | Block-01 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-02-22 17:00
603F-CC-1170 | Block-01 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-02-22 17:00
603F-CC-1175 | Block-01 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-1175 | Block-01 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-1180 | Block-01 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-01-21 08:00 | 2026-01-21 17:00
603F-CC-1180 | Block-01 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-21 08:00 | 2026-01-21 17:00
603F-CC-1185 | Block-01 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-02-13 17:00
603F-CC-1185 | Block-01 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-02-13 17:00
603F-CC-1190 | Block-01 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2026-01-09 08:00 | 2026-01-09 17:00
603F-CC-1190 | Block-01 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-09 08:00 | 2026-01-09 17:00
603F-CC-1195 | Block-01 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-02-02 17:00
603F-CC-1195 | Block-01 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 94 | 94 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-02-02 17:00
603F-CC-1200 | Block-01 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-02-13 17:00
603F-CC-1200 | Block-01 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-02-13 17:00
603F-CC-1205 | Block-01 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-02-13 17:00
603F-CC-1205 | Block-01 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-02-13 17:00
603F-CC-1210 | Block-01 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-1210 | Block-01 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-1215 | Block-01 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-01-25 08:00 | 2026-01-25 17:00
603F-CC-1215 | Block-01 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-25 08:00 | 2026-01-25 17:00
603F-CC-1220 | Block-01 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-02-23 17:00
603F-CC-1225 | Block-01 -LT Cable Terminations - LT Panel To IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-1230 | Block-01 -LT Cable Terminations - Inverter To LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-1235 | Block-01 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-02-07 07:00 | 2026-02-07 17:00
603F-CC-1240 | Block-01 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-02-09 07:00 | 2026-02-09 17:00
603F-CC-1245 | Block-01 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-02-23 07:00 | 2026-02-23 17:00
603F-CC-1250 | Block-01 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-23 07:00 | 2026-02-23 17:00
603F-CC-1320 | Block-02 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2026-01-03 08:00 | 2026-02-18 17:00
603F-CC-1320 | Block-02 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 3780 | 3780 | 0 | 0 | 1 | 2026-01-03 08:00 | 2026-02-18 17:00
603F-CC-1325 | Block-02 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-02-19 17:00
603F-CC-1330 | Block-02 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2026-01-16 08:00 | 2026-02-18 17:00
603F-CC-1330 | Block-02 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2026-01-16 08:00 | 2026-02-18 17:00
603F-CC-1335 | Block-02 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-02-18 17:00
603F-CC-1335 | Block-02 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-02-18 17:00
603F-CC-1340 | Block-02 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-03-18 08:00 | 2026-03-18 17:00
603F-CC-1340 | Block-02 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-03-18 08:00 | 2026-03-18 17:00
603F-CC-1345 | Block-02 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2026-02-07 08:00 | 2026-03-15 17:00
603F-CC-1345 | Block-02 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 4.93 | 5 | 0 | 0 | 1 | 2026-02-07 08:00 | 2026-03-15 17:00
603F-CC-1350 | Block-02 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2026-02-06 08:00 | 2026-03-12 17:00
603F-CC-1350 | Block-02 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 315 | 315 | 0 | 0 | 1 | 2026-02-06 08:00 | 2026-03-12 17:00
603F-CC-1355 | Block-02 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-02-06 08:00 | 2026-03-12 17:00
603F-CC-1355 | Block-02 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 315 | 315 | 0 | 0 | 1 | 2026-02-06 08:00 | 2026-03-12 17:00
603F-CC-1360 | Block-02 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-02-06 08:00 | 2026-03-12 17:00
603F-CC-1360 | Block-02 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2026-02-06 08:00 | 2026-03-12 17:00
603F-CC-1365 | Block-02 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 1125 | 0 | 0 | 1 | 2026-02-09 08:00 | 2026-03-13 17:00
603F-CC-1370 | Block-02 -Module Installation | Solar-MT12-B | Module - Construction | Material | 10.88 | 11 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-03-15 17:00
603F-CC-1370 | Block-02 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 9882 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-03-15 17:00
603F-CC-1375 | Block-02 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 522 | 252 | 0 | 0.67442 | 2026-04-07 08:00
603F-CC-1380 | Block-02 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2026-02-09 | 2026-03-15 17:00
603F-CC-1380 | Block-02 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2026-02-09 | 2026-03-15 17:00
603F-CC-1385 | Block-02 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-03-15 08:00 | 2026-03-20 17:00
603F-CC-1385 | Block-02 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 30 | 30 | 0 | 0 | 1 | 2026-03-15 08:00 | 2026-03-20 17:00
603F-CC-1390 | Block-02 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 81 | 0 | 0 | 1 | 2026-03-15 08:00 | 2026-03-23 17:00
603F-CC-1395 | Block-02 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-1395 | Block-02 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-1400 | Block-02 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-1400 | Block-02 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-1405 | Block-02 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 0 | 1845 | 0 | 0
603F-CC-1405 | Block-02 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-1410 | Block-02 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 0 | 495 | 0 | 0
603F-CC-1410 | Block-02 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-1415 | Block-02 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-02-03 17:00
603F-CC-1415 | Block-02 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-02-03 17:00
603F-CC-1415 | Block-02 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-02-03 17:00
603F-CC-1415 | Block-02 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-02-03 17:00
603F-CC-1420 | Block-02 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-02-02 17:00
603F-CC-1420 | Block-02 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-02-02 17:00
603F-CC-1420 | Block-02 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-02-02 17:00
603F-CC-1425 | Block-02 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-1425 | Block-02 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-1430 | Block-02 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-07 08:00 | 2026-03-07 17:00
603F-CC-1430 | Block-02 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-07 08:00 | 2026-03-07 17:00
603F-CC-1435 | Block-02 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-01-29 08:00 | 2026-01-29 17:00
603F-CC-1435 | Block-02 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-29 08:00 | 2026-01-29 17:00
603F-CC-1440 | Block-02 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-24 17:00
603F-CC-1440 | Block-02 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-24 17:00
603F-CC-1445 | Block-02 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-03-05 08:00 | 2026-03-05 17:00
603F-CC-1445 | Block-02 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-05 08:00 | 2026-03-05 17:00
603F-CC-1450 | Block-02 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-24 17:00
603F-CC-1450 | Block-02 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-24 17:00
603F-CC-1455 | Block-02 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-1455 | Block-02 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-1460 | Block-02 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-1460 | Block-02 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-1465 | Block-02 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-1470 | Block-02 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-1475 | Block-02 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-02-08 08:00 | 2026-03-15 17:00
603F-CC-1475 | Block-02 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-08 08:00 | 2026-03-15 17:00
603F-CC-1475 | Block-02 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-08 08:00 | 2026-03-15 17:00
603F-CC-1475 | Block-02 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-08 08:00 | 2026-03-15 17:00
603F-CC-1475 | Block-02 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2026-02-08 08:00 | 2026-03-15 17:00
603F-CC-1475 | Block-02 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-08 08:00 | 2026-03-15 17:00
603F-CC-1480 | Block-02 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2026-02-07 08:00 | 2026-02-07 17:00
603F-CC-1480 | Block-02 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 5.3 | 5 | 0 | 0 | 1 | 2026-02-07 08:00 | 2026-02-07 17:00
603F-CC-1485 | Block-02 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-10 08:00 | 2026-03-22 17:00
603F-CC-1485 | Block-02 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 4 | 4 | 0 | 0 | 1 | 2025-12-10 08:00 | 2026-03-22 17:00
603F-CC-1490 | Block-02 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-03-20 17:00
603F-CC-1490 | Block-02 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-03-20 17:00
603F-CC-1495 | Block-02 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-15 08:00 | 2026-03-20 08:00
603F-CC-1495 | Block-02 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-03-15 08:00 | 2026-03-20 08:00
603F-CC-1500 | Block-02 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-02-09 08:00 | 2026-02-09 17:00
603F-CC-1500 | Block-02 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-09 08:00 | 2026-02-09 17:00
603F-CC-1505 | Block-02 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-17 17:00
603F-CC-1505 | Block-02 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-17 17:00
603F-CC-1510 | Block-02 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2026-02-07 08:00 | 2026-02-07 17:00
603F-CC-1510 | Block-02 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-07 08:00 | 2026-02-07 17:00
603F-CC-1515 | Block-02 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-15 17:00
603F-CC-1515 | Block-02 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 60 | 60 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-15 17:00
603F-CC-1520 | Block-02 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-15 08:00 | 2026-03-15 17:00
603F-CC-1520 | Block-02 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-15 08:00 | 2026-03-15 17:00
603F-CC-1525 | Block-02 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-15 08:00 | 2026-03-15 17:00
603F-CC-1525 | Block-02 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-15 08:00 | 2026-03-15 17:00
603F-CC-1530 | Block-02 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-1530 | Block-02 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-1535 | Block-02 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-1535 | Block-02 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-1540 | Block-02 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-23 17:00
603F-CC-1545 | Block-02 -LT Cable Terminations - LT Panel To IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-03-15 08:00 | 2026-03-17 17:00
603F-CC-1550 | Block-02 -LT Cable Terminations - Inverter To LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-03-15 08:00 | 2026-03-20 17:00
603F-CC-1555 | Block-02 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-13 07:00 | 2026-03-13 17:00
603F-CC-1560 | Block-02 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-18 07:00 | 2026-03-18 17:00
603F-CC-1565 | Block-02 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-20 07:00 | 2026-03-20 17:00
603F-CC-1570 | Block-02 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-20 07:00 | 2026-03-20 17:00
603F-CC-1640 | Block-03 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2026-01-07 08:00 | 2026-04-23 10:00
603F-CC-1640 | Block-03 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5928 | 5928 | 0 | 0 | 1 | 2026-01-07 08:00 | 2026-04-23 10:00
603F-CC-1645 | Block-03 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-05-14 10:00
603F-CC-1650 | Block-03 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-04-23 14:00
603F-CC-1650 | Block-03 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-04-23 14:00
603F-CC-1655 | Block-03 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-04-17 10:00
603F-CC-1655 | Block-03 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-04-17 10:00
603F-CC-1660 | Block-03 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-05-20 08:00 | 2026-06-20 14:00
603F-CC-1660 | Block-03 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-05-20 08:00 | 2026-06-20 14:00
603F-CC-1665 | Block-03 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2026-03-16 08:00 | 2026-03-16 15:00
603F-CC-1665 | Block-03 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 5.26 | 5 | 0 | 0 | 1 | 2026-03-16 08:00 | 2026-03-16 15:00
603F-CC-1670 | Block-03 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2026-04-01 08:00 | 2026-05-12 10:00
603F-CC-1670 | Block-03 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-04-01 08:00 | 2026-05-12 10:00
603F-CC-1675 | Block-03 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-04-01 08:00 | 2026-05-12 11:00
603F-CC-1675 | Block-03 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-04-01 08:00 | 2026-05-12 11:00
603F-CC-1680 | Block-03 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-04-02 08:00 | 2026-05-13 11:00
603F-CC-1680 | Block-03 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2026-04-02 08:00 | 2026-05-13 11:00
603F-CC-1685 | Block-03 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 1125 | 0 | 0 | 1 | 2026-04-03 08:00 | 2026-05-14 12:00
603F-CC-1690 | Block-03 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 16 | 0.5 | 0 | 0.9697 | 2026-04-05 14:00
603F-CC-1690 | Block-03 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 9288 | 594 | 0 | 0.93989 | 2026-04-05 14:00
603F-CC-1695 | Block-03 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 0 | 774 | 0 | 0
603F-CC-1700 | Block-03 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2026-03-24 09:00 | 2026-04-11 12:00
603F-CC-1700 | Block-03 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2026-03-24 09:00 | 2026-04-11 12:00
603F-CC-1705 | Block-03 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-04-14 08:00 | 2026-04-17 12:00
603F-CC-1705 | Block-03 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-04-14 08:00 | 2026-04-17 12:00
603F-CC-1710 | Block-03 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 72 | 9 | 0 | 0.88889 | 2026-04-15 14:00
603F-CC-1715 | Block-03 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-1715 | Block-03 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-1720 | Block-03 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-1720 | Block-03 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-1725 | Block-03 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 0 | 1845 | 0 | 0
603F-CC-1725 | Block-03 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-1730 | Block-03 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 0 | 495 | 0 | 0
603F-CC-1730 | Block-03 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-1735 | Block-03 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-02-02 08:00
603F-CC-1735 | Block-03 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-02-02 08:00
603F-CC-1735 | Block-03 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-02-02 08:00
603F-CC-1735 | Block-03 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-02-02 08:00
603F-CC-1740 | Block-03 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-03-11 17:00
603F-CC-1740 | Block-03 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-03-11 17:00
603F-CC-1740 | Block-03 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-03-11 17:00
603F-CC-1745 | Block-03 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-04-13 08:00 | 2026-04-14 11:00
603F-CC-1745 | Block-03 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-13 08:00 | 2026-04-14 11:00
603F-CC-1750 | Block-03 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-04-15 08:00 | 2026-04-15 12:00
603F-CC-1750 | Block-03 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-15 08:00 | 2026-04-15 12:00
603F-CC-1755 | Block-03 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-02-27 08:00 | 2026-03-02 17:00
603F-CC-1755 | Block-03 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-27 08:00 | 2026-03-02 17:00
603F-CC-1760 | Block-03 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-04-02 08:00 | 2026-04-02 13:00
603F-CC-1760 | Block-03 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-02 08:00 | 2026-04-02 13:00
603F-CC-1765 | Block-03 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-04-11 08:00 | 2026-04-12 14:00
603F-CC-1765 | Block-03 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-11 08:00 | 2026-04-12 14:00
603F-CC-1770 | Block-03 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-04-02 08:00 | 2026-04-02 10:00
603F-CC-1770 | Block-03 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-02 08:00 | 2026-04-02 10:00
603F-CC-1775 | Block-03 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-04-16 09:00 | 2026-04-17 12:00
603F-CC-1775 | Block-03 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-16 09:00 | 2026-04-17 12:00
603F-CC-1780 | Block-03 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-04-17 12:00 | 2026-04-17 14:00
603F-CC-1780 | Block-03 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-17 12:00 | 2026-04-17 14:00
603F-CC-1785 | Block-03 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-05-06 08:00 | 2026-05-06 14:00
603F-CC-1790 | Block-03 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-14 08:00 | 2026-04-14 12:00
603F-CC-1795 | Block-03 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-03-16 08:00 | 2026-04-08 14:00
603F-CC-1795 | Block-03 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-16 08:00 | 2026-04-08 14:00
603F-CC-1795 | Block-03 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-16 08:00 | 2026-04-08 14:00
603F-CC-1795 | Block-03 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-16 08:00 | 2026-04-08 14:00
603F-CC-1795 | Block-03 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2026-03-16 08:00 | 2026-04-08 14:00
603F-CC-1795 | Block-03 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-16 08:00 | 2026-04-08 14:00
603F-CC-1800 | Block-03 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2026-03-16 08:00 | 2026-03-16 09:00
603F-CC-1800 | Block-03 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 9.2 | 9 | 0 | 0 | 1 | 2026-03-16 08:00 | 2026-03-16 09:00
603F-CC-1805 | Block-03 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-04-20 10:00
603F-CC-1805 | Block-03 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 4 | 4 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-04-20 10:00
603F-CC-1810 | Block-03 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-04-20 12:00
603F-CC-1810 | Block-03 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-04-20 12:00
603F-CC-1815 | Block-03 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-04-15 08:00 | 2026-04-20 12:00
603F-CC-1815 | Block-03 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-04-15 08:00 | 2026-04-20 12:00
603F-CC-1820 | Block-03 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-18 08:00 | 2026-03-18 17:00
603F-CC-1820 | Block-03 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-18 08:00 | 2026-03-18 17:00
603F-CC-1825 | Block-03 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-04-12 12:00 | 2026-04-13 10:00
603F-CC-1825 | Block-03 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-04-12 12:00 | 2026-04-13 10:00
603F-CC-1830 | Block-03 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2026-02-06 08:00 | 2026-02-06 17:00
603F-CC-1830 | Block-03 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-06 08:00 | 2026-02-06 17:00
603F-CC-1835 | Block-03 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-04-08 14:00 | 2026-04-17 10:00
603F-CC-1835 | Block-03 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 94 | 94 | 0 | 0 | 1 | 2026-04-08 14:00 | 2026-04-17 10:00
603F-CC-1840 | Block-03 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-14 08:00 | 2026-04-14 12:00
603F-CC-1840 | Block-03 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-14 08:00 | 2026-04-14 12:00
603F-CC-1845 | Block-03 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-15 08:00 | 2026-04-15 12:00
603F-CC-1845 | Block-03 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-15 08:00 | 2026-04-15 12:00
603F-CC-1850 | Block-03 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-04-03 09:00 | 2026-04-03 10:00
603F-CC-1850 | Block-03 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-03 09:00 | 2026-04-03 10:00
603F-CC-1855 | Block-03 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-04-14 08:00 | 2026-04-14 15:00
603F-CC-1855 | Block-03 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-14 08:00 | 2026-04-14 15:00
603F-CC-1860 | Block-03 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-20 12:00 | 2026-04-22 09:00
603F-CC-1865 | Block-03 -LT Cable Terminations - LT Panel To IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-04-17 08:00 | 2026-04-17 15:00
603F-CC-1870 | Block-03 -LT Cable Terminations - Inverter To LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-04-08 11:00 | 2026-04-28 10:00
603F-CC-1875 | Block-03 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-12 15:00 | 2026-04-12 15:00
603F-CC-1880 | Block-03 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-17 07:00 | 2026-04-17 17:00
603F-CC-1885 | Block-03 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-15 07:00 | 2026-04-15 17:00
603F-CC-1890 | Block-03 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-20 07:00 | 2026-04-20 17:00
603F-CC-1960 | Block-04 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-04-16 10:00
603F-CC-1960 | Block-04 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5928 | 5928 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-04-16 10:00
603F-CC-1965 | Block-04 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-04-16 10:00
603F-CC-1970 | Block-04 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2026-03-28 08:00 | 2026-04-23 14:00
603F-CC-1970 | Block-04 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2026-03-28 08:00 | 2026-04-23 14:00
603F-CC-1975 | Block-04 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2026-01-25 08:00 | 2026-04-08 14:00
603F-CC-1975 | Block-04 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2026-01-25 08:00 | 2026-04-08 14:00
603F-CC-1980 | Block-04 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-04-09 08:00 | 2026-04-09 14:00
603F-CC-1980 | Block-04 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-04-09 08:00 | 2026-04-09 14:00
603F-CC-1985 | Block-04 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-04-28 14:00
603F-CC-1985 | Block-04 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 5 | 5 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-04-28 14:00
603F-CC-1990 | Block-04 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2026-02-14 08:00 | 2026-05-19 10:00
603F-CC-1990 | Block-04 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-02-14 08:00 | 2026-05-19 10:00
603F-CC-1995 | Block-04 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-02-14 08:00 | 2026-05-19 11:00
603F-CC-1995 | Block-04 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-02-14 08:00 | 2026-05-19 11:00
603F-CC-2000 | Block-04 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-02-20 08:00 | 2026-05-19 11:00
603F-CC-2000 | Block-04 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2026-02-20 08:00 | 2026-05-19 11:00
603F-CC-2005 | Block-04 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 810 | 315 | 0 | 0.72 | 2026-02-23 08:00
603F-CC-2010 | Block-04 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 16 | 0.5 | 0 | 0.9697 | 2026-03-28 14:00
603F-CC-2010 | Block-04 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 9648 | 234 | 0 | 0.97632 | 2026-03-28 14:00
603F-CC-2015 | Block-04 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 288 | 486 | 0 | 0.37209 | 2026-05-13 12:00
603F-CC-2020 | Block-04 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2026-02-26 11:00 | 2026-04-20 10:00
603F-CC-2020 | Block-04 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2026-02-26 11:00 | 2026-04-20 10:00
603F-CC-2025 | Block-04 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-04-11 14:00 | 2026-04-28 09:00
603F-CC-2025 | Block-04 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-04-11 14:00 | 2026-04-28 09:00
603F-CC-2030 | Block-04 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 72 | 9 | 0 | 0.88889 | 2026-04-15 14:00
603F-CC-2035 | Block-04 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-2035 | Block-04 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-2040 | Block-04 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-2040 | Block-04 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-2045 | Block-04 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 0 | 1845 | 0 | 0
603F-CC-2045 | Block-04 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-2050 | Block-04 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 0 | 495 | 0 | 0
603F-CC-2050 | Block-04 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-2055 | Block-04 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-03-11 17:00
603F-CC-2055 | Block-04 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-03-11 17:00
603F-CC-2055 | Block-04 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-03-11 17:00
603F-CC-2055 | Block-04 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-03-11 17:00
603F-CC-2060 | Block-04 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2026-01-26 08:00 | 2026-02-11 17:00
603F-CC-2060 | Block-04 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-26 08:00 | 2026-02-11 17:00
603F-CC-2060 | Block-04 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-26 08:00 | 2026-02-11 17:00
603F-CC-2065 | Block-04 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-04-07 08:00 | 2026-04-07 11:00
603F-CC-2065 | Block-04 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-07 08:00 | 2026-04-07 11:00
603F-CC-2070 | Block-04 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-04-14 08:00 | 2026-04-14 12:00
603F-CC-2070 | Block-04 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-14 08:00 | 2026-04-14 12:00
603F-CC-2075 | Block-04 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-03-25 08:00 | 2026-03-31 11:00
603F-CC-2075 | Block-04 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-25 08:00 | 2026-03-31 11:00
603F-CC-2080 | Block-04 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-04-04 08:00 | 2026-04-04 14:00
603F-CC-2080 | Block-04 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-04 08:00 | 2026-04-04 14:00
603F-CC-2085 | Block-04 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-03-28 08:00 | 2026-04-01 13:00
603F-CC-2085 | Block-04 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-28 08:00 | 2026-04-01 13:00
603F-CC-2090 | Block-04 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-04-04 08:00 | 2026-04-04 11:00
603F-CC-2090 | Block-04 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-04 08:00 | 2026-04-04 11:00
603F-CC-2095 | Block-04 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-04-16 14:00 | 2026-04-17 10:00
603F-CC-2095 | Block-04 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-16 14:00 | 2026-04-17 10:00
603F-CC-2100 | Block-04 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-04-17 10:00 | 2026-04-17 12:00
603F-CC-2100 | Block-04 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-17 10:00 | 2026-04-17 12:00
603F-CC-2105 | Block-04 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-04-23 08:00 | 2026-04-23 14:00
603F-CC-2110 | Block-04 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-06 08:00 | 2026-04-06 12:00
603F-CC-2115 | Block-04 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-04-28 15:00
603F-CC-2115 | Block-04 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-04-28 15:00
603F-CC-2115 | Block-04 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-04-28 15:00
603F-CC-2115 | Block-04 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-04-28 15:00
603F-CC-2115 | Block-04 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-04-28 15:00
603F-CC-2115 | Block-04 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-04-28 15:00
603F-CC-2120 | Block-04 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-04-17 09:00
603F-CC-2120 | Block-04 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 9.8 | 10 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-04-17 09:00
603F-CC-2125 | Block-04 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-04-20 12:00
603F-CC-2125 | Block-04 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 4 | 4 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-04-20 12:00
603F-CC-2130 | Block-04 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-04-20 12:00
603F-CC-2130 | Block-04 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-04-20 12:00
603F-CC-2135 | Block-04 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-04-15 08:00 | 2026-04-20 12:00
603F-CC-2135 | Block-04 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-04-15 08:00 | 2026-04-20 12:00
603F-CC-2140 | Block-04 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-18 08:00 | 2026-03-18 17:00
603F-CC-2140 | Block-04 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-18 08:00 | 2026-03-18 17:00
603F-CC-2145 | Block-04 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-04-10 12:00 | 2026-04-15 14:00
603F-CC-2145 | Block-04 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-04-10 12:00 | 2026-04-15 14:00
603F-CC-2150 | Block-04 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2026-03-14 08:00 | 2026-03-14 17:00
603F-CC-2150 | Block-04 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-14 08:00 | 2026-03-14 17:00
603F-CC-2155 | Block-04 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-04-17 10:00
603F-CC-2155 | Block-04 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 94 | 94 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-04-17 10:00
603F-CC-2160 | Block-04 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-15 08:00 | 2026-04-15 12:00
603F-CC-2160 | Block-04 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-15 08:00 | 2026-04-15 12:00
603F-CC-2165 | Block-04 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-15 08:00 | 2026-04-15 12:00
603F-CC-2165 | Block-04 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-15 08:00 | 2026-04-15 12:00
603F-CC-2170 | Block-04 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-04-11 08:00 | 2026-04-11 09:00
603F-CC-2170 | Block-04 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-11 08:00 | 2026-04-11 09:00
603F-CC-2175 | Block-04 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-04-28 08:00 | 2026-04-28 15:00
603F-CC-2175 | Block-04 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-28 08:00 | 2026-04-28 15:00
603F-CC-2180 | Block-04 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-20 12:00 | 2026-04-22 09:00
603F-CC-2185 | Block-04 -LT Cable Terminations - LT Panel To IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-04-15 13:00 | 2026-04-15 13:00
603F-CC-2190 | Block-04 -LT Cable Terminations - Inverter To LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-04-08 12:00 | 2026-04-28 10:00
603F-CC-2195 | Block-04 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-05 13:00 | 2026-04-06 12:00
603F-CC-2200 | Block-04 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-08 13:00 | 2026-04-09 12:00
603F-CC-2205 | Block-04 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-09 15:00 | 2026-04-09 15:00
603F-CC-2210 | Block-04 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-20 07:00 | 2026-04-20 17:00
603F-CC-2280 | Block-05 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-02-07 17:00
603F-CC-2280 | Block-05 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5928 | 5928 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-02-07 17:00
603F-CC-2285 | Block-05 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-03-13 17:00
603F-CC-2290 | Block-05 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2026-01-29 08:00 | 2026-02-07 17:00
603F-CC-2290 | Block-05 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2026-01-29 08:00 | 2026-02-07 17:00
603F-CC-2295 | Block-05 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2026-01-23 08:00 | 2026-02-02 17:00
603F-CC-2295 | Block-05 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2026-01-23 08:00 | 2026-02-02 17:00
603F-CC-2300 | Block-05 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-03-18 08:00 | 2026-03-18 17:00
603F-CC-2300 | Block-05 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-03-18 08:00 | 2026-03-18 17:00
603F-CC-2305 | Block-05 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-18 17:00
603F-CC-2305 | Block-05 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 5.01 | 5 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-18 17:00
603F-CC-2310 | Block-05 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2026-02-12 08:00 | 2026-03-20 17:00
603F-CC-2310 | Block-05 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-02-12 08:00 | 2026-03-20 17:00
603F-CC-2315 | Block-05 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-02-12 08:00 | 2026-03-20 17:00
603F-CC-2315 | Block-05 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-02-12 08:00 | 2026-03-20 17:00
603F-CC-2320 | Block-05 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-03-22 17:00
603F-CC-2320 | Block-05 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-03-22 17:00
603F-CC-2325 | Block-05 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 1125 | 0 | 0 | 1 | 2026-02-20 08:00 | 2026-03-22 17:00
603F-CC-2330 | Block-05 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 17 | 0 | 0 | 1 | 2026-03-07 08:00 | 2026-03-23 17:00
603F-CC-2330 | Block-05 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 9882 | 0 | 0 | 1 | 2026-03-07 08:00 | 2026-03-23 17:00
603F-CC-2335 | Block-05 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 612 | 162 | 0 | 0.7907 | 2026-05-13 08:00
603F-CC-2340 | Block-05 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-18 17:00
603F-CC-2340 | Block-05 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-18 17:00
603F-CC-2345 | Block-05 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-03-20 17:00
603F-CC-2345 | Block-05 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-03-20 17:00
603F-CC-2350 | Block-05 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 81 | 0 | 0 | 1 | 2026-03-13 08:00 | 2026-03-22 17:00
603F-CC-2355 | Block-05 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-2355 | Block-05 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-2360 | Block-05 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-2360 | Block-05 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-2365 | Block-05 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 1845 | 0 | 0 | 1 | 2026-04-24 08:00 | 2026-04-24 13:00
603F-CC-2365 | Block-05 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-04-24 08:00 | 2026-04-24 13:00
603F-CC-2370 | Block-05 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 495 | 0 | 0 | 1 | 2026-04-24 09:00 | 2026-04-24 12:00
603F-CC-2370 | Block-05 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-04-24 09:00 | 2026-04-24 12:00
603F-CC-2375 | Block-05 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2026-01-23 08:00 | 2026-02-06 17:00
603F-CC-2375 | Block-05 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-23 08:00 | 2026-02-06 17:00
603F-CC-2375 | Block-05 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-23 08:00 | 2026-02-06 17:00
603F-CC-2375 | Block-05 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-23 08:00 | 2026-02-06 17:00
603F-CC-2380 | Block-05 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2026-01-24 08:00 | 2026-02-04 17:00
603F-CC-2380 | Block-05 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-24 08:00 | 2026-02-04 17:00
603F-CC-2380 | Block-05 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-24 08:00 | 2026-02-04 17:00
603F-CC-2385 | Block-05 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-11 08:00 | 2026-03-11 17:00
603F-CC-2385 | Block-05 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-11 08:00 | 2026-03-11 17:00
603F-CC-2390 | Block-05 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-17 08:00 | 2026-03-18 17:00
603F-CC-2390 | Block-05 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-17 08:00 | 2026-03-18 17:00
603F-CC-2395 | Block-05 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-02-08 08:00 | 2026-02-09 17:00
603F-CC-2395 | Block-05 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-08 08:00 | 2026-02-09 17:00
603F-CC-2400 | Block-05 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-24 17:00
603F-CC-2400 | Block-05 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-24 17:00
603F-CC-2405 | Block-05 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-03-15 08:00 | 2026-03-15 17:00
603F-CC-2405 | Block-05 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-15 08:00 | 2026-03-15 17:00
603F-CC-2410 | Block-05 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-24 17:00
603F-CC-2410 | Block-05 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-24 17:00
603F-CC-2415 | Block-05 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-2415 | Block-05 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-2420 | Block-05 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-2420 | Block-05 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-2425 | Block-05 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-2430 | Block-05 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-2435 | Block-05 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-10 17:00
603F-CC-2435 | Block-05 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-10 17:00
603F-CC-2435 | Block-05 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-10 17:00
603F-CC-2435 | Block-05 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-10 17:00
603F-CC-2435 | Block-05 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-10 17:00
603F-CC-2435 | Block-05 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-10 17:00
603F-CC-2440 | Block-05 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-11 17:00
603F-CC-2440 | Block-05 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 10 | 10 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-11 17:00
603F-CC-2445 | Block-05 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-03-20 17:00
603F-CC-2445 | Block-05 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 4 | 4 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-03-20 17:00
603F-CC-2450 | Block-05 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-20 17:00
603F-CC-2450 | Block-05 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-20 17:00
603F-CC-2455 | Block-05 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-2455 | Block-05 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-2460 | Block-05 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-2460 | Block-05 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-2465 | Block-05 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-03-11 08:00 | 2026-03-12 17:00
603F-CC-2465 | Block-05 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-03-11 08:00 | 2026-03-12 17:00
603F-CC-2470 | Block-05 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2026-02-09 08:00 | 2026-02-09 17:00
603F-CC-2470 | Block-05 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-09 08:00 | 2026-02-09 17:00
603F-CC-2475 | Block-05 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-03-09 08:00 | 2026-03-09 17:00
603F-CC-2475 | Block-05 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 94 | 94 | 0 | 0 | 1 | 2026-03-09 08:00 | 2026-03-09 17:00
603F-CC-2480 | Block-05 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-2480 | Block-05 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-2485 | Block-05 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-2485 | Block-05 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-2490 | Block-05 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-03-18 08:00 | 2026-03-18 17:00
603F-CC-2490 | Block-05 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-18 08:00 | 2026-03-18 17:00
603F-CC-2495 | Block-05 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-02-27 08:00 | 2026-02-27 17:00
603F-CC-2495 | Block-05 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-27 08:00 | 2026-02-27 17:00
603F-CC-2500 | Block-05 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-2505 | Block-05 -LT Cable Terminations - LT Panel To IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-03-15 08:00 | 2026-03-18 17:00
603F-CC-2510 | Block-05 -LT Cable Terminations - Inverter To LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-14 17:00
603F-CC-2515 | Block-05 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-14 07:00 | 2026-03-14 17:00
603F-CC-2520 | Block-05 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-18 07:00 | 2026-03-18 17:00
603F-CC-2525 | Block-05 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-20 07:00 | 2026-03-20 17:00
603F-CC-2530 | Block-05 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-20 07:00 | 2026-03-20 17:00
603F-CC-2600 | Block-06 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4679 | 4680 | 0 | 0 | 1 | 2025-12-27 08:00 | 2026-02-21 17:00
603F-CC-2600 | Block-06 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5792 | 5792 | 0 | 0 | 1 | 2025-12-27 08:00 | 2026-02-21 17:00
603F-CC-2605 | Block-06 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2025-12-30 08:00 | 2026-02-22 17:00
603F-CC-2610 | Block-06 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-02-02 17:00
603F-CC-2610 | Block-06 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 621 | 621 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-02-02 17:00
603F-CC-2615 | Block-06 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-02-02 17:00
603F-CC-2615 | Block-06 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-02-02 17:00
603F-CC-2620 | Block-06 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-05-20 08:00 | 2026-06-20 14:00
603F-CC-2620 | Block-06 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-05-20 08:00 | 2026-06-20 14:00
603F-CC-2625 | Block-06 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-03-18 17:00
603F-CC-2625 | Block-06 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 5 | 5 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-03-18 17:00
603F-CC-2630 | Block-06 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2026-01-22 08:00 | 2026-03-22 17:00
603F-CC-2630 | Block-06 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-01-22 08:00 | 2026-03-22 17:00
603F-CC-2635 | Block-06 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-01-22 08:00 | 2026-03-22 17:00
603F-CC-2635 | Block-06 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-01-22 08:00 | 2026-03-22 17:00
603F-CC-2640 | Block-06 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-01-24 08:00 | 2026-03-22 17:00
603F-CC-2640 | Block-06 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2026-01-24 08:00 | 2026-03-22 17:00
603F-CC-2645 | Block-06 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 1125 | 0 | 0 | 1 | 2026-01-26 08:00 | 2026-03-22 17:00
603F-CC-2650 | Block-06 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 17 | 0 | 0 | 1 | 2026-02-22 11:00 | 2026-03-22 12:00
603F-CC-2650 | Block-06 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 9882 | 0 | 0 | 1 | 2026-02-22 11:00 | 2026-03-22 12:00
603F-CC-2655 | Block-06 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 774 | 0 | 0 | 1 | 2026-05-13 08:00 | 2026-05-13 13:00
603F-CC-2660 | Block-06 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2026-01-19 11:00 | 2026-03-09 17:00
603F-CC-2660 | Block-06 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2026-01-19 11:00 | 2026-03-09 17:00
603F-CC-2665 | Block-06 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-01-26 11:00 | 2026-03-16 13:00
603F-CC-2665 | Block-06 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-01-26 11:00 | 2026-03-16 13:00
603F-CC-2670 | Block-06 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 63 | 18 | 0 | 0.77778 | 2026-03-14 11:00
603F-CC-2675 | Block-06 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-2675 | Block-06 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-2680 | Block-06 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-2680 | Block-06 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-2685 | Block-06 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 0 | 1845 | 0 | 0
603F-CC-2685 | Block-06 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-2690 | Block-06 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 252 | 243 | 0 | 0.50909 | 2026-04-24 08:00
603F-CC-2690 | Block-06 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 20 | 19 | 0 | 0.51282 | 2026-04-24 08:00
603F-CC-2695 | Block-06 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-02-04 17:00
603F-CC-2695 | Block-06 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-02-04 17:00
603F-CC-2695 | Block-06 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-02-04 17:00
603F-CC-2695 | Block-06 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-02-04 17:00
603F-CC-2700 | Block-06 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2026-01-24 08:00 | 2026-02-28 17:00
603F-CC-2700 | Block-06 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-24 08:00 | 2026-02-28 17:00
603F-CC-2700 | Block-06 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-24 08:00 | 2026-02-28 17:00
603F-CC-2705 | Block-06 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-06 08:00 | 2026-03-06 17:00
603F-CC-2705 | Block-06 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-06 08:00 | 2026-03-06 17:00
603F-CC-2710 | Block-06 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-24 08:00 | 2026-03-26 12:00
603F-CC-2710 | Block-06 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-24 08:00 | 2026-03-26 12:00
603F-CC-2715 | Block-06 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-02-20 08:00 | 2026-02-26 17:00
603F-CC-2715 | Block-06 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-20 08:00 | 2026-02-26 17:00
603F-CC-2720 | Block-06 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-11 08:00 | 2026-03-11 17:00
603F-CC-2720 | Block-06 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-11 08:00 | 2026-03-11 17:00
603F-CC-2725 | Block-06 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-22 17:00
603F-CC-2725 | Block-06 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-22 17:00
603F-CC-2730 | Block-06 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-11 08:00 | 2026-03-11 17:00
603F-CC-2730 | Block-06 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-11 08:00 | 2026-03-11 17:00
603F-CC-2735 | Block-06 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-03-24 08:00 | 2026-03-26 11:00
603F-CC-2735 | Block-06 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-24 08:00 | 2026-03-26 11:00
603F-CC-2740 | Block-06 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-03-22 08:00 | 2026-03-22 13:00
603F-CC-2740 | Block-06 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-22 08:00 | 2026-03-22 13:00
603F-CC-2745 | Block-06 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-22 08:00 | 2026-03-22 12:00
603F-CC-2750 | Block-06 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-13 08:00 | 2026-03-13 17:00
603F-CC-2755 | Block-06 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-01-22 08:00 | 2026-03-20 17:00
603F-CC-2755 | Block-06 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-22 08:00 | 2026-03-20 17:00
603F-CC-2755 | Block-06 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-22 08:00 | 2026-03-20 17:00
603F-CC-2755 | Block-06 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-22 08:00 | 2026-03-20 17:00
603F-CC-2755 | Block-06 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2026-01-22 08:00 | 2026-03-20 17:00
603F-CC-2755 | Block-06 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-22 08:00 | 2026-03-20 17:00
603F-CC-2760 | Block-06 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2026-01-20 08:00 | 2026-02-11 17:00
603F-CC-2760 | Block-06 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 9.2 | 9 | 0 | 0 | 1 | 2026-01-20 08:00 | 2026-02-11 17:00
603F-CC-2765 | Block-06 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-03-18 17:00
603F-CC-2765 | Block-06 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 5.9 | 6 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-03-18 17:00
603F-CC-2770 | Block-06 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-20 17:00
603F-CC-2770 | Block-06 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-20 17:00
603F-CC-2775 | Block-06 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-2775 | Block-06 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-2780 | Block-06 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-2780 | Block-06 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-2785 | Block-06 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-03-18 08:00 | 2026-03-18 17:00
603F-CC-2785 | Block-06 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-03-18 08:00 | 2026-03-18 17:00
603F-CC-2790 | Block-06 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2026-02-07 08:00 | 2026-02-07 17:00
603F-CC-2790 | Block-06 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-07 08:00 | 2026-02-07 17:00
603F-CC-2795 | Block-06 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-01-22 08:00 | 2026-02-11 17:00
603F-CC-2795 | Block-06 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 94 | 94 | 0 | 0 | 1 | 2026-01-22 08:00 | 2026-02-11 17:00
603F-CC-2800 | Block-06 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-2800 | Block-06 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-2805 | Block-06 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-18 08:00 | 2026-03-18 17:00
603F-CC-2805 | Block-06 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-18 08:00 | 2026-03-18 17:00
603F-CC-2810 | Block-06 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-03-18 08:00 | 2026-03-18 17:00
603F-CC-2810 | Block-06 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-18 08:00 | 2026-03-18 17:00
603F-CC-2815 | Block-06 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-2815 | Block-06 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-2820 | Block-06 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-2825 | Block-06 -LT Cable Terminations - LT Panel To IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-2830 | Block-06 -LT Cable Terminations - Inverter To LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-2835 | Block-06 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-15 07:00 | 2026-03-15 17:00
603F-CC-2840 | Block-06 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-18 07:00 | 2026-03-18 17:00
603F-CC-2845 | Block-06 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-20 07:00 | 2026-03-20 17:00
603F-CC-2850 | Block-06 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-20 07:00 | 2026-03-20 17:00
603F-CC-2920 | Block-07 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4743 | 45 | 0 | 0.9906 | 2025-11-25 08:00
603F-CC-2920 | Block-07 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5844 | 5785 | 143 | 0 | 0.97588 | 2025-11-25 08:00
603F-CC-2925 | Block-07 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2259 | 135 | 0 | 0.94361 | 2025-12-04 08:00
603F-CC-2930 | Block-07 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 449 | 28 | 0 | 0.9413 | 2025-12-12 08:00
603F-CC-2930 | Block-07 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 621 | 15 | 0 | 0.97642 | 2025-12-12 08:00
603F-CC-2935 | Block-07 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-03-27 17:00
603F-CC-2935 | Block-07 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-03-27 17:00
603F-CC-2940 | Block-07 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 0 | 225 | 0 | 0
603F-CC-2940 | Block-07 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-2945 | Block-07 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-04-20 12:00
603F-CC-2945 | Block-07 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 4.92 | 5 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-04-20 12:00
603F-CC-2950 | Block-07 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 7875 | 1125 | 0 | 0.875 | 2026-01-22 08:00
603F-CC-2950 | Block-07 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 494 | 432 | 62 | 0 | 0.87449 | 2026-01-22 08:00
603F-CC-2955 | Block-07 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 1971 | 279 | 0 | 0.876 | 2026-01-22 08:00
603F-CC-2955 | Block-07 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 494 | 432 | 62 | 0 | 0.87449 | 2026-01-22 08:00
603F-CC-2960 | Block-07 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 1575 | 675 | 0 | 0.7 | 2026-01-29 08:00
603F-CC-2960 | Block-07 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 341 | 146 | 0 | 0.70021 | 2026-01-29 08:00
603F-CC-2965 | Block-07 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 504 | 621 | 0 | 0.448 | 2026-01-30 08:00
603F-CC-2970 | Block-07 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 12 | 4.5 | 0 | 0.72727 | 2026-04-04 10:00
603F-CC-2970 | Block-07 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 6867 | 3015 | 0 | 0.6949 | 2026-04-04 10:00
603F-CC-2975 | Block-07 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 0 | 774 | 0 | 0
603F-CC-2980 | Block-07 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2026-03-23 09:00 | 2026-04-07 10:00
603F-CC-2980 | Block-07 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2026-03-23 09:00 | 2026-04-07 10:00
603F-CC-2985 | Block-07 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-03-26 08:00 | 2026-04-11 15:00
603F-CC-2985 | Block-07 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-03-26 08:00 | 2026-04-11 15:00
603F-CC-2990 | Block-07 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 54 | 27 | 0 | 0.66667 | 2026-04-12 10:00
603F-CC-2995 | Block-07 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-2995 | Block-07 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-3000 | Block-07 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-3000 | Block-07 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-3005 | Block-07 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 0 | 1845 | 0 | 0
603F-CC-3005 | Block-07 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-3010 | Block-07 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 0 | 495 | 0 | 0
603F-CC-3010 | Block-07 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-3015 | Block-07 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2026-01-15 08:00 | 2026-02-13 17:00
603F-CC-3015 | Block-07 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 0 | 0 | 0 | 0 | 2026-01-15 08:00 | 2026-02-13 17:00
603F-CC-3015 | Block-07 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 0 | 0 | 0 | 0 | 2026-01-15 08:00 | 2026-02-13 17:00
603F-CC-3015 | Block-07 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 0 | 0 | 0 | 0 | 2026-01-15 08:00 | 2026-02-13 17:00
603F-CC-3020 | Block-07 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2025-12-10 08:00 | 2026-01-20 17:00
603F-CC-3020 | Block-07 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-10 08:00 | 2026-01-20 17:00
603F-CC-3020 | Block-07 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-10 08:00 | 2026-01-20 17:00
603F-CC-3025 | Block-07 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-3025 | Block-07 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-3030 | Block-07 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-04-17 08:00 | 2026-04-17 12:00
603F-CC-3030 | Block-07 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-17 08:00 | 2026-04-17 12:00
603F-CC-3035 | Block-07 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-02-02 08:00 | 2026-04-11 12:00
603F-CC-3035 | Block-07 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-02 08:00 | 2026-04-11 12:00
603F-CC-3040 | Block-07 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-04-10 08:00 | 2026-04-10 14:00
603F-CC-3040 | Block-07 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-10 08:00 | 2026-04-10 14:00
603F-CC-3045 | Block-07 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-02-22 08:00 | 2026-03-09 17:00
603F-CC-3045 | Block-07 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-22 08:00 | 2026-03-09 17:00
603F-CC-3050 | Block-07 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-04-10 08:00 | 2026-04-10 11:00
603F-CC-3050 | Block-07 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-10 08:00 | 2026-04-10 11:00
603F-CC-3055 | Block-07 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-04-16 14:00 | 2026-04-17 10:00
603F-CC-3055 | Block-07 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-16 14:00 | 2026-04-17 10:00
603F-CC-3060 | Block-07 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-04-17 10:00 | 2026-04-17 12:00
603F-CC-3060 | Block-07 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-17 10:00 | 2026-04-17 12:00
603F-CC-3065 | Block-07 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-04-18 12:00 | 2026-04-19 11:00
603F-CC-3070 | Block-07 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-14 08:00 | 2026-04-14 12:00
603F-CC-3075 | Block-07 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-30 12:00
603F-CC-3075 | Block-07 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-30 12:00
603F-CC-3075 | Block-07 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-30 12:00
603F-CC-3075 | Block-07 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-30 12:00
603F-CC-3075 | Block-07 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-30 12:00
603F-CC-3075 | Block-07 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-30 12:00
603F-CC-3080 | Block-07 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 15:00
603F-CC-3080 | Block-07 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 10.9 | 11 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 15:00
603F-CC-3085 | Block-07 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2026-01-04 08:00 | 2026-02-23 17:00
603F-CC-3085 | Block-07 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 5.9 | 6 | 0 | 0 | 1 | 2026-01-04 08:00 | 2026-02-23 17:00
603F-CC-3090 | Block-07 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-01-26 08:00 | 2026-01-27 17:00
603F-CC-3090 | Block-07 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-01-26 08:00 | 2026-01-27 17:00
603F-CC-3095 | Block-07 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-04-12 12:00 | 2026-04-15 09:00
603F-CC-3095 | Block-07 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-04-12 12:00 | 2026-04-15 09:00
603F-CC-3100 | Block-07 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-3100 | Block-07 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-3105 | Block-07 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-04-09 09:00 | 2026-04-11 12:00
603F-CC-3105 | Block-07 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-04-09 09:00 | 2026-04-11 12:00
603F-CC-3110 | Block-07 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2026-02-17 08:00 | 2026-02-17 17:00
603F-CC-3110 | Block-07 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-17 08:00 | 2026-02-17 17:00
603F-CC-3115 | Block-07 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-27 17:00
603F-CC-3115 | Block-07 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 94 | 94 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-27 17:00
603F-CC-3120 | Block-07 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-10 12:00 | 2026-04-11 09:00
603F-CC-3120 | Block-07 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-10 12:00 | 2026-04-11 09:00
603F-CC-3125 | Block-07 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-10 12:00 | 2026-04-11 09:00
603F-CC-3125 | Block-07 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-10 12:00 | 2026-04-11 09:00
603F-CC-3130 | Block-07 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-04-14 10:00 | 2026-04-14 11:00
603F-CC-3130 | Block-07 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-14 10:00 | 2026-04-14 11:00
603F-CC-3135 | Block-07 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-04-20 12:00 | 2026-04-20 12:00
603F-CC-3135 | Block-07 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-20 12:00 | 2026-04-20 12:00
603F-CC-3140 | Block-07 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-20 08:00 | 2026-04-22 12:00
603F-CC-3145 | Block-07 -LT Cable Terminations - LT Panel To IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-04-15 08:00 | 2026-04-15 15:00
603F-CC-3150 | Block-07 -LT Cable Terminations - Inverter To LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-04-03 08:00 | 2026-04-12 13:00
603F-CC-3155 | Block-07 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-01 11:00 | 2026-04-01 11:00
603F-CC-3160 | Block-07 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-10 07:00 | 2026-04-10 17:00
603F-CC-3165 | Block-07 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-11 13:00 | 2026-04-12 12:00
603F-CC-3170 | Block-07 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-14 13:00 | 2026-04-15 13:00
603F-CC-3240 | Block-08 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2025-12-15 08:00 | 2026-02-19 17:00
603F-CC-3240 | Block-08 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5928 | 5928 | 0 | 0 | 1 | 2025-12-15 08:00 | 2026-02-19 17:00
603F-CC-3245 | Block-08 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2025-12-26 08:00 | 2026-02-20 17:00
603F-CC-3250 | Block-08 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-31 08:00 | 2026-02-17 17:00
603F-CC-3250 | Block-08 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2025-12-31 08:00 | 2026-02-17 17:00
603F-CC-3255 | Block-08 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2026-01-03 08:00 | 2026-02-18 17:00
603F-CC-3255 | Block-08 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2026-01-03 08:00 | 2026-02-18 17:00
603F-CC-3260 | Block-08 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-05-22 08:00 | 2026-05-22 14:00
603F-CC-3260 | Block-08 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-05-22 08:00 | 2026-05-22 14:00
603F-CC-3265 | Block-08 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2026-01-28 08:00 | 2026-05-10 11:00
603F-CC-3265 | Block-08 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 5.26 | 5 | 0 | 0 | 1 | 2026-01-28 08:00 | 2026-05-10 11:00
603F-CC-3270 | Block-08 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2026-01-20 08:00 | 2026-05-20 09:00
603F-CC-3270 | Block-08 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-01-20 08:00 | 2026-05-20 09:00
603F-CC-3275 | Block-08 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-01-20 12:00 | 2026-05-20 14:00
603F-CC-3275 | Block-08 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-01-20 12:00 | 2026-05-20 14:00
603F-CC-3280 | Block-08 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 1953 | 297 | 0 | 0.868 | 2026-01-24 08:00
603F-CC-3280 | Block-08 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 421 | 66 | 0 | 0.86448 | 2026-01-24 08:00
603F-CC-3285 | Block-08 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 378 | 747 | 0 | 0.336 | 2026-01-25 08:00
603F-CC-3290 | Block-08 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 15 | 0 | 0 | 1 | 2026-04-06 10:00
603F-CC-3290 | Block-08 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 8244 | 0 | 0 | 1 | 2026-04-06 10:00
603F-CC-3295 | Block-08 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 0 | 774 | 0 | 0
603F-CC-3300 | Block-08 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2026-01-28 08:00 | 2026-04-12 14:00
603F-CC-3300 | Block-08 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2026-01-28 08:00 | 2026-04-12 14:00
603F-CC-3305 | Block-08 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-04-10 08:00 | 2026-04-28 11:00
603F-CC-3305 | Block-08 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-04-10 08:00 | 2026-04-28 11:00
603F-CC-3310 | Block-08 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 27 | 54 | 0 | 0.33333 | 2026-04-28 13:00
603F-CC-3315 | Block-08 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-3315 | Block-08 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-3320 | Block-08 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-3320 | Block-08 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-3325 | Block-08 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 0 | 1845 | 0 | 0
603F-CC-3325 | Block-08 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-3330 | Block-08 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 0 | 495 | 0 | 0
603F-CC-3330 | Block-08 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-3335 | Block-08 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2026-01-13 08:00 | 2026-02-12 17:00
603F-CC-3335 | Block-08 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-13 08:00 | 2026-02-12 17:00
603F-CC-3335 | Block-08 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-13 08:00 | 2026-02-12 17:00
603F-CC-3335 | Block-08 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-13 08:00 | 2026-02-12 17:00
603F-CC-3340 | Block-08 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2026-02-07 08:00 | 2026-02-15 17:00
603F-CC-3340 | Block-08 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-07 08:00 | 2026-02-15 17:00
603F-CC-3340 | Block-08 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-07 08:00 | 2026-02-15 17:00
603F-CC-3345 | Block-08 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-3345 | Block-08 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-3350 | Block-08 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-3350 | Block-08 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-3355 | Block-08 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-01-28 08:00 | 2026-01-31 17:00
603F-CC-3355 | Block-08 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-28 08:00 | 2026-01-31 17:00
603F-CC-3360 | Block-08 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-3360 | Block-08 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-3365 | Block-08 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-02-27 08:00 | 2026-02-28 17:00
603F-CC-3365 | Block-08 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-27 08:00 | 2026-02-28 17:00
603F-CC-3370 | Block-08 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-3370 | Block-08 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-3375 | Block-08 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 0 | 0 | 0 | 0 | 2026-04-04 10:00 | 2026-04-04 13:00
603F-CC-3375 | Block-08 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 0 | 0 | 0 | 0 | 2026-04-04 10:00 | 2026-04-04 13:00
603F-CC-3380 | Block-08 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-04-17 08:00 | 2026-04-17 12:00
603F-CC-3380 | Block-08 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-17 08:00 | 2026-04-17 08:00
603F-CC-3385 | Block-08 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-04-18 10:00 | 2026-04-19 09:00
603F-CC-3390 | Block-08 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-04 08:00 | 2026-04-04 12:00
603F-CC-3395 | Block-08 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-04-28 10:00
603F-CC-3395 | Block-08 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-04-28 10:00
603F-CC-3395 | Block-08 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-04-28 10:00
603F-CC-3395 | Block-08 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-04-28 10:00
603F-CC-3395 | Block-08 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-04-28 10:00
603F-CC-3395 | Block-08 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-04-28 10:00
603F-CC-3400 | Block-08 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2026-01-28 08:00 | 2026-03-27 17:00
603F-CC-3400 | Block-08 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 9.2 | 9 | 0 | 0 | 1 | 2026-01-28 08:00 | 2026-03-27 17:00
603F-CC-3405 | Block-08 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2026-01-09 08:00 | 2026-04-07 10:00
603F-CC-3405 | Block-08 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 6.2 | 6 | 0 | 0 | 1 | 2026-01-09 08:00 | 2026-04-07 10:00
603F-CC-3410 | Block-08 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-04-12 10:00
603F-CC-3410 | Block-08 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-04-12 10:00
603F-CC-3415 | Block-08 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-04-12 08:00 | 2026-04-20 10:00
603F-CC-3415 | Block-08 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-04-12 08:00 | 2026-04-20 10:00
603F-CC-3420 | Block-08 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-3420 | Block-08 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-3425 | Block-08 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-04-06 08:00 | 2026-04-08 13:00
603F-CC-3425 | Block-08 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-04-06 08:00 | 2026-04-08 13:00
603F-CC-3430 | Block-08 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-02-16 17:00
603F-CC-3430 | Block-08 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-02-16 17:00
603F-CC-3435 | Block-08 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-01-29 08:00 | 2026-04-07 12:00
603F-CC-3435 | Block-08 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 94 | 94 | 0 | 0 | 1 | 2026-01-29 08:00 | 2026-04-07 12:00
603F-CC-3440 | Block-08 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-11 08:00 | 2026-04-11 12:00
603F-CC-3440 | Block-08 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-11 08:00 | 2026-04-11 12:00
603F-CC-3445 | Block-08 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-08 08:00 | 2026-04-08 12:00
603F-CC-3445 | Block-08 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-08 08:00 | 2026-04-08 12:00
603F-CC-3450 | Block-08 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-04-10 08:00 | 2026-04-10 09:00
603F-CC-3450 | Block-08 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-10 08:00 | 2026-04-10 09:00
603F-CC-3455 | Block-08 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-04-12 08:00 | 2026-04-12 15:00
603F-CC-3455 | Block-08 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-12 08:00 | 2026-04-12 15:00
603F-CC-3460 | Block-08 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-14 10:00 | 2026-04-22 12:00
603F-CC-3465 | Block-08 -LT Cable Terminations - LT Panel to IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-04-09 14:00 | 2026-04-15 12:00
603F-CC-3470 | Block-08 -LT Cable Terminations - Inverter to LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-04-06 14:00 | 2026-04-11 12:00
603F-CC-3475 | Block-08 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-10 15:00 | 2026-04-10 15:00
603F-CC-3480 | Block-08 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-10 15:00 | 2026-04-10 15:00
603F-CC-3485 | Block-08 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-12 07:00 | 2026-04-12 17:00
603F-CC-3490 | Block-08 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-12 07:00 | 2026-04-12 17:00
603F-CC-3560 | Block-09 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2026-01-09 08:00 | 2026-04-02 17:00
603F-CC-3560 | Block-09 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5928 | 5928 | 0 | 0 | 1 | 2026-01-09 08:00 | 2026-04-02 17:00
603F-CC-3565 | Block-09 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2026-01-20 08:00 | 2026-04-02 09:00
603F-CC-3570 | Block-09 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2026-01-22 08:00 | 2026-02-02 17:00
603F-CC-3570 | Block-09 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2026-01-22 08:00 | 2026-02-02 17:00
603F-CC-3575 | Block-09 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2026-01-23 08:00 | 2026-02-02 17:00
603F-CC-3575 | Block-09 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2026-01-23 08:00 | 2026-02-02 17:00
603F-CC-3580 | Block-09 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-04-02 08:00 | 2026-04-02 13:00
603F-CC-3580 | Block-09 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-04-02 08:00 | 2026-04-02 13:00
603F-CC-3585 | Block-09 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-03-30 10:00
603F-CC-3585 | Block-09 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 5.26 | 5 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-03-30 10:00
603F-CC-3590 | Block-09 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2026-02-02 08:00 | 2026-04-25 10:00
603F-CC-3590 | Block-09 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-02-02 08:00 | 2026-04-25 10:00
603F-CC-3595 | Block-09 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-02-02 12:00 | 2026-04-25 15:00
603F-CC-3595 | Block-09 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-02-02 12:00 | 2026-04-25 15:00
603F-CC-3600 | Block-09 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-02-06 08:00 | 2026-04-25 13:00
603F-CC-3600 | Block-09 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2026-02-06 08:00 | 2026-04-25 13:00
603F-CC-3605 | Block-09 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 1125 | 0 | 0 | 1 | 2026-02-07 08:00 | 2026-04-28 12:00
603F-CC-3610 | Block-09 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 17 | 0 | 0 | 1 | 2026-02-22 11:00 | 2026-04-26 12:00
603F-CC-3610 | Block-09 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 9882 | 0 | 0 | 1 | 2026-02-22 11:00 | 2026-04-26 12:00
603F-CC-3615 | Block-09 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 180 | 594 | 0 | 0.23256 | 2026-05-13 08:00
603F-CC-3620 | Block-09 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2026-02-26 11:00 | 2026-03-23 17:00
603F-CC-3620 | Block-09 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2026-02-26 11:00 | 2026-03-23 17:00
603F-CC-3625 | Block-09 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-03-13 08:00 | 2026-03-27 17:00
603F-CC-3625 | Block-09 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 48 | 48 | 0 | 0 | 1 | 2026-03-13 08:00 | 2026-03-27 17:00
603F-CC-3630 | Block-09 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 81 | 0 | 0 | 1 | 2026-03-16 10:00 | 2026-05-16 10:00
603F-CC-3635 | Block-09 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-3635 | Block-09 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-3640 | Block-09 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-05-22 08:00 | 2026-05-22 14:00
603F-CC-3640 | Block-09 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-05-22 08:00 | 2026-05-22 14:00
603F-CC-3645 | Block-09 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 0 | 1845 | 0 | 0
603F-CC-3645 | Block-09 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-3650 | Block-09 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 0 | 495 | 0 | 0
603F-CC-3650 | Block-09 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-3655 | Block-09 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-01-27 17:00
603F-CC-3655 | Block-09 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-01-27 17:00
603F-CC-3655 | Block-09 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-01-27 17:00
603F-CC-3655 | Block-09 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-01-27 17:00
603F-CC-3660 | Block-09 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-01-26 17:00
603F-CC-3660 | Block-09 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-01-26 17:00
603F-CC-3660 | Block-09 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-01-26 17:00
603F-CC-3665 | Block-09 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-25 08:00 | 2026-03-13 17:00
603F-CC-3665 | Block-09 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-25 08:00 | 2026-03-13 17:00
603F-CC-3670 | Block-09 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-3670 | Block-09 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-3675 | Block-09 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-01-21 08:00 | 2026-01-28 17:00
603F-CC-3675 | Block-09 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-21 08:00 | 2026-01-28 17:00
603F-CC-3680 | Block-09 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-01-29 08:00 | 2026-01-30 17:00
603F-CC-3680 | Block-09 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-29 08:00 | 2026-01-30 17:00
603F-CC-3685 | Block-09 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-02-01 08:00 | 2026-02-05 17:00
603F-CC-3685 | Block-09 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-01 08:00 | 2026-02-05 17:00
603F-CC-3690 | Block-09 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-01-30 17:00
603F-CC-3690 | Block-09 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-01-30 17:00
603F-CC-3695 | Block-09 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-04-03 08:00 | 2026-04-03 12:00
603F-CC-3695 | Block-09 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-03 08:00 | 2026-04-03 12:00
603F-CC-3700 | Block-09 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-04-02 12:00 | 2026-04-03 09:00
603F-CC-3700 | Block-09 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-02 12:00 | 2026-04-03 09:00
603F-CC-3705 | Block-09 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-04-03 08:00 | 2026-04-03 17:00
603F-CC-3710 | Block-09 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-29 08:00 | 2026-03-29 17:00
603F-CC-3715 | Block-09 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-02-27 17:00
603F-CC-3715 | Block-09 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-02-27 17:00
603F-CC-3715 | Block-09 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-02-27 17:00
603F-CC-3715 | Block-09 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-02-27 17:00
603F-CC-3715 | Block-09 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-02-27 17:00
603F-CC-3715 | Block-09 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-02-27 17:00
603F-CC-3720 | Block-09 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-02-27 17:00
603F-CC-3720 | Block-09 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 12.5 | 13 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-02-27 17:00
603F-CC-3725 | Block-09 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-03-28 17:00
603F-CC-3725 | Block-09 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 4 | 4 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-03-28 17:00
603F-CC-3730 | Block-09 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-23 17:00
603F-CC-3730 | Block-09 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-23 17:00
603F-CC-3735 | Block-09 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-3735 | Block-09 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-3740 | Block-09 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-02-26 17:00
603F-CC-3740 | Block-09 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-02-26 17:00
603F-CC-3745 | Block-09 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-03-13 08:00 | 2026-03-13 17:00
603F-CC-3745 | Block-09 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-03-13 08:00 | 2026-03-13 17:00
603F-CC-3750 | Block-09 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2026-01-29 08:00 | 2026-01-29 17:00
603F-CC-3750 | Block-09 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-29 08:00 | 2026-01-29 17:00
603F-CC-3755 | Block-09 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-03-08 17:00
603F-CC-3755 | Block-09 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 94 | 94 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-03-08 17:00
603F-CC-3760 | Block-09 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-13 08:00 | 2026-03-13 17:00
603F-CC-3760 | Block-09 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-13 08:00 | 2026-03-13 17:00
603F-CC-3765 | Block-09 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-13 08:00 | 2026-03-13 17:00
603F-CC-3765 | Block-09 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-13 08:00 | 2026-03-13 17:00
603F-CC-3770 | Block-09 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-03-24 08:00 | 2026-03-24 17:00
603F-CC-3770 | Block-09 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-24 08:00 | 2026-03-24 17:00
603F-CC-3775 | Block-09 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-03-13 08:00 | 2026-03-13 17:00
603F-CC-3775 | Block-09 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-13 08:00 | 2026-03-13 17:00
603F-CC-3780 | Block-09 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-03 08:00 | 2026-04-03 17:00
603F-CC-3785 | Block-09 -LT Cable Terminations - LT Panel to IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-03-27 08:00 | 2026-03-29 17:00
603F-CC-3790 | Block-09 -LT Cable Terminations - Inverter to LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-26 08:00
603F-CC-3795 | Block-09 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-18 07:00 | 2026-03-18 17:00
603F-CC-3800 | Block-09 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-29 07:00 | 2026-03-29 17:00
603F-CC-3805 | Block-09 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-26 07:00 | 2026-03-26 17:00
603F-CC-3810 | Block-09 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-27 07:00 | 2026-03-27 17:00
603F-CC-3880 | Block-10 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2025-12-16 08:00 | 2026-03-17 17:00
603F-CC-3880 | Block-10 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5916 | 5916 | 0 | 0 | 1 | 2025-12-16 08:00 | 2026-03-17 17:00
603F-CC-3885 | Block-10 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2025-12-23 08:00 | 2026-03-24 17:00
603F-CC-3890 | Block-10 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2026-01-07 08:00 | 2026-02-02 17:00
603F-CC-3890 | Block-10 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2026-01-07 08:00 | 2026-02-02 17:00
603F-CC-3895 | Block-10 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2026-01-07 08:00 | 2026-02-02 17:00
603F-CC-3895 | Block-10 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2026-01-07 08:00 | 2026-02-02 17:00
603F-CC-3900 | Block-10 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-05-20 08:00 | 2026-05-20 14:00
603F-CC-3900 | Block-10 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-05-20 08:00 | 2026-05-20 14:00
603F-CC-3905 | Block-10 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-04-17 12:00
603F-CC-3905 | Block-10 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 5.13 | 5 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-04-17 12:00
603F-CC-3910 | Block-10 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2026-01-14 08:00 | 2026-04-22 10:00
603F-CC-3910 | Block-10 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 493 | 493 | 0 | 0 | 1 | 2026-01-14 08:00 | 2026-04-22 10:00
603F-CC-3915 | Block-10 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-01-14 12:00 | 2026-04-22 15:00
603F-CC-3915 | Block-10 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 493 | 493 | 0 | 0 | 1 | 2026-01-14 12:00 | 2026-04-22 15:00
603F-CC-3920 | Block-10 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-01-14 08:00 | 2026-04-23 10:00
603F-CC-3920 | Block-10 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 470 | 0 | 0 | 1 | 2026-01-14 08:00 | 2026-04-23 10:00
603F-CC-3925 | Block-10 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 1125 | 0 | 0 | 1 | 2026-01-15 08:00 | 2026-04-25 12:00
603F-CC-3930 | Block-10 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 17 | 0 | 0 | 1 | 2026-02-04 11:00 | 2026-05-22 10:00
603F-CC-3930 | Block-10 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 9882 | 0 | 0 | 1 | 2026-02-04 11:00 | 2026-05-22 10:00
603F-CC-3935 | Block-10 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 0 | 774 | 0 | 0
603F-CC-3940 | Block-10 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2016 | 0 | 0 | 1 | 2026-01-12 11:00 | 2026-03-27 17:00
603F-CC-3940 | Block-10 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2026-01-12 11:00 | 2026-03-27 17:00
603F-CC-3945 | Block-10 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-03-26 08:00 | 2026-04-07 09:00
603F-CC-3945 | Block-10 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-03-26 08:00 | 2026-04-07 09:00
603F-CC-3950 | Block-10 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 81 | 0 | 0 | 1 | 2026-03-29 08:00
603F-CC-3955 | Block-10 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-3955 | Block-10 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-3960 | Block-10 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-3960 | Block-10 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-3965 | Block-10 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 0 | 1845 | 0 | 0
603F-CC-3965 | Block-10 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-3970 | Block-10 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 0 | 495 | 0 | 0
603F-CC-3970 | Block-10 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-3975 | Block-10 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2026-01-04 08:00 | 2026-01-10 17:00
603F-CC-3975 | Block-10 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-04 08:00 | 2026-01-10 17:00
603F-CC-3975 | Block-10 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-04 08:00 | 2026-01-10 17:00
603F-CC-3975 | Block-10 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-04 08:00 | 2026-01-10 17:00
603F-CC-3980 | Block-10 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2026-02-04 08:00 | 2026-02-08 17:00
603F-CC-3980 | Block-10 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-04 08:00 | 2026-02-08 17:00
603F-CC-3980 | Block-10 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-04 08:00 | 2026-02-08 17:00
603F-CC-3985 | Block-10 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-06 08:00 | 2026-03-06 17:00
603F-CC-3985 | Block-10 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-06 08:00 | 2026-03-06 17:00
603F-CC-3990 | Block-10 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-3990 | Block-10 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-3995 | Block-10 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-01-15 08:00 | 2026-01-15 17:00
603F-CC-3995 | Block-10 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-15 08:00 | 2026-01-15 17:00
603F-CC-4000 | Block-10 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-24 17:00
603F-CC-4000 | Block-10 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-24 17:00
603F-CC-4005 | Block-10 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-02-20 08:00 | 2026-03-23 17:00
603F-CC-4005 | Block-10 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-20 08:00 | 2026-03-23 17:00
603F-CC-4010 | Block-10 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-24 17:00
603F-CC-4010 | Block-10 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-24 17:00
603F-CC-4015 | Block-10 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-04-03 08:00 | 2026-04-03 12:00
603F-CC-4015 | Block-10 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-03 08:00 | 2026-04-03 12:00
603F-CC-4020 | Block-10 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-04-02 12:00 | 2026-04-03 09:00
603F-CC-4020 | Block-10 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-02 12:00 | 2026-04-03 09:00
603F-CC-4025 | Block-10 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-04-03 08:00 | 2026-04-03 17:00
603F-CC-4030 | Block-10 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-4035 | Block-10 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-03-27 17:00
603F-CC-4035 | Block-10 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-03-27 17:00
603F-CC-4035 | Block-10 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-03-27 17:00
603F-CC-4035 | Block-10 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-03-27 17:00
603F-CC-4035 | Block-10 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-03-27 17:00
603F-CC-4035 | Block-10 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-03-27 17:00
603F-CC-4040 | Block-10 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2026-01-26 08:00 | 2026-02-09 17:00
603F-CC-4040 | Block-10 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 9.2 | 9 | 0 | 0 | 1 | 2026-01-26 08:00 | 2026-02-09 17:00
603F-CC-4045 | Block-10 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-12 08:00 | 2026-03-28 17:00
603F-CC-4045 | Block-10 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 4 | 4 | 0 | 0 | 1 | 2025-12-12 08:00 | 2026-03-28 17:00
603F-CC-4050 | Block-10 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-03-23 17:00
603F-CC-4050 | Block-10 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-03-23 17:00
603F-CC-4055 | Block-10 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-27 08:00 | 2026-03-29 17:00
603F-CC-4055 | Block-10 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-03-27 08:00 | 2026-03-29 17:00
603F-CC-4060 | Block-10 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-4060 | Block-10 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-4065 | Block-10 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-4065 | Block-10 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-4070 | Block-10 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2026-01-24 08:00 | 2026-01-24 17:00
603F-CC-4070 | Block-10 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-24 08:00 | 2026-01-24 17:00
603F-CC-4075 | Block-10 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-01-08 08:00 | 2026-03-23 17:00
603F-CC-4075 | Block-10 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 94 | 94 | 0 | 0 | 1 | 2026-01-08 08:00 | 2026-03-23 17:00
603F-CC-4080 | Block-10 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-4080 | Block-10 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-4085 | Block-10 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-4085 | Block-10 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-4090 | Block-10 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-03-27 08:00 | 2026-03-27 17:00
603F-CC-4090 | Block-10 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-27 08:00 | 2026-03-27 17:00
603F-CC-4095 | Block-10 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-03-27 08:00 | 2026-03-27 17:00
603F-CC-4095 | Block-10 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-27 08:00 | 2026-03-27 17:00
603F-CC-4100 | Block-10 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-03 08:00 | 2026-04-03 17:00
603F-CC-4105 | Block-10 -LT Cable Terminations - LT Panel to IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-03-21 08:00 | 2026-03-29 17:00
603F-CC-4110 | Block-10 -LT Cable Terminations - Inverter to LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-4115 | Block-10 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-23 07:00 | 2026-03-23 17:00
603F-CC-4120 | Block-10 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-29 07:00 | 2026-03-29 17:00
603F-CC-4125 | Block-10 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-30 07:00 | 2026-03-30 17:00
603F-CC-4130 | Block-10 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-27 07:00 | 2026-03-27 17:00
603F-CC-4200 | Block-11 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2025-12-12 08:00 | 2026-01-10 17:00
603F-CC-4200 | Block-11 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5844 | 5844 | 0 | 0 | 1 | 2025-12-12 08:00 | 2026-01-10 17:00
603F-CC-4205 | Block-11 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2025-12-23 08:00 | 2026-01-16 17:00
603F-CC-4210 | Block-11 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-29 08:00 | 2026-01-20 17:00
603F-CC-4210 | Block-11 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2025-12-29 08:00 | 2026-01-20 17:00
603F-CC-4215 | Block-11 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2025-12-30 08:00 | 2026-01-13 17:00
603F-CC-4215 | Block-11 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2025-12-30 08:00 | 2026-01-13 17:00
603F-CC-4220 | Block-11 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-4220 | Block-11 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-4225 | Block-11 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2025-12-29 | 2026-02-19 17:00
603F-CC-4225 | Block-11 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 5.03 | 5 | 0 | 0 | 1 | 2025-12-29 | 2026-02-19 17:00
603F-CC-4230 | Block-11 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2026-01-14 08:00 | 2026-02-09 17:00
603F-CC-4230 | Block-11 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 493 | 493 | 0 | 0 | 1 | 2026-01-14 08:00 | 2026-02-09 17:00
603F-CC-4235 | Block-11 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-01-14 12:00 | 2026-02-09 12:00
603F-CC-4235 | Block-11 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 493 | 493 | 0 | 0 | 1 | 2026-01-14 12:00 | 2026-02-09 12:00
603F-CC-4240 | Block-11 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-01-14 08:00 | 2026-02-09 17:00
603F-CC-4240 | Block-11 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2026-01-14 08:00 | 2026-02-09 17:00
603F-CC-4245 | Block-11 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 1125 | 0 | 0 | 1 | 2026-01-19 08:00 | 2026-02-19 17:00
603F-CC-4250 | Block-11 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 17 | 0 | 0 | 1 | 2026-01-25 11:00 | 2026-02-21 17:00
603F-CC-4250 | Block-11 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 9882 | 0 | 0 | 1 | 2026-01-25 11:00 | 2026-02-21 17:00
603F-CC-4255 | Block-11 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 567 | 207 | 0 | 0.73256 | 2026-02-12 08:00
603F-CC-4260 | Block-11 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2026-01-01 11:00 | 2026-02-19 17:00
603F-CC-4260 | Block-11 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2026-01-01 11:00 | 2026-02-19 17:00
603F-CC-4265 | Block-11 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-01-27 11:00 | 2026-02-18 17:00
603F-CC-4265 | Block-11 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-01-27 11:00 | 2026-02-18 17:00
603F-CC-4270 | Block-11 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 81 | 0 | 0 | 1 | 2026-02-17 08:00 | 2026-02-24 17:00
603F-CC-4275 | Block-11 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-02-22 08:00 | 2026-02-22 17:00
603F-CC-4275 | Block-11 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-02-22 08:00 | 2026-02-22 17:00
603F-CC-4280 | Block-11 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-20 17:00
603F-CC-4280 | Block-11 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-20 17:00
603F-CC-4285 | Block-11 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 1773 | 72 | 0 | 0.96098 | 2026-02-16 08:00
603F-CC-4285 | Block-11 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 38 | 1 | 0 | 0.97436 | 2026-02-16 08:00
603F-CC-4290 | Block-11 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 495 | 0 | 0 | 1 | 2026-02-22 08:00 | 2026-02-22 17:00
603F-CC-4290 | Block-11 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-02-22 08:00 | 2026-02-22 17:00
603F-CC-4295 | Block-11 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2025-12-13 08:00 | 2026-01-02 17:00
603F-CC-4295 | Block-11 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-13 08:00 | 2026-01-02 17:00
603F-CC-4295 | Block-11 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-13 08:00 | 2026-01-02 17:00
603F-CC-4295 | Block-11 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-13 08:00 | 2026-01-02 17:00
603F-CC-4300 | Block-11 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2025-12-21 08:00 | 2026-01-02 17:00
603F-CC-4300 | Block-11 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-21 08:00 | 2026-01-02 17:00
603F-CC-4300 | Block-11 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-21 08:00 | 2026-01-02 17:00
603F-CC-4305 | Block-11 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-01-07 08:00 | 2026-01-09 17:00
603F-CC-4305 | Block-11 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-07 08:00 | 2026-01-09 17:00
603F-CC-4310 | Block-11 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-01-10 17:00
603F-CC-4310 | Block-11 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-01-10 17:00
603F-CC-4315 | Block-11 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2025-12-31 08:00 | 2026-01-03 17:00
603F-CC-4315 | Block-11 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-31 08:00 | 2026-01-03 17:00
603F-CC-4320 | Block-11 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-01-03 08:00 | 2026-01-04 17:00
603F-CC-4320 | Block-11 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-03 08:00 | 2026-01-04 17:00
603F-CC-4325 | Block-11 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-01-07 17:00
603F-CC-4325 | Block-11 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-01-07 17:00
603F-CC-4330 | Block-11 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-01-03 08:00 | 2026-01-04 17:00
603F-CC-4330 | Block-11 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-03 08:00 | 2026-01-04 17:00
603F-CC-4335 | Block-11 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 177 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-25 17:00
603F-CC-4335 | Block-11 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-25 17:00
603F-CC-4340 | Block-11 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-24 17:00
603F-CC-4340 | Block-11 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-24 17:00
603F-CC-4345 | Block-11 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-25 17:00
603F-CC-4350 | Block-11 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-4355 | Block-11 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-02-19 17:00
603F-CC-4355 | Block-11 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-02-19 17:00
603F-CC-4355 | Block-11 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-02-19 17:00
603F-CC-4355 | Block-11 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-02-19 17:00
603F-CC-4355 | Block-11 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-02-19 17:00
603F-CC-4355 | Block-11 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-02-19 17:00
603F-CC-4360 | Block-11 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2026-01-13 08:00 | 2026-01-27 17:00
603F-CC-4360 | Block-11 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 9.2 | 9 | 0 | 0 | 1 | 2026-01-13 08:00 | 2026-01-27 17:00
603F-CC-4365 | Block-11 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2026-01-08 08:00 | 2026-02-23 17:00
603F-CC-4365 | Block-11 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 6.6 | 7 | 0 | 0 | 1 | 2026-01-08 08:00 | 2026-02-23 17:00
603F-CC-4370 | Block-11 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-02-22 17:00
603F-CC-4370 | Block-11 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-02-22 17:00
603F-CC-4375 | Block-11 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-4375 | Block-11 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-4380 | Block-11 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-01-05 17:00
603F-CC-4380 | Block-11 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-01-05 17:00
603F-CC-4385 | Block-11 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-01-30 17:00
603F-CC-4385 | Block-11 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-01-30 17:00
603F-CC-4390 | Block-11 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-01-10 17:00
603F-CC-4390 | Block-11 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-01-10 17:00
603F-CC-4395 | Block-11 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-01-14 08:00 | 2026-01-31 17:00
603F-CC-4395 | Block-11 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 94 | 94 | 0 | 0 | 1 | 2026-01-14 08:00 | 2026-01-31 17:00
603F-CC-4400 | Block-11 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-01-31 17:00
603F-CC-4400 | Block-11 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-01-31 17:00
603F-CC-4405 | Block-11 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-01-30 17:00
603F-CC-4405 | Block-11 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-01-30 17:00
603F-CC-4410 | Block-11 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-02-11 08:00 | 2026-02-11 17:00
603F-CC-4410 | Block-11 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-11 08:00 | 2026-02-11 17:00
603F-CC-4415 | Block-11 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-01-22 08:00 | 2026-01-22 17:00
603F-CC-4415 | Block-11 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-22 08:00 | 2026-01-22 17:00
603F-CC-4420 | Block-11 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-02-23 17:00
603F-CC-4425 | Block-11 -LT Cable Terminations - LT Panel to IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-4430 | Block-11 -LT Cable Terminations - Inverter to LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-4435 | Block-11 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-02-12 07:00 | 2026-02-12 17:00
603F-CC-4440 | Block-11 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-02-19 07:00 | 2026-02-19 17:00
603F-CC-4445 | Block-11 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-02-19 07:00 | 2026-02-19 17:00
603F-CC-4450 | Block-11 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-19 07:00 | 2026-02-19 17:00
603F-CC-4520 | Block-12 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2025-11-21 08:00 | 2025-12-22 17:00
603F-CC-4520 | Block-12 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5844 | 5844 | 0 | 0 | 1 | 2025-11-21 08:00 | 2025-12-22 17:00
603F-CC-4525 | Block-12 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2025-11-23 08:00 | 2025-12-27 17:00
603F-CC-4530 | Block-12 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-07 08:00 | 2026-02-18 17:00
603F-CC-4530 | Block-12 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2025-12-07 08:00 | 2026-02-18 17:00
603F-CC-4535 | Block-12 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2025-12-07 08:00 | 2025-12-25 17:00
603F-CC-4535 | Block-12 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2025-12-07 08:00 | 2025-12-25 17:00
603F-CC-4540 | Block-12 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-02-12 08:00 | 2026-02-12 17:00
603F-CC-4540 | Block-12 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-02-12 08:00 | 2026-02-12 17:00
603F-CC-4545 | Block-12 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2025-12-07 08:00 | 2026-02-19 17:00
603F-CC-4545 | Block-12 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 5 | 5.44 | 0 | 0 | 1 | 2025-12-07 08:00 | 2026-02-19 17:00
603F-CC-4550 | Block-12 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2025-12-09 08:00 | 2026-01-10 17:00
603F-CC-4550 | Block-12 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2025-12-09 08:00 | 2026-01-10 17:00
603F-CC-4555 | Block-12 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2025-12-09 | 2026-01-10 12:00
603F-CC-4555 | Block-12 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2025-12-09 | 2026-01-10 12:00
603F-CC-4560 | Block-12 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2025-12-16 08:00 | 2026-01-22 17:00
603F-CC-4560 | Block-12 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2025-12-16 08:00 | 2026-01-22 17:00
603F-CC-4565 | Block-12 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 1125 | 0 | 0 | 1 | 2026-02-01 08:00 | 2026-02-17 17:00
603F-CC-4570 | Block-12 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 17 | 0 | 0 | 1 | 2025-12-30 11:00 | 2026-01-24 11:00
603F-CC-4570 | Block-12 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 9882 | 0 | 0 | 1 | 2025-12-30 11:00 | 2026-01-24 11:00
603F-CC-4575 | Block-12 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 774 | 0 | 0 | 1 | 2026-02-12 08:00 | 2026-03-08 17:00
603F-CC-4580 | Block-12 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2025-12-12 11:00 | 2026-02-18 17:00
603F-CC-4580 | Block-12 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2025-12-12 11:00 | 2026-02-18 17:00
603F-CC-4585 | Block-12 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-01-26 11:00 | 2026-01-26 11:00
603F-CC-4585 | Block-12 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 48 | 48 | 0 | 0 | 1 | 2026-01-26 11:00 | 2026-01-26 11:00
603F-CC-4590 | Block-12 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 81 | 0 | 0 | 1 | 2026-01-21 11:00 | 2026-02-04 17:00
603F-CC-4595 | Block-12 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-02-13 17:00
603F-CC-4595 | Block-12 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-02-13 17:00
603F-CC-4600 | Block-12 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-02-18 17:00
603F-CC-4600 | Block-12 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-02-18 17:00
603F-CC-4605 | Block-12 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 1845 | 0 | 0 | 1 | 2026-02-14 08:00 | 2026-02-16 17:00
603F-CC-4605 | Block-12 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-02-14 08:00 | 2026-02-16 17:00
603F-CC-4610 | Block-12 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 495 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-02-22 17:00
603F-CC-4610 | Block-12 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-02-22 17:00
603F-CC-4615 | Block-12 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2025-11-21 08:00 | 2025-12-11 17:00
603F-CC-4615 | Block-12 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-21 08:00 | 2025-12-11 17:00
603F-CC-4615 | Block-12 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-21 08:00 | 2025-12-11 17:00
603F-CC-4615 | Block-12 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-21 08:00 | 2025-12-11 17:00
603F-CC-4620 | Block-12 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2025-11-22 08:00 | 2025-12-15 17:00
603F-CC-4620 | Block-12 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-22 08:00 | 2025-12-15 17:00
603F-CC-4620 | Block-12 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-22 08:00 | 2025-12-15 17:00
603F-CC-4625 | Block-12 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-01-09 17:00
603F-CC-4625 | Block-12 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-01-09 17:00
603F-CC-4630 | Block-12 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-01-10 17:00
603F-CC-4630 | Block-12 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-01-10 17:00
603F-CC-4635 | Block-12 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2025-12-11 08:00 | 2025-12-18 17:00
603F-CC-4635 | Block-12 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-11 08:00 | 2025-12-18 17:00
603F-CC-4640 | Block-12 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2025-12-25 08:00 | 2025-12-26 17:00
603F-CC-4640 | Block-12 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-25 08:00 | 2025-12-26 17:00
603F-CC-4645 | Block-12 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2025-12-16 08:00 | 2025-12-26 11:36
603F-CC-4645 | Block-12 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-16 08:00 | 2025-12-26 11:36
603F-CC-4650 | Block-12 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2025-12-25 08:00 | 2025-12-26 17:00
603F-CC-4650 | Block-12 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-25 08:00 | 2025-12-26 17:00
603F-CC-4655 | Block-12 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-02-16 17:00
603F-CC-4655 | Block-12 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-02-16 17:00
603F-CC-4660 | Block-12 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-02-16 08:00
603F-CC-4660 | Block-12 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-02-16 08:00
603F-CC-4665 | Block-12 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-02-16 17:00
603F-CC-4670 | Block-12 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-02-16 17:00
603F-CC-4675 | Block-12 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2025-12-23 08:00 | 2026-02-18 17:00
603F-CC-4675 | Block-12 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-23 08:00 | 2026-02-18 17:00
603F-CC-4675 | Block-12 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-23 08:00 | 2026-02-18 17:00
603F-CC-4675 | Block-12 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-23 08:00 | 2026-02-18 17:00
603F-CC-4675 | Block-12 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2025-12-23 08:00 | 2026-02-18 17:00
603F-CC-4675 | Block-12 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-23 08:00 | 2026-02-18 17:00
603F-CC-4680 | Block-12 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2025-12-20 08:00 | 2026-02-18 17:00
603F-CC-4680 | Block-12 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 10.9 | 11 | 0 | 0 | 1 | 2025-12-20 08:00 | 2026-02-18 17:00
603F-CC-4685 | Block-12 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-02-23 17:00
603F-CC-4685 | Block-12 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 5.9 | 6 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-02-23 17:00
603F-CC-4690 | Block-12 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-01-27 08:00 | 2026-02-23 17:00
603F-CC-4690 | Block-12 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-01-27 08:00 | 2026-02-23 17:00
603F-CC-4695 | Block-12 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-19 17:00
603F-CC-4695 | Block-12 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-19 17:00
603F-CC-4700 | Block-12 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2025-12-29 08:00 | 2025-12-29 17:00
603F-CC-4700 | Block-12 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-29 08:00 | 2025-12-29 17:00
603F-CC-4705 | Block-12 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-01-12 17:00
603F-CC-4705 | Block-12 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-01-12 17:00
603F-CC-4710 | Block-12 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2025-12-23 08:00 | 2025-12-23 17:00
603F-CC-4710 | Block-12 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-23 08:00 | 2025-12-23 17:00
603F-CC-4715 | Block-12 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2025-12-25 08:00 | 2026-01-04 17:00
603F-CC-4715 | Block-12 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2025-12-25 08:00 | 2026-01-04 17:00
603F-CC-4720 | Block-12 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-01-10 17:00
603F-CC-4720 | Block-12 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-01-10 17:00
603F-CC-4725 | Block-12 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-01-10 17:00
603F-CC-4725 | Block-12 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-01-10 17:00
603F-CC-4730 | Block-12 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-01-28 08:00 | 2026-01-28 17:00
603F-CC-4730 | Block-12 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-28 08:00 | 2026-01-28 17:00
603F-CC-4735 | Block-12 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-4735 | Block-12 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-4740 | Block-12 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-02-23 17:00
603F-CC-4745 | Block-12 -LT Cable Terminations - LT Panel to IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-02-04 08:00 | 2026-02-19 17:00
603F-CC-4750 | Block-12 -LT Cable Terminations - Inverter to LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-4755 | Block-12 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-02-09 07:00 | 2026-02-09 17:00
603F-CC-4760 | Block-12 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-02-11 07:00 | 2026-02-11 17:00
603F-CC-4765 | Block-12 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-02-19 07:00 | 2026-02-19 17:00
603F-CC-4770 | Block-12 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-19 07:00 | 2026-02-19 17:00
603F-CC-4860 | Block-13 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2025-04-18 07:00 | 2026-01-04 17:00
603F-CC-4860 | Block-13 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5928 | 5928 | 0 | 0 | 1 | 2025-04-18 07:00 | 2026-01-04 17:00
603F-CC-4865 | Block-13 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2025-05-05 07:00 | 2026-01-10 17:00
603F-CC-4870 | Block-13 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-11-20 08:00 | 2026-01-12 17:00
603F-CC-4870 | Block-13 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2025-11-20 08:00 | 2026-01-12 17:00
603F-CC-4875 | Block-13 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2025-11-28 08:00 | 2026-02-18 17:00
603F-CC-4875 | Block-13 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2025-11-28 08:00 | 2026-02-18 17:00
603F-CC-4880 | Block-13 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-05-20 17:00
603F-CC-4880 | Block-13 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-05-20 17:00
603F-CC-4885 | Block-13 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2025-11-15 08:00 | 2026-02-19 17:00
603F-CC-4885 | Block-13 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 5 | 5 | 0 | 0 | 1 | 2025-11-15 08:00 | 2026-02-19 17:00
603F-CC-4890 | Block-13 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2025-12-29 08:00 | 2026-02-09 08:00
603F-CC-4890 | Block-13 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2025-12-29 08:00 | 2026-02-09 08:00
603F-CC-4895 | Block-13 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2025-12-29 12:00 | 2026-02-09 17:00
603F-CC-4895 | Block-13 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 493 | 493 | 0 | 0 | 1 | 2025-12-29 12:00 | 2026-02-09 17:00
603F-CC-4900 | Block-13 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2025-12-30 08:00 | 2026-02-09 17:00
603F-CC-4900 | Block-13 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2025-12-30 08:00 | 2026-02-09 17:00
603F-CC-4905 | Block-13 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 1125 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-02-11 17:00
603F-CC-4910 | Block-13 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 17 | 0 | 0 | 1 | 2026-01-21 11:00 | 2026-02-15 17:00
603F-CC-4910 | Block-13 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 9882 | 0 | 0 | 1 | 2026-01-21 11:00 | 2026-02-15 17:00
603F-CC-4915 | Block-13 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 765 | 9 | 0 | 0.98837 | 2026-05-13 08:00
603F-CC-4920 | Block-13 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2025-11-26 11:00 | 2026-02-18 17:00
603F-CC-4920 | Block-13 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 81 | 0 | 0 | 1 | 2025-11-26 11:00 | 2026-02-18 17:00
603F-CC-4925 | Block-13 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-4925 | Block-13 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 48 | 48 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-4930 | Block-13 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 81 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-19 17:00
603F-CC-4935 | Block-13 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-4935 | Block-13 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-4940 | Block-13 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 0 | 0 | 0 | 2026-02-23 08:00 | 2026-02-23 17:00
603F-CC-4940 | Block-13 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 0 | 0 | 0 | 0 | 2026-02-23 08:00 | 2026-02-23 17:00
603F-CC-4945 | Block-13 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 0 | 1845 | 0 | 0
603F-CC-4945 | Block-13 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-4950 | Block-13 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 495 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-02-21 17:00
603F-CC-4950 | Block-13 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-02-21 17:00
603F-CC-4955 | Block-13 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2025-07-02 07:00 | 2026-02-02 17:00
603F-CC-4955 | Block-13 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-07-02 07:00 | 2026-02-02 17:00
603F-CC-4955 | Block-13 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-07-02 07:00 | 2026-02-02 17:00
603F-CC-4955 | Block-13 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-07-02 07:00 | 2026-02-02 17:00
603F-CC-4960 | Block-13 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-02-02 17:00
603F-CC-4960 | Block-13 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-02-02 17:00
603F-CC-4960 | Block-13 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-02-02 17:00
603F-CC-4965 | Block-13 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-17 08:00 | 2026-02-17 17:00
603F-CC-4965 | Block-13 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-17 08:00 | 2026-02-17 17:00
603F-CC-4970 | Block-13 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-17 08:00 | 2026-02-18 17:00
603F-CC-4970 | Block-13 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-17 08:00 | 2026-02-18 17:00
603F-CC-4975 | Block-13 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-02-07 08:00 | 2026-02-07 17:00
603F-CC-4975 | Block-13 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-07 08:00 | 2026-02-07 17:00
603F-CC-4980 | Block-13 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-01 08:00 | 2026-02-05 17:00
603F-CC-4980 | Block-13 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-01 08:00 | 2026-02-05 17:00
603F-CC-4985 | Block-13 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-02-06 08:00 | 2026-02-18 17:00
603F-CC-4985 | Block-13 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-06 08:00 | 2026-02-18 17:00
603F-CC-4990 | Block-13 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-03 08:00 | 2026-02-05 17:00
603F-CC-4990 | Block-13 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-03 08:00 | 2026-02-05 17:00
603F-CC-4995 | Block-13 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-24 17:00
603F-CC-4995 | Block-13 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-24 17:00
603F-CC-5000 | Block-13 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-5000 | Block-13 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-5005 | Block-13 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-25 17:00
603F-CC-5010 | Block-13 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-5015 | Block-13 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2025-11-24 08:00 | 2026-02-19 17:00
603F-CC-5015 | Block-13 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-24 08:00 | 2026-02-19 17:00
603F-CC-5015 | Block-13 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-24 08:00 | 2026-02-19 17:00
603F-CC-5015 | Block-13 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-24 08:00 | 2026-02-19 17:00
603F-CC-5015 | Block-13 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4 | 3.7 | 0 | 0 | 1 | 2025-11-24 08:00 | 2026-02-19 17:00
603F-CC-5015 | Block-13 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-24 08:00 | 2026-02-19 17:00
603F-CC-5020 | Block-13 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2025-11-22 08:00 | 2025-11-24 17:00
603F-CC-5020 | Block-13 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 12 | 9.63 | 0 | 0 | 1 | 2025-11-22 08:00 | 2025-11-24 17:00
603F-CC-5025 | Block-13 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-03 08:00 | 2026-02-23 17:00
603F-CC-5025 | Block-13 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 4 | 4 | 0 | 0 | 1 | 2025-12-03 08:00 | 2026-02-23 17:00
603F-CC-5030 | Block-13 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-02-23 17:00
603F-CC-5030 | Block-13 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-02-23 17:00
603F-CC-5035 | Block-13 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-19 17:00
603F-CC-5035 | Block-13 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-19 17:00
603F-CC-5040 | Block-13 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-02-17 08:00 | 2026-02-17 17:00
603F-CC-5040 | Block-13 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-17 08:00 | 2026-02-17 17:00
603F-CC-5045 | Block-13 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-5045 | Block-13 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-5050 | Block-13 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 0 | 0 | 0 | 0 | 2026-02-04 08:00 | 2026-02-05 08:00
603F-CC-5050 | Block-13 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 270 | 0 | 0 | 1 | 2026-02-04 08:00 | 2026-02-05 08:00
603F-CC-5055 | Block-13 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2025-11-25 08:00 | 2026-02-18 17:00
603F-CC-5055 | Block-13 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2025-11-25 08:00 | 2026-02-18 17:00
603F-CC-5060 | Block-13 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-19 17:00
603F-CC-5060 | Block-13 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-19 17:00
603F-CC-5065 | Block-13 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-5065 | Block-13 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-5070 | Block-13 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-5070 | Block-13 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-5075 | Block-13 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-5075 | Block-13 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-5080 | Block-13 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-02-22 17:00
603F-CC-5085 | Block-13 -LT Cable Terminations - LT Panel to IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-5090 | Block-13 -LT Cable Terminations - Inverter to LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-5095 | Block-13 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-02-07 07:00 | 2026-02-07 17:00
603F-CC-5100 | Block-13 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-02-19 07:00 | 2026-02-19 17:00
603F-CC-5105 | Block-13 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-02-19 07:00 | 2026-02-19 17:00
603F-CC-5110 | Block-13 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-19 07:00 | 2026-02-19 17:00
603F-CC-5160 | Block-14 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2025-05-03 07:00 | 2026-03-13 17:00
603F-CC-5160 | Block-14 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5916 | 5916 | 0 | 0 | 1 | 2025-05-03 07:00 | 2026-03-13 17:00
603F-CC-5165 | Block-14 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2025-11-22 08:00 | 2026-03-14 17:00
603F-CC-5170 | Block-14 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-08 08:00 | 2026-01-21 17:00
603F-CC-5170 | Block-14 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2025-12-08 08:00 | 2026-01-21 17:00
603F-CC-5175 | Block-14 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2025-12-20 08:00 | 2026-03-10 17:00
603F-CC-5175 | Block-14 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2025-12-20 08:00 | 2026-03-10 17:00
603F-CC-5180 | Block-14 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-05-16 08:00 | 2026-05-16 14:00
603F-CC-5180 | Block-14 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-05-16 08:00 | 2026-05-16 14:00
603F-CC-5185 | Block-14 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2025-12-06 08:00 | 2026-03-27 17:00
603F-CC-5185 | Block-14 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 5 | 5 | 0 | 0 | 1 | 2025-12-06 08:00 | 2026-03-27 17:00
603F-CC-5190 | Block-14 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2026-01-16 08:00 | 2026-05-19 09:00
603F-CC-5190 | Block-14 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 493 | 493 | 0 | 0 | 1 | 2026-01-16 08:00 | 2026-05-19 09:00
603F-CC-5195 | Block-14 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-01-16 12:00 | 2026-05-19 14:00
603F-CC-5195 | Block-14 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 493 | 493 | 0 | 0 | 1 | 2026-01-16 12:00 | 2026-05-19 14:00
603F-CC-5200 | Block-14 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-01-21 08:00 | 2026-05-22 09:00
603F-CC-5200 | Block-14 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2026-01-21 08:00 | 2026-05-22 09:00
603F-CC-5205 | Block-14 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 1125 | 0 | 0 | 1 | 2026-01-23 08:00 | 2026-05-23 10:00
603F-CC-5210 | Block-14 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 17 | 0 | 0 | 1 | 2026-04-01 08:00 | 2026-05-23 14:00
603F-CC-5210 | Block-14 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 9882 | 0 | 0 | 1 | 2026-04-01 08:00 | 2026-05-23 14:00
603F-CC-5215 | Block-14 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 0 | 774 | 0 | 0
603F-CC-5220 | Block-14 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2025-12-12 08:00 | 2026-03-27 17:00
603F-CC-5220 | Block-14 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2025-12-12 08:00 | 2026-03-27 17:00
603F-CC-5225 | Block-14 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-30 09:00
603F-CC-5225 | Block-14 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 48 | 48 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-30 09:00
603F-CC-5230 | Block-14 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 72 | 9 | 0 | 0.88889 | 2026-04-10 10:00
603F-CC-5235 | Block-14 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-5235 | Block-14 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-5240 | Block-14 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-5240 | Block-14 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-5245 | Block-14 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 0 | 1845 | 0 | 0
603F-CC-5245 | Block-14 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-5250 | Block-14 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 0 | 495 | 0 | 0
603F-CC-5250 | Block-14 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-5255 | Block-14 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2025-08-27 08:00 | 2026-02-05 17:00
603F-CC-5255 | Block-14 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-08-27 08:00 | 2026-02-05 17:00
603F-CC-5255 | Block-14 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-08-27 08:00 | 2026-02-05 17:00
603F-CC-5255 | Block-14 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-08-27 08:00 | 2026-02-05 17:00
603F-CC-5260 | Block-14 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-12 17:00
603F-CC-5260 | Block-14 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-12 17:00
603F-CC-5260 | Block-14 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-12 17:00
603F-CC-5265 | Block-14 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-04-07 08:00 | 2026-04-07 11:00
603F-CC-5265 | Block-14 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-07 08:00 | 2026-04-07 11:00
603F-CC-5270 | Block-14 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-04-11 08:00 | 2026-04-11 12:00
603F-CC-5270 | Block-14 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-11 08:00 | 2026-04-11 12:00
603F-CC-5275 | Block-14 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-04-02 08:00 | 2026-04-04 12:00
603F-CC-5275 | Block-14 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-02 08:00 | 2026-04-04 12:00
603F-CC-5280 | Block-14 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-04-04 08:00 | 2026-04-04 14:00
603F-CC-5280 | Block-14 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-04 08:00 | 2026-04-04 14:00
603F-CC-5285 | Block-14 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-03-15 08:00 | 2026-03-16 17:00
603F-CC-5285 | Block-14 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-15 08:00 | 2026-03-16 17:00
603F-CC-5290 | Block-14 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-04-04 08:00 | 2026-04-04 11:00
603F-CC-5290 | Block-14 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-04 08:00 | 2026-04-04 11:00
603F-CC-5295 | Block-14 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-04-11 13:00 | 2026-04-12 09:00
603F-CC-5295 | Block-14 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-11 13:00 | 2026-04-12 09:00
603F-CC-5300 | Block-14 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-04-11 09:00 | 2026-04-12 13:00
603F-CC-5300 | Block-14 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-11 09:00 | 2026-04-12 13:00
603F-CC-5305 | Block-14 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-04-18 08:00 | 2026-04-19 14:00
603F-CC-5310 | Block-14 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-06 08:00 | 2026-04-06 12:00
603F-CC-5315 | Block-14 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-03-27 17:00
603F-CC-5315 | Block-14 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-03-27 17:00
603F-CC-5315 | Block-14 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-03-27 17:00
603F-CC-5315 | Block-14 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-03-27 17:00
603F-CC-5315 | Block-14 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4 | 4 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-03-27 17:00
603F-CC-5315 | Block-14 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-03-27 17:00
603F-CC-5320 | Block-14 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2025-12-10 08:00 | 2026-03-10 17:00
603F-CC-5320 | Block-14 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 12 | 12 | 0 | 0 | 1 | 2025-12-10 08:00 | 2026-03-10 17:00
603F-CC-5325 | Block-14 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-04 08:00 | 2026-04-07 10:00
603F-CC-5325 | Block-14 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 4 | 4 | 0 | 0 | 1 | 2025-12-04 08:00 | 2026-04-07 10:00
603F-CC-5330 | Block-14 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-04-12 12:00
603F-CC-5330 | Block-14 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-04-12 12:00
603F-CC-5335 | Block-14 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-04-15 12:00 | 2026-04-17 12:00
603F-CC-5335 | Block-14 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-04-15 12:00 | 2026-04-17 12:00
603F-CC-5340 | Block-14 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-27 14:00 | 2026-03-28 09:00
603F-CC-5340 | Block-14 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-27 14:00 | 2026-03-28 09:00
603F-CC-5345 | Block-14 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-03-09 12:00 | 2026-03-10 10:00
603F-CC-5345 | Block-14 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-03-09 12:00 | 2026-03-10 10:00
603F-CC-5350 | Block-14 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-02-13 17:00
603F-CC-5350 | Block-14 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-02-13 17:00
603F-CC-5355 | Block-14 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-01-03 08:00 | 2026-03-10 17:00
603F-CC-5355 | Block-14 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 94 | 94 | 0 | 0 | 1 | 2026-01-03 08:00 | 2026-03-10 17:00
603F-CC-5360 | Block-14 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-14 12:00 | 2026-04-15 09:00
603F-CC-5360 | Block-14 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-14 12:00 | 2026-04-15 09:00
603F-CC-5365 | Block-14 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-15 12:00 | 2026-04-15 12:00
603F-CC-5365 | Block-14 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-15 12:00 | 2026-04-15 12:00
603F-CC-5370 | Block-14 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-04-11 08:00 | 2026-04-11 09:00
603F-CC-5370 | Block-14 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-11 08:00 | 2026-04-11 09:00
603F-CC-5375 | Block-14 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-04-09 12:00 | 2026-04-09 12:00
603F-CC-5375 | Block-14 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-09 12:00 | 2026-04-09 12:00
603F-CC-5380 | Block-14 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-20 08:00 | 2026-04-22 12:00
603F-CC-5385 | Block-14 -LT Cable Terminations - LT Panel to IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-04-03 08:00 | 2026-04-15 14:00
603F-CC-5390 | Block-14 -LT Cable Terminations - Inverter to LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-04-03 08:00 | 2026-04-17 12:00
603F-CC-5395 | Block-14 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-05 13:00 | 2026-04-06 12:00
603F-CC-5400 | Block-14 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-12 07:00 | 2026-04-12 17:00
603F-CC-5405 | Block-14 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-11 07:00 | 2026-04-11 17:00
603F-CC-5410 | Block-14 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-15 07:00 | 2026-04-15 17:00
603F-CC-5480 | Block-15 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2025-04-19 07:00 | 2026-02-16 17:00
603F-CC-5480 | Block-15 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5916 | 5916 | 0 | 0 | 1 | 2025-04-19 07:00 | 2026-02-16 17:00
603F-CC-5485 | Block-15 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2025-11-20 08:00 | 2026-02-22 17:00
603F-CC-5490 | Block-15 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2026-01-22 08:00 | 2026-02-14 17:00
603F-CC-5490 | Block-15 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2026-01-22 08:00 | 2026-02-14 17:00
603F-CC-5495 | Block-15 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2026-02-05 08:00 | 2026-02-05 17:00
603F-CC-5495 | Block-15 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2026-02-05 08:00 | 2026-02-05 17:00
603F-CC-5500 | Block-15 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-5500 | Block-15 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-5505 | Block-15 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2025-12-23 08:00 | 2026-02-19 17:00
603F-CC-5505 | Block-15 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 4.86 | 5 | 0 | 0 | 1 | 2025-12-23 08:00 | 2026-02-19 17:00
603F-CC-5510 | Block-15 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2026-01-21 08:00 | 2026-02-24 17:00
603F-CC-5510 | Block-15 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 493 | 493 | 0 | 0 | 1 | 2026-01-21 08:00 | 2026-02-24 17:00
603F-CC-5515 | Block-15 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-01-21 12:00 | 2026-02-24 12:00
603F-CC-5515 | Block-15 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-01-21 12:00 | 2026-02-24 12:00
603F-CC-5520 | Block-15 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-02-02 08:00 | 2026-02-24 17:00
603F-CC-5520 | Block-15 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2026-02-02 08:00 | 2026-02-24 17:00
603F-CC-5525 | Block-15 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 1125 | 0 | 0 | 1 | 2026-01-25 08:00 | 2026-02-05 17:00
603F-CC-5530 | Block-15 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 17 | 0 | 0 | 1 | 2026-02-06 11:00 | 2026-02-25 17:00
603F-CC-5530 | Block-15 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 9882 | 0 | 0 | 1 | 2026-02-06 11:00 | 2026-02-25 17:00
603F-CC-5535 | Block-15 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 765 | 9 | 0 | 0.98837 | 2026-04-09 08:00
603F-CC-5540 | Block-15 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2026-02-08 15:00 | 2026-02-19 17:00
603F-CC-5540 | Block-15 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2026-02-08 15:00 | 2026-02-19 17:00
603F-CC-5545 | Block-15 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-02-22 08:00 | 2026-03-04 17:00
603F-CC-5545 | Block-15 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-02-22 08:00 | 2026-03-04 17:00
603F-CC-5550 | Block-15 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 81 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-04 17:00
603F-CC-5555 | Block-15 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-5555 | Block-15 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-5560 | Block-15 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-03-04 08:00 | 2026-03-04 17:00
603F-CC-5560 | Block-15 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-03-04 08:00 | 2026-03-04 17:00
603F-CC-5565 | Block-15 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 1845 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-04 17:00
603F-CC-5565 | Block-15 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-04 17:00
603F-CC-5570 | Block-15 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 495 | 0 | 0 | 1 | 2026-03-04 08:00 | 2026-03-04 17:00
603F-CC-5570 | Block-15 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-03-04 08:00 | 2026-03-04 17:00
603F-CC-5575 | Block-15 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2025-07-25 07:00 | 2026-02-12 17:00
603F-CC-5575 | Block-15 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-07-25 07:00 | 2026-02-12 17:00
603F-CC-5575 | Block-15 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-07-25 07:00 | 2026-02-12 17:00
603F-CC-5575 | Block-15 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-07-25 07:00 | 2026-02-12 17:00
603F-CC-5580 | Block-15 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2026-01-26 08:00 | 2026-02-18 17:00
603F-CC-5580 | Block-15 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-26 08:00 | 2026-02-18 17:00
603F-CC-5580 | Block-15 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-26 08:00 | 2026-02-18 17:00
603F-CC-5585 | Block-15 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-24 17:00
603F-CC-5585 | Block-15 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-24 17:00
603F-CC-5590 | Block-15 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-24 17:00
603F-CC-5590 | Block-15 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-24 17:00
603F-CC-5595 | Block-15 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-02-20 08:00 | 2026-02-23 17:00
603F-CC-5595 | Block-15 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-20 08:00 | 2026-02-23 17:00
603F-CC-5600 | Block-15 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-20 17:00
603F-CC-5600 | Block-15 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-20 17:00
603F-CC-5605 | Block-15 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-20 17:00
603F-CC-5605 | Block-15 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-20 17:00
603F-CC-5610 | Block-15 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-20 17:00
603F-CC-5610 | Block-15 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-20 17:00
603F-CC-5615 | Block-15 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-5615 | Block-15 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-5620 | Block-15 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-03-06 08:00 | 2026-03-06 17:00
603F-CC-5620 | Block-15 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-06 08:00 | 2026-03-06 08:00
603F-CC-5625 | Block-15 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-5630 | Block-15 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-23 08:00 | 2026-02-23 17:00
603F-CC-5635 | Block-15 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-02-04 08:00 | 2026-03-04 17:00
603F-CC-5635 | Block-15 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-04 08:00 | 2026-03-04 17:00
603F-CC-5635 | Block-15 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-04 08:00 | 2026-03-04 17:00
603F-CC-5635 | Block-15 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-04 08:00 | 2026-03-04 17:00
603F-CC-5635 | Block-15 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2026-02-04 08:00 | 2026-03-04 17:00
603F-CC-5635 | Block-15 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-04 08:00 | 2026-03-04 17:00
603F-CC-5640 | Block-15 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2026-01-01 08:00 | 2026-01-06 17:00
603F-CC-5640 | Block-15 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 9.5 | 10 | 0 | 0 | 1 | 2026-01-01 08:00 | 2026-01-06 17:00
603F-CC-5645 | Block-15 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-05 08:00 | 2026-02-25 17:00
603F-CC-5645 | Block-15 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 4 | 4 | 0 | 0 | 1 | 2025-12-05 08:00 | 2026-02-25 17:00
603F-CC-5650 | Block-15 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-03-02 17:00
603F-CC-5650 | Block-15 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-03-02 17:00
603F-CC-5655 | Block-15 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-5655 | Block-15 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-5660 | Block-15 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-02-25 08:00 | 2026-02-25 17:00
603F-CC-5660 | Block-15 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-25 08:00 | 2026-02-25 17:00
603F-CC-5665 | Block-15 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-02-25 08:00 | 2026-02-25 17:00
603F-CC-5665 | Block-15 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-02-25 08:00 | 2026-02-25 17:00
603F-CC-5670 | Block-15 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2026-02-15 08:00 | 2026-02-15 17:00
603F-CC-5670 | Block-15 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-15 08:00 | 2026-02-15 17:00
603F-CC-5675 | Block-15 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-02-02 08:00 | 2026-02-07 17:00
603F-CC-5675 | Block-15 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 94 | 94 | 0 | 0 | 1 | 2026-02-02 08:00 | 2026-02-07 17:00
603F-CC-5680 | Block-15 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-02-26 17:00
603F-CC-5680 | Block-15 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-02-26 17:00
603F-CC-5685 | Block-15 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-5685 | Block-15 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-5690 | Block-15 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-02-25 08:00 | 2026-02-25 17:00
603F-CC-5690 | Block-15 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-25 08:00 | 2026-02-25 17:00
603F-CC-5695 | Block-15 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-02-22 08:00 | 2026-02-22 17:00
603F-CC-5695 | Block-15 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-22 08:00 | 2026-02-22 17:00
603F-CC-5700 | Block-15 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-03-04 17:00
603F-CC-5705 | Block-15 -LT Cable Terminations - LT Panel to IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-04 17:00
603F-CC-5710 | Block-15 -LT Cable Terminations - Inverter to LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-03-02 17:00
603F-CC-5715 | Block-15 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-03 07:00 | 2026-03-03 17:00
603F-CC-5720 | Block-15 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-03 07:00 | 2026-03-03 17:00
603F-CC-5725 | Block-15 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-03 07:00 | 2026-03-03 17:00
603F-CC-5730 | Block-15 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-03 07:00 | 2026-03-03 17:00
603F-CC-5800 | Block-16 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2025-12-20 08:00 | 2026-04-13 10:00
603F-CC-5800 | Block-16 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5928 | 5928 | 0 | 0 | 1 | 2025-12-20 08:00 | 2026-04-13 10:00
603F-CC-5805 | Block-16 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2026-01-07 08:00 | 2026-04-15 10:00
603F-CC-5810 | Block-16 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-04-14 09:00
603F-CC-5810 | Block-16 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-04-14 09:00
603F-CC-5815 | Block-16 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2026-01-16 08:00 | 2026-04-15 12:00
603F-CC-5815 | Block-16 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2026-01-16 08:00 | 2026-04-15 12:00
603F-CC-5820 | Block-16 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-05-14 08:00 | 2026-05-14 14:00
603F-CC-5820 | Block-16 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-05-14 08:00 | 2026-05-14 14:00
603F-CC-5825 | Block-16 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-04-27 12:00
603F-CC-5825 | Block-16 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 4.86 | 5 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-04-27 12:00
603F-CC-5830 | Block-16 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2026-02-14 08:00 | 2026-05-11 10:00
603F-CC-5830 | Block-16 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-02-14 08:00 | 2026-05-11 10:00
603F-CC-5835 | Block-16 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-02-14 12:00 | 2026-05-11 15:00
603F-CC-5835 | Block-16 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-02-14 12:00 | 2026-05-11 15:00
603F-CC-5840 | Block-16 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-02-22 12:00 | 2026-05-12 15:00
603F-CC-5840 | Block-16 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2026-02-22 12:00 | 2026-05-12 15:00
603F-CC-5845 | Block-16 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 1125 | 0 | 0 | 1 | 2026-02-24 12:00 | 2026-05-13 12:00
603F-CC-5850 | Block-16 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 17 | 0 | 0 | 1 | 2026-02-27 15:00 | 2026-05-15 09:00
603F-CC-5850 | Block-16 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 9882 | 0 | 0 | 1 | 2026-02-27 15:00 | 2026-05-15 09:00
603F-CC-5855 | Block-16 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 0 | 774 | 0 | 0
603F-CC-5860 | Block-16 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-05-06 12:00
603F-CC-5860 | Block-16 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-05-06 12:00
603F-CC-5865 | Block-16 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-04-01 12:00 | 2026-05-06 13:00
603F-CC-5865 | Block-16 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-04-01 12:00 | 2026-05-06 13:00
603F-CC-5870 | Block-16 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 81 | 0 | 0 | 1 | 2026-03-30 14:00 | 2026-05-16 12:00
603F-CC-5875 | Block-16 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-5875 | Block-16 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-5880 | Block-16 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-5880 | Block-16 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-5885 | Block-16 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 0 | 1845 | 0 | 0
603F-CC-5885 | Block-16 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-5890 | Block-16 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 0 | 495 | 0 | 0
603F-CC-5890 | Block-16 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-5895 | Block-16 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2026-01-18 08:00 | 2026-02-08 17:00
603F-CC-5895 | Block-16 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-18 08:00 | 2026-02-08 17:00
603F-CC-5895 | Block-16 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-18 08:00 | 2026-02-08 17:00
603F-CC-5895 | Block-16 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-18 08:00 | 2026-02-08 17:00
603F-CC-5900 | Block-16 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2026-01-13 08:00 | 2026-02-26 17:00
603F-CC-5900 | Block-16 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-13 08:00 | 2026-02-26 17:00
603F-CC-5900 | Block-16 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-13 08:00 | 2026-02-26 17:00
603F-CC-5905 | Block-16 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-04-09 08:00 | 2026-04-09 11:00
603F-CC-5905 | Block-16 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-09 08:00 | 2026-04-09 11:00
603F-CC-5910 | Block-16 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-04-09 08:00 | 2026-04-10 12:00
603F-CC-5910 | Block-16 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-09 08:00 | 2026-04-10 12:00
603F-CC-5915 | Block-16 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-02-14 08:00 | 2026-02-18 17:00
603F-CC-5915 | Block-16 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-14 08:00 | 2026-02-18 17:00
603F-CC-5920 | Block-16 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-27 08:00 | 2026-02-27 17:00
603F-CC-5920 | Block-16 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-27 08:00 | 2026-02-27 17:00
603F-CC-5925 | Block-16 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-02-22 08:00 | 2026-02-26 17:00
603F-CC-5925 | Block-16 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-22 08:00 | 2026-02-26 17:00
603F-CC-5930 | Block-16 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-27 08:00 | 2026-02-27 17:00
603F-CC-5930 | Block-16 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-27 08:00 | 2026-02-27 17:00
603F-CC-5935 | Block-16 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-04-16 10:00 | 2026-04-16 13:00
603F-CC-5935 | Block-16 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-16 10:00 | 2026-04-16 13:00
603F-CC-5940 | Block-16 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-04-17 12:00 | 2026-04-17 12:00
603F-CC-5940 | Block-16 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-17 12:00 | 2026-04-17 12:00
603F-CC-5945 | Block-16 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-04-22 08:00 | 2026-04-23 14:00
603F-CC-5950 | Block-16 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-13 08:00 | 2026-04-13 12:00
603F-CC-5955 | Block-16 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-04-28 10:00
603F-CC-5955 | Block-16 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-04-28 10:00
603F-CC-5955 | Block-16 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-04-28 10:00
603F-CC-5955 | Block-16 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-04-28 10:00
603F-CC-5955 | Block-16 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-04-28 10:00
603F-CC-5955 | Block-16 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-04-28 10:00
603F-CC-5960 | Block-16 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-27 17:00
603F-CC-5960 | Block-16 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 12.9 | 13 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-27 17:00
603F-CC-5965 | Block-16 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-07 08:00 | 2026-04-07 10:00
603F-CC-5965 | Block-16 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 4 | 4 | 0 | 0 | 1 | 2025-12-07 08:00 | 2026-04-07 10:00
603F-CC-5970 | Block-16 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-04-12 12:00
603F-CC-5970 | Block-16 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-04-12 12:00
603F-CC-5975 | Block-16 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-04-14 12:00 | 2026-04-20 12:00
603F-CC-5975 | Block-16 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-04-14 12:00 | 2026-04-20 12:00
603F-CC-5980 | Block-16 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-5980 | Block-16 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-5985 | Block-16 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-04-09 12:00 | 2026-04-11 12:00
603F-CC-5985 | Block-16 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-04-09 12:00 | 2026-04-11 12:00
603F-CC-5990 | Block-16 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2026-02-14 08:00 | 2026-02-14 17:00
603F-CC-5990 | Block-16 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-14 08:00 | 2026-02-14 17:00
603F-CC-5995 | Block-16 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-04-21 10:00
603F-CC-5995 | Block-16 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 94 | 94 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-04-21 10:00
603F-CC-6000 | Block-16 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-12 12:00 | 2026-04-12 14:00
603F-CC-6000 | Block-16 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-12 12:00 | 2026-04-12 14:00
603F-CC-6005 | Block-16 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-11 12:00 | 2026-04-11 12:00
603F-CC-6005 | Block-16 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-11 12:00 | 2026-04-11 12:00
603F-CC-6010 | Block-16 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-04-11 08:00 | 2026-04-11 12:00
603F-CC-6010 | Block-16 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-11 08:00 | 2026-04-11 12:00
603F-CC-6015 | Block-16 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-04-20 08:00 | 2026-04-20 15:00
603F-CC-6015 | Block-16 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-20 08:00 | 2026-04-20 15:00
603F-CC-6020 | Block-16 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-12 12:00 | 2026-04-22 10:00
603F-CC-6025 | Block-16 -LT Cable Terminations - LT Panel to IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-04-15 08:00 | 2026-04-15 09:00
603F-CC-6030 | Block-16 -LT Cable Terminations - Inverter to LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-04-03 10:00 | 2026-04-28 10:00
603F-CC-6035 | Block-16 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-03 14:00 | 2026-04-03 14:00
603F-CC-6040 | Block-16 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-10 07:00 | 2026-04-10 17:00
603F-CC-6045 | Block-16 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-13 07:00 | 2026-04-13 17:00
603F-CC-6050 | Block-16 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-13 13:00 | 2026-04-13 14:00
603F-CC-6120 | Block-17 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2025-11-29 08:00 | 2026-01-13 17:00
603F-CC-6120 | Block-17 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5844 | 5844 | 0 | 0 | 1 | 2025-11-29 08:00 | 2026-01-13 17:00
603F-CC-6125 | Block-17 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2025-12-09 08:00 | 2026-01-18 17:00
603F-CC-6130 | Block-17 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-20 08:00 | 2026-02-18 17:00
603F-CC-6130 | Block-17 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2025-12-20 08:00 | 2026-02-18 17:00
603F-CC-6135 | Block-17 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2025-12-30 08:00 | 2026-01-18 17:00
603F-CC-6135 | Block-17 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2025-12-30 08:00 | 2026-01-18 17:00
603F-CC-6140 | Block-17 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-6140 | Block-17 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-6145 | Block-17 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2025-12-26 08:00 | 2026-02-18 17:00
603F-CC-6145 | Block-17 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 4.86 | 5 | 0 | 0 | 1 | 2025-12-26 08:00 | 2026-02-18 17:00
603F-CC-6150 | Block-17 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2026-01-21 08:00 | 2026-02-25 17:00
603F-CC-6150 | Block-17 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-01-21 08:00 | 2026-02-25 17:00
603F-CC-6155 | Block-17 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-01-21 12:00 | 2026-02-25 12:00
603F-CC-6155 | Block-17 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-01-21 12:00 | 2026-02-25 12:00
603F-CC-6160 | Block-17 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-01-23 12:00 | 2026-02-25 12:00
603F-CC-6160 | Block-17 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2026-01-23 12:00 | 2026-02-25 12:00
603F-CC-6165 | Block-17 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 1125 | 0 | 0 | 1 | 2026-01-23 08:00 | 2026-01-26 17:00
603F-CC-6170 | Block-17 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 17 | 0 | 0 | 1 | 2026-01-27 15:00 | 2026-03-03 17:00
603F-CC-6170 | Block-17 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 9882 | 0 | 0 | 1 | 2026-01-27 15:00 | 2026-03-03 17:00
603F-CC-6175 | Block-17 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 0 | 774 | 0 | 0
603F-CC-6180 | Block-17 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2025-12-26 15:00 | 2026-02-18 17:00
603F-CC-6180 | Block-17 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2025-12-26 15:00 | 2026-02-18 17:00
603F-CC-6185 | Block-17 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-03-02 17:00
603F-CC-6185 | Block-17 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-03-02 17:00
603F-CC-6190 | Block-17 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 81 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-03-02 17:00
603F-CC-6195 | Block-17 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-6195 | Block-17 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-6200 | Block-17 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-6200 | Block-17 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-6205 | Block-17 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 0 | 1845 | 0 | 0
603F-CC-6205 | Block-17 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-6210 | Block-17 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 180 | 315 | 0 | 0.36364 | 2026-03-04 08:00
603F-CC-6210 | Block-17 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 15 | 24 | 0 | 0.38462 | 2026-03-04 08:00
603F-CC-6215 | Block-17 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2025-11-29 08:00 | 2025-12-16 17:00
603F-CC-6215 | Block-17 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-29 08:00 | 2025-12-16 17:00
603F-CC-6215 | Block-17 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-29 08:00 | 2025-12-16 17:00
603F-CC-6215 | Block-17 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-29 08:00 | 2025-12-16 17:00
603F-CC-6220 | Block-17 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2025-11-26 08:00 | 2025-12-29 17:00
603F-CC-6220 | Block-17 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-26 08:00 | 2025-12-29 17:00
603F-CC-6220 | Block-17 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-26 08:00 | 2025-12-29 17:00
603F-CC-6225 | Block-17 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-01-19 08:00 | 2026-01-20 17:00
603F-CC-6225 | Block-17 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-19 08:00 | 2026-01-20 17:00
603F-CC-6230 | Block-17 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-02-13 17:00
603F-CC-6230 | Block-17 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-02-13 17:00
603F-CC-6235 | Block-17 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-01-03 08:00 | 2026-01-10 17:00
603F-CC-6235 | Block-17 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-03 08:00 | 2026-01-10 17:00
603F-CC-6240 | Block-17 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-07 08:00 | 2026-02-07 08:00
603F-CC-6240 | Block-17 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-25 08:00 | 2026-01-26 08:00
603F-CC-6245 | Block-17 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-02-05 17:00
603F-CC-6245 | Block-17 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-02-05 17:00
603F-CC-6250 | Block-17 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-01-26 08:00 | 2026-01-26 17:00
603F-CC-6250 | Block-17 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-26 08:00 | 2026-01-26 17:00
603F-CC-6255 | Block-17 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-02-23 08:00 | 2026-02-23 17:00
603F-CC-6255 | Block-17 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-23 08:00 | 2026-02-23 17:00
603F-CC-6260 | Block-17 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-02-23 08:00 | 2026-02-23 08:00
603F-CC-6260 | Block-17 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-23 08:00 | 2026-02-23 08:00
603F-CC-6265 | Block-17 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-04 08:00 | 2026-03-04 17:00
603F-CC-6270 | Block-17 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-6275 | Block-17 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-01-09 08:00 | 2026-02-19 17:00
603F-CC-6275 | Block-17 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-09 08:00 | 2026-02-19 17:00
603F-CC-6275 | Block-17 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-09 08:00 | 2026-02-19 17:00
603F-CC-6275 | Block-17 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-09 08:00 | 2026-02-19 17:00
603F-CC-6275 | Block-17 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2026-01-09 08:00 | 2026-02-19 17:00
603F-CC-6275 | Block-17 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-09 08:00 | 2026-02-19 17:00
603F-CC-6280 | Block-17 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2026-01-03 08:00 | 2026-01-20 17:00
603F-CC-6280 | Block-17 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 10.8 | 11 | 0 | 0 | 1 | 2026-01-03 08:00 | 2026-01-20 17:00
603F-CC-6285 | Block-17 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-03 08:00 | 2026-02-26 17:00
603F-CC-6285 | Block-17 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 4 | 4 | 0 | 0 | 1 | 2025-12-03 08:00 | 2026-02-26 17:00
603F-CC-6290 | Block-17 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-03-02 17:00
603F-CC-6290 | Block-17 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-03-02 17:00
603F-CC-6295 | Block-17 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-02-23 08:00 | 2026-02-23 17:00
603F-CC-6295 | Block-17 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-02-23 08:00 | 2026-02-23 17:00
603F-CC-6300 | Block-17 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-01-06 08:00 | 2026-01-06 17:00
603F-CC-6300 | Block-17 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-06 08:00 | 2026-01-06 17:00
603F-CC-6305 | Block-17 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 11844 | 0 | 0 | 1 | 2026-01-25 08:00 | 2026-02-22 17:00
603F-CC-6305 | Block-17 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-01-25 08:00 | 2026-02-22 17:00
603F-CC-6310 | Block-17 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2025-12-28 08:00 | 2025-12-28 17:00
603F-CC-6310 | Block-17 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-28 08:00 | 2025-12-28 17:00
603F-CC-6315 | Block-17 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-01-17 17:00
603F-CC-6315 | Block-17 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 96 | 96 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-01-17 17:00
603F-CC-6320 | Block-17 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 0 | 0 | 0 | 0 | 2026-01-25 08:00 | 2026-01-25 17:00
603F-CC-6320 | Block-17 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-25 08:00 | 2026-01-25 17:00
603F-CC-6325 | Block-17 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-25 08:00 | 2026-01-25 17:00
603F-CC-6325 | Block-17 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-01-25 08:00 | 2026-01-25 17:00
603F-CC-6330 | Block-17 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-6330 | Block-17 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-6335 | Block-17 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-6335 | Block-17 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-6340 | Block-17 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-02-21 17:00
603F-CC-6345 | Block-17 -LT Cable Terminations - LT Panel to IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-23 17:00
603F-CC-6350 | Block-17 -LT Cable Terminations - Inverter to LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-03-01 08:00 | 2026-03-01 17:00
603F-CC-6355 | Block-17 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-02-14 07:00 | 2026-03-14 17:00
603F-CC-6360 | Block-17 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-02-14 07:00 | 2026-02-14 17:00
603F-CC-6365 | Block-17 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-04 07:00 | 2026-03-04 17:00
603F-CC-6370 | Block-17 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-03 07:00 | 2026-03-03 17:00
603F-CC-6440 | Block-18 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 2000 | 1998 | 0 | 0 | 1 | 2025-12-14 08:00 | 2026-03-21 13:38
603F-CC-6440 | Block-18 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5416 | 5416 | 0 | 0 | 1 | 2025-12-14 08:00 | 2026-03-30 12:22
603F-CC-6445 | Block-18 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2025-12-17 10:10 | 2026-04-06 12:00
603F-CC-6450 | Block-18 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2026-01-11 08:00 | 2026-03-30 10:00
603F-CC-6450 | Block-18 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2026-01-11 08:00 | 2026-03-30 10:00
603F-CC-6455 | Block-18 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2026-01-21 08:00 | 2026-02-18 17:00
603F-CC-6455 | Block-18 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2026-01-21 08:00 | 2026-02-18 17:00
603F-CC-6460 | Block-18 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-05-14 08:00 | 2026-05-14 14:00
603F-CC-6460 | Block-18 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-05-14 08:00 | 2026-05-14 14:00
603F-CC-6465 | Block-18 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-04-27 11:00
603F-CC-6465 | Block-18 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 4.86 | 5 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-04-27 11:00
603F-CC-6470 | Block-18 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 8712 | 288 | 0 | 0.968 | 2026-02-05 08:00
603F-CC-6470 | Block-18 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 494 | 478 | 16 | 0 | 0.96761 | 2026-02-05 08:00
603F-CC-6475 | Block-18 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2178 | 702 | 0 | 0.75625 | 2026-02-05 12:00
603F-CC-6475 | Block-18 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 494 | 478 | 16 | 0 | 0.96761 | 2026-02-05 12:00
603F-CC-6480 | Block-18 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2079 | 1890 | 0 | 0.52381 | 2026-02-08 12:00
603F-CC-6480 | Block-18 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 449 | 38 | 0 | 0.92197 | 2026-02-08 12:00
603F-CC-6485 | Block-18 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 729 | 396 | 0 | 0.648 | 2026-02-09 08:00
603F-CC-6490 | Block-18 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 15 | 2 | 0 | 0.88235 | 2026-02-15 12:00
603F-CC-6490 | Block-18 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 8604 | 1278 | 0 | 0.87067 | 2026-02-15 12:00
603F-CC-6495 | Block-18 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 0 | 774 | 0 | 0
603F-CC-6500 | Block-18 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2026-01-22 15:00 | 2026-04-12 14:00
603F-CC-6500 | Block-18 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2026-01-22 15:00 | 2026-04-12 14:00
603F-CC-6505 | Block-18 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-04-09 12:00 | 2026-04-28 10:00
603F-CC-6505 | Block-18 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-04-09 12:00 | 2026-04-28 10:00
603F-CC-6510 | Block-18 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 72 | 9 | 0 | 0.88889 | 2026-04-17 11:00
603F-CC-6515 | Block-18 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-6515 | Block-18 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-6520 | Block-18 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-6520 | Block-18 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-6525 | Block-18 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 0 | 1845 | 0 | 0
603F-CC-6525 | Block-18 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-6530 | Block-18 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 0 | 495 | 0 | 0
603F-CC-6530 | Block-18 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-6535 | Block-18 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2025-12-31 08:00 | 2026-01-26 17:00
603F-CC-6535 | Block-18 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-31 08:00 | 2026-01-26 17:00
603F-CC-6535 | Block-18 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-31 08:00 | 2026-01-26 17:00
603F-CC-6535 | Block-18 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-31 08:00 | 2026-01-26 17:00
603F-CC-6540 | Block-18 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2025-12-08 08:00 | 2026-02-07 17:00
603F-CC-6540 | Block-18 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-08 08:00 | 2026-02-07 17:00
603F-CC-6540 | Block-18 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-08 08:00 | 2026-02-07 17:00
603F-CC-6545 | Block-18 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-6545 | Block-18 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-6550 | Block-18 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-04-17 08:00 | 2026-04-17 12:00
603F-CC-6550 | Block-18 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-17 08:00 | 2026-04-17 12:00
603F-CC-6555 | Block-18 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-02-09 08:00 | 2026-02-11 17:00
603F-CC-6555 | Block-18 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-09 08:00 | 2026-02-11 17:00
603F-CC-6560 | Block-18 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-09 08:00 | 2026-02-11 17:00
603F-CC-6560 | Block-18 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-09 08:00 | 2026-02-11 17:00
603F-CC-6565 | Block-18 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-02-15 08:00 | 2026-02-15 17:00
603F-CC-6565 | Block-18 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-15 08:00 | 2026-02-15 17:00
603F-CC-6570 | Block-18 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-09 08:00 | 2026-02-09 17:00
603F-CC-6570 | Block-18 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-09 08:00 | 2026-02-09 17:00
603F-CC-6575 | Block-18 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-04-14 10:00 | 2026-04-14 13:00
603F-CC-6575 | Block-18 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-14 10:00 | 2026-04-14 13:00
603F-CC-6580 | Block-18 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-04-13 13:00 | 2026-04-14 10:00
603F-CC-6580 | Block-18 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-13 13:00 | 2026-04-14 10:00
603F-CC-6585 | Block-18 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-04-23 08:00 | 2026-04-23 14:00
603F-CC-6590 | Block-18 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-18 17:00
603F-CC-6595 | Block-18 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-01-31 08:00 | 2026-04-28 11:00
603F-CC-6595 | Block-18 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-31 08:00 | 2026-04-28 11:00
603F-CC-6595 | Block-18 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-31 08:00 | 2026-04-28 11:00
603F-CC-6595 | Block-18 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-31 08:00 | 2026-04-28 11:00
603F-CC-6595 | Block-18 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2026-01-31 08:00 | 2026-04-28 11:00
603F-CC-6595 | Block-18 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-31 08:00 | 2026-04-28 11:00
603F-CC-6600 | Block-18 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2026-01-29 08:00 | 2026-03-27 17:00
603F-CC-6600 | Block-18 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 10.8 | 11 | 0 | 0 | 1 | 2026-01-29 08:00 | 2026-03-27 17:00
603F-CC-6605 | Block-18 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-04 08:00 | 2026-04-07 12:00
603F-CC-6605 | Block-18 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 4 | 4 | 0 | 0 | 1 | 2025-12-04 08:00 | 2026-04-07 12:00
603F-CC-6610 | Block-18 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-04-12 10:00
603F-CC-6610 | Block-18 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-04-12 10:00
603F-CC-6615 | Block-18 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-04-14 08:00 | 2026-04-20 14:00
603F-CC-6615 | Block-18 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-04-14 08:00 | 2026-04-20 14:00
603F-CC-6620 | Block-18 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-6620 | Block-18 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-6625 | Block-18 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-31 17:00
603F-CC-6625 | Block-18 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-31 17:00
603F-CC-6630 | Block-18 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-01-30 17:00
603F-CC-6630 | Block-18 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-01-30 17:00
603F-CC-6635 | Block-18 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-04-09 08:00 | 2026-04-18 11:00
603F-CC-6635 | Block-18 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 96 | 96 | 0 | 0 | 1 | 2026-04-09 08:00 | 2026-04-18 11:00
603F-CC-6640 | Block-18 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-31 08:00 | 2026-03-31 17:00
603F-CC-6640 | Block-18 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-31 08:00 | 2026-03-31 17:00
603F-CC-6645 | Block-18 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-31 08:00 | 2026-03-31 17:00
603F-CC-6645 | Block-18 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-31 08:00 | 2026-03-31 17:00
603F-CC-6650 | Block-18 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-03-31 08:00 | 2026-03-31 14:00
603F-CC-6650 | Block-18 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-31 08:00 | 2026-03-31 14:00
603F-CC-6655 | Block-18 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-04-20 08:00 | 2026-04-20 15:00
603F-CC-6655 | Block-18 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-20 08:00 | 2026-04-20 15:00
603F-CC-6660 | Block-18 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-12 10:00 | 2026-04-22 10:00
603F-CC-6665 | Block-18 -LT Cable Terminations - LT Panel to IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-04-13 08:00 | 2026-04-15 14:00
603F-CC-6670 | Block-18 -LT Cable Terminations - Inverter to LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-04-12 09:00 | 2026-04-28 14:00
603F-CC-6675 | Block-18 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-13 15:00 | 2026-04-13 15:00
603F-CC-6680 | Block-18 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-14 15:00 | 2026-04-14 15:00
603F-CC-6685 | Block-18 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-13 07:00 | 2026-04-13 17:00
603F-CC-6690 | Block-18 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-13 07:00 | 2026-04-13 17:00
603F-CC-6760 | Block-19 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2025-11-30 08:00 | 2026-04-10 14:00
603F-CC-6760 | Block-19 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5844 | 5844 | 0 | 0 | 1 | 2025-11-30 08:00 | 2026-04-10 14:00
603F-CC-6765 | Block-19 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2025-12-05 08:00 | 2026-05-06 10:00
603F-CC-6770 | Block-19 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-02-05 17:00
603F-CC-6770 | Block-19 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-02-05 17:00
603F-CC-6775 | Block-19 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2026-01-01 08:00 | 2026-03-23 17:00
603F-CC-6775 | Block-19 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2026-01-01 08:00 | 2026-03-23 17:00
603F-CC-6780 | Block-19 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-05-10 08:00 | 2026-05-10 14:00
603F-CC-6780 | Block-19 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-05-10 08:00 | 2026-05-10 14:00
603F-CC-6785 | Block-19 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2026-01-15 08:00 | 2026-04-18 12:00
603F-CC-6785 | Block-19 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 4.86 | 5 | 0 | 0 | 1 | 2026-01-15 08:00 | 2026-04-18 12:00
603F-CC-6790 | Block-19 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2026-02-14 08:00 | 2026-05-06 12:00
603F-CC-6790 | Block-19 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-02-14 08:00 | 2026-05-06 12:00
603F-CC-6795 | Block-19 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-02-14 12:00 | 2026-05-06 10:00
603F-CC-6795 | Block-19 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-02-14 12:00 | 2026-05-06 10:00
603F-CC-6800 | Block-19 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-02-14 12:00 | 2026-05-06 10:00
603F-CC-6800 | Block-19 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2026-02-14 12:00 | 2026-05-06 10:00
603F-CC-6805 | Block-19 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 1125 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-05-06 14:00
603F-CC-6810 | Block-19 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 17 | 0 | 0 | 1 | 2026-02-18 11:00 | 2026-05-07 12:00
603F-CC-6810 | Block-19 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 9882 | 0 | 0 | 1 | 2026-02-18 11:00 | 2026-05-07 12:00
603F-CC-6815 | Block-19 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 0 | 774 | 0 | 0
603F-CC-6820 | Block-19 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2026-01-15 15:00 | 2026-03-26 17:00
603F-CC-6820 | Block-19 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2026-01-15 15:00 | 2026-03-26 17:00
603F-CC-6825 | Block-19 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-01-27 15:00 | 2026-03-26 17:00
603F-CC-6825 | Block-19 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-01-27 15:00 | 2026-03-26 17:00
603F-CC-6830 | Block-19 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 81 | 0 | 0 | 1 | 2026-03-24 08:00 | 2026-05-15 10:00
603F-CC-6835 | Block-19 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-6835 | Block-19 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-6840 | Block-19 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-6840 | Block-19 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-6845 | Block-19 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 0 | 1845 | 0 | 0
603F-CC-6845 | Block-19 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-6850 | Block-19 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 0 | 495 | 0 | 0
603F-CC-6850 | Block-19 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-6855 | Block-19 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-01-30 17:00
603F-CC-6855 | Block-19 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-01-30 17:00
603F-CC-6855 | Block-19 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-01-30 17:00
603F-CC-6855 | Block-19 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-01-30 17:00
603F-CC-6860 | Block-19 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2026-01-11 08:00 | 2026-02-05 17:00
603F-CC-6860 | Block-19 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-11 08:00 | 2026-02-05 17:00
603F-CC-6860 | Block-19 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-11 08:00 | 2026-02-05 17:00
603F-CC-6865 | Block-19 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-11 08:00 | 2026-03-11 17:00
603F-CC-6865 | Block-19 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-11 08:00 | 2026-03-11 17:00
603F-CC-6870 | Block-19 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-04-02 08:00 | 2026-04-03 17:00
603F-CC-6870 | Block-19 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-02 08:00 | 2026-04-03 17:00
603F-CC-6875 | Block-19 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-02-07 08:00 | 2026-02-18 17:00
603F-CC-6875 | Block-19 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-07 08:00 | 2026-02-18 17:00
603F-CC-6880 | Block-19 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-02-16 17:00
603F-CC-6880 | Block-19 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-02-16 17:00
603F-CC-6885 | Block-19 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-10 17:00
603F-CC-6885 | Block-19 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-10 17:00
603F-CC-6890 | Block-19 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-02-16 17:00
603F-CC-6890 | Block-19 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-02-16 17:00
603F-CC-6895 | Block-19 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-04-03 08:00 | 2026-04-03 12:00
603F-CC-6895 | Block-19 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-03 08:00 | 2026-04-03 12:00
603F-CC-6900 | Block-19 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-04-02 12:00 | 2026-04-03 09:00
603F-CC-6900 | Block-19 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-02 12:00 | 2026-04-03 09:00
603F-CC-6905 | Block-19 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-04-03 08:00 | 2026-04-03 17:00
603F-CC-6910 | Block-19 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-22 08:00 | 2026-03-22 17:00
603F-CC-6915 | Block-19 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-01-27 08:00 | 2026-03-01 17:00
603F-CC-6915 | Block-19 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-27 08:00 | 2026-03-01 17:00
603F-CC-6915 | Block-19 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-27 08:00 | 2026-03-01 17:00
603F-CC-6915 | Block-19 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-27 08:00 | 2026-03-01 17:00
603F-CC-6915 | Block-19 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2026-01-27 08:00 | 2026-03-01 17:00
603F-CC-6915 | Block-19 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-27 08:00 | 2026-03-01 17:00
603F-CC-6920 | Block-19 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2026-01-19 08:00 | 2026-03-01 17:00
603F-CC-6920 | Block-19 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 10.8 | 11 | 0 | 0 | 1 | 2026-01-19 08:00 | 2026-03-01 17:00
603F-CC-6925 | Block-19 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-05 08:00 | 2026-03-27 17:00
603F-CC-6925 | Block-19 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 4 | 4 | 0 | 0 | 1 | 2025-12-05 08:00 | 2026-03-27 17:00
603F-CC-6930 | Block-19 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-23 17:00
603F-CC-6930 | Block-19 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-23 17:00
603F-CC-6935 | Block-19 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-6935 | Block-19 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-6940 | Block-19 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-02-16 17:00
603F-CC-6940 | Block-19 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-02-16 17:00
603F-CC-6945 | Block-19 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-6945 | Block-19 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-6950 | Block-19 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2026-02-04 08:00 | 2026-02-05 17:00
603F-CC-6950 | Block-19 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-04 08:00 | 2026-02-05 17:00
603F-CC-6955 | Block-19 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-04-07 10:00
603F-CC-6955 | Block-19 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 96 | 96 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-04-07 10:00
603F-CC-6960 | Block-19 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-6960 | Block-19 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-6965 | Block-19 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-6965 | Block-19 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-6970 | Block-19 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-6970 | Block-19 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-6975 | Block-19 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-6975 | Block-19 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-6980 | Block-19 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-03 08:00 | 2026-04-03 17:00
603F-CC-6985 | Block-19 -LT Cable Terminations - LT Panel to IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-27 08:00
603F-CC-6990 | Block-19 -LT Cable Terminations - Inverter to LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-27 17:00
603F-CC-6995 | Block-19 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-02-21 07:00 | 2026-02-21 17:00
603F-CC-7000 | Block-19 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-23 07:00 | 2026-03-23 17:00
603F-CC-7005 | Block-19 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-26 07:00 | 2026-03-26 17:00
603F-CC-7010 | Block-19 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-27 07:00 | 2026-03-27 17:00
603F-CC-7080 | Block-20 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2025-11-25 08:00 | 2026-01-13 17:00
603F-CC-7080 | Block-20 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5844 | 5844 | 0 | 0 | 1 | 2025-11-25 08:00 | 2026-01-13 17:00
603F-CC-7085 | Block-20 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2025-11-29 08:00 | 2026-01-18 17:00
603F-CC-7090 | Block-20 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-22 08:00 | 2026-01-18 17:00
603F-CC-7090 | Block-20 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2025-12-22 08:00 | 2026-01-18 17:00
603F-CC-7095 | Block-20 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2025-12-24 08:00 | 2026-01-13 17:00
603F-CC-7095 | Block-20 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2025-12-24 08:00 | 2026-01-13 17:00
603F-CC-7100 | Block-20 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-01-18 08:00 | 2026-05-14 11:00
603F-CC-7100 | Block-20 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-01-18 08:00 | 2026-05-14 11:00
603F-CC-7105 | Block-20 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-04-08 14:00
603F-CC-7105 | Block-20 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 4.86 | 5 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-04-08 14:00
603F-CC-7110 | Block-20 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2026-01-03 08:00 | 2026-05-18 11:00
603F-CC-7110 | Block-20 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 493 | 493 | 0 | 0 | 1 | 2026-01-03 08:00 | 2026-05-18 11:00
603F-CC-7115 | Block-20 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-01-03 12:00 | 2026-05-18 09:00
603F-CC-7115 | Block-20 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 493 | 493 | 0 | 0 | 1 | 2026-01-03 12:00 | 2026-05-18 09:00
603F-CC-7120 | Block-20 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2115 | 135 | 0 | 0.94 | 2026-01-07 12:00
603F-CC-7120 | Block-20 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 458 | 29 | 0 | 0.94045 | 2026-01-07 12:00
603F-CC-7125 | Block-20 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 468 | 657 | 0 | 0.416 | 2026-01-09 08:00
603F-CC-7130 | Block-20 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 14 | 2.5 | 0 | 0.84848 | 2026-04-05 12:00
603F-CC-7130 | Block-20 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 7785 | 2097 | 0 | 0.7878 | 2026-04-05 12:00
603F-CC-7135 | Block-20 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 0 | 774 | 0 | 0
603F-CC-7140 | Block-20 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2026-01-08 08:00 | 2026-03-26 17:00
603F-CC-7140 | Block-20 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2026-01-08 08:00 | 2026-03-26 17:00
603F-CC-7145 | Block-20 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-03-26 09:00 | 2026-04-11 11:00
603F-CC-7145 | Block-20 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-03-26 09:00 | 2026-04-11 11:00
603F-CC-7150 | Block-20 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 63 | 18 | 0 | 0.77778 | 2026-04-12 13:00
603F-CC-7155 | Block-20 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-7155 | Block-20 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-7160 | Block-20 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-7160 | Block-20 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-7165 | Block-20 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 0 | 1845 | 0 | 0
603F-CC-7165 | Block-20 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-7170 | Block-20 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 0 | 495 | 0 | 0
603F-CC-7170 | Block-20 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-7175 | Block-20 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2025-11-30 08:00 | 2025-12-13 17:00
603F-CC-7175 | Block-20 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-30 08:00 | 2025-12-13 17:00
603F-CC-7175 | Block-20 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-30 08:00 | 2025-12-13 17:00
603F-CC-7175 | Block-20 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-30 08:00 | 2025-12-13 17:00
603F-CC-7180 | Block-20 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2025-11-25 08:00 | 2025-12-22 17:00
603F-CC-7180 | Block-20 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-25 08:00 | 2025-12-22 17:00
603F-CC-7180 | Block-20 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-25 08:00 | 2025-12-22 17:00
603F-CC-7185 | Block-20 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-01-09 08:00 | 2026-01-16 17:00
603F-CC-7185 | Block-20 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-09 08:00 | 2026-01-16 17:00
603F-CC-7190 | Block-20 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-01-30 17:00
603F-CC-7190 | Block-20 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-01-30 17:00
603F-CC-7195 | Block-20 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-02-20 17:00
603F-CC-7195 | Block-20 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-02-20 17:00
603F-CC-7200 | Block-20 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-01-16 08:00 | 2026-01-16 17:00
603F-CC-7200 | Block-20 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-16 08:00 | 2026-01-16 17:00
603F-CC-7205 | Block-20 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2025-12-15 08:00 | 2025-12-27 17:00
603F-CC-7205 | Block-20 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-15 08:00 | 2025-12-27 17:00
603F-CC-7210 | Block-20 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-01-16 08:00 | 2026-01-16 08:00
603F-CC-7210 | Block-20 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-16 08:00 | 2026-01-16 08:00
603F-CC-7215 | Block-20 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-04-12 08:00 | 2026-04-12 17:00
603F-CC-7215 | Block-20 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-12 08:00 | 2026-04-12 17:00
603F-CC-7220 | Block-20 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-04-12 08:00 | 2026-04-12 12:00
603F-CC-7220 | Block-20 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-12 08:00 | 2026-04-12 08:00
603F-CC-7225 | Block-20 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-04-13 08:00 | 2026-04-13 14:00
603F-CC-7230 | Block-20 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-20 08:00 | 2026-02-20 12:00
603F-CC-7235 | Block-20 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-02-06 08:00 | 2026-03-23 17:00
603F-CC-7235 | Block-20 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-06 08:00 | 2026-03-23 17:00
603F-CC-7235 | Block-20 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-06 08:00 | 2026-03-23 17:00
603F-CC-7235 | Block-20 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-06 08:00 | 2026-03-23 17:00
603F-CC-7235 | Block-20 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2026-02-06 08:00 | 2026-03-23 17:00
603F-CC-7235 | Block-20 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-06 08:00 | 2026-03-23 17:00
603F-CC-7240 | Block-20 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2026-01-09 08:00 | 2026-02-06 17:00
603F-CC-7240 | Block-20 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 10.8 | 11 | 0 | 0 | 1 | 2026-01-09 08:00 | 2026-02-06 17:00
603F-CC-7245 | Block-20 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-08 08:00 | 2026-04-12 10:00
603F-CC-7245 | Block-20 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 4 | 4 | 0 | 0 | 1 | 2025-12-08 08:00 | 2026-04-12 10:00
603F-CC-7250 | Block-20 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-04-12 10:00
603F-CC-7250 | Block-20 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-04-12 10:00
603F-CC-7255 | Block-20 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-7255 | Block-20 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-7260 | Block-20 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-01-06 08:00 | 2026-01-06 17:00
603F-CC-7260 | Block-20 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-06 08:00 | 2026-01-06 17:00
603F-CC-7265 | Block-20 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-7265 | Block-20 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-7270 | Block-20 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2025-12-27 08:00 | 2025-12-27 17:00
603F-CC-7270 | Block-20 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-27 08:00 | 2025-12-27 17:00
603F-CC-7275 | Block-20 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-01-06 08:00 | 2026-04-06 10:00
603F-CC-7275 | Block-20 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 96 | 96 | 0 | 0 | 1 | 2026-01-06 08:00 | 2026-04-06 10:00
603F-CC-7280 | Block-20 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-7280 | Block-20 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-7285 | Block-20 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-7285 | Block-20 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-7290 | Block-20 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-7290 | Block-20 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-7295 | Block-20 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-7295 | Block-20 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-7300 | Block-20 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-12 10:00 | 2026-04-14 14:00
603F-CC-7305 | Block-20 -LT Cable Terminations - LT Panel to IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-7310 | Block-20 -LT Cable Terminations - Inverter to LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-26 17:00
603F-CC-7315 | Block-20 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-02-08 07:00 | 2026-02-08 17:00
603F-CC-7320 | Block-20 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-10 07:00 | 2026-04-10 17:00
603F-CC-7325 | Block-20 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-11 07:00 | 2026-04-11 17:00
603F-CC-7330 | Block-20 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-11 07:00 | 2026-04-11 17:00
603F-CC-7400 | Block-21 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2025-11-24 08:00 | 2026-01-26 17:00
603F-CC-7400 | Block-21 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5844 | 5844 | 0 | 0 | 1 | 2025-11-24 08:00 | 2026-01-26 17:00
603F-CC-7405 | Block-21 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2025-12-02 08:00 | 2026-01-28 17:00
603F-CC-7410 | Block-21 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-07 08:00 | 2026-01-27 17:00
603F-CC-7410 | Block-21 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2025-12-07 08:00 | 2026-01-27 17:00
603F-CC-7415 | Block-21 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-01-05 17:00
603F-CC-7415 | Block-21 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-01-05 17:00
603F-CC-7420 | Block-21 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-05-11 08:00 | 2026-05-11 14:00
603F-CC-7420 | Block-21 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-05-11 08:00 | 2026-05-11 14:00
603F-CC-7425 | Block-21 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2025-12-26 08:00 | 2026-01-28 17:00
603F-CC-7425 | Block-21 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 4.87 | 5 | 0 | 0 | 1 | 2025-12-26 08:00 | 2026-01-28 17:00
603F-CC-7430 | Block-21 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 8874 | 126 | 0 | 0.986 | 2026-01-12 08:00
603F-CC-7430 | Block-21 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 493 | 486 | 7 | 0 | 0.9858 | 2026-01-12 08:00
603F-CC-7435 | Block-21 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2223 | 27 | 0 | 0.988 | 2026-01-12 12:00
603F-CC-7435 | Block-21 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 493 | 486 | 7 | 0 | 0.9858 | 2026-01-12 12:00
603F-CC-7440 | Block-21 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2088 | 162 | 0 | 0.928 | 2026-01-17 12:00
603F-CC-7440 | Block-21 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 451 | 36 | 0 | 0.92608 | 2026-01-17 12:00
603F-CC-7445 | Block-21 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 756 | 369 | 0 | 0.672 | 2026-01-19 08:00
603F-CC-7450 | Block-21 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 14 | 2.5 | 0 | 0.84848 | 2026-02-19 08:00
603F-CC-7450 | Block-21 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 8064 | 1818 | 0 | 0.81603 | 2026-02-19 08:00
603F-CC-7455 | Block-21 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 0 | 774 | 0 | 0
603F-CC-7460 | Block-21 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2025-12-29 15:00 | 2026-03-05 17:00
603F-CC-7460 | Block-21 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2025-12-29 15:00 | 2026-03-05 17:00
603F-CC-7465 | Block-21 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-01-26 15:00 | 2026-01-27 15:00
603F-CC-7465 | Block-21 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-01-26 15:00 | 2026-01-27 15:00
603F-CC-7470 | Block-21 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 54 | 27 | 0 | 0.66667 | 2026-04-09 10:00
603F-CC-7475 | Block-21 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-7475 | Block-21 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-7480 | Block-21 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-7480 | Block-21 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-7485 | Block-21 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 0 | 1845 | 0 | 0
603F-CC-7485 | Block-21 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-7490 | Block-21 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 0 | 495 | 0 | 0
603F-CC-7490 | Block-21 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-7495 | Block-21 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2025-12-15 08:00 | 2026-01-15 17:00
603F-CC-7495 | Block-21 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-15 08:00 | 2026-01-15 17:00
603F-CC-7495 | Block-21 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-15 08:00 | 2026-01-15 17:00
603F-CC-7495 | Block-21 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-15 08:00 | 2026-01-15 17:00
603F-CC-7500 | Block-21 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2025-12-16 08:00 | 2026-01-19 17:00
603F-CC-7500 | Block-21 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-16 08:00 | 2026-01-19 17:00
603F-CC-7500 | Block-21 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-16 08:00 | 2026-01-19 17:00
603F-CC-7505 | Block-21 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-7505 | Block-21 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-7510 | Block-21 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-04-14 08:00 | 2026-04-14 12:00
603F-CC-7510 | Block-21 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-14 08:00 | 2026-04-14 12:00
603F-CC-7515 | Block-21 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-01-06 08:00 | 2026-01-15 17:00
603F-CC-7515 | Block-21 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-06 08:00 | 2026-01-15 17:00
603F-CC-7520 | Block-21 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-01-21 08:00 | 2026-01-21 17:00
603F-CC-7520 | Block-21 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-21 08:00 | 2026-01-21 17:00
603F-CC-7525 | Block-21 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-01-28 08:00 | 2026-03-23 17:00
603F-CC-7525 | Block-21 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-28 08:00 | 2026-03-23 17:00
603F-CC-7530 | Block-21 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-01-21 08:00 | 2026-01-21 17:00
603F-CC-7530 | Block-21 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-21 08:00 | 2026-01-21 17:00
603F-CC-7535 | Block-21 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-04-12 10:00 | 2026-04-12 13:00
603F-CC-7535 | Block-21 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-12 10:00 | 2026-04-12 13:00
603F-CC-7540 | Block-21 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-04-12 10:00 | 2026-04-12 14:00
603F-CC-7540 | Block-21 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-12 10:00 | 2026-04-12 14:00
603F-CC-7545 | Block-21 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-04-13 08:00 | 2026-04-13 14:00
603F-CC-7550 | Block-21 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-7555 | Block-21 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-03-02 17:00
603F-CC-7555 | Block-21 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-03-02 17:00
603F-CC-7555 | Block-21 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-03-02 17:00
603F-CC-7555 | Block-21 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-03-02 17:00
603F-CC-7555 | Block-21 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-03-02 17:00
603F-CC-7555 | Block-21 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-03-02 17:00
603F-CC-7560 | Block-21 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2025-12-30 08:00 | 2026-01-05 17:00
603F-CC-7560 | Block-21 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 9.3 | 9 | 0 | 0 | 1 | 2025-12-30 08:00 | 2026-01-05 17:00
603F-CC-7565 | Block-21 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-06 08:00 | 2026-04-12 10:00
603F-CC-7565 | Block-21 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 4 | 4 | 0 | 0 | 1 | 2025-12-06 08:00 | 2026-04-12 10:00
603F-CC-7570 | Block-21 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-04-12 10:00
603F-CC-7570 | Block-21 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-04-12 10:00
603F-CC-7575 | Block-21 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-30 08:00 | 2026-04-07 12:00
603F-CC-7575 | Block-21 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-03-30 08:00 | 2026-04-07 12:00
603F-CC-7580 | Block-21 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-01-22 08:00 | 2026-01-22 17:00
603F-CC-7580 | Block-21 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-22 08:00 | 2026-01-22 17:00
603F-CC-7585 | Block-21 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-03-05 08:00 | 2026-03-05 17:00
603F-CC-7585 | Block-21 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-03-05 08:00 | 2026-03-05 17:00
603F-CC-7590 | Block-21 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2026-01-26 08:00 | 2026-01-26 17:00
603F-CC-7590 | Block-21 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-26 08:00 | 2026-01-26 17:00
603F-CC-7595 | Block-21 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-01-09 17:00
603F-CC-7595 | Block-21 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-01-09 17:00
603F-CC-7600 | Block-21 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-7600 | Block-21 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-7605 | Block-21 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-7605 | Block-21 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-7610 | Block-21 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-7610 | Block-21 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-7615 | Block-21 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-02-11 08:00 | 2026-02-11 17:00
603F-CC-7615 | Block-21 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-11 08:00 | 2026-02-11 17:00
603F-CC-7620 | Block-21 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-12 10:00 | 2026-04-14 14:00
603F-CC-7625 | Block-21 -LT Cable Terminations - LT Panel to IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-04-03 17:00
603F-CC-7630 | Block-21 -LT Cable Terminations - Inverter to LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-04 17:00
603F-CC-7635 | Block-21 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-02-19 07:00 | 2026-02-19 17:00
603F-CC-7640 | Block-21 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-06 07:00 | 2026-04-06 17:00
603F-CC-7645 | Block-21 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-06 07:00 | 2026-04-06 17:00
603F-CC-7650 | Block-21 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-11 07:00 | 2026-04-11 17:00
603F-CC-7720 | Block-22 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2025-11-25 08:00 | 2026-01-03 17:00
603F-CC-7720 | Block-22 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5844 | 5844 | 0 | 0 | 1 | 2025-11-25 08:00 | 2026-01-03 17:00
603F-CC-7725 | Block-22 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2025-12-03 08:00 | 2026-01-05 17:00
603F-CC-7730 | Block-22 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-11 08:00 | 2025-12-27 17:00
603F-CC-7730 | Block-22 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2025-12-11 08:00 | 2025-12-27 17:00
603F-CC-7735 | Block-22 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2025-12-16 08:00 | 2025-12-27 12:19
603F-CC-7735 | Block-22 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2025-12-16 08:00 | 2025-12-27 12:19
603F-CC-7740 | Block-22 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-7740 | Block-22 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-7745 | Block-22 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2025-12-30 08:00 | 2026-02-19 17:00
603F-CC-7745 | Block-22 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 4.87 | 5 | 0 | 0 | 1 | 2025-12-30 08:00 | 2026-02-19 17:00
603F-CC-7750 | Block-22 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2026-01-01 08:00 | 2026-01-30
603F-CC-7750 | Block-22 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 493 | 493 | 0 | 0 | 1 | 2026-01-01 08:00 | 2026-01-30
603F-CC-7755 | Block-22 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-01-01 12:00 | 2026-02-24 12:00
603F-CC-7755 | Block-22 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 493 | 493 | 0 | 0 | 1 | 2026-01-01 12:00 | 2026-02-24 12:00
603F-CC-7760 | Block-22 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-01-01 12:00 | 2026-02-18 17:00
603F-CC-7760 | Block-22 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2026-01-01 12:00 | 2026-02-18 17:00
603F-CC-7765 | Block-22 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 1125 | 0 | 0 | 1 | 2026-01-03 08:00 | 2026-01-30 17:00
603F-CC-7770 | Block-22 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 17 | 0 | 0 | 1 | 2026-02-02 11:00 | 2026-02-19 17:00
603F-CC-7770 | Block-22 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 9882 | 0 | 0 | 1 | 2026-02-02 11:00 | 2026-02-19 17:00
603F-CC-7775 | Block-22 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 774 | 0 | 0 | 1 | 2026-03-06 08:00 | 2026-05-13 09:00
603F-CC-7780 | Block-22 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2025-12-30 15:00 | 2026-02-19 17:00
603F-CC-7780 | Block-22 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2025-12-30 15:00 | 2026-02-19 17:00
603F-CC-7785 | Block-22 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-01-26 08:00 | 2026-01-26 17:00
603F-CC-7785 | Block-22 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-01-26 08:00 | 2026-01-26 17:00
603F-CC-7790 | Block-22 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 81 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-02-26 17:00
603F-CC-7795 | Block-22 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-7795 | Block-22 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-7800 | Block-22 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-02-28 08:00 | 2026-03-06 17:00
603F-CC-7800 | Block-22 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-02-28 08:00 | 2026-03-06 17:00
603F-CC-7805 | Block-22 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 0 | 0 | 0 | 0 | 2026-03-03 08:00 | 2026-03-04 17:00
603F-CC-7805 | Block-22 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 0 | 0 | 0 | 0 | 2026-03-03 08:00 | 2026-03-04 17:00
603F-CC-7810 | Block-22 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 495 | 0 | 0 | 1 | 2026-03-04 08:00 | 2026-03-04 17:00
603F-CC-7810 | Block-22 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-03-04 08:00 | 2026-03-04 17:00
603F-CC-7815 | Block-22 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2025-12-31 08:00 | 2026-01-14 17:00
603F-CC-7815 | Block-22 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-31 08:00 | 2026-01-14 17:00
603F-CC-7815 | Block-22 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-31 08:00 | 2026-01-14 17:00
603F-CC-7815 | Block-22 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-31 08:00 | 2026-01-14 17:00
603F-CC-7820 | Block-22 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2026-01-01 08:00 | 2026-01-26 17:00
603F-CC-7820 | Block-22 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-01 08:00 | 2026-01-26 17:00
603F-CC-7820 | Block-22 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-01 08:00 | 2026-01-26 17:00
603F-CC-7825 | Block-22 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-05 08:00 | 2026-02-08 17:00
603F-CC-7825 | Block-22 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-15 08:00 | 2026-02-19 17:00
603F-CC-7830 | Block-22 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-24 17:00
603F-CC-7830 | Block-22 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-24 17:00
603F-CC-7835 | Block-22 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-01-23 08:00 | 2026-01-25 17:00
603F-CC-7835 | Block-22 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-23 08:00 | 2026-01-25 17:00
603F-CC-7840 | Block-22 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-01-29 08:00 | 2026-01-29 17:00
603F-CC-7840 | Block-22 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-29 08:00 | 2026-01-29 17:00
603F-CC-7845 | Block-22 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-02-01 08:00 | 2026-02-19 17:00
603F-CC-7845 | Block-22 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-01 08:00 | 2026-02-19 17:00
603F-CC-7850 | Block-22 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-01-29 08:00 | 2026-01-29 17:00
603F-CC-7850 | Block-22 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-07 08:00 | 2026-02-11 17:00
603F-CC-7855 | Block-22 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-7855 | Block-22 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-7860 | Block-22 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-03-06 08:00 | 2026-03-06 17:00
603F-CC-7860 | Block-22 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-06 08:00 | 2026-03-06 08:00
603F-CC-7865 | Block-22 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-7870 | Block-22 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-28 08:00 | 2026-02-28 17:00
603F-CC-7875 | Block-22 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-02-19 17:00
603F-CC-7875 | Block-22 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-02-19 17:00
603F-CC-7875 | Block-22 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-02-19 17:00
603F-CC-7875 | Block-22 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-02-19 17:00
603F-CC-7875 | Block-22 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-02-19 17:00
603F-CC-7875 | Block-22 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-02-19 17:00
603F-CC-7880 | Block-22 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-01-06 17:00
603F-CC-7880 | Block-22 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 9.3 | 9 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-01-06 17:00
603F-CC-7885 | Block-22 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-04 08:00 | 2026-02-25 17:00
603F-CC-7885 | Block-22 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 4 | 4 | 0 | 0 | 1 | 2025-12-04 08:00 | 2026-02-25 17:00
603F-CC-7890 | Block-22 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-01-13 08:00 | 2026-03-02 17:00
603F-CC-7890 | Block-22 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-01-13 08:00 | 2026-03-02 17:00
603F-CC-7895 | Block-22 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 0 | 0 | 0 | 0 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-7895 | Block-22 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 0 | 0 | 0 | 0 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-7900 | Block-22 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-02-04 08:00 | 2026-02-04 17:00
603F-CC-7900 | Block-22 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-04 08:00 | 2026-02-04 17:00
603F-CC-7905 | Block-22 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-02-20 08:00 | 2026-02-20 17:00
603F-CC-7905 | Block-22 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-02-20 08:00 | 2026-02-20 17:00
603F-CC-7910 | Block-22 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2026-01-26 08:00 | 2026-01-26 17:00
603F-CC-7910 | Block-22 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-26 08:00 | 2026-01-26 17:00
603F-CC-7915 | Block-22 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2025-12-30 12:19 | 2026-01-09 17:00
603F-CC-7915 | Block-22 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 94 | 94 | 0 | 0 | 1 | 2025-12-30 12:19 | 2026-01-09 17:00
603F-CC-7920 | Block-22 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-02-21 17:00
603F-CC-7920 | Block-22 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-02-21 17:00
603F-CC-7925 | Block-22 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-22 08:00 | 2026-02-22 17:00
603F-CC-7925 | Block-22 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-22 08:00 | 2026-02-22 17:00
603F-CC-7930 | Block-22 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-7930 | Block-22 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-7935 | Block-22 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-7935 | Block-22 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-7940 | Block-22 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-02-26 17:00
603F-CC-7945 | Block-22 -LT Cable Terminations - LT Panel to IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-7950 | Block-22 -LT Cable Terminations - Inverter to LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-03-04 08:00 | 2026-03-04 17:00
603F-CC-7955 | Block-22 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-02-16 07:00 | 2026-02-16 17:00
603F-CC-7960 | Block-22 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 0 | 0 | 0 | 0 | 2026-03-03 07:00 | 2026-03-03 17:00
603F-CC-7965 | Block-22 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 0 | 0 | 0 | 0 | 2026-03-04 07:00 | 2026-03-04 17:00
603F-CC-7970 | Block-22 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 0 | 0 | 0 | 0 | 2026-03-04 07:00 | 2026-03-04 17:00
603F-CC-8040 | Block-23 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2025-11-26 08:00 | 2026-01-24 17:00
603F-CC-8040 | Block-23 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5844 | 5844 | 0 | 0 | 1 | 2025-11-26 08:00 | 2026-01-24 17:00
603F-CC-8045 | Block-23 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2025-12-06 08:00 | 2026-01-24 17:00
603F-CC-8050 | Block-23 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-07 08:00 | 2026-01-17 17:00
603F-CC-8050 | Block-23 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2025-12-07 08:00 | 2026-01-17 17:00
603F-CC-8055 | Block-23 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-01-17 17:00
603F-CC-8055 | Block-23 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-01-17 17:00
603F-CC-8060 | Block-23 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-05-13 08:00 | 2026-05-13 14:00
603F-CC-8060 | Block-23 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-05-13 08:00 | 2026-05-13 14:00
603F-CC-8065 | Block-23 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-03-23 17:00
603F-CC-8065 | Block-23 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 4.87 | 5 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-03-23 17:00
603F-CC-8070 | Block-23 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-05-07 14:00
603F-CC-8070 | Block-23 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-05-07 14:00
603F-CC-8075 | Block-23 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-01-10 12:00 | 2026-05-07 12:00
603F-CC-8075 | Block-23 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-01-10 12:00 | 2026-05-07 12:00
603F-CC-8080 | Block-23 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-01-19 08:00 | 2026-05-15 12:00
603F-CC-8080 | Block-23 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2026-01-19 08:00 | 2026-05-15 12:00
603F-CC-8085 | Block-23 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 1125 | 0 | 0 | 1 | 2026-01-21 08:00 | 2026-05-15 15:00
603F-CC-8090 | Block-23 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 17 | 0 | 0 | 1 | 2026-02-23 08:00 | 2026-05-21 10:00
603F-CC-8090 | Block-23 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 9882 | 0 | 0 | 1 | 2026-02-23 08:00 | 2026-05-21 10:00
603F-CC-8095 | Block-23 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 0 | 774 | 0 | 0
603F-CC-8100 | Block-23 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2026-01-02 16:00 | 2026-03-23 17:00
603F-CC-8100 | Block-23 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2026-01-02 16:00 | 2026-03-23 17:00
603F-CC-8105 | Block-23 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-02-03 15:00 | 2026-04-23 14:00
603F-CC-8105 | Block-23 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-02-03 15:00 | 2026-04-23 14:00
603F-CC-8110 | Block-23 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 72 | 9 | 0 | 0.88889 | 2026-03-24 08:00
603F-CC-8115 | Block-23 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-8115 | Block-23 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-8120 | Block-23 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-8120 | Block-23 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-8125 | Block-23 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 0 | 1845 | 0 | 0
603F-CC-8125 | Block-23 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-8130 | Block-23 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 0 | 495 | 0 | 0
603F-CC-8130 | Block-23 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-8135 | Block-23 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2025-12-22 08:00 | 2026-01-18 17:00
603F-CC-8135 | Block-23 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-22 08:00 | 2026-01-18 17:00
603F-CC-8135 | Block-23 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-22 08:00 | 2026-01-18 17:00
603F-CC-8135 | Block-23 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-22 08:00 | 2026-01-18 17:00
603F-CC-8140 | Block-23 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2026-01-04 08:00 | 2026-01-29 17:00
603F-CC-8140 | Block-23 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-04 08:00 | 2026-01-29 17:00
603F-CC-8140 | Block-23 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-04 08:00 | 2026-01-29 17:00
603F-CC-8145 | Block-23 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-8145 | Block-23 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-8150 | Block-23 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-04-03 08:00 | 2026-04-03 17:00
603F-CC-8150 | Block-23 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-03 08:00 | 2026-04-03 17:00
603F-CC-8155 | Block-23 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-01-13 08:00 | 2026-01-20 17:00
603F-CC-8155 | Block-23 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-13 08:00 | 2026-01-20 17:00
603F-CC-8160 | Block-23 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-8160 | Block-23 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-8165 | Block-23 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-8165 | Block-23 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-8170 | Block-23 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-8170 | Block-23 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-8175 | Block-23 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-04-03 08:00 | 2026-04-03 12:00
603F-CC-8175 | Block-23 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-03 08:00 | 2026-04-03 12:00
603F-CC-8180 | Block-23 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-04-02 12:00 | 2026-04-03 09:00
603F-CC-8180 | Block-23 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-02 12:00 | 2026-04-03 09:00
603F-CC-8185 | Block-23 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-04-03 08:00 | 2026-04-03 17:00
603F-CC-8190 | Block-23 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-8195 | Block-23 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-02-02 17:00
603F-CC-8195 | Block-23 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-02-02 17:00
603F-CC-8195 | Block-23 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-02-02 17:00
603F-CC-8195 | Block-23 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-02-02 17:00
603F-CC-8195 | Block-23 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-02-02 17:00
603F-CC-8195 | Block-23 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-02-02 17:00
603F-CC-8200 | Block-23 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2026-01-09 08:00 | 2026-02-01 17:00
603F-CC-8200 | Block-23 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 9.3 | 9 | 0 | 0 | 1 | 2026-01-09 08:00 | 2026-02-01 17:00
603F-CC-8205 | Block-23 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-08 08:00 | 2026-03-27 17:00
603F-CC-8205 | Block-23 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 4 | 4 | 0 | 0 | 1 | 2025-12-08 08:00 | 2026-03-27 17:00
603F-CC-8210 | Block-23 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-23 17:00
603F-CC-8210 | Block-23 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-23 17:00
603F-CC-8215 | Block-23 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-8215 | Block-23 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-8220 | Block-23 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-02-01 08:00 | 2026-02-01 17:00
603F-CC-8220 | Block-23 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-01 08:00 | 2026-02-01 17:00
603F-CC-8225 | Block-23 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-8225 | Block-23 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-8230 | Block-23 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2026-01-24 08:00 | 2026-01-24 17:00
603F-CC-8230 | Block-23 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-24 08:00 | 2026-01-24 17:00
603F-CC-8235 | Block-23 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-03-23 17:00
603F-CC-8235 | Block-23 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-01-02 08:00 | 2026-03-23 17:00
603F-CC-8240 | Block-23 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-8240 | Block-23 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-8245 | Block-23 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-8245 | Block-23 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-8250 | Block-23 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-04-23 10:00
603F-CC-8250 | Block-23 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-04-23 10:00
603F-CC-8255 | Block-23 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-04-23 13:00
603F-CC-8255 | Block-23 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-04-23 13:00
603F-CC-8260 | Block-23 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-03 08:00 | 2026-04-03 17:00
603F-CC-8265 | Block-23 -LT Cable Terminations - LT Panel to IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-8270 | Block-23 -LT Cable Terminations - Inverter to LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-26 08:00
603F-CC-8275 | Block-23 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-22 13:00 | 2026-03-23 12:00
603F-CC-8280 | Block-23 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-24 07:00 | 2026-03-24 17:00
603F-CC-8285 | Block-23 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-26 07:00 | 2026-03-26 17:00
603F-CC-8290 | Block-23 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-27 07:00 | 2026-03-27 17:00
603F-CC-8360 | Block-24 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2025-11-28 08:00 | 2026-03-31 17:00
603F-CC-8360 | Block-24 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5844 | 5844 | 0 | 0 | 1 | 2025-11-28 08:00 | 2026-03-31 17:00
603F-CC-8365 | Block-24 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2025-12-16 08:00 | 2026-03-31 09:00
603F-CC-8370 | Block-24 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-15 08:00 | 2026-02-07 17:00
603F-CC-8370 | Block-24 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2025-12-15 08:00 | 2026-02-07 17:00
603F-CC-8375 | Block-24 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2025-12-31 08:00 | 2026-02-07 17:00
603F-CC-8375 | Block-24 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2025-12-31 08:00 | 2026-02-07 17:00
603F-CC-8380 | Block-24 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-05-13 08:00 | 2026-05-20 11:00
603F-CC-8380 | Block-24 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-05-13 08:00 | 2026-05-20 11:00
603F-CC-8385 | Block-24 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2026-01-29 08:00 | 2026-04-05 10:00
603F-CC-8385 | Block-24 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 4.87 | 5 | 0 | 0 | 1 | 2026-01-29 08:00 | 2026-04-05 10:00
603F-CC-8390 | Block-24 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2026-02-15 08:00 | 2026-05-09 10:00
603F-CC-8390 | Block-24 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 493 | 493 | 0 | 0 | 1 | 2026-02-15 08:00 | 2026-05-09 10:00
603F-CC-8395 | Block-24 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-02-15 12:00 | 2026-05-09 15:00
603F-CC-8395 | Block-24 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 493 | 493 | 0 | 0 | 1 | 2026-02-15 12:00 | 2026-05-09 15:00
603F-CC-8400 | Block-24 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-02-23 08:00 | 2026-05-09 12:00
603F-CC-8400 | Block-24 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2026-02-23 08:00 | 2026-05-09 12:00
603F-CC-8405 | Block-24 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 1125 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-05-12 11:00
603F-CC-8410 | Block-24 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 17 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-05-16 10:00
603F-CC-8410 | Block-24 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 9882 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-05-16 10:00
603F-CC-8415 | Block-24 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 0 | 774 | 0 | 0
603F-CC-8420 | Block-24 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2026-01-29 12:00 | 2026-03-02 17:00
603F-CC-8420 | Block-24 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2026-01-29 12:00 | 2026-03-02 17:00
603F-CC-8425 | Block-24 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-03-01 08:00 | 2026-04-08 14:00
603F-CC-8425 | Block-24 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-03-01 08:00 | 2026-04-08 14:00
603F-CC-8430 | Block-24 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 81 | 0 | 0 | 1 | 2026-04-17 08:00 | 2026-05-18 14:00
603F-CC-8435 | Block-24 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-8435 | Block-24 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-8440 | Block-24 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-8440 | Block-24 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-8445 | Block-24 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 0 | 1845 | 0 | 0
603F-CC-8445 | Block-24 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-8450 | Block-24 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 0 | 495 | 0 | 0
603F-CC-8450 | Block-24 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-8455 | Block-24 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-02-14 17:00
603F-CC-8455 | Block-24 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-02-14 17:00
603F-CC-8455 | Block-24 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-02-14 17:00
603F-CC-8455 | Block-24 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-02-14 17:00
603F-CC-8460 | Block-24 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 292 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-03-05 17:00
603F-CC-8460 | Block-24 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 0 | 0 | 0 | 0 | 2026-02-24 08:00 | 2026-03-05 17:00
603F-CC-8460 | Block-24 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 0 | 0 | 0 | 0 | 2026-02-24 08:00 | 2026-03-05 17:00
603F-CC-8465 | Block-24 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-8465 | Block-24 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-8470 | Block-24 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-04-13 08:00 | 2026-04-14 12:00
603F-CC-8470 | Block-24 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-13 08:00 | 2026-04-14 12:00
603F-CC-8475 | Block-24 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-02-14 08:00 | 2026-02-18 17:00
603F-CC-8475 | Block-24 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-14 08:00 | 2026-02-18 17:00
603F-CC-8480 | Block-24 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-02-26 17:00
603F-CC-8480 | Block-24 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-02-26 17:00
603F-CC-8485 | Block-24 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-03-15 08:00 | 2026-03-23 17:00
603F-CC-8485 | Block-24 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-15 08:00 | 2026-03-23 17:00
603F-CC-8490 | Block-24 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-02-26 17:00
603F-CC-8490 | Block-24 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-02-26 17:00
603F-CC-8495 | Block-24 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-04-12 08:00 | 2026-04-12 10:00
603F-CC-8495 | Block-24 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-12 08:00 | 2026-04-12 10:00
603F-CC-8500 | Block-24 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-04-12 08:00 | 2026-04-12 14:00
603F-CC-8500 | Block-24 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-04-12 08:00 | 2026-04-12 14:00
603F-CC-8505 | Block-24 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-04-13 12:00 | 2026-04-13 15:00
603F-CC-8510 | Block-24 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-09 08:00 | 2026-04-09 12:00
603F-CC-8515 | Block-24 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-03-30 10:00
603F-CC-8515 | Block-24 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-03-30 10:00
603F-CC-8515 | Block-24 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-03-30 10:00
603F-CC-8515 | Block-24 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-03-30 10:00
603F-CC-8515 | Block-24 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-03-30 10:00
603F-CC-8515 | Block-24 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-16 08:00 | 2026-03-30 10:00
603F-CC-8520 | Block-24 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2026-02-11 08:00 | 2026-03-01 17:00
603F-CC-8520 | Block-24 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 10.6 | 11 | 0 | 0 | 1 | 2026-02-11 08:00 | 2026-03-01 17:00
603F-CC-8525 | Block-24 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-07 08:00 | 2026-04-12 10:00
603F-CC-8525 | Block-24 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 4 | 4 | 0 | 0 | 1 | 2025-12-07 08:00 | 2026-04-12 10:00
603F-CC-8530 | Block-24 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-04-12 10:00
603F-CC-8530 | Block-24 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-04-12 10:00
603F-CC-8535 | Block-24 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-31 08:00 | 2026-04-08 12:00
603F-CC-8535 | Block-24 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-03-31 08:00 | 2026-04-08 12:00
603F-CC-8540 | Block-24 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-06 08:00 | 2026-03-06 17:00
603F-CC-8540 | Block-24 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-06 08:00 | 2026-03-06 17:00
603F-CC-8545 | Block-24 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-30 12:00
603F-CC-8545 | Block-24 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-30 12:00
603F-CC-8550 | Block-24 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-8550 | Block-24 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-02 17:00
603F-CC-8555 | Block-24 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-02-07 08:00 | 2026-03-01 17:00
603F-CC-8555 | Block-24 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 94 | 94 | 0 | 0 | 1 | 2026-02-07 08:00 | 2026-03-01 17:00
603F-CC-8560 | Block-24 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-27 08:00 | 2026-03-30 17:00
603F-CC-8560 | Block-24 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-27 08:00 | 2026-03-30 17:00
603F-CC-8565 | Block-24 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-24 08:00 | 2026-03-24 17:00
603F-CC-8565 | Block-24 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-24 08:00 | 2026-03-24 17:00
603F-CC-8570 | Block-24 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-03-27 08:00 | 2026-03-27 17:00
603F-CC-8570 | Block-24 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-27 08:00 | 2026-03-27 17:00
603F-CC-8575 | Block-24 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-03-27 08:00 | 2026-03-27 17:00
603F-CC-8575 | Block-24 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-27 08:00 | 2026-03-27 17:00
603F-CC-8580 | Block-24 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-12 10:00 | 2026-04-14 14:00
603F-CC-8585 | Block-24 -LT Cable Terminations - LT Panel to IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-03-30 08:00 | 2026-04-09 14:00
603F-CC-8590 | Block-24 -LT Cable Terminations - Inverter to LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-03-23 10:00 | 2026-03-24 17:00
603F-CC-8595 | Block-24 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-18 07:00 | 2026-03-18 17:00
603F-CC-8600 | Block-24 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-06 07:00 | 2026-04-06 17:00
603F-CC-8605 | Block-24 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-04-06 07:00 | 2026-04-06 17:00
603F-CC-8610 | Block-24 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-04-11 09:00 | 2026-04-11 12:00
603F-CC-8680 | Block-25 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2025-05-27 07:03 | 2026-03-14 17:00
603F-CC-8680 | Block-25 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5928 | 5928 | 0 | 0 | 1 | 2025-05-27 07:03 | 2026-03-14 17:00
603F-CC-8685 | Block-25 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2714.8 | 2718 | 0 | 0 | 1 | 2025-11-27 08:00 | 2026-03-16 17:00
603F-CC-8690 | Block-25 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-03-14 17:00
603F-CC-8690 | Block-25 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-03-14 17:00
603F-CC-8695 | Block-25 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-03-14 17:00
603F-CC-8695 | Block-25 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-03-14 17:00
603F-CC-8700 | Block-25 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-03-18 08:00 | 2026-03-18 17:00
603F-CC-8700 | Block-25 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-03-18 08:00 | 2026-03-18 17:00
603F-CC-8705 | Block-25 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-22 17:00
603F-CC-8705 | Block-25 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 4.87 | 5 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-22 17:00
603F-CC-8710 | Block-25 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-03-16 17:00
603F-CC-8710 | Block-25 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-03-16 17:00
603F-CC-8715 | Block-25 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-02-24 12:00 | 2026-03-16 12:00
603F-CC-8715 | Block-25 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-02-24 12:00 | 2026-03-16 12:00
603F-CC-8720 | Block-25 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-02-27 12:00 | 2026-03-17 12:00
603F-CC-8720 | Block-25 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2026-02-27 12:00 | 2026-03-17 12:00
603F-CC-8725 | Block-25 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 1125 | 0 | 0 | 1 | 2026-02-28 12:00 | 2026-03-16 12:00
603F-CC-8730 | Block-25 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 17 | 0 | 0 | 1 | 2026-03-01 12:00 | 2026-03-17 17:00
603F-CC-8730 | Block-25 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 9882 | 0 | 0 | 1 | 2026-03-01 12:00 | 2026-03-17 17:00
603F-CC-8735 | Block-25 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 513 | 261 | 0 | 0.66279 | 2026-05-13 08:00
603F-CC-8740 | Block-25 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2026-03-13 15:00 | 2026-03-22 17:00
603F-CC-8740 | Block-25 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2026-03-13 15:00 | 2026-03-22 17:00
603F-CC-8745 | Block-25 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-03-22 15:00 | 2026-03-23 17:00
603F-CC-8745 | Block-25 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-03-22 15:00 | 2026-03-23 17:00
603F-CC-8750 | Block-25 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 81 | 0 | 0 | 1 | 2026-03-22 15:00 | 2026-03-23 17:00
603F-CC-8755 | Block-25 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-8755 | Block-25 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-8760 | Block-25 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-8760 | Block-25 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-8765 | Block-25 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 1845 | 0 | 0 | 1 | 2026-04-24 08:00 | 2026-04-24 14:00
603F-CC-8765 | Block-25 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 0 | 0 | 0 | 0 | 2026-04-24 08:00 | 2026-04-24 14:00
603F-CC-8770 | Block-25 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 0 | 495 | 0 | 0
603F-CC-8770 | Block-25 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-8775 | Block-25 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2026-02-22 08:00 | 2026-02-26 17:00
603F-CC-8775 | Block-25 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-22 08:00 | 2026-02-26 17:00
603F-CC-8775 | Block-25 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-22 08:00 | 2026-02-26 17:00
603F-CC-8775 | Block-25 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-22 08:00 | 2026-02-26 17:00
603F-CC-8780 | Block-25 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2026-02-22 08:00 | 2026-02-27 17:00
603F-CC-8780 | Block-25 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-22 08:00 | 2026-02-27 17:00
603F-CC-8780 | Block-25 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-22 08:00 | 2026-02-27 17:00
603F-CC-8785 | Block-25 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-11 08:00 | 2026-03-11 17:00
603F-CC-8785 | Block-25 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-11 08:00 | 2026-03-11 17:00
603F-CC-8790 | Block-25 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-14 08:00 | 2026-03-18 17:00
603F-CC-8790 | Block-25 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-14 08:00 | 2026-03-18 17:00
603F-CC-8795 | Block-25 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-15 17:00
603F-CC-8795 | Block-25 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-15 17:00
603F-CC-8800 | Block-25 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-25 08:00 | 2026-02-25 17:00
603F-CC-8800 | Block-25 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-25 08:00 | 2026-02-25 17:00
603F-CC-8805 | Block-25 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-28 17:00
603F-CC-8805 | Block-25 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-24 08:00 | 2026-02-28 17:00
603F-CC-8810 | Block-25 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-25 08:00 | 2026-02-25 17:00
603F-CC-8810 | Block-25 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-25 08:00 | 2026-02-25 17:00
603F-CC-8815 | Block-25 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-8815 | Block-25 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-8820 | Block-25 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-8820 | Block-25 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-8825 | Block-25 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-22 08:00 | 2026-03-22 17:00
603F-CC-8830 | Block-25 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-13 08:00 | 2026-03-13 17:00
603F-CC-8835 | Block-25 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-20 17:00
603F-CC-8835 | Block-25 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-20 17:00
603F-CC-8835 | Block-25 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-20 17:00
603F-CC-8835 | Block-25 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-20 17:00
603F-CC-8835 | Block-25 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-20 17:00
603F-CC-8835 | Block-25 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-20 17:00
603F-CC-8840 | Block-25 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-14 17:00
603F-CC-8840 | Block-25 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 12.2 | 12 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-14 17:00
603F-CC-8845 | Block-25 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-06 08:00 | 2026-03-13 17:00
603F-CC-8845 | Block-25 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 4 | 4 | 0 | 0 | 1 | 2025-12-06 08:00 | 2026-03-13 17:00
603F-CC-8850 | Block-25 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-20 17:00
603F-CC-8850 | Block-25 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-20 17:00
603F-CC-8855 | Block-25 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-8855 | Block-25 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-8860 | Block-25 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-06 08:00 | 2026-03-06 17:00
603F-CC-8860 | Block-25 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-06 08:00 | 2026-03-06 17:00
603F-CC-8865 | Block-25 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-03-16 08:00 | 2026-03-18 08:00
603F-CC-8865 | Block-25 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-03-16 08:00 | 2026-03-18 08:00
603F-CC-8870 | Block-25 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2026-02-27 08:00 | 2026-02-27 17:00
603F-CC-8870 | Block-25 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-27 08:00 | 2026-02-27 17:00
603F-CC-8875 | Block-25 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-22 17:00
603F-CC-8875 | Block-25 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 94 | 94 | 0 | 0 | 1 | 2026-03-10 08:00 | 2026-03-22 17:00
603F-CC-8880 | Block-25 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-8880 | Block-25 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-8885 | Block-25 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-17 08:00 | 2026-03-17 17:00
603F-CC-8885 | Block-25 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-17 08:00 | 2026-03-17 17:00
603F-CC-8890 | Block-25 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-03-16 08:00 | 2026-03-16 17:00
603F-CC-8890 | Block-25 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-16 08:00 | 2026-03-16 17:00
603F-CC-8895 | Block-25 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-03-16 08:00 | 2026-03-16 17:00
603F-CC-8895 | Block-25 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-16 08:00 | 2026-03-16 17:00
603F-CC-8900 | Block-25 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-8905 | Block-25 -LT Cable Terminations - LT Panel to IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-8910 | Block-25 -LT Cable Terminations - Inverter to LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-23 17:00
603F-CC-8915 | Block-25 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-18 07:00 | 2026-03-18 17:00
603F-CC-8920 | Block-25 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-20 07:00 | 2026-03-20 17:00
603F-CC-8925 | Block-25 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-20 07:00 | 2026-03-20 17:00
603F-CC-8930 | Block-25 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-20 07:00 | 2026-03-20 17:00
603F-CC-9000 | Block-26 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2025-06-13 07:00 | 2026-03-09 17:00
603F-CC-9000 | Block-26 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5844 | 5844 | 0 | 0 | 1 | 2025-06-13 07:00 | 2026-03-09 17:00
603F-CC-9005 | Block-26 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2025-11-24 08:00 | 2026-03-14 17:00
603F-CC-9010 | Block-26 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-02-10 17:00
603F-CC-9010 | Block-26 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-02-10 17:00
603F-CC-9015 | Block-26 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-02-10 17:00
603F-CC-9015 | Block-26 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-02-10 17:00
603F-CC-9020 | Block-26 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-03-18 08:00 | 2026-03-18 17:00
603F-CC-9020 | Block-26 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-03-18 08:00 | 2026-03-18 17:00
603F-CC-9025 | Block-26 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-03-18 17:00
603F-CC-9025 | Block-26 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 4.87 | 5 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-03-18 17:00
603F-CC-9030 | Block-26 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2026-02-10 08:00 | 2026-03-14 17:00
603F-CC-9030 | Block-26 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-02-10 08:00 | 2026-03-14 17:00
603F-CC-9035 | Block-26 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-02-10 12:00 | 2026-03-14 12:00
603F-CC-9035 | Block-26 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 494 | 494 | 0 | 0 | 1 | 2026-02-10 12:00 | 2026-03-14 12:00
603F-CC-9040 | Block-26 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2026-02-16 12:00 | 2026-03-15 12:00
603F-CC-9040 | Block-26 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2026-02-16 12:00 | 2026-03-15 12:00
603F-CC-9045 | Block-26 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 1125 | 0 | 0 | 1 | 2026-02-18 08:00 | 2026-03-15 12:00
603F-CC-9050 | Block-26 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 17 | 0 | 0 | 1 | 2026-02-20 15:00 | 2026-03-18 11:00
603F-CC-9050 | Block-26 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 9882 | 0 | 0 | 1 | 2026-02-20 15:00 | 2026-03-18 11:00
603F-CC-9055 | Block-26 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 774 | 0 | 0 | 1 | 2026-04-09 08:00 | 2026-05-13 13:00
603F-CC-9060 | Block-26 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2026-01-30 15:00 | 2026-03-11 17:00
603F-CC-9060 | Block-26 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2026-01-30 15:00 | 2026-03-11 17:00
603F-CC-9065 | Block-26 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-02-19 15:00 | 2026-03-20 11:00
603F-CC-9065 | Block-26 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-02-19 15:00 | 2026-03-20 11:00
603F-CC-9070 | Block-26 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 81 | 0 | 0 | 1 | 2026-03-14 15:00 | 2026-03-20 11:00
603F-CC-9075 | Block-26 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-04-24 08:00 | 2026-04-24 14:00
603F-CC-9075 | Block-26 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-04-24 08:00 | 2026-04-24 14:00
603F-CC-9080 | Block-26 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 0 | 243 | 0 | 0
603F-CC-9080 | Block-26 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-9085 | Block-26 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 1845 | 0 | 0 | 1 | 2026-04-24 08:00 | 2026-04-24 13:00
603F-CC-9085 | Block-26 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-04-24 08:00 | 2026-04-24 13:00
603F-CC-9090 | Block-26 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 0 | 495 | 0 | 0
603F-CC-9090 | Block-26 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 0 | 39 | 0 | 0
603F-CC-9095 | Block-26 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2026-01-28 08:00 | 2026-02-15 17:00
603F-CC-9095 | Block-26 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-28 08:00 | 2026-02-15 17:00
603F-CC-9095 | Block-26 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-28 08:00 | 2026-02-15 17:00
603F-CC-9095 | Block-26 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-28 08:00 | 2026-02-15 17:00
603F-CC-9100 | Block-26 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-02-18 17:00
603F-CC-9100 | Block-26 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-02-18 17:00
603F-CC-9100 | Block-26 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-13 08:00 | 2026-02-18 17:00
603F-CC-9105 | Block-26 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-9105 | Block-26 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-9110 | Block-26 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-03-22 08:00 | 2026-03-23 17:00
603F-CC-9110 | Block-26 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-22 08:00 | 2026-03-23 17:00
603F-CC-9115 | Block-26 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-9115 | Block-26 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-9120 | Block-26 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-02-26 17:00
603F-CC-9120 | Block-26 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-02-26 17:00
603F-CC-9125 | Block-26 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2026-03-15 08:00 | 2026-03-20 17:00
603F-CC-9125 | Block-26 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-15 08:00 | 2026-03-20 17:00
603F-CC-9130 | Block-26 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-02-26 17:00
603F-CC-9130 | Block-26 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-26 08:00 | 2026-02-26 17:00
603F-CC-9135 | Block-26 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-9135 | Block-26 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-23 08:00 | 2026-03-23 17:00
603F-CC-9140 | Block-26 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-03-22 08:00 | 2026-03-22 17:00
603F-CC-9140 | Block-26 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-22 08:00 | 2026-03-22 17:00
603F-CC-9145 | Block-26 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-22 08:00 | 2026-03-22 17:00
603F-CC-9150 | Block-26 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-13 08:00 | 2026-03-13 17:00
603F-CC-9155 | Block-26 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-02-11 08:00 | 2026-03-20 17:00
603F-CC-9155 | Block-26 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-14 08:00 | 2026-03-20 17:00
603F-CC-9155 | Block-26 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-14 08:00 | 2026-03-20 17:00
603F-CC-9155 | Block-26 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-14 08:00 | 2026-03-20 17:00
603F-CC-9155 | Block-26 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4.08 | 4 | 0 | 0 | 1 | 2026-02-11 08:00 | 2026-03-20 17:00
603F-CC-9155 | Block-26 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-14 08:00 | 2026-03-20 17:00
603F-CC-9160 | Block-26 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-03-01 17:00
603F-CC-9160 | Block-26 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 9.1 | 9 | 0 | 0 | 1 | 2026-01-30 08:00 | 2026-03-01 17:00
603F-CC-9165 | Block-26 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-06 08:00 | 2026-02-24 17:00
603F-CC-9165 | Block-26 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 4 | 4 | 0 | 0 | 1 | 2025-12-06 08:00 | 2026-02-24 17:00
603F-CC-9170 | Block-26 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-03-02 17:00
603F-CC-9170 | Block-26 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-03-02 17:00
603F-CC-9175 | Block-26 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-9175 | Block-26 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-9180 | Block-26 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-9180 | Block-26 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-02-19 17:00
603F-CC-9185 | Block-26 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-03-11 08:00 | 2026-03-11 17:00
603F-CC-9185 | Block-26 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-03-11 08:00 | 2026-03-11 17:00
603F-CC-9190 | Block-26 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2026-02-17 08:00 | 2026-02-17 17:00
603F-CC-9190 | Block-26 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-02-17 08:00 | 2026-02-17 17:00
603F-CC-9195 | Block-26 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-02-11 08:00 | 2026-02-13 17:00
603F-CC-9195 | Block-26 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 94 | 94 | 0 | 0 | 1 | 2026-02-11 08:00 | 2026-02-13 17:00
603F-CC-9200 | Block-26 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-09 08:00 | 2026-03-09 17:00
603F-CC-9200 | Block-26 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-09 08:00 | 2026-03-09 17:00
603F-CC-9205 | Block-26 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-09 08:00 | 2026-03-09 17:00
603F-CC-9205 | Block-26 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-09 08:00 | 2026-03-09 17:00
603F-CC-9210 | Block-26 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-9210 | Block-26 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-9215 | Block-26 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 0 | 0 | 0 | 0 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-9215 | Block-26 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 0 | 0 | 0 | 0 | 2026-03-12 08:00 | 2026-03-12 17:00
603F-CC-9220 | Block-26 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-20 08:00 | 2026-03-20 17:00
603F-CC-9225 | Block-26 -LT Cable Terminations - LT Panel to IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-03-15 08:00 | 2026-03-16 17:00
603F-CC-9230 | Block-26 -LT Cable Terminations - Inverter to LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-03-16 08:00 | 2026-03-17 17:00
603F-CC-9235 | Block-26 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-13 07:00 | 2026-03-13 17:00
603F-CC-9240 | Block-26 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-18 07:00 | 2026-03-18 17:00
603F-CC-9245 | Block-26 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-20 07:00 | 2026-03-20 17:00
603F-CC-9250 | Block-26 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-20 07:00 | 2026-03-20 17:00
603F-CC-9320 | Block-27 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MP01 | Piling Manpower | Labor | 4788 | 4788 | 0 | 0 | 1 | 2025-11-21 07:03 | 2025-12-19 17:00
603F-CC-9320 | Block-27 -Piling - MMS (Marking, Auguring & Concreting) | Solar-MT01-B | Piling Stub - MMS - Construction | Material | 5916 | 5916 | 0 | 0 | 1 | 2025-11-21 07:03 | 2025-12-19 17:00
603F-CC-9325 | Block-27 -Pile Capping | Solar-MP01 | Piling Manpower | Labor | 2394 | 2394 | 0 | 0 | 1 | 2025-11-23 08:00 | 2025-12-20 17:00
603F-CC-9330 | Block-27 -Piling - LT Cable Hanger System | Solar-MP01 | Piling Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-07 08:00 | 2025-12-20 17:00
603F-CC-9330 | Block-27 -Piling - LT Cable Hanger System | Solar-MT02-B | Piling Stub - LT Cable Hanger - Construction | Material | 660 | 660 | 0 | 0 | 1 | 2025-12-07 08:00 | 2025-12-20 17:00
603F-CC-9335 | Block-27 -Piling - Inverters | Solar-MP01 | Piling Manpower | Labor | 405 | 405 | 0 | 0 | 1 | 2025-12-07 08:00 | 2025-12-19 17:00
603F-CC-9335 | Block-27 -Piling - Inverters | Solar-MT03-B | Piling Stub - Invertor - Construction | Material | 93 | 93 | 0 | 0 | 1 | 2025-12-07 08:00 | 2025-12-19 17:00
603F-CC-9340 | Block-27 -Piling - Robotic Docking System | Solar-MP01 | Piling Manpower | Labor | 225 | 225 | 0 | 0 | 1 | 2026-03-01 08:00 | 2026-03-01 17:00
603F-CC-9340 | Block-27 -Piling - Robotic Docking System | Solar-MT04-B | Piling Stub - Robot Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-03-01 08:00 | 2026-03-01 17:00
603F-CC-9345 | Block-27 -Array Earthing | Solar-MP05 | ACDC Manpower | Labor | 900 | 900 | 0 | 0 | 1 | 2025-12-06 08:00 | 2026-02-19 17:00
603F-CC-9345 | Block-27 -Array Earthing | Solar-MT05-B | Earthing - Construction | Material | 4.1 | 4 | 0 | 0 | 1 | 2025-12-06 08:00 | 2026-02-19 17:00
603F-CC-9350 | Block-27 -MMS Erection - Torque Tube/Raftar | Solar-MP07 | FT Manpower | Labor | 9000 | 9000 | 0 | 0 | 1 | 2025-12-09 08:00 | 2026-01-10 17:00
603F-CC-9350 | Block-27 -MMS Erection - Torque Tube/Raftar | Solar-MT09-B | MMS - Rafter - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2025-12-09 08:00 | 2026-01-10 17:00
603F-CC-9355 | Block-27 -MMS Erection - Transmission Shaft/Bracing | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2025-12-09 12:00 | 2026-01-10 12:00
603F-CC-9355 | Block-27 -MMS Erection - Transmission Shaft/Bracing | Solar-MT10-B | MMS - Bracing - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2025-12-09 12:00 | 2026-01-10 12:00
603F-CC-9360 | Block-27 -MMS Erection - Purlin | Solar-MP07 | FT Manpower | Labor | 2250 | 2250 | 0 | 0 | 1 | 2025-12-16 08:00 | 2026-01-14 12:00
603F-CC-9360 | Block-27 -MMS Erection - Purlin | Solar-MT11-B | MMS - FT Purlin - Construction | Material | 487 | 487 | 0 | 0 | 1 | 2025-12-16 08:00 | 2026-01-14 12:00
603F-CC-9365 | Block-27 -MMS - RFI Completion | Solar-MP07 | FT Manpower | Labor | 1125 | 1125 | 0 | 0 | 1 | 2026-01-07 08:00 | 2026-01-25 17:00
603F-CC-9370 | Block-27 -Module Installation | Solar-MT12-B | Module - Construction | Material | 16.5 | 17 | 0 | 0 | 1 | 2026-01-20 16:00 | 2026-03-01 17:00
603F-CC-9370 | Block-27 -Module Installation | Solar-MP03 | Module Manpower | Labor | 9882 | 9881 | 0 | 0 | 1 | 2026-01-20 16:00 | 2026-03-01 17:00
603F-CC-9375 | Block-27 -Module - RFI Completion | Solar-MP03 | Module Manpower | Labor | 774 | 774 | 0 | 0 | 1 | 2026-04-09 08:00 | 2026-05-13 11:00
603F-CC-9380 | Block-27 -DC Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 2196 | 2196 | 0 | 0 | 1 | 2025-12-13 15:00 | 2026-02-19 17:00
603F-CC-9380 | Block-27 -DC Cable Laying | Solar-MT13-B | DC Cable - Construction | Material | 122 | 122 | 0 | 0 | 1 | 2025-12-13 15:00 | 2026-02-19 17:00
603F-CC-9385 | Block-27 -Module Interconnection & MC4 Termination | Solar-MP05 | ACDC Manpower | Labor | 1197 | 1197 | 0 | 0 | 1 | 2026-01-25 11:00 | 2026-03-06 17:00
603F-CC-9385 | Block-27 -Module Interconnection & MC4 Termination | Solar-MT14-B | MC4 Connector - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2026-01-25 11:00 | 2026-03-06 17:00
603F-CC-9390 | Block-27 -VOC Testing | Solar-MP05 | ACDC Manpower | Labor | 81 | 81 | 0 | 0 | 1 | 2026-02-03 08:00 | 2026-03-06 17:00
603F-CC-9395 | Block-27 -Robotic Structure - Docking Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-03-01 08:00 | 2026-03-01 17:00
603F-CC-9395 | Block-27 -Robotic Structure - Docking Station Installation | Solar-MT15-B | Robot Structure - Docking - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-03-01 08:00 | 2026-03-01 17:00
603F-CC-9400 | Block-27 -Robotic Structure - Reverse Station Installation | Solar-MP06 | Robot Installation Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2026-03-04 08:00 | 2026-03-06 17:00
603F-CC-9400 | Block-27 -Robotic Structure - Reverse Station Installation | Solar-MT16-B | Robot Structure - Reverse - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-03-04 08:00 | 2026-03-06 17:00
603F-CC-9405 | Block-27 -Robotic Structure - Bridges Installation | Solar-MP06 | Robot Installation Manpower | Labor | 1845 | 0 | 0 | 0 | 0 | 2026-03-03 08:00 | 2026-03-04 17:00
603F-CC-9405 | Block-27 -Robotic Structure - Bridges Installation | Solar-MT17-B | Robot Structure - Bridges - Construction | Material | 39 | 0 | 0 | 0 | 0 | 2026-03-03 08:00 | 2026-03-04 17:00
603F-CC-9410 | Block-27 -Robot Installation | Solar-MP06 | Robot Installation Manpower | Labor | 495 | 495 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-9410 | Block-27 -Robot Installation | Solar-MT18-B | Robots - Construction | Material | 39 | 39 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-9415 | Block-27 -IDT Foundation Up To Rail | Solar-MP04 | IDT Civil Manpower | Labor | 1224 | 1224 | 0 | 0 | 1 | 2025-11-25 08:00 | 2025-12-10 17:00
603F-CC-9415 | Block-27 -IDT Foundation Up To Rail | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-25 08:00 | 2025-12-10 17:00
603F-CC-9415 | Block-27 -IDT Foundation Up To Rail | Solar-MT38-B | IDT Station - Rail - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-25 08:00 | 2025-12-10 17:00
603F-CC-9415 | Block-27 -IDT Foundation Up To Rail | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-25 08:00 | 2025-12-10 17:00
603F-CC-9420 | Block-27 -HT & LT Station - Slab | Solar-MP04 | IDT Civil Manpower | Labor | 972 | 972 | 0 | 0 | 1 | 2025-11-25 08:00 | 2025-12-10 17:00
603F-CC-9420 | Block-27 -HT & LT Station - Slab | Solar-MT37-B | IDT Station - Foundation Bolt & Inserts - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-25 08:00 | 2025-12-10 17:00
603F-CC-9420 | Block-27 -HT & LT Station - Slab | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-11-25 08:00 | 2025-12-10 17:00
603F-CC-9425 | Block-27 -HT & LT Station - Shed Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-01-09 17:00
603F-CC-9425 | Block-27 -HT & LT Station - Shed Installation | Solar-MT22-B | IDT Shed - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-05 08:00 | 2026-01-09 17:00
603F-CC-9430 | Block-27 -HT & LT Station - Sheeting Installation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2026-01-11 08:00 | 2026-01-11 17:00
603F-CC-9430 | Block-27 -HT & LT Station - Sheeting Installation | Solar-MT23-B | IDT Sheeting - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-11 08:00 | 2026-01-11 17:00
603F-CC-9435 | Block-27 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MP04 | IDT Civil Manpower | Labor | 819 | 819 | 0 | 0 | 1 | 2025-12-11 08:00 | 2025-12-17 17:00
603F-CC-9435 | Block-27 -IDT Foundation - Grade Slab Casting & Dyke Wall | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-11 08:00 | 2025-12-17 17:00
603F-CC-9440 | Block-27 -NIFPS Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2025-12-15 08:00 | 2025-12-16 17:00
603F-CC-9440 | Block-27 -NIFPS Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-15 08:00 | 2025-12-16 17:00
603F-CC-9445 | Block-27 -BOT Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 720 | 720 | 0 | 0 | 1 | 2025-12-09 08:00 | 2025-12-15 17:00
603F-CC-9445 | Block-27 -BOT Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-09 08:00 | 2025-12-15 17:00
603F-CC-9450 | Block-27 -Aux Transformer Foundation | Solar-MP04 | IDT Civil Manpower | Labor | 216 | 216 | 0 | 0 | 1 | 2025-12-15 08:00 | 2025-12-16 17:00
603F-CC-9450 | Block-27 -Aux Transformer Foundation | Solar-MT36-B | IDT Station - Rebar - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-15 08:00 | 2025-12-16 17:00
603F-CC-9455 | Block-27 -IDT Area - Fencing | Solar-MP04 | IDT Civil Manpower | Labor | 117 | 117 | 0 | 0 | 1 | 2026-03-06 08:00 | 2026-03-06 17:00
603F-CC-9455 | Block-27 -IDT Area - Fencing | Solar-MT26-B | IDT - Fencing - Construction - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-06 08:00 | 2026-03-06 17:00
603F-CC-9460 | Block-27 -IDT Area - Gate Installation | Solar-MP04 | IDT Civil Manpower | Labor | 45 | 45 | 0 | 0 | 1 | 2026-03-06 08:00 | 2026-03-06 17:00
603F-CC-9460 | Block-27 -IDT Area - Gate Installation | Solar-MT27-B | IDT - Gate - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-03-06 08:00 | 2026-03-06 09:48
603F-CC-9465 | Block-27 -IDT Area - Gravel Filling | Solar-MP04 | IDT Civil Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-04 08:00 | 2026-03-04 17:00
603F-CC-9470 | Block-27 -HT LT Station - Staircase | Solar-MP04 | IDT Civil Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-03 08:00 | 2026-03-03 17:00
603F-CC-9475 | Block-27 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-02-19 17:00
603F-CC-9475 | Block-27 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT42-B | LT Cable - Clamps - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-02-19 17:00
603F-CC-9475 | Block-27 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT40-B | LT Cable - Fasteners - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-02-19 17:00
603F-CC-9475 | Block-27 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT43-B | LT Cable - Hangers - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-02-19 17:00
603F-CC-9475 | Block-27 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT41-B | LT Cable - Messenger wire - Construction | Material | 4 | 4 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-02-19 17:00
603F-CC-9475 | Block-27 -Cable Hanger - Structure & Messenger Wire Erection | Solar-MT39-B | LT Cable - Support Structure - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-11 08:00 | 2026-02-19 17:00
603F-CC-9480 | Block-27 -LT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 1872 | 1872 | 0 | 0 | 1 | 2025-12-24 08:00 | 2025-12-26 17:00
603F-CC-9480 | Block-27 -LT Cable Laying | Solar-MT29-B | LT Cable - Construction | Material | 10.7 | 11 | 0 | 0 | 1 | 2025-12-24 08:00 | 2025-12-26 17:00
603F-CC-9485 | Block-27 -HT Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 477 | 477 | 0 | 0 | 1 | 2025-12-06 08:00 | 2026-03-04 17:00
603F-CC-9485 | Block-27 -HT Cable Laying | Solar-MT30-B | HT Cable - Construction | Material | 4 | 4 | 0 | 0 | 1 | 2025-12-06 08:00 | 2026-03-04 17:00
603F-CC-9490 | Block-27 -FO Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 603 | 603 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-03-04 17:00
603F-CC-9490 | Block-27 -FO Cable Laying | Solar-MT31-B | FO Cable - Construction | Material | 1.1 | 1 | 0 | 0 | 1 | 2026-01-10 08:00 | 2026-03-04 17:00
603F-CC-9495 | Block-27 -Control Cable Laying | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-04 08:00
603F-CC-9495 | Block-27 -Control Cable Laying | Solar-MT32-B | Control Cable - Construction | Material | 0.74 | 1 | 0 | 0 | 1 | 2026-03-02 08:00 | 2026-03-04 08:00
603F-CC-9500 | Block-27 -HT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 54 | 54 | 0 | 0 | 1 | 2025-12-15 08:00 | 2025-12-15 17:00
603F-CC-9500 | Block-27 -HT Panel Erection | Solar-MT20-B | HT Panel - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-15 08:00 | 2025-12-15 17:00
603F-CC-9505 | Block-27 -LT Panel Erection | Solar-MP05 | ACDC Manpower | Labor | 144 | 144 | 0 | 0 | 1 | 2026-01-06 08:00 | 2026-01-24 17:00
603F-CC-9505 | Block-27 -LT Panel Erection | Solar-MT21-B | LT Panel - Construction | Material | 16 | 16 | 0 | 0 | 1 | 2026-01-06 08:00 | 2026-01-24 17:00
603F-CC-9510 | Block-27 -IDT Erection | Solar-MP05 | ACDC Manpower | Labor | 270 | 270 | 0 | 0 | 1 | 2025-12-25 08:00 | 2025-12-25 17:00
603F-CC-9510 | Block-27 -IDT Erection | Solar-MT19-B | IDT - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-25 08:00 | 2025-12-25 17:00
603F-CC-9515 | Block-27 -Inverter Installation | Solar-MP05 | ACDC Manpower | Labor | 243 | 243 | 0 | 0 | 1 | 2025-12-15 08:00 | 2026-01-03 17:00
603F-CC-9515 | Block-27 -Inverter Installation | Solar-MT33-B | Invertor - Construction | Material | 47 | 47 | 0 | 0 | 1 | 2025-12-15 08:00 | 2026-01-03 17:00
603F-CC-9520 | Block-27 -SCADA & SACU Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-01-25 08:00 | 2026-01-25 17:00
603F-CC-9520 | Block-27 -SCADA & SACU Installation | Solar-MT34-B | SCADA & SACU - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-25 08:00 | 2026-01-25 17:00
603F-CC-9525 | Block-27 -ACDB Installation | Solar-MT35-B | ACDB - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-01-12 17:00
603F-CC-9525 | Block-27 -ACDB Installation | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-01-12 08:00 | 2026-01-12 17:00
603F-CC-9530 | Block-27 -Aux Transformer - Installation | Solar-MP05 | ACDC Manpower | Labor | 72 | 72 | 0 | 0 | 1 | 2025-12-16 08:00 | 2025-12-16 17:00
603F-CC-9530 | Block-27 -Aux Transformer - Installation | Solar-MT25-B | Aux Transformer - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2025-12-16 08:00 | 2025-12-16 17:00
603F-CC-9535 | Block-27 -NIFPS - Installation | Solar-MP05 | ACDC Manpower | Labor | 180 | 180 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-01-17 17:00
603F-CC-9535 | Block-27 -NIFPS - Installation | Solar-MT24-B | NIFPS - Construction | Material | 1 | 1 | 0 | 0 | 1 | 2026-01-17 08:00 | 2026-01-17 17:00
603F-CC-9540 | Block-27 -HT Cable Terminations - IDT Side | Solar-MP05 | ACDC Manpower | Labor | 36 | 36 | 0 | 0 | 1 | 2026-02-21 08:00 | 2026-02-26 17:00
603F-CC-9545 | Block-27 -LT Cable Terminations - LT Panel to IDT | Solar-MP05 | ACDC Manpower | Labor | 261 | 261 | 0 | 0 | 1 | 2026-02-19 08:00 | 2026-03-03 17:00
603F-CC-9550 | Block-27 -LT Cable Terminations - Inverter to LT Panel | Solar-MP05 | ACDC Manpower | Labor | 135 | 135 | 0 | 0 | 1 | 2026-03-01 08:00 | 2026-03-01 17:00
603F-CC-9555 | Block-27 -IDT Filtration | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-02-18 07:00 | 2026-02-18 17:00
603F-CC-9560 | Block-27 -IDT Testing | Solar-MP09 | IDT Filtration & Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-04 07:00 | 2026-03-04 17:00
603F-CC-9565 | Block-27 -HT Panel Testing | Solar-MP10 | HT Panel Testing | Labor | 18 | 18 | 0 | 0 | 1 | 2026-03-03 07:00 | 2026-03-03 17:00
603F-CC-9570 | Block-27 -LT Panel Testing | Solar-MP11 | LT Panel Testing | Labor | 36 | 36 | 0 | 0 | 1 | 2026-03-04 07:00 | 2026-03-04 17:00
603F-CL-1000 | Block-01 -Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1010 | Block-02 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1020 | Block-03 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1030 | Block-04 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1040 | Block-05 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1050 | Block-06 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1060 | Block-07 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1100 | Block-08 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1110 | Block-09 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1120 | Block-10 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1130 | Block-11 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1140 | Block-12 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1150 | Block-13 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1160 | Block-14 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1170 | Block-15 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1200 | Block-16 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1210 | Block-17 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1220 | Block-18 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1230 | Block-19 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1240 | Block-20 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1250 | Block-21 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1260 | Block-22 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1270 | Block-23 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1280 | Block-24 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1290 | Block-25 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1300 | Block-26 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-CL-1310 | Block-27 - Contract Closure | Solar-MP16 | Contract Closure Resource | Labor | 1125 | 0 | 1125 | 0 | 0
603F-EN-1000 | Project Technology Finalization | Solar-MP13 | Engineering Resource | Labor | 4995 | 4995 | 0 | 0 | 1 | 2025-02-15 07:00 | 2025-02-18 17:00
603F-EN-1010 | Array Layout Overall Plant Layout | Solar-MP13 | Engineering Resource | Labor | 44946 | 44946 | 0 | 0 | 1 | 2025-04-03 | 2025-04-03
603F-EN-1020 | Distribution Transformer Foundation (Precast Type) Layout And RC Details (Ornet) | Solar-MP13 | Engineering Resource | Labor | 9081 | 9081 | 0 | 0 | 1 | 2025-03-27 | 2025-03-28
603F-EN-1030 | GA & RC Details Of Burnt Oil Pit For DT | Solar-MP13 | Engineering Resource | Labor | 9081 | 9081 | 0 | 0 | 1 | 2025-03-26 | 2025-03-27
603F-EN-1040 | Fix Tilt Typical Pile Details | Solar-MP13 | Engineering Resource | Labor | 5904 | 5904 | 0 | 0 | 1 | 2025-03-24 | 2025-03-25
603F-EN-1050 | Typical Pile Details For Docking Station | Solar-MP13 | Engineering Resource | Labor | 5220 | 5220 | 0 | 0 | 1 | 2025-04-30 | 2025-04-30
603F-EN-1060 | Inverter Typical Pile Details | Solar-MP13 | Engineering Resource | Labor | 5445 | 5445 | 0 | 0 | 1 | 2025-07-02 07:00 | 2025-07-03 17:00
603F-EN-1070 | Road Layout | Solar-MP13 | Engineering Resource | Labor | 30870 | 30870 | 0 | 0 | 1 | 2025-04-10 | 2025-04-10
603F-EN-1080 | IDT Station HT Panel Platfrom Foundation Layout And Details | Solar-MP13 | Engineering Resource | Labor | 8622 | 8622 | 0 | 0 | 1 | 2025-03-26 | 2025-03-27
603F-EN-1090 | IDT Station HT Panel Platfrom R.C.C Details Slab AndBeam Layout | Solar-MP13 | Engineering Resource | Labor | 8622 | 8622 | 0 | 0 | 1 | 2025-03-27 | 2025-03-28
603F-EN-1100 | IDT Station Layout Plan And Details | Solar-MP13 | Engineering Resource | Labor | 8622 | 8622 | 0 | 0 | 1 | 2025-03-26 | 2025-03-27
603F-EN-1110 | IDT Station Fencing Layout And Details | Solar-MP13 | Engineering Resource | Labor | 8622 | 8622 | 0 | 0 | 1 | 2025-03-26 | 2025-03-27
603F-EN-1120 | Typical Array Earthing Details | Solar-MP13 | Engineering Resource | Labor | 1593 | 1593 | 0 | 0 | 1 | 2025-04-08 | 2025-04-08
603F-EN-1130 | Typical Array LigHTning Protection Details | Solar-MP13 | Engineering Resource | Labor | 14985 | 14985 | 0 | 0 | 1 | 2025-04-08 | 2025-04-08
603F-EN-1140 | LT Cable Trench Section Typical Details Drawing | Solar-MP13 | Engineering Resource | Labor | 14985 | 14985 | 0 | 0 | 1 | 2025-08-05 07:00 | 2025-08-07 17:00
603F-EN-1150 | Earthing Layout Of IDT Station -Type-BB (33Kv Switchgear) | Solar-MP13 | Engineering Resource | Labor | 9531 | 9531 | 0 | 0 | 1 | 2025-04-01 | 2025-04-01
603F-EN-1160 | Robotic Docking Station Pile Layout | Solar-MP13 | Engineering Resource | Labor | 8172 | 8172 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-1200 | GA of 2Px28 MMS Exterior Table (MMS Fix Tilt GA) | Solar-MP13 | Engineering Resource | Labor | 6354 | 6354 | 0 | 0 | 1 | 2025-03-18 | 2025-03-18
603F-EN-1210 | GA of 2Px28 MMS Interior Table (MMS Fix Tilt GA) | Solar-MP13 | Engineering Resource | Labor | 6354 | 6354 | 0 | 0 | 1 | 2025-03-18 | 2025-03-18
603F-EN-1220 | MMS Fix Tilt Fabrication Drawings (Exterior) | Solar-MP13 | Engineering Resource | Labor | 6354 | 6354 | 0 | 0 | 1 | 2025-03-18 | 2025-03-18
603F-EN-1230 | MMS Fix Tilt Fabrication Drawings (Interior) | Solar-MP13 | Engineering Resource | Labor | 6354 | 6354 | 0 | 0 | 1 | 2025-03-18 | 2025-03-18
603F-EN-1240 | Robotic Cleaning System Docking Station Structure GA Details | Solar-MP13 | Engineering Resource | Labor | 1134 | 1134 | 0 | 0 | 1 | 2025-05-12 | 2025-05-12
603F-EN-1250 | Robotic Cleaning System Docking Station Structure Fabrication Details (Common) | Solar-MP13 | Engineering Resource | Labor | 1134 | 1134 | 0 | 0 | 1 | 2025-05-12 | 2025-05-12
603F-EN-1260 | Robotic Cleaning System Docking Station Structure Fabrication Details (Leapting) | Solar-MP13 | Engineering Resource | Labor | 1134 | 1134 | 0 | 0 | 1 | 2025-05-20 | 2025-05-20
603F-EN-1270 | Inverter Mounting Structure GA | Solar-MP13 | Engineering Resource | Labor | 1134 | 1134 | 0 | 0 | 1 | 2025-03-22 | 2025-03-22
603F-EN-1280 | Inverter Mounting Structure Fabrication | Solar-MP13 | Engineering Resource | Labor | 5445 | 5445 | 0 | 0 | 1 | 2025-03-22 | 2025-03-22
603F-EN-1290 | IDT Station - HT - LT Panel Supporting Platformlayout And Details Of Structural Steel Shed | Solar-MP13 | Engineering Resource | Labor | 8622 | 8622 | 0 | 0 | 1 | 2025-03-26 | 2025-03-27
603F-EN-1300 | IDT Station-HT-LT Panel Platfrom LT Panel Supporting Arragement | Solar-MP13 | Engineering Resource | Labor | 8622 | 8622 | 0 | 0 | 1 | 2025-03-27 | 2025-03-28
603F-EN-1310 | HT & FO Cable Routing Layout | Solar-MP13 | Engineering Resource | Labor | 4086 | 4086 | 0 | 0 | 1 | 2025-06-03 | 2025-06-03
603F-EN-1320 | HT Cable Typical Section Details Drawing | Solar-MP13 | Engineering Resource | Labor | 4086 | 4086 | 0 | 0 | 1 | 2025-06-03 | 2025-06-03
603F-EN-1330 | HT Cable Schedule | Solar-MP13 | Engineering Resource | Labor | 4086 | 4086 | 0 | 0 | 1 | 2025-06-03 | 2025-06-03
603F-EN-1340 | FO Cable Schedule | Solar-MP13 | Engineering Resource | Labor | 4086 | 4086 | 0 | 0 | 1 | 2025-06-03 | 2025-06-03
603F-EN-1350 | Typical DC String Cable Arrangement | Solar-MP13 | Engineering Resource | Labor | 15435 | 15435 | 0 | 0 | 1 | 2025-08-02 07:00 | 2025-08-04 17:00
603F-EN-1360 | Cable Hanger Arrangement- GA | Solar-MP13 | Engineering Resource | Labor | 3177 | 3177 | 0 | 0 | 1 | 2025-03-28 | 2025-03-28
603F-EN-1370 | Cable Hanger Arrangement- Fabrication | Solar-MP13 | Engineering Resource | Labor | 3177 | 3177 | 0 | 0 | 1 | 2025-05-16 | 2025-05-16
603F-EN-1380 | Equipment Layout Of IDT Station-Type-BB (33Kv Switchgear) | Solar-MP13 | Engineering Resource | Labor | 9531 | 9531 | 0 | 0 | 1 | 2025-03-28 | 2025-03-28
603F-EN-1390 | Illumination Layout Of IDT Station Type-BB (33Kv Switchgear) | Solar-MP13 | Engineering Resource | Labor | 9531 | 9531 | 0 | 0 | 1 | 2025-04-01 | 2025-04-01
603F-EN-1400 | Cable Route Layout Of IDT Station -Type-BB (33Kv Switchgear) | Solar-MP13 | Engineering Resource | Labor | 9531 | 9531 | 0 | 0 | 1 | 2025-04-01 | 2025-04-01
603F-EN-1410 | Control & Auxiliary Cable Schedule Of IDT Station | Solar-MP13 | Engineering Resource | Labor | 9531 | 9531 | 0 | 0 | 1 | 2025-04-01 | 2025-04-01
603F-EN-1420 | GA Drawings With List Of Fittings For IDT | Solar-MP13 | Engineering Resource | Labor | 909 | 909 | 0 | 0 | 1 | 2025-04-26 | 2025-04-28
603F-EN-1430 | GA Of Marshalling Box & Wiring Diagram And Schematic Diagram Of Cooling System | Solar-MP13 | Engineering Resource | Labor | 909 | 909 | 0 | 0 | 1 | 2025-04-26 | 2025-04-28
603F-EN-1440 | NIFPS (Nitrogen Injection & Fire Protection System) Drawings | Solar-MP13 | Engineering Resource | Labor | 909 | 909 | 0 | 0 | 1 | 2025-04-26 | 2025-04-28
603F-EN-1450 | GTP Of IDT | Solar-MP13 | Engineering Resource | Labor | 1359 | 1359 | 0 | 0 | 1 | 2025-04-26 | 2025-04-28
603F-EN-1460 | O&M Manual Of IDT | Solar-MP13 | Engineering Resource | Labor | 909 | 909 | 0 | 0 | 1 | 2025-04-26 | 2025-04-28
603F-EN-1470 | Inverter Datasheet | Solar-MP13 | Engineering Resource | Labor | 909 | 909 | 0 | 0 | 1 | 2025-05-20 | 2025-05-20
603F-EN-1480 | Inverter Installation Manual | Solar-MP13 | Engineering Resource | Labor | 8172 | 8172 | 0 | 0 | 1 | 2025-05-20 | 2025-05-20
603F-EN-1490 | PV Module Data Sheet | Solar-MP13 | Engineering Resource | Labor | 909 | 909 | 0 | 0 | 1 | 2025-06-30 07:00 | 2025-06-30 17:00
603F-EN-1500 | PV Module Installation Manual | Solar-MP13 | Engineering Resource | Labor | 1359 | 1359 | 0 | 0 | 1 | 2025-06-30 07:00 | 2025-06-30 17:00
603F-EN-1510 | GTP Of HT Cable 3C X 300Sq.Mm | Solar-MP13 | Engineering Resource | Labor | 306 | 306 | 0 | 0 | 1 | 2025-03-19 | 2025-03-20
603F-EN-1520 | GTP Of DC Cable | Solar-MP13 | Engineering Resource | Labor | 909 | 909 | 0 | 0 | 1 | 2025-05-20 | 2025-05-20
603F-EN-1530 | GTP Of FO Cable For Armord Cable | Solar-MP13 | Engineering Resource | Labor | 1359 | 1359 | 0 | 0 | 1 | 2025-05-16 | 2025-05-16
603F-EN-1540 | Module Allocation Schedule | Solar-MP13 | Engineering Resource | Labor | 909 | 909 | 0 | 0 | 1 | 2025-10-27 07:00 | 2025-10-31 17:00
603F-EN-1550 | GTP Of LT Cable | Solar-MP13 | Engineering Resource | Labor | 1359 | 1359 | 0 | 0 | 1 | 2025-05-20 | 2025-05-21
603F-EN-1560 | Robot Communication Box GA And Foundation | Solar-MP13 | Engineering Resource | Labor | 909 | 909 | 0 | 0 | 1 | 2025-05-20 | 2025-05-21
603F-EN-1570 | Robot Installation Manual (Civil) | Solar-MP13 | Engineering Resource | Labor | 1359 | 1359 | 0 | 0 | 1 | 2025-05-20 | 2025-05-21
603F-EN-1580 | GA,GTP, SLD & Schematics for Outdoor Switchgear- TYPE BB | Solar-MP13 | Engineering Resource | Labor | 306 | 306 | 0 | 0 | 1 | 2025-04-28 | 2025-04-28
603F-EN-1590 | GA & GTP of Equipment Outline TDS1GL3XS_Trolly Mount | Solar-MP13 | Engineering Resource | Labor | 306 | 306 | 0 | 0 | 1 | 2025-03-08 | 2025-03-08
603F-EN-1600 | Pile Foundation Layout For Block-01 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-08 | 2025-04-08
603F-EN-1610 | Pile Foundation Layout For Block-02 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-08 | 2025-04-08
603F-EN-1620 | Pile Foundation Layout For Block-03 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-08 | 2025-04-08
603F-EN-1630 | Pile Foundation Layout For Block-04 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-08 | 2025-04-08
603F-EN-1640 | Pile Foundation Layout For Block-05 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-08 | 2025-04-08
603F-EN-1650 | Pile Foundation Layout For Block-06 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-08 | 2025-04-08
603F-EN-1660 | Pile Foundation Layout For Block-07 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-08 | 2025-04-08
603F-EN-1670 | Pile Foundation Layout For Block-08 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-08 | 2025-04-08
603F-EN-1680 | Pile Foundation Layout For Block-09 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-08 | 2025-04-08
603F-EN-1690 | Pile Foundation Layout For Block-10 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-08 | 2025-04-08
603F-EN-1700 | Pile Foundation Layout For Block-11 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-08 | 2025-04-08
603F-EN-1710 | Pile Foundation Layout For Block-12 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-08 | 2025-04-08
603F-EN-1720 | Pile Foundation Layout For Block-13 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-08 | 2025-04-08
603F-EN-1730 | Pile Foundation Layout For Block-14 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-08 | 2025-04-08
603F-EN-1740 | Pile Foundation Layout For Block-15 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-08 | 2025-04-08
603F-EN-1750 | Pile Foundation Layout For Block-16 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-08 | 2025-04-08
603F-EN-1760 | Pile Foundation Layout For Block-17 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-08 | 2025-04-08
603F-EN-1770 | Pile Foundation Layout For Block-18 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-10 | 2025-04-10
603F-EN-1780 | Pile Foundation Layout For Block-19 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-10 | 2025-04-10
603F-EN-1790 | Pile Foundation Layout For Block-20 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-10 | 2025-04-10
603F-EN-1800 | Pile Foundation Layout For Block-21 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-10 | 2025-04-10
603F-EN-1810 | Pile Foundation Layout For Block-22 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-10 | 2025-04-10
603F-EN-1820 | Pile Foundation Layout For Block-23 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-14 | 2025-04-14
603F-EN-1830 | Pile Foundation Layout For Block-24 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-14 | 2025-04-14
603F-EN-1840 | Pile Foundation Layout For Block-25 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-14 | 2025-04-14
603F-EN-1850 | Pile Foundation Layout For Block-26 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-14 | 2025-04-14
603F-EN-1860 | Pile Foundation Layout For Block-27 | Solar-MP13 | Engineering Resource | Labor | 3096 | 3096 | 0 | 0 | 1 | 2025-04-14 | 2025-04-14
603F-EN-1900 | Array Earthing Layout For Block-01 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-1910 | Array Earthing Layout For Block-02 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-1920 | Array Earthing Layout For Block-03 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-1930 | Array Earthing Layout For Block-04 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-1940 | Array Earthing Layout For Block-05 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-1950 | Array Earthing Layout For Block-06 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-1960 | Array Earthing Layout For Block-07 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-1970 | Array Earthing Layout For Block-08 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-1980 | Array Earthing Layout For Block-09 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-1990 | Array Earthing Layout For Block-10 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-2000 | Array Earthing Layout For Block-11 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-2010 | Array Earthing Layout For Block-12 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-2020 | Array Earthing Layout For Block-13 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-2030 | Array Earthing Layout For Block-14 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-2040 | Array Earthing Layout For Block-15 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-2050 | Array Earthing Layout For Block-16 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-2060 | Array Earthing Layout For Block-17 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-2070 | Array Earthing Layout For Block-18 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-2080 | Array Earthing Layout For Block-19 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-2090 | Array Earthing Layout For Block-20 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-2100 | Array Earthing Layout For Block-21 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-2110 | Array Earthing Layout For Block-22 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-2120 | Array Earthing Layout For Block-23 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-2130 | Array Earthing Layout For Block-24 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-2140 | Array Earthing Layout For Block-25 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-2150 | Array Earthing Layout For Block-26 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-2160 | Array Earthing Layout For Block-27 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-03 | 2025-05-03
603F-EN-2200 | LT Cable Routing Layout For Block-01 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2210 | LT Cable Routing Layout For Block-02 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2220 | LT Cable Routing Layout For Block-03 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2230 | LT Cable Routing Layout For Block-04 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2240 | LT Cable Routing Layout For Block-05 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2250 | LT Cable Routing Layout For Block-06 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2260 | LT Cable Routing Layout For Block-07 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2270 | LT Cable Routing Layout For Block-08 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2280 | LT Cable Routing Layout For Block-09 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2290 | LT Cable Routing Layout For Block-10 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2300 | LT Cable Routing Layout For Block-11 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2310 | LT Cable Routing Layout For Block-12 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2320 | LT Cable Routing Layout For Block-13 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2330 | LT Cable Routing Layout For Block-14 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2340 | LT Cable Routing Layout For Block-15 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2350 | LT Cable Routing Layout For Block-16 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2360 | LT Cable Routing Layout For Block-17 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2370 | LT Cable Routing Layout For Block-18 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2380 | LT Cable Routing Layout For Block-19 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2390 | LT Cable Routing Layout For Block-20 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2400 | LT Cable Routing Layout For Block-21 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2410 | LT Cable Routing Layout For Block-22 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2420 | LT Cable Routing Layout For Block-23 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2430 | LT Cable Routing Layout For Block-24 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2440 | LT Cable Routing Layout For Block-25 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2450 | LT Cable Routing Layout For Block-26 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2460 | LT Cable Routing Layout For Block-27 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2500 | LT Cable Schedule For Block-01 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2510 | LT Cable Schedule For Block-02 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2520 | LT Cable Schedule For Block-03 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2530 | LT Cable Schedule For Block-04 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2540 | LT Cable Schedule For Block-05 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2550 | LT Cable Schedule For Block-06 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2560 | LT Cable Schedule For Block-07 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2570 | LT Cable Schedule For Block-08 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2580 | LT Cable Schedule For Block-09 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2590 | LT Cable Schedule For Block-10 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2600 | LT Cable Schedule For Block-11 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2610 | LT Cable Schedule For Block-12 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2620 | LT Cable Schedule For Block-13 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2630 | LT Cable Schedule For Block-14 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2640 | LT Cable Schedule For Block-15 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2650 | LT Cable Schedule For Block-16 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2660 | LT Cable Schedule For Block-17 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2670 | LT Cable Schedule For Block-18 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2680 | LT Cable Schedule For Block-19 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2690 | LT Cable Schedule For Block-20 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2700 | LT Cable Schedule For Block-21 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2710 | LT Cable Schedule For Block-22 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2720 | LT Cable Schedule For Block-23 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2730 | LT Cable Schedule For Block-24 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2740 | LT Cable Schedule For Block-25 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2750 | LT Cable Schedule For Block-26 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-02 | 2025-05-02
603F-EN-2760 | LT Cable Schedule For Block-27 | Solar-MP13 | Engineering Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2800 | Messenger Wire And Cable Hanger Arrangement Layout For Block-01 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-04-30 | 2025-04-30
603F-EN-2810 | Messenger Wire And Cable Hanger Arrangement Layout For Block-02 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-04-30 | 2025-04-30
603F-EN-2820 | Messenger Wire And Cable Hanger Arrangement Layout For Block-03 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-04-30 | 2025-04-30
603F-EN-2830 | Messenger Wire And Cable Hanger Arrangement Layout For Block-04 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-04-30 | 2025-04-30
603F-EN-2840 | Messenger Wire And Cable Hanger Arrangement Layout For Block-05 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-04-30 | 2025-04-30
603F-EN-2850 | Messenger Wire And Cable Hanger Arrangement Layout For Block-06 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-04-30 | 2025-04-30
603F-EN-2860 | Messenger Wire And Cable Hanger Arrangement Layout For Block-07 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-04-30 | 2025-04-30
603F-EN-2870 | Messenger Wire And Cable Hanger Arrangement Layout For Block-08 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-04-30 | 2025-04-30
603F-EN-2880 | Messenger Wire And Cable Hanger Arrangement Layout For Block-09 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2890 | Messenger Wire And Cable Hanger Arrangement Layout For Block-10 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2900 | Messenger Wire And Cable Hanger Arrangement Layout For Block-11 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2910 | Messenger Wire And Cable Hanger Arrangement Layout For Block-12 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2920 | Messenger Wire And Cable Hanger Arrangement Layout For Block-13 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2930 | Messenger Wire And Cable Hanger Arrangement Layout For Block-14 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2940 | Messenger Wire And Cable Hanger Arrangement Layout For Block-15 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2950 | Messenger Wire And Cable Hanger Arrangement Layout For Block-16 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2960 | Messenger Wire And Cable Hanger Arrangement Layout For Block-17 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2970 | Messenger Wire And Cable Hanger Arrangement Layout For Block-18 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2980 | Messenger Wire And Cable Hanger Arrangement Layout For Block-19 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-2990 | Messenger Wire And Cable Hanger Arrangement Layout For Block-20 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-3000 | Messenger Wire And Cable Hanger Arrangement Layout For Block-21 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-3010 | Messenger Wire And Cable Hanger Arrangement Layout For Block-22 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-3020 | Messenger Wire And Cable Hanger Arrangement Layout For Block-23 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-3030 | Messenger Wire And Cable Hanger Arrangement Layout For Block-24 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-3040 | Messenger Wire And Cable Hanger Arrangement Layout For Block-25 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-3050 | Messenger Wire And Cable Hanger Arrangement Layout For Block-26 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-EN-3060 | Messenger Wire And Cable Hanger Arrangement Layout For Block-27 | Solar-MP13 | Engineering Resource | Labor | 270 | 270 | 0 | 0 | 1 | 2025-05-05 | 2025-05-05
603F-HT-1000 | Block-01 -Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1010 | Block-01 -Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1020 | Block-01 -Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1030 | Block-01 -Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1040 | Block-01 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1050 | Block-01 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1060 | Block-01 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1070 | Block-01 -HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1100 | Block-02 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1110 | Block-02 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1120 | Block-02 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1130 | Block-02 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1140 | Block-02 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1150 | Block-02 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1160 | Block-02 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1170 | Block-02 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1200 | Block-03 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1210 | Block-03 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1220 | Block-03 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1230 | Block-03 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1240 | Block-03 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1250 | Block-03 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1260 | Block-03 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1270 | Block-03 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1300 | Block-04 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1310 | Block-04 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1320 | Block-04 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1330 | Block-04 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1340 | Block-04 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1350 | Block-04 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1360 | Block-04 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1370 | Block-04 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1400 | Block-05 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1410 | Block-05 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1420 | Block-05 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1430 | Block-05 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1440 | Block-05 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1450 | Block-05 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1460 | Block-05 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1470 | Block-05 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1500 | Block-06 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1510 | Block-06 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1520 | Block-06 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1530 | Block-06 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1540 | Block-06 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1550 | Block-06 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1560 | Block-06 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1570 | Block-06 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1600 | Block-07 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1610 | Block-07 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1620 | Block-07 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1630 | Block-07 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1640 | Block-07 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1650 | Block-07 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1660 | Block-07 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1670 | Block-07 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1700 | Block-08 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1710 | Block-08 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1720 | Block-08 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1730 | Block-08 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1740 | Block-08 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1750 | Block-08 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1760 | Block-08 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1770 | Block-08 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1800 | Block-09 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1810 | Block-09 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1820 | Block-09 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1830 | Block-09 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1840 | Block-09 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1850 | Block-09 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1860 | Block-09 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1870 | Block-09 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1900 | Block-10 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1910 | Block-10 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1920 | Block-10 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1930 | Block-10 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1940 | Block-10 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1950 | Block-10 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1960 | Block-10 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-1970 | Block-10 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2000 | Block-11 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2010 | Block-11 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2020 | Block-11 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2030 | Block-11 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2040 | Block-11 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2050 | Block-11 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2060 | Block-11 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2070 | Block-11 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2100 | Block-12 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2110 | Block-12 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2120 | Block-12 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2130 | Block-12 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2140 | Block-12 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2150 | Block-12 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2160 | Block-12 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2170 | Block-12 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2200 | Block-13 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2210 | Block-13 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2220 | Block-13 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2230 | Block-13 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2240 | Block-13 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2250 | Block-13 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2260 | Block-13 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2270 | Block-13 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2300 | Block-14 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2310 | Block-14 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2320 | Block-14 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2330 | Block-14 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2340 | Block-14 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2350 | Block-14 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2360 | Block-14 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2370 | Block-14 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2400 | Block-15 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2410 | Block-15 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2420 | Block-15 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2430 | Block-15 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2440 | Block-15 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2450 | Block-15 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2460 | Block-15 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2470 | Block-15 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2500 | Block-16 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2510 | Block-16 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2520 | Block-16 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2530 | Block-16 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2540 | Block-16 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2550 | Block-16 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2560 | Block-16 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2570 | Block-16 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2600 | Block-17 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2610 | Block-17 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2620 | Block-17 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2630 | Block-17 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2640 | Block-17 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2650 | Block-17 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2660 | Block-17 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2670 | Block-17 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2700 | Block-18 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2710 | Block-18 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2720 | Block-18 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2730 | Block-18 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2740 | Block-18 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2750 | Block-18 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2760 | Block-18 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2770 | Block-18 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2800 | Block-19 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2810 | Block-19 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2820 | Block-19 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2830 | Block-19 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2840 | Block-19 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2850 | Block-19 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2860 | Block-19 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2870 | Block-19 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2900 | Block-20 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2910 | Block-20 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2920 | Block-20 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2930 | Block-20 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2940 | Block-20 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2950 | Block-20 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2960 | Block-20 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-2970 | Block-20 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3000 | Block-21 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3010 | Block-21 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3020 | Block-21 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3030 | Block-21 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3040 | Block-21 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3050 | Block-21 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3060 | Block-21 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3070 | Block-21 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3100 | Block-22 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3110 | Block-22 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3120 | Block-22 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3130 | Block-22 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3140 | Block-22 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3150 | Block-22 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3160 | Block-22 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3170 | Block-22 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3200 | Block-23 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3210 | Block-23 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3220 | Block-23 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3230 | Block-23 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3240 | Block-23 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3250 | Block-23 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3260 | Block-23 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3270 | Block-23 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3300 | Block-24 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3310 | Block-24 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3320 | Block-24 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3330 | Block-24 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3340 | Block-24 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3350 | Block-24 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3360 | Block-24 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3370 | Block-24 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3400 | Block-25 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3410 | Block-25 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3420 | Block-25 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3430 | Block-25 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3440 | Block-25 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3450 | Block-25 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3460 | Block-25 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3470 | Block-25 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3500 | Block-26 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3510 | Block-26 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3520 | Block-26 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3530 | Block-26 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3540 | Block-26 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3550 | Block-26 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3560 | Block-26 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3570 | Block-26 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3600 | Block-27 - Final Inspection Offer To O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3610 | Block-27 - Punch Point Identification By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3620 | Block-27 - Punch Point Rectification By Project Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3630 | Block-27 - Punch Point Closure Validation By O&M Team | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3640 | Block-27 -Submission of As-built Drawings,OEM Manuals, Warranty Certificates etc. through DMS | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3650 | Block-27 -House Keeping & Removal of Scraps | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3660 | Block-27 -Handing Over of Mandatory Spares | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-HT-3670 | Block-27 - HOTO Sign Off | Solar-MP17 | HOTO Resource | Labor | 558 | 0 | 558 | 0 | 0
603F-PR-1000 | Piling Stub MMS-Boq & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 4086 | 4086 | 0 | 0 | 1 | 2025-02-19 07:00 | 2025-02-22 17:00
603F-PR-1010 | Piling Stub MMS-TBER | Solar-MP14 | Procurement Resource | Labor | 3267 | 3267 | 0 | 0 | 1 | 2025-02-23 07:00 | 2025-03-06 17:00
603F-PR-1020 | Piling Stub MMS-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 3267 | 3267 | 0 | 0 | 1 | 2025-03-07 07:00 | 2025-03-07 17:00
603F-PR-1030 | Piling Stub MMS-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 1638 | 1638 | 0 | 0 | 1 | 2025-03-07 07:00 | 2025-03-08 17:00
603F-PR-1040 | Piling Stub MMS-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 4086 | 4086 | 0 | 0 | 1 | 2025-03-09 07:00 | 2025-03-10 17:00
603F-PR-1050 | Piling Stub MMS-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 15255 | 15255 | 0 | 0 | 1 | 2025-03-24 07:00 | 2025-07-11 17:00
603F-PR-1060 | Piling Stub MMS-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 3816 | 3816 | 0 | 0 | 1 | 2025-03-31 07:00 | 2025-05-28 07:03
603F-PR-1070 | Piling Stub MMS-Receipt At Site-Lot-01 | Solar-MT01-A | Piling Stub - MMS - Supply | Material | 52596 | 0 | 0 | 0 | 0 | 2025-04-03 07:03 | 2025-05-31 07:03
603F-PR-1070 | Piling Stub MMS-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 3816 | 3816 | 0 | 0 | 1 | 2025-04-03 07:03 | 2025-05-31 07:03
603F-PR-1080 | Piling Stub MMS-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 3816 | 3816 | 0 | 0 | 1 | 2025-04-02 07:03 | 2025-05-30 07:00
603F-PR-1090 | Piling Stub MMS-Receipt At Site-Lot-02 | Solar-MT01-A | Piling Stub - MMS - Supply | Material | 52596 | 0 | 0 | 0 | 0 | 2025-04-04 07:03 | 2025-06-01 07:03
603F-PR-1090 | Piling Stub MMS-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 3816 | 3816 | 0 | 0 | 1 | 2025-04-04 07:03 | 2025-06-01 07:03
603F-PR-1100 | Piling Stub MMS-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 3816 | 3420 | 0 | 0 | 1 | 2025-07-11 07:00 | 2025-07-19 17:00
603F-PR-1110 | Piling Stub MMS-Receipt At Site-Lot-03 | Solar-MT01-A | Piling Stub - MMS - Supply | Material | 52596 | 0 | 0 | 0 | 0 | 2025-07-22 08:00 | 2025-07-30 10:33
603F-PR-1110 | Piling Stub MMS-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 3816 | 3816 | 0 | 0 | 1 | 2025-07-22 08:00 | 2025-07-30 10:33
603F-PR-1120 | Piling Stub Inverter-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 36 | 36 | 0 | 0 | 1 | 2025-03-06 07:00 | 2025-03-09 17:00
603F-PR-1130 | Piling Stub Inverter-TBER | Solar-MP14 | Procurement Resource | Labor | 27 | 27 | 0 | 0 | 1 | 2025-03-10 07:00 | 2025-03-21 17:00
603F-PR-1140 | Piling Stub Inverter-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 27 | 27 | 0 | 0 | 1 | 2025-03-22 07:00 | 2025-03-22 17:00
603F-PR-1150 | Piling Stub Inverter-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-03-22 07:00 | 2025-03-23 17:00
603F-PR-1160 | Piling Stub Inverter-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 36 | 36 | 0 | 0 | 1 | 2025-03-24 07:00 | 2025-03-25 17:00
603F-PR-1170 | Piling Stub Inverter-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 126 | 126 | 0 | 0 | 1 | 2025-04-04 07:00 | 2025-05-04 17:00
603F-PR-1180 | Piling Stub Inverter-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 36 | 36 | 0 | 0 | 1 | 2025-05-05 07:00 | 2025-05-12 17:00
603F-PR-1190 | Piling Stub Inverter-Receipt At Site-Lot-01 | Solar-MT03-A | Piling Stub - Invertor - Supply | Material | 837 | 0 | 0 | 0 | 0 | 2025-05-06 07:00 | 2025-05-10 07:34
603F-PR-1190 | Piling Stub Inverter-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 36 | 36 | 0 | 0 | 1 | 2025-05-06 07:00 | 2025-05-10 07:34
603F-PR-1200 | Piling Stub Inverter-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 36 | 36 | 0 | 0 | 1 | 2025-05-08 07:00 | 2025-05-12 17:00
603F-PR-1210 | Piling Stub Inverter-Receipt At Site-Lot-02 | Solar-MT03-A | Piling Stub - Invertor - Supply | Material | 837 | 0 | 0 | 0 | 0 | 2025-05-10 07:00 | 2025-05-14 17:00
603F-PR-1210 | Piling Stub Inverter-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 36 | 36 | 0 | 0 | 1 | 2025-05-10 07:00 | 2025-05-14 17:00
603F-PR-1220 | Piling Stub-LT Cable Support Structure-Boq & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-02-19 07:00 | 2025-02-22 17:00
603F-PR-1230 | Piling Stub-LT Cable Support Structure-TBER | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-02-23 07:00 | 2025-03-06 17:00
603F-PR-1240 | Piling Stub-LT Cable Support Structure-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-07 07:00 | 2025-03-07 17:00
603F-PR-1250 | Piling Stub-LT Cable Support Structure-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-07 07:00 | 2025-03-08 17:00
603F-PR-1260 | Piling Stub-Lt Cable Support Structure-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-03-09 07:00 | 2025-03-10 17:00
603F-PR-1270 | Piling Stub-LT Cable Support Structure-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 54 | 54 | 0 | 0 | 1 | 2025-04-16 07:00 | 2025-05-17 17:00
603F-PR-1280 | Piling Stub-LT Cable Support Structure-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-18 07:00 | 2025-05-21 17:00
603F-PR-1290 | Piling Stub-LT Cable Support Structure-Receipt At Site-Lot-01 | Solar-MT02-A | Piling Stub - LT Cable Hanger - Supply | Material | 5940 | 0 | 0 | 0 | 0 | 2025-05-11 07:00 | 2025-05-24 17:00
603F-PR-1290 | Piling Stub-LT Cable Support Structure-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-11 07:00 | 2025-05-24 17:00
603F-PR-1300 | Piling Stub-LT Cable Support Structure-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-25 07:00 | 2025-06-01 17:00
603F-PR-1310 | Piling Stub-LT Cable Support Structure-Receipt At Site-Lot-02 | Solar-MT02-A | Piling Stub - LT Cable Hanger - Supply | Material | 5940 | 0 | 0 | 0 | 0 | 2025-05-30 07:00 | 2025-06-06 17:00
603F-PR-1310 | Piling Stub-LT Cable Support Structure-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-30 07:00 | 2025-06-06 17:00
603F-PR-1320 | Piling Stub-Robotic Docking Station-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 36 | 36 | 0 | 0 | 1 | 2025-03-14 07:00 | 2025-03-17 17:00
603F-PR-1330 | Piling Stub-Robotic Docking Station-TBER | Solar-MP14 | Procurement Resource | Labor | 27 | 27 | 0 | 0 | 1 | 2025-03-18 07:00 | 2025-03-29 17:00
603F-PR-1340 | Piling Stub-Robotic Docking Station-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 27 | 27 | 0 | 0 | 1 | 2025-03-30 07:00 | 2025-03-30 17:00
603F-PR-1350 | Piling Stub-Robotic Docking Station-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-03-30 07:00 | 2025-03-31 17:00
603F-PR-1360 | Piling Stub-Robotic Docking Station-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 36 | 36 | 0 | 0 | 1 | 2025-04-01 07:00 | 2025-04-02 17:00
603F-PR-1370 | Piling Stub-Robotic Docking Station-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 126 | 0 | 0 | 0 | 0 | 2025-05-03 07:00 | 2025-09-01 17:00
603F-PR-1380 | Piling Stub-Robotic Docking Station-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 36 | 0 | 0 | 0 | 0 | 2025-09-01 07:00 | 2025-09-07 17:00
603F-PR-1390 | Piling Stub-Robotic Docking Station-Receipt At Site-Lot-01 | Solar-MT04-A | Piling Stub - Robot Docking - Supply | Material | 351 | 0 | 0 | 0 | 0 | 2025-09-05 07:00 | 2025-09-09 17:00
603F-PR-1390 | Piling Stub-Robotic Docking Station-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 36 | 0 | 0 | 0 | 0 | 2025-09-05 07:00 | 2025-09-09 17:00
603F-PR-1400 | Piling Stub-Robotic Docking Station-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 36 | 0 | 0 | 0 | 0 | 2025-09-01 07:00 | 2025-09-07 17:00
603F-PR-1410 | Piling Stub-Robotic Docking Station-Receipt At Site-Lot-02 | Solar-MT04-A | Piling Stub - Robot Docking - Supply | Material | 351 | 0 | 0 | 0 | 0 | 2025-09-05 07:00 | 2025-09-10 07:00
603F-PR-1410 | Piling Stub-Robotic Docking Station-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 36 | 36 | 0 | 0 | 1 | 2025-09-05 07:00 | 2025-09-10 07:00
603F-PR-1420 | MMS - FT-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 9810 | 9810 | 0 | 0 | 1 | 2025-02-19 07:00 | 2025-02-22 17:00
603F-PR-1430 | MMS - FT-TBER | Solar-MP14 | Procurement Resource | Labor | 7848 | 7848 | 0 | 0 | 1 | 2025-02-19 07:00 | 2025-03-02 17:00
603F-PR-1440 | MMS - FT-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 7848 | 7848 | 0 | 0 | 1 | 2025-03-03 07:00 | 2025-03-03 17:00
603F-PR-1450 | MMS - FT-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 3924 | 3924 | 0 | 0 | 1 | 2025-03-03 07:00 | 2025-03-04 17:00
603F-PR-1460 | Mms - FT-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 9810 | 9810 | 0 | 0 | 1 | 2025-03-05 07:00 | 2025-03-06 17:00
603F-PR-1470 | MMS - FT-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 36612 | 36612 | 0 | 0 | 1 | 2025-04-10 07:00 | 2025-12-22 17:00
603F-PR-1480 | MMS - FT-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 9153 | 9153 | 0 | 0 | 1 | 2025-04-15 07:00 | 2025-07-03 17:00
603F-PR-1490 | MMS - FT-Receipt At Site-Lot-01 | Solar-MT10-A | MMS - Bracing - Supply | Material | 4383 | 4383 | 0 | 0 | 1 | 2025-04-17 07:00 | 2025-07-16 17:00
603F-PR-1490 | MMS - FT-Receipt At Site-Lot-01 | Solar-MT11-A | MMS - FT Purlin - Supply | Material | 4383 | 4383 | 0 | 0 | 1 | 2025-04-17 07:00 | 2025-07-16 17:00
603F-PR-1490 | MMS - FT-Receipt At Site-Lot-01 | Solar-MT09-A | MMS - Rafter - Supply | Material | 4383 | 4383 | 0 | 0 | 1 | 2025-04-17 07:00 | 2025-07-16 17:00
603F-PR-1490 | MMS - FT-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 9153 | 9153 | 0 | 0 | 1 | 2025-04-17 07:00 | 2025-07-16 17:00
603F-PR-1500 | MMS - FT-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 9153 | 9153 | 0 | 0 | 1 | 2025-07-16 07:00 | 2025-07-31 17:00
603F-PR-1510 | MMS - FT-Receipt At Site-Lot-02 | Solar-MT10-A | MMS - Bracing - Supply | Material | 4383 | 4383 | 0 | 0 | 1 | 2025-07-30 07:00 | 2025-08-07 17:00
603F-PR-1510 | MMS - FT-Receipt At Site-Lot-02 | Solar-MT11-A | MMS - FT Purlin - Supply | Material | 4383 | 4383 | 0 | 0 | 1 | 2025-07-30 07:00 | 2025-08-07 17:00
603F-PR-1510 | MMS - FT-Receipt At Site-Lot-02 | Solar-MT09-A | MMS - Rafter - Supply | Material | 4383 | 4383 | 0 | 0 | 1 | 2025-07-30 07:00 | 2025-08-07 17:00
603F-PR-1510 | MMS - FT-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 9153 | 9153 | 0 | 0 | 1 | 2025-07-30 07:00 | 2025-08-07 17:00
603F-PR-1520 | Inverter-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 5076 | 5076 | 0 | 0 | 1 | 2025-02-20 07:00 | 2025-02-23 17:00
603F-PR-1530 | Inverter-TBER | Solar-MP14 | Procurement Resource | Labor | 4059 | 4059 | 0 | 0 | 1 | 2025-02-20 07:00 | 2025-03-03 17:00
603F-PR-1540 | Inverter-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 4059 | 4059 | 0 | 0 | 1 | 2025-03-04 07:00 | 2025-03-04 17:00
603F-PR-1550 | Inverter-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 2025 | 2025 | 0 | 0 | 1 | 2025-03-04 07:00 | 2025-03-05 17:00
603F-PR-1560 | Inverter-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 5076 | 5076 | 0 | 0 | 1 | 2025-03-06 07:00 | 2025-03-07 17:00
603F-PR-1570 | Inverter-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 18945 | 18945 | 0 | 0 | 1 | 2025-02-25 07:00 | 2025-03-15 07:09
603F-PR-1580 | Inverter-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 4734 | 4734 | 0 | 0 | 1 | 2025-07-04 07:00 | 2025-07-05 17:00
603F-PR-1590 | Inverter-Receipt At Site--Lot-01 | Solar-MT33-A | Invertor - Supply | Material | 419 | 0 | 0 | 0 | 0 | 2025-07-08 07:00 | 2025-07-30 17:00
603F-PR-1590 | Inverter-Receipt At Site--Lot-01 | Solar-MP14 | Procurement Resource | Labor | 4734 | 4734 | 0 | 0 | 1 | 2025-07-08 07:00 | 2025-07-30 17:00
603F-PR-1600 | Inverter-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 4734 | 4734 | 0 | 0 | 1 | 2025-10-08 07:00 | 2025-10-20 17:00
603F-PR-1610 | Inverter-Receipt At Site--Lot-02 | Solar-MT33-A | Invertor - Supply | Material | 419 | 0 | 0 | 0 | 0 | 2025-10-22 07:00 | 2025-10-30 17:00
603F-PR-1610 | Inverter-Receipt At Site--Lot-02 | Solar-MP14 | Procurement Resource | Labor | 4734 | 4734 | 0 | 0 | 1 | 2025-10-22 07:00 | 2025-10-30 17:00
603F-PR-1620 | IDT (Incl. NIFPS)-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 3897 | 3897 | 0 | 0 | 1 | 2025-02-20 07:00 | 2025-02-23 17:00
603F-PR-1630 | IDT (Incl. NIFPS)-TBER | Solar-MP14 | Procurement Resource | Labor | 3114 | 3114 | 0 | 0 | 1 | 2025-02-20 07:00 | 2025-03-03 17:00
603F-PR-1640 | IDT (Incl. NIFPS)-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 3114 | 3114 | 0 | 0 | 1 | 2025-03-04 07:00 | 2025-03-04 17:00
603F-PR-1650 | IDT (Incl. NIFPS)-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 1557 | 1557 | 0 | 0 | 1 | 2025-03-04 07:00 | 2025-03-05 17:00
603F-PR-1660 | IDT (Incl. NIFPS)-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 3897 | 3897 | 0 | 0 | 1 | 2025-03-06 07:00 | 2025-03-07 17:00
603F-PR-1670 | IDT (Incl. NIFPS)-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 14544 | 14544 | 0 | 0 | 1 | 2025-04-01 07:00 | 2025-11-23 17:00
603F-PR-1680 | IDT (Incl. NIFPS)-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 3636 | 3636 | 0 | 0 | 1 | 2025-11-09 07:00 | 2025-11-13 17:00
603F-PR-1690 | IDT (Incl. NIFPS)-Receipt At Site-Lot-01 | Solar-MT19-A | IDT - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-11-13 07:00 | 2025-11-15 17:00
603F-PR-1690 | IDT (Incl. NIFPS)-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 3636 | 3636 | 0 | 0 | 1 | 2025-11-13 07:00 | 2025-11-15 17:00
603F-PR-1700 | IDT (Incl. NIFPS)-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 3636 | 1215 | 0 | 0 | 1 | 2025-11-09 07:00 | 2025-11-24 17:00
603F-PR-1710 | IDT (Incl. NIFPS)-Receipt At Site-Lot-02 | Solar-MT19-A | IDT - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-11-18 07:00 | 2025-11-27 17:00
603F-PR-1710 | IDT (Incl. NIFPS)-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 3636 | 1215 | 0 | 0 | 1 | 2025-11-18 07:00 | 2025-11-27 17:00
603F-PR-1720 | HT Panel-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 522 | 522 | 0 | 0 | 1 | 2025-02-20 07:00 | 2025-02-23 17:00
603F-PR-1730 | HT Panel-TBER | Solar-MP14 | Procurement Resource | Labor | 414 | 414 | 0 | 0 | 1 | 2025-02-20 07:00 | 2025-03-03 17:00
603F-PR-1740 | HT Panel-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 414 | 414 | 0 | 0 | 1 | 2025-03-04 07:00 | 2025-03-04 17:00
603F-PR-1750 | HT Panel-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 207 | 207 | 0 | 0 | 1 | 2025-03-04 07:00 | 2025-03-05 17:00
603F-PR-1760 | HT Panel-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 522 | 522 | 0 | 0 | 1 | 2025-03-06 07:00 | 2025-03-07 17:00
603F-PR-1770 | HT Panel-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 1935 | 1935 | 0 | 0 | 1 | 2025-03-20 07:00 | 2025-04-10 07:59
603F-PR-1780 | HT Panel-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 486 | 486 | 0 | 0 | 1 | 2025-06-03 07:00 | 2025-06-08 17:00
603F-PR-1790 | HT Panel-Receipt At Site-Lot-01 | Solar-MT20-A | HT Panel - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-06-09 07:00 | 2025-06-14 17:00
603F-PR-1790 | HT Panel-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 486 | 486 | 0 | 0 | 1 | 2025-06-09 07:00 | 2025-06-14 17:00
603F-PR-1800 | HT Panel-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 486 | 486 | 0 | 0 | 1 | 2025-06-15 07:00 | 2025-06-20 17:00
603F-PR-1810 | HT Panel-Receipt At Site-Lot-02 | Solar-MT20-A | HT Panel - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-06-21 07:00 | 2025-06-26 17:00
603F-PR-1810 | HT Panel-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 486 | 486 | 0 | 0 | 1 | 2025-06-21 07:00 | 2025-06-26 17:00
603F-PR-1820 | LT Panel-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 549 | 549 | 0 | 0 | 1 | 2025-02-20 07:00 | 2025-02-23 17:00
603F-PR-1830 | LT Panel-TBER | Solar-MP14 | Procurement Resource | Labor | 432 | 432 | 0 | 0 | 1 | 2025-02-20 07:00 | 2025-03-03 17:00
603F-PR-1840 | LT Panel-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 432 | 432 | 0 | 0 | 1 | 2025-03-04 07:00 | 2025-03-04 17:00
603F-PR-1850 | LT Panel-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 216 | 216 | 0 | 0 | 1 | 2025-03-04 07:00 | 2025-03-05 17:00
603F-PR-1860 | LT Panel-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 549 | 549 | 0 | 0 | 1 | 2025-03-06 07:00 | 2025-03-07 17:00
603F-PR-1870 | LT Panel-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 2034 | 2034 | 0 | 0 | 1 | 2025-11-09 07:00 | 2025-11-15 17:00
603F-PR-1880 | LT Panel-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 504 | 504 | 0 | 0 | 1 | 2025-11-09 07:00 | 2025-11-12 07:00
603F-PR-1890 | LT Panel-Receipt At Site-Lot-01 | Solar-MT21-A | LT Panel - Supply | Material | 144 | 0 | 0 | 0 | 0 | 2025-11-13 07:00 | 2025-11-15 17:00
603F-PR-1890 | LT Panel-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 504 | 504 | 0 | 0 | 1 | 2025-11-13 07:00 | 2025-11-15 17:00
603F-PR-1900 | LT Panel-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 504 | 504 | 0 | 0 | 1 | 2025-11-09 07:00 | 2025-11-12 17:00
603F-PR-1910 | LT Panel-Receipt At Site-Lot-02 | Solar-MT21-A | LT Panel - Supply | Material | 144 | 0 | 0 | 0 | 0 | 2025-11-13 07:00 | 2025-11-15 17:00
603F-PR-1910 | LT Panel-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 504 | 504 | 0 | 0 | 1 | 2025-11-13 07:00 | 2025-11-15 17:00
603F-PR-1920 | Earthing Flat-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 180 | 180 | 0 | 0 | 1 | 2025-02-21 07:00 | 2025-02-24 17:00
603F-PR-1930 | Earthing Flat-TBER | Solar-MP14 | Procurement Resource | Labor | 144 | 144 | 0 | 0 | 1 | 2025-02-21 07:00 | 2025-03-04 17:00
603F-PR-1940 | Earthing Flat-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 144 | 144 | 0 | 0 | 1 | 2025-03-05 07:00 | 2025-03-05 17:00
603F-PR-1950 | Earthing Flat-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 72 | 72 | 0 | 0 | 1 | 2025-03-05 07:00 | 2025-03-06 17:00
603F-PR-1960 | Earthing Flat-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 180 | 180 | 0 | 0 | 1 | 2025-03-07 07:00 | 2025-03-08 17:00
603F-PR-1970 | Earthing Flat-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 684 | 684 | 0 | 0 | 1 | 2025-04-08 07:00 | 2025-05-08 17:00
603F-PR-1980 | Earthing Flat-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 171 | 171 | 0 | 0 | 1 | 2025-04-23 07:00 | 2025-04-28 07:00
603F-PR-1990 | Earthing Flat-Receipt At Site-Lot-01 | Solar-MT05-A | Earthing - Supply | Material | 46 | 0 | 0 | 0 | 0 | 2025-04-26 07:00 | 2025-05-01 17:00
603F-PR-1990 | Earthing Flat-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 171 | 171 | 0 | 0 | 1 | 2025-04-26 07:00 | 2025-05-01 17:00
603F-PR-2000 | Earthing Flat-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 171 | 171 | 0 | 0 | 1 | 2025-04-29 07:00 | 2025-05-04 17:00
603F-PR-2010 | Earthing Flat-Receipt At Site-Lot-02 | Solar-MT05-A | Earthing - Supply | Material | 46 | 0 | 0 | 0 | 0 | 2025-05-22 07:00 | 2025-05-26 17:00
603F-PR-2010 | Earthing Flat-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 171 | 171 | 0 | 0 | 1 | 2025-05-22 07:00 | 2025-05-26 17:00
603F-PR-2020 | IDT Station - Rebar-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 171 | 171 | 0 | 0 | 1 | 2025-02-21 07:00 | 2025-02-24 17:00
603F-PR-2030 | IDT Station - Rebar-TBER | Solar-MP14 | Procurement Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-02-24 07:00 | 2025-02-24 17:00
603F-PR-2040 | IDT Station - Rebar-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-02-25 07:00 | 2025-02-25 17:00
603F-PR-2050 | IDT Station - Rebar-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 72 | 72 | 0 | 0 | 1 | 2025-02-25 07:00 | 2025-02-26 17:00
603F-PR-2060 | IDT Station - Rebar-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 171 | 171 | 0 | 0 | 1 | 2025-02-27 07:00 | 2025-02-28 17:00
603F-PR-2070 | IDT Station - Rebar-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 639 | 639 | 0 | 0 | 1 | 2025-03-01 07:00 | 2025-03-20 17:00
603F-PR-2080 | IDT Station - Rebar-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 162 | 162 | 0 | 0 | 1 | 2025-03-13 07:00 | 2025-03-16 17:00
603F-PR-2090 | IDT Station - Rebar-Receipt At Site-Lot-01 | Solar-MT36-A | IDT Station - Rebar - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-03-15 07:00 | 2025-03-18 17:00
603F-PR-2090 | IDT Station - Rebar-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 162 | 162 | 0 | 0 | 1 | 2025-03-15 07:00 | 2025-03-18 17:00
603F-PR-2100 | IDT Station - Rebar-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 162 | 162 | 0 | 0 | 1 | 2025-03-16 07:00 | 2025-03-20 17:00
603F-PR-2110 | IDT Station - Rebar-Receipt At Site-Lot-02 | Solar-MT36-A | IDT Station - Rebar - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-03-18 07:00 | 2025-03-22 17:00
603F-PR-2110 | IDT Station - Rebar-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 162 | 162 | 0 | 0 | 1 | 2025-03-18 07:00 | 2025-03-22 17:00
603F-PR-2120 | IDT Station - Foundation Bolt & Inserts-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-02-21 07:00 | 2025-02-24 17:00
603F-PR-2130 | IDT Station - Foundation Bolt & Inserts-TBER | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-02-24 07:00 | 2025-02-24 17:00
603F-PR-2140 | IDT Station - Foundation Bolt & Inserts-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-02-25 07:00 | 2025-02-25 17:00
603F-PR-2150 | IDT Station - Foundation Bolt & Inserts-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-02-25 07:00 | 2025-02-26 17:00
603F-PR-2160 | IDT Station - Foundation Bolt & Inserts-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-02-27 07:00 | 2025-02-28 17:00
603F-PR-2170 | IDT Station - Foundation Bolt & Inserts-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 54 | 54 | 0 | 0 | 1 | 2025-03-31 07:00 | 2025-05-17 16:46
603F-PR-2180 | IDT Station - Foundation Bolt & Inserts-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-04-12 07:00 | 2025-04-24 17:00
603F-PR-2190 | IDT Station - Foundation Bolt & Inserts-Receipt At Site-Lot-01 | Solar-MT37-A | IDT Station - Foundation Bolt & Inserts - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-04-15 07:00 | 2025-04-27 17:00
603F-PR-2190 | IDT Station - Foundation Bolt & Inserts-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-04-15 07:00 | 2025-04-27 17:00
603F-PR-2200 | IDT Station - Foundation Bolt & Inserts-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-04-25 07:00 | 2025-05-07 17:00
603F-PR-2210 | IDT Station - Foundation Bolt & Inserts-Receipt At Site-Lot-02 | Solar-MT37-A | IDT Station - Foundation Bolt & Inserts - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-04-29 07:00 | 2025-05-11 17:00
603F-PR-2210 | IDT Station - Foundation Bolt & Inserts-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-04-29 07:00 | 2025-05-11 17:00
603F-PR-2220 | IDT Station - Rail-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 63 | 63 | 0 | 0 | 1 | 2025-02-21 07:00 | 2025-02-24 17:00
603F-PR-2230 | IDT Station - Rail-TBER | Solar-MP14 | Procurement Resource | Labor | 45 | 45 | 0 | 0 | 1 | 2025-02-24 07:00 | 2025-02-24 17:00
603F-PR-2240 | IDT Station - Rail-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 45 | 45 | 0 | 0 | 1 | 2025-02-25 07:00 | 2025-02-25 17:00
603F-PR-2250 | IDT Station - Rail-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 27 | 27 | 0 | 0 | 1 | 2025-02-25 07:00 | 2025-02-26 17:00
603F-PR-2260 | IDT Station - Rail-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 63 | 63 | 0 | 0 | 1 | 2025-02-27 07:00 | 2025-02-28 17:00
603F-PR-2270 | IDT Station - Rail-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 225 | 225 | 0 | 0 | 1 | 2025-03-31 07:00 | 2025-05-17 08:47
603F-PR-2280 | IDT Station - Rail-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 54 | 54 | 0 | 0 | 1 | 2025-04-12 07:00 | 2025-04-24 17:00
603F-PR-2290 | IDT Station - Rail-Receipt For Site-Lot-01 | Solar-MT38-A | IDT Station - Rail - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-04-25 07:00 | 2025-05-07 17:00
603F-PR-2290 | IDT Station - Rail-Receipt For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 54 | 54 | 0 | 0 | 1 | 2025-04-25 07:00 | 2025-05-07 17:00
603F-PR-2300 | IDT Station - Rail-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 54 | 54 | 0 | 0 | 1 | 2025-04-25 07:00 | 2025-05-07 17:00
603F-PR-2310 | IDT Station - Rail-Receipt For Site-Lot-02 | Solar-MT38-A | IDT Station - Rail - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-04-29 07:00 | 2025-05-11 17:00
603F-PR-2310 | IDT Station - Rail-Receipt For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 54 | 54 | 0 | 0 | 1 | 2025-04-29 07:00 | 2025-05-11 17:00
603F-PR-2320 | IDT Station - Structure, Sheeting & Fasteners-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 243 | 243 | 0 | 0 | 1 | 2025-02-22 07:00 | 2025-02-25 17:00
603F-PR-2330 | IDT Station - Structure, Sheeting & Fasteners-TBER | Solar-MP14 | Procurement Resource | Labor | 198 | 198 | 0 | 0 | 1 | 2025-02-24 07:00 | 2025-02-25 17:00
603F-PR-2340 | IDT Station - Structure, Sheeting & Fasteners-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 198 | 198 | 0 | 0 | 1 | 2025-02-26 07:00 | 2025-02-26 17:00
603F-PR-2350 | IDT Station - Structure, Sheeting & Fasteners-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 99 | 99 | 0 | 0 | 1 | 2025-02-26 07:00 | 2025-02-27 17:00
603F-PR-2360 | IDT Station - Structure, Sheeting & Fasteners-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 243 | 243 | 0 | 0 | 1 | 2025-02-28 07:00 | 2025-03-01 17:00
603F-PR-2370 | IDT Station - Structure, Sheeting & Fasteners-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 918 | 918 | 0 | 0 | 1 | 2025-05-14 07:00 | 2025-07-04 17:00
603F-PR-2380 | IDT Station - Structure, Sheeting & Fasteners-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 225 | 225 | 0 | 0 | 1 | 2025-05-15 07:00 | 2025-06-13 17:00
603F-PR-2390 | IDT Station - Structure, Sheeting & Fasteners-Receipt At Site-Lot-01 | Solar-MT22-A | IDT Shed - Supply | Material | 9 | 9 | 0 | 0 | 1 | 2025-05-20 07:00 | 2025-05-27 17:00
603F-PR-2390 | IDT Station - Structure, Sheeting & Fasteners-Receipt At Site-Lot-01 | Solar-MT23-A | IDT Sheeting - Supply | Material | 9 | 9 | 0 | 0 | 1 | 2025-05-20 07:00 | 2025-05-27 17:00
603F-PR-2390 | IDT Station - Structure, Sheeting & Fasteners-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 225 | 225 | 0 | 0 | 1 | 2025-05-20 07:00 | 2025-05-27 17:00
603F-PR-2400 | IDT Station - Structure, Sheeting & Fasteners-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 225 | 225 | 0 | 0 | 1 | 2025-12-28 07:00 | 2025-12-28 17:00
603F-PR-2410 | IDT Station - Structure, Sheeting & Fasteners-Receipt At Site-Lot-02 | Solar-MT22-A | IDT Shed - Supply | Material | 9 | 9 | 0 | 0 | 1 | 2026-01-01 07:00 | 2026-01-02 17:00
603F-PR-2410 | IDT Station - Structure, Sheeting & Fasteners-Receipt At Site-Lot-02 | Solar-MT23-A | IDT Sheeting - Supply | Material | 9 | 9 | 0 | 0 | 1 | 2026-01-01 07:00 | 2026-01-02 17:00
603F-PR-2410 | IDT Station - Structure, Sheeting & Fasteners-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 225 | 225 | 0 | 0 | 1 | 2026-01-01 07:00 | 2026-01-02 17:00
603F-PR-2420 | LT Cable - Support Structure-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 54 | 54 | 0 | 0 | 1 | 2025-02-22 07:00 | 2025-02-25 17:00
603F-PR-2430 | LT Cable - Support Structure-TBER | Solar-MP14 | Procurement Resource | Labor | 45 | 45 | 0 | 0 | 1 | 2025-02-22 07:00 | 2025-03-05 17:00
603F-PR-2440 | LT Cable - Support Structure-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 45 | 45 | 0 | 0 | 1 | 2025-03-06 07:00 | 2025-03-06 17:00
603F-PR-2450 | LT Cable - Support Structure-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-03-06 07:00 | 2025-03-07 17:00
603F-PR-2460 | LT Cable - Support Structure-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 54 | 54 | 0 | 0 | 1 | 2025-03-08 07:00 | 2025-03-09 17:00
603F-PR-2470 | LT Cable - Support Structure-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 207 | 207 | 0 | 0 | 1 | 2025-04-09 07:00 | 2025-05-23 07:00
603F-PR-2480 | LT Cable - Support Structure-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 54 | 54 | 0 | 0 | 1 | 2025-05-11 07:00 | 2025-05-22 17:00
603F-PR-2490 | LT Cable - Support Structure-Receipt At Site-Lot-01 | Solar-MT39-A | LT Cable - Support Structure - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-05-14 07:00 | 2025-05-23 17:00
603F-PR-2490 | LT Cable - Support Structure-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 54 | 54 | 0 | 0 | 1 | 2025-05-14 07:00 | 2025-05-23 17:00
603F-PR-2500 | LT Cable - Support Structure-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 54 | 54 | 0 | 0 | 1 | 2025-05-23 07:00 | 2025-05-28 17:00
603F-PR-2510 | LT Cable - Support Structure-Receipt At Site-Lot-02 | Solar-MT39-A | LT Cable - Support Structure - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-05-27 07:00 | 2025-06-03 17:00
603F-PR-2510 | LT Cable - Support Structure-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 54 | 54 | 0 | 0 | 1 | 2025-05-27 07:00 | 2025-06-03 17:00
603F-PR-2520 | LT Cable - Fasteners-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-02-22 07:00 | 2025-02-25 17:00
603F-PR-2530 | LT Cable - Fasteners-TBER | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-02-22 07:00 | 2025-03-05 17:00
603F-PR-2540 | LT Cable - Fasteners-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-06 07:00 | 2025-03-06 17:00
603F-PR-2550 | LT Cable - Fasteners-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 0 | 0 | 0 | 0 | 0 | 2025-03-06 07:00 | 2025-03-07 17:00
603F-PR-2560 | LT Cable - Fasteners-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-08 07:00 | 2025-03-09 17:00
603F-PR-2570 | LT Cable - Fasteners-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 27 | 27 | 0 | 0 | 1 | 2025-05-23 07:00 | 2025-05-25 16:42
603F-PR-2580 | LT Cable - Fasteners-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-30 07:00 | 2025-05-30 17:00
603F-PR-2590 | LT Cable - Fasteners-Receipt At Site-Lot-01 | Solar-MT40-A | LT Cable - Fasteners - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-06-04 07:00 | 2025-06-04 17:00
603F-PR-2590 | LT Cable - Fasteners-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-06-04 07:00 | 2025-06-04 17:00
603F-PR-2600 | LT Cable - Fasteners-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-30 07:00 | 2025-05-30 17:00
603F-PR-2610 | LT Cable - Fasteners-Receipt At Site-Lot-02 | Solar-MT40-A | LT Cable - Fasteners - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-06-04 07:00 | 2025-06-04 17:00
603F-PR-2610 | LT Cable - Fasteners-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-06-04 07:00 | 2025-06-04 17:00
603F-PR-2620 | LT Cable - Messenger Wire-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 144 | 144 | 0 | 0 | 1 | 2025-02-22 07:00 | 2025-02-25 17:00
603F-PR-2630 | LT Cable - Messenger Wire-TBER | Solar-MP14 | Procurement Resource | Labor | 117 | 117 | 0 | 0 | 1 | 2025-02-22 07:00 | 2025-03-05 17:00
603F-PR-2640 | LT Cable - Messenger Wire-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 117 | 117 | 0 | 0 | 1 | 2025-03-06 07:00 | 2025-03-06 17:00
603F-PR-2650 | LT Cable - Messenger Wire-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 54 | 54 | 0 | 0 | 1 | 2025-03-06 07:00 | 2025-03-07 17:00
603F-PR-2660 | LT Cable - Messenger Wire-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 144 | 144 | 0 | 0 | 1 | 2025-03-08 07:00 | 2025-03-09 17:00
603F-PR-2670 | LT Cable - Messenger Wire-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 531 | 531 | 0 | 0 | 1 | 2025-04-01 07:00 | 2025-04-30 17:00
603F-PR-2680 | LT Cable - Messenger Wire-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-04-04 07:00 | 2025-04-23 17:00
603F-PR-2690 | LT Cable - Messenger Wire-Receipt At Site-Lot-01 | Solar-MT41-A | LT Cable - Messenger wire - Supply | Material | 37 | 0 | 0 | 0 | 0 | 2025-04-04 07:00 | 2025-05-03 17:00
603F-PR-2690 | LT Cable - Messenger Wire-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-04-04 07:00 | 2025-05-03 17:00
603F-PR-2700 | LT Cable - Messenger Wire-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-04-06 07:00 | 2025-05-20 17:00
603F-PR-2710 | LT Cable - Messenger Wire-Receipt At Site-Lot-02 | Solar-MT41-A | LT Cable - Messenger wire - Supply | Material | 37 | 0 | 0 | 0 | 0 | 2025-04-06 07:00 | 2025-05-23 17:00
603F-PR-2710 | LT Cable - Messenger Wire-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-04-06 07:00 | 2025-05-23 17:00
603F-PR-2720 | LT Cable - Clamps-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-02-22 07:00 | 2025-02-25 17:00
603F-PR-2730 | LT Cable - Clamps-TBER | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-02-22 07:00 | 2025-03-05 17:00
603F-PR-2740 | LT Cable - Clamps-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-06 07:00 | 2025-03-06 17:00
603F-PR-2750 | LT Cable - Clamps-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-06 07:00 | 2025-03-07 17:00
603F-PR-2760 | LT Cable - Clamps-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-03-08 07:00 | 2025-03-09 17:00
603F-PR-2770 | LT Cable - Clamps-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 54 | 54 | 0 | 0 | 1 | 2025-04-01 07:00 | 2025-04-30 17:00
603F-PR-2780 | LT Cable - Clamps-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-11 07:00 | 2025-05-30 17:00
603F-PR-2790 | LT Cable - Clamps-Receipt At Site-Lot-01 | Solar-MT42-A | LT Cable - Clamps - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-04-04 07:00 | 2025-05-03 17:00
603F-PR-2790 | LT Cable - Clamps-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-04-04 07:00 | 2025-05-03 17:00
603F-PR-2800 | LT Cable - Clamps-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-04-06 07:00 | 2025-05-20 17:00
603F-PR-2810 | LT Cable - Clamps-Receipt At Site-Lot-02 | Solar-MT42-A | LT Cable - Clamps - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-04-06 07:00 | 2025-05-23 17:00
603F-PR-2810 | LT Cable - Clamps-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-04-06 07:00 | 2025-05-23 17:00
603F-PR-2820 | LT Cable - Hangers-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 144 | 144 | 0 | 0 | 1 | 2025-02-22 07:00 | 2025-02-25 17:00
603F-PR-2830 | LT Cable - Hangers-TBER | Solar-MP14 | Procurement Resource | Labor | 117 | 117 | 0 | 0 | 1 | 2025-02-22 07:00 | 2025-03-05 17:00
603F-PR-2840 | LT Cable - Hangers-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 117 | 117 | 0 | 0 | 1 | 2025-03-06 07:00 | 2025-03-06 17:00
603F-PR-2850 | LT Cable - Hangers-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 54 | 54 | 0 | 0 | 1 | 2025-03-06 07:00 | 2025-03-07 17:00
603F-PR-2860 | LT Cable - Hangers-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 144 | 144 | 0 | 0 | 1 | 2025-03-08 07:00 | 2025-03-09 17:00
603F-PR-2870 | LT Cable - Hangers-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 180 | 0 | 0 | 0 | 0 | 2025-04-01 | 2026-01-12 17:00
603F-PR-2880 | LT Cable - Hangers-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-04-04 | 2025-05-13 17:00
603F-PR-2890 | LT Cable - Hangers-Receipt At Site-Lot-01 | Solar-MT43-A | LT Cable - Hangers - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-04-04 | 2025-05-23 17:00
603F-PR-2890 | LT Cable - Hangers-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-04-04 | 2025-05-23 17:00
603F-PR-2900 | LT Cable - Hangers-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-04-06 | 2025-12-21 17:00
603F-PR-2910 | LT Cable - Hangers-Receipt At Site-Lot-02 | Solar-MT43-A | LT Cable - Hangers - Supply | Material | 9 | 9 | 0 | 0 | 1 | 2025-04-06 | 2025-12-22 17:00
603F-PR-2910 | LT Cable - Hangers-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-04-06 | 2025-12-22 17:00
603F-PR-2920 | LT Cable-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 1638 | 1638 | 0 | 0 | 1 | 2025-02-23 07:00 | 2025-02-26 17:00
603F-PR-2930 | LT Cable-TBER | Solar-MP14 | Procurement Resource | Labor | 1305 | 1305 | 0 | 0 | 1 | 2025-02-23 07:00 | 2025-03-06 17:00
603F-PR-2940 | LT Cable-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 1305 | 1305 | 0 | 0 | 1 | 2025-03-07 07:00 | 2025-03-07 17:00
603F-PR-2950 | LT Cable-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 657 | 657 | 0 | 0 | 1 | 2025-03-07 07:00 | 2025-03-08 17:00
603F-PR-2960 | LT Cable-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 1638 | 1638 | 0 | 0 | 1 | 2025-03-09 07:00 | 2025-03-10 15:00
603F-PR-2970 | LT Cable-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 6102 | 6102 | 0 | 0 | 1 | 2025-03-31 15:00 | 2025-05-20 07:01
603F-PR-2980 | LT Cable-Dispatch For Site-Lot-01 (To be used from surplus available from Phase I and Phase II.) | Solar-MP14 | Procurement Resource | Labor | 1521 | 1521 | 0 | 0 | 1 | 2025-06-18 07:00 | 2025-07-16 17:00
603F-PR-2990 | LT Cable-Receipt At Site-Lot-01 | Solar-MT29-A | LT Cable - Supply | Material | 111 | 0 | 0 | 0 | 0 | 2025-07-17 07:00 | 2025-08-07 17:00
603F-PR-2990 | LT Cable-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 1521 | 1521 | 0 | 0 | 1 | 2025-07-17 07:00 | 2025-08-07 17:00
603F-PR-3000 | LT Cable-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 1521 | 1521 | 0 | 0 | 1 | 2025-08-08 07:00 | 2025-09-30 17:00
603F-PR-3010 | LT Cable-Receipt At Site-Lot-02 | Solar-MT29-A | LT Cable - Supply | Material | 111 | 0 | 0 | 0 | 0 | 2025-09-27 07:00 | 2025-10-10 17:00
603F-PR-3010 | LT Cable-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 1521 | 1521 | 0 | 0 | 1 | 2025-09-27 07:00 | 2025-10-10 17:00
603F-PR-3020 | Control Cables-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 27 | 27 | 0 | 0 | 1 | 2025-02-23 07:00 | 2025-02-26 17:00
603F-PR-3030 | Control Cables-TBER | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-02-23 07:00 | 2025-03-06 17:00
603F-PR-3040 | Control Cables-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-03-07 07:00 | 2025-03-07 17:00
603F-PR-3050 | Control Cables-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-07 07:00 | 2025-03-08 17:00
603F-PR-3060 | Control Cables-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 27 | 27 | 0 | 0 | 1 | 2025-03-09 07:00 | 2025-03-10 17:00
603F-PR-3070 | Control Cables-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 99 | 99 | 0 | 0 | 1 | 2025-03-20 07:00 | 2025-04-05 07:00
603F-PR-3080 | Control Cables-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 27 | 27 | 0 | 0 | 1 | 2025-04-24 07:00 | 2025-05-03 17:00
603F-PR-3090 | Control Cables-Receipt At Site-Lot-01 | Solar-MT32-A | Control Cable - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-05-05 07:00 | 2025-05-14 17:00
603F-PR-3090 | Control Cables-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 27 | 27 | 0 | 0 | 1 | 2025-05-05 07:00 | 2025-05-14 17:00
603F-PR-3100 | Control Cables-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 27 | 27 | 0 | 0 | 1 | 2025-05-30 07:00 | 2025-06-08 17:00
603F-PR-3110 | Control Cables-Receipt At Site-Lot-02 | Solar-MT32-A | Control Cable - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-06-06 07:00 | 2025-06-15 17:00
603F-PR-3110 | Control Cables-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 27 | 27 | 0 | 0 | 1 | 2025-06-06 07:00 | 2025-06-15 17:00
603F-PR-3120 | Ht Cable-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 2223 | 2223 | 0 | 0 | 1 | 2025-02-23 07:00 | 2025-02-26 17:00
603F-PR-3130 | Ht Cable-TBER | Solar-MP14 | Procurement Resource | Labor | 1773 | 1773 | 0 | 0 | 1 | 2025-02-23 07:00 | 2025-03-06 17:00
603F-PR-3140 | HT Cable-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 1773 | 1773 | 0 | 0 | 1 | 2025-03-07 07:00 | 2025-03-07 17:00
603F-PR-3150 | HT Cable-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 891 | 891 | 0 | 0 | 1 | 2025-03-07 07:00 | 2025-03-08 17:00
603F-PR-3160 | Ht Cable-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 2223 | 2223 | 0 | 0 | 1 | 2025-03-09 07:00 | 2025-03-10 17:00
603F-PR-3170 | HT Cable-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 8289 | 8289 | 0 | 0 | 1 | 2025-03-31 07:00 | 2025-04-20 17:00
603F-PR-3180 | HT Cable-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 2070 | 2070 | 0 | 0 | 1 | 2025-07-12 07:00 | 2025-07-31 17:00
603F-PR-3190 | HT Cable-Receipt At Site-Lot-01 | Solar-MT30-A | HT Cable - Supply | Material | 36 | 0 | 0 | 0 | 0 | 2025-07-29 07:00 | 2025-08-20 17:00
603F-PR-3190 | HT Cable-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 2070 | 2070 | 0 | 0 | 1 | 2025-07-29 07:00 | 2025-08-20 17:00
603F-PR-3200 | HT Cable-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 2070 | 2070 | 0 | 0 | 1 | 2025-07-20 07:00 | 2025-11-14 17:00
603F-PR-3210 | HT Cable-Receipt At Site-Lot-02 | Solar-MT30-A | HT Cable - Supply | Material | 36 | 0 | 0 | 0 | 0 | 2025-08-18 07:00 | 2025-11-18 07:00
603F-PR-3210 | HT Cable-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 2070 | 2070 | 0 | 0 | 1 | 2025-08-18 07:00 | 2025-11-18 07:00
603F-PR-3220 | Fiber Optic Cable-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-02-24 07:00 | 2025-02-27 17:00
603F-PR-3230 | Fiber Optic Cable-TBER | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-02-24 07:00 | 2025-03-07 17:00
603F-PR-3240 | Fiber Optic Cable-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-03-08 07:00 | 2025-03-08 17:00
603F-PR-3250 | Fiber Optic Cable-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-08 07:00 | 2025-03-09 17:00
603F-PR-3260 | Fiber Optic Cable-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-03-10 07:00 | 2025-03-11 17:00
603F-PR-3270 | Fiber Optic Cable-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 72 | 72 | 0 | 0 | 1 | 2025-03-20 07:00 | 2025-04-10 17:00
603F-PR-3280 | Fiber Optic Cable-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-11-17 07:00 | 2025-11-20 17:00
603F-PR-3290 | Fiber Optic Cable-Receipt At Site-Lot-01 | Solar-MT31-A | FO Cable - Supply | Material | 10 | 0 | 0 | 0 | 0 | 2025-11-21 07:00 | 2025-11-22 17:00
603F-PR-3290 | Fiber Optic Cable-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-11-21 07:00 | 2025-11-22 17:00
603F-PR-3300 | Fiber Optic Cable-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-11-17 07:00 | 2025-11-20 17:00
603F-PR-3310 | Fiber Optic Cable-Receipt At Site-Lot-02 | Solar-MT31-A | FO Cable - Supply | Material | 10 | 0 | 0 | 0 | 0 | 2025-11-21 07:00 | 2025-11-22 17:00
603F-PR-3310 | Fiber Optic Cable-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-11-21 07:00 | 2025-11-22 17:00
603F-PR-3320 | Inverter Structure - Support Beam & Column-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-02-23 07:00 | 2025-02-26 17:00
603F-PR-3330 | Inverter Structure - Support Beam & Column-TBER | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-02-23 07:00 | 2025-03-06 17:00
603F-PR-3340 | Inverter Structure - Support Beam & Column-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-07 07:00 | 2025-03-07 17:00
603F-PR-3350 | Inverter Structure - Support Beam & Column-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-07 07:00 | 2025-03-08 17:00
603F-PR-3360 | Inverter Structure - Support Beam & Column-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-03-09 07:00 | 2025-03-10 17:00
603F-PR-3370 | Inverter Structure - Support Beam & Column-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 54 | 54 | 0 | 0 | 1 | 2025-05-04 07:00 | 2025-05-30 17:00
603F-PR-3380 | Inverter Structure - Support Beam & Column-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-07 07:00 | 2025-05-21 17:00
603F-PR-3390 | Inverter Structure - Support Beam & Column-Receipt At Site-Lot-01 | Solar-MT44-A | Inverter Structure - Support beam & Column - Supply | Material | 419 | 419 | 0 | 0 | 1 | 2025-05-08 07:00 | 2025-05-29 17:00
603F-PR-3390 | Inverter Structure - Support Beam & Column-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-08 07:00 | 2025-05-29 17:00
603F-PR-3400 | Inverter Structure - Support Beam & Column-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-18 07:00 | 2025-05-23 17:00
603F-PR-3410 | Inverter Structure - Support Beam & Column-Receipt At Site-Lot-02 | Solar-MT44-A | Inverter Structure - Support beam & Column - Supply | Material | 419 | 419 | 0 | 0 | 1 | 2025-05-23 07:00 | 2025-06-04 17:00
603F-PR-3410 | Inverter Structure - Support Beam & Column-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-23 07:00 | 2025-06-04 17:00
603F-PR-3420 | Inverter Structure - Fasteners-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-02-24 07:00 | 2025-02-27 17:00
603F-PR-3430 | Inverter Structure - Fasteners-TBER | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-02-24 07:00 | 2025-03-07 17:00
603F-PR-3440 | Inverter Structure - Fasteners-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-08 07:00 | 2025-03-08 17:00
603F-PR-3450 | Inverter Structure - Fasteners-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-08 07:00 | 2025-03-09 17:00
603F-PR-3460 | Inverter Structure - Fasteners-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-03-10 07:00 | 2025-03-11 17:00
603F-PR-3470 | Inverter Structure - Fasteners-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 54 | 54 | 0 | 0 | 1 | 2025-05-23 07:00 | 2025-05-25 17:00
603F-PR-3480 | Inverter Structure - Fasteners-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-30 07:00 | 2025-05-30 17:00
603F-PR-3490 | Inverter Structure - Fasteners-Receipt At Site-Lot-01 | Solar-MT45-A | Inverter Structure - Fasteners - Supply | Material | 419 | 0 | 0 | 0 | 0 | 2025-06-04 07:00 | 2025-06-04 17:00
603F-PR-3490 | Inverter Structure - Fasteners-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-06-04 07:00 | 2025-06-04 17:00
603F-PR-3500 | Inverter Structure - Fasteners-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-30 07:00 | 2025-05-30 17:00
603F-PR-3510 | Inverter Structure - Fasteners-Receipt At Site-Lot-02 | Solar-MT45-A | Inverter Structure - Fasteners - Supply | Material | 419 | 0 | 0 | 0 | 0 | 2025-06-04 07:00 | 2025-06-04 07:05
603F-PR-3510 | Inverter Structure - Fasteners-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-06-04 07:00 | 2025-06-04 07:05
603F-PR-3520 | Inverter Structure - Canopy-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-02-24 07:00 | 2025-02-27 17:00
603F-PR-3530 | Inverter Structure - Canopy-TBER | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-02-24 07:00 | 2025-03-07 17:00
603F-PR-3540 | Inverter Structure - Canopy-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-08 07:00 | 2025-03-08 17:00
603F-PR-3550 | Inverter Structure - Canopy-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-08 07:00 | 2025-03-09 17:00
603F-PR-3560 | Inverter Structure - Canopy-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-03-10 07:00 | 2025-03-11 17:00
603F-PR-3570 | Inverter Structure - Canopy-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 54 | 54 | 0 | 0 | 1 | 2025-05-16 07:00 | 2025-06-30 07:00
603F-PR-3580 | Inverter Structure - Canopy-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-19 07:00 | 2025-05-31 07:00
603F-PR-3590 | Inverter Structure - Canopy-Receipt At Site-Lot-01 | Solar-MT46-A | Inverter Structure - Canopy - Supply | Material | 419 | 0 | 0 | 0 | 0 | 2025-05-22 07:00 | 2025-06-03 07:00
603F-PR-3590 | Inverter Structure - Canopy-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-22 07:00 | 2025-06-03 07:00
603F-PR-3600 | Inverter Structure - Canopy-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-06-01 07:00 | 2025-06-15 07:00
603F-PR-3610 | Inverter Structure - Canopy-Receipt At Site-Lot-02 | Solar-MT46-A | Inverter Structure - Canopy - Supply | Material | 419 | 0 | 0 | 0 | 0 | 2025-06-04 07:00 | 2025-06-18 17:00
603F-PR-3610 | Inverter Structure - Canopy-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-06-04 07:00 | 2025-06-18 17:00
603F-PR-3620 | Inverter Structure - Self Tapping Screw-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-02-24 07:00 | 2025-02-27 17:00
603F-PR-3630 | Inverter Structure - Self Tapping Screw-TBER | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-02-24 07:00 | 2025-03-07 17:00
603F-PR-3640 | Inverter Structure - Self Tapping Screw-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-08 07:00 | 2025-03-08 17:00
603F-PR-3650 | Inverter Structure - Self Tapping Screw-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 0 | 0 | 0 | 0 | 0 | 2025-03-08 07:00 | 2025-03-09 17:00
603F-PR-3660 | Inverter Structure - Self Tapping Screw-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-10 07:00 | 2025-03-11 17:00
603F-PR-3670 | Inverter Structure - Self Tapping Screw-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 27 | 27 | 0 | 0 | 1 | 2025-03-12 07:00 | 2025-03-20 17:00
603F-PR-3680 | Inverter Structure - Self Tapping Screw-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-21 07:00 | 2025-03-23 17:00
603F-PR-3690 | Inverter Structure - Self Tapping Screw-Receipt At Site-Lot-01 | Solar-MT47-A | Inverter Structure - Self Tapping Screw - Supply | Material | 419 | 0 | 0 | 0 | 0 | 2025-03-25 07:00 | 2025-03-26 17:00
603F-PR-3690 | Inverter Structure - Self Tapping Screw-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-25 07:00 | 2025-03-26 17:00
603F-PR-3700 | Inverter Structure - Self Tapping Screw-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-26 07:00 | 2025-03-27 17:00
603F-PR-3710 | Inverter Structure - Self Tapping Screw-Receipt At Site-Lot-02 | Solar-MT47-A | Inverter Structure - Self Tapping Screw - Supply | Material | 419 | 0 | 0 | 0 | 0 | 2025-03-28 07:00 | 2025-03-29 17:00
603F-PR-3710 | Inverter Structure - Self Tapping Screw-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-28 07:00 | 2025-03-29 17:00
603F-PR-3720 | Robotic Cleaning System - Robotic Structure-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 513 | 513 | 0 | 0 | 1 | 2025-02-26 07:00 | 2025-03-01 17:00
603F-PR-3730 | Robotic Cleaning System - Robotic Structure-TBER | Solar-MP14 | Procurement Resource | Labor | 405 | 405 | 0 | 0 | 1 | 2025-02-26 07:00 | 2025-03-09 17:00
603F-PR-3740 | Robotic Cleaning System - Robotic Structure-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 405 | 405 | 0 | 0 | 1 | 2025-03-10 07:00 | 2025-03-10 17:00
603F-PR-3750 | Robotic Cleaning System - Robotic Structure-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 207 | 207 | 0 | 0 | 1 | 2025-03-10 07:00 | 2025-03-11 17:00
603F-PR-3760 | Robotic Cleaning System - Robotic Structure-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 513 | 513 | 0 | 0 | 1 | 2025-03-12 07:00 | 2025-03-13 17:00
603F-PR-3770 | Robotic Cleaning System - Robotic Structure-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 1908 | 1908 | 0 | 0 | 1 | 2025-05-16 07:00 | 2025-06-05 07:22
603F-PR-3780 | Robotic Cleaning System - Robotic Structure-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 477 | 0 | 0 | 0 | 0 | 2025-09-01 07:00 | 2025-09-07 17:00
603F-PR-3790 | Robotic Cleaning System - Robotic Structure-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 477 | 0 | 0 | 0 | 0 | 2025-09-06 07:00 | 2025-09-12 17:00
603F-PR-3790 | Robotic Cleaning System - Robotic Structure-Receipt At Site-Lot-01 | Solar-MT17-A | Robot Structure - Bridges - Supply | Material | 351 | 0 | 0 | 0 | 0 | 2025-09-06 07:00 | 2025-09-12 17:00
603F-PR-3790 | Robotic Cleaning System - Robotic Structure-Receipt At Site-Lot-01 | Solar-MT15-A | Robot Structure - Docking-Supply | Material | 351 | 0 | 0 | 0 | 0 | 2025-09-06 07:00 | 2025-09-12 17:00
603F-PR-3790 | Robotic Cleaning System - Robotic Structure-Receipt At Site-Lot-01 | Solar-MT16-A | Robot Structure - Reverse - Supply | Material | 351 | 0 | 0 | 0 | 0 | 2025-09-06 07:00 | 2025-09-12 17:00
603F-PR-3800 | Robotic Cleaning System - Robotic Structure-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 477 | 0 | 0 | 0 | 0 | 2025-09-01 07:00 | 2025-09-07 17:00
603F-PR-3810 | Robotic Cleaning System - Robotic Structure-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 477 | 0 | 0 | 0 | 0 | 2025-09-06 07:00 | 2025-09-12 17:00
603F-PR-3810 | Robotic Cleaning System - Robotic Structure-Receipt At Site-Lot-02 | Solar-MT17-A | Robot Structure - Bridges - Supply | Material | 351 | 0 | 0 | 0 | 0 | 2025-09-06 07:00 | 2025-09-12 17:00
603F-PR-3810 | Robotic Cleaning System - Robotic Structure-Receipt At Site-Lot-02 | Solar-MT15-A | Robot Structure - Docking-Supply | Material | 351 | 0 | 0 | 0 | 0 | 2025-09-06 07:00 | 2025-09-12 17:00
603F-PR-3810 | Robotic Cleaning System - Robotic Structure-Receipt At Site-Lot-02 | Solar-MT16-A | Robot Structure - Reverse - Supply | Material | 351 | 0 | 0 | 0 | 0 | 2025-09-06 07:00 | 2025-09-12 17:00
603F-PR-3820 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 1089 | 1089 | 0 | 0 | 1 | 2025-02-26 07:00 | 2025-03-01 17:00
603F-PR-3830 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-TBER | Solar-MP14 | Procurement Resource | Labor | 873 | 873 | 0 | 0 | 1 | 2025-02-26 07:00 | 2025-03-09 17:00
603F-PR-3840 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 873 | 873 | 0 | 0 | 1 | 2025-03-10 07:00 | 2025-03-10 17:00
603F-PR-3850 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 432 | 432 | 0 | 0 | 1 | 2025-03-10 07:00 | 2025-03-11 17:00
603F-PR-3860 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 1089 | 1089 | 0 | 0 | 1 | 2025-03-12 07:00 | 2025-03-13 17:00
603F-PR-3870 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 4068 | 4068 | 0 | 0 | 1 | 2025-05-16 07:00 | 2025-06-05 07:01
603F-PR-3880 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Dispatch From China-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 1017 | 1017 | 0 | 0 | 1 | 2025-06-12 07:00 | 2025-06-12 17:00
603F-PR-3890 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Transportation & Custom Clearance-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 1017 | 1017 | 0 | 0 | 1 | 2025-06-13 07:00 | 2025-09-09 17:00
603F-PR-3900 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 1017 | 1017 | 0 | 0 | 1 | 2025-09-08 07:00 | 2025-09-11 17:00
603F-PR-3900 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Receipt At Site-Lot-01 | Solar-MT18-A | Robots - Supply | Material | 351 | 0 | 0 | 0 | 0 | 2025-09-08 07:00 | 2025-09-11 17:00
603F-PR-3910 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Dispatch From China-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 1017 | 1017 | 0 | 0 | 1 | 2025-06-12 07:00 | 2025-06-12 17:00
603F-PR-3920 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Transportation & Custom Clearance-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 1017 | 1017 | 0 | 0 | 1 | 2025-06-13 07:00 | 2025-09-09 17:00
603F-PR-3930 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 1017 | 1017 | 0 | 0 | 1 | 2025-09-08 07:00 | 2025-09-11 17:00
603F-PR-3930 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Receipt At Site-Lot-02 | Solar-MT18-A | Robots - Supply | Material | 351 | 0 | 0 | 0 | 0 | 2025-09-08 07:00 | 2025-09-11 17:00
603F-PR-3940 | DC Cable-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 1359 | 1359 | 0 | 0 | 1 | 2025-02-23 07:00 | 2025-02-26 17:00
603F-PR-3950 | DC Cable-TBER | Solar-MP14 | Procurement Resource | Labor | 1089 | 1089 | 0 | 0 | 1 | 2025-02-23 07:00 | 2025-03-06 17:00
603F-PR-3960 | DC Cable-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 1089 | 1089 | 0 | 0 | 1 | 2025-03-07 07:00 | 2025-03-07 17:00
603F-PR-3970 | DC Cable-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 549 | 549 | 0 | 0 | 1 | 2025-03-07 07:00 | 2025-03-08 17:00
603F-PR-3980 | DC Cable-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 1359 | 1359 | 0 | 0 | 1 | 2025-03-09 07:00 | 2025-03-10 17:00
603F-PR-3990 | DC Cable-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 5085 | 5085 | 0 | 0 | 1 | 2025-03-20 07:00 | 2025-04-20 07:00
603F-PR-4000 | DC Cable-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 1269 | 1269 | 0 | 0 | 1 | 2025-05-30 07:00 | 2025-06-12 17:00
603F-PR-4010 | DC Cable-Receipt At Site-Lot-01 | Solar-MT13-A | DC Cable - Supply | Material | 1098 | 0 | 0 | 0 | 0 | 2025-06-09 07:00 | 2025-06-24 17:00
603F-PR-4010 | DC Cable-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 1269 | 1269 | 0 | 0 | 1 | 2025-06-09 07:00 | 2025-06-24 17:00
603F-PR-4020 | DC Cable-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 1269 | 1269 | 0 | 0 | 1 | 2025-06-23 07:00 | 2025-07-01 17:00
603F-PR-4030 | DC Cable-Receipt At Site-Lot-02 | Solar-MT13-A | DC Cable - Supply | Material | 1098 | 0 | 0 | 0 | 0 | 2025-06-27 07:00 | 2025-10-31 17:00
603F-PR-4030 | DC Cable-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 1269 | 1269 | 0 | 0 | 1 | 2025-06-27 07:00 | 2025-10-31 17:00
603F-PR-4040 | Mc4 Connector-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-02-26 07:00 | 2025-03-01 17:00
603F-PR-4050 | Mc4 Connector-TBER | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-02-26 07:00 | 2025-03-09 17:00
603F-PR-4060 | Mc4 Connector-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-10 07:00 | 2025-03-10 17:00
603F-PR-4070 | Mc4 Connector-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-10 07:00 | 2025-03-11 17:00
603F-PR-4080 | Mc4 Connector-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 18 | 18 | 0 | 0 | 1 | 2025-03-12 07:00 | 2025-03-13 17:00
603F-PR-4090 | Mc4 Connector-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 54 | 54 | 0 | 0 | 1 | 2025-05-05 07:00 | 2025-05-20 07:44
603F-PR-4100 | Mc4 Connector-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-11 07:00 | 2025-06-19 17:00
603F-PR-4110 | Mc4 Connector-Receipt At Site-Lot-01 | Solar-MT14-A | MC4 Connector - Supply | Material | 419 | 0 | 0 | 0 | 0 | 2025-05-14 07:00 | 2025-06-30 17:00
603F-PR-4110 | Mc4 Connector-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-14 07:00 | 2025-06-30 17:00
603F-PR-4120 | Mc4 Connector-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-18 07:00 | 2025-06-19 17:00
603F-PR-4130 | Mc4 Connector-Receipt For Site-Lot-02 | Solar-MT14-A | MC4 Connector - Supply | Material | 419 | 0 | 0 | 0 | 0 | 2025-05-21 07:00 | 2025-06-30 17:00
603F-PR-4130 | Mc4 Connector-Receipt For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-21 07:00 | 2025-06-30 17:00
603F-PR-4140 | Module-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 21789 | 21789 | 0 | 0 | 1 | 2025-02-23 07:00 | 2025-02-26 17:00
603F-PR-4150 | Module-TBER | Solar-MP14 | Procurement Resource | Labor | 17433 | 17433 | 0 | 0 | 1 | 2025-02-23 07:00 | 2025-03-06 17:00
603F-PR-4160 | Module-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 17433 | 17433 | 0 | 0 | 1 | 2025-03-07 07:00 | 2025-03-07 17:00
603F-PR-4170 | Module-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 8721 | 8721 | 0 | 0 | 1 | 2025-03-07 07:00 | 2025-03-08 17:00
603F-PR-4180 | Module-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 21789 | 21789 | 0 | 0 | 1 | 2025-03-09 07:00 | 2025-03-10 17:00
603F-PR-4190 | Module-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 81360 | 81360 | 0 | 0 | 1 | 2025-10-12 07:00 | 2025-11-25 17:00
603F-PR-4200 | Module-Dispatch From China-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 31680 | 31680 | 0 | 0 | 1 | 2025-10-25 07:00 | 2026-01-01 08:02
603F-PR-4210 | Module-Transportation & Custom Clearance-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 31680 | 26289 | 0 | 0 | 1 | 2025-12-06 08:02 | 2026-02-14 17:00
603F-PR-4220 | Module-Receipt At Site-Lot-01 | Solar-MT12-A | Module - Supply | Material | 220 | 220 | 0 | 0 | 1 | 2025-12-28 08:02 | 2026-02-16 17:00
603F-PR-4220 | Module-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 15759 | 15759 | 0 | 0 | 1 | 2025-12-28 08:02 | 2026-02-16 17:00
603F-PR-4230 | Module-Dispatch From China-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 20340 | 20340 | 0 | 0 | 1 | 2025-10-25 07:00 | 2026-01-19 17:00
603F-PR-4240 | Module-Transportation & Custom Clearance-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 20340 | 20340 | 0 | 0 | 1 | 2025-10-25 07:00 | 2026-03-06 17:00
603F-PR-4250 | Module-Receipt Site At-Lot-02 | Solar-MT12-A | Module - Supply | Material | 141 | 141 | 0 | 0 | 1 | 2026-01-02 07:00 | 2026-03-10 17:00
603F-PR-4250 | Module-Receipt Site At-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 10170 | 10170 | 0 | 0 | 1 | 2026-01-02 07:00 | 2026-03-10 17:00
603F-PR-4252 | Module-Dispatch From China-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 5120 | 5120 | 0 | 0 | 1 | 2026-01-03 08:00 | 2026-01-26 16:00
603F-PR-4254 | Module-Transportation & Custom Clearance-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 5760 | 5760 | 0 | 0 | 1 | 2026-01-20 16:00 | 2026-03-14 17:00
603F-PR-4256 | Module-Receipt Site At-Lot-03 | Solar-MT12-A | Module - Supply | Material | 80 | 80 | 0 | 0 | 1 | 2026-03-12 07:00 | 2026-03-24 16:00
603F-PR-4256 | Module-Receipt Site At-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 5760 | 5760 | 0 | 0 | 1 | 2026-03-12 07:00 | 2026-03-24 16:00
603F-PR-4260 | SCADA-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 81 | 81 | 0 | 0 | 1 | 2025-02-23 07:00 | 2025-02-26 17:00
603F-PR-4270 | SCADA-TBER | Solar-MP14 | Procurement Resource | Labor | 63 | 63 | 0 | 0 | 1 | 2025-02-23 07:00 | 2025-03-06 17:00
603F-PR-4280 | SCADA-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 63 | 63 | 0 | 0 | 1 | 2025-03-07 07:00 | 2025-03-07 17:00
603F-PR-4290 | SCADA-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 36 | 36 | 0 | 0 | 1 | 2025-03-07 07:00 | 2025-03-08 17:00
603F-PR-4300 | SCADA-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 81 | 81 | 0 | 0 | 1 | 2025-03-09 07:00 | 2025-03-10 17:00
603F-PR-4310 | SCADA-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 306 | 306 | 0 | 0 | 1 | 2025-05-05 07:00 | 2025-05-20 07:00
603F-PR-4320 | SCADA-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 72 | 72 | 0 | 0 | 1 | 2025-05-11 | 2025-05-25 17:00
603F-PR-4330 | SCADA-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 72 | 72 | 0 | 0 | 1 | 2025-05-14 | 2025-05-31 17:00
603F-PR-4330 | SCADA-Receipt At Site-Lot-01 | Solar-MT50-A | SCADA - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-05-14 | 2025-05-31 17:00
603F-PR-4340 | SCADA-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 72 | 72 | 0 | 0 | 1 | 2025-05-18 | 2025-05-25 07:00
603F-PR-4350 | SCADA-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 72 | 72 | 0 | 0 | 1 | 2025-05-21 | 2025-05-31 17:00
603F-PR-4350 | SCADA-Receipt At Site-Lot-02 | Solar-MT50-A | SCADA - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-05-21 | 2025-05-31 17:00
603F-PR-4360 | IDT Fencing & Gate-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-02-25 07:00 | 2025-02-28 17:00
603F-PR-4370 | IDT Fencing & Gate-TBER | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-02-25 07:00 | 2025-03-08 17:00
603F-PR-4380 | IDT Fencing & Gate-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-09 07:00 | 2025-03-09 17:00
603F-PR-4390 | IDT Fencing & Gate-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 0 | 0 | 0 | 0 | 0 | 2025-03-09 07:00 | 2025-03-10 17:00
603F-PR-4400 | IDT Fencing & Gate-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-11 07:00 | 2025-03-12 17:00
603F-PR-4410 | IDT Fencing & Gate-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 27 | 27 | 0 | 0 | 1 | 2025-04-12 07:00 | 2025-06-10 17:00
603F-PR-4420 | IDT Fencing & Gate-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-06-14 07:00 | 2025-06-18 17:00
603F-PR-4430 | IDT Fencing & Gate-Receipt At Site-Lot-01 | Solar-MT26-A | IDT - Fencing - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-06-20 07:00 | 2025-06-23 17:00
603F-PR-4430 | IDT Fencing & Gate-Receipt At Site-Lot-01 | Solar-MT27-A | IDT - Gate - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-06-20 07:00 | 2025-06-23 17:00
603F-PR-4430 | IDT Fencing & Gate-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-06-20 07:00 | 2025-06-23 17:00
603F-PR-4440 | IDT Fencing & Gate-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-06-14 07:00 | 2025-06-18 17:00
603F-PR-4450 | IDT Fencing & Gate-Receipt At Site-Lot-02 | Solar-MT26-A | IDT - Fencing - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-07-20 07:00 | 2025-07-23 17:00
603F-PR-4450 | IDT Fencing & Gate-Receipt At Site-Lot-02 | Solar-MT27-A | IDT - Gate - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-07-20 07:00 | 2025-07-23 17:00
603F-PR-4450 | IDT Fencing & Gate-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-07-20 07:00 | 2025-07-23 17:00
603F-PR-4460 | Electrical AC/DC Works-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 630 | 630 | 0 | 0 | 1 | 2025-02-21 07:00 | 2025-02-24 17:00
603F-PR-4470 | Electrical AC/DC Works-TBER | Solar-MP14 | Procurement Resource | Labor | 504 | 504 | 0 | 0 | 1 | 2025-02-21 07:00 | 2025-03-04 17:00
603F-PR-4480 | Electrical AC/DC Works-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 504 | 504 | 0 | 0 | 1 | 2025-03-05 07:00 | 2025-03-05 17:00
603F-PR-4490 | Electrical AC/DC Works-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 252 | 252 | 0 | 0 | 1 | 2025-03-05 07:00 | 2025-03-06 17:00
603F-PR-4500 | Electrical AC/DC Works-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 630 | 630 | 0 | 0 | 1 | 2025-03-07 07:00 | 2025-03-08 17:00
603F-PR-4510 | Electrical AC/DC Works-Manufacturing Clearance & Manufacturing | Solar-MP14 | Procurement Resource | Labor | 2367 | 2367 | 0 | 0 | 1 | 2025-03-26 07:00 | 2025-05-23 17:00
603F-PR-4520 | Electrical AC/DC Works-Dispatch For Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 594 | 594 | 0 | 0 | 1 | 2025-03-26 07:00 | 2025-05-31 17:00
603F-PR-4530 | Electrical AC/DC Works-Receipt At Site-Lot-01 | Solar-MT51-A | Electrical AC DC Material - Supply | Material | 9 | 9 | 0 | 0 | 1 | 2025-03-26 07:00 | 2025-06-06 17:00
603F-PR-4530 | Electrical AC/DC Works-Receipt At Site-Lot-01 | Solar-MP14 | Procurement Resource | Labor | 594 | 594 | 0 | 0 | 1 | 2025-03-26 07:00 | 2025-06-06 17:00
603F-PR-4540 | Electrical AC/DC Works-Dispatch For Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 594 | 594 | 0 | 0 | 1 | 2025-06-02 07:00 | 2025-06-19 17:00
603F-PR-4550 | Electrical AC/DC Works-Receipt At Site-Lot-02 | Solar-MT51-A | Electrical AC DC Material - Supply | Material | 9 | 9 | 0 | 0 | 1 | 2025-06-25 07:00 | 2025-06-28 17:00
603F-PR-4550 | Electrical AC/DC Works-Receipt At Site-Lot-02 | Solar-MP14 | Procurement Resource | Labor | 594 | 594 | 0 | 0 | 1 | 2025-06-25 07:00 | 2025-06-28 17:00
603F-PR-4560 | Piling Stub Inverter-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 36 | 36 | 0 | 0 | 1 | 2025-05-13 07:00 | 2025-05-17 17:00
603F-PR-4570 | Piling Stub Inverter-Receipt At Site-Lot-03 | Solar-MT03-A | Piling Stub - Invertor - Supply | Material | 837 | 0 | 0 | 0 | 0 | 2025-05-14 07:00 | 2025-07-18 17:00
603F-PR-4570 | Piling Stub Inverter-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 36 | 36 | 0 | 0 | 1 | 2025-05-14 07:00 | 2025-07-18 17:00
603F-PR-4580 | Piling Stub-LT Cable Support Structure-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-06-07 07:00 | 2025-06-10 17:00
603F-PR-4590 | Piling Stub-LT Cable Support Structure-Receipt At Site-Lot-03 | Solar-MT02-A | Piling Stub - LT Cable Hanger - Supply | Material | 5940 | 0 | 0 | 0 | 0 | 2025-06-12 07:00 | 2025-06-14 17:00
603F-PR-4590 | Piling Stub-LT Cable Support Structure-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-06-12 07:00 | 2025-06-14 17:00
603F-PR-4600 | Piling Stub-Robotic Docking Station-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 36 | 36 | 0 | 0 | 1 | 2025-09-02 07:00 | 2025-09-06 17:00
603F-PR-4610 | Piling Stub-Robotic Docking Station-Receipt At Site-Lot-03 | Solar-MT04-A | Piling Stub - Robot Docking - Supply | Material | 351 | 0 | 0 | 0 | 0 | 2025-09-08 07:00 | 2025-09-10 17:00
603F-PR-4610 | Piling Stub-Robotic Docking Station-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 36 | 36 | 0 | 0 | 1 | 2025-09-08 07:00 | 2025-09-10 17:00
603F-PR-4620 | MMS - FT-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 9153 | 9153 | 0 | 0 | 1 | 2025-12-28 07:00 | 2025-12-28 17:00
603F-PR-4630 | MMS - FT-Receipt At Site-Lot-03 | Solar-MT10-A | MMS - Bracing - Supply | Material | 4383 | 4383 | 0 | 0 | 1 | 2026-01-01 07:00 | 2026-01-03 17:00
603F-PR-4630 | MMS - FT-Receipt At Site-Lot-03 | Solar-MT11-A | MMS - FT Purlin - Supply | Material | 4383 | 4383 | 0 | 0 | 1 | 2026-01-01 07:00 | 2026-01-03 17:00
603F-PR-4630 | MMS - FT-Receipt At Site-Lot-03 | Solar-MT09-A | MMS - Rafter - Supply | Material | 4383 | 4383 | 0 | 0 | 1 | 2026-01-01 07:00 | 2026-01-03 17:00
603F-PR-4630 | MMS - FT-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 9153 | 9153 | 0 | 0 | 1 | 2026-01-01 07:00 | 2026-01-03 17:00
603F-PR-4640 | Inverter-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 4734 | 4734 | 0 | 0 | 1 | 2025-10-08 07:00 | 2025-10-20 17:00
603F-PR-4650 | Inverter-Receipt At Site--Lot-03 | Solar-MT33-A | Invertor - Supply | Material | 419 | 0 | 0 | 0 | 0 | 2025-10-22 07:00 | 2025-10-30 17:00
603F-PR-4650 | Inverter-Receipt At Site--Lot-03 | Solar-MP14 | Procurement Resource | Labor | 4734 | 4734 | 0 | 0 | 1 | 2025-10-22 07:00 | 2025-10-30 17:00
603F-PR-4660 | IDT (Incl. NIFPS)-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 3636 | 3636 | 0 | 0 | 1 | 2025-11-23 07:00 | 2025-11-25 17:00
603F-PR-4670 | IDT (Incl. NIFPS)-Receipt At Site-Lot-03 | Solar-MT19-A | IDT - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-11-26 07:00 | 2025-11-26 17:00
603F-PR-4670 | IDT (Incl. NIFPS)-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 3636 | 3636 | 0 | 0 | 1 | 2025-11-26 07:00 | 2025-11-26 17:00
603F-PR-4680 | HT Panel-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 486 | 0 | 0 | 0 | 0 | 2025-09-01 07:00 | 2025-09-06 17:00
603F-PR-4690 | HT Panel-Receipt At Site-Lot-03 | Solar-MT20-A | HT Panel - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-09-07 07:00 | 2025-09-12 17:00
603F-PR-4690 | HT Panel-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 486 | 0 | 0 | 0 | 0 | 2025-09-07 07:00 | 2025-09-12 17:00
603F-PR-4700 | LT Panel-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 504 | 504 | 0 | 0 | 1 | 2025-11-09 07:00 | 2025-11-12 17:00
603F-PR-4710 | LT Panel-Receipt At Site-Lot-03 | Solar-MT21-A | LT Panel - Supply | Material | 144 | 0 | 0 | 0 | 0 | 2025-11-13 07:00 | 2025-11-15 17:00
603F-PR-4710 | LT Panel-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 504 | 504 | 0 | 0 | 1 | 2025-11-13 07:00 | 2025-11-15 17:00
603F-PR-4720 | Earthing Flat-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 171 | 171 | 0 | 0 | 1 | 2025-05-23 07:00 | 2025-05-27 17:00
603F-PR-4730 | Earthing Flat-Receipt At Site-Lot-03 | Solar-MT05-A | Earthing - Supply | Material | 46 | 0 | 0 | 0 | 0 | 2025-05-25 07:00 | 2025-05-31 17:00
603F-PR-4730 | Earthing Flat-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 171 | 171 | 0 | 0 | 1 | 2025-05-25 07:00 | 2025-05-31 17:00
603F-PR-4740 | IDT Station - Rebar-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 162 | 162 | 0 | 0 | 1 | 2025-03-20 07:00 | 2025-03-26 17:00
603F-PR-4750 | IDT Station - Rebar-Receipt At Site-Lot-03 | Solar-MT36-A | IDT Station - Rebar - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-03-22 07:00 | 2025-03-31 17:00
603F-PR-4750 | IDT Station - Rebar-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 162 | 162 | 0 | 0 | 1 | 2025-03-22 07:00 | 2025-03-31 17:00
603F-PR-4760 | IDT Station - Foundation Bolt & Inserts-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-15 16:46 | 2025-05-30 16:46
603F-PR-4770 | IDT Station - Foundation Bolt & Inserts-Receipt At Site-Lot-03 | Solar-MT37-A | IDT Station - Foundation Bolt & Inserts - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-05-22 16:46 | 2025-05-30 16:46
603F-PR-4770 | IDT Station - Foundation Bolt & Inserts-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-22 16:46 | 2025-05-30 16:46
603F-PR-4780 | IDT Station - Rail-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 54 | 54 | 0 | 0 | 1 | 2025-05-18 08:47 | 2025-05-28 08:47
603F-PR-4790 | IDT Station - Rail-Receipt For Site-Lot-03 | Solar-MT38-A | IDT Station - Rail - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-05-22 08:47 | 2025-05-30 08:47
603F-PR-4790 | IDT Station - Rail-Receipt For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 54 | 54 | 0 | 0 | 1 | 2025-05-22 08:47 | 2025-05-30 08:47
603F-PR-4800 | IDT Station - Structure, Sheeting & Fasteners-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 225 | 225 | 0 | 0 | 1 | 2025-12-28 07:00 | 2025-12-29 17:00
603F-PR-4810 | IDT Station - Structure, Sheeting & Fasteners-Receipt At Site-Lot-03 | Solar-MT22-A | IDT Shed - Supply | Material | 9 | 9 | 0 | 0 | 1 | 2026-01-02 07:00 | 2026-01-03 17:00
603F-PR-4810 | IDT Station - Structure, Sheeting & Fasteners-Receipt At Site-Lot-03 | Solar-MT23-A | IDT Sheeting - Supply | Material | 9 | 9 | 0 | 0 | 1 | 2026-01-02 07:00 | 2026-01-03 17:00
603F-PR-4810 | IDT Station - Structure, Sheeting & Fasteners-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 225 | 225 | 0 | 0 | 1 | 2026-01-02 07:00 | 2026-01-03 17:00
603F-PR-4820 | LT Cable - Support Structure-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 54 | 54 | 0 | 0 | 1 | 2025-05-30 07:00 | 2025-06-02 17:00
603F-PR-4830 | LT Cable - Support Structure-Receipt At Site-Lot-03 | Solar-MT39-A | LT Cable - Support Structure - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-06-01 07:00 | 2025-06-12 17:00
603F-PR-4830 | LT Cable - Support Structure-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 54 | 54 | 0 | 0 | 1 | 2025-06-01 07:00 | 2025-06-12 17:00
603F-PR-4840 | LT Cable - Fasteners-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-30 16:42 | 2025-05-30 16:42
603F-PR-4850 | LT Cable - Fasteners-Receipt At Site-Lot-03 | Solar-MT40-A | LT Cable - Fasteners - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-05-04 16:42 | 2025-05-04 16:42
603F-PR-4850 | LT Cable - Fasteners-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-04 16:42 | 2025-05-04 16:42
603F-PR-4860 | LT Cable - Messenger Wire-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-04-10 07:00 | 2025-05-25 17:00
603F-PR-4870 | LT Cable - Messenger Wire-Receipt At Site-Lot-03 | Solar-MT41-A | LT Cable - Messenger wire - Supply | Material | 37 | 0 | 0 | 0 | 0 | 2025-04-10 07:00 | 2025-05-31 17:00
603F-PR-4870 | LT Cable - Messenger Wire-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-04-10 07:00 | 2025-05-31 17:00
603F-PR-4880 | LT Cable - Clamps-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-23 07:00 | 2025-05-27 17:00
603F-PR-4890 | LT Cable - Clamps-Receipt At Site-Lot-03 | Solar-MT42-A | LT Cable - Clamps - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-04-10 07:00 | 2025-05-31 17:00
603F-PR-4890 | LT Cable - Clamps-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-04-10 07:00 | 2025-05-31 17:00
603F-PR-4900 | LT Cable - Hangers-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-05-23 07:00 | 2025-12-23 17:00
603F-PR-4910 | LT Cable - Hangers-Receipt At Site-Lot-03 | Solar-MT43-A | LT Cable - Hangers - Supply | Material | 9 | 9 | 0 | 0 | 1 | 2025-04-10 | 2025-12-26 17:00
603F-PR-4910 | LT Cable - Hangers-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 135 | 135 | 0 | 0 | 1 | 2025-04-10 | 2025-12-26 17:00
603F-PR-4920 | LT Cable-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 1521 | 1521 | 0 | 0 | 1 | 2025-10-13 07:00 | 2025-10-27 17:00
603F-PR-4930 | LT Cable-Receipt At Site-Lot-03 | Solar-MT29-A | LT Cable - Supply | Material | 111 | 0 | 0 | 0 | 0 | 2025-10-28 07:00 | 2025-11-01 17:00
603F-PR-4930 | LT Cable-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 1521 | 1521 | 0 | 0 | 1 | 2025-10-28 07:00 | 2025-11-01 17:00
603F-PR-4940 | Control Cables-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 27 | 27 | 0 | 0 | 1 | 2025-05-30 07:00 | 2025-06-08 17:00
603F-PR-4950 | Control Cables-Receipt At Site-Lot-03 | Solar-MT32-A | Control Cable - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-06-06 07:00 | 2025-06-15 17:00
603F-PR-4950 | Control Cables-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 27 | 27 | 0 | 0 | 1 | 2025-06-06 07:00 | 2025-06-15 17:00
603F-PR-4960 | HT Cable-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 2070 | 2070 | 0 | 0 | 1 | 2025-09-17 07:00 | 2025-11-18 17:00
603F-PR-4970 | HT Cable-Receipt At Site-Lot-03 | Solar-MT30-A | HT Cable - Supply | Material | 36 | 0 | 0 | 0 | 0 | 2025-11-16 07:00 | 2025-11-27 17:00
603F-PR-4970 | HT Cable-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 2070 | 2070 | 0 | 0 | 1 | 2025-11-16 07:00 | 2025-11-27 17:00
603F-PR-4980 | Fiber Optic Cable-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 18 | 27 | 0 | 0 | 1 | 2025-11-17 07:00 | 2025-11-20 17:00
603F-PR-4990 | Fiber Optic Cable-Receipt At Site-Lot-03 | Solar-MT31-A | FO Cable - Supply | Material | 10 | 0 | 0 | 0 | 0 | 2025-11-21 07:00 | 2025-11-22 17:00
603F-PR-4990 | Fiber Optic Cable-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 18 | 27 | 0 | 0 | 1 | 2025-11-21 07:00 | 2025-11-22 17:00
603F-PR-5000 | Inverter Structure - Support Beam & Column-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-11-26 07:00 | 2025-11-29 17:00
603F-PR-5010 | Inverter Structure - Support Beam & Column-Receipt At Site-Lot-03 | Solar-MT44-A | Inverter Structure - Support beam & Column - Supply | Material | 419 | 419 | 0 | 0 | 1 | 2025-12-28 07:00 | 2026-01-03 17:00
603F-PR-5010 | Inverter Structure - Support Beam & Column-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-12-28 07:00 | 2026-01-03 17:00
603F-PR-5020 | Inverter Structure - Fasteners-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-05-30 07:00 | 2025-05-30 17:00
603F-PR-5030 | Inverter Structure - Fasteners-Receipt At Site-Lot-03 | Solar-MT45-A | Inverter Structure - Fasteners - Supply | Material | 419 | 0 | 0 | 0 | 0 | 2025-06-04 07:00 | 2025-06-04 17:00
603F-PR-5030 | Inverter Structure - Fasteners-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-06-04 07:00 | 2025-06-04 17:00
603F-PR-5040 | Inverter Structure - Canopy-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-07-01 07:00 | 2025-07-10 07:00
603F-PR-5050 | Inverter Structure - Canopy-Receipt At Site-Lot-03 | Solar-MT46-A | Inverter Structure - Canopy - Supply | Material | 419 | 0 | 0 | 0 | 0 | 2025-07-04 07:00 | 2025-07-14 17:00
603F-PR-5050 | Inverter Structure - Canopy-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-07-04 07:00 | 2025-07-14 17:00
603F-PR-5060 | Inverter Structure - Self Tapping Screw-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-03-30 07:00 | 2025-03-31 17:00
603F-PR-5070 | Inverter Structure - Self Tapping Screw-Receipt At Site-Lot-03 | Solar-MT47-A | Inverter Structure - Self Tapping Screw - Supply | Material | 419 | 0 | 0 | 0 | 0 | 2025-04-01 07:00 | 2025-04-02 17:00
603F-PR-5070 | Inverter Structure - Self Tapping Screw-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-04-01 07:00 | 2025-04-02 17:00
603F-PR-5080 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Dispatch From China-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 0 | 0 | 0 | 0 | 0 | 2025-06-12 07:00 | 2025-06-12 17:00
603F-PR-5090 | Robotic Cleaning System - Robots (Incl Docking & Return Station)-Transportation & Custom Clearance-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 0 | 0 | 0 | 0 | 0 | 2025-06-08 07:00 | 2025-09-09 17:00
603F-PR-5110 | Robotic Cleaning System - Robotic Structure-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 477 | 0 | 0 | 0 | 0 | 2025-09-01 07:00 | 2025-09-07 17:00
603F-PR-5120 | Robotic Cleaning System - Robotic Structure-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 477 | 0 | 0 | 0 | 0 | 2025-09-06 07:00 | 2025-09-12 17:00
603F-PR-5120 | Robotic Cleaning System - Robotic Structure-Receipt At Site-Lot-03 | Solar-MT17-A | Robot Structure - Bridges - Supply | Material | 351 | 0 | 0 | 0 | 0 | 2025-09-06 07:00 | 2025-09-12 17:00
603F-PR-5120 | Robotic Cleaning System - Robotic Structure-Receipt At Site-Lot-03 | Solar-MT15-A | Robot Structure - Docking-Supply | Material | 351 | 0 | 0 | 0 | 0 | 2025-09-06 07:00 | 2025-09-12 17:00
603F-PR-5120 | Robotic Cleaning System - Robotic Structure-Receipt At Site-Lot-03 | Solar-MT16-A | Robot Structure - Reverse - Supply | Material | 351 | 0 | 0 | 0 | 0 | 2025-09-06 07:00 | 2025-09-12 17:00
603F-PR-5130 | DC Cable-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 1269 | 1539 | 0 | 0 | 1 | 2025-09-03 07:00 | 2025-11-24 17:00
603F-PR-5140 | DC Cable-Receipt At Site-Lot-03 | Solar-MT13-A | DC Cable - Supply | Material | 1098 | 0 | 0 | 0 | 0 | 2025-10-06 07:00 | 2025-11-27 17:00
603F-PR-5140 | DC Cable-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 1269 | 1539 | 0 | 0 | 1 | 2025-10-06 07:00 | 2025-11-27 17:00
603F-PR-5150 | Mc4 Connector-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-06-01 07:00 | 2025-06-19 17:00
603F-PR-5160 | Mc4 Connector-Receipt For Site-Lot-03 | Solar-MT14-A | MC4 Connector - Supply | Material | 419 | 0 | 0 | 0 | 0 | 2025-06-01 07:00 | 2025-06-30 17:00
603F-PR-5160 | Mc4 Connector-Receipt For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-06-01 07:00 | 2025-06-30 17:00
603F-PR-5190 | SCADA-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 72 | 72 | 0 | 0 | 1 | 2025-05-18 07:00 | 2025-05-25 07:00
603F-PR-5200 | SCADA-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 72 | 72 | 0 | 0 | 1 | 2025-05-21 07:00 | 2025-05-31 17:00
603F-PR-5200 | SCADA-Receipt At Site-Lot-03 | Solar-MT50-A | SCADA - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-05-21 07:00 | 2025-05-31 17:00
603F-PR-5210 | IDT Fencing & Gate-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-06-14 07:00 | 2025-06-18 17:00
603F-PR-5220 | IDT Fencing & Gate-Receipt At Site-Lot-03 | Solar-MT26-A | IDT - Fencing - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-06-20 07:00 | 2025-06-23 17:00
603F-PR-5220 | IDT Fencing & Gate-Receipt At Site-Lot-03 | Solar-MT27-A | IDT - Gate - Supply | Material | 9 | 0 | 0 | 0 | 0 | 2025-06-20 07:00 | 2025-06-23 17:00
603F-PR-5220 | IDT Fencing & Gate-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 9 | 9 | 0 | 0 | 1 | 2025-06-20 07:00 | 2025-06-23 17:00
603F-PR-5230 | Electrical AC/DC Works-Dispatch For Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 594 | 594 | 0 | 0 | 1 | 2025-07-01 07:00 | 2025-07-10 17:00
603F-PR-5240 | Electrical AC/DC Works-Receipt At Site-Lot-03 | Solar-MT51-A | Electrical AC DC Material - Supply | Material | 9 | 9 | 0 | 0 | 1 | 2025-07-18 07:00 | 2025-07-19 17:00
603F-PR-5240 | Electrical AC/DC Works-Receipt At Site-Lot-03 | Solar-MP14 | Procurement Resource | Labor | 594 | 594 | 0 | 0 | 1 | 2025-07-18 07:00 | 2025-07-19 17:00
603F-PR-6000 | Civil, MMS & Module Installation Works-Boq & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 18162 | 18162 | 0 | 0 | 1 | 2025-03-06 07:00 | 2025-03-09 17:00
603F-PR-6010 | Civil, Mms & Module Installation Works-TBER | Solar-MP14 | Procurement Resource | Labor | 18162 | 18162 | 0 | 0 | 1 | 2025-03-06 07:00 | 2025-03-17 17:00
603F-PR-6020 | Civil, MMS & Module Installation Works-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 18162 | 18162 | 0 | 0 | 1 | 2025-03-18 07:00 | 2025-03-18 17:00
603F-PR-6030 | Civil, MMS & Module Installation Works-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 18162 | 18162 | 0 | 0 | 1 | 2025-03-18 07:00 | 2025-03-19 17:00
603F-PR-6040 | Civil, Mms & Module Installation Works-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 18162 | 18162 | 0 | 0 | 1 | 2025-03-20 07:00 | 2025-03-21 17:00
603F-PR-6050 | Electrical AC DC Works-BOQ & Tech Specs Release | Solar-MP14 | Procurement Resource | Labor | 18162 | 18162 | 0 | 0 | 1 | 2025-03-06 07:00 | 2025-03-09 17:00
603F-PR-6060 | Electrical AC DC Works-TBER | Solar-MP14 | Procurement Resource | Labor | 18162 | 18162 | 0 | 0 | 1 | 2025-03-06 07:00 | 2025-03-17 17:00
603F-PR-6070 | Electrical AC DC Works-Purchase Requistion | Solar-MP14 | Procurement Resource | Labor | 18162 | 18162 | 0 | 0 | 1 | 2025-03-18 07:00 | 2025-03-18 17:00
603F-PR-6080 | Electrical AC DC Works-Note For Approval | Solar-MP14 | Procurement Resource | Labor | 18162 | 18162 | 0 | 0 | 1 | 2025-03-18 07:00 | 2025-03-19 17:00
603F-PR-6090 | Electrical AC DC Works-LOI / PO Release | Solar-MP14 | Procurement Resource | Labor | 18162 | 18162 | 0 | 0 | 1 | 2025-03-20 07:00 | 2025-03-21 17:00
PR-CA-04-010 | Consent To Establish (CTE) Pollution Board (Under Intimation Of State PCB) | Solar-MP15 | Land Resource | Labor | 15138 | 15138 | 0 | 0 | 1 | 2025-03-11 08:00 | 2025-03-11 16:00
PR-CA-27-015 | EAR Policy | Solar-MP15 | Land Resource | Labor | 15138 | 15138 | 0 | 0 | 1 | 2025-03-23 08:00 | 2025-03-29 16:00
PR-CA-27-017 | GST No. Certificate | Solar-MP15 | Land Resource | Labor | 15138 | 15138 | 0 | 0 | 1 | 2025-02-15 08:00 | 2025-02-15 16:00
PR-CA-27-018 | Contract Labour Registration (CLRA) Liscense | Solar-MP15 | Land Resource | Labor | 15138 | 15138 | 0 | 0 | 1 | 2025-02-15 08:00 | 2025-02-15 16:00
PR-CA-27-019 | Registration Under Buildings And Other Construction Works (BOCW) | Solar-MP15 | Land Resource | Labor | 15138 | 15138 | 0 | 0 | 1 | 2025-02-15 08:00 | 2025-02-15 16:00
PR-CA-27-020 | SPV Name Finalization | Solar-MP15 | Land Resource | Labor | 15138 | 15138 | 0 | 0 | 1 | 2025-02-28 08:00 | 2025-03-05 16:00