## 1. Read Me
DPR ↔ Oracle P6 — Data Mapping Scheme
What this is | A field-level map of how data moves between the DPR application and Oracle P6, in both directions, for every sheet in the DPR. Each row names the exact source and destination, the transform applied, and the file that does it.
Two directions
P6 → DPR (inbound) | Tab 3. A scheduled/triggered sync pulls Projects, WBS, Activities and Resource Assignments from the P6 REST API into our Postgres tables. The DPR sheets are then rendered FROM those tables — no sheet calls P6 directly.
DPR → P6 (outbound) | Tab 4. Only runs on an explicit Push to P6 of an approved entry. Writes back Actual dates, Status, Percent Complete and Actual/Remaining Units. Nothing is auto-pushed on save.
Source of truth
P6 owns | Activity identity (Id, Name), the schedule (Planned/Baseline/Forecast dates), the resource assignments and their Planned Units. A re-sync overwrites our copy of these.
DPR owns | Daily progress figures, DPR-level (custom) activities, contractor manpower, productivity, machinery, charging schedule, issues, and every column in tab 7. A re-sync never touches these — see the guard rules on tab 3.
Shared / contested | Actual Start, Actual Finish, Percent Complete, Scope (Total Quantity) and UOM are written from both sides. Tab 8 sets out which write wins and when.
Reading the tabs
Tab 2 | Pipeline overview — every hop, with the file that performs it.
Tab 3 | P6 → DPR field mapping (P6 object/field → our table/column).
Tab 4 | DPR → P6 field mapping (UI field → P6 REST payload field).
Tab 5 | Every DPR sheet across Solar / Wind / PSS / BESS, with its source and push behaviour.
Tab 6 | Column-level mapping for each row shape the sheets are built from.
Tab 7 | Data that exists only in the DPR and is never sent to P6.
Tab 8 | Row-matching keys and the write-precedence rules.
Colour key | Green = inbound (P6 → DPR). Orange = outbound (DPR → P6). Purple = DPR-only.
Generated from | Repo DPR_Latest_Prod @ branch main. Verified against the code, not documentation.

## 2. Pipeline Overview
Pipeline Overview — every hop, end to end
No DPR sheet talks to P6 directly. Everything inbound arrives via the sync into Postgres; everything outbound leaves via the push service on an approved entry.
# | Direction | Hop | What moves | Trigger | Performed by (file) | Lands in
1 | P6 → DPR | P6 REST: GET /project | Project header: dates, DataDate, EPS, baseline project id, summary labour units | Sync (manual / scheduled) | sync_all_p6_data.py → sync_data() | p6_projects, projects
2 | P6 → DPR | P6 REST: GET /resource | UnitOfMeasureName per resource — becomes the UOM shown on the sheets | Same sync run | sync_all_p6_data.py (resource_uom lookup) | in-memory lookup
3 | P6 → DPR | P6 REST: GET /calendar | HoursPerDay per calendar — drives the Hours/Day column on manpower sheets | Same sync run | sync_all_p6_data.py (calendar_hours lookup) | solar_activities.hours_per_day
4 | P6 → DPR | P6 REST: GET /resourceAssignment | Per-assignment Planned / Actual / Remaining units, resource type and id | Same sync run | sync_all_p6_data.py | solar_resource_assignments
5 | P6 → DPR | Aggregate Material assignments | SUM(PlannedUnits)=Scope, SUM(ActualUnits)=Cumulative, SUM(RemainingUnits)=Balance. Resources with WEIGHTAGE in the id are excluded. | Same sync run | sync_all_p6_data.py (ra_agg) | solar_activities.total_quantity / cumulative / balance
6 | P6 → DPR | P6 REST: GET /activity | Activity identity, status, WBS, planned / forecast / baseline / actual dates, % complete | Same sync run | sync_all_p6_data.py | solar_activities
7 | P6 → DPR | P6 REST: GET /wbs | WBS tree used for grouping and headings on the sheets | Same sync run | sync_all_p6_data.py | solar_wbs
8 | P6 → DPR | Sheet read API | Table rows shaped into the columns each DPR sheet expects (see tab 5 for which API per sheet) | User opens a sheet | app/routers/oracle_p6.py | HTTP response → React state
9 | DPR only | Draft create / open | A draft row per (supervisor, project, sheet, date). Carry-over fills the contractor sheet. | User opens a sheet for a date | app/routers/dpr_supervisor.py → get_draft_entry() | dpr_supervisor_entries
10 | DPR only | Save draft | Whole grid saved as data_json; per-row values also written out to the columns below | Save / autosave | app/routers/dpr_supervisor.py → save_draft_entry() | dpr_supervisor_entries.data_json
11 | DPR only | Save draft — writeback | Scope → total_quantity; actual/forecast dates → date columns; ~28 UI-only fields → dpr_metadata JSONB | Every save | app/routers/dpr_supervisor.py (save_draft_entry) | solar_activities
12 | DPR only | Save draft — daily progress | todayValue / yesterdayValue / history[] written per activity per date | Every save and on submit | dpr_supervisor.py → _write_daily_progress_from_entry() | dpr_daily_progress
13 | DPR only | Approval chain | draft → submitted_to_pm → approved_by_pm → final_approved (with reject paths). A versioned copy of data_json is kept at each step. | Supervisor / Site PM / PMAG action | app/routers/dpr_supervisor.py | dpr_supervisor_entries.status, dpr_entry_snapshots
14 | DPR → P6 | Push to P6 — resolve | row.activityId → solar_activities.activity_id (scoped to project) → object_id; then its resource assignments filtered by sheet type (Material or Labor) | Explicit 'Push to P6' on an approved entry | app/services/p6_push_service.py | (resolution only)
15 | DPR → P6 | P6 REST: PUT /activity | ActualStartDate, ActualFinishDate, Status, PercentComplete, PhysicalPercentComplete | Same push | p6_push_service.py → _push_activity_to_p6() | P6 Activity
16 | DPR → P6 | P6 REST: PUT /resourceAssignment | ActualUnits, RemainingUnits, PlannedUnits (only if scope changed), PercentComplete | Same push | p6_push_service.py → _push_resource_assignment_to_p6() | P6 Resource Assignment
17 | DPR → P6 | Audit trail | One row per field pushed: old value, new value, success/failure, P6 error text, who pushed | Same push | p6_push_service.py → _log_push_audit() | push_audit
18 | P6 → DPR | Next sync overwrites | P6 re-reads its own values back over ours. Guarded columns (tab 3) survive; the rest do not. | Next sync run | sync_all_p6_data.py | solar_activities, solar_resource_assignments

## 3. P6 to DPR (inbound)
P6 → DPR (inbound) · sync_all_p6_data.py
Base URL: https://sin1.p6.oraclecloud.com/adani/p6ws/restapi · paged at 500 rows · all dates via parse_date(), which also corrects P6 far-future years (>2100 → −100 years).
P6 object | P6 REST endpoint | P6 field | Transform applied | Our table | Our column | Overwritten on re-sync? | Where it surfaces in the DPR
Project | GET /project | ObjectId | int | p6_projects / projects | "ObjectId" / object_id | Yes (key) | Project selector, all sheets
Project | GET /project | Id | as-is | p6_projects / projects | "Id" / id | Yes | Project code
Project | GET /project | Name | as-is | p6_projects / projects | "Name" / name | Yes | Header on every sheet
Project | GET /project | ParentEPSName | as-is | p6_projects / projects | "ParentEPSName" / parent_eps | Yes | Drives project type + Rajasthan / Outside-Khavda / Mandvi sheet variants
Project | GET /project | DataDate | parse_date | p6_projects / projects | "DataDate" / data_date | Yes | Cut-off: progress on or before this date is P6's, after it is the DPR's
Project | GET /project | StartDate / FinishDate | parse_date | p6_projects / projects | start_date / finish_date | Yes | Summary sheets
Project | GET /project | SummaryBaselineStartDate / SummaryBaselineFinishDate | parse_date | projects | baseline_start / baseline_finish | Yes | Summary sheets
Project | GET /project | ScheduledFinishDate | parse_date | projects | scheduled_finish | Yes | Summary sheets
Project | GET /project | SummaryPlannedLaborUnits / SummaryActualLaborUnits | parse_float | projects | summary_planned_labor_units / summary_actual_labor_units | Yes | Summary / manpower rollups
Project | GET /project | CurrentBaselineProjectObjectId | int | p6_projects | "CurrentBaselineProjectObjectId" | Yes | Used to fetch the TRUE baseline dates (see Activity baseline rows below)
Project | GET /project | LastUpdateDate / LastUpdateUser | parse_date / as-is | p6_projects / projects | last_update_date / last_update_user | Yes (then overwritten by the latest activity's values) | 'Last updated' badge
Project | (derived) | Name + ParentEPSName keyword scan | WIND/WTG/LOC. → wind; PSS/SUBSTATION → pss; else solar | projects | project_type | Only if currently NULL or 'solar' — a manually set type is never overwritten | Which sheet set the project gets (tab 5)
WBS | GET /wbs | ObjectId / ParentObjectId / Code / Name / Status | as-is | solar_wbs | object_id / parent_object_id / code / name / status | Yes | Category headings and grouping
Resource | GET /resource | UnitOfMeasureName | lookup by ResourceObjectId | solar_activities | uom | Only when non-empty | UOM column on every progress sheet
Calendar | GET /calendar | HoursPerDay | lookup by CalendarObjectId, default 8.0 | solar_activities / solar_resource_assignments | hours_per_day | Yes | Hours/Day column on manpower sheets
Activity | GET /activity | ObjectId | int | solar_activities | object_id | Yes (key) | Internal row key
Activity | GET /activity | Id | as-is | solar_activities | activity_id | Yes | Activity ID column — the key the push matches on
Activity | GET /activity | Name | as-is | solar_activities | name | Yes | Description column
Activity | GET /activity | Status | as-is | solar_activities | status | Yes | Status column
Activity | GET /activity | Type | as-is | solar_activities | activity_type | Yes | —
Activity | GET /activity | WBSObjectId / WBSName | int / as-is | solar_activities | wbs_object_id / wbs_name | Yes | Phase / Block / category heading
Activity | GET /activity | PlannedStartDate | parse_date | solar_activities | planned_start | Yes | Plan Start (also the default row order)
Activity | GET /activity | PlannedFinishDate | parse_date | solar_activities | planned_finish | Yes | Plan Finish
Activity | GET /activity | StartDate | parse_date | solar_activities | start_date | Yes — but the DPR writes here too | Forecast Start
Activity | GET /activity | FinishDate | parse_date | solar_activities | finish_date | Yes — but the DPR writes here too | Forecast Finish
Activity | GET /activity | (baseline) 1. dates from CurrentBaselineProjectObjectId 2. Baseline1StartDate 3. BaselineStartDate | First non-null of the three, in that order | solar_activities | baseline_start | Yes | Baseline Start. BL1 is only a fallback — it is not necessarily the baseline P6 has designated as current.
Activity | GET /activity | (baseline) same precedence for finish | First non-null of the three | solar_activities | baseline_finish | Yes | Baseline Finish
Activity | GET /activity | ActualStartDate | parse_date | solar_activities | actual_start | Yes — contested, see tab 8 | Actual Start
Activity | GET /activity | ActualFinishDate | parse_date | solar_activities | actual_finish | Yes — contested, see tab 8 | Actual Finish
Activity | GET /activity | PercentComplete | parse_float, stored RAW. P6 returns a 0–1 fraction: 117,559 of the 119,130 non-zero rows in the current database are ≤ 1. The UI multiplies by 100 to display it. See the scale warning on tab 8. | solar_activities | percent_complete | Yes — contested | Physical Progress %
Activity | GET /activity | Notes | as-is | solar_activities | remarks | Yes | Remarks (P6-sourced)
Activity | GET /activity | LastUpdateDate / LastUpdateUser | parse_date / as-is | solar_activities | p6_last_update_date / p6_last_update_user | Yes | Audit column
Activity | (derived from RA) | SUM(PlannedUnits) over Material assignments, excluding resource ids containing WEIGHTAGE | parse_float, summed per activity | solar_activities | total_quantity | GUARDED — only overwritten when the incoming sum > 0, so a DPR-entered scope survives a sync that returns 0 | Scope / Total Quantity
Activity | (derived from RA) | SUM(ActualUnits) over the same assignments | parse_float, summed | solar_activities | cumulative | GUARDED — same condition as total_quantity | Completed / Cumulative
Activity | (derived from RA) | SUM(RemainingUnits) over the same assignments | parse_float, summed | solar_activities | balance | GUARDED — same condition as total_quantity | Balance
ResourceAssignment | GET /resourceAssignment | ObjectId | int | solar_resource_assignments | object_id | Yes (key) | assignmentId on manpower timephased rows
ResourceAssignment | GET /resourceAssignment | ActivityObjectId | int | solar_resource_assignments | activity_object_id | Yes | Join back to the activity
ResourceAssignment | GET /resourceAssignment | ResourceId / ResourceName | as-is | solar_resource_assignments | resource_id / resource_name | Yes | Resource column / resource picker
ResourceAssignment | GET /resourceAssignment | ResourceType | as-is — 'Material' ¦ 'Labor' ¦ 'Nonlabor' | solar_resource_assignments | resource_type | Yes | Decides which sheet an assignment belongs to: Material → progress sheets, Labor → manpower, Nonlabor → date anchoring only
ResourceAssignment | GET /resourceAssignment | PlannedUnits | parse_float | solar_resource_assignments | planned_units | Yes | Scope basis + proportional split on push
ResourceAssignment | GET /resourceAssignment | ActualUnits | parse_float | solar_resource_assignments | actual_units | Yes — contested | Completed / Actual Days
ResourceAssignment | GET /resourceAssignment | RemainingUnits | parse_float | solar_resource_assignments | remaining_units | Yes — contested | Balance / Remaining Days
ResourceAssignment | GET /resourceAssignment | BudgetAtCompletionUnits | parse_float | solar_resource_assignments | budget_at_completion_units | Yes | Budgeted Days
ResourceAssignment | GET /resourceAssignment | AtCompletionUnits | parse_float | solar_resource_assignments | at_completion_units | Yes | At-completion rollups
ResourceAssignment | GET /resourceAssignment | UnitsPercentComplete | parse_float | solar_resource_assignments | percent_complete | Yes | % Completion
ResourceAssignment | GET /resourceAssignment | ActualStartDate / ActualFinishDate | parse_date | solar_resource_assignments | actual_start / actual_finish | Yes | Manpower actual dates

## 4. DPR to P6 (outbound)
DPR → P6 (outbound) · app/services/p6_push_service.py
Runs only on an explicit Push to P6. Nothing is pushed on save or on submit. Every field below is written to push_audit with its old and new value, success/failure and the P6 error text.
DPR field (data_json key) | Fallback keys accepted | P6 REST call | P6 payload field | Transform / rule | Condition — when is it sent | Audited as
activityId | — | (resolution) | — | SELECT object_id FROM solar_activities WHERE activity_id = :activityId AND project_object_id = :project | Always first. If it does not resolve, the row is skipped and counted as skipped. | —
actualStart | actualStartDate, actualForecastStart | PUT /activity | ActualStartDate | parse_date → '<ISO>T08:00:00'. The fixed time stops P6 rolling the date back a day across time zones. | Whenever the row carries a start date (full override — the DPR value always wins) | ActualStartDate
actualFinish | actualFinishDate, actualForecastFinish | PUT /activity | ActualFinishDate | parse_date → '<ISO>T16:00:00'. Same time-zone guard. | Whenever the row carries a finish date (full override) | ActualFinishDate
status | Status | PUT /activity | Status | Normalised to P6's vocabulary: not started → 'Not Started'; in progress¦started → 'In Progress'; completed¦finished → 'Completed' | If blank or 'unknown', it is DERIVED: a finish date → Completed, else a start date → In Progress | Status
completionPercentage | percentComplete, progress | PUT /activity | PercentComplete + PhysicalPercentComplete | value ÷ 100 (P6 takes 0.0–1.0). A computed value from the resource assignments takes precedence over the typed one. | When dates or quantities are being pushed | PhysicalPercentComplete
(rule) actual finish present | — | PUT /activity | PercentComplete = 1.0 | Forced to 100%. P6's own rule: an activity with an ActualFinishDate IS complete. | Overrides any lower value in the row | PhysicalPercentComplete
(rule) actual start, no finish, no % | — | PUT /activity | PercentComplete = 0.01 | A 1% anchor. Without >0 actual units P6 discards the start date on the next schedule recalculation — the 'vanishing dates' problem. | Only when no percentage could be worked out any other way | PhysicalPercentComplete
cumulative | actualQty, actual | PUT /resourceAssignment | ActualUnits | SINGLE assignment: ActualUnits = the value as-is. MULTIPLE: split by each assignment's share of PlannedUnits (planned ÷ total planned). | First choice for the actual figure | ActualUnits
completed | — | PUT /resourceAssignment | ActualUnits | Same single/proportional rule. Used by the Wind, PSS and BESS progress sheets, which carry a cumulative 'Completed' rather than a daily figure. | Used when 'cumulative' is absent | ActualUnits
todayValue | — | PUT /resourceAssignment | ActualUnits | INCREMENTAL: ActualUnits = existing ActualUnits + todayValue (proportionally split across multiple assignments). This is the only incremental path — the two above are absolute. | Last resort, when neither cumulative nor completed is present | ActualUnits
(derived) | — | PUT /resourceAssignment | RemainingUnits | max(0, PlannedUnits − ActualUnits). Never negative. | Always sent alongside ActualUnits | RemainingUnits
scope | totalQuantity | PUT /resourceAssignment | PlannedUnits | Only sent when it differs from the current summed PlannedUnits by more than 0.01. Split proportionally across multiple assignments. | Scope-change detection — otherwise PlannedUnits is left alone | PlannedUnits
selectedResourceId | — | (targeting) | — | Narrows the push to one resource assignment. If the activity has exactly one assignment it is selected automatically. | Optional — set from the Resource picker on the sheet | —
(rule) activity has no Material/Labor assignments | — | PUT /resourceAssignment | ActualUnits on the Nonlabor (Weightage) assignment | ActualUnits = PlannedUnits × (percent ÷ 100). Anchors the dates for activities that carry no real resource — Testing, Clearance and similar. | Only when the activity push succeeded and a percentage was computed | ActualUnits
uom | — | (local only) | — | Written to solar_activities.uom via COALESCE — never sent to P6. | When present on the row | —
agencyName | vendor, vendorName | (local only) | — | Written to solar_activities.agency_name — never sent to P6. | When present | —
lineKm | — | (local only) | — | Written to solar_activities.line_km — never sent to P6. | When present | —
totalPole | — | (local only) | — | Written to solar_activities.total_pole — never sent to P6. | When present | —
Which resource assignments a sheet writes to (SHEET_RESOURCE_MAP)
Sheet type | P6 resource filter | Meaning
dp_qty, dp_block, dp_vendor_idt, dp_vendor_block, dc_sheet, ac_sheet, testing_commissioning | MT → resource_type = 'Material' | Quantity-bearing progress sheets
wind_progress, wind_summary | MT → resource_type = 'Material' | Wind progress
pss_progress, pss_summary | MT → resource_type = 'Material' | PSS progress
bess_civil, bess_electrical, bess_bop, bess_testing, bess_dp_qty | MT → resource_type = 'Material' | BESS progress
manpower_details, manpower_details_2 | MP → resource_type = 'Labor' | Solar manpower
wind_manpower, pss_manpower, bess_manpower | MP → resource_type = 'Labor' | Wind / PSS / BESS manpower
Any sheet NOT in this list | — none — | Push is rejected with 'does not support P6 push' (see tab 7)

## 5. All DPR Sheets
Every sheet in the DPR — all four project types
sheet_type is the value stored on dpr_supervisor_entries and the key used everywhere else. Sheets marked 'No' under Pushes to P6 are rejected by the push service — their data lives only in the DPR.
Project type | Sheet ID (sheet_type) | Tab label | Data entry? | Where the rows come from | Backing table(s) | Pushes to P6? | P6 resource type | Notes
Solar | summary | Summary | No | Derived from the other solar sheets | solar_activities | No | — | Read-only rollup
Solar | dp_qty | DP Qty | No | GET /oracle-p6/dp-qty-data → rebuilt on every open | solar_activities + dpr_daily_progress | Yes | Material | Cumulative recomputed server-side from daily progress
Solar | dc_sheet | DC Side | Yes | GET /oracle-p6/dc-sheet-data | solar_activities (+ dpr_metadata) | Yes | Material | Vendor / plot columns come from dpr_metadata
Solar | ac_sheet | AC Side | Yes | GET /oracle-p6/ac-sheet-data | solar_activities (+ dpr_metadata) | Yes | Material | Most columns are DPR-only, held in dpr_metadata
Solar | testing_commissioning | Testing & Commissioning | Yes | universal_progress_rebuild on the saved draft | solar_activities + dpr_daily_progress | Yes | Material | Usually has no Material resource — dates anchored via Nonlabor
Solar | manpower_details | Labour Days | Yes | GET /oracle-p6/manpower-details-data | solar_resource_assignments (Labor) | Yes | Labor | Falls back to activity rows when no Labor resource exists
Solar | manpower_details_2 | Manpower (Contractor) | Yes | Carried across dates from the DPR's own history | dpr_supervisor_entries only | Yes (mapped MP) | Labor | On Mandvi it is a fully manual sheet with a fixed activity list — see tab 7
Solar | resource | Machinery Sheet | Yes | Typed by hand | dpr_supervisor_entries only | No | — | DPR-only
Solar | issues | Issues | No | Issues module | issues | No | — | DPR-only
Solar | switchyard | Switchyard | Yes | universal_progress_rebuild | solar_activities + dpr_daily_progress | No | — | Rajasthan projects only
Solar | transmission_line | Transmission Line | Yes | universal_progress_rebuild | solar_activities + dpr_daily_progress | No | — | Rajasthan projects only
Solar | infra_works | Infra Works | Yes | universal_progress_rebuild | solar_activities + dpr_daily_progress | No | — | Rajasthan projects only
Wind | wind_summary | Summary | No | Derived from wind_progress in the browser | solar_activities | Yes | Material | Read-only rollup
Wind | wind_progress | Progress Sheet | Yes | GET /dpr-activities/wind-progress/{id} | solar_activities + dpr_metadata | Yes | Material | Feeder, vendor, coords, soil-test status all live in dpr_metadata
Wind | wind_stone_column | Stone Column | Yes | Derived: one row per WTG location | solar_activities | No | — | Row per WTG, sorted numerically
Wind | wind_33kv | 33KV | Yes | GET /oracle-p6/wind-33kv-data/{id} | solar_activities | No | — | One row per unique WTG location
Wind | wind_33kv_oh | 33KV OH | Yes | Typed by hand | dpr_supervisor_entries only | No | — | DPR-only
Wind | wind_erection | Erection | Yes | Starts empty — locations defined by the user | dpr_supervisor_entries only | No | — | DPR-only
Wind | wind_manpower | Labour Days | Yes | GET /oracle-p6/manpower-details-data | solar_resource_assignments (Labor) | Yes | Labor | —
Wind | manpower_details_2 | Manpower (Contractor) | Yes | Mandvi: manual, fixed activity list. Others: P6 timephased. | dpr_supervisor_entries / solar_resource_assignments | Yes (mapped MP) | Labor | See tab 7 for the standing activity list
Wind | wind_machinery | Machinery Sheet | Yes | Typed by hand | dpr_supervisor_entries only | No | — | DPR-only
Wind | wind_productivity | Productivity | Yes | GET /oracle-p6/wind-achievements/{id} | solar_activities counts + wind_achievements | No | — | Resource counts typed in; work done counted from P6 activities
Wind | wind_pss | PSS | Yes | GET /oracle-p6/wind-pss-data/{id} | solar_activities | No | — | Outside-Khavda projects only
Wind | wind_ehv | EHV | Yes | GET /oracle-p6/wind-ehv-data/{id} | solar_activities | No | — | Outside-Khavda projects only
Wind | issues | Issues | No | Issues module | issues | No | — | DPR-only
PSS | pss_summary | Summary | No | Derived | solar_activities | Yes | Material | Read-only rollup
PSS | pss_civil_peb | Civil and PEB | Yes | GET /oracle-p6/pss-civil-peb-data/{id} | solar_activities grouped by WBS heading | No | — | Grouped into category headings by WBS name pattern
PSS | pss_electrical | Electrical | Yes | GET /oracle-p6/pss-electrical-data/{id} | solar_activities grouped by WBS heading | No | — | Same heading grouping
PSS | pss_tl_visual | 400KV Transmission Visual | Yes | GET /oracle-p6/pss-transmission-visual/{id} | solar_activities | No | — | —
PSS | pss_transmission | 400KV Transmission | Yes | GET /oracle-p6/pss-progress-data/{id} | solar_activities | No | — | Supports DPR-level activities
PSS | pss_manpower | Manpower | Yes | GET /oracle-p6/manpower-details-data | solar_resource_assignments (Labor) | Yes | Labor | —
PSS | manpower_details_2 | Manpower (Contractor) | Yes | P6 timephased resources | solar_resource_assignments | Yes (mapped MP) | Labor | —
PSS | issues | Issues | Yes | Issues module | issues | No | — | DPR-only
BESS | bess_summary | Summary | No | Derived from bess_dp_qty in the browser | solar_activities | No | — | Read-only rollup
BESS | bess_dp_qty | DP Qty | Yes | GET /oracle-p6/bess-data/{id}?category=... (all three merged) | solar_activities + dpr_custom_activities | Yes | Material | Rolls up Civil + Electrical + Testing, including DPR-level rows
BESS | bess_civil | Civil | Yes | GET /oracle-p6/bess-data/{id}?category=civil | solar_activities + dpr_custom_activities | Yes | Material | Bulk upload of DPR activities; delete via the bin in Remarks
BESS | bess_electrical | Electrical | Yes | GET /oracle-p6/bess-data/{id}?category=electrical | solar_activities + dpr_custom_activities | Yes | Material | Bulk upload of DPR activities; delete via the bin in Remarks
BESS | bess_testing | Testing & Comm. | Yes | GET /oracle-p6/bess-data/{id}?category=testing | solar_activities + dpr_custom_activities | Yes | Material | Bulk upload of DPR activities; delete via the bin in Remarks
BESS | bess_bop | BOP | Yes | GET /oracle-p6/bess-data/{id}?category=bop | solar_activities + dpr_custom_activities | Yes | Material | Registered for push; not on the default tab list
BESS | bess_manpower | Manpower | Yes | GET /oracle-p6/manpower-details-data | solar_resource_assignments (Labor) | Yes | Labor | —
BESS | bess_productivity | Productivity | Yes | Typed by hand | dpr_supervisor_entries only | No | — | DPR-only
BESS | bess_charging_schedule | Charging Schedule | Yes | Typed by hand | dpr_supervisor_entries only | No | — | DPR-only
BESS | issues | Issues | No | Issues module | issues | No | — | DPR-only

## 6. Sheet Field Mapping
Column-level mapping, by row shape
The DPR sheets are built from a handful of shared row shapes rather than one shape per sheet. Mapping the shapes covers every sheet; tab 5 says which shape each sheet uses.
Row shape (used by) | UI column | data_json key | Read from (P6 → DPR) | Written to on save (DPR → local) | Pushed to P6 as | Direction
DP Qty (dp_qty, bess_dp_qty) | Sl No | slNo | Row counter — not stored | — | — | DPR only
DP Qty (dp_qty, bess_dp_qty) | Activity ID | activityId | solar_activities.activity_id ← P6 Activity.Id | — | Match key for the push | P6 → DPR
DP Qty (dp_qty, bess_dp_qty) | Description | description | solar_activities.name ← P6 Activity.Name | — | — | P6 → DPR
DP Qty (dp_qty, bess_dp_qty) | Total Quantity | totalQuantity | solar_activities.total_quantity ← SUM(PlannedUnits) | solar_activities.total_quantity | PlannedUnits (only if changed >0.01) | Both ways
DP Qty (dp_qty, bess_dp_qty) | UOM | uom | solar_activities.uom ← P6 Resource.UnitOfMeasureName | solar_activities.uom | Not sent to P6 | Both ways
DP Qty (dp_qty, bess_dp_qty) | Base Plan Start / Finish | basePlanStart / basePlanFinish | solar_activities.planned_start / planned_finish | — | — | P6 → DPR
DP Qty (dp_qty, bess_dp_qty) | Forecast Start / Finish | forecastStart / forecastFinish | solar_activities.start_date / finish_date | solar_activities.start_date / finish_date | Not sent to P6 | Both ways
DP Qty (dp_qty, bess_dp_qty) | Actual Start | actualStart | solar_activities.actual_start | solar_activities.actual_start | Activity.ActualStartDate (T08:00:00) | Both ways
DP Qty (dp_qty, bess_dp_qty) | Actual Finish | actualFinish | solar_activities.actual_finish | solar_activities.actual_finish | Activity.ActualFinishDate (T16:00:00) | Both ways
DP Qty (dp_qty, bess_dp_qty) | Phase | phase | solar_activities.wbs_name ← P6 Activity.WBSName | — | — | P6 → DPR
DP Qty (dp_qty, bess_dp_qty) | Yesterday | yesterdayValue | dpr_daily_progress for entry_date − 1 | dpr_daily_progress | — | DPR only
DP Qty (dp_qty, bess_dp_qty) | Today | todayValue | dpr_daily_progress for entry_date | dpr_daily_progress | ActualUnits (incremental, last-resort path) | Both ways
DP Qty (dp_qty, bess_dp_qty) | Cumulative | cumulative | COMPUTED: SUM(today_value) for all dates before entry_date, + today | — | ActualUnits (absolute — first choice) | Both ways
DP Qty (dp_qty, bess_dp_qty) | Balance | balance | COMPUTED: totalQuantity − cumulative, floored at 0 | — | RemainingUnits | DPR → P6
DP Qty (dp_qty, bess_dp_qty) | Block Capacity / SPV / Priority / Plot / Scope / Front / Hold / New Block Nom | blockCapacity, spvNumber, priority, plot, scope, front, hold, newBlockNom | solar_activities columns of the same name | solar_activities.dpr_metadata (JSONB) | Not sent to P6 | DPR only
DP Qty (dp_qty, bess_dp_qty) | Remarks | remarks | Draft only | dpr_supervisor_entries.data_json | Not sent to P6 | DPR only
Progress grid (pss_*, bess_civil/electrical/testing, wind_pss, wind_ehv) | Activity ID | activityId | solar_activities.activity_id, or DPR-{project}-{id} for a DPR-level row | — | Match key | P6 → DPR
Progress grid (pss_*, bess_civil/electrical/testing, wind_pss, wind_ehv) | Description | description | solar_activities.name / dpr_custom_activities.description | dpr_custom_activities.description (DPR rows) | — | P6 → DPR
Progress grid (pss_*, bess_civil/electrical/testing, wind_pss, wind_ehv) | Block | block | solar_activities.new_block_nom → plot → wbs_name (first non-empty) | dpr_metadata.block / dpr_custom_activities.block | — | Both ways
Progress grid (pss_*, bess_civil/electrical/testing, wind_pss, wind_ehv) | Status | status | solar_activities.status ← P6 Activity.Status | dpr_custom_activities.status | Activity.Status (normalised / derived) | Both ways
Progress grid (pss_*, bess_civil/electrical/testing, wind_pss, wind_ehv) | Priority | priority | dpr_metadata.priority | dpr_metadata.priority | Not sent to P6 | DPR only
Progress grid (pss_*, bess_civil/electrical/testing, wind_pss, wind_ehv) | Duration | duration | extraData.duration | dpr_custom_activities.extra_data | Not sent to P6 | DPR only
Progress grid (pss_*, bess_civil/electrical/testing, wind_pss, wind_ehv) | Plan Start / Plan Finish | plannedStart / plannedFinish | solar_activities.planned_start / planned_finish | dpr_custom_activities.planned_start / planned_finish | — | P6 → DPR
Progress grid (pss_*, bess_civil/electrical/testing, wind_pss, wind_ehv) | Actual Start / Actual Finish | actualStart / actualFinish | solar_activities.actual_start / actual_finish | solar_activities.actual_start / actual_finish | Activity.ActualStartDate / ActualFinishDate | Both ways
Progress grid (pss_*, bess_civil/electrical/testing, wind_pss, wind_ehv) | Forecast Start / Finish | forecastStart / forecastFinish | solar_activities.start_date / finish_date | dpr_metadata / extra_data | Not sent to P6 | Both ways
Progress grid (pss_*, bess_civil/electrical/testing, wind_pss, wind_ehv) | SO Vendor Name | soVendorName | dpr_metadata.soVendorName | dpr_metadata.soVendorName | Not sent to P6 | DPR only
Progress grid (pss_*, bess_civil/electrical/testing, wind_pss, wind_ehv) | UOM | uom | solar_activities.uom | solar_activities.uom / dpr_custom_activities.uom | Not sent to P6 | Both ways
Progress grid (pss_*, bess_civil/electrical/testing, wind_pss, wind_ehv) | Scope | scope | solar_activities.total_quantity | solar_activities.total_quantity | PlannedUnits (only if changed) | Both ways
Progress grid (pss_*, bess_civil/electrical/testing, wind_pss, wind_ehv) | Completed | completed | solar_activities.cumulative ← SUM(ActualUnits) | dpr_metadata.completed / dpr_custom_activities.cumulative | ActualUnits (absolute) | Both ways
Progress grid (pss_*, bess_civil/electrical/testing, wind_pss, wind_ehv) | Physical Progress % | physicalProgress | solar_activities.percent_complete, ×100 for display — see the scale warning on tab 8 | extra_data.physicalProgress | PercentComplete ÷ 100 — but a computed value wins | Both ways
Progress grid (pss_*, bess_civil/electrical/testing, wind_pss, wind_ehv) | Balance | balance | COMPUTED: Scope − Completed, floored at 0 | — | RemainingUnits | DPR → P6
Progress grid (pss_*, bess_civil/electrical/testing, wind_pss, wind_ehv) | Remarks | remarks | solar_activities.remarks ← P6 Activity.Notes | dpr_custom_activities.remarks | Not sent to P6 | Both ways
Progress grid (pss_*, bess_civil/electrical/testing, wind_pss, wind_ehv) | 7 day columns (BESS only) | historyValues{ISO date} | dpr_daily_progress by date | dpr_daily_progress + extra_data.historyValues | Rolled into ActualUnits | DPR only
Wind Progress (wind_progress) | Activity ID / Description / Status | activityId / description / status | solar_activities | — | Match key / Status | Both ways
Wind Progress (wind_progress) | Substation / SPV / Location / Activity Group | substation / spv / locations / activityGroup | dpr_metadata, else parsed from the activity name | dpr_metadata | Not sent to P6 | DPR only
Wind Progress (wind_progress) | Feeder | feeder | dpr_metadata.feeder | dpr_metadata.feeder | Not sent to P6 | DPR only
Wind Progress (wind_progress) | WTG FDN Vendor | wtgFdnVendor | dpr_metadata.wtgFdnVendor | dpr_metadata.wtgFdnVendor | Not sent to P6 | DPR only
Wind Progress (wind_progress) | FDN Allotment Date | fdnAllotmentDate | dpr_metadata.fdnAllotmentDate | dpr_metadata.fdnAllotmentDate | Not sent to P6 | DPR only
Wind Progress (wind_progress) | Stone Column Contractor | stoneColumnContractor | dpr_metadata.stoneColumnContractor | dpr_metadata.stoneColumnContractor | Not sent to P6 | DPR only
Wind Progress (wind_progress) | Soil Test Status | soilTestStatus | dpr_metadata.soilTestStatus | dpr_metadata.soilTestStatus | Not sent to P6 | DPR only
Wind Progress (wind_progress) | Coord E / Coord N | wtgCoordE / wtgCoordN | dpr_metadata.wtgCoordE / wtgCoordN | dpr_metadata | Not sent to P6 | DPR only
Wind Progress (wind_progress) | Resource | selectedResourceId | solar_resource_assignments.resource_id | dpr_metadata.selectedResourceId | Targets which assignment the push writes to | Both ways
Wind Progress (wind_progress) | Scope / Completed / Physical Progress % | scope / completed / physicalProgress | solar_activities | solar_activities + dpr_metadata | PlannedUnits / ActualUnits / PercentComplete | Both ways
Wind Progress (wind_progress) | Baseline Start | baselineStart | solar_activities.baseline_start (current baseline, BL1 fallback) | — | — | P6 → DPR
Labour Days (manpower_details, wind_manpower, pss_manpower, bess_manpower) | Activity ID / Description | activityId / description | solar_activities via the Labor assignment | — | Match key | P6 → DPR
Labour Days (manpower_details, wind_manpower, pss_manpower, bess_manpower) | Block | block | solar_activities.new_block_nom → plot → wbs_name | dpr_metadata.block | — | Both ways
Labour Days (manpower_details, wind_manpower, pss_manpower, bess_manpower) | Hours/Day | hoursPerDay | solar_resource_assignments.hours_per_day ← P6 Calendar.HoursPerDay (default 8) | — | — | P6 → DPR
Labour Days (manpower_details, wind_manpower, pss_manpower, bess_manpower) | Budgeted Days | budgetedUnits | solar_resource_assignments.planned_units ← PlannedUnits | — | PlannedUnits (only if scope changed) | P6 → DPR
Labour Days (manpower_details, wind_manpower, pss_manpower, bess_manpower) | Actual Days | actualUnits | solar_resource_assignments.actual_units ← ActualUnits | — | ActualUnits | Both ways
Labour Days (manpower_details, wind_manpower, pss_manpower, bess_manpower) | Remaining Days | remainingUnits | solar_resource_assignments.remaining_units ← RemainingUnits | — | RemainingUnits | Both ways
Labour Days (manpower_details, wind_manpower, pss_manpower, bess_manpower) | % Completion | percentComplete | solar_resource_assignments.percent_complete ← UnitsPercentComplete | — | PercentComplete ÷ 100 | Both ways
Labour Days (manpower_details, wind_manpower, pss_manpower, bess_manpower) | Required / Available / Gap | required / available / gap | Draft only — Gap is computed as Required − Available | dpr_supervisor_entries.data_json | Not sent to P6 | DPR only
Labour Days (manpower_details, wind_manpower, pss_manpower, bess_manpower) | Day columns (7) | history[] / historyValues{} | dpr_daily_progress | dpr_daily_progress | Rolled into ActualUnits | DPR only
Contractor Manpower (manpower_details_2) | Sr No | (row position) | Position in the standing activity order — see tab 7 | — | — | DPR only
Contractor Manpower (manpower_details_2) | Activity | activity | Fixed standing list (Mandvi) — no P6 source | dpr_supervisor_entries.data_json | Not sent to P6 | DPR only
Contractor Manpower (manpower_details_2) | Contractor | contractor | Typed by hand; carried across dates | dpr_supervisor_entries.data_json | Not sent to P6 | DPR only
Contractor Manpower (manpower_details_2) | SO Scope / UOM | soScope / uom | Typed by hand | dpr_supervisor_entries.data_json | Not sent to P6 | DPR only
Contractor Manpower (manpower_details_2) | Agreed Manpower (per day) | agreedValues{ISO date} | Typed by hand, keyed by the date it was entered against | dpr_supervisor_entries.data_json | Not sent to P6 | DPR only
Contractor Manpower (manpower_details_2) | Available Manpower (per day) | availableValues{ISO date} | Typed by hand, keyed by the date it was entered against | dpr_supervisor_entries.data_json | Not sent to P6 | DPR only
Contractor Manpower (manpower_details_2) | (non-Mandvi variant) | assignmentId | solar_resource_assignments.object_id — the row key for P6 timephased rows | dpr_supervisor_entries.data_json | ActualUnits on that assignment | Both ways
Machinery (resource, wind_machinery) | Sr no / Vendor Name / Area / Equipment Name | srNo / vendorName / area / equipmentName | Typed by hand — no P6 source | dpr_supervisor_entries.data_json | Not sent to P6 | DPR only
Machinery (resource, wind_machinery) | Day columns | (date-keyed) | Typed by hand | dpr_supervisor_entries.data_json | Not sent to P6 | DPR only

## 7. DPR-Only Data
DPR-only data — never sent to P6
This is the part of the DPR that P6 has no concept of. A re-sync cannot damage any of it, because the sync only writes the tables and columns listed on tab 3.
What | Where it lives | How it is created | Why it never reaches P6 | Survives a P6 re-sync?
DPR-level (custom) activities | dpr_custom_activities | Added inline ('Add DPR Activity') or bulk-uploaded from a spreadsheet on BESS Civil / Electrical / Testing | They do not exist in P6 — there is no ObjectId to write against. Activity ids are minted locally as DPR-{project}-{id}. | Yes — separate table
Daily progress figures | dpr_daily_progress | Written on every draft save, keyed (activity, date, sheet_type) | P6 holds only a cumulative ActualUnits, not a per-day series. The daily detail is the DPR's alone; only the total is pushed. | Yes — separate table
Draft grids and their history | dpr_supervisor_entries.data_json | Every save writes the whole grid as JSON | It is the working document, not a schedule fact. | Yes — separate table
Approval snapshots | dpr_entry_snapshots | A versioned copy at each approval step, with who and when | Audit record of the DPR workflow. | Yes — separate table
Contractor manpower | dpr_supervisor_entries (manpower_details_2) | Typed by hand against a fixed activity list on Mandvi; carried across dates automatically | Agreed vs Available manpower per contractor per day has no P6 equivalent. | Yes — separate table
Wind standing activity list | Code constant, both sides | WIND_CONTRACTOR_ACTIVITIES: Soil Test, WTG Foundation, USS Electrical, 33KV Line, Road & Crane Pad, PSS, 220KV Line, WTG Erection, WTG Main Crane Package, Misc Packages | A fixed reporting layout, not a schedule. Every date renders in this order so the dates line up. | n/a — code
Machinery sheets | dpr_supervisor_entries (resource, wind_machinery) | Typed by hand | Plant on site is not modelled in the P6 schedule. | Yes — separate table
Productivity (Wind) | wind_achievements + counts from solar_activities | Resource counts (Rigs / Gangs / Cranes) typed per month; work done counted from P6 activities | The ratio is a reporting measure, not a schedule field. | Yes — separate table
Productivity & Charging Schedule (BESS) | dpr_supervisor_entries | Typed by hand | No P6 equivalent. | Yes — separate table
Issues | issues | Raised in the Issues module | Not a schedule object. | Yes — separate table
UI-only activity attributes (~28 fields) | solar_activities.dpr_metadata (JSONB) | Merged on every draft save: feeder, wtgFdnVendor, fdnAllotmentDate, stoneColumnContractor, soilTestStatus, wtgCoordE/N, substation, spv, locations, vendorName, soVendorName, contractorName, priority, noOfDays, selectedResourceId, completed, remarks, agencyName, plot, newBlockNom, block, holdDueToWtg, front, vendor, baselinePriority | P6 has no field for any of them. | Yes — dpr_metadata is a column the sync never writes to
Column show/hide preferences | column_preferences | Per user, per project, per sheet | Presentation only. | Yes
Push audit trail | push_audit | One row per field per push attempt | It is the record OF the push. | Yes

## 8. Keys & Precedence
Row-matching keys and write precedence
How a row on a DPR sheet is tied to a P6 object, and who wins when both sides write the same field.
Topic | Rule | Where it is enforced | Consequence if it goes wrong
Primary row key (outbound) | row.activityId → SELECT object_id FROM solar_activities WHERE activity_id = :activityId AND project_object_id = :project | p6_push_service.py → _get_activity_object_id() | No match → the row is silently skipped and counted as 'skipped' in the push summary.
Row key (inbound) | P6 Activity.ObjectId is the primary key of solar_activities; ON CONFLICT (object_id) DO UPDATE | sync_all_p6_data.py | An activity deleted in P6 is cleaned up by the stale-record sweep.
Resource assignment key | P6 ResourceAssignment.ObjectId → solar_resource_assignments.object_id, exposed to the UI as assignmentId | sync_all_p6_data.py / manpower-timephased-data | A changed assignment id orphans the manpower row's typed values.
DPR-level activity key | Minted locally as DPR-{projectId}-{id}; resolved against dpr_custom_activities, never against P6 | custom_activities.py / dpr_supervisor.py | Never pushed — by design.
Activity resolution fallbacks | For daily progress the lookup tries, in order: (1) activity_id ILIKE, (2) object_id as an integer, (3) activity NAME ILIKE, (4) dpr_custom_activities.activity_id, (5) the DPR-{project}-{id} pattern | dpr_supervisor.py → _write_daily_progress_from_entry() | The name-match step can bind progress to the wrong activity if two activities share a name.
Scope / UOM / Cumulative / Balance | GUARDED on the way in: the sync only overwrites total_quantity, uom, balance and cumulative when the incoming value is non-zero / non-empty. A DPR-entered scope therefore survives a sync that returns nothing. | sync_all_p6_data.py (CASE WHEN … in the ON CONFLICT clause) | Without the guard, an activity with no Material resource in P6 would have its DPR scope zeroed on every sync.
Actual Start / Actual Finish | CONTESTED. The DPR pushes them as a full override — a value typed on the sheet always wins over P6's. But the next inbound sync writes P6's values back over ours, so P6 wins in the end. | p6_push_service.py (dates_override) vs sync_all_p6_data.py | A date typed in the DPR but never pushed is lost at the next sync. Push before syncing.
Percent Complete — SCALE WARNING | The scale is NOT consistent, and this is worth knowing before anyone builds a report on the column. P6 returns PercentComplete as a 0–1 fraction and the sync stores it raw: 117,559 of the 119,130 non-zero rows currently in solar_activities are ≤ 1. But 1,571 rows sit above 1, of which 1,321 are exactly 100 — so the same column holds both scales. The UI multiplies by 100 to display, which is right for the fraction rows and wrong for the rest. | sync_all_p6_data.py (stores raw) / formatPhysicalProgress() in PSSProgressTable.tsx (×100) | The 1,321 rows at exactly 100 display as 10000%. A code comment in PSSProgressTable.tsx asserts the opposite convention ('stored 0-100 … never scaled') and contradicts the code beneath it.
Percent Complete — on push | The push computes its own percentage from the resource assignments — (Σ ActualUnits ÷ Σ PlannedUnits) × 100, capped at 100 — which is genuinely on a 0–100 scale, then divides by 100 for P6's 0.0–1.0 API. This computed value takes precedence over any percentage typed on the sheet. | p6_push_service.py → _push_activity_to_p6() | The computed path is self-consistent. A raw typed percentage passed straight through is the ambiguous case.
dpr_metadata | DPR-owned. The sync never writes this column, so it is safe from any P6 round-trip. | dpr_supervisor.py (JSONB merge with ¦¦) | None — this is the safe place for UI-only fields.
Vanishing dates guard | An activity with an ActualStartDate but zero actual units has its start date discarded by P6 on the next schedule recalculation. The push therefore always sends at least 1% (or 100% when a finish date is present). | p6_push_service.py | Without it, dates pushed successfully disappear from P6 a day later.
Weightage resources | Resource ids containing WEIGHTAGE are excluded from the Scope / Cumulative / Balance aggregation, but ARE used as Nonlabor anchors for activities that carry no real resource. | sync_all_p6_data.py (is_material) / p6_push_service.py | Including them would inflate Scope on every activity that carries one.
Data date | Daily progress is only counted into the cumulative when progress_date > the project's DataDate. Anything on or before it is already reflected in P6's own ActualUnits. | dpr_supervisor.py → universal_progress_rebuild() | Ignoring it double-counts progress that P6 has already absorbed.
Push preconditions | Only an entry whose sheet_type appears in SHEET_RESOURCE_MAP can be pushed; a row needs an activityId plus at least one of todayValue / completed / actual dates / uom / status, or it is skipped. | p6_push_service.py → push_approved_entry_to_p6() | A sheet missing from the map is rejected outright with 'does not support P6 push'.