BRD for DPR Phase-III

Business Requirements Document Template

To aid in the creation of a successfully complete BRD document, please adhere to the following guidelines

| Purpose | A requirement is a documented condition or capability to which the product, service, or system must conform in meeting project objectives. Requirements management is a systematic approach to eliciting, organizing, and documenting the requirements of the product, service, or system. The Business Requirements Definition document serves as the project baseline that explains, in business terms, what is to be accomplished as a business outcome being delivered by implementing a technology solution. Because requirements are dynamic, the BRD is a progressive document in that the objective is to record what is known at the time and then build on it as the project progresses. It is from this document that the more specific design documentation (Solution Requirement Specification) can be produced based on the needs of the project and any unique and/or complementary methodology. The business requirement document (BRD) describes the high-level business needs whereas the Solution Requirement Document outlines the functions required to fulfil the business needs. BRD answers the questions what the business wants to do whereas the Solution Requirements Specification gives an answer to how it should be done. Whereas a business requirement states the “why” for a project, a functional requirement outlines the “what”. Functional requirements are very detailed and provide information on how business needs and goals will be delivered through a specific project/program. |
| --- | --- |
| Objective | The objective of a business requirement document. To get an agreement among stakeholders Communicate with the IT/Tech/Analytics/Cybersecurity teams, the business needs, the customer needs, and what the solution need to do to satisfy business and customer outcomes. To determine the input to the next phase of project Describe the details of the needs of the customer and business that the solution intends to meet The BRD is also the mechanism by way we at Adani drive standardization of tools, platforms, solutions across the group. The cost associated with the tools, platform proliferation on both licensing and as well as implementation teams add to greater expense, training, and quality issues |
| Key Elements | A business unit representative who has a thorough understanding of the business processes drafts the BRD and is the owner of the BRD. The most critical component of a business requirement document is the scope of the project/initiative/innovation along with the restriction and constraints. The scope comprises of three key things What are the problems which the business wants to solve? What are the restrictions? Is it worth investing the time and money required for the project? The Value proposition has to be approximate and signed off by the BU Owner/Leadership Defining business requirements is mandatory required deliverable for all projects |
| BRD Template Completion | Collecting requirements is not as straightforward as it may first appear. It can become challenging because requirements: - aren’t always obvious - can come from many and varied sources - need to be managed by cross-functional groups of people - can be hard to express clearly in words - can be expressed at different levels of detail For a project that is an enhancement to an existing product, service, or system, the project team reviews existing documentation; therefore, the BRD tends to be briefer. However, a project that is developing a new product, service, or system would tend to generate a longer and more detailed document. - Do not include the Template Guidelines in your final document. Enter the project information document contributors and version control. - Complete the document utilizing suggested text where applicable. Note that the blue text is NOT to be included in your final document. Its purpose is to either provide guidance for completing the document - Once changes are made to your document and you’re ready to finalize, ensure that you update your Table of Contents (TOC) section. - Route the document for review and approval to those individuals identified as per the process flow - Because the BRD is a dynamic document, once the Project Team obtains approval, the BRD is to be retained and modified as necessary to record any additional, changed, or cancelled requirements. - If changes are to be made, update the Revision History information accordingly. - The Business Requirements Definition document is to be retained with other project-related documentation and maintained in accordance with the business line’s records retention policy. |
| Empowerment & Scalability | This template is provided as a guideline to follow in producing the minimum basic information needed to successfully complete a Business Requirements Definition document. Business Teams are empowered to use this template as needed to address any specific requirements of the proposed project at hand. The amount of detail included in the template will depend on the size and complexity of the project. Depending on project or business line needs, requirements can be added, |
| Ownership | The primary ownership and responsibility of generating the Business Requirement Document is with the Business Unit, Section 3,4,5 of the document has to be written and owned by the business Section 6 is to be filled in by the appropriate BU Service Teams (IT/Tech/Analytics/CyberSecurity) Section 7,8,9 has to be filled up jointly by BU Owner and BU Service Teams |

Document Control

| S.No. | Name | Role | Signature |
| --- | --- | --- | --- |
| 1 | Priyanka Pandey | Author – BA, Cognitbotz |  |
| 2 | Prashant Khanderia | Reviewer – DM, Cognitbotz |  |
| 3 | Adithya Kumar | Approver – DGM, Adani |  |

Revision History

| Revision | Date of Change | Revision Description |
| --- | --- | --- |
| NA | NA | NA |

Referenced Documents

| Ref No. | Document ID | Document Title |
| --- | --- | --- |
|  | NA | NA |

Confidentiality

This document contains restricted information pertaining to Adani. The access level for the document is specified above. The addressee should honour this access rights by preventing intentional or accidental access outside the access scope.

Disclaimer

This document is solely for the information of Adani and should not be used, circulated, quoted or otherwise referred to for any other purpose, nor included or referred to in whole or in part in any document without our prior written consent.

Table of Contents

2.1 In-Scope	7

2.2 Out of Scope	7

4.1 As-Is Business Process (Current State)	9

4.2 To-Be Business Process (Future State – New / Changed)	9

5.	Business Use Cases	10

6.	Business Requirements	11

7.	Functional Requirements	13

8.	Non-Functional Requirements	15

9.	Solution Overview	16

10.	Key Constraints and Assumptions	19

11.	System Integration Details	20

13.	Expected Business Outcomes	23

14.	Risk & Mitigation	24

15.	Estimations and timeline	25

16. Schedule Dependencies	26

- Purpose

The purpose of this BRD is to define the business requirements for DPR Phase III, which aims to transform DPR into a unified EPC execution platform integrating Engineering, Procurement, Construction, Material Management, Reconciliation, SAP, and Primavera P6.
The document serves as a baseline for solution design, development, testing, and deployment.

- Scope

DPR Phase-III covers end-to-end EPC execution with real-time material intelligence, vendor accountability, and management visibility across Solar, Wind, and PSS projects.

### 2.1 In-Scope

- Engineering document and drawing management

- BOQ and material quantity derivation

- Procurement lifecycle tracking (PR, PO, SO, delivery, GRN)

- Material planning, issuance, return, and reconciliation

- Vendor‑wise and block‑wise material accountability

- JMR automation

- SAP and Primavera P6 integrations

- Role‑based dashboards and reporting

### 2.2 Out of Scope

The following items are explicitly excluded from the scope of this BRD:

- Financial accounting beyond SAP references

- Non-EPC project execution

- Third-party vendor systems not defined in integrations

- Terms and Definitions

| Term / Acronym | Definition |
| --- | --- |
| Primavera P6 (P6) | The enterprise planning and scheduling system used as the core engine for work breakdown structures, activity sequencing, baselines, critical path analysis, and planned vs actual progress tracking. |
| Digital DPR (Daily Progress Report) | A centralized digital system for capturing, approving, and monitoring daily site progress, replacing Excel-based reporting and synchronizing approved execution data with Primavera P6. |
| DPR | Daily Progress Report capturing site-level execution updates, delays, issues, and dependencies, subject to approval workflows before integration with planning systems. |
| SAP | The enterprise ERP system used for procurement, inventory management, PO/SO tracking, financial approvals, and integration with project execution data. |
| PMAG | Project Monitoring and Assurance Group responsible for creating projects, governance, cross-project execution oversight, schedule assurance, risk identification, and escalation management. |
| EPC | Engineering, Procurement, Construction |
| BOQ | Bill of Quantities |
| AFC | Approved for Construction |
| SO | Service Order |
| GRN | Goods Receipt Note |
| JMR | Joint Measurement Record |
| MIRS | Material Issue Receipt Slip |
| MRRS | Material Return Receipt Slip |
| PO (Purchase Order) | A commercial document issued through SAP authorizing procurement of materials or services, subject to amendments and approval workflows. |
| SO (Sales Order) | A commercial document recorded in SAP representing vendor or supplier commitments linked to procurement and delivery timelines. |
| PO/SO Amendments | Approved changes to purchase or sales orders that may impact project timelines, logistics planning, and CAPEX forecasts. |
| Alerts & Notifications | Automated system-generated messages triggered by delays, risks, deviations, or approval requirements across integrated systems. |

- Business Requirements Summary

AGEL currently uses Oracle Primavera P6 for planning and DPR for execution progress tracking. However, gaps exist in material visibility, procurement tracking, and cross-functional integration across Engineering, Procurement, and Construction. DPR Phase III aims to transform DPR into a unified EPC execution and material intelligence platform by integrating Engineering, Procurement, Material Management, Reconciliation, SAP, and Primavera P6 into a single ecosystem.

## 4.1 As-Is Business Process (Current State)

| Process ID | Scope / Steps |
| --- | --- |
| AS 1 | Project planning and scheduling are managed independently in Primavera P6, with no real-time operational linkage to material availability or execution readiness. |
| AS 2 | Daily execution progress is captured in DPR based on site inputs, without validating dependencies such as engineering approvals or material readiness. |
| AS 3 | Material master, stock, and procurement data exist in SAP but are not actively leveraged during execution planning or activity validation in DPR. |
| AS 4 | DPR records physical progress even when materials are unavailable, leading to execution risks, rework, and inaccurate progress reporting. |
| AS 5 | BOQ preparation and revisions are handled manually or offline, with limited linkage to engineering drawings and site execution quantities. |
| AS 6 | Material issue, return, and consumption tracking are maintained through manual registers or spreadsheets, lacking system-driven validation and audit trails. |
| AS 7 | Material reconciliation and JMR preparation are manual, time-consuming, and prone to discrepancies across site, store, and billing teams. |
| AS 8 | Engineering, Procurement, and Construction teams operate in silos, resulting in limited management-level visibility, delayed decision-making, and reactive issue resolution. |

## 4.2 To-Be Business Process (Future State – New / Changed)

| Process ID | Scope / Steps |
| --- | --- |
| TB 1 | DPR functions as a centralized EPC execution platform, serving as the single system of record for Engineering, Procurement, Construction, and Material Management activities. |
| TB 2 | Engineering drawings are centrally managed with revision and AFC control and are mandatorily linked to activities before execution is allowed. |
| TB 3 | BOQ and material quantities are system-derived from engineering drawings, with automatic recalculation on drawing revisions and impact analysis on procurement and execution. |
| TB 4 | Procurement lifecycle is tracked end-to-end (PR, PO, SO, dispatch, delivery, GRN) with SAP synchronization and linkage to BOQ, activities, and vendors. |
| TB 5 | Construction execution is validated by the system by enforcing dependencies on approved drawings, procurement completion, and material availability before progress capture. |
| TB 6 | Material planning, allocation, and issuance are automated at block-wise and vendor-wise levels, with system-controlled quantity limits based on approved BOQ. |
| TB 7 | Material reconciliation and JMR generation are system-driven, with vendor-wise reconciliation statements, approval workflows, audit trails, and SAP reference linkage. |
| TB 8 | Unified real-time dashboards provide operational and management users with visibility into EPC readiness, material risks, procurement delays, and vendor performance. |

- Business Use Cases

| Use Case # | Use Case Name | Primary Business Requirement Addressed | Main Action |
| --- | --- | --- | --- |
| UC-01 | Centralized EPC Execution Management | BR-01, BR-02, BR-07 | Use DPR as the single platform to execute EPC activities with enforced dependencies on engineering approvals, procurement status, and material availability. |
| UC-02 | Engineering-Driven BOQ & Material Planning | BR-02, BR-03, BR-04, BR-05 | Manage engineering drawings and revisions to automatically derive BOQ quantities and compute material requirements for execution and procurement planning. |
| UC-03 | End-to-End Procurement Lifecycle Tracking | BR-06, BR-07 | Track PR, PO, SO, dispatch, delivery, and GRN statuses synchronized with SAP and validated before construction progress is recorded. |
| UC-04 | Block-wise & Vendor-wise Material Issuance | BR-08, BR-09, BR-10, BR-16 | Allocate, issue, and return materials by block and vendor with BOQ-controlled limits and full audit traceability. |
| UC-05 | Automated Material Reconciliation | BR-10, BR-11, BR-16 | Generate vendor-wise and SO-wise material reconciliation statements with multi-level approval workflows. |
| UC-06 | JMR Generation & Billing Readiness | BR-12 | Auto-generate Joint Measurement Records from executed quantities and link them to BOQ and Service Orders for billing reference. |
| UC-07 | Workflow, Alerts & Governance | BR-13, BR-14 | Execute configurable approval workflows and notify stakeholders through alerts, escalations, and delay notifications. |
| UC-08 | EPC Management Visibility & Decision Support | BR-15 | Provide real-time dashboards and KPIs for operational teams and management to monitor EPC readiness, risks, and vendor performance. |

  - Business Requirements

| BR ID | Business Requirement | Description / Business Need | Business Outcome / Value |
| --- | --- | --- | --- |
| BR-01 | Centralized EPC Execution Platform | DPR shall act as a single source of truth for Engineering, Procurement, Construction, and Material Management data and processes. | Eliminates data silos and improves cross-functional coordination. |
| BR-02 | Engineering Document Control | The system shall maintain a Master Document List (MDL) with drawing revisions, approval status, and AFC control mapped to execution activities. | Prevents execution on unapproved drawings and improves design governance. |
| BR-03 | Engineering-Driven BOQ Management | BOQ shall be derived and maintained based on approved engineering drawings at project, block, activity, vendor, and revision levels. | Ensures quantity accuracy and alignment between design and execution. |
| BR-04 | Automated BOQ & Material Recalculation | Any drawing revision shall automatically trigger BOQ updates, material requirement recalculation, and procurement impact analysis. | Reduces manual errors and prevents downstream material mismatches. |
| BR-05 | Material Requirement Planning | The system shall calculate daily, weekly, and monthly material requirements based on BOQ, execution plans, and progress. | Improves material availability planning and reduces site disruptions. |
| BR-06 | End-to-End Procurement Visibility | DPR shall track PR, PO, SO, dispatch, delivery, GRN, and inspection statuses with SAP synchronization. | Provides transparency and early risk identification in procurement. |
| BR-07 | Execution Dependency Enforcement | Construction execution shall be allowed only when engineering approvals, procurement status, and material availability criteria are met. | Prevents premature execution and rework. |
| BR-08 | Block-wise & Vendor-wise Material Allocation | Materials shall be allocated, issued, and returned at block and vendor levels with BOQ-based quantity controls. | Establishes vendor accountability and controlled material usage. |
| BR-09 | Material Issue & Return Control | Material issues and returns shall be system-recorded with audit trails and auto-generated MIRS/MRRS. | Improves inventory accuracy and traceability. |
| BR-10 | Consumption & Variance Monitoring | The system shall compare planned consumption against actual issuance and execution quantities. | Reduces material wastage and highlights abnormal consumption. |
| BR-11 | Automated Material Reconciliation | DPR shall auto-generate vendor-wise and SO-wise reconciliation with approval workflows across Site, Store, Billing, and PM. | Minimizes disputes and reconciliation cycle time. |
| BR-12 | JMR Automation | Joint Measurement Records shall be system-generated from executed quantities and linked to BOQ and SO. | Accelerates billing and improves measurement accuracy. |
| BR-13 | Workflow & Approval Governance | The system shall support configurable approval workflows with role-based access and audit logging. | Strengthens process compliance and accountability. |
| BR-14 | Alerts & Notifications | DPR shall provide system alerts, email notifications, escalation reminders, and dependency/delay alerts. | Enables proactive issue resolution. |
| BR-15 | Management Dashboards & KPIs | Real-time dashboards shall provide EPC readiness, procurement risks, material shortages, and vendor performance visibility. | Supports informed, faster management decision-making. |
| BR-16 | Vendor Accountability | The system shall clearly identify issued, consumed, returned, and recoverable material quantities per vendor. | Improves contractual control and cost recovery. |

  - Functional Requirements

| Req # | Description |  |
| --- | --- | --- |
| FR-01 | Engineering Document Repository | The system shall provide a centralized repository to store, manage, and track all engineering documents and drawings across projects. |
| FR-02 | Master Document List (MDL) Management | The system shall maintain a Master Document List including document/drawing number, revision, approval status, and AFC identification. |
| FR-03 | Engineering–P6 Activity Mapping | Engineering deliverables shall be mapped to Primavera P6 activities, and drawing delays or revisions shall reflect on dashboards and alerts. |
| FR-04 | AFC Dependency Enforcement | The system shall block construction progress updates unless the relevant AFC drawing is available and approved. |
| FR-05 | Multi-Level BOQ Management | The system shall maintain BOQ at project, block, activity, vendor, and revision levels with version control. |
| FR-06 | BOQ Revision History | The system shall retain complete BOQ revision history and identify the latest approved BOQ version for execution. |
| FR-07 | Activity-to-Material Mapping | Activities shall be mapped to materials with defined consumption norms reusable across projects. |
| FR-08 | BOQ-Driven Material Requirement Calculation | The system shall auto-calculate material requirements and forecast shortages based on planned and actual execution quantities. |
| FR-09 | AutoCAD-Based BOQ Derivation | The system shall support BOQ generation from AutoCAD drawings using layer-wise quantity extraction and block-wise derivation. |
| FR-10 | BOQ Recalculation on Drawing Change | Any drawing revision shall automatically trigger BOQ updates, material recalculation, and procurement impact analysis. |
| FR-11 | Procurement Lifecycle Tracking | The system shall track PR, PO, SO, dispatch, delivery, GRN, inspection, and MDCC status for all materials and services. |
| FR-12 | Vendor & SO Management | The system shall maintain vendor profiles with SO mapping, scope definition, activity allocation, and performance indicators. |
| FR-13 | SAP Procurement Synchronization | SO and vendor data shall be synchronized from SAP and mapped to BOQ quantities, activities, and vendor allocations in DPR. |
| FR-14 | Procurement-Based Execution Validation | The system shall validate construction execution against procurement completion and material availability status. |
| FR-15 | Material Requirement Planning (MRP) | The system shall calculate daily, weekly, and monthly material requirements by activity and block. |
| FR-16 | Real-time Stock Validation | Planned material requirements shall be compared with SAP-fetched inventory in real time to identify shortages. |
| FR-17 | Block-wise & Vendor-wise Allocation | Site users shall allocate material quantities by block and vendor, with system-enforced limits based on BOQ quantities. |
| FR-18 | Automated Issuance Request Generation | The system shall auto-generate material issuance requests upon successful allocation approval. |
| FR-19 | Material Issue Tracking | Materials issued shall be linked to Vendor, Block, Activity, and SO, with automatic stock balance updates. |
| FR-20 | Material Return Tracking | The system shall record material returns with quantity, reason, approval, and audit trail. |
| FR-21 | MIRS & MRRS Generation | The system shall auto-generate Material Issue Receipt Slips (MIRS) and Material Return Receipt Slips (MRRS) downloadable in Excel and PDF formats. |
| FR-22 | Consumption & Variance Monitoring | The system shall calculate expected material consumption from executed quantities and BOQ norms and flag variances. |
| FR-23 | Vendor-wise Material Reconciliation | The system shall generate reconciliation statements showing issued, consumed, returned, pending, and recoverable quantities by vendor and SO. |
| FR-24 | Reconciliation Approval Workflow | Material reconciliation shall follow a multi-level approval workflow: Site → Store → Billing → PM. |
| FR-25 | Reconciliation History & Audit Logs | The system shall maintain full reconciliation history, revisions, approvals, and audit records. |
| FR-26 | JMR Auto-Generation | The system shall auto-generate Joint Measurement Records from executed quantities and link them to BOQ and SO. |
| FR-27 | Drawing-Based Quantity Extraction for JMR | The system shall support drawing uploads and area-based quantity extraction for JMR preparation. |
| FR-28 | Configurable Workflow Management | The system shall provide configurable approval workflows for engineering, BOQ, material issuance, reconciliation, JMR, and vendor allocations. |
| FR-29 | Notifications & Alerts | The system shall generate email notifications, system alerts, escalation reminders, and dependency/delay alerts for relevant stakeholders. |

  - Non-Functional Requirements

The following non-functional requirements define quality, performance, security, and reliability expectations:

| Req # | Non-Functional Requirement | Description |
| --- | --- | --- |
| NFR-01 | Data Accuracy | Ensure high accuracy and consistency of engineering, BOQ, procurement, material, and execution data across DPR, SAP, and Primavera P6 systems. |
| NFR-02 | Performance | Support near real-time data refresh for dashboards, material availability checks, execution validations, and management analytics without impacting operational performance. |
| NFR-03 | Scalability | The system shall support scale-up to multiple projects, sites, vendors, and users across Solar, Wind, and PSS portfolios without architectural redesign. |
| NFR-04 | Security | Enforce role-based access control (RBAC), secure authentication, data encryption (in transit and at rest), and protection of sensitive procurement and commercial data. |
| NFR-05 | Integration Reliability | SAP and Primavera P6 integrations shall be stable, bi-directional, and include retry, exception handling, monitoring, and failure alerts to avoid data loss. |
| NFR-06 | Auditability & Compliance | Maintain complete audit trails for approvals, revisions, material transactions, reconciliations, JMRs, and workflow actions with user, timestamp, and change history. |
| NFR-07 | Availability | Ensure high system availability for site, project, and management users, especially during execution, billing, and reporting periods. |
| NFR-08 | Usability | Provide intuitive, role-specific user interfaces for site teams, engineers, procurement, stores, and management to minimize training effort and data entry errors. |
| NFR-09 | Configurability | Approval workflows, dashboards, notifications, and reporting views shall be configurable without code changes to support evolving business needs. |
| NFR-10 | Data Retention & History | Historical data, revisions, reconciliations, and transaction records shall be preserved for audit, compliance, and analytics purposes. |

  - Solution Overview

The DPR Phase-2 solution transforms the existing DPR application into a centralized EPC Execution and Material Intelligence Platform, integrating Engineering, Procurement, Construction, and Material Management into a single, controlled ecosystem.

The solution establishes DPR as the system of execution and operational intelligence, while SAP and Primavera P6 continue to serve as authoritative enterprise systems for ERP and scheduling respectively. All EPC processes are driven by engineering data, BOQ, material availability, and vendor accountability, ensuring execution is system-validated and data-driven.

9.1 High-Level Solution Architecture

The solution follows an API-driven, modular architecture with DPR at the core:

- DPR Core Platform

  - Central execution layer

  - Process orchestration and validations

  - Workflow, audit, dashboards, and alerts

- Enterprise Systems Integration

  - SAP for material, procurement, and financial references

  - Primavera P6 for planning, schedules, and progress sync

  - AutoCAD / PDF for drawing-driven BOQ

  - Drone systems (select projects) for physical progress verification

9.2 Functional Solution Components

Engineering & Design Control

- Centralized engineering document repository with MDL

- Drawing revision and approval workflows

- AFC-based dependency enforcement

- Mapping of engineering deliverables to Primavera P6 activities

BOQ & Quantity Intelligence

- BOQ derived directly from engineering drawings

- Multi-level BOQ management (project, block, activity, vendor)

- AutoCAD-based quantity extraction

- Automatic BOQ and material recalculation on drawing changes

Procurement Management

- End-to-end procurement lifecycle tracking (PR → GRN)

- SAP-synchronized SO and vendor data

- Mapping of procurement quantities to BOQ and activities

- Execution validation against procurement readiness

Material Management

- Material Requirement Planning (daily/weekly/monthly)

- Real-time stock validation with SAP inventory

- Block-wise and vendor-wise material allocation

- Controlled material issuance and returns

- Automated MIRS/MRRS generation

- Consumption and variance analysis

Material Reconciliation & JMR

- Vendor-wise and SO-wise reconciliation

- Activity and block-level reconciliation views

- Multi-level approval workflows

- Automated JMR generation linked to BOQ and SO

- Drawing-based quantity extraction for measurements

Workflow, Alerts & Governance

- Configurable workflows for all EPC processes

- Email notifications, alerts, and escalation rules

- Dependency and delay alerts

- Complete audit trails for all transactions

  - Key Constraints and Assumptions

10.1 Key Constraints

| Category | Constraint Description |
| --- | --- |
| System Boundaries | Existing enterprise systems such as SAP, Primavera P6, Digital DPR, Module Tracker, and Transmission Connectivity Dashboard will continue to remain the systems of record for their respective domains. DPR Phase-2 will not replace these systems. |
| Automation Limits | Critical business actions such as engineering approvals, BOQ revisions, material issuance, reconciliation, and JMR approvals require human validation and approval; full automation without approvals is not permitted. |
| Integration Dependency | DPR functionality and validations are dependent on timely and accurate data synchronization from SAP and Primavera P6; delays or failures in integration may impact execution workflows. |
| Infrastructure | No new on-site hardware or physical infrastructure changes are planned; the solution must operate within the existing IT infrastructure and deployment standards. |
| Portfolio Scope | The implementation scope is limited to Solar and Wind projects; other business verticals are excluded from DPR Phase-2. |
| Change Control | Any changes beyond the approved SOW scope will require formal change requests, impact analysis, and business approval. |
| User Adoption | Effective system usage is dependent on business users following defined workflows and data entry standards; deviations may impact data quality and reporting. |

10.2 Assumptions

The following assumptions apply to the successful execution of DPR Phase-2:

| Assumption ID | Assumption Description |
| --- | --- |
| A-01 | Existing enterprise systems (Primavera P6, SAP, Digital DPR, Module Tracker, Transmission Connectivity Dashboard) support standard API-based integrations required for bidirectional data exchange. |
| A-02 | Source systems provide accurate, complete, and timely data for material masters, stock, procurement, schedules, and execution quantities. |
| A-03 | SAP modules (MM, PS, FI/CO, SD) are configured and accessible for integration as per defined business processes. |
| A-04 | Primavera P6 schedules (L2/L3/L4) are maintained consistently and updated by planning teams to enable reliable execution validation. |
| A-05 | Engineering drawings uploaded into DPR are approved and maintained with proper revision discipline. |
| A-06 | Business stakeholders are available for requirement validation, UAT, approvals, and sign-off within planned timelines. |
| A-07 | Users will be trained and will adhere to standardized workflows for engineering, material, procurement, and reconciliation processes. |

  - System Integration Details

11.1 SAP Integration

| Integration Area | SAP Module | Purpose / Data Exchanged | Integration Direction |
| --- | --- | --- | --- |
| Material Management | MM | Material master, inventory, GRN, stock movements, material issuance | SAP → DPR |
| Project Structuring | PS | WBS mapping, project structure, cost tracking references | SAP → DPR |
| Finance & Controlling | FI/CO | Billing references, reconciliation data, cost tracking references | SAP ↔ DPR |
| Service Orders | SD | Service Order (SO) references for vendor and activity mapping | SAP → DPR |
| Vendor Collaboration (Optional) | Ariba | Vendor onboarding, procurement collaboration | SAP/Ariba → DPR |
| Material Transactions | MM | Material issue and return transactions, stock adjustments | DPR → SAP |
| Reconciliation & Billing | FI/CO | Material reconciliation references and JMR references | DPR → SAP |
| Integration Processing | All | Real-time and scheduled batch sync with exception handling, retry logic, and audit logging | Bi-directional |

11.2 Primavera P6 Integration

| Integration Area | System | Purpose / Data Exchanged | Integration Direction |
| --- | --- | --- | --- |
| Project Planning | Primavera P6 | Sync L2/L3/L4 schedules, WBS hierarchy, activity dependencies, baselines, revised dates, and milestones | P6 → DPR |
| Progress Updates | Primavera P6 | Executed quantities and physical progress update activity completion status | DPR → P6 |
| Schedule Governance | Primavera P6 | Planned vs actual comparison for monitoring delays and execution readiness | Bi-directional |

11.3 AutoCAD / Drawing Integration

| Integration Area | Tool | Purpose / Data Exchanged | Integration Direction |
| --- | --- | --- | --- |
| Drawing Management | AutoCAD / PDF | Upload drawings with revision control and approval status | AutoCAD/PDF → DPR |
| BOQ Derivation | AutoCAD | Layer-wise quantity extraction and block-wise BOQ derivation | AutoCAD → DPR |
| Activity Mapping | DPR | Link drawings to activities and BOQ for execution validation | DPR Internal |

11.4 Drone Monitoring Integration (Selected Projects)

| Integration Area | Technology | Purpose / Data Exchanged | Integration Direction |
| --- | --- | --- | --- |
| Visual Progress Tracking | Drone Imagery | Upload geo-tagged drone images for site progress monitoring | Drone System → DPR |
| Quantity Verification | Drone Analytics | Physical quantity verification against planned and executed quantities | Drone System → DPR |
| Management Visibility | DPR Dashboard | Visual and data-driven progress validation for management review | DPR Internal |

  - Deliverables

| Deliverable ID | Deliverable Name | Description / Coverage |
| --- | --- | --- |
| DEL-01 | Engineering Document Management Module | Configured centralized repository for engineering deliverables including MDL, drawing revisions, approval status, AFC control, and mapping to P6 activities. |
| DEL-02 | Master Document List (MDL) | MDL with document/drawing number, revision history, approval status, and audit trail integrated with execution controls. |
| DEL-03 | BOQ Management Module | BOQ setup across project, block, activity, vendor, and revision levels with full version control and approval workflow. |
| DEL-04 | AutoCAD-Driven BOQ Derivation | Capability to upload AutoCAD drawings and generate BOQ quantities using layer-wise extraction and block-wise derivation. |
| DEL-05 | BOQ–Material Mapping & Norms | Configured activity-to-material mapping with standard consumption norms reusable across projects. |
| DEL-06 | Procurement Management Module | End-to-end procurement lifecycle tracking including PR, PO, SO, dispatch, delivery, GRN, inspection, and MDCC status. |
| DEL-07 | SAP Procurement Integration | SAP-integrated SO and vendor data synchronized and mapped to activities, BOQ quantities, and vendor allocations. |
| DEL-08 | Material Requirement Planning (MRP) Engine | Automated daily, weekly, and monthly material requirement calculations with shortage alerts and procurement forecasting. |
| DEL-09 | Block-wise & Vendor-wise Material Allocation | Functionality for site teams to allocate materials by block and vendor with BOQ-based allocation controls. |
| DEL-10 | Material Issuance & Return Module | System-driven material issue and return tracking linked to Vendor, Block, Activity, and SO with stock auto-updates. |
| DEL-11 | MIRS & MRRS Reports | Auto-generated Material Issue Receipt Slip (MIRS) and Material Return Receipt Slip (MRRS) downloadable in Excel and PDF. |
| DEL-12 | Consumption & Variance Tracking | Automated tracking of planned vs actual material consumption with variance flags for over-issuance, shortages, and pending returns. |
| DEL-13 | Material Reconciliation Engine | Vendor-wise, activity-wise, block-wise, and SO-wise reconciliation statements with revision control. |
| DEL-14 | Reconciliation Approval Workflow | Configured approval workflow for reconciliation: Site → Store → Billing → PM with audit logs. |
| DEL-15 | JMR Automation Module | Auto-generated Joint Measurement Records linked to BOQ and SO based on executed quantities. |
| DEL-16 | Drawing-Based JMR Quantity Extraction | Support for drawing upload and area-based quantity extraction for JMR preparation. |
| DEL-17 | Workflow Configuration Framework | Configurable approval workflows for engineering, BOQ revisions, material issuance, reconciliation, JMR, and vendor allocations. |
| DEL-18 | Notifications & Alerts System | Email notifications, system alerts, escalation reminders, and dependency/delay alerts across EPC processes. |
| DEL-19 | Role-Based Dashboards & Reports | Operational and management dashboards providing real-time visibility into engineering, procurement, material, and EPC risks. |
| DEL-20 | Audit Logs & Traceability Reports | Complete audit trails for document changes, approvals, material transactions, reconciliations, and JMRs. |

## Expected Business Outcomes

- Single source of truth for EPC execution

- Engineering-driven material and procurement planning

- Vendor-wise material accountability

- Reduced reconciliation delays and material wastage

- Improved management decision-making through real-time visibility

  - Risk & Mitigation

| Risk | Description | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Data Integration Risk | API limitations or data inconsistencies across systems | Delayed or inaccurate reporting | Early integration testing, validation rules, fallback monitoring |
| User Adoption Risk | Resistance to moving from Excel/manual processes | Low platform utilization | Training, role-based dashboards, leadership sponsorship |
| Data Quality Risk | Inaccurate or incomplete source data | Incorrect insights and decisions | Clear data ownership, validation checks, audit logs |
| Approval Bottlenecks | Delays in Human-in-the-Loop approvals | Slower execution | Defined SLAs, alerts, escalation workflows |
| Performance Risk | Slow dashboard or chatbot response | Reduced trust in system | Scalable architecture, performance monitoring |
| Security & Compliance Risk | Unauthorized access or data leakage | Regulatory and business impact | RBAC, SSO, encryption, audit trails |
| Change Management Risk | Scope creep or late requirement changes | Timeline and delivery risk | Governance reviews, change control process |

  - Estimations and timeline

Estimation:

Timeline:

Estimation Bifurcation:

| Module | Days |
| --- | --- |

## 16. Schedule Dependencies

The project schedule is dependent on the following:

- Availability of source system access (Primavera P6, SAP, Digital DPR, Connectivity systems)

- Availability of sample data for DPR, logistics, connectivity, and procurement

- Timely business stakeholder participation for:

  - Requirement validation

  - Design reviews

  - Scenario validation

- Finalization of approval hierarchies and governance rules

- Enterprise IT security and compliance clearances

- Stability of source system APIs during implementation