## A16D
Block | Piling |  |  |  | Piling Cap |  |  |  | Rafter |  |  |  | Bracing |  |  |  | Purlin |  |  |  | Module Installation
| Actual as per Scope | DRONE | DPR | VARIATION | Actual as per Scope | DRONE | DPR | VARIATION | Actual as per Scope | DRONE | DPR | VARIATION | Actual as per Scope | DRONE | DPR | VARIATION | Actual as per Scope | DRONE | DPR | VARIATION | Actual as per Scope | DRONE | DPR | VARIATION
A16D_B01 | 5928 | 5928 | 5928 | 0 | 5928 | 5928 | 5928 | 0 | 494 | 494 | 494 | 0 | 494 | 494 | 494 | 0 | 494 | 494 | 494 | 0 | 494 | 494 | 494 | 0
A16D_B02 | 3780 | 3780 | 3780 | 0 | 3780 | 3780 | 3780 | 0 | 315 | 315 | 315 | 0 | 315 | 315 | 315 | 0 | 315 | 315 | 315 | 0 | 315 | 315 | 315 | 0
A16D_B03 | 5928 | 5927 | 5928 | -1 | 5928 | 5927 | 5830 | 97 | 494 | 436 | 417 | 19 | 494 | 433 | 417 | 16 | 494 | 419 | 397 | 22 | 494 | 352 | 347 | 5
A16D_B04 | 5928 | 5928 | 5928 | 0 | 5928 | 5928 | 5928 | 0 | 494 | 477 | 468 | 9 | 494 | 447 | 468 | -21 | 494 | 389 | 383 | 6 | 494 | 358 | 358 | 0
A16D_B05 | 5928 | 5928 | 5928 | 0 | 5928 | 5928 | 5928 | 0 | 494 | 494 | 494 | 0 | 494 | 494 | 494 | 0 | 494 | 494 | 494 | 0 | 494 | 494 | 494 | 0
A16D_B06 | 5928 | 5928 | 5928 | 0 | 5928 | 5928 | 5928 | 0 | 494 | 494 | 494 | 0 | 494 | 494 | 494 | 0 | 494 | 494 | 494 | 0 | 494 | 494 | 494 | 0
A16D_B07 | 5928 | 5580 | 5676 | -96 | 5928 | 5580 | 5577 | 3 | 494 | 374 | 390 | -16 | 494 | 365 | 390 | -25 | 494 | 343 | 337 | 6 | 494 | 314 | 316 | -2
A16D_B08 | 5928 | 5928 | 5928 | 0 | 5928 | 5928 | 5928 | 0 | 494 | 420 | 391 | 29 | 494 | 418 | 391 | 27 | 494 | 407 | 397 | 10 | 494 | 345 | 369 | -24
A16D_B09 | 5928 | 5928 | 5928 | 0 | 5928 | 5928 | 5928 | 0 | 494 | 494 | 494 | 0 | 494 | 494 | 494 | 0 | 494 | 494 | 494 | 0 | 494 | 494 | 494 | 0
A16D_B10 | 5916 | 5916 | 5916 | 0 | 5916 | 5916 | 5916 | 0 | 493 | 493 | 493 | 0 | 493 | 493 | 493 | 0 | 493 | 493 | 493 | 0 | 493 | 491 | 480 | 11
A16D_B11 | 5916 | 5916 | 5916 | 0 | 5916 | 5916 | 5916 | 0 | 493 | 493 | 493 | 0 | 493 | 493 | 493 | 0 | 493 | 493 | 493 | 0 | 493 | 493 | 493 | 0
A16D_B12 | 5916 | 5916 | 5916 | 0 | 5916 | 5916 | 5916 | 0 | 493 | 493 | 493 | 0 | 493 | 493 | 493 | 0 | 493 | 493 | 493 | 0 | 493 | 492 | 493 | -1
A16D_B13 | 5928 | 5928 | 5928 | 0 | 5928 | 5928 | 5928 | 0 | 494 | 494 | 494 | 0 | 494 | 494 | 494 | 0 | 494 | 494 | 494 | 0 | 494 | 493 | 494 | -1
A16D_B14 | 5916 | 5916 | 5916 | 0 | 5916 | 5916 | 5916 | 0 | 493 | 392 | 350 | 42 | 493 | 390 | 350 | 40 | 493 | 350 | 350 | 0 | 493 | 291 | 339 | -48
A16D_B15 | 5916 | 5916 | 5916 | 0 | 5916 | 5916 | 5916 | 0 | 493 | 493 | 493 | 0 | 493 | 493 | 493 | 0 | 493 | 493 | 493 | 0 | 493 | 491 | 493 | -2
A16D_B16 | 5928 | 5928 | 5928 | 0 | 5928 | 5868 | 5928 | -60 | 494 | 465 | 487 | -22 | 494 | 462 | 487 | -25 | 494 | 461 | 462 | -1 | 494 | 450 | 462 | -12
A16D_B17 | 5928 | 5928 | 5928 | 0 | 5928 | 5928 | 5928 | 0 | 494 | 494 | 494 | 0 | 494 | 494 | 494 | 0 | 494 | 494 | 494 | 0 | 494 | 494 | 494 | 0
A16D_B18 | 5928 | 5928 | 5928 | 0 | 5928 | 5928 | 5928 | 0 | 494 | 470 | 474 | -4 | 494 | 458 | 474 | -16 | 494 | 393 | 396 | -3 | 494 | 371 | 375 | -4
A16D_B19 | 5928 | 5928 | 5928 | 0 | 5928 | 5904 | 5874 | 30 | 494 | 479 | 490 | -11 | 494 | 473 | 490 | -17 | 494 | 459 | 479 | -20 | 494 | 454 | 462 | -8
A16D_B20 | 5916 | 5916 | 5916 | 0 | 5916 | 5916 | 5916 | 0 | 493 | 381 | 381 | 0 | 493 | 381 | 381 | 0 | 493 | 381 | 381 | 0 | 493 | 349 | 381 | -32
A16D_B21 | 5916 | 5916 | 5916 | 0 | 5916 | 5916 | 5916 | 0 | 493 | 394 | 395 | -1 | 493 | 394 | 395 | -1 | 493 | 391 | 414 | -23 | 493 | 384 | 380 | 4
A16D_B22 | 5916 | 5916 | 5916 | 0 | 5916 | 5916 | 5916 | 0 | 493 | 493 | 493 | 0 | 493 | 493 | 493 | 0 | 493 | 493 | 493 | 0 | 493 | 493 | 493 | 0
A16D_B23 | 5928 | 5928 | 5928 | 0 | 5928 | 5928 | 5928 | 0 | 494 | 456 | 461 | -5 | 494 | 429 | 461 | -32 | 494 | 429 | 431 | -2 | 494 | 427 | 428 | -1
A16D_B24 | 5916 | 5916 | 5916 | 0 | 5916 | 5916 | 5916 | 0 | 493 | 492 | 491 | 1 | 493 | 492 | 491 | 1 | 493 | 489 | 491 | -2 | 493 | 469 | 489 | -20
A16D_B25 | 5928 | 5928 | 5928 | 0 | 5928 | 5928 | 5928 | 0 | 494 | 494 | 494 | 0 | 494 | 494 | 494 | 0 | 494 | 494 | 494 | 0 | 494 | 489 | 494 | -5
A16D_B26 | 5928 | 5928 | 5928 | 0 | 5928 | 5928 | 5928 | 0 | 494 | 494 | 494 | 0 | 494 | 494 | 494 | 0 | 494 | 494 | 494 | 0 | 494 | 494 | 494 | 0
A16D_B27 | 5916 | 5916 | 5916 | 0 | 5916 | 5916 | 5916 | 0 | 493 | 493 | 493 | 0 | 493 | 493 | 493 | 0 | 493 | 493 | 493 | 0 | 493 | 493 | 493 | 0
Total | 157788 | 157439 | 157536 | -97 | 157788 | 157355 | 157285 | 70 | 13149 | 12461 | 12420 | 41 | 13149 | 12367 | 12420 | -53 | 13149 | 12136 | 12143 | -7 | 13149 | 11778 | 11918 | -140