# DPR Fields Mapping to Primavera P6 API

This document provides a mapping of DPR sheet fields to corresponding Primavera P6 API objects and REST endpoints for integration.

# DP Qty Sheet

| DPR Field | P6 Object | API Endpoint |
| --- | --- | --- |
| Description | Activity | GET /activities |
| Total Quantity | ResourceAssignment | GET /resourceAssignments |
| UOM | ResourceAssignment | GET /resourceAssignments |
| Base Plan Start/Finish | Activity | GET /activities |
| Actual Start/Finish | Activity | PUT /activities/{id} |
| Forecast Start/Finish | Activity | GET /activities |
| Remarks | Activity | PUT /activities/{id} |

# DP Block Sheet

| DPR Field | P6 Object | API Endpoint |
| --- | --- | --- |
| Block Capacity (Mwac) | Project/WBS | GET /projects |
| Phase | WBS | GET /wbs |
| Block | WBS | GET /wbs |
| SPV Number | Project | GET /projects |
| Priority | ActivityCode | GET /activityCodes |

# DP Vendor IDT Sheet

| DPR Field | P6 Object | API Endpoint |
| --- | --- | --- |
| Activity_ID | Activity | GET /activities |
| Activities | Activity | GET /activities |
| Plot | ActivityCode | GET /activityCodes |
| New Block Nom | ActivityCode | GET /activityCodes |
| Priority | ActivityCode | POST /activityCodeAssignments |
| Contractor Name | Resource | GET /resources |
| Scope | Activity | GET /activities |
| Front | Activity | GET /activities |
| Actual | Activity | GET /activities |
| % Completion | Activity | GET /activities |

# DP Vendor Block Sheet

| DPR Field | P6 Object | API Endpoint |
| --- | --- | --- |
| Activity_ID | Activity | GET /activities |
| Activities | Activity | GET /activities |
| Plot | ActivityCode | GET /activityCodes |
| New Block Nom | ActivityCode | GET /activityCodes |
| Priority | ActivityCode | POST /activityCodeAssignments |
| Contractor Name | Resource | GET /resources |
| Scope | Activity | GET /activities |
| Hold Due to WTG | Activity | GET /activities |
| Front | Activity | GET /activities |
| Actual | Activity | GET /activities |
| % Completion | Activity | GET /activities |

# Manpower Details

| DPR Field | P6 Object | API Endpoint |
| --- | --- | --- |
| Activity_ID | Activity | GET /activities |
| Block | WBS | GET /wbs |
| Contractor Name | Resource | GET /resources |
| Activity | Activity | GET /activities |